## Sheet1
Activity ID | Activity Name | WBS | Discipline | Start | Finish | Early Start | Late Start | Late Finish | Forecast Finish | Duration (Planned) | Duration (Actual) | Variance (days) | % Complete | Float (days) | Milestone | Critical Path | Predecessor | Status | Early Finish
D-PM-001 | Letter of Award (LOA) | 1.0 Project Management | PM | 2024-10-01 | 2024-10-15 | 2024-10-01 | 2024-10-15 | 2024-10-15 | 2024-10-15 | 15 | 15 | 0 | 100 | 0 | YES | NO |  | Complete | 2024-10-15
D-PM-002 | Kick-Off Meeting Completed | 1.0 Project Management | PM | 2024-10-16 | 2024-11-10 | 2024-10-16 | 2024-11-10 | 2024-11-10 | 2024-11-10 | 25 | 25 | 0 | 100 | 0 | YES | NO | D-PM-001 | Complete | 2024-11-10
D-PM-010 | Baseline Schedule Approved | 1.0 Project Management | PM | 2024-11-11 | 2024-12-15 | 2024-11-11 | 2024-12-20 | 2024-12-20 | 2024-12-20 | 35 | 40 | 5 | 100 | 0 | NO | NO | D-PM-002 | Complete | 2024-12-15
D-E-001 | FEED Package Review | 2.0 Engineering | Engineering | 2024-10-15 | 2025-01-15 | 2024-10-15 | 2024-10-20 | 2025-01-28 | 2025-01-28 | 92 | 100 | 13 | 100 | 5 | NO | NO | D-PM-001 | Complete | 2025-01-15
D-E-005 | Process Datasheet — Column | 2.0 Engineering | Engineering | 2024-12-01 | 2025-03-01 | 2024-12-01 | 2024-12-10 | 2025-03-15 | 2025-03-15 | 91 | 96 | 14 | 100 | 0 | NO | YES | D-E-001 | Complete | 2025-03-01
D-E-010 | IFC Drawings — Civil | 2.0 Engineering | Civil Engineering | 2025-01-15 | 2025-04-15 | 2025-01-15 | 2025-01-25 | 2025-06-01 | 2025-06-01 | 90 | 128 | 47 | 100 | 2 | YES | NO | D-E-005 | Complete | 2025-04-15
D-E-015 | IFC Drawings — Structural | 2.0 Engineering | Structural Engineering | 2025-02-01 | 2025-05-01 | 2025-02-01 | 2025-02-15 | 2025-06-20 | 2025-06-20 | 90 | 126 | 50 | 100 | 3 | NO | NO | D-E-010 | Complete | 2025-05-01
D-E-020 | IFC Drawings — Piping | 2.0 Engineering | Piping Engineering | 2025-03-01 | 2025-06-15 | 2025-03-01 | 2025-04-01 | 2025-07-30 | 2025-07-30 | 106 | 120 | 45 | 100 | 0 | NO | YES | D-E-015 | Complete | 2025-06-15
D-E-025 | IFC Drawings — Electrical | 2.0 Engineering | Electrical Engineering | 2025-03-15 | 2025-06-30 | 2025-03-15 | 2025-04-10 | 2025-07-20 | 2025-07-20 | 107 | 101 | 20 | 100 | 4 | NO | NO | D-E-020 | Complete | 2025-06-30
D-E-030 | Vendor Drawing Approvals — Column Internals | 2.0 Engineering | Process Engineering | 2025-06-01 | 2025-09-01 | 2025-06-01 | 2025-07-15 | 2025-11-10 | 2025-11-10 | 92 | 118 | 70 | 100 | 0 | NO | YES | D-E-005 | Complete | 2025-09-01
D-P-001 | Column Internals — Procurement & Delivery | 3.0 Procurement | Procurement | 2025-06-01 | 2026-04-15 | 2025-06-01 | 2025-07-01 | 2026-04-15 | 2026-07-10 | 319 |  |  | 40 | 0 | YES | YES | D-E-030 | In Progress | 2026-04-15
D-P-010 | Structural Steel Supply | 3.0 Procurement | Procurement | 2025-04-01 | 2025-10-15 | 2025-04-01 | 2025-04-15 | 2025-10-28 | 2025-10-28 | 197 | 197 | 13 | 100 | 15 | NO | NO | D-E-015 | Complete | 2025-10-15
D-P-020 | Piping Materials Supply — Train A | 3.0 Procurement | Procurement | 2025-05-01 | 2025-12-01 | 2025-05-01 | 2025-06-01 | 2025-12-20 | 2025-12-20 | 214 | 203 | 19 | 100 | 8 | NO | NO | D-E-020 | Complete | 2025-12-01
D-P-030 | Electrical Cables & Equipment | 3.0 Procurement | Procurement | 2025-06-01 | 2026-01-15 | 2025-06-01 | 2025-07-01 | 2026-02-10 | 2026-02-10 | 228 | 224 | 26 | 100 | 5 | NO | NO | D-E-025 | Complete | 2026-01-15
D-P-040 | Instrumentation Packages | 3.0 Procurement | Procurement | 2025-07-01 | 2026-02-01 | 2025-07-01 | 2025-08-01 | 2026-02-01 | 2026-03-15 | 215 |  | 42 | 90 | 6 | NO | NO | D-E-025 | In Progress | 2026-02-01
D-P-045 | Heat Exchanger Bundle | 3.0 Procurement | Procurement | 2025-08-01 | 2026-05-20 | 2025-08-01 | 2025-09-15 | 2026-05-20 | 2026-07-28 | 292 |  | 69 | 65 | 3 | NO | NO | D-E-030 | In Progress | 2026-05-20
D-C-001 | Site Clearance & Grading | 4.0 Construction | Civil | 2025-03-01 | 2025-04-30 | 2025-03-01 | 2025-03-10 | 2025-05-15 | 2025-05-15 | 61 | 66 | 15 | 100 | 20 | NO | NO |  | Complete | 2025-04-30
D-C-005 | Excavation Works | 4.0 Construction | Civil | 2025-04-15 | 2025-06-30 | 2025-04-15 | 2025-06-01 | 2025-08-20 | 2025-08-20 | 76 | 80 | 51 | 100 | 0 | NO | YES | D-C-001 | Complete | 2025-06-30
D-C-010 | Piling Works | 4.0 Construction | Civil | 2025-05-01 | 2025-07-31 | 2025-05-01 | 2025-06-20 | 2025-09-10 | 2025-09-10 | 91 | 82 | 41 | 100 | 0 | NO | YES | D-C-005 | Complete | 2025-07-31
D-C-015 | Column Foundation — Concrete Works | 4.0 Construction | Civil | 2025-07-15 | 2026-03-20 | 2025-07-15 | 2025-10-15 | 2026-03-20 | 2026-06-05 | 249 |  |  | 62 | 0 | YES | YES | D-C-010 | In Progress | 2026-03-20
D-C-020 | Equipment Pads — Heat Exchanger | 4.0 Construction | Civil | 2025-08-01 | 2026-03-01 | 2025-08-01 | 2025-10-01 | 2026-03-01 | 2026-05-15 | 212 |  | 75 | 55 | 5 | NO | NO | D-C-010 | In Progress | 2026-03-01
D-C-022 | Structural Steel Erection — Main Frame | 4.0 Construction | Structural | 2025-10-01 | 2026-05-10 | 2025-10-01 | 2025-10-01 | 2026-05-10 | 2026-08-25 | 221 |  | 107 | 0 | 2 | NO | YES | D-C-015 D-P-010 | Not Started | 2026-05-10
D-C-030 | Underground Piping — Main Headers | 4.0 Construction | Piping | 2025-09-01 | 2026-04-15 | 2025-09-01 | 2025-11-01 | 2026-04-15 | 2026-07-01 | 226 |  | 77 | 40 | 0 | NO | YES | D-C-015 | In Progress | 2026-04-15
D-C-035 | Aboveground Piping Prefabrication | 4.0 Construction | Piping | 2025-10-01 | 2026-06-01 | 2025-10-01 | 2025-11-15 | 2026-06-01 | 2026-08-01 | 243 |  | 61 | 50 | 0 | NO | YES | D-P-020 | In Progress | 2026-06-01
D-C-060 | Piping Installation — Train A | 4.0 Construction | Piping | 2026-01-15 | 2026-07-15 | 2026-01-15 | 2026-01-15 | 2026-07-15 | 2026-10-20 | 181 |  | 97 | 0 | 0 | NO | YES | D-C-035 D-P-001 | Not Started | 2026-07-15
D-C-070 | Column Erection | 4.0 Construction | Structural | 2026-04-01 | 2026-07-01 | 2026-04-01 | 2026-04-01 | 2026-07-01 | 2026-09-15 | 91 |  | 106 | 0 | 0 | YES | YES | D-C-015 D-P-001 | Not Started | 2026-07-01
D-E-031 | Main Substation — Cable Pulling | 4.0 Construction | Electrical | 2026-01-01 | 2026-06-30 | 2026-01-01 | 2026-01-01 | 2026-06-30 | 2026-09-12 | 180 |  | 74 | 0 | 1 | NO | YES | D-P-030 D-C-022 | Not Started | 2026-06-30
D-E-040 | Instrumentation Installation — Train A | 4.0 Construction | Instrumentation | 2026-04-01 | 2026-08-31 | 2026-04-01 | 2026-04-01 | 2026-08-31 | 2026-11-15 | 153 |  | 76 | 0 | 3 | NO | NO | D-P-040 D-C-060 | Not Started | 2026-08-31
D-C-080 | Insulation & Painting Works | 4.0 Construction | Civil | 2026-06-01 | 2026-10-31 | 2026-06-01 | 2026-06-01 | 2026-10-31 | 2027-01-20 | 153 |  | 81 | 0 | 5 | NO | NO | D-C-060 D-C-070 | Not Started | 2026-10-31
D-MC-001 | Mechanical Completion (MC) | 5.0 Commissioning | Commissioning | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2027-03-15 | 1 |  | 104 | 0 | 0 | YES | YES | D-C-080 D-E-031 D-E-040 | Not Started | 2026-12-01
D-MC-010 | Pre-Commissioning Activities | 5.0 Commissioning | Commissioning | 2026-10-01 | 2027-01-15 | 2026-10-01 | 2026-10-01 | 2027-01-15 | 2027-04-01 | 107 |  | 77 | 0 | 0 | NO | YES | D-C-060 D-E-031 | Not Started | 2027-01-15
D-MC-020 | Loop Checks & Functional Testing | 5.0 Commissioning | Commissioning | 2027-01-01 | 2027-03-15 | 2027-01-01 | 2027-01-01 | 2027-03-15 | 2027-05-01 | 74 |  | 47 | 0 | 0 | NO | YES | D-MC-010 | Not Started | 2027-03-15
D-MC-002 | Ready for Start-Up (RFSU) | 5.0 Commissioning | Commissioning | 2027-02-01 | 2027-02-01 | 2027-02-01 | 2027-02-01 | 2027-02-01 | 2027-05-20 | 1 |  | 108 | 0 | 0 | YES | YES | D-MC-001 D-MC-020 | Not Started | 2027-02-01