## CP analaysis
Activity ID | Activity Name | Start | Finish | BL Project Start | BL Project Finish | Variance - BL Project Start Date | Variance - BL Project Finish Date | Total Float | Longest Path | CP Issue Type | Corrected CP Status | Duration vs BL (days) | Recovery / Risk Note
Borouge EU3 H2 Extraction EPC Project - MPR - Feb-2026 |  | 07-Nov-24 A | 2027-07-20 | 2024-11-14 | 2027-07-20 | 5 | 0 | 0 |  | FALSE NEGATIVE — Add to CP | MISSED CRITICAL — 0 Float | 0d vs BL | Set Longest Path = Yes; monitor as critical deliverable
COMPANY / PKG 1&2 Interfaces |  | 24-Apr-25 A | 24-Apr-25 A | 2025-04-18 | 2025-04-18 | -4 | -4
Engineering |  | 24-Apr-25 A | 24-Apr-25 A | 2025-04-18 | 2025-04-18 | -4 | -4
Required Inputs from COMPANY / Pkg 1&2 |  | 24-Apr-25 A | 24-Apr-25 A | 2025-04-18 | 2025-04-18 | -4 | -4
A60780 | Receipt of Approved vendor data for FG & OG compressor |  | 24-Apr-25 A |  | 2025-04-18 | -4 | -4 |  | Yes
Project Management |  | 07-Nov-24 A | 2027-07-20 | 2025-04-18 | 2027-07-20 | 112 | 0 | 0 |  | FALSE NEGATIVE — Add to CP | MISSED CRITICAL — 0 Float | 0d vs BL | Set Longest Path = Yes; monitor as critical deliverable
Project Management |  | 07-Nov-24 A | 06-Dec-24 A | 2025-04-18 | 2025-05-17 | 116 | 116
Project Management Interim Milestones |  | 07-Nov-24 A | 06-Dec-24 A | 2025-04-18 | 2025-05-17 | 116 | 116
A1-PM-PMM-0002 | 10.A-Kick-off Meeting Completed |  | 06-Dec-24 A |  | 2025-05-17 | 116 | 116 |  | Yes | FALSE POSITIVE — Remove from CP | COMPLETED — Not driving schedule | +116d early vs BL | Activity done — remove Longest Path flag to clear CP noise
A1-PM-PMM-0001 | Letter of Award (LOA) Recieved - Project Commencement Date |  | 07-Nov-24 A |  | 2025-04-18 | 116 | 116 |  | Yes | FALSE POSITIVE — Remove from CP | COMPLETED — Not driving schedule | +116d early vs BL | Activity done — remove Longest Path flag to clear CP noise
Procurement |  | 01-Jun-25 A | 01-Jun-25 A | 2025-07-15 | 2025-07-15 | 32 | 32
Procurement Interim Milestones |  | 01-Jun-25 A | 01-Jun-25 A | 2025-07-15 | 2025-07-15 | 32 | 32
Subcontracts |  | 01-Jun-25 A | 01-Jun-25 A | 2025-07-15 | 2025-07-15 | 32 | 32
A1-PM-PRM-0016 | 63.C-Piling subcontract award |  | 01-Jun-25 A |  | 2025-07-15 | 32 | 32 |  | Yes | FALSE POSITIVE — Remove from CP | COMPLETED — Not driving schedule | +32d early vs BL | Activity done — remove Longest Path flag to clear CP noise
Commissioning |  | 2027-07-20 | 2027-07-20 | 2027-07-20 | 2027-07-20 | 0 | 0 | 0 |  | FALSE NEGATIVE — Add to CP | MISSED CRITICAL — 0 Float | 0d vs BL | Set Longest Path = Yes; monitor as critical deliverable
Commissioning Interim Milestones |  | 2027-07-20 | 2027-07-20 | 2027-07-20 | 2027-07-20 | 0 | 0 | 0 |  | FALSE NEGATIVE — Add to CP | MISSED CRITICAL — 0 Float | 0d vs BL | Set Longest Path = Yes; monitor as critical deliverable
Mechanical Completion & Ready for START UP |  | 2027-07-20 | 2027-07-20 | 2027-07-20 | 2027-07-20 | 0 | 0 | 0 |  | FALSE NEGATIVE — Add to CP | MISSED CRITICAL — 0 Float | 0d vs BL | Set Longest Path = Yes; monitor as critical deliverable
A1-PM-CMM-0005 | 144.F-PROVISIONAL ACCEPTANCE CERTIFICATE |  | 2027-07-20 |  | 2027-07-20 | 0 | 0 | 0 | Yes
Others |  | 2027-01-20 | 2027-07-20 | 2027-01-20 | 2027-07-20 | 0 | 0 | 0 |  | FALSE NEGATIVE — Add to CP | MISSED CRITICAL — 0 Float | 0d vs BL | Set Longest Path = Yes; monitor as critical deliverable
Project Key Milestones |  | 2027-01-20 | 2027-07-20 | 2027-01-20 | 2027-07-20 | 0 | 0 | 0 |  | FALSE NEGATIVE — Add to CP | MISSED CRITICAL — 0 Float | 0d vs BL | Set Longest Path = Yes; monitor as critical deliverable
A1-PM-PKM-0004 | Provisional Acceptance Certificate (PAC) |  | 2027-07-20 |  | 2027-07-20 | 0 | 0 | 0 | Yes
A1-PM-PKM-0003 | Ready for Start-up (RFSU) |  | 2027-04-21 |  | 2027-04-21 | 0 | 0 | 0 | Yes
A1-PM-PKM-0002 | Mechanical Completion (MC) |  | 2027-01-20 |  | 2027-01-20 | 0 | 0 | 0 | Yes
Home Office Services |  | 14-Nov-24 A | 19-Sep-25 A | 2024-11-14 | 2025-11-10 | 0 | 37
Detailed Design - EDDR |  | 04-Dec-24 A | 19-Sep-25 A | 2024-12-04 | 2025-11-10 | 0 | 37
Package 3 |  | 04-Dec-24 A | 19-Sep-25 A | 2024-12-04 | 2025-11-10 | 0 | 37
Project Management |  | 04-Dec-24 A | 19-Sep-25 A | 2024-12-04 | 2025-11-06 | 0 | 35
Preliminaries |  | 04-Dec-24 A | 23-May-25 A | 2024-12-04 | 2024-12-16 | 0 | -113
A53320 | Receipt of Source Data | 05-Dec-24 A | 23-May-25 A | 2024-12-05 | 2024-12-16 | 0 | -113 |  | Yes
A53280 | Engineering Subcontractor KOM | 04-Dec-24 A | 04-Dec-24 A | 2024-12-04 | 2024-12-05 | 0 | 0 |  | Yes
TA related Inputs |  | 08-Apr-25 A | 19-Sep-25 A | 2025-09-19 | 2025-11-06 | 118 | 35
TA Phase |  | 08-Apr-25 A | 22-Apr-25 A | 2025-09-19 | 2025-09-22 | 118 | 109
A28140 | Receipt of Approved Topo, UG & geotechnical investigation report | 08-Apr-25 A | 22-Apr-25 A | 2025-09-19 | 2025-09-22 | 118 | 109 |  | Yes | FALSE POSITIVE — Remove from CP | COMPLETED — Not driving schedule | +109d early vs BL | Activity done — remove Longest Path flag to clear CP noise
Ist Issuance of Vendor Data Receipt-1 |  | 27-Aug-25 A | 27-Aug-25 A | 2025-09-19 | 2025-09-19 | 17 | 17
Mechanical |  | 27-Aug-25 A | 27-Aug-25 A | 2025-09-19 | 2025-09-19 | 17 | 17
A28770 | Compressors (FG & OG)_1st issuance of Vendor Data Receipt |  | 27-Aug-25 A |  | 2025-09-19 | 17 | 17 |  | Yes | FALSE POSITIVE — Remove from CP | COMPLETED — Not driving schedule | +17d early vs BL | Activity done — remove Longest Path flag to clear CP noise
Approved Vender Data Receipt |  | 19-Sep-25 A | 19-Sep-25 A | 2025-11-06 | 2025-11-06 | 35 | 35
Mechanical |  | 19-Sep-25 A | 19-Sep-25 A | 2025-11-06 | 2025-11-06 | 35 | 35
A28150 | Compressors (FG & OG)_Approved Vendor Data Receipt |  | 19-Sep-25 A |  | 2025-11-06 | 35 | 35 |  | Yes | FALSE POSITIVE — Remove from CP | COMPLETED — Not driving schedule | +35d early vs BL | Activity done — remove Longest Path flag to clear CP noise
Turnaround (TA) |  | 01-Jan-25 A | 05-Feb-25 A | 2025-09-19 | 2025-10-21 | 187 | 185
Subcontracting Support |  | 01-Jan-25 A | 05-Feb-25 A | 2025-09-19 | 2025-10-21 | 187 | 185
SOW & Requisition for Topo & UG survey |  | 01-Jan-25 A | 05-Feb-25 A | 2025-09-19 | 2025-10-21 | 187 | 185
A28870 | SOW & Requisition for Topo & UG survey_IFD/IFC | 27-Jan-25 A | 05-Feb-25 A | 2025-10-14 | 2025-10-21 | 186 | 185 |  | Yes | FALSE POSITIVE — Remove from CP | COMPLETED — Not driving schedule | +185d early vs BL | Activity done — remove Longest Path flag to clear CP noise
A56120 | SOW & Requisition for Topo & UG survey_RCC | 13-Jan-25 A | 24-Jan-25 A | 2025-09-26 | 2025-10-17 | 184 | 191 |  | Yes | FALSE POSITIVE — Remove from CP | COMPLETED — Not driving schedule | +191d early vs BL | Activity done — remove Longest Path flag to clear CP noise
A56110 | SOW & Requisition for Topo & UG survey_IFR | 01-Jan-25 A | 09-Jan-25 A | 2025-09-19 | 2025-09-26 | 187 | 187 |  | Yes | FALSE POSITIVE — Remove from CP | COMPLETED — Not driving schedule | +187d early vs BL | Activity done — remove Longest Path flag to clear CP noise
SOW & Requisition for Geotechnical investigation |  | 01-Jan-25 A | 05-Feb-25 A | 2025-09-19 | 2025-10-21 | 187 | 185
A56150 | SOW & Requisition for Geotechnical investigation_IFD/IFC | 27-Jan-25 A | 05-Feb-25 A | 2025-10-14 | 2025-10-21 | 186 | 185 |  | Yes | FALSE POSITIVE — Remove from CP | COMPLETED — Not driving schedule | +185d early vs BL | Activity done — remove Longest Path flag to clear CP noise
A56140 | SOW & Requisition for Geotechnical investigation_RCC | 13-Jan-25 A | 24-Jan-25 A | 2025-09-26 | 2025-10-17 | 184 | 191 |  | Yes | FALSE POSITIVE — Remove from CP | COMPLETED — Not driving schedule | +191d early vs BL | Activity done — remove Longest Path flag to clear CP noise
A56130 | SOW & Requisition for Geotechnical investigation_IFR | 01-Jan-25 A | 09-Jan-25 A | 2025-09-19 | 2025-09-26 | 187 | 187 |  | Yes | FALSE POSITIVE — Remove from CP | COMPLETED — Not driving schedule | +187d early vs BL | Activity done — remove Longest Path flag to clear CP noise
Balance of Plant |  | 10-Apr-25 A | 15-Sep-25 A | 2025-03-19 | 2025-11-10 | -16 | 41
Civil/Structural/Architectural |  | 10-Apr-25 A | 15-Sep-25 A | 2025-03-19 | 2025-11-10 | -16 | 41
Structure & Foundation design - Mechanical |  | 10-Apr-25 A | 15-Sep-25 A | 2025-03-19 | 2025-11-10 | -16 | 41
Foundation drawing PSA-2 FeedGas Compressor 13-KC-701 |  | 19-Jul-25 A | 22-Aug-25 A | 2025-08-12 | 2025-08-27 | 16 | 3
A49020 | Foundation drawing PSA-2 FeedGas Compressor 13-KC-701_IFR | 19-Jul-25 A | 22-Aug-25 A | 2025-08-12 | 2025-08-27 | 16 | 3 |  | Yes | FALSE POSITIVE — Remove from CP | COMPLETED — Not driving schedule | +3d early vs BL | Activity done — remove Longest Path flag to clear CP noise
Foundation drawing PSA-2 OffGas Compressor 13-KC-702 |  | 30-Jun-25 A | 05-Sep-25 A | 2025-08-22 | 2025-11-10 | 39 | 47
A49130 | Foundation drawing PSA-2 OffGas Compressor 13-KC-702_RCA | 23-Aug-25 A | 29-Aug-25 A | 2025-10-20 | 2025-11-10 | 40 | 52 |  | Yes | FALSE POSITIVE — Remove from CP | COMPLETED — Not driving schedule | +52d early vs BL | Activity done — remove Longest Path flag to clear CP noise
A49140 | Foundation drawing PSA-2 OffGas Compressor 13-KC-702_IFD/IFC | 30-Aug-25 A | 05-Sep-25 A | 2025-11-04 | 2025-11-06 | 47 | 45 |  | Yes | FALSE POSITIVE — Remove from CP | COMPLETED — Not driving schedule | +45d early vs BL | Activity done — remove Longest Path flag to clear CP noise
A49120 | Foundation drawing PSA-2 OffGas Compressor 13-KC-702_IFA | 16-Aug-25 A | 22-Aug-25 A | 2025-10-16 | 2025-10-21 | 43 | 43 |  | Yes | FALSE POSITIVE — Remove from CP | COMPLETED — Not driving schedule | +43d early vs BL | Activity done — remove Longest Path flag to clear CP noise
A18880 | Foundation drawing PSA-2 OffGas Compressor 13-KC-702_IFR | 30-Jun-25 A | 10-Jul-25 A | 2025-09-09 | 2025-09-24 | 51 | 54 |  | Yes | FALSE POSITIVE — Remove from CP | COMPLETED — Not driving schedule | +54d early vs BL | Activity done — remove Longest Path flag to clear CP noise
A49110 | Foundation drawing PSA-2 OffGas Compressor 13-KC-702_RCC | 11-Jul-25 A | 15-Aug-25 A | 2025-08-22 | 2025-09-12 | 30 | 21 |  | Yes | FALSE POSITIVE — Remove from CP | COMPLETED — Not driving schedule | +21d early vs BL | Activity done — remove Longest Path flag to clear CP noise
Pile Layout Compressor Shelter & SR8001 |  | 01-Jul-25 A | 13-Sep-25 A | 2025-08-29 | 2025-10-22 | 43 | 28
A17660 | Pile Layout Compressor Shelter & SR8001_RCA | 25-Aug-25 A | 06-Sep-25 A | 2025-10-01 | 2025-10-22 | 27 | 33 |  | Yes | FALSE POSITIVE — Remove from CP | COMPLETED — Not driving schedule | +33d early vs BL | Activity done — remove Longest Path flag to clear CP noise
A17670 | Pile Layout Compressor Shelter & SR8001_IFD/IFC | 08-Sep-25 A | 13-Sep-25 A | 2025-10-17 | 2025-10-21 | 29 | 26 |  | Yes | FALSE POSITIVE — Remove from CP | COMPLETED — Not driving schedule | +26d early vs BL | Activity done — remove Longest Path flag to clear CP noise
A17650 | Pile Layout Compressor Shelter & SR8001_IFA | 25-Aug-25 A | 30-Aug-25 A | 2025-09-26 | 2025-10-01 | 24 | 22 |  | Yes | FALSE POSITIVE — Remove from CP | COMPLETED — Not driving schedule | +22d early vs BL | Activity done — remove Longest Path flag to clear CP noise
A17640 | Pile Layout Compressor Shelter & SR8001_RCC | 14-Jul-25 A | 22-Aug-25 A | 2025-09-08 | 2025-09-29 | 40 | 27 |  | Yes | FALSE POSITIVE — Remove from CP | COMPLETED — Not driving schedule | +27d early vs BL | Activity done — remove Longest Path flag to clear CP noise
A17630 | Pile Layout Compressor Shelter & SR8001_IFR | 01-Jul-25 A | 12-Jul-25 A | 2025-08-29 | 2025-09-05 | 43 | 40 |  | Yes | FALSE POSITIVE — Remove from CP | COMPLETED — Not driving schedule | +40d early vs BL | Activity done — remove Longest Path flag to clear CP noise
Pile Reinforcement Drawing |  | 01-Jul-25 A | 18-Jul-25 A | 2025-07-28 | 2025-08-04 | 19 | 12
A17480 | Pile Reinforcement Drawing_IFR | 01-Jul-25 A | 18-Jul-25 A | 2025-07-28 | 2025-08-04 | 19 | 12 |  | Yes | FALSE POSITIVE — Remove from CP | COMPLETED — Not driving schedule | +12d early vs BL | Activity done — remove Longest Path flag to clear CP noise
Pile Layout PSA-2 FeedGas Compressor 13-KC-701 |  | 10-Apr-25 A | 15-Sep-25 A | 2025-03-19 | 2025-10-13 | -16 | 21
A48320 | Pile Layout PSA-2 FeedGas Compressor 13-KC-701_RCC | 16-Aug-25 A | 22-Aug-25 A | 2025-09-22 | 2025-10-13 | 25 | 37 |  | Yes | FALSE POSITIVE — Remove from CP | COMPLETED — Not driving schedule | +37d early vs BL | Activity done — remove Longest Path flag to clear CP noise
A17570 | Pile Layout PSA-2 FeedGas Compressor 13-KC-701_IFD/IFC | 08-Sep-25 A | 15-Sep-25 A | 2025-09-19 | 2025-09-23 | 9 | 6 |  | Yes | FALSE POSITIVE — Remove from CP | COMPLETED — Not driving schedule | +6d early vs BL | Activity done — remove Longest Path flag to clear CP noise
A17560 | Pile Layout PSA-2 FeedGas Compressor 13-KC-701_RCA | 18-Aug-25 A | 05-Sep-25 A | 2025-08-27 | 2025-09-17 | 7 | 9 |  | Yes | FALSE POSITIVE — Remove from CP | COMPLETED — Not driving schedule | +9d early vs BL | Activity done — remove Longest Path flag to clear CP noise
A17550 | Pile Layout PSA-2 FeedGas Compressor 13-KC-701_IFA | 22-Aug-25 A | 29-Aug-25 A | 2025-08-22 | 2025-08-27 | 0 | -2 |  | Yes
A17530 | Pile Layout PSA-2 FeedGas Compressor 13-KC-701_IFR | 10-Apr-25 A | 15-Aug-25 A | 2025-03-19 | 2025-03-26 | -16 | -101 |  | Yes
Pile Layout PSA-2 OffGas Compressor 13-KC-702 |  | 01-Jul-25 A | 15-Sep-25 A | 2025-08-25 | 2025-10-16 | 39 | 24
A17610 | Pile Layout PSA-2 OffGas Compressor 13-KC-702_RCA | 01-Aug-25 A | 06-Sep-25 A | 2025-09-25 | 2025-10-16 | 39 | 29 |  | Yes | FALSE POSITIVE — Remove from CP | COMPLETED — Not driving schedule | +29d early vs BL | Activity done — remove Longest Path flag to clear CP noise
A17620 | Pile Layout PSA-2 OffGas Compressor 13-KC-702_IFD/IFC | 08-Sep-25 A | 15-Sep-25 A | 2025-10-13 | 2025-10-15 | 25 | 22 |  | Yes | FALSE POSITIVE — Remove from CP | COMPLETED — Not driving schedule | +22d early vs BL | Activity done — remove Longest Path flag to clear CP noise
A17600 | Pile Layout PSA-2 OffGas Compressor 13-KC-702_IFA | 25-Aug-25 A | 30-Aug-25 A | 2025-09-22 | 2025-09-25 | 20 | 18 |  | Yes | FALSE POSITIVE — Remove from CP | COMPLETED — Not driving schedule | +18d early vs BL | Activity done — remove Longest Path flag to clear CP noise
A17590 | Pile Layout PSA-2 OffGas Compressor 13-KC-702_RCC | 14-Jul-25 A | 22-Aug-25 A | 2025-09-02 | 2025-09-23 | 36 | 23 |  | Yes | FALSE POSITIVE — Remove from CP | COMPLETED — Not driving schedule | +23d early vs BL | Activity done — remove Longest Path flag to clear CP noise
A17580 | Pile Layout PSA-2 OffGas Compressor 13-KC-702_IFR | 01-Jul-25 A | 11-Jul-25 A | 2025-08-25 | 2025-09-01 | 39 | 37 |  | Yes | FALSE POSITIVE — Remove from CP | COMPLETED — Not driving schedule | +37d early vs BL | Activity done — remove Longest Path flag to clear CP noise
Subcontract Services |  | 14-Nov-24 A | 11-May-25 A | 2024-11-14 | 2025-08-18 | 0 | 71
Detail Engineering Subcontract |  | 14-Nov-24 A | 06-Dec-24 A | 2024-11-14 | 2024-11-29 | 0 | -4
A61120 | Subcontract Awarded/Signed | 29-Nov-24 A | 06-Dec-24 A | 2024-11-27 | 2024-11-29 | -2 | -4 |  | Yes
A61110 | Bid analysis and clarifications | 23-Nov-24 A | 29-Nov-24 A | 2024-11-22 | 2024-11-26 | -1 | -2 |  | Yes
A61100 | Technical Bid analysis and clarifications | 19-Nov-24 A | 22-Nov-24 A | 2024-11-19 | 2024-11-21 | 0 | 0 |  | Yes
A61090 | Issue RFQ to CONTRACTORs | 14-Nov-24 A | 15-Nov-24 A | 2024-11-14 | 2024-11-18 | 0 | 2 |  | Yes | FALSE POSITIVE — Remove from CP | COMPLETED — Not driving schedule | +2d early vs BL | Activity done — remove Longest Path flag to clear CP noise
Main Construction |  | 09-Dec-24 A | 10-Mar-25 A | 2024-12-09 | 2025-04-04 | 0 | 20
A61200 | Subcontract Awarded/Signed | 07-Mar-25 A | 10-Mar-25 A | 2025-03-07 | 2025-04-04 | 0 | 20 |  | Yes | FALSE POSITIVE — Remove from CP | COMPLETED — Not driving schedule | +20d early vs BL | Activity done — remove Longest Path flag to clear CP noise
A61190 | Bid analysis and clarifications | 16-Feb-25 A | 25-Feb-25 A | 2025-02-06 | 2025-03-06 | -7 | 8 |  | Yes | FALSE POSITIVE — Remove from CP | COMPLETED — Not driving schedule | +8d early vs BL | Activity done — remove Longest Path flag to clear CP noise
A61180 | Technical Bid analysis and clarifications | 02-Feb-25 A | 15-Feb-25 A | 2025-01-08 | 2025-02-05 | -18 | -7 |  | Yes
A61170 | Issue RFQ to CONTRACTORs | 09-Dec-24 A | 01-Feb-25 A | 2024-12-09 | 2025-01-06 | 0 | -19 |  | Yes
Topgraphic |  | 01-Jan-25 A | 20-Mar-25 A | 2025-01-06 | 2025-05-02 | 3 | 32
A61240 | Subcontract Awarded/Signed | 02-Mar-25 A | 20-Mar-25 A | 2025-04-04 | 2025-05-02 | 24 | 32 |  | Yes | FALSE POSITIVE — Remove from CP | COMPLETED — Not driving schedule | +32d early vs BL | Activity done — remove Longest Path flag to clear CP noise
A61230 | Bid analysis and clarifications | 04-Feb-25 A | 01-Mar-25 A | 2025-03-05 | 2025-04-02 | 21 | 23 |  | Yes | FALSE POSITIVE — Remove from CP | COMPLETED — Not driving schedule | +23d early vs BL | Activity done — remove Longest Path flag to clear CP noise
A61220 | Technical Bid analysis and clarifications | 04-Jan-25 A | 03-Feb-25 A | 2025-02-04 | 2025-03-04 | 21 | 22 |  | Yes | FALSE POSITIVE — Remove from CP | COMPLETED — Not driving schedule | +22d early vs BL | Activity done — remove Longest Path flag to clear CP noise
A61210 | Issue RFQ to CONTRACTORs | 01-Jan-25 A | 03-Jan-25 A | 2025-01-06 | 2025-02-03 | 3 | 22 |  | Yes | FALSE POSITIVE — Remove from CP | COMPLETED — Not driving schedule | +22d early vs BL | Activity done — remove Longest Path flag to clear CP noise
Piling |  | 01-Apr-25 A | 11-May-25 A | 2025-04-18 | 2025-08-18 | 13 | 71
A61280 | Subcontract Awarded/Signed | 05-May-25 A | 11-May-25 A | 2025-07-21 | 2025-08-18 | 55 | 71 |  | Yes | FALSE POSITIVE — Remove from CP | COMPLETED — Not driving schedule | +71d early vs BL | Activity done — remove Longest Path flag to clear CP noise
A61270 | Bid analysis and clarifications | 28-Apr-25 A | 04-May-25 A | 2025-06-19 | 2025-07-17 | 38 | 54 |  | Yes | FALSE POSITIVE — Remove from CP | COMPLETED — Not driving schedule | +54d early vs BL | Activity done — remove Longest Path flag to clear CP noise
A61260 | Technical Bid analysis and clarifications | 21-Apr-25 A | 27-Apr-25 A | 2025-05-19 | 2025-06-16 | 20 | 36 |  | Yes | FALSE POSITIVE — Remove from CP | COMPLETED — Not driving schedule | +36d early vs BL | Activity done — remove Longest Path flag to clear CP noise
A61250 | Issue RFQ to CONTRACTORs | 01-Apr-25 A | 20-Apr-25 A | 2025-04-18 | 2025-05-16 | 13 | 20 |  | Yes | FALSE POSITIVE — Remove from CP | COMPLETED — Not driving schedule | +20d early vs BL | Activity done — remove Longest Path flag to clear CP noise
Construction and Pre-Commissioning |  | 09-Jan-25 A | 2027-01-20 | 2025-05-22 | 2027-01-20 | 114 | 0 | 0 |  | FALSE NEGATIVE — Add to CP | MISSED CRITICAL — 0 Float | 0d vs BL | Set Longest Path = Yes; monitor as critical deliverable
Civil Construction |  | 09-Jan-25 A | 2026-09-10 | 2025-05-22 | 2026-09-10 | 114 | 0 | 0 |  | FALSE NEGATIVE — Add to CP | MISSED CRITICAL — 0 Float | 0d vs BL | Set Longest Path = Yes; monitor as critical deliverable
Foundations |  | 31-Jul-25 A | 2026-03-23 | 2025-09-27 | 2026-01-08 | 49 | -63 | 0 |  | FALSE NEGATIVE — Add to CP | MISSED CRITICAL — 0 Float | -63d vs BL | Set Longest Path = Yes; monitor as critical deliverable
GF Foundations |  | 31-Jul-25 A | 2026-03-23 | 2025-09-27 | 2026-01-08 | 49 | -63 | 0 |  | FALSE NEGATIVE — Add to CP | MISSED CRITICAL — 0 Float | -63d vs BL | Set Longest Path = Yes; monitor as critical deliverable
FG/OG Compressor and Shleter Foundation including shelter concrete trench |  | 31-Jul-25 A | 2026-03-23 | 2025-09-27 | 2026-01-08 | 49 | -63 | 0 |  | FALSE NEGATIVE — Add to CP | MISSED CRITICAL — 0 Float | -63d vs BL | Set Longest Path = Yes; monitor as critical deliverable
A15660 | Excavation | 31-Jul-25 A | 23-Aug-25 A | 2025-12-18 | 2026-01-08 | 121 | 120 |  | Yes | FALSE POSITIVE — Remove from CP | COMPLETED — Not driving schedule | +120d early vs BL | Activity done — remove Longest Path flag to clear CP noise
A15890 | Back filling and compaction in layers | 2026-03-07 | 2026-03-23 | 2025-11-15 | 2025-12-31 | -96 | -70 | 0 | Yes | FASTER THAN BL — Recovery | IN PROGRESS / FUTURE | -70d vs BL finish | Backfilling: 16d curr vs 46d BL (−30d FASTER). 85d total downstream recovery.
A15880 | Protective Coating | 2026-02-28 | 2026-03-16 | 2025-11-08 | 2025-12-25 | -96 | -69 | 0 | Yes | FASTER THAN BL — Recovery | IN PROGRESS / FUTURE | -69d vs BL finish | Protective coating: 16d curr vs 47d BL (−31d FASTER). Recovery built in.
A15870 | Formwork removal | 2026-02-21 | 2026-03-09 | 2025-11-01 | 2025-12-11 | -96 | -75 | 0 | Yes | FASTER THAN BL — Recovery | IN PROGRESS / FUTURE | -75d vs BL finish | Formwork removal: 16d curr vs 40d BL (−24d FASTER). Recovery built in.
A15860 | Concrete Curing | 27-Dec-25 A | 2026-03-04 | 2025-10-25 | 2025-12-11 | -54 | -71 | 0 | Yes | OVERRUN — Acceleration needed | IN PROGRESS / FUTURE | -71d vs BL finish | Concrete curing: 67d curr vs 47d BL (+20d). Cannot chemically accelerate.
A15850 | Concrete pouring | 19-Dec-25 A | 2026-03-09 | 2025-10-25 | 2025-12-04 | -48 | -81 | 0 | Yes | OVERRUN — Acceleration needed | IN PROGRESS / FUTURE | -81d vs BL finish | Concrete pour: 80d curr vs 40d BL (+40d). Night shift to recover 5-7d.
A15840 | Rebar works | 15-Dec-25 A | 2026-02-28 | 2025-10-18 | 2025-11-27 | -50 | -79 | 0 | Yes | OVERRUN — Acceleration needed | IN PROGRESS / FUTURE | -79d vs BL finish | Rebar: 75d curr vs 40d BL (+35d). Additional crew set required.
A15790 | Formworks | 19-Dec-25 A | 2026-02-28 | 2025-10-18 | 2025-11-27 | -54 | -79 | 0 | Yes | OVERRUN — Acceleration needed | IN PROGRESS / FUTURE | -79d vs BL finish | Formworks: 71d curr vs 40d BL (+31d). Overlapping sets to compress.
A15750 | Water proofing and bitumen coating/sheet | 15-Oct-25 A | 2026-02-28 | 2025-10-11 | 2025-10-30 | -4 | -103 | 0 | Yes | OVERRUN — Acceleration needed | IN PROGRESS / FUTURE | -103d vs BL finish | Waterproofing: 136d curr vs 19d BL (+117d). Critical compression needed.
A15740 | Lean concrete | 25-Aug-25 A | 30-Aug-25 A | 2025-10-04 | 2025-10-23 | 34 | 48 |  | Yes | FALSE POSITIVE — Remove from CP | COMPLETED — Not driving schedule | +48d early vs BL | Activity done — remove Longest Path flag to clear CP noise
A15670 | Surface leveling and compaction | 11-Aug-25 A | 25-Aug-25 A | 2025-09-27 | 2025-10-16 | 40 | 46 |  | Yes | FALSE POSITIVE — Remove from CP | COMPLETED — Not driving schedule | +46d early vs BL | Activity done — remove Longest Path flag to clear CP noise
Structural Steel and Shades |  | 2026-05-19 | 2026-09-10 | 2026-05-10 | 2026-09-10 | -7 | 0 | 0 |  | FALSE NEGATIVE — Add to CP | MISSED CRITICAL — 0 Float | 0d vs BL | Set Longest Path = Yes; monitor as critical deliverable
GF Steel Works |  | 2026-05-19 | 2026-09-10 | 2026-05-10 | 2026-09-10 | -7 | 0 | 0 |  | FALSE NEGATIVE — Add to CP | MISSED CRITICAL — 0 Float | 0d vs BL | Set Longest Path = Yes; monitor as critical deliverable
A23500 | Piping Platforms | 2026-08-12 | 2026-09-10 | 2026-08-11 | 2026-09-10 | 0 | 0 | 0 | Yes
A17810 | Compressors Area- Steel Structure Erection | 2026-05-19 | 2026-09-10 | 2026-05-10 | 2026-09-10 | -7 | 0 | 0 | Yes
A17820 | Pipe Rack SR81 - Structure Installation | 2026-06-28 | 2026-09-10 | 2026-06-27 | 2026-09-10 | 0 | 0 | 0 | Yes
Others |  | 09-Jan-25 A | 20-Jun-25 A | 2025-05-22 | 2026-02-15 | 114 | 206
Topographic |  | 09-Jan-25 A | 23-May-25 A | 2025-05-22 | 2025-08-12 | 114 | 70
Topographic/UG Survey |  | 09-Jan-25 A | 22-May-25 A | 2025-05-22 | 2025-08-12 | 114 | 71
E1100 | Reports of Getech Investigation / UG Scanning | 16-May-25 A | 22-May-25 A | 2025-08-09 | 2025-08-12 | 72 | 71 |  | Yes | FALSE POSITIVE — Remove from CP | COMPLETED — Not driving schedule | +71d early vs BL | Activity done — remove Longest Path flag to clear CP noise
E1060 | Geotech / Survery of Site | 09-May-25 A | 15-May-25 A | 2025-08-02 | 2025-08-05 | 72 | 71 |  | Yes | FALSE POSITIVE — Remove from CP | COMPLETED — Not driving schedule | +71d early vs BL | Activity done — remove Longest Path flag to clear CP noise
E1090 | Mobilization of Geotech / UG Scanning | 01-May-25 A | 08-May-25 A | 2025-07-26 | 2025-07-29 | 73 | 71 |  | Yes | FALSE POSITIVE — Remove from CP | COMPLETED — Not driving schedule | +71d early vs BL | Activity done — remove Longest Path flag to clear CP noise
E1110 | CICPA Passes for Geotech Sub Contractor | 21-Mar-25 A | 17-Apr-25 A | 2025-07-10 | 2025-07-20 | 96 | 81 |  | Yes | FALSE POSITIVE — Remove from CP | COMPLETED — Not driving schedule | +81d early vs BL | Activity done — remove Longest Path flag to clear CP noise
E1070 | Topo/ UG Scanning Survey | 18-Apr-25 A | 30-Apr-25 A | 2025-07-08 | 2025-07-13 | 69 | 63 |  | Yes | FALSE POSITIVE — Remove from CP | COMPLETED — Not driving schedule | +63d early vs BL | Activity done — remove Longest Path flag to clear CP noise
E1080 | TBE & PO issuance of Geotech / UG Scanning | 02-Mar-25 A | 20-Mar-25 A | 2025-07-01 | 2025-07-08 | 104 | 95 |  | Yes | FALSE POSITIVE — Remove from CP | COMPLETED — Not driving schedule | +95d early vs BL | Activity done — remove Longest Path flag to clear CP noise
A28960 | TBE for Topo,UG & Getechnical Survey_IFD/IFC | 11-Feb-25 A | 01-Mar-25 A | 2025-06-23 | 2025-06-28 | 113 | 103 |  | Yes | FALSE POSITIVE — Remove from CP | COMPLETED — Not driving schedule | +103d early vs BL | Activity done — remove Longest Path flag to clear CP noise
A56200 | TBE for Topo,UG & Getechnical Survey_RCC | 16-Jan-25 A | 10-Feb-25 A | 2025-05-29 | 2025-06-12 | 114 | 106 |  | Yes | FALSE POSITIVE — Remove from CP | COMPLETED — Not driving schedule | +106d early vs BL | Activity done — remove Longest Path flag to clear CP noise
A56190 | TBE for Topo,UG & Getechnical Survey_IFR | 09-Jan-25 A | 15-Jan-25 A | 2025-05-22 | 2025-05-27 | 114 | 114 |  | Yes | FALSE POSITIVE — Remove from CP | COMPLETED — Not driving schedule | +114d early vs BL | Activity done — remove Longest Path flag to clear CP noise
Geotech/ Topographic/UG Survey |  | 11-Feb-25 A | 23-May-25 A | 2025-05-22 | 2025-07-31 | 86 | 59
E1040 | Reports of Getech Investigation / UG Scanning | 17-May-25 A | 23-May-25 A | 2025-07-22 | 2025-07-31 | 57 | 59 |  | Yes | FALSE POSITIVE — Remove from CP | COMPLETED — Not driving schedule | +59d early vs BL | Activity done — remove Longest Path flag to clear CP noise
E1030 | Geotech / Survery of Site | 10-May-25 A | 16-May-25 A | 2025-07-08 | 2025-07-17 | 51 | 53 |  | Yes | FALSE POSITIVE — Remove from CP | COMPLETED — Not driving schedule | +53d early vs BL | Activity done — remove Longest Path flag to clear CP noise
E1020 | Mobilization of Geotech / UG Scanning | 01-May-25 A | 08-May-25 A | 2025-07-01 | 2025-07-06 | 52 | 50 |  | Yes | FALSE POSITIVE — Remove from CP | COMPLETED — Not driving schedule | +50d early vs BL | Activity done — remove Longest Path flag to clear CP noise
E1050 | CICPA Passes for Geotech Sub Contractor | 21-Mar-25 A | 17-Apr-25 A | 2025-06-09 | 2025-06-23 | 69 | 58 |  | Yes | FALSE POSITIVE — Remove from CP | COMPLETED — Not driving schedule | +58d early vs BL | Activity done — remove Longest Path flag to clear CP noise
E1010 | TBE & PO issuance of Geotech / UG Scanning | 02-Mar-25 A | 20-Mar-25 A | 2025-05-29 | 2025-06-05 | 76 | 67 |  | Yes | FALSE POSITIVE — Remove from CP | COMPLETED — Not driving schedule | +67d early vs BL | Activity done — remove Longest Path flag to clear CP noise
E1000 | RFQ of Geotech / UG Scanning | 11-Feb-25 A | 01-Mar-25 A | 2025-05-22 | 2025-05-27 | 86 | 75 |  | Yes | FALSE POSITIVE — Remove from CP | COMPLETED — Not driving schedule | +75d early vs BL | Activity done — remove Longest Path flag to clear CP noise
Piling (No required) |  | 20-Jun-25 A | 20-Jun-25 A | 2025-07-01 | 2026-02-15 | 10 | 206
Piling Works |  | 20-Jun-25 A | 20-Jun-25 A | 2025-07-01 | 2026-02-15 | 10 | 206
A15550 | Piling Work (Compressors, Sheds & Equipment) | 20-Jun-25 A | 20-Jun-25 A | 2025-11-26 | 2026-02-15 | 137 | 206 |  | Yes | FALSE POSITIVE — Remove from CP | COMPLETED — Not driving schedule | +206d early vs BL | Activity done — remove Longest Path flag to clear CP noise
A23610 | Mobilization for Production Piles | 20-Jun-25 A | 20-Jun-25 A | 2025-09-13 | 2025-09-27 | 73 | 85 |  | Yes | FALSE POSITIVE — Remove from CP | COMPLETED — Not driving schedule | +85d early vs BL | Activity done — remove Longest Path flag to clear CP noise
A15650 | Test Piles (including curing time) | 20-Jun-25 A | 20-Jun-25 A | 2025-08-17 | 2025-09-13 | 50 | 73 |  | Yes | FALSE POSITIVE — Remove from CP | COMPLETED — Not driving schedule | +73d early vs BL | Activity done — remove Longest Path flag to clear CP noise
A15730 | Mobilization of piling contractor | 20-Jun-25 A | 20-Jun-25 A | 2025-07-22 | 2025-08-10 | 28 | 44 |  | Yes | FALSE POSITIVE — Remove from CP | COMPLETED — Not driving schedule | +44d early vs BL | Activity done — remove Longest Path flag to clear CP noise
A15690 | Data for Test pile |  | 20-Jun-25 A |  | 2025-08-10 | 44 | 44 |  | Yes | FALSE POSITIVE — Remove from CP | COMPLETED — Not driving schedule | +44d early vs BL | Activity done — remove Longest Path flag to clear CP noise
A15720 | PO for Piling Contractor | 20-Jun-25 A | 20-Jun-25 A | 2025-07-01 | 2025-07-15 | 10 | 22 |  | Yes | FALSE POSITIVE — Remove from CP | COMPLETED — Not driving schedule | +22d early vs BL | Activity done — remove Longest Path flag to clear CP noise
Mechanical Construction |  | 2026-03-24 | 2026-12-01 | 2026-03-15 | 2026-12-01 | -7 | 0 | 0 |  | FALSE NEGATIVE — Add to CP | MISSED CRITICAL — 0 Float | 0d vs BL | Set Longest Path = Yes; monitor as critical deliverable
Equipment erection and installation |  | 2026-03-24 | 2026-12-01 | 2026-03-15 | 2026-12-01 | -7 | 0 | 0 |  | FALSE NEGATIVE — Add to CP | MISSED CRITICAL — 0 Float | 0d vs BL | Set Longest Path = Yes; monitor as critical deliverable
GF Feed Gas Compressor and Auxilary Equipment Errection |  | 2026-03-24 | 2026-12-01 | 2026-03-15 | 2026-12-01 | -7 | 0 | 0 |  | FALSE NEGATIVE — Add to CP | MISSED CRITICAL — 0 Float | 0d vs BL | Set Longest Path = Yes; monitor as critical deliverable
Feed Gas (FG) Compressor Installation |  | 2026-03-24 | 2026-12-01 | 2026-03-15 | 2026-12-01 | -7 | 0 | 0 |  | FALSE NEGATIVE — Add to CP | MISSED CRITICAL — 0 Float | 0d vs BL | Set Longest Path = Yes; monitor as critical deliverable
C1009 | Punch List Close Out FG Compressor | 2026-11-21 | 2026-12-01 | 2026-11-19 | 2026-12-01 | 0 | 0 | 0 | Yes
C1008 | E&I Installation - FG Compressor | 2026-10-05 | 2026-11-19 | 2026-10-04 | 2026-11-19 | 0 | 0 | 0 | Yes
C1007 | Installation of Piping - FG Compressor | 2026-09-12 | 2026-11-02 | 2026-09-10 | 2026-11-02 | 0 | 0 | 0 | Yes
C1001 | Installation of FG Compressor (Setting of Pad, Preparation, Position and Leveling) | 2026-05-05 | 2026-05-18 | 2026-04-26 | 2026-05-10 | -7 | -7 | 0 | Yes
C1002 | Setting of FG Compressor Base Plate (Temporary settng, Elevation, Level, Tolerance, Position) | 2026-04-11 | 2026-05-04 | 2026-04-01 | 2026-04-26 | -7 | -7 | 0 | Yes
C1000 | FG Foundation Plan - Foundation Check & Dimensional Examination - FG Compressor | 2026-03-24 | 2026-04-09 | 2026-03-15 | 2026-04-01 | -7 | -7 | 0 | Yes
Pre-commissioning |  | 2026-12-02 | 2027-01-20 | 2026-12-01 | 2027-01-20 | 0 | 0 | 0 |  | FALSE NEGATIVE — Add to CP | MISSED CRITICAL — 0 Float | 0d vs BL | Set Longest Path = Yes; monitor as critical deliverable
GF Pre Commissioning FG/OG Compressor |  | 2026-12-02 | 2027-01-20 | 2026-12-01 | 2027-01-20 | 0 | 0 | 0 |  | FALSE NEGATIVE — Add to CP | MISSED CRITICAL — 0 Float | 0d vs BL | Set Longest Path = Yes; monitor as critical deliverable
C1014 | Pre-commissioning punchlist clearing | 2027-01-04 | 2027-01-20 | 2027-01-03 | 2027-01-20 | 0 | 0 | 0 | Yes
C1013 | Final compressor/driver alignment | 2026-12-14 | 2027-01-03 | 2026-12-13 | 2027-01-03 | 0 | 0 | 0 | Yes
C1010 | Flushing/Airblowing and inspection of piping | 2026-12-02 | 2026-12-19 | 2026-12-01 | 2026-12-19 | 0 | 0 | 0 | Yes
C1011 | Lube Oil Flushing | 2026-12-02 | 2026-12-13 | 2026-12-01 | 2026-12-13 | 0 | 0 | 0 | Yes

## CP Legend
Critical Path Analysis — Correction Legend
COLOUR CODE | MEANING
RED | FALSE POSITIVE — Activity is DONE and ahead of baseline. Remove from Longest Path flag. 67 activities.
AMBER | OVERRUN — Activity is in progress but finishing later than baseline. Duration longer than planned.
GREEN | RECOVERY BUILT IN — Activity planned to be faster than baseline, offsetting upstream delays.
BLUE | FALSE NEGATIVE — Activity has 0 float but NOT marked as Longest Path. Add to CP monitoring. 20 activities.
KEY FINDINGS
False positives | 67 activities on Longest Path that are DONE (completed early vs BL). Remove to clean CP display.
False negatives | 20 activities with 0 float NOT on Longest Path: Civil Construction, Foundations, FG/OG Shelter,
Structural Steel, Mechanical Construction, Pre-commissioning. These ARE driving the project end date.
Civil overruns | A15750 (+117d dur), A15850 (+40d), A15840 (+35d), A15790 (+31d), A15860 (+20d)
Civil recovery | A15870/A15880/A15890 planned at 16d each vs 40-47d BL = 85 DAYS built-in downstream recovery
Net project impact | 85d downstream recovery absorbs 70-103d foundation delay. C1000 only 7d late. MC ON BASELINE.
Compressor chain | C1000-C1014 each 1-2 days shorter than BL = 13 days total compression. PAC variance: 0 days.
OPTIMAL REORGANISATION SAVINGS
Remove 67 false positives | Clears CP noise, focuses PM bandwidth on 25 real future critical activities
Add 20 false negatives | Proper monitoring of actual zero-float WBS chain driving project end date
Recognise 85d civil recovery | Downstream civil compression absorbs foundation delay — prevents unnecessary panic acceleration
Recover 7-day C1000 slip | 1 day/week overtime on foundation check + baseplate setting recovers the residual slip
Total recoverable time | ~7 days residual slip to project MC if optimal CP structure applied from Feb 2026