## Benchmark
Category | Benchmark Metric | Typical Range / Reference | Use in Future Projects
Total Construction Productivity | Total construction manhours | ~80,000–85,000 MH (from summary sheet) | Baseline labour requirement for similar process unit
Discipline Cost Distribution | Civil | 20–30% of construction cost | Detect scope imbalance
| Mechanical (equipment + piping) | 35–45% | Key driver in process plants
| Electrical | 10–15% | Power & cable intensive plants may be higher
| Instrumentation | 8–12% | Control system complexity indicator
Steel Structure | Labour productivity | 35–60 MH / ton | Benchmark for steel erection
Civil Works | Concrete installation | 4–8 MH / m³ | Civil productivity benchmark
Piling Works | Piling productivity | 6–12 MH / pile (typical industrial) | Foundation cost comparison
Piping Installation | Labour productivity | 0.8–1.5 MH / inch-dia (GF) | Piping productivity baseline
| Brownfield piping | 1.5–3 MH / inch-dia | Congestion impact benchmark
Mechanical Equipment | Installation labour | 150–600 MH per major equipment | Equipment erection comparison
Heat Exchangers | Installation + alignment | 200–400 MH typical | Mechanical benchmark
Vessels / Drums | Installation | 150–350 MH | Equipment install reference
Electrical | Cable laying productivity | 0.15–0.40 MH / meter | Electrical labour benchmarking
| Cable termination | 1–3 MH per cable | Commissioning planning
Instrumentation | Instrument loop installation | 12–25 MH per loop | Controls installation benchmark
Greenfield vs Brownfield | Productivity difference | BF typically 20–50% lower productivity | Risk adjustment factor
Procurement Lead Time | Vessels / Drums | 16–24 weeks | Schedule benchmarking
| Heat exchangers | 18–28 weeks | Long-lead planning
| Transformers | 20–30 weeks | Electrical critical path
Construction Duration | Mechanical erection window | ~4–6 months | Scheduling benchmark
Commissioning Preparation | E&I completion before commissioning | 3–6 months before start-up | Commissioning readiness indicator

## Summary
What is going well
Area / Package | Benchmark Duration | Observed Project Duration | Efficiency Driver
Equipment manufacturing and inspection | 18–28 weeks typical | ~16–22 weeks for several items | Early vendor engagement
Mechanical equipment installation | 5–6 months typical | ~4–5 months | Parallel installation activities
Steel structure erection | 4–5 months typical | ~3–4 months | Efficient erection sequencing
Major vessel / cooler installation | 2–3 months typical | ~1.5–2 months | Good crane planning and site readiness
Underground piping installation | 4–5 months typical | ~3–4 months | Early civil completion enabling piping works
What is not going so well.
Area / Package | Benchmark Duration | Observed Project Duration | Likely Reason
Engineering (IFC / Documentation release) | 4–6 months | ~6–8 months | Extended document approval cycles and multiple revision stages
Equipment procurement & deliveries | 16–24 weeks typical | ~20–30+ weeks for several items | Long-lead equipment and vendor coordination
Civil finishing / infrastructure (roads, pavement, architectural works) | 3–4 months typical | ~5–6 months | Works scheduled late in project and dependent on other packages
Electrical heat tracing & loop testing | 3–4 months typical | ~6 months | Sequential execution with cabling and instrumentation
Cabling & E&I integration | 3–5 months typical | ~6+ months | Integration with existing plant (brownfield interfaces)
Commissioning preparation window | 3–4 months typical | ~5 months | Large system integration scope

## Sheet3 (hidden)
Strategic Intelligence from the Benchmark Comparison
This project shows a common EPC pattern:
Construction productivity > Engineering / Integration productivity
Meaning:
Site execution teams are efficient
Bottlenecks occur in engineering approvals and system integration
For future projects this suggests:
Increase front-end engineering maturity before procurement
Accelerate E&I engineering freeze
Introduce earlier commissioning planning
Monitor vendor documentation cycles

## Scorecard
Area | Score / 100 | Assessment | Basis
Project Management | 85 | Strong | Slightly ahead of plan; governance and reporting appear stable
Engineering / EDDR | 65 | Moderate | Progress is materially behind benchmark pace and document cycle looks extended
Procurement – HO Services | 70 | Moderate | Mostly advanced, but still below ideal close-out rate for this stage
Manufacturing & Delivery | 82 | Strong | Ahead of revised baseline; deliveries and vendor progress appear better than benchmark
Bulk Materials | 55 | Weak | Significantly behind expected readiness for this project phase
Main Automation Equipment | 72 | Moderate | Some slippage, but still generally recoverable
Main Electrical Equipment | 76 | Moderate | Slightly below benchmark, but not critical yet
Civil Construction | 50 | Weak | Largest underperformance versus benchmark among core site disciplines
Mechanical Construction | 60 | Weak to Moderate | Behind benchmark; installation pace not yet matching expected construction window
Electrical Construction | 78 | Stable | Roughly on plan, but dependent on upstream material and cabling readiness
Construction & Pre-commissioning Overall | 52 | Weak | Main project drag; construction productivity below expected benchmark
Commissioning Readiness | 68 | Moderate Risk | Still achievable, but only if construction and E&I close-out recover on time
Overall Project Benchmark Index: 68 / 100
Summary:
The project is showing good performance in management and manufacturing/delivery, but site execution and engineering maturity are lagging, especially in civil, bulk materials, and overall construction/pre-commissioning.

## Heatmap
Rank | Delay Driver | Heat Level | Why it matters | Current Benchmark View
1 | Construction & Pre-commissioning | High | Largest variance against plan; directly affects mechanical completion and handover | Materially slower than benchmark
2 | Civil Construction | High | Civil readiness constrains mechanical, E&I, roads, and close-out works | Well behind benchmark
3 | Bulk Materials | High | Delays in material availability ripple into piping, E&I, and construction productivity | Significantly behind benchmark
4 | Engineering / EDDR | Medium-High | Late engineering maturity reduces procurement efficiency and creates downstream rework risk | Slower than benchmark
5 | Mechanical Construction | Medium-High | Installation pace appears below expected window for this project stage | Behind benchmark
Area | Heat Level | Comment
Procurement – HO Services | Medium | Near completion but not yet fully closed out
Main Automation Equipment | Medium | Manageable slippage, but could affect integration
Main Electrical Equipment | Medium | Slightly behind; monitor against commissioning path
E&I Integration / Cabling / Heat Tracing | Medium-High | Based on schedule structure, this remains a likely late-project pressure point
Heat map takeaway
The project’s primary risk is not heavy equipment delivery anymore. The bigger issue is now conversion of engineering and materials into completed construction and pre-commissioning progress.

## Sheet6 (hidden)
Benchmark Area | Typical Good Range | Borouge Indication | Reuse in Other Projects
Engineering maturity by mid-project | 85–95% | Below ideal | Compare EDDR/document close-out rate
Procurement close-out | 90–100% | Slightly below ideal | Check if procurement is still constraining site
Manufacturing / delivery progress | 30–40%+ at current stage depending on weighting | Better than benchmark | Useful sign of vendor-side strength
Bulk material readiness | Should support construction without major constraint | Below benchmark | Early warning metric for site slowdown
Civil construction productivity | Should be materially advanced before peak mech/E&I | Underperforming | Good predictor of downstream congestion
Mechanical construction productivity | 4–6 month efficient execution windows | Slower than benchmark | Compare equipment installation performance
Electrical construction readiness | Should track close to construction plan | Stable but dependent | Good indicator for commissioning readiness
Construction & pre-commissioning overall | Should track near revised baseline | Weak | Best single indicator of schedule health
Commissioning readiness | E&I and mechanical completion should support start-up window | Moderate risk | Can be used as final project readiness score

## Legend
Variance vs Benchmark / Plan | Rating | Score
Ahead by more than 2 percentage points | Green | 85–100
Within +/- 2 points | Amber-Green | 70–84
Behind by 2–5 points | Amber | 55–69
Behind by 5–10 points | Red-Amber | 40–54
Behind by more than 10 points | Red | Below 40
KPI | Why it matters
Engineering maturity % | Predicts procurement and rework risk
Procurement close-out % | Shows whether material readiness will constrain site
Bulk material readiness % | Strong leading indicator for field productivity
Civil progress % | Determines whether downstream trades can flow
Mechanical construction % | Measures erection productivity
Electrical / Instrument progress % | Key for pre-commissioning and start-up
Construction & Pre-commissioning % | Best overall execution health metric
Variance to revised baseline | Most practical management control indicator

## Management review
Bottom-line management view
Where the project is stronger than benchmark
Project management
Manufacturing and delivery
General procurement control
Where the project is weaker than benchmark
Civil construction
Bulk materials readiness
Engineering / EDDR maturity
Mechanical construction
Overall construction and pre-commissioning conversion
Main conclusion
This project looks like a case where upstream management and supply-side performance are reasonably strong, but field conversion into installed progress is underperforming. In other words, the project is not primarily suffering from lack of planning or vendor activity — it is suffering from execution conversion at site and readiness interfaces. | Activity ID | Activity Name | Stage Gate | Early Planned Start | Late Planned Start | Actual Date | Original Duration | Start [Actual] | Late Start | Finish [Actual] | Early Planed Finish | Late Finish | Total Float
A40790 | A40790 | MASTER DELIVERABLE REGISTER (MDR) | Start | 2024-11-28 | 2024-11-28 | 2024-11-28 | 6 | 28-Nov-24 A | 2026-03-02 | 19-Dec-24 A | 2026-02-20 | 2026-03-02
A40840 | A40840 | PLANNING PACKAGE / EDDR | Start | 2025-01-01 | 2025-01-01 | 2025-01-01 | 6 | 01-Jan-25 A | 2027-01-20 | 22-Jan-25 A | 2026-02-20 | 2027-01-20
#N/A | #N/A | PROJECT EXECUTION PLAN (Engineering) | Start | 2025-01-09 | 2025-01-09 | 2025-01-09
A40940 | A40940 | FEED VERIFICATION REPORT | Start | 2025-01-10 | 2025-01-10 | 2025-01-10 | 6 | 27-Mar-25 A | 2026-03-02 | 04-Apr-25 A | 2026-02-20 | 2026-03-02
A1930 | A1930 | CRITICALITY RATING REPORT | Start | 2025-06-21 | 2025-06-21 | 2025-06-21 | 6 | 21-Jun-25 A | 2027-01-20 | 12-Jul-25 A | 2026-02-20 | 2027-01-20
A41100 | A41100 | PROJECT CLOSE OUT REPORT | Start | 2025-12-31 | 2026-01-30 | 2025-10-25 | 2 | 2026-03-23 | 2026-11-27 | 2026-03-25 | 2026-03-25 | 2026-12-01 | 179
A55980 | A55980 | OPERATING MANUAL INCLUDING OPERATING PROCEDURES/GUIDELINES INCLUDING STARTUP AND SHUTDOWN PROCEDURE | Start | 2026-02-14 | 2026-03-16 | - | 6 | 2026-02-20 | 2026-11-19 | 2026-02-27 | 2026-02-27 | 2026-11-26 | 194
A55790 | A55790 | ELECTRICAL LOAD SUMMARY FOR UTILITIES & OFFSITES AREA | Start | 2025-02-14 | 2025-02-14 | 2025-02-14 | 6 | 14-Feb-25 A | 2026-03-27 | 20-Mar-25 A | 2026-02-20 | 2026-03-27
A55900 | A55900 | UNDERGROUND 33KV CABLE ROUTING LAYOUT OVERALL - UPDATE | Start | 2025-10-01 | 2025-10-01 | 2025-10-01 | 6 | 17-Oct-25 A | 2026-09-10 | 25-Oct-25 A | 2026-02-20 | 2026-09-10
A55950 | A55950 | TECHNICAL BID EVALUATION FOR THIRD PARTY HSE STUDIES | Start | 2025-02-25 | 2025-02-25 | 2025-02-25 | 6 | 25-Feb-25 A | 2026-03-02 | 18-Mar-25 A | 2026-02-20 | 2026-03-02
A40990 | A40990 | SITE VISIT REPORT FOR BOP | Start | 2025-03-01 | 2025-03-01 | 2025-03-01 | 6 | 15-Mar-25 A | 2026-03-02 | 22-Mar-25 A | 2026-02-20 | 2026-03-02
A41200 | A41200 | UTILITY DESIGN BASIS | Start | 2024-12-27 | 2024-12-27 | 2024-12-27 | 6 | 27-Dec-24 A | 2026-03-19 | 17-Jan-25 A | 2026-02-20 | 2026-03-19
A41250 | A41250 | CRITICALITY RATING OF SYSTEM | Start | 2025-01-10 | 2025-01-10 | 2025-01-10 | 6 | 10-Jan-25 A | 2026-11-30 | 06-Jun-25 A | 2026-02-20 | 2026-11-30
A41350 | A41350 | PROCESS DATSHEET FOR PSA2 FEED GAS COMPRESSOR 1ST STAGE SUCTION DRUM | Start | 2024-12-31 | 2024-12-31 | 2024-12-31 | 2 | 31-Dec-24 A | 2026-03-02 | 24-Jan-25 A | 2026-02-20 | 2026-03-02
A41400 | A41400 | PROCESS DATSHEET FOR PSA2 FEED GAS COMPRESSOR 1ST STAGE COOLER | Start | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2 | 01-Jan-25 A | 2026-03-02 | 26-Jan-25 A | 2026-02-20 | 2026-03-02
A41450 | A41450 | PROCESS DATSHEET FOR PSA2 FEED GAS COMPRESSOR 2ND STAGE SUCTION DRUM | Start | 2024-12-31 | 2024-12-31 | 2024-12-31 | 2 | 31-Dec-24 A | 2026-03-02 | 24-Jan-25 A | 2026-02-20 | 2026-03-02
A41500 | A41500 | PROCESS DATSHEET FOR PSA2 FEED GAS COMPRESSOR 2ND STAGE COOLER | Start | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2 | 01-Jan-25 A | 2026-03-02 | 26-Jan-25 A | 2026-02-20 | 2026-03-02
A41600 | A41600 | PROCESS DATSHEET FOR PSA2 FEED GAS COMPRESSOR 3RD STAGE COOLER | Start | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2 | 01-Jan-25 A | 2026-03-02 | 26-Jan-25 A | 2026-02-20 | 2026-03-02
A41650 | A41650 | PROCESS DATSHEET FOR PSA2 FEED GAS COMPRESSOR 3RD STAGE DISCHARGE DRUM | Start | 2024-12-31 | 2024-12-31 | 2024-12-31 | 2 | 31-Dec-24 A | 2026-03-02 | 24-Jan-25 A | 2026-02-20 | 2026-03-02
A2630 | A2630 | PROCESS DATSHEET FOR PSA2 OFF GAS COMPRESSOR INTERSTAGE COOLER - 13-HE-708 | Start | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2 | 01-Jan-25 A | 2026-03-02 | 26-Jan-25 A | 2026-02-20 | 2026-03-02
A2730 | A2730 | PROCESS DATSHEET FOR PSA2 OFF GAS COMPRESSOR AFTERCOOLER - 13-HE-709 | Start | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2 | 01-Jan-25 A | 2026-03-02 | 26-Jan-25 A | 2026-02-20 | 2026-03-02
A2830 | A2830 | PROCESS DATSHEET FOR 52-SP-14067 VHP BOILER FEED WATER PREHEATER DRIPLEG | Start | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2 | 01-Jan-25 A | 2026-03-02 | 06-Jun-25 A | 2026-02-20 | 2026-03-02
A41720 | A41720 | PROCESS DATSHEET FOR 50-HE-1410 C4 GUARD ADSORBER REGENERATION GAS COOLER | Start | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2 | 01-Jan-25 A | 2026-03-02 | 27-Apr-25 A | 2026-02-20 | 2026-03-02
A2980 | A2980 | PROCESS DATSHEET FOR 50-VV-1403 C4 GUARD ADSORBER REGENERATION GAS COALESCER | Start | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2 | 01-Jan-25 A | 2026-03-02 | 30-Jan-25 A | 2026-02-20 | 2026-03-02
A41730 | A41730 | PROCESS DATSHEET FOR 70-PC-1407 WATER COLLECTION SUMP PUMP II | Start | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2 | 01-Jan-25 A | 2026-03-02 | 24-Jan-25 A | 2026-02-20 | 2026-03-02
A3080 | A3080 | PROCESS DATSHEET FOR 70-PC-1409 A/B SANITARY WASTE WATER SUMP PUMP | Start | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2 | 01-Jan-25 A | 2026-03-02 | 24-Jan-25 A | 2026-02-20 | 2026-03-02
A28230 | A28230 | PROCESS DATASHEET OF OFF-GAS COMPRESSOR COALESCER | Start | 2025-01-02 | 2025-01-02 | 2025-01-02 | 2 | 18-Jun-25 A | 2027-01-20 | 21-Jun-25 A | 2026-02-20 | 2027-01-20
A3180 | A3180 | ISOLATION PHILOSOPHY | Start | 2025-01-03 | 2025-01-03 | 2025-01-03 | 6 | 03-Jan-25 A | 2026-11-19 | 24-Jan-25 A | 2026-02-20 | 2026-11-19
A41870 | A41870 | VENT AND DRAIN PHILOSOPHY | Start | 2025-01-03 | 2025-01-03 | 2025-01-03 | 6 | 03-Jan-25 A | 2026-11-19 | 24-Jan-25 A | 2026-02-20 | 2026-11-19
A41820 | A41820 | RELIEF AND BLOWDOWN PHILOSOPHY | Start | 2025-01-09 | 2025-01-09 | 2025-01-09 | 6 | 09-Jan-25 A | 2026-11-19 | 30-Jan-25 A | 2026-02-20 | 2026-11-19
A41970 | A41970 | PROCESS SAFEGUARDING DIAGRAM: FEED PRETREATMENT | Start | 2025-01-04 | 2025-01-04 | 2025-01-04 | 11 | 04-Jan-25 A | 2026-03-02 | 25-Jan-25 A | 2026-02-20 | 2026-03-02
A42020 | A42020 | PROCESS SAFEGUARDING DIAGRAM: WASH WATER SYSTEM | Start | 2025-01-04 | 2025-01-04 | 2025-01-04 | 11 | 04-Jan-25 A | 2026-03-02 | 25-Jan-25 A | 2026-02-20 | 2026-03-02
A42070 | A42070 | PROCESS SAFEGUARDING DIAGRAM: CRACKED GAS COMPRESSION | Start | 2025-01-04 | 2025-01-04 | 2025-01-04 | 11 | 04-Jan-25 A | 2026-03-02 | 25-Jan-25 A | 2026-02-20 | 2026-03-02
A42120 | A42120 | PROCESS SAFEGUARDING DIAGRAM: C1/C2 SEPARATION | Start | 2025-01-04 | 2025-01-04 | 2025-01-04 | 11 | 04-Jan-25 A | 2026-03-02 | 25-Jan-25 A | 2026-02-20 | 2026-03-02
A42170 | A42170 | PROCESS SAFEGUARDING DIAGRAM: H2 EXTRACTION UNIT | Start | 2025-01-04 | 2025-01-04 | 2025-01-04 | 11 | 04-Jan-25 A | 2026-03-02 | 25-Jan-25 A | 2026-02-20 | 2026-03-02
A42220 | A42220 | PROCESS SAFEGUARDING DIAGRAM: H2 EXTRACTION UNIT II | Start | 2025-01-04 | 2025-01-04 | 2025-01-04 | 11 | 04-Jan-25 A | 2026-03-02 | 25-Jan-25 A | 2026-02-20 | 2026-03-02
A42270 | A42270 | PROCESS SAFEGUARDING DIAGRAM: C4 SELECTIVE HYDROGENATION IV | Start | 2025-01-04 | 2025-01-04 | 2025-01-04 | 11 | 04-Jan-25 A | 2026-03-02 | 25-Jan-25 A | 2026-02-20 | 2026-03-02
A42320 | A42320 | PROCESS SAFEGUARDING DIAGRAM: FUEL GAS SYSTEM | Start | 2025-01-04 | 2025-01-04 | 2025-01-04 | 11 | 04-Jan-25 A | 2026-03-02 | 25-Jan-25 A | 2026-02-20 | 2026-03-02
A42370 | A42370 | PROCESS SAFEGUARDING DIAGRAM: REGENERATION SYSTEM | Start | 2025-01-04 | 2025-01-04 | 2025-01-04 | 11 | 04-Jan-25 A | 2026-03-02 | 25-Jan-25 A | 2026-02-20 | 2026-03-02
A42420 | A42420 | PROCESS SAFEGUARDING DIAGRAM: BOILER FEED WATER SYSTEM | Start | 2025-01-04 | 2025-01-04 | 2025-01-04 | 11 | 04-Jan-25 A | 2026-03-02 | 25-Jan-25 A | 2026-02-20 | 2026-03-02
A42470 | A42470 | PROCESS SAFEGUARDING DIAGRAM: CONDENSATE COLLECTION SYSTEM | Start | 2025-01-04 | 2025-01-04 | 2025-01-04 | 11 | 04-Jan-25 A | 2026-03-02 | 25-Jan-25 A | 2026-02-20 | 2026-03-02
A42520 | A42520 | PROCESS SAFEGUARDING DIAGRAM: COOLING WATER SYSTEM | Start | 2025-01-04 | 2025-01-04 | 2025-01-04 | 11 | 04-Jan-25 A | 2026-03-02 | 25-Jan-25 A | 2026-02-20 | 2026-03-02
A42620 | A42620 | PROCESS SAFEGUARDING DIAGRAM: BLOWDOWN VESSELS AND ACID GAS FLARE | Start | 2025-01-04 | 2025-01-04 | 2025-01-04 | 11 | 04-Jan-25 A | 2026-03-02 | 25-Jan-25 A | 2026-02-20 | 2026-03-02
A42670 | A42670 | PROCESS SAFEGUARDING DIAGRAM: SLOP,SEWER AND DRAINAGE SYSTEM | Start | 2025-01-04 | 2025-01-04 | 2025-01-04 | 11 | 04-Jan-25 A | 2026-03-02 | 25-Jan-25 A | 2026-02-20 | 2026-03-02
A4130 | A4130 | PROCESS SAFEGUARDING DIAGRAM: SLOP,SEWER AND DRAINAGE SYSTEM II | Start | 2025-01-04 | 2025-01-04 | 2025-01-04 | 11 | 04-Jan-25 A | 2026-03-02 | 25-Jan-25 A | 2026-02-20 | 2026-03-02
A4180 | A4180 | SAFEGUARDING MEMORENDUM | Start | 2025-08-23 | 2025-08-23 | 2025-08-23 | 6 | 02-Sep-25 A | 2027-01-18 | 13-Sep-25 A | 2026-02-20 | 2027-01-18
A42810 | A42810 | PROCESS DATSHEET FOR CONTROL VALVE | Start | 2025-02-20 | 2025-02-20 | 2025-02-20 | 6 | 20-Feb-25 A | 2026-03-02 | 27-Apr-25 A | 2026-02-20 | 2026-03-02
A42960 | A42960 | PROCESS CALCULATION REPORT | Start | 2025-02-20 | 2025-02-20 | 2025-02-20 | 6 | 20-Feb-25 A | 2026-12-22 | 26-Dec-25 A | 2026-02-20 | 2026-12-22
A43110 | A43110 | FLARE RELIEF & BLOWDOWN REPORT | Start | 2025-04-20 | 2025-04-20 | 2025-04-20 | 6 | 03-May-25 A | 2026-11-23 | 11-May-25 A | 2026-02-20 | 2026-11-23
A43160 | A43160 | FLARE RELIEF LOAD SUMMARY | Start | 2025-02-04 | 2025-02-04 | 2025-02-04 | 6 | 31-Jan-25 A | 2026-03-25 | 11-Mar-25 A | 2026-02-20 | 2026-03-25
A43260 | A43260 | 3D MODELLING PROCEDURE | Start | 2025-03-01 | 2025-03-01 | 2025-03-01 | 6 | 01-Mar-25 A | 2026-03-02 | 20-Apr-25 A | 2026-02-20 | 2026-03-02
A55400 | A55400 | 3D MODEL EXECUTION PHILOSOPHY | Start | 2025-03-25 | 2025-03-25 | 2025-03-25 | 6 | 25-Mar-25 A | 2026-10-19 | 15-Apr-25 A | 2026-02-20 | 2026-10-19
A55450 | A55450 | CLASH CHECK PROCEDURE | Start | 2025-03-22 | 2025-03-22 | 2025-03-22 | 6 | 22-Mar-25 A | 2026-10-19 | 12-Apr-25 A | 2026-02-20 | 2026-10-19
A55480 | A55480 | DELIVERABLES EXTRACTION PROCEDURE | Start | 2025-01-22 | 2025-01-22 | 2025-01-22 | 6 | 23-Jan-25 A | 2026-10-19 | 12-Feb-25 A | 2026-02-20 | 2026-10-19
A27960 | A27960 | DATA HANDOVER PROCEDURE | Start | 2025-06-21 | 2025-06-21 | 2025-06-21 | 6 | 21-Jun-25 A | 2026-10-19 | 12-Jul-25 A | 2026-02-20 | 2026-10-19
A28060 | A28060 | SPI EXTRACTION PROCEDURE | Start | 2025-06-21 | 2025-06-21 | 2025-06-21 | 6 | 01-Jul-25 A | 2026-11-30 | 12-Jul-25 A | 2026-02-20 | 2026-11-30
A43310 | A43310 | 3D MODEL REVIEW PROCEDURE | Start | 2025-03-25 | 2025-03-25 | 2025-03-25 | 6 | 25-Mar-25 A | 2027-01-20 | 15-Apr-25 A | 2026-02-20 | 2027-01-20
A43410 | A43410 | PLOT PLAN CLOSE OUT REPORT | Start | 2025-04-19 | 2025-04-19 | 2025-04-19 | 6 | 19-Apr-25 A | 2027-01-20 | 10-May-25 A | 2026-02-20 | 2027-01-20
A45270 | A45270 | FIRST MATERIAL TAKE OFF | Start | 2025-10-25 | 2025-10-25 | 2025-10-25 | 6 | 02-Jun-25 A | 2026-04-22 | 06-Jun-25 A | 2026-02-20 | 2026-04-22
A43460 | A43460 | STRESS CRITICAL LINE LIST | Start | 2025-04-15 | 2025-04-15 | 2025-04-15 | 11 | 15-Apr-25 A | 2026-12-28 | 06-May-25 A | 2026-02-20 | 2026-12-28
A43510 | A43510 | UTILITY STATION LOCATION PLAN | Start | 2025-04-15 | 2025-04-15 | 2025-04-15 | 6 | 15-Apr-25 A | 2027-01-20 | 06-May-25 A | 2026-02-20 | 2027-01-20
A43560 | A43560 | 30% 3D MODEL REVIEW REPORT | Start | 2025-04-25 | 2025-04-25 | 2025-04-25 | 6 | 25-Apr-25 A | 2026-03-02 | 16-May-25 A | 2026-02-20 | 2026-03-02
A43610 | A43610 | 30% 3D MODEL REVIEW CLOSEOUT REPORT | Start | 2025-06-21 | 2025-06-21 | 2025-06-21 | 6 | 01-Jul-25 A | 2026-03-02 | 12-Jul-25 A | 2026-02-20 | 2026-03-02
A43660 | A43660 | DATASHEETS FOR BALL VALVES | Start | 2025-01-16 | 2025-01-16 | 2025-01-16 | 6 | 16-Jan-25 A | 2026-03-17 | 14-May-25 A | 2026-02-20 | 2026-03-17
A43710 | A43710 | DATASHEETS FOR CHECK VALVES | Start | 2025-01-23 | 2025-01-23 | 2025-01-23 | 2 | 23-Jan-25 A | 2026-03-17 | 14-May-25 A | 2026-02-20 | 2026-03-17
A43760 | A43760 | DATASHEETS FOR DOUBLE BLOCK & BLEED VALVES | Start | 2025-01-27 | 2025-01-27 | 2025-01-27 | 6 | 27-Jan-25 A | 2026-03-17 | 01-Aug-25 A | 2026-02-20 | 2026-03-17
A43810 | A43810 | DATASHEETS FOR BUTTERFLY VALVES | Start | 2025-01-16 | 2025-01-16 | 2025-01-16 | 2 | 16-Jan-25 A | 2026-03-17 | 12-Jun-25 A | 2026-02-20 | 2026-03-17
A43860 | A43860 | DATASHEETS FOR NEEDLE VALVES | Start | 2025-01-16 | 2025-01-16 | 2025-01-16 | 2 | 01-Aug-25 A | 2026-03-17 | 05-Aug-25 A | 2026-02-20 | 2026-03-17
A43910 | A43910 | DATASHEETS FOR INSULATING GASKETS | Start | 2025-09-08 | 2025-09-08 | 2025-09-08 | 2 | 22-Sep-25 A | 2026-03-17 | 29-Sep-25 A | 2026-02-20 | 2026-03-17
A43960 | A43960 | Datasheets for Flame Arrestors | Start | 2025-04-20 | 2025-04-20 | 2025-04-20 | 2 | 20-Apr-25 A | 2026-04-17 | 11-May-25 A | 2026-02-20 | 2026-04-17
A44010 | A44010 | DATASHEETS FOR FLAME BIRD SCREEN | Start | 2025-04-15 | 2025-04-15 | 2025-04-15 | 2 | 15-Apr-25 A | 2026-04-17 | 06-May-25 A | 2026-02-20 | 2026-04-17
A44060 | A44060 | DATASHEETS FOR HOSE COUPLING | Start | 2025-06-21 | 2025-06-21 | 2025-06-21 | 6 | 01-Jul-25 A | 2026-03-17 | 12-Jul-25 A | 2026-02-20 | 2026-03-17
A44110 | A44110 | DATASHEETS FOR STRAINERS | Start | 2025-04-14 | 2025-04-14 | 2025-04-14 | 6 | 14-Apr-25 A | 2026-04-17 | 05-May-25 A | 2026-02-20 | 2026-04-17
A44160 | A44160 | DATASHEETS FOR SPRING HANGERS | Start | 2025-04-14 | 2025-04-14 | 2025-04-14 | 2 | 25-Apr-25 A | 2026-03-19 | 30-Apr-25 A | 2026-02-20 | 2026-03-19
A44210 | A44210 | DATASHEETS FOR RIGID STRUTS | Start | 2025-04-15 | 2025-04-15 | 2025-04-15 | 2 | 15-Apr-25 A | 2026-12-23 | 06-May-25 A | 2026-02-20 | 2026-12-23
A45220 | A45220 | PLOT PLAN | Start | 2025-03-14 | 2025-03-14 | 2025-03-14 | 6 | 14-Mar-25 A | 2026-03-02 | 27-Apr-25 A | 2026-02-20 | 2026-03-02
A45300 | A45300 | SECOND MATERIAL TAKE OFF | Start | 2026-01-01 | 2026-01-31 | - | 6 | 23-Dec-25 A | 2026-03-25 | 15-Jan-26 A | 2026-02-20 | 2026-03-25
A44260 | A44260 | 60% 3D MODEL REVIEW REPORT | Start | 2025-09-11 | 2025-09-11 | 2025-09-11 | 6 | 26-Sep-25 A | 2026-03-19 | 02-Oct-25 A | 2026-02-20 | 2026-03-19
A44360 | A44360 | PIPING ISOMETRICS (LARGE BORE) | Start | 2026-01-01 | 2026-01-31 | - | 34 | 14-Jan-26 A | 2026-03-13 | 2026-03-27 | 2026-03-27 | 2026-04-17 | 15
A44410 | A44410 | 90% 3D MODEL REVIEW REPORT | Start | 2026-04-02 | 2026-05-02 | - | 6 | 2026-03-06 | 2026-11-12 | 2026-03-13 | 2026-03-13 | 2026-11-20 | 179
A44460 | A44460 | 90% 3D MODEL REVIEW CLOSEOUT REPORT | Start | 2026-05-02 | 2026-06-01 | - | 6 | 2026-03-13 | 2026-11-20 | 2026-03-23 | 2026-03-23 | 2026-11-27 | 179
A45330 | A45330 | FINAL MATERIAL TAKE OFF | Start | 2026-06-01 | 2026-07-01 | - | 6 | 2026-03-06 | 2026-03-27 | 2026-03-13 | 2026-03-13 | 2026-04-03 | 15
A44510 | A44510 | PIPING ISOMETRICS(SMALL BORE) | Start | 2026-01-31 | 2026-03-02 | - | 23 | 2026-03-06 | 2026-03-27 | 2026-04-07 | 2026-04-07 | 2026-04-28 | 15
A44540 | A44540 | PIPING GA DRAWINGS & KEY PLAN FOR PIPING GADS | Start | 2026-03-02 | 2026-04-01 | - | 37 | 05-Dec-25 A | 2026-03-19 | 18-Dec-25 A | 2026-02-20 | 2026-03-19
A44590 | A44590 | PIPING TIE-INS SCHEDULE | Start | 2026-04-01 | 2026-05-01 | - | 6 | 2026-02-20 | 2026-08-19 | 2026-02-27 | 2026-02-27 | 2026-08-26 | 128
A44720 | A44720 | MATERIAL REQUISITION FOR PIPING BULK | Start | 2025-04-15 | 2025-04-15 | 2025-04-15 | 6 | 15-Apr-25 A | 2026-03-19 | 06-May-25 A | 2026-02-20 | 2026-03-19
A44820 | A44820 | MATERIAL REQUISITION FOR PIPING SPECIALITY ITEMS | Start | 2025-04-14 | 2025-04-14 | 2025-04-14 | 6 | 15-Sep-25 A | 2026-04-17 | 16-Sep-25 A | 2026-02-20 | 2026-04-17
A44870 | A44870 | MATERIAL REQUISITION FOR SPRING HANGERS | Start | 2025-04-22 | 2025-04-22 | 2025-04-22 | 2 | 22-Apr-25 A | 2026-03-19 | 13-May-25 A | 2026-02-20 | 2026-03-19
A44920 | A44920 | MATERIAL REQUISITION FOR RIGID STRUTS | Start | 2025-04-22 | 2025-04-22 | 2025-04-22 | 6 | 22-Apr-25 A | 2026-12-28 | 13-May-25 A | 2026-02-20 | 2026-12-28
A60270 | A60270 | TECHNICAL BID EVALUATION (TBE) FOR PIPING BULK | Start | 2025-08-23 | 2025-08-23 | 2025-08-23 | 8 | 09-Aug-25 A | 2026-04-09 | 12-Aug-25 A | 2026-02-20 | 2026-04-09
A45020 | A45020 | TECHNICAL BID EVALUATION (TBE) FOR MANUAL VALVES | Start | 2025-11-06 | 2025-12-06 | - | 6 | 19-Sep-25 A | 2026-05-15 | 25-Sep-25 A | 2026-02-20 | 2026-05-15
A56590 | A56590 | TECHNICAL BID EVALUATION (TBE) FOR PIPING SPECIALITY ITEMS | Start | 2025-11-01 | 2025-12-01 | - | 11 | 05-Feb-26 A | 2026-04-17 | 10-Feb-26 A | 2026-02-20 | 2026-04-17
A45120 | A45120 | TECHNICAL BID EVALUATION (TBE) FOR SPRING HANGERS | Start | 2025-11-15 | 2025-12-15 | - | 11 | 2026-02-27 | 2026-10-27 | 2026-03-16 | 2026-03-16 | 2026-11-11 | 172
A45170 | A45170 | TECHNICAL BID EVALUATION (TBE) FOR RIGID STRUTS | Start | 2025-12-01 | 2025-12-31 | - | 6 | 2026-02-20 | 2026-11-23 | 2026-02-27 | 2026-02-27 | 2026-11-30 | 196
A47530 | A47530 | ELECTRICAL SYSTEM OPERATING PHILOSOPHY | Start | 2025-12-10 | 2026-01-09 | - | 6 | 2026-02-20 | 2026-11-23 | 2026-02-27 | 2026-02-27 | 2026-11-30 | 196
A47580 | A47580 | TECHNICAL DATA SHEET FOR TRANSFORMER (POWER AND DISTRIBUTION) | Start | 2024-12-23 | 2024-12-23 | 2024-12-23 | 2 | 23-Dec-24 A | 2026-03-02 | 13-Jan-25 A | 2026-02-20 | 2026-03-02
A47630 | A47630 | TECHNICAL DATA SHEET FOR LV MOTORS | Start | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2 | 01-Jan-25 A | 2026-03-02 | 22-Jan-25 A | 2026-02-20 | 2026-03-02
A9880 | A9880 | TECHNICAL DATA SHEET FOR EMERGENCY DIESEL GENERATOR | Start | 2025-01-09 | 2025-01-09 | 2025-01-09 | 2 | 09-Jan-25 A | 2026-03-02 | 02-Mar-25 A | 2026-02-20 | 2026-03-02
A9930 | A9930 | TECHNICAL DATA SHEET FOR 11KV SWITCHGEAR | Start | 2024-12-19 | 2024-12-19 | 2024-12-19 | 2 | 19-Dec-24 A | 2026-03-02 | 09-Jan-25 A | 2026-02-20 | 2026-03-02
A9980 | A9980 | TECHNICAL DATA SHEET FOR LV SWITCHGEAR | Start | 2024-12-27 | 2024-12-27 | 2024-12-27 | 2 | 27-Dec-24 A | 2026-03-02 | 17-Jan-25 A | 2026-02-20 | 2026-03-02
A10030 | A10030 | TECHNICAL DATA SHEET FOR LV VARIABLE FREQUENCY DRIVE | Start | 2025-01-31 | 2025-01-31 | 2025-01-31 | 2 | 31-Jan-25 A | 2026-03-02 | 21-Feb-25 A | 2026-02-20 | 2026-03-02
A10080 | A10080 | TECHNICAL DATA SHEET FOR NEUTRAL EARTHING RESISTOR | Start | 2024-12-19 | 2024-12-19 | 2024-12-19 | 2 | 19-Dec-24 A | 2026-03-02 | 09-Jan-25 A | 2026-02-20 | 2026-03-02
A10130 | A10130 | TECHNICAL DATA SHEET FOR POWER, CONTROL AND EARTHING CABLES | Start | 2025-01-10 | 2025-01-10 | 2025-01-10 | 2 | 10-Jan-25 A | 2026-03-19 | 20-Apr-25 A | 2026-02-20 | 2026-03-19
A10180 | A10180 | TECHNICAL DATA SHEET FOR DIRECT CURRENT UPS SYSTEM | Start | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2 | 01-Jan-25 A | 2026-03-02 | 22-Jan-25 A | 2026-02-20 | 2026-03-02
A10230 | A10230 | TECHNICAL DATA SHEET FOR STATIC AC UPS SYSTEM | Start | 2024-12-27 | 2024-12-27 | 2024-12-27 | 2 | 27-Dec-24 A | 2026-03-02 | 17-Jan-25 A | 2026-02-20 | 2026-03-02
A10280 | A10280 | TECHNICAL DATA SHEET FOR POWER FACTOR CORRECTION CAPACITOR | Start | 2025-01-20 | 2025-01-20 | 2025-01-20 | 2 | 20-Jan-25 A | 2026-03-02 | 21-Feb-25 A | 2026-02-20 | 2026-03-02
A10630 | A10630 | SCOPE OF WORK FOR CATHODIC PROTECTION | Start | 2025-07-23 | 2025-07-23 | 2025-07-23 | 6 | 08-Aug-25 A | 2026-05-15 | 14-Aug-25 A | 2026-02-20 | 2026-05-15
A11130 | A11130 | IO LIST FOR SCMS | Start | 2025-01-24 | 2025-01-24 | 2025-01-24 | 6 | 24-Jan-25 A | 2027-01-20 | 24-Feb-25 A | 2026-02-20 | 2027-01-20
A11180 | A11180 | POWER SYSTEM STUDY REPORT - LOAD FLOW, SHORT CIRCUIT AND MOTOR STARTING | Start | 2025-04-28 | 2025-04-28 | 2025-04-28 | 6 | 28-Apr-25 A | 2026-03-02 | 19-May-25 A | 2026-02-20 | 2026-03-02
A11230 | A11230 | POWER SYSTEM STUDY REPORT - ARC FLASH, HARMONICS RESONANCE | Start | 2025-07-21 | 2025-07-21 | 2025-07-21 | 6 | 18-Jul-25 A | 2026-03-02 | 11-Aug-25 A | 2026-02-20 | 2026-03-02
A11280 | A11280 | PSCAD STUDY REPORT - TRANSIENT STABILITY AND INSULATION COORDINATION | Start | 2025-05-01 | 2025-05-01 | 2025-05-01 | 6 | 01-May-25 A | 2026-11-23 | 22-May-25 A | 2026-02-20 | 2026-11-23
A11530 | A11530 | SINGLE LINE DIAGRAM FOR 11KV SWITCHGEAR | Start | 2025-01-31 | 2025-01-31 | 2025-01-31 | 6 | 31-Jan-25 A | 2026-03-02 | 21-Feb-25 A | 2026-02-20 | 2026-03-02
A11580 | A11580 | SINGLE LINE DIAGRAM FOR AC UPS | Start | 2025-10-04 | 2025-10-04 | 2025-10-04 | 6 | 26-Aug-25 A | 2026-12-08 | 02-Sep-25 A | 2026-02-20 | 2026-12-08
A11630 | A11630 | SINGLE LINE DIAGRAM FOR DC UPS | Start | 2025-02-03 | 2025-02-03 | 2025-02-03 | 6 | 03-Feb-25 A | 2026-12-08 | 24-Feb-25 A | 2026-02-20 | 2026-12-08
A11680 | A11680 | SINGLE LINE DIAGRAM FOR LV SWITCHGEAR | Start | 2025-01-20 | 2025-01-20 | 2025-01-20 | 6 | 20-Jan-25 A | 2027-01-01 | 21-Feb-25 A | 2026-02-20 | 2027-01-01
A11830 | A11830 | CABLE AND TRAY ROUTING LAYOUT - OUTDOOR | Start | 2025-11-21 | 2025-12-21 | 2025-12-24 | 6 | 01-Oct-25 A | 2026-09-01 | 10-Oct-25 A | 2026-02-20 | 2026-09-01
A11880 | A11880 | CABLE AND TRAY ROUTING LAYOUT - INDOOR | Start | 2025-12-06 | 2026-01-05 | 2025-12-20 | 6 | 2026-03-09 | 2026-08-06 | 2026-03-16 | 2026-03-16 | 2026-08-13 | 108
A12080 | A12080 | UPDATION OF EARTHING LAYOUT BUTENE 1, EU3, B3/EU3 | Start | 2026-01-05 | 2026-02-04 | 2025-12-20 | 6 | 10-Sep-25 A | 2026-04-14 | 15-Sep-25 A | 2026-02-20 | 2026-04-14
A10380 | A10380 | NEUTRAL EARTHING RESISTOR SIZING CALCULATION | Start | 2024-12-13 | 2024-12-13 | 2024-12-13 | 6 | 13-Dec-24 A | 2026-04-02 | 09-Jan-25 A | 2026-02-20 | 2026-04-02
A11930 | A11930 | ELECTRICAL SUBSTATION BUILDING LAYOUT | Start | 2025-01-03 | 2025-01-03 | 2025-01-03 | 6 | 03-Jan-25 A | 2026-03-14 | 24-Jan-25 A | 2026-02-20 | 2026-03-14
A12280 | A12280 | SYSTEM ARCHITECTURE DIAGRAM FOR IPCS | Start | 2025-02-12 | 2025-02-12 | 2025-02-12 | 6 | 12-Feb-25 A | 2027-01-20 | 05-Mar-25 A | 2026-02-20 | 2027-01-20
A12330 | A12330 | SYSTEM ARCHITECTURE DIAGRAM FOR SCMS - UPDATE | Start | 2025-06-17 | 2025-06-17 | 2025-06-17 | 6 | 01-Jul-25 A | 2027-01-20 | 08-Jul-25 A | 2026-02-20 | 2027-01-20
A12380 | A12380 | INTERCONNECTION SCHEDULE | Start | 2025-10-30 | 2025-11-29 | 2025-12-20 | 6 | 2026-02-20 | 2026-11-04 | 2026-02-27 | 2026-02-27 | 2026-11-11 | 183
A12430 | A12430 | MATERIAL REQUISITION FOR TRANSFORMER (POWER AND DISTRIBUTION) | Start | 2024-12-19 | 2024-12-19 | 2024-12-19 | 6 | 19-Dec-24 A | 2026-03-02 | 09-Jan-25 A | 2026-02-20 | 2026-03-02
A12480 | A12480 | MATERIAL REQUISITION FOR 11KV SWITCHGEAR | Start | 2025-02-13 | 2025-02-13 | 2025-02-13 | 6 | 13-Feb-25 A | 2026-03-02 | 06-Mar-25 A | 2026-02-20 | 2026-03-02
A12530 | A12530 | MATERIAL REQUISITION FOR LV SWITCHGEAR | Start | 2025-01-20 | 2025-01-20 | 2025-01-20 | 6 | 20-Jan-25 A | 2026-03-02 | 28-Feb-25 A | 2026-02-20 | 2026-03-02
A12630 | A12630 | MATERIAL REQUISITION FOR POWER, CONTROL AND EARTHING CABLES | Start | 2025-04-22 | 2025-04-22 | 2025-04-22 | 6 | 22-Apr-25 A | 2026-03-19 | 13-May-25 A | 2026-02-20 | 2026-03-19
A12680 | A12680 | MATERIAL REQUISITION FOR EMERGENCY DIESEL GENERATOR | Start | 2025-01-01 | 2025-01-01 | 2025-01-01 | 6 | 01-Jan-25 A | 2026-03-02 | 22-Jan-25 A | 2026-02-20 | 2026-03-02
A12730 | A12730 | MATERIAL REQUISITION FOR AC UPS | Start | 2025-01-01 | 2025-01-01 | 2025-01-01 | 6 | 01-Jan-25 A | 2026-03-02 | 22-Jan-25 A | 2026-02-20 | 2026-03-02
A12780 | A12780 | MATERIAL REQUISITION FOR DC UPS | Start | 2025-01-31 | 2025-01-31 | 2025-01-31 | 6 | 31-Jan-25 A | 2026-03-02 | 21-Feb-25 A | 2026-02-20 | 2026-03-02
A12830 | A12830 | MATERIAL REQUISITION FOR LV VARIABLE FREQUENCY DRIVE | Start | 2025-01-31 | 2025-01-31 | 2025-01-31 | 6 | 31-Jan-25 A | 2026-03-02 | 21-Feb-25 A | 2026-02-20 | 2026-03-02
A12880 | A12880 | MATERIAL REQUISITION FOR NEUTRAL GROUNDING RESISTOR | Start | 2024-12-13 | 2024-12-13 | 2024-12-13 | 6 | 13-Dec-24 A | 2026-03-02 | 17-Jan-25 A | 2026-02-20 | 2026-03-02
A13680 | A13680 | INSTRUMENT DATASHEET FOR ELECTRONIC TRANSMITTERS (PRESSURE / LEVEL / DP) | Start | 2025-03-26 | 2025-03-26 | 2025-03-26 | 1 | 26-Mar-25 A | 2026-03-02 | 16-Apr-25 A | 2026-02-20 | 2026-03-02
A13730 | A13730 | INSTRUMENT DATASHEET FOR ELECTRONIC TRANSMITTERS (FLOW) | Start | 2025-03-13 | 2025-03-13 | 2025-03-13 | 1 | 13-Mar-25 A | 2026-03-02 | 27-Apr-25 A | 2026-02-20 | 2026-03-02
A13780 | A13780 | INSTRUMENT DATASHEET FOR LOOP POWERED INDICATOR | Start | 2025-04-07 | 2025-04-07 | 2025-04-07 | 1 | 07-Apr-25 A | 2027-01-20 | 28-Apr-25 A | 2026-02-20 | 2027-01-20
A13830 | A13830 | INSTRUMENT DATASHEET FOR FLOW ELEMENT (ORIFICE PLATE) | Start | 2025-04-07 | 2025-04-07 | 2025-04-07 | 1 | 07-Apr-25 A | 2026-03-02 | 28-Apr-25 A | 2026-02-20 | 2026-03-02
A13880 | A13880 | INSTRUMENT DATASHEET FOR FLOW ELEMENT (VENTURI TUBE) | Start | 2025-03-13 | 2025-03-13 | 2025-03-13 | 1 | 13-Mar-25 A | 2026-03-02 | 27-Apr-25 A | 2026-02-20 | 2026-03-02
A14030 | A14030 | INSTRUMENT DATASHEET FOR TEMPERATURE GAUGES / THERMOWELL | Start | 2025-03-13 | 2025-03-13 | 2025-03-13 | 1 | 13-Mar-25 A | 2026-03-02 | 28-Apr-25 A | 2026-02-20 | 2026-03-02
A14080 | A14080 | INSTRUMENT DATASHEET FOR LEVEL TRANSMITTERS (GWR TYPE) | Start | 2025-03-13 | 2025-03-13 | 2025-03-13 | 1 | 13-Mar-25 A | 2026-03-02 | 27-Apr-25 A | 2026-02-20 | 2026-03-02
A14130 | A14130 | INSTRUMENT DATASHEET FOR ANALYZERS | Start | 2025-06-21 | 2025-06-21 | 2025-06-21 | 1 | 01-Jul-25 A | 2026-03-02 | 12-Jul-25 A | 2026-02-20 | 2026-03-02
A14180 | A14180 | INSTRUMENT DATASHEET FOR LEVEL GAUGES (MAGNETIC TYPE) | Start | 2025-03-13 | 2025-03-13 | 2025-03-13 | 1 | 13-Mar-25 A | 2026-03-02 | 27-Apr-25 A | 2026-02-20 | 2026-03-02
A14230 | A14230 | INSTRUMENT DATASHEET FOR FIRE & GAS DETECTORS | Start | 2025-05-26 | 2025-05-26 | 2025-05-26 | 1 | 26-May-25 A | 2026-03-19 | 05-Jul-25 A | 2026-02-20 | 2026-03-19
A14980 | A14980 | INSTRUMENT DATASHEET FOR CONTROL VALVES | Start | 2025-03-13 | 2025-03-13 | 2025-03-13 | 2 | 13-Mar-25 A | 2026-03-19 | 27-Apr-25 A | 2026-02-20 | 2026-03-19
A15080 | A15080 | INSTRUMENT DATASHEET FOR MOTOR OPERATED VALVES | Start | 2025-03-13 | 2025-03-13 | 2025-03-13 | 2 | 24-Mar-25 A | 2026-03-19 | 27-Apr-25 A | 2026-02-20 | 2026-03-19
A14430 | A14430 | INSTRUMENT DATASHEET FOR ESD VALVES | Start | 2025-03-13 | 2025-03-13 | 2025-03-13 | 1 | 13-Mar-25 A | 2026-03-02 | 27-Apr-25 A | 2026-02-20 | 2026-03-02
A14480 | A14480 | INSTRUMENT DATASHEET FOR ROTAMETER | Start | 2025-03-13 | 2025-03-13 | 2025-03-13 | 1 | 13-Mar-25 A | 2026-03-02 | 27-Apr-25 A | 2026-02-20 | 2026-03-02
A14530 | A14530 | SCOPE OF WORK FOR THE ICSS SYSTEM | Start | 2025-06-21 | 2025-06-21 | 2025-06-21 | 6 | 01-Jul-25 A | 2026-03-19 | 12-Jul-25 A | 2026-02-20 | 2026-03-19
A14580 | A14580 | MATERIAL REQUISITION FOR ELECTRONIC TRANSMITTERS | Start | 2025-03-25 | 2025-03-25 | 2025-03-25 | 2 | 25-Mar-25 A | 2026-03-19 | 28-Apr-25 A | 2026-02-20 | 2026-03-19
A14630 | A14630 | MATERIAL REQUISITION FOR FLOW ELEMENT (ORIFICE PLATE) | Start | 2025-03-14 | 2025-03-14 | 2025-03-14 | 2 | 14-Mar-25 A | 2026-06-04 | 29-Apr-25 A | 2026-02-20 | 2026-06-04
A14680 | A14680 | MATERIAL REQUISITION FOR FLOW ELEMENT (VENTURI TUBE) | Start | 2025-03-13 | 2025-03-13 | 2025-03-13 | 2 | 13-Mar-25 A | 2026-03-02 | 30-Apr-25 A | 2026-02-20 | 2026-03-02
A14780 | A14780 | MATERIAL REQUISITION FOR TEMPERATURE GAUGES / PRESSURE GAUGES | Start | 2025-03-25 | 2025-03-25 | 2025-03-25 | 2 | 25-Mar-25 A | 2026-03-19 | 30-Apr-25 A | 2026-02-20 | 2026-03-19
A14830 | A14830 | MATERIAL REQUISITION FOR ANALYZERS | Start | 2025-06-21 | 2025-06-21 | 2025-06-21 | 2 | 01-Jul-25 A | 2026-03-17 | 15-Jul-25 A | 2026-02-20 | 2026-03-17
A14880 | A14880 | MATERIAL REQUISITION FOR LEVEL TRANSMITTERS (GWR TYPE) | Start | 2025-03-26 | 2025-03-26 | 2025-03-26 | 2 | 26-Mar-25 A | 2026-03-19 | 28-Apr-25 A | 2026-02-20 | 2026-03-19
A14930 | A14930 | MATERIAL REQUISITION FOR LEVEL GAUGES (MAGNETIC TYPE) | Start | 2025-03-25 | 2025-03-25 | 2025-03-25 | 2 | 25-Mar-25 A | 2026-03-02 | 23-Apr-25 A | 2026-02-20 | 2026-03-02
A15130 | A15130 | MATERIAL REQUISITION FOR ESD VALVES | Start | 2025-03-24 | 2025-03-24 | 2025-03-24 | 2 | 24-Mar-25 A | 2026-03-02 | 30-Apr-25 A | 2026-02-20 | 2026-03-02
A15180 | A15180 | MATERIAL REQUISITION FOR ROTAMETER | Start | 2025-03-25 | 2025-03-25 | 2025-03-25 | 1 | 25-Mar-25 A | 2026-03-19 | 01-May-25 A | 2026-02-20 | 2026-03-19
A15230 | A15230 | MATERIAL REQUISITION FOR INSTRUMENT CABLES | Start | 2025-05-27 | 2025-05-27 | 2025-05-27 | 2 | 27-May-25 A | 2026-03-19 | 05-Jul-25 A | 2026-02-20 | 2026-03-19
A47690 | A47690 | MATERIAL REQUISITION FOR JUNCTION BOXES | Start | 2025-05-27 | 2025-05-27 | 2025-05-27 | 2 | 27-May-25 A | 2026-03-05 | 05-Jul-25 A | 2026-02-20 | 2026-03-05
A47740 | A47740 | MATERIAL REQUISITION FOR ICSS SYSTEM | Start | 2024-12-31 | 2024-12-31 | 2024-12-31 | 2 | 31-Dec-24 A | 2026-03-02 | 23-Jan-25 A | 2026-02-20 | 2026-03-02
A47780 | A47780 | MATERIAL REQUISITION FOR FIRE DETECTION SYSTEM & LFCP | Start | 2025-06-09 | 2025-06-09 | 2025-06-09 | 2 | 09-Jun-25 A | 2026-03-19 | 05-Jul-25 A | 2026-02-20 | 2026-03-19
A15430 | A15430 | OVERALL CONTROL SYSTEM ARCHITECTURE DRAWING | Start | 2025-06-09 | 2025-06-09 | 2025-06-09 | 6 | 09-Jun-25 A | 2026-11-23 | 05-Jul-25 A | 2026-02-20 | 2026-11-23
A15480 | A15480 | INSTRUMENT INDEX | Start | 2025-05-25 | 2025-05-25 | 2025-05-25 | 6 | 10-Jun-25 A | 2026-11-23 | 05-Jul-25 A | 2026-02-20 | 2026-11-23
A15530 | A15530 | INSTRUMENT & F&G I/O LIST | Start | 2025-05-26 | 2025-05-26 | 2025-05-26 | 6 | 26-May-25 A | 2026-11-23 | 05-Jul-25 A | 2026-02-20 | 2026-11-23
A15580 | A15580 | CABLE BLOCK DIAGRAM | Start | 2025-05-08 | 2025-05-08 | 2025-05-08 | 17 | 08-May-25 A | 2026-11-23 | 06-Aug-25 A | 2026-02-20 | 2026-11-23
A15630 | A15630 | PROCESS & PNEUMATIC HOOKUP DRAWINGS | Start | 2025-12-15 | 2026-01-14 | 2025-12-20 | 6 | 2026-02-20 | 2026-11-23 | 2026-02-27 | 2026-02-27 | 2026-11-30 | 196
A15680 | A15680 | JUNCTION BOX SCHEDULE | Start | 2025-05-26 | 2025-05-26 | 2025-05-26 | 6 | 26-May-25 A | 2026-11-26 | 07-Jul-25 A | 2026-02-20 | 2026-11-26
A47940 | A47940 | INSTRUMENT CABLE SCHEDULE | Start | 2025-05-26 | 2025-05-26 | 2025-05-26 | 6 | 27-Jun-25 A | 2026-11-26 | 05-Jul-25 A | 2026-02-20 | 2026-11-26
A47990 | A47990 | INSTRUMENT & JB WIRING DIAGRAM | Start | 2025-12-22 | 2026-01-21 | 2025-12-20 | 6 | 20-Dec-25 A | 2026-12-18 | 12-Jan-26 A | 2026-02-20 | 2026-12-18
A48040 | A48040 | SIS BUILDING EQUIPMENT LAYOUT | Start | 2025-04-08 | 2025-04-08 | 2025-04-08 | 6 | 08-Apr-25 A | 2026-03-14 | 29-Apr-25 A | 2026-02-20 | 2026-03-14
A48090 | A48090 | INSTRUMENT LOCATION LAYOUT | Start | 2025-12-29 | 2026-01-28 | 2025-12-20 | 6 | 2026-04-03 | 2026-11-19 | 2026-04-10 | 2026-04-10 | 2026-11-26 | 164
A15930 | A15930 | INSTRUMENT CABLE & TRENCH ROUTING LAYOUT | Start | 2026-01-05 | 2026-02-04 | 2025-12-20 | 6 | 20-Dec-25 A | 2026-12-18 | 01-Jan-26 A | 2026-02-20 | 2026-12-18
A15980 | A15980 | MCT INSTALLATION DRAWING | Start | 2026-01-12 | 2026-02-11 | 2025-10-28 | 6 | 10-Nov-25 A | 2026-12-22 | 21-Nov-25 A | 2026-02-20 | 2026-12-22
A48130 | A48130 | INSTRUMENTATION & CONTROL MATERIAL TAKE OFF | Start | 2026-01-19 | 2026-02-18 | 2025-12-20 | 6 | 19-Dec-25 A | 2026-04-07 | 26-Dec-25 A | 2026-02-20 | 2026-04-07
A16080 | A16080 | INSTRUMENT LOOP DIAGRAM | Start | 2026-01-26 | 2026-02-25 | 2025-12-20 | 6 | 2026-03-09 | 2026-11-04 | 2026-03-16 | 2026-03-16 | 2026-11-11 | 172
A16130 | A16130 | TECHNICAL BID EVALUATION FOR ELECTRONIC TRANSMITTERS | Start | 2026-02-02 | 2026-03-04 | 2025-12-20 | 3 | 19-Dec-25 A | 2027-01-06 | 24-Dec-25 A | 2026-02-20 | 2027-01-06
A16180 | A16180 | TECHNICAL BID EVALUATION FOR FLOW ELEMENT (ORIFICE PLATE) | Start | 2025-09-02 | 2025-09-02 | 2025-09-02 | 8 | 01-Sep-25 A | 2026-06-04 | 23-Sep-25 A | 2026-02-20 | 2026-06-04
A16230 | A16230 | TECHNICAL BID EVALUATION FOR FLOW ELEMENT (VENTURI TUBE) | Start | 2025-09-29 | 2025-09-29 | 2025-09-29 | 8 | 01-Sep-25 A | 2026-04-30 | 10-Sep-25 A | 2026-02-20 | 2026-04-30
A16280 | A16280 | TECHNICAL BID EVALUATION FOR TEMPERATURE ELEMENT / THERMOWELL | Start | 2026-02-23 | 2026-03-25 | 2025-12-20 | 6 | 19-Dec-25 A | 2026-12-22 | 26-Dec-25 A | 2026-02-20 | 2026-12-22
A48180 | A48180 | TECHNICAL BID EVALUATION FOR TEMPERATURE GAUGES / PRESSURE GAUGES | Start | 2026-03-02 | 2026-04-01 | 2025-12-25 | 6 | 19-Dec-25 A | 2026-04-30 | 26-Dec-25 A | 2026-02-20 | 2026-04-30
A16380 | A16380 | TECHNICAL BID EVALUATION FOR ANALYZERS | Start | 2025-06-21 | 2025-06-21 | 2025-06-21 | 8 | 01-May-25 A | 2026-11-28 | 25-May-25 A | 2026-02-20 | 2026-11-28
A16430 | A16430 | TECHNICAL BID EVALUATION FOR LEVEL GAUGES (MAGNETIC TYPE) | Start | 2025-11-01 | 2025-12-01 | 2025-11-22 | 3 | 07-Aug-25 A | 2026-03-25 | 20-Aug-25 A | 2026-02-20 | 2026-03-25
A16480 | A16480 | TECHNICAL BID EVALUATION FOR CONTROL VALVES | Start | 2025-08-23 | 2025-08-23 | 2025-08-23 | 8 | 23-Aug-25 A | 2026-03-25 | 18-Sep-25 A | 2026-02-20 | 2026-03-25
A16530 | A16530 | TECHNICAL BID EVALUATION FOR FIRE & GAS DETECTORS | Start | 2025-11-13 | 2025-12-13 | 2025-12-20 | 14 | 01-Dec-25 A | 2026-04-20 | 13-Feb-26 A | 2026-02-20 | 2026-04-20
A16580 | A16580 | TECHNICAL BID EVALUATION FOR LEVEL TRANSMITTERS (GWR TYPE) | Start | 2025-08-23 | 2025-08-23 | 2025-08-23 | 6 | 23-Aug-25 A | 2027-01-20 | 18-Sep-25 A | 2026-02-20 | 2027-01-20
A48230 | A48230 | TECHNICAL BID EVALUATION FOR MOTOR OPERATED VALVES | Start | 2025-08-01 | 2025-08-01 | 2025-08-01 | 11 | 16-May-25 A | 2026-05-11 | 22-Aug-25 A | 2026-02-20 | 2026-05-11
A16680 | A16680 | TECHNICAL BID EVALUATION FOR ESD VALVES | Start | 2025-09-10 | 2025-09-10 | 2025-09-10 | 6 | 01-Oct-25 A | 2026-12-28 | 07-Oct-25 A | 2026-02-20 | 2026-12-28
A16730 | A16730 | TECHNICAL BID EVALUATION FOR ROTAMETER | Start | 2025-11-14 | 2025-12-14 | 2025-11-22 | 6 | 30-Nov-25 A | 2026-12-22 | 08-Dec-25 A | 2026-02-20 | 2026-12-22
A57510 | A57510 | TECHNICAL BID EVALUATION FOR INSTRUMENT CABLES | Start | 2025-11-21 | 2025-12-21 | 2025-12-20 | 6 | 30-Jul-25 A | 2026-03-19 | 31-Jul-25 A | 2026-02-20 | 2026-03-19
A16830 | A16830 | TECHNICAL BID EVALUATION FOR JUNCTION BOXES | Start | 2025-11-28 | 2025-12-28 | 2025-11-22 | 5 | 28-Nov-25 A | 2026-03-05 | 12-Dec-25 A | 2026-02-20 | 2026-03-05
A16880 | A16880 | TECHNICAL BID EVALUATION FOR ICSS SYSTEM | Start | 2025-05-26 | 2025-05-26 | 2025-05-26 | 11 | 26-May-25 A | 2026-03-18 | 28-May-25 A | 2026-02-20 | 2026-03-18
A48260 | A48260 | TECHNICAL BID EVALUATION FOR FIRE DETECTION SYSTEM & LFCP | Start | 2025-09-18 | 2025-09-18 | 2025-09-18 | 6 | 01-Oct-25 A | 2026-03-19 | 09-Oct-25 A | 2026-02-20 | 2026-03-19
A50810 | A50810 | DATASHEET FOR FIBER OPTIC CABLE | Start | 2025-01-30 | 2025-01-30 | 2025-01-30 | 6 | 30-Jan-25 A | 2026-03-19 | 20-Feb-25 A | 2026-02-20 | 2026-03-19
A50910 | A50910 | DATASHEET FOR PAGA | Start | 2025-01-10 | 2025-01-10 | 2025-01-10 | 6 | 10-Jan-25 A | 2026-03-19 | 20-Mar-25 A | 2026-02-20 | 2026-03-19
A50960 | A50960 | DATASHEET FOR ACCESS CONTROL SYSTEM | Start | 2025-01-15 | 2025-01-15 | 2025-01-15 | 6 | 15-Jan-25 A | 2026-03-19 | 27-Apr-25 A | 2026-02-20 | 2026-03-19
A51010 | A51010 | DATASHEET FOR DIGITAL NETWORK AND TELEPHONE SYSTEM | Start | 2025-01-15 | 2025-01-15 | 2025-01-15 | 6 | 15-Jan-25 A | 2026-03-19 | 27-Apr-25 A | 2026-02-20 | 2026-03-19
A51060 | A51060 | BLOCK DIAGRAM FOR PROCESS CCTV | Start | 2024-12-30 | 2024-12-30 | 2024-12-30 | 6 | 30-Dec-24 A | 2026-03-19 | 20-Jan-25 A | 2026-02-20 | 2026-03-19
A51110 | A51110 | BLOCK DIAGRAM FOR PAGA | Start | 2024-12-30 | 2024-12-30 | 2024-12-30 | 6 | 30-Dec-24 A | 2026-03-19 | 20-Jan-25 A | 2026-02-20 | 2026-03-19
A51210 | A51210 | BLOCK DIAGRAM FOR ACCESS CONTROL SYSTEM | Start | 2024-12-30 | 2024-12-30 | 2024-12-30 | 6 | 30-Dec-24 A | 2026-03-19 | 20-Jan-25 A | 2026-02-20 | 2026-03-19
A51260 | A51260 | OVERALL TELECOM SYSTEM BLOCK DIAGRAM | Start | 2025-01-25 | 2025-01-25 | 2025-01-25 | 6 | 25-Jan-25 A | 2027-01-18 | 27-Apr-25 A | 2026-02-20 | 2027-01-18
A51310 | A51310 | WIRING DIAGRAM FOR PROCESS CCTV | Start | 2025-01-08 | 2025-01-08 | 2025-01-08 | 6 | 08-Jan-25 A | 2027-01-20 | 12-Feb-25 A | 2026-02-20 | 2027-01-20
A51360 | A51360 | WIRING DIAGRAM FOR PAGA | Start | 2025-01-09 | 2025-01-09 | 2025-01-09 | 6 | 09-Jan-25 A | 2027-01-20 | 12-Feb-25 A | 2026-02-20 | 2027-01-20
A51410 | A51410 | WIRING DIAGRAM FOR DIGITAL NETWORK AND TELEPHONE SYSTEM | Start | 2025-01-16 | 2025-01-16 | 2025-01-16 | 6 | 22-Jan-25 A | 2026-11-23 | 2026-02-27 | 2026-02-27 | 2026-11-30 | 196
A51460 | A51460 | WIRING DIAGRAM FOR ACCESS CONTROL SYSTEM | Start | 2025-01-16 | 2025-01-16 | 2025-01-16 | 6 | 22-Jan-25 A | 2026-11-23 | 2026-02-27 | 2026-02-27 | 2026-11-30 | 196
A51560 | A51560 | TELECOM SYSTEM MATERIAL TAKE OFF | Start | 2025-06-27 | 2025-06-27 | 2025-06-27 | 11 | 01-May-25 A | 2026-11-23 | 08-May-25 A | 2026-02-20 | 2026-11-23
A51730 | A51730 | VOLTAGE DROP CALCULATION FOR PAGA SYSTEM | Start | 2025-11-06 | 2025-12-06 | 2025-12-20 | 6 | 2026-02-20 | 2026-11-23 | 2026-02-27 | 2026-02-27 | 2026-11-30 | 196
A23580 | A23580 | TELECOM EQUIPMENT LIST | Start | 2025-03-10 | 2025-03-10 | 2025-03-10 | 6 | 10-Mar-25 A | 2027-01-20 | 27-Apr-25 A | 2026-02-20 | 2027-01-20
A51800 | A51800 | TELECOM TIE-IN SCHEDULE | Start | 2025-03-13 | 2025-03-13 | 2025-03-13 | 11 | 13-Mar-25 A | 2027-01-20 | 27-Apr-25 A | 2026-02-20 | 2027-01-20
A51840 | A51840 | CENTRAL CONTROL ROOM EQUIPMENT LAYOUT FOR TELECOM | Start | 2025-06-21 | 2025-06-21 | 2025-06-21 | 6 | 01-Jul-25 A | 2026-12-28 | 13-Jul-25 A | 2026-02-20 | 2026-12-28
A51890 | A51890 | TELECOMMUNICATION CORE ALLOCATION DRAWING FOR FIBER OPTIC CABLE | Start | 2025-03-13 | 2025-03-13 | 2025-03-13 | 6 | 15-Apr-25 A | 2027-01-20 | 28-Apr-25 A | 2026-02-20 | 2027-01-20
A23780 | A23780 | MATERIAL REQUISITIONS FOR TELECOM SYSTEM (PAGA, CCTV, ACS, TELEPHONE & LAN SYSTEM) | Start | 2025-03-14 | 2025-03-14 | 2025-03-14 | 6 | 14-Mar-25 A | 2026-03-19 | 26-Apr-25 A | 2026-02-20 | 2026-03-19
A51920 | A51920 | MATERIAL REQUISITIONS FOR TELECOM CABLES | Start | 2025-05-01 | 2025-05-01 | 2025-05-01 | 6 | 01-May-25 A | 2026-11-23 | 22-May-25 A | 2026-02-20 | 2026-11-23
A57040 | A57040 | TECHNICAL BID EVALUATION FOR TELECOM SYSTEM (PAGA, CCTV, ACS, TELEPHONE & LAN SYSTEM) | Start | 2025-11-10 | 2025-12-10 | 2025-10-31 | 3 | 21-Nov-25 A | 2026-05-13 | 25-Nov-25 A | 2026-02-20 | 2026-05-13
A51980 | A51980 | TECHNICAL BID EVALUATION FOR TELECOM CABLES | Start | 2025-11-17 | 2025-12-17 | 2025-12-20 | 6 | 2026-02-20 | 2026-11-23 | 2026-02-27 | 2026-02-27 | 2026-11-30 | 196
A54590 | A54590 | MECHANICAL DATASHEET FOR PSA2 FEED GAS COMPRESSOR 1ST STAGE SUCTION DRUM (TAG NO. 13-VV-705) | Start | 2024-12-31 | 2024-12-31 | 2024-12-31 | 1 | 31-Dec-24 A | 2026-03-02 | 06-Feb-25 A | 2026-02-20 | 2026-03-02
A54640 | A54640 | MECHANICAL DATASHEET FOR PSA2 FEED GAS COMPRESSOR 2ND STAGE SUCTION DRUM (TAG NO. 13-VV-706) | Start | 2024-12-31 | 2024-12-31 | 2024-12-31 | 1 | 31-Dec-24 A | 2026-03-02 | 06-Feb-25 A | 2026-02-20 | 2026-03-02
A54690 | A54690 | MECHANICAL DATASHEET FOR PSA2 FEED GAS COMPRESSOR 3RD STAGE SUCTION DRUM (TAG NO. 13-VV-707) | Start | 2024-12-31 | 2024-12-31 | 2024-12-31 | 1 | 31-Dec-24 A | 2026-03-02 | 06-Feb-25 A | 2026-02-20 | 2026-03-02
A54790 | A54790 | MECHANICAL DATASHEET FOR PSA2 OFF GAS BUFFER DRUM (TAG NO. 13-VV-712) | Start | 2024-12-31 | 2024-12-31 | 2024-12-31 | 1 | 31-Dec-24 A | 2026-03-02 | 06-Feb-25 A | 2026-02-20 | 2026-03-02
A54840 | A54840 | MECHANICAL DATASHEET FOR PSA2 OFF GAS COMPRESSOR 2ND STAGE SUCTION DRUM (TAG NO. 13-VV-713) | Start | 2024-12-31 | 2024-12-31 | 2024-12-31 | 1 | 31-Dec-24 A | 2026-03-02 | 06-Feb-25 A | 2026-02-20 | 2026-03-02
A27210 | A27210 | MECHANICAL DATASHEET FOR PSA2 SLOP DRUM (TAG NO. 70-VV-1415) | Start | 2025-01-01 | 2025-01-01 | 2025-01-01 | 1 | 01-Jan-25 A | 2026-03-02 | 06-Feb-25 A | 2026-02-20 | 2026-03-02
A55010 | A55010 | MECHANICAL DATASHEET FOR PSA2 FEED GAS COMPRESSOR 3RD STAGE COOLER (TAG NO. 13-HE-703) | Start | 2025-01-20 | 2025-01-20 | 2025-01-20 | 1 | 20-Jan-25 A | 2026-03-02 | 26-Feb-25 A | 2026-02-20 | 2026-03-02
A55100 | A55100 | MECHANICAL DATASHEET FOR PSA2 OFF GAS COMPRESSOR AFTERCOOLER(TAG NO. 13-HE-709) | Start | 2025-02-04 | 2025-02-04 | 2025-02-04 | 1 | 25-Feb-25 A | 2026-03-02 | 26-Feb-25 A | 2026-02-20 | 2026-03-02
A55180 | A55180 | MECHANICAL DATASHEET FOR C4 GUARD ADSORBER REGENERATION GAS COOLER(TAG NO. 50-HE-1410) | Start | 2025-02-27 | 2025-02-27 | 2025-02-27 | 1 | 27-Feb-25 A | 2026-03-02 | 20-Mar-25 A | 2026-02-20 | 2026-03-02
A27610 | A27610 | MECHANICAL DATASHEET FOR VHP BOILER FEED WATER PREHEATER DRIPLEG | Start | 2025-06-21 | 2025-06-21 | 2025-06-21 | 1 | 01-Jul-25 A | 2026-03-02 | 12-Jul-25 A | 2026-02-20 | 2026-03-02
A27510 | A27510 | MECHANICAL DATASHEET FOR PSA2 OFF GAS COMPRESSOR DISCHARGE DRIPLEG -13-SP-7004 | Start | 2025-01-01 | 2025-01-01 | 2025-01-01 | 1 | 01-Jan-25 A | 2026-03-02 | 24-Jan-25 A | 2026-02-20 | 2026-03-02
A55360 | A55360 | MECHANICAL DATASHEET FOR TAIL GAS SILENCER | Start | 2025-06-21 | 2025-06-21 | 2025-06-21 | 1 | 01-Jul-25 A | 2026-11-30 | 12-Jul-25 A | 2026-02-20 | 2026-11-30
A45910 | A45910 | MATERIAL REQUISITON FOR PRESSURE VESSELS & INTERNALS | Start | 2025-01-17 | 2025-01-17 | 2025-01-17 | 6 | 17-Jan-25 A | 2026-03-02 | 07-Feb-25 A | 2026-02-20 | 2026-03-02
A45360 | A45360 | MATERIAL REQUISITON FOR SHELL AND TUBE HEAT EXCHANGERS | Start | 2025-02-21 | 2025-02-21 | 2025-02-21 | 6 | 21-Feb-25 A | 2026-03-02 | 14-Mar-25 A | 2026-02-20 | 2026-03-02
A45410 | A45410 | MATERIAL REQUISITON FOR COALSCER | Start | 2025-02-28 | 2025-02-28 | 2025-02-28 | 6 | 28-Feb-25 A | 2026-03-02 | 21-Mar-25 A | 2026-02-20 | 2026-03-02
A57190 | A57190 | TECHNICAL BID EVALUATION FOR PRESSURE VESSELS & INTERNALS | Start | 2025-04-17 | 2025-04-17 | 2025-04-17 | 6 | 28-Apr-25 A | 2026-03-19 | 03-May-25 A | 2026-02-20 | 2026-03-19
A45510 | A45510 | TECHNICAL BID EVALUATION FOR COALSCER | Start | 2025-12-15 | 2026-01-14 | 2025-12-20 | 3 | 24-Jan-26 A | 2026-11-09 | 25-Jan-26 A | 2026-02-20 | 2026-11-09
A45610 | A45610 | MECHANICAL DATA SHEET FOR EOT CRANE FOR FEED GAS COMPRESSOR | Start | 2025-01-27 | 2025-01-27 | 2025-01-27 | 6 | 27-Jan-25 A | 2026-03-02 | 26-Feb-25 A | 2026-02-20 | 2026-03-02
A45660 | A45660 | MECHANICAL DATA SHEET EOT CRANE FOR OFF GAS COMPRESSOR | Start | 2025-01-27 | 2025-01-27 | 2025-01-27 | 6 | 27-Jan-25 A | 2026-03-02 | 26-Feb-25 A | 2026-02-20 | 2026-03-02
A45710 | A45710 | MATERIAL REQUISITON FOR CENTRIFUGAL PUMP | Start | 2025-01-27 | 2025-01-27 | 2025-01-27 | 6 | 27-Jan-25 A | 2026-03-02 | 21-Mar-25 A | 2026-02-20 | 2026-03-02
A45810 | A45810 | TECHNICAL BID EVALUATION FOR CENTRIFUGAL PUMP | Start | 2025-06-21 | 2025-06-21 | 2025-06-21 | 3 | 10-Jun-25 A | 2026-05-26 | 12-Jun-25 A | 2026-02-20 | 2026-05-26
A52030 | A52030 | MATERIAL SELECTION DIAGRAMS (MSD) | Start | 2025-04-15 | 2025-04-15 | 2025-04-15 | 6 | 16-Apr-25 A | 2026-12-28 | 25-Jul-25 A | 2026-02-20 | 2026-12-28
A52070 | A52070 | MATERIAL SELECTION & CORROSION CONTROL REPORT | Start | 2025-04-16 | 2025-04-16 | 2025-04-16 | 6 | 15-Apr-25 A | 2026-12-22 | 07-May-25 A | 2026-02-20 | 2026-12-22
A52100 | A52100 | HVAC DESIGN BASIS | Start | 2025-03-13 | 2025-03-13 | 2025-03-13 | 6 | 13-Mar-25 A | 2027-01-20 | 26-Apr-25 A | 2026-02-20 | 2027-01-20
A52150 | A52150 | HVAC EQUIPMENT AND ACCESSORIES SPECIFICATIONS | Start | 2025-03-23 | 2025-03-23 | 2025-03-23 | 6 | 23-Mar-25 A | 2027-01-20 | 13-Apr-25 A | 2026-02-20 | 2027-01-20
A52200 | A52200 | HVAC COOLING LOAD CALCULATION AND EQUIPMENT SIZING | Start | 2025-04-20 | 2025-04-20 | 2025-04-20 | 11 | 20-Apr-25 A | 2026-03-19 | 11-May-25 A | 2026-02-20 | 2026-03-19
A52340 | A52340 | HVAC TECHNICAL DATA SHEET FOR CHEMICAL FILTER UNIT | Start | 2025-05-26 | 2025-05-26 | 2025-05-26 | 2 | 26-May-25 A | 2026-03-19 | 05-Jul-25 A | 2026-02-20 | 2026-03-19
A52390 | A52390 | HVAC TECHNICAL DATA SHEET FOR INERTIA FILTER WITH BLEED FAN | Start | 2025-05-26 | 2025-05-26 | 2025-05-26 | 2 | 26-May-25 A | 2026-03-19 | 05-Jul-25 A | 2026-02-20 | 2026-03-19
A52490 | A52490 | HVAC TECHNICAL DATA SHEET FOR ELECTRIC DUCT HEATER | Start | 2025-05-26 | 2025-05-26 | 2025-05-26 | 2 | 26-May-25 A | 2026-03-19 | 01-Jun-25 A | 2026-02-20 | 2026-03-19
A52540 | A52540 | HVAC AIRFLOW SCHEMATIC DIAGRAMS | Start | 2025-04-25 | 2025-04-25 | 2025-04-25 | 6 | 25-Apr-25 A | 2026-11-02 | 16-May-25 A | 2026-02-20 | 2026-11-02
A52640 | A52640 | HVAC EQUIPMENT AND DUCTING LAYOUTS | Start | 2025-06-27 | 2025-06-27 | 2025-06-27 | 6 | 29-Jun-25 A | 2026-11-02 | 18-Jul-25 A | 2026-02-20 | 2026-11-02
A52690 | A52690 | HVAC DUCTING SECTION LAYOUT | Start | 2025-07-25 | 2025-07-25 | 2025-07-25 | 6 | 03-Aug-25 A | 2027-01-20 | 18-Aug-25 A | 2026-02-20 | 2027-01-20
A52740 | A52740 | HVAC CHILLED WATER PIPING LAYOUTS & SECTIONS | Start | 2025-09-10 | 2025-09-10 | 2025-09-10 | 6 | 10-Jul-25 A | 2027-01-20 | 07-Oct-25 A | 2026-02-20 | 2027-01-20
A52790 | A52790 | HVAC DUCTING AND INSTRUMENTATION DIAGRAMS | Start | 2025-06-17 | 2025-06-17 | 2025-06-17 | 6 | 17-Jun-25 A | 2026-11-02 | 08-Jul-25 A | 2026-02-20 | 2026-11-02
A52840 | A52840 | HVAC CHILLED WATER PIPING AND INSTRUMENTATION DIAGRAMS | Start | 2025-06-02 | 2025-06-02 | 2025-06-02 | 6 | 02-Jun-25 A | 2026-11-02 | 05-Jul-25 A | 2026-02-20 | 2026-11-02
A52890 | A52890 | HVAC EQUIPMENT SCHEDULES | Start | 2025-11-06 | 2025-12-06 | 2025-10-25 | 6 | 09-Jun-25 A | 2026-12-22 | 12-Jul-25 A | 2026-02-20 | 2026-12-22
A52940 | A52940 | HVAC SYSTEM SEQUENCE OF OPERATION AND CONTROL PHILOSOPHY | Start | 2025-06-21 | 2025-06-21 | 2025-06-21 | 6 | 01-Jul-25 A | 2027-01-20 | 16-Jul-25 A | 2026-02-20 | 2027-01-20
A52990 | A52990 | HVAC SYSTEM CAUSE & EFFECT | Start | 2025-11-17 | 2025-12-17 | 2025-12-10 | 6 | 21-Nov-25 A | 2027-01-20 | 28-Nov-25 A | 2026-02-20 | 2027-01-20
A53040 | A53040 | HVAC EXTERNAL STATIC PRESSURE CALCULATION | Start | 2025-11-24 | 2025-12-24 | 2025-10-25 | 6 | 2026-02-20 | 2026-11-23 | 2026-02-27 | 2026-02-27 | 2026-11-30 | 196
A53090 | A53090 | HVAC CHILLED WATER PUMP HEAD CALCULATION | Start | 2025-09-16 | 2025-09-16 | 2025-09-16 | 6 | 01-Oct-25 A | 2027-01-20 | 13-Oct-25 A | 2026-02-20 | 2027-01-20
A53140 | A53140 | HVAC STANDARD INSTALLATION DETAILS | Start | 2025-04-25 | 2025-04-25 | 2025-04-25 | 6 | 25-Apr-25 A | 2027-01-20 | 16-May-25 A | 2026-02-20 | 2027-01-20
A53190 | A53190 | MATERIAL REQUISITION FOR HVAC EQUIPMENTS | Start | 2025-06-02 | 2025-06-02 | 2025-06-02 | 6 | 02-Jun-25 A | 2026-03-19 | 05-Jul-25 A | 2026-02-20 | 2026-03-19
A17180 | A17180 | GENERAL NOTES FOR CIVIL AND CONCRETE WORKS | Start | 2025-01-30 | 2025-01-30 | 2025-01-30 | 6 | 30-Jan-25 A | 2027-01-20 | 20-Feb-25 A | 2026-02-20 | 2027-01-20
A48270 | A48270 | GENERAL NOTES FOR STRUCTURAL STEEL WORKS | Start | 2025-01-16 | 2025-01-16 | 2025-01-16 | 6 | 16-Jan-25 A | 2026-11-30 | 20-Feb-25 A | 2026-02-20 | 2026-11-30
A17280 | A17280 | STANDARD DETAILS FOR STAIR AND LADDER FOUNDATION | Start | 2025-06-21 | 2025-06-21 | 2025-06-21 | 6 | 01-Jul-25 A | 2026-11-30 | 11-Jul-25 A | 2026-02-20 | 2026-11-30
A50190 | A50190 | ROAD AND PAVING LAYOUT | Start | 2025-06-21 | 2025-06-21 | 2025-06-21 | 6 | 02-Jun-25 A | 2026-07-29 | 07-Jul-25 A | 2026-02-20 | 2026-07-29
A17430 | A17430 | SITE GRADING LAYOUT | Start | 2025-08-23 | 2025-08-23 | 2025-08-23 | 6 | 03-Sep-25 A | 2027-01-20 | 15-Sep-25 A | 2026-02-20 | 2027-01-20
A17530 | A17530 | PILE LAYOUT PSA-2 FEEDGAS COMPRESSOR 13-KC-701 | Start | 2025-04-10 | 2025-04-10 | 2025-04-10 | 6 | 10-Apr-25 A | 2026-02-21 | 15-Aug-25 A | 2026-02-20 | 2026-02-21
A17580 | A17580 | PILE LAYOUT PSA-2 OFFGAS COMPRESSOR 13-KC-702 | Start | 2025-06-21 | 2025-06-21 | 2025-06-21 | 6 | 01-Jul-25 A | 2026-02-21 | 11-Jul-25 A | 2026-02-20 | 2026-02-21
A17630 | A17630 | PILE LAYOUT COMPRESSOR SHELTER & SR8001 | Start | 2025-06-21 | 2025-06-21 | 2025-06-21 | 6 | 01-Jul-25 A | 2026-02-21 | 12-Jul-25 A | 2026-02-20 | 2026-02-21
A48330 | A48330 | PILE LAYOUT PSA-2 UNIT - HYDROGEN PURIFICATION 13-XA-710 | Start | 2025-06-21 | 2025-06-21 | 2025-06-21 | 6 | 30-Jun-25 A | 2026-03-02 | 11-Jul-25 A | 2026-02-20 | 2026-03-02
A48380 | A48380 | ARCHITECTURAL DRAWING- SUBSTATION, SIS BUILDING | Start | 2025-02-05 | 2025-02-05 | 2025-02-05 | 6 | 05-Feb-25 A | 2026-03-14 | 11-Mar-25 A | 2026-02-20 | 2026-03-14
A48420 | A48420 | FOUNDATION LAYOUT, SECTION AND DETAILS- SUBSTATION, SIS BUILDING | Start | 2025-04-21 | 2025-04-21 | 2025-04-21 | 17 | 21-Apr-25 A | 2026-03-14 | 12-May-25 A | 2026-02-20 | 2026-03-14
A17880 | A17880 | STRUCTURAL CONCRETE GA, SECTION AND DETAILS- SUBSTATION, SIS BUILDING | Start | 2025-04-21 | 2025-04-21 | 2025-04-21 | 17 | 21-Apr-25 A | 2026-03-14 | 12-May-25 A | 2026-02-20 | 2026-03-14
A48470 | A48470 | DESIGN CALCULATION REPORT FOR SUBSTATION, SIS BUILDING | Start | 2025-04-20 | 2025-04-20 | 2025-04-20 | 17 | 20-Apr-25 A | 2026-03-14 | 11-May-25 A | 2026-02-20 | 2026-03-14
A48510 | A48510 | STRUCTURAL GA, SECTION AND DETAILS - PIPE RACK SR8001 | Start | 2025-08-23 | 2025-08-23 | 2025-08-23 | 17 | 02-Jun-25 A | 2026-03-02 | 20-Jun-25 A | 2026-02-20 | 2026-03-02
A48550 | A48550 | DESIGN CALCULATION REPORT FOR STRUCTURAL STEEL - PIPE RACK SR8001 | Start | 2026-01-15 | 2026-02-14 | - | 17 | 02-Jun-25 A | 2026-03-02 | 13-Jun-25 A | 2026-02-20 | 2026-03-02
A48570 | A48570 | FOUNDATION LAYOUT, SECTION AND DETAILS - PIPE RACK SR8001 | Start | 2025-06-21 | 2025-06-21 | 2025-06-21 | 6 | 25-Jun-25 A | 2026-03-02 | 12-Jul-25 A | 2026-02-20 | 2026-03-02
A18130 | A18130 | DESIGN CALCULATION REPORT FOR FOUNDATIONS - PIPE RACK SR8001 | Start | 2025-06-21 | 2025-06-21 | 2025-06-21 | 6 | 01-Jul-25 A | 2027-01-20 | 12-Jul-25 A | 2026-02-20 | 2027-01-20
A18230 | A18230 | DESIGN CALCULATION REPORT FOR STRUCTURAL STEEL - PIPE RACK 13-I-08001 | Start | 2025-08-23 | 2025-08-23 | 2025-08-23 | 11 | 07-Jul-25 A | 2026-03-02 | 18-Jul-25 A | 2026-02-20 | 2026-03-02
A48680 | A48680 | FOUNDATION LAYOUT, SECTION AND DETAILS - PIPE RACK 13-I-08001 | Start | 2025-06-21 | 2025-06-21 | 2025-06-21 | 6 | 30-Jun-25 A | 2026-03-02 | 15-Jul-25 A | 2026-02-20 | 2026-03-02
A48700 | A48700 | DESIGN CALCULATION REPORT FOR FOUNDATIONS - PIPE RACK 13-I-08001 | Start | 2025-06-21 | 2025-06-21 | 2025-06-21 | 6 | 02-Jul-25 A | 2026-03-02 | 12-Jul-25 A | 2026-02-20 | 2026-03-02
A48760 | A48760 | DESIGN CALCULATION REPORT FOR STRUCTURAL STEEL - PIPE BRIDGE SR81 | Start | 2025-06-21 | 2025-06-21 | 2025-06-21 | 6 | 03-Jul-25 A | 2026-03-02 | 20-Jul-25 A | 2026-02-20 | 2026-03-02
A18630 | A18630 | FOUNDATION DRAWING- COMPRESSOR SHELTER | Start | 2025-06-21 | 2025-06-21 | 2025-06-21 | 6 | 01-Jul-25 A | 2027-01-20 | 12-Jul-25 A | 2026-02-20 | 2027-01-20
A48950 | A48950 | DESIGN CALCULATION REPORT FOR STRUCTURAL STEEL- COMPRESSOR SHELTER | Start | 2025-08-23 | 2025-08-23 | 2025-08-23 | 17 | 01-Sep-25 A | 2026-12-07 | 13-Sep-25 A | 2026-02-20 | 2026-12-07
A48970 | A48970 | DESIGN CALCULATION REPORT FOR FOUNDATIONS- COMPRESSOR SHELTER | Start | 2025-06-21 | 2025-06-21 | 2025-06-21 | 6 | 28-Jun-25 A | 2027-01-20 | 15-Jul-25 A | 2026-02-20 | 2027-01-20
A49020 | A49020 | FOUNDATION DRAWING PSA-2 FEEDGAS COMPRESSOR 13-KC-701 | Start | 2025-04-19 | 2025-04-19 | 2025-04-19 | 11 | 19-Jul-25 A | 2026-02-21 | 22-Aug-25 A | 2026-02-20 | 2026-02-21
A49060 | A49060 | DESIGN CALCULATION REPORT PSA-2 FEEDGAS COMPRESSOR 13-KC-701 | Start | 2025-04-12 | 2025-04-12 | 2025-04-12 | 11 | 12-Apr-25 A | 2027-01-20 | 27-Jul-25 A | 2026-02-20 | 2027-01-20
A18880 | A18880 | FOUNDATION DRAWING PSA-2 OFFGAS COMPRESSOR 13-KC-702 | Start | 2025-06-21 | 2025-06-21 | 2025-06-21 | 11 | 30-Jun-25 A | 2026-02-21 | 10-Jul-25 A | 2026-02-20 | 2026-02-21
A18930 | A18930 | DESIGN CALCULATION REPORT PSA-2 OFFGAS COMPRESSOR 13-KC-702 | Start | 2025-08-23 | 2025-08-23 | 2025-08-23 | 11 | 01-Sep-25 A | 2027-01-18 | 13-Sep-25 A | 2026-02-20 | 2027-01-18
A18980 | A18980 | FOUNDATION DRAWING- LUBE OIL UNIT FOR PSA-2 FEEDGAS COMPRESSOR | Start | 2025-04-12 | 2025-04-12 | 2025-04-12 | 6 | 12-Apr-25 A | 2027-01-20 | 03-May-25 A | 2026-02-20 | 2027-01-20
A19030 | A19030 | DESIGN CALCULATION REPORT FOR FOUNDATION OF LUBE OIL UNIT FOR PSA-2 FEEDGAS COMPRESSOR | Start | 2025-04-13 | 2025-04-13 | 2025-04-13 | 6 | 13-Apr-25 A | 2027-01-20 | 03-May-25 A | 2026-02-20 | 2027-01-20
A49190 | A49190 | FOUNDATION DRAWING PSA-2 FEED GAS COMPRESSOR 2ND STAGE DISCHARGE DRUM 13-VV-707 | Start | 2025-04-20 | 2025-04-20 | 2025-04-20 | 6 | 20-Apr-25 A | 2026-05-11 | 11-May-25 A | 2026-02-20 | 2026-05-11
A49210 | A49210 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 FEED GAS COMPRESSOR 2ND STAGE DISCHARGE DRUM 13-VV-707 | Start | 2025-04-20 | 2025-04-20 | 2025-04-20 | 6 | 20-Apr-25 A | 2027-01-20 | 11-May-25 A | 2026-02-20 | 2027-01-20
A19330 | A19330 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 FEED GAS COMPRESSOR AFTERCOOLER 13-HE-704 | Start | 2025-04-28 | 2025-04-28 | 2025-04-28 | 6 | 28-Apr-25 A | 2027-01-20 | 03-May-25 A | 2026-02-20 | 2027-01-20
A19380 | A19380 | FOUNDATION DRAWING PSA-2 FEED GAS COMPRESSOR 2ND STAGE SUCTION DRUM 13-VV-706 | Start | 2025-04-16 | 2025-04-16 | 2025-04-16 | 6 | 16-Apr-25 A | 2026-05-14 | 03-May-25 A | 2026-02-20 | 2026-05-14
A49290 | A49290 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 FEED GAS COMPRESSOR 2ND STAGE SUCTION DRUM 13-VV-706 | Start | 2025-04-15 | 2025-04-15 | 2025-04-15 | 6 | 16-Apr-25 A | 2027-01-20 | 03-May-25 A | 2026-02-20 | 2027-01-20
A49310 | A49310 | FOUNDATION DRAWING PSA-2 FEED GAS COMPRESSOR INTERSTAGE COOLER 13-HE-703 | Start | 2025-04-24 | 2025-04-24 | 2025-04-24 | 6 | 24-Apr-25 A | 2026-05-03 | 15-May-25 A | 2026-02-20 | 2026-05-03
A49330 | A49330 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 FEED GAS COMPRESSOR INTERSTAGE COOLER 13-HE-703 | Start | 2025-04-24 | 2025-04-24 | 2025-04-24 | 6 | 24-Apr-25 A | 2027-01-20 | 15-May-25 A | 2026-02-20 | 2027-01-20
A19580 | A19580 | FOUNDATION DRAWING PSA-2 FEED GAS COMPRESSOR 1ST STAGE SUCTION DRUM 13-VV-705 | Start | 2025-04-24 | 2025-04-24 | 2025-04-24 | 6 | 24-Apr-25 A | 2026-05-14 | 15-May-25 A | 2026-02-20 | 2026-05-14
A19680 | A19680 | FOUNDATION DRAWING PSA-2 OFFGAS COMPRESSOR 2ND STAGE SUCTION DRUM 13-VV-713 | Start | 2025-04-15 | 2025-04-15 | 2025-04-15 | 6 | 15-Apr-25 A | 2026-05-14 | 06-May-25 A | 2026-02-20 | 2026-05-14
A19730 | A19730 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 OFFGAS COMPRESSOR 2ND STAGE SUCTION DRUM 13-VV-713 | Start | 2025-04-20 | 2025-04-20 | 2025-04-20 | 6 | 20-Apr-25 A | 2027-01-20 | 11-May-25 A | 2026-02-20 | 2027-01-20
A19830 | A19830 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 OFFGAS COMPRESSOR AFTERCOOLER 13-HE-709 | Start | 2025-04-28 | 2025-04-28 | 2025-04-28 | 6 | 28-Apr-25 A | 2027-01-20 | 19-May-25 A | 2026-02-20 | 2027-01-20
A49450 | A49450 | FOUNDATION DRAWING PSA-2 OFFGAS BUFFER DRUM 13-VV-712 | Start | 2025-04-22 | 2025-04-22 | 2025-04-22 | 6 | 22-Apr-25 A | 2026-05-14 | 13-May-25 A | 2026-02-20 | 2026-05-14
A49470 | A49470 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 OFFGAS BUFFER DRUM 13-VV-712 | Start | 2025-04-22 | 2025-04-22 | 2025-04-22 | 6 | 22-Apr-25 A | 2027-01-20 | 13-May-25 A | 2026-02-20 | 2027-01-20
A19980 | A19980 | FOUNDATION DRAWING PSA-2 OFFGAS COMPRESSOR DISCHARGE DRIPLEG 13-SP-7004 | Start | 2025-04-16 | 2025-04-16 | 2025-04-16 | 6 | 16-Apr-25 A | 2026-05-03 | 07-May-25 A | 2026-02-20 | 2026-05-03
A20030 | A20030 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 OFFGAS COMPRESSOR DISCHARGE DRIPLEG 13-SP-7004 | Start | 2025-04-16 | 2025-04-16 | 2025-04-16 | 6 | 16-Apr-25 A | 2027-01-20 | 07-May-25 A | 2026-02-20 | 2027-01-20
A20080 | A20080 | FOUNDATION DRAWING PSA-2 OFFGAS COMPRESSOR INTERSTAGE COOLER 13-HE-708 | Start | 2025-04-24 | 2025-04-24 | 2025-04-24 | 6 | 01-May-25 A | 2026-03-29 | 15-May-25 A | 2026-02-20 | 2026-03-29
A49580 | A49580 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 OFFGAS COMPRESSOR INTERSTAGE COOLER 13-HE-708 | Start | 2025-04-28 | 2025-04-28 | 2025-04-28 | 6 | 28-Apr-25 A | 2027-01-20 | 19-May-25 A | 2026-02-20 | 2027-01-20
A49600 | A49600 | FOUNDATION DRAWING PSA-2 UNIT - HYDROGEN PURIFICATION 13-XA-710 | Start | 2025-04-23 | 2025-04-23 | 2025-04-23 | 6 | 05-May-25 A | 2027-01-20 | 14-May-25 A | 2026-02-20 | 2027-01-20
A49620 | A49620 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 UNIT - HYDROGEN PURIFICATION 13-XA-710 | Start | 2025-05-26 | 2025-05-26 | 2025-05-26 | 6 | 26-May-25 A | 2027-01-20 | 07-Jul-25 A | 2026-02-20 | 2027-01-20
A20330 | A20330 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 SLOP DRUM 70-VV-1415 | Start | 2025-08-01 | 2025-08-01 | 2025-08-01 | 6 | 01-Aug-25 A | 2027-01-20 | 22-Aug-25 A | 2026-02-20 | 2027-01-20
A20380 | A20380 | SUMP PIT PLAN AND DETAILS ACCIDENTALLY OIL CONTAMINATED WATER COLLECTION 70-TD-1407 | Start | 2025-08-01 | 2025-08-01 | 2025-08-01 | 6 | 18-Aug-25 A | 2026-05-06 | 22-Aug-25 A | 2026-02-20 | 2026-05-06
A49730 | A49730 | DESIGN CALCULATION REPORT FOR ACCIDENTALLY OIL CONTAMINATED WATER COLLECTION SUMP PIT 70-TD-1407 | Start | 2025-08-23 | 2025-08-23 | 2025-08-23 | 6 | 23-Aug-25 A | 2026-05-06 | 13-Sep-25 A | 2026-02-20 | 2026-05-06
A49750 | A49750 | SUMP PIT PLAN AND DETAILS OILY WATER 70-TD-1408 | Start | 2025-08-01 | 2025-08-01 | 2025-08-01 | 6 | 01-Aug-25 A | 2026-05-06 | 22-Aug-25 A | 2026-02-20 | 2026-05-06
A49770 | A49770 | DESIGN CALCULATION REPORT FOR OILY WATER SUMP PIT 70-TD-1408 | Start | 2025-08-23 | 2025-08-23 | 2025-08-23 | 6 | 23-Aug-25 A | 2026-05-06 | 13-Sep-25 A | 2026-02-20 | 2026-05-06
A20580 | A20580 | SUMP PIT PLAN AND DETAILS SANITARY WASTE WATER 70-TD-1409 | Start | 2025-08-23 | 2025-08-23 | 2025-08-23 | 6 | 23-Aug-25 A | 2026-10-26 | 13-Sep-25 A | 2026-02-20 | 2026-10-26
A20630 | A20630 | DESIGN CALCULATION REPORT FOR SANITARY WASTE WATER SUMP PIT 70-TD-1409 | Start | 2025-08-23 | 2025-08-23 | 2025-08-23 | 6 | 23-Aug-25 A | 2026-10-26 | 13-Sep-25 A | 2026-02-20 | 2026-10-26
A20680 | A20680 | TRANSFORMER FOUNDATION DRAWING FOR BAY-A TO BAY-E | Start | 2025-11-17 | 2025-12-17 | 2025-10-25 | 6 | 2026-02-20 | 2026-11-23 | 2026-02-27 | 2026-02-27 | 2026-11-30 | 196
A49880 | A49880 | DESIGN CALCULATION REPORT FOR FOUNDATION- TRANSFORMER FOR BAY-A TO BAY-E | Start | 2025-11-24 | 2025-12-24 | 2025-10-25 | 6 | 2026-02-20 | 2026-11-23 | 2026-02-27 | 2026-02-27 | 2026-11-30 | 196
A20780 | A20780 | STRUCTRAL STEEL GA AND DETAILS FIELD SUPPORTS SF8100 | Start | 2026-01-15 | 2026-02-14 | 2025-10-25 | 6 | 20-Dec-25 A | 2026-05-28 | 12-Jan-26 A | 2026-02-20 | 2026-05-28
A20830 | A20830 | DESIGN CALCULATION REPORT FOR STRUCTURAL STEEL FIELD SUPPORTS SF8100 | Start | 2026-01-22 | 2026-02-21 | 2025-10-25 | 6 | 20-Dec-25 A | 2026-12-17 | 12-Jan-26 A | 2026-02-20 | 2026-12-17
A20880 | A20880 | FOUNDATION LAYOUT, SECTION AND DETAILS FIELD SUPPORTS SF8100 | Start | 2026-01-29 | 2026-02-28 | 2025-10-25 | 6 | 20-Dec-25 A | 2026-12-22 | 01-Jan-26 A | 2026-02-20 | 2026-12-22
A20930 | A20930 | DESIGN CALCULATION REPORT FOR FOUNDATIONS FIELD SUPPORTS SF8100 | Start | 2026-02-05 | 2026-03-07 | 2025-10-25 | 6 | 20-Dec-25 A | 2026-12-22 | 01-Jan-26 A | 2026-02-20 | 2026-12-22
A20980 | A20980 | STRUCTRAL STEEL GA AND DETAILS FIELD SUPPORTS SF8200 | Start | 2026-02-12 | 2026-03-14 | 2025-10-25 | 6 | 03-Jul-25 A | 2026-05-28 | 20-Jul-25 A | 2026-02-20 | 2026-05-28
A49960 | A49960 | DESIGN CALCULATION REPORT FOR STRUCTURAL STEEL FIELD SUPPORTS SF8200 | Start | 2026-02-19 | 2026-03-21 | 2025-10-25 | 6 | 19-Aug-25 A | 2026-04-16 | 25-Aug-25 A | 2026-02-20 | 2026-04-16
A21080 | A21080 | FOUNDATION LAYOUT, SECTION AND DETAILS FIELD SUPPORTS SF8200 | Start | 2026-02-26 | 2026-03-28 | 2025-10-25 | 6 | 19-Dec-25 A | 2026-12-22 | 26-Dec-25 A | 2026-02-20 | 2026-12-22
A50020 | A50020 | DESIGN CALCULATION REPORT FOR FOUNDATIONS FIELD SUPPORTS SF8200 | Start | 2026-03-05 | 2026-04-04 | 2025-10-25 | 6 | 19-Dec-25 A | 2026-12-22 | 26-Dec-25 A | 2026-02-20 | 2026-12-22
A21180 | A21180 | STRUCTRAL STEEL GA AND DETAILS FIELD SUPPORTS SF8300 | Start | 2026-03-12 | 2026-04-11 | 2025-10-25 | 6 | 2026-02-27 | 2026-04-23 | 2026-03-09 | 2026-03-09 | 2026-05-01 | 39
A21230 | A21230 | DESIGN CALCULATION REPORT FOR STRUCTURAL STEEL FIELD SUPPORTS SF8300 | Start | 2026-03-19 | 2026-04-18 | 2025-10-25 | 6 | 2026-02-27 | 2026-11-23 | 2026-03-09 | 2026-03-09 | 2026-11-30 | 191
A50090 | A50090 | FOUNDATION LAYOUT, SECTION AND DETAILS FIELD SUPPORTS SF8300 | Start | 2026-03-26 | 2026-04-25 | 2025-10-25 | 6 | 20-Dec-25 A | 2026-12-22 | 01-Jan-26 A | 2026-02-20 | 2026-12-22
A21330 | A21330 | DESIGN CALCULATION REPORT FOR FOUNDATIONS FIELD SUPPORTS SF8300 | Start | 2026-04-02 | 2026-05-02 | 2025-10-25 | 6 | 20-Dec-25 A | 2026-12-22 | 01-Jan-26 A | 2026-02-20 | 2026-12-22
A21380 | A21380 | FIREWATER VALVE PIT PLAN, SECTION AND DETAILS | Start | 2025-09-19 | 2025-09-19 | 2025-09-19 | 6 | 01-Oct-25 A | 2026-04-20 | 10-Oct-25 A | 2026-02-20 | 2026-04-20
A50170 | A50170 | COOLING WATER VALVE PIT PLAN, SECTION AND DETAILS | Start | 2025-09-19 | 2025-09-19 | 2025-09-19 | 6 | 01-Oct-25 A | 2026-06-28 | 10-Oct-25 A | 2026-02-20 | 2026-06-28
A50340 | A50340 | FOUNDATION DRAWING FOR EQUIPMENT 50-HE-1410 | Start | 2025-05-02 | 2025-05-02 | 2025-05-02 | 6 | 02-May-25 A | 2026-03-29 | 23-May-25 A | 2026-02-20 | 2026-03-29
A50390 | A50390 | DESIGN CALCULATION FOR FOUNDATION OF EQUIPMENT 50-HE-1410 | Start | 2025-05-02 | 2025-05-02 | 2025-05-02 | 6 | 02-May-25 A | 2027-01-20 | 23-May-25 A | 2026-02-20 | 2027-01-20
A50470 | A50470 | FOUNDATION LAYOUT AND DETAILS, FIELD SUPPORTS IN CA37 | Start | 2026-01-17 | 2026-02-16 | 2025-10-25 | 6 | 2026-02-27 | 2026-11-23 | 2026-03-09 | 2026-03-09 | 2026-11-30 | 191
A50500 | A50500 | DESIGN CALCULATION REPORT OF STRUCTURAL STEEL FIELD SUPPORTS CA37 | Start | 2026-01-24 | 2026-02-23 | 2025-10-25 | 6 | 2026-02-20 | 2026-04-16 | 2026-02-27 | 2026-02-27 | 2026-04-23 | 39
A50530 | A50530 | DESIGN CALCULATION REPORT OF FOUNDATIONS FIELD SUPPORTS CA37 | Start | 2026-01-31 | 2026-03-02 | 2025-10-25 | 6 | 2026-02-27 | 2026-11-23 | 2026-03-09 | 2026-03-09 | 2026-11-30 | 191
A22130 | A22130 | ADEQUACY CHECK OF PIPE RACK SR70 | Start | 2026-02-14 | 2026-03-16 | 2025-10-25 | 6 | 2026-02-20 | 2026-04-06 | 2026-02-27 | 2026-02-27 | 2026-04-13 | 31
A50700 | A50700 | ADEQUACY CHECK OF U&O RACK SR37 | Start | 2026-03-14 | 2026-04-13 | 2025-10-25 | 6 | 2026-03-09 | 2026-04-21 | 2026-03-16 | 2026-03-16 | 2026-04-29 | 31
A22380 | A22380 | TIE-IN MANHOLE MODIFICATION DRAWING | Start | 2026-03-21 | 2026-04-20 | 2025-10-25 | 6 | 2026-02-20 | 2026-11-23 | 2026-02-27 | 2026-02-27 | 2026-11-30 | 196
A22430 | A22430 | MTO FOR CIVIL WORKS | Start | 2026-03-28 | 2026-04-27 | 2025-10-25 | 11 | 05-May-25 A | 2026-11-23 | 16-May-25 A | 2026-02-20 | 2026-11-23
A40720 | A40720 | MTO FOR STRUCTURAL STEEL | Start | 2026-04-04 | 2026-05-04 | 2025-10-25 | 6 | 17-Feb-25 A | 2026-03-19 | 28-Feb-25 A | 2026-02-20 | 2026-03-19
A46010 | A46010 | ENGINEERING HSE PLAN | Start | 2025-01-30 | 2025-01-30 | 2025-01-30 | 6 | 30-Jan-25 A | 2026-03-02 | 20-Feb-25 A | 2026-02-20 | 2026-03-02
A46060 | A46060 | PROJECT HSE PHILOSOPHY | Start | 2024-12-31 | 2024-12-31 | 2024-12-31 | 6 | 31-Dec-24 A | 2026-03-02 | 23-Jan-25 A | 2026-02-20 | 2026-03-02
A46110 | A46110 | FIRE PROTECTION AND DETECTION PHILOSOPHY | Start | 2025-02-07 | 2025-02-07 | 2025-02-07 | 6 | 07-Feb-25 A | 2026-03-02 | 28-Feb-25 A | 2026-02-20 | 2026-03-02
A46160 | A46160 | HAZARDOUS AREA CLASSIFICATION SCHEDULE | Start | 2025-01-17 | 2025-01-17 | 2025-01-17 | 6 | 17-Jan-25 A | 2026-03-19 | 07-Feb-25 A | 2026-02-20 | 2026-03-19
A46210 | A46210 | HAZARDOUS AREA CLASSIFICATION LAYOUTS | Start | 2025-04-06 | 2025-04-06 | 2025-04-06 | 6 | 06-Apr-25 A | 2027-01-20 | 27-Apr-25 A | 2026-02-20 | 2027-01-20
A46260 | A46260 | FIRE ZONE LAYOUT | Start | 2025-04-02 | 2025-04-02 | 2025-04-02 | 6 | 02-Apr-25 A | 2027-01-20 | 23-Apr-25 A | 2026-02-20 | 2027-01-20
A46310 | A46310 | FIRE PROTECTION AND SAFETY EQUIPMENT LAYOUTS (PLANT) | Start | 2025-03-28 | 2025-03-28 | 2025-03-28 | 6 | 28-Mar-25 A | 2026-04-20 | 21-Apr-25 A | 2026-02-20 | 2026-04-20
A46360 | A46360 | FIRE PROTECTION AND SAFETY EQUIPMENT LAYOUTS (BUILDING) | Start | 2025-02-27 | 2025-02-27 | 2025-02-27 | 6 | 27-Feb-25 A | 2026-04-20 | 20-Mar-25 A | 2026-02-20 | 2026-04-20
A46410 | A46410 | ESCAPE ROUTE AND SAFETY SIGNS LAYOUTS (PLANT) | Start | 2025-04-16 | 2025-04-16 | 2025-04-16 | 6 | 16-Apr-25 A | 2026-04-20 | 07-May-25 A | 2026-02-20 | 2026-04-20
A46460 | A46460 | ESCAPE ROUTE AND SAFETY SIGNS LAYOUTS (BUILDING) | Start | 2025-02-27 | 2025-02-27 | 2025-02-27 | 6 | 27-Feb-25 A | 2026-04-20 | 20-Mar-25 A | 2026-02-20 | 2026-04-20
A46510 | A46510 | FIRE & GAS DETECTORS LAYOUTS (PLANT) | Start | 2025-04-06 | 2025-04-06 | 2025-04-06 | 6 | 06-Apr-25 A | 2026-04-20 | 27-Apr-25 A | 2026-02-20 | 2026-04-20
A46560 | A46560 | FIRE & GAS DETECTORS LAYOUTS (BUILDING) | Start | 2025-02-27 | 2025-02-27 | 2025-02-27 | 6 | 27-Feb-25 A | 2026-04-20 | 20-Mar-25 A | 2026-02-20 | 2026-04-20
A46610 | A46610 | F&G CAUSE AND EFFECTS MATRIX | Start | 2026-01-01 | 2026-01-31 | - | 6 | 2026-02-20 | 2026-11-23 | 2026-02-27 | 2026-02-27 | 2026-11-30 | 196
A46660 | A46660 | PASSIVE FIRE PROTECTION SCHEDULE | Start | 2025-02-28 | 2025-02-28 | 2025-02-28 | 6 | 28-Feb-25 A | 2027-01-20 | 21-Mar-25 A | 2026-02-20 | 2027-01-20
A46710 | A46710 | PASSIVE FIRE PROTECTION LAYOUTS | Start | 2025-04-08 | 2025-04-08 | 2025-04-08 | 6 | 08-Apr-25 A | 2027-01-20 | 29-Apr-25 A | 2026-02-20 | 2027-01-20
A46760 | A46760 | SPECIFICATION FOR FIRE PROTECTION AND SAFETY EQUIPMENT | Start | 2025-02-07 | 2025-02-07 | 2025-02-07 | 6 | 07-Feb-25 A | 2026-04-20 | 28-Feb-25 A | 2026-02-20 | 2026-04-20
A46810 | A46810 | SPECIFICATION FOR CLEAN AGENT SYSTEM | Start | 2025-02-11 | 2025-02-11 | 2025-02-11 | 6 | 11-Feb-25 A | 2026-05-05 | 04-Mar-25 A | 2026-02-20 | 2026-05-05
A46860 | A46860 | DATASHEETS FOR FIRE PROTECTION AND SAFETY EQUIPMENT | Start | 2025-04-17 | 2025-04-17 | 2025-04-17 | 6 | 17-Apr-25 A | 2026-04-20 | 08-May-25 A | 2026-02-20 | 2026-04-20
A46910 | A46910 | FIRE WATER LAYOUT | Start | 2025-04-17 | 2025-04-17 | 2025-04-17 | 6 | 17-Apr-25 A | 2027-01-20 | 08-May-25 A | 2026-02-20 | 2027-01-20
A46960 | A46960 | P&ID - FIREWATER NETWORK | Start | 2025-02-21 | 2025-02-21 | 2025-02-21 | 11 | 21-Feb-25 A | 2026-11-25 | 14-Mar-25 A | 2026-02-20 | 2026-11-25
A47010 | A47010 | P&ID - DELUGE SPRAY SYSTEM | Start | 2025-04-19 | 2025-04-19 | 2025-04-19 | 11 | 19-Apr-25 A | 2026-11-26 | 10-May-25 A | 2026-02-20 | 2026-11-26
A47060 | A47060 | P&ID - CLEAN AGENT SYSTEM | Start | 2025-02-21 | 2025-02-21 | 2025-02-21 | 11 | 21-Feb-25 A | 2026-11-26 | 14-Mar-25 A | 2026-02-20 | 2026-11-26
A9080 | A9080 | FIREWATER DEMAND REPORT | Start | 2025-01-17 | 2025-01-17 | 2025-01-17 | 6 | 17-Jan-25 A | 2026-11-30 | 11-Mar-25 A | 2026-02-20 | 2026-11-30
A47080 | A47080 | FIREWATER HYDRAULIC REPORT | Start | 2025-06-21 | 2025-06-21 | 2025-06-21 | 6 | 02-Jul-25 A | 2026-11-30 | 11-Jul-25 A | 2026-02-20 | 2026-11-30
A47130 | A47130 | FIREWATER LINE LIST | Start | 2025-02-28 | 2025-02-28 | 2025-02-28 | 6 | 28-Feb-25 A | 2026-11-30 | 21-Mar-25 A | 2026-02-20 | 2026-11-30
A47230 | A47230 | MR FOR CLEAN AGENT SYSTEM | Start | 2025-02-28 | 2025-02-28 | 2025-02-28 | 6 | 28-Feb-25 A | 2026-05-05 | 21-Mar-25 A | 2026-02-20 | 2026-05-05
A47280 | A47280 | HSE ACTION TRACKING REGISTER | Start | 2025-12-01 | 2025-12-31 | 2025-10-25 | 6 | 03-Nov-25 A | 2026-12-22 | 17-Nov-25 A | 2026-02-20 | 2026-12-22
A47330 | A47330 | HAZID ENVID OHID CLOSEOUT REPORT | Start | 2025-08-23 | 2025-08-23 | 2025-08-23 | 6 | 01-Sep-25 A | 2026-04-02 | 12-Sep-25 A | 2026-02-20 | 2026-04-02
A47380 | A47380 | ISD CLOSEOUT REPORT | Start | 2025-09-18 | 2025-09-18 | 2025-09-18 | 6 | 01-Oct-25 A | 2026-12-22 | 09-Oct-25 A | 2026-02-20 | 2026-12-22
A47430 | A47430 | HAZOP CLOSEOUT REPORT | Start | 2025-09-01 | 2025-09-01 | 2025-09-01 | 6 | 01-Aug-25 A | 2026-03-19 | 16-Aug-25 A | 2026-02-20 | 2026-03-19
A47480 | A47480 | PHSER 3 CLOSEOUT REPORT | Start | 2025-12-29 | 2026-01-28 | 2025-10-25 | 6 | 2026-03-16 | 2026-11-23 | 2026-03-24 | 2026-03-24 | 2026-11-30 | 179
A41150 | A41150 | ENERGY REVIEW CLOSEOUT REPORT | Start | 2026-01-05 | 2026-02-04 | 2025-10-25 | 11 | 2026-02-24 | 2026-11-13 | 2026-03-11 | 2026-03-11 | 2026-11-30 | 188
A13480 | A13480 | SIL/LOPA CLOSEOUT REPORT | Start | 2026-01-12 | 2026-02-11 | 2025-10-25 | 6 | 2026-02-20 | 2026-11-12 | 2026-02-27 | 2026-02-27 | 2026-11-20 | 190
A40360 | A40360 | SITE VISIT REPORT BEFORE TA | Start | 2025-01-21 | 2025-01-21 | 2025-01-21 | 6 | 09-Jan-25 A | 2026-03-27 | 16-Jan-25 A | 2026-02-20 | 2026-03-27
B1-DE-TA-PIP-0001 | B1-DE-TA-PIP-0001 | WORK PACK - PIPING -01 | Start | 2024-11-27 | 2024-11-27 | 2024-11-27 | 1 | 27-Nov-24 A | 2026-03-27 | 18-Dec-24 A | 2026-02-20 | 2026-03-27
B1-DE-TA-PIP-0002 | B1-DE-TA-PIP-0002 | WORK PACK - PIPING -02 | Start | 2024-11-27 | 2024-11-27 | 2024-11-27 | 1 | 27-Nov-24 A | 2026-03-27 | 18-Dec-24 A | 2026-02-20 | 2026-03-27
B1-DE-TA-PIP-0003 | B1-DE-TA-PIP-0003 | WORK PACK - PIPING -03 | Start | 2024-11-27 | 2024-11-27 | 2024-11-27 | 1 | 27-Nov-24 A | 2026-03-27 | 18-Dec-24 A | 2026-02-20 | 2026-03-27
B1-DE-TA-PIP-0004 | B1-DE-TA-PIP-0004 | WORK PACK - PIPING -04 | Start | 2024-11-28 | 2024-11-28 | 2024-11-28 | 1 | 27-Nov-24 A | 2026-03-27 | 18-Dec-24 A | 2026-02-20 | 2026-03-27
B1-DE-TA-PIP-0005 | B1-DE-TA-PIP-0005 | WORK PACK - PIPING -05 | Start | 2024-11-27 | 2024-11-27 | 2024-11-27 | 1 | 27-Nov-24 A | 2026-03-27 | 18-Dec-24 A | 2026-02-20 | 2026-03-27
B1-DE-TA-PIP-0006 | B1-DE-TA-PIP-0006 | WORK PACK - PIPING -06 | Start | 2024-11-27 | 2024-11-27 | 2024-11-27 | 1 | 27-Nov-24 A | 2026-03-27 | 18-Dec-24 A | 2026-02-20 | 2026-03-27
B1-DE-TA-PIP-0007 | B1-DE-TA-PIP-0007 | WORK PACK - PIPING -07 | Start | 2024-11-29 | 2024-11-29 | 2024-11-29 | 1 | 27-Nov-24 A | 2026-03-27 | 18-Dec-24 A | 2026-02-20 | 2026-03-27
B1-DE-TA-PIP-0008 | B1-DE-TA-PIP-0008 | WORK PACK - PIPING -08 | Start | 2024-11-28 | 2024-11-28 | 2024-11-28 | 1 | 27-Nov-24 A | 2026-03-27 | 18-Dec-24 A | 2026-02-20 | 2026-03-27
B1-DE-TA-PIP-0009 | B1-DE-TA-PIP-0009 | WORK PACK - PIPING -09 | Start | 2024-11-28 | 2024-11-28 | 2024-11-28 | 1 | 27-Nov-24 A | 2026-03-27 | 18-Dec-24 A | 2026-02-20 | 2026-03-27
B1-DE-TA-PIP-0010 | B1-DE-TA-PIP-0010 | WORK PACK - PIPING -10 | Start | 2024-11-28 | 2024-11-28 | 2024-11-28 | 1 | 27-Nov-24 A | 2026-03-27 | 18-Dec-24 A | 2026-02-20 | 2026-03-27
B1-DE-TA-PIP-0011 | B1-DE-TA-PIP-0011 | WORK PACK - PIPING -11 | Start | 2024-11-28 | 2024-11-28 | 2024-11-28 | 1 | 27-Nov-24 A | 2026-03-27 | 18-Dec-24 A | 2026-02-20 | 2026-03-27
B1-DE-TA-PIP-0012 | B1-DE-TA-PIP-0012 | WORK PACK - PIPING -12 | Start | 2024-11-28 | 2024-11-28 | 2024-11-28 | 1 | 27-Nov-24 A | 2026-03-27 | 18-Dec-24 A | 2026-02-20 | 2026-03-27
B1-DE-TA-PIP-0013 | B1-DE-TA-PIP-0013 | WORK PACK - PIPING -13 | Start | 2024-11-28 | 2024-11-28 | 2024-11-28 | 1 | 27-Nov-24 A | 2026-03-27 | 18-Dec-24 A | 2026-02-20 | 2026-03-27
B1-DE-TA-PIP-0014 | B1-DE-TA-PIP-0014 | WORK PACK - PIPING -14 | Start | 2024-11-28 | 2024-11-28 | 2024-11-28 | 1 | 27-Nov-24 A | 2026-03-27 | 18-Dec-24 A | 2026-02-20 | 2026-03-27
B1-DE-TA-PIP-0015 | B1-DE-TA-PIP-0015 | WORK PACK - PIPING -15 | Start | 2024-11-28 | 2024-11-28 | 2024-11-28 | 1 | 27-Nov-24 A | 2026-03-27 | 18-Dec-24 A | 2026-02-20 | 2026-03-27
B1-DE-TA-PIP-0016 | B1-DE-TA-PIP-0016 | WORK PACK - PIPING -16 | Start | 2024-11-28 | 2024-11-28 | 2024-11-28 | 1 | 27-Nov-24 A | 2026-03-27 | 18-Dec-24 A | 2026-02-20 | 2026-03-27
B1-DE-TA-PIP-0017 | B1-DE-TA-PIP-0017 | WORK PACK - PIPING -17 | Start | 2024-11-28 | 2024-11-28 | 2024-11-28 | 1 | 27-Nov-24 A | 2026-03-27 | 18-Dec-24 A | 2026-02-20 | 2026-03-27
B1-DE-TA-PIP-0018 | B1-DE-TA-PIP-0018 | WORK PACK - PIPING -18 | Start | 2024-11-28 | 2024-11-28 | 2024-11-28 | 1 | 27-Nov-24 A | 2026-03-27 | 18-Dec-24 A | 2026-02-20 | 2026-03-27
new added Doc | new added Doc | ROAD AND PAVING LAYOUT H2 EXTRACTION UNIT -GREEN FIELD | Start | 2025-07-25 | 2025-07-25 | 2025-07-25
| Borouge EU3 H2 Extraction EPC Project - MPR - Feb-2026 |  |  | 2026-02-20 |  |  | 699 | 07-Nov-24 A | 2026-02-21 | 2027-07-20 | 2027-07-20 | 2027-07-20 | 0
| COMPANY / PKG 1&2 Interfaces |  |  | 2026-02-20 |  |  | 565 | 20-Nov-24 A | 2026-02-27 | 2027-01-20 | 2027-01-20 | 2027-07-20 | 129
| Engineering |  |  | 2026-02-20 |  |  | 380 | 20-Nov-24 A | 2026-05-11 | 2026-05-06 | 2026-05-06 | 2027-07-20 | 314
| Required Inputs from COMPANY / Pkg 1&2 |  |  | 2026-02-20 |  |  | 326 | 20-Nov-24 A | 2026-05-11 | 2026-02-20 | 2026-02-20 | 2027-07-20 | 368
| A60700 | Receipt of Drawings for all UG systems |  |  |  |  | 0 |  |  | 20-Nov-24 A
| A60720 | Receipt of Native files of 3D model, STAAD model, calculations for brown field - Pkg 1&2 |  |  |  |  | 0 |  |  | 15-Jan-25 A
| A60730 | Receipt of PSCAD native files for electrical studies - Pkg 1&2 |  |  |  |  | 0 |  |  | 15-Jan-25 A
| A60750 | Receipt of FEED datasheets for all telecom systems - Pkg 1&2 |  |  |  |  | 0 |  |  | 15-Jan-25 A
| A60660 | Receipt of SPI database login |  |  |  |  | 0 |  |  | 11-Feb-25 A
| A60740 | Receipt of System architecture & cable block diagram for MCMS, compressor control |  |  |  |  | 0 |  |  | 13-Feb-25 A
| A60760 | Receipt of Piping TA MTO |  |  |  |  | 0 |  |  | 20-Feb-25 A
| A60770 | Receipt of Approved Vendor data - GAD for PSA-2 unit |  |  |  |  | 0 |  |  | 17-Mar-25 A
| A60690 | Receipt of Unit Plot Plan Native File - Pkg 1&2 |  |  |  |  | 0 |  |  | 25-Mar-25 A
| A5200 | TA Construction Dossier (IFC) - Pkg 1&2 |  |  |  |  | 0 |  |  | 04-Apr-25 A
| A60780 | Receipt of Approved vendor data for FG & OG compressor |  |  |  |  | 0 |  |  | 24-Apr-25 A
| A60710 | Receipt of Native files of 3D model building & structural design (FEED stage) - Pkg 1&2 |  |  |  |  | 0 |  |  | 20-May-25 A
| A60790 | Receipt of Design parameters within received line list - Pkg 1&2 |  |  |  |  | 0 |  |  | 15-Jun-25 A
| P&IDs Status |  |  | 2026-02-20 |  |  | 220 | 19-Jun-25 A | 2026-05-11 | 2026-02-20 | 2026-02-20 | 2027-07-20 | 368
| A60670 | Receipt of Updated P&ID's - Pkg 1&2 - Pre-HAZOP |  |  |  |  | 0 |  |  | 19-Jun-25 A
| A60680 | Receipt of Updated P&ID's Updated Line List (Tie-in list, PDS etc) - Pkg 1&2 - Pre-60% Model Review |  |  |  |  | 0 |  |  | 05-Sep-25 A
| A61030 | Latest Path of Mark-up P&ID by Pkg 3 |  |  |  |  | 0 |  |  | 12-Dec-25 A
| A61020 | Receipt of Final P&ID's - Pkg 1&2 - IFC |  |  |  |  | 0 |  |  | 2026-02-20 | 2026-02-20 | 2026-05-11 | 54
| A62490 | Receipt of Final Process Data for Piping Line list - Pkg 1&2 - IFC |  |  |  |  | 0 |  |  | 2026-02-20 | 2026-02-20 | 2027-07-20 | 356
| SP3D Database Status | [5 empty] | 237 | 25-Apr-25 A |  | 19-Nov-25 A
| A60650 | Receipt of SP3D database from COMPANY (Not correct) |  |  |  |  | 0 |  |  | 25-Apr-25 A
| A61010 | Receipt of corrected SP3D database from COMPANY |  |  |  |  | 0 |  |  | 19-Nov-25 A
| Required Inputs from Pkg 3 to Pkg 1&2 |  |  | 2026-03-19 |  |  | 318 | 04-Mar-25 A | 2026-09-25 | 2026-05-06 | 2026-05-06 | 2026-09-25 | 102
| A60990 | Selection for Option of MV motor (650% or 500% of rated current) or Starting VFD for Off Comp. |  |  |  |  | 0 |  |  | 04-Mar-25 A
| A60810 | All EPC Contractor G status input (detail refer Main Activities for P&ID) |  |  |  |  | 0 |  |  | 13-Mar-25 A
| A60860 | Cause and effect update |  |  |  |  | 0 |  |  | 13-Mar-25 A
| A60880 | Review & Confirmation on compressor GAD, Foundation plan & Anchor bolt locations |  |  |  |  | 0 |  |  | 20-Mar-25 A
| A61000 | Compressor Motor VDDR Motor datasheet - Electrical Cable list |  |  |  |  | 0 |  |  | 20-Mar-25 A
| A60920 | GF Balance of Plant maturity w.r.t. Compressor & PSA2 model integration |  |  |  |  | 0 |  |  | 27-Mar-25 A
| A60940 | Homerun cable length with its datasheet required for UCP signal IS calculation |  |  |  |  | 0 |  |  | 04-Apr-25 A
| A60930 | H2-SIS layout required + power cable details. |  |  |  |  | 0 |  |  | 16-Apr-25 A
| A60900 | List of inputs required in compressor process loop |  |  |  |  | 0 |  |  | 23-Apr-25 A
| A60910 | By-pass line sizing and routing and hot gas bypass valve details |  |  |  |  | 0 |  |  | 23-Apr-25 A
| A60960 | Follow up HAZOP/LOPA Recommendations report - 13-KC-701 - PSA2 Feed Gas Compressor - Pkg 3 related |  |  |  |  | 0 |  |  | 23-Apr-25 A
| A60980 | Safty Follow up HAZOP/LOPA Recommendations Package 1c - Pkg 3 related |  |  |  |  | 0 |  |  | 23-Apr-25 A
| A60890 | Review and Confirmation by Pkg -3 contractor as per issue 02 for EICT Cables |  |  |  |  | 0 |  |  | 15-May-25 A
| A60970 | HSE Action Tracking Register - Pkg 3 Actions |  |  |  |  | 0 |  |  | 20-May-25 A
| A60820 | All EPC Contractor H status input (detail refer Main Activities for P&ID) |  |  |  |  | 0 |  |  | 18-Jun-25 A
| A60840 | Mechanical data sheet (vendor data sheet) of vessels and exchangers |  |  |  |  | 0 |  |  | 20-Jun-25 A
| A60830 | Piping isos for main process piping and 3D model |  |  |  |  | 0 |  |  | 31-Jul-25 A
| A60870 | Instrument data sheet for level, pressure and temperature |  |  |  |  | 0 |  |  | 2026-03-19 | 2026-03-19 | 2026-09-25 | 136
| A60850 | Data sheet of control valve, shut down, PSV, check valve and flow element (vendor data sheet) |  |  |  |  | 0 |  |  | 2026-05-06 | 2026-05-06 | 2026-09-25 | 102
| A60950 | Vendor manuals package to be provided by EPC Contractor for Linde's review |  |  |  |  | 0 |  |  | 2026-05-06 | 2026-05-06 | 2026-09-25 | 102
| Procurement |  |  | 2026-02-20 |  |  | 503 | 15-Apr-25 A | 2026-02-27 | 2026-10-07 | 2026-10-07 | 2027-01-20 | 105
| A5190 | Free Issue TA Material latest delivery |  |  |  |  | 0 |  |  | 15-Apr-25 A
| A5210 | BFW Preheater - Delivery |  |  |  |  | 0 |  |  | 15-Apr-25 A
| A5170 | Key Vendor Data (LLI, Package Details and Design Data) |  |  |  |  | 0 |  |  | 2026-02-20 | 2026-02-20 | 2026-03-11 | 25
| A9950 | PSA Unit Delivery - Delivery |  |  |  |  | 0 |  |  | 2026-02-20 | 2026-02-20 | 2026-04-25 | 81
| A61070 | Approved Key Vendor Data (LLI, Package Details and Design Data) |  |  |  |  | 0 |  |  | 2026-02-20 | 2026-02-20 | 2026-03-11 | 25
| 78.D | OG Compressor - Delivery |  |  |  |  | 0 |  |  | 2026-03-01 | 2026-03-01 | 2026-06-04 | 119
| 76.D | FG Compressor - Delivery |  |  |  |  | 0 |  |  | 2026-03-03 | 2026-03-03 | 2026-03-11 | 10
| Feed Gas Compressor - Delivery |  |  | 2026-02-20 |  |  | 95 | 13-Feb-26 A | 2026-02-27 | 2026-05-25 | 2026-05-25 | 2027-01-20 | 240
| A62360 | VSD |  |  |  |  | 0 |  |  | 13-Feb-26 A
| A62350 | UCP |  |  |  |  | 0 |  |  | 2026-02-20 | 2026-02-20 | 2026-02-27 | 10
| A62300 | Feed Gas Compressor (incl. Baseplate, Gear, Gas seal module & Booster) |  |  |  |  | 0 |  |  | 2026-03-03 | 2026-03-03 | 2026-03-11 | 10
| A62330 | Capital Spares |  |  |  |  | 0 |  |  | 2026-03-09 | 2026-03-09 | 2027-01-20 | 396
| A62340 | Main Driver (Motor) for FGC |  |  |  |  | 0 |  |  | 2026-03-09 | 2026-03-09 | 2026-06-24 | 134
| A62310 | LO Console |  |  |  |  | 0 |  |  | 2026-03-16 | 2026-03-16 | 2026-08-23 | 200
| A62370 | Transformer |  |  |  |  | 0 |  |  | 2026-04-27 | 2026-04-27 | 2026-08-23 | 148
| A62320 | Anti-surge valve |  |  |  |  | 0 |  |  | 2026-05-25 | 2026-05-25 | 2026-09-27 | 156
| Off Gas Compressor: Vendor - Delivery |  |  | 2026-02-20 |  |  | 15 | 2026-02-20 | 2026-05-25 | 2026-03-07 | 2026-03-07 | 2026-08-31 | 177
| A62410 | UCP |  |  |  |  | 0 |  |  | 2026-02-20 | 2026-02-20 | 2026-05-25 | 119
| A62390 | Capital Spares |  |  |  |  | 0 |  |  | 2026-02-22 | 2026-02-22 | 2026-05-28 | 119
| A62380 | Off Gas Compressor |  |  |  |  | 0 |  |  | 2026-03-01 | 2026-03-01 | 2026-06-04 | 119
| A62420 | Lube Oil Unit |  |  |  |  | 0 |  |  | 2026-03-01 | 2026-03-01 | 2026-07-01 | 153
| A62400 | Main Driver (Motor) for OGC |  |  |  |  | 0 |  |  | 2026-03-04 | 2026-03-04 | 2026-07-04 | 153
| A62430 | Seal Gas Unit |  |  |  |  | 0 |  |  | 2026-03-07 | 2026-03-07 | 2026-08-31 | 221
| PSA Unit: Vendor - Delivery |  |  | 2026-02-20 |  |  | 384 | 03-Sep-25 A | 2026-07-10 | 2026-10-07 | 2026-10-07 | 2026-12-21 | 75
| A62440 | PSA Pressure vessels |  |  |  |  | 0 |  |  | 03-Sep-25 A
| A62460 | PLC Cabinet |  |  |  |  | 0 |  |  | 03-Sep-25 A
| A62450 | PSA Valve Skid |  |  |  |  | 0 |  |  | 2026-02-20 | 2026-02-20 | 2026-07-10 | 176
| A62470 | Adsorbent Material (PO pending) |  |  |  |  | 0 |  |  | 2026-08-21 | 2026-08-21 | 2026-10-11 | 64
| A62480 | Analyzer (PO pending) |  |  |  |  | 0 |  |  | 2026-10-07 | 2026-10-07 | 2026-12-21 | 94
| Construction & Commissioning |  |  | 2027-01-20 |  |  | 0 | 2027-01-20 | 2027-04-27 | 2027-01-20 | 2027-01-20 | 2027-04-27 | 83
| A40220 | Potable Water and Service water (Needs) |  |  |  |  | 0 |  |  | 2027-01-20 | 2027-01-20 | 2027-04-27 | 83
| A40230 | SANITARY Water system (Needs) |  |  |  |  | 0 |  |  | 2027-01-20 | 2027-01-20 | 2027-04-27 | 83
| A40240 | Chilled Water for Safety Shower |  |  |  |  | 0 |  |  | 2027-01-20 | 2027-01-20 | 2027-04-27 | 83
| A40250 | Instrument Air (Needs) for Boiler RFSU |  |  |  |  | 0 |  |  | 2027-01-20 | 2027-01-20 | 2027-04-27 | 83
| A40260 | Fire Water (Needs) |  |  |  |  | 0 |  |  | 2027-01-20 | 2027-01-20 | 2027-04-27 | 83
| A40270 | ETP (Effluent Treatment Package) System (Needs) |  |  |  |  | 0 |  |  | 2027-01-20 | 2027-01-20 | 2027-04-27 | 83
| A40280 | Demin water (Needs) |  |  |  |  | 0 |  |  | 2027-01-20 | 2027-01-20 | 2027-04-27 | 83
| A40290 | Nitrogen (Needs) |  |  |  |  | 0 |  |  | 2027-01-20 | 2027-01-20 | 2027-04-27 | 83
| Project Management |  |  | 2026-02-20 |  |  | 672 | 07-Nov-24 A | 2026-03-02 | 2027-07-20 | 2027-07-20 | 2027-07-20 | 0
| Project Management Deliverables |  |  | 2026-02-20 |  |  | 218 | 22-Mar-25 A | 2026-03-27 | 2026-03-17 | 2026-03-17 | 2027-07-20 | 351
| A1-PM-PMD-0002 | PM-002-Project Coordination Procedure |  |  |  |  | 0 |  |  | 18-Apr-25 A
| A1-PM-PMD-0020 | PM-030-Worksite HSE Plan |  | 2026-02-20 |  |  | 5 | 25-May-25 A | 2026-06-11 | 28-May-25 A | 2026-02-20 | 2026-06-11
| A1-PM-PMD-0017 | PM-017-HSE Training plan & procedure |  | 2026-02-20 |  |  | 5 | 21-Jun-25 A | 2026-06-11 | 12-Jul-25 A | 2026-02-20 | 2026-06-11
| A1-PM-PMD-0019 | PM-029-Recovery Plan |  | 2026-02-20 |  |  | 5 | 25-May-25 A | 2026-06-11 | 12-Jul-25 A | 2026-02-20 | 2026-06-11
| A1-PM-PMD-0025 | PM-039-List of Claims for Damage |  | 2026-02-20 |  |  | 5 | 25-May-25 A | 2026-06-11 | 12-Jul-25 A | 2026-02-20 | 2026-06-11
| A1-PM-PMD-0031 | PM-048-HSE Audit Procedure |  | 2026-02-20 |  |  | 5 | 21-Jun-25 A | 2026-06-11 | 12-Jul-25 A | 2026-02-20 | 2026-06-11
| A1-PM-PMD-0052 | PM-082-Interface Responsibility Philosophy |  | 2026-02-20 |  |  | 5 | 21-Jun-25 A | 2026-06-11 | 12-Jul-25 A | 2026-02-20 | 2026-06-11
| A1-PM-PMD-0064 | PM-094-Package 1 Deliverables IFC |  | 2026-03-12 |  |  | 5 | 15-May-25 A | 2026-06-26 | 12-Jul-25 A | 2026-03-12 | 2026-06-26
| A1-PM-PMD-0029 | PM-046-Procurement Status Report |  | 2026-02-20 |  |  | 5 | 25-May-25 A | 2026-06-11 | 25-Jul-25 A | 2026-02-20 | 2026-06-11
| A1-PM-PMD-0036 | PM-054-Master Document schedule and Status Report |  | 2026-02-20 |  |  | 5 | 25-May-25 A | 2026-06-11 | 25-Jul-25 A | 2026-02-20 | 2026-06-11
| A1-PM-PMD-0001 | PM-001-Job Bulletins |  | 2026-02-20 |  |  | 5 | 25-May-25 A | 2026-03-27 | 15-Aug-25 A | 2026-02-20 | 2026-03-27
| A1-PM-PMD-0003 | PM-003-Code of accounts |  | 2026-02-20 |  |  | 5 | 25-May-25 A | 2026-06-11 | 15-Aug-25 A | 2026-02-20 | 2026-06-11
| A1-PM-PMD-0011 | PM-011-Project Engineering CADD Applications & Deliverables Guideline |  | 2026-02-20 |  |  | 5 | 25-May-25 A | 2026-06-11 | 21-Aug-25 A | 2026-02-20 | 2026-06-11
| A1-PM-PMD-0012 | PM-012-PDS / Smart3D Raceways Guideline |  | 2026-02-20 |  |  | 5 | 25-May-25 A | 2026-06-11 | 23-Aug-25 A | 2026-02-20 | 2026-06-11
| A1-PM-PMD-0004 | PM-004-PDS / Smart3D 3D Modeling Guideline for End User |  | 2026-02-20 |  |  | 5 | 25-May-25 A | 2026-06-11 | 25-Aug-25 A | 2026-02-20 | 2026-06-11
| A1-PM-PMD-0021 | PM-031-Temporary Site Establishment plan |  | 2026-02-20 |  |  | 5 | 25-May-25 A | 2026-06-11 | 25-Aug-25 A | 2026-02-20 | 2026-06-11
| A1-PM-PMD-0037 | PM-057-Project Specification |  | 2026-02-20 |  |  | 5 | 25-May-25 A | 2026-06-11 | 25-Aug-25 A | 2026-02-20 | 2026-06-11
| A1-PM-PMD-0005 | PM-005-SPI (Smart Plant Instrumentation) INtoos Guideline for End User |  | 2026-02-20 |  |  | 5 | 25-May-25 A | 2026-06-11 | 26-Aug-25 A | 2026-02-20 | 2026-06-11
| A1-PM-PMD-0022 | PM-032-Tie-in & Interface Matrix |  | 2026-02-20 |  |  | 5 | 25-May-25 A | 2026-06-11 | 26-Aug-25 A | 2026-02-20 | 2026-06-11
| A1-PM-PMD-0034 | PM-052-Contract Trending procedure |  | 2026-02-20 |  |  | 5 | 25-May-25 A | 2026-06-11 | 26-Aug-25 A | 2026-02-20 | 2026-06-11
| A1-PM-PMD-0040 | PM-063-Insurance claim status report |  | 2026-02-20 |  |  | 5 | 23-Aug-25 A | 2026-06-11 | 26-Aug-25 A | 2026-02-20 | 2026-06-11
| A1-PM-PMD-0013 | PM-013-PDS / Smart3D Generated List of Drawings / Documents |  | 2026-02-20 |  |  | 5 | 25-May-25 A | 2026-06-11 | 27-Aug-25 A | 2026-02-20 | 2026-06-11
| A1-PM-PMD-0018 | PM-028-Project Organization Charts |  | 2026-02-20 |  |  | 5 | 25-May-25 A | 2026-06-11 | 27-Aug-25 A | 2026-02-20 | 2026-06-11
| A1-PM-PMD-0035 | PM-053-Contract Trend notice / Log |  | 2026-02-20 |  |  | 6 | 22-Mar-25 A | 2026-06-11 | 27-Aug-25 A | 2026-02-20 | 2026-06-11
| A1-PM-PMD-0006 | PM-006-SP PID (Smart Plant P&ID ) Guideline for End User |  | 2026-02-20 |  |  | 5 | 25-May-25 A | 2026-06-11 | 30-Aug-25 A | 2026-02-20 | 2026-06-11
| A1-PM-PMD-0023 | PM-037-Document/Drawing Index |  | 2026-02-20 |  |  | 5 | 25-May-25 A | 2026-06-11 | 30-Aug-25 A | 2026-02-20 | 2026-06-11
| A1-PM-PMD-0041 | PM-064-Claims |  | 2026-02-20 |  |  | 5 | 27-Aug-25 A | 2026-06-11 | 30-Aug-25 A | 2026-02-20 | 2026-06-11
| A1-PM-PMD-0014 | PM-014-Documentation and CADD Systems / Database Handover Schedule |  | 2026-02-20 |  |  | 5 | 25-May-25 A | 2026-06-11 | 01-Sep-25 A | 2026-02-20 | 2026-06-11
| A1-PM-PMD-0038 | PM-061-Insurance Policies |  | 2026-02-20 |  |  | 5 | 25-May-25 A | 2026-06-11 | 01-Sep-25 A | 2026-02-20 | 2026-06-11
| A1-PM-PMD-0007 | PM-007-SPEL (Smart Plant Electrical) Guideline for End Users |  | 2026-02-20 |  |  | 5 | 25-May-25 A | 2026-06-11 | 02-Sep-25 A | 2026-02-20 | 2026-06-11
| A1-PM-PMD-0024 | PM-038-Documentation List |  | 2026-02-20 |  |  | 5 | 25-May-25 A | 2026-06-11 | 04-Sep-25 A | 2026-02-20 | 2026-06-11
| A1-PM-PMD-0042 | PM-065-Requests for Variation |  | 2026-02-20 |  |  | 5 | 01-Sep-25 A | 2026-06-11 | 04-Sep-25 A | 2026-02-20 | 2026-06-11
| A1-PM-PMD-0015 | PM-015-CADD Systems As-built Database and System integrated Deliverables (PDS/IN Tools/SP PID/SPEL/ETAP/ Caesar-II / STA |  | 2026-02-20 |  |  | 5 | 25-May-25 A | 2026-06-11 | 05-Sep-25 A | 2026-02-20 | 2026-06-11
| A1-PM-PMD-0039 | PM-062-Insurance Claims |  | 2026-02-20 |  |  | 5 | 25-Aug-25 A | 2026-06-11 | 05-Sep-25 A | 2026-02-20 | 2026-06-11
| A1-PM-PMD-0016 | PM-016-Site Mobilization Plan |  | 2026-02-20 |  |  | 6 | 25-May-25 A | 2026-06-11 | 07-Sep-25 A | 2026-02-20 | 2026-06-11
| A1-PM-PMD-0008 | PM-008-PDS / Smart3D CADD Area/Model Index/ Plan |  | 2026-02-20 |  |  | 5 | 25-May-25 A | 2026-06-11 | 08-Sep-25 A | 2026-02-20 | 2026-06-11
| A1-PM-PMD-0043 | PM-073-Feed Documents |  | 2026-02-20 |  |  | 5 | 25-May-25 A | 2026-06-11 | 08-Sep-25 A | 2026-02-20 | 2026-06-11
| A1-PM-PMD-0051 | PM-081-Interface Management Plan - EPC |  | 2026-02-20 |  |  | 5 | 25-May-25 A | 2026-06-11 | 10-Sep-25 A | 2026-02-20 | 2026-06-11
| A1-PM-PMD-0009 | PM-009-CADD Project Hierarchy & Setup Guideline (PDS /Intools/ SP PID/ SPEL) |  | 2026-02-20 |  |  | 5 | 25-May-25 A | 2026-06-11 | 12-Sep-25 A | 2026-02-20 | 2026-06-11
| A1-PM-PMD-0010 | PM-010-PDS / Smart3D Physical Support Modeling Guideline for End Users |  | 2026-02-20 |  |  | 5 | 25-May-25 A | 2026-06-11 | 16-Sep-25 A | 2026-02-20 | 2026-06-11
| A1-PM-PMD-0050 | PM-080-Project IT/EDMS Requirements |  | 2026-02-20 |  |  | 5 | 25-May-25 A | 2026-06-11 | 16-Sep-25 A | 2026-02-20 | 2026-06-11
| A1-PM-PMD-0032 | PM-049-Risk Analysis |  | 2026-02-20 |  |  | 5 | 25-May-25 A | 2026-06-11 | 17-Sep-25 A | 2026-02-20 | 2026-06-11
| A1-PM-PMD-0030 | PM-047-Project Execution Plan |  |  |  |  | 0 |  |  | 12-Nov-25 A
| A1-PM-PMD-0044 | PM-074-Asset Integrated Management System (AIMS) / Project Integrity Management Plan |  | 2026-02-20 |  |  | 5 | 08-Aug-25 A | 2027-06-25 | 18-Dec-25 A | 2026-02-20 | 2027-06-25
| A1-PM-PMD-0054 | PM-084-EPC Responsibility Matrix for ICT & IT/OT |  | 2026-02-20 |  |  | 5 | 08-Aug-25 A | 2026-06-11 | 18-Dec-25 A | 2026-02-20 | 2026-06-11
| A1-PM-PMD-0053 | PM-083-EPC Responsibility Matrix for Control Systems |  | 2026-02-20 |  |  | 5 | 25-Jul-25 A | 2026-06-11 | 19-Dec-25 A | 2026-02-20 | 2026-06-11
| A1-PM-PMD-0055 | PM-085-Interface Point Registers |  | 2026-02-20 |  |  | 5 | 08-Aug-25 A | 2026-06-11 | 19-Dec-25 A | 2026-02-20 | 2026-06-11
| A1-PM-PMD-0056 | PM-086-Interface Dependency Table |  | 2026-02-20 |  |  | 5 | 14-Jul-25 A | 2026-06-11 | 19-Dec-25 A | 2026-02-20 | 2026-06-11
| A1-PM-PMD-0057 | PM-087-Master Boundary Interface Layout Drawing |  | 2026-02-20 |  |  | 5 | 20-Jun-25 A | 2026-06-11 | 19-Dec-25 A | 2026-02-20 | 2026-06-11
| A1-PM-PMD-0058 | PM-088-Process and Utilities Overall Block Flow Diagram Borouge-4 Facilities |  | 2026-02-20 |  |  | 5 | 21-Jul-25 A | 2026-06-11 | 19-Dec-25 A | 2026-02-20 | 2026-06-11
| A1-PM-PMD-0060 | PM-090-Piping External/Internal Connections Layout drawings |  | 2026-02-20 |  |  | 5 | 08-Aug-25 A | 2026-06-10 | 19-Dec-25 A | 2026-02-20 | 2026-06-10
| A1-PM-PMD-0045 | PM-075-Constructability Action Closeout Report |  | 2026-02-20 |  |  | 5 | 28-Oct-25 A | 2027-06-25 | 2026-02-20 | 2026-02-20 | 2027-06-25 | 351
| A1-PM-PMD-0059 | PM-089-Process and Utilities Block Flow Diagram Interconnecting |  | 2026-02-20 |  |  | 5 | 08-Aug-25 A | 2026-06-10 | 2026-02-20 | 2026-02-20 | 2026-06-11 | 79
| A1-PM-PMD-0061 | PM-091-MRB Index |  | 2026-02-20 |  |  | 5 | 01-Aug-25 A | 2026-06-08 | 2026-02-24 | 2026-02-24 | 2026-06-10 | 77
| A1-PM-PMD-0026 | PM-040-List of Commissioning Spares |  | 2026-02-20 |  |  | 5 | 30-Jul-25 A | 2027-07-07 | 2026-02-24 | 2026-02-24 | 2027-07-09 | 358
| A1-PM-PMD-0049 | PM-079-Synergies Study Report |  | 2026-02-20 |  |  | 5 | 08-Sep-25 A | 2026-06-11 | 2026-02-24 | 2026-02-24 | 2026-06-16 | 80
| A1-PM-PMD-0027 | PM-041-List of startup spares |  | 2026-02-20 |  |  | 5 | 25-Aug-25 A | 2027-07-07 | 2026-02-26 | 2026-02-26 | 2027-07-13 | 358
| A1-PM-PMD-0046 | PM-076-Project Training Requirements and Training Plan |  | 2026-02-20 |  |  | 5 | 2026-02-20 | 2027-06-28 | 2026-02-27 | 2026-02-27 | 2027-07-02 | 351
| A1-PM-PMD-0062 | PM-092-Material Record Book (MRB) |  | 2026-03-03 |  |  | 5 | 01-Aug-25 A | 2026-06-18 | 2026-03-05 | 2026-03-05 | 2026-06-19 | 77
| A1-PM-PMD-0028 | PM-045-Project Close out Report |  | 2026-02-27 |  |  | 5 | 2026-02-27 | 2027-07-14 | 2026-03-05 | 2026-03-05 | 2027-07-20 | 358
| A1-PM-PMD-0047 | PM-077-Operating Procedure/Guidelines |  | 2026-02-27 |  |  | 5 | 2026-02-27 | 2027-07-05 | 2026-03-06 | 2026-03-06 | 2027-07-09 | 351
| A1-PM-PMD-0048 | PM-078-Guidelines for Acceptance of Work |  | 2026-03-06 |  |  | 5 | 2026-03-06 | 2027-07-12 | 2026-03-13 | 2026-03-13 | 2027-07-16 | 351
| A1-PM-PMD-0063 | PM-093-QA/QC Dossiers |  | 2026-03-12 |  |  | 5 | 01-Aug-25 A | 2026-06-26 | 2026-03-16 | 2026-03-16 | 2026-06-30 | 77
| A1-PM-PMD-0033 | PM-050-Acceptance Certificate |  | 2026-03-13 |  |  | 5 | 2026-03-13 | 2027-07-17 | 2026-03-17 | 2026-03-17 | 2027-07-20 | 613
| Project Control Deliverables |  |  | 2026-02-20 |  |  | 256 | 15-Feb-25 A | 2026-03-27 | 2026-02-27 | 2026-02-27 | 2026-11-13 | 185
| A1-PM-PCD-0015 | PC-015-Annual Reports |  | 2026-02-20 |  |  | 2 | 15-May-25 A | 2026-03-27 | 23-May-25 A | 2026-02-20 | 2026-03-27
| A1-PM-PCD-0009 | PC-009-Detailed Commissioning and Pre Commissioning Schedule |  | 2026-02-20 |  |  | 2 | 15-Feb-25 A | 2026-03-27 | 17-Jun-25 A | 2026-02-20 | 2026-03-27
| A1-PM-PCD-0037 | PC-037-Schedule Risk Analysis Reports |  | 2026-02-20 |  |  | 2 | 15-Feb-25 A | 2026-03-27 | 28-Jun-25 A | 2026-02-20 | 2026-03-27
| A1-PM-PCD-0010 | PC-010-Variations |  | 2026-02-20 |  |  | 2 | 21-Jun-25 A | 2026-03-27 | 12-Jul-25 A | 2026-02-20 | 2026-03-27
| A1-PM-PCD-0011 | PC-011-Document/Drawing Index |  | 2026-02-20 |  |  | 2 | 21-Jun-25 A | 2026-03-27 | 12-Jul-25 A | 2026-02-20 | 2026-03-27
| A1-PM-PCD-0013 | PC-013-Spares Lists |  | 2026-02-20 |  |  | 2 | 21-Jun-25 A | 2026-03-27 | 12-Jul-25 A | 2026-02-20 | 2026-03-27
| A1-PM-PCD-0035 | PC-035-Back charges Status Report |  | 2026-02-20 |  |  | 2 | 21-Jun-25 A | 2026-03-27 | 12-Jul-25 A | 2026-02-20 | 2026-03-27
| A1-PM-PCD-0016 | PC-016-Monthly Reports |  | 2026-02-20 |  |  | 2 | 26-May-25 A | 2026-03-27 | 20-Jul-25 A | 2026-02-20 | 2026-03-27
| A1-PM-PCD-0017 | PC-017-Weekly Reports |  | 2026-02-20 |  |  | 2 | 25-May-25 A | 2026-03-27 | 19-Aug-25 A | 2026-02-20 | 2026-03-27
| A1-PM-PCD-0014 | PC-014-Suppliers Lists |  | 2026-02-20 |  |  | 2 | 19-Aug-25 A | 2026-03-27 | 20-Aug-25 A | 2026-02-20 | 2026-03-27
| A1-PM-PCD-0012 | PC-012-Specialty Item List |  | 2026-02-20 |  |  | 2 | 21-Jun-25 A | 2026-03-27 | 21-Aug-25 A | 2026-02-20 | 2026-03-27
| A1-PM-PCD-0018 | PC-018-Forecasts for Completion |  | 2026-02-20 |  |  | 2 | 25-May-25 A | 2026-03-27 | 21-Aug-25 A | 2026-02-20 | 2026-03-27
| A1-PM-PCD-0033 | PC-033-Bank Bonds and Guarantees |  | 2026-02-20 |  |  | 2 | 25-May-25 A | 2026-03-27 | 26-Aug-25 A | 2026-02-20 | 2026-03-27
| A1-PM-PCD-0030 | PC-030-Technical Queries |  | 2026-02-20 |  |  | 2 | 25-May-25 A | 2026-03-27 | 27-Aug-25 A | 2026-02-20 | 2026-03-27
| A1-PM-PCD-0027 | PC-027-Change Orders |  | 2026-02-20 |  |  | 2 | 25-Aug-25 A | 2026-03-27 | 29-Aug-25 A | 2026-02-20 | 2026-03-27
| A1-PM-PCD-0029 | PC-029-Site Queries |  | 2026-02-20 |  |  | 2 | 27-Aug-25 A | 2026-03-27 | 29-Aug-25 A | 2026-02-20 | 2026-03-27
| A1-PM-PCD-0025 | PC-025-Engineering Document Change Note |  | 2026-02-20 |  |  | 2 | 25-May-25 A | 2026-03-27 | 02-Sep-25 A | 2026-02-20 | 2026-03-27
| A1-PM-PCD-0024 | PC-024-P&ID change notes |  | 2026-02-20 |  |  | 2 | 06-Sep-25 A | 2026-03-27 | 07-Sep-25 A | 2026-02-20 | 2026-03-27
| A1-PM-PCD-0028 | PC-028-Field Queries |  | 2026-02-20 |  |  | 2 | 01-Sep-25 A | 2026-03-27 | 08-Sep-25 A | 2026-02-20 | 2026-03-27
| A1-PM-PCD-0026 | PC-026-Query Form |  | 2026-02-20 |  |  | 2 | 25-May-25 A | 2026-03-27 | 09-Sep-25 A | 2026-02-20 | 2026-03-27
| A1-PM-PCD-0036 | PC-036-Progress Review and Certification Procedure |  | 2026-02-20 |  |  | 2 | 15-Feb-25 A | 2026-03-27 | 10-Sep-25 A | 2026-02-20 | 2026-03-27
| A1-PM-PCD-0034 | PC-034-Cash Flow Forecast |  | 2026-02-20 |  |  | 2 | 25-May-25 A | 2026-03-27 | 14-Oct-25 A | 2026-02-20 | 2026-03-27
| A1-PM-PCD-0002 | PC-002-Distribution Matrix |  | 2026-02-20 |  |  | 2 | 04-Mar-25 A | 2026-03-27 | 03-Nov-25 A | 2026-02-20 | 2026-03-27
| A1-PM-PCD-0008 | PC-008-Detailed Control Log / Schedule |  | 2026-02-20 |  |  | 2 | 15-Feb-25 A | 2026-03-27 | 08-Nov-25 A | 2026-02-20 | 2026-03-27
| A1-PM-PCD-0005 | PC-005-Detailed Procurement schedule |  | 2026-02-20 |  |  | 2 | 15-Feb-25 A | 2026-03-27 | 14-Nov-25 A | 2026-02-20 | 2026-03-27
| A1-PM-PCD-0039 | PC-039-Equipment Deployment Plan |  | 2026-02-20 |  |  | 2 | 15-Feb-25 A | 2026-03-27 | 15-Nov-25 A | 2026-02-20 | 2026-03-27
| A1-PM-PCD-0040 | PC-040-Planning Package |  | 2026-02-20 |  |  | 2 | 15-Feb-25 A | 2026-03-27 | 15-Nov-25 A | 2026-02-20 | 2026-03-27
| A1-PM-PCD-0001 | PC-001-Procedures |  | 2026-02-20 |  |  | 2 | 15-Feb-25 A | 2026-03-27 | 17-Nov-25 A | 2026-02-20 | 2026-03-27
| A1-PM-PCD-0003 | PC-003-Time Schedule / Program |  | 2026-02-20 |  |  | 2 | 15-Feb-25 A | 2026-03-27 | 17-Nov-25 A | 2026-02-20 | 2026-03-27
| A1-PM-PCD-0004 | PC-004-Overall Project Schedule |  | 2026-02-20 |  |  | 2 | 15-Feb-25 A | 2026-03-27 | 17-Nov-25 A | 2026-02-20 | 2026-03-27
| A1-PM-PCD-0006 | PC-006-Detailed Engineering Schedule |  | 2026-02-20 |  |  | 2 | 15-Feb-25 A | 2026-03-27 | 17-Nov-25 A | 2026-02-20 | 2026-03-27
| A1-PM-PCD-0007 | PC-007-Detailed Construction Schedule |  | 2026-02-20 |  |  | 2 | 15-Feb-25 A | 2026-03-27 | 17-Nov-25 A | 2026-02-20 | 2026-03-27
| A1-PM-PCD-0019 | PC-019-Project Execution Plan |  |  |  |  | 0 |  |  | 17-Nov-25 A
| A1-PM-PCD-0020 | PC-020-FAT Procedures |  | 2026-02-20 |  |  | 2 | 15-Feb-25 A | 2026-11-06 | 17-Nov-25 A | 2026-02-20 | 2026-11-06
| A1-PM-PCD-0038 | PC-038-Manpower Mobilization Plan |  | 2026-02-20 |  |  | 2 | 15-Feb-25 A | 2026-03-27 | 19-Nov-25 A | 2026-02-20 | 2026-03-27
| A1-PM-PCD-0031 | PC-031-Invoices |  | 2026-02-20 |  |  | 2 | 25-May-25 A | 2026-03-27 | 20-Nov-25 A | 2026-02-20 | 2026-03-27
| A1-PM-PCD-0032 | PC-032-Invoices Status Report |  | 2026-02-20 |  |  | 2 | 25-May-25 A | 2026-03-27 | 20-Nov-25 A | 2026-02-20 | 2026-03-27
| A1-PM-PCD-0021 | PC-021-FAT Reports |  | 2026-02-20 |  |  | 2 | 2026-02-20 | 2026-11-06 | 2026-02-23 | 2026-02-23 | 2026-11-09 | 185
| A1-PM-PCD-0022 | PC-022-SAT Procedures |  | 2026-02-24 |  |  | 2 | 2026-02-24 | 2026-11-10 | 2026-02-25 | 2026-02-25 | 2026-11-11 | 185
| A1-PM-PCD-0023 | PC-023-SAT Reports |  | 2026-02-26 |  |  | 2 | 2026-02-26 | 2026-11-12 | 2026-02-27 | 2026-02-27 | 2026-11-13 | 185
| Project Risk Analysis Workshops |  |  | 2026-03-12 |  |  | 460 | 25-May-25 A | 2026-06-26 | 2027-03-25 | 2027-03-25 | 2027-07-09 | 77
| A1-PM-PRA-0001 | PRA01-Project Risk Analysis - Risk Identifications Workshop |  |  |  |  | 0 |  |  | 25-May-25 A
| A1-PM-PRA-0002 | PRA02-Project Risk Analysis Workshop - Update - Q01 |  |  |  |  | 0 |  |  | 21-Jun-25 A
| A1-PM-PRA-0003 | PRA03-Project Risk Analysis Workshop - Update - Q02 |  |  |  |  | 0 |  |  | 20-Aug-25 A
| A1-PM-PRA-0004 | PRA04-Project Risk Analysis Workshop - Update - Q03 |  |  |  |  | 0 |  |  | 24-Oct-25 A
| A1-PM-PRA-0005 | PRA05-Project Risk Analysis Workshop - Update - Q04 |  |  |  |  | 0 |  |  | 2026-03-12 | 2026-03-12 | 2026-06-26 | 77
| A1-PM-PRA-0006 | PRA06-Project Risk Analysis Workshop - Update - Q05 |  |  |  |  | 0 |  |  | 2026-07-16 | 2026-07-16 | 2026-10-30 | 77
| A1-PM-PRA-0007 | PRA07-Project Risk Analysis Workshop - Update - Q06 |  |  |  |  | 0 |  |  | 2026-11-19 | 2026-11-19 | 2027-03-05 | 77
| A1-PM-PRA-0008 | PRA08-Project Risk Analysis Workshop - Update - Q07 |  |  |  |  | 0 |  |  | 2027-03-25 | 2027-03-25 | 2027-07-09 | 77
| Schedule Risk Analysis Workshops |  |  | 2026-02-20 |  |  | 402 | 15-May-25 A | 2026-06-19 | 2027-04-05 | 2027-04-05 | 2027-07-20 | 77
| A1-PM-SRA-0001 | SRA01-Schedule Risk Analysis Workshop - Baseline Schedule |  |  |  |  | 0 |  |  | 15-May-25 A
| A1-PM-SRA-0002 | SRA02-Schedule Risk Analysis Workshop - UpdatedSchedule - Q01 |  |  |  |  | 0 |  |  | 10-Jul-25 A
| A1-PM-SRA-0003 | SRA03-Schedule Risk Analysis Workshop - Updated Schedule - Q02 |  |  |  |  | 0 |  |  | 17-Sep-25 A
| A1-PM-SRA-0004 | SRA04-Schedule Risk Analysis Workshop - Updated Schedule - Q03 |  |  |  |  | 0 |  |  | 2026-02-20 | 2026-02-20 | 2026-06-19 | 86
| A1-PM-SRA-0005 | SRA05-Schedule Risk Analysis Workshop - Updated Schedule - Q04 |  |  |  |  | 0 |  |  | 2026-06-25 | 2026-06-25 | 2026-10-23 | 86
| A1-PM-SRA-0006 | SRA06-Schedule Risk Analysis Workshop - Updated Schedule - Q05 |  |  |  |  | 0 |  |  | 2026-10-29 | 2026-10-29 | 2027-02-26 | 86
| A1-PM-SRA-0007 | SRA07-Schedule Risk Analysis Workshop - Updated Schedule - Q06 |  |  |  |  | 0 |  |  | 2027-03-04 | 2027-03-04 | 2027-07-02 | 86
| A1-PM-SRA-0008 | SRA08-Schedule Risk Analysis Workshop - Updated Schedule - Q07 |  |  |  |  | 0 |  |  | 2027-04-05 | 2027-04-05 | 2027-07-20 | 77
| Project Lesson Learn Workshops |  |  | 2026-03-17 |  |  | 462 | 25-May-25 A | 2026-07-07 | 2027-03-30 | 2027-03-30 | 2027-07-20 | 81
| A1-PM-LLW-0001 | PRA01-Project Lesson Learn Workshop - Lesson Learn Identifications |  |  |  |  | 0 |  |  | 25-May-25 A
| A1-PM-LLW-0002 | PRA02-Project Lesson Learn Workshop - Update - Q01 |  |  |  |  | 0 |  |  | 21-Jun-25 A
| A1-PM-LLW-0003 | PRA03-Project Lesson Learn Workshop - Update - Q02 |  |  |  |  | 0 |  |  | 15-Sep-25 A
| A1-PM-LLW-0004 | PRA04-Project Lesson Learn Workshop - Update - Q03 |  |  |  |  | 0 |  |  | 01-Oct-25 A
| A1-PM-LLW-0005 | PRA05-Project Lesson Learn Workshop - Update - Q04 |  |  |  |  | 0 |  |  | 2026-03-17 | 2026-03-17 | 2026-07-07 | 81
| A1-PM-LLW-0006 | PRA06-Project Lesson Learn Workshop - Update - Q05 |  |  |  |  | 0 |  |  | 2026-07-21 | 2026-07-21 | 2026-11-10 | 81
| A1-PM-LLW-0007 | PRA07-Project Lesson Learn Workshop - Update - Q06 |  |  |  |  | 0 |  |  | 2026-11-24 | 2026-11-24 | 2027-03-16 | 81
| A1-PM-LLW-0008 | PRA08-Project Lesson Learn Workshop - Update - Q07 |  |  |  |  | 0 |  |  | 2027-03-30 | 2027-03-30 | 2027-07-20 | 81
| Project Management Interim Milestones | [5 empty] | 160 | 07-Nov-24 A |  | 30-Oct-25 A
| A1-PM-PMM-0001 | Letter of Award (LOA) Recieved - Project Commencement Date |  |  |  |  | 0 |  |  | 07-Nov-24 A
| A1-PM-PMM-0002 | 10.A-Kick-off Meeting Completed |  |  |  |  | 0 |  |  | 06-Dec-24 A
| A1-PM-PMM-0004 | 1.A*-Issue Coordination Procedure |  |  |  |  | 0 |  |  | 30-Apr-25 A
| A1-PM-PMM-0003 | 1.A*-Issue Overall Project Execution Plan |  |  |  |  | 0 |  |  | 30-Oct-25 A
| QAQC Interim Milestones | [5 empty] | 0 | 26-May-25 A |  | 26-May-25 A
| General Project Management |  |  | 2027-01-21 |  |  | 0 | 26-May-25 A | 2027-07-20 | 26-May-25 A | 2027-01-21 | 2027-07-20 | 129
| A1-PM-QCM-0001 | 1.A*-Issue Project Quality Procedures (Final Issue). |  |  |  |  | 0 |  |  | 26-May-25 A
| HSE Interim Milestones | [5 empty] | 0 | 30-Apr-25 A |  | 30-Apr-25 A
| A1-PM-HSM-0001 | 1.A*-Issue Project HSE Procedure. |  |  |  |  | 0 |  |  | 30-Apr-25 A
| Project Control Interim Milestones | [5 empty] | 0 | 24-Mar-25 A |  | 24-Mar-25 A
| A1-PM-PCM-0002 | 2.A-Issue Progress Measurement & Reporting System |  |  |  |  | 0 |  |  | 24-Mar-25 A
| A1-PM-PCM-0003 | 2.A-Issue Cost Control Procedure |  |  |  |  | 0 |  |  | 24-Mar-25 A
| A1-PM-PCM-0004 | 2.A-Issue Planning Docs |  |  |  |  | 0 |  |  | 24-Mar-25 A
| A1-PM-PCM-0001 | 2.A-Issue Project Control Propcedures |  |  |  |  | 0 |  |  | 24-Mar-25 A
| Moblization of Key Personnel | [5 empty] | 155 | 15-Nov-24 A |  | 13-Nov-25 A
| A1-PM-KPM-0007 | Moblization of Procurement Manager (s) * |  |  |  |  | 0 |  |  | 15-Nov-24 A
| A1-PM-KPM-0010 | Moblization of Project Control Manager* |  |  |  |  | 0 |  |  | 15-Nov-24 A
| A1-PM-KPM-0002 | Moblization of Project Turnaround Manager * |  |  |  |  | 0 |  |  | 21-Nov-24 A
| A1-PM-KPM-0005 | Moblization of Lead Discipline and Supervisory Engineers * - RAD |  |  |  |  | 0 |  |  | 01-Dec-24 A
| A1-PM-KPM-0009 | Moblization of Project Traffic and Logistics Manager |  |  |  |  | 0 |  |  | 01-Dec-24 A
| A1-PM-KPM-0001 | Moblization of Project Director or Project Manager * |  |  |  |  | 0 |  |  | 18-Dec-24 A
| A1-PM-KPM-0017 | Moblization of Project HSE Manager(s) (Home Office/Construction) |  |  |  |  | 0 |  |  | 20-Dec-24 A
| A1-PM-KPM-0008 | Moblization of Project Commercial/Prime Contracts Manager |  |  |  |  | 0 |  |  | 01-Jan-25 A
| A1-PM-KPM-0006 | Moblization of Process Manager (s) * |  |  |  |  | 0 |  |  | 01-Feb-25 A
| A1-PM-KPM-0003 | Moblization of Engineering Manager * |  |  |  |  | 0 |  |  | 15-Feb-25 A
| A1-PM-KPM-0004 | Moblization of Quality Assurance and Quality Control Manager (Home Office/SITE) |  |  |  |  | 0 |  |  | 20-Feb-25 A
| A1-PM-KPM-0015 | Moblization of Project Construction Chief Field Engineer |  |  |  |  | 0 |  |  | 01-Mar-25 A
| A1-PM-KPM-0012 | Moblization of Construction Planner |  |  |  |  | 0 |  |  | 27-Mar-25 A
| A1-PM-KPM-0018 | Moblization of Lead Cost Engineer / Estimator |  |  |  |  | 0 |  |  | 01-Apr-25 A
| A1-PM-KPM-0014 | Moblization of Project Construction Director/Manager(s)* |  |  |  |  | 0 |  |  | 14-Apr-25 A
| A1-PM-KPM-0016 | Moblization of Project Construction Field Superintendent |  |  |  |  | 0 |  |  | 15-Apr-25 A
| A1-PM-KPM-0021 | Moblization of Project IT Manager |  |  |  |  | 0 |  |  | 15-May-25 A
| A1-PM-KPM-0013 | Moblization of Project Contracts/Subcontracts Manager* |  |  |  |  | 0 |  |  | 01-Jun-25 A
| A1-PM-KPM-0011 | Moblization of Lead Planner |  |  |  |  | 0 |  |  | 21-Jun-25 A
| A1-PM-KPM-0022 | Moblization of Field Engineering Manager |  |  |  |  | 0 |  |  | 22-Aug-25 A
| A1-PM-KPM-0019 | Moblization of Project Commissioning Manager* |  |  |  |  | 0 |  |  | 13-Nov-25 A
| A1-PM-KPM-0020 | Moblization of Project Training Manager* |  |  |  |  | 0 |  |  | 13-Nov-25 A
| Detailed Design and Engineering |  |  | 2026-02-20 |  |  | 412 | 02-Apr-25 A | 2026-03-27 | 2027-01-21 | 2027-01-21 | 2027-07-20 | 129
| Engineering Workshops |  |  | 2026-03-06 |  |  | 183 | 25-May-25 A | 2026-03-27 | 2026-03-06 | 2026-03-06 | 2026-03-27 | 15
| A1-PM-EWS-0001 | Engineering Workshops - 30% Model Review |  |  |  |  | 0 |  |  | 25-May-25 A
| A1-PM-EWS-0002 | Engineering Workshops - 60% Model Review |  |  |  |  | 0 |  |  | 19-Sep-25 A
| A1-PM-EWS-0003 | Engineering Workshops - 90% Model Review |  |  |  |  | 0 |  |  | 2026-03-06 | 2026-03-06 | 2026-03-27 | 15
| Engineering Interim Milestones |  |  | 2026-02-20 |  |  | 412 | 02-Apr-25 A | 2026-03-27 | 2027-01-21 | 2027-01-21 | 2027-07-20 | 129
| A1-PM-EIM-0001 | 1.A*-Issue Engineering Procedure. |  |  |  |  | 0 |  |  | 30-Apr-25 A
| A1-PM-EIM-0002 | 8.A*-As Built drawings handover to COMPANY |  |  |  |  | 0 |  |  | 2027-01-21 | 2027-01-21 | 2027-07-20 | 129
| Detail Engineering |  |  | 2026-02-20 |  |  | 247 | 02-Apr-25 A | 2026-03-27 | 2026-06-04 | 2026-06-04 | 2027-07-20 | 294
| A1-PM-EIM-0036 | 45.B-Design for Turnaround Works |  |  |  |  | 0 |  |  | 02-Apr-25 A
| A1-PM-EIM-0008 | 14.B*-Issue IFC Plot Plans, Equipment Layouts etc. complete |  |  |  |  | 0 |  |  | 06-May-25 A
| A1-PM-EIM-0019 | 25.B-Complete 30% 3D-CAD model review |  |  |  |  | 0 |  |  | 25-May-25 A
| A1-PM-EIM-0009 | 15.B-Utility Consumption Issued for U&O |  |  |  |  | 0 |  |  | 20-Jun-25 A
| A1-PM-EIM-0004 | 10.B-Issue for COMPANY approval all documents for HAZOP / SIL review |  |  |  |  | 0 |  |  | 21-Jun-25 A
| A1-PM-EIM-0025 | 31.B*-Issue 1st MTO and MRs for piping bulk materials |  |  |  |  | 0 |  |  | 21-Jun-25 A
| A1-PM-EIM-0030 | 36.B-Issue first MTO and MRs for electrical bulk materials |  |  |  |  | 0 |  |  | 21-Jun-25 A
| A1-PM-EIM-0032 | 39.B-Issue first MTO and MRs for instrument bulk materials |  |  |  |  | 0 |  |  | 21-Jun-25 A
| A1-PM-EIM-0006 | 12.B-Process design frozen |  |  |  |  | 0 |  |  | 18-Aug-25 A
| A1-PM-EIM-0018 | 24.B-Issue IFC 95% of Civil / Structural drawings etc. for all Buildings. |  |  |  |  | 0 |  |  | 01-Sep-25 A
| A1-PM-EIM-0005 | 11.B-Complete HAZOP/ SIL Review and submit Close Out Report with all actions closed. |  |  |  |  | 0 |  |  | 05-Sep-25 A
| A1-PM-EIM-0013 | 19.B*-Issue MRs for all Major Equipment & Packages for purchase. |  |  |  |  | 0 |  |  | 16-Sep-25 A
| A1-PM-EIM-0020 | 26.B*-Complete 60% 3D-CAD model review |  |  |  |  | 0 |  |  | 18-Sep-25 A
| A1-PM-EIM-0015 | 21.B*-Issue IFC all underground services drawings |  |  |  |  | 0 |  |  | 15-Nov-25 A
| A1-PM-EIM-0003 | 9.B*-Issue Utility demands, associated line sizes and electrical load data and equipment ratings final. |  |  |  |  | 0 |  |  | 2026-02-20 | 2026-02-20 | 2026-03-27 | 25
| A1-PM-EIM-0022 | 28.B*-Start issue piping isometrics IFC |  |  |  |  | 0 |  |  | 2026-02-20 | 2026-02-20 | 2026-03-27 | 25
| A1-PM-EIM-0010 | 16.B-Effluent Summary & Flare Loads Frozen for U&O |  |  |  |  | 0 |  |  | 2026-02-24 | 2026-02-24 | 2026-03-27 | 23
| A1-PM-EIM-0011 | 17.B-Steam Balance Frozen for U&O |  |  |  |  | 0 |  |  | 2026-02-24 | 2026-02-24 | 2026-03-27 | 23
| A1-PM-EIM-0026 | 32.B-Issue Intermediate MTO and MR’s for piping bulk materials |  |  |  |  | 0 |  |  | 2026-02-24 | 2026-02-24 | 2026-03-27 | 23
| A1-PM-EIM-0021 | 27.B-Complete 90% 3D-CAD model review |  |  |  |  | 0 |  |  | 2026-03-06 | 2026-03-06 | 2026-05-06 | 44
| A1-PM-EIM-0016 | 22.B*-Issue IFC all foundation & superstructure drawings for all Equipment & Packages |  |  |  |  | 0 |  |  | 2026-03-23 | 2026-03-23 | 2027-07-20 | 347
| A1-PM-EIM-0027 | 33.B-Issue final MTO and MRs for piping bulk materials |  |  |  |  | 0 |  |  | 2026-04-08 | 2026-04-08 | 2026-06-12 | 47
| A1-PM-EIM-0007 | 13.B*-Issue IFC PFDs, P&IDs, Data Sheets, Equipment Lists, Line Lists complete incorporating HAZOP comments |  |  |  |  | 0 |  |  | 2026-04-14 | 2026-04-14 | 2027-01-18 | 200
| A1-PM-EIM-0012 | 18.B-Issue IFC all Single Line Diagrams, Hazardous Area classification details for all facilities (complete). |  |  |  |  | 0 |  |  | 2026-04-14 | 2026-04-14 | 2027-01-01 | 189
| A1-PM-EIM-0028 | 34.B-Establish piping interface details and finalize procedures with COMPANY |  |  |  |  | 0 |  |  | 2026-04-21 | 2026-04-21 | 2026-10-16 | 128
| A1-PM-EIM-0033 | 41.B*-Issue IFC Electrical/Instrument layouts, interconnection diagrams etc. including all building control SYSTEMS, HVA |  |  |  |  | 0 |  |  | 2026-04-21 | 2026-04-21 | 2027-01-01 | 183
| A1-PM-EIM-0035 | 44.B-Issue Operating, Maintenance and Safety Manual. |  |  |  |  | 0 |  |  | 2026-04-21 | 2026-04-21 | 2027-01-20 | 196
| A1-PM-EIM-0014 | 20.B*-Receipt of key VENDOR data (by major equipment) |  |  |  |  | 0 |  |  | 2026-04-23 | 2026-04-23 | 2026-08-14 | 81
| A1-PM-EIM-0024 | 30.B-Complete Piping Isometrics IFC |  |  |  |  | 0 |  |  | 2026-05-01 | 2026-05-01 | 2026-05-22 | 15
| A1-PM-EIM-0029 | 35.B*-Issue IFC Electrical cable schedules, cable layouts, equipment layouts earthing layouts, lighting layouts, JB deta |  |  |  |  | 0 |  |  | 2026-05-06 | 2026-05-06 | 2026-10-05 | 108
| A1-PM-EIM-0034 | 42.B-Finalize and issue IFC all instrumentation loop diagrams. |  |  |  |  | 0 |  |  | 2026-05-06 | 2026-05-06 | 2027-01-01 | 172
| A1-PM-EIM-0017 | 23.B-Issue IFC 95% of Civil / Structural drawings for pipe supports, pipe trestles, sleepers etc. complete. |  |  |  |  | 0 |  |  | 2026-05-14 | 2026-05-14 | 2026-06-26 | 31
| A1-PM-EIM-0031 | 38.B*-Issue IFC Instrument cable schedules, cable layouts, equipment layouts, JB details, trench details etc. complete |  |  |  |  | 0 |  |  | 2026-06-03 | 2026-06-03 | 2027-01-18 | 164
| A1-PM-EIM-0023 | 29.B-Issue 50% Piping Isometrics IFC |  |  |  |  | 0 |  |  | 2026-06-04 | 2026-06-04 | 2027-01-18 | 162
| Procurement Deliverables |  |  | 2026-02-20 |  |  | 154 | 03-Mar-25 A | 2026-07-23 | 2026-02-24 | 2026-02-24 | 2026-07-27 | 109
| A1-PM-PRD-0021 | PM-058-Subcontract technical & commercial bid evaluation |  | 2026-02-20 |  |  | 5 | 03-Mar-25 A | 2026-07-23 | 28-May-25 A | 2026-02-20 | 2026-07-23
| A1-PM-PRD-0004 | PM-021-Procurement Plan |  | 2026-02-20 |  |  | 5 | 25-May-25 A | 2026-07-23 | 15-Jun-25 A | 2026-02-20 | 2026-07-23
| A1-PM-PRD-0005 | PM-022-Procurement Control Log |  | 2026-02-20 |  |  | 5 | 21-Jun-25 A | 2026-07-23 | 12-Jul-25 A | 2026-02-20 | 2026-07-23
| A1-PM-PRD-0007 | PM-024-Shipping Forecast |  | 2026-02-20 |  |  | 5 | 21-Jun-25 A | 2026-07-23 | 12-Jul-25 A | 2026-02-20 | 2026-07-23
| A1-PM-PRD-0008 | PM-025-Copy of priced and unpriced Purchase Order |  | 2026-02-20 |  |  | 5 | 21-Jun-25 A | 2026-07-23 | 12-Jul-25 A | 2026-02-20 | 2026-07-23
| A1-PM-PRD-0009 | PM-026-Vendor Schedules |  | 2026-02-20 |  |  | 5 | 21-Jun-25 A | 2026-07-23 | 12-Jul-25 A | 2026-02-20 | 2026-07-23
| A1-PM-PRD-0010 | PM-027-Shipping Progress Report |  | 2026-02-20 |  |  | 5 | 21-Jun-25 A | 2026-07-23 | 12-Jul-25 A | 2026-02-20 | 2026-07-23
| A1-PM-PRD-0011 | PM-033-Commercial Bid Analysis |  | 2026-02-20 |  |  | 5 | 21-Jun-25 A | 2026-07-23 | 12-Jul-25 A | 2026-02-20 | 2026-07-23
| A1-PM-PRD-0012 | PM-034-Subcontract Award Recommendation |  | 2026-02-20 |  |  | 5 | 21-Jun-25 A | 2026-07-23 | 12-Jul-25 A | 2026-02-20 | 2026-07-23
| A1-PM-PRD-0013 | PM-035-Vendor Prequalification's |  | 2026-02-20 |  |  | 5 | 21-Jun-25 A | 2026-07-23 | 12-Jul-25 A | 2026-02-20 | 2026-07-23
| A1-PM-PRD-0014 | PM-036-Vendor Technical Queries /Answers |  | 2026-02-20 |  |  | 5 | 21-Jun-25 A | 2026-07-23 | 12-Jul-25 A | 2026-02-20 | 2026-07-23
| A1-PM-PRD-0015 | PM-042-Subcontract Bidders List |  | 2026-02-20 |  |  | 5 | 21-Jun-25 A | 2026-07-23 | 12-Jul-25 A | 2026-02-20 | 2026-07-23
| A1-PM-PRD-0016 | PM-043-Vendors List / Bidders Lists |  | 2026-02-20 |  |  | 5 | 21-Jun-25 A | 2026-07-23 | 12-Jul-25 A | 2026-02-20 | 2026-07-23
| A1-PM-PRD-0022 | PM-059-Subcontract control log |  | 2026-02-20 |  |  | 5 | 21-Jun-25 A | 2026-07-23 | 12-Jul-25 A | 2026-02-20 | 2026-07-23
| A1-PM-PRD-0023 | PM-060-Award Recommendation |  | 2026-02-20 |  |  | 5 | 21-Jun-25 A | 2026-07-23 | 12-Jul-25 A | 2026-02-20 | 2026-07-23
| A1-PM-PRD-0024 | PM-066-Copy of Bill of Loading |  | 2026-02-20 |  |  | 5 | 21-Jun-25 A | 2026-07-23 | 12-Jul-25 A | 2026-02-20 | 2026-07-23
| A1-PM-PRD-0025 | PM-067-Delivery Certificate on Site |  | 2026-02-20 |  |  | 5 | 21-Jun-25 A | 2026-07-23 | 12-Jul-25 A | 2026-02-20 | 2026-07-23
| A1-PM-PRD-0026 | PM-068-Subcontract status report |  | 2026-02-20 |  |  | 5 | 21-Jun-25 A | 2026-07-23 | 12-Jul-25 A | 2026-02-20 | 2026-07-23
| A1-PM-PRD-0027 | PM-069-Sub contractor performance feed back report |  | 2026-02-20 |  |  | 5 | 21-Jun-25 A | 2026-07-23 | 12-Jul-25 A | 2026-02-20 | 2026-07-23
| A1-PM-PRD-0028 | PM-070-Material Status Report |  | 2026-02-20 |  |  | 5 | 21-Jun-25 A | 2026-07-23 | 12-Jul-25 A | 2026-02-20 | 2026-07-23
| A1-PM-PRD-0029 | PM-071-Purchasing Status Report |  | 2026-02-20 |  |  | 5 | 21-Jun-25 A | 2026-07-23 | 12-Jul-25 A | 2026-02-20 | 2026-07-23
| A1-PM-PRD-0020 | PM-056-Vendor Manufacturing Quality Plan |  | 2026-02-20 |  |  | 5 | 21-Jun-25 A | 2026-07-23 | 23-Jul-25 A | 2026-02-20 | 2026-07-23
| A1-PM-PRD-0001 | PM-018-Equipment Delivery and storage Plan |  | 2026-02-20 |  |  | 5 | 25-May-25 A | 2026-07-23 | 25-Aug-25 A | 2026-02-20 | 2026-07-23
| A1-PM-PRD-0003 | PM-020-Procurement Procedures |  | 2026-02-20 |  |  | 5 | 01-Jun-25 A | 2026-07-23 | 25-Aug-25 A | 2026-02-20 | 2026-07-23
| A1-PM-PRD-0006 | PM-023-Transportation Plan & Procedure |  | 2026-02-20 |  |  | 5 | 24-May-25 A | 2026-07-23 | 25-Aug-25 A | 2026-02-20 | 2026-07-23
| A1-PM-PRD-0017 | PM-044-Vendor List |  | 2026-02-20 |  |  | 5 | 12-Jun-25 A | 2026-07-23 | 25-Aug-25 A | 2026-02-20 | 2026-07-23
| A1-PM-PRD-0019 | PM-055-Subcontract Pre Qualification |  | 2026-02-20 |  |  | 5 | 19-Jun-25 A | 2026-07-23 | 25-Aug-25 A | 2026-02-20 | 2026-07-23
| A1-PM-PRD-0002 | PM-019-Subcontracting Procedure |  | 2026-02-20 |  |  | 5 | 25-May-25 A | 2026-07-23 | 02-Sep-25 A | 2026-02-20 | 2026-07-23
| A1-PM-PRD-0018 | PM-051-Copy of unpriced sub contract agreement |  | 2026-02-20 |  |  | 5 | 19-Jun-25 A | 2026-07-23 | 02-Sep-25 A | 2026-02-20 | 2026-07-23
| A1-PM-PRD-0030 | PM-072-Vendor Performance feed back report |  | 2026-02-20 |  |  | 5 | 25-Oct-25 A | 2026-07-23 | 2026-02-24 | 2026-02-24 | 2026-07-27 | 109
| Procurement Interim Milestones |  |  | 2026-02-20 |  |  | 461 | 21-Feb-25 A | 2026-05-04 | 2027-01-20 | 2027-01-20 | 2027-07-20 | 129
| A1-PM-PRM-0001 | 1.A*-Issue Procurement Procedures. |  |  |  |  | 0 |  |  | 28-Mar-25 A
| A1-PM-PRM-0002 | 7.A-VENDOR training and visits planned |  |  |  |  | 0 |  |  | 2026-10-18 | 2026-10-18 | 2027-01-03 | 67
| Procurement Equipment & Materials |  |  | 2026-03-19 |  |  | 221 | 21-Feb-25 A | 2026-06-12 | 2026-05-13 | 2026-05-13 | 2027-01-20 | 180
| A1-PM-PRM-0015 | 62.C-Issue purchase order Piping MTO for Shut Down Works |  |  |  |  | 0 |  |  | 21-Feb-25 A
| A1-PM-PRM-0013 | 60.C-Issue purchase orders for all Shut Down Materials (Piping, Electrical and Instrumentation |  |  |  |  | 0 |  |  | 28-Mar-25 A
| A1-PM-PRM-0003 | 49.C*-Issue purchase order for Compressors Centrifugal / Reciprocating |  |  |  |  | 0 |  |  | 30-May-25 A
| A1-PM-PRM-0004 | 50.C*-Issue purchase orders for Furnaces |  |  |  |  | 0 |  |  | 21-Jun-25 A
| A1-PM-PRM-0012 | 59.C*-Issue first purchase orders for bulk electrical materials |  |  |  |  | 0 |  |  | 21-Jun-25 A
| A1-PM-PRM-0014 | 61.C*-Issue first purchase orders for bulk instrument materials |  |  |  |  | 0 |  |  | 21-Jun-25 A
| A1-PM-PRM-0005 | 51.C*-Issue purchase orders for all remaining Mechanical / Rotating Equipment & Equipment Packages |  |  |  |  | 0 |  |  | 01-Sep-25 A
| A1-PM-PRM-0008 | 55.C*-Issue first purchase order for piping bulk materials |  |  |  |  | 0 |  |  | 19-Sep-25 A
| A1-PM-PRM-0007 | 54.C*-Issue purchase order for all major instrument control SYSTEMS |  |  |  |  | 0 |  |  | 21-Nov-25 A
| A1-PM-PRM-0009 | 56.C-Issue intermediate purchase order for piping bulk materials |  |  |  |  | 0 |  |  | 2026-03-19 | 2026-03-19 | 2026-06-12 | 61
| A1-PM-PRM-0011 | 58.C-Issue purchase orders for all field instrument tagged items |  |  |  |  | 0 |  |  | 2026-03-25 | 2026-03-25 | 2027-01-20 | 216
| A1-PM-PRM-0010 | 57.C-Issue final purchase order for piping bulk materials |  |  |  |  | 0 |  |  | 2026-04-22 | 2026-04-22 | 2026-06-12 | 37
| A1-PM-PRM-0006 | 52.C*-Issue purchase orders for all major electrical Equipment |  |  |  |  | 0 |  |  | 2026-05-13 | 2026-05-13 | 2027-01-20 | 180
| Subcontracts | [5 empty] | 257 | 30-May-25 A |  | 01-Sep-25 A
| A1-PM-PRM-0024 | 71.C*-Buildings subcontract award |  |  |  |  | 0 |  |  | 30-May-25 A
| A1-PM-PRM-0016 | 63.C-Piling subcontract award |  |  |  |  | 0 |  |  | 01-Jun-25 A
| A1-PM-PRM-0017 | 64.C*-Civil subcontract award |  |  |  |  | 0 |  |  | 15-Jun-25 A
| A1-PM-PRM-0019 | 66.C*-Mechanical subcontract award |  |  |  |  | 0 |  |  | 15-Jun-25 A
| A1-PM-PRM-0020 | 67.C-Insulation subcontract award |  |  |  |  | 0 |  |  | 15-Jun-25 A
| A1-PM-PRM-0021 | 68.C-Painting subcontract award |  |  |  |  | 0 |  |  | 15-Jun-25 A
| A1-PM-PRM-0022 | 69.C*-Electrical subcontract award |  |  |  |  | 0 |  |  | 15-Jun-25 A
| A1-PM-PRM-0023 | 70.C*-Instrument subcontract award |  |  |  |  | 0 |  |  | 15-Jun-25 A
| A1-PM-PRM-0018 | 65.C-Steel fabrication/erection subcontract award |  |  |  |  | 0 |  |  | 01-Sep-25 A
| Manufacturing & Delivery |  |  | 2026-02-20 |  |  | 441 | 20-Mar-25 A | 2026-05-04 | 2027-01-20 | 2027-01-20 | 2027-07-20 | 129
| A1-PM-PRM-0041 | 94.D-Piping MTO for Shut Down Works Delivered to SITE |  |  |  |  | 0 |  |  | 20-Mar-25 A
| A1-PM-PRM-0026 | 77.D*-Furnaces delivered to SITE |  |  |  |  | 0 |  |  | 10-Sep-25 A
| A1-PM-PRM-0033 | 84.D*-Bulk piping materials initial MTO delivered to SITE |  |  |  |  | 0 |  |  | 2026-02-20 | 2026-02-20 | 2026-05-06 | 95
| A1-PM-PRM-0025 | 76.D*-Compressors Centrifugal / Reciprocating delivered to SITE |  |  |  |  | 0 |  |  | 2026-03-03 | 2026-03-03 | 2026-05-04 | 53
| A1-PM-PRM-0034 | 85.D*-Bulk piping materials intermediate MTO delivered to SITE |  |  |  |  | 0 |  |  | 2026-04-18 | 2026-04-18 | 2026-07-15 | 77
| A1-PM-PRM-0035 | 86.D*-Bulk piping materials final MTO delivered to SITE |  |  |  |  | 0 |  |  | 2026-08-22 | 2026-08-22 | 2026-10-07 | 41
| A1-PM-PRM-0029 | 80.D*-HVAC, Fire Detection and Fire Fighting SYSTEMS for all buildings delivered to SITE |  |  |  |  | 0 |  |  | 2026-08-26 | 2026-08-26 | 2026-12-28 | 106
| A1-PM-PRM-0036 | 88.D-Bulk electrical materials final MTO delivered to SITE |  |  |  |  | 0 |  |  | 2026-08-31 | 2026-08-31 | 2026-12-10 | 127
| A1-PM-PRM-0027 | 78.D*-Remaining Mechanical / Rotating Equipment & Equipment Packages delivered to SITE |  |  |  |  | 0 |  |  | 2026-09-13 | 2026-09-13 | 2027-07-20 | 388
| A1-PM-PRM-0037 | 90.D-Bulk instrument materials final MTO delivered to SITE |  |  |  |  | 0 |  |  | 2026-09-24 | 2026-09-24 | 2026-10-07 | 16
| A1-PM-PRM-0032 | 83.D-Field instrument tagged items delivered to SITE |  |  |  |  | 0 |  |  | 2026-09-27 | 2026-09-27 | 2026-12-10 | 93
| A1-PM-PRM-0028 | 79.D*-All major electrical Equipment delivered to SITE |  |  |  |  | 0 |  |  | 2026-09-29 | 2026-09-29 | 2027-01-03 | 120
| A1-PM-PRM-0030 | 81.D*-Major instrument control SYSTEMS delivered to SITE |  |  |  |  | 0 |  |  | 2026-09-29 | 2026-09-29 | 2026-12-10 | 90
| A1-PM-PRM-0031 | 82.D-Instrument Control SYSTEMS for CCB delivered to SITE |  |  |  |  | 0 |  |  | 2026-09-29 | 2026-09-29 | 2026-12-10 | 90
| A1-PM-PRM-0038 | 91.D-Insurance spares for all equipment & packages arrival at SITE and handover to COMPANY |  |  |  |  | 0 |  |  | 2027-01-20 | 2027-01-20 | 2027-07-20 | 155
| A1-PM-PRM-0039 | 92.D*-Operating Spares for all item’s arrival at SITE and handover to COMPANY. |  |  |  |  | 0 |  |  | 2027-01-20 | 2027-01-20 | 2027-07-20 | 155
| A1-PM-PRM-0040 | 93.D*-All VENDOR Documentation Handed over to COMPANY |  |  |  |  | 0 |  |  | 2027-01-20 | 2027-01-20 | 2027-07-20 | 155
| Construction |  |  | 2026-02-20 |  |  | 489 | 10-Mar-25 A | 2026-07-30 | 2027-03-10 | 2027-03-10 | 2027-07-20 | 94
| Construction Deliverables |  |  | 2026-02-20 |  |  | 469 | 10-Mar-25 A | 2026-08-14 | 2027-03-10 | 2027-03-10 | 2027-04-21 | 30
| A1-PM-COD-0020 | CS-020-Test Certificate |  | 2026-02-20 |  |  | 5 | 10-Mar-25 A | 2026-08-14 | 26-Mar-25 A | 2026-02-20 | 2026-08-14
| A1-PM-COD-0028 | CS-028-Construction execution methodologies (work methods) |  | 2026-02-20 |  |  | 15 | 01-Apr-25 A | 2026-08-22 | 07-Apr-25 A | 2026-02-20 | 2026-08-22
| A1-PM-COD-0007 | CS-007-Time Schedule / Programme |  | 2026-02-20 |  |  | 5 | 19-Mar-25 A | 2026-08-14 | 19-Jun-25 A | 2026-02-20 | 2026-08-14
| A1-PM-COD-0018 | CS-018-Quality Assurance Docs |  | 2026-02-20 |  |  | 5 | 02-Jun-25 A | 2026-08-14 | 19-Jun-25 A | 2026-02-20 | 2026-08-14
| A1-PM-COD-0013 | CS-013-Locking List |  | 2026-02-20 |  |  | 5 | 02-Jun-25 A | 2026-08-14 | 20-Jun-25 A | 2026-02-20 | 2026-08-14
| A1-PM-COD-0027 | CS-027-Temporary facilities plan |  | 2026-02-20 |  |  | 5 | 21-Jun-25 A | 2026-08-14 | 30-Jun-25 A | 2026-02-20 | 2026-08-14
| A1-PM-COD-0029 | CS-029-Logistics plan |  | 2026-02-20 |  |  | 5 | 21-Jun-25 A | 2026-08-14 | 30-Jun-25 A | 2026-02-20 | 2026-08-14
| A1-PM-COD-0004 | CS-004-Procedures |  | 2026-02-20 |  |  | 5 | 21-Jun-25 A | 2026-08-14 | 12-Jul-25 A | 2026-02-20 | 2026-08-14
| A1-PM-COD-0006 | CS-006-Method Statements |  | 2026-02-20 |  |  | 5 | 21-Jun-25 A | 2026-08-14 | 12-Jul-25 A | 2026-02-20 | 2026-08-14
| A1-PM-COD-0008 | CS-008-Lifting |  | 2026-02-20 |  |  | 5 | 21-Jun-25 A | 2026-08-14 | 12-Jul-25 A | 2026-02-20 | 2026-08-14
| A1-PM-COD-0009 | CS-009-Site plans |  | 2026-02-20 |  |  | 5 | 21-Jun-25 A | 2026-08-14 | 12-Jul-25 A | 2026-02-20 | 2026-08-14
| A1-PM-COD-0010 | CS-010-Demolition plan |  | 2026-02-20 |  |  | 5 | 21-Jun-25 A | 2026-08-14 | 12-Jul-25 A | 2026-02-20 | 2026-08-14
| A1-PM-COD-0011 | CS-011-Temporary Works |  | 2026-02-20 |  |  | 5 | 21-Jun-25 A | 2026-08-14 | 12-Jul-25 A | 2026-02-20 | 2026-08-14
| A1-PM-COD-0012 | CS-012-label |  | 2026-02-20 |  |  | 5 | 21-Jun-25 A | 2026-08-14 | 12-Jul-25 A | 2026-02-20 | 2026-08-14
| A1-PM-COD-0014 | CS-014-Technical Bid Analysis |  | 2026-02-20 |  |  | 5 | 21-Jun-25 A | 2026-08-14 | 12-Jul-25 A | 2026-02-20 | 2026-08-14
| A1-PM-COD-0032 | CS-032-Camp and Accommodation Plan |  | 2026-02-20 |  |  | 5 | 21-Jun-25 A | 2026-08-14 | 12-Jul-25 A | 2026-02-20 | 2026-08-14
| A1-PM-COD-0026 | CS-026-Civil Specifications |  | 2026-02-20 |  |  | 5 | 21-Jun-25 A | 2026-08-14 | 31-Jul-25 A | 2026-02-20 | 2026-08-14
| A1-PM-COD-0025 | CS-025-Electrical Specifications |  | 2026-02-20 |  |  | 5 | 21-Jun-25 A | 2026-08-14 | 20-Aug-25 A | 2026-02-20 | 2026-08-14
| A1-PM-COD-0003 | CS-003-Execution Plan |  | 2026-02-20 |  |  | 5 | 25-May-25 A | 2026-08-14 | 15-Nov-25 A | 2026-02-20 | 2026-08-14
| A1-PM-COD-0019 | CS-019-HSE |  | 2026-02-20 |  |  | 5 | 01-Oct-25 A | 2026-08-14 | 18-Dec-25 A | 2026-02-20 | 2026-08-14
| A1-PM-COD-0017 | CS-017-Check List |  | 2026-02-20 |  |  | 5 | 15-Oct-25 A | 2026-08-14 | 19-Dec-25 A | 2026-02-20 | 2026-08-14
| A1-PM-COD-0021 | CS-021-Quality Control Procedure |  | 2026-02-20 |  |  | 5 | 01-Oct-25 A | 2026-08-14 | 19-Dec-25 A | 2026-02-20 | 2026-08-14
| A1-PM-COD-0022 | CS-022-Construction Strategies |  | 2026-02-20 |  |  | 5 | 21-Jun-25 A | 2026-08-14 | 19-Dec-25 A | 2026-02-20 | 2026-08-14
| A1-PM-COD-0023 | CS-023-Concession Requests |  | 2026-02-20 |  |  | 5 | 01-Sep-25 A | 2026-08-14 | 19-Dec-25 A | 2026-02-20 | 2026-08-14
| A1-PM-COD-0024 | CS-024-Non-Conformance Requests |  | 2026-02-20 |  |  | 5 | 01-Sep-25 A | 2026-08-14 | 19-Dec-25 A | 2026-02-20 | 2026-08-14
| A1-PM-COD-0030 | CS-030-mobilisation/demobilisation plan |  | 2026-02-20 |  |  | 5 | 01-Jul-25 A | 2026-08-14 | 19-Dec-25 A | 2026-02-20 | 2026-08-14
| A1-PM-COD-0034 | CS-034-Field Construction Execution plan |  | 2026-02-20 |  |  | 21 | 08-Apr-25 A | 2027-02-08 | 19-Dec-25 A | 2026-02-20 | 2027-02-08
| A1-PM-COD-0005 | CS-005-Field instructions |  | 2026-02-20 |  |  | 5 | 01-Sep-25 A | 2026-08-14 | 2026-02-20 | 2026-02-20 | 2026-08-17 | 126
| A1-PM-COD-0016 | CS-016-Punch List |  | 2026-02-20 |  |  | 5 | 21-Jun-25 A | 2026-08-14 | 2026-02-20 | 2026-02-20 | 2026-08-17 | 126
| A1-PM-COD-0033 | CS-033-Construction logistic plan |  | 2026-02-20 |  |  | 5 | 01-Aug-25 A | 2026-08-14 | 2026-02-23 | 2026-02-23 | 2026-08-17 | 126
| A1-PM-COD-0031 | CS-031-Construction Cleanliness Plant |  | 2026-02-20 |  |  | 5 | 01-Aug-25 A | 2026-08-14 | 2026-02-24 | 2026-02-24 | 2026-08-19 | 126
| A1-PM-COD-0015 | CS-015-Insulation / Painting / Fire Proofing |  | 2026-02-20 |  |  | 5 | 01-Apr-25 A | 2026-08-14 | 2026-02-26 | 2026-02-26 | 2026-08-21 | 126
| A1-PM-COD-0001 | CS-001-QC Dossier |  | 2027-01-21 |  |  | 5 | 2027-01-21 | 2027-03-04 | 2027-01-27 | 2027-01-27 | 2027-03-10 | 30
| A1-PM-COD-0002 | CS-002-Construction Handover Dossier ( ALL Discipline wise) |  | 2027-03-08 |  |  | 5 | 22-Jun-25 A | 2027-04-19 | 2027-03-10 | 2027-03-10 | 2027-04-21 | 30
| Construction Interim Milestones |  |  | 2026-04-09 |  |  | 456 | 25-Mar-25 A | 2026-07-30 | 2027-02-21 | 2027-02-21 | 2027-07-20 | 107
| A1-PM-CIM-0004 | 3.A-Tie-in/Shutdown philosophy etc. (Excluding Hydrotesting, Drying, Purging, PRE-COMMISSIONING and COMMISSIONING Proced |  |  |  |  | 0 |  |  | 31-May-25 A
| A1-PM-CIM-0001 | 3.A-Issue Construction Execution Plan (Excluding Hydrotesting, Drying, Purging, PRE-COMMISSIONING and COMMISSIONING Proc |  |  |  |  | 0 |  |  | 21-Jun-25 A
| A1-PM-CIM-0002 | 3.A-Issue Construction Execution Procedures (Excluding Hydrotesting, Drying, Purging, PRE-COMMISSIONING and COMMISSIONIN |  |  |  |  | 0 |  |  | 21-Jun-25 A
| A1-PM-CIM-0003 | 3.A-Issue Construction Execution Method Statements (Excluding Hydrotesting, Drying, Purging, PRE-COMMISSIONING and COMMI |  |  |  |  | 0 |  |  | 21-Jun-25 A
| A1-PM-CIM-0005 | 4.A-Issue Hydrotesting Procedures and plan (Final). |  |  |  |  | 0 |  |  | 2026-04-14 | 2026-04-14 | 2027-02-08 | 215
| A1-PM-CIM-0006 | 4.A-Issue Drying Procedures and plan (Final). |  |  |  |  | 0 |  |  | 2026-04-14 | 2026-04-14 | 2027-02-08 | 215
| A1-PM-CIM-0007 | 4.A-Issue Purging Procedures and plan (Final). |  |  |  |  | 0 |  |  | 2026-04-14 | 2026-04-14 | 2027-02-08 | 215
| A1-PM-CIM-0008 | 4.A-Issue PRECOMMISSIONING Procedures and plan (Final). |  |  |  |  | 0 |  |  | 2026-04-14 | 2026-04-14 | 2027-02-08 | 215
| A1-PM-CIM-0009 | 4.A-Issue COMMISSIONING Procedures and plan (Final). |  |  |  |  | 0 |  |  | 2026-04-14 | 2026-04-14 | 2027-02-08 | 215
| A1-PM-CIM-0010 | 4.A-Issue Handover Procedures and plan (Final). |  |  |  |  | 0 |  |  | 2026-04-14 | 2026-04-14 | 2026-12-09 | 172
| A1-PM-CIM-0024 | 113.E-Start Piping Prefabrication |  |  |  |  | 0 |  |  | 25-Mar-25 A
| A1-PM-CIM-0028 | 117.E-Start Piping erection |  |  |  |  | 0 |  |  | 15-Apr-25 A
| A1-PM-CIM-0034 | 123.E-Complete all piping tie-ins (Including Interface Tie-Ins) |  |  |  |  | 0 |  |  | 20-May-25 A
| A1-PM-CIM-0011 | 94.E*-Commence on SITE |  |  |  |  | 0 |  |  | 31-May-25 A
| A1-PM-CIM-0013 | 96.E-Complete SITE preparation and grading works |  |  |  |  | 0 |  |  | 21-Jun-25 A
| A1-PM-CIM-0012 | 95.E-Complete Construction of Temporary Facilities at SITE. |  |  |  |  | 0 |  |  | 15-Nov-25 A
| A1-PM-CIM-0015 | 101.E-Complete all Piperack foundations |  |  |  |  | 0 |  |  | 2026-04-09 | 2026-04-09 | 2027-01-20 | 245
| A1-PM-CIM-0017 | 103.E-Complete installation of all underground electrical cabling |  |  |  |  | 0 |  |  | 2026-05-07 | 2026-05-07 | 2026-12-09 | 185
| A1-PM-CIM-0019 | 105.E-Trench for data highway cables SIS to Control Building available |  |  |  |  | 0 |  |  | 2026-05-07 | 2026-05-07 | 2027-01-20 | 221
| A1-PM-CIM-0039 | 128.E-Trench for Main Electrical Feeder cables Main to Unit Substations available |  |  |  |  | 0 |  |  | 2026-05-07 | 2026-05-07 | 2026-08-15 | 85
| A1-PM-CIM-0021 | 110.E-Complete installation of Turbines/Compressors |  |  |  |  | 0 |  |  | 2026-05-18 | 2026-05-18 | 2027-01-20 | 212
| A1-PM-CIM-0023 | 112.E-Completion of Heavy Lifts |  |  |  |  | 0 |  |  | 2026-05-18 | 2026-05-18 | 2026-07-30 | 63
| A1-PM-CIM-0018 | 104.E-Complete installation of all underground instrument cabling |  |  |  |  | 0 |  |  | 2026-06-20 | 2026-06-20 | 2026-12-09 | 149
| A1-PM-CIM-0014 | 100.E-Complete construction of foundations for all remaining mechanical, rotating & packaged equipment |  |  |  |  | 0 |  |  | 2026-06-25 | 2026-06-25 | 2026-08-22 | 48
| A1-PM-CIM-0016 | 102.E-Complete all underground piping |  |  |  |  | 0 |  |  | 2026-07-19 | 2026-07-19 | 2027-01-20 | 159
| A1-PM-CIM-0020 | 106.E-Complete installation of steel structural works for shelters, and Package Units etc. |  |  |  |  | 0 |  |  | 2026-09-10 | 2026-09-10 | 2027-01-20 | 113
| A1-PM-CIM-0037 | 126.E-Complete installation of platforms, walkways, crossovers etc. |  |  |  |  | 0 |  |  | 2026-09-10 | 2026-09-10 | 2027-01-20 | 113
| A1-PM-CIM-0025 | 114.E-Complete prefabrication 50% piping. |  |  |  |  | 0 |  |  | 2026-09-17 | 2026-09-17 | 2027-01-20 | 107
| A1-PM-CIM-0041 | 130.E-Complete Street lighting |  |  |  |  | 0 |  |  | 2026-10-03 | 2026-10-03 | 2027-01-20 | 94
| A1-PM-CIM-0026 | 115.E-Complete prefabrication 98% piping |  |  |  |  | 0 |  |  | 2026-10-05 | 2026-10-05 | 2027-01-20 | 92
| A1-PM-CIM-0036 | 125.E-Complete Heat Tracing, Insulation, Fire Proofing and Painting works |  |  |  |  | 0 |  |  | 2026-10-05 | 2026-10-05 | 2027-01-20 | 92
| A1-PM-CIM-0038 | 127.E-Complete installation of all Substation electrical equipment |  |  |  |  | 0 |  |  | 2026-10-18 | 2026-10-18 | 2027-01-20 | 82
| A1-PM-CIM-0027 | 116.E-Complete installation of pipe supports, sleepers, trestles etc. |  |  |  |  | 0 |  |  | 2026-10-22 | 2026-10-22 | 2027-01-20 | 77
| A1-PM-CIM-0029 | 118.E-Piping erection 50% Complete |  |  |  |  | 0 |  |  | 2026-10-22 | 2026-10-22 | 2027-01-20 | 77
| A1-PM-CIM-0030 | 119.E-Piping Erection 100% complete |  |  |  |  | 0 |  |  | 2026-10-22 | 2026-10-22 | 2027-01-20 | 77
| A1-PM-CIM-0022 | 111.E-Complete installation of all remaining mechanical, rotating & packaged equipment |  |  |  |  | 0 |  |  | 2026-11-02 | 2026-11-02 | 2027-01-20 | 68
| A1-PM-CIM-0031 | 120.E-Commence hydrotesting of Pipework |  |  |  |  | 0 |  |  | 2026-11-16 | 2026-11-16 | 2027-01-20 | 56
| A1-PM-CIM-0032 | 121.E-Piping Hydrotesting 50% complete |  |  |  |  | 0 |  |  | 2026-11-16 | 2026-11-16 | 2027-01-20 | 56
| A1-PM-CIM-0033 | 122.E-Piping Hydrotesting 100% complete |  |  |  |  | 0 |  |  | 2026-12-03 | 2026-12-03 | 2027-01-20 | 41
| A1-PM-CIM-0035 | 124.E-Complete Fire Water System including tanks, pumps and piping works up to Mechanical Completion. |  |  |  |  | 0 |  |  | 2026-12-03 | 2026-12-03 | 2027-01-20 | 41
| A1-PM-CIM-0040 | 129.E-Complete electrical cabling and termination works (field works) for all plant facilities including continuity chec |  |  |  |  | 0 |  |  | 2026-12-21 | 2026-12-21 | 2027-01-20 | 26
| Eelectrical |  |  | 2027-01-20 |  |  | 22 | 2027-01-20 | 2027-04-21 | 2027-02-21 | 2027-02-21 | 2027-07-20 | 107
| A1-PM-CIM-0042 | 131.E-Power from TRANSCO (Needs) |  |  |  |  | 0 |  |  | 2027-01-20 | 2027-01-20 | 2027-07-20 | 226
| A1-PM-CIM-0043 | 134.E-Complete motor run |  |  |  |  | 0 |  |  | 2027-02-21 | 2027-02-21 | 2027-04-21 | 51
| Instrumentation |  |  | 2026-11-08 |  |  | 37 | 2026-11-08 | 2027-04-21 | 2026-12-21 | 2026-12-21 | 2027-04-21 | 104
| A1-PM-CIM-0044 | 135.E-Control System Cables including Fiber opticinstalled and tested |  |  |  |  | 0 |  |  | 2026-11-08 | 2026-11-08 | 2027-04-21 | 141
| A1-PM-CIM-0045 | 136.E-Complete instrumentation system loop checks and other PRE-COMMISSIONING checks |  |  |  |  | 0 |  |  | 2026-12-21 | 2026-12-21 | 2027-04-21 | 104
| Mechanical Completion & Ready for START UP |  |  | 2027-01-20 |  |  | 0 | 2027-01-20 | 2027-07-20 | 2027-01-20 | 2027-01-20 | 2027-07-20 | 181
| A1-PM-CIM-0046 | 138.F-Mechanical Completion |  |  |  |  | 0 |  |  | 2027-01-20 | 2027-01-20 | 2027-07-20 | 226
| Construction Workshops |  |  | 2026-02-20 |  |  | 25 | 27-Aug-25 A | 2026-12-22 | 29-Aug-25 A | 2026-02-20 | 2026-12-22
| A1-PM-CWS-0001 | Constructabilty Workshop |  | 2026-02-20 |  |  | 5 | 27-Aug-25 A | 2026-12-22 | 27-Aug-25 A | 2026-02-20 | 2026-12-22
| A1-PM-CWS-0002 | SIMOPS Workshop |  | 2026-02-20 |  |  | 5 | 28-Aug-25 A | 2026-12-22 | 29-Aug-25 A | 2026-02-20 | 2026-12-22
| Commissioning |  |  | 2026-02-20 |  |  | 433 | 01-Aug-25 A | 2026-08-12 | 2027-07-20 | 2027-07-20 | 2027-07-20 | 0
| Commissioning Deliverables |  |  | 2026-02-20 |  |  | 166 | 01-Aug-25 A | 2026-08-12 | 2026-07-10 | 2026-07-10 | 2026-12-30 | 124
| A1-PM-CMD-0001 | CM-001-Performance Test Run Procedure |  | 2026-02-20 |  |  | 15 | 01-Aug-25 A | 2026-08-12 | 2026-03-06 | 2026-03-06 | 2026-08-26 | 124
| A1-PM-CMD-0002 | CM-002-Performance Test Run Report |  | 2026-03-06 |  |  | 15 | 2026-03-06 | 2026-08-27 | 2026-03-27 | 2026-03-27 | 2026-09-16 | 124
| A1-PM-CMD-0003 | CM-003-Commissioning Procedures |  | 2026-03-27 |  |  | 15 | 2026-03-27 | 2026-09-17 | 2026-04-17 | 2026-04-17 | 2026-10-07 | 124
| A1-PM-CMD-0004 | CM-004-Pre-Commisioning & Commissioning Schedule |  | 2026-04-17 |  |  | 15 | 2026-04-17 | 2026-10-08 | 2026-05-08 | 2026-05-08 | 2026-10-28 | 124
| A1-PM-CMD-0005 | CM-005-Pre-Commisioning & Commissioning systems identification drawings (P&IDs, single line diagram, etc) |  | 2026-05-08 |  |  | 15 | 2026-05-08 | 2026-10-29 | 2026-05-29 | 2026-05-29 | 2026-11-18 | 124
| A1-PM-CMD-0006 | CM-006-Pre- Commissioning Procedure |  | 2026-05-29 |  |  | 15 | 2026-05-29 | 2026-11-19 | 2026-06-19 | 2026-06-19 | 2026-12-09 | 124
| A1-PM-CMD-0007 | CM-007-Pre-Commisioning & Commissioning Method of Statements |  | 2026-06-19 |  |  | 15 | 2026-06-19 | 2026-12-10 | 2026-07-10 | 2026-07-10 | 2026-12-30 | 124
| Commissioning Interim Milestones |  |  | 2026-09-14 |  |  | 222 | 2026-09-14 | 2027-04-21 | 2027-07-20 | 2027-07-20 | 2027-07-20 | 0
| A1-PM-CMM-0001 | 6.A-Training program for COMPANY staff issued to COMPANY for APPROVAL |  |  |  |  | 0 |  |  | 2027-01-20 | 2027-01-20 | 2027-04-21 | 114
| A1-PM-CMM-0006 | 5.A-Issue SYSTEMS definition IFC & SYSTEMS completion Schedule |  |  |  |  | 0 |  |  | 2027-01-21 | 2027-01-21 | 2027-04-21 | 65
| A1-PM-CMM-0004 | 143.F-Issue "AS BUILT STATUS”
| operating/Maintenance & Safety Manual | 0 | [6 empty] | 2026-09-14 | 2026-09-14 | 2027-07-20 | 222
| A1-PM-CMM-0003 | 142.F-Commercial Production |  |  |  |  | 0 |  |  | 2027-04-14 | 2027-04-14 | 2027-07-20 | 83
| A1-PM-CMM-0002 | 145.F-Ready for Start-Up |  |  |  |  | 0 |  |  | 2027-04-22 | 2027-04-22 | 2027-07-20 | 64
| A1-PM-CMM-0005 | 144.F-PROVISIONAL ACCEPTANCE CERTIFICATE |  |  |  |  | 0 |  |  | 2027-07-20 | 2027-07-20 | 2027-07-20 | 0
| HSE Management |  |  | 2026-02-20 |  |  | 419 | 17-Feb-25 A | 2026-03-02 | 2026-09-25 | 2026-09-25 | 2027-01-20 | 84
| HSE Deliverables |  |  | 2026-02-20 |  |  | 306 | 17-Feb-25 A | 2026-04-02 | 2026-04-21 | 2026-04-21 | 2026-12-09 | 167
| A1-PM-HSD-0001 | S-001-Procedures & Management of Change |  | 2026-02-20 |  |  | 5 | 17-Feb-25 A | 2026-04-02 | 03-Mar-25 A | 2026-02-20 | 2026-04-02
| A1-PM-HSD-0014 | S-014-Bill of material |  | 2026-02-20 |  |  | 5 | 02-Jun-25 A | 2026-08-21 | 09-Jun-25 A | 2026-02-20 | 2026-08-21
| A1-PM-HSD-0015 | S-015-Safety Schedule / Sheets |  | 2026-02-20 |  |  | 5 | 09-Jun-25 A | 2026-09-04 | 20-Jun-25 A | 2026-02-20 | 2026-09-04
| A1-PM-HSD-0007 | S-007-Project Construction HSE Plan / House Keeping Plan |  | 2026-02-20 |  |  | 30 | 10-Jun-25 A | 2026-12-09 | 11-Jul-25 A | 2026-02-20 | 2026-12-09
| A1-PM-HSD-0005 | S-005-Site Plans / Plot Plans / Key Plans |  | 2026-02-20 |  |  | 5 | 21-Jun-25 A | 2026-09-04 | 12-Jul-25 A | 2026-02-20 | 2026-09-04
| A1-PM-HSD-0006 | S-006-Overall Fire Water & Ringman Header Layout |  | 2026-02-20 |  |  | 5 | 21-Jun-25 A | 2026-09-04 | 12-Jul-25 A | 2026-02-20 | 2026-09-04
| A1-PM-HSD-0009 | S-009-HSE Layouts |  | 2026-02-20 |  |  | 5 | 21-Jun-25 A | 2026-09-04 | 12-Jul-25 A | 2026-02-20 | 2026-09-04
| A1-PM-HSD-0016 | S-016-Technical Bid Analysis |  | 2026-02-20 |  |  | 5 | 21-Jun-25 A | 2026-09-04 | 12-Jul-25 A | 2026-02-20 | 2026-09-04
| A1-PM-HSD-0030 | S-030-Risk Assessment |  | 2026-02-20 |  |  | 5 | 21-Jun-25 A | 2026-08-21 | 12-Jul-25 A | 2026-02-20 | 2026-08-21
| A1-PM-HSD-0034 | S-034-Specifications |  | 2026-02-20 |  |  | 5 | 21-Jun-25 A | 2026-08-21 | 12-Jul-25 A | 2026-02-20 | 2026-08-21
| A1-PM-HSD-0021 | S-021-HAZOP / SIL (LOPA) Reports |  |  |  |  | 0 |  |  | 18-Jul-25 A
| A1-PM-HSD-0018 | S-018-Equipment List |  | 2026-02-20 |  |  | 5 | 21-Jun-25 A | 2026-09-04 | 21-Jul-25 A | 2026-02-20 | 2026-09-04
| A1-PM-HSD-0031 | S-031-Process Philosophies & HSE Plan |  | 2026-02-20 |  |  | 30 | 14-Jul-25 A | 2026-12-09 | 13-Aug-25 A | 2026-02-20 | 2026-12-09
| A1-PM-HSD-0032 | S-032-Philosophies |  | 2026-02-20 |  |  | 5 | 14-Aug-25 A | 2026-08-21 | 19-Aug-25 A | 2026-02-20 | 2026-08-21
| A1-PM-HSD-0033 | S-033-Data sheets (ALL Type of Safety Data sheets) |  | 2026-02-20 |  |  | 5 | 20-Aug-25 A | 2026-08-21 | 26-Aug-25 A | 2026-02-20 | 2026-08-21
| A1-PM-HSD-0022 | S-022-Hazard Study / Fire Protection Design Study / Noise Vibration Study/ SIMOPS Study |  | 2026-02-20 |  |  | 5 | 11-Aug-25 A | 2026-09-04 | 29-Aug-25 A | 2026-02-20 | 2026-09-04
| A1-PM-HSD-0003 | S-003-HSE Requirements |  | 2026-02-20 |  |  | 5 | 03-Mar-25 A | 2026-09-04 | 06-Sep-25 A | 2026-02-20 | 2026-09-04
| A1-PM-HSD-0029 | S-029-COSHH Assessments |  | 2026-04-17 |  |  | 5 | 01-Aug-25 A | 2026-09-04 | 25-Sep-25 A | 2026-04-17 | 2026-09-04
| A1-PM-HSD-0039 | S-039-Waste Management Plan |  | 2026-02-20 |  |  | 5 | 25-May-25 A | 2026-04-02 | 06-Jan-26 A | 2026-02-20 | 2026-04-02
| A1-PM-HSD-0002 | S-002-Requisition / Supply Specifications/ Technical Specifications |  | 2026-02-20 |  |  | 5 | 01-Aug-25 A | 2026-08-21 | 2026-02-20 | 2026-02-20 | 2026-08-21 | 130
| A1-PM-HSD-0004 | S-004-Fire Fighting Diagram / Fire Protection Diagram |  | 2026-02-20 |  |  | 5 | 01-Aug-25 A | 2026-09-04 | 2026-02-20 | 2026-02-20 | 2026-09-04 | 140
| A1-PM-HSD-0008 | S-008-Fire Proofing Zone layout (Plant / Area Wise) |  | 2026-02-20 |  |  | 5 | 01-Aug-25 A | 2026-09-04 | 2026-02-20 | 2026-02-20 | 2026-09-04 | 140
| A1-PM-HSD-0010 | S-010-Hazardous area Layouts |  | 2026-02-20 |  |  | 5 | 22-Jul-25 A | 2026-09-04 | 2026-02-20 | 2026-02-20 | 2026-09-04 | 140
| A1-PM-HSD-0011 | S-011-Fire Exposure Envelop Drawings / Heat Flux Boundary Drawings |  | 2026-02-20 |  |  | 5 | 01-Aug-25 A | 2026-09-04 | 2026-02-20 | 2026-02-20 | 2026-09-04 | 140
| A1-PM-HSD-0012 | S-012-Fire Alarm Drawings (Plant) |  | 2026-02-20 |  |  | 5 | 01-Aug-25 A | 2026-09-04 | 2026-02-20 | 2026-02-20 | 2026-09-04 | 140
| A1-PM-HSD-0013 | S-013-Fire Alarm Drawings (Building) |  | 2026-02-20 |  |  | 5 | 01-Aug-25 A | 2026-09-04 | 2026-02-20 | 2026-02-20 | 2026-09-04 | 140
| A1-PM-HSD-0017 | S-017-Hazard and Effect Register / HSECES Register/ HSE Critical Activities |  | 2026-02-20 |  |  | 5 | 01-Aug-25 A | 2026-09-04 | 2026-02-20 | 2026-02-20 | 2026-09-04 | 140
| A1-PM-HSD-0023 | S-023-Quality Assurance Docs |  | 2026-02-20 |  |  | 5 | 05-Aug-25 A | 2026-09-04 | 2026-02-20 | 2026-02-20 | 2026-09-04 | 140
| A1-PM-HSD-0019 | S-019-Fire and Safety Calculations / Explosion Over Pressure Calculations / Hydraulic Calculation |  | 2026-02-20 |  |  | 5 | 01-Aug-25 A | 2026-09-04 | 2026-02-23 | 2026-02-23 | 2026-09-07 | 140
| A1-PM-HSD-0020 | S-020-Hydraulic Calculations Report |  | 2026-02-20 |  |  | 5 | 04-Aug-25 A | 2026-09-04 | 2026-02-23 | 2026-02-23 | 2026-09-07 | 140
| A1-PM-HSD-0026 | S-026-Environmental / Effluent Disposal System/ Gas Dispersion /Environmental Pollution Reports / Fugitive Emissions Rep |  | 2026-02-20 |  |  | 5 | 04-Aug-25 A | 2026-09-04 | 2026-02-23 | 2026-02-23 | 2026-09-07 | 140
| A1-PM-HSD-0028 | S-028-QRA Reports |  | 2026-02-20 |  |  | 5 | 05-Aug-25 A | 2026-09-04 | 2026-02-23 | 2026-02-23 | 2026-09-07 | 140
| A1-PM-HSD-0036 | S-036-Safety Equipment and safety Routes Layout |  | 2026-02-20 |  |  | 5 | 04-Aug-25 A | 2026-08-21 | 2026-02-23 | 2026-02-23 | 2026-08-24 | 130
| A1-PM-HSD-0024 | S-024-Manufacturing Data Report |  | 2026-02-20 |  |  | 5 | 04-Aug-25 A | 2026-09-04 | 2026-02-24 | 2026-02-24 | 2026-09-08 | 140
| A1-PM-HSD-0025 | S-025-Installation, Operation and Maintenance |  | 2026-02-20 |  |  | 5 | 01-Aug-25 A | 2026-09-04 | 2026-02-24 | 2026-02-24 | 2026-09-08 | 140
| A1-PM-HSD-0027 | S-027-HSE Report / Close out Report/Atmospheric Relief System Report/ HSE- Safety Reviews |  | 2026-02-20 |  |  | 5 | 05-Aug-25 A | 2026-09-04 | 2026-02-24 | 2026-02-24 | 2026-09-08 | 140
| A1-PM-HSD-0035 | S-035-Ergonomic Study/ Human Factor Engineering / Assessment |  | 2026-02-20 |  |  | 5 | 02-Aug-25 A | 2026-08-21 | 2026-02-24 | 2026-02-24 | 2026-08-25 | 130
| A1-PM-HSD-0037 | S-037-PHSER and Close Out Report |  | 2026-02-24 |  |  | 5 | 2026-02-24 | 2026-08-25 | 2026-03-02 | 2026-03-02 | 2026-08-31 | 130
| A1-PM-HSD-0038 | S-038-List of Applicable Regulatory Requirements |  | 2026-03-03 |  |  | 5 | 2026-03-03 | 2026-09-01 | 2026-03-09 | 2026-03-09 | 2026-09-07 | 130
| A1-PM-HSD-0040 | S-040-HSEIA Screening/ HSEIA Report/ HSEIA Dossier |  | 2026-04-14 |  |  | 5 | 2026-04-14 | 2026-09-01 | 2026-04-21 | 2026-04-21 | 2026-09-07 | 100
| A1-PM-HSD-0041 | S-041-HSE deliverables as per HSE-RM-ST02 EPC deliverable requirements; not limited to : Building Fire and Safety revie |  | 2026-04-17 |  |  | 5 | 01-Aug-25 A | 2026-09-04 | 2026-04-21 | 2026-04-21 | 2026-09-07 | 100
| HSE Studies |  |  | 2026-02-20 |  |  | 319 | 01-May-25 A | 2026-03-02 | 2026-09-25 | 2026-09-25 | 2027-01-20 | 84
| HAZID/ENVID/OHID |  |  | 2026-02-20 |  |  | 181 | 01-May-25 A | 2026-03-02 | 2026-03-16 | 2026-03-16 | 2026-08-31 | 120
| A58780 | HAZID / ENVID / OHID Workshop |  | 2026-02-20 |  |  | 11 | 01-May-25 A | 2026-03-02 | 10-May-25 A | 2026-02-20 | 2026-03-02
| A60330 | HAZID / ENVID / OHID /_IFR |  | 2026-02-20 |  |  | 11 | 11-May-25 A | 2026-08-07 | 20-May-25 A | 2026-02-20 | 2026-08-07
| A58790 | HAZID / ENVID / OHID /_RCC |  | 2026-02-20 |  |  | 17 | 26-May-25 A | 2026-08-07 | 01-Sep-25 A | 2026-02-20 | 2026-08-07
| A58800 | HAZID / ENVID / OHID /_IFA |  | 2026-02-20 |  |  | 17 | 02-Sep-25 A | 2026-08-07 | 08-Sep-25 A | 2026-02-20 | 2026-08-07
| A58810 | HAZID / ENVID / OHID /_RCA |  | 2026-02-20 |  |  | 17 | 15-Dec-25 A | 2026-08-07 | 22-Dec-25 A | 2026-02-20 | 2026-08-07
| A58820 | HAZID / ENVID / OHID /_IFD/IFC |  | 2026-02-20 |  |  | 17 | 2026-02-20 | 2026-08-07 | 2026-03-16 | 2026-03-16 | 2026-08-31 | 120
| Inherent Safer Design Review |  |  | 2026-02-20 |  |  | 164 | 23-Jul-25 A | 2026-12-04 | 2026-04-08 | 2026-04-08 | 2027-01-20 | 205
| A59430 | Inherent Safer Design Review Preparation |  | 2026-02-20 |  |  | 11 | 23-Jul-25 A | 2026-12-04 | 31-Jul-25 A | 2026-02-20 | 2026-12-04
| A60460 | Inherent Safer Design Review_IFR |  | 2026-02-20 |  |  | 11 | 01-Aug-25 A | 2026-12-04 | 28-Aug-25 A | 2026-02-20 | 2026-12-04
| A59440 | Inherent Safer Design Review_RCC |  | 2026-02-20 |  |  | 17 | 28-Aug-25 A | 2026-12-04 | 04-Sep-25 A | 2026-02-20 | 2026-12-04
| A59450 | Inherent Safer Design Review_IFA |  | 2026-02-20 |  |  | 17 | 05-Sep-25 A | 2026-12-04 | 11-Sep-25 A | 2026-02-20 | 2026-12-04
| A59460 | Inherent Safer Design Review_RCA |  | 2026-02-20 |  |  | 17 | 2026-02-20 | 2026-12-04 | 2026-03-16 | 2026-03-16 | 2026-12-29 | 205
| A59470 | Inherent Safer Design Review_IFD/IFC |  | 2026-03-16 |  |  | 17 | 2026-03-16 | 2026-12-29 | 2026-04-08 | 2026-04-08 | 2027-01-20 | 205
| Bow-tie Development & HSE Critical Equipment & Systems and Performance Standards |  |  | 2026-02-20 |  |  | 164 | 25-Jul-25 A | 2026-03-02 | 2026-04-08 | 2026-04-08 | 2026-08-31 | 103
| A59280 | Bow-tie Development & HSE Critical Equipment & Systems and Performance Standards_Workshop |  | 2026-02-20 |  |  | 11 | 25-Jul-25 A | 2026-03-02 | 31-Jul-25 A | 2026-02-20 | 2026-03-02
| A60430 | Bow-tie Development & HSE Critical Equipment & Systems and Performance Standards_IFR |  | 2026-02-20 |  |  | 11 | 01-Aug-25 A | 2026-07-15 | 25-Aug-25 A | 2026-02-20 | 2026-07-15
| A59290 | Bow-tie Development & HSE Critical Equipment & Systems and Performance Standards_RCC |  | 2026-02-20 |  |  | 17 | 26-Aug-25 A | 2026-07-15 | 04-Sep-25 A | 2026-02-20 | 2026-07-15
| A59300 | Bow-tie Development & HSE Critical Equipment & Systems and Performance Standards_IFA |  | 2026-02-20 |  |  | 17 | 05-Sep-25 A | 2026-07-15 | 11-Sep-25 A | 2026-02-20 | 2026-07-15
| A59310 | Bow-tie Development & HSE Critical Equipment & Systems and Performance Standards_RCA |  | 2026-02-20 |  |  | 17 | 2026-02-20 | 2026-07-15 | 2026-03-16 | 2026-03-16 | 2026-08-07 | 103
| A59320 | Bow-tie Development & HSE Critical Equipment & Systems and Performance Standards_IFD/IFC |  | 2026-03-16 |  |  | 17 | 2026-03-16 | 2026-08-07 | 2026-04-08 | 2026-04-08 | 2026-08-31 | 103
| HSECES and Performance Standards |  |  | 2026-02-20 |  |  | 178 | 23-Jul-25 A | 2026-10-19 | 2026-05-26 | 2026-05-26 | 2027-01-20 | 172
| A61970 | HSE Critical Equipment & Systems and Performance Standards_Preparation |  | 2026-02-20 |  |  | 7 | 23-Jul-25 A | 2026-10-19 | 31-Jul-25 A | 2026-02-20 | 2026-10-19
| A61980 | HSE Critical Equipment & Systems and Performance Standards_IFR |  | 2026-02-20 |  |  | 11 | 01-Aug-25 A | 2026-10-19 | 28-Aug-25 A | 2026-02-20 | 2026-10-19
| A61990 | HSE Critical Equipment & Systems and Performance Standards_RCC |  | 2026-02-20 |  |  | 17 | 2026-02-20 | 2026-10-19 | 2026-03-16 | 2026-03-16 | 2026-11-11 | 172
| A62000 | HSE Critical Equipment & Systems and Performance Standards_IFA |  | 2026-03-16 |  |  | 17 | 2026-03-16 | 2026-11-11 | 2026-04-08 | 2026-04-08 | 2026-12-04 | 172
| A62010 | HSE Critical Equipment & Systems and Performance Standards_RCA |  | 2026-04-08 |  |  | 17 | 2026-04-08 | 2026-12-04 | 2026-05-01 | 2026-05-01 | 2026-12-29 | 172
| A62020 | HSE Critical Equipment & Systems and Performance Standards_IFD/IFC |  | 2026-05-01 |  |  | 17 | 2026-05-01 | 2026-12-29 | 2026-05-26 | 2026-05-26 | 2027-01-20 | 172
| HAZOP |  |  | 2026-02-20 |  |  | 102 | 01-Jul-25 A | 2026-03-25 | 22-Sep-25 A | 2026-02-20 | 2026-04-02
| A62030 | HAZOP_Workshop |  | 2026-02-20 |  |  | 11 | 01-Jul-25 A | 2026-03-25 | 11-Jul-25 A | 2026-02-20 | 2026-03-25
| A62040 | HAZOP_IFR |  | 2026-02-20 |  |  | 11 | 12-Jul-25 A | 2026-04-02 | 25-Aug-25 A | 2026-02-20 | 2026-04-02
| A62050 | HAZOP_RCC |  | 2026-02-20 |  |  | 17 | 26-Aug-25 A | 2026-04-02 | 01-Sep-25 A | 2026-02-20 | 2026-04-02
| A62060 | HAZOP_IFA |  | 2026-02-20 |  |  | 17 | 02-Sep-25 A | 2026-04-02 | 08-Sep-25 A | 2026-02-20 | 2026-04-02
| A62070 | HAZOP_RCA |  | 2026-02-20 |  |  | 17 | 09-Sep-25 A | 2026-04-02 | 15-Sep-25 A | 2026-02-20 | 2026-04-02
| A62080 | HAZOP_IFD/IFC |  | 2026-02-20 |  |  | 17 | 16-Sep-25 A | 2026-04-02 | 22-Sep-25 A | 2026-02-20 | 2026-04-02
| SIL |  |  | 2026-02-20 |  |  | 30 | 15-Aug-25 A | 2026-03-25 | 25-Sep-25 A | 2026-02-20 | 2026-04-02
| A23200 | SIL Review Workshop |  | 2026-02-20 |  |  | 14 | 15-Aug-25 A | 2026-03-25 | 17-Aug-25 A | 2026-02-20 | 2026-03-25
| A60510 | Issue for Company Review |  | 2026-02-20 |  |  | 14 | 18-Aug-25 A | 2026-04-02 | 28-Aug-25 A | 2026-02-20 | 2026-04-02
| A23210 | Issue for Company Approval |  | 2026-02-20 |  |  | 11 | 05-Sep-25 A | 2026-04-02 | 11-Sep-25 A | 2026-02-20 | 2026-04-02
| A23220 | Issue for Construction |  | 2026-02-20 |  |  | 5 | 12-Sep-25 A | 2026-04-02 | 25-Sep-25 A | 2026-02-20 | 2026-04-02
| Fire and Explosion Risk Assessment (FERA) |  |  | 2026-02-20 |  |  | 167 | 01-Aug-25 A | 2026-07-09 | 2026-04-14 | 2026-04-14 | 2026-08-31 | 100
| A59480 | Fire and Explosion Risk Assessment (FERA)_Preparation |  | 2026-02-20 |  |  | 6 | 01-Aug-25 A | 2026-07-09 | 20-Aug-25 A | 2026-02-20 | 2026-07-09
| A60470 | Fire and Explosion Risk Assessment (FERA)_IFR |  | 2026-02-20 |  |  | 28 | 22-Aug-25 A | 2026-07-09 | 31-Oct-25 A | 2026-02-20 | 2026-07-09
| A59490 | Fire and Explosion Risk Assessment (FERA)_RCC |  | 2026-02-20 |  |  | 16 | 2026-02-20 | 2026-07-09 | 2026-03-13 | 2026-03-13 | 2026-07-31 | 100
| A59500 | Fire and Explosion Risk Assessment (FERA)_IFA |  | 2026-03-13 |  |  | 3 | 2026-03-13 | 2026-07-31 | 2026-03-19 | 2026-03-19 | 2026-08-05 | 100
| A59510 | Fire and Explosion Risk Assessment (FERA)_RCA |  | 2026-03-19 |  |  | 16 | 2026-03-19 | 2026-08-06 | 2026-04-09 | 2026-04-09 | 2026-08-27 | 100
| A59520 | Fire and Explosion Risk Assessment (FERA)_IFD/IFC |  | 2026-04-09 |  |  | 2 | 2026-04-09 | 2026-08-27 | 2026-04-14 | 2026-04-14 | 2026-08-31 | 100
| QRA |  |  | 2026-02-20 |  |  | 109 | 07-Jul-25 A | 2026-03-17 | 2026-04-14 | 2026-04-14 | 2026-08-31 | 100
| A60590 | Workshop - QRA |  | 2026-02-20 |  |  | 15 | 07-Jul-25 A | 2026-03-17 | 15-Jul-25 A | 2026-02-20 | 2026-03-17
| A60600 | QRA Report_IFR |  | 2026-02-20 |  |  | 28 | 16-Jul-25 A | 2026-07-09 | 28-Aug-25 A | 2026-02-20 | 2026-07-09
| A60610 | QRA Report_RCC |  | 2026-02-20 |  |  | 16 | 2026-02-20 | 2026-07-09 | 2026-03-13 | 2026-03-13 | 2026-07-31 | 100
| A60620 | QRA Report_IFA |  | 2026-03-13 |  |  | 3 | 2026-03-13 | 2026-07-31 | 2026-03-19 | 2026-03-19 | 2026-08-05 | 100
| A60630 | QRA Report_RCA |  | 2026-03-19 |  |  | 16 | 2026-03-19 | 2026-08-06 | 2026-04-09 | 2026-04-09 | 2026-08-27 | 100
| A60640 | QRA Report_IFD/IFC |  | 2026-04-09 |  |  | 2 | 2026-04-09 | 2026-08-27 | 2026-04-14 | 2026-04-14 | 2026-08-31 | 100
| BRA |  |  | 2026-02-20 |  |  | 113 | 07-Jul-25 A | 2026-11-30 | 2026-04-14 | 2026-04-14 | 2027-01-20 | 202
| A23290 | Workshop - BRA |  | 2026-02-20 |  |  | 15 | 07-Jul-25 A | 2026-11-30 | 15-Jul-25 A | 2026-02-20 | 2026-11-30
| A60540 | BRA Report_IFR |  | 2026-02-20 |  |  | 28 | 16-Jul-25 A | 2026-11-30 | 28-Aug-25 A | 2026-02-20 | 2026-11-30
| A60550 | BRA Report_RCC |  | 2026-02-20 |  |  | 16 | 2026-02-20 | 2026-11-30 | 2026-03-13 | 2026-03-13 | 2026-12-22 | 202
| A60560 | BRA Report_IFA |  | 2026-03-13 |  |  | 3 | 2026-03-13 | 2026-12-22 | 2026-03-19 | 2026-03-19 | 2026-12-25 | 202
| A60570 | BRA Report_RCA |  | 2026-03-19 |  |  | 16 | 2026-03-19 | 2026-12-28 | 2026-04-09 | 2026-04-09 | 2027-01-18 | 202
| A60580 | BRA Report_IFD/IFC |  | 2026-04-09 |  |  | 2 | 2026-04-09 | 2027-01-18 | 2026-04-14 | 2026-04-14 | 2027-01-20 | 202
| Escape Evacuation and Rescue Assessment (EERA) |  |  | 2026-02-20 |  |  | 113 | 01-Aug-25 A | 2026-07-09 | 2026-04-14 | 2026-04-14 | 2026-08-31 | 100
| A59530 | Escape Evacuation and Rescue Assessment (EERA)_Preparation |  | 2026-02-20 |  |  | 6 | 01-Aug-25 A | 2026-07-09 | 15-Aug-25 A | 2026-02-20 | 2026-07-09
| A60480 | Escape Evacuation and Rescue Assessment (EERA)_IFR |  | 2026-02-20 |  |  | 6 | 16-Aug-25 A | 2026-07-09 | 31-Oct-25 A | 2026-02-20 | 2026-07-09
| A59540 | Escape Evacuation and Rescue Assessment (EERA)_RCC |  | 2026-02-20 |  |  | 16 | 2026-02-20 | 2026-07-09 | 2026-03-13 | 2026-03-13 | 2026-07-31 | 100
| A59550 | Escape Evacuation and Rescue Assessment (EERA)_IFA |  | 2026-03-13 |  |  | 3 | 2026-03-13 | 2026-07-31 | 2026-03-19 | 2026-03-19 | 2026-08-05 | 100
| A59560 | Escape Evacuation and Rescue Assessment (EERA)_RCA |  | 2026-03-19 |  |  | 16 | 2026-03-19 | 2026-08-06 | 2026-04-09 | 2026-04-09 | 2026-08-27 | 100
| A59570 | Escape Evacuation and Rescue Assessment (EERA)_IFD/IFC |  | 2026-04-09 |  |  | 2 | 2026-04-09 | 2026-08-27 | 2026-04-14 | 2026-04-14 | 2026-08-31 | 100
| Emergency Systems Survivability Analysis (ESSA) |  |  | 2026-02-20 |  |  | 113 | 01-Aug-25 A | 2026-07-09 | 2026-04-14 | 2026-04-14 | 2026-08-31 | 100
| A60340 | Emergency Systems Survivability Analysis (ESSA)_Preparation |  | 2026-02-20 |  |  | 6 | 01-Aug-25 A | 2026-07-09 | 15-Aug-25 A | 2026-02-20 | 2026-07-09
| A58830 | Emergency Systems Survivability Analysis (ESSA)_IFR |  | 2026-02-20 |  |  | 28 | 18-Aug-25 A | 2026-07-09 | 31-Oct-25 A | 2026-02-20 | 2026-07-09
| A58840 | Emergency Systems Survivability Analysis (ESSA)_RCC |  | 2026-02-20 |  |  | 16 | 2026-02-20 | 2026-07-09 | 2026-03-13 | 2026-03-13 | 2026-07-31 | 100
| A58850 | Emergency Systems Survivability Analysis (ESSA)_IFA |  | 2026-03-13 |  |  | 3 | 2026-03-13 | 2026-07-31 | 2026-03-19 | 2026-03-19 | 2026-08-05 | 100
| A58860 | Emergency Systems Survivability Analysis (ESSA)_RCA |  | 2026-03-19 |  |  | 16 | 2026-03-19 | 2026-08-06 | 2026-04-09 | 2026-04-09 | 2026-08-27 | 100
| A58870 | Emergency Systems Survivability Analysis (ESSA)_IFD/IFC |  | 2026-04-09 |  |  | 2 | 2026-04-09 | 2026-08-27 | 2026-04-14 | 2026-04-14 | 2026-08-31 | 100
| Risk Reduction ALARP Workshop |  |  | 2026-02-20 |  |  | 38 | 28-Jul-25 A | 2026-11-27 | 2026-04-15 | 2026-04-15 | 2027-01-20 | 201
| A59130 | Risk Reduction ALARP Workshop |  | 2026-02-20 |  |  | 6 | 28-Jul-25 A | 2026-11-27 | 07-Aug-25 A | 2026-02-20 | 2026-11-27
| A60400 | Risk Reduction ALARP Workshop Report_IFR |  | 2026-02-20 |  |  | 6 | 2026-02-20 | 2026-11-27 | 2026-02-27 | 2026-02-27 | 2026-12-07 | 201
| A59140 | Risk Reduction ALARP Workshop_Report RCC |  | 2026-02-27 |  |  | 11 | 2026-02-27 | 2026-12-07 | 2026-03-16 | 2026-03-16 | 2026-12-22 | 201
| A59150 | Risk Reduction ALARP Workshop Report_IFA |  | 2026-03-16 |  |  | 3 | 2026-03-16 | 2026-12-22 | 2026-03-20 | 2026-03-20 | 2026-12-25 | 201
| A59160 | Risk Reduction ALARP Workshop Report_RCA |  | 2026-03-20 |  |  | 16 | 2026-03-20 | 2026-12-28 | 2026-04-10 | 2026-04-10 | 2027-01-18 | 201
| A59170 | Risk Reduction ALARP Workshop Report_IFD/IFC |  | 2026-04-13 |  |  | 2 | 2026-04-13 | 2027-01-18 | 2026-04-15 | 2026-04-15 | 2027-01-20 | 201
| Air Emission Dispersion Assessment |  |  | 2026-02-20 |  |  | 167 | 01-Aug-25 A | 2026-07-09 | 2026-04-14 | 2026-04-14 | 2026-08-31 | 100
| A60390 | Air Emission Dispersion Assessment_Preparation |  | 2026-02-20 |  |  | 6 | 01-Aug-25 A | 2026-07-09 | 15-Aug-25 A | 2026-02-20 | 2026-07-09
| A59080 | Air Emission Dispersion Assessment_IFR |  | 2026-02-20 |  |  | 6 | 16-Aug-25 A | 2026-07-09 | 25-Sep-25 A | 2026-02-20 | 2026-07-09
| A59090 | Air Emission Dispersion Assessment_RCC |  | 2026-02-20 |  |  | 16 | 2026-02-20 | 2026-07-09 | 2026-03-13 | 2026-03-13 | 2026-07-31 | 100
| A59100 | Air Emission Dispersion Assessment_IFA |  | 2026-03-13 |  |  | 3 | 2026-03-13 | 2026-07-31 | 2026-03-19 | 2026-03-19 | 2026-08-05 | 100
| A59110 | Air Emission Dispersion Assessment_RCA |  | 2026-03-19 |  |  | 16 | 2026-03-19 | 2026-08-06 | 2026-04-09 | 2026-04-09 | 2026-08-27 | 100
| A59120 | Air Emission Dispersion Assessment_IFD/IFC |  | 2026-04-09 |  |  | 2 | 2026-04-09 | 2026-08-27 | 2026-04-14 | 2026-04-14 | 2026-08-31 | 100
| Noise Study & Contours Report |  |  | 2026-02-20 |  |  | 164 | 01-Aug-25 A | 2026-03-17 | 2026-04-08 | 2026-04-08 | 2026-08-31 | 103
| A62090 | Noise study & control report_Preparation |  | 2026-02-20 |  |  | 6 | 01-Aug-25 A | 2026-03-17 | 15-Aug-25 A | 2026-02-20 | 2026-03-17
| A62100 | Noise study & control report_IFR |  | 2026-02-20 |  |  | 6 | 16-Aug-25 A | 2026-07-15 | 25-Sep-25 A | 2026-02-20 | 2026-07-15
| A62110 | Noise study & control report_RCC |  | 2026-02-20 |  |  | 14 | 2026-02-20 | 2026-07-15 | 2026-03-11 | 2026-03-11 | 2026-08-04 | 103
| A62120 | Noise study & control report_IFA |  | 2026-03-12 |  |  | 3 | 2026-03-12 | 2026-08-04 | 2026-03-17 | 2026-03-17 | 2026-08-07 | 103
| A62130 | Noise study & control report_RCA |  | 2026-03-17 |  |  | 14 | 2026-03-17 | 2026-08-07 | 2026-04-06 | 2026-04-06 | 2026-08-27 | 103
| A62140 | Noise study & control report_IFD/IFC |  | 2026-04-06 |  |  | 2 | 2026-04-06 | 2026-08-27 | 2026-04-08 | 2026-04-08 | 2026-08-31 | 103
| Best Available Techniques Study (BAT) |  |  | 2026-02-20 |  |  | 86 | 01-Aug-25 A | 2026-03-17 | 2026-03-23 | 2026-03-23 | 2026-08-31 | 116
| A60360 | Best Available Techniques Study_Workshop |  | 2026-02-20 |  |  | 6 | 01-Aug-25 A | 2026-03-17 | 20-Aug-25 A | 2026-02-20 | 2026-03-17
| A58940 | Best Available Techniques Study_RCC |  | 2026-02-20 |  |  | 16 | 21-Aug-25 A | 2026-03-27 | 29-Aug-25 A | 2026-02-20 | 2026-03-27
| A58930 | Best Available Techniques Study_IFR |  | 2026-02-20 |  |  | 6 | 21-Aug-25 A | 2026-03-17 | 18-Sep-25 A | 2026-02-20 | 2026-03-17
| A58950 | Best Available Techniques Study_IFA |  | 2026-02-20 |  |  | 3 | 2026-02-20 | 2026-07-31 | 2026-02-25 | 2026-02-25 | 2026-08-05 | 116
| A58960 | Best Available Techniques Study_RCA |  | 2026-02-25 |  |  | 16 | 2026-02-25 | 2026-08-06 | 2026-03-19 | 2026-03-19 | 2026-08-27 | 116
| A58970 | Best Available Techniques Study_IFD/IFC |  | 2026-03-19 |  |  | 2 | 2026-03-19 | 2026-08-27 | 2026-03-23 | 2026-03-23 | 2026-08-31 | 116
| Energy Review Workshop & Report |  |  | 2026-02-20 |  |  | 97 | 01-Sep-25 A | 2026-03-27 | 2026-04-21 | 2026-04-21 | 2027-01-20 | 196
| A59380 | Energy Review Workshop |  | 2026-02-20 |  |  | 6 | 01-Sep-25 A | 2026-03-27 | 19-Sep-25 A | 2026-02-20 | 2026-03-27
| A60450 | Energy Review Workshop & Report_IFR |  | 2026-02-20 |  |  | 6 | 2026-02-20 | 2026-11-23 | 2026-02-27 | 2026-02-27 | 2026-11-30 | 196
| A59390 | Energy Review Workshop & Report_RCC |  | 2026-02-27 |  |  | 16 | 2026-02-27 | 2026-11-30 | 2026-03-23 | 2026-03-23 | 2026-12-22 | 196
| A59400 | Energy Review Workshop & Report_IFA |  | 2026-03-23 |  |  | 3 | 2026-03-23 | 2026-12-22 | 2026-03-26 | 2026-03-26 | 2026-12-25 | 196
| A59410 | Energy Review Workshop & Report_RCA |  | 2026-03-26 |  |  | 16 | 2026-03-26 | 2026-12-28 | 2026-04-17 | 2026-04-17 | 2027-01-18 | 196
| A59420 | Energy Review Workshop & Report_IFD/IFC |  | 2026-04-17 |  |  | 2 | 2026-04-17 | 2027-01-18 | 2026-04-21 | 2026-04-21 | 2027-01-20 | 196
| Vent & Flare Dispersion and Radiation Study |  |  | 2026-02-20 |  |  | 102 | 01-Oct-25 A | 2026-03-27 | 2026-04-14 | 2026-04-14 | 2027-01-20 | 202
| A59630 | Vent & Flare Dispersion and Radiation Study Preparation ---- |  | 2026-02-20 |  |  | 6 | 01-Oct-25 A | 2026-03-27 | 15-Oct-25 A | 2026-02-20 | 2026-03-27
| A60500 | Vent & Flare Dispersion and Radiation Study_IFR |  | 2026-02-20 |  |  | 6 | 16-Oct-25 A | 2026-03-27 | 31-Oct-25 A | 2026-02-20 | 2026-03-27
| A59640 | Vent & Flare Dispersion and Radiation Study_RCC |  | 2026-02-20 |  |  | 16 | 2026-02-20 | 2026-11-30 | 2026-03-13 | 2026-03-13 | 2026-12-22 | 202
| A59650 | Vent & Flare Dispersion and Radiation Study_IFA |  | 2026-03-13 |  |  | 3 | 2026-03-13 | 2026-12-22 | 2026-03-19 | 2026-03-19 | 2026-12-25 | 202
| A59660 | Vent & Flare Dispersion and Radiation Study_RCA |  | 2026-03-19 |  |  | 16 | 2026-03-19 | 2026-12-28 | 2026-04-09 | 2026-04-09 | 2027-01-18 | 202
| A59670 | Vent & Flare Dispersion and Radiation Study_IFD/IFC |  | 2026-04-09 |  |  | 2 | 2026-04-09 | 2027-01-18 | 2026-04-14 | 2026-04-14 | 2027-01-20 | 202
| Environment Impact Assessment |  |  | 2026-02-20 |  |  | 75 | 28-Aug-25 A | 2026-07-15 | 2026-04-08 | 2026-04-08 | 2026-08-31 | 103
| A60380 | Environment Impact Assessment_Workshop ---- |  | 2026-02-20 |  |  | 6 | 28-Aug-25 A | 2026-07-15 | 05-Sep-25 A | 2026-02-20 | 2026-07-15
| A59030 | Environment Impact Assessment_IFR |  | 2026-02-20 |  |  | 6 | 06-Sep-25 A | 2026-07-15 | 18-Sep-25 A | 2026-02-20 | 2026-07-15
| A59040 | Environment Impact Assessment_RCC |  | 2026-02-20 |  |  | 14 | 2026-02-20 | 2026-07-15 | 2026-03-11 | 2026-03-11 | 2026-08-04 | 103
| A59050 | Environment Impact Assessment_IFA |  | 2026-03-12 |  |  | 3 | 2026-03-12 | 2026-08-04 | 2026-03-17 | 2026-03-17 | 2026-08-07 | 103
| A59060 | Environment Impact Assessment_RCA |  | 2026-03-17 |  |  | 14 | 2026-03-17 | 2026-08-07 | 2026-04-06 | 2026-04-06 | 2026-08-27 | 103
| A59070 | Environment Impact Assessment_IFD/IFC |  | 2026-04-06 |  |  | 2 | 2026-04-06 | 2026-08-27 | 2026-04-08 | 2026-04-08 | 2026-08-31 | 103
| Ergonomics and Human Factor Engineering Study |  |  | 2026-02-20 |  |  | 112 | 25-Aug-25 A | 2026-09-11 | 2026-07-01 | 2026-07-01 | 2027-01-20 | 146
| A60320 | Ergonomics and Human Factor Engineering Study Workshop |  | 2026-02-20 |  |  | 5 | 25-Aug-25 A | 2026-09-11 | 01-Sep-25 A | 2026-02-20 | 2026-09-11
| A58730 | Ergonomics and Human Factor Engineering Study_IFR |  | 2026-02-20 |  |  | 6 | 2026-02-20 | 2026-09-11 | 2026-02-27 | 2026-02-27 | 2026-09-21 | 146
| A58740 | Ergonomics and Human Factor Engineering Study_RCC |  | 2026-02-27 |  |  | 24 | 2026-02-27 | 2026-09-21 | 2026-04-02 | 2026-04-02 | 2026-10-22 | 146
| A58750 | Ergonomics and Human Factor Engineering Study_IFA |  | 2026-04-02 |  |  | 24 | 2026-04-02 | 2026-10-22 | 2026-05-05 | 2026-05-05 | 2026-11-25 | 146
| A58760 | Ergonomics and Human Factor Engineering Study_RCA |  | 2026-05-05 |  |  | 24 | 2026-05-05 | 2026-11-25 | 2026-06-08 | 2026-06-08 | 2026-12-29 | 146
| A58770 | Ergonomics and Human Factor Engineering Study_IFD/IFC |  | 2026-06-08 |  |  | 17 | 2026-06-08 | 2026-12-29 | 2026-07-01 | 2026-07-01 | 2027-01-20 | 146
| Dropped Objects Study (DOS) |  |  | 2026-02-20 |  |  | 63 | 2026-02-20 | 2026-10-26 | 2026-05-19 | 2026-05-19 | 2027-01-20 | 176
| A60350 | Dropped Objects Study (DOS)_Workshop |  | 2026-02-20 |  |  | 6 | 2026-02-20 | 2026-10-26 | 2026-02-27 | 2026-02-27 | 2026-11-02 | 176
| A58880 | Dropped Objects Study (DOS)_IFR |  | 2026-02-27 |  |  | 20 | 2026-02-27 | 2026-11-02 | 2026-03-27 | 2026-03-27 | 2026-11-30 | 176
| A58890 | Dropped Objects Study (DOS)_RCC |  | 2026-03-27 |  |  | 16 | 2026-03-27 | 2026-11-30 | 2026-04-20 | 2026-04-20 | 2026-12-22 | 176
| A58900 | Dropped Objects Study (DOS)_IFA |  | 2026-04-20 |  |  | 3 | 2026-04-20 | 2026-12-22 | 2026-04-23 | 2026-04-23 | 2026-12-25 | 176
| A58910 | Dropped Objects Study (DOS)_RCA |  | 2026-04-24 |  |  | 16 | 2026-04-24 | 2026-12-28 | 2026-05-15 | 2026-05-15 | 2027-01-18 | 176
| A58920 | Dropped Objects Study (DOS)_IFD/IFC |  | 2026-05-15 |  |  | 2 | 2026-05-15 | 2027-01-18 | 2026-05-19 | 2026-05-19 | 2027-01-20 | 176
| 3D F&G mapping study |  |  | 2026-02-20 |  |  | 48 | 2026-02-20 | 2026-11-13 | 2026-04-29 | 2026-04-29 | 2027-01-20 | 191
| A60370 | 3D F&G mapping study_Preparation |  | 2026-02-20 |  |  | 6 | 2026-02-20 | 2026-11-13 | 2026-02-27 | 2026-02-27 | 2026-11-23 | 191
| A58980 | 3D F&G mapping study_IFR |  | 2026-02-27 |  |  | 6 | 2026-02-27 | 2026-11-23 | 2026-03-09 | 2026-03-09 | 2026-11-30 | 191
| A58990 | 3D F&G mapping study_RCC |  | 2026-03-09 |  |  | 16 | 2026-03-09 | 2026-11-30 | 2026-03-30 | 2026-03-30 | 2026-12-22 | 191
| A59000 | 3D F&G mapping study_IFA |  | 2026-03-31 |  |  | 3 | 2026-03-31 | 2026-12-22 | 2026-04-03 | 2026-04-03 | 2026-12-25 | 191
| A59010 | 3D F&G mapping study_RCA |  | 2026-04-03 |  |  | 16 | 2026-04-03 | 2026-12-28 | 2026-04-27 | 2026-04-27 | 2027-01-18 | 191
| A59020 | 3D F&G mapping study_IFD/IFC |  | 2026-04-27 |  |  | 2 | 2026-04-27 | 2027-01-18 | 2026-04-29 | 2026-04-29 | 2027-01-20 | 191
| E-HAZOP |  |  | 2026-02-20 |  |  | 102 | 25-Aug-25 A | 2026-03-17 | 2026-04-21 | 2026-04-21 | 2027-01-20 | 196
| A62150 | E-HAZOP_Workshop |  | 2026-02-20 |  |  | 3 | 25-Aug-25 A | 2026-03-17 | 01-Sep-25 A | 2026-02-20 | 2026-03-17
| A62160 | E-HAZOP_IFR |  | 2026-02-20 |  |  | 6 | 2026-02-20 | 2026-11-23 | 2026-02-27 | 2026-02-27 | 2026-11-30 | 196
| A62170 | E-HAZOP_RCC |  | 2026-02-27 |  |  | 16 | 2026-02-27 | 2026-11-30 | 2026-03-23 | 2026-03-23 | 2026-12-22 | 196
| A62180 | E-HAZOP_IFA |  | 2026-03-23 |  |  | 3 | 2026-03-23 | 2026-12-22 | 2026-03-26 | 2026-03-26 | 2026-12-25 | 196
| A62190 | E-HAZOP_RCA |  | 2026-03-26 |  |  | 16 | 2026-03-26 | 2026-12-28 | 2026-04-17 | 2026-04-17 | 2027-01-18 | 196
| A62200 | E-HAZOP_IFD/IFC |  | 2026-04-17 |  |  | 2 | 2026-04-17 | 2027-01-18 | 2026-04-21 | 2026-04-21 | 2027-01-20 | 196
| Constructability Review |  |  | 2026-02-20 |  |  | 146 | 27-Aug-25 A | 2026-12-22 | 2026-03-23 | 2026-03-23 | 2027-01-20 | 218
| A59180 | Constructability Review Workshop |  | 2026-02-20 |  |  | 6 | 27-Aug-25 A | 2026-12-22 | 27-Aug-25 A | 2026-02-20 | 2026-12-22
| A60410 | Constructability Review_IFR |  | 2026-02-20 |  |  | 6 | 17-Nov-25 A | 2026-12-22 | 30-Nov-25 A | 2026-02-20 | 2026-12-22
| A59190 | Constructability Review_RCC |  | 2026-02-20 |  |  | 16 | 01-Dec-25 A | 2026-12-22 | 10-Dec-25 A | 2026-02-20 | 2026-12-22
| A59200 | Constructability Review_IFA |  | 2026-02-20 |  |  | 3 | 2026-02-20 | 2026-12-22 | 2026-02-25 | 2026-02-25 | 2026-12-25 | 218
| A59210 | Constructability Review_RCA |  | 2026-02-25 |  |  | 16 | 2026-02-25 | 2026-12-28 | 2026-03-19 | 2026-03-19 | 2027-01-18 | 218
| A59220 | Constructability Review_IFD/IFC |  | 2026-03-19 |  |  | 2 | 2026-03-19 | 2027-01-18 | 2026-03-23 | 2026-03-23 | 2027-01-20 | 218
| SIMPOS |  |  | 2026-02-20 |  |  | 170 | 25-Aug-25 A | 2026-12-22 | 2026-03-23 | 2026-03-23 | 2027-01-20 | 218
| A59680 | SIMOPS Workshop |  | 2026-02-20 |  |  | 6 | 25-Aug-25 A | 2026-12-22 | 28-Aug-25 A | 2026-02-20 | 2026-12-22
| A60520 | SIMOPS Report_IFR |  | 2026-02-20 |  |  | 6 | 11-Nov-25 A | 2026-12-22 | 30-Nov-25 A | 2026-02-20 | 2026-12-22
| A59690 | SIMOPS Report_RCC |  | 2026-02-20 |  |  | 16 | 08-Dec-25 A | 2026-12-22 | 16-Dec-25 A | 2026-02-20 | 2026-12-22
| A59700 | SIMOPS Report_IFA |  | 2026-02-20 |  |  | 3 | 2026-02-20 | 2026-12-22 | 2026-02-25 | 2026-02-25 | 2026-12-25 | 218
| A59710 | SIMOPS Report_RCA |  | 2026-02-25 |  |  | 16 | 2026-02-25 | 2026-12-28 | 2026-03-19 | 2026-03-19 | 2027-01-18 | 218
| A59720 | SIMOPS Report_IFD/IFC |  | 2026-03-19 |  |  | 2 | 2026-03-19 | 2027-01-18 | 2026-03-23 | 2026-03-23 | 2027-01-20 | 218
| HSEIA |  |  | 2026-02-20 |  |  | 44 | 24-Dec-25 A | 2026-04-02 | 2026-03-26 | 2026-03-26 | 2027-01-20 | 214
| A61370 | HSEIA Report Preparation |  | 2026-02-20 |  |  | 6 | 24-Dec-25 A | 2026-04-02 | 31-Dec-25 A | 2026-02-20 | 2026-04-02
| A61380 | HSEIA Report_IFR |  | 2026-02-20 |  |  | 6 | 01-Jan-26 A | 2026-04-02 | 06-Jan-26 A | 2026-02-20 | 2026-04-02
| A61390 | HSEIA Report_RCC |  | 2026-02-20 |  |  | 16 | 07-Jan-26 A | 2026-12-29 | 23-Jan-26 A | 2026-02-20 | 2026-12-29
| A62500 | Assesemnt on new requirements by COMPANY |  | 2026-02-20 |  |  | 21 | 13-Feb-26 A | 2026-12-29 | 2026-02-27 | 2026-02-27 | 2027-01-06 | 210
| A61400 | HSEIA Report_IFA |  | 2026-03-02 |  |  | 3 | 2026-03-02 | 2027-01-06 | 2026-03-05 | 2026-03-05 | 2027-01-11 | 222
| A61410 | HSEIA Report_RCA |  | 2026-03-05 |  |  | 5 | 2026-03-05 | 2027-01-11 | 2026-03-12 | 2026-03-12 | 2027-01-18 | 222
| A61420 | HSEIA Report_IFD/IFC |  | 2026-03-12 |  |  | 2 | 2026-03-12 | 2027-01-18 | 2026-03-16 | 2026-03-16 | 2027-01-20 | 222
| A61840 | HSEIA Report ADNOC Approval |  | 2026-02-20 |  |  | 25 | 2026-02-20 | 2026-04-02 | 2026-03-26 | 2026-03-26 | 2026-05-06 | 29
| PHSER III |  |  | 2026-03-06 |  |  | 48 | 2026-03-06 | 2026-07-01 | 2026-05-13 | 2026-05-13 | 2026-09-08 | 84
| A59330 | PHSER III_Workshop |  | 2026-03-06 |  |  | 6 | 2026-03-06 | 2026-07-01 | 2026-03-13 | 2026-03-13 | 2026-07-09 | 84
| A60440 | PHSER III_IFR |  | 2026-03-13 |  |  | 6 | 2026-03-13 | 2026-07-09 | 2026-03-23 | 2026-03-23 | 2026-07-17 | 84
| A59340 | PHSER III_RCC |  | 2026-03-23 |  |  | 16 | 2026-03-23 | 2026-07-17 | 2026-04-14 | 2026-04-14 | 2026-08-07 | 84
| A59350 | PHSER III_IFA |  | 2026-04-14 |  |  | 3 | 2026-04-14 | 2026-08-07 | 2026-04-17 | 2026-04-17 | 2026-08-13 | 84
| A59360 | PHSER III_RCA |  | 2026-04-17 |  |  | 16 | 2026-04-17 | 2026-08-13 | 2026-05-11 | 2026-05-11 | 2026-09-03 | 84
| A59370 | PHSER III_IFD/IFC |  | 2026-05-11 |  |  | 2 | 2026-05-11 | 2026-09-04 | 2026-05-13 | 2026-05-13 | 2026-09-08 | 84
| PHSER IV |  |  | 2026-05-13 |  |  | 48 | 2026-05-13 | 2026-09-08 | 2026-07-20 | 2026-07-20 | 2026-11-13 | 84
| A61850 | PHSER IV_Workshop |  | 2026-05-13 |  |  | 6 | 2026-05-13 | 2026-09-08 | 2026-05-21 | 2026-05-21 | 2026-09-15 | 84
| A61900 | PHSER IV_IFR |  | 2026-05-21 |  |  | 6 | 2026-05-21 | 2026-09-15 | 2026-05-28 | 2026-05-28 | 2026-09-23 | 84
| A61860 | PHSER IV_RCC |  | 2026-05-28 |  |  | 16 | 2026-05-28 | 2026-09-23 | 2026-06-19 | 2026-06-19 | 2026-10-15 | 84
| A61870 | PHSER IV_IFA |  | 2026-06-19 |  |  | 3 | 2026-06-19 | 2026-10-15 | 2026-06-24 | 2026-06-24 | 2026-10-20 | 84
| A61880 | PHSER IV_RCA |  | 2026-06-24 |  |  | 16 | 2026-06-24 | 2026-10-20 | 2026-07-16 | 2026-07-16 | 2026-11-11 | 84
| A61890 | PHSER IV_IFD/IFC |  | 2026-07-16 |  |  | 2 | 2026-07-16 | 2026-11-11 | 2026-07-20 | 2026-07-20 | 2026-11-13 | 84
| PHSER V |  |  | 2026-07-20 |  |  | 48 | 2026-07-20 | 2026-11-13 | 2026-09-25 | 2026-09-25 | 2027-01-20 | 84
| A61910 | PHSER V_Workshop |  | 2026-07-20 |  |  | 6 | 2026-07-20 | 2026-11-13 | 2026-07-28 | 2026-07-28 | 2026-11-23 | 84
| A61960 | PHSER V_IFR |  | 2026-07-28 |  |  | 6 | 2026-07-28 | 2026-11-23 | 2026-08-05 | 2026-08-05 | 2026-11-30 | 84
| A61920 | PHSER V_RCC |  | 2026-08-05 |  |  | 16 | 2026-08-05 | 2026-11-30 | 2026-08-26 | 2026-08-26 | 2026-12-22 | 84
| A61930 | PHSER V_FA |  | 2026-08-26 |  |  | 3 | 2026-08-26 | 2026-12-22 | 2026-09-01 | 2026-09-01 | 2026-12-25 | 84
| A61940 | PHSER V_RCA |  | 2026-09-01 |  |  | 16 | 2026-09-01 | 2026-12-28 | 2026-09-22 | 2026-09-22 | 2027-01-18 | 84
| A61950 | PHSER V_IFD/IFC |  | 2026-09-23 |  |  | 2 | 2026-09-23 | 2027-01-18 | 2026-09-25 | 2026-09-25 | 2027-01-20 | 84
| QA/QC Management |  |  | 2026-02-20 |  |  | 400 | 12-May-25 A | 2026-03-20 | 2026-06-11 | 2026-06-11 | 2027-07-20 | 288
| QAQC Deliverables |  |  | 2026-02-20 |  |  | 275 | 25-May-25 A | 2026-03-20 | 2026-06-11 | 2026-06-11 | 2027-04-21 | 224
| A1-PM-QCD-0011 | PCQ-011-Site Contractors Quality Plans |  | 2026-02-20 |  |  | 5 | 25-May-25 A | 2026-03-27 | 03-Sep-25 A | 2026-02-20 | 2026-03-27
| A1-PM-QCD-0012 | PCQ-012-Worksite Quality Plan |  | 2026-02-20 |  |  | 5 | 03-Sep-25 A | 2026-11-06 | 15-Sep-25 A | 2026-02-20 | 2026-11-06
| A1-PM-QCD-0001 | PCQ-001-Inspection Record |  | 2026-02-20 |  |  | 5 | 08-Aug-25 A | 2026-03-20 | 2026-02-26 | 2026-02-26 | 2026-03-27 | 20
| A1-PM-QCD-0002 | PCQ-002-Inspection Check List |  | 2026-03-03 |  |  | 5 | 08-Aug-25 A | 2027-01-11 | 2026-03-09 | 2026-03-09 | 2027-01-15 | 224
| A1-PM-QCD-0003 | PCQ-003-Test Certificate |  | 2026-03-12 |  |  | 5 | 14-Aug-25 A | 2027-01-20 | 2026-03-18 | 2026-03-18 | 2027-01-26 | 224
| A1-PM-QCD-0004 | PCQ-004-Inspection and Test Plan Vendor |  | 2026-03-23 |  |  | 5 | 14-Aug-25 A | 2027-01-29 | 2026-03-27 | 2026-03-27 | 2027-02-04 | 224
| A1-PM-QCD-0005 | PCQ-005-Inspection and Test Plan Site |  | 2026-04-07 |  |  | 5 | 16-Jun-25 A | 2027-02-15 | 2026-04-07 | 2026-04-07 | 2027-02-15 | 224
| A1-PM-QCD-0006 | PCQ-006-Inspection and Test Plan |  | 2026-04-16 |  |  | 5 | 16-Jun-25 A | 2027-02-24 | 2026-04-16 | 2026-04-16 | 2027-02-24 | 224
| A1-PM-QCD-0007 | PCQ-007-Quality Assurance Docs |  | 2026-04-27 |  |  | 5 | 15-Aug-25 A | 2027-03-05 | 2026-04-27 | 2026-04-27 | 2027-03-05 | 224
| A1-PM-QCD-0008 | PCQ-008-Inspection Guidelines (Source and Field) |  | 2026-05-06 |  |  | 5 | 15-Aug-25 A | 2027-03-16 | 2026-05-06 | 2026-05-06 | 2027-03-16 | 224
| A1-PM-QCD-0009 | PCQ-009-Inspection / Expediting / Reports |  | 2026-05-15 |  |  | 5 | 15-Aug-25 A | 2027-03-25 | 2026-05-15 | 2026-05-15 | 2027-03-25 | 224
| A1-PM-QCD-0010 | PCQ-010-Vendor Shop Inspection & Quality Control Plans |  | 2026-05-26 |  |  | 5 | 18-Aug-25 A | 2027-04-05 | 2026-05-26 | 2026-05-26 | 2027-04-05 | 224
| A1-PM-QCD-0013 | PCQ-013-Inspection Plan and Schedule |  | 2026-06-04 |  |  | 5 | 15-Aug-25 A | 2027-04-14 | 2026-06-04 | 2026-06-04 | 2027-04-14 | 224
| A1-PM-QCD-0014 | PCQ-014-Inspection Release Report |  | 2026-06-05 |  |  | 5 | 2026-06-05 | 2027-04-15 | 2026-06-11 | 2026-06-11 | 2027-04-21 | 224
| QAQC Audit Plan |  |  | 2026-02-20 |  |  | 380 | 12-May-25 A | 2027-07-20 | 25-May-25 A | 2026-02-20 | 2027-07-20
| A1-PM-QAP-0001 | QAQC Audit Plan |  | 2026-02-20 |  |  | 380 | 12-May-25 A | 2027-07-20 | 25-May-25 A | 2026-02-20 | 2027-07-20
| Contractor's Temporary Facilities | [5 empty] | 0 | 20-Jan-25 A |  | 20-Jan-25 A
| Home Office | [5 empty] | 0 | 20-Jan-25 A |  | 20-Jan-25 A
| A1-PM-CTF-0001 | Home Office Ready for IPMT Moblization |  |  |  |  | 0 |  |  | 20-Jan-25 A
| Others |  |  | 2026-02-20 |  |  | 672 | 20-Dec-24 A | 2026-03-27 | 2027-07-20 | 2027-07-20 | 2027-07-20 | 0
| Project Key Milestones |  |  | 2026-02-20 |  |  | 739 | 12-Apr-25 A | 2026-03-27 | 2027-07-20 | 2027-07-20 | 2027-07-20 | 0
| A1-PM-PKM-0001 | Turnaround Scope Completion (TA) |  | 2026-02-20 |  |  | 47 | 12-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A1-PM-PKM-0002 | Mechanical Completion (MC) |  |  |  |  | 0 |  |  | 2027-01-20 | 2027-01-20 | 2027-01-20 | 0
| A1-PM-PKM-0003 | Ready for Start-up (RFSU) |  |  |  |  | 0 |  |  | 2027-04-21 | 2027-04-21 | 2027-04-21 | 0
| A1-PM-PKM-0004 | Provisional Acceptance Certificate (PAC) |  |  |  |  | 0 |  |  | 2027-07-20 | 2027-07-20 | 2027-07-20 | 0
| Weekly Progress Report |  |  | 2026-02-20 |  |  | 558 | 03-Jan-25 A | 2026-07-16 | 2027-02-24 | 2027-02-24 | 2027-07-20 | 105
| A1-PM-WPR-0001 | Weekly Progress Report Issuance - WPR0001 |  |  |  |  | 0 |  |  | 03-Jan-25 A
| A1-PM-WPR-0002 | Weekly Progress Report Issuance - WPR0002 |  |  |  |  | 0 |  |  | 10-Jan-25 A
| A1-PM-WPR-0003 | Weekly Progress Report Issuance - WPR0003 |  |  |  |  | 0 |  |  | 17-Jan-25 A
| A1-PM-WPR-0004 | Weekly Progress Report Issuance - WPR0004 |  |  |  |  | 0 |  |  | 24-Jan-25 A
| A1-PM-WPR-0005 | Weekly Progress Report Issuance - WPR0005 |  |  |  |  | 0 |  |  | 31-Jan-25 A
| A1-PM-WPR-0006 | Weekly Progress Report Issuance - WPR0006 |  |  |  |  | 0 |  |  | 07-Feb-25 A
| A1-PM-WPR-0007 | Weekly Progress Report Issuance - WPR0007 |  |  |  |  | 0 |  |  | 14-Feb-25 A
| A1-PM-WPR-0008 | Weekly Progress Report Issuance - WPR0008 |  |  |  |  | 0 |  |  | 21-Feb-25 A
| A1-PM-WPR-0009 | Weekly Progress Report Issuance - WPR0009 |  |  |  |  | 0 |  |  | 28-Feb-25 A
| A1-PM-WPR-0016 | Weekly Progress Report Issuance - WPR0016 |  |  |  |  | 0 |  |  | 18-Apr-25 A
| A1-PM-WPR-0010 | Weekly Progress Report Issuance - WPR0010 |  |  |  |  | 0 |  |  | 06-May-25 A
| A1-PM-WPR-0011 | Weekly Progress Report Issuance - WPR0011 |  |  |  |  | 0 |  |  | 06-May-25 A
| A1-PM-WPR-0012 | Weekly Progress Report Issuance - WPR0012 |  |  |  |  | 0 |  |  | 06-May-25 A
| A1-PM-WPR-0013 | Weekly Progress Report Issuance - WPR0013 |  |  |  |  | 0 |  |  | 06-May-25 A
| A1-PM-WPR-0014 | Weekly Progress Report Issuance - WPR0014 |  |  |  |  | 0 |  |  | 06-May-25 A
| A1-PM-WPR-0015 | Weekly Progress Report Issuance - WPR0015 |  |  |  |  | 0 |  |  | 06-May-25 A
| A1-PM-WPR-0017 | Weekly Progress Report Issuance - WPR0017 |  |  |  |  | 0 |  |  | 09-May-25 A
| A1-PM-WPR-0018 | Weekly Progress Report Issuance - WPR0018 |  |  |  |  | 0 |  |  | 09-May-25 A
| A1-PM-WPR-0019 | Weekly Progress Report Issuance - WPR0019 |  |  |  |  | 0 |  |  | 13-May-25 A
| A1-PM-WPR-0020 | Weekly Progress Report Issuance - WPR0020 |  |  |  |  | 0 |  |  | 21-May-25 A
| A1-PM-WPR-0021 | Weekly Progress Report Issuance - WPR0021 |  |  |  |  | 0 |  |  | 28-May-25 A
| A1-PM-WPR-0023 | Weekly Progress Report Issuance - WPR0023 |  |  |  |  | 0 |  |  | 06-Jun-25 A
| A1-PM-WPR-0022 | Weekly Progress Report Issuance - WPR0022 |  |  |  |  | 0 |  |  | 08-Jun-25 A
| A1-PM-WPR-0024 | Weekly Progress Report Issuance - WPR0024 |  |  |  |  | 0 |  |  | 13-Jun-25 A
| A1-PM-WPR-0025 | Weekly Progress Report Issuance - WPR0025 |  |  |  |  | 0 |  |  | 21-Jun-25 A
| A1-PM-WPR-0026 | Weekly Progress Report Issuance - WPR0026 |  |  |  |  | 0 |  |  | 30-Jun-25 A
| A1-PM-WPR-0027 | Weekly Progress Report Issuance - WPR0027 |  |  |  |  | 0 |  |  | 10-Jul-25 A
| A1-PM-WPR-0028 | Weekly Progress Report Issuance - WPR0028 |  |  |  |  | 0 |  |  | 18-Jul-25 A
| A1-PM-WPR-0029 | Weekly Progress Report Issuance - WPR0029 |  |  |  |  | 0 |  |  | 22-Aug-25 A
| A1-PM-WPR-0034 | Weekly Progress Report Issuance - WPR0034 |  |  |  |  | 0 |  |  | 27-Aug-25 A
| A1-PM-WPR-0030 | Weekly Progress Report Issuance - WPR0030 |  |  |  |  | 0 |  |  | 27-Aug-25 A
| A1-PM-WPR-0031 | Weekly Progress Report Issuance - WPR0031 |  |  |  |  | 0 |  |  | 02-Sep-25 A
| A1-PM-WPR-0032 | Weekly Progress Report Issuance - WPR0032 |  |  |  |  | 0 |  |  | 07-Sep-25 A
| A1-PM-WPR-0037 | Weekly Progress Report Issuance - WPR0037 |  |  |  |  | 0 |  |  | 12-Sep-25 A
| A1-PM-WPR-0033 | Weekly Progress Report Issuance - WPR0033 |  |  |  |  | 0 |  |  | 13-Sep-25 A
| A1-PM-WPR-0035 | Weekly Progress Report Issuance - WPR0035 |  |  |  |  | 0 |  |  | 15-Sep-25 A
| A1-PM-WPR-0036 | Weekly Progress Report Issuance - WPR0036 |  |  |  |  | 0 |  |  | 15-Sep-25 A
| A1-PM-WPR-0038 | Weekly Progress Report Issuance - WPR0038 |  |  |  |  | 0 |  |  | 19-Sep-25 A
| A1-PM-WPR-0039 | Weekly Progress Report Issuance - WPR0039 |  |  |  |  | 0 |  |  | 03-Oct-25 A
| A1-PM-WPR-0040 | Weekly Progress Report Issuance - WPR0040 |  |  |  |  | 0 |  |  | 10-Oct-25 A
| A1-PM-WPR-0041 | Weekly Progress Report Issuance - WPR0041 |  |  |  |  | 0 |  |  | 17-Oct-25 A
| A1-PM-WPR-0042 | Weekly Progress Report Issuance - WPR0042 |  |  |  |  | 0 |  |  | 24-Oct-25 A
| A1-PM-WPR-0043 | Weekly Progress Report Issuance - WPR0043 |  |  |  |  | 0 |  |  | 30-Oct-25 A
| A1-PM-WPR-0044 | Weekly Progress Report Issuance - WPR0044 |  |  |  |  | 0 |  |  | 04-Nov-25 A
| A1-PM-WPR-0045 | Weekly Progress Report Issuance - WPR0045 |  |  |  |  | 0 |  |  | 12-Nov-25 A
| A1-PM-WPR-0046 | Weekly Progress Report Issuance - WPR0046 |  |  |  |  | 0 |  |  | 18-Nov-25 A
| A1-PM-WPR-0047 | Weekly Progress Report Issuance - WPR0047 |  |  |  |  | 0 |  |  | 2026-02-20 | 2026-02-20 | 2026-07-16 | 183
| A1-PM-WPR-0048 | Weekly Progress Report Issuance - WPR0048 |  |  |  |  | 0 |  |  | 2026-02-25 | 2026-02-25 | 2026-07-21 | 183
| A1-PM-WPR-0049 | Weekly Progress Report Issuance - WPR0049 |  |  |  |  | 0 |  |  | 2026-03-03 | 2026-03-03 | 2026-07-27 | 183
| A1-PM-WPR-0050 | Weekly Progress Report Issuance - WPR0050 |  |  |  |  | 0 |  |  | 2026-03-08 | 2026-03-08 | 2026-08-02 | 183
| A1-PM-WPR-0051 | Weekly Progress Report Issuance - WPR0051 |  |  |  |  | 0 |  |  | 2026-03-14 | 2026-03-14 | 2026-08-07 | 183
| A1-PM-WPR-0052 | Weekly Progress Report Issuance - WPR0052 |  |  |  |  | 0 |  |  | 2026-03-19 | 2026-03-19 | 2026-08-13 | 183
| A1-PM-WPR-0053 | Weekly Progress Report Issuance - WPR0053 |  |  |  |  | 0 |  |  | 2026-03-25 | 2026-03-25 | 2026-08-18 | 183
| A1-PM-WPR-0054 | Weekly Progress Report Issuance - WPR0054 |  |  |  |  | 0 |  |  | 2026-03-31 | 2026-03-31 | 2026-08-24 | 183
| A1-PM-WPR-0055 | Weekly Progress Report Issuance - WPR0055 |  |  |  |  | 0 |  |  | 2026-04-05 | 2026-04-05 | 2026-08-30 | 183
| A1-PM-WPR-0056 | Weekly Progress Report Issuance - WPR0056 |  |  |  |  | 0 |  |  | 2026-04-11 | 2026-04-11 | 2026-09-04 | 183
| A1-PM-WPR-0057 | Weekly Progress Report Issuance - WPR0057 |  |  |  |  | 0 |  |  | 2026-04-16 | 2026-04-16 | 2026-09-10 | 183
| A1-PM-WPR-0058 | Weekly Progress Report Issuance - WPR0058 |  |  |  |  | 0 |  |  | 2026-04-22 | 2026-04-22 | 2026-09-15 | 183
| A1-PM-WPR-0059 | Weekly Progress Report Issuance - WPR0059 |  |  |  |  | 0 |  |  | 2026-04-28 | 2026-04-28 | 2026-09-21 | 183
| A1-PM-WPR-0060 | Weekly Progress Report Issuance - WPR0060 |  |  |  |  | 0 |  |  | 2026-05-03 | 2026-05-03 | 2026-09-27 | 183
| A1-PM-WPR-0061 | Weekly Progress Report Issuance - WPR0061 |  |  |  |  | 0 |  |  | 2026-05-09 | 2026-05-09 | 2026-10-02 | 183
| A1-PM-WPR-0062 | Weekly Progress Report Issuance - WPR0062 |  |  |  |  | 0 |  |  | 2026-05-14 | 2026-05-14 | 2026-10-08 | 183
| A1-PM-WPR-0063 | Weekly Progress Report Issuance - WPR0063 |  |  |  |  | 0 |  |  | 2026-05-20 | 2026-05-20 | 2026-10-13 | 183
| A1-PM-WPR-0064 | Weekly Progress Report Issuance - WPR0064 |  |  |  |  | 0 |  |  | 2026-05-26 | 2026-05-26 | 2026-10-19 | 183
| A1-PM-WPR-0065 | Weekly Progress Report Issuance - WPR0065 |  |  |  |  | 0 |  |  | 2026-05-31 | 2026-05-31 | 2026-10-25 | 183
| A1-PM-WPR-0066 | Weekly Progress Report Issuance - WPR0066 |  |  |  |  | 0 |  |  | 2026-06-06 | 2026-06-06 | 2026-10-30 | 183
| A1-PM-WPR-0067 | Weekly Progress Report Issuance - WPR0067 |  |  |  |  | 0 |  |  | 2026-06-11 | 2026-06-11 | 2026-11-05 | 183
| A1-PM-WPR-0068 | Weekly Progress Report Issuance - WPR0068 |  |  |  |  | 0 |  |  | 2026-06-17 | 2026-06-17 | 2026-11-10 | 183
| A1-PM-WPR-0069 | Weekly Progress Report Issuance - WPR0069 |  |  |  |  | 0 |  |  | 2026-06-23 | 2026-06-23 | 2026-11-16 | 183
| A1-PM-WPR-0070 | Weekly Progress Report Issuance - WPR0070 |  |  |  |  | 0 |  |  | 2026-06-28 | 2026-06-28 | 2026-11-22 | 183
| A1-PM-WPR-0071 | Weekly Progress Report Issuance - WPR0071 |  |  |  |  | 0 |  |  | 2026-07-04 | 2026-07-04 | 2026-11-27 | 183
| A1-PM-WPR-0072 | Weekly Progress Report Issuance - WPR0072 |  |  |  |  | 0 |  |  | 2026-07-09 | 2026-07-09 | 2026-12-03 | 183
| A1-PM-WPR-0073 | Weekly Progress Report Issuance - WPR0073 |  |  |  |  | 0 |  |  | 2026-07-15 | 2026-07-15 | 2026-12-08 | 183
| A1-PM-WPR-0074 | Weekly Progress Report Issuance - WPR0074 |  |  |  |  | 0 |  |  | 2026-07-21 | 2026-07-21 | 2026-12-14 | 183
| A1-PM-WPR-0075 | Weekly Progress Report Issuance - WPR0075 |  |  |  |  | 0 |  |  | 2026-07-26 | 2026-07-26 | 2026-12-20 | 183
| A1-PM-WPR-0076 | Weekly Progress Report Issuance - WPR0076 |  |  |  |  | 0 |  |  | 2026-08-01 | 2026-08-01 | 2026-12-25 | 183
| A1-PM-WPR-0077 | Weekly Progress Report Issuance - WPR0077 |  |  |  |  | 0 |  |  | 2026-08-06 | 2026-08-06 | 2026-12-31 | 183
| A1-PM-WPR-0078 | Weekly Progress Report Issuance - WPR0078 |  |  |  |  | 0 |  |  | 2026-08-12 | 2026-08-12 | 2027-01-05 | 183
| A1-PM-WPR-0079 | Weekly Progress Report Issuance - WPR0079 |  |  |  |  | 0 |  |  | 2026-08-18 | 2026-08-18 | 2027-01-11 | 183
| A1-PM-WPR-0080 | Weekly Progress Report Issuance - WPR0080 |  |  |  |  | 0 |  |  | 2026-08-23 | 2026-08-23 | 2027-01-17 | 183
| A1-PM-WPR-0081 | Weekly Progress Report Issuance - WPR0081 |  |  |  |  | 0 |  |  | 2026-08-29 | 2026-08-29 | 2027-01-22 | 183
| A1-PM-WPR-0082 | Weekly Progress Report Issuance - WPR0082 |  |  |  |  | 0 |  |  | 2026-09-03 | 2026-09-03 | 2027-01-28 | 183
| A1-PM-WPR-0083 | Weekly Progress Report Issuance - WPR0083 |  |  |  |  | 0 |  |  | 2026-09-09 | 2026-09-09 | 2027-02-02 | 183
| A1-PM-WPR-0084 | Weekly Progress Report Issuance - WPR0084 |  |  |  |  | 0 |  |  | 2026-09-15 | 2026-09-15 | 2027-02-08 | 183
| A1-PM-WPR-0085 | Weekly Progress Report Issuance - WPR0085 |  |  |  |  | 0 |  |  | 2026-09-20 | 2026-09-20 | 2027-02-14 | 183
| A1-PM-WPR-0086 | Weekly Progress Report Issuance - WPR0086 |  |  |  |  | 0 |  |  | 2026-09-26 | 2026-09-26 | 2027-02-19 | 183
| A1-PM-WPR-0087 | Weekly Progress Report Issuance - WPR0087 |  |  |  |  | 0 |  |  | 2026-10-01 | 2026-10-01 | 2027-02-25 | 183
| A1-PM-WPR-0088 | Weekly Progress Report Issuance - WPR0088 |  |  |  |  | 0 |  |  | 2026-10-07 | 2026-10-07 | 2027-03-02 | 183
| A1-PM-WPR-0089 | Weekly Progress Report Issuance - WPR0089 |  |  |  |  | 0 |  |  | 2026-10-13 | 2026-10-13 | 2027-03-08 | 183
| A1-PM-WPR-0090 | Weekly Progress Report Issuance - WPR0090 |  |  |  |  | 0 |  |  | 2026-10-18 | 2026-10-18 | 2027-03-14 | 183
| A1-PM-WPR-0091 | Weekly Progress Report Issuance - WPR0091 |  |  |  |  | 0 |  |  | 2026-10-24 | 2026-10-24 | 2027-03-19 | 183
| A1-PM-WPR-0092 | Weekly Progress Report Issuance - WPR0092 |  |  |  |  | 0 |  |  | 2026-10-29 | 2026-10-29 | 2027-03-25 | 183
| A1-PM-WPR-0093 | Weekly Progress Report Issuance - WPR0093 |  |  |  |  | 0 |  |  | 2026-11-04 | 2026-11-04 | 2027-03-30 | 183
| A1-PM-WPR-0094 | Weekly Progress Report Issuance - WPR0094 |  |  |  |  | 0 |  |  | 2026-11-10 | 2026-11-10 | 2027-04-05 | 183
| A1-PM-WPR-0095 | Weekly Progress Report Issuance - WPR0095 |  |  |  |  | 0 |  |  | 2026-11-15 | 2026-11-15 | 2027-04-11 | 183
| A1-PM-WPR-0096 | Weekly Progress Report Issuance - WPR0096 |  |  |  |  | 0 |  |  | 2026-11-21 | 2026-11-21 | 2027-04-16 | 183
| A1-PM-WPR-0097 | Weekly Progress Report Issuance - WPR0097 |  |  |  |  | 0 |  |  | 2026-11-26 | 2026-11-26 | 2027-04-22 | 183
| A1-PM-WPR-0098 | Weekly Progress Report Issuance - WPR0098 |  |  |  |  | 0 |  |  | 2026-12-02 | 2026-12-02 | 2027-04-27 | 183
| A1-PM-WPR-0099 | Weekly Progress Report Issuance - WPR0099 |  |  |  |  | 0 |  |  | 2026-12-08 | 2026-12-08 | 2027-05-03 | 183
| A1-PM-WPR-0100 | Weekly Progress Report Issuance - WPR0100 |  |  |  |  | 0 |  |  | 2026-12-13 | 2026-12-13 | 2027-05-09 | 183
| A1-PM-WPR-0101 | Weekly Progress Report Issuance - WPR0101 |  |  |  |  | 0 |  |  | 2026-12-19 | 2026-12-19 | 2027-05-14 | 183
| A1-PM-WPR-0102 | Weekly Progress Report Issuance - WPR0102 |  |  |  |  | 0 |  |  | 2026-12-24 | 2026-12-24 | 2027-05-20 | 183
| A1-PM-WPR-0103 | Weekly Progress Report Issuance - WPR0103 |  |  |  |  | 0 |  |  | 2026-12-30 | 2026-12-30 | 2027-05-25 | 183
| A1-PM-WPR-0104 | Weekly Progress Report Issuance - WPR0104 |  |  |  |  | 0 |  |  | 2027-01-05 | 2027-01-05 | 2027-05-31 | 183
| A1-PM-WPR-0105 | Weekly Progress Report Issuance - WPR0105 |  |  |  |  | 0 |  |  | 2027-01-10 | 2027-01-10 | 2027-06-06 | 183
| A1-PM-WPR-0106 | Weekly Progress Report Issuance - WPR0106 |  |  |  |  | 0 |  |  | 2027-01-16 | 2027-01-16 | 2027-06-11 | 183
| A1-PM-WPR-0107 | Weekly Progress Report Issuance - WPR0107 |  |  |  |  | 0 |  |  | 2027-01-21 | 2027-01-21 | 2027-06-17 | 183
| A1-PM-WPR-0108 | Weekly Progress Report Issuance - WPR0108 |  |  |  |  | 0 |  |  | 2027-01-27 | 2027-01-27 | 2027-06-22 | 183
| A1-PM-WPR-0109 | Weekly Progress Report Issuance - WPR0109 |  |  |  |  | 0 |  |  | 2027-02-02 | 2027-02-02 | 2027-06-28 | 183
| A1-PM-WPR-0110 | Weekly Progress Report Issuance - WPR0110 |  |  |  |  | 0 |  |  | 2027-02-07 | 2027-02-07 | 2027-07-04 | 183
| A1-PM-WPR-0111 | Weekly Progress Report Issuance - WPR0111 |  |  |  |  | 0 |  |  | 2027-02-13 | 2027-02-13 | 2027-07-09 | 183
| A1-PM-WPR-0112 | Weekly Progress Report Issuance - WPR0112 |  |  |  |  | 0 |  |  | 2027-02-18 | 2027-02-18 | 2027-07-15 | 183
| A1-PM-WPR-0113 | Weekly Progress Report Issuance - WPR0113 |  |  |  |  | 0 |  |  | 2027-02-24 | 2027-02-24 | 2027-07-20 | 183
| Monthly Progress Report |  |  | 2026-02-20 |  |  | 790 | 20-Dec-24 A | 2026-07-21 | 2027-02-18 | 2027-02-18 | 2027-07-20 | 152
| A1-PM-MPR-0001 | Monthly Progress Report Issuance - MPR001 |  |  |  |  | 0 |  |  | 20-Dec-24 A
| A1-PM-MPR-0002 | Monthly Progress Report Issuance - MPR002 |  |  |  |  | 0 |  |  | 24-Jan-25 A
| A1-PM-MPR-0004 | Monthly Progress Report Issuance - MPR004 |  |  |  |  | 0 |  |  | 14-Apr-25 A
| A1-PM-MPR-0005 | Monthly Progress Report Issuance - MPR005 |  |  |  |  | 0 |  |  | 13-May-25 A
| A1-PM-MPR-0003 | Monthly Progress Report Issuance - MPR003 |  |  |  |  | 0 |  |  | 17-Jun-25 A
| A1-PM-MPR-0006 | Monthly Progress Report Issuance - MPR006 |  |  |  |  | 0 |  |  | 17-Jun-25 A
| A1-PM-MPR-0007 | Monthly Progress Report Issuance - MPR007 |  |  |  |  | 0 |  |  | 01-Jul-25 A
| A1-PM-MPR-0008 | Monthly Progress Report Issuance - MPR008 |  |  |  |  | 0 |  |  | 22-Aug-25 A
| A1-PM-MPR-0009 | Monthly Progress Report Issuance - MPR009 |  |  |  |  | 0 |  |  | 10-Sep-25 A
| A1-PM-MPR-0010 | Monthly Progress Report Issuance - MPR010 |  |  |  |  | 0 |  |  | 30-Oct-25 A
| A1-PM-MPR-0011 | Monthly Progress Report Issuance - MPR011 |  |  |  |  | 0 |  |  | 21-Nov-25 A
| A1-PM-MPR-0012 | Monthly Progress Report Issuance - MPR012 |  |  |  |  | 0 |  |  | 2026-02-20 | 2026-02-20 | 2026-07-21 | 190
| A1-PM-MPR-0013 | Monthly Progress Report Issuance - MPR013 |  |  |  |  | 0 |  |  | 2026-03-14 | 2026-03-14 | 2026-08-13 | 190
| A1-PM-MPR-0014 | Monthly Progress Report Issuance - MPR014 |  |  |  |  | 0 |  |  | 2026-04-11 | 2026-04-11 | 2026-09-10 | 190
| A1-PM-MPR-0015 | Monthly Progress Report Issuance - MPR015 |  |  |  |  | 0 |  |  | 2026-05-03 | 2026-05-03 | 2026-10-02 | 190
| A1-PM-MPR-0016 | Monthly Progress Report Issuance - MPR016 |  |  |  |  | 0 |  |  | 2026-05-26 | 2026-05-26 | 2026-10-25 | 190
| A1-PM-MPR-0017 | Monthly Progress Report Issuance - MPR017 |  |  |  |  | 0 |  |  | 2026-06-17 | 2026-06-17 | 2026-11-16 | 190
| A1-PM-MPR-0018 | Monthly Progress Report Issuance - MPR018 |  |  |  |  | 0 |  |  | 2026-07-15 | 2026-07-15 | 2026-12-14 | 190
| A1-PM-MPR-0019 | Monthly Progress Report Issuance - MPR019 |  |  |  |  | 0 |  |  | 2026-08-06 | 2026-08-06 | 2027-01-05 | 190
| A1-PM-MPR-0020 | Monthly Progress Report Issuance - MPR020 |  |  |  |  | 0 |  |  | 2026-09-03 | 2026-09-03 | 2027-02-02 | 190
| A1-PM-MPR-0021 | Monthly Progress Report Issuance - MPR021 |  |  |  |  | 0 |  |  | 2026-09-26 | 2026-09-26 | 2027-02-25 | 190
| A1-PM-MPR-0022 | Monthly Progress Report Issuance - MPR022 |  |  |  |  | 0 |  |  | 2026-10-18 | 2026-10-18 | 2027-03-19 | 190
| A1-PM-MPR-0023 | Monthly Progress Report Issuance - MPR023 |  |  |  |  | 0 |  |  | 2026-11-15 | 2026-11-15 | 2027-04-16 | 190
| A1-PM-MPR-0024 | Monthly Progress Report Issuance - MPR024 |  |  |  |  | 0 |  |  | 2026-12-08 | 2026-12-08 | 2027-05-09 | 190
| A1-PM-MPR-0025 | Monthly Progress Report Issuance - MPR025 |  |  |  |  | 0 |  |  | 2026-12-30 | 2026-12-30 | 2027-05-31 | 190
| A1-PM-MPR-0026 | Monthly Progress Report Issuance - MPR026 |  |  |  |  | 0 |  |  | 2027-01-27 | 2027-01-27 | 2027-06-28 | 190
| A1-PM-MPR-0027 | Monthly Progress Report Issuance - MPR027 |  |  |  |  | 0 |  |  | 2027-02-18 | 2027-02-18 | 2027-07-20 | 190
| Team Building Workshops |  |  | 2026-02-20 |  |  | 561 | 06-Mar-25 A | 2026-10-05 | 2026-12-04 | 2026-12-04 | 2027-07-20 | 228
| A1-PM-TBW-0001 | TBW01-Team Building Event-001 |  |  |  |  | 0 |  |  | 06-Mar-25 A
| A1-PM-TBW-0002 | TBW01-Team Building Event-002 |  |  |  |  | 0 |  |  | 21-Jun-25 A
| A1-PM-TBW-0003 | TBW01-Team Building Event-003 |  |  |  |  | 0 |  |  | 12-Aug-25 A
| A1-PM-TBW-0004 | TBW01-Team Building Event-004 |  |  |  |  | 0 |  |  | 2026-02-20 | 2026-02-20 | 2026-10-05 | 285
| A1-PM-TBW-0005 | TBW01-Team Building Event-005 |  |  |  |  | 0 |  |  | 2026-05-26 | 2026-05-26 | 2027-01-09 | 285
| A1-PM-TBW-0006 | TBW01-Team Building Event-006 |  |  |  |  | 0 |  |  | 2026-08-30 | 2026-08-30 | 2027-04-15 | 285
| A1-PM-TBW-0007 | TBW01-Team Building Event-007 |  |  |  |  | 0 |  |  | 2026-12-04 | 2026-12-04 | 2027-07-20 | 285
| Invoicing Plan |  |  | 2026-02-20 |  |  | 655 | 07-Feb-25 A | 2026-06-06 | 2027-04-05 | 2027-04-05 | 2027-07-20 | 106
| A1-PM-MIP-0001 | Monthly Invoicing Plan - MIP001 (Advanced Payment) |  |  |  |  | 0 |  |  | 07-Feb-25 A
| A1-PM-MIP-0002 | Monthly Invoicing Plan - MIP002 |  |  |  |  | 0 |  |  | 07-Mar-25 A
| A1-PM-MIP-0003 | Monthly Invoicing Plan - MIP003 |  |  |  |  | 0 |  |  | 10-Apr-25 A
| A1-PM-MIP-0004 | Monthly Invoicing Plan - MIP004 |  |  |  |  | 0 |  |  | 10-May-25 A
| A1-PM-MIP-0005 | Monthly Invoicing Plan - MIP005 |  |  |  |  | 0 |  |  | 21-Jun-25 A
| A1-PM-MIP-0006 | Monthly Invoicing Plan - MIP006 |  |  |  |  | 0 |  |  | 21-Jun-25 A
| A1-PM-MIP-0007 | Monthly Invoicing Plan - MIP007 |  |  |  |  | 0 |  |  | 21-Jun-25 A
| A1-PM-MIP-0008 | Monthly Invoicing Plan - MIP008 |  |  |  |  | 0 |  |  | 29-Aug-25 A
| A1-PM-MIP-0009 | Monthly Invoicing Plan - MIP009 |  |  |  |  | 0 |  |  | 19-Sep-25 A
| A1-PM-MIP-0010 | Monthly Invoicing Plan - MIP010 |  |  |  |  | 0 |  |  | 24-Oct-25 A
| A1-PM-MIP-0011 | Monthly Invoicing Plan - MIP011 |  |  |  |  | 0 |  |  | 11-Nov-25 A
| A1-PM-MIP-0012 | Monthly Invoicing Plan - MIP012 |  |  |  |  | 0 |  |  | 2026-02-20 | 2026-02-20 | 2026-06-06 | 133
| A1-PM-MIP-0013 | Monthly Invoicing Plan - MIP013 |  |  |  |  | 0 |  |  | 2026-03-08 | 2026-03-08 | 2026-06-22 | 133
| A1-PM-MIP-0014 | Monthly Invoicing Plan - MIP014 |  |  |  |  | 0 |  |  | 2026-04-05 | 2026-04-05 | 2026-07-20 | 133
| A1-PM-MIP-0015 | Monthly Invoicing Plan - MIP015 |  |  |  |  | 0 |  |  | 2026-05-06 | 2026-05-06 | 2026-08-20 | 133
| A1-PM-MIP-0016 | Monthly Invoicing Plan - MIP016 |  |  |  |  | 0 |  |  | 2026-06-05 | 2026-06-05 | 2026-09-19 | 133
| A1-PM-MIP-0017 | Monthly Invoicing Plan - MIP017 |  |  |  |  | 0 |  |  | 2026-07-06 | 2026-07-06 | 2026-10-20 | 133
| A1-PM-MIP-0018 | Monthly Invoicing Plan - MIP018 |  |  |  |  | 0 |  |  | 2026-08-05 | 2026-08-05 | 2026-11-19 | 133
| A1-PM-MIP-0019 | Monthly Invoicing Plan - MIP019 |  |  |  |  | 0 |  |  | 2026-08-05 | 2026-08-05 | 2026-11-19 | 133
| A1-PM-MIP-0020 | Monthly Invoicing Plan - MIP020 |  |  |  |  | 0 |  |  | 2026-09-05 | 2026-09-05 | 2026-12-20 | 133
| A1-PM-MIP-0021 | Monthly Invoicing Plan - MIP021 |  |  |  |  | 0 |  |  | 2026-10-06 | 2026-10-06 | 2027-01-20 | 133
| A1-PM-MIP-0022 | Monthly Invoicing Plan - MIP022 |  |  |  |  | 0 |  |  | 2026-11-05 | 2026-11-05 | 2027-02-19 | 133
| A1-PM-MIP-0023 | Monthly Invoicing Plan - MIP023 |  |  |  |  | 0 |  |  | 2026-12-06 | 2026-12-06 | 2027-03-22 | 133
| A1-PM-MIP-0024 | Monthly Invoicing Plan - MIP024 |  |  |  |  | 0 |  |  | 2027-01-05 | 2027-01-05 | 2027-04-21 | 133
| A1-PM-MIP-0025 | Monthly Invoicing Plan - MIP025 |  |  |  |  | 0 |  |  | 2027-02-05 | 2027-02-05 | 2027-05-22 | 133
| A1-PM-MIP-0026 | Monthly Invoicing Plan - MIP026 |  |  |  |  | 0 |  |  | 2027-03-08 | 2027-03-08 | 2027-06-22 | 133
| A1-PM-MIP-0027 | Monthly Invoicing Plan - MIP027 |  |  |  |  | 0 |  |  | 2027-04-05 | 2027-04-05 | 2027-07-20 | 133
| Home Office Services |  |  | 2026-02-20 |  |  | 695 | 14-Nov-24 A | 2026-02-21 | 2027-07-14 | 2027-07-14 | 2027-07-20 | 4
| Detailed Design - EDDR |  |  | 2026-02-20 |  |  | 511 | 27-Nov-24 A | 2026-02-21 | 2026-09-25 | 2026-09-25 | 2027-07-20 | 213
| Package 1&2 | [5 empty] | 0 | 01-Aug-25 A |  | 22-Aug-25 A
| Deliverables to be Recieved from Pkg 1&2 | [5 empty] | 0 | 01-Aug-25 A |  | 22-Aug-25 A
| 1B-DE-P12-0001 | Civil / Architecture / Structure - 63 Deleverables |  |  |  |  | 0 |  |  | 01-Aug-25 A
| 1B-DE-P12-0011 | Construction - 30 Deleverables |  |  |  |  | 0 |  |  | 04-Aug-25 A
| 1B-DE-P12-0021 | Electrical Engineering - 73 Deleverables |  |  |  |  | 0 |  |  | 05-Aug-25 A
| 1B-DE-P12-0031 | HVAC - 26 Deleverables |  |  |  |  | 0 |  |  | 06-Aug-25 A
| 1B-DE-P12-0041 | Instrument and Control System - 90 Deleverables |  |  |  |  | 0 |  |  | 07-Aug-25 A
| 1B-DE-P12-0051 | IT/TELECOM - 69 Deleverables |  |  |  |  | 0 |  |  | 08-Aug-25 A
| 1B-DE-P12-0061 | Material and Corrosion - 24 Deleverables |  |  |  |  | 0 |  |  | 11-Aug-25 A
| 1B-DE-P12-0071 | Mechanical Rotating - 19 Deleverables |  |  |  |  | 0 |  |  | 12-Aug-25 A
| 1B-DE-P12-0081 | Mechanical Rotating/Package - 9 Deleverables |  |  |  |  | 0 |  |  | 13-Aug-25 A
| 1B-DE-P12-0091 | MS-Mechanical Static - 9 Deleverables |  |  |  |  | 0 |  |  | 14-Aug-25 A
| 1B-DE-P12-0101 | Piping Engineering - 43 Deleverables |  |  |  |  | 0 |  |  | 15-Aug-25 A
| 1B-DE-P12-0111 | Process and Safety Engineering - 38 Deleverables |  |  |  |  | 0 |  |  | 18-Aug-25 A
| 1B-DE-P12-0121 | Project Control - 29 Deleverables |  |  |  |  | 0 |  |  | 19-Aug-25 A
| 1B-DE-P12-0131 | Project Control Quality - 14 Deleverables |  |  |  |  | 0 |  |  | 20-Aug-25 A
| 1B-DE-P12-0141 | Project Management - 86 Deleverables |  |  |  |  | 0 |  |  | 21-Aug-25 A
| 1B-DE-P12-0151 | Safety - 11 Deleverables |  |  |  |  | 0 |  |  | 22-Aug-25 A
| Package 3 |  |  | 2026-02-20 |  |  | 511 | 27-Nov-24 A | 2026-02-21 | 2026-09-25 | 2026-09-25 | 2027-07-20 | 213
| Milestone |  |  | 2026-09-25 |  |  | 467 | 11-Dec-24 A | 2027-01-20 | 2026-09-25 | 2026-09-25 | 2027-01-20 | 84
| General |  |  | 2026-09-25 |  |  | 467 | 11-Dec-24 A | 2027-01-20 | 2026-09-25 | 2026-09-25 | 2027-01-20 | 84
| Turnaround | [5 empty] | 0 | 11-Dec-24 A |  | 11-Dec-24 A
| A40690 | Commencement of TA Engginering Works |  |  |  |  | 0 | 11-Dec-24 A
| Balance of Plant |  |  | 2026-09-25 |  |  | 467 | 11-Dec-24 A | 2027-01-20 | 2026-09-25 | 2026-09-25 | 2027-01-20 | 84
| A120 | Commencement of BOP Engineering Works |  |  |  |  | 0 | 11-Dec-24 A
| A40320 | Completion of Engineering |  | 2026-09-25 |  |  | 0 | 2026-09-25 | 2027-01-20 |  |  |  | 84
| General / Common |  |  | 2026-02-20 |  |  | 40 | 27-Nov-24 A | 2026-03-27 | 21-Jan-25 A | 2026-02-20 | 2026-03-27
| MSE1300 | Site Survey & Data Collection / FEED Verification |  | 2026-02-20 |  |  | 40 | 27-Nov-24 A | 2026-03-27 | 21-Jan-25 A | 2026-02-20 | 2026-03-27
| Preliminaries |  |  | 2026-02-20 |  |  | 32 | 04-Dec-24 A | 2026-02-21 | 23-May-25 A | 2026-02-20 | 2026-03-27
| A53280 | Engineering Subcontractor KOM |  | 2026-02-20 |  |  | 1 | 04-Dec-24 A | 2026-02-21 | 04-Dec-24 A | 2026-02-20 | 2026-02-21
| A53290 | LOA Request |  | 2026-02-20 |  |  | 8 | 05-Dec-24 A | 2026-03-02 | 13-Dec-24 A | 2026-02-20 | 2026-03-02
| A53330 | Medicals and CICPA Passes |  | 2026-02-20 |  |  | 16 | 05-Dec-24 A | 2026-03-02 | 24-Dec-24 A | 2026-02-20 | 2026-03-02
| A53340 | Site Visit for BOP |  | 2026-02-20 |  |  | 6 | 25-Dec-24 A | 2026-03-02 | 31-Dec-24 A | 2026-02-20 | 2026-03-02
| A40350 | Site Visit for TA Activities (CSA, Piping) |  | 2026-02-20 |  |  | 6 | 09-Jan-25 A | 2026-03-27 | 16-Jan-25 A | 2026-02-20 | 2026-03-27
| A53320 | Receipt of Source Data |  | 2026-02-20 |  |  | 8 | 05-Dec-24 A | 2026-02-21 | 23-May-25 A | 2026-02-20 | 2026-02-21
| TA related Inputs |  |  | 2026-02-20 |  |  | 492 | 12-Dec-24 A | 2026-02-21 | 2026-06-16 | 2026-06-16 | 2027-07-20 | 285
| TA Phase |  |  | 2026-02-20 |  |  | 202 | 12-Dec-24 A | 2026-02-21 | 22-Apr-25 A | 2026-02-20 | 2026-03-27
| A55740 | Receipt of HSE third party offers by RAD (Descon) |  | 2026-02-20 |  |  | 1 | 12-Dec-24 A | 2026-03-02 | 12-Dec-24 A | 2026-02-20 | 2026-03-02
| A40330 | Receipt of Approved ICT Site Adequacy Report |  | 2026-02-20 |  |  | 1 | 12-Feb-25 A | 2026-03-27 | 13-Feb-25 A | 2026-02-20 | 2026-03-27
| A40340 | Receipt of Approved Electrical Site Adequacy Report |  | 2026-02-20 |  |  | 1 | 12-Feb-25 A | 2026-03-27 | 13-Feb-25 A | 2026-02-20 | 2026-03-27
| A28140 | Receipt of Approved Topo, UG & geotechnical investigation report |  | 2026-02-20 |  |  | 1 | 08-Apr-25 A | 2026-02-21 | 22-Apr-25 A | 2026-02-20 | 2026-02-21
| Vendor Offer Receipt (to enable Eng Subcon to perform TBE) | [5 empty] | 23 | 09-Jan-25 A |  | 15-Jul-25 A
| Piping |  |  | 2026-02-20 |  |  | 8 | 03-Feb-25 A | 2026-05-15 | 24-Feb-25 A | 2026-05-22 | 2027-06-28 | 285
| A53550 | Piping Bulk_All Technical Vendor Offers Receipt |  |  |  |  | 0 |  |  | 03-Feb-25 A
| A53560 | Manual Valves_All Technical Vendor Offers Receipt |  |  |  |  | 0 |  |  | 11-Feb-25 A
| A53590 | Rigid Struts_All Technical Vendor Offers Receipt |  |  |  |  | 0 |  |  | 17-Feb-25 A
| A53580 | Spring Hangers_All Technical Vendor Offers Receipt |  |  |  |  | 0 |  |  | 21-Feb-25 A
| A53570 | Piping Speciality Items_All Technical Vendor Offers Receipt |  |  |  |  | 0 |  |  | 24-Feb-25 A
| Mechanical |  |  | 2026-02-27 |  |  | 0 | 07-Feb-25 A | 2027-06-28 | 07-May-25 A | 2026-02-27 | 2027-06-28 | 346
| A53440 | Pressure Vessels & Internals_All Technical Vendor Offers Receipt |  |  |  |  | 0 |  |  | 07-Feb-25 A
| A53400 | Heat Exchangers_All Technical Vendor Offers Receipt |  |  |  |  | 0 |  |  | 14-Mar-25 A
| A53410 | Centrifugal Pump_All Technical Vendor Offers Receipt |  |  |  |  | 0 |  |  | 21-Mar-25 A
| A53430 | Coalscer_All Technical Vendor Offers Receipt |  |  |  |  | 0 |  |  | 21-Mar-25 A
| A53420 | EOT Crane_All Technical Vendor Offers Receipt |  |  |  |  | 0 |  |  | 07-May-25 A
| Electrical |  |  | 2026-02-20 |  |  | 0 | 09-Jan-25 A | 2026-03-19 | 13-May-25 A | 2026-02-20 | 2027-06-28 | 351
| A53600 | Transformer (Power And Distribution)_All Technical Vendor Offers Receipt |  |  |  |  | 0 |  |  | 09-Jan-25 A
| A53670 | Neutral Grounding Resistor_All Technical Vendor Offers Receipt |  |  |  |  | 0 |  |  | 17-Jan-25 A
| A53630 | AC UPS_All Technical Vendor Offers Receipt |  |  |  |  | 0 |  |  | 22-Jan-25 A
| A53680 | Emergency Diesel Generator Set_All Technical Vendor Offers Receipt |  |  |  |  | 0 |  |  | 22-Jan-25 A
| A53640 | DC UPS_All Technical Vendor Offers Receipt |  |  |  |  | 0 |  |  | 21-Feb-25 A
| A53690 | LV Variable Frequency Drive_All Technical Vendor Offers Receipt |  |  |  |  | 0 |  |  | 21-Feb-25 A
| A53620 | LV Switchgear_All Technical Vendor Offers Receipt |  |  |  |  | 0 |  |  | 28-Feb-25 A
| A53610 | 11KV Switchgear_All Technical Vendor Offers Receipt |  |  |  |  | 0 |  |  | 06-Mar-25 A
| A53650 | Capacitor Bank_All Technical Vendor Offers Receipt |  |  |  |  | 0 |  |  | 21-Apr-25 A
| A53660 | Power, Control And Earthing Cables_All Technical Vendor Offers Receipt |  |  |  |  | 0 |  |  | 13-May-25 A
| Instrumentation & Controls |  |  | 2026-02-20 |  |  | 0 | 23-Apr-25 A | 2026-03-19 | 15-Jul-25 A | 2026-03-27 | 2027-07-06 | 332
| A25950 | Level Gauges (Magnetic Type)_All Technical Vendor Offers Receipt |  |  |  |  | 0 |  |  | 23-Apr-25 A
| A53740 | ICSS System_All Technical Vendor Offers Receipt |  |  |  |  | 0 |  |  | 24-Apr-25 A
| A25960 | Control Valves_All Technical Vendor Offers Receipt |  |  |  |  | 0 |  |  | 27-Apr-25 A
| A25990 | Motor Operated Valves_All Technical Vendor Offers Receipt |  |  |  |  | 0 |  |  | 27-Apr-25 A
| A53700 | Electronic Transmitters_All Technical Vendor Offers Receipt |  |  |  |  | 0 |  |  | 28-Apr-25 A
| A25980 | Level Transmitters (GWR type)_All Technical Vendor Offers Receipt |  |  |  |  | 0 |  |  | 28-Apr-25 A
| A53710 | Flow Element (Orifice Plate)_All Technical Vendor Offers Receipt |  |  |  |  | 0 |  |  | 29-Apr-25 A
| A25910 | Flow Element (Venturi Tube)_All Technical Vendor Offers Receipt |  |  |  |  | 0 |  |  | 30-Apr-25 A
| A25930 | Temperature Gauges / Pressure Gauges_All Technical Vendor Offers Receipt |  |  |  |  | 0 |  |  | 30-Apr-25 A
| A26000 | ESD Valves_All Technical Vendor Offers Receipt |  |  |  |  | 0 |  |  | 30-Apr-25 A
| A26010 | Rotameter_All Technical Vendor Offers Receipt |  |  |  |  | 0 |  |  | 01-May-25 A
| A25920 | Temperature Element / Thermowell_All Technical Vendor Offers Receipt |  |  |  |  | 0 |  |  | 07-May-25 A
| A53750 | Fire Detection System & LFCP_All Technical Vendor Offers Receipt |  |  |  |  | 0 |  |  | 12-Jun-25 A
| A25970 | Fire & Gas Detectors_All Technical Vendor Offers Receipt |  |  |  |  | 0 |  |  | 05-Jul-25 A
| A53720 | Instrument Cables_All Technical Vendor Offers Receipt |  |  |  |  | 0 |  |  | 05-Jul-25 A
| A53730 | Junction Boxes_All Technical Vendor Offers Receipt |  |  |  |  | 0 |  |  | 05-Jul-25 A
| A25940 | Analyzers_All Technical Vendor Offers Receipt |  |  |  |  | 0 |  |  | 15-Jul-25 A
| Telecom |  |  | 2026-02-20 |  |  | 0 | 26-Apr-25 A | 2027-06-28 | 22-May-25 A | 2026-02-20 | 2027-06-28 | 351
| A53760 | Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_All Technical Vendor Offers Receipt |  |  |  |  | 0 |  |  | 26-Apr-25 A
| A53770 | Telecom Cables_All Technical Vendor Offers Receipt |  |  |  |  | 0 |  |  | 22-May-25 A
| HVAC |  |  | 2026-02-20 |  |  | 0 | 03-Jun-25 A | 2027-06-28 | 03-Jun-25 A | 2026-02-20 | 2027-06-28 | 351
| A53780 | HVAC Equipments_All Technical Vendor Offers Receipt |  |  |  |  | 0 |  |  | 03-Jun-25 A
| Ist Issuance of Vendor Data Receipt-1 |  |  | 2026-02-20 |  |  | 354 | 03-Feb-25 A | 2026-03-19 | 2026-05-22 | 2026-05-22 | 2027-07-06 | 292
| A53830 | Rigid Struts_1st issuance of Vendor Data Receipt |  |  |  |  | 0 |  |  | 24-Mar-25 A
| A53810 | Piping Speciality Items_1st issuance of Vendor Data Receipt |  |  |  |  | 0 |  |  | 05-Aug-25 A
| A53790 | Piping Bulk_1st issuance of Vendor Data Receipt |  |  |  |  | 0 |  |  | 2026-02-20 | 2026-02-20 | 2027-06-28 | 351
| A53800 | Manual Valves_1st issuance of Vendor Data Receipt |  |  |  |  | 0 |  |  | 2026-02-20 | 2026-02-20 | 2026-05-15 | 61
| A53820 | Spring Hangers_1st issuance of Vendor Data Receipt |  |  |  |  | 0 |  |  | 2026-05-22 | 2026-05-22 | 2027-04-22 | 238
| A28770 | Compressors (FG & OG)_1st issuance of Vendor Data Receipt |  |  |  |  | 0 |  |  | 27-Aug-25 A
| A53500 | Heat Exchangers_1st issuance of Vendor Data Receipt |  |  |  |  | 0 |  |  | 02-Sep-25 A
| A53540 | Pressure Vessels & Internals_1st issuance of Vendor Data Receipt |  |  |  |  | 0 |  |  | 02-Sep-25 A
| A28780 | PSA Unit_1st issuance of Vendor Data Receipt |  |  |  |  | 0 |  |  | 09-Sep-25 A
| A53510 | Centrifugal Pump_1st issuance of Vendor Data Receipt |  |  |  |  | 0 |  |  | 30-Oct-25 A
| A53520 | EOT Crane_1st issuance of Vendor Data Receipt |  |  |  |  | 0 |  |  | 04-Nov-25 A
| A53530 | Coalscer_1st issuance of Vendor Data Receipt |  |  |  |  | 0 |  |  | 2026-02-27 | 2026-02-27 | 2027-06-28 | 346
| A53840 | Transformer (Power And Distribution)_1st issuance of Vendor Data Receipt |  |  |  |  | 0 |  |  | 2026-02-20 | 2026-02-20 | 2026-11-23 | 196
| A53850 | 11KV Switchgear_1st issuance of Vendor Data Receipt |  |  |  |  | 0 |  |  | 2026-02-20 | 2026-02-20 | 2027-06-28 | 351
| A53860 | LV Switchgear_1st issuance of Vendor Data Receipt |  |  |  |  | 0 |  |  | 2026-02-20 | 2026-02-20 | 2027-06-28 | 351
| A53870 | AC UPS_1st issuance of Vendor Data Receipt |  |  |  |  | 0 |  |  | 2026-02-20 | 2026-02-20 | 2027-06-28 | 351
| A53880 | DC UPS_1st issuance of Vendor Data Receipt |  |  |  |  | 0 |  |  | 2026-02-20 | 2026-02-20 | 2026-03-19 | 20
| A53890 | Capacitor Bank_1st issuance of Vendor Data Receipt |  |  |  |  | 0 |  |  | 2026-02-20 | 2026-02-20 | 2027-06-28 | 351
| A53900 | Power, Control And Earthing Cables_1st issuance of Vendor Data Receipt |  |  |  |  | 0 |  |  | 2026-02-20 | 2026-02-20 | 2027-06-28 | 351
| A53910 | Neutral Grounding Resistor_1st issuance of Vendor Data Receipt |  |  |  |  | 0 |  |  | 2026-02-20 | 2026-02-20 | 2027-06-28 | 351
| A53920 | Emergency Diesel Generator Set_1st issuance of Vendor Data Receipt |  |  |  |  | 0 |  |  | 2026-02-20 | 2026-02-20 | 2027-01-20 | 239
| A53930 | LV Variable Frequency Drive_1st issuance of Vendor Data Receipt |  |  |  |  | 0 |  |  | 2026-02-20 | 2026-02-20 | 2027-06-28 | 351
| A53990 | Analyzers_1st issuance of Vendor Data Receipt |  |  |  |  | 0 |  |  | 03-Feb-25 A
| A54020 | Fire & Gas Detectors_1st issuance of Vendor Data Receipt |  |  |  |  | 0 |  |  | 17-Mar-25 A
| A53970 | Temperature Element / Thermowell_1st issuance of Vendor Data Receipt |  |  |  |  | 0 |  |  | 18-Mar-25 A
| A53980 | Temperature Gauges / Pressure Gauges_1st issuance of Vendor Data Receipt |  |  |  |  | 0 |  |  | 29-May-25 A
| A54060 | Rotameter_1st issuance of Vendor Data Receipt |  |  |  |  | 0 |  |  | 29-May-25 A
| A54070 | Instrument Cables_1st issuance of Vendor Data Receipt |  |  |  |  | 0 |  |  | 30-Nov-25 A
| A53950 | Flow Element (Orifice Plate)_1st issuance of Vendor Data Receipt |  |  |  |  | 0 |  |  | 2026-02-20 | 2026-02-20 | 2027-06-28 | 351
| A53960 | Flow Element (Venturi Tube)_1st issuance of Vendor Data Receipt |  |  |  |  | 0 |  |  | 2026-02-20 | 2026-02-20 | 2027-06-28 | 351
| A54000 | Level Gauges (Magnetic Type)_1st issuance of Vendor Data Receipt |  |  |  |  | 0 |  |  | 2026-02-20 | 2026-02-20 | 2027-06-28 | 351
| A54010 | Control Valves_1st issuance of Vendor Data Receipt |  |  |  |  | 0 |  |  | 2026-02-20 | 2026-02-20 | 2027-06-28 | 351
| A54030 | Level Transmitters (GWR type)_1st issuance of Vendor Data Receipt |  |  |  |  | 0 |  |  | 2026-02-20 | 2026-02-20 | 2027-06-28 | 351
| A54040 | Motor Operated Valves_1st issuance of Vendor Data Receipt |  |  |  |  | 0 |  |  | 2026-02-20 | 2026-02-20 | 2027-06-28 | 351
| A54050 | ESD Valves_1st issuance of Vendor Data Receipt |  |  |  |  | 0 |  |  | 2026-02-20 | 2026-02-20 | 2027-06-28 | 351
| A54090 | ICSS System_1st issuance of Vendor Data Receipt |  |  |  |  | 0 |  |  | 2026-02-20 | 2026-02-20 | 2027-06-28 | 351
| A54100 | Fire Detection System & LFCP_1st issuance of Vendor Data Receipt |  |  |  |  | 0 |  |  | 2026-02-20 | 2026-02-20 | 2026-03-19 | 20
| A54080 | Junction Boxes_1st issuance of Vendor Data Receipt |  |  |  |  | 0 |  |  | 2026-03-12 | 2026-03-12 | 2027-07-06 | 343
| A53940 | Electronic Transmitters_1st issuance of Vendor Data Receipt |  |  |  |  | 0 |  |  | 2026-03-27 | 2026-03-27 | 2027-06-28 | 325
| A54120 | Telecom Cables_1st issuance of Vendor Data Receipt |  |  |  |  | 0 |  |  | 18-Mar-25 A
| A54110 | Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_1st issuance of Vendor Data Receipt |  |  |  |  | 0 |  |  | 2026-02-20 | 2026-02-20 | 2027-06-28 | 351
| A54130 | HVAC Equipments_1st issuance of Vendor Data Receipt |  |  |  |  | 0 |  |  | 2026-02-20 | 2026-02-20 | 2027-06-28 | 351
| Approved Vender Data Receipt |  |  | 2026-02-20 |  |  | 291 | 04-Mar-25 A | 2026-03-19 | 2026-06-16 | 2026-06-16 | 2027-07-20 | 285
| A54160 | Piping Speciality Items_Approved Vendor Data Receipt |  |  |  |  | 0 |  |  | 26-Aug-25 A
| A54180 | Rigid Struts_Approved Vendor Data Receipt |  |  |  |  | 0 |  |  | 2026-02-20 | 2026-02-20 | 2026-03-19 | 20
| A54150 | Manual Valves_Approved Vendor Data Receipt |  |  |  |  | 0 |  |  | 2026-03-05 | 2026-03-05 | 2026-05-29 | 61
| A54140 | Piping Bulk_Approved Vendor Data Receipt |  |  |  |  | 0 |  |  | 2026-03-16 | 2026-03-16 | 2027-07-20 | 351
| A54170 | Spring Hangers_Approved Vendor Data Receipt |  |  |  |  | 0 |  |  | 2026-06-16 | 2026-06-16 | 2027-05-14 | 238
| A55640 | PSA Unit_Approved Vendor Data Receipt |  |  |  |  | 0 |  |  | 10-Jun-25 A
| A53450 | Heat Exchangers_Approved Vendor Data Receipt |  |  |  |  | 0 |  |  | 02-Sep-25 A
| A53490 | Pressure Vessels & Internals_Approved Vendor Data Receipt |  |  |  |  | 0 |  |  | 02-Sep-25 A
| A28150 | Compressors (FG & OG)_Approved Vendor Data Receipt |  |  |  |  | 0 |  |  | 19-Sep-25 A
| A53460 | Centrifugal Pump_Approved Vendor Data Receipt |  |  |  |  | 0 |  |  | 2026-02-20 | 2026-02-20 | 2026-03-19 | 20
| A53470 | EOT Crane_Approved Vendor Data Receipt |  |  |  |  | 0 |  |  | 2026-02-20 | 2026-02-20 | 2026-03-19 | 20
| A53480 | Coalscer_Approved Vendor Data Receipt |  |  |  |  | 0 |  |  | 2026-03-24 | 2026-03-24 | 2027-07-20 | 346
| A54230 | DC UPS_Approved Vendor Data Receipt |  |  |  |  | 0 |  |  | 2026-02-20 | 2026-02-20 | 2026-03-19 | 20
| A54270 | Emergency Diesel Generator Set_Approved Vendor Data Receipt |  |  |  |  | 0 |  |  | 2026-02-20 | 2026-02-20 | 2027-01-20 | 239
| A55650 | Notice to proceed - All Electrical equipment footprint & load data to freeze Electrical building Equipment layout |  |  |  |  | 0 |  |  | 2026-02-20 | 2026-02-20 | 2027-07-20 | 368
| A54190 | Transformer (Power And Distribution)_Approved Vendor Data Receipt |  |  |  |  | 0 |  |  | 2026-03-16 | 2026-03-16 | 2026-12-22 | 201
| A54200 | 11KV Switchgear_Approved Vendor Data Receipt |  |  |  |  | 0 |  |  | 2026-03-16 | 2026-03-16 | 2027-07-20 | 351
| A54210 | LV Switchgear_Approved Vendor Data Receipt |  |  |  |  | 0 |  |  | 2026-03-16 | 2026-03-16 | 2027-07-20 | 351
| A54220 | AC UPS_Approved Vendor Data Receipt |  |  |  |  | 0 |  |  | 2026-03-16 | 2026-03-16 | 2027-07-20 | 351
| A54240 | Capacitor Bank_Approved Vendor Data Receipt |  |  |  |  | 0 |  |  | 2026-03-16 | 2026-03-16 | 2027-07-20 | 351
| A54250 | Power, Control And Earthing Cables_Approved Vendor Data Receipt |  |  |  |  | 0 |  |  | 2026-03-16 | 2026-03-16 | 2027-07-20 | 351
| A54260 | Neutral Grounding Resistor_Approved Vendor Data Receipt |  |  |  |  | 0 |  |  | 2026-03-16 | 2026-03-16 | 2027-07-20 | 351
| A54280 | LV Variable Frequency Drive_Approved Vendor Data Receipt |  |  |  |  | 0 |  |  | 2026-03-16 | 2026-03-16 | 2027-07-20 | 351
| A54340 | Analyzers_Approved Vendor Data Receipt |  |  |  |  | 0 |  |  | 04-Mar-25 A
| A54370 | Fire & Gas Detectors_Approved Vendor Data Receipt |  |  |  |  | 0 |  |  | 09-Apr-25 A
| A54410 | Rotameter_Approved Vendor Data Receipt |  |  |  |  | 0 |  |  | 23-May-25 A
| A54330 | Temperature Gauges / Pressure Gauges_Approved Vendor Data Receipt |  |  |  |  | 0 |  |  | 29-May-25 A
| A55660 | Notice to proceed - All ICT equipment footprint & load data to freeze SIS Equipment layout |  |  |  |  | 0 |  |  | 23-Jun-25 A
| A54320 | Temperature Element / Thermowell_Approved Vendor Data Receipt |  |  |  |  | 0 |  |  | 2026-02-20 | 2026-02-20 | 2026-03-19 | 20
| A54420 | Instrument Cables_Approved Vendor Data Receipt |  |  |  |  | 0 |  |  | 2026-02-20 | 2026-02-20 | 2026-03-19 | 20
| A54450 | Fire Detection System & LFCP_Approved Vendor Data Receipt |  |  |  |  | 0 |  |  | 2026-02-20 | 2026-02-20 | 2026-03-19 | 20
| A54300 | Flow Element (Orifice Plate)_Approved Vendor Data Receipt |  |  |  |  | 0 |  |  | 2026-03-16 | 2026-03-16 | 2027-07-20 | 351
| A54310 | Flow Element (Venturi Tube)_Approved Vendor Data Receipt |  |  |  |  | 0 |  |  | 2026-03-16 | 2026-03-16 | 2027-07-20 | 351
| A54350 | Level Gauges (Magnetic Type)_Approved Vendor Data Receipt |  |  |  |  | 0 |  |  | 2026-03-16 | 2026-03-16 | 2027-07-20 | 351
| A54360 | Control Valves_Approved Vendor Data Receipt |  |  |  |  | 0 |  |  | 2026-03-16 | 2026-03-16 | 2027-07-20 | 351
| A54380 | Level Transmitters (GWR type)_Approved Vendor Data Receipt |  |  |  |  | 0 |  |  | 2026-03-16 | 2026-03-16 | 2027-07-20 | 351
| A54390 | Motor Operated Valves_Approved Vendor Data Receipt |  |  |  |  | 0 |  |  | 2026-03-16 | 2026-03-16 | 2027-07-20 | 351
| A54400 | ESD Valves_Approved Vendor Data Receipt |  |  |  |  | 0 |  |  | 2026-03-16 | 2026-03-16 | 2027-07-20 | 351
| A54440 | ICSS System_Approved Vendor Data Receipt |  |  |  |  | 0 |  |  | 2026-03-16 | 2026-03-16 | 2027-07-20 | 351
| A54430 | Junction Boxes_Approved Vendor Data Receipt |  |  |  |  | 0 |  |  | 2026-03-26 | 2026-03-26 | 2027-07-20 | 343
| A54290 | Electronic Transmitters_Approved Vendor Data Receipt |  |  |  |  | 0 |  |  | 2026-04-21 | 2026-04-21 | 2027-07-20 | 325
| A54470 | Telecom Cables_Approved Vendor Data Receipt |  |  |  |  | 0 |  |  | 2026-02-20 | 2026-02-20 | 2026-03-19 | 20
| A54460 | Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_Approved Vendor Data Receipt |  |  |  |  | 0 |  |  | 2026-03-16 | 2026-03-16 | 2027-07-20 | 351
| A54480 | HVAC Equipments_Approved Vendor Data Receipt |  |  |  |  | 0 |  |  | 2026-03-16 | 2026-03-16 | 2027-07-20 | 351
| Workshops / Studies / Model Reviews |  |  | 2026-02-20 |  |  | 182 | 05-May-25 A | 2026-03-02 | 2026-03-16 | 2026-03-16 | 2026-11-23 | 179
| A53350 | Design Review |  | 2026-02-20 |  |  | 3 | 05-May-25 A | 2026-03-02 | 09-May-25 A | 2026-02-20 | 2026-03-02
| A53370 | 30% Model Review |  | 2026-02-20 |  |  | 1 | 13-May-25 A | 2026-03-02 | 16-May-25 A | 2026-02-20 | 2026-03-02
| A53360 | Plot Plan Review |  | 2026-02-20 |  |  | 1 | 13-May-25 A | 2026-03-02 | 21-May-25 A | 2026-02-20 | 2026-03-02
| A25330 | PHA (HAZID/ENVID/OHID) |  | 2026-02-20 |  |  | 5 | 03-Jul-25 A | 2026-03-02 | 03-Jul-25 A | 2026-02-20 | 2026-03-02
| A25340 | ISD Workshop |  | 2026-02-20 |  |  | 1 | 04-Jul-25 A | 2026-04-02 | 04-Jul-25 A | 2026-02-20 | 2026-04-02
| A25350 | HAZOP |  | 2026-02-20 |  |  | 7 | 08-Jul-25 A | 2026-03-02 | 20-Jul-25 A | 2026-02-20 | 2026-03-02
| A55690 | Bow-Tie |  | 2026-02-20 |  |  | 1 | 12-Aug-25 A | 2026-03-02 | 12-Aug-25 A | 2026-02-20 | 2026-03-02
| A53260 | SIL/LOPA |  | 2026-02-20 |  |  | 2 | 17-Aug-25 A | 2026-03-02 | 20-Aug-25 A | 2026-02-20 | 2026-03-02
| A55730 | Constructability Review |  | 2026-02-20 |  |  | 1 | 27-Aug-25 A | 2026-03-19 | 27-Aug-25 A | 2026-02-20 | 2026-03-19
| A55720 | SIMOPS |  | 2026-02-20 |  |  | 1 | 28-Aug-25 A | 2026-03-19 | 28-Aug-25 A | 2026-02-20 | 2026-03-19
| A53380 | 60% Model Review |  | 2026-02-20 |  |  | 17 | 08-Sep-25 A | 2026-03-02 | 18-Sep-25 A | 2026-02-20 | 2026-03-02
| A55680 | HSEIA Screening |  | 2026-02-20 |  |  | 1 | 01-Jan-26 A | 2026-04-02 | 06-Jan-26 A | 2026-02-20 | 2026-04-02
| A55700 | E-HAZOP |  | 2026-02-20 |  |  | 1 | 2026-02-20 | 2026-03-17 | 2026-02-23 | 2026-02-23 | 2026-03-18 | 18
| A55710 | ALARP Demonstration |  | 2026-02-20 |  |  | 1 | 2026-02-20 | 2026-03-26 | 2026-02-23 | 2026-02-23 | 2026-03-27 | 24
| A53270 | Energy Review |  | 2026-02-23 |  |  | 1 | 2026-02-23 | 2026-03-18 | 2026-02-24 | 2026-02-24 | 2026-03-19 | 18
| A53390 | 90% Model Review |  | 2026-02-26 |  |  | 6 | 2026-02-26 | 2026-03-19 | 2026-03-06 | 2026-03-06 | 2026-03-27 | 15
| A53250 | PHSER-3 |  | 2026-03-13 |  |  | 1 | 2026-03-13 | 2026-11-20 | 2026-03-16 | 2026-03-16 | 2026-11-23 | 179
| Turnaround (TA) |  |  | 2026-02-20 |  |  | 208 | 27-Nov-24 A | 2026-02-21 | 21-Jun-25 A | 2026-02-20 | 2026-03-27
| TA - Engineering Workpack |  |  | 2026-02-20 |  |  | 202 | 27-Nov-24 A | 2026-03-27 | 12-Apr-25 A | 2026-02-20 | 2026-03-27
| B1-DE-TA-TAD-0001 | Verify TA Dossier & Provid List of Missing Materials to EPC Contractor |  | 2026-02-20 |  |  | 17 | 07-Jan-25 A | 2026-03-27 | 27-Mar-25 A | 2026-02-20 | 2026-03-27
| B1-DE-TA-TAD-0002 | Engineering Support During Pre-TA & TA Phase |  |  |  |  | 53 | 17-Jan-25 A |  | 12-Apr-25 A
| Piping Driven - Workpack |  |  | 2026-02-20 |  |  | 28 | 27-Nov-24 A | 2026-03-27 | 10-Feb-25 A | 2026-02-20 | 2026-03-27
| Preliminary Workpack |  |  | 2026-02-20 |  |  | 5 | 27-Nov-24 A | 2026-03-27 | 13-Jan-25 A | 2026-02-20 | 2026-03-27
| B1-DE-TA-PIP-0019 | Workpack Piping Nos. 0019 Preliminary Issuance |  | 2026-02-20 |  |  | 1 | 27-Nov-24 A | 2026-03-27 | 18-Dec-24 A | 2026-02-20 | 2026-03-27
| B1-DE-TA-PIP-0020 | Workpack Piping Nos. 0020 Preliminary Issuance |  | 2026-02-20 |  |  | 1 | 27-Nov-24 A | 2026-03-27 | 18-Dec-24 A | 2026-02-20 | 2026-03-27
| B1-DE-TA-PIP-0021 | Workpack Piping Nos. 0021 Preliminary Issuance |  | 2026-02-20 |  |  | 1 | 27-Nov-24 A | 2026-03-27 | 18-Dec-24 A | 2026-02-20 | 2026-03-27
| B1-DE-TA-PIP-0022 | Workpack Piping Nos. 0022 Preliminary Issuance |  | 2026-02-20 |  |  | 1 | 27-Nov-24 A | 2026-03-27 | 18-Dec-24 A | 2026-02-20 | 2026-03-27
| B1-DE-TA-PIP-0023 | Workpack Piping Nos. 0023 Preliminary Issuance |  | 2026-02-20 |  |  | 1 | 27-Nov-24 A | 2026-03-27 | 18-Dec-24 A | 2026-02-20 | 2026-03-27
| B1-DE-TA-PIP-0024 | Workpack Piping Nos. 0024 Preliminary Issuance |  | 2026-02-20 |  |  | 1 | 27-Nov-24 A | 2026-03-27 | 18-Dec-24 A | 2026-02-20 | 2026-03-27
| B1-DE-TA-PIP-0025 | Workpack Piping Nos. 0025 Preliminary Issuance |  | 2026-02-20 |  |  | 1 | 27-Nov-24 A | 2026-03-27 | 18-Dec-24 A | 2026-02-20 | 2026-03-27
| B1-DE-TA-PIP-0026 | Workpack Piping Nos. 0026 Preliminary Issuance |  | 2026-02-20 |  |  | 1 | 27-Nov-24 A | 2026-03-27 | 18-Dec-24 A | 2026-02-20 | 2026-03-27
| B1-DE-TA-PIP-0027 | Workpack Piping Nos. 0025 Preliminary Issuance |  | 2026-02-20 |  |  | 1 | 27-Nov-24 A | 2026-03-27 | 18-Dec-24 A | 2026-02-20 | 2026-03-27
| B1-DE-TA-PIP-0028 | Workpack Piping Nos. 0026 Preliminary Issuance |  | 2026-02-20 |  |  | 1 | 27-Nov-24 A | 2026-03-27 | 18-Dec-24 A | 2026-02-20 | 2026-03-27
| B1-DE-TA-PIP-0029 | Workpack Piping Nos. 0027 Preliminary Issuance |  | 2026-02-20 |  |  | 1 | 27-Nov-24 A | 2026-03-27 | 18-Dec-24 A | 2026-02-20 | 2026-03-27
| B1-DE-TA-PIP-0030 | Workpack Piping Nos. 0028 Preliminary Issuance |  | 2026-02-20 |  |  | 1 | 27-Nov-24 A | 2026-03-27 | 18-Dec-24 A | 2026-02-20 | 2026-03-27
| B1-DE-TA-PIP-0031 | Workpack Piping Nos. 0029 Preliminary Issuance |  | 2026-02-20 |  |  | 1 | 27-Nov-24 A | 2026-03-27 | 18-Dec-24 A | 2026-02-20 | 2026-03-27
| B1-DE-TA-PIP-0032 | Workpack Piping Nos. 0030 Preliminary Issuance |  | 2026-02-20 |  |  | 1 | 17-Dec-24 A | 2026-03-27 | 07-Jan-25 A | 2026-02-20 | 2026-03-27
| B1-DE-TA-PIP-0033 | Workpack Piping Nos. 0031 Preliminary Issuance |  | 2026-02-20 |  |  | 1 | 17-Dec-24 A | 2026-03-27 | 07-Jan-25 A | 2026-02-20 | 2026-03-27
| B1-DE-TA-PIP-0034 | Workpack Piping Nos. 0032 Preliminary Issuance |  | 2026-02-20 |  |  | 1 | 17-Dec-24 A | 2026-03-27 | 07-Jan-25 A | 2026-02-20 | 2026-03-27
| B1-DE-TA-PIP-0035 | Workpack Piping Nos. 0033 Preliminary Issuance |  | 2026-02-20 |  |  | 1 | 17-Dec-24 A | 2026-03-27 | 07-Jan-25 A | 2026-02-20 | 2026-03-27
| B1-DE-TA-PIP-0036 | Workpack Piping Nos. 0034 Preliminary Issuance |  | 2026-02-20 |  |  | 1 | 17-Dec-24 A | 2026-03-27 | 07-Jan-25 A | 2026-02-20 | 2026-03-27
| B1-DE-TA-PIP-0037 | Workpack Piping Nos. 0035 Preliminary Issuance |  | 2026-02-20 |  |  | 1 | 17-Dec-24 A | 2026-03-27 | 07-Jan-25 A | 2026-02-20 | 2026-03-27
| B1-DE-TA-PIP-0038 | Workpack Piping Nos. 0036 Preliminary Issuance |  | 2026-02-20 |  |  | 1 | 17-Dec-24 A | 2026-03-27 | 07-Jan-25 A | 2026-02-20 | 2026-03-27
| B1-DE-TA-PIP-0039 | Workpack Piping Nos. 0037 Preliminary Issuance |  | 2026-02-20 |  |  | 1 | 17-Dec-24 A | 2026-03-27 | 07-Jan-25 A | 2026-02-20 | 2026-03-27
| B1-DE-TA-PIP-0040 | Workpack Piping Nos. 0038 Preliminary Issuance |  | 2026-02-20 |  |  | 1 | 17-Dec-24 A | 2026-03-27 | 07-Jan-25 A | 2026-02-20 | 2026-03-27
| B1-DE-TA-PIP-0041 | Workpack Piping Nos. 0039 Preliminary Issuance |  | 2026-02-20 |  |  | 1 | 17-Dec-24 A | 2026-03-27 | 07-Jan-25 A | 2026-02-20 | 2026-03-27
| B1-DE-TA-PIP-0042 | Workpack Piping Nos. 0040 Preliminary Issuance |  | 2026-02-20 |  |  | 1 | 17-Dec-24 A | 2026-03-27 | 07-Jan-25 A | 2026-02-20 | 2026-03-27
| B1-DE-TA-PIP-0043 | Workpack Piping Nos. 0041 Preliminary Issuance |  | 2026-02-20 |  |  | 1 | 23-Dec-24 A | 2026-03-27 | 13-Jan-25 A | 2026-02-20 | 2026-03-27
| B1-DE-TA-PIP-0044 | Workpack Piping Nos. 0042 Preliminary Issuance |  | 2026-02-20 |  |  | 1 | 23-Dec-24 A | 2026-03-27 | 13-Jan-25 A | 2026-02-20 | 2026-03-27
| B1-DE-TA-PIP-0045 | Workpack Piping Nos. 0003 Preliminary Issuance |  | 2026-02-20 |  |  | 1 | 23-Dec-24 A | 2026-03-27 | 13-Jan-25 A | 2026-02-20 | 2026-03-27
| B1-DE-TA-PIP-0046 | Workpack Nos. 41 to 52 - Preliminary Issuance |  | 2026-02-20 |  |  | 1 | 23-Dec-24 A | 2026-03-27 | 13-Jan-25 A | 2026-02-20 | 2026-03-27
| B1-DE-TA-PIP-0047 | Workpack Nos. 41 to 52 - Preliminary Issuance |  | 2026-02-20 |  |  | 1 | 23-Dec-24 A | 2026-03-27 | 13-Jan-25 A | 2026-02-20 | 2026-03-27
| B1-DE-TA-PIP-0048 | Workpack Nos. 41 to 52 - Preliminary Issuance |  | 2026-02-20 |  |  | 1 | 23-Dec-24 A | 2026-03-27 | 13-Jan-25 A | 2026-02-20 | 2026-03-27
| B1-DE-TA-PIP-0049 | Workpack Nos. 41 to 52 - Preliminary Issuance |  | 2026-02-20 |  |  | 1 | 23-Dec-24 A | 2026-03-27 | 13-Jan-25 A | 2026-02-20 | 2026-03-27
| B1-DE-TA-PIP-0050 | Workpack Nos. 41 to 52 - Preliminary Issuance |  | 2026-02-20 |  |  | 1 | 23-Dec-24 A | 2026-03-27 | 13-Jan-25 A | 2026-02-20 | 2026-03-27
| B1-DE-TA-PIP-0051 | Workpack Nos. 41 to 52 - Preliminary Issuance |  | 2026-02-20 |  |  | 1 | 23-Dec-24 A | 2026-03-27 | 13-Jan-25 A | 2026-02-20 | 2026-03-27
| B1-DE-TA-PIP-0052 | Workpack Nos. 41 to 52 - Preliminary Issuance |  | 2026-02-20 |  |  | 1 | 23-Dec-24 A | 2026-03-27 | 13-Jan-25 A | 2026-02-20 | 2026-03-27
| Final Workpack |  |  | 2026-02-20 |  |  | 10 | 19-Dec-24 A | 2026-03-27 | 10-Feb-25 A | 2026-02-20 | 2026-03-27
| A40430 | Workpack Nos. 1 to 10 - Final Issuance |  | 2026-02-20 |  |  | 2 | 19-Dec-24 A | 2026-03-27 | 15-Jan-25 A | 2026-02-20 | 2026-03-27
| A40440 | Workpack Nos. 11 to 20 - Final Issuance |  | 2026-02-20 |  |  | 2 | 19-Dec-24 A | 2026-03-27 | 15-Jan-25 A | 2026-02-20 | 2026-03-27
| A40450 | Workpack Nos. 21 to 30 - Final Issuance |  | 2026-02-20 |  |  | 2 | 08-Jan-25 A | 2026-03-27 | 06-Feb-25 A | 2026-02-20 | 2026-03-27
| A40460 | Workpack Nos. 31 to 40 - Final Issuance |  | 2026-02-20 |  |  | 2 | 08-Jan-25 A | 2026-03-27 | 06-Feb-25 A | 2026-02-20 | 2026-03-27
| A40470 | Workpack Nos. 41 to 52 - Final Issuance |  | 2026-02-20 |  |  | 2 | 24-Dec-24 A | 2026-03-27 | 10-Feb-25 A | 2026-02-20 | 2026-03-27
| ICT Driven - Workpack |  |  | 2026-02-20 |  |  | 40 | 02-Jan-25 A | 2026-03-27 | 20-Jan-25 A | 2026-02-20 | 2026-03-27
| A40480 | Workpack Nos. 53 to 56 - Preliminary Issuance |  | 2026-02-20 |  |  | 1 | 02-Jan-25 A | 2026-03-27 | 07-Jan-25 A | 2026-02-20 | 2026-03-27
| A40490 | Workpack Nos. 57 to 59 - Preliminary Issuance |  | 2026-02-20 |  |  | 1 | 02-Jan-25 A | 2026-03-27 | 07-Jan-25 A | 2026-02-20 | 2026-03-27
| A40500 | Workpack Nos. 60 to 63 - Preliminary Issuance |  | 2026-02-20 |  |  | 1 | 02-Jan-25 A | 2026-03-27 | 07-Jan-25 A | 2026-02-20 | 2026-03-27
| A40510 | Workpack Nos. 64 to 67 - Preliminary Issuance |  | 2026-02-20 |  |  | 1 | 06-Jan-25 A | 2026-03-27 | 16-Jan-25 A | 2026-02-20 | 2026-03-27
| A40520 | Workpack Nos. 68 to 70 - Preliminary Issuance |  | 2026-02-20 |  |  | 1 | 06-Jan-25 A | 2026-03-27 | 16-Jan-25 A | 2026-02-20 | 2026-03-27
| A40530 | Workpack Nos. 53 to 56 - Final Issuance |  | 2026-02-20 |  |  | 2 | 08-Jan-25 A | 2026-03-27 | 16-Jan-25 A | 2026-02-20 | 2026-03-27
| A40540 | Workpack Nos. 57 to 59 - Final Issuance |  | 2026-02-20 |  |  | 2 | 08-Jan-25 A | 2026-03-27 | 16-Jan-25 A | 2026-02-20 | 2026-03-27
| A40550 | Workpack Nos. 60 to 63 - Final Issuance |  | 2026-02-20 |  |  | 2 | 08-Jan-25 A | 2026-03-27 | 16-Jan-25 A | 2026-02-20 | 2026-03-27
| A40560 | Workpack Nos. 64 to 67 - Final Issuance |  | 2026-02-20 |  |  | 2 | 17-Jan-25 A | 2026-03-27 | 20-Jan-25 A | 2026-02-20 | 2026-03-27
| A40570 | Workpack Nos. 68 to 70 - Final Issuance |  | 2026-02-20 |  |  | 2 | 17-Jan-25 A | 2026-03-27 | 20-Jan-25 A | 2026-02-20 | 2026-03-27
| Civil/Structural/Architectural Driven - Workpack |  |  | 2026-02-20 |  |  | 21 | 31-Dec-24 A | 2026-03-27 | 29-Jan-25 A | 2026-02-20 | 2026-03-27
| A40580 | Workpack No. 71 - Preliminary Issuance |  | 2026-02-20 |  |  | 3 | 31-Dec-24 A | 2026-03-27 | 03-Jan-25 A | 2026-02-20 | 2026-03-27
| A40590 | Workpack Nos. 72 - Preliminary Issuance |  | 2026-02-20 |  |  | 2 | 01-Jan-25 A | 2026-03-27 | 06-Jan-25 A | 2026-02-20 | 2026-03-27
| A40600 | Workpack No. 71 - Final Issuance |  | 2026-02-20 |  |  | 3 | 04-Jan-25 A | 2026-03-27 | 16-Jan-25 A | 2026-02-20 | 2026-03-27
| A40610 | Workpack No. 72 - Final Issuance |  | 2026-02-20 |  |  | 2 | 29-Jan-25 A | 2026-03-27 | 29-Jan-25 A | 2026-02-20 | 2026-03-27
| Electrical Driven - Workpack |  |  | 2026-02-20 |  |  | 41 | 27-Dec-24 A | 2026-03-27 | 17-Jan-25 A | 2026-02-20 | 2026-03-27
| A40650 | Workpack Nos. 73 - Preliminary Issuance |  | 2026-02-20 |  |  | 2 | 27-Dec-24 A | 2026-03-27 | 02-Jan-25 A | 2026-02-20 | 2026-03-27
| A40660 | Workpack Nos. 74 - Preliminary Issuance |  | 2026-02-20 |  |  | 2 | 27-Dec-24 A | 2026-03-27 | 02-Jan-25 A | 2026-02-20 | 2026-03-27
| A40670 | Workpack Nos. 75 - Preliminary Issuance |  | 2026-02-20 |  |  | 1 | 27-Dec-24 A | 2026-03-27 | 02-Jan-25 A | 2026-02-20 | 2026-03-27
| A40620 | Workpack No. 73 - Final Issuance |  | 2026-02-20 |  |  | 3 | 03-Jan-25 A | 2026-03-27 | 17-Jan-25 A | 2026-02-20 | 2026-03-27
| A40630 | Workpack No. 74 - Final Issuance |  | 2026-02-20 |  |  | 5 | 03-Jan-25 A | 2026-03-27 | 17-Jan-25 A | 2026-02-20 | 2026-03-27
| A40640 | Workpack No. 75 - Final Issuance |  | 2026-02-20 |  |  | 3 | 03-Jan-25 A | 2026-03-27 | 17-Jan-25 A | 2026-02-20 | 2026-03-27
| Subcontracting Support |  |  | 2026-02-20 |  |  | 108 | 01-Jan-25 A | 2026-02-21 | 21-Jun-25 A | 2026-02-20 | 2026-03-27
| SOW & Requisition for ICT System Modification |  |  | 2026-02-20 |  |  | 23 | 15-Jan-25 A | 2026-03-27 | 28-Feb-25 A | 2026-02-20 | 2026-03-27
| A56050 | SOW & Requisition for ICT System Modification_IFR |  | 2026-02-20 |  |  | 6 | 15-Jan-25 A | 2026-03-27 | 30-Jan-25 A | 2026-02-20 | 2026-03-27
| A56060 | SOW & Requisition for ICT System Modification_RCC |  | 2026-02-20 |  |  | 16 | 31-Jan-25 A | 2026-03-27 | 12-Feb-25 A | 2026-02-20 | 2026-03-27
| A56070 | SOW & Requisition for ICT System Modification_IFD/IFC |  | 2026-02-20 |  |  | 6 | 13-Feb-25 A | 2026-03-27 | 28-Feb-25 A | 2026-02-20 | 2026-03-27
| SOW & Requisition for Electrical System Modification |  |  | 2026-02-20 |  |  | 23 | 07-Jan-25 A | 2026-03-27 | 14-Feb-25 A | 2026-02-20 | 2026-03-27
| A56080 | SOW & Requisition for Electrical System Modification_IFR |  | 2026-02-20 |  |  | 6 | 07-Jan-25 A | 2026-03-27 | 22-Jan-25 A | 2026-02-20 | 2026-03-27
| A56090 | SOW & Requisition for Electrical System Modification_RCC |  | 2026-02-20 |  |  | 16 | 23-Jan-25 A | 2026-03-27 | 31-Jan-25 A | 2026-02-20 | 2026-03-27
| A56100 | SOW & Requisition for Electrical System Modification_IFD/IFC |  | 2026-02-20 |  |  | 6 | 03-Feb-25 A | 2026-03-27 | 14-Feb-25 A | 2026-02-20 | 2026-03-27
| SOW & Requisition for Topo & UG survey |  |  | 2026-02-20 |  |  | 23 | 01-Jan-25 A | 2026-02-21 | 05-Feb-25 A | 2026-02-20 | 2026-02-21
| A56110 | SOW & Requisition for Topo & UG survey_IFR |  | 2026-02-20 |  |  | 6 | 01-Jan-25 A | 2026-02-21 | 09-Jan-25 A | 2026-02-20 | 2026-02-21
| A56120 | SOW & Requisition for Topo & UG survey_RCC |  | 2026-02-20 |  |  | 16 | 13-Jan-25 A | 2026-02-21 | 24-Jan-25 A | 2026-02-20 | 2026-02-21
| A28870 | SOW & Requisition for Topo & UG survey_IFD/IFC |  | 2026-02-20 |  |  | 6 | 27-Jan-25 A | 2026-02-21 | 05-Feb-25 A | 2026-02-20 | 2026-02-21
| SOW & Requisition for Geotechnical investigation |  |  | 2026-02-20 |  |  | 23 | 01-Jan-25 A | 2026-02-21 | 05-Feb-25 A | 2026-02-20 | 2026-02-21
| A56130 | SOW & Requisition for Geotechnical investigation_IFR |  | 2026-02-20 |  |  | 6 | 01-Jan-25 A | 2026-02-21 | 09-Jan-25 A | 2026-02-20 | 2026-02-21
| A56140 | SOW & Requisition for Geotechnical investigation_RCC |  | 2026-02-20 |  |  | 16 | 13-Jan-25 A | 2026-02-21 | 24-Jan-25 A | 2026-02-20 | 2026-02-21
| A56150 | SOW & Requisition for Geotechnical investigation_IFD/IFC |  | 2026-02-20 |  |  | 6 | 27-Jan-25 A | 2026-02-21 | 05-Feb-25 A | 2026-02-20 | 2026-02-21
| SOW & Requisition for Third party HSE studies |  |  | 2026-02-20 |  |  | 39 | 30-Jan-25 A | 2026-03-02 | 01-Jun-25 A | 2026-02-20 | 2026-03-02
| A56160 | SOW & Requisition for HSE third party studies_IFR |  | 2026-02-20 |  |  | 6 | 30-Jan-25 A | 2026-03-02 | 20-Feb-25 A | 2026-02-20 | 2026-03-02
| A56170 | SOW & Requisition for HSE third party studies_RCC |  | 2026-02-20 |  |  | 16 | 21-Feb-25 A | 2026-03-02 | 27-Feb-25 A | 2026-02-20 | 2026-03-02
| A56180 | SOW & Requisition for HSE third party studies_IFD/IFC |  | 2026-02-20 |  |  | 17 | 28-Feb-25 A | 2026-03-02 | 01-Jun-25 A | 2026-02-20 | 2026-03-02
| Technical Bid Evaluation for Third Party HSE Studies |  |  | 2026-02-20 |  |  | 31 | 25-Feb-25 A | 2026-03-02 | 21-Jun-25 A | 2026-02-20 | 2026-03-02
| A55960 | Technical Bid Evaluation for Third Party HSE Studies_RCA |  | 2026-02-20 |  |  | 16 | 19-Mar-25 A | 2026-03-02 | 04-Jun-25 A | 2026-02-20 | 2026-03-02
| A55970 | Technical Bid Evaluation for Third Party HSE Studies_IFD/IFC |  | 2026-02-20 |  |  | 11 | 05-Jun-25 A | 2026-03-02 | 21-Jun-25 A | 2026-02-20 | 2026-03-02
| MTO Support |  |  | 2026-02-20 |  |  | 122 | 01-Feb-25 A | 2026-03-19 | 07-Mar-25 A | 2026-02-20 | 2026-03-27
| A40730 | Issue Preliminary MTO for ICT Bulks |  | 2026-02-20 |  |  | 6 | 01-Feb-25 A | 2026-03-27 | 07-Feb-25 A | 2026-02-20 | 2026-03-27
| A40750 | Issue Final MTO for Piping Bulks |  | 2026-02-20 |  |  | 6 | 10-Feb-25 A | 2026-03-27 | 19-Feb-25 A | 2026-02-20 | 2026-03-27
| A40740 | Issue Preliminary MTO for Electrical Bulks |  | 2026-02-20 |  |  | 6 | 13-Feb-25 A | 2026-03-27 | 26-Feb-25 A | 2026-02-20 | 2026-03-27
| A40780 | Issue Final MTO for Electrical Bulks |  | 2026-02-20 |  |  | 6 | 17-Feb-25 A | 2026-03-27 | 27-Feb-25 A | 2026-02-20 | 2026-03-27
| A40710 | Issue Preliminary MTO for Piping Bulks |  | 2026-02-20 |  |  | 6 | 18-Feb-25 A | 2026-03-27 | 28-Feb-25 A | 2026-02-20 | 2026-03-27
| A40760 | Issue Final MTO for Structural Steel Bulks |  | 2026-02-20 |  |  | 7 | 24-Feb-25 A | 2026-03-27 | 28-Feb-25 A | 2026-02-20 | 2026-03-27
| A40770 | Issue Final MTO for ICT Bulks |  | 2026-02-20 |  |  | 6 | 14-Feb-25 A | 2026-03-27 | 07-Mar-25 A | 2026-02-20 | 2026-03-27
| Master Deliverable Register (MDR) |  |  | 2026-02-20 |  |  | 39 | 28-Nov-24 A | 2026-03-02 | 16-Jan-25 A | 2026-02-20 | 2027-01-20
| A40800 | Master Deliverable Register (MDR)_RCC |  | 2026-02-20 |  |  | 16 | 19-Dec-24 A | 2027-01-20 | 26-Dec-24 A | 2026-02-20 | 2027-01-20
| A40810 | Master Deliverable Register (MDR)_IFA |  | 2026-02-20 |  |  | 3 | 27-Dec-24 A | 2027-01-20 | 02-Jan-25 A | 2026-02-20 | 2027-01-20
| A40820 | Master Deliverable Register (MDR)_RCA |  | 2026-02-20 |  |  | 16 | 03-Jan-25 A | 2027-01-20 | 09-Jan-25 A | 2026-02-20 | 2027-01-20
| A40830 | Master Deliverable Register (MDR)_IFD/IFC |  | 2026-02-20 |  |  | 2 | 10-Jan-25 A | 2027-01-20 | 16-Jan-25 A | 2026-02-20 | 2027-01-20
| Planning Package / EDDR |  |  | 2026-02-20 |  |  | 81 | 01-Jan-25 A | 2027-01-20 | 13-Apr-25 A | 2026-02-20 | 2027-01-20
| A40850 | Planning Package / EDDR_RCC |  | 2026-02-20 |  |  | 16 | 23-Jan-25 A | 2027-01-20 | 21-Mar-25 A | 2026-02-20 | 2027-01-20
| A40860 | Planning Package / EDDR_IFA |  | 2026-02-20 |  |  | 3 | 22-Mar-25 A | 2027-01-20 | 29-Mar-25 A | 2026-02-20 | 2027-01-20
| A40870 | Planning Package / EDDR_RCA |  | 2026-02-20 |  |  | 58 | 30-Mar-25 A | 2027-01-20 | 04-Apr-25 A | 2026-02-20 | 2027-01-20
| A40880 | Planning Package / EDDR_IFD/IFC |  | 2026-02-20 |  |  | 2 | 07-Apr-25 A | 2027-01-20 | 13-Apr-25 A | 2026-02-20 | 2027-01-20
| Project Execution Plan |  |  | 2026-02-20 |  |  | 193 | 03-Mar-25 A | 2026-06-26 | 01-Sep-25 A | 2026-02-20 | 2026-06-26
| A40890 | Project Execution Plan_IFR |  | 2026-02-20 |  |  | 6 | 03-Mar-25 A | 2026-06-26 | 22-Mar-25 A | 2026-02-20 | 2026-06-26
| A40900 | Project Execution Plan_RCC |  | 2026-02-20 |  |  | 16 | 23-Mar-25 A | 2026-06-26 | 29-Mar-25 A | 2026-02-20 | 2026-06-26
| A40910 | Project Execution Plan_IFA |  | 2026-02-20 |  |  | 3 | 30-Mar-25 A | 2026-06-26 | 05-Apr-25 A | 2026-02-20 | 2026-06-26
| A40920 | Project Execution Plan_RCA |  | 2026-02-20 |  |  | 6 | 31-Mar-25 A | 2026-06-26 | 06-Apr-25 A | 2026-02-20 | 2026-06-26
| A40930 | Project Execution Plan_IFD/IFC |  | 2026-02-20 |  |  | 2 | 31-Aug-25 A | 2026-06-26 | 01-Sep-25 A | 2026-02-20 | 2026-06-26
| FEED Verification Report |  |  | 2026-02-20 |  |  | 117 | 27-Mar-25 A | 2026-03-02 | 15-May-25 A | 2026-02-20 | 2027-01-20
| A40950 | FEED Verification Report_RCC |  | 2026-02-20 |  |  | 11 | 07-Apr-25 A | 2026-03-02 | 18-Apr-25 A | 2026-02-20 | 2026-03-02
| A40960 | FEED Verification Report_IFA |  | 2026-02-20 |  |  | 3 | 21-Apr-25 A | 2027-01-20 | 30-Apr-25 A | 2026-02-20 | 2027-01-20
| A40970 | FEED Verification Report_RCA |  | 2026-02-20 |  |  | 16 | 01-May-25 A | 2027-01-20 | 08-May-25 A | 2026-02-20 | 2027-01-20
| A40980 | FEED Verification Report_IFD/IFC |  | 2026-02-20 |  |  | 2 | 02-May-25 A | 2027-01-20 | 15-May-25 A | 2026-02-20 | 2027-01-20
| Site Visit Report for BOP |  |  | 2026-02-20 |  |  | 42 | 15-Mar-25 A | 2026-03-02 | 20-Jun-25 A | 2026-02-20 | 2026-03-02
| A41000 | Site Visit Report for BOP_RCC |  | 2026-02-20 |  |  | 16 | 23-Mar-25 A | 2026-03-02 | 29-Mar-25 A | 2026-02-20 | 2026-03-02
| A41010 | Site Visit Report for BOP_IFA |  | 2026-02-20 |  |  | 3 | 30-Mar-25 A | 2026-03-02 | 05-Apr-25 A | 2026-02-20 | 2026-03-02
| A41020 | Site Visit Report for BOP_RCA |  | 2026-02-20 |  |  | 16 | 06-Apr-25 A | 2026-03-02 | 13-Jun-25 A | 2026-02-20 | 2026-03-02
| A41030 | Site Visit Report for BOP_IFD/IFC |  | 2026-02-20 |  |  | 2 | 14-Jun-25 A | 2026-03-02 | 20-Jun-25 A | 2026-02-20 | 2026-03-02
| Project Risk Register |  |  | 2026-02-20 |  |  | 173 | 21-Feb-25 A | 2027-01-20 | 13-Sep-25 A | 2026-02-20 | 2027-01-20
| A41040 | Project Risk Register_IFR |  | 2026-02-20 |  |  | 17 | 21-Feb-25 A | 2027-01-20 | 10-Jun-25 A | 2026-02-20 | 2027-01-20
| A41050 | Project Risk Register_RCC |  | 2026-02-20 |  |  | 24 | 30-Jul-25 A | 2027-01-20 | 24-Aug-25 A | 2026-02-20 | 2027-01-20
| A41060 | Project Risk Register_IFA |  | 2026-02-20 |  |  | 17 | 13-Aug-25 A | 2027-01-20 | 31-Aug-25 A | 2026-02-20 | 2027-01-20
| A41070 | Project Risk Register_RCA |  | 2026-02-20 |  |  | 16 | 20-Aug-25 A | 2027-01-20 | 06-Sep-25 A | 2026-02-20 | 2027-01-20
| A41080 | Project Risk Register_IFD/IFC |  | 2026-02-20 |  |  | 17 | 26-Aug-25 A | 2027-01-20 | 13-Sep-25 A | 2026-02-20 | 2027-01-20
| Project Lesson Learnt Register |  |  | 2026-02-20 |  |  | 137 | 09-Jan-25 A | 2027-01-20 | 14-Sep-25 A | 2026-02-20 | 2027-01-20
| A41090 | Project Lesson Learnt Register_IFR |  | 2026-02-20 |  |  | 6 | 09-Jan-25 A | 2027-01-20 | 10-Jun-25 A | 2026-02-20 | 2027-01-20
| A1890 | Project Lesson Learnt Register_RCC |  | 2026-02-20 |  |  | 16 | 01-Aug-25 A | 2027-01-20 | 24-Aug-25 A | 2026-02-20 | 2027-01-20
| A1900 | Project Lesson Learnt Register_IFA |  | 2026-02-20 |  |  | 3 | 08-Aug-25 A | 2027-01-20 | 30-Aug-25 A | 2026-02-20 | 2027-01-20
| A1910 | Project Lesson Learnt Register_RCA |  | 2026-02-20 |  |  | 16 | 28-Aug-25 A | 2027-01-20 | 06-Sep-25 A | 2026-02-20 | 2027-01-20
| A1920 | Project Lesson Learnt Register_IFD/IFC |  | 2026-02-20 |  |  | 2 | 10-Sep-25 A | 2027-01-20 | 14-Sep-25 A | 2026-02-20 | 2027-01-20
| Criticality Rating Report |  |  | 2026-02-20 |  |  | 127 | 21-Jun-25 A | 2027-01-20 | 13-Sep-25 A | 2026-02-20 | 2027-01-20
| A1940 | Criticality Rating Report_RCC |  | 2026-02-20 |  |  | 16 | 08-Aug-25 A | 2027-01-20 | 24-Aug-25 A | 2026-02-20 | 2027-01-20
| A1950 | Criticality Rating Report_IFA |  | 2026-02-20 |  |  | 3 | 21-Aug-25 A | 2027-01-20 | 30-Aug-25 A | 2026-02-20 | 2027-01-20
| A1960 | Criticality Rating Report_RCA |  | 2026-02-20 |  |  | 16 | 20-Aug-25 A | 2027-01-20 | 06-Sep-25 A | 2026-02-20 | 2027-01-20
| A1970 | Criticality Rating Report_IFD/IFC |  | 2026-02-20 |  |  | 2 | 10-Sep-25 A | 2027-01-20 | 13-Sep-25 A | 2026-02-20 | 2027-01-20
| Project Close Out Report |  |  | 2026-03-23 |  |  | 38 | 2026-03-23 | 2026-11-27 | 2026-05-14 | 2026-05-14 | 2027-01-20 | 179
| A41110 | Project Close Out Report_RCC |  | 2026-03-25 |  |  | 16 | 2026-03-25 | 2026-12-02 | 2026-04-16 | 2026-04-16 | 2026-12-23 | 179
| A41120 | Project Close Out Report_IFA |  | 2026-04-16 |  |  | 3 | 2026-04-16 | 2026-12-23 | 2026-04-21 | 2026-04-21 | 2026-12-29 | 179
| A41130 | Project Close Out Report_RCA |  | 2026-04-21 |  |  | 16 | 2026-04-21 | 2026-12-29 | 2026-05-13 | 2026-05-13 | 2027-01-19 | 179
| A41140 | Project Close Out Report_IFD/IFC |  | 2026-05-13 |  |  | 1 | 2026-05-13 | 2027-01-19 | 2026-05-14 | 2026-05-14 | 2027-01-20 | 179
| Energy Review Closeout Report |  |  | 2026-02-24 |  |  | 48 | 2026-02-24 | 2026-11-13 | 2026-05-01 | 2026-05-01 | 2027-01-20 | 188
| A41160 | Energy Review Closeout Report_RCC |  | 2026-03-11 |  |  | 16 | 2026-03-11 | 2026-11-30 | 2026-04-02 | 2026-04-02 | 2026-12-22 | 188
| A41170 | Energy Review Closeout Report_IFA |  | 2026-04-02 |  |  | 3 | 2026-04-02 | 2026-12-22 | 2026-04-07 | 2026-04-07 | 2026-12-25 | 188
| A41180 | Energy Review Closeout Report_RCA |  | 2026-04-07 |  |  | 16 | 2026-04-07 | 2026-12-28 | 2026-04-29 | 2026-04-29 | 2027-01-18 | 188
| A41190 | Energy Review Closeout Report_IFD/IFC |  | 2026-04-29 |  |  | 2 | 2026-04-29 | 2027-01-18 | 2026-05-01 | 2026-05-01 | 2027-01-20 | 188
| Process |  |  | 2026-02-20 |  |  | 354 | 27-Dec-24 A | 2026-03-02 | 2026-04-23 | 2026-04-23 | 2027-01-20 | 194
| Utility Design Basis |  |  | 2026-02-20 |  |  | 260 | 27-Dec-24 A | 2026-03-19 | 18-Aug-25 A | 2026-02-20 | 2027-01-20
| A41210 | Utility Design Basis_RCC |  | 2026-02-20 |  |  | 16 | 18-Jan-25 A | 2027-01-20 | 31-Jan-25 A | 2026-02-20 | 2027-01-20
| A41220 | Utility Design Basis_IFA |  | 2026-02-20 |  |  | 3 | 01-Aug-25 A | 2027-01-20 | 04-Aug-25 A | 2026-02-20 | 2027-01-20
| A41230 | Utility Design Basis_RCA |  | 2026-02-20 |  |  | 16 | 05-Aug-25 A | 2027-01-20 | 12-Aug-25 A | 2026-02-20 | 2027-01-20
| A41240 | Utility Design Basis_IFD/IFC |  | 2026-02-20 |  |  | 2 | 13-Aug-25 A | 2027-01-20 | 18-Aug-25 A | 2026-02-20 | 2027-01-20
| Criticality Rating of System |  |  | 2026-02-20 |  |  | 341 | 10-Jan-25 A | 2026-11-30 | 2026-04-14 | 2026-04-14 | 2027-01-20 | 202
| A41260 | Criticality Rating of System_RCC |  | 2026-02-20 |  |  | 16 | 2026-02-20 | 2026-11-30 | 2026-03-13 | 2026-03-13 | 2026-12-22 | 202
| A41270 | Criticality Rating of System_IFA |  | 2026-03-13 |  |  | 3 | 2026-03-13 | 2026-12-22 | 2026-03-19 | 2026-03-19 | 2026-12-25 | 202
| A41280 | Criticality Rating of System_RCA |  | 2026-03-19 |  |  | 16 | 2026-03-19 | 2026-12-28 | 2026-04-09 | 2026-04-09 | 2027-01-18 | 202
| A41290 | Criticality Rating of System_IFD/IFC |  | 2026-04-09 |  |  | 2 | 2026-04-09 | 2027-01-18 | 2026-04-14 | 2026-04-14 | 2027-01-20 | 202
| List Of Process Simulation Cases |  |  | 2026-02-20 |  |  | 256 | 27-Dec-24 A | 2027-01-20 | 12-Jul-25 A | 2026-02-20 | 2027-01-20
| A41300 | List Of Process Simulation Cases_IFR |  | 2026-02-20 |  |  | 6 | 27-Dec-24 A | 2027-01-20 | 17-Jan-25 A | 2026-02-20 | 2027-01-20
| A41310 | List Of Process Simulation Cases_RCC |  | 2026-02-20 |  |  | 16 | 03-Jun-25 A | 2027-01-20 | 21-Jun-25 A | 2026-02-20 | 2027-01-20
| A41320 | List Of Process Simulation Cases_IFA |  | 2026-02-20 |  |  | 3 | 23-Jun-25 A | 2027-01-20 | 28-Jun-25 A | 2026-02-20 | 2027-01-20
| A41330 | List Of Process Simulation Cases_RCA |  | 2026-02-20 |  |  | 16 | 20-Jun-25 A | 2027-01-20 | 05-Jul-25 A | 2026-02-20 | 2027-01-20
| A41340 | List Of Process Simulation Cases_IFD/IFC |  | 2026-02-20 |  |  | 2 | 09-Jul-25 A | 2027-01-20 | 12-Jul-25 A | 2026-02-20 | 2027-01-20
| Isolation Philosophy |  |  | 2026-02-20 |  |  | 263 | 03-Jan-25 A | 2026-11-19 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| A3190 | Isolation Philosophy_RCC |  | 2026-02-20 |  |  | 16 | 18-Apr-25 A | 2027-01-20 | 19-Apr-25 A | 2026-02-20 | 2027-01-20
| A41790 | Isolation Philosophy_IFA |  | 2026-02-20 |  |  | 3 | 20-Apr-25 A | 2027-01-20 | 13-Jun-25 A | 2026-02-20 | 2027-01-20
| A41800 | Isolation Philosophy_RCA |  | 2026-02-20 |  |  | 16 | 14-Jun-25 A | 2027-01-20 | 21-Jun-25 A | 2026-02-20 | 2027-01-20
| A41810 | Isolation Philosophy_IFD/IFC |  | 2026-02-20 |  |  | 2 | 19-Dec-25 A | 2027-01-20 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| Relief and Blowdown Philosophy |  |  | 2026-02-20 |  |  | 319 | 09-Jan-25 A | 2026-11-19 | 2026-03-17 | 2026-03-17 | 2027-01-20 | 221
| A41830 | Relief and Blowdown Philosophy_RCC |  | 2026-02-20 |  |  | 16 | 31-Jan-25 A | 2026-12-28 | 20-Apr-25 A | 2026-02-20 | 2026-12-28
| A41840 | Relief and Blowdown Philosophy_IFA |  | 2026-02-20 |  |  | 3 | 10-Dec-25 A | 2026-12-28 | 19-Dec-25 A | 2026-02-20 | 2026-12-28
| A41850 | Relief and Blowdown Philosophy_RCA |  | 2026-02-20 |  |  | 16 | 2026-02-20 | 2026-12-28 | 2026-03-13 | 2026-03-13 | 2027-01-18 | 221
| A41860 | Relief and Blowdown Philosophy_IFD/IFC |  | 2026-03-13 |  |  | 2 | 2026-03-13 | 2027-01-18 | 2026-03-17 | 2026-03-17 | 2027-01-20 | 221
| Vent and Drain Philosophy |  |  | 2026-02-20 |  |  | 340 | 03-Jan-25 A | 2026-11-19 | 2026-04-23 | 2026-04-23 | 2027-01-20 | 194
| A41880 | Vent and Drain Philosophy_RCC |  | 2026-02-20 |  |  | 16 | 25-Jan-25 A | 2027-01-18 | 20-Apr-25 A | 2026-02-20 | 2027-01-18
| A41890 | Vent and Drain Philosophy_IFA |  | 2026-02-20 |  |  | 3 | 21-Apr-25 A | 2027-01-18 | 17-Jun-25 A | 2026-02-20 | 2027-01-18
| A41900 | Vent and Drain Philosophy_RCA |  | 2026-02-20 |  |  | 16 | 31-Jul-25 A | 2027-01-18 | 15-Aug-25 A | 2026-02-20 | 2027-01-18
| A41910 | Vent and Drain Philosophy_IFD/IFC |  | 2026-04-21 |  |  | 2 | 2026-04-21 | 2027-01-18 | 2026-04-23 | 2026-04-23 | 2027-01-20 | 194
| Operating manual including operating procedure/guidelines including startup and shutdown procedure |  |  | 2026-02-20 |  |  | 43 | 2026-02-20 | 2026-11-19 | 2026-04-21 | 2026-04-21 | 2027-01-18 | 194
| A55990 | Operating manual including operating procedure/guidelines including startup and shutdown procedure_RCC |  | 2026-02-27 |  |  | 16 | 2026-02-27 | 2026-11-26 | 2026-03-23 | 2026-03-23 | 2026-12-18 | 194
| A56000 | Operating manual including operating procedure/guidelines including startup and shutdown procedure_IFA |  | 2026-03-23 |  |  | 3 | 2026-03-23 | 2026-12-18 | 2026-03-26 | 2026-03-26 | 2026-12-23 | 194
| A56010 | Operating manual including operating procedure/guidelines including startup and shutdown procedure_RCA |  | 2026-03-26 |  |  | 16 | 2026-03-26 | 2026-12-23 | 2026-04-17 | 2026-04-17 | 2027-01-14 | 194
| A56020 | Operating manual including operating procedure/guidelines including startup and shutdown procedure_IFD/IFC |  | 2026-04-17 |  |  | 2 | 2026-04-17 | 2027-01-14 | 2026-04-21 | 2026-04-21 | 2027-01-18 | 194
| Process Safeguarding Diagram: List |  |  | 2026-02-20 |  |  | 217 | 04-Jan-25 A | 2026-03-02 | 28-Jun-25 A | 2026-02-20 | 2026-11-19
| A41920 | Process Safeguarding Diagram: List_IFR |  | 2026-02-20 |  |  | 11 | 04-Jan-25 A | 2026-03-02 | 25-Jan-25 A | 2026-02-20 | 2026-03-02
| A41930 | Process Safeguarding Diagram: List_RCC |  | 2026-02-20 |  |  | 16 | 26-Jan-25 A | 2026-03-02 | 20-Feb-25 A | 2026-02-20 | 2026-03-02
| A41940 | Process Safeguarding Diagram: List_IFH |  | 2026-02-20 |  |  | 11 | 21-Feb-25 A | 2026-03-02 | 27-May-25 A | 2026-02-20 | 2026-03-02
| A41950 | Process Safeguarding Diagram: List_RCA |  | 2026-02-20 |  |  | 16 | 28-May-25 A | 2026-11-19 | 21-Jun-25 A | 2026-02-20 | 2026-11-19
| A41960 | Process Safeguarding Diagram: List_IFD/IFC |  | 2026-02-20 |  |  | 2 | 22-Jun-25 A | 2026-11-19 | 28-Jun-25 A | 2026-02-20 | 2026-11-19
| Process Safeguarding Diagram: Feed Pretreatment |  |  | 2026-02-20 |  |  | 217 | 04-Jan-25 A | 2026-03-02 | 28-Jun-25 A | 2026-02-20 | 2027-01-20
| A41980 | Process Safeguarding Diagram: Feed Pretreatment_RCC |  | 2026-02-20 |  |  | 16 | 26-Jan-25 A | 2026-03-02 | 20-Feb-25 A | 2026-02-20 | 2026-03-02
| A41990 | Process Safeguarding Diagram: Feed Pretreatment_IFH |  | 2026-02-20 |  |  | 11 | 21-Feb-25 A | 2026-03-02 | 27-May-25 A | 2026-02-20 | 2026-03-02
| A42000 | Process Safeguarding Diagram: Feed Pretreatment_RCA |  | 2026-02-20 |  |  | 16 | 28-May-25 A | 2027-01-20 | 21-Jun-25 A | 2026-02-20 | 2027-01-20
| A42010 | Process Safeguarding Diagram: Feed Pretreatment_IFD/IFC |  | 2026-02-20 |  |  | 2 | 22-Jun-25 A | 2027-01-20 | 28-Jun-25 A | 2026-02-20 | 2027-01-20
| Process Safeguarding Diagram: Wash Water System |  |  | 2026-02-20 |  |  | 217 | 04-Jan-25 A | 2026-03-02 | 28-Jun-25 A | 2026-02-20 | 2027-01-20
| A42030 | Process Safeguarding Diagram: Wash Water System_RCC |  | 2026-02-20 |  |  | 16 | 26-Jan-25 A | 2026-03-02 | 20-Feb-25 A | 2026-02-20 | 2026-03-02
| A42040 | Process Safeguarding Diagram: Wash Water System_IFH |  | 2026-02-20 |  |  | 11 | 21-Feb-25 A | 2026-03-02 | 27-May-25 A | 2026-02-20 | 2026-03-02
| A42050 | Process Safeguarding Diagram: Wash Water System_RCA |  | 2026-02-20 |  |  | 16 | 28-May-25 A | 2027-01-20 | 21-Jun-25 A | 2026-02-20 | 2027-01-20
| A42060 | Process Safeguarding Diagram: Wash Water System_IFD/IFC |  | 2026-02-20 |  |  | 2 | 22-Jun-25 A | 2027-01-20 | 28-Jun-25 A | 2026-02-20 | 2027-01-20
| Process Safeguarding Diagram: Cracked Gas Compression |  |  | 2026-02-20 |  |  | 217 | 04-Jan-25 A | 2026-03-02 | 28-Jun-25 A | 2026-02-20 | 2027-01-20
| A42080 | Process Safeguarding Diagram: Cracked Gas Compression_RCC |  | 2026-02-20 |  |  | 16 | 26-Jan-25 A | 2026-03-02 | 20-Feb-25 A | 2026-02-20 | 2026-03-02
| A42090 | Process Safeguarding Diagram: Cracked Gas Compression_IFH |  | 2026-02-20 |  |  | 11 | 21-Feb-25 A | 2026-03-02 | 27-May-25 A | 2026-02-20 | 2026-03-02
| A42100 | Process Safeguarding Diagram: Cracked Gas Compression_RCA |  | 2026-02-20 |  |  | 16 | 28-May-25 A | 2027-01-20 | 21-Jun-25 A | 2026-02-20 | 2027-01-20
| A42110 | Process Safeguarding Diagram: Cracked Gas Compression_IFD/IFC |  | 2026-02-20 |  |  | 2 | 22-Jun-25 A | 2027-01-20 | 28-Jun-25 A | 2026-02-20 | 2027-01-20
| Process Safeguarding Diagram: C1/C2 Separation |  |  | 2026-02-20 |  |  | 217 | 04-Jan-25 A | 2026-03-02 | 28-Jun-25 A | 2026-02-20 | 2027-01-20
| A42130 | Process Safeguarding Diagram: C1/C2 Separation_RCC |  | 2026-02-20 |  |  | 16 | 26-Jan-25 A | 2026-03-02 | 20-Feb-25 A | 2026-02-20 | 2026-03-02
| A42140 | Process Safeguarding Diagram: C1/C2 Separation_IFH |  | 2026-02-20 |  |  | 11 | 21-Feb-25 A | 2026-03-02 | 27-May-25 A | 2026-02-20 | 2026-03-02
| A42150 | Process Safeguarding Diagram: C1/C2 Separation_RCA |  | 2026-02-20 |  |  | 16 | 28-May-25 A | 2027-01-20 | 21-Jun-25 A | 2026-02-20 | 2027-01-20
| A42160 | Process Safeguarding Diagram: C1/C2 Separation_IFD/IFC |  | 2026-02-20 |  |  | 2 | 22-Jun-25 A | 2027-01-20 | 28-Jun-25 A | 2026-02-20 | 2027-01-20
| Process Safeguarding Diagram: H2 Extraction Unit |  |  | 2026-02-20 |  |  | 217 | 04-Jan-25 A | 2026-03-02 | 28-Jun-25 A | 2026-02-20 | 2027-01-20
| A42180 | Process Safeguarding Diagram: H2 Extraction Unit_RCC |  | 2026-02-20 |  |  | 16 | 26-Jan-25 A | 2026-03-02 | 20-Feb-25 A | 2026-02-20 | 2026-03-02
| A42190 | Process Safeguarding Diagram: H2 Extraction Unit_IFH |  | 2026-02-20 |  |  | 11 | 21-Feb-25 A | 2026-03-02 | 27-May-25 A | 2026-02-20 | 2026-03-02
| A42200 | Process Safeguarding Diagram: H2 Extraction Unit_RCA |  | 2026-02-20 |  |  | 16 | 28-May-25 A | 2027-01-20 | 21-Jun-25 A | 2026-02-20 | 2027-01-20
| A42210 | Process Safeguarding Diagram: H2 Extraction Unit_IFD/IFC |  | 2026-02-20 |  |  | 2 | 22-Jun-25 A | 2027-01-20 | 28-Jun-25 A | 2026-02-20 | 2027-01-20
| Process Safeguarding Diagram: H2 Extraction Unit II |  |  | 2026-02-20 |  |  | 217 | 04-Jan-25 A | 2026-03-02 | 28-Jun-25 A | 2026-02-20 | 2027-01-20
| A42230 | Process Safeguarding Diagram: H2 Extraction Unit II_RCC |  | 2026-02-20 |  |  | 16 | 26-Jan-25 A | 2026-03-02 | 20-Feb-25 A | 2026-02-20 | 2026-03-02
| A42240 | Process Safeguarding Diagram: H2 Extraction Unit II_IFH |  | 2026-02-20 |  |  | 11 | 21-Feb-25 A | 2026-03-02 | 27-May-25 A | 2026-02-20 | 2026-03-02
| A42250 | Process Safeguarding Diagram: H2 Extraction Unit II_RCA |  | 2026-02-20 |  |  | 16 | 28-May-25 A | 2027-01-20 | 21-Jun-25 A | 2026-02-20 | 2027-01-20
| A42260 | Process Safeguarding Diagram: H2 Extraction Unit II_IFD/IFC |  | 2026-02-20 |  |  | 2 | 22-Jun-25 A | 2027-01-20 | 28-Jun-25 A | 2026-02-20 | 2027-01-20
| Process Safeguarding Diagram: C4 Selective Hydrogenation IV |  |  | 2026-02-20 |  |  | 217 | 04-Jan-25 A | 2026-03-02 | 28-Jun-25 A | 2026-02-20 | 2027-01-20
| A42280 | Process Safeguarding Diagram: C4 Selective Hydrogenation IV_RCC |  | 2026-02-20 |  |  | 16 | 26-Jan-25 A | 2026-03-02 | 20-Feb-25 A | 2026-02-20 | 2026-03-02
| A42290 | Process Safeguarding Diagram: C4 Selective Hydrogenation IV_IFH |  | 2026-02-20 |  |  | 11 | 21-Feb-25 A | 2026-03-02 | 27-May-25 A | 2026-02-20 | 2026-03-02
| A42300 | Process Safeguarding Diagram: C4 Selective Hydrogenation IV_RCA |  | 2026-02-20 |  |  | 16 | 28-May-25 A | 2027-01-20 | 21-Jun-25 A | 2026-02-20 | 2027-01-20
| A42310 | Process Safeguarding Diagram: C4 Selective Hydrogenation IV_IFD/IFC |  | 2026-02-20 |  |  | 2 | 22-Jun-25 A | 2027-01-20 | 28-Jun-25 A | 2026-02-20 | 2027-01-20
| Process Safeguarding Diagram: Fuel Gas System |  |  | 2026-02-20 |  |  | 217 | 04-Jan-25 A | 2026-03-02 | 28-Jun-25 A | 2026-02-20 | 2027-01-20
| A42330 | Process Safeguarding Diagram: Fuel Gas System_RCC |  | 2026-02-20 |  |  | 16 | 26-Jan-25 A | 2026-03-02 | 20-Feb-25 A | 2026-02-20 | 2026-03-02
| A42340 | Process Safeguarding Diagram: Fuel Gas System_IFH |  | 2026-02-20 |  |  | 11 | 21-Feb-25 A | 2026-03-02 | 27-May-25 A | 2026-02-20 | 2026-03-02
| A42350 | Process Safeguarding Diagram: Fuel Gas System_RCA |  | 2026-02-20 |  |  | 16 | 28-May-25 A | 2027-01-20 | 21-Jun-25 A | 2026-02-20 | 2027-01-20
| A42360 | Process Safeguarding Diagram: Fuel Gas System_IFD/IFC |  | 2026-02-20 |  |  | 2 | 22-Jun-25 A | 2027-01-20 | 28-Jun-25 A | 2026-02-20 | 2027-01-20
| Process Safeguarding Diagram: Regeneration System |  |  | 2026-02-20 |  |  | 217 | 04-Jan-25 A | 2026-03-02 | 28-Jun-25 A | 2026-02-20 | 2027-01-20
| A42380 | Process Safeguarding Diagram: Regeneration System_RCC |  | 2026-02-20 |  |  | 16 | 26-Jan-25 A | 2026-03-02 | 20-Feb-25 A | 2026-02-20 | 2026-03-02
| A42390 | Process Safeguarding Diagram: Regeneration System_IFH |  | 2026-02-20 |  |  | 11 | 21-Feb-25 A | 2026-03-02 | 27-May-25 A | 2026-02-20 | 2026-03-02
| A42400 | Process Safeguarding Diagram: Regeneration System_RCA |  | 2026-02-20 |  |  | 16 | 28-May-25 A | 2027-01-20 | 21-Jun-25 A | 2026-02-20 | 2027-01-20
| A42410 | Process Safeguarding Diagram: Regeneration System_IFD/IFC |  | 2026-02-20 |  |  | 2 | 22-Jun-25 A | 2027-01-20 | 28-Jun-25 A | 2026-02-20 | 2027-01-20
| Process Safeguarding Diagram: Boiler Feed Water System |  |  | 2026-02-20 |  |  | 217 | 04-Jan-25 A | 2026-03-02 | 28-Jun-25 A | 2026-02-20 | 2027-01-20
| A42430 | Process Safeguarding Diagram: Boiler Feed Water System_RCC |  | 2026-02-20 |  |  | 16 | 26-Jan-25 A | 2026-03-02 | 20-Feb-25 A | 2026-02-20 | 2026-03-02
| A42440 | Process Safeguarding Diagram: Boiler Feed Water System_IFH |  | 2026-02-20 |  |  | 11 | 21-Feb-25 A | 2026-03-02 | 27-May-25 A | 2026-02-20 | 2026-03-02
| A42450 | Process Safeguarding Diagram: Boiler Feed Water System_RCA |  | 2026-02-20 |  |  | 16 | 28-May-25 A | 2027-01-20 | 21-Jun-25 A | 2026-02-20 | 2027-01-20
| A42460 | Process Safeguarding Diagram: Boiler Feed Water System_IFD/IFC |  | 2026-02-20 |  |  | 2 | 22-Jun-25 A | 2027-01-20 | 28-Jun-25 A | 2026-02-20 | 2027-01-20
| Process Safeguarding Diagram: Condensate Collection System |  |  | 2026-02-20 |  |  | 217 | 04-Jan-25 A | 2026-03-02 | 28-Jun-25 A | 2026-02-20 | 2027-01-20
| A42480 | Process Safeguarding Diagram: Condensate Collection System_RCC |  | 2026-02-20 |  |  | 16 | 26-Jan-25 A | 2026-03-02 | 20-Feb-25 A | 2026-02-20 | 2026-03-02
| A42490 | Process Safeguarding Diagram: Condensate Collection System_IFH |  | 2026-02-20 |  |  | 11 | 21-Feb-25 A | 2026-03-02 | 27-May-25 A | 2026-02-20 | 2026-03-02
| A42500 | Process Safeguarding Diagram: Condensate Collection System_RCA |  | 2026-02-20 |  |  | 16 | 28-May-25 A | 2027-01-20 | 21-Jun-25 A | 2026-02-20 | 2027-01-20
| A42510 | Process Safeguarding Diagram: Condensate Collection System_IFD/IFC |  | 2026-02-20 |  |  | 2 | 22-Jun-25 A | 2027-01-20 | 28-Jun-25 A | 2026-02-20 | 2027-01-20
| Process Safeguarding Diagram: Cooling Water System |  |  | 2026-02-20 |  |  | 217 | 04-Jan-25 A | 2026-03-02 | 28-Jun-25 A | 2026-02-20 | 2027-01-20
| A42530 | Process Safeguarding Diagram: Cooling Water System_RCC |  | 2026-02-20 |  |  | 16 | 26-Jan-25 A | 2026-03-02 | 20-Feb-25 A | 2026-02-20 | 2026-03-02
| A42540 | Process Safeguarding Diagram: Cooling Water System_IFH |  | 2026-02-20 |  |  | 11 | 21-Feb-25 A | 2026-03-02 | 27-May-25 A | 2026-02-20 | 2026-03-02
| A42550 | Process Safeguarding Diagram: Cooling Water System_RCA |  | 2026-02-20 |  |  | 16 | 28-May-25 A | 2027-01-20 | 21-Jun-25 A | 2026-02-20 | 2027-01-20
| A42560 | Process Safeguarding Diagram: Cooling Water System_IFD/IFC |  | 2026-02-20 |  |  | 2 | 22-Jun-25 A | 2027-01-20 | 28-Jun-25 A | 2026-02-20 | 2027-01-20
| Process Safeguarding Diagram: Utility System For H2 Extraction Unit |  |  | 2026-02-20 |  |  | 217 | 04-Jan-25 A | 2026-03-02 | 28-Jun-25 A | 2026-02-20 | 2027-01-20
| A42570 | Process Safeguarding Diagram: Utility System For H2 Extraction Unit_IFR |  | 2026-02-20 |  |  | 11 | 04-Jan-25 A | 2026-03-02 | 25-Jan-25 A | 2026-02-20 | 2026-03-02
| A42580 | Process Safeguarding Diagram: Utility System For H2 Extraction Unit_RCC |  | 2026-02-20 |  |  | 16 | 26-Jan-25 A | 2026-03-02 | 20-Feb-25 A | 2026-02-20 | 2026-03-02
| A42590 | Process Safeguarding Diagram: Utility System For H2 Extraction Unit_IFH |  | 2026-02-20 |  |  | 11 | 21-Feb-25 A | 2026-03-02 | 27-May-25 A | 2026-02-20 | 2026-03-02
| A42600 | Process Safeguarding Diagram: Utility System For H2 Extraction Unit_RCA |  | 2026-02-20 |  |  | 16 | 28-May-25 A | 2027-01-20 | 21-Jun-25 A | 2026-02-20 | 2027-01-20
| A42610 | Process Safeguarding Diagram: Utility System For H2 Extraction Unit_IFD/IFC |  | 2026-02-20 |  |  | 2 | 22-Jun-25 A | 2027-01-20 | 28-Jun-25 A | 2026-02-20 | 2027-01-20
| Process Safeguarding Diagram: Blowdown Vessels And Acid Gas Flare |  |  | 2026-02-20 |  |  | 217 | 04-Jan-25 A | 2026-03-02 | 28-Jun-25 A | 2026-02-20 | 2027-01-20
| A42630 | Process Safeguarding Diagram: Blowdown Vessels And Acid Gas Flare_RCC |  | 2026-02-20 |  |  | 16 | 26-Jan-25 A | 2026-03-02 | 20-Feb-25 A | 2026-02-20 | 2026-03-02
| A42640 | Process Safeguarding Diagram: Blowdown Vessels And Acid Gas Flare_IFH |  | 2026-02-20 |  |  | 11 | 21-Feb-25 A | 2026-03-02 | 27-May-25 A | 2026-02-20 | 2026-03-02
| A42650 | Process Safeguarding Diagram: Blowdown Vessels And Acid Gas Flare_RCA |  | 2026-02-20 |  |  | 16 | 28-May-25 A | 2027-01-20 | 21-Jun-25 A | 2026-02-20 | 2027-01-20
| A42660 | Process Safeguarding Diagram: Blowdown Vessels And Acid Gas Flare_IFD/IFC |  | 2026-02-20 |  |  | 2 | 22-Jun-25 A | 2027-01-20 | 28-Jun-25 A | 2026-02-20 | 2027-01-20
| Process Safeguarding Diagram: Slop,Sewer And Drainage System |  |  | 2026-02-20 |  |  | 217 | 04-Jan-25 A | 2026-03-02 | 28-Jun-25 A | 2026-02-20 | 2027-01-20
| A42680 | Process Safeguarding Diagram: Slop,Sewer And Drainage System_RCC |  | 2026-02-20 |  |  | 16 | 26-Jan-25 A | 2026-03-02 | 20-Feb-25 A | 2026-02-20 | 2026-03-02
| A42690 | Process Safeguarding Diagram: Slop,Sewer And Drainage System_IFH |  | 2026-02-20 |  |  | 11 | 21-Feb-25 A | 2026-03-02 | 27-May-25 A | 2026-02-20 | 2026-03-02
| A42700 | Process Safeguarding Diagram: Slop,Sewer And Drainage System_RCA |  | 2026-02-20 |  |  | 16 | 28-May-25 A | 2027-01-20 | 21-Jun-25 A | 2026-02-20 | 2027-01-20
| A42710 | Process Safeguarding Diagram: Slop,Sewer And Drainage System_IFD/IFC |  | 2026-02-20 |  |  | 2 | 22-Jun-25 A | 2027-01-20 | 28-Jun-25 A | 2026-02-20 | 2027-01-20
| Process Safeguarding Diagram: Slop,Sewer And Drainage System II |  |  | 2026-02-20 |  |  | 217 | 04-Jan-25 A | 2026-03-02 | 28-Jun-25 A | 2026-02-20 | 2027-01-20
| A4140 | Process Safeguarding Diagram: Slop,Sewer And Drainage System II_RCC |  | 2026-02-20 |  |  | 16 | 26-Jan-25 A | 2026-03-02 | 20-Feb-25 A | 2026-02-20 | 2026-03-02
| A4150 | Process Safeguarding Diagram: Slop,Sewer And Drainage System II_IFH |  | 2026-02-20 |  |  | 11 | 21-Feb-25 A | 2026-03-02 | 27-May-25 A | 2026-02-20 | 2026-03-02
| A4160 | Process Safeguarding Diagram: Slop,Sewer And Drainage System II_RCA |  | 2026-02-20 |  |  | 16 | 28-May-25 A | 2026-03-02 | 21-Jun-25 A | 2026-02-20 | 2026-03-02
| A4170 | Process Safeguarding Diagram: Slop,Sewer And Drainage System II_IFD/IFC |  | 2026-02-20 |  |  | 2 | 22-Jun-25 A | 2027-01-20 | 28-Jun-25 A | 2026-02-20 | 2027-01-20
| Utility Consumption |  |  | 2026-02-20 |  |  | 87 | 21-Jun-25 A | 2026-03-25 | 2026-02-24 | 2026-02-24 | 2026-03-27 | 23
| A42760 | Utility Consumption_IFR |  | 2026-02-20 |  |  | 6 | 21-Jun-25 A | 2026-03-25 | 12-Jul-25 A | 2026-02-20 | 2026-03-25
| A42770 | Utility Consumption_RCC |  | 2026-02-20 |  |  | 16 | 02-Oct-25 A | 2026-03-25 | 22-Oct-25 A | 2026-02-20 | 2026-03-25
| A42780 | Utility Consumption_IFA |  | 2026-02-20 |  |  | 3 | 16-Dec-25 A | 2026-03-25 | 26-Dec-25 A | 2026-02-20 | 2026-03-25
| A42790 | Utility Consumption_RCA |  | 2026-02-20 |  |  | 16 | 16-Dec-25 A | 2026-03-25 | 26-Dec-25 A | 2026-02-20 | 2026-03-25
| A42800 | Utility Consumption_IFD/IFC |  | 2026-02-20 |  |  | 2 | 2026-02-20 | 2026-03-25 | 2026-02-24 | 2026-02-24 | 2026-03-27 | 23
| Safeguarding Memorendum |  |  | 2026-02-20 |  |  | 72 | 02-Sep-25 A | 2027-01-18 | 2026-02-24 | 2026-02-24 | 2027-01-20 | 237
| A42720 | Safeguarding Memorandum_RCC |  | 2026-02-20 |  |  | 16 | 17-Sep-25 A | 2027-01-18 | 06-Oct-25 A | 2026-02-20 | 2027-01-18
| A42730 | Safeguarding Memorandum_IFA |  | 2026-02-20 |  |  | 3 | 06-Oct-25 A | 2027-01-18 | 25-Nov-25 A | 2026-02-20 | 2027-01-18
| A42740 | Safeguarding Memorandum_RCA |  | 2026-02-20 |  |  | 16 | 25-Nov-25 A | 2027-01-18 | 29-Dec-25 A | 2026-02-20 | 2027-01-18
| A42750 | Safeguarding Memorandum_IFD/IFC |  | 2026-02-20 |  |  | 2 | 2026-02-20 | 2027-01-18 | 2026-02-24 | 2026-02-24 | 2027-01-20 | 237
| Process Utility Adequacy Check Report |  |  | 2026-02-20 |  |  | 61 | 10-Oct-25 A | 2026-03-27 | 19-Jan-26 A | 2026-02-20 | 2026-03-27
| A43210 | Process Utility Adequacy Check Report_IFR |  | 2026-02-20 |  |  | 6 | 10-Oct-25 A | 2026-03-27 | 17-Oct-25 A | 2026-02-20 | 2026-03-27
| A43220 | Process Utility Adequacy Check Report_RCC |  | 2026-02-20 |  |  | 16 | 11-Oct-25 A | 2026-03-27 | 24-Oct-25 A | 2026-02-20 | 2026-03-27
| A43230 | Process Utility Adequacy Check Report_IFA |  | 2026-02-20 |  |  | 3 | 19-Dec-25 A | 2026-03-27 | 24-Dec-25 A | 2026-02-20 | 2026-03-27
| A43240 | Process Utility Adequacy Check Report_RCA |  | 2026-02-20 |  |  | 16 | 24-Dec-25 A | 2026-03-27 | 15-Jan-26 A | 2026-02-20 | 2026-03-27
| A43250 | Process Utility Adequacy Check Report_IFD/IFC |  | 2026-02-20 |  |  | 2 | 15-Jan-26 A | 2026-03-27 | 19-Jan-26 A | 2026-02-20 | 2026-03-27
| Process Datasheet for PSA2 Feed Gas Compressor 1st Stage Suction Drum |  |  | 2026-02-20 |  |  | 124 | 31-Dec-24 A | 2026-03-02 | 21-May-25 A | 2026-02-20 | 2027-01-20
| A41360 | Process Datasheet for PSA2 Feed Gas Compressor 1st Stage Suction Drum_RCC |  | 2026-02-20 |  |  | 16 | 25-Jan-25 A | 2027-01-20 | 18-Mar-25 A | 2026-02-20 | 2027-01-20
| A41370 | Process Datasheet for PSA2 Feed Gas Compressor 1st Stage Suction Drum_IFA |  | 2026-02-20 |  |  | 2 | 19-Mar-25 A | 2027-01-20 | 19-Apr-25 A | 2026-02-20 | 2027-01-20
| A41380 | Process Datasheet for PSA2 Feed Gas Compressor 1st Stage Suction Drum_RCA |  | 2026-02-20 |  |  | 16 | 20-Apr-25 A | 2027-01-20 | 14-May-25 A | 2026-02-20 | 2027-01-20
| A41390 | Process Datasheet for PSA2 Feed Gas Compressor 1st Stage Suction Drum_IFD/IFC |  | 2026-02-20 |  |  | 2 | 15-May-25 A | 2027-01-20 | 21-May-25 A | 2026-02-20 | 2027-01-20
| Process Datasheet for PSA2 Feed Gas Compressor 1st Stage Cooler |  |  | 2026-02-20 |  |  | 131 | 01-Jan-25 A | 2026-03-02 | 21-Jun-25 A | 2026-02-20 | 2027-01-20
| A41410 | Process Datasheet for PSA2 Feed Gas Compressor 1st Stage Cooler_RCC |  | 2026-02-20 |  |  | 16 | 27-Jan-25 A | 2027-01-20 | 19-Mar-25 A | 2026-02-20 | 2027-01-20
| A41420 | Process Datasheet for PSA2 Feed Gas Compressor 1st Stage Cooler_IFA |  | 2026-02-20 |  |  | 2 | 20-Mar-25 A | 2027-01-20 | 20-May-25 A | 2026-02-20 | 2027-01-20
| A41430 | Process Datasheet for PSA2 Feed Gas Compressor 1st Stage Cooler_RCA |  | 2026-02-20 |  |  | 16 | 21-May-25 A | 2027-01-20 | 02-Jun-25 A | 2026-02-20 | 2027-01-20
| A41440 | Process Datasheet for PSA2 Feed Gas Compressor 1st Stage Cooler_IFD/IFC |  | 2026-02-20 |  |  | 2 | 03-Jun-25 A | 2027-01-20 | 21-Jun-25 A | 2026-02-20 | 2027-01-20
| Process Datasheet for PSA2 Feed Gas Compressor 2nd Stage Suction Drum |  |  | 2026-02-20 |  |  | 123 | 31-Dec-24 A | 2026-03-02 | 21-May-25 A | 2026-02-20 | 2027-01-20
| A41460 | Process Datasheet for PSA2 Feed Gas Compressor 2nd Stage Suction Drum_RCC |  | 2026-02-20 |  |  | 16 | 25-Jan-25 A | 2027-01-20 | 18-Mar-25 A | 2026-02-20 | 2027-01-20
| A41470 | Process Datasheet for PSA2 Feed Gas Compressor 2nd Stage Suction Drum_IFA |  | 2026-02-20 |  |  | 2 | 19-Mar-25 A | 2027-01-20 | 19-Apr-25 A | 2026-02-20 | 2027-01-20
| A41480 | Process Datasheet for PSA2 Feed Gas Compressor 2nd Stage Suction Drum_RCA |  | 2026-02-20 |  |  | 16 | 20-Apr-25 A | 2027-01-20 | 14-May-25 A | 2026-02-20 | 2027-01-20
| A41490 | Process Datasheet for PSA2 Feed Gas Compressor 2nd Stage Suction Drum_IFD/IFC |  | 2026-02-20 |  |  | 2 | 15-May-25 A | 2027-01-20 | 21-May-25 A | 2026-02-20 | 2027-01-20
| Process Datasheet for PSA2 Feed Gas Compressor 2nd Stage Cooler |  |  | 2026-02-20 |  |  | 131 | 01-Jan-25 A | 2026-03-02 | 21-Jun-25 A | 2026-02-20 | 2027-01-20
| A41510 | Process Datasheet for PSA2 Feed Gas Compressor 2nd Stage Cooler_RCC |  | 2026-02-20 |  |  | 16 | 27-Jan-25 A | 2027-01-20 | 19-Mar-25 A | 2026-02-20 | 2027-01-20
| A41520 | Process Datasheet for PSA2 Feed Gas Compressor 2nd Stage Cooler_IFA |  | 2026-02-20 |  |  | 2 | 20-Mar-25 A | 2027-01-20 | 20-May-25 A | 2026-02-20 | 2027-01-20
| A41530 | Process Datasheet for PSA2 Feed Gas Compressor 2nd Stage Cooler_RCA |  | 2026-02-20 |  |  | 16 | 21-May-25 A | 2027-01-20 | 02-Jun-25 A | 2026-02-20 | 2027-01-20
| A41540 | Process Datasheet for PSA2 Feed Gas Compressor 2nd Stage Cooler_IFD/IFC |  | 2026-02-20 |  |  | 2 | 03-Jun-25 A | 2027-01-20 | 21-Jun-25 A | 2026-02-20 | 2027-01-20
| Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Suction Drum |  |  | 2026-02-20 |  |  | 123 | 31-Dec-24 A | 2026-03-02 | 20-May-25 A | 2026-02-20 | 2027-01-20
| A41550 | Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Suction Drum_IFR |  | 2026-02-20 |  |  | 2 | 31-Dec-24 A | 2026-03-02 | 24-Jan-25 A | 2026-02-20 | 2026-03-02
| A41560 | Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Suction Drum_RCC |  | 2026-02-20 |  |  | 16 | 25-Jan-25 A | 2027-01-20 | 18-Mar-25 A | 2026-02-20 | 2027-01-20
| A41570 | Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Suction Drum_IFA |  | 2026-02-20 |  |  | 2 | 19-Mar-25 A | 2027-01-20 | 19-Apr-25 A | 2026-02-20 | 2027-01-20
| A41580 | Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Suction Drum_RCA |  | 2026-02-20 |  |  | 16 | 20-Apr-25 A | 2027-01-20 | 13-May-25 A | 2026-02-20 | 2027-01-20
| A41590 | Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Suction Drum_IFD/IFC |  | 2026-02-20 |  |  | 2 | 14-May-25 A | 2027-01-20 | 20-May-25 A | 2026-02-20 | 2027-01-20
| Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Cooler |  |  | 2026-02-20 |  |  | 232 | 01-Jan-25 A | 2026-03-02 | 20-Jul-25 A | 2026-02-20 | 2027-01-20
| A41610 | Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Cooler_RCC |  | 2026-02-20 |  |  | 16 | 27-Jan-25 A | 2027-01-20 | 19-Mar-25 A | 2026-02-20 | 2027-01-20
| A41620 | Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Cooler_IFA |  | 2026-02-20 |  |  | 2 | 20-Mar-25 A | 2027-01-20 | 21-Jun-25 A | 2026-02-20 | 2027-01-20
| A41630 | Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Cooler_RCA |  | 2026-02-20 |  |  | 16 | 28-Jun-25 A | 2027-01-20 | 14-Jul-25 A | 2026-02-20 | 2027-01-20
| A41640 | Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Cooler_IFD/IFC |  | 2026-02-20 |  |  | 2 | 16-Jul-25 A | 2027-01-20 | 20-Jul-25 A | 2026-02-20 | 2027-01-20
| Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Discharge Drum |  |  | 2026-02-20 |  |  | 37 | 31-Dec-24 A | 2026-03-02 | 20-May-25 A | 2026-02-20 | 2027-01-20
| A41660 | Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Discharge Drum_RCC |  | 2026-02-20 |  |  | 16 | 25-Jan-25 A | 2027-01-20 | 18-Mar-25 A | 2026-02-20 | 2027-01-20
| A2550 | Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Discharge Drum_IFA |  | 2026-02-20 |  |  | 2 | 19-Mar-25 A | 2027-01-20 | 19-Apr-25 A | 2026-02-20 | 2027-01-20
| A2560 | Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Discharge Drum_RCA |  | 2026-02-20 |  |  | 16 | 20-Apr-25 A | 2027-01-20 | 13-May-25 A | 2026-02-20 | 2027-01-20
| A2570 | Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Discharge Drum_IFD/IFC |  | 2026-02-20 |  |  | 2 | 14-May-25 A | 2027-01-20 | 20-May-25 A | 2026-02-20 | 2027-01-20
| Process Datasheet for PSA2 Off Gas Buffer Drum - 13-VV-712 |  |  | 2026-02-20 |  |  | 132 | 31-Dec-24 A | 2026-03-02 | 12-Jun-25 A | 2026-02-20 | 2027-01-20
| A2580 | Process Datasheet for PSA2 Off Gas Buffer Drum - 13-VV-712_IFR |  | 2026-02-20 |  |  | 2 | 31-Dec-24 A | 2026-03-02 | 24-Jan-25 A | 2026-02-20 | 2026-03-02
| A2590 | Process Datasheet for PSA2 Off Gas Buffer Drum - 13-VV-712_RCC |  | 2026-02-20 |  |  | 16 | 25-Jan-25 A | 2027-01-20 | 14-May-25 A | 2026-02-20 | 2027-01-20
| A2600 | Process Datasheet for PSA2 Off Gas Buffer Drum - 13-VV-712_IFA |  | 2026-02-20 |  |  | 2 | 15-May-25 A | 2027-01-20 | 21-May-25 A | 2026-02-20 | 2027-01-20
| A2610 | Process Datasheet for PSA2 Off Gas Buffer Drum - 13-VV-712_RCA |  | 2026-02-20 |  |  | 16 | 22-May-25 A | 2027-01-20 | 02-Jun-25 A | 2026-02-20 | 2027-01-20
| A2620 | Process Datasheet for PSA2 Off Gas Buffer Drum - 13-VV-712_IFD/IFC |  | 2026-02-20 |  |  | 2 | 03-Jun-25 A | 2027-01-20 | 12-Jun-25 A | 2026-02-20 | 2027-01-20
| Process Datasheet for PSA2 Off Gas Compressor Interstage Cooler - 13-HE-708 |  |  | 2026-02-20 |  |  | 131 | 01-Jan-25 A | 2026-03-02 | 21-Jun-25 A | 2026-02-20 | 2027-01-20
| A2640 | Process Datasheet for PSA2 Off Gas Compressor Interstage Cooler - 13-HE-708_RCC |  | 2026-02-20 |  |  | 16 | 27-Jan-25 A | 2027-01-20 | 19-Mar-25 A | 2026-02-20 | 2027-01-20
| A2650 | Process Datasheet for PSA2 Off Gas Compressor Interstage Cooler - 13-HE-708_IFA |  | 2026-02-20 |  |  | 2 | 20-Mar-25 A | 2027-01-20 | 20-May-25 A | 2026-02-20 | 2027-01-20
| A2660 | Process Datasheet for PSA2 Off Gas Compressor Interstage Cooler - 13-HE-708_RCA |  | 2026-02-20 |  |  | 16 | 21-May-25 A | 2027-01-20 | 11-Jun-25 A | 2026-02-20 | 2027-01-20
| A2670 | Process Datasheet for PSA2 Off Gas Compressor Interstage Cooler - 13-HE-708_IFD/IFC |  | 2026-02-20 |  |  | 2 | 12-Jun-25 A | 2027-01-20 | 21-Jun-25 A | 2026-02-20 | 2027-01-20
| Process Datasheet for PSA2 Off Gas Compressor 2Nd Stage Suction Drum 13-VV-713 |  |  | 2026-02-20 |  |  | 132 | 31-Dec-24 A | 2026-03-02 | 13-Jun-25 A | 2026-02-20 | 2027-01-20
| A2680 | Process Datasheet for PSA2 Off Gas Compressor 2Nd Stage Suction Drum 13-VV-713_IFR |  | 2026-02-20 |  |  | 2 | 31-Dec-24 A | 2026-03-02 | 24-Jan-25 A | 2026-02-20 | 2026-03-02
| A41670 | Process Datasheet for PSA2 Off Gas Compressor 2Nd Stage Suction Drum 13-VV-713_RCC |  | 2026-02-20 |  |  | 16 | 25-Jan-25 A | 2027-01-20 | 14-May-25 A | 2026-02-20 | 2027-01-20
| A41680 | Process Datasheet for PSA2 Off Gas Compressor 2Nd Stage Suction Drum 13-VV-713_IFA |  | 2026-02-20 |  |  | 2 | 15-May-25 A | 2027-01-20 | 21-May-25 A | 2026-02-20 | 2027-01-20
| A41690 | Process Datasheet for PSA2 Off Gas Compressor 2Nd Stage Suction Drum 13-VV-713_RCA |  | 2026-02-20 |  |  | 16 | 22-May-25 A | 2027-01-20 | 02-Jun-25 A | 2026-02-20 | 2027-01-20
| A2720 | Process Datasheet for PSA2 Off Gas Compressor 2Nd Stage Suction Drum 13-VV-713_IFD/IFC |  | 2026-02-20 |  |  | 2 | 03-Jun-25 A | 2027-01-20 | 13-Jun-25 A | 2026-02-20 | 2027-01-20
| Process Datasheet for PSA2 Off Gas Compressor Aftercooler - 13-HE-709 |  |  | 2026-02-20 |  |  | 301 | 01-Jan-25 A | 2026-03-02 | 2026-02-24 | 2026-02-24 | 2027-01-20 | 237
| A2740 | Process Datasheet for PSA2 Off Gas Compressor Aftercooler - 13-HE-709_RCC |  | 2026-02-20 |  |  | 16 | 27-Jan-25 A | 2027-01-18 | 19-Mar-25 A | 2026-02-20 | 2027-01-18
| A2750 | Process Datasheet for PSA2 Off Gas Compressor Aftercooler - 13-HE-709_IFA |  | 2026-02-20 |  |  | 2 | 20-Mar-25 A | 2027-01-18 | 20-May-25 A | 2026-02-20 | 2027-01-18
| A2760 | Process Datasheet for PSA2 Off Gas Compressor Aftercooler - 13-HE-709_RCA |  | 2026-02-20 |  |  | 16 | 21-May-25 A | 2027-01-18 | 11-Jun-25 A | 2026-02-20 | 2027-01-18
| A2770 | Process Datasheet for PSA2 Off Gas Compressor Aftercooler - 13-HE-709_IFD/IFC |  | 2026-02-20 |  |  | 2 | 2026-02-20 | 2027-01-18 | 2026-02-24 | 2026-02-24 | 2027-01-20 | 237
| Process Datasheet for PSA2 Off Gas Compressor Discharge Dripleg - 13-SP-7004* |  |  | 2026-02-20 |  |  | 220 | 01-Jan-25 A | 2026-03-02 | 25-Jun-25 A | 2026-02-20 | 2027-01-18
| A2780 | Process Datasheet for PSA2 Off Gas Compressor Discharge Dripleg - 13-SP-7004_IFR |  | 2026-02-20 |  |  | 2 | 01-Jan-25 A | 2026-03-02 | 24-Jan-25 A | 2026-02-20 | 2026-03-02
| A2790 | Process Datasheet for PSA2 Off Gas Compressor Discharge Dripleg - 13-SP-7004_RCC |  | 2026-02-20 |  |  | 16 | 25-Jan-25 A | 2027-01-18 | 05-May-25 A | 2026-02-20 | 2027-01-18
| A2800 | Process Datasheet for PSA2 Off Gas Compressor Discharge Dripleg - 13-SP-7004_IFA |  | 2026-02-20 |  |  | 2 | 06-May-25 A | 2027-01-18 | 11-Jun-25 A | 2026-02-20 | 2027-01-18
| A2810 | Process Datasheet for PSA2 Off Gas Compressor Discharge Dripleg - 13-SP-7004_RCA |  | 2026-02-20 |  |  | 16 | 12-Jun-25 A | 2027-01-18 | 21-Jun-25 A | 2026-02-20 | 2027-01-18
| A55750 | Process Datasheet for PSA2 Off Gas Compressor Discharge Dripleg - 13-SP-7004_IFD/IFC |  | 2026-02-20 |  |  | 6 | 23-Jun-25 A | 2027-01-18 | 25-Jun-25 A | 2026-02-20 | 2027-01-18
| Process Datasheet for 52-SP-14067 Vhp Boiler Feed Water Preheater Dripleg |  |  | 2026-02-20 |  |  | 335 | 01-Jan-25 A | 2026-03-02 | 2026-04-10 | 2026-04-10 | 2027-01-20 | 203
| A2840 | Process Datasheet for 52-SP-14067 Vhp Boiler Feed Water Preheater Dripleg_RCC |  | 2026-02-20 |  |  | 16 | 2026-02-20 | 2026-12-02 | 2026-03-13 | 2026-03-13 | 2026-12-23 | 203
| A2850 | Process Datasheet for 52-SP-14067 Vhp Boiler Feed Water Preheater Dripleg_IFA |  | 2026-03-13 |  |  | 2 | 2026-03-13 | 2026-12-23 | 2026-03-17 | 2026-03-17 | 2026-12-25 | 203
| A41700 | Process Datasheet for 52-SP-14067 Vhp Boiler Feed Water Preheater Dripleg_RCA |  | 2026-03-18 |  |  | 16 | 2026-03-18 | 2026-12-28 | 2026-04-08 | 2026-04-08 | 2027-01-18 | 203
| A41710 | Process Datasheet for 52-SP-14067 Vhp Boiler Feed Water Preheater Dripleg_IFD/IFC |  | 2026-04-08 |  |  | 2 | 2026-04-08 | 2027-01-18 | 2026-04-10 | 2026-04-10 | 2027-01-20 | 203
| Process Datasheet for 50-HE-1410 C4 Guard Adsorber Regeneration Gas Cooler |  |  | 2026-02-20 |  |  | 215 | 01-Jan-25 A | 2026-03-02 | 2026-02-24 | 2026-02-24 | 2027-01-20 | 237
| A2890 | Process Datasheet for 50-HE-1410 C4 Guard Adsorber Regeneration Gas Cooler_RCC |  | 2026-02-20 |  |  | 16 | 28-Apr-25 A | 2027-01-18 | 04-May-25 A | 2026-02-20 | 2027-01-18
| A2900 | Process Datasheet for 50-HE-1410 C4 Guard Adsorber Regeneration Gas Cooler_IFA |  | 2026-02-20 |  |  | 2 | 05-May-25 A | 2027-01-18 | 30-May-25 A | 2026-02-20 | 2027-01-18
| A2910 | Process Datasheet for 50-HE-1410 C4 Guard Adsorber Regeneration Gas Cooler_RCA |  | 2026-02-20 |  |  | 16 | 01-Jun-25 A | 2027-01-18 | 21-Jun-25 A | 2026-02-20 | 2027-01-18
| A2920 | Process Datasheet for 50-HE-1410 C4 Guard Adsorber Regeneration Gas Cooler_IFD/IFC |  | 2026-02-20 |  |  | 2 | 2026-02-20 | 2027-01-18 | 2026-02-24 | 2026-02-24 | 2027-01-20 | 237
| Process Datasheet for 50-VV-1403 C4 Guard Adsorber Regeneration Gas Coalescer |  |  | 2026-02-20 |  |  | 319 | 01-Jan-25 A | 2026-03-02 | 2026-03-20 | 2026-03-20 | 2027-01-20 | 219
| A2990 | Process Datasheet for 50-VV-1403 C4 Guard Adsorber Regeneration Gas Coalescer_RCC |  | 2026-02-20 |  |  | 16 | 31-Jan-25 A | 2026-12-23 | 20-Apr-25 A | 2026-02-20 | 2026-12-23
| A3000 | Process Datasheet for 50-VV-1403 C4 Guard Adsorber Regeneration Gas Coalescer_IFA |  | 2026-02-20 |  |  | 2 | 2026-02-20 | 2026-12-23 | 2026-02-24 | 2026-02-24 | 2026-12-25 | 219
| A3010 | Process Datasheet for 50-VV-1403 C4 Guard Adsorber Regeneration Gas Coalescer_RCA |  | 2026-02-24 |  |  | 16 | 2026-02-24 | 2026-12-28 | 2026-03-17 | 2026-03-17 | 2027-01-18 | 219
| A3020 | Process Datasheet for 50-VV-1403 C4 Guard Adsorber Regeneration Gas Coalescer_IFD/IFC |  | 2026-03-18 |  |  | 2 | 2026-03-18 | 2027-01-18 | 2026-03-20 | 2026-03-20 | 2027-01-20 | 219
| Process Datasheet for 70-PC-1407 Water Collection Sump Pump II |  |  | 2026-02-20 |  |  | 272 | 01-Jan-25 A | 2026-03-02 | 13-Jan-26 A | 2026-02-20 | 2027-01-20
| A41740 | Process Datasheet for 70-PC-1407 Water Collection Sump Pump II_RCC |  | 2026-02-20 |  |  | 16 | 25-Jan-25 A | 2027-01-20 | 02-May-25 A | 2026-02-20 | 2027-01-20
| A41750 | Process Datasheet for 70-PC-1407 Water Collection Sump Pump II_IFA |  | 2026-02-20 |  |  | 2 | 03-May-25 A | 2027-01-20 | 19-Sep-25 A | 2026-02-20 | 2027-01-20
| A41760 | Process Datasheet for 70-PC-1407 Water Collection Sump Pump II_RCA |  | 2026-02-20 |  |  | 16 | 19-Dec-25 A | 2027-01-20 | 09-Jan-26 A | 2026-02-20 | 2027-01-20
| A41770 | Process Datasheet for 70-PC-1407 Water Collection Sump Pump II_IFD/IFC |  | 2026-02-20 |  |  | 2 | 09-Jan-26 A | 2027-01-20 | 13-Jan-26 A | 2026-02-20 | 2027-01-20
| Process Datasheet for 70-PC-1409 A/B Sanitary Waste Water Sump Pump |  |  | 2026-02-20 |  |  | 297 | 01-Jan-25 A | 2026-03-02 | 12-Nov-25 A | 2026-02-20 | 2027-01-20
| A3090 | Process Datasheet for 70-PC-1409 A/B Sanitary Waste Water Sump Pump_RCC |  | 2026-02-20 |  |  | 16 | 25-Jan-25 A | 2027-01-20 | 02-May-25 A | 2026-02-20 | 2027-01-20
| A3100 | Process Datasheet for 70-PC-1409 A/B Sanitary Waste Water Sump Pump_IFA |  | 2026-02-20 |  |  | 2 | 01-Aug-25 A | 2027-01-20 | 05-Aug-25 A | 2026-02-20 | 2027-01-20
| A3110 | Process Datasheet for 70-PC-1409 A/B Sanitary Waste Water Sump Pump_RCA |  | 2026-02-20 |  |  | 16 | 05-Aug-25 A | 2027-01-20 | 25-Aug-25 A | 2026-02-20 | 2027-01-20
| A3120 | Process Datasheet for 70-PC-1409 A/B Sanitary Waste Water Sump Pump_IFD/IFC |  | 2026-02-20 |  |  | 2 | 02-Sep-25 A | 2027-01-20 | 12-Nov-25 A | 2026-02-20 | 2027-01-20
| Process Datasheet for 70-VV-1415 PSA2 Slop Drum |  |  | 2026-02-20 |  |  | 216 | 01-Jan-25 A | 2026-03-02 | 03-Nov-25 A | 2026-02-20 | 2027-01-20
| A3130 | Process Datasheet for 70-VV-1415 PSA2 Slop Drum_IFR |  | 2026-02-20 |  |  | 2 | 01-Jan-25 A | 2026-03-02 | 24-Jan-25 A | 2026-02-20 | 2026-03-02
| A3140 | Process Datasheet for 70-VV-1415 PSA2 Slop Drum_RCC |  | 2026-02-20 |  |  | 16 | 25-Jan-25 A | 2027-01-20 | 05-May-25 A | 2026-02-20 | 2027-01-20
| A3150 | Process Datasheet for 70-VV-1415 PSA2 Slop Drum_IFA |  | 2026-02-20 |  |  | 2 | 06-May-25 A | 2027-01-20 | 11-Jun-25 A | 2026-02-20 | 2027-01-20
| A3160 | Process Datasheet for 70-VV-1415 PSA2 Slop Drum_RCA |  | 2026-02-20 |  |  | 16 | 12-Jun-25 A | 2027-01-20 | 21-Jun-25 A | 2026-02-20 | 2027-01-20
| A41780 | Process Datasheet for 70-VV-1415 PSA2 Slop Drum_IFD/IFC |  | 2026-02-20 |  |  | 2 | 24-Oct-25 A | 2027-01-20 | 03-Nov-25 A | 2026-02-20 | 2027-01-20
| Process Datasheet of Off-Gas Compressor Coalescer |  |  | 2026-02-20 |  |  | 252 | 05-Jun-25 A | 2027-01-20 | 12-Jul-25 A | 2026-02-20 | 2027-01-20
| A28240 | Process Datasheet of Off-Gas Compressor Coalescer_RCC |  | 2026-02-20 |  |  | 16 | 05-Jun-25 A | 2027-01-20 | 25-Jun-25 A | 2026-02-20 | 2027-01-20
| A55760 | Process Datasheet of Off-Gas Compressor Coalescer_IFA |  | 2026-02-20 |  |  | 2 | 26-Jun-25 A | 2027-01-20 | 28-Jun-25 A | 2026-02-20 | 2027-01-20
| A55770 | Process Datasheet of Off-Gas Compressor Coalescer_RCA |  | 2026-02-20 |  |  | 16 | 20-Jun-25 A | 2027-01-20 | 05-Jul-25 A | 2026-02-20 | 2027-01-20
| A55780 | Process Datasheet of Off-Gas Compressor Coalescer_IFD/IFC |  | 2026-02-20 |  |  | 2 | 10-Jul-25 A | 2027-01-20 | 12-Jul-25 A | 2026-02-20 | 2027-01-20
| Sample Point /Connection Lists |  |  | 2026-02-20 |  |  | 139 | 21-Jun-25 A | 2027-01-18 | 2026-02-24 | 2026-02-24 | 2027-01-20 | 237
| A43060 | Sample Point /Connection Lists_IFR |  | 2026-02-20 |  |  | 6 | 21-Jun-25 A | 2027-01-18 | 12-Jul-25 A | 2026-02-20 | 2027-01-18
| A43070 | Sample Point /Connection Lists_RCC |  | 2026-02-20 |  |  | 16 | 01-Oct-25 A | 2027-01-18 | 27-Oct-25 A | 2026-02-20 | 2027-01-18
| A43080 | Sample Point /Connection Lists_IFA |  | 2026-02-20 |  |  | 3 | 28-Oct-25 A | 2027-01-18 | 31-Oct-25 A | 2026-02-20 | 2027-01-18
| A43090 | Sample Point /Connection Lists_RCA |  | 2026-02-20 |  |  | 16 | 01-Nov-25 A | 2027-01-18 | 05-Nov-25 A | 2026-02-20 | 2027-01-18
| A43100 | Sample Point /Connection Lists_IFD/IFC |  | 2026-02-20 |  |  | 2 | 2026-02-20 | 2027-01-18 | 2026-02-24 | 2026-02-24 | 2027-01-20 | 237
| Process Calculation Report |  |  | 2026-02-20 |  |  | 282 | 20-Feb-25 A | 2026-12-22 | 2026-03-23 | 2026-03-23 | 2027-01-20 | 218
| A42970 | Process Calculation Report_RCC |  | 2026-02-20 |  |  | 16 | 26-Dec-25 A | 2026-12-22 | 10-Jan-26 A | 2026-02-20 | 2026-12-22
| A42980 | Process Calculation Report_IFA |  | 2026-02-20 |  |  | 3 | 2026-02-20 | 2026-12-22 | 2026-02-25 | 2026-02-25 | 2026-12-25 | 218
| A42990 | Process Calculation Report_RCA |  | 2026-02-25 |  |  | 16 | 2026-02-25 | 2026-12-28 | 2026-03-19 | 2026-03-19 | 2027-01-18 | 218
| A43000 | Process Calculation Report_IFD/IFC |  | 2026-03-19 |  |  | 2 | 2026-03-19 | 2027-01-18 | 2026-03-23 | 2026-03-23 | 2027-01-20 | 218
| Process Datasheet for Control Valve |  |  | 2026-02-20 |  |  | 158 | 20-Feb-25 A | 2026-03-02 | 12-Jul-25 A | 2026-02-20 | 2027-01-20
| A42820 | Process Datasheet for Control Valve_RCC |  | 2026-02-20 |  |  | 16 | 28-Apr-25 A | 2027-01-20 | 21-Jun-25 A | 2026-02-20 | 2027-01-20
| A42830 | Process Datasheet for Control Valve_IFA |  | 2026-02-20 |  |  | 3 | 22-Jun-25 A | 2027-01-20 | 28-Jun-25 A | 2026-02-20 | 2027-01-20
| A42840 | Process Datasheet for Control Valve_RCA |  | 2026-02-20 |  |  | 16 | 29-Jun-25 A | 2027-01-20 | 05-Jul-25 A | 2026-02-20 | 2027-01-20
| A42850 | Process Datasheet for Control Valve_IFD/IFC |  | 2026-02-20 |  |  | 2 | 06-Jul-25 A | 2027-01-20 | 12-Jul-25 A | 2026-02-20 | 2027-01-20
| Process Datasheet for Relief Valve |  |  | 2026-02-20 |  |  | 275 | 25-Jan-25 A | 2026-03-02 | 19-Jan-26 A | 2026-02-20 | 2027-01-20
| A42860 | Process Datasheet for Relief Valve_IFR |  | 2026-02-20 |  |  | 6 | 25-Jan-25 A | 2026-03-02 | 20-Apr-25 A | 2026-02-20 | 2026-03-02
| A42870 | Process Datasheet for Relief Valve_RCC |  | 2026-02-20 |  |  | 16 | 16-Jul-25 A | 2027-01-20 | 01-Aug-25 A | 2026-02-20 | 2027-01-20
| A42880 | Process Datasheet for Relief Valve_IFA |  | 2026-02-20 |  |  | 3 | 19-Dec-25 A | 2027-01-20 | 24-Dec-25 A | 2026-02-20 | 2027-01-20
| A42890 | Process Datasheet for Relief Valve_RCA |  | 2026-02-20 |  |  | 16 | 24-Dec-25 A | 2027-01-20 | 15-Jan-26 A | 2026-02-20 | 2027-01-20
| A42900 | Process Datasheet for Relief Valve_IFD/IFC |  | 2026-02-20 |  |  | 2 | 15-Jan-26 A | 2027-01-20 | 19-Jan-26 A | 2026-02-20 | 2027-01-20
| Process Datasheet for Flow Instrument |  |  | 2026-02-20 |  |  | 320 | 20-Feb-25 A | 2026-03-02 | 2026-03-23 | 2026-03-23 | 2027-01-20 | 218
| A42910 | Process Datasheet for Flow Instrument_IFR |  | 2026-02-20 |  |  | 6 | 20-Feb-25 A | 2026-03-02 | 25-Apr-25 A | 2026-02-20 | 2026-03-02
| A42920 | Process Datasheet for Flow Instrument_RCC |  | 2026-02-20 |  |  | 16 | 26-Apr-25 A | 2026-12-22 | 26-May-25 A | 2026-02-20 | 2026-12-22
| A42930 | Process Datasheet for Flow Instrument_IFA |  | 2026-02-20 |  |  | 3 | 2026-02-20 | 2026-12-22 | 2026-02-25 | 2026-02-25 | 2026-12-25 | 218
| A42940 | Process Datasheet for Flow Instrument_RCA |  | 2026-02-25 |  |  | 16 | 2026-02-25 | 2026-12-28 | 2026-03-19 | 2026-03-19 | 2027-01-18 | 218
| A42950 | Process Datasheet for Flow Instrument_IFD/IFC |  | 2026-03-19 |  |  | 2 | 2026-03-19 | 2027-01-18 | 2026-03-23 | 2026-03-23 | 2027-01-20 | 218
| Flare Relief Load Summary |  |  | 2026-02-20 |  |  | 278 | 31-Jan-25 A | 2026-03-25 | 2026-02-24 | 2026-02-24 | 2026-03-27 | 23
| A43170 | Flare Relief Load Summary_RCC |  | 2026-02-20 |  |  | 16 | 12-Mar-25 A | 2026-03-25 | 20-Apr-25 A | 2026-02-20 | 2026-03-25
| A43180 | Flare Relief Load Summary_IFA |  | 2026-02-20 |  |  | 3 | 09-Dec-25 A | 2026-03-25 | 19-Dec-25 A | 2026-02-20 | 2026-03-25
| A43190 | Flare Relief Load Summary_RCA |  | 2026-02-20 |  |  | 16 | 16-Dec-25 A | 2026-03-25 | 13-Feb-26 A | 2026-02-20 | 2026-03-25
| A43200 | Flare Relief Load Summary_IFD/IFC |  | 2026-02-20 |  |  | 2 | 2026-02-20 | 2026-03-25 | 2026-02-24 | 2026-02-24 | 2026-03-27 | 23
| Flare Relief & Blowdown Report |  |  | 2026-02-20 |  |  | 103 | 03-May-25 A | 2026-11-23 | 2026-03-17 | 2026-03-17 | 2027-01-20 | 221
| A43120 | Flare Relief & Blowdown Report_RCC |  | 2026-02-20 |  |  | 16 | 05-May-25 A | 2026-12-28 | 18-May-25 A | 2026-02-20 | 2026-12-28
| A43130 | Flare Relief & Blowdown Report_IFA |  | 2026-02-20 |  |  | 3 | 05-Dec-25 A | 2026-12-28 | 19-Dec-25 A | 2026-02-20 | 2026-12-28
| A43140 | Flare Relief & Blowdown Report_RCA |  | 2026-02-20 |  |  | 16 | 2026-02-20 | 2026-12-28 | 2026-03-13 | 2026-03-13 | 2027-01-18 | 221
| A43150 | Flare Relief & Blowdown Report_IFD/IFC |  | 2026-03-13 |  |  | 2 | 2026-03-13 | 2027-01-18 | 2026-03-17 | 2026-03-17 | 2027-01-20 | 221
| Dynamic Flare Simulation Study |  |  | 2026-02-20 |  |  | 43 | 2026-02-20 | 2026-11-23 | 2026-04-21 | 2026-04-21 | 2027-01-20 | 196
| A43010 | Dynamic Flare Simulation Study_IFR |  | 2026-02-20 |  |  | 6 | 2026-02-20 | 2026-11-23 | 2026-02-27 | 2026-02-27 | 2026-11-30 | 196
| A43020 | Dynamic Flare Simulation Study_RCC |  | 2026-02-27 |  |  | 16 | 2026-02-27 | 2026-11-30 | 2026-03-23 | 2026-03-23 | 2026-12-22 | 196
| A43030 | Dynamic Flare Simulation Study_IFA |  | 2026-03-23 |  |  | 3 | 2026-03-23 | 2026-12-22 | 2026-03-26 | 2026-03-26 | 2026-12-25 | 196
| A43040 | Dynamic Flare Simulation Study_RCA |  | 2026-03-26 |  |  | 16 | 2026-03-26 | 2026-12-28 | 2026-04-17 | 2026-04-17 | 2027-01-18 | 196
| A43050 | Dynamic Flare Simulation Study_IFD/IFC |  | 2026-04-17 |  |  | 2 | 2026-04-17 | 2027-01-18 | 2026-04-21 | 2026-04-21 | 2027-01-20 | 196
| 3D Modelling Procedure |  |  | 2026-02-20 |  |  | 224 | 01-Mar-25 A | 2026-03-02 | 15-Oct-25 A | 2026-02-20 | 2027-01-20
| A43270 | 3D Modelling Procedure_RCC |  | 2026-02-20 |  |  | 16 | 21-Apr-25 A | 2027-01-20 | 28-Apr-25 A | 2026-02-20 | 2027-01-20
| A43280 | 3D Modelling Procedure_IFA |  | 2026-02-20 |  |  | 3 | 29-Apr-25 A | 2027-01-20 | 21-Jun-25 A | 2026-02-20 | 2027-01-20
| A43290 | 3D Modelling Procedure_RCA |  | 2026-02-20 |  |  | 16 | 01-Aug-25 A | 2027-01-20 | 23-Aug-25 A | 2026-02-20 | 2027-01-20
| A43300 | 3D Modelling Procedure_IFD/IFC |  | 2026-02-20 |  |  | 2 | 12-Oct-25 A | 2027-01-20 | 15-Oct-25 A | 2026-02-20 | 2027-01-20
| 3D Model Execution Philosophy |  |  | 2026-02-20 |  |  | 224 | 25-Mar-25 A | 2026-10-19 | 14-Oct-25 A | 2026-02-20 | 2027-01-20
| A55410 | 3D Model Execution Philosophy_RCC |  | 2026-02-20 |  |  | 16 | 16-Apr-25 A | 2027-01-20 | 28-Apr-25 A | 2026-02-20 | 2027-01-20
| A55420 | 3D Model Execution Philosophy_IFA |  | 2026-02-20 |  |  | 3 | 29-Apr-25 A | 2027-01-20 | 21-Jun-25 A | 2026-02-20 | 2027-01-20
| A55430 | 3D Model Execution Philosophy_RCA |  | 2026-02-20 |  |  | 16 | 20-Jul-25 A | 2027-01-20 | 08-Aug-25 A | 2026-02-20 | 2027-01-20
| A55440 | 3D Model Execution Philosophy_IFD/IFC |  | 2026-02-20 |  |  | 2 | 11-Oct-25 A | 2027-01-20 | 14-Oct-25 A | 2026-02-20 | 2027-01-20
| 3D Model Review Procedure |  |  | 2026-02-20 |  |  | 248 | 25-Mar-25 A | 2027-01-20 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| A43320 | 3D Model Review Procedure_RCC |  | 2026-02-20 |  |  | 16 | 16-Apr-25 A | 2027-01-20 | 28-Apr-25 A | 2026-02-20 | 2027-01-20
| A43330 | 3D Model Review Procedure_IFA |  | 2026-02-20 |  |  | 3 | 29-Apr-25 A | 2027-01-20 | 21-Jun-25 A | 2026-02-20 | 2027-01-20
| A43340 | 3D Model Review Procedure_RCA |  | 2026-02-20 |  |  | 16 | 22-Jun-25 A | 2027-01-20 | 05-Sep-25 A | 2026-02-20 | 2027-01-20
| A43350 | 3D Model Review Procedure_IFD/IFC |  | 2026-02-20 |  |  | 2 | 19-Dec-25 A | 2027-01-20 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| Clash Check Procedure |  |  | 2026-02-20 |  |  | 117 | 22-Mar-25 A | 2026-10-19 | 11-May-25 A | 2026-02-20 | 2027-01-20
| A27870 | Clash Check Procedure_RCC |  | 2026-02-20 |  |  | 16 | 13-Apr-25 A | 2027-01-20 | 20-Apr-25 A | 2026-02-20 | 2027-01-20
| A27880 | Clash Check Procedure_IFA |  | 2026-02-20 |  |  | 3 | 21-Apr-25 A | 2027-01-20 | 27-Apr-25 A | 2026-02-20 | 2027-01-20
| A55460 | Clash Check Procedure_RCA |  | 2026-02-20 |  |  | 16 | 28-Apr-25 A | 2027-01-20 | 04-May-25 A | 2026-02-20 | 2027-01-20
| A55470 | Clash Check Procedure_IFD/IFC |  | 2026-02-20 |  |  | 2 | 05-May-25 A | 2027-01-20 | 11-May-25 A | 2026-02-20 | 2027-01-20
| Deliverables Extraction Procedure |  |  | 2026-02-20 |  |  | 38 | 23-Jan-25 A | 2026-10-19 | 12-Mar-25 A | 2026-02-20 | 2027-01-20
| A55490 | Deliverables Extraction Procedure_RCC |  | 2026-02-20 |  |  | 16 | 13-Feb-25 A | 2027-01-20 | 19-Feb-25 A | 2026-02-20 | 2027-01-20
| A55500 | Deliverables Extraction Procedure_IFA |  | 2026-02-20 |  |  | 3 | 20-Feb-25 A | 2027-01-20 | 26-Feb-25 A | 2026-02-20 | 2027-01-20
| A55510 | Deliverables Extraction Procedure_RCA |  | 2026-02-20 |  |  | 16 | 27-Feb-25 A | 2027-01-20 | 05-Mar-25 A | 2026-02-20 | 2027-01-20
| A55520 | Deliverables Extraction Procedure_IFD/IFC |  | 2026-02-20 |  |  | 2 | 06-Mar-25 A | 2027-01-20 | 12-Mar-25 A | 2026-02-20 | 2027-01-20
| Data Handover Procedure |  |  | 2026-02-20 |  |  | 212 | 21-Jun-25 A | 2026-10-19 | 2026-04-14 | 2026-04-14 | 2026-12-09 | 172
| A27970 | Data Handover Procedure_RCC |  | 2026-02-20 |  |  | 16 | 2026-02-20 | 2026-10-19 | 2026-03-13 | 2026-03-13 | 2026-11-10 | 172
| A55530 | Data Handover Procedure_IFA |  | 2026-03-13 |  |  | 3 | 2026-03-13 | 2026-11-10 | 2026-03-19 | 2026-03-19 | 2026-11-13 | 172
| A55540 | Data Handover Procedure_RCA |  | 2026-03-19 |  |  | 16 | 2026-03-19 | 2026-11-16 | 2026-04-09 | 2026-04-09 | 2026-12-07 | 172
| A55550 | Data Handover Procedure_IFD/IFC |  | 2026-04-09 |  |  | 2 | 2026-04-09 | 2026-12-07 | 2026-04-14 | 2026-04-14 | 2026-12-09 | 172
| Stress Critical Line List |  |  | 2026-02-20 |  |  | 287 | 15-Apr-25 A | 2026-12-28 | 2026-03-17 | 2026-03-17 | 2027-01-20 | 221
| A43470 | Stress Critical Line List_RCC |  | 2026-02-20 |  |  | 16 | 07-May-25 A | 2026-12-28 | 13-May-25 A | 2026-02-20 | 2026-12-28
| A43480 | Stress Critical Line List_IFA |  | 2026-02-20 |  |  | 3 | 04-Dec-25 A | 2026-12-28 | 19-Dec-25 A | 2026-02-20 | 2026-12-28
| A43490 | Stress Critical Line List_RCA |  | 2026-02-20 |  |  | 16 | 2026-02-20 | 2026-12-28 | 2026-03-13 | 2026-03-13 | 2027-01-18 | 221
| A43500 | Stress Critical Line List_IFD/IFC |  | 2026-03-13 |  |  | 2 | 2026-03-13 | 2027-01-18 | 2026-03-17 | 2026-03-17 | 2027-01-20 | 221
| Datasheets for Ball Valves |  |  | 2026-02-20 |  |  | 255 | 16-Jan-25 A | 2026-03-17 | 21-Nov-25 A | 2026-02-20 | 2026-03-17
| A43670 | Datasheets for Ball Valves_RCC |  | 2026-02-20 |  |  | 16 | 01-Aug-25 A | 2026-03-17 | 25-Aug-25 A | 2026-02-20 | 2026-03-17
| A43680 | Datasheets for Ball Valves_IFA |  | 2026-02-20 |  |  | 3 | 22-Oct-25 A | 2026-03-17 | 30-Oct-25 A | 2026-02-20 | 2026-03-17
| A43690 | Datasheets for Ball Valves_RCA |  | 2026-02-20 |  |  | 16 | 31-Oct-25 A | 2026-03-17 | 07-Nov-25 A | 2026-02-20 | 2026-03-17
| A43700 | Datasheets for Ball Valves_IFD/IFC |  | 2026-02-20 |  |  | 2 | 10-Nov-25 A | 2026-03-17 | 21-Nov-25 A | 2026-02-20 | 2026-03-17
| Datasheets for Double Block & Bleed Valves |  |  | 2026-02-20 |  |  | 208 | 27-Jan-25 A | 2026-03-17 | 22-Aug-25 A | 2026-02-20 | 2026-03-19
| A43770 | Datasheets for Double Block & Bleed Valves_RCC |  | 2026-02-20 |  |  | 16 | 02-Aug-25 A | 2026-03-19 | 10-Aug-25 A | 2026-02-20 | 2026-03-19
| A43780 | Datasheets for Double Block & Bleed Valves_IFA |  | 2026-02-20 |  |  | 3 | 11-Aug-25 A | 2026-03-19 | 15-Aug-25 A | 2026-02-20 | 2026-03-19
| A43790 | Datasheets for Double Block & Bleed Valves_RCA |  | 2026-02-20 |  |  | 16 | 16-Aug-25 A | 2026-03-19 | 20-Aug-25 A | 2026-02-20 | 2026-03-19
| A43800 | Datasheets for Double Block & Bleed Valves_IFD/IFC |  | 2026-02-20 |  |  | 2 | 21-Aug-25 A | 2026-03-19 | 22-Aug-25 A | 2026-02-20 | 2026-03-19
| Datasheets for Check Valves |  |  | 2026-02-20 |  |  | 232 | 23-Jan-25 A | 2026-03-17 | 17-Nov-25 A | 2026-02-20 | 2026-03-19
| A43720 | Datasheets for Check Valves_RCC |  | 2026-02-20 |  |  | 16 | 15-May-25 A | 2026-03-19 | 21-Jun-25 A | 2026-02-20 | 2026-03-19
| A43730 | Datasheets for Check Valves_IFA |  | 2026-02-20 |  |  | 3 | 06-Aug-25 A | 2026-03-19 | 12-Aug-25 A | 2026-02-20 | 2026-03-19
| A43740 | Datasheets for Check Valves_RCA |  | 2026-02-20 |  |  | 16 | 02-Sep-25 A | 2026-03-19 | 03-Nov-25 A | 2026-02-20 | 2026-03-19
| A43750 | Datasheets for Check Valves_IFD/IFC |  | 2026-02-20 |  |  | 2 | 04-Nov-25 A | 2026-03-19 | 17-Nov-25 A | 2026-02-20 | 2026-03-19
| Datasheets for Butterfly Valves |  |  | 2026-02-20 |  |  | 246 | 16-Jan-25 A | 2026-03-17 | 20-Nov-25 A | 2026-02-20 | 2026-03-19
| A43820 | Datasheets for Butterfly Valves_RCC |  | 2026-02-20 |  |  | 16 | 04-Aug-25 A | 2026-03-19 | 27-Aug-25 A | 2026-02-20 | 2026-03-19
| A43830 | Datasheets for Butterfly Valves_IFA |  | 2026-02-20 |  |  | 3 | 31-Aug-25 A | 2026-03-19 | 03-Sep-25 A | 2026-02-20 | 2026-03-19
| A43840 | Datasheets for Butterfly Valves_RCA |  | 2026-02-20 |  |  | 16 | 20-Sep-25 A | 2026-03-19 | 13-Oct-25 A | 2026-02-20 | 2026-03-19
| A43850 | Datasheets for Butterfly Valves_IFD/IFC |  | 2026-02-20 |  |  | 2 | 10-Nov-25 A | 2026-03-19 | 20-Nov-25 A | 2026-02-20 | 2026-03-19
| Datasheets for Needle Valves |  |  | 2026-02-20 |  |  | 200 | 01-Aug-25 A | 2026-03-17 | 22-Aug-25 A | 2026-02-20 | 2026-03-19
| A43870 | Datasheets for Needle Valves_RCC |  | 2026-02-20 |  |  | 16 | 06-Aug-25 A | 2026-03-19 | 12-Aug-25 A | 2026-02-20 | 2026-03-19
| A43880 | Datasheets for Needle Valves_IFA |  | 2026-02-20 |  |  | 3 | 13-Aug-25 A | 2026-03-19 | 15-Aug-25 A | 2026-02-20 | 2026-03-19
| A43890 | Datasheets for Needle Valves_RCA |  | 2026-02-20 |  |  | 16 | 16-Aug-25 A | 2026-03-19 | 20-Aug-25 A | 2026-02-20 | 2026-03-19
| A43900 | Datasheets for Needle Valves_IFD/IFC |  | 2026-02-20 |  |  | 2 | 20-Aug-25 A | 2026-03-19 | 22-Aug-25 A | 2026-02-20 | 2026-03-19
| Datasheets for Insulating Gaskets |  |  | 2026-02-20 |  |  | 58 | 22-Sep-25 A | 2026-03-17 | 13-Jan-26 A | 2026-02-20 | 2026-03-17
| A43920 | Datasheets for Insulating Gaskets_RCC |  | 2026-02-20 |  |  | 16 | 23-Sep-25 A | 2026-03-17 | 06-Oct-25 A | 2026-02-20 | 2026-03-17
| A43930 | Datasheets for Insulating Gaskets_IFA |  | 2026-02-20 |  |  | 3 | 03-Dec-25 A | 2026-03-17 | 18-Dec-25 A | 2026-02-20 | 2026-03-17
| A43940 | Datasheets for Insulating Gaskets_RCA |  | 2026-02-20 |  |  | 16 | 19-Dec-25 A | 2026-03-17 | 09-Jan-26 A | 2026-02-20 | 2026-03-17
| A43950 | Datasheets for Insulating Gaskets_IFD/IFC |  | 2026-02-20 |  |  | 2 | 09-Jan-26 A | 2026-03-17 | 13-Jan-26 A | 2026-02-20 | 2026-03-17
| Datasheets for Flame Arrestors |  |  | 2026-02-20 |  |  | 125 | 20-Apr-25 A | 2026-04-17 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| A43970 | Datasheets for Flame Arrestors_RCC |  | 2026-02-20 |  |  | 16 | 12-May-25 A | 2027-01-20 | 18-May-25 A | 2026-02-20 | 2027-01-20
| A43980 | Datasheets for Flame Arrestors_IFA |  | 2026-02-20 |  |  | 3 | 19-May-25 A | 2027-01-20 | 25-May-25 A | 2026-02-20 | 2027-01-20
| A43990 | Datasheets for Flame Arrestors_RCA |  | 2026-02-20 |  |  | 16 | 26-May-25 A | 2027-01-20 | 14-Oct-25 A | 2026-02-20 | 2027-01-20
| A44000 | Datasheets for Flame Arrestors_IFD/IFC |  | 2026-02-20 |  |  | 2 | 19-Dec-25 A | 2027-01-20 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| Datasheets for Flame Bird Screen |  |  | 2026-02-20 |  |  | 193 | 15-Apr-25 A | 2026-04-17 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| A44020 | Datasheets for Flame Bird Screen_RCC |  | 2026-02-20 |  |  | 16 | 07-May-25 A | 2027-01-20 | 13-May-25 A | 2026-02-20 | 2027-01-20
| A44030 | Datasheets for Flame Bird Screen_IFA |  | 2026-02-20 |  |  | 3 | 20-Aug-25 A | 2027-01-20 | 27-Aug-25 A | 2026-02-20 | 2027-01-20
| A44040 | Datasheets for Flame Bird Screen_RCA |  | 2026-02-20 |  |  | 16 | 01-Oct-25 A | 2027-01-20 | 27-Oct-25 A | 2026-02-20 | 2027-01-20
| A44050 | Datasheets for Flame Bird Screen_IFD/IFC |  | 2026-02-20 |  |  | 2 | 19-Dec-25 A | 2027-01-20 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| Datasheets for Hose Coupling |  |  | 2026-02-20 |  |  | 128 | 01-Jul-25 A | 2026-03-17 | 23-Dec-25 A | 2026-02-20 | 2026-03-17
| A44070 | Datasheets for Hose Coupling_RCC |  | 2026-02-20 |  |  | 16 | 05-Jul-25 A | 2026-03-17 | 25-Jul-25 A | 2026-02-20 | 2026-03-17
| A44080 | Datasheets for Hose Coupling_IFA |  | 2026-02-20 |  |  | 3 | 05-Aug-25 A | 2026-03-17 | 12-Aug-25 A | 2026-02-20 | 2026-03-17
| A44090 | Datasheets for Hose Coupling_RCA |  | 2026-02-20 |  |  | 16 | 09-Aug-25 A | 2026-03-17 | 27-Aug-25 A | 2026-02-20 | 2026-03-17
| A44100 | Datasheets for Hose Coupling_IFD/IFC |  | 2026-02-20 |  |  | 2 | 19-Dec-25 A | 2026-03-17 | 23-Dec-25 A | 2026-02-20 | 2026-03-17
| Datasheets for Strainers |  |  | 2026-02-20 |  |  | 188 | 14-Apr-25 A | 2026-04-17 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| A44120 | Datasheets for Strainers_RCC |  | 2026-02-20 |  |  | 16 | 06-May-25 A | 2027-01-20 | 12-May-25 A | 2026-02-20 | 2027-01-20
| A44130 | Datasheets for Strainers_IFA |  | 2026-02-20 |  |  | 3 | 13-May-25 A | 2027-01-20 | 01-Sep-25 A | 2026-02-20 | 2027-01-20
| A44140 | Datasheets for Strainers_RCA |  | 2026-02-20 |  |  | 16 | 02-Sep-25 A | 2027-01-20 | 08-Sep-25 A | 2026-02-20 | 2027-01-20
| A44150 | Datasheets for Strainers_IFD/IFC |  | 2026-02-20 |  |  | 2 | 19-Dec-25 A | 2027-01-20 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| Datasheets for Spring Hangers |  |  | 2026-02-20 |  |  | 306 | 25-Apr-25 A | 2026-03-19 | 2026-03-23 | 2026-03-23 | 2027-01-18 | 215
| A44170 | Datasheets for Spring Hangers_RCC |  | 2026-02-20 |  |  | 16 | 01-May-25 A | 2026-12-18 | 15-May-25 A | 2026-02-20 | 2026-12-18
| A44180 | Datasheets for Spring Hangers_IFA |  | 2026-02-20 |  |  | 3 | 2026-02-20 | 2026-12-18 | 2026-02-25 | 2026-02-25 | 2026-12-23 | 215
| A44190 | Datasheets for Spring Hangers_RCA |  | 2026-02-25 |  |  | 16 | 2026-02-25 | 2026-12-23 | 2026-03-19 | 2026-03-19 | 2027-01-14 | 215
| A44200 | Datasheets for Spring Hangers_IFD/IFC |  | 2026-03-19 |  |  | 2 | 2026-03-19 | 2027-01-14 | 2026-03-23 | 2026-03-23 | 2027-01-18 | 215
| Datasheets for Rigid Struts |  |  | 2026-02-20 |  |  | 301 | 15-Apr-25 A | 2026-12-23 | 2026-03-17 | 2026-03-17 | 2027-01-18 | 219
| A44220 | Datasheets for Rigid Struts_RCC |  | 2026-02-20 |  |  | 16 | 07-May-25 A | 2026-12-23 | 13-May-25 A | 2026-02-20 | 2026-12-23
| A44230 | Datasheets for Rigid Struts_IFA |  | 2026-02-20 |  |  | 3 | 10-Dec-25 A | 2026-12-23 | 17-Dec-25 A | 2026-02-20 | 2026-12-23
| A44240 | Datasheets for Rigid Struts_RCA |  | 2026-02-20 |  |  | 16 | 2026-02-20 | 2026-12-23 | 2026-03-13 | 2026-03-13 | 2027-01-14 | 219
| A44250 | Datasheets for Rigid Struts_IFD/IFC |  | 2026-03-13 |  |  | 2 | 2026-03-13 | 2027-01-14 | 2026-03-17 | 2026-03-17 | 2027-01-18 | 219
| Datasheet for Piping Speciality Items |  |  | 2026-02-20 |  |  | 131 | 01-Sep-25 A | 2026-04-17 | 2026-03-23 | 2026-03-23 | 2027-01-18 | 215
| A54490 | Datasheet for Piping Speciality Items_IFR |  | 2026-02-20 |  |  | 2 | 01-Sep-25 A | 2026-04-17 | 12-Sep-25 A | 2026-02-20 | 2026-04-17
| A54500 | Datasheet for Piping Speciality Items_RCC |  | 2026-02-20 |  |  | 16 | 15-Sep-25 A | 2026-12-17 | 19-Sep-25 A | 2026-02-20 | 2026-12-17
| A54510 | Datasheet for Piping Speciality Items_IFA |  | 2026-02-20 |  |  | 3 | 2026-02-20 | 2026-12-17 | 2026-02-25 | 2026-02-25 | 2026-12-22 | 214
| A54520 | Datasheet for Piping Speciality Items_RCA |  | 2026-02-25 |  |  | 16 | 2026-02-25 | 2026-12-23 | 2026-03-19 | 2026-03-19 | 2027-01-14 | 215
| A54530 | Datasheet for Piping Speciality Items_IFD/IFC |  | 2026-03-19 |  |  | 2 | 2026-03-19 | 2027-01-14 | 2026-03-23 | 2026-03-23 | 2027-01-18 | 215
| Material Requisition for Piping Bulk |  |  | 2026-02-20 |  |  | 260 | 15-Apr-25 A | 2026-03-19 | 16-Jan-26 A | 2026-02-20 | 2026-03-19
| A44730 | Material Requisition for Piping Bulk_RCC |  | 2026-02-20 |  |  | 16 | 20-Jul-25 A | 2026-03-19 | 10-Aug-25 A | 2026-02-20 | 2026-03-19
| A44740 | Material Requisition for Piping Bulk_IFA |  | 2026-02-20 |  |  | 3 | 15-Oct-25 A | 2026-03-19 | 29-Oct-25 A | 2026-02-20 | 2026-03-19
| A44750 | Material Requisition for Piping Bulk_RCA |  | 2026-02-20 |  |  | 16 | 30-Oct-25 A | 2026-03-19 | 10-Nov-25 A | 2026-02-20 | 2026-03-19
| A44760 | Material Requisition for Piping Bulk_IFD/IFC |  | 2026-02-20 |  |  | 2 | 14-Jan-26 A | 2026-03-19 | 16-Jan-26 A | 2026-02-20 | 2026-03-19
| Material Requisition for HDPE Piping Bulk |  |  | 2026-02-20 |  |  | 100 | 15-Oct-25 A | 2026-03-17 | 2026-02-24 | 2026-02-24 | 2026-03-19 | 18
| A60050 | Material Requisition for HDPE Piping Bulk_IFR |  | 2026-02-20 |  |  | 6 | 15-Oct-25 A | 2026-03-17 | 26-Oct-25 A | 2026-02-20 | 2026-03-17
| A60060 | Material Requisition for HDPE Piping Bulk_RCC |  | 2026-02-20 |  |  | 16 | 26-Oct-25 A | 2026-03-17 | 10-Nov-25 A | 2026-02-20 | 2026-03-17
| A60070 | Material Requisition for HDPE Piping Bulk_IFA |  | 2026-02-20 |  |  | 3 | 10-Nov-25 A | 2026-03-17 | 27-Nov-25 A | 2026-02-20 | 2026-03-17
| A60080 | Material Requisition for HDPE Piping Bulk_RCA |  | 2026-02-20 |  |  | 16 | 27-Nov-25 A | 2026-03-17 | 16-Dec-25 A | 2026-02-20 | 2026-03-17
| A60090 | Material Requisition for HDPE Piping Bulk_IFD/IFC |  | 2026-02-20 |  |  | 2 | 2026-02-20 | 2026-03-17 | 2026-02-24 | 2026-02-24 | 2026-03-19 | 18
| Material Requisition for Manual Valves |  |  | 2026-02-20 |  |  | 129 | 01-Jul-25 A | 2026-03-19 | 10-Oct-25 A | 2026-02-20 | 2026-03-19
| A44770 | Material Requisition for Manual Valves_IFR |  | 2026-02-20 |  |  | 1 | 01-Jul-25 A | 2026-03-19 | 12-Jul-25 A | 2026-02-20 | 2026-03-19
| A44780 | Material Requisition for Manual Valves_RCC |  | 2026-02-20 |  |  | 6 | 21-Aug-25 A | 2026-03-19 | 31-Aug-25 A | 2026-02-20 | 2026-03-19
| A44790 | Material Requisition for Manual Valves_IFA |  | 2026-02-20 |  |  | 1 | 01-Sep-25 A | 2026-03-19 | 10-Sep-25 A | 2026-02-20 | 2026-03-19
| A44800 | Material Requisition for Manual Valves_RCA |  | 2026-02-20 |  |  | 16 | 11-Sep-25 A | 2026-03-19 | 15-Sep-25 A | 2026-02-20 | 2026-03-19
| A44810 | Material Requisition for Manual Valves_IFD/IFC |  | 2026-02-20 |  |  | 2 | 22-Sep-25 A | 2026-03-19 | 10-Oct-25 A | 2026-02-20 | 2026-03-19
| Material Requisition for Piping Speciality Items |  |  | 2026-02-20 |  |  | 147 | 15-Sep-25 A | 2026-04-17 | 2026-04-14 | 2026-04-14 | 2027-01-20 | 202
| A44830 | Material Requisition for Piping Speciality Items_RCC |  | 2026-02-20 |  |  | 16 | 2026-02-20 | 2026-11-30 | 2026-03-13 | 2026-03-13 | 2026-12-22 | 202
| A44840 | Material Requisition for Piping Speciality Items_IFA |  | 2026-03-13 |  |  | 3 | 2026-03-13 | 2026-12-22 | 2026-03-19 | 2026-03-19 | 2026-12-25 | 202
| A44850 | Material Requisition for Piping Speciality Items_RCA |  | 2026-03-19 |  |  | 16 | 2026-03-19 | 2026-12-28 | 2026-04-09 | 2026-04-09 | 2027-01-18 | 202
| A44860 | Material Requisition for Piping Speciality Items_IFD/IFC |  | 2026-04-09 |  |  | 2 | 2026-04-09 | 2027-01-18 | 2026-04-14 | 2026-04-14 | 2027-01-20 | 202
| Material Requisition for Spring Hangers |  |  | 2026-02-20 |  |  | 222 | 22-Apr-25 A | 2026-03-19 | 2026-03-25 | 2026-03-25 | 2027-01-20 | 215
| A44880 | Material Requisition for Spring Hangers_RCC |  | 2026-02-20 |  |  | 16 | 14-May-25 A | 2026-03-30 | 20-May-25 A | 2026-02-20 | 2026-03-30
| A44890 | Material Requisition for Spring Hangers_IFA |  | 2026-02-20 |  |  | 3 | 04-Dec-25 A | 2026-12-28 | 18-Dec-25 A | 2026-02-20 | 2026-12-28
| A44900 | Material Requisition for Spring Hangers_RCA |  | 2026-02-20 |  |  | 16 | 2026-02-20 | 2026-12-28 | 2026-03-13 | 2026-03-13 | 2027-01-18 | 221
| A44910 | Material Requisition for Spring Hangers_IFD/IFC |  | 2026-03-23 |  |  | 2 | 2026-03-23 | 2027-01-18 | 2026-03-25 | 2026-03-25 | 2027-01-20 | 215
| Material Requisition for Rigid Struts |  |  | 2026-02-20 |  |  | 216 | 22-Apr-25 A | 2026-12-28 | 2026-03-20 | 2026-03-20 | 2027-01-20 | 219
| A44930 | Material Requisition for Rigid Struts_RCC |  | 2026-02-20 |  |  | 16 | 14-May-25 A | 2026-12-28 | 20-May-25 A | 2026-02-20 | 2026-12-28
| A44940 | Material Requisition for Rigid Struts_IFA |  | 2026-02-20 |  |  | 3 | 01-Dec-25 A | 2026-12-28 | 12-Dec-25 A | 2026-02-20 | 2026-12-28
| A44950 | Material Requisition for Rigid Struts_RCA |  | 2026-02-20 |  |  | 16 | 2026-02-20 | 2026-12-28 | 2026-03-13 | 2026-03-13 | 2027-01-18 | 221
| A44960 | Material Requisition for Rigid Struts_IFD/IFC |  | 2026-03-18 |  |  | 2 | 2026-03-18 | 2027-01-18 | 2026-03-20 | 2026-03-20 | 2027-01-20 | 219
| Utility Station Location Plan |  |  | 2026-02-20 |  |  | 231 | 15-Apr-25 A | 2027-01-20 | 19-Jan-26 A | 2026-02-20 | 2027-01-20
| A43520 | Utility Station Location Plan_RCC |  | 2026-02-20 |  |  | 16 | 20-Jul-25 A | 2027-01-20 | 08-Aug-25 A | 2026-02-20 | 2027-01-20
| A43530 | Utility Station Location Plan_IFA |  | 2026-02-20 |  |  | 3 | 19-Dec-25 A | 2027-01-20 | 24-Dec-25 A | 2026-02-20 | 2027-01-20
| A43540 | Utility Station Location Plan_RCA |  | 2026-02-20 |  |  | 16 | 24-Dec-25 A | 2027-01-20 | 15-Jan-26 A | 2026-02-20 | 2027-01-20
| A43550 | Utility Station Location Plan_IFD/IFC |  | 2026-02-20 |  |  | 2 | 15-Jan-26 A | 2027-01-20 | 19-Jan-26 A | 2026-02-20 | 2027-01-20
| 30% 3D Model Review Report |  |  | 2026-02-20 |  |  | 108 | 25-Apr-25 A | 2026-03-02 | 21-Aug-25 A | 2026-02-20 | 2026-03-17
| A43570 | 30% 3D Model Review Report_RCC |  | 2026-02-20 |  |  | 16 | 17-May-25 A | 2026-03-17 | 23-May-25 A | 2026-02-20 | 2026-03-17
| A43580 | 30% 3D Model Review Report_IFA |  | 2026-02-20 |  |  | 3 | 24-May-25 A | 2026-03-17 | 10-Aug-25 A | 2026-02-20 | 2026-03-17
| A43590 | 30% 3D Model Review Report_RCA |  | 2026-02-20 |  |  | 16 | 11-Aug-25 A | 2026-03-17 | 15-Aug-25 A | 2026-02-20 | 2026-03-17
| A43600 | 30% 3D Model Review Report_IFD/IFC |  | 2026-02-20 |  |  | 2 | 16-Aug-25 A | 2026-03-17 | 21-Aug-25 A | 2026-02-20 | 2026-03-17
| 30% 3D Model Review Closeout Report |  |  | 2026-02-20 |  |  | 120 | 01-Jul-25 A | 2026-03-02 | 19-Dec-25 A | 2026-02-20 | 2026-03-18
| A43620 | 30% 3D Model Review Closeout Report_RCC |  | 2026-02-20 |  |  | 16 | 27-Aug-25 A | 2026-03-18 | 27-Nov-25 A | 2026-02-20 | 2026-03-18
| A43630 | 30% 3D Model Review Closeout Report_IFA |  | 2026-02-20 |  |  | 3 | 27-Nov-25 A | 2026-03-18 | 02-Dec-25 A | 2026-02-20 | 2026-03-18
| A43640 | 30% 3D Model Review Closeout Report_RCA |  | 2026-02-20 |  |  | 16 | 02-Dec-25 A | 2026-03-18 | 15-Dec-25 A | 2026-02-20 | 2026-03-18
| A43650 | 30% 3D Model Review Closeout Report_IFD/IFC |  | 2026-02-20 |  |  | 2 | 10-Dec-25 A | 2026-03-18 | 19-Dec-25 A | 2026-02-20 | 2026-03-18
| Plot Plan |  |  | 2026-02-20 |  |  | 228 | 09-Mar-25 A | 2026-03-02 | 25-Oct-25 A | 2026-02-20 | 2026-10-16
| A55670 | Plot Plan_Preliminary issuance for Plot plan workshop |  | 2026-02-20 |  |  | 6 | 09-Mar-25 A | 2026-03-02 | 12-Mar-25 A | 2026-02-20 | 2026-03-02
| A45230 | Plot Plan_RCC |  | 2026-02-20 |  |  | 16 | 28-Apr-25 A | 2026-03-19 | 11-Jun-25 A | 2026-02-20 | 2026-03-19
| A45240 | Plot Plan_IFA |  | 2026-02-20 |  |  | 3 | 03-Oct-25 A | 2026-03-19 | 10-Oct-25 A | 2026-02-20 | 2026-03-19
| A45250 | Plot Plan_RCA |  | 2026-02-20 |  |  | 16 | 02-Oct-25 A | 2026-10-16 | 24-Oct-25 A | 2026-02-20 | 2026-10-16
| A45260 | Plot Plan_IFD/IFC |  | 2026-02-20 |  |  | 2 | 23-Oct-25 A | 2026-10-16 | 25-Oct-25 A | 2026-02-20 | 2026-10-16
| Plot Plan Review Report |  |  | 2026-02-20 |  |  | 121 | 19-Apr-25 A | 2027-01-20 | 16-Oct-25 A | 2026-02-20 | 2027-01-20
| A43360 | Plot Plan Review Report_IFR |  | 2026-02-20 |  |  | 6 | 19-Apr-25 A | 2027-01-20 | 10-May-25 A | 2026-02-20 | 2027-01-20
| A43370 | Plot Plan Review Report_RCC |  | 2026-02-20 |  |  | 16 | 11-May-25 A | 2027-01-20 | 17-May-25 A | 2026-02-20 | 2027-01-20
| A43380 | Plot Plan Review Report_IFA |  | 2026-02-20 |  |  | 3 | 18-May-25 A | 2027-01-20 | 21-Jun-25 A | 2026-02-20 | 2027-01-20
| A43390 | Plot Plan Review Report_RCA |  | 2026-02-20 |  |  | 16 | 22-Jun-25 A | 2027-01-20 | 28-Jun-25 A | 2026-02-20 | 2027-01-20
| A43400 | Plot Plan Review Report_IFD/IFC |  | 2026-02-20 |  |  | 2 | 10-Oct-25 A | 2027-01-20 | 16-Oct-25 A | 2026-02-20 | 2027-01-20
| First Material Take Off |  |  | 2026-02-20 |  |  | 21 | 02-Jun-25 A | 2026-04-22 | 27-Jun-25 A | 2026-02-20 | 2026-04-22
| A45280 | First Material Take Off_RCC |  | 2026-02-20 |  |  | 16 | 09-Jun-25 A | 2026-04-22 | 20-Jun-25 A | 2026-02-20 | 2026-04-22
| A45290 | First Material Take Off_IFD/IFC |  | 2026-02-20 |  |  | 2 | 23-Jun-25 A | 2026-04-22 | 27-Jun-25 A | 2026-02-20 | 2026-04-22
| Plot Plan Close Out Report |  |  | 2026-02-20 |  |  | 136 | 19-Apr-25 A | 2027-01-20 | 18-Dec-25 A | 2026-02-20 | 2027-01-20
| A43420 | Plot Plan Close Out report_RCC |  | 2026-02-20 |  |  | 16 | 11-May-25 A | 2027-01-20 | 17-May-25 A | 2026-02-20 | 2027-01-20
| A43430 | Plot Plan Close Out report_IFA |  | 2026-02-20 |  |  | 3 | 10-Oct-25 A | 2027-01-20 | 14-Oct-25 A | 2026-02-20 | 2027-01-20
| A43440 | Plot Plan Close Out report_RCA |  | 2026-02-20 |  |  | 16 | 10-Oct-25 A | 2027-01-20 | 27-Oct-25 A | 2026-02-20 | 2027-01-20
| A43450 | Plot Plan Close Out report_IFD/IFC |  | 2026-02-20 |  |  | 2 | 15-Dec-25 A | 2027-01-20 | 18-Dec-25 A | 2026-02-20 | 2027-01-20
| Manual Valves List (Valves MTOs) |  |  | 2026-02-20 |  |  | 231 | 25-Feb-25 A | 2027-01-20 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| A44690 | Manual Valves List (Valves MTOs)_IFR |  | 2026-02-20 |  |  | 6 | 25-Feb-25 A | 2027-01-20 | 10-Apr-25 A | 2026-02-20 | 2027-01-20
| A44700 | Manual Valves List (Valves MTOs)_RCC |  | 2026-02-20 |  |  | 16 | 02-Aug-25 A | 2027-01-20 | 25-Aug-25 A | 2026-02-20 | 2027-01-20
| A44710 | Manual Valves List (Valves MTOs)_IFD/IFC |  | 2026-02-20 |  |  | 2 | 19-Dec-25 A | 2027-01-20 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| Technical Bid Evaluation (TBE) for Rigid Struts |  |  | 2026-02-20 |  |  | 43 | 2026-02-20 | 2026-11-23 | 2026-04-21 | 2026-04-21 | 2027-01-20 | 196
| A45180 | Technical Bid Evaluation (TBE) for Rigid Struts_RCC |  | 2026-02-27 |  |  | 16 | 2026-02-27 | 2026-11-30 | 2026-03-23 | 2026-03-23 | 2026-12-22 | 196
| A45190 | Technical Bid Evaluation (TBE) for Rigid Struts_IFA |  | 2026-03-23 |  |  | 3 | 2026-03-23 | 2026-12-22 | 2026-03-26 | 2026-03-26 | 2026-12-25 | 196
| A45200 | Technical Bid Evaluation (TBE) for Rigid Struts_RCA |  | 2026-03-26 |  |  | 16 | 2026-03-26 | 2026-12-28 | 2026-04-17 | 2026-04-17 | 2027-01-18 | 196
| A45210 | Technical Bid Evaluation (TBE) for Rigid Struts_IFD/IFC |  | 2026-04-17 |  |  | 2 | 2026-04-17 | 2027-01-18 | 2026-04-21 | 2026-04-21 | 2027-01-20 | 196
| 60% 3D Model Review Report |  |  | 2026-02-20 |  |  | 64 | 26-Sep-25 A | 2026-03-19 | 21-Jan-26 A | 2026-02-20 | 2027-01-20
| A44270 | 60% 3D Model Review Report_RCC |  | 2026-02-20 |  |  | 16 | 13-Oct-25 A | 2027-01-20 | 04-Nov-25 A | 2026-02-20 | 2027-01-20
| A44280 | 60% 3D Model Review Report_IFA |  | 2026-02-20 |  |  | 3 | 19-Dec-25 A | 2027-01-20 | 24-Dec-25 A | 2026-02-20 | 2027-01-20
| A44290 | 60% 3D Model Review Report_RCA |  | 2026-02-20 |  |  | 16 | 24-Dec-25 A | 2027-01-20 | 15-Jan-26 A | 2026-02-20 | 2027-01-20
| A44300 | 60% 3D Model Review Report_IFD/IFC |  | 2026-02-20 |  |  | 2 | 19-Jan-26 A | 2027-01-20 | 21-Jan-26 A | 2026-02-20 | 2027-01-20
| 60% 3D Model Review Closeout Report |  |  | 2026-02-20 |  |  | 48 | 2026-02-20 | 2026-07-22 | 2026-04-29 | 2026-04-29 | 2027-01-20 | 191
| A44310 | 60% 3D Model Review Closeout Report_IFR |  | 2026-02-20 |  |  | 11 | 2026-02-20 | 2026-07-22 | 2026-03-09 | 2026-03-09 | 2026-08-06 | 108
| A44320 | 60% 3D Model Review Closeout Report_RCC |  | 2026-03-09 |  |  | 16 | 2026-03-09 | 2026-10-22 | 2026-03-30 | 2026-03-30 | 2026-11-13 | 164
| A44330 | 60% 3D Model Review Closeout Report_IFA |  | 2026-03-31 |  |  | 3 | 2026-03-31 | 2026-11-13 | 2026-04-03 | 2026-04-03 | 2026-11-18 | 164
| A44340 | 60% 3D Model Review Closeout Report_RCA |  | 2026-04-03 |  |  | 16 | 2026-04-03 | 2026-12-28 | 2026-04-27 | 2026-04-27 | 2027-01-18 | 191
| A44350 | 60% 3D Model Review Closeout Report_IFD/IFC |  | 2026-04-27 |  |  | 2 | 2026-04-27 | 2027-01-18 | 2026-04-29 | 2026-04-29 | 2027-01-20 | 191
| Piping Stress Analysis Reports |  |  | 2026-02-20 |  |  | 127 | 06-Jul-25 A | 2026-05-20 | 23-Jan-26 A | 2026-02-20 | 2026-05-20
| A44640 | Piping Stress Analysis Reports_IFR |  | 2026-02-20 |  |  | 23 | 06-Jul-25 A | 2026-05-20 | 31-Jul-25 A | 2026-02-20 | 2026-05-20
| A44650 | Piping Stress Analysis Reports_RCC |  | 2026-02-20 |  |  | 16 | 20-Jul-25 A | 2026-05-20 | 07-Aug-25 A | 2026-02-20 | 2026-05-20
| A44660 | Piping Stress Analysis Reports_IFA |  | 2026-02-20 |  |  | 11 | 19-Dec-25 A | 2026-05-20 | 05-Jan-26 A | 2026-02-20 | 2026-05-20
| A44670 | Piping Stress Analysis Reports_RCA |  | 2026-02-20 |  |  | 16 | 05-Jan-26 A | 2026-05-20 | 14-Jan-26 A | 2026-02-20 | 2026-05-20
| A44680 | Piping Stress Analysis Reports_IFD/IFC |  | 2026-02-20 |  |  | 6 | 15-Jan-26 A | 2026-05-20 | 23-Jan-26 A | 2026-02-20 | 2026-05-20
| Piping GA Drawings & Key Plan for Piping GADs |  |  | 2026-02-20 |  |  | 88 | 01-Dec-25 A | 2026-03-19 | 2026-04-07 | 2026-04-07 | 2027-01-20 | 206
| A44550 | Piping GA Drawings & Key Plan for Piping GADs_RCC |  | 2026-02-20 |  |  | 16 | 01-Dec-25 A | 2026-03-19 | 02-Dec-25 A | 2026-02-20 | 2026-03-19
| A44560 | Piping GA Drawings & Key Plan for Piping GADs_IFA |  | 2026-02-20 |  |  | 11 | 2026-02-20 | 2026-12-07 | 2026-03-09 | 2026-03-09 | 2026-12-22 | 206
| A44570 | Piping GA Drawings & Key Plan for Piping GADs_RCA |  | 2026-03-09 |  |  | 16 | 2026-03-09 | 2026-12-22 | 2026-03-30 | 2026-03-30 | 2027-01-13 | 206
| A44580 | Piping GA Drawings & Key Plan for Piping GADs_IFD/IFC |  | 2026-03-31 |  |  | 6 | 2026-03-31 | 2027-01-13 | 2026-04-07 | 2026-04-07 | 2027-01-20 | 206
| Piping Isometrics (large bore) |  |  | 2026-02-20 |  |  | 94 | 14-Jan-26 A | 2026-03-13 | 2026-06-04 | 2026-06-04 | 2026-08-28 | 62
| A44370 | Piping Isometrics (large bore)_RCC |  | 2026-03-30 |  |  | 16 | 2026-03-30 | 2026-06-23 | 2026-04-20 | 2026-04-20 | 2026-07-15 | 62
| A44380 | Piping Isometrics (large bore)_IFA |  | 2026-04-20 |  |  | 11 | 2026-04-20 | 2026-07-15 | 2026-05-05 | 2026-05-05 | 2026-07-30 | 62
| A44390 | Piping Isometrics (large bore)_RCA |  | 2026-05-06 |  |  | 16 | 2026-05-06 | 2026-07-30 | 2026-05-27 | 2026-05-27 | 2026-08-21 | 62
| A44400 | Piping Isometrics (large bore)_IFD/IFC |  | 2026-05-27 |  |  | 6 | 2026-05-27 | 2026-08-21 | 2026-06-04 | 2026-06-04 | 2026-08-28 | 62
| Second Material Take Off |  |  | 2026-02-20 |  |  | 24 | 23-Dec-25 A | 2026-03-25 | 2026-02-24 | 2026-02-24 | 2026-03-27 | 23
| A45310 | Second Material Take Off_RCC |  | 2026-02-20 |  |  | 16 | 16-Jan-26 A | 2026-03-25 | 23-Jan-26 A | 2026-02-20 | 2026-03-25
| A45320 | Second Material Take Off_IFD/IFC |  | 2026-02-20 |  |  | 2 | 23-Jan-26 A | 2026-03-25 | 2026-02-24 | 2026-02-24 | 2026-03-27 | 23
| 90% 3D Model Review Report |  |  | 2026-03-06 |  |  | 67 | 2026-03-06 | 2026-11-12 | 2026-06-08 | 2026-06-08 | 2027-01-20 | 162
| A44420 | 90% 3D Model Review Report_RCC |  | 2026-03-13 |  |  | 16 | 2026-03-13 | 2026-11-30 | 2026-04-06 | 2026-04-06 | 2026-12-22 | 186
| A44430 | 90% 3D Model Review Report_IFA |  | 2026-04-06 |  |  | 3 | 2026-04-06 | 2026-12-22 | 2026-04-09 | 2026-04-09 | 2026-12-25 | 186
| A44440 | 90% 3D Model Review Report_RCA |  | 2026-04-09 |  |  | 16 | 2026-04-09 | 2026-12-28 | 2026-05-01 | 2026-05-01 | 2027-01-18 | 186
| A44450 | 90% 3D Model Review Report_IFD/IFC |  | 2026-06-04 |  |  | 2 | 2026-06-04 | 2027-01-18 | 2026-06-08 | 2026-06-08 | 2027-01-20 | 162
| Piping Isometrics(Small Bore) |  |  | 2026-03-06 |  |  | 41 | 2026-03-06 | 2026-03-27 | 2026-05-01 | 2026-05-01 | 2026-05-22 | 15
| A44520 | Piping Isometrics(Small Bore)_RCC |  | 2026-04-07 |  |  | 16 | 2026-04-07 | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-05-20 | 15
| A44530 | Piping Isometrics(Small Bore)_IFD/IFC |  | 2026-04-29 |  |  | 2 | 2026-04-29 | 2026-05-20 | 2026-05-01 | 2026-05-01 | 2026-05-22 | 15
| Piping Tie-Ins Schedule |  |  | 2026-02-20 |  |  | 43 | 2026-02-20 | 2026-08-19 | 2026-04-21 | 2026-04-21 | 2026-10-16 | 128
| A44600 | Piping Tie-Ins Schedule_RCC |  | 2026-02-27 |  |  | 16 | 2026-02-27 | 2026-08-26 | 2026-03-23 | 2026-03-23 | 2026-09-17 | 128
| A44610 | Piping Tie-Ins Schedule_IFA |  | 2026-03-23 |  |  | 3 | 2026-03-23 | 2026-09-17 | 2026-03-26 | 2026-03-26 | 2026-09-22 | 128
| A44620 | Piping Tie-Ins Schedule_RCA |  | 2026-03-26 |  |  | 16 | 2026-03-26 | 2026-09-23 | 2026-04-17 | 2026-04-17 | 2026-10-14 | 128
| A44630 | Piping Tie-Ins Schedule_IFD/IFC |  | 2026-04-17 |  |  | 2 | 2026-04-17 | 2026-10-14 | 2026-04-21 | 2026-04-21 | 2026-10-16 | 128
| 90% 3D Model Review Closeout Report |  |  | 2026-03-13 |  |  | 43 | 2026-03-13 | 2026-11-20 | 2026-05-13 | 2026-05-13 | 2027-01-20 | 181
| A44470 | 90% 3D Model Review Closeout Report_RCC |  | 2026-03-23 |  |  | 16 | 2026-03-23 | 2026-11-30 | 2026-04-14 | 2026-04-14 | 2026-12-22 | 181
| A44480 | 90% 3D Model Review Closeout Report_IFA |  | 2026-04-14 |  |  | 3 | 2026-04-14 | 2026-12-22 | 2026-04-17 | 2026-04-17 | 2026-12-25 | 181
| A44490 | 90% 3D Model Review Closeout Report_RCA |  | 2026-04-17 |  |  | 16 | 2026-04-17 | 2026-12-28 | 2026-05-11 | 2026-05-11 | 2027-01-18 | 181
| A44500 | 90% 3D Model Review Closeout Report_IFD/IFC |  | 2026-05-11 |  |  | 2 | 2026-05-11 | 2027-01-18 | 2026-05-13 | 2026-05-13 | 2027-01-20 | 181
| Final Material Take Off |  |  | 2026-03-06 |  |  | 24 | 2026-03-06 | 2026-03-27 | 2026-04-08 | 2026-04-08 | 2026-05-04 | 18
| A45340 | Final Material Take Off_RCC |  | 2026-03-13 |  |  | 16 | 2026-03-13 | 2026-04-09 | 2026-04-06 | 2026-04-06 | 2026-04-30 | 18
| A45350 | Final Material Take Off_IFD/IFC |  | 2026-04-06 |  |  | 2 | 2026-04-06 | 2026-04-30 | 2026-04-08 | 2026-04-08 | 2026-05-04 | 18
| Mechanical Static |  |  | 2026-02-20 |  |  | 346 | 31-Dec-24 A | 2026-03-02 | 2026-04-14 | 2026-04-14 | 2027-01-20 | 202
| Mechanical Datasheet For Psa2 Feed Gas Compressor 1St Stage Suction Drum (Tag No. 13-Vv-705) |  |  | 2026-02-20 |  |  | 132 | 31-Dec-24 A | 2026-03-02 | 10-May-25 A | 2026-02-20 | 2027-01-20
| A54600 | Mechanical Datasheet For Psa2 Feed Gas Compressor 1St Stage Suction Drum (Tag No. 13-Vv-705)_RCC |  | 2026-02-20 |  |  | 16 | 07-Feb-25 A | 2027-01-20 | 19-Apr-25 A | 2026-02-20 | 2027-01-20
| A54610 | Mechanical Datasheet For Psa2 Feed Gas Compressor 1St Stage Suction Drum (Tag No. 13-Vv-705)_IFA |  | 2026-02-20 |  |  | 3 | 20-Apr-25 A | 2027-01-20 | 26-Apr-25 A | 2026-02-20 | 2027-01-20
| A54620 | Mechanical Datasheet For Psa2 Feed Gas Compressor 1St Stage Suction Drum (Tag No. 13-Vv-705)_RCA |  | 2026-02-20 |  |  | 16 | 27-Apr-25 A | 2027-01-20 | 03-May-25 A | 2026-02-20 | 2027-01-20
| A54630 | Mechanical Datasheet For Psa2 Feed Gas Compressor 1St Stage Suction Drum (Tag No. 13-Vv-705)_IFD/IFC |  | 2026-02-20 |  |  | 2 | 04-May-25 A | 2027-01-20 | 10-May-25 A | 2026-02-20 | 2027-01-20
| Mechanical Datasheet For Psa2 Feed Gas Compressor 2Nd Stage Suction Drum (Tag No. 13-Vv-706) |  |  | 2026-02-20 |  |  | 131 | 31-Dec-24 A | 2026-03-02 | 10-May-25 A | 2026-02-20 | 2027-01-20
| A54650 | Mechanical Datasheet For Psa2 Feed Gas Compressor 2Nd Stage Suction Drum (Tag No. 13-Vv-706)_RCC |  | 2026-02-20 |  |  | 16 | 07-Feb-25 A | 2027-01-20 | 19-Apr-25 A | 2026-02-20 | 2027-01-20
| A54660 | Mechanical Datasheet For Psa2 Feed Gas Compressor 2Nd Stage Suction Drum (Tag No. 13-Vv-706)_IFA |  | 2026-02-20 |  |  | 3 | 20-Apr-25 A | 2027-01-20 | 26-Apr-25 A | 2026-02-20 | 2027-01-20
| A54670 | Mechanical Datasheet For Psa2 Feed Gas Compressor 2Nd Stage Suction Drum (Tag No. 13-Vv-706)_RCA |  | 2026-02-20 |  |  | 16 | 27-Apr-25 A | 2027-01-20 | 03-May-25 A | 2026-02-20 | 2027-01-20
| A54680 | Mechanical Datasheet For Psa2 Feed Gas Compressor 2Nd Stage Suction Drum (Tag No. 13-Vv-706)_IFD/IFC |  | 2026-02-20 |  |  | 2 | 04-May-25 A | 2027-01-20 | 10-May-25 A | 2026-02-20 | 2027-01-20
| Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Suction Drum (Tag No. 13-Vv-707) |  |  | 2026-02-20 |  |  | 130 | 31-Dec-24 A | 2026-03-02 | 10-May-25 A | 2026-02-20 | 2027-01-20
| A54700 | Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Suction Drum (Tag No. 13-Vv-707)_RCC |  | 2026-02-20 |  |  | 16 | 07-Feb-25 A | 2027-01-20 | 19-Apr-25 A | 2026-02-20 | 2027-01-20
| A54710 | Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Suction Drum (Tag No. 13-Vv-707)_IFA |  | 2026-02-20 |  |  | 3 | 20-Apr-25 A | 2027-01-20 | 26-Apr-25 A | 2026-02-20 | 2027-01-20
| A54720 | Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Suction Drum (Tag No. 13-Vv-707)_RCA |  | 2026-02-20 |  |  | 16 | 27-Apr-25 A | 2027-01-20 | 03-May-25 A | 2026-02-20 | 2027-01-20
| A54730 | Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Suction Drum (Tag No. 13-Vv-707)_IFD/IFC |  | 2026-02-20 |  |  | 2 | 04-May-25 A | 2027-01-20 | 10-May-25 A | 2026-02-20 | 2027-01-20
| Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Discharge Drum (Tag No. 13-Vv-Xxx) |  |  | 2026-02-20 |  |  | 148 | 31-Dec-24 A | 2026-03-02 | 05-Jul-25 A | 2026-02-20 | 2027-01-20
| A54740 | Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Discharge Drum (Tag No. 13-Vv-Xxx)_IFR |  | 2026-02-20 |  |  | 1 | 31-Dec-24 A | 2026-03-02 | 24-Jan-25 A | 2026-02-20 | 2026-03-02
| A54750 | Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Discharge Drum (Tag No. 13-Vv-Xxx)_RCC |  | 2026-02-20 |  |  | 16 | 25-Jan-25 A | 2027-01-20 | 19-Apr-25 A | 2026-02-20 | 2027-01-20
| A54760 | Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Discharge Drum (Tag No. 13-Vv-Xxx)_IFA |  | 2026-02-20 |  |  | 3 | 20-Apr-25 A | 2027-01-20 | 21-Jun-25 A | 2026-02-20 | 2027-01-20
| A54770 | Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Discharge Drum (Tag No. 13-Vv-Xxx)_RCA |  | 2026-02-20 |  |  | 16 | 22-Jun-25 A | 2027-01-20 | 28-Jun-25 A | 2026-02-20 | 2027-01-20
| A54780 | Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Discharge Drum (Tag No. 13-Vv-Xxx)_IFD/IFC |  | 2026-02-20 |  |  | 2 | 29-Jun-25 A | 2027-01-20 | 05-Jul-25 A | 2026-02-20 | 2027-01-20
| Mechanical Datasheet For Psa2 Off Gas Buffer Drum (Tag No. 13-Vv-712) |  |  | 2026-02-20 |  |  | 128 | 31-Dec-24 A | 2026-03-02 | 10-May-25 A | 2026-02-20 | 2027-01-20
| A54800 | Mechanical Datasheet For Psa2 Off Gas Buffer Drum (Tag No. 13-Vv-712)_RCC |  | 2026-02-20 |  |  | 16 | 07-Feb-25 A | 2027-01-20 | 19-Apr-25 A | 2026-02-20 | 2027-01-20
| A54810 | Mechanical Datasheet For Psa2 Off Gas Buffer Drum (Tag No. 13-Vv-712)_IFA |  | 2026-02-20 |  |  | 3 | 20-Apr-25 A | 2027-01-20 | 26-Apr-25 A | 2026-02-20 | 2027-01-20
| A54820 | Mechanical Datasheet For Psa2 Off Gas Buffer Drum (Tag No. 13-Vv-712)_RCA |  | 2026-02-20 |  |  | 16 | 27-Apr-25 A | 2027-01-20 | 03-May-25 A | 2026-02-20 | 2027-01-20
| A54830 | Mechanical Datasheet For Psa2 Off Gas Buffer Drum (Tag No. 13-Vv-712)_IFD/IFC |  | 2026-02-20 |  |  | 2 | 04-May-25 A | 2027-01-20 | 10-May-25 A | 2026-02-20 | 2027-01-20
| Mechanical Datasheet For Psa2 Off Gas Compressor 2Nd Stage Suction Drum (Tag No. 13-Vv-713) |  |  | 2026-02-20 |  |  | 127 | 31-Dec-24 A | 2026-03-02 | 10-May-25 A | 2026-02-20 | 2027-01-20
| A54850 | Mechanical Datasheet For Psa2 Off Gas Compressor 2Nd Stage Suction Drum (Tag No. 13-Vv-713)_RCC |  | 2026-02-20 |  |  | 16 | 07-Feb-25 A | 2027-01-20 | 19-Apr-25 A | 2026-02-20 | 2027-01-20
| A54860 | Mechanical Datasheet For Psa2 Off Gas Compressor 2Nd Stage Suction Drum (Tag No. 13-Vv-713)_IFA |  | 2026-02-20 |  |  | 3 | 20-Apr-25 A | 2027-01-20 | 26-Apr-25 A | 2026-02-20 | 2027-01-20
| A54870 | Mechanical Datasheet For Psa2 Off Gas Compressor 2Nd Stage Suction Drum (Tag No. 13-Vv-713)_RCA |  | 2026-02-20 |  |  | 16 | 27-Apr-25 A | 2027-01-20 | 03-May-25 A | 2026-02-20 | 2027-01-20
| A54880 | Mechanical Datasheet For Psa2 Off Gas Compressor 2Nd Stage Suction Drum (Tag No. 13-Vv-713)_IFD/IFC |  | 2026-02-20 |  |  | 2 | 04-May-25 A | 2027-01-20 | 10-May-25 A | 2026-02-20 | 2027-01-20
| Mechanical Datasheet For Psa2 Slop Drum (Tag No. 70-Vv-1415) |  |  | 2026-02-20 |  |  | 126 | 01-Jan-25 A | 2026-03-02 | 10-May-25 A | 2026-02-20 | 2027-01-20
| A27220 | Mechanical Datasheet For Psa2 Slop Drum (Tag No. 70-Vv-1415)_RCC |  | 2026-02-20 |  |  | 16 | 07-Feb-25 A | 2027-01-20 | 19-Apr-25 A | 2026-02-20 | 2027-01-20
| A27230 | Mechanical Datasheet For Psa2 Slop Drum (Tag No. 70-Vv-1415)_IFA |  | 2026-02-20 |  |  | 3 | 20-Apr-25 A | 2027-01-20 | 26-Apr-25 A | 2026-02-20 | 2027-01-20
| A54890 | Mechanical Datasheet For Psa2 Slop Drum (Tag No. 70-Vv-1415)_RCA |  | 2026-02-20 |  |  | 16 | 27-Apr-25 A | 2027-01-20 | 03-May-25 A | 2026-02-20 | 2027-01-20
| A54900 | Mechanical Datasheet For Psa2 Slop Drum (Tag No. 70-Vv-1415)_IFD/IFC |  | 2026-02-20 |  |  | 2 | 04-May-25 A | 2027-01-20 | 10-May-25 A | 2026-02-20 | 2027-01-20
| Mechanical Datasheet For Psa2 Feed Gas Compressor 1St Stage Cooler (Tag No. 13-He-703) |  |  | 2026-02-20 |  |  | 125 | 07-Jan-25 A | 2026-03-02 | 10-May-25 A | 2026-02-20 | 2026-03-02
| A54910 | Mechanical Datasheet For Psa2 Feed Gas Compressor 1St Stage Cooler (Tag No. 13-He-703)_IFR |  | 2026-02-20 |  |  | 1 | 07-Jan-25 A | 2026-03-02 | 06-Feb-25 A | 2026-02-20 | 2026-03-02
| A54920 | Mechanical Datasheet For Psa2 Feed Gas Compressor 1St Stage Cooler (Tag No. 13-He-703)_RCC |  | 2026-02-20 |  |  | 16 | 07-Feb-25 A | 2026-03-02 | 19-Apr-25 A | 2026-02-20 | 2026-03-02
| A54930 | Mechanical Datasheet For Psa2 Feed Gas Compressor 1St Stage Cooler (Tag No. 13-He-703)_IFA |  | 2026-02-20 |  |  | 3 | 20-Apr-25 A | 2026-03-02 | 26-Apr-25 A | 2026-02-20 | 2026-03-02
| A54940 | Mechanical Datasheet For Psa2 Feed Gas Compressor 1St Stage Cooler (Tag No. 13-He-703)_RCA |  | 2026-02-20 |  |  | 16 | 27-Apr-25 A | 2026-03-02 | 03-May-25 A | 2026-02-20 | 2026-03-02
| A54950 | Mechanical Datasheet For Psa2 Feed Gas Compressor 1St Stage Cooler (Tag No. 13-He-703)_IFD/IFC |  | 2026-02-20 |  |  | 2 | 04-May-25 A | 2026-03-02 | 10-May-25 A | 2026-02-20 | 2026-03-02
| Mechanical Datasheet For Psa2 Feed Gas Compressor 2Nd Stage Cooler (Tag No. 13-He-704) |  |  | 2026-02-20 |  |  | 104 | 14-Feb-25 A | 2026-03-02 | 03-May-25 A | 2026-02-20 | 2026-03-02
| A54960 | Mechanical Datasheet For Psa2 Feed Gas Compressor 2Nd Stage Cooler (Tag No. 13-He-704)_IFR |  | 2026-02-20 |  |  | 1 | 14-Feb-25 A | 2026-03-02 | 07-Mar-25 A | 2026-02-20 | 2026-03-02
| A54970 | Mechanical Datasheet For Psa2 Feed Gas Compressor 2Nd Stage Cooler (Tag No. 13-He-704)_RCC |  | 2026-02-20 |  |  | 16 | 08-Mar-25 A | 2026-03-02 | 14-Mar-25 A | 2026-02-20 | 2026-03-02
| A54980 | Mechanical Datasheet For Psa2 Feed Gas Compressor 2Nd Stage Cooler (Tag No. 13-He-704)_IFA |  | 2026-02-20 |  |  | 3 | 15-Mar-25 A | 2026-03-02 | 21-Mar-25 A | 2026-02-20 | 2026-03-02
| A54990 | Mechanical Datasheet For Psa2 Feed Gas Compressor 2Nd Stage Cooler (Tag No. 13-He-704)_RCA |  | 2026-02-20 |  |  | 16 | 22-Mar-25 A | 2026-03-02 | 30-Apr-25 A | 2026-02-20 | 2026-03-02
| A55000 | Mechanical Datasheet For Psa2 Feed Gas Compressor 2Nd Stage Cooler (Tag No. 13-He-704)_IFD/IFC |  | 2026-02-20 |  |  | 2 | 01-May-25 A | 2026-03-02 | 03-May-25 A | 2026-02-20 | 2026-03-02
| Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Cooler (Tag No. 13-He-703) |  |  | 2026-02-20 |  |  | 142 | 20-Jan-25 A | 2026-03-02 | 14-Jun-25 A | 2026-02-20 | 2026-03-02
| A55020 | Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Cooler (Tag No. 13-He-703)_RCC |  | 2026-02-20 |  |  | 16 | 27-Feb-25 A | 2026-03-02 | 19-Apr-25 A | 2026-02-20 | 2026-03-02
| A55030 | Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Cooler (Tag No. 13-He-703)_IFA |  | 2026-02-20 |  |  | 3 | 20-Apr-25 A | 2026-03-02 | 26-Apr-25 A | 2026-02-20 | 2026-03-02
| A55040 | Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Cooler (Tag No. 13-He-703)_RCA |  | 2026-02-20 |  |  | 16 | 08-Jun-25 A | 2026-03-02 | 10-Jun-25 A | 2026-02-20 | 2026-03-02
| A55050 | Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Cooler (Tag No. 13-He-703)_IFD/IFC |  | 2026-02-20 |  |  | 2 | 11-Jun-25 A | 2026-03-02 | 14-Jun-25 A | 2026-02-20 | 2026-03-02
| Mechanical Datasheet For Psa2 Off Gas Compressor Interstage Cooler(Tag No. 13-He-708) |  |  | 2026-02-20 |  |  | 119 | 25-Feb-25 A | 2026-03-02 | 09-May-25 A | 2026-02-20 | 2026-03-02
| A55060 | Mechanical Datasheet For Psa2 Off Gas Compressor Interstage Cooler(Tag No. 13-He-708)_IFR |  | 2026-02-20 |  |  | 1 | 25-Feb-25 A | 2026-03-02 | 26-Feb-25 A | 2026-02-20 | 2026-03-02
| A55070 | Mechanical Datasheet For Psa2 Off Gas Compressor Interstage Cooler(Tag No. 13-He-708)_RCC |  | 2026-02-20 |  |  | 16 | 27-Feb-25 A | 2026-03-02 | 04-Mar-25 A | 2026-02-20 | 2026-03-02
| A27430 | Mechanical Datasheet For Psa2 Off Gas Compressor Interstage Cooler(Tag No. 13-He-708)_IFA |  | 2026-02-20 |  |  | 3 | 05-Mar-25 A | 2026-03-02 | 25-Apr-25 A | 2026-02-20 | 2026-03-02
| A55080 | Mechanical Datasheet For Psa2 Off Gas Compressor Interstage Cooler(Tag No. 13-He-708)_RCA |  | 2026-02-20 |  |  | 16 | 26-Apr-25 A | 2026-03-02 | 02-May-25 A | 2026-02-20 | 2026-03-02
| A55090 | Mechanical Datasheet For Psa2 Off Gas Compressor Interstage Cooler(Tag No. 13-He-708)_IFD/IFC |  | 2026-02-20 |  |  | 2 | 03-May-25 A | 2026-03-02 | 09-May-25 A | 2026-02-20 | 2026-03-02
| Mechanical Datasheet For Psa2 Off Gas Compressor Aftercooler(Tag No. 13-He-709) |  |  | 2026-02-20 |  |  | 104 | 25-Feb-25 A | 2026-03-02 | 09-May-25 A | 2026-02-20 | 2026-03-02
| A55110 | Mechanical Datasheet For Psa2 Off Gas Compressor Aftercooler(Tag No. 13-He-709)_RCC |  | 2026-02-20 |  |  | 16 | 27-Feb-25 A | 2026-03-02 | 04-Mar-25 A | 2026-02-20 | 2026-03-02
| A55120 | Mechanical Datasheet For Psa2 Off Gas Compressor Aftercooler(Tag No. 13-He-709)_IFA |  | 2026-02-20 |  |  | 3 | 05-Mar-25 A | 2026-03-02 | 25-Apr-25 A | 2026-02-20 | 2026-03-02
| A55130 | Mechanical Datasheet For Psa2 Off Gas Compressor Aftercooler(Tag No. 13-He-709)_RCA |  | 2026-02-20 |  |  | 16 | 26-Apr-25 A | 2026-03-02 | 02-May-25 A | 2026-02-20 | 2026-03-02
| A55140 | Mechanical Datasheet For Psa2 Off Gas Compressor Aftercooler(Tag No. 13-He-709)_IFD/IFC |  | 2026-02-20 |  |  | 2 | 03-May-25 A | 2026-03-02 | 09-May-25 A | 2026-02-20 | 2026-03-02
| Mechanical Datasheet For Psa2 Off Gas Compressor Discharge Dripleg -13-Sp-7004 |  |  | 2026-02-20 |  |  | 119 | 01-Jan-25 A | 2026-03-02 | 10-May-25 A | 2026-02-20 | 2027-01-20
| A27520 | Mechanical Datasheet For Psa2 Off Gas Compressor Discharge Dripleg -13-Sp-7004_RCC |  | 2026-02-20 |  |  | 16 | 25-Jan-25 A | 2027-01-20 | 19-Apr-25 A | 2026-02-20 | 2027-01-20
| A55150 | Mechanical Datasheet For Psa2 Off Gas Compressor Discharge Dripleg -13-Sp-7004_IFA |  | 2026-02-20 |  |  | 3 | 20-Apr-25 A | 2027-01-20 | 26-Apr-25 A | 2026-02-20 | 2027-01-20
| A55160 | Mechanical Datasheet For Psa2 Off Gas Compressor Discharge Dripleg -13-Sp-7004_RCA |  | 2026-02-20 |  |  | 16 | 27-Apr-25 A | 2027-01-20 | 03-May-25 A | 2026-02-20 | 2027-01-20
| A55170 | Mechanical Datasheet For Psa2 Off Gas Compressor Discharge Dripleg -13-Sp-7004_IFD/IFC |  | 2026-02-20 |  |  | 2 | 04-May-25 A | 2027-01-20 | 10-May-25 A | 2026-02-20 | 2027-01-20
| Mechanical Datasheet For C4 Guard Adsorber Regeneration Gas Cooler(Tag No. 50-He-1410) |  |  | 2026-02-20 |  |  | 118 | 27-Feb-25 A | 2026-03-02 | 10-May-25 A | 2026-02-20 | 2026-03-02
| A55190 | Mechanical Datasheet For C4 Guard Adsorber Regeneration Gas Cooler(Tag No. 50-He-1410)_RCC |  | 2026-02-20 |  |  | 16 | 21-Mar-25 A | 2026-03-02 | 19-Apr-25 A | 2026-02-20 | 2026-03-02
| A55200 | Mechanical Datasheet For C4 Guard Adsorber Regeneration Gas Cooler(Tag No. 50-He-1410)_IFA |  | 2026-02-20 |  |  | 3 | 20-Apr-25 A | 2026-03-02 | 26-Apr-25 A | 2026-02-20 | 2026-03-02
| A55210 | Mechanical Datasheet For C4 Guard Adsorber Regeneration Gas Cooler(Tag No. 50-He-1410)_RCA |  | 2026-02-20 |  |  | 16 | 27-Apr-25 A | 2026-03-02 | 03-May-25 A | 2026-02-20 | 2026-03-02
| A55220 | Mechanical Datasheet For C4 Guard Adsorber Regeneration Gas Cooler(Tag No. 50-He-1410)_IFD/IFC |  | 2026-02-20 |  |  | 2 | 04-May-25 A | 2026-03-02 | 10-May-25 A | 2026-02-20 | 2026-03-02
| Mechanical Datasheet For Vhp Boiler Feed Water Preheater Dripleg |  |  | 2026-02-20 |  |  | 212 | 01-Jul-25 A | 2026-03-02 | 2026-04-14 | 2026-04-14 | 2027-01-20 | 202
| A55230 | Mechanical Datasheet For Vhp Boiler Feed Water Preheater Dripleg_RCC |  | 2026-02-20 |  |  | 16 | 2026-02-20 | 2026-11-30 | 2026-03-13 | 2026-03-13 | 2026-12-22 | 202
| A55240 | Mechanical Datasheet For Vhp Boiler Feed Water Preheater Dripleg_IFA |  | 2026-03-13 |  |  | 3 | 2026-03-13 | 2026-12-22 | 2026-03-19 | 2026-03-19 | 2026-12-25 | 202
| A55250 | Mechanical Datasheet For Vhp Boiler Feed Water Preheater Dripleg_RCA |  | 2026-03-19 |  |  | 16 | 2026-03-19 | 2026-12-28 | 2026-04-09 | 2026-04-09 | 2027-01-18 | 202
| A55260 | Mechanical Datasheet For Vhp Boiler Feed Water Preheater Dripleg_IFD/IFC |  | 2026-04-09 |  |  | 2 | 2026-04-09 | 2027-01-18 | 2026-04-14 | 2026-04-14 | 2027-01-20 | 202
| Mechanical Datasheet For Off-Gas Compressor Coalescer |  |  | 2026-02-20 |  |  | 34 | 13-Jan-25 A | 2026-03-02 | 03-Mar-25 A | 2026-02-20 | 2026-03-02
| A55270 | Mechanical Datasheet For Off-Gas Compressor Coalescer_IFR |  | 2026-02-20 |  |  | 1 | 13-Jan-25 A | 2026-03-02 | 03-Feb-25 A | 2026-02-20 | 2026-03-02
| A55280 | Mechanical Datasheet For Off-Gas Compressor Coalescer_RCC |  | 2026-02-20 |  |  | 16 | 04-Feb-25 A | 2026-03-02 | 10-Feb-25 A | 2026-02-20 | 2026-03-02
| A55290 | Mechanical Datasheet For Off-Gas Compressor Coalescer_IFA |  | 2026-02-20 |  |  | 3 | 11-Feb-25 A | 2026-03-02 | 17-Feb-25 A | 2026-02-20 | 2026-03-02
| A55300 | Mechanical Datasheet For Off-Gas Compressor Coalescer_RCA |  | 2026-02-20 |  |  | 16 | 18-Feb-25 A | 2026-03-02 | 24-Feb-25 A | 2026-02-20 | 2026-03-02
| A27700 | Mechanical Datasheet For Off-Gas Compressor Coalescer_IFD/IFC |  | 2026-02-20 |  |  | 2 | 25-Feb-25 A | 2026-03-02 | 03-Mar-25 A | 2026-02-20 | 2026-03-02
| Mechanical Datasheet For Guard Adsorber Regeneration Gas Coalescer |  |  | 2026-02-20 |  |  | 116 | 06-Jan-25 A | 2026-03-02 | 10-May-25 A | 2026-02-20 | 2026-03-02
| A55310 | Mechanical Datasheet For Guard Adsorber Regeneration Gas Coalescer_IFR |  | 2026-02-20 |  |  | 1 | 06-Jan-25 A | 2026-03-02 | 14-Mar-25 A | 2026-02-20 | 2026-03-02
| A55320 | Mechanical Datasheet For Guard Adsorber Regeneration Gas Coalescer_RCC |  | 2026-02-20 |  |  | 16 | 15-Mar-25 A | 2026-03-02 | 19-Apr-25 A | 2026-02-20 | 2026-03-02
| A55330 | Mechanical Datasheet For Guard Adsorber Regeneration Gas Coalescer_IFA |  | 2026-02-20 |  |  | 3 | 20-Apr-25 A | 2026-03-02 | 26-Apr-25 A | 2026-02-20 | 2026-03-02
| A55340 | Mechanical Datasheet For Guard Adsorber Regeneration Gas Coalescer_RCA |  | 2026-02-20 |  |  | 16 | 27-Apr-25 A | 2026-03-02 | 03-May-25 A | 2026-02-20 | 2026-03-02
| A55350 | Mechanical Datasheet For Guard Adsorber Regeneration Gas Coalescer_IFD/IFC |  | 2026-02-20 |  |  | 2 | 04-May-25 A | 2026-03-02 | 10-May-25 A | 2026-02-20 | 2026-03-02
| Mechanical Datasheet For Tail Gas Silencer |  |  | 2026-02-20 |  |  | 211 | 01-Jul-25 A | 2026-11-30 | 2026-04-14 | 2026-04-14 | 2027-01-20 | 202
| A55370 | Mechanical Datasheet For Tail Gas Silencer_RCC |  | 2026-02-20 |  |  | 16 | 2026-02-20 | 2026-11-30 | 2026-03-13 | 2026-03-13 | 2026-12-22 | 202
| A55380 | Mechanical Datasheet For Tail Gas Silencer_IFA |  | 2026-03-13 |  |  | 3 | 2026-03-13 | 2026-12-22 | 2026-03-19 | 2026-03-19 | 2026-12-25 | 202
| A27790 | Mechanical Datasheet For Tail Gas Silencer_RCA |  | 2026-03-19 |  |  | 16 | 2026-03-19 | 2026-12-28 | 2026-04-09 | 2026-04-09 | 2027-01-18 | 202
| A55390 | Mechanical Datasheet For Tail Gas Silencer_IFD/IFC |  | 2026-04-09 |  |  | 2 | 2026-04-09 | 2027-01-18 | 2026-04-14 | 2026-04-14 | 2027-01-20 | 202
| Material Requisiton for Coalscer |  |  | 2026-02-20 |  |  | 118 | 28-Feb-25 A | 2026-03-02 | 14-May-25 A | 2026-02-20 | 2026-03-02
| A45420 | Material Requisiton for Coalscer_RCC |  | 2026-02-20 |  |  | 16 | 22-Mar-25 A | 2026-03-02 | 21-Apr-25 A | 2026-02-20 | 2026-03-02
| A45430 | Material Requisiton for Coalscer_IFA |  | 2026-02-20 |  |  | 3 | 22-Apr-25 A | 2026-03-02 | 30-Apr-25 A | 2026-02-20 | 2026-03-02
| A45440 | Material Requisiton for Coalscer_RCA |  | 2026-02-20 |  |  | 16 | 01-May-25 A | 2026-03-02 | 07-May-25 A | 2026-02-20 | 2026-03-02
| A45450 | Material Requisiton for Coalscer_IFD/IFC |  | 2026-02-20 |  |  | 2 | 08-May-25 A | 2026-03-02 | 14-May-25 A | 2026-02-20 | 2026-03-02
| Material Requisiton for Shell and Tube Heat Exchangers |  |  | 2026-02-20 |  |  | 153 | 21-Feb-25 A | 2026-03-02 | 20-Jun-25 A | 2026-02-20 | 2026-03-02
| A45370 | Material Requisiton for Heat Exchangers_RCC |  | 2026-02-20 |  |  | 16 | 01-Jun-25 A | 2026-03-02 | 05-Jun-25 A | 2026-02-20 | 2026-03-02
| A45380 | Material Requisiton for Heat Exchangers_IFA |  | 2026-02-20 |  |  | 3 | 06-Jun-25 A | 2026-03-02 | 10-Jun-25 A | 2026-02-20 | 2026-03-02
| A45390 | Material Requisiton for Heat Exchangers_RCA |  | 2026-02-20 |  |  | 16 | 11-Jun-25 A | 2026-03-02 | 15-Jun-25 A | 2026-02-20 | 2026-03-02
| A45400 | Material Requisiton for Heat Exchangers_IFD/IFC |  | 2026-02-20 |  |  | 2 | 16-Jun-25 A | 2026-03-02 | 20-Jun-25 A | 2026-02-20 | 2026-03-02
| Material Requisiton for Pressure Vessels & Internals |  |  | 2026-02-20 |  |  | 122 | 17-Jan-25 A | 2026-03-02 | 09-May-25 A | 2026-02-20 | 2026-03-02
| A45920 | Material Requisiton for Pressure Vessels & Internals_RCC |  | 2026-02-20 |  |  | 16 | 08-Feb-25 A | 2026-03-02 | 14-Feb-25 A | 2026-02-20 | 2026-03-02
| A45930 | Material Requisiton for Pressure Vessels & Internals_IFA |  | 2026-02-20 |  |  | 3 | 15-Feb-25 A | 2026-03-02 | 25-Apr-25 A | 2026-02-20 | 2026-03-02
| A45940 | Material Requisiton for Pressure Vessels & Internals_RCA |  | 2026-02-20 |  |  | 16 | 26-Apr-25 A | 2026-03-02 | 02-May-25 A | 2026-02-20 | 2026-03-02
| A45950 | Material Requisiton for Pressure Vessels & Internals_IFD/IFC |  | 2026-02-20 |  |  | 2 | 03-May-25 A | 2026-03-02 | 09-May-25 A | 2026-02-20 | 2026-03-02
| Mechanical Rotating |  |  | 2026-02-20 |  |  | 151 | 04-Jan-25 A | 2026-03-02 | 28-Jun-25 A | 2026-02-20 | 2026-03-02
| Mechanical Datasheet For Sanitary Water Collection Pump |  |  | 2026-02-20 |  |  | 132 | 05-Feb-25 A | 2026-03-02 | 10-May-25 A | 2026-02-20 | 2026-03-02
| A54540 | Mechanical Datasheet For Sanitary Water Collection Pump_IFR |  | 2026-02-20 |  |  | 2 | 05-Feb-25 A | 2026-03-02 | 26-Feb-25 A | 2026-02-20 | 2026-03-02
| A54550 | Mechanical Datasheet For Sanitary Water Collection Pump_RCC |  | 2026-02-20 |  |  | 16 | 27-Feb-25 A | 2026-03-02 | 19-Apr-25 A | 2026-02-20 | 2026-03-02
| A54560 | Mechanical Datasheet For Sanitary Water Collection Pump_IFA |  | 2026-02-20 |  |  | 3 | 20-Apr-25 A | 2026-03-02 | 26-Apr-25 A | 2026-02-20 | 2026-03-02
| A54570 | Mechanical Datasheet For Sanitary Water Collection Pump_RCA |  | 2026-02-20 |  |  | 16 | 27-Apr-25 A | 2026-03-02 | 03-May-25 A | 2026-02-20 | 2026-03-02
| A54580 | Mechanical Datasheet For Sanitary Water Collection Pump_IFD/IFC |  | 2026-02-20 |  |  | 2 | 04-May-25 A | 2026-03-02 | 10-May-25 A | 2026-02-20 | 2026-03-02
| Mechanical Data Sheet for EOT Crane for Feed Gas Compressor |  |  | 2026-02-20 |  |  | 151 | 27-Jan-25 A | 2026-03-02 | 28-Jun-25 A | 2026-02-20 | 2026-03-02
| A45620 | Mechanical Data Sheet for EOT Crane for Feed Gas Compressor_RCC |  | 2026-02-20 |  |  | 16 | 27-Feb-25 A | 2026-03-02 | 19-Apr-25 A | 2026-02-20 | 2026-03-02
| A45630 | Mechanical Data Sheet for EOT Crane for Feed Gas Compressor_IFA |  | 2026-02-20 |  |  | 3 | 20-Apr-25 A | 2026-03-02 | 10-Jun-25 A | 2026-02-20 | 2026-03-02
| A45640 | Mechanical Data Sheet for EOT Crane for Feed Gas Compressor_RCA |  | 2026-02-20 |  |  | 16 | 11-Jun-25 A | 2026-03-02 | 21-Jun-25 A | 2026-02-20 | 2026-03-02
| A45650 | Mechanical Data Sheet for EOT Crane for Feed Gas Compressor_IFD/IFC |  | 2026-02-20 |  |  | 2 | 22-Jun-25 A | 2026-03-02 | 28-Jun-25 A | 2026-02-20 | 2026-03-02
| Mechanical Data Sheet EOT Crane for Off Gas Compressor |  |  | 2026-02-20 |  |  | 151 | 27-Jan-25 A | 2026-03-02 | 28-Jun-25 A | 2026-02-20 | 2026-03-02
| A45670 | Mechanical Data Sheet EOT Crane for Off Gas Compressor_RCC |  | 2026-02-20 |  |  | 16 | 27-Feb-25 A | 2026-03-02 | 18-Mar-25 A | 2026-02-20 | 2026-03-02
| A45680 | Mechanical Data Sheet EOT Crane for Off Gas Compressor_IFA |  | 2026-02-20 |  |  | 3 | 19-Mar-25 A | 2026-03-02 | 10-Jun-25 A | 2026-02-20 | 2026-03-02
| A45690 | Mechanical Data Sheet EOT Crane for Off Gas Compressor_RCA |  | 2026-02-20 |  |  | 16 | 11-Jun-25 A | 2026-03-02 | 21-Jun-25 A | 2026-02-20 | 2026-03-02
| A45700 | Mechanical Data Sheet EOT Crane for Off Gas Compressor_IFD/IFC |  | 2026-02-20 |  |  | 2 | 22-Jun-25 A | 2026-03-02 | 28-Jun-25 A | 2026-02-20 | 2026-03-02
| Mechanical Datasheet for Water Collection Sump Pump |  |  | 2026-02-20 |  |  | 130 | 04-Jan-25 A | 2026-03-02 | 10-May-25 A | 2026-02-20 | 2026-03-02
| A45560 | Mechanical Datasheet for Water Collection Sump Pump_IFR |  | 2026-02-20 |  |  | 2 | 04-Jan-25 A | 2026-03-02 | 25-Jan-25 A | 2026-02-20 | 2026-03-02
| A45570 | Mechanical Datasheet for Water Collection Sump Pump_RCC |  | 2026-02-20 |  |  | 16 | 26-Jan-25 A | 2026-03-02 | 19-Apr-25 A | 2026-02-20 | 2026-03-02
| A45580 | Mechanical Datasheet for Water Collection Sump Pump_IFA |  | 2026-02-20 |  |  | 3 | 20-Apr-25 A | 2026-03-02 | 26-Apr-25 A | 2026-02-20 | 2026-03-02
| A45590 | Mechanical Datasheet for Water Collection Sump Pump_RCA |  | 2026-02-20 |  |  | 16 | 27-Apr-25 A | 2026-03-02 | 03-May-25 A | 2026-02-20 | 2026-03-02
| A45600 | Mechanical Datasheet for Water Collection Sump Pump_IFD/IFC |  | 2026-02-20 |  |  | 2 | 04-May-25 A | 2026-03-02 | 10-May-25 A | 2026-02-20 | 2026-03-02
| Material Requisiton for EOT Crane |  |  | 2026-02-20 |  |  | 141 | 15-Apr-25 A | 2026-03-02 | 13-Jun-25 A | 2026-02-20 | 2026-03-02
| A45760 | Material Requisiton for EOT Crane_IFR |  | 2026-02-20 |  |  | 3 | 15-Apr-25 A | 2026-03-02 | 06-May-25 A | 2026-02-20 | 2026-03-02
| A45770 | Material Requisiton for EOT Crane_RCC |  | 2026-02-20 |  |  | 16 | 07-May-25 A | 2026-03-02 | 13-May-25 A | 2026-02-20 | 2026-03-02
| A45780 | Material Requisiton for EOT Crane_IFA |  | 2026-02-20 |  |  | 3 | 14-May-25 A | 2026-03-02 | 20-May-25 A | 2026-02-20 | 2026-03-02
| A45790 | Material Requisiton for EOT Crane_RCA |  | 2026-02-20 |  |  | 16 | 21-May-25 A | 2026-03-02 | 02-Jun-25 A | 2026-02-20 | 2026-03-02
| A45800 | Material Requisiton for EOT Crane_IFD/IFC |  | 2026-02-20 |  |  | 2 | 03-Jun-25 A | 2026-03-02 | 13-Jun-25 A | 2026-02-20 | 2026-03-02
| Material Requisiton for Centrifugal Pump |  |  | 2026-02-20 |  |  | 136 | 27-Jan-25 A | 2026-03-02 | 21-Jun-25 A | 2026-02-20 | 2026-03-02
| A45720 | Material Requisiton for Centrifugal Pump_RCC |  | 2026-02-20 |  |  | 16 | 22-Mar-25 A | 2026-03-02 | 19-Apr-25 A | 2026-02-20 | 2026-03-02
| A45730 | Material Requisiton for Centrifugal Pump_IFA |  | 2026-02-20 |  |  | 3 | 20-Apr-25 A | 2026-03-02 | 01-May-25 A | 2026-02-20 | 2026-03-02
| A45740 | Material Requisiton for Centrifugal Pump_RCA |  | 2026-02-20 |  |  | 16 | 02-May-25 A | 2026-03-02 | 26-May-25 A | 2026-02-20 | 2026-03-02
| A45750 | Material Requisiton for Centrifugal Pump_IFD/IFC |  | 2026-02-20 |  |  | 2 | 27-May-25 A | 2026-03-02 | 21-Jun-25 A | 2026-02-20 | 2026-03-02
| Safety |  |  | 2026-02-20 |  |  | 369 | 31-Dec-24 A | 2026-03-02 | 2026-05-14 | 2026-05-14 | 2027-01-20 | 179
| Engineering HSE Plan |  |  | 2026-02-20 |  |  | 103 | 30-Jan-25 A | 2026-03-02 | 19-May-25 A | 2026-02-20 | 2027-01-20
| A46020 | Engineering HSE Plan_RCC |  | 2026-02-20 |  |  | 16 | 21-Feb-25 A | 2027-01-20 | 27-Feb-25 A | 2026-02-20 | 2027-01-20
| A46030 | Engineering HSE Plan_IFA |  | 2026-02-20 |  |  | 3 | 28-Feb-25 A | 2027-01-20 | 06-Mar-25 A | 2026-02-20 | 2027-01-20
| A46040 | Engineering HSE Plan_RCA |  | 2026-02-20 |  |  | 16 | 07-Mar-25 A | 2027-01-20 | 12-May-25 A | 2026-02-20 | 2027-01-20
| A46050 | Engineering HSE Plan_IFD/IFC |  | 2026-02-20 |  |  | 2 | 13-May-25 A | 2027-01-20 | 19-May-25 A | 2026-02-20 | 2027-01-20
| Project HSE Philosophy |  |  | 2026-02-20 |  |  | 112 | 31-Dec-24 A | 2026-03-02 | 20-May-25 A | 2026-02-20 | 2027-01-20
| A46070 | Project HSE Philosophy_RCC |  | 2026-02-20 |  |  | 16 | 24-Jan-25 A | 2026-04-02 | 03-Mar-25 A | 2026-02-20 | 2026-04-02
| A46080 | Project HSE Philosophy_IFA |  | 2026-02-20 |  |  | 3 | 04-Mar-25 A | 2026-04-02 | 10-Mar-25 A | 2026-02-20 | 2026-04-02
| A46090 | Project HSE Philosophy_RCA |  | 2026-02-20 |  |  | 16 | 11-Mar-25 A | 2027-01-20 | 13-Mar-25 A | 2026-02-20 | 2027-01-20
| A46100 | Project HSE Philosophy_IFD/IFC |  | 2026-02-20 |  |  | 2 | 14-Mar-25 A | 2027-01-20 | 20-May-25 A | 2026-02-20 | 2027-01-20
| Fire Protection and Detection Philosophy |  |  | 2026-02-20 |  |  | 246 | 07-Feb-25 A | 2026-03-02 | 19-Nov-25 A | 2026-02-20 | 2027-01-20
| A46120 | Fire Protection and Detection Philosophy_RCC |  | 2026-02-20 |  |  | 16 | 01-Mar-25 A | 2027-01-20 | 21-Jun-25 A | 2026-02-20 | 2027-01-20
| A46130 | Fire Protection and Detection Philosophy_IFA |  | 2026-02-20 |  |  | 3 | 22-Jun-25 A | 2027-01-20 | 28-Jun-25 A | 2026-02-20 | 2027-01-20
| A46140 | Fire Protection and Detection Philosophy_RCA |  | 2026-02-20 |  |  | 16 | 28-Aug-25 A | 2027-01-20 | 16-Oct-25 A | 2026-02-20 | 2027-01-20
| A46150 | Fire Protection and Detection Philosophy_IFD/IFC |  | 2026-02-20 |  |  | 2 | 10-Nov-25 A | 2027-01-20 | 19-Nov-25 A | 2026-02-20 | 2027-01-20
| Hazardous Area Classification Schedule |  |  | 2026-02-20 |  |  | 256 | 17-Jan-25 A | 2026-03-19 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| A46170 | Hazardous Area Classification Schedule_RCC |  | 2026-02-20 |  |  | 16 | 08-Feb-25 A | 2026-03-19 | 06-May-25 A | 2026-02-20 | 2026-03-19
| A46180 | Hazardous Area Classification Schedule_IFA |  | 2026-02-20 |  |  | 3 | 07-May-25 A | 2026-03-19 | 20-May-25 A | 2026-02-20 | 2026-03-19
| A46190 | Hazardous Area Classification Schedule_RCA |  | 2026-02-20 |  |  | 16 | 23-Jun-25 A | 2027-01-20 | 22-Aug-25 A | 2026-02-20 | 2027-01-20
| A46200 | Hazardous Area Classification Schedule_IFD/IFC |  | 2026-02-20 |  |  | 2 | 19-Dec-25 A | 2027-01-20 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| Fire Protection and Safety Equipment Layouts (Building) |  |  | 2026-02-20 |  |  | 241 | 27-Feb-25 A | 2026-04-20 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| A46370 | Fire Protection and Safety Equipment Layouts (Building)_RCC |  | 2026-02-20 |  |  | 16 | 21-Mar-25 A | 2027-01-20 | 21-Jun-25 A | 2026-02-20 | 2027-01-20
| A46380 | Fire Protection and Safety Equipment Layouts (Building)_IFA |  | 2026-02-20 |  |  | 3 | 22-Jun-25 A | 2027-01-20 | 28-Jul-25 A | 2026-02-20 | 2027-01-20
| A46390 | Fire Protection and Safety Equipment Layouts (Building)_RCA |  | 2026-02-20 |  |  | 16 | 29-Jul-25 A | 2027-01-20 | 27-Aug-25 A | 2026-02-20 | 2027-01-20
| A46400 | Fire Protection and Safety Equipment Layouts (Building)_IFD/IFC |  | 2026-02-20 |  |  | 2 | 19-Dec-25 A | 2027-01-20 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| Escape Route and Safety Signs Layouts (Building) |  |  | 2026-02-20 |  |  | 241 | 27-Feb-25 A | 2026-04-20 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| A46470 | Escape Route and Safety Signs Layouts (Building)_RCC |  | 2026-02-20 |  |  | 16 | 21-Mar-25 A | 2027-01-20 | 21-Jun-25 A | 2026-02-20 | 2027-01-20
| A46480 | Escape Route and Safety Signs Layouts (Building)_IFA |  | 2026-02-20 |  |  | 3 | 01-Oct-25 A | 2027-01-20 | 07-Oct-25 A | 2026-02-20 | 2027-01-20
| A46490 | Escape Route and Safety Signs Layouts (Building)_RCA |  | 2026-02-20 |  |  | 16 | 03-Oct-25 A | 2027-01-20 | 14-Oct-25 A | 2026-02-20 | 2027-01-20
| A46500 | Escape Route and Safety Signs Layouts (Building)_IFD/IFC |  | 2026-02-20 |  |  | 2 | 19-Dec-25 A | 2027-01-20 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| Fire & Gas Detectors Layouts (Building) |  |  | 2026-02-20 |  |  | 241 | 27-Feb-25 A | 2026-04-20 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| A46570 | Fire & Gas Detectors Layouts (Building)_RCC |  | 2026-02-20 |  |  | 16 | 21-Mar-25 A | 2027-01-20 | 21-Jun-25 A | 2026-02-20 | 2027-01-20
| A46580 | Fire & Gas Detectors Layouts (Building)_IFA |  | 2026-02-20 |  |  | 3 | 22-Jun-25 A | 2027-01-20 | 16-Jul-25 A | 2026-02-20 | 2027-01-20
| A46590 | Fire & Gas Detectors Layouts (Building)_RCA |  | 2026-02-20 |  |  | 16 | 08-Sep-25 A | 2027-01-20 | 07-Oct-25 A | 2026-02-20 | 2027-01-20
| A46600 | Fire & Gas Detectors Layouts (Building)_IFD/IFC |  | 2026-02-20 |  |  | 2 | 19-Dec-25 A | 2027-01-20 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| F&G Cause and Effects Matrix |  |  | 2026-02-20 |  |  | 43 | 2026-02-20 | 2026-11-23 | 2026-04-21 | 2026-04-21 | 2027-01-20 | 196
| A46620 | F&G Cause and Effects Matrix_RCC |  | 2026-02-27 |  |  | 16 | 2026-02-27 | 2026-11-30 | 2026-03-23 | 2026-03-23 | 2026-12-22 | 196
| A46630 | F&G Cause and Effects Matrix_IFA |  | 2026-03-23 |  |  | 3 | 2026-03-23 | 2026-12-22 | 2026-03-26 | 2026-03-26 | 2026-12-25 | 196
| A46640 | F&G Cause and Effects Matrix_RCA |  | 2026-03-26 |  |  | 16 | 2026-03-26 | 2026-12-28 | 2026-04-17 | 2026-04-17 | 2027-01-18 | 196
| A46650 | F&G Cause and Effects Matrix_IFD/IFC |  | 2026-04-17 |  |  | 2 | 2026-04-17 | 2027-01-18 | 2026-04-21 | 2026-04-21 | 2027-01-20 | 196
| Specification for Fire Protection and Safety Equipment |  |  | 2026-02-20 |  |  | 259 | 07-Feb-25 A | 2026-04-20 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| A46770 | Specification for Fire Protection and Safety Equipment_RCC |  | 2026-02-20 |  |  | 16 | 01-Mar-25 A | 2027-01-20 | 31-Jul-25 A | 2026-02-20 | 2027-01-20
| A46780 | Specification for Fire Protection and Safety Equipment_IFA |  | 2026-02-20 |  |  | 3 | 01-Oct-25 A | 2027-01-20 | 07-Oct-25 A | 2026-02-20 | 2027-01-20
| A46790 | Specification for Fire Protection and Safety Equipment_RCA |  | 2026-02-20 |  |  | 16 | 03-Oct-25 A | 2027-01-20 | 14-Oct-25 A | 2026-02-20 | 2027-01-20
| A46800 | Specification for Fire Protection and Safety Equipment_IFD/IFC |  | 2026-02-20 |  |  | 2 | 19-Dec-25 A | 2027-01-20 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| Specification for Clean Agent System |  |  | 2026-02-20 |  |  | 189 | 11-Feb-25 A | 2026-05-05 | 10-Oct-25 A | 2026-02-20 | 2027-01-20
| A46820 | Specification for Clean Agent System_RCC |  | 2026-02-20 |  |  | 16 | 05-Mar-25 A | 2027-01-20 | 21-Jun-25 A | 2026-02-20 | 2027-01-20
| A46830 | Specification for Clean Agent System_IFA |  | 2026-02-20 |  |  | 3 | 22-Jun-25 A | 2027-01-20 | 30-Jun-25 A | 2026-02-20 | 2027-01-20
| A46840 | Specification for Clean Agent System_RCA |  | 2026-02-20 |  |  | 16 | 12-Jul-25 A | 2027-01-20 | 30-Jul-25 A | 2026-02-20 | 2027-01-20
| A46850 | Specification for Clean Agent System_IFD/IFC |  | 2026-02-20 |  |  | 2 | 01-Oct-25 A | 2027-01-20 | 10-Oct-25 A | 2026-02-20 | 2027-01-20
| MR for Clean Agent System |  |  | 2026-02-20 |  |  | 213 | 28-Feb-25 A | 2026-05-05 | 10-Oct-25 A | 2026-02-20 | 2026-05-05
| A47240 | MR for Clean Agent System_RCC |  | 2026-02-20 |  |  | 16 | 22-Mar-25 A | 2026-05-05 | 21-Jun-25 A | 2026-02-20 | 2026-05-05
| A47250 | MR for Clean Agent System_IFA |  | 2026-02-20 |  |  | 3 | 22-Jun-25 A | 2026-05-05 | 23-Aug-25 A | 2026-02-20 | 2026-05-05
| A47260 | MR for Clean Agent System_RCA |  | 2026-02-20 |  |  | 16 | 24-Aug-25 A | 2026-05-05 | 30-Aug-25 A | 2026-02-20 | 2026-05-05
| A47270 | MR for Clean Agent System_IFD/IFC |  | 2026-02-20 |  |  | 2 | 01-Oct-25 A | 2026-05-05 | 10-Oct-25 A | 2026-02-20 | 2026-05-05
| Firewater Line List |  |  | 2026-02-20 |  |  | 286 | 28-Feb-25 A | 2026-11-30 | 2026-04-17 | 2026-04-17 | 2027-01-20 | 199
| A47140 | Firewater Line List_RCC |  | 2026-02-20 |  |  | 16 | 2026-02-20 | 2026-11-30 | 2026-03-13 | 2026-03-13 | 2026-12-22 | 202
| A47150 | Firewater Line List_IFA |  | 2026-03-19 |  |  | 3 | 2026-03-19 | 2026-12-22 | 2026-03-24 | 2026-03-24 | 2026-12-25 | 199
| A47160 | Firewater Line List_RCA |  | 2026-03-24 |  |  | 16 | 2026-03-24 | 2026-12-28 | 2026-04-15 | 2026-04-15 | 2027-01-18 | 199
| A47170 | Firewater Line List_IFD/IFC |  | 2026-04-15 |  |  | 2 | 2026-04-15 | 2027-01-18 | 2026-04-17 | 2026-04-17 | 2027-01-20 | 199
| Passive Fire Protection schedule |  |  | 2026-02-20 |  |  | 250 | 28-Feb-25 A | 2027-01-20 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| A46670 | Passive Fire Protection schedule_RCC |  | 2026-02-20 |  |  | 16 | 22-Mar-25 A | 2027-01-20 | 21-Jun-25 A | 2026-02-20 | 2027-01-20
| A46680 | Passive Fire Protection schedule_IFA |  | 2026-02-20 |  |  | 3 | 22-Jun-25 A | 2027-01-20 | 18-Jul-25 A | 2026-02-20 | 2027-01-20
| A46690 | Passive Fire Protection schedule_RCA |  | 2026-02-20 |  |  | 16 | 08-Sep-25 A | 2027-01-20 | 07-Oct-25 A | 2026-02-20 | 2027-01-20
| A46700 | Passive Fire Protection schedule_IFD/IFC |  | 2026-02-20 |  |  | 2 | 19-Dec-25 A | 2027-01-20 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| Firewater Demand Report |  |  | 2026-02-20 |  |  | 230 | 17-Jan-25 A | 2026-11-30 | 03-Nov-25 A | 2026-02-20 | 2027-01-20
| A9090 | Firewater Demand Report_RCC |  | 2026-02-20 |  |  | 16 | 12-Mar-25 A | 2027-01-20 | 21-Jul-25 A | 2026-02-20 | 2027-01-20
| A9100 | Firewater Demand Report_IFA |  | 2026-02-20 |  |  | 3 | 22-Jul-25 A | 2027-01-20 | 06-Sep-25 A | 2026-02-20 | 2027-01-20
| A9110 | Firewater Demand Report_RCA |  | 2026-02-20 |  |  | 16 | 07-Sep-25 A | 2027-01-20 | 13-Sep-25 A | 2026-02-20 | 2027-01-20
| A47070 | Firewater Demand Report_IFD/IFC |  | 2026-02-20 |  |  | 2 | 30-Oct-25 A | 2027-01-20 | 03-Nov-25 A | 2026-02-20 | 2027-01-20
| HAZID ENVID OHID Closeout Report |  |  | 2026-02-20 |  |  | 103 | 01-Sep-25 A | 2026-04-02 | 2026-03-17 | 2026-03-17 | 2027-01-20 | 221
| A47340 | HAZID ENVID OHID Closeout Report_RCC |  | 2026-02-20 |  |  | 16 | 05-Sep-25 A | 2026-11-20 | 20-Sep-25 A | 2026-02-20 | 2026-11-20
| A47350 | HAZID ENVID OHID Closeout Report_IFA |  | 2026-02-20 |  |  | 3 | 28-Nov-25 A | 2026-11-20 | 19-Dec-25 A | 2026-02-20 | 2026-11-20
| A47360 | HAZID ENVID OHID Closeout Report_RCA |  | 2026-02-20 |  |  | 16 | 2026-02-20 | 2026-12-28 | 2026-03-13 | 2026-03-13 | 2027-01-18 | 221
| A47370 | HAZID ENVID OHID Closeout Report_IFD/IFC |  | 2026-03-13 |  |  | 2 | 2026-03-13 | 2027-01-18 | 2026-03-17 | 2026-03-17 | 2027-01-20 | 221
| Escape Route and Safety Signs Layouts (Plant) |  |  | 2026-02-20 |  |  | 222 | 16-Apr-25 A | 2026-04-20 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| A46420 | Escape Route and Safety Signs Layouts (Plant)_RCC |  | 2026-02-20 |  |  | 16 | 08-May-25 A | 2027-01-20 | 21-Jun-25 A | 2026-02-20 | 2027-01-20
| A46430 | Escape Route and Safety Signs Layouts (Plant)_IFA |  | 2026-02-20 |  |  | 3 | 22-Jun-25 A | 2027-01-20 | 28-Jul-25 A | 2026-02-20 | 2027-01-20
| A46440 | Escape Route and Safety Signs Layouts (Plant)_RCA |  | 2026-02-20 |  |  | 16 | 29-Jul-25 A | 2027-01-20 | 30-Aug-25 A | 2026-02-20 | 2027-01-20
| A46450 | Escape Route and Safety Signs Layouts (Plant)_IFD/IFC |  | 2026-02-20 |  |  | 2 | 19-Dec-25 A | 2027-01-20 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| Fire & Gas Detectors Layouts (Plant) |  |  | 2026-02-20 |  |  | 222 | 06-Apr-25 A | 2026-04-20 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| A46520 | Fire & Gas Detectors Layouts (Plant)_RCC |  | 2026-02-20 |  |  | 16 | 28-Apr-25 A | 2027-01-20 | 21-Jun-25 A | 2026-02-20 | 2027-01-20
| A46530 | Fire & Gas Detectors Layouts (Plant)_IFA |  | 2026-02-20 |  |  | 3 | 22-Jun-25 A | 2027-01-20 | 28-Jun-25 A | 2026-02-20 | 2027-01-20
| A46540 | Fire & Gas Detectors Layouts (Plant)_RCA |  | 2026-02-20 |  |  | 16 | 01-Sep-25 A | 2027-01-20 | 07-Oct-25 A | 2026-02-20 | 2027-01-20
| A46550 | Fire & Gas Detectors Layouts (Plant)_IFD/IFC |  | 2026-02-20 |  |  | 2 | 19-Dec-25 A | 2027-01-20 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| Passive Fire Protection Layouts |  |  | 2026-02-20 |  |  | 245 | 08-Apr-25 A | 2027-01-20 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| A46720 | Passive Fire Protection Layouts_RCC |  | 2026-02-20 |  |  | 16 | 30-Apr-25 A | 2027-01-20 | 21-Jun-25 A | 2026-02-20 | 2027-01-20
| A46730 | Passive Fire Protection Layouts_IFA |  | 2026-02-20 |  |  | 3 | 22-Jun-25 A | 2027-01-20 | 29-Jul-25 A | 2026-02-20 | 2027-01-20
| A46740 | Passive Fire Protection Layouts_RCA |  | 2026-02-20 |  |  | 16 | 08-Sep-25 A | 2027-01-20 | 07-Oct-25 A | 2026-02-20 | 2027-01-20
| A46750 | Passive Fire Protection Layouts_IFD/IFC |  | 2026-02-20 |  |  | 2 | 19-Dec-25 A | 2027-01-20 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| HAZOP Closeout Report |  |  | 2026-02-20 |  |  | 86 | 01-Aug-25 A | 2026-03-19 | 04-Sep-25 A | 2026-02-20 | 2026-03-19
| A47440 | HAZOP Closeout Report_RCC |  | 2026-02-20 |  |  | 16 | 04-Aug-25 A | 2026-03-19 | 25-Aug-25 A | 2026-02-20 | 2026-03-19
| A47450 | HAZOP Closeout Report_IFA |  | 2026-02-20 |  |  | 3 | 25-Aug-25 A | 2026-03-19 | 28-Aug-25 A | 2026-02-20 | 2026-03-19
| A47460 | HAZOP Closeout Report_RCA |  | 2026-02-20 |  |  | 16 | 29-Aug-25 A | 2026-03-19 | 31-Aug-25 A | 2026-02-20 | 2026-03-19
| A47470 | HAZOP Closeout Report_IFD/IFC |  | 2026-02-20 |  |  | 2 | 01-Sep-25 A | 2026-03-19 | 04-Sep-25 A | 2026-02-20 | 2026-03-19
| Fire Protection and Safety Equipment Layouts (Plant) |  |  | 2026-02-20 |  |  | 267 | 28-Mar-25 A | 2026-04-20 | 2026-02-24 | 2026-02-24 | 2027-01-20 | 237
| A46320 | Fire Protection and Safety Equipment Layouts (Plant)_RCC |  | 2026-02-20 |  |  | 16 | 22-Apr-25 A | 2027-01-18 | 21-Jun-25 A | 2026-02-20 | 2027-01-18
| A46330 | Fire Protection and Safety Equipment Layouts (Plant)_IFA |  | 2026-02-20 |  |  | 3 | 22-Jun-25 A | 2027-01-18 | 28-Jul-25 A | 2026-02-20 | 2027-01-18
| A46340 | Fire Protection and Safety Equipment Layouts (Plant)_RCA |  | 2026-02-20 |  |  | 16 | 29-Jul-25 A | 2027-01-18 | 30-Aug-25 A | 2026-02-20 | 2027-01-18
| A46350 | Fire Protection and Safety Equipment Layouts (Plant)_IFD/IFC |  | 2026-02-20 |  |  | 2 | 2026-02-20 | 2027-01-18 | 2026-02-24 | 2026-02-24 | 2027-01-20 | 237
| Firewater Hydraulic Report |  |  | 2026-02-20 |  |  | 212 | 02-Jul-25 A | 2026-11-30 | 2026-04-14 | 2026-04-14 | 2027-01-20 | 202
| A47090 | Firewater Hydraulic Report_RCC |  | 2026-02-20 |  |  | 16 | 2026-02-20 | 2026-11-30 | 2026-03-13 | 2026-03-13 | 2026-12-22 | 202
| A47100 | Firewater Hydraulic Report_IFA |  | 2026-03-13 |  |  | 3 | 2026-03-13 | 2026-12-22 | 2026-03-19 | 2026-03-19 | 2026-12-25 | 202
| A47110 | Firewater Hydraulic Report_RCA |  | 2026-03-19 |  |  | 16 | 2026-03-19 | 2026-12-28 | 2026-04-09 | 2026-04-09 | 2027-01-18 | 202
| A47120 | Firewater Hydraulic Report_IFD/IFC |  | 2026-04-09 |  |  | 2 | 2026-04-09 | 2027-01-18 | 2026-04-14 | 2026-04-14 | 2027-01-20 | 202
| Datasheets for Fire Protection and Safety Equipment |  |  | 2026-02-20 |  |  | 217 | 17-Apr-25 A | 2026-04-20 | 23-Dec-25 A | 2026-02-20 | 2026-06-12
| A46870 | Datasheets for Fire Protection and Safety Equipment_RCC |  | 2026-02-20 |  |  | 16 | 09-May-25 A | 2026-06-12 | 21-Jun-25 A | 2026-02-20 | 2026-06-12
| A46880 | Datasheets for Fire Protection and Safety Equipment_IFA |  | 2026-02-20 |  |  | 3 | 18-Aug-25 A | 2026-06-12 | 25-Aug-25 A | 2026-02-20 | 2026-06-12
| A46890 | Datasheets for Fire Protection and Safety Equipment_RCA |  | 2026-02-20 |  |  | 16 | 01-Sep-25 A | 2026-06-12 | 07-Oct-25 A | 2026-02-20 | 2026-06-12
| A46900 | Datasheets for Fire Protection and Safety Equipment_IFD/IFC |  | 2026-02-20 |  |  | 2 | 19-Dec-25 A | 2026-06-12 | 23-Dec-25 A | 2026-02-20 | 2026-06-12
| Fire Zone Layout |  |  | 2026-02-20 |  |  | 278 | 02-Apr-25 A | 2027-01-20 | 10-Sep-25 A | 2026-02-20 | 2027-01-20
| A46270 | Fire Zone Layout_RCC |  | 2026-02-20 |  |  | 16 | 24-Apr-25 A | 2027-01-20 | 12-Aug-25 A | 2026-02-20 | 2027-01-20
| A46280 | Fire Zone Layout_IFA |  | 2026-02-20 |  |  | 3 | 13-Aug-25 A | 2027-01-20 | 15-Aug-25 A | 2026-02-20 | 2027-01-20
| A46290 | Fire Zone Layout_RCA |  | 2026-02-20 |  |  | 16 | 16-Aug-25 A | 2027-01-20 | 07-Sep-25 A | 2026-02-20 | 2027-01-20
| A46300 | Fire Zone Layout_IFD/IFC |  | 2026-02-20 |  |  | 2 | 08-Sep-25 A | 2027-01-20 | 10-Sep-25 A | 2026-02-20 | 2027-01-20
| Hazardous Area Classification Layouts |  |  | 2026-02-20 |  |  | 228 | 06-Apr-25 A | 2027-01-20 | 13-Jan-26 A | 2026-02-20 | 2027-01-20
| A46220 | Hazardous Area Classification Layouts_RCC |  | 2026-02-20 |  |  | 16 | 28-Apr-25 A | 2027-01-20 | 21-Jun-25 A | 2026-02-20 | 2027-01-20
| A46230 | Hazardous Area Classification Layouts_IFA |  | 2026-02-20 |  |  | 3 | 22-Jun-25 A | 2027-01-20 | 29-Aug-25 A | 2026-02-20 | 2027-01-20
| A46240 | Hazardous Area Classification Layouts_RCA |  | 2026-02-20 |  |  | 16 | 19-Dec-25 A | 2027-01-20 | 09-Jan-26 A | 2026-02-20 | 2027-01-20
| A46250 | Hazardous Area Classification Layouts_IFD/IFC |  | 2026-02-20 |  |  | 2 | 09-Jan-26 A | 2027-01-20 | 13-Jan-26 A | 2026-02-20 | 2027-01-20
| MR for Fire Protection and Safety Equipment |  |  | 2026-02-20 |  |  | 146 | 14-May-25 A | 2026-05-22 | 25-Dec-25 A | 2026-02-20 | 2026-06-12
| A47180 | MR for Fire Protection and Safety Equipment_IFR |  | 2026-02-20 |  |  | 6 | 04-Jun-25 A | 2026-05-22 | 13-Jun-25 A | 2026-02-20 | 2026-05-22
| A47190 | MR for Fire Protection and Safety Equipment_RCC |  | 2026-02-20 |  |  | 16 | 14-May-25 A | 2026-06-12 | 21-Jun-25 A | 2026-02-20 | 2026-06-12
| A47200 | MR for Fire Protection and Safety Equipment_IFA |  | 2026-02-20 |  |  | 3 | 23-Jun-25 A | 2026-06-12 | 21-Jul-25 A | 2026-02-20 | 2026-06-12
| A47210 | MR for Fire Protection and Safety Equipment_RCA |  | 2026-02-20 |  |  | 16 | 01-Jul-25 A | 2026-06-12 | 28-Jul-25 A | 2026-02-20 | 2026-06-12
| A47220 | MR for Fire Protection and Safety Equipment_IFD/IFC |  | 2026-02-20 |  |  | 2 | 23-Dec-25 A | 2026-06-12 | 25-Dec-25 A | 2026-02-20 | 2026-06-12
| Fire Water Layout |  |  | 2026-02-20 |  |  | 215 | 17-Apr-25 A | 2027-01-20 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| A46920 | Fire Water Layout_RCC |  | 2026-02-20 |  |  | 16 | 09-May-25 A | 2027-01-20 | 21-Jun-25 A | 2026-02-20 | 2027-01-20
| A46930 | Fire Water Layout_IFA |  | 2026-02-20 |  |  | 3 | 27-Jun-25 A | 2027-01-20 | 21-Jul-25 A | 2026-02-20 | 2027-01-20
| A46940 | Fire Water Layout_RCA |  | 2026-02-20 |  |  | 16 | 01-Jul-25 A | 2027-01-20 | 28-Jul-25 A | 2026-02-20 | 2027-01-20
| A46950 | Fire Water Layout_IFD/IFC |  | 2026-02-20 |  |  | 2 | 19-Dec-25 A | 2027-01-20 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| P&ID - Firewater Network |  |  | 2026-02-20 |  |  | 292 | 21-Feb-25 A | 2026-11-25 | 2026-04-14 | 2026-04-14 | 2027-01-18 | 200
| A46970 | P&ID - Firewater Network_RCC |  | 2026-02-20 |  |  | 16 | 2026-02-20 | 2026-11-25 | 2026-03-13 | 2026-03-13 | 2026-12-17 | 199
| A46980 | P&ID - Firewater Network_IFA |  | 2026-03-13 |  |  | 3 | 2026-03-13 | 2026-12-17 | 2026-03-19 | 2026-03-19 | 2026-12-22 | 199
| A46990 | P&ID - Firewater Network_RCA |  | 2026-03-19 |  |  | 16 | 2026-03-19 | 2026-12-23 | 2026-04-09 | 2026-04-09 | 2027-01-14 | 200
| A47000 | P&ID - Firewater Network_IFD/IFC |  | 2026-04-09 |  |  | 2 | 2026-04-09 | 2027-01-14 | 2026-04-14 | 2026-04-14 | 2027-01-18 | 200
| P&ID - Deluge Spray System |  |  | 2026-02-20 |  |  | 223 | 19-Apr-25 A | 2026-11-26 | 2026-04-14 | 2026-04-14 | 2027-01-18 | 200
| A47020 | P&ID - Deluge Spray System_RCC |  | 2026-02-20 |  |  | 16 | 2026-02-20 | 2026-11-26 | 2026-03-13 | 2026-03-13 | 2026-12-18 | 200
| A47030 | P&ID - Deluge Spray System_IFA |  | 2026-03-13 |  |  | 3 | 2026-03-13 | 2026-12-18 | 2026-03-19 | 2026-03-19 | 2026-12-23 | 200
| A47040 | P&ID - Deluge Spray System_RCA |  | 2026-03-19 |  |  | 16 | 2026-03-19 | 2026-12-23 | 2026-04-09 | 2026-04-09 | 2027-01-14 | 200
| A47050 | P&ID - Deluge Spray System_IFD/IFC |  | 2026-04-09 |  |  | 2 | 2026-04-09 | 2027-01-14 | 2026-04-14 | 2026-04-14 | 2027-01-18 | 200
| P&ID - Clean Agent System |  |  | 2026-02-20 |  |  | 292 | 21-Feb-25 A | 2026-11-26 | 2026-04-14 | 2026-04-14 | 2027-01-18 | 200
| A9040 | P&ID - Clean Agent System_RCC |  | 2026-02-20 |  |  | 16 | 2026-02-20 | 2026-11-26 | 2026-03-13 | 2026-03-13 | 2026-12-18 | 200
| A9050 | P&ID - Clean Agent System_IFA |  | 2026-03-13 |  |  | 3 | 2026-03-13 | 2026-12-18 | 2026-03-19 | 2026-03-19 | 2026-12-23 | 200
| A9060 | P&ID - Clean Agent System_RCA |  | 2026-03-19 |  |  | 16 | 2026-03-19 | 2026-12-23 | 2026-04-09 | 2026-04-09 | 2027-01-14 | 200
| A9070 | P&ID - Clean Agent System_IFD/IFC |  | 2026-04-09 |  |  | 2 | 2026-04-09 | 2027-01-14 | 2026-04-14 | 2026-04-14 | 2027-01-18 | 200
| ISD Closeout Report |  |  | 2026-02-20 |  |  | 106 | 01-Oct-25 A | 2026-12-22 | 2026-03-23 | 2026-03-23 | 2027-01-20 | 218
| A47390 | ISD Closeout Report_RCC |  | 2026-02-20 |  |  | 16 | 20-Oct-25 A | 2026-12-22 | 17-Nov-25 A | 2026-02-20 | 2026-12-22
| A47400 | ISD Closeout Report_IFA |  | 2026-02-20 |  |  | 3 | 2026-02-20 | 2026-12-22 | 2026-02-25 | 2026-02-25 | 2026-12-25 | 218
| A47410 | ISD Closeout Report_RCA |  | 2026-02-25 |  |  | 16 | 2026-02-25 | 2026-12-28 | 2026-03-19 | 2026-03-19 | 2027-01-18 | 218
| A47420 | ISD Closeout Report_IFD/IFC |  | 2026-03-19 |  |  | 2 | 2026-03-19 | 2027-01-18 | 2026-03-23 | 2026-03-23 | 2027-01-20 | 218
| PHSER 3 Closeout Report |  |  | 2026-03-16 |  |  | 43 | 2026-03-16 | 2026-11-23 | 2026-05-14 | 2026-05-14 | 2027-01-20 | 179
| A47490 | PHSER 3 Closeout Report_RCC |  | 2026-03-24 |  |  | 16 | 2026-03-24 | 2026-11-30 | 2026-04-15 | 2026-04-15 | 2026-12-22 | 179
| A47500 | PHSER 3 Closeout Report_IFA |  | 2026-04-15 |  |  | 3 | 2026-04-15 | 2026-12-22 | 2026-04-20 | 2026-04-20 | 2026-12-25 | 179
| A47510 | PHSER 3 Closeout Report_RCA |  | 2026-04-20 |  |  | 16 | 2026-04-20 | 2026-12-28 | 2026-05-12 | 2026-05-12 | 2027-01-18 | 179
| A47520 | PHSER 3 Closeout Report_IFD/IFC |  | 2026-05-12 |  |  | 2 | 2026-05-12 | 2027-01-18 | 2026-05-14 | 2026-05-14 | 2027-01-20 | 179
| HSE Action Tracking Register |  |  | 2026-02-20 |  |  | 71 | 03-Nov-25 A | 2026-12-22 | 2026-03-23 | 2026-03-23 | 2027-01-20 | 218
| A47290 | HSE Action Tracking Register_RCC |  | 2026-02-20 |  |  | 16 | 19-Dec-25 A | 2026-12-22 | 09-Jan-26 A | 2026-02-20 | 2026-12-22
| A47300 | HSE Action Tracking Register_IFA |  | 2026-02-20 |  |  | 3 | 2026-02-20 | 2026-12-22 | 2026-02-25 | 2026-02-25 | 2026-12-25 | 218
| A47310 | HSE Action Tracking Register_RCA |  | 2026-02-25 |  |  | 16 | 2026-02-25 | 2026-12-28 | 2026-03-19 | 2026-03-19 | 2027-01-18 | 218
| A47320 | HSE Action Tracking Register_IFD/IFC |  | 2026-03-19 |  |  | 2 | 2026-03-19 | 2027-01-18 | 2026-03-23 | 2026-03-23 | 2027-01-20 | 218
| Scope Of Work For Cathodic Protection |  |  | 2026-02-20 |  |  | 97 | 08-Aug-25 A | 2026-05-15 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| A10640 | Scope Of Work For Cathodic Protection_RCC |  | 2026-02-20 |  |  | 16 | 15-Aug-25 A | 2026-05-15 | 19-Sep-25 A | 2026-02-20 | 2026-05-15
| A10650 | Scope Of Work For Cathodic Protection_IFA |  | 2026-02-20 |  |  | 3 | 03-Nov-25 A | 2026-05-15 | 10-Nov-25 A | 2026-02-20 | 2026-05-15
| A10660 | Scope Of Work For Cathodic Protection_RCA |  | 2026-02-20 |  |  | 16 | 11-Nov-25 A | 2027-01-20 | 20-Nov-25 A | 2026-02-20 | 2027-01-20
| A10670 | Scope Of Work For Cathodic Protection_IFD/IFC |  | 2026-02-20 |  |  | 2 | 19-Dec-25 A | 2027-01-20 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| Electrical System Operating Philosophy |  |  | 2026-02-20 |  |  | 43 | 2026-02-20 | 2026-11-23 | 2026-04-21 | 2026-04-21 | 2027-01-20 | 196
| A47540 | Electrical System Operating Philosophy_RCC |  | 2026-02-27 |  |  | 16 | 2026-02-27 | 2026-11-30 | 2026-03-23 | 2026-03-23 | 2026-12-22 | 196
| A47550 | Electrical System Operating Philosophy_IFA |  | 2026-03-23 |  |  | 3 | 2026-03-23 | 2026-12-22 | 2026-03-26 | 2026-03-26 | 2026-12-25 | 196
| A47560 | Electrical System Operating Philosophy_RCA |  | 2026-03-26 |  |  | 16 | 2026-03-26 | 2026-12-28 | 2026-04-17 | 2026-04-17 | 2027-01-18 | 196
| A47570 | Electrical System Operating Philosophy_IFD/IFC |  | 2026-04-17 |  |  | 2 | 2026-04-17 | 2027-01-18 | 2026-04-21 | 2026-04-21 | 2027-01-20 | 196
| Technical Data Sheet For Transformer (Power and Distribution) |  |  | 2026-02-20 |  |  | 146 | 23-Dec-24 A | 2026-03-02 | 03-Jul-25 A | 2026-02-20 | 2026-03-02
| A47590 | Technical Data Sheet For Transformer (Power and Distribution)_RCC |  | 2026-02-20 |  |  | 16 | 14-Jan-25 A | 2026-03-02 | 06-May-25 A | 2026-02-20 | 2026-03-02
| A47600 | Technical Data Sheet For Transformer (Power and Distribution)_IFA |  | 2026-02-20 |  |  | 3 | 07-May-25 A | 2026-03-02 | 19-Jun-25 A | 2026-02-20 | 2026-03-02
| A47610 | Technical Data Sheet For Transformer (Power and Distribution)_RCA |  | 2026-02-20 |  |  | 16 | 20-Jun-25 A | 2026-03-02 | 26-Jun-25 A | 2026-02-20 | 2026-03-02
| A47620 | Technical Data Sheet For Transformer (Power and Distribution)_IFD/IFC |  | 2026-02-20 |  |  | 2 | 27-Jun-25 A | 2026-03-02 | 03-Jul-25 A | 2026-02-20 | 2026-03-02
| Technical Data Sheet For LV Motors |  |  | 2026-02-20 |  |  | 106 | 01-Jan-25 A | 2026-03-02 | 03-May-25 A | 2026-02-20 | 2027-01-20
| A9840 | Technical Data Sheet For LV Motors_RCC |  | 2026-02-20 |  |  | 16 | 23-Jan-25 A | 2027-01-20 | 28-Feb-25 A | 2026-02-20 | 2027-01-20
| A9850 | Technical Data Sheet For LV Motors_IFA |  | 2026-02-20 |  |  | 3 | 01-Mar-25 A | 2027-01-20 | 19-Apr-25 A | 2026-02-20 | 2027-01-20
| A9860 | Technical Data Sheet For LV Motors_RCA |  | 2026-02-20 |  |  | 16 | 20-Apr-25 A | 2027-01-20 | 26-Apr-25 A | 2026-02-20 | 2027-01-20
| A9870 | Technical Data Sheet For LV Motors_IFD/IFC |  | 2026-02-20 |  |  | 2 | 27-Apr-25 A | 2027-01-20 | 03-May-25 A | 2026-02-20 | 2027-01-20
| Technical Data Sheet For Emergency Diesel Generator |  |  | 2026-02-20 |  |  | 208 | 09-Jan-25 A | 2026-03-02 | 10-Sep-25 A | 2026-02-20 | 2026-03-02
| A9890 | Technical Data Sheet For Emergency Diesel Generator_RCC |  | 2026-02-20 |  |  | 16 | 03-Mar-25 A | 2026-03-02 | 02-May-25 A | 2026-02-20 | 2026-03-02
| A9900 | Technical Data Sheet For Emergency Diesel Generator_IFA |  | 2026-02-20 |  |  | 3 | 03-May-25 A | 2026-03-02 | 16-May-25 A | 2026-02-20 | 2026-03-02
| A9910 | Technical Data Sheet For Emergency Diesel Generator_RCA |  | 2026-02-20 |  |  | 16 | 19-Aug-25 A | 2026-03-02 | 08-Sep-25 A | 2026-02-20 | 2026-03-02
| A9920 | Technical Data Sheet For Emergency Diesel Generator_IFD/IFC |  | 2026-02-20 |  |  | 2 | 09-Sep-25 A | 2026-03-02 | 10-Sep-25 A | 2026-02-20 | 2026-03-02
| Technical Data Sheet For Intergrated Protection Control Panel |  |  | 2026-02-20 |  |  | 97 | 01-May-25 A | 2026-03-02 | 06-Jun-25 A | 2026-02-20 | 2026-03-02
| A58390 | Technical Data Sheet For IPCS_IFR |  | 2026-02-20 |  |  | 2 | 01-May-25 A | 2026-03-02 | 05-May-25 A | 2026-02-20 | 2026-03-02
| A58400 | Technical Data Sheet For IPCS_RCC |  | 2026-02-20 |  |  | 16 | 06-May-25 A | 2026-03-02 | 16-May-25 A | 2026-02-20 | 2026-03-02
| A58410 | Technical Data Sheet For IPCS_IFA |  | 2026-02-20 |  |  | 3 | 19-May-25 A | 2026-03-02 | 23-May-25 A | 2026-02-20 | 2026-03-02
| A58420 | Technical Data Sheet For IPCS_RCA |  | 2026-02-20 |  |  | 16 | 26-May-25 A | 2026-03-02 | 30-May-25 A | 2026-02-20 | 2026-03-02
| A58430 | Technical Data Sheet For IPCS_IFD/IFC |  | 2026-02-20 |  |  | 2 | 02-Jun-25 A | 2026-03-02 | 06-Jun-25 A | 2026-02-20 | 2026-03-02
| Technical Data Sheet For SCMS |  |  | 2026-02-20 |  |  | 97 | 05-May-25 A | 2026-03-02 | 13-Jun-25 A | 2026-02-20 | 2026-03-02
| A59900 | Technical Data Sheet For SCMS_IFR |  | 2026-02-20 |  |  | 2 | 05-May-25 A | 2026-03-02 | 09-May-25 A | 2026-02-20 | 2026-03-02
| A59910 | Technical Data Sheet For SCMS_RCC |  | 2026-02-20 |  |  | 16 | 12-May-25 A | 2026-03-02 | 23-May-25 A | 2026-02-20 | 2026-03-02
| A59920 | Technical Data Sheet For SCMS_IFA |  | 2026-02-20 |  |  | 3 | 26-May-25 A | 2026-03-02 | 30-May-25 A | 2026-02-20 | 2026-03-02
| A59930 | Technical Data Sheet For SCMS_RCA |  | 2026-02-20 |  |  | 16 | 02-Jun-25 A | 2026-03-02 | 06-Jun-25 A | 2026-02-20 | 2026-03-02
| A59940 | Technical Data Sheet For SCMS_IFD/IFC |  | 2026-02-20 |  |  | 2 | 09-Jun-25 A | 2026-03-02 | 13-Jun-25 A | 2026-02-20 | 2026-03-02
| Technical Data Sheet For 11KV Switchgear |  |  | 2026-02-20 |  |  | 140 | 19-Dec-24 A | 2026-03-02 | 21-Jun-25 A | 2026-02-20 | 2026-03-02
| A9940 | Technical Data Sheet For 11KV Switchgear_RCC |  | 2026-02-20 |  |  | 16 | 10-Jan-25 A | 2026-03-02 | 14-Feb-25 A | 2026-02-20 | 2026-03-02
| A47640 | Technical Data Sheet For 11KV Switchgear_IFA |  | 2026-02-20 |  |  | 3 | 15-Feb-25 A | 2026-03-02 | 21-Mar-25 A | 2026-02-20 | 2026-03-02
| A9960 | Technical Data Sheet For 11KV Switchgear_RCA |  | 2026-02-20 |  |  | 16 | 22-Mar-25 A | 2026-03-02 | 02-Jun-25 A | 2026-02-20 | 2026-03-02
| A9970 | Technical Data Sheet For 11KV Switchgear_IFD/IFC |  | 2026-02-20 |  |  | 2 | 03-Jun-25 A | 2026-03-02 | 21-Jun-25 A | 2026-02-20 | 2026-03-02
| Technical Data Sheet For LV Switchgear |  |  | 2026-02-20 |  |  | 127 | 27-Dec-24 A | 2026-03-02 | 11-May-25 A | 2026-02-20 | 2026-03-02
| A9990 | Technical Data Sheet For LV Switchgear_RCC |  | 2026-02-20 |  |  | 16 | 18-Jan-25 A | 2026-03-02 | 20-Apr-25 A | 2026-02-20 | 2026-03-02
| A10000 | Technical Data Sheet For LV Switchgear_IFA |  | 2026-02-20 |  |  | 3 | 21-Apr-25 A | 2026-03-02 | 27-Apr-25 A | 2026-02-20 | 2026-03-02
| A10010 | Technical Data Sheet For LV Switchgear_RCA |  | 2026-02-20 |  |  | 16 | 28-Apr-25 A | 2026-03-02 | 04-May-25 A | 2026-02-20 | 2026-03-02
| A10020 | Technical Data Sheet For LV Switchgear_IFD/IFC |  | 2026-02-20 |  |  | 2 | 06-May-25 A | 2026-03-02 | 11-May-25 A | 2026-02-20 | 2026-03-02
| Technical Data Sheet For LV Variable Frequency Drive |  |  | 2026-02-20 |  |  | 145 | 31-Jan-25 A | 2026-03-02 | 05-Jul-25 A | 2026-02-20 | 2026-03-02
| A10040 | Technical Data Sheet For LV Variable Frequency Drive_RCC |  | 2026-02-20 |  |  | 16 | 22-Feb-25 A | 2026-03-02 | 20-Apr-25 A | 2026-02-20 | 2026-03-02
| A10050 | Technical Data Sheet For LV Variable Frequency Drive_IFA |  | 2026-02-20 |  |  | 3 | 21-Apr-25 A | 2026-03-02 | 21-Jun-25 A | 2026-02-20 | 2026-03-02
| A10060 | Technical Data Sheet For LV Variable Frequency Drive_RCA |  | 2026-02-20 |  |  | 16 | 22-Jun-25 A | 2026-03-02 | 28-Jun-25 A | 2026-02-20 | 2026-03-02
| A10070 | Technical Data Sheet For LV Variable Frequency Drive_IFD/IFC |  | 2026-02-20 |  |  | 2 | 29-Jun-25 A | 2026-03-02 | 05-Jul-25 A | 2026-02-20 | 2026-03-02
| Technical Data Sheet For Neutral Earthing Resistor |  |  | 2026-02-20 |  |  | 133 | 19-Dec-24 A | 2026-03-02 | 21-Jun-25 A | 2026-02-20 | 2026-03-02
| A10090 | Technical Data Sheet For Neutral Earthing Resistor_RCC |  | 2026-02-20 |  |  | 16 | 10-Jan-25 A | 2026-03-02 | 21-Feb-25 A | 2026-02-20 | 2026-03-02
| A10100 | Technical Data Sheet For Neutral Earthing Resistor_IFA |  | 2026-02-20 |  |  | 3 | 22-Feb-25 A | 2026-03-02 | 06-Mar-25 A | 2026-02-20 | 2026-03-02
| A10110 | Technical Data Sheet For Neutral Earthing Resistor_RCA |  | 2026-02-20 |  |  | 16 | 07-Mar-25 A | 2026-03-02 | 29-May-25 A | 2026-02-20 | 2026-03-02
| A10120 | Technical Data Sheet For Neutral Earthing Resistor_IFD/IFC |  | 2026-02-20 |  |  | 2 | 30-May-25 A | 2026-03-02 | 21-Jun-25 A | 2026-02-20 | 2026-03-02
| Technical Data Sheet For Interposting Relay Panel |  |  | 2026-02-20 |  |  | 39 | 01-Aug-25 A | 2026-04-28 | 17-Sep-25 A | 2026-02-20 | 2027-01-20
| A58240 | Technical Data Sheet For Interpopsting Relay Panel _IFR |  | 2026-02-20 |  |  | 2 | 01-Aug-25 A | 2026-04-28 | 08-Aug-25 A | 2026-02-20 | 2026-04-28
| A58250 | Technical Data Sheet For Interpopsting Relay Panel_RCC |  | 2026-02-20 |  |  | 16 | 11-Aug-25 A | 2027-01-20 | 22-Aug-25 A | 2026-02-20 | 2027-01-20
| A58260 | Technical Data Sheet For Interpopsting Relay Panel_IFA |  | 2026-02-20 |  |  | 3 | 25-Aug-25 A | 2027-01-20 | 29-Aug-25 A | 2026-02-20 | 2027-01-20
| A58270 | Technical Data Sheet For Interpopsting Relay Panel_RCA |  | 2026-02-20 |  |  | 16 | 01-Sep-25 A | 2027-01-20 | 12-Sep-25 A | 2026-02-20 | 2027-01-20
| A58280 | Technical Data Sheet For Interpopsting Relay Panel_IFD/IFC |  | 2026-02-20 |  |  | 2 | 15-Sep-25 A | 2027-01-20 | 17-Sep-25 A | 2026-02-20 | 2027-01-20
| Technical Data Sheet For Power, Control And Earthing Cables |  |  | 2026-02-20 |  |  | 201 | 10-Jan-25 A | 2026-03-19 | 05-Sep-25 A | 2026-02-20 | 2026-03-19
| A10140 | Technical Data Sheet For Power, Control And Earthing Cables_RCC |  | 2026-02-20 |  |  | 16 | 21-Apr-25 A | 2026-03-19 | 19-May-25 A | 2026-02-20 | 2026-03-19
| A10150 | Technical Data Sheet For Power, Control And Earthing Cables_IFA |  | 2026-02-20 |  |  | 3 | 20-May-25 A | 2026-03-19 | 11-Jun-25 A | 2026-02-20 | 2026-03-19
| A10160 | Technical Data Sheet For Power, Control And Earthing Cables_RCA |  | 2026-02-20 |  |  | 16 | 25-Aug-25 A | 2026-03-19 | 29-Aug-25 A | 2026-02-20 | 2026-03-19
| A10170 | Technical Data Sheet For Power, Control And Earthing Cables_IFD/IFC |  | 2026-02-20 |  |  | 2 | 01-Sep-25 A | 2026-03-19 | 05-Sep-25 A | 2026-02-20 | 2026-03-19
| Technical Data Sheet For Direct Current UPS System |  |  | 2026-02-20 |  |  | 103 | 01-Jan-25 A | 2026-03-02 | 21-Jun-25 A | 2026-02-20 | 2026-03-02
| A10190 | Technical Data Sheet For Direct Current UPS System_RCC |  | 2026-02-20 |  |  | 16 | 23-Jan-25 A | 2026-03-02 | 07-Mar-25 A | 2026-02-20 | 2026-03-02
| A10200 | Technical Data Sheet For Direct Current UPS System_IFA |  | 2026-02-20 |  |  | 3 | 08-Mar-25 A | 2026-03-02 | 21-Mar-25 A | 2026-02-20 | 2026-03-02
| A10210 | Technical Data Sheet For Direct Current UPS System_RCA |  | 2026-02-20 |  |  | 16 | 22-Mar-25 A | 2026-03-02 | 02-Jun-25 A | 2026-02-20 | 2026-03-02
| A10220 | Technical Data Sheet For Direct Current UPS System_IFD/IFC |  | 2026-02-20 |  |  | 2 | 03-Jun-25 A | 2026-03-02 | 21-Jun-25 A | 2026-02-20 | 2026-03-02
| Technical Data Sheet For Static AC UPS System |  |  | 2026-02-20 |  |  | 27 | 27-Dec-24 A | 2026-03-02 | 28-Jun-25 A | 2026-02-20 | 2026-03-02
| A10240 | Technical Data Sheet For Static AC UPS System_RCC |  | 2026-02-20 |  |  | 16 | 18-Jan-25 A | 2026-03-02 | 18-Feb-25 A | 2026-02-20 | 2026-03-02
| A10250 | Technical Data Sheet For Static AC UPS System_IFA |  | 2026-02-20 |  |  | 3 | 19-Feb-25 A | 2026-03-02 | 12-Jun-25 A | 2026-02-20 | 2026-03-02
| A10260 | Technical Data Sheet For Static AC UPS System_RCA |  | 2026-02-20 |  |  | 16 | 13-Jun-25 A | 2026-03-02 | 21-Jun-25 A | 2026-02-20 | 2026-03-02
| A10270 | Technical Data Sheet For Static AC UPS System_IFD/IFC |  | 2026-02-20 |  |  | 2 | 22-Jun-25 A | 2026-03-02 | 28-Jun-25 A | 2026-02-20 | 2026-03-02
| Technical Data Sheet For Power Factor Correction Capacitor |  |  | 2026-02-20 |  |  | 191 | 20-Jan-25 A | 2026-03-02 | 28-Aug-25 A | 2026-02-20 | 2026-03-02
| A10290 | Technical Data Sheet For Power Factor Correction Capacitor_RCC |  | 2026-02-20 |  |  | 16 | 19-Jul-25 A | 2026-03-02 | 08-Aug-25 A | 2026-02-20 | 2026-03-02
| A10300 | Technical Data Sheet For Power Factor Correction Capacitor_IFA |  | 2026-02-20 |  |  | 3 | 09-Aug-25 A | 2026-03-02 | 12-Aug-25 A | 2026-02-20 | 2026-03-02
| A10310 | Technical Data Sheet For Power Factor Correction Capacitor_RCA |  | 2026-02-20 |  |  | 16 | 12-Aug-25 A | 2026-03-02 | 26-Aug-25 A | 2026-02-20 | 2026-03-02
| A10320 | Technical Data Sheet For Power Factor Correction Capacitor_IFD/IFC |  | 2026-02-20 |  |  | 2 | 26-Aug-25 A | 2026-03-02 | 28-Aug-25 A | 2026-02-20 | 2026-03-02
| Neutral Earthing Resistor Sizing Calculation |  |  | 2026-02-20 |  |  | 134 | 13-Dec-24 A | 2026-04-02 | 13-May-25 A | 2026-02-20 | 2027-01-20
| A10390 | Neutral Earthing Resistor Sizing Calculation_RCC |  | 2026-02-20 |  |  | 16 | 10-Jan-25 A | 2027-01-20 | 21-Feb-25 A | 2026-02-20 | 2027-01-20
| A10400 | Neutral Earthing Resistor Sizing Calculation_IFA |  | 2026-02-20 |  |  | 3 | 22-Feb-25 A | 2027-01-20 | 12-Mar-25 A | 2026-02-20 | 2027-01-20
| A10410 | Neutral Earthing Resistor Sizing Calculation_RCA |  | 2026-02-20 |  |  | 16 | 13-Mar-25 A | 2027-01-20 | 06-May-25 A | 2026-02-20 | 2027-01-20
| A10420 | Neutral Earthing Resistor Sizing Calculation_IFD/IFC |  | 2026-02-20 |  |  | 2 | 07-May-25 A | 2027-01-20 | 13-May-25 A | 2026-02-20 | 2027-01-20
| Interposting Relay Panel Sizing Calculation |  |  | 2026-02-20 |  |  | 43 | 2026-02-20 | 2026-05-14 | 2026-04-21 | 2026-04-21 | 2027-01-20 | 196
| A58290 | Interpopsting Relay Panel Sizing Calculation_IFR |  | 2026-02-20 |  |  | 6 | 2026-02-20 | 2026-05-14 | 2026-02-27 | 2026-02-27 | 2026-05-22 | 60
| A58300 | Interpopsting Relay Panel Sizing Calculation_RCC |  | 2026-02-27 |  |  | 16 | 2026-02-27 | 2026-05-22 | 2026-03-23 | 2026-03-23 | 2026-06-15 | 60
| A58310 | Interpopsting Relay Panel Sizing Calculation_IFA |  | 2026-03-23 |  |  | 3 | 2026-03-23 | 2026-06-15 | 2026-03-26 | 2026-03-26 | 2026-06-18 | 60
| A58320 | Interpopsting Relay Panel Sizing Calculation_RCA |  | 2026-03-26 |  |  | 16 | 2026-03-26 | 2026-12-28 | 2026-04-17 | 2026-04-17 | 2027-01-18 | 196
| A58330 | Interpopsting Relay Panel Sizing Calculation_IFD/IFC |  | 2026-04-17 |  |  | 2 | 2026-04-17 | 2027-01-18 | 2026-04-21 | 2026-04-21 | 2027-01-20 | 196
| Transformer Sizing Calculation |  |  | 2026-02-20 |  |  | 151 | 29-Mar-25 A | 2026-03-02 | 28-Jun-25 A | 2026-02-20 | 2027-01-20
| A10680 | Transformer Sizing Calculation_IFR |  | 2026-02-20 |  |  | 6 | 29-Mar-25 A | 2026-03-02 | 06-Apr-25 A | 2026-02-20 | 2026-03-02
| A10690 | Transformer Sizing Calculation_RCC |  | 2026-02-20 |  |  | 16 | 30-Mar-25 A | 2027-01-20 | 13-Apr-25 A | 2026-02-20 | 2027-01-20
| A10700 | Transformer Sizing Calculation_IFA |  | 2026-02-20 |  |  | 3 | 14-Apr-25 A | 2027-01-20 | 20-Apr-25 A | 2026-02-20 | 2027-01-20
| A10710 | Transformer Sizing Calculation_RCA |  | 2026-02-20 |  |  | 16 | 21-Apr-25 A | 2027-01-20 | 21-Jun-25 A | 2026-02-20 | 2027-01-20
| A10720 | Transformer Sizing Calculation_IFD/IFC |  | 2026-02-20 |  |  | 2 | 22-Jun-25 A | 2027-01-20 | 28-Jun-25 A | 2026-02-20 | 2027-01-20
| Electrical Load List - EU3 H2 Extraction Unit |  |  | 2026-02-20 |  |  | 227 | 19-Dec-24 A | 2026-03-02 | 30-Apr-25 A | 2026-02-20 | 2026-03-27
| A10330 | Electrical Load List - EU3 H2 Extraction Unit_IFR |  | 2026-02-20 |  |  | 6 | 19-Dec-24 A | 2026-03-02 | 09-Jan-25 A | 2026-02-20 | 2026-03-02
| A10340 | Electrical Load List - EU3 H2 Extraction Unit_RCC |  | 2026-02-20 |  |  | 16 | 10-Jan-25 A | 2026-03-02 | 18-Feb-25 A | 2026-02-20 | 2026-03-02
| A10350 | Electrical Load List - EU3 H2 Extraction Unit_IFA |  | 2026-02-20 |  |  | 3 | 25-Feb-25 A | 2026-03-27 | 13-Mar-25 A | 2026-02-20 | 2026-03-27
| A10360 | Electrical Load List - EU3 H2 Extraction Unit_RCA |  | 2026-02-20 |  |  | 16 | 14-Mar-25 A | 2026-03-27 | 29-Apr-25 A | 2026-02-20 | 2026-03-27
| A10370 | Electrical Load List - EU3 H2 Extraction Unit_IFD/IFC |  | 2026-02-20 |  |  | 2 | 30-Apr-25 A | 2026-03-27 | 30-Apr-25 A | 2026-02-20 | 2026-03-27
| Electrical Load Summary for Utilities & Offsites Area |  |  | 2026-02-20 |  |  | 280 | 14-Feb-25 A | 2026-03-27 | 19-Jan-26 A | 2026-02-20 | 2026-03-27
| A55800 | Electrical Load Summary for Utilities & Offsites Area_RCC |  | 2026-02-20 |  |  | 16 | 30-Sep-25 A | 2026-03-27 | 16-Oct-25 A | 2026-02-20 | 2026-03-27
| A55810 | Electrical Load Summary for Utilities & Offsites Area_IFA |  | 2026-02-20 |  |  | 3 | 19-Dec-25 A | 2026-03-27 | 24-Dec-25 A | 2026-02-20 | 2026-03-27
| A55820 | Electrical Load Summary for Utilities & Offsites Area_RCA |  | 2026-02-20 |  |  | 16 | 24-Dec-25 A | 2026-03-27 | 15-Jan-26 A | 2026-02-20 | 2026-03-27
| A28320 | Electrical Load Summary for Utilities & Offsites Area_IFD/IFC |  | 2026-02-20 |  |  | 2 | 15-Jan-26 A | 2026-03-27 | 19-Jan-26 A | 2026-02-20 | 2026-03-27
| AC UPS Sizing Calculation |  |  | 2026-02-20 |  |  | 266 | 01-Aug-25 A | 2026-04-02 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| A10930 | AC UPS Sizing Calculation_IFR |  | 2026-02-20 |  |  | 6 | 01-Aug-25 A | 2026-04-02 | 15-Aug-25 A | 2026-02-20 | 2026-04-02
| A10940 | AC UPS Sizing Calculation_RCC |  | 2026-02-20 |  |  | 16 | 04-Aug-25 A | 2027-01-20 | 22-Aug-25 A | 2026-02-20 | 2027-01-20
| A10950 | AC UPS Sizing Calculation_IFA |  | 2026-02-20 |  |  | 3 | 17-Sep-25 A | 2027-01-20 | 09-Oct-25 A | 2026-02-20 | 2027-01-20
| A10960 | AC UPS Sizing Calculation_RCA |  | 2026-02-20 |  |  | 16 | 24-Sep-25 A | 2027-01-20 | 16-Oct-25 A | 2026-02-20 | 2027-01-20
| A10970 | AC UPS Sizing Calculation_IFD/IFC |  | 2026-02-20 |  |  | 2 | 19-Dec-25 A | 2027-01-20 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| DC UPS Sizing Calculation |  |  | 2026-02-20 |  |  | 261 | 30-Mar-25 A | 2026-04-02 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| A10980 | DC UPS Sizing Calculation_IFR |  | 2026-02-20 |  |  | 6 | 30-Mar-25 A | 2026-04-02 | 13-Apr-25 A | 2026-02-20 | 2026-04-02
| A10990 | DC UPS Sizing Calculation_RCC |  | 2026-02-20 |  |  | 16 | 01-Apr-25 A | 2027-01-20 | 20-Apr-25 A | 2026-02-20 | 2027-01-20
| A11000 | DC UPS Sizing Calculation_IFA |  | 2026-02-20 |  |  | 3 | 21-Apr-25 A | 2027-01-20 | 27-Apr-25 A | 2026-02-20 | 2027-01-20
| A11010 | DC UPS Sizing Calculation_RCA |  | 2026-02-20 |  |  | 16 | 15-May-25 A | 2027-01-20 | 21-Jun-25 A | 2026-02-20 | 2027-01-20
| A11020 | DC UPS Sizing Calculation_IFD/IFC |  | 2026-02-20 |  |  | 2 | 19-Dec-25 A | 2027-01-20 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| EDG Sizing Calculation |  |  | 2026-02-20 |  |  | 166 | 19-Dec-24 A | 2026-03-02 | 28-Jun-25 A | 2026-02-20 | 2027-01-20
| A11030 | EDG Sizing Calculation_IFR |  | 2026-02-20 |  |  | 6 | 19-Dec-24 A | 2026-03-02 | 09-Jan-25 A | 2026-02-20 | 2026-03-02
| A11040 | EDG Sizing Calculation_RCC |  | 2026-02-20 |  |  | 16 | 10-Jan-25 A | 2027-01-20 | 20-Feb-25 A | 2026-02-20 | 2027-01-20
| A11050 | EDG Sizing Calculation_IFA |  | 2026-02-20 |  |  | 3 | 21-Feb-25 A | 2027-01-20 | 20-Apr-25 A | 2026-02-20 | 2027-01-20
| A11060 | EDG Sizing Calculation_RCA |  | 2026-02-20 |  |  | 16 | 21-Apr-25 A | 2027-01-20 | 21-Jun-25 A | 2026-02-20 | 2027-01-20
| A11070 | EDG Sizing Calculation_IFD/IFC |  | 2026-02-20 |  |  | 2 | 22-Jun-25 A | 2027-01-20 | 28-Jun-25 A | 2026-02-20 | 2027-01-20
| IO List For IPCS |  |  | 2026-02-20 |  |  | 192 | 29-Mar-25 A | 2027-01-20 | 18-Sep-25 A | 2026-02-20 | 2027-01-20
| A11080 | IO List For IPCS_IFR |  | 2026-02-20 |  |  | 6 | 29-Mar-25 A | 2027-01-20 | 06-Apr-25 A | 2026-02-20 | 2027-01-20
| A11090 | IO List For IPCS_RCC |  | 2026-02-20 |  |  | 16 | 01-Apr-25 A | 2027-01-20 | 13-Apr-25 A | 2026-02-20 | 2027-01-20
| A11100 | IO List For IPCS_IFA |  | 2026-02-20 |  |  | 3 | 14-Apr-25 A | 2027-01-20 | 20-Apr-25 A | 2026-02-20 | 2027-01-20
| A11110 | IO List For IPCS_RCA |  | 2026-02-20 |  |  | 16 | 30-Apr-25 A | 2027-01-20 | 21-Jun-25 A | 2026-02-20 | 2027-01-20
| A11120 | IO List For IPCS_IFD/IFC |  | 2026-02-20 |  |  | 2 | 22-Jun-25 A | 2027-01-20 | 18-Sep-25 A | 2026-02-20 | 2027-01-20
| IO List For SCMS |  |  | 2026-02-20 |  |  | 192 | 24-Jan-25 A | 2027-01-20 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| A11140 | IO List For SCMS_RCC |  | 2026-02-20 |  |  | 16 | 25-Feb-25 A | 2027-01-20 | 20-Apr-25 A | 2026-02-20 | 2027-01-20
| A11150 | IO List For SCMS_IFA |  | 2026-02-20 |  |  | 3 | 21-Apr-25 A | 2027-01-20 | 27-Apr-25 A | 2026-02-20 | 2027-01-20
| A11160 | IO List For SCMS_RCA |  | 2026-02-20 |  |  | 16 | 21-Apr-25 A | 2027-01-20 | 21-Jun-25 A | 2026-02-20 | 2027-01-20
| A11170 | IO List For SCMS_IFD/IFC |  | 2026-02-20 |  |  | 2 | 22-Jun-25 A | 2027-01-20 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| Power System Study Report - ARC Flash, Harmonics Resonance |  |  | 2026-02-20 |  |  | 112 | 18-Jul-25 A | 2026-03-02 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| A11240 | Power System Study Report - ARC Flash, Harmonics Resonance_RCC |  | 2026-02-20 |  |  | 16 | 12-Aug-25 A | 2027-01-20 | 28-Aug-25 A | 2026-02-20 | 2027-01-20
| A11250 | Power System Study Report - ARC Flash, Harmonics Resonance_IFA |  | 2026-02-20 |  |  | 3 | 04-Sep-25 A | 2027-01-20 | 10-Oct-25 A | 2026-02-20 | 2027-01-20
| A11260 | Power System Study Report - ARC Flash, Harmonics Resonance_RCA |  | 2026-02-20 |  |  | 16 | 20-Sep-25 A | 2027-01-20 | 17-Oct-25 A | 2026-02-20 | 2027-01-20
| A11270 | Power System Study Report - ARC Flash, Harmonics Resonance_IFD/IFC |  | 2026-02-20 |  |  | 2 | 19-Dec-25 A | 2027-01-20 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| Power System Study Report - Load Flow, Short Circuit and Motor Starting |  |  | 2026-02-20 |  |  | 165 | 28-Apr-25 A | 2026-03-02 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| A11190 | Power System Study Report - Load Flow, Short Circuit and Motor Starting_RCC |  | 2026-02-20 |  |  | 16 | 25-Jun-25 A | 2027-01-20 | 25-Jul-25 A | 2026-02-20 | 2027-01-20
| A11200 | Power System Study Report - Load Flow, Short Circuit and Motor Starting_IFA |  | 2026-02-20 |  |  | 3 | 26-Jul-25 A | 2027-01-20 | 28-Aug-25 A | 2026-02-20 | 2027-01-20
| A11210 | Power System Study Report - Load Flow, Short Circuit and Motor Starting_RCA |  | 2026-02-20 |  |  | 16 | 20-Aug-25 A | 2027-01-20 | 04-Sep-25 A | 2026-02-20 | 2027-01-20
| A11220 | Power System Study Report - Load Flow, Short Circuit and Motor Starting_IFD/IFC |  | 2026-02-20 |  |  | 2 | 19-Dec-25 A | 2027-01-20 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| PSCAD Study Report - Transient Stability And Insulation Coordination |  |  | 2026-02-20 |  |  | 160 | 01-May-25 A | 2026-11-23 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| A11290 | Pscad Study Report - Transient Stability And Insulation Coordination_RCC |  | 2026-02-20 |  |  | 16 | 11-Jun-25 A | 2027-01-20 | 25-Jul-25 A | 2026-02-20 | 2027-01-20
| A11300 | Pscad Study Report - Transient Stability And Insulation Coordination_IFA |  | 2026-02-20 |  |  | 3 | 31-Jul-25 A | 2027-01-20 | 26-Sep-25 A | 2026-02-20 | 2027-01-20
| A11310 | Pscad Study Report - Transient Stability And Insulation Coordination_RCA |  | 2026-02-20 |  |  | 16 | 10-Sep-25 A | 2027-01-20 | 03-Oct-25 A | 2026-02-20 | 2027-01-20
| A11320 | Pscad Study Report - Transient Stability And Insulation Coordination_IFD/IFC |  | 2026-02-20 |  |  | 2 | 19-Dec-25 A | 2027-01-20 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| Power System Study Report - Protection Coordination and Relay Setting |  |  | 2026-02-20 |  |  | 43 | 2026-02-20 | 2026-11-23 | 2026-04-21 | 2026-04-21 | 2027-01-20 | 196
| A11330 | Power System Study Report - Protection Coordination and Relay Setting_IFR |  | 2026-02-20 |  |  | 6 | 2026-02-20 | 2026-11-23 | 2026-02-27 | 2026-02-27 | 2026-11-30 | 196
| A11340 | Power System Study Report - Protection Coordination and Relay Setting_RCC |  | 2026-02-27 |  |  | 16 | 2026-02-27 | 2026-11-30 | 2026-03-23 | 2026-03-23 | 2026-12-22 | 196
| A11350 | Power System Study Report - Protection Coordination and Relay Setting_IFA |  | 2026-03-23 |  |  | 3 | 2026-03-23 | 2026-12-22 | 2026-03-26 | 2026-03-26 | 2026-12-25 | 196
| A11360 | Power System Study Report - Protection Coordination and Relay Setting_RCA |  | 2026-03-26 |  |  | 16 | 2026-03-26 | 2026-12-28 | 2026-04-17 | 2026-04-17 | 2027-01-18 | 196
| A11370 | Power System Study Report - Protection Coordination and Relay Setting_IFD/IFC |  | 2026-04-17 |  |  | 2 | 2026-04-17 | 2027-01-18 | 2026-04-21 | 2026-04-21 | 2027-01-20 | 196
| Material Requisition For Transformer (Power And Distribution) |  |  | 2026-02-20 |  |  | 146 | 19-Dec-24 A | 2026-03-02 | 28-Jun-25 A | 2026-02-20 | 2026-03-02
| A12440 | Material Requisition For Transformer (Power And Distribution)_RCC |  | 2026-02-20 |  |  | 16 | 10-Jan-25 A | 2026-03-02 | 18-Feb-25 A | 2026-02-20 | 2026-03-02
| A12450 | Material Requisition For Transformer (Power And Distribution)_IFA |  | 2026-02-20 |  |  | 3 | 19-Feb-25 A | 2026-03-02 | 21-Mar-25 A | 2026-02-20 | 2026-03-02
| A12460 | Material Requisition For Transformer (Power And Distribution)_RCA |  | 2026-02-20 |  |  | 16 | 22-Mar-25 A | 2026-03-02 | 21-Jun-25 A | 2026-02-20 | 2026-03-02
| A12470 | Material Requisition For Transformer (Power And Distribution)_IFD/IFC |  | 2026-02-20 |  |  | 2 | 22-Jun-25 A | 2026-03-02 | 28-Jun-25 A | 2026-02-20 | 2026-03-02
| Material Requisition For 11KV Switchgear |  |  | 2026-02-20 |  |  | 120 | 13-Feb-25 A | 2026-03-02 | 12-May-25 A | 2026-02-20 | 2026-03-02
| A12490 | Material Requisition For 11KV Switchgear_RCC |  | 2026-02-20 |  |  | 16 | 07-Mar-25 A | 2026-03-02 | 21-Apr-25 A | 2026-02-20 | 2026-03-02
| A12500 | Material Requisition For 11KV Switchgear_IFA |  | 2026-02-20 |  |  | 3 | 22-Apr-25 A | 2026-03-02 | 28-Apr-25 A | 2026-02-20 | 2026-03-02
| A12510 | Material Requisition For 11KV Switchgear_RCA |  | 2026-02-20 |  |  | 16 | 29-Apr-25 A | 2026-03-02 | 05-May-25 A | 2026-02-20 | 2026-03-02
| A12520 | Material Requisition For 11KV Switchgear_IFD/IFC |  | 2026-02-20 |  |  | 2 | 06-May-25 A | 2026-03-02 | 12-May-25 A | 2026-02-20 | 2026-03-02
| Material Requisition For LV Switchgear |  |  | 2026-02-20 |  |  | 195 | 20-Jan-25 A | 2026-03-02 | 11-Jul-25 A | 2026-02-20 | 2026-03-02
| A12540 | Material Requisition For LV Switchgear_RCC |  | 2026-02-20 |  |  | 16 | 01-Mar-25 A | 2026-03-02 | 06-May-25 A | 2026-02-20 | 2026-03-02
| A12550 | Material Requisition For LV Switchgear_IFA |  | 2026-02-20 |  |  | 3 | 07-May-25 A | 2026-03-02 | 21-Jun-25 A | 2026-02-20 | 2026-03-02
| A12560 | Material Requisition For LV Switchgear_RCA |  | 2026-02-20 |  |  | 16 | 23-Jun-25 A | 2026-03-02 | 04-Jul-25 A | 2026-02-20 | 2026-03-02
| A12570 | Material Requisition For LV Switchgear_IFD/IFC |  | 2026-02-20 |  |  | 2 | 07-Jul-25 A | 2026-03-02 | 11-Jul-25 A | 2026-02-20 | 2026-03-02
| Material Requisition For Capacitor Bank |  |  | 2026-02-20 |  |  | 173 | 03-Mar-25 A | 2026-03-02 | 04-Sep-25 A | 2026-02-20 | 2026-03-02
| A12580 | Material Requisition For Capacitor Bank_IFR |  | 2026-02-20 |  |  | 6 | 03-Mar-25 A | 2026-03-02 | 27-Apr-25 A | 2026-02-20 | 2026-03-02
| A12590 | Material Requisition For Capacitor Bank_RCC |  | 2026-02-20 |  |  | 16 | 28-Apr-25 A | 2026-03-02 | 04-May-25 A | 2026-02-20 | 2026-03-02
| A12600 | Material Requisition For Capacitor Bank_IFA |  | 2026-02-20 |  |  | 3 | 05-May-25 A | 2026-03-02 | 21-Jun-25 A | 2026-02-20 | 2026-03-02
| A12610 | Material Requisition For Capacitor Bank_RCA |  | 2026-02-20 |  |  | 16 | 22-Jun-25 A | 2026-03-02 | 28-Aug-25 A | 2026-02-20 | 2026-03-02
| A12620 | Material Requisition For Capacitor Bank_IFD/IFC |  | 2026-02-20 |  |  | 2 | 29-Aug-25 A | 2026-03-02 | 04-Sep-25 A | 2026-02-20 | 2026-03-02
| Material Requisition For Power, Control And Earthing Cables |  |  | 2026-02-20 |  |  | 118 | 22-Apr-25 A | 2026-03-19 | 2026-02-20 | 2026-02-20 | 2026-03-19 | 20
| A12640 | Material Requisition For Power, Control And Earthing Cables_RCC |  | 2026-02-20 |  |  | 16 | 26-May-25 A | 2026-03-19 | 31-Jul-25 A | 2026-02-20 | 2026-03-19
| A12650 | Material Requisition For Power, Control And Earthing Cables_IFA |  | 2026-02-20 |  |  | 3 | 01-Aug-25 A | 2026-03-19 | 20-Aug-25 A | 2026-02-20 | 2026-03-19
| A12660 | Material Requisition For Power, Control And Earthing Cables_RCA |  | 2026-02-20 |  |  | 16 | 15-Sep-25 A | 2026-03-19 | 15-Oct-25 A | 2026-02-20 | 2026-03-19
| A12670 | Material Requisition For Power, Control And Earthing Cables_IFD/IFC |  | 2026-02-20 |  |  | 2 | 20-Sep-25 A | 2026-03-19 | 2026-02-20 | 2026-02-20 | 2026-03-19 | 20
| Material Requisition For Emergency Diesel Generator |  |  | 2026-02-20 |  |  | 144 | 01-Jan-25 A | 2026-03-02 | 28-Jun-25 A | 2026-02-20 | 2026-03-02
| A12690 | Material Requisition For Emergency Diesel Generator_RCC |  | 2026-02-20 |  |  | 16 | 23-Jan-25 A | 2026-03-02 | 07-Mar-25 A | 2026-02-20 | 2026-03-02
| A12700 | Material Requisition For Emergency Diesel Generator_IFA |  | 2026-02-20 |  |  | 3 | 08-Mar-25 A | 2026-03-02 | 20-Apr-25 A | 2026-02-20 | 2026-03-02
| A12710 | Material Requisition For Emergency Diesel Generator_RCA |  | 2026-02-20 |  |  | 16 | 21-Apr-25 A | 2026-03-02 | 21-Jun-25 A | 2026-02-20 | 2026-03-02
| A12720 | Material Requisition For Emergency Diesel Generator_IFD/IFC |  | 2026-02-20 |  |  | 2 | 22-Jun-25 A | 2026-03-02 | 28-Jun-25 A | 2026-02-20 | 2026-03-02
| Material Requisition For AC UPS |  |  | 2026-02-20 |  |  | 172 | 01-Jan-25 A | 2026-03-02 | 30-Apr-25 A | 2026-02-20 | 2026-03-02
| A12740 | Material Requisition For AC UPS_RCC |  | 2026-02-20 |  |  | 16 | 25-Feb-25 A | 2026-03-02 | 07-Mar-25 A | 2026-02-20 | 2026-03-02
| A12750 | Material Requisition For AC UPS_IFA |  | 2026-02-20 |  |  | 3 | 10-Mar-25 A | 2026-03-02 | 21-Mar-25 A | 2026-02-20 | 2026-03-02
| A12760 | Material Requisition For AC UPS_RCA |  | 2026-02-20 |  |  | 16 | 24-Mar-25 A | 2026-03-02 | 04-Apr-25 A | 2026-02-20 | 2026-03-02
| A12770 | Material Requisition For AC UPS_IFD/IFC |  | 2026-02-20 |  |  | 2 | 07-Apr-25 A | 2026-03-02 | 30-Apr-25 A | 2026-02-20 | 2026-03-02
| Material Requisition For DC UPS |  |  | 2026-02-20 |  |  | 112 | 31-Jan-25 A | 2026-03-02 | 28-Jun-25 A | 2026-02-20 | 2026-03-02
| A12790 | Material Requisition For DC UPS_RCC |  | 2026-02-20 |  |  | 16 | 21-Feb-25 A | 2026-03-02 | 14-Mar-25 A | 2026-02-20 | 2026-03-02
| A12800 | Material Requisition For DC UPS_IFA |  | 2026-02-20 |  |  | 3 | 13-Mar-25 A | 2026-03-02 | 21-Mar-25 A | 2026-02-20 | 2026-03-02
| A12810 | Material Requisition For DC UPS_RCA |  | 2026-02-20 |  |  | 16 | 22-Mar-25 A | 2026-03-02 | 21-Jun-25 A | 2026-02-20 | 2026-03-02
| A12820 | Material Requisition For DC UPS_IFD/IFC |  | 2026-02-20 |  |  | 2 | 22-Jun-25 A | 2026-03-02 | 28-Jun-25 A | 2026-02-20 | 2026-03-02
| Material Requisition For LV Variable Frequency Drive |  |  | 2026-02-20 |  |  | 154 | 31-Jan-25 A | 2026-03-02 | 12-Jul-25 A | 2026-02-20 | 2026-03-02
| A12840 | Material Requisition For LV Variable Frequency Drive_RCC |  | 2026-02-20 |  |  | 16 | 22-Feb-25 A | 2026-03-02 | 21-Jun-25 A | 2026-02-20 | 2026-03-02
| A12850 | Material Requisition For LV Variable Frequency Drive_IFA |  | 2026-02-20 |  |  | 3 | 22-Jun-25 A | 2026-03-02 | 28-Jun-25 A | 2026-02-20 | 2026-03-02
| A12860 | Material Requisition For LV Variable Frequency Drive_RCA |  | 2026-02-20 |  |  | 16 | 27-Jun-25 A | 2026-03-02 | 05-Jul-25 A | 2026-02-20 | 2026-03-02
| A12870 | Material Requisition For LV Variable Frequency Drive_IFD/IFC |  | 2026-02-20 |  |  | 2 | 06-Jul-25 A | 2026-03-02 | 12-Jul-25 A | 2026-02-20 | 2026-03-02
| Material Requisition For Neutral Grounding Resistor |  |  | 2026-02-20 |  |  | 105 | 13-Dec-24 A | 2026-03-02 | 15-Oct-25 A | 2026-02-20 | 2026-03-02
| A12890 | Material Requisition For Neutral Grounding Resistor_RCC |  | 2026-02-20 |  |  | 16 | 08-Jan-25 A | 2026-03-02 | 10-Feb-25 A | 2026-02-20 | 2026-03-02
| A12900 | Material Requisition For Neutral Grounding Resistor_IFA |  | 2026-02-20 |  |  | 3 | 11-Feb-25 A | 2026-03-02 | 14-Mar-25 A | 2026-02-20 | 2026-03-02
| A12910 | Material Requisition For Neutral Grounding Resistor_RCA |  | 2026-02-20 |  |  | 16 | 15-Mar-25 A | 2026-03-02 | 06-May-25 A | 2026-02-20 | 2026-03-02
| A12920 | Material Requisition For Neutral Grounding Resistor_IFD/IFC |  | 2026-02-20 |  |  | 2 | 01-Sep-25 A | 2026-03-02 | 15-Oct-25 A | 2026-02-20 | 2026-03-02
| Material Requisition For Interposting Relay Panel |  |  | 2026-02-20 |  |  | 154 | 01-Sep-25 A | 2026-04-28 | 2026-04-27 | 2026-04-27 | 2026-07-17 | 60
| A58340 | Material Requisition For Interpopsting Relay Panel_IFR |  | 2026-02-20 |  |  | 6 | 01-Sep-25 A | 2026-04-28 | 05-Sep-25 A | 2026-02-20 | 2026-04-28
| A58350 | Material Requisition For Interpopsting Relay Panel_RCC |  | 2026-02-20 |  |  | 16 | 2026-02-20 | 2026-05-27 | 2026-03-13 | 2026-03-13 | 2026-06-18 | 69
| A58360 | Material Requisition For Interpopsting Relay Panel_IFA |  | 2026-03-26 |  |  | 3 | 2026-03-26 | 2026-06-18 | 2026-04-01 | 2026-04-01 | 2026-06-23 | 60
| A58370 | Material Requisition For Interpopsting Relay Panel_RCA |  | 2026-04-01 |  |  | 16 | 2026-04-01 | 2026-06-24 | 2026-04-22 | 2026-04-22 | 2026-07-15 | 60
| A58380 | Material Requisition For Interpopsting Relay Panel_IFD/IFC |  | 2026-04-22 |  |  | 2 | 2026-04-22 | 2026-07-15 | 2026-04-27 | 2026-04-27 | 2026-07-17 | 60
| Material Requisition For Integrated Protection Control Panel |  |  | 2026-02-20 |  |  | 36 | 19-Jul-25 A | 2026-05-04 | 04-Sep-25 A | 2026-02-20 | 2027-01-20
| A58140 | Material Requisition For IPCS_IFR |  | 2026-02-20 |  |  | 6 | 19-Jul-25 A | 2026-05-04 | 25-Jul-25 A | 2026-02-20 | 2026-05-04
| A58150 | Material Requisition For IPCS_RCC |  | 2026-02-20 |  |  | 16 | 26-Jul-25 A | 2027-01-20 | 14-Aug-25 A | 2026-02-20 | 2027-01-20
| A58160 | Material Requisition For IPCS_IFA |  | 2026-02-20 |  |  | 3 | 14-Aug-25 A | 2027-01-20 | 17-Aug-25 A | 2026-02-20 | 2027-01-20
| A58170 | Material Requisition For IPCS_RCA |  | 2026-02-20 |  |  | 16 | 17-Aug-25 A | 2027-01-20 | 30-Aug-25 A | 2026-02-20 | 2027-01-20
| A58180 | Material Requisition For IPCS_IFD/IFC |  | 2026-02-20 |  |  | 2 | 30-Aug-25 A | 2027-01-20 | 04-Sep-25 A | 2026-02-20 | 2027-01-20
| Material Requisition For SCMS |  |  | 2026-02-20 |  |  | 36 | 19-Jul-25 A | 2026-03-20 | 04-Sep-25 A | 2026-02-20 | 2026-03-20
| A59950 | Material Requisition For SCMS_IFR |  | 2026-02-20 |  |  | 6 | 19-Jul-25 A | 2026-03-20 | 25-Jul-25 A | 2026-02-20 | 2026-03-20
| A59960 | Material Requisition For SCMS_RCC |  | 2026-02-20 |  |  | 16 | 26-Jul-25 A | 2026-03-20 | 14-Aug-25 A | 2026-02-20 | 2026-03-20
| A59970 | Material Requisition For SCMS_IFA |  | 2026-02-20 |  |  | 3 | 14-Aug-25 A | 2026-03-20 | 17-Aug-25 A | 2026-02-20 | 2026-03-20
| A59980 | Material Requisition For SCMS_RCA |  | 2026-02-20 |  |  | 16 | 17-Aug-25 A | 2026-03-20 | 30-Aug-25 A | 2026-02-20 | 2026-03-20
| A59990 | Material Requisition For SCMS_IFD/IFC |  | 2026-02-20 |  |  | 2 | 30-Aug-25 A | 2026-03-20 | 04-Sep-25 A | 2026-02-20 | 2026-03-20
| Key Single Line Diagram - Hydrogen Extraction Unit |  |  | 2026-02-20 |  |  | 261 | 28-May-25 A | 2026-03-02 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| A11380 | Key Single Line Diagram - Hydrogen Extraction Unit_IFR |  | 2026-02-20 |  |  | 6 | 28-May-25 A | 2026-03-02 | 07-Jun-25 A | 2026-02-20 | 2026-03-02
| A11390 | Key Single Line Diagram - Hydrogen Extraction Unit_RCC |  | 2026-02-20 |  |  | 16 | 30-May-25 A | 2027-01-20 | 14-Jun-25 A | 2026-02-20 | 2027-01-20
| A11400 | Key Single Line Diagram - Hydrogen Extraction Unit_IFA |  | 2026-02-20 |  |  | 3 | 15-Jun-25 A | 2027-01-20 | 21-Jun-25 A | 2026-02-20 | 2027-01-20
| A11410 | Key Single Line Diagram - Hydrogen Extraction Unit_RCA |  | 2026-02-20 |  |  | 16 | 01-Jul-25 A | 2027-01-20 | 10-Sep-25 A | 2026-02-20 | 2027-01-20
| A11420 | Key Single Line Diagram - Hydrogen Extraction Unit_IFD/IFC |  | 2026-02-20 |  |  | 2 | 19-Dec-25 A | 2027-01-20 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| Single Line Diagram For Integrated Protection Control Panel |  |  | 2026-02-20 |  |  | 147 | 19-Aug-25 A | 2026-03-20 | 2026-04-14 | 2026-04-14 | 2027-01-01 | 189
| A58440 | Single Line Diagram For IPCS_IFR |  | 2026-02-20 |  |  | 6 | 19-Aug-25 A | 2026-03-20 | 25-Aug-25 A | 2026-02-20 | 2026-03-20
| A58450 | Single Line Diagram For IPCS_RCC |  | 2026-02-20 |  |  | 16 | 2026-02-20 | 2026-11-11 | 2026-03-13 | 2026-03-13 | 2026-12-03 | 189
| A58460 | Single Line Diagram For IPCS_IFA |  | 2026-03-13 |  |  | 3 | 2026-03-13 | 2026-12-03 | 2026-03-19 | 2026-03-19 | 2026-12-08 | 189
| A58470 | Single Line Diagram For IPCS_RCA |  | 2026-03-19 |  |  | 16 | 2026-03-19 | 2026-12-09 | 2026-04-09 | 2026-04-09 | 2026-12-30 | 189
| A58480 | Single Line Diagram For IPCS_IFD/IFC |  | 2026-04-09 |  |  | 2 | 2026-04-09 | 2026-12-30 | 2026-04-14 | 2026-04-14 | 2027-01-01 | 189
| Single Line Diagram For SCMS |  |  | 2026-02-20 |  |  | 147 | 19-Aug-25 A | 2026-03-20 | 2026-04-14 | 2026-04-14 | 2027-01-01 | 189
| A60000 | Single Line Diagram For SCMS_IFR |  | 2026-02-20 |  |  | 6 | 19-Aug-25 A | 2026-03-20 | 25-Aug-25 A | 2026-02-20 | 2026-03-20
| A60010 | Single Line Diagram For SCMS_RCC |  | 2026-02-20 |  |  | 16 | 2026-02-20 | 2026-11-11 | 2026-03-13 | 2026-03-13 | 2026-12-03 | 189
| A60020 | Single Line Diagram For SCMS_IFA |  | 2026-03-13 |  |  | 3 | 2026-03-13 | 2026-12-03 | 2026-03-19 | 2026-03-19 | 2026-12-08 | 189
| A60030 | Single Line Diagram For SCMS_RCA |  | 2026-03-19 |  |  | 16 | 2026-03-19 | 2026-12-09 | 2026-04-09 | 2026-04-09 | 2026-12-30 | 189
| A60040 | Single Line Diagram For SCMS_IFD/IFC |  | 2026-04-09 |  |  | 2 | 2026-04-09 | 2026-12-30 | 2026-04-14 | 2026-04-14 | 2027-01-01 | 189
| Single Line Diagram For 11KV Switchgear |  |  | 2026-02-20 |  |  | 224 | 31-Jan-25 A | 2026-03-02 | 23-Aug-25 A | 2026-02-20 | 2027-01-01
| A11540 | Single Line Diagram For 11KV Switchgear_RCC |  | 2026-02-20 |  |  | 16 | 22-Feb-25 A | 2027-01-01 | 20-Apr-25 A | 2026-02-20 | 2027-01-01
| A11550 | Single Line Diagram For 11KV Switchgear_IFA |  | 2026-02-20 |  |  | 3 | 21-Apr-25 A | 2027-01-01 | 27-Apr-25 A | 2026-02-20 | 2027-01-01
| A11560 | Single Line Diagram For 11KV Switchgear_RCA |  | 2026-02-20 |  |  | 16 | 28-Apr-25 A | 2027-01-01 | 21-Jun-25 A | 2026-02-20 | 2027-01-01
| A11570 | Single Line Diagram For 11KV Switchgear_IFD/IFC |  | 2026-02-20 |  |  | 2 | 22-Jun-25 A | 2027-01-01 | 23-Aug-25 A | 2026-02-20 | 2027-01-01
| Single Line Diagram For AC UPS |  |  | 2026-02-20 |  |  | 67 | 26-Aug-25 A | 2026-12-08 | 23-Dec-25 A | 2026-02-20 | 2027-01-01
| A11590 | Single Line Diagram For AC UPS_RCC |  | 2026-02-20 |  |  | 16 | 02-Sep-25 A | 2027-01-01 | 05-Sep-25 A | 2026-02-20 | 2027-01-01
| A11600 | Single Line Diagram For AC UPS_IFA |  | 2026-02-20 |  |  | 3 | 08-Sep-25 A | 2027-01-01 | 12-Sep-25 A | 2026-02-20 | 2027-01-01
| A11610 | Single Line Diagram For AC UPS_RCA |  | 2026-02-20 |  |  | 16 | 01-Nov-25 A | 2027-01-01 | 21-Nov-25 A | 2026-02-20 | 2027-01-01
| A11620 | Single Line Diagram For AC UPS_IFD/IFC |  | 2026-02-20 |  |  | 2 | 19-Dec-25 A | 2027-01-01 | 23-Dec-25 A | 2026-02-20 | 2027-01-01
| Single Line Diagram For DC UPS |  |  | 2026-02-20 |  |  | 248 | 03-Feb-25 A | 2026-12-08 | 25-Dec-25 A | 2026-02-20 | 2027-01-01
| A11640 | Single Line Diagram For DC UPS_RCC |  | 2026-02-20 |  |  | 16 | 25-Feb-25 A | 2026-12-08 | 18-Mar-25 A | 2026-02-20 | 2026-12-08
| A11650 | Single Line Diagram For DC UPS_IFA |  | 2026-02-20 |  |  | 3 | 19-Mar-25 A | 2027-01-01 | 29-Apr-25 A | 2026-02-20 | 2027-01-01
| A11660 | Single Line Diagram For DC UPS_RCA |  | 2026-02-20 |  |  | 16 | 30-Apr-25 A | 2027-01-01 | 02-Jun-25 A | 2026-02-20 | 2027-01-01
| A11670 | Single Line Diagram For DC UPS_IFD/IFC |  | 2026-02-20 |  |  | 2 | 23-Dec-25 A | 2027-01-01 | 25-Dec-25 A | 2026-02-20 | 2027-01-01
| Single Line Diagram For LV Switchgear |  |  | 2026-02-20 |  |  | 256 | 20-Jan-25 A | 2027-01-01 | 23-Dec-25 A | 2026-02-20 | 2027-01-01
| A11690 | Single Line Diagram For LV Switchgear_RCC |  | 2026-02-20 |  |  | 16 | 22-Feb-25 A | 2027-01-01 | 06-May-25 A | 2026-02-20 | 2027-01-01
| A11700 | Single Line Diagram For LV Switchgear_IFA |  | 2026-02-20 |  |  | 3 | 07-May-25 A | 2027-01-01 | 21-Jun-25 A | 2026-02-20 | 2027-01-01
| A11710 | Single Line Diagram For LV Switchgear_RCA |  | 2026-02-20 |  |  | 16 | 15-Jul-25 A | 2027-01-01 | 10-Sep-25 A | 2026-02-20 | 2027-01-01
| A11720 | Single Line Diagram For LV Switchgear_IFD/IFC |  | 2026-02-20 |  |  | 2 | 19-Dec-25 A | 2027-01-01 | 23-Dec-25 A | 2026-02-20 | 2027-01-01
| Single Line Diagram For Lighting And Small Power |  |  | 2026-02-20 |  |  | 38 | 28-Oct-25 A | 2026-12-08 | 2026-03-17 | 2026-03-17 | 2027-01-01 | 208
| A11730 | Single Line Diagram For Lighting And Small Power_IFR |  | 2026-02-20 |  |  | 6 | 28-Oct-25 A | 2026-12-08 | 05-Nov-25 A | 2026-02-20 | 2026-12-08
| A11740 | Single Line Diagram For Lighting And Small Power_RCC |  | 2026-02-20 |  |  | 16 | 05-Nov-25 A | 2026-12-08 | 14-Nov-25 A | 2026-02-20 | 2026-12-08
| A11750 | Single Line Diagram For Lighting And Small Power_IFA |  | 2026-02-20 |  |  | 3 | 23-Jan-26 A | 2026-12-08 | 2026-02-20 | 2026-02-20 | 2026-12-08 | 208
| A11760 | Single Line Diagram For Lighting And Small Power_RCA |  | 2026-02-20 |  |  | 16 | 2026-02-20 | 2026-12-09 | 2026-03-13 | 2026-03-13 | 2026-12-30 | 208
| A11770 | Single Line Diagram For Lighting And Small Power_IFD/IFC |  | 2026-03-13 |  |  | 2 | 2026-03-13 | 2026-12-30 | 2026-03-17 | 2026-03-17 | 2027-01-01 | 208
| One Line Diagram 220/33 KV Main Substation (Unit No-80) - Update |  |  | 2026-02-20 |  |  | 172 | 25-Mar-25 A | 2027-01-20 | 28-Jun-25 A | 2026-02-20 | 2027-01-20
| A28330 | One Line Diagram 220/33 KV Main Substation (Unit No-80) - Update_IFR |  | 2026-02-20 |  |  | 6 | 25-Mar-25 A | 2027-01-20 | 28-Apr-25 A | 2026-02-20 | 2027-01-20
| A55830 | One Line Diagram 220/33 KV Main Substation (Unit No-80) - Update_RCC |  | 2026-02-20 |  |  | 16 | 29-Apr-25 A | 2027-01-20 | 15-May-25 A | 2026-02-20 | 2027-01-20
| A55840 | One Line Diagram 220/33 KV Main Substation (Unit No-80) - Update_IFA |  | 2026-02-20 |  |  | 3 | 16-May-25 A | 2027-01-20 | 04-Jun-25 A | 2026-02-20 | 2027-01-20
| A55850 | One Line Diagram 220/33 KV Main Substation (Unit No-80) - Update_RCA |  | 2026-02-20 |  |  | 16 | 05-Jun-25 A | 2027-01-20 | 21-Jun-25 A | 2026-02-20 | 2027-01-20
| A55860 | One Line Diagram 220/33 KV Main Substation (Unit No-80) - Update_IFD/IFC |  | 2026-02-20 |  |  | 2 | 22-Jun-25 A | 2027-01-20 | 28-Jun-25 A | 2026-02-20 | 2027-01-20
| Protection and Metering One Line Diagram 220/33 KV Main Substation 33 KV Switchgear 80-ES-1802 - Upd |  |  | 2026-02-20 |  |  | 232 | 18-Feb-25 A | 2027-01-20 | 13-Jan-26 A | 2026-02-20 | 2027-01-20
| A55870 | Protection and Metering One Line Diagram 220/33 KV Main Substation 33 KV Switchgear 80-ES-1802 - Update_IFR |  | 2026-02-20 |  |  | 6 | 18-Feb-25 A | 2027-01-20 | 11-Mar-25 A | 2026-02-20 | 2027-01-20
| A55880 | Protection and Metering One Line Diagram 220/33 KV Main Substation 33 KV Switchgear 80-ES-1802 - Update_RCC |  | 2026-02-20 |  |  | 16 | 12-Mar-25 A | 2027-01-20 | 18-Mar-25 A | 2026-02-20 | 2027-01-20
| A55890 | Protection and Metering One Line Diagram 220/33 KV Main Substation 33 KV Switchgear 80-ES-1802 - Update_IFA |  | 2026-02-20 |  |  | 3 | 16-May-25 A | 2027-01-20 | 21-Jun-25 A | 2026-02-20 | 2027-01-20
| A28410 | Protection and Metering One Line Diagram 220/33 KV Main Substation 33 KV Switchgear 80-ES-1802 - Update_RCA |  | 2026-02-20 |  |  | 16 | 19-Dec-25 A | 2027-01-20 | 09-Jan-26 A | 2026-02-20 | 2027-01-20
| A28420 | Protection and Metering One Line Diagram 220/33 KV Main Substation 33 KV Switchgear 80-ES-1802 - Update_IFD/IFC |  | 2026-02-20 |  |  | 2 | 09-Jan-26 A | 2027-01-20 | 13-Jan-26 A | 2026-02-20 | 2027-01-20
| Electrical Legend Sheet |  |  | 2026-02-20 |  |  | 161 | 28-Mar-25 A | 2026-11-30 | 28-Jun-25 A | 2026-02-20 | 2027-01-20
| A12130 | Electrical Legend Sheet_IFR |  | 2026-02-20 |  |  | 6 | 28-Mar-25 A | 2026-11-30 | 06-Apr-25 A | 2026-02-20 | 2026-11-30
| A12140 | Electrical Legend Sheet_RCC |  | 2026-02-20 |  |  | 16 | 31-Mar-25 A | 2027-01-20 | 13-Apr-25 A | 2026-02-20 | 2027-01-20
| A12150 | Electrical Legend Sheet_IFA |  | 2026-02-20 |  |  | 3 | 14-Apr-25 A | 2027-01-20 | 20-Apr-25 A | 2026-02-20 | 2027-01-20
| A12160 | Electrical Legend Sheet_RCA |  | 2026-02-20 |  |  | 16 | 21-Apr-25 A | 2027-01-20 | 21-Jun-25 A | 2026-02-20 | 2027-01-20
| A12170 | Electrical Legend Sheet_IFD/IFC |  | 2026-02-20 |  |  | 2 | 22-Jun-25 A | 2027-01-20 | 28-Jun-25 A | 2026-02-20 | 2027-01-20
| Electrical Equipment And Motor List |  |  | 2026-02-20 |  |  | 217 | 28-Mar-25 A | 2026-11-30 | 04-May-25 A | 2026-02-20 | 2027-01-20
| A12230 | Electrical Equipment And Motor List_IFR |  | 2026-02-20 |  |  | 6 | 28-Mar-25 A | 2026-11-30 | 06-Apr-25 A | 2026-02-20 | 2026-11-30
| A12240 | Electrical Equipment And Motor List_RCC |  | 2026-02-20 |  |  | 16 | 31-Mar-25 A | 2027-01-20 | 13-Apr-25 A | 2026-02-20 | 2027-01-20
| A12250 | Electrical Equipment And Motor List_IFA |  | 2026-02-20 |  |  | 3 | 14-Apr-25 A | 2027-01-20 | 20-Apr-25 A | 2026-02-20 | 2027-01-20
| A12260 | Electrical Equipment And Motor List_RCA |  | 2026-02-20 |  |  | 16 | 18-Apr-25 A | 2027-01-20 | 27-Apr-25 A | 2026-02-20 | 2027-01-20
| A12270 | Electrical Equipment And Motor List_IFD/IFC |  | 2026-02-20 |  |  | 2 | 28-Apr-25 A | 2027-01-20 | 04-May-25 A | 2026-02-20 | 2027-01-20
| System Architecture Diagram For IPCS |  |  | 2026-02-20 |  |  | 236 | 12-Feb-25 A | 2027-01-20 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| A12290 | System Architecture Diagram For IPCS_RCC |  | 2026-02-20 |  |  | 16 | 06-Mar-25 A | 2027-01-20 | 20-Apr-25 A | 2026-02-20 | 2027-01-20
| A12300 | System Architecture Diagram For IPCS_IFA |  | 2026-02-20 |  |  | 3 | 21-Apr-25 A | 2027-01-20 | 27-Apr-25 A | 2026-02-20 | 2027-01-20
| A12310 | System Architecture Diagram For IPCS_RCA |  | 2026-02-20 |  |  | 16 | 15-Aug-25 A | 2027-01-20 | 04-Sep-25 A | 2026-02-20 | 2027-01-20
| A12320 | System Architecture Diagram For IPCS_IFD/IFC |  | 2026-02-20 |  |  | 2 | 19-Dec-25 A | 2027-01-20 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| System Architecture Diagram For SCMS - Update |  |  | 2026-02-20 |  |  | 39 | 01-Jul-25 A | 2027-01-20 | 08-Sep-25 A | 2026-02-20 | 2027-01-20
| A12340 | System Architecture Diagram For SCMS - Update_RCC |  | 2026-02-20 |  |  | 16 | 09-Jul-25 A | 2027-01-20 | 30-Jul-25 A | 2026-02-20 | 2027-01-20
| A12350 | System Architecture Diagram For SCMS - Update_IFA |  | 2026-02-20 |  |  | 3 | 31-Jul-25 A | 2027-01-20 | 20-Aug-25 A | 2026-02-20 | 2027-01-20
| A12360 | System Architecture Diagram For SCMS - Update_RCA |  | 2026-02-20 |  |  | 16 | 21-Aug-25 A | 2027-01-20 | 01-Sep-25 A | 2026-02-20 | 2027-01-20
| A12370 | System Architecture Diagram For SCMS - Update_IFD/IFC |  | 2026-02-20 |  |  | 2 | 02-Sep-25 A | 2027-01-20 | 08-Sep-25 A | 2026-02-20 | 2027-01-20
| Capacitor Bank Sizing Calculation |  |  | 2026-02-20 |  |  | 207 | 22-Mar-25 A | 2026-03-02 | 16-Oct-25 A | 2026-02-20 | 2027-01-20
| A10780 | Capacitor Bank Sizing Calculation_IFR |  | 2026-02-20 |  |  | 6 | 30-Apr-25 A | 2026-03-02 | 19-May-25 A | 2026-02-20 | 2026-03-02
| A10790 | Capacitor Bank Sizing Calculation_RCC |  | 2026-02-20 |  |  | 16 | 22-Mar-25 A | 2027-01-20 | 26-May-25 A | 2026-02-20 | 2027-01-20
| A10800 | Capacitor Bank Sizing Calculation_IFA |  | 2026-02-20 |  |  | 3 | 27-May-25 A | 2027-01-20 | 21-Jun-25 A | 2026-02-20 | 2027-01-20
| A10810 | Capacitor Bank Sizing Calculation_RCA |  | 2026-02-20 |  |  | 16 | 20-Jul-25 A | 2027-01-20 | 22-Aug-25 A | 2026-02-20 | 2027-01-20
| A10820 | Capacitor Bank Sizing Calculation_IFD/IFC |  | 2026-02-20 |  |  | 2 | 10-Oct-25 A | 2027-01-20 | 16-Oct-25 A | 2026-02-20 | 2027-01-20
| Technical Bid Evaluation For 11KV Switchgear |  |  | 2026-02-20 |  |  | 132 | 01-Jul-25 A | 2027-01-20 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| A12980 | Technical Bid Evaluation For 11KV Switchgear_IFR |  | 2026-02-20 |  |  | 6 | 01-Jul-25 A | 2027-01-20 | 18-Jul-25 A | 2026-02-20 | 2027-01-20
| A12990 | Technical Bid Evaluation For 11KV Switchgear_RCC |  | 2026-02-20 |  |  | 16 | 21-Jul-25 A | 2027-01-20 | 22-Aug-25 A | 2026-02-20 | 2027-01-20
| A13000 | Technical Bid Evaluation For 11KV Switchgear_IFA |  | 2026-02-20 |  |  | 3 | 27-Oct-25 A | 2027-01-20 | 05-Nov-25 A | 2026-02-20 | 2027-01-20
| A13010 | Technical Bid Evaluation For 11KV Switchgear_RCA |  | 2026-02-20 |  |  | 16 | 06-Nov-25 A | 2027-01-20 | 17-Nov-25 A | 2026-02-20 | 2027-01-20
| A13020 | Technical Bid Evaluation For 11KV Switchgear_IFD/IFC |  | 2026-02-20 |  |  | 2 | 19-Dec-25 A | 2027-01-20 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| Technical Bid Evaluation For DC UPS |  |  | 2026-02-20 |  |  | 61 | 01-Oct-25 A | 2026-03-19 | 19-Jan-26 A | 2026-02-20 | 2027-01-20
| A13130 | Technical Bid Evaluation For DC UPS_IFR |  | 2026-02-20 |  |  | 6 | 01-Oct-25 A | 2026-03-19 | 10-Oct-25 A | 2026-02-20 | 2026-03-19
| A13140 | Technical Bid Evaluation For DC UPS_RCC |  | 2026-02-20 |  |  | 16 | 08-Oct-25 A | 2026-03-19 | 24-Oct-25 A | 2026-02-20 | 2026-03-19
| A13150 | Technical Bid Evaluation For DC UPS_IFA |  | 2026-02-20 |  |  | 3 | 19-Dec-25 A | 2026-03-19 | 24-Dec-25 A | 2026-02-20 | 2026-03-19
| A13160 | Technical Bid Evaluation For DC UPS_RCA |  | 2026-02-20 |  |  | 16 | 24-Dec-25 A | 2027-01-20 | 15-Jan-26 A | 2026-02-20 | 2027-01-20
| A13170 | Technical Bid Evaluation For DC UPS_IFD/IFC |  | 2026-02-20 |  |  | 2 | 15-Jan-26 A | 2027-01-20 | 19-Jan-26 A | 2026-02-20 | 2027-01-20
| Cable (MV and LV) Sizing Calculation |  |  | 2026-02-20 |  |  | 95 | 19-Feb-25 A | 2026-10-05 | 16-Oct-25 A | 2026-02-20 | 2027-01-20
| A10730 | Cable (MV and LV) Sizing Calculation_IFR |  | 2026-02-20 |  |  | 6 | 19-Feb-25 A | 2026-10-05 | 12-Mar-25 A | 2026-02-20 | 2026-10-05
| A10740 | Cable (MV and LV) Sizing Calculation_RCC |  | 2026-02-20 |  |  | 16 | 13-Mar-25 A | 2027-01-20 | 06-May-25 A | 2026-02-20 | 2027-01-20
| A10750 | Cable (MV and LV) Sizing Calculation_IFA |  | 2026-02-20 |  |  | 3 | 07-May-25 A | 2027-01-20 | 19-Jun-25 A | 2026-02-20 | 2027-01-20
| A10760 | Cable (MV and LV) Sizing Calculation_RCA |  | 2026-02-20 |  |  | 16 | 20-Jun-25 A | 2027-01-20 | 26-Jun-25 A | 2026-02-20 | 2027-01-20
| A10770 | Cable (MV and LV) Sizing Calculation_IFD/IFC |  | 2026-02-20 |  |  | 2 | 10-Oct-25 A | 2027-01-20 | 16-Oct-25 A | 2026-02-20 | 2027-01-20
| Lighting Design Calculation |  |  | 2026-02-20 |  |  | 143 | 31-Jul-25 A | 2027-01-20 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| A10830 | Lighting Design Calculation_IFR |  | 2026-02-20 |  |  | 6 | 31-Jul-25 A | 2027-01-20 | 15-Aug-25 A | 2026-02-20 | 2027-01-20
| A10840 | Lighting Design Calculation_RCC |  | 2026-02-20 |  |  | 16 | 02-Aug-25 A | 2027-01-20 | 22-Aug-25 A | 2026-02-20 | 2027-01-20
| A10850 | Lighting Design Calculation_IFA |  | 2026-02-20 |  |  | 3 | 01-Oct-25 A | 2027-01-20 | 09-Oct-25 A | 2026-02-20 | 2027-01-20
| A10860 | Lighting Design Calculation_RCA |  | 2026-02-20 |  |  | 16 | 01-Oct-25 A | 2027-01-20 | 17-Oct-25 A | 2026-02-20 | 2027-01-20
| A10870 | Lighting Design Calculation_IFD/IFC |  | 2026-02-20 |  |  | 2 | 19-Dec-25 A | 2027-01-20 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| Earthing and Lightning Protection Calculation |  |  | 2026-02-20 |  |  | 87 | 31-Jul-25 A | 2027-01-18 | 2026-02-24 | 2026-02-24 | 2027-01-20 | 237
| A10880 | Earthing and Lightning Protection Calculation_IFR |  | 2026-02-20 |  |  | 6 | 31-Jul-25 A | 2027-01-18 | 11-Aug-25 A | 2026-02-20 | 2027-01-18
| A10890 | Earthing and Lightning Protection Calculation_RCC |  | 2026-02-20 |  |  | 16 | 10-Aug-25 A | 2027-01-18 | 30-Aug-25 A | 2026-02-20 | 2027-01-18
| A10900 | Earthing and Lightning Protection Calculation_IFA |  | 2026-02-20 |  |  | 3 | 24-Sep-25 A | 2027-01-18 | 09-Oct-25 A | 2026-02-20 | 2027-01-18
| A10910 | Earthing and Lightning Protection Calculation_RCA |  | 2026-02-20 |  |  | 16 | 28-Sep-25 A | 2027-01-18 | 16-Oct-25 A | 2026-02-20 | 2027-01-18
| A10920 | Earthing and Lightning Protection Calculation_IFD/IFC |  | 2026-02-20 |  |  | 2 | 2026-02-20 | 2027-01-18 | 2026-02-24 | 2026-02-24 | 2027-01-20 | 237
| Power And Control Cable Schedule |  |  | 2026-02-20 |  |  | 61 | 01-Aug-25 A | 2026-10-05 | 19-Jan-26 A | 2026-02-20 | 2026-10-05
| A12180 | Power And Control Cable Schedule_IFR |  | 2026-02-20 |  |  | 6 | 01-Aug-25 A | 2026-10-05 | 15-Aug-25 A | 2026-02-20 | 2026-10-05
| A12190 | Power And Control Cable Schedule_RCC |  | 2026-02-20 |  |  | 16 | 08-Aug-25 A | 2026-10-05 | 22-Aug-25 A | 2026-02-20 | 2026-10-05
| A12200 | Power And Control Cable Schedule_IFA |  | 2026-02-20 |  |  | 3 | 19-Dec-25 A | 2026-10-05 | 24-Dec-25 A | 2026-02-20 | 2026-10-05
| A12210 | Power And Control Cable Schedule_RCA |  | 2026-02-20 |  |  | 16 | 24-Dec-25 A | 2026-10-05 | 15-Jan-26 A | 2026-02-20 | 2026-10-05
| A12220 | Power And Control Cable Schedule_IFD/IFC |  | 2026-02-20 |  |  | 2 | 15-Jan-26 A | 2026-10-05 | 19-Jan-26 A | 2026-02-20 | 2026-10-05
| Interconnection Schedule |  |  | 2026-02-20 |  |  | 43 | 2026-02-20 | 2026-11-04 | 2026-04-21 | 2026-04-21 | 2027-01-01 | 183
| A12390 | Interconnection Schedule_RCC |  | 2026-02-27 |  |  | 16 | 2026-02-27 | 2026-11-11 | 2026-03-23 | 2026-03-23 | 2026-12-03 | 183
| A12400 | Interconnection Schedule_IFA |  | 2026-03-23 |  |  | 3 | 2026-03-23 | 2026-12-03 | 2026-03-26 | 2026-03-26 | 2026-12-08 | 183
| A12410 | Interconnection Schedule_RCA |  | 2026-03-26 |  |  | 16 | 2026-03-26 | 2026-12-09 | 2026-04-17 | 2026-04-17 | 2026-12-30 | 183
| A12420 | Interconnection Schedule_IFD/IFC |  | 2026-04-17 |  |  | 2 | 2026-04-17 | 2026-12-30 | 2026-04-21 | 2026-04-21 | 2027-01-01 | 183
| Electrical Substation Building Layout |  |  | 2026-02-20 |  |  | 274 | 03-Jan-25 A | 2026-03-14 | 30-Dec-25 A | 2026-02-20 | 2027-01-20
| A11940 | Electrical Substation Building Layout_RCC |  | 2026-02-20 |  |  | 16 | 25-Jan-25 A | 2026-03-14 | 15-May-25 A | 2026-02-20 | 2026-03-14
| A11950 | Electrical Substation Building Layout_IFA |  | 2026-02-20 |  |  | 3 | 16-May-25 A | 2026-03-14 | 23-Aug-25 A | 2026-02-20 | 2026-03-14
| A11960 | Electrical Substation Building Layout_RCA |  | 2026-02-20 |  |  | 16 | 24-Aug-25 A | 2027-01-20 | 30-Aug-25 A | 2026-02-20 | 2027-01-20
| A11970 | Electrical Substation Building Layout_IFD/IFC |  | 2026-02-20 |  |  | 2 | 26-Dec-25 A | 2027-01-20 | 30-Dec-25 A | 2026-02-20 | 2027-01-20
| Cable and Tray Routing Layout - Outdoor |  |  | 2026-02-20 |  |  | 92 | 01-Oct-25 A | 2026-09-01 | 2026-04-15 | 2026-04-15 | 2026-10-05 | 124
| A11840 | Cable and Tray Routing Layout - Outdoor_RCC |  | 2026-02-20 |  |  | 16 | 19-Dec-25 A | 2026-09-01 | 21-Jan-26 A | 2026-02-20 | 2026-09-01
| A11850 | Cable and Tray Routing Layout - Outdoor_IFA |  | 2026-02-20 |  |  | 3 | 2026-02-20 | 2026-09-01 | 2026-02-25 | 2026-02-25 | 2026-09-04 | 137
| A11860 | Cable and Tray Routing Layout - Outdoor_RCA |  | 2026-02-25 |  |  | 16 | 2026-02-25 | 2026-09-04 | 2026-03-19 | 2026-03-19 | 2026-09-28 | 137
| A11870 | Cable and Tray Routing Layout - Outdoor_IFD/IFC |  | 2026-04-07 |  |  | 6 | 2026-04-07 | 2026-09-28 | 2026-04-15 | 2026-04-15 | 2026-10-05 | 124
| Underground 33KV Cable Routing Layout Overall - Update |  |  | 2026-02-20 |  |  | 122 | 17-Oct-25 A | 2026-09-10 | 2026-04-15 | 2026-04-15 | 2026-10-05 | 124
| A55910 | Underground 33KV Cable Routing Layout Overall - Update_RCC |  | 2026-02-20 |  |  | 16 | 27-Oct-25 A | 2026-09-10 | 06-Nov-25 A | 2026-02-20 | 2026-09-10
| A55920 | Underground 33KV Cable Routing Layout Overall - Update_IFA |  | 2026-02-20 |  |  | 3 | 10-Dec-25 A | 2026-09-10 | 19-Dec-25 A | 2026-02-20 | 2026-09-10
| A55930 | Underground 33KV Cable Routing Layout Overall - Update_RCA |  | 2026-02-20 |  |  | 16 | 2026-02-20 | 2026-09-10 | 2026-03-13 | 2026-03-13 | 2026-10-01 | 144
| A55940 | Underground 33KV Cable Routing Layout Overall - Update_IFD/IFC |  | 2026-04-13 |  |  | 2 | 2026-04-13 | 2026-10-01 | 2026-04-15 | 2026-04-15 | 2026-10-05 | 124
| Cable and Tray Routing Layout - Indoor |  |  | 2026-03-09 |  |  | 43 | 2026-03-09 | 2026-08-06 | 2026-05-06 | 2026-05-06 | 2026-10-05 | 108
| A11890 | Cable and Tray Routing Layout - Indoor_RCC |  | 2026-03-16 |  |  | 16 | 2026-03-16 | 2026-08-13 | 2026-04-07 | 2026-04-07 | 2026-09-04 | 108
| A11900 | Cable and Tray Routing Layout - Indoor_IFA |  | 2026-04-07 |  |  | 3 | 2026-04-07 | 2026-09-04 | 2026-04-10 | 2026-04-10 | 2026-09-09 | 108
| A11910 | Cable and Tray Routing Layout - Indoor_RCA |  | 2026-04-13 |  |  | 16 | 2026-04-13 | 2026-09-10 | 2026-05-04 | 2026-05-04 | 2026-10-01 | 108
| A11920 | Cable and Tray Routing Layout - Indoor_IFD/IFC |  | 2026-05-04 |  |  | 2 | 2026-05-04 | 2026-10-01 | 2026-05-06 | 2026-05-06 | 2026-10-05 | 108
| Overall Lighting & Small Power Layout |  |  | 2026-02-20 |  |  | 118 | 23-Aug-25 A | 2026-10-05 | 23-Jan-26 A | 2026-02-20 | 2026-10-05
| A11980 | Overall Lighting & Small Power Layout_IFR |  | 2026-02-20 |  |  | 6 | 23-Aug-25 A | 2026-10-05 | 13-Sep-25 A | 2026-02-20 | 2026-10-05
| A11990 | Overall Lighting & Small Power Layout_RCC |  | 2026-02-20 |  |  | 16 | 28-Aug-25 A | 2026-10-05 | 20-Sep-25 A | 2026-02-20 | 2026-10-05
| A12000 | Overall Lighting & Small Power Layout_IFA |  | 2026-02-20 |  |  | 3 | 19-Dec-25 A | 2026-10-05 | 24-Dec-25 A | 2026-02-20 | 2026-10-05
| A12010 | Overall Lighting & Small Power Layout_RCA |  | 2026-02-20 |  |  | 16 | 24-Dec-25 A | 2026-10-05 | 15-Jan-26 A | 2026-02-20 | 2026-10-05
| A12020 | Overall Lighting & Small Power Layout_IFD/IFC |  | 2026-02-20 |  |  | 6 | 15-Jan-26 A | 2026-10-05 | 23-Jan-26 A | 2026-02-20 | 2026-10-05
| Earthing And Lightning Protection System Layout |  |  | 2026-02-20 |  |  | 59 | 20-Dec-25 A | 2026-09-01 | 2026-03-26 | 2026-03-26 | 2026-10-05 | 137
| A12030 | Earthing And Lightning Protection System Layout_IFR |  | 2026-02-20 |  |  | 6 | 20-Dec-25 A | 2026-09-01 | 12-Jan-26 A | 2026-02-20 | 2026-09-01
| A12040 | Earthing And Lightning Protection System Layout_RCC |  | 2026-02-20 |  |  | 16 | 12-Jan-26 A | 2026-09-01 | 17-Jan-26 A | 2026-02-20 | 2026-09-01
| A12050 | Earthing And Lightning Protection System Layout_IFA |  | 2026-02-20 |  |  | 3 | 2026-02-20 | 2026-09-01 | 2026-02-25 | 2026-02-25 | 2026-09-04 | 137
| A12060 | Earthing And Lightning Protection System Layout_RCA |  | 2026-02-25 |  |  | 16 | 2026-02-25 | 2026-09-04 | 2026-03-19 | 2026-03-19 | 2026-09-28 | 137
| A12070 | Earthing And Lightning Protection System Layout_IFD/IFC |  | 2026-03-19 |  |  | 6 | 2026-03-19 | 2026-09-28 | 2026-03-26 | 2026-03-26 | 2026-10-05 | 137
| Updation of Earthing Layout Butene 1, EU3, B3/EU3 |  |  | 2026-02-20 |  |  | 136 | 10-Sep-25 A | 2026-04-14 | 2026-04-17 | 2026-04-17 | 2027-01-20 | 199
| A12090 | Updation of Earthing Layout Butene 1, EU3, B3/EU3_RCC |  | 2026-02-20 |  |  | 16 | 2026-02-20 | 2026-11-25 | 2026-03-13 | 2026-03-13 | 2026-12-17 | 199
| A12100 | Updation of Earthing Layout Butene 1, EU3, B3/EU3_IFA |  | 2026-03-13 |  |  | 3 | 2026-03-13 | 2026-12-17 | 2026-03-19 | 2026-03-19 | 2026-12-22 | 199
| A12110 | Updation of Earthing Layout Butene 1, EU3, B3/EU3_RCA |  | 2026-03-19 |  |  | 16 | 2026-03-19 | 2026-12-22 | 2026-04-09 | 2026-04-09 | 2027-01-13 | 199
| A12120 | Updation of Earthing Layout Butene 1, EU3, B3/EU3_IFD/IFC |  | 2026-04-09 |  |  | 6 | 2026-04-09 | 2027-01-13 | 2026-04-17 | 2026-04-17 | 2027-01-20 | 199
| Electrical Bulk MTO |  |  | 2026-02-20 |  |  | 73 | 20-Apr-25 A | 2026-04-14 | 25-May-25 A | 2026-02-20 | 2026-05-26
| A13430 | Electrical Bulk MTO_IFR |  | 2026-02-20 |  |  | 6 | 20-Apr-25 A | 2026-04-14 | 11-May-25 A | 2026-02-20 | 2026-04-14
| A13440 | Electrical Bulk MTO_RCC |  | 2026-02-20 |  |  | 16 | 12-May-25 A | 2026-04-14 | 18-May-25 A | 2026-02-20 | 2026-04-14
| A13470 | Electrical Bulk MTO_IFD/IFC |  | 2026-02-20 |  |  | 2 | 19-May-25 A | 2026-05-26 | 25-May-25 A | 2026-02-20 | 2026-05-26
| Scope of Work for the ICSS System |  |  | 2026-02-20 |  |  | 212 | 01-Jul-25 A | 2026-03-19 | 2026-04-14 | 2026-04-14 | 2027-01-20 | 202
| A14540 | Scope of Work for the ICSS System_RCC |  | 2026-02-20 |  |  | 16 | 2026-02-20 | 2026-11-30 | 2026-03-13 | 2026-03-13 | 2026-12-22 | 202
| A14550 | Scope of Work for the ICSS System_IFA |  | 2026-03-13 |  |  | 3 | 2026-03-13 | 2026-12-22 | 2026-03-19 | 2026-03-19 | 2026-12-25 | 202
| A14560 | Scope of Work for the ICSS System_RCA |  | 2026-03-19 |  |  | 16 | 2026-03-19 | 2026-12-28 | 2026-04-09 | 2026-04-09 | 2027-01-18 | 202
| A14570 | Scope of Work for the ICSS System_IFD/IFC |  | 2026-04-09 |  |  | 2 | 2026-04-09 | 2027-01-18 | 2026-04-14 | 2026-04-14 | 2027-01-20 | 202
| Scope of Work for the MCMS System |  |  | 2026-02-20 |  |  | 212 | 01-Mar-25 A | 2026-03-19 | 2026-04-14 | 2026-04-14 | 2027-01-20 | 202
| A58490 | Scope of Work for the MCMS System_IFR |  | 2026-02-20 |  |  | 6 | 01-Mar-25 A | 2026-03-19 | 10-Mar-25 A | 2026-02-20 | 2026-03-19
| A58500 | Scope of Work for the MCMS System_RCC |  | 2026-02-20 |  |  | 16 | 2026-02-20 | 2026-11-30 | 2026-03-13 | 2026-03-13 | 2026-12-22 | 202
| A58510 | Scope of Work for the MCMS System_IFA |  | 2026-03-13 |  |  | 3 | 2026-03-13 | 2026-12-22 | 2026-03-19 | 2026-03-19 | 2026-12-25 | 202
| A58520 | Scope of Work for the MCMSSystem_RCA |  | 2026-03-19 |  |  | 16 | 2026-03-19 | 2026-12-28 | 2026-04-09 | 2026-04-09 | 2027-01-18 | 202
| A58530 | Scope of Work for the MCMS System_IFD/IFC |  | 2026-04-09 |  |  | 2 | 2026-04-09 | 2027-01-18 | 2026-04-14 | 2026-04-14 | 2027-01-20 | 202
| Instrument Datasheet for ESD Valves |  |  | 2026-02-20 |  |  | 293 | 13-Mar-25 A | 2026-03-02 | 2026-02-24 | 2026-02-24 | 2026-03-19 | 18
| A14440 | Instrument Datasheet for ESD Valves_RCC |  | 2026-02-20 |  |  | 16 | 28-Apr-25 A | 2026-03-17 | 13-Jun-25 A | 2026-02-20 | 2026-03-17
| A14450 | Instrument Datasheet for ESD Valves_IFA |  | 2026-02-20 |  |  | 3 | 14-Jun-25 A | 2026-03-17 | 21-Jun-25 A | 2026-02-20 | 2026-03-17
| A14460 | Instrument Datasheet for ESD Valves_RCA |  | 2026-02-20 |  |  | 16 | 24-Nov-25 A | 2026-03-17 | 22-Jan-26 A | 2026-02-20 | 2026-03-17
| A14470 | Instrument Datasheet for ESD Valves_IFD/IFC |  | 2026-02-20 |  |  | 2 | 2026-02-20 | 2026-03-17 | 2026-02-24 | 2026-02-24 | 2026-03-19 | 18
| Instrument Datasheet for Control Valves |  |  | 2026-02-20 |  |  | 196 | 13-Mar-25 A | 2026-03-19 | 10-Sep-25 A | 2026-02-20 | 2026-03-19
| A14280 | Instrument Datasheet for Control Valves_IFR |  | 2026-02-20 |  |  | 1 | 13-Mar-25 A | 2026-03-19 | 27-Apr-25 A | 2026-02-20 | 2026-03-19
| A14290 | Instrument Datasheet for Control Valves_RCC |  | 2026-02-20 |  |  | 16 | 28-Apr-25 A | 2026-03-19 | 21-Jun-25 A | 2026-02-20 | 2026-03-19
| A14300 | Instrument Datasheet for Control Valves_IFA |  | 2026-02-20 |  |  | 3 | 22-Jun-25 A | 2026-03-19 | 28-Jun-25 A | 2026-02-20 | 2026-03-19
| A14310 | Instrument Datasheet for Control Valves_RCA |  | 2026-02-20 |  |  | 16 | 19-Aug-25 A | 2026-03-19 | 08-Sep-25 A | 2026-02-20 | 2026-03-19
| A14320 | Instrument Datasheet for Control Valves_IFD/IFC |  | 2026-02-20 |  |  | 2 | 09-Sep-25 A | 2026-03-19 | 10-Sep-25 A | 2026-02-20 | 2026-03-19
| Instrument Datasheet for Motor Operated Valves |  |  | 2026-02-20 |  |  | 195 | 13-Mar-25 A | 2026-03-19 | 10-Sep-25 A | 2026-02-20 | 2026-03-19
| A14330 | Instrument Datasheet for Motor Operated Valves_IFR |  | 2026-02-20 |  |  | 1 | 13-Mar-25 A | 2026-03-19 | 27-Apr-25 A | 2026-02-20 | 2026-03-19
| A14340 | Instrument Datasheet for Motor Operated Valves_RCC |  | 2026-02-20 |  |  | 16 | 28-Apr-25 A | 2026-03-19 | 13-Jun-25 A | 2026-02-20 | 2026-03-19
| A14350 | Instrument Datasheet for Motor Operated Valves_IFA |  | 2026-02-20 |  |  | 3 | 14-Jun-25 A | 2026-03-19 | 21-Jun-25 A | 2026-02-20 | 2026-03-19
| A14360 | Instrument Datasheet for Motor Operated Valves_RCA |  | 2026-02-20 |  |  | 16 | 19-Aug-25 A | 2026-03-19 | 08-Sep-25 A | 2026-02-20 | 2026-03-19
| A14370 | Instrument Datasheet for Motor Operated Valves_IFD/IFC |  | 2026-02-20 |  |  | 2 | 09-Sep-25 A | 2026-03-19 | 10-Sep-25 A | 2026-02-20 | 2026-03-19
| Instrument Datasheet for Analyzers |  |  | 2026-02-20 |  |  | 166 | 01-Jul-25 A | 2026-03-02 | 2026-02-24 | 2026-02-24 | 2026-03-17 | 15
| A14140 | Instrument Datasheet for Analyzers_RCC |  | 2026-02-20 |  |  | 16 | 04-Aug-25 A | 2026-03-13 | 25-Aug-25 A | 2026-02-20 | 2026-03-13
| A14150 | Instrument Datasheet for Analyzers_IFA |  | 2026-02-20 |  |  | 3 | 22-Aug-25 A | 2026-03-13 | 30-Aug-25 A | 2026-02-20 | 2026-03-13
| A14160 | Instrument Datasheet for Analyzers_RCA |  | 2026-02-20 |  |  | 16 | 25-Aug-25 A | 2026-03-13 | 06-Sep-25 A | 2026-02-20 | 2026-03-13
| A14170 | Instrument Datasheet for Analyzers_IFD/IFC |  | 2026-02-20 |  |  | 2 | 2026-02-20 | 2026-03-13 | 2026-02-24 | 2026-02-24 | 2026-03-17 | 15
| Instrument Datasheet for Flow Element (Orifice Plate) |  |  | 2026-02-20 |  |  | 244 | 07-Apr-25 A | 2026-03-02 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| A13840 | Instrument Datasheet for Flow Element (Orifice Plate)_RCC |  | 2026-02-20 |  |  | 16 | 29-Apr-25 A | 2027-01-20 | 21-Jun-25 A | 2026-02-20 | 2027-01-20
| A13850 | Instrument Datasheet for Flow Element (Orifice Plate)_IFA |  | 2026-02-20 |  |  | 3 | 22-Jun-25 A | 2027-01-20 | 28-Jun-25 A | 2026-02-20 | 2027-01-20
| A13860 | Instrument Datasheet for Flow Element (Orifice Plate)_RCA |  | 2026-02-20 |  |  | 16 | 29-Jun-25 A | 2027-01-20 | 05-Jul-25 A | 2026-02-20 | 2027-01-20
| A13870 | Instrument Datasheet for Flow Element (Orifice Plate)_IFD/IFC |  | 2026-02-20 |  |  | 2 | 19-Dec-25 A | 2027-01-20 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| Instrument Datasheet for Flow Element (Venturi Tube) |  |  | 2026-02-20 |  |  | 178 | 13-Mar-25 A | 2026-03-02 | 22-Aug-25 A | 2026-02-20 | 2026-03-02
| A13890 | Instrument Datasheet for Flow Element (Venturi Tube)_RCC |  | 2026-02-20 |  |  | 16 | 28-Apr-25 A | 2026-03-02 | 13-Jun-25 A | 2026-02-20 | 2026-03-02
| A13900 | Instrument Datasheet for Flow Element (Venturi Tube)_IFA |  | 2026-02-20 |  |  | 3 | 14-Jun-25 A | 2026-03-02 | 21-Jun-25 A | 2026-02-20 | 2026-03-02
| A13910 | Instrument Datasheet for Flow Element (Venturi Tube)_RCA |  | 2026-02-20 |  |  | 16 | 22-Jun-25 A | 2026-03-02 | 28-Jun-25 A | 2026-02-20 | 2026-03-02
| A13920 | Instrument Datasheet for Flow Element (Venturi Tube)_IFD/IFC |  | 2026-02-20 |  |  | 2 | 19-Aug-25 A | 2026-03-02 | 22-Aug-25 A | 2026-02-20 | 2026-03-02
| Instrument Datasheet for Rotameter |  |  | 2026-02-20 |  |  | 222 | 13-Mar-25 A | 2026-03-02 | 21-Nov-25 A | 2026-02-20 | 2026-03-19
| A14490 | Instrument Datasheet for Rotameter_RCC |  | 2026-02-20 |  |  | 16 | 28-Apr-25 A | 2026-03-19 | 13-Jun-25 A | 2026-02-20 | 2026-03-19
| A14500 | Instrument Datasheet for Rotameter_IFA |  | 2026-02-20 |  |  | 3 | 14-Jun-25 A | 2026-03-19 | 21-Jun-25 A | 2026-02-20 | 2026-03-19
| A14510 | Instrument Datasheet for Rotameter_RCA |  | 2026-02-20 |  |  | 16 | 22-Jun-25 A | 2026-03-19 | 08-Sep-25 A | 2026-02-20 | 2026-03-19
| A14520 | Instrument Datasheet for Rotameter_IFD/IFC |  | 2026-02-20 |  |  | 2 | 14-Nov-25 A | 2026-03-19 | 21-Nov-25 A | 2026-02-20 | 2026-03-19
| Instrument Datasheet for Electronic Transmitters (Pressure / Level / DP) |  |  | 2026-02-20 |  |  | 241 | 26-Mar-25 A | 2026-03-02 | 23-Dec-25 A | 2026-02-20 | 2026-03-19
| A13690 | Instrument Datasheet for Electronic Transmitters (Pressure / Level / DP)_RCC |  | 2026-02-20 |  |  | 16 | 17-Apr-25 A | 2026-03-19 | 02-May-25 A | 2026-02-20 | 2026-03-19
| A13700 | Instrument Datasheet for Electronic Transmitters (Pressure / Level / DP)_IFA |  | 2026-02-20 |  |  | 3 | 19-Aug-25 A | 2026-03-19 | 23-Aug-25 A | 2026-02-20 | 2026-03-19
| A13710 | Instrument Datasheet for Electronic Transmitters (Pressure / Level / DP)_RCA |  | 2026-02-20 |  |  | 16 | 16-Aug-25 A | 2026-03-19 | 30-Aug-25 A | 2026-02-20 | 2026-03-19
| A13720 | Instrument Datasheet for Electronic Transmitters (Pressure / Level / DP)_IFD/IFC |  | 2026-02-20 |  |  | 2 | 19-Dec-25 A | 2026-03-19 | 23-Dec-25 A | 2026-02-20 | 2026-03-19
| Instrument Datasheet for Electronic Transmitters (Flow) |  |  | 2026-02-20 |  |  | 240 | 13-Mar-25 A | 2026-03-02 | 23-Dec-25 A | 2026-02-20 | 2026-03-19
| A13740 | Instrument Datasheet for Electronic Transmitters (Flow)_RCC |  | 2026-02-20 |  |  | 16 | 28-Apr-25 A | 2026-03-19 | 04-May-25 A | 2026-02-20 | 2026-03-19
| A13750 | Instrument Datasheet for Electronic Transmitters (Flow)_IFA |  | 2026-02-20 |  |  | 3 | 05-May-25 A | 2026-03-19 | 21-Jun-25 A | 2026-02-20 | 2026-03-19
| A13760 | Instrument Datasheet for Electronic Transmitters (Flow)_RCA |  | 2026-02-20 |  |  | 16 | 22-Jun-25 A | 2026-03-19 | 10-Sep-25 A | 2026-02-20 | 2026-03-19
| A13770 | Instrument Datasheet for Electronic Transmitters (Flow)_IFD/IFC |  | 2026-02-20 |  |  | 2 | 19-Dec-25 A | 2026-03-19 | 23-Dec-25 A | 2026-02-20 | 2026-03-19
| Instrument Datasheet for Temperature Transmitters (Head mounted) |  |  | 2026-02-20 |  |  | 284 | 25-Mar-25 A | 2026-03-02 | 2026-02-24 | 2026-02-24 | 2027-01-20 | 237
| A14380 | Instrument Datasheet for Temperature Transmitters (Head mounted)_IFR |  | 2026-02-20 |  |  | 1 | 25-Mar-25 A | 2026-03-02 | 21-Jun-25 A | 2026-02-20 | 2026-03-02
| A14390 | Instrument Datasheet for Temperature Transmitters (Head mounted)_RCC |  | 2026-02-20 |  |  | 16 | 22-Jun-25 A | 2027-01-18 | 28-Jun-25 A | 2026-02-20 | 2027-01-18
| A14400 | Instrument Datasheet for Temperature Transmitters (Head mounted)_IFA |  | 2026-02-20 |  |  | 3 | 29-Jun-25 A | 2027-01-18 | 05-Jul-25 A | 2026-02-20 | 2027-01-18
| A14410 | Instrument Datasheet for Temperature Transmitters (Head mounted)_RCA |  | 2026-02-20 |  |  | 16 | 06-Jul-25 A | 2027-01-18 | 12-Jul-25 A | 2026-02-20 | 2027-01-18
| A14420 | Instrument Datasheet for Temperature Transmitters (Head mounted)_IFD/IFC |  | 2026-02-20 |  |  | 2 | 2026-02-20 | 2027-01-18 | 2026-02-24 | 2026-02-24 | 2027-01-20 | 237
| Instrument Datasheet for Level Transmitters (GWR type) |  |  | 2026-02-20 |  |  | 232 | 13-Mar-25 A | 2026-03-02 | 18-Dec-25 A | 2026-02-20 | 2027-01-20
| A14090 | Instrument Datasheet for Level Transmitters (GWR type)_RCC |  | 2026-02-20 |  |  | 16 | 28-Apr-25 A | 2026-03-19 | 23-Jun-25 A | 2026-02-20 | 2026-03-19
| A14100 | Instrument Datasheet for Level Transmitters (GWR type)_IFA |  | 2026-02-20 |  |  | 3 | 19-Aug-25 A | 2026-03-19 | 23-Aug-25 A | 2026-02-20 | 2026-03-19
| A14110 | Instrument Datasheet for Level Transmitters (GWR type)_RCA |  | 2026-02-20 |  |  | 16 | 03-Nov-25 A | 2027-01-20 | 21-Nov-25 A | 2026-02-20 | 2027-01-20
| A14120 | Instrument Datasheet for Level Transmitters (GWR type)_IFD/IFC |  | 2026-02-20 |  |  | 2 | 08-Dec-25 A | 2027-01-20 | 18-Dec-25 A | 2026-02-20 | 2027-01-20
| Instrument Datasheet for Temperature Element / Thermowell |  |  | 2026-02-20 |  |  | 237 | 29-May-25 A | 2026-03-02 | 23-Dec-25 A | 2026-02-20 | 2026-03-19
| A13930 | Instrument Datasheet for Temperature Element / Thermowell_IFR |  | 2026-02-20 |  |  | 1 | 29-May-25 A | 2026-03-02 | 20-Jun-25 A | 2026-02-20 | 2026-03-02
| A13940 | Instrument Datasheet for Temperature Element / Thermowell_RCC |  | 2026-02-20 |  |  | 16 | 30-May-25 A | 2026-03-19 | 28-Jun-25 A | 2026-02-20 | 2026-03-19
| A13950 | Instrument Datasheet for Temperature Element / Thermowell_IFA |  | 2026-02-20 |  |  | 3 | 30-Jun-25 A | 2026-03-19 | 07-Jul-25 A | 2026-02-20 | 2026-03-19
| A13960 | Instrument Datasheet for Temperature Element / Thermowell_RCA |  | 2026-02-20 |  |  | 16 | 02-Jul-25 A | 2026-03-19 | 18-Jul-25 A | 2026-02-20 | 2026-03-19
| A13970 | Instrument Datasheet for Temperature Element / Thermowell_IFD/IFC |  | 2026-02-20 |  |  | 2 | 19-Dec-25 A | 2026-03-19 | 23-Dec-25 A | 2026-02-20 | 2026-03-19
| Instrument Datasheet for Temperature Gauges / Thermowell |  |  | 2026-02-20 |  |  | 236 | 13-Mar-25 A | 2026-03-02 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| A14040 | Instrument Datasheet for Temperature Gauges / Thermowell_RCC |  | 2026-02-20 |  |  | 16 | 19-Apr-25 A | 2027-01-20 | 13-Jun-25 A | 2026-02-20 | 2027-01-20
| A14050 | Instrument Datasheet for Temperature Gauges / Thermowell_IFA |  | 2026-02-20 |  |  | 3 | 11-Jul-25 A | 2027-01-20 | 28-Jul-25 A | 2026-02-20 | 2027-01-20
| A14060 | Instrument Datasheet for Temperature Gauges / Thermowell_RCA |  | 2026-02-20 |  |  | 16 | 20-Oct-25 A | 2027-01-20 | 12-Nov-25 A | 2026-02-20 | 2027-01-20
| A14070 | Instrument Datasheet for Temperature Gauges / Thermowell_IFD/IFC |  | 2026-02-20 |  |  | 2 | 19-Dec-25 A | 2027-01-20 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| Instrument Datasheet for Pressure Gauges |  |  | 2026-02-20 |  |  | 235 | 21-Apr-25 A | 2026-03-02 | 23-Dec-25 A | 2026-02-20 | 2027-01-18
| A13980 | Instrument Datasheet for Pressure Gauges_IFR |  | 2026-02-20 |  |  | 1 | 21-Apr-25 A | 2026-03-02 | 27-Apr-25 A | 2026-02-20 | 2026-03-02
| A13990 | Instrument Datasheet for Pressure Gauges_RCC |  | 2026-02-20 |  |  | 16 | 26-Jun-25 A | 2026-12-22 | 20-Jul-25 A | 2026-02-20 | 2026-12-22
| A14000 | Instrument Datasheet for Pressure Gauges_IFA |  | 2026-02-20 |  |  | 3 | 31-Jul-25 A | 2026-12-22 | 13-Aug-25 A | 2026-02-20 | 2026-12-22
| A14010 | Instrument Datasheet for Pressure Gauges_RCA |  | 2026-02-20 |  |  | 16 | 01-Nov-25 A | 2027-01-18 | 21-Nov-25 A | 2026-02-20 | 2027-01-18
| A14020 | Instrument Datasheet for Pressure Gauges_IFD/IFC |  | 2026-02-20 |  |  | 2 | 19-Dec-25 A | 2027-01-18 | 23-Dec-25 A | 2026-02-20 | 2027-01-18
| Instrument Datasheet for Level Gauges (Magnetic Type) |  |  | 2026-02-20 |  |  | 169 | 13-Mar-25 A | 2026-03-02 | 22-Aug-25 A | 2026-02-20 | 2026-03-02
| A14190 | Instrument Datasheet for Level Gauges (Magnetic Type)_RCC |  | 2026-02-20 |  |  | 16 | 24-Apr-25 A | 2026-03-02 | 13-Jun-25 A | 2026-02-20 | 2026-03-02
| A14200 | Instrument Datasheet for Level Gauges (Magnetic Type)_IFA |  | 2026-02-20 |  |  | 3 | 14-Jun-25 A | 2026-03-02 | 21-Jun-25 A | 2026-02-20 | 2026-03-02
| A14210 | Instrument Datasheet for Level Gauges (Magnetic Type)_RCA |  | 2026-02-20 |  |  | 16 | 22-Jun-25 A | 2026-03-02 | 28-Jun-25 A | 2026-02-20 | 2026-03-02
| A14220 | Instrument Datasheet for Level Gauges (Magnetic Type)_IFD/IFC |  | 2026-02-20 |  |  | 2 | 19-Aug-25 A | 2026-03-02 | 22-Aug-25 A | 2026-02-20 | 2026-03-02
| Instrument Datasheet for Fire & Gas Detectors |  |  | 2026-02-20 |  |  | 122 | 26-May-25 A | 2026-03-19 | 23-Dec-25 A | 2026-02-20 | 2026-03-19
| A14240 | Instrument Datasheet for Fire & Gas Detectors_RCC |  | 2026-02-20 |  |  | 11 | 07-Aug-25 A | 2026-03-19 | 01-Sep-25 A | 2026-02-20 | 2026-03-19
| A14250 | Instrument Datasheet for Fire & Gas Detectors_IFA |  | 2026-02-20 |  |  | 3 | 26-Sep-25 A | 2026-03-19 | 13-Oct-25 A | 2026-02-20 | 2026-03-19
| A14260 | Instrument Datasheet for Fire & Gas Detectors_RCA |  | 2026-02-20 |  |  | 16 | 10-Oct-25 A | 2026-03-19 | 25-Oct-25 A | 2026-02-20 | 2026-03-19
| A14270 | Instrument Datasheet for Fire & Gas Detectors_IFD/IFC |  | 2026-02-20 |  |  | 2 | 19-Dec-25 A | 2026-03-19 | 23-Dec-25 A | 2026-02-20 | 2026-03-19
| Instrument Datasheet for Loop Powered Indicator |  |  | 2026-02-20 |  |  | 132 | 07-Apr-25 A | 2027-01-20 | 05-Jul-25 A | 2026-02-20 | 2027-01-20
| A13790 | Instrument Datasheet for Loop Powered Indicator_RCC |  | 2026-02-20 |  |  | 16 | 29-Apr-25 A | 2027-01-20 | 30-May-25 A | 2026-02-20 | 2027-01-20
| A13800 | Instrument Datasheet for Loop Powered Indicator_IFA |  | 2026-02-20 |  |  | 3 | 01-Jun-25 A | 2027-01-20 | 21-Jun-25 A | 2026-02-20 | 2027-01-20
| A13810 | Instrument Datasheet for Loop Powered Indicator_RCA |  | 2026-02-20 |  |  | 16 | 22-Jun-25 A | 2027-01-20 | 28-Jun-25 A | 2026-02-20 | 2027-01-20
| A13820 | Instrument Datasheet for Loop Powered Indicator_IFD/IFC |  | 2026-02-20 |  |  | 2 | 29-Jun-25 A | 2027-01-20 | 05-Jul-25 A | 2026-02-20 | 2027-01-20
| Material Requisition for ESD Valves |  |  | 2026-02-20 |  |  | 225 | 24-Mar-25 A | 2026-03-02 | 03-Sep-25 A | 2026-02-20 | 2026-03-19
| A15140 | Material Requisition for ESD Valves_RCC |  | 2026-02-20 |  |  | 16 | 01-May-25 A | 2026-03-19 | 21-Jun-25 A | 2026-02-20 | 2026-03-19
| A15150 | Material Requisition for ESD Valves_IFA |  | 2026-02-20 |  |  | 3 | 22-Jun-25 A | 2026-03-19 | 28-Jun-25 A | 2026-02-20 | 2026-03-19
| A15160 | Material Requisition for ESD Valves_RCA |  | 2026-02-20 |  |  | 16 | 29-Jun-25 A | 2026-03-19 | 27-Aug-25 A | 2026-02-20 | 2026-03-19
| A15170 | Material Requisition for ESD Valves_IFD/IFC |  | 2026-02-20 |  |  | 2 | 28-Aug-25 A | 2026-03-19 | 03-Sep-25 A | 2026-02-20 | 2026-03-19
| Material Requisition for Control Valves |  |  | 2026-02-20 |  |  | 197 | 13-Mar-25 A | 2026-03-19 | 19-Sep-25 A | 2026-02-20 | 2026-03-19
| A14990 | Material Requisition for Control Valves_RCC |  | 2026-02-20 |  |  | 16 | 28-Apr-25 A | 2026-03-19 | 21-Jun-25 A | 2026-02-20 | 2026-03-19
| A15000 | Material Requisition for Control Valves_IFA |  | 2026-02-20 |  |  | 3 | 22-Jun-25 A | 2026-03-19 | 28-Jun-25 A | 2026-02-20 | 2026-03-19
| A15010 | Material Requisition for Control Valves_RCA |  | 2026-02-20 |  |  | 16 | 29-Jun-25 A | 2026-03-19 | 02-Sep-25 A | 2026-02-20 | 2026-03-19
| A15020 | Material Requisition for Control Valves_IFD/IFC |  | 2026-02-20 |  |  | 2 | 10-Sep-25 A | 2026-03-19 | 19-Sep-25 A | 2026-02-20 | 2026-03-19
| Material Requisition for Motor Operated Valves |  |  | 2026-02-20 |  |  | 196 | 24-Mar-25 A | 2026-03-19 | 13-Sep-25 A | 2026-02-20 | 2026-03-19
| A15090 | Material Requisition for Motor Operated Valves_RCC |  | 2026-02-20 |  |  | 16 | 28-Apr-25 A | 2026-03-19 | 13-Jun-25 A | 2026-02-20 | 2026-03-19
| A15100 | Material Requisition for Motor Operated Valves_IFA |  | 2026-02-20 |  |  | 3 | 14-Jun-25 A | 2026-03-19 | 21-Jun-25 A | 2026-02-20 | 2026-03-19
| A15110 | Material Requisition for Motor Operated Valves_RCA |  | 2026-02-20 |  |  | 16 | 22-Jun-25 A | 2026-03-19 | 08-Sep-25 A | 2026-02-20 | 2026-03-19
| A15120 | Material Requisition for Motor Operated Valves_IFD/IFC |  | 2026-02-20 |  |  | 2 | 11-Sep-25 A | 2026-03-19 | 13-Sep-25 A | 2026-02-20 | 2026-03-19
| Material Requisition for Analyzers |  |  | 2026-02-20 |  |  | 168 | 01-Jul-25 A | 2026-03-17 | 2026-02-26 | 2026-02-26 | 2026-03-19 | 15
| A14840 | Material Requisition for Analyzers_RCC |  | 2026-02-20 |  |  | 16 | 01-Aug-25 A | 2026-03-17 | 25-Aug-25 A | 2026-02-20 | 2026-03-17
| A14850 | Material Requisition for Analyzers_IFA |  | 2026-02-20 |  |  | 3 | 26-Aug-25 A | 2026-03-17 | 30-Aug-25 A | 2026-02-20 | 2026-03-17
| A14860 | Material Requisition for Analyzers_RCA |  | 2026-02-20 |  |  | 16 | 20-Aug-25 A | 2026-03-17 | 11-Sep-25 A | 2026-02-20 | 2026-03-17
| A14870 | Material Requisition for Analyzers_IFD/IFC |  | 2026-02-24 |  |  | 2 | 2026-02-24 | 2026-03-17 | 2026-02-26 | 2026-02-26 | 2026-03-19 | 15
| Material Requisition for Flow Element (Orifice Plate) |  |  | 2026-02-20 |  |  | 246 | 14-Mar-25 A | 2026-06-04 | 25-Dec-25 A | 2026-02-20 | 2027-01-20
| A14640 | Material Requisition for Flow Element (Orifice Plate)_RCC |  | 2026-02-20 |  |  | 16 | 30-Apr-25 A | 2027-01-20 | 21-Jun-25 A | 2026-02-20 | 2027-01-20
| A14650 | Material Requisition for Flow Element (Orifice Plate)_IFA |  | 2026-02-20 |  |  | 3 | 22-Jun-25 A | 2027-01-20 | 28-Jun-25 A | 2026-02-20 | 2027-01-20
| A14660 | Material Requisition for Flow Element (Orifice Plate)_RCA |  | 2026-02-20 |  |  | 16 | 29-Jun-25 A | 2027-01-20 | 05-Jul-25 A | 2026-02-20 | 2027-01-20
| A14670 | Material Requisition for Flow Element (Orifice Plate)_IFD/IFC |  | 2026-02-20 |  |  | 2 | 23-Dec-25 A | 2027-01-20 | 25-Dec-25 A | 2026-02-20 | 2027-01-20
| Material Requisition for Flow Element (Venturi Tube) |  |  | 2026-02-20 |  |  | 172 | 13-Mar-25 A | 2026-03-02 | 15-Sep-25 A | 2026-02-20 | 2026-03-02
| A14690 | Material Requisition for Flow Element (Venturi Tube)_RCC |  | 2026-02-20 |  |  | 16 | 01-May-25 A | 2026-03-02 | 21-Jun-25 A | 2026-02-20 | 2026-03-02
| A14700 | Material Requisition for Flow Element (Venturi Tube)_IFA |  | 2026-02-20 |  |  | 3 | 22-Jun-25 A | 2026-03-02 | 28-Jun-25 A | 2026-02-20 | 2026-03-02
| A14710 | Material Requisition for Flow Element (Venturi Tube)_RCA |  | 2026-02-20 |  |  | 16 | 22-Aug-25 A | 2026-03-02 | 11-Sep-25 A | 2026-02-20 | 2026-03-02
| A14720 | Material Requisition for Flow Element (Venturi Tube)_IFD/IFC |  | 2026-02-20 |  |  | 2 | 12-Sep-25 A | 2026-03-02 | 15-Sep-25 A | 2026-02-20 | 2026-03-02
| Material Requisition for Rotameter |  |  | 2026-02-20 |  |  | 204 | 25-Mar-25 A | 2026-03-19 | 04-Oct-25 A | 2026-02-20 | 2026-03-19
| A15190 | Material Requisition for Rotameter_RCC |  | 2026-02-20 |  |  | 16 | 02-May-25 A | 2026-03-19 | 21-Jun-25 A | 2026-02-20 | 2026-03-19
| A15200 | Material Requisition for Rotameter_IFA |  | 2026-02-20 |  |  | 3 | 14-Jun-25 A | 2026-03-19 | 28-Jun-25 A | 2026-02-20 | 2026-03-19
| A15210 | Material Requisition for Rotameter_RCA |  | 2026-02-20 |  |  | 16 | 22-Jun-25 A | 2026-03-19 | 07-Jul-25 A | 2026-02-20 | 2026-03-19
| A15220 | Material Requisition for Rotameter_IFD/IFC |  | 2026-02-20 |  |  | 2 | 26-Sep-25 A | 2026-03-19 | 04-Oct-25 A | 2026-02-20 | 2026-03-19
| Material Requisition for Electronic Transmitters |  |  | 2026-02-20 |  |  | 241 | 25-Mar-25 A | 2026-03-19 | 25-Dec-25 A | 2026-02-20 | 2026-03-19
| A14590 | Material Requisition for Electronic Transmitters_RCC |  | 2026-02-20 |  |  | 16 | 29-Apr-25 A | 2026-03-19 | 30-Jul-25 A | 2026-02-20 | 2026-03-19
| A14600 | Material Requisition for Electronic Transmitters_IFA |  | 2026-02-20 |  |  | 3 | 31-Jul-25 A | 2026-03-19 | 23-Aug-25 A | 2026-02-20 | 2026-03-19
| A14610 | Material Requisition for Electronic Transmitters_RCA |  | 2026-02-20 |  |  | 16 | 24-Aug-25 A | 2026-03-19 | 06-Sep-25 A | 2026-02-20 | 2026-03-19
| A14620 | Material Requisition for Electronic Transmitters_IFD/IFC |  | 2026-02-20 |  |  | 2 | 23-Dec-25 A | 2026-03-19 | 25-Dec-25 A | 2026-02-20 | 2026-03-19
| Material Requisition for Level Transmitters (GWR type) |  |  | 2026-02-20 |  |  | 215 | 26-Mar-25 A | 2026-03-19 | 28-Aug-25 A | 2026-02-20 | 2026-03-19
| A14890 | Material Requisition for Level Transmitters (GWR type)_RCC |  | 2026-02-20 |  |  | 16 | 04-Jul-25 A | 2026-03-19 | 28-Jul-25 A | 2026-02-20 | 2026-03-19
| A14900 | Material Requisition for Level Transmitters (GWR type)_IFA |  | 2026-02-20 |  |  | 3 | 31-Jul-25 A | 2026-03-19 | 11-Aug-25 A | 2026-02-20 | 2026-03-19
| A14910 | Material Requisition for Level Transmitters (GWR type)_RCA |  | 2026-02-20 |  |  | 16 | 01-Aug-25 A | 2026-03-19 | 19-Aug-25 A | 2026-02-20 | 2026-03-19
| A14920 | Material Requisition for Level Transmitters (GWR type)_IFD/IFC |  | 2026-02-20 |  |  | 2 | 20-Aug-25 A | 2026-03-19 | 28-Aug-25 A | 2026-02-20 | 2026-03-19
| Material Requisition for Temperature Element / Thermowell |  |  | 2026-02-20 |  |  | 176 | 13-Mar-25 A | 2026-03-19 | 23-Jan-26 A | 2026-02-20 | 2026-03-19
| A14730 | Material Requisition for Temperature Element / Thermowell_IFR |  | 2026-02-20 |  |  | 2 | 13-Mar-25 A | 2026-03-19 | 07-May-25 A | 2026-02-20 | 2026-03-19
| A14740 | Material Requisition for Temperature Element / Thermowell_RCC |  | 2026-02-20 |  |  | 16 | 19-Dec-25 A | 2026-03-19 | 09-Jan-26 A | 2026-02-20 | 2026-03-19
| A14750 | Material Requisition for Temperature Element / Thermowell_IFA |  | 2026-02-20 |  |  | 3 | 09-Jan-26 A | 2026-03-19 | 15-Jan-26 A | 2026-02-20 | 2026-03-19
| A14760 | Material Requisition for Temperature Element / Thermowell_RCA |  | 2026-02-20 |  |  | 16 | 15-Jan-26 A | 2026-03-19 | 20-Jan-26 A | 2026-02-20 | 2026-03-19
| A14770 | Material Requisition for Temperature Element / Thermowell_IFD/IFC |  | 2026-02-20 |  |  | 2 | 20-Jan-26 A | 2026-03-19 | 23-Jan-26 A | 2026-02-20 | 2026-03-19
| Material Requisition for Temperature Gauges / Pressure Gauges |  |  | 2026-02-20 |  |  | 298 | 25-Mar-25 A | 2026-03-19 | 2026-03-23 | 2026-03-23 | 2027-01-20 | 218
| A14790 | Material Requisition for Temperature Gauges / Pressure Gauges_RCC |  | 2026-02-20 |  |  | 16 | 01-May-25 A | 2026-03-19 | 21-Jun-25 A | 2026-02-20 | 2026-03-19
| A14800 | Material Requisition for Temperature Gauges / Pressure Gauges_IFA |  | 2026-02-20 |  |  | 3 | 2026-02-20 | 2026-12-22 | 2026-02-25 | 2026-02-25 | 2026-12-25 | 218
| A14810 | Material Requisition for Temperature Gauges / Pressure Gauges_RCA |  | 2026-02-25 |  |  | 16 | 2026-02-25 | 2026-12-28 | 2026-03-19 | 2026-03-19 | 2027-01-18 | 218
| A14820 | Material Requisition for Temperature Gauges / Pressure Gauges_IFD/IFC |  | 2026-03-19 |  |  | 2 | 2026-03-19 | 2027-01-18 | 2026-03-23 | 2026-03-23 | 2027-01-20 | 218
| Material Requisition for Level Gauges (Magnetic Type) |  |  | 2026-02-20 |  |  | 180 | 25-Mar-25 A | 2026-03-02 | 17-Sep-25 A | 2026-02-20 | 2026-03-02
| A14940 | Material Requisition for Level Gauges (Magnetic Type)_RCC |  | 2026-02-20 |  |  | 16 | 24-Apr-25 A | 2026-03-02 | 30-Jul-25 A | 2026-02-20 | 2026-03-02
| A14950 | Material Requisition for Level Gauges (Magnetic Type)_IFA |  | 2026-02-20 |  |  | 3 | 31-Jul-25 A | 2026-03-02 | 26-Aug-25 A | 2026-02-20 | 2026-03-02
| A14960 | Material Requisition for Level Gauges (Magnetic Type)_RCA |  | 2026-02-20 |  |  | 16 | 27-Aug-25 A | 2026-03-02 | 02-Sep-25 A | 2026-02-20 | 2026-03-02
| A14970 | Material Requisition for Level Gauges (Magnetic Type)_IFD/IFC |  | 2026-02-20 |  |  | 2 | 03-Sep-25 A | 2026-03-02 | 17-Sep-25 A | 2026-02-20 | 2026-03-02
| Material Requisition for Fire & Gas Detectors |  |  | 2026-02-20 |  |  | 124 | 27-May-25 A | 2026-03-19 | 25-Dec-25 A | 2026-02-20 | 2026-03-19
| A15030 | Material Requisition for Fire & Gas Detectors_IFR |  | 2026-02-20 |  |  | 2 | 27-May-25 A | 2026-03-19 | 05-Jul-25 A | 2026-02-20 | 2026-03-19
| A15040 | Material Requisition for Fire & Gas Detectors_RCC |  | 2026-02-20 |  |  | 16 | 07-Jul-25 A | 2026-03-19 | 30-Jul-25 A | 2026-02-20 | 2026-03-19
| A15050 | Material Requisition for Fire & Gas Detectors_IFA |  | 2026-02-20 |  |  | 3 | 26-Sep-25 A | 2026-03-19 | 06-Oct-25 A | 2026-02-20 | 2026-03-19
| A15060 | Material Requisition for Fire & Gas Detectors_RCA |  | 2026-02-20 |  |  | 11 | 29-Sep-25 A | 2026-03-19 | 20-Oct-25 A | 2026-02-20 | 2026-03-19
| A15070 | Material Requisition for Fire & Gas Detectors_IFD/IFC |  | 2026-02-20 |  |  | 2 | 23-Dec-25 A | 2026-03-19 | 25-Dec-25 A | 2026-02-20 | 2026-03-19
| Material Requisition for Instrument Cables |  |  | 2026-02-20 |  |  | 81 | 27-May-25 A | 2026-03-19 | 08-Aug-25 A | 2026-02-20 | 2026-03-19
| A47660 | Material Requisition for Instrument Cables_IFA |  | 2026-02-20 |  |  | 3 | 02-Jun-25 A | 2026-03-19 | 06-Jun-25 A | 2026-02-20 | 2026-03-19
| A47650 | Material Requisition for Instrument Cables_RCC |  | 2026-02-20 |  |  | 16 | 07-Jul-25 A | 2026-03-19 | 18-Jul-25 A | 2026-02-20 | 2026-03-19
| A47670 | Material Requisition for Instrument Cables_RCA |  | 2026-02-20 |  |  | 16 | 21-Jul-25 A | 2026-03-19 | 01-Aug-25 A | 2026-02-20 | 2026-03-19
| A47680 | Material Requisition for Instrument Cables_IFD/IFC |  | 2026-02-20 |  |  | 2 | 04-Aug-25 A | 2026-03-19 | 08-Aug-25 A | 2026-02-20 | 2026-03-19
| Material Requisition for Junction Boxes |  |  | 2026-02-20 |  |  | 127 | 27-May-25 A | 2026-03-05 | 19-Dec-25 A | 2026-02-20 | 2026-03-19
| A47700 | Material Requisition for Junction Boxes_RCC |  | 2026-02-20 |  |  | 16 | 22-Sep-25 A | 2026-03-19 | 09-Oct-25 A | 2026-02-20 | 2026-03-19
| A47710 | Material Requisition for Junction Boxes_IFA |  | 2026-02-20 |  |  | 3 | 21-Oct-25 A | 2026-03-19 | 03-Nov-25 A | 2026-02-20 | 2026-03-19
| A47720 | Material Requisition for Junction Boxes_RCA |  | 2026-02-20 |  |  | 16 | 03-Nov-25 A | 2026-03-19 | 13-Nov-25 A | 2026-02-20 | 2026-03-19
| A47730 | Material Requisition for Junction Boxes_IFD/IFC |  | 2026-02-20 |  |  | 2 | 30-Nov-25 A | 2026-03-19 | 19-Dec-25 A | 2026-02-20 | 2026-03-19
| Material Requisition for ICSS System |  |  | 2026-02-20 |  |  | 157 | 31-Dec-24 A | 2026-03-02 | 14-Aug-25 A | 2026-02-20 | 2026-03-02
| A47750 | Material Requisition for ICSS System_RCC |  | 2026-02-20 |  |  | 16 | 01-May-25 A | 2026-03-02 | 30-May-25 A | 2026-02-20 | 2026-03-02
| A47760 | Material Requisition for ICSS System_IFA |  | 2026-02-20 |  |  | 3 | 02-Jun-25 A | 2026-03-02 | 21-Jun-25 A | 2026-02-20 | 2026-03-02
| A47770 | Material Requisition for ICSS System_RCA |  | 2026-02-20 |  |  | 16 | 22-Jun-25 A | 2026-03-02 | 28-Jun-25 A | 2026-02-20 | 2026-03-02
| A15370 | Material Requisition for ICSS System_IFD/IFC |  | 2026-02-20 |  |  | 2 | 04-Aug-25 A | 2026-03-02 | 14-Aug-25 A | 2026-02-20 | 2026-03-02
| Material Requisition for MCMS System |  |  | 2026-02-20 |  |  | 36 | 20-Apr-25 A | 2026-03-02 | 07-May-25 A | 2026-02-20 | 2026-03-02
| A58190 | Material Requisition for MCMS System_IFR |  | 2026-02-20 |  |  | 2 | 20-Apr-25 A | 2026-03-02 | 24-Apr-25 A | 2026-02-20 | 2026-03-02
| A58200 | Material Requisition for MCMS System_RCC |  | 2026-02-20 |  |  | 16 | 25-Apr-25 A | 2026-03-02 | 27-Apr-25 A | 2026-02-20 | 2026-03-02
| A58210 | Material Requisition for MCMS System_IFA |  | 2026-02-20 |  |  | 3 | 28-Apr-25 A | 2026-03-02 | 01-May-25 A | 2026-02-20 | 2026-03-02
| A58220 | Material Requisition for MCMS System_RCA |  | 2026-02-20 |  |  | 16 | 02-May-25 A | 2026-03-02 | 05-May-25 A | 2026-02-20 | 2026-03-02
| A58230 | Material Requisition for MCMS System_IFD/IFC |  | 2026-02-20 |  |  | 2 | 05-May-25 A | 2026-03-02 | 07-May-25 A | 2026-02-20 | 2026-03-02
| Technical Bid Evaluation for ESD Valves |  |  | 2026-02-20 |  |  | 103 | 01-Oct-25 A | 2026-12-28 | 2026-03-17 | 2026-03-17 | 2027-01-20 | 221
| A48240 | Technical Bid Evaluation for ESD Valves_RCC |  | 2026-02-20 |  |  | 16 | 03-Oct-25 A | 2026-12-28 | 14-Oct-25 A | 2026-02-20 | 2026-12-28
| A16700 | Technical Bid Evaluation for ESD Valves_IFA |  | 2026-02-20 |  |  | 3 | 28-Nov-25 A | 2026-12-28 | 11-Dec-25 A | 2026-02-20 | 2026-12-28
| A16710 | Technical Bid Evaluation for ESD Valves_RCA |  | 2026-02-20 |  |  | 16 | 2026-02-20 | 2026-12-28 | 2026-03-13 | 2026-03-13 | 2027-01-18 | 221
| A16720 | Technical Bid Evaluation for ESD Valves_IFD/IFC |  | 2026-03-13 |  |  | 2 | 2026-03-13 | 2027-01-18 | 2026-03-17 | 2026-03-17 | 2027-01-20 | 221
| Technical Bid Evaluation for Rotameter |  |  | 2026-02-20 |  |  | 86 | 30-Nov-25 A | 2026-12-22 | 2026-03-23 | 2026-03-23 | 2027-01-20 | 218
| A16740 | Technical Bid Evaluation for Rotameter_RCC |  | 2026-02-20 |  |  | 16 | 19-Dec-25 A | 2026-12-22 | 09-Jan-26 A | 2026-02-20 | 2026-12-22
| A48250 | Technical Bid Evaluation for Rotameter_IFA |  | 2026-02-20 |  |  | 3 | 2026-02-20 | 2026-12-22 | 2026-02-25 | 2026-02-25 | 2026-12-25 | 218
| A16760 | Technical Bid Evaluation for Rotameter_RCA |  | 2026-02-25 |  |  | 16 | 2026-02-25 | 2026-12-28 | 2026-03-19 | 2026-03-19 | 2027-01-18 | 218
| A16770 | Technical Bid Evaluation for Rotameter_IFD/IFC |  | 2026-03-19 |  |  | 2 | 2026-03-19 | 2027-01-18 | 2026-03-23 | 2026-03-23 | 2027-01-20 | 218
| Technical Bid Evaluation for Level Transmitters (GWR type) |  |  | 2026-02-20 |  |  | 103 | 23-Aug-25 A | 2027-01-20 | 13-Jan-26 A | 2026-02-20 | 2027-01-20
| A16590 | Technical Bid Evaluation for Level Transmitters (GWR type)_RCC |  | 2026-02-20 |  |  | 16 | 05-Sep-25 A | 2027-01-20 | 29-Sep-25 A | 2026-02-20 | 2027-01-20
| A16600 | Technical Bid Evaluation for Level Transmitters (GWR type)_IFA |  | 2026-02-20 |  |  | 3 | 28-Nov-25 A | 2027-01-20 | 18-Dec-25 A | 2026-02-20 | 2027-01-20
| A16610 | Technical Bid Evaluation for Level Transmitters (GWR type)_RCA |  | 2026-02-20 |  |  | 16 | 19-Dec-25 A | 2027-01-20 | 09-Jan-26 A | 2026-02-20 | 2027-01-20
| A16620 | Technical Bid Evaluation for Level Transmitters (GWR type)_IFD/IFC |  | 2026-02-20 |  |  | 2 | 09-Jan-26 A | 2027-01-20 | 13-Jan-26 A | 2026-02-20 | 2027-01-20
| Technical Bid Evaluation for Temperature Element / Thermowell |  |  | 2026-02-20 |  |  | 66 | 19-Dec-25 A | 2026-12-22 | 2026-03-23 | 2026-03-23 | 2027-01-20 | 218
| A16290 | Technical Bid Evaluation for Temperature Element / Thermowell_RCC |  | 2026-02-20 |  |  | 16 | 26-Dec-25 A | 2026-12-22 | 19-Jan-26 A | 2026-02-20 | 2026-12-22
| A16300 | Technical Bid Evaluation for Temperature Element / Thermowell_IFA |  | 2026-02-20 |  |  | 3 | 2026-02-20 | 2026-12-22 | 2026-02-25 | 2026-02-25 | 2026-12-25 | 218
| A16310 | Technical Bid Evaluation for Temperature Element / Thermowell_RCA |  | 2026-02-25 |  |  | 16 | 2026-02-25 | 2026-12-28 | 2026-03-19 | 2026-03-19 | 2027-01-18 | 218
| A16320 | Technical Bid Evaluation for Temperature Element / Thermowell_IFD/IFC |  | 2026-03-19 |  |  | 2 | 2026-03-19 | 2027-01-18 | 2026-03-23 | 2026-03-23 | 2027-01-20 | 218
| SIL/LOPA CLoseout Report |  |  | 2026-02-20 |  |  | 43 | 2026-02-20 | 2026-11-12 | 2026-04-21 | 2026-04-21 | 2027-01-20 | 196
| A13490 | SIL/LOPA Closeout Report_RCC |  | 2026-02-27 |  |  | 16 | 2026-02-27 | 2026-11-30 | 2026-03-23 | 2026-03-23 | 2026-12-22 | 196
| A13500 | SIL/LOPA Closeout Report_IFA |  | 2026-03-23 |  |  | 3 | 2026-03-23 | 2026-12-22 | 2026-03-26 | 2026-03-26 | 2026-12-25 | 196
| A13510 | SIL/LOPA Closeout Report_RCA |  | 2026-03-26 |  |  | 16 | 2026-03-26 | 2026-12-28 | 2026-04-17 | 2026-04-17 | 2027-01-18 | 196
| A13520 | SIL/LOPA Closeout Report_IFD/IFC |  | 2026-04-17 |  |  | 2 | 2026-04-17 | 2027-01-18 | 2026-04-21 | 2026-04-21 | 2027-01-20 | 196
| Overall Control System Architecture Drawing |  |  | 2026-02-20 |  |  | 130 | 09-Jun-25 A | 2026-11-23 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| A15440 | Overall Control System Architecture Drawing_RCC |  | 2026-02-20 |  |  | 16 | 06-Jul-25 A | 2027-01-20 | 30-Jul-25 A | 2026-02-20 | 2027-01-20
| A15450 | Overall Control System Architecture Drawing_IFA |  | 2026-02-20 |  |  | 3 | 31-Jul-25 A | 2027-01-20 | 09-Sep-25 A | 2026-02-20 | 2027-01-20
| A15460 | Overall Control System Architecture Drawing_RCA |  | 2026-02-20 |  |  | 16 | 10-Sep-25 A | 2027-01-20 | 16-Sep-25 A | 2026-02-20 | 2027-01-20
| A15470 | Overall Control System Architecture Drawing_IFD/IFC |  | 2026-02-20 |  |  | 2 | 19-Dec-25 A | 2027-01-20 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| Instrument Index |  |  | 2026-02-20 |  |  | 172 | 10-Jun-25 A | 2026-11-23 | 2026-03-17 | 2026-03-17 | 2027-01-20 | 221
| A15490 | Instrument Index_RCC |  | 2026-02-20 |  |  | 16 | 01-Aug-25 A | 2026-12-28 | 25-Aug-25 A | 2026-02-20 | 2026-12-28
| A15500 | Instrument Index_IFA |  | 2026-02-20 |  |  | 3 | 22-Aug-25 A | 2026-12-28 | 30-Aug-25 A | 2026-02-20 | 2026-12-28
| A15510 | Instrument Index_RCA |  | 2026-02-20 |  |  | 16 | 2026-02-20 | 2026-12-28 | 2026-03-13 | 2026-03-13 | 2027-01-18 | 221
| A15520 | Instrument Index_IFD/IFC |  | 2026-03-13 |  |  | 2 | 2026-03-13 | 2027-01-18 | 2026-03-17 | 2026-03-17 | 2027-01-20 | 221
| Instrument & F&G I/O list |  |  | 2026-02-20 |  |  | 119 | 26-May-25 A | 2026-11-23 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| A15540 | Instrument & F&G I/O list_RCC |  | 2026-02-20 |  |  | 16 | 06-Jul-25 A | 2027-01-20 | 10-Aug-25 A | 2026-02-20 | 2027-01-20
| A47820 | Instrument & F&G I/O list_IFA |  | 2026-02-20 |  |  | 3 | 11-Aug-25 A | 2027-01-20 | 20-Aug-25 A | 2026-02-20 | 2027-01-20
| A47830 | Instrument & F&G I/O list_RCA |  | 2026-02-20 |  |  | 16 | 21-Aug-25 A | 2027-01-20 | 01-Sep-25 A | 2026-02-20 | 2027-01-20
| A47840 | Instrument & F&G I/O list_IFD/IFC |  | 2026-02-20 |  |  | 2 | 19-Dec-25 A | 2027-01-20 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| Cable Block Diagram |  |  | 2026-02-20 |  |  | 183 | 08-May-25 A | 2026-11-23 | 2026-02-24 | 2026-02-24 | 2027-01-20 | 237
| A15600 | Cable Block Diagram_IFA |  | 2026-02-20 |  |  | 3 | 14-Aug-25 A | 2027-01-18 | 20-Aug-25 A | 2026-02-20 | 2027-01-18
| A47850 | Cable Block Diagram_RCA |  | 2026-02-20 |  |  | 16 | 21-Aug-25 A | 2027-01-18 | 01-Sep-25 A | 2026-02-20 | 2027-01-18
| A15590 | Cable Block Diagram_RCC |  | 2026-02-20 |  |  | 16 | 07-Aug-25 A | 2027-01-18 | 13-Sep-25 A | 2026-02-20 | 2027-01-18
| A15620 | Cable Block Diagram_IFD/IFC |  | 2026-02-20 |  |  | 2 | 2026-02-20 | 2027-01-18 | 2026-02-24 | 2026-02-24 | 2027-01-20 | 237
| Process & Pneumatic Hookup Drawings |  |  | 2026-02-20 |  |  | 43 | 2026-02-20 | 2026-11-23 | 2026-04-21 | 2026-04-21 | 2027-01-20 | 196
| A47860 | Process & Pneumatic Hookup Drawings_RCC |  | 2026-02-27 |  |  | 16 | 2026-02-27 | 2026-11-30 | 2026-03-23 | 2026-03-23 | 2026-12-22 | 196
| A47870 | Process & Pneumatic Hookup Drawings_IFA |  | 2026-03-23 |  |  | 3 | 2026-03-23 | 2026-12-22 | 2026-03-26 | 2026-03-26 | 2026-12-25 | 196
| A47880 | Process & Pneumatic Hookup Drawings_RCA |  | 2026-03-26 |  |  | 16 | 2026-03-26 | 2026-12-28 | 2026-04-17 | 2026-04-17 | 2027-01-18 | 196
| A47890 | Process & Pneumatic Hookup Drawings_IFD/IFC |  | 2026-04-17 |  |  | 2 | 2026-04-17 | 2027-01-18 | 2026-04-21 | 2026-04-21 | 2027-01-20 | 196
| Junction Box Schedule |  |  | 2026-02-20 |  |  | 174 | 26-May-25 A | 2026-11-26 | 2026-04-14 | 2026-04-14 | 2027-01-20 | 202
| A47900 | Junction Box Schedule_RCC |  | 2026-02-20 |  |  | 16 | 2026-02-20 | 2026-11-30 | 2026-03-13 | 2026-03-13 | 2026-12-22 | 202
| A47910 | Junction Box Schedule_IFA |  | 2026-03-13 |  |  | 3 | 2026-03-13 | 2026-12-22 | 2026-03-19 | 2026-03-19 | 2026-12-25 | 202
| A47920 | Junction Box Schedule_RCA |  | 2026-03-19 |  |  | 16 | 2026-03-19 | 2026-12-28 | 2026-04-09 | 2026-04-09 | 2027-01-18 | 202
| A47930 | Junction Box Schedule_IFD/IFC |  | 2026-04-09 |  |  | 2 | 2026-04-09 | 2027-01-18 | 2026-04-14 | 2026-04-14 | 2027-01-20 | 202
| Instrument Cable Schedule |  |  | 2026-02-20 |  |  | 169 | 27-Jun-25 A | 2026-11-26 | 2026-04-14 | 2026-04-14 | 2027-01-18 | 200
| A47950 | Instrument Cable Schedule_RCC |  | 2026-02-20 |  |  | 16 | 2026-02-20 | 2026-11-26 | 2026-03-13 | 2026-03-13 | 2026-12-18 | 200
| A47960 | Instrument Cable Schedule_IFA |  | 2026-03-13 |  |  | 3 | 2026-03-13 | 2026-12-18 | 2026-03-19 | 2026-03-19 | 2026-12-23 | 200
| A47970 | Instrument Cable Schedule_RCA |  | 2026-03-19 |  |  | 16 | 2026-03-19 | 2026-12-23 | 2026-04-09 | 2026-04-09 | 2027-01-14 | 200
| A47980 | Instrument Cable Schedule_IFD/IFC |  | 2026-04-09 |  |  | 2 | 2026-04-09 | 2027-01-14 | 2026-04-14 | 2026-04-14 | 2027-01-18 | 200
| SIS Building Equipment Layout |  |  | 2026-02-20 |  |  | 223 | 08-Apr-25 A | 2026-03-14 | 27-Jun-25 A | 2026-02-20 | 2026-03-14
| A48050 | SIS Building Equipment Layout_RCC |  | 2026-02-20 |  |  | 16 | 30-Apr-25 A | 2026-03-14 | 30-May-25 A | 2026-02-20 | 2026-03-14
| A48060 | SIS Building Equipment Layout_IFA |  | 2026-02-20 |  |  | 3 | 02-Jun-25 A | 2026-03-14 | 06-Jun-25 A | 2026-02-20 | 2026-03-14
| A48070 | SIS Building Equipment Layout_RCA |  | 2026-02-20 |  |  | 16 | 09-Jun-25 A | 2026-03-14 | 20-Jun-25 A | 2026-02-20 | 2026-03-14
| A48080 | SIS Building Equipment Layout_IFD/IFC |  | 2026-02-20 |  |  | 2 | 23-Jun-25 A | 2026-03-14 | 27-Jun-25 A | 2026-02-20 | 2026-03-14
| Instrument & JB Wiring Diagram |  |  | 2026-02-20 |  |  | 55 | 20-Dec-25 A | 2026-12-18 | 2026-03-23 | 2026-03-23 | 2027-01-18 | 215
| A48000 | Instrument & JB wiring Diagram_RCC |  | 2026-02-20 |  |  | 16 | 12-Jan-26 A | 2026-12-18 | 17-Jan-26 A | 2026-02-20 | 2026-12-18
| A48010 | Instrument & JB wiring Diagram_IFA |  | 2026-02-20 |  |  | 3 | 2026-02-20 | 2026-12-18 | 2026-02-25 | 2026-02-25 | 2026-12-23 | 215
| A48020 | Instrument & JB wiring Diagram_RCA |  | 2026-02-25 |  |  | 16 | 2026-02-25 | 2026-12-23 | 2026-03-19 | 2026-03-19 | 2027-01-14 | 215
| A48030 | Instrument & JB wiring Diagram_IFD/IFC |  | 2026-03-19 |  |  | 2 | 2026-03-19 | 2027-01-14 | 2026-03-23 | 2026-03-23 | 2027-01-18 | 215
| Instrument Loop Diagram |  |  | 2026-03-09 |  |  | 43 | 2026-03-09 | 2026-11-04 | 2026-05-06 | 2026-05-06 | 2027-01-01 | 172
| A48140 | Instrument Loop Diagram_RCC |  | 2026-03-16 |  |  | 16 | 2026-03-16 | 2026-11-11 | 2026-04-07 | 2026-04-07 | 2026-12-03 | 172
| A16100 | Instrument Loop Diagram_IFA |  | 2026-04-07 |  |  | 3 | 2026-04-07 | 2026-12-03 | 2026-04-10 | 2026-04-10 | 2026-12-08 | 172
| A16110 | Instrument Loop Diagram_RCA |  | 2026-04-13 |  |  | 16 | 2026-04-13 | 2026-12-09 | 2026-05-04 | 2026-05-04 | 2026-12-30 | 172
| A16120 | Instrument Loop Diagram_IFD/IFC |  | 2026-05-04 |  |  | 2 | 2026-05-04 | 2026-12-30 | 2026-05-06 | 2026-05-06 | 2027-01-01 | 172
| Instrument Location Layout |  |  | 2026-04-03 |  |  | 43 | 2026-04-03 | 2026-11-19 | 2026-06-03 | 2026-06-03 | 2027-01-18 | 164
| A48100 | Instrument Location Layout_RCC |  | 2026-04-13 |  |  | 16 | 2026-04-13 | 2026-11-26 | 2026-05-04 | 2026-05-04 | 2026-12-18 | 164
| A15900 | Instrument Location Layout_IFA |  | 2026-05-04 |  |  | 3 | 2026-05-04 | 2026-12-18 | 2026-05-08 | 2026-05-08 | 2026-12-23 | 164
| A48110 | Instrument Location Layout_RCA |  | 2026-05-08 |  |  | 16 | 2026-05-08 | 2026-12-23 | 2026-05-29 | 2026-05-29 | 2027-01-14 | 164
| A15920 | Instrument Location Layout_IFD/IFC |  | 2026-05-29 |  |  | 2 | 2026-05-29 | 2027-01-14 | 2026-06-03 | 2026-06-03 | 2027-01-18 | 164
| Instrument Cable & trench routing layout |  |  | 2026-02-20 |  |  | 36 | 20-Dec-25 A | 2026-12-18 | 2026-03-23 | 2026-03-23 | 2027-01-18 | 215
| A15940 | Instrument Cable & trench routing layout_RCC |  | 2026-02-20 |  |  | 16 | 01-Jan-26 A | 2026-12-18 | 17-Jan-26 A | 2026-02-20 | 2026-12-18
| A15950 | Instrument Cable & trench routing layout_IFA |  | 2026-02-20 |  |  | 3 | 2026-02-20 | 2026-12-18 | 2026-02-25 | 2026-02-25 | 2026-12-23 | 215
| A15960 | Instrument Cable & trench routing layout_RCA |  | 2026-02-25 |  |  | 16 | 2026-02-25 | 2026-12-23 | 2026-03-19 | 2026-03-19 | 2027-01-14 | 215
| A48120 | Instrument Cable & trench routing layout_IFD/IFC |  | 2026-03-19 |  |  | 2 | 2026-03-19 | 2027-01-14 | 2026-03-23 | 2026-03-23 | 2027-01-18 | 215
| MCT Installation Drawing |  |  | 2026-02-20 |  |  | 86 | 10-Nov-25 A | 2026-12-22 | 2026-03-23 | 2026-03-23 | 2027-01-20 | 218
| A15990 | MCT Installation Drawing_RCC |  | 2026-02-20 |  |  | 16 | 19-Dec-25 A | 2026-12-22 | 09-Jan-26 A | 2026-02-20 | 2026-12-22
| A16000 | MCT Installation Drawing_IFA |  | 2026-02-20 |  |  | 3 | 2026-02-20 | 2026-12-22 | 2026-02-25 | 2026-02-25 | 2026-12-25 | 218
| A16010 | MCT Installation Drawing_RCA |  | 2026-02-25 |  |  | 16 | 2026-02-25 | 2026-12-28 | 2026-03-19 | 2026-03-19 | 2027-01-18 | 218
| A16020 | MCT Installation Drawing_IFD/IFC |  | 2026-03-19 |  |  | 2 | 2026-03-19 | 2027-01-18 | 2026-03-23 | 2026-03-23 | 2027-01-20 | 218
| Instrumentation & Control Material Take Off |  |  | 2026-02-20 |  |  | 47 | 19-Dec-25 A | 2026-04-07 | 2026-02-24 | 2026-02-24 | 2027-01-20 | 237
| A16040 | Instrumentation & Control Material Take Off_RCC |  | 2026-02-20 |  |  | 16 | 26-Dec-25 A | 2027-01-18 | 19-Jan-26 A | 2026-02-20 | 2027-01-18
| A16070 | Instrumentation & Control Material Take Off_IFD/IFC |  | 2026-02-20 |  |  | 2 | 2026-02-20 | 2027-01-18 | 2026-02-24 | 2026-02-24 | 2027-01-20 | 237
| SPI |  |  | 2026-02-20 |  |  | 242 | 25-Mar-25 A | 2026-11-30 | 2026-04-14 | 2026-04-14 | 2027-01-20 | 202
| SPI Execution Philoshpy |  |  | 2026-02-20 |  |  | 242 | 25-Mar-25 A | 2026-11-30 | 2026-04-14 | 2026-04-14 | 2027-01-20 | 202
| A55560 | SPI Execution Philoshpy_IFR |  | 2026-02-20 |  |  | 6 | 25-Mar-25 A | 2026-11-30 | 28-Apr-25 A | 2026-02-20 | 2026-11-30
| A55570 | SPI Execution Philoshpy_RCC |  | 2026-02-20 |  |  | 16 | 2026-02-20 | 2026-11-30 | 2026-03-13 | 2026-03-13 | 2026-12-22 | 202
| A55580 | SPI Execution Philoshpy_IFA |  | 2026-03-13 |  |  | 3 | 2026-03-13 | 2026-12-22 | 2026-03-19 | 2026-03-19 | 2026-12-25 | 202
| A55590 | SPI Execution Philoshpy_RCA |  | 2026-03-19 |  |  | 16 | 2026-03-19 | 2026-12-28 | 2026-04-09 | 2026-04-09 | 2027-01-18 | 202
| A28050 | SPI Execution Philoshpy_IFD/IFC |  | 2026-04-09 |  |  | 2 | 2026-04-09 | 2027-01-18 | 2026-04-14 | 2026-04-14 | 2027-01-20 | 202
| SPI Extraction Procedure |  |  | 2026-02-20 |  |  | 212 | 01-Jul-25 A | 2026-11-30 | 2026-04-14 | 2026-04-14 | 2027-01-20 | 202
| A55600 | SPI Extraction Procedure_RCC |  | 2026-02-20 |  |  | 16 | 2026-02-20 | 2026-11-30 | 2026-03-13 | 2026-03-13 | 2026-12-22 | 202
| A55610 | SPI Extraction Procedure_IFA |  | 2026-03-13 |  |  | 3 | 2026-03-13 | 2026-12-22 | 2026-03-19 | 2026-03-19 | 2026-12-25 | 202
| A55620 | SPI Extraction Procedure_RCA |  | 2026-03-19 |  |  | 16 | 2026-03-19 | 2026-12-28 | 2026-04-09 | 2026-04-09 | 2027-01-18 | 202
| A55630 | SPI Extraction Procedure_IFD/IFC |  | 2026-04-09 |  |  | 2 | 2026-04-09 | 2027-01-18 | 2026-04-14 | 2026-04-14 | 2027-01-20 | 202
| Civil/Structural/Architectural |  |  | 2026-02-20 |  |  | 485 | 16-Jan-25 A | 2026-02-21 | 2026-05-14 | 2026-05-14 | 2027-01-20 | 179
| Structure & Foundation design - Piperack & other pipe supports |  |  | 2026-02-20 |  |  | 194 | 21-Apr-25 A | 2026-03-02 | 2026-05-14 | 2026-05-14 | 2027-01-20 | 179
| Structural GA, Section and Details - Pipe Rack SR8001 |  |  | 2026-02-20 |  |  | 65 | 02-Jun-25 A | 2026-03-02 | 08-Aug-25 A | 2026-02-20 | 2026-03-02
| A48520 | Structural GA, Section and Details - Pipe Rack SR8001_RCC |  | 2026-02-20 |  |  | 16 | 23-Jun-25 A | 2026-03-02 | 04-Jul-25 A | 2026-02-20 | 2026-03-02
| A18000 | Structural GA, Section and Details - Pipe Rack SR8001_IFA |  | 2026-02-20 |  |  | 11 | 07-Jul-25 A | 2026-03-02 | 18-Jul-25 A | 2026-02-20 | 2026-03-02
| A48530 | Structural GA, Section and Details - Pipe Rack SR8001_RCA |  | 2026-02-20 |  |  | 16 | 21-Jul-25 A | 2026-03-02 | 01-Aug-25 A | 2026-02-20 | 2026-03-02
| A48540 | Structural GA, Section and Details - Pipe Rack SR8001_IFD/IFC |  | 2026-02-20 |  |  | 6 | 04-Aug-25 A | 2026-03-02 | 08-Aug-25 A | 2026-02-20 | 2026-03-02
| Design Calculation Report for Structural Steel - Pipe Rack SR8001 |  |  | 2026-02-20 |  |  | 65 | 02-Jun-25 A | 2026-03-02 | 01-Aug-25 A | 2026-02-20 | 2027-01-20
| A48560 | Design Calculation Report for Structural Steel - Pipe Rack SR8001_RCC |  | 2026-02-20 |  |  | 16 | 16-Jun-25 A | 2027-01-20 | 27-Jun-25 A | 2026-02-20 | 2027-01-20
| A18050 | Design Calculation Report for Structural Steel - Pipe Rack SR8001_IFA |  | 2026-02-20 |  |  | 11 | 30-Jun-25 A | 2027-01-20 | 11-Jul-25 A | 2026-02-20 | 2027-01-20
| A18060 | Design Calculation Report for Structural Steel - Pipe Rack SR8001_RCA |  | 2026-02-20 |  |  | 16 | 14-Jul-25 A | 2027-01-20 | 25-Jul-25 A | 2026-02-20 | 2027-01-20
| A18070 | Design Calculation Report for Structural Steel - Pipe Rack SR8001_IFD/IFC |  | 2026-02-20 |  |  | 6 | 28-Jul-25 A | 2027-01-20 | 01-Aug-25 A | 2026-02-20 | 2027-01-20
| Foundation layout, Section and Details - Pipe Rack SR8001 |  |  | 2026-02-20 |  |  | 91 | 25-Jun-25 A | 2026-03-02 | 23-Dec-25 A | 2026-02-20 | 2026-03-02
| A48580 | Foundation layout, Section and Details - Pipe Rack SR8001_RCC |  | 2026-02-20 |  |  | 16 | 14-Jul-25 A | 2026-03-02 | 22-Aug-25 A | 2026-02-20 | 2026-03-02
| A48590 | Foundation layout, Section and Details - Pipe Rack SR8001_IFA |  | 2026-02-20 |  |  | 3 | 31-Oct-25 A | 2026-03-02 | 11-Nov-25 A | 2026-02-20 | 2026-03-02
| A18110 | Foundation layout, Section and Details - Pipe Rack SR8001_RCA |  | 2026-02-20 |  |  | 16 | 13-Nov-25 A | 2026-03-02 | 21-Nov-25 A | 2026-02-20 | 2026-03-02
| A18120 | Foundation layout, Section and Details - Pipe Rack SR8001_IFD/IFC |  | 2026-02-20 |  |  | 2 | 19-Dec-25 A | 2026-03-02 | 23-Dec-25 A | 2026-02-20 | 2026-03-02
| Design Calculation Report for Foundations - Pipe Rack SR8001 |  |  | 2026-02-20 |  |  | 91 | 01-Jul-25 A | 2027-01-20 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| A48600 | Design Calculation Report for Foundations - Pipe Rack SR8001_RCC |  | 2026-02-20 |  |  | 16 | 14-Jul-25 A | 2027-01-20 | 22-Aug-25 A | 2026-02-20 | 2027-01-20
| A48610 | Design Calculation Report for Foundations - Pipe Rack SR8001_IFA |  | 2026-02-20 |  |  | 3 | 31-Oct-25 A | 2027-01-20 | 11-Nov-25 A | 2026-02-20 | 2027-01-20
| A48620 | Design Calculation Report for Foundations - Pipe Rack SR8001_RCA |  | 2026-02-20 |  |  | 16 | 12-Nov-25 A | 2027-01-20 | 21-Nov-25 A | 2026-02-20 | 2027-01-20
| A18170 | Design Calculation Report for Foundations - Pipe Rack SR8001_IFD/IFC |  | 2026-02-20 |  |  | 2 | 19-Dec-25 A | 2027-01-20 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| Structural GA, Section and Details - Pipe Rack 13-I-08001 |  |  | 2026-02-20 |  |  | 68 | 01-Aug-25 A | 2026-03-02 | 24-Dec-25 A | 2026-02-20 | 2026-06-28
| A18180 | Structural GA, Section and Details - Pipe Rack 13-I-08001_IFR |  | 2026-02-20 |  |  | 11 | 01-Aug-25 A | 2026-03-02 | 15-Aug-25 A | 2026-02-20 | 2026-03-02
| A18190 | Structural GA, Section and Details - Pipe Rack 13-I-08001_RCC |  | 2026-02-20 |  |  | 16 | 04-Aug-25 A | 2026-03-02 | 22-Aug-25 A | 2026-02-20 | 2026-03-02
| A48630 | Structural GA, Section and Details - Pipe Rack 13-I-08001_IFA |  | 2026-02-20 |  |  | 6 | 25-Aug-25 A | 2026-03-02 | 29-Aug-25 A | 2026-02-20 | 2026-03-02
| A48640 | Structural GA, Section and Details - Pipe Rack 13-I-08001_RCA |  | 2026-02-20 |  |  | 16 | 01-Sep-25 A | 2026-06-28 | 22-Oct-25 A | 2026-02-20 | 2026-06-28
| A48650 | Structural GA, Section and Details - Pipe Rack 13-I-08001_IFD/IFC |  | 2026-02-20 |  |  | 3 | 19-Dec-25 A | 2026-06-28 | 24-Dec-25 A | 2026-02-20 | 2026-06-28
| Design Calculation Report for Structural Steel - Pipe Rack 13-I-08001 |  |  | 2026-02-20 |  |  | 52 | 07-Jul-25 A | 2026-03-02 | 12-Sep-25 A | 2026-02-20 | 2026-03-02
| A18240 | Design Calculation Report for Structural Steel - Pipe Rack 13-I-08001_RCC |  | 2026-02-20 |  |  | 16 | 21-Jul-25 A | 2026-03-02 | 08-Aug-25 A | 2026-02-20 | 2026-03-02
| A18250 | Design Calculation Report for Structural Steel - Pipe Rack 13-I-08001_IFA |  | 2026-02-20 |  |  | 6 | 11-Aug-25 A | 2026-03-02 | 19-Aug-25 A | 2026-02-20 | 2026-03-02
| A48660 | Design Calculation Report for Structural Steel - Pipe Rack 13-I-08001_RCA |  | 2026-02-20 |  |  | 16 | 20-Aug-25 A | 2026-03-02 | 05-Sep-25 A | 2026-02-20 | 2026-03-02
| A48670 | Design Calculation Report for Structural Steel - Pipe Rack 13-I-08001_IFD/IFC |  | 2026-02-20 |  |  | 3 | 08-Sep-25 A | 2026-03-02 | 12-Sep-25 A | 2026-02-20 | 2026-03-02
| Foundation layout, Section and Details - Pipe Rack 13-I-08001 |  |  | 2026-02-20 |  |  | 80 | 30-Jun-25 A | 2026-03-02 | 23-Dec-25 A | 2026-02-20 | 2026-03-02
| A18290 | Foundation layout, Section and Details - Pipe Rack 13-I-08001_RCC |  | 2026-02-20 |  |  | 16 | 16-Jul-25 A | 2026-03-02 | 22-Aug-25 A | 2026-02-20 | 2026-03-02
| A18300 | Foundation layout, Section and Details - Pipe Rack 13-I-08001_IFA |  | 2026-02-20 |  |  | 3 | 25-Aug-25 A | 2026-03-02 | 29-Aug-25 A | 2026-02-20 | 2026-03-02
| A18310 | Foundation layout, Section and Details - Pipe Rack 13-I-08001_RCA |  | 2026-02-20 |  |  | 16 | 11-Aug-25 A | 2026-03-02 | 05-Sep-25 A | 2026-02-20 | 2026-03-02
| A48690 | Foundation layout, Section and Details - Pipe Rack 13-I-08001_IFD/IFC |  | 2026-02-20 |  |  | 2 | 19-Dec-25 A | 2026-03-02 | 23-Dec-25 A | 2026-02-20 | 2026-03-02
| Design Calculation Report for Foundations - Pipe Rack 13-I-08001 |  |  | 2026-02-20 |  |  | 80 | 02-Jul-25 A | 2026-03-02 | 23-Dec-25 A | 2026-02-20 | 2026-03-02
| A48710 | Design Calculation Report for Foundations - Pipe Rack 13-I-08001_RCC |  | 2026-02-20 |  |  | 16 | 14-Jul-25 A | 2026-03-02 | 22-Aug-25 A | 2026-02-20 | 2026-03-02
| A18350 | Design Calculation Report for Foundations - Pipe Rack 13-I-08001_IFA |  | 2026-02-20 |  |  | 3 | 25-Aug-25 A | 2026-03-02 | 29-Aug-25 A | 2026-02-20 | 2026-03-02
| A48720 | Design Calculation Report for Foundations - Pipe Rack 13-I-08001_RCA |  | 2026-02-20 |  |  | 16 | 18-Aug-25 A | 2026-03-02 | 05-Sep-25 A | 2026-02-20 | 2026-03-02
| A48730 | Design Calculation Report for Foundations - Pipe Rack 13-I-08001_IFD/IFC |  | 2026-02-20 |  |  | 2 | 19-Dec-25 A | 2026-03-02 | 23-Dec-25 A | 2026-02-20 | 2026-03-02
| Structral steel GA and details Field Supports SF8200 |  |  | 2026-02-20 |  |  | 115 | 03-Jul-25 A | 2026-05-28 | 2026-03-23 | 2026-03-23 | 2026-06-26 | 70
| A20990 | Structral steel GA and details Field Supports SF8200_RCC |  | 2026-02-20 |  |  | 16 | 19-Dec-25 A | 2026-05-28 | 09-Jan-26 A | 2026-02-20 | 2026-05-28
| A21000 | Structral steel GA and details Field Supports SF8200_IFA |  | 2026-02-20 |  |  | 3 | 2026-02-20 | 2026-05-28 | 2026-02-25 | 2026-02-25 | 2026-06-02 | 70
| A21010 | Structral steel GA and details Field Supports SF8200_RCA |  | 2026-02-25 |  |  | 16 | 2026-02-25 | 2026-06-03 | 2026-03-19 | 2026-03-19 | 2026-06-24 | 70
| A21020 | Structral steel GA and details Field Supports SF8200_IFD/IFC |  | 2026-03-19 |  |  | 2 | 2026-03-19 | 2026-06-24 | 2026-03-23 | 2026-03-23 | 2026-06-26 | 70
| Design Calculation Report for structural steel Field Supports SF8200 |  |  | 2026-02-20 |  |  | 131 | 19-Aug-25 A | 2026-04-16 | 2026-03-23 | 2026-03-23 | 2026-06-18 | 63
| A49970 | Design Calculation Report for structural steel Field Supports SF8200_RCC |  | 2026-02-20 |  |  | 16 | 19-Dec-25 A | 2026-05-14 | 09-Jan-26 A | 2026-02-20 | 2026-05-14
| A49980 | Design Calculation Report for structural steel Field Supports SF8200_IFA |  | 2026-02-20 |  |  | 3 | 2026-02-20 | 2026-05-14 | 2026-02-25 | 2026-02-25 | 2026-05-19 | 60
| A49990 | Design Calculation Report for structural steel Field Supports SF8200_RCA |  | 2026-02-25 |  |  | 16 | 2026-02-25 | 2026-05-25 | 2026-03-19 | 2026-03-19 | 2026-06-15 | 63
| A21070 | Design Calculation Report for structural steel Field Supports SF8200_IFD/IFC |  | 2026-03-19 |  |  | 2 | 2026-03-19 | 2026-06-16 | 2026-03-23 | 2026-03-23 | 2026-06-18 | 63
| Foundation Layout, Section and details Field Supports SF8200 |  |  | 2026-02-20 |  |  | 70 | 19-Dec-25 A | 2026-12-22 | 2026-03-26 | 2026-03-26 | 2027-01-20 | 214
| A21090 | Foundation Layout, Section and details Field Supports SF8200_RCC |  | 2026-02-20 |  |  | 16 | 26-Dec-25 A | 2026-12-22 | 19-Jan-26 A | 2026-02-20 | 2026-12-22
| A21100 | Foundation Layout, Section and details Field Supports SF8200_IFA |  | 2026-02-25 |  |  | 3 | 2026-02-25 | 2026-12-22 | 2026-03-02 | 2026-03-02 | 2026-12-25 | 214
| A50000 | Foundation Layout, Section and details Field Supports SF8200_RCA |  | 2026-03-02 |  |  | 16 | 2026-03-02 | 2026-12-28 | 2026-03-24 | 2026-03-24 | 2027-01-18 | 214
| A50010 | Foundation Layout, Section and details Field Supports SF8200_IFD/IFC |  | 2026-03-24 |  |  | 2 | 2026-03-24 | 2027-01-18 | 2026-03-26 | 2026-03-26 | 2027-01-20 | 214
| Design Calculation Report for Foundations Field Supports SF8200 |  |  | 2026-02-20 |  |  | 70 | 19-Dec-25 A | 2026-12-22 | 2026-03-26 | 2026-03-26 | 2027-01-20 | 214
| A50030 | Design Calculation Report for Foundations Field Supports SF8200_RCC |  | 2026-02-20 |  |  | 16 | 26-Dec-25 A | 2026-12-22 | 19-Jan-26 A | 2026-02-20 | 2026-12-22
| A21150 | Design Calculation Report for Foundations Field Supports SF8200_IFA |  | 2026-02-25 |  |  | 3 | 2026-02-25 | 2026-12-22 | 2026-03-02 | 2026-03-02 | 2026-12-25 | 214
| A21160 | Design Calculation Report for Foundations Field Supports SF8200_RCA |  | 2026-03-02 |  |  | 16 | 2026-03-02 | 2026-12-28 | 2026-03-24 | 2026-03-24 | 2027-01-18 | 214
| A21170 | Design Calculation Report for Foundations Field Supports SF8200_IFD/IFC |  | 2026-03-24 |  |  | 2 | 2026-03-24 | 2027-01-18 | 2026-03-26 | 2026-03-26 | 2027-01-20 | 214
| Structural GA and Details, Field supports in CA37 |  |  | 2026-02-20 |  |  | 43 | 2026-02-20 | 2026-04-16 | 2026-04-21 | 2026-04-21 | 2026-06-22 | 44
| A50430 | Structural GA and Details, Field supports in CA37_IFR |  | 2026-02-20 |  |  | 6 | 2026-02-20 | 2026-04-16 | 2026-02-27 | 2026-02-27 | 2026-04-23 | 39
| A50440 | Structural GA and Details, Field supports in CA37_RCC |  | 2026-02-27 |  |  | 16 | 2026-02-27 | 2026-04-28 | 2026-03-23 | 2026-03-23 | 2026-05-19 | 42
| A21900 | Structural GA and Details, Field supports in CA37_IFA |  | 2026-03-23 |  |  | 3 | 2026-03-23 | 2026-05-19 | 2026-03-26 | 2026-03-26 | 2026-05-25 | 42
| A50450 | Structural GA and Details, Field supports in CA37_RCA |  | 2026-03-26 |  |  | 16 | 2026-03-26 | 2026-05-27 | 2026-04-17 | 2026-04-17 | 2026-06-18 | 44
| A50460 | Structural GA and Details, Field supports in CA37_IFD/IFC |  | 2026-04-17 |  |  | 2 | 2026-04-17 | 2026-06-18 | 2026-04-21 | 2026-04-21 | 2026-06-22 | 44
| Design Calculation report of structural steel Field supports CA37 |  |  | 2026-02-20 |  |  | 43 | 2026-02-20 | 2026-04-16 | 2026-04-21 | 2026-04-21 | 2026-06-22 | 44
| A21990 | Design Calculation report of structural steel Field supports CA37_RCC |  | 2026-02-27 |  |  | 16 | 2026-02-27 | 2026-04-28 | 2026-03-23 | 2026-03-23 | 2026-05-19 | 42
| A50510 | Design Calculation report of structural steel Field supports CA37_IFA |  | 2026-03-23 |  |  | 3 | 2026-03-23 | 2026-05-19 | 2026-03-26 | 2026-03-26 | 2026-05-25 | 42
| A50520 | Design Calculation report of structural steel Field supports CA37_RCA |  | 2026-03-26 |  |  | 16 | 2026-03-26 | 2026-05-27 | 2026-04-17 | 2026-04-17 | 2026-06-18 | 44
| A22020 | Design Calculation report of structural steel Field supports CA37_IFD/IFC |  | 2026-04-17 |  |  | 2 | 2026-04-17 | 2026-06-18 | 2026-04-21 | 2026-04-21 | 2026-06-22 | 44
| Design Calculation report of Foundations Field supports CA37 |  |  | 2026-02-27 |  |  | 43 | 2026-02-27 | 2026-11-23 | 2026-04-29 | 2026-04-29 | 2027-01-20 | 191
| A50540 | Design Calculation report of Foundations Field supports CA37_RCC |  | 2026-03-09 |  |  | 16 | 2026-03-09 | 2026-11-30 | 2026-03-30 | 2026-03-30 | 2026-12-22 | 191
| A50550 | Design Calculation report of Foundations Field supports CA37_IFA |  | 2026-03-31 |  |  | 3 | 2026-03-31 | 2026-12-22 | 2026-04-03 | 2026-04-03 | 2026-12-25 | 191
| A22060 | Design Calculation report of Foundations Field supports CA37_RCA |  | 2026-04-03 |  |  | 16 | 2026-04-03 | 2026-12-28 | 2026-04-27 | 2026-04-27 | 2027-01-18 | 191
| A50560 | Design Calculation report of Foundations Field supports CA37_IFD/IFC |  | 2026-04-27 |  |  | 2 | 2026-04-27 | 2027-01-18 | 2026-04-29 | 2026-04-29 | 2027-01-20 | 191
| Foundation layout and details, Field supports in CA37 |  |  | 2026-02-27 |  |  | 43 | 2026-02-27 | 2026-11-23 | 2026-04-29 | 2026-04-29 | 2027-01-20 | 191
| A50480 | Foundation layout and details, Field supports in CA37_RCC |  | 2026-03-09 |  |  | 16 | 2026-03-09 | 2026-11-30 | 2026-03-30 | 2026-03-30 | 2026-12-22 | 191
| A21950 | Foundation layout and details, Field supports in CA37_IFA |  | 2026-03-31 |  |  | 3 | 2026-03-31 | 2026-12-22 | 2026-04-03 | 2026-04-03 | 2026-12-25 | 191
| A21960 | Foundation layout and details, Field supports in CA37_RCA |  | 2026-04-03 |  |  | 16 | 2026-04-03 | 2026-12-28 | 2026-04-27 | 2026-04-27 | 2027-01-18 | 191
| A50490 | Foundation layout and details, Field supports in CA37_IFD/IFC |  | 2026-04-27 |  |  | 2 | 2026-04-27 | 2027-01-18 | 2026-04-29 | 2026-04-29 | 2027-01-20 | 191
| Structural GA, Section and Details - Pipe Bridge SR81 |  |  | 2026-02-20 |  |  | 43 | 23-Jun-25 A | 2026-03-02 | 14-Aug-25 A | 2026-02-20 | 2026-03-02
| A48740 | Structural GA, Section and Details - Pipe Bridge SR81_IFR |  | 2026-02-20 |  |  | 6 | 23-Jun-25 A | 2026-03-02 | 02-Jul-25 A | 2026-02-20 | 2026-03-02
| A18390 | Structural GA, Section and Details - Pipe Bridge SR81_RCC |  | 2026-02-20 |  |  | 16 | 03-Jul-25 A | 2026-03-02 | 18-Jul-25 A | 2026-02-20 | 2026-03-02
| A18400 | Structural GA, Section and Details - Pipe Bridge SR81_IFA |  | 2026-02-20 |  |  | 3 | 21-Jul-25 A | 2026-03-02 | 25-Jul-25 A | 2026-02-20 | 2026-03-02
| A18410 | Structural GA, Section and Details - Pipe Bridge SR81_RCA |  | 2026-02-20 |  |  | 16 | 28-Jul-25 A | 2026-03-02 | 08-Aug-25 A | 2026-02-20 | 2026-03-02
| A48750 | Structural GA, Section and Details - Pipe Bridge SR81_IFD/IFC |  | 2026-02-20 |  |  | 2 | 11-Aug-25 A | 2026-03-02 | 14-Aug-25 A | 2026-02-20 | 2026-03-02
| Design Calculation Report for Structural Steel - Pipe Bridge SR81 |  |  | 2026-02-20 |  |  | 50 | 03-Jul-25 A | 2026-03-02 | 12-Sep-25 A | 2026-02-20 | 2026-03-02
| A18440 | Design Calculation Report for Structural Steel - Pipe Bridge SR81_RCC |  | 2026-02-20 |  |  | 16 | 21-Jul-25 A | 2026-03-02 | 08-Aug-25 A | 2026-02-20 | 2026-03-02
| A18450 | Design Calculation Report for Structural Steel - Pipe Bridge SR81_IFA |  | 2026-02-20 |  |  | 3 | 11-Aug-25 A | 2026-03-02 | 15-Aug-25 A | 2026-02-20 | 2026-03-02
| A48770 | Design Calculation Report for Structural Steel - Pipe Bridge SR81_RCA |  | 2026-02-20 |  |  | 16 | 18-Aug-25 A | 2026-03-02 | 05-Sep-25 A | 2026-02-20 | 2026-03-02
| A18470 | Design Calculation Report for Structural Steel - Pipe Bridge SR81_IFD/IFC |  | 2026-02-20 |  |  | 2 | 08-Sep-25 A | 2026-03-02 | 12-Sep-25 A | 2026-02-20 | 2026-03-02
| Design Calculation Report for Foundations - Pipe Bridge SR81 |  |  | 2026-02-20 |  |  | 47 | 21-Apr-25 A | 2026-03-02 | 17-Jul-25 A | 2026-02-20 | 2026-03-02
| A48830 | Design Calculation Report for Foundations - Pipe Bridge SR81_IFR |  | 2026-02-20 |  |  | 6 | 21-Apr-25 A | 2026-03-02 | 12-May-25 A | 2026-02-20 | 2026-03-02
| A48840 | Design Calculation Report for Foundations - Pipe Bridge SR81_RCC |  | 2026-02-20 |  |  | 16 | 13-May-25 A | 2026-03-02 | 19-May-25 A | 2026-02-20 | 2026-03-02
| A48850 | Design Calculation Report for Foundations - Pipe Bridge SR81_IFA |  | 2026-02-20 |  |  | 3 | 20-May-25 A | 2026-03-02 | 20-Jun-25 A | 2026-02-20 | 2026-03-02
| A48860 | Design Calculation Report for Foundations - Pipe Bridge SR81_RCA |  | 2026-02-20 |  |  | 16 | 23-Jun-25 A | 2026-03-02 | 11-Jul-25 A | 2026-02-20 | 2026-03-02
| A48870 | Design Calculation Report for Foundations - Pipe Bridge SR81_IFD/IFC |  | 2026-02-20 |  |  | 2 | 14-Jul-25 A | 2026-03-02 | 17-Jul-25 A | 2026-02-20 | 2026-03-02
| Foundation layout, Section and Details - Pipe Bridge SR81 |  |  | 2026-02-20 |  |  | 47 | 21-Apr-25 A | 2026-03-02 | 13-Sep-25 A | 2026-02-20 | 2026-03-02
| A48780 | Foundation layout, Section and Details - Pipe Bridge SR81_IFR |  | 2026-02-20 |  |  | 6 | 21-Apr-25 A | 2026-03-02 | 12-May-25 A | 2026-02-20 | 2026-03-02
| A48790 | Foundation layout, Section and Details - Pipe Bridge SR81_RCC |  | 2026-02-20 |  |  | 16 | 13-May-25 A | 2026-03-02 | 19-May-25 A | 2026-02-20 | 2026-03-02
| A48800 | Foundation layout, Section and Details - Pipe Bridge SR81_IFA |  | 2026-02-20 |  |  | 3 | 20-May-25 A | 2026-03-02 | 20-Jun-25 A | 2026-02-20 | 2026-03-02
| A48810 | Foundation layout, Section and Details - Pipe Bridge SR81_RCA |  | 2026-02-20 |  |  | 16 | 21-Jun-25 A | 2026-03-02 | 06-Sep-25 A | 2026-02-20 | 2026-03-02
| A48820 | Foundation layout, Section and Details - Pipe Bridge SR81_IFD/IFC |  | 2026-02-20 |  |  | 2 | 08-Sep-25 A | 2026-03-02 | 13-Sep-25 A | 2026-02-20 | 2026-03-02
| Structral steel GA and details Field Supports SF8300 |  |  | 2026-02-27 |  |  | 43 | 2026-02-27 | 2026-04-23 | 2026-04-29 | 2026-04-29 | 2026-06-24 | 40
| A50040 | Structral steel GA and details Field Supports SF8300_RCC |  | 2026-03-09 |  |  | 16 | 2026-03-09 | 2026-05-01 | 2026-03-30 | 2026-03-30 | 2026-05-25 | 39
| A50050 | Structral steel GA and details Field Supports SF8300_IFA |  | 2026-03-31 |  |  | 3 | 2026-03-31 | 2026-05-25 | 2026-04-03 | 2026-04-03 | 2026-05-28 | 39
| A50060 | Structral steel GA and details Field Supports SF8300_RCA |  | 2026-04-03 |  |  | 16 | 2026-04-03 | 2026-05-29 | 2026-04-27 | 2026-04-27 | 2026-06-22 | 40
| A50070 | Structral steel GA and details Field Supports SF8300_IFD/IFC |  | 2026-04-27 |  |  | 2 | 2026-04-27 | 2026-06-22 | 2026-04-29 | 2026-04-29 | 2026-06-24 | 40
| Design Calculation Report for structural steel Field Supports SF8300 |  |  | 2026-02-27 |  |  | 43 | 2026-02-27 | 2026-11-23 | 2026-04-29 | 2026-04-29 | 2027-01-20 | 191
| A21240 | Design Calculation Report for structural steel Field Supports SF8300_RCC |  | 2026-03-09 |  |  | 16 | 2026-03-09 | 2026-11-30 | 2026-03-30 | 2026-03-30 | 2026-12-22 | 191
| A21250 | Design Calculation Report for structural steel Field Supports SF8300_IFA |  | 2026-03-31 |  |  | 3 | 2026-03-31 | 2026-12-22 | 2026-04-03 | 2026-04-03 | 2026-12-25 | 191
| A21260 | Design Calculation Report for structural steel Field Supports SF8300_RCA |  | 2026-04-03 |  |  | 16 | 2026-04-03 | 2026-12-28 | 2026-04-27 | 2026-04-27 | 2027-01-18 | 191
| A50080 | Design Calculation Report for structural steel Field Supports SF8300_IFD/IFC |  | 2026-04-27 |  |  | 2 | 2026-04-27 | 2027-01-18 | 2026-04-29 | 2026-04-29 | 2027-01-20 | 191
| Design Calculation Report for Foundations Field Supports SF8300 |  |  | 2026-02-20 |  |  | 88 | 20-Dec-25 A | 2026-12-22 | 2026-05-04 | 2026-05-04 | 2027-01-20 | 187
| A21340 | Design Calculation Report for Foundations Field Supports SF8300_RCC |  | 2026-02-20 |  |  | 16 | 01-Jan-26 A | 2026-12-22 | 16-Jan-26 A | 2026-02-20 | 2026-12-22
| A50120 | Design Calculation Report for Foundations Field Supports SF8300_IFA |  | 2026-04-03 |  |  | 3 | 2026-04-03 | 2026-12-22 | 2026-04-08 | 2026-04-08 | 2026-12-25 | 187
| A50130 | Design Calculation Report for Foundations Field Supports SF8300_RCA |  | 2026-04-08 |  |  | 16 | 2026-04-08 | 2026-12-28 | 2026-04-30 | 2026-04-30 | 2027-01-18 | 187
| A50140 | Design Calculation Report for Foundations Field Supports SF8300_IFD/IFC |  | 2026-04-30 |  |  | 2 | 2026-04-30 | 2027-01-18 | 2026-05-04 | 2026-05-04 | 2027-01-20 | 187
| Foundation Layout, Section and details Field Supports SF8300 |  |  | 2026-02-20 |  |  | 86 | 20-Dec-25 A | 2026-12-22 | 2026-05-04 | 2026-05-04 | 2027-01-20 | 187
| A50100 | Foundation Layout, Section and details Field Supports SF8300_RCC |  | 2026-02-20 |  |  | 16 | 01-Jan-26 A | 2026-12-22 | 15-Jan-26 A | 2026-02-20 | 2026-12-22
| A50110 | Foundation Layout, Section and details Field Supports SF8300_IFA |  | 2026-04-03 |  |  | 3 | 2026-04-03 | 2026-12-22 | 2026-04-08 | 2026-04-08 | 2026-12-25 | 187
| A21310 | Foundation Layout, Section and details Field Supports SF8300_RCA |  | 2026-04-08 |  |  | 16 | 2026-04-08 | 2026-12-28 | 2026-04-30 | 2026-04-30 | 2027-01-18 | 187
| A21320 | Foundation Layout, Section and details Field Supports SF8300_IFD/IFC |  | 2026-04-30 |  |  | 2 | 2026-04-30 | 2027-01-18 | 2026-05-04 | 2026-05-04 | 2027-01-20 | 187
| Structral steel GA and details Field Supports SF8100 |  |  | 2026-02-20 |  |  | 86 | 20-Dec-25 A | 2026-05-28 | 2026-05-04 | 2026-05-04 | 2026-06-26 | 39
| A49900 | Structral steel GA and details Field Supports SF8100_RCC |  | 2026-02-20 |  |  | 16 | 12-Jan-26 A | 2026-05-28 | 15-Jan-26 A | 2026-02-20 | 2026-05-28
| A49910 | Structral steel GA and details Field Supports SF8100_IFA |  | 2026-04-03 |  |  | 3 | 2026-04-03 | 2026-05-28 | 2026-04-08 | 2026-04-08 | 2026-06-02 | 39
| A49920 | Structral steel GA and details Field Supports SF8100_RCA |  | 2026-04-08 |  |  | 16 | 2026-04-08 | 2026-06-03 | 2026-04-30 | 2026-04-30 | 2026-06-24 | 39
| A49930 | Structral steel GA and details Field Supports SF8100_IFD/IFC |  | 2026-04-30 |  |  | 2 | 2026-04-30 | 2026-06-24 | 2026-05-04 | 2026-05-04 | 2026-06-26 | 39
| Design Calculation Report for structural steel Field Supports SF8100 |  |  | 2026-02-20 |  |  | 86 | 20-Dec-25 A | 2026-12-17 | 2026-05-04 | 2026-05-04 | 2027-01-18 | 185
| A20840 | Design Calculation Report for structural steel Field Supports SF8100_RCC |  | 2026-02-20 |  |  | 16 | 12-Jan-26 A | 2026-12-17 | 15-Jan-26 A | 2026-02-20 | 2026-12-17
| A20850 | Design Calculation Report for structural steel Field Supports SF8100_IFA |  | 2026-04-03 |  |  | 3 | 2026-04-03 | 2026-12-17 | 2026-04-08 | 2026-04-08 | 2026-12-22 | 184
| A20860 | Design Calculation Report for structural steel Field Supports SF8100_RCA |  | 2026-04-08 |  |  | 16 | 2026-04-08 | 2026-12-23 | 2026-04-30 | 2026-04-30 | 2027-01-14 | 185
| A20870 | Design Calculation Report for structural steel Field Supports SF8100_IFD/IFC |  | 2026-04-30 |  |  | 2 | 2026-04-30 | 2027-01-14 | 2026-05-04 | 2026-05-04 | 2027-01-18 | 185
| Design Calculation Report for Foundations Field Supports SF8100 |  |  | 2026-02-20 |  |  | 83 | 20-Dec-25 A | 2026-12-22 | 2026-05-08 | 2026-05-08 | 2027-01-20 | 184
| A20940 | Design Calculation Report for Foundations Field Supports SF8100_RCC |  | 2026-02-20 |  |  | 16 | 01-Jan-26 A | 2026-12-22 | 15-Jan-26 A | 2026-02-20 | 2026-12-22
| A49940 | Design Calculation Report for Foundations Field Supports SF8100_IFA |  | 2026-04-08 |  |  | 3 | 2026-04-08 | 2026-12-22 | 2026-04-14 | 2026-04-14 | 2026-12-25 | 184
| A49950 | Design Calculation Report for Foundations Field Supports SF8100_RCA |  | 2026-04-14 |  |  | 16 | 2026-04-14 | 2026-12-28 | 2026-05-05 | 2026-05-05 | 2027-01-18 | 184
| A20970 | Design Calculation Report for Foundations Field Supports SF8100_IFD/IFC |  | 2026-05-05 |  |  | 2 | 2026-05-05 | 2027-01-18 | 2026-05-08 | 2026-05-08 | 2027-01-20 | 184
| Foundation Layout, Section and details Field Supports SF8100 |  |  | 2026-02-20 |  |  | 83 | 20-Dec-25 A | 2026-12-22 | 2026-05-08 | 2026-05-08 | 2027-01-20 | 184
| A20890 | Foundation Layout, Section and details Field Supports SF8100_RCC |  | 2026-02-20 |  |  | 16 | 01-Jan-26 A | 2026-12-22 | 15-Jan-26 A | 2026-02-20 | 2026-12-22
| A20900 | Foundation Layout, Section and details Field Supports SF8100_IFA |  | 2026-04-08 |  |  | 3 | 2026-04-08 | 2026-12-22 | 2026-04-14 | 2026-04-14 | 2026-12-25 | 184
| A20910 | Foundation Layout, Section and details Field Supports SF8100_RCA |  | 2026-04-14 |  |  | 16 | 2026-04-14 | 2026-12-28 | 2026-05-05 | 2026-05-05 | 2027-01-18 | 184
| A20920 | Foundation Layout, Section and details Field Supports SF8100_IFD/IFC |  | 2026-05-05 |  |  | 2 | 2026-05-05 | 2027-01-18 | 2026-05-08 | 2026-05-08 | 2027-01-20 | 184
| Adequacy check of Pipe rack SR70 |  |  | 2026-02-20 |  |  | 43 | 2026-02-20 | 2026-04-06 | 2026-04-21 | 2026-04-21 | 2026-06-18 | 42
| A22140 | Adequacy check of Pipe rack SR70_RCC |  | 2026-02-27 |  |  | 16 | 2026-02-27 | 2026-04-22 | 2026-03-23 | 2026-03-23 | 2026-05-14 | 38
| A50610 | Adequacy check of Pipe rack SR70_IFA |  | 2026-03-23 |  |  | 3 | 2026-03-23 | 2026-05-14 | 2026-03-26 | 2026-03-26 | 2026-05-19 | 38
| A50620 | Adequacy check of Pipe rack SR70_RCA |  | 2026-03-26 |  |  | 16 | 2026-03-26 | 2026-05-25 | 2026-04-17 | 2026-04-17 | 2026-06-15 | 42
| A50630 | Adequacy check of Pipe rack SR70_IFD/IFC |  | 2026-04-17 |  |  | 2 | 2026-04-17 | 2026-06-16 | 2026-04-21 | 2026-04-21 | 2026-06-18 | 42
| Structural GA and Details, Pipe Rack SR70 |  |  | 2026-02-27 |  |  | 43 | 2026-02-27 | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-06-26 | 43
| A50570 | Structural GA and Details, Pipe Rack SR70_IFR |  | 2026-02-27 |  |  | 6 | 2026-02-27 | 2026-04-29 | 2026-03-09 | 2026-03-09 | 2026-05-06 | 43
| A50580 | Structural GA and Details, Pipe Rack SR70_RCC |  | 2026-03-09 |  |  | 16 | 2026-03-09 | 2026-05-06 | 2026-03-30 | 2026-03-30 | 2026-05-28 | 43
| A50590 | Structural GA and Details, Pipe Rack SR70_IFA |  | 2026-03-31 |  |  | 3 | 2026-03-31 | 2026-05-28 | 2026-04-03 | 2026-04-03 | 2026-06-02 | 43
| A50600 | Structural GA and Details, Pipe Rack SR70_RCA |  | 2026-04-03 |  |  | 16 | 2026-04-03 | 2026-06-03 | 2026-04-27 | 2026-04-27 | 2026-06-24 | 43
| A22120 | Structural GA and Details, Pipe Rack SR70_IFD/IFC |  | 2026-04-27 |  |  | 2 | 2026-04-27 | 2026-06-24 | 2026-04-29 | 2026-04-29 | 2026-06-26 | 43
| Adequacy check of Pipe rack SR73 |  |  | 2026-02-27 |  |  | 43 | 2026-02-27 | 2026-04-14 | 2026-04-29 | 2026-04-29 | 2026-06-22 | 38
| A50660 | Adequacy check of Pipe rack SR73_IFR |  | 2026-02-27 |  |  | 6 | 2026-02-27 | 2026-04-14 | 2026-03-09 | 2026-03-09 | 2026-04-21 | 31
| A22240 | Adequacy check of Pipe rack SR73_RCC |  | 2026-03-09 |  |  | 16 | 2026-03-09 | 2026-04-28 | 2026-03-30 | 2026-03-30 | 2026-05-19 | 36
| A22250 | Adequacy check of Pipe rack SR73_IFA |  | 2026-03-31 |  |  | 3 | 2026-03-31 | 2026-05-19 | 2026-04-03 | 2026-04-03 | 2026-05-25 | 36
| A22260 | Adequacy check of Pipe rack SR73_RCA |  | 2026-04-03 |  |  | 16 | 2026-04-03 | 2026-05-27 | 2026-04-27 | 2026-04-27 | 2026-06-18 | 38
| A50670 | Adequacy check of Pipe rack SR73_IFD/IFC |  | 2026-04-27 |  |  | 2 | 2026-04-27 | 2026-06-18 | 2026-04-29 | 2026-04-29 | 2026-06-22 | 38
| Structural GA and Details, Pipe Rack SR73 |  |  | 2026-03-16 |  |  | 43 | 2026-03-16 | 2026-04-29 | 2026-05-14 | 2026-05-14 | 2026-06-26 | 31
| A22180 | Structural GA and Details, Pipe Rack SR73_IFR |  | 2026-03-16 |  |  | 6 | 2026-03-16 | 2026-04-29 | 2026-03-24 | 2026-03-24 | 2026-05-06 | 31
| A22190 | Structural GA and Details, Pipe Rack SR73_RCC |  | 2026-03-24 |  |  | 16 | 2026-03-24 | 2026-05-06 | 2026-04-15 | 2026-04-15 | 2026-05-28 | 31
| A22200 | Structural GA and Details, Pipe Rack SR73_IFA |  | 2026-04-15 |  |  | 3 | 2026-04-15 | 2026-05-28 | 2026-04-20 | 2026-04-20 | 2026-06-02 | 31
| A50640 | Structural GA and Details, Pipe Rack SR73_RCA |  | 2026-04-20 |  |  | 16 | 2026-04-20 | 2026-06-03 | 2026-05-12 | 2026-05-12 | 2026-06-24 | 31
| A50650 | Structural GA and Details, Pipe Rack SR73_IFD/IFC |  | 2026-05-12 |  |  | 2 | 2026-05-12 | 2026-06-24 | 2026-05-14 | 2026-05-14 | 2026-06-26 | 31
| Adequacy check of U&O Rack SR37 |  |  | 2026-03-09 |  |  | 43 | 2026-03-09 | 2026-04-21 | 2026-05-06 | 2026-05-06 | 2026-06-24 | 35
| A50710 | Adequacy check of U&O Rack SR37_RCC |  | 2026-03-16 |  |  | 16 | 2026-03-16 | 2026-05-01 | 2026-04-07 | 2026-04-07 | 2026-05-25 | 34
| A50720 | Adequacy check of U&O Rack SR37_IFA |  | 2026-04-07 |  |  | 3 | 2026-04-07 | 2026-05-25 | 2026-04-10 | 2026-04-10 | 2026-05-28 | 34
| A22360 | Adequacy check of U&O Rack SR37_RCA |  | 2026-04-13 |  |  | 16 | 2026-04-13 | 2026-05-29 | 2026-05-04 | 2026-05-04 | 2026-06-22 | 35
| A22370 | Adequacy check of U&O Rack SR37_IFD/IFC |  | 2026-05-04 |  |  | 2 | 2026-05-04 | 2026-06-22 | 2026-05-06 | 2026-05-06 | 2026-06-24 | 35
| Structural GA and Details, U&O Rack SR37 |  |  | 2026-03-16 |  |  | 43 | 2026-03-16 | 2026-04-29 | 2026-05-14 | 2026-05-14 | 2026-06-26 | 31
| A50680 | Structural GA and Details, U&O Rack SR37_IFR |  | 2026-03-16 |  |  | 6 | 2026-03-16 | 2026-04-29 | 2026-03-24 | 2026-03-24 | 2026-05-06 | 31
| A50690 | Structural GA and Details, U&O Rack SR37_RCC |  | 2026-03-24 |  |  | 16 | 2026-03-24 | 2026-05-06 | 2026-04-15 | 2026-04-15 | 2026-05-28 | 31
| A22300 | Structural GA and Details, U&O Rack SR37_IFA |  | 2026-04-15 |  |  | 3 | 2026-04-15 | 2026-05-28 | 2026-04-20 | 2026-04-20 | 2026-06-02 | 31
| A22310 | Structural GA and Details, U&O Rack SR37_RCA |  | 2026-04-20 |  |  | 16 | 2026-04-20 | 2026-06-03 | 2026-05-12 | 2026-05-12 | 2026-06-24 | 31
| A22320 | Structural GA and Details, U&O Rack SR37_IFD/IFC |  | 2026-05-12 |  |  | 2 | 2026-05-12 | 2026-06-24 | 2026-05-14 | 2026-05-14 | 2026-06-26 | 31
| Structure & Foundation design - Mechanical |  |  | 2026-02-20 |  |  | 268 | 10-Apr-25 A | 2026-02-21 | 2026-03-23 | 2026-03-23 | 2027-01-20 | 218
| Foundation Drawing- Lube Oil unit for PSA-2 FeedGas Compressor |  |  | 2026-02-20 |  |  | 204 | 12-Apr-25 A | 2027-01-20 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| A18990 | Foundation Drawing- Lube Oil unit for PSA-2 FeedGas Compressor_RCC |  | 2026-02-20 |  |  | 16 | 04-May-25 A | 2027-01-20 | 10-May-25 A | 2026-02-20 | 2027-01-20
| A19000 | Foundation Drawing- Lube Oil unit for PSA-2 FeedGas Compressor_IFA |  | 2026-02-20 |  |  | 3 | 11-May-25 A | 2027-01-20 | 21-Jun-25 A | 2026-02-20 | 2027-01-20
| A19010 | Foundation Drawing- Lube Oil unit for PSA-2 FeedGas Compressor_RCA |  | 2026-02-20 |  |  | 16 | 27-Jun-25 A | 2027-01-20 | 15-Aug-25 A | 2026-02-20 | 2027-01-20
| A19020 | Foundation Drawing- Lube Oil unit for PSA-2 FeedGas Compressor_IFD/IFC |  | 2026-02-20 |  |  | 2 | 19-Dec-25 A | 2027-01-20 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| Design Calculation report for foundation of Lube Oil unit for PSA-2 FeedGas Compressor |  |  | 2026-02-20 |  |  | 204 | 13-Apr-25 A | 2027-01-20 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| A19040 | Design Calculation report for foundation of Lube Oil unit for PSA-2 FeedGas Compressor_RCC |  | 2026-02-20 |  |  | 16 | 04-May-25 A | 2027-01-20 | 10-May-25 A | 2026-02-20 | 2027-01-20
| A19050 | Design Calculation report for foundation of Lube Oil unit for PSA-2 FeedGas Compressor_IFA |  | 2026-02-20 |  |  | 3 | 11-May-25 A | 2027-01-20 | 21-Jun-25 A | 2026-02-20 | 2027-01-20
| A19060 | Design Calculation report for foundation of Lube Oil unit for PSA-2 FeedGas Compressor_RCA |  | 2026-02-20 |  |  | 16 | 27-Jun-25 A | 2027-01-20 | 15-Aug-25 A | 2026-02-20 | 2027-01-20
| A19070 | Design Calculation report for foundation of Lube Oil unit for PSA-2 FeedGas Compressor_IFD/IFC |  | 2026-02-20 |  |  | 2 | 19-Dec-25 A | 2027-01-20 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| Foundation Drawing- Lube Oil unit for PSA-2 OffGas Compressor |  |  | 2026-02-20 |  |  | 101 | 26-May-25 A | 2027-01-20 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| A19080 | Foundation Drawing- Lube Oil unit for PSA-2 OffGas Compressor_IFR |  | 2026-02-20 |  |  | 6 | 26-May-25 A | 2027-01-20 | 05-Jul-25 A | 2026-02-20 | 2027-01-20
| A19090 | Foundation Drawing- Lube Oil unit for PSA-2 OffGas Compressor_RCC |  | 2026-02-20 |  |  | 16 | 07-Jul-25 A | 2027-01-20 | 01-Aug-25 A | 2026-02-20 | 2027-01-20
| A19100 | Foundation Drawing- Lube Oil unit for PSA-2 OffGas Compressor_IFA |  | 2026-02-20 |  |  | 3 | 04-Aug-25 A | 2027-01-20 | 08-Aug-25 A | 2026-02-20 | 2027-01-20
| A49150 | Foundation Drawing- Lube Oil unit for PSA-2 OffGas Compressor_RCA |  | 2026-02-20 |  |  | 16 | 07-Aug-25 A | 2027-01-20 | 15-Aug-25 A | 2026-02-20 | 2027-01-20
| A49160 | Foundation Drawing- Lube Oil unit for PSA-2 OffGas Compressor_IFD/IFC |  | 2026-02-20 |  |  | 2 | 19-Dec-25 A | 2027-01-20 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| Design Calculation report for foundation of Lube Oil unit for PSA-2 OffGas Compressor |  |  | 2026-02-20 |  |  | 101 | 26-May-25 A | 2027-01-20 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| A49170 | Design Calculation report for foundation of Lube Oil unit for PSA-2 OffGas Compressor_IFR |  | 2026-02-20 |  |  | 6 | 26-May-25 A | 2027-01-20 | 05-Jul-25 A | 2026-02-20 | 2027-01-20
| A19140 | Design Calculation report for foundation of Lube Oil unit for PSA-2 OffGas Compressor_RCC |  | 2026-02-20 |  |  | 16 | 07-Jul-25 A | 2027-01-20 | 01-Aug-25 A | 2026-02-20 | 2027-01-20
| A19150 | Design Calculation report for foundation of Lube Oil unit for PSA-2 OffGas Compressor_IFA |  | 2026-02-20 |  |  | 3 | 04-Aug-25 A | 2027-01-20 | 08-Aug-25 A | 2026-02-20 | 2027-01-20
| A19160 | Design Calculation report for foundation of Lube Oil unit for PSA-2 OffGas Compressor_RCA |  | 2026-02-20 |  |  | 16 | 07-Aug-25 A | 2027-01-20 | 15-Aug-25 A | 2026-02-20 | 2027-01-20
| A49180 | Design Calculation report for foundation of Lube Oil unit for PSA-2 OffGas Compressor_IFD/IFC |  | 2026-02-20 |  |  | 2 | 19-Dec-25 A | 2027-01-20 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| Foundation drawing PSA-2 FeedGas Compressor 13-KC-701 |  |  | 2026-02-20 |  |  | 156 | 19-Jul-25 A | 2026-02-21 | 2026-03-17 | 2026-03-17 | 2027-01-20 | 221
| A49030 | Foundation drawing PSA-2 FeedGas Compressor 13-KC-701_RCC |  | 2026-02-20 |  |  | 16 | 01-Aug-25 A | 2026-12-28 | 29-Aug-25 A | 2026-02-20 | 2026-12-28
| A18800 | Foundation drawing PSA-2 FeedGas Compressor 13-KC-701_IFA |  | 2026-02-20 |  |  | 3 | 01-Sep-25 A | 2026-12-28 | 05-Sep-25 A | 2026-02-20 | 2026-12-28
| A49040 | Foundation drawing PSA-2 FeedGas Compressor 13-KC-701_RCA |  | 2026-02-20 |  |  | 16 | 2026-02-20 | 2026-12-28 | 2026-03-13 | 2026-03-13 | 2027-01-18 | 221
| A49050 | Foundation drawing PSA-2 FeedGas Compressor 13-KC-701_IFD/IFC |  | 2026-03-13 |  |  | 2 | 2026-03-13 | 2027-01-18 | 2026-03-17 | 2026-03-17 | 2027-01-20 | 221
| Design Calculation Report PSA-2 FeedGas Compressor 13-KC-701 |  |  | 2026-02-20 |  |  | 210 | 12-Apr-25 A | 2027-01-20 | 13-Jan-26 A | 2026-02-20 | 2027-01-20
| A49070 | Design Calculation Report PSA-2 FeedGas Compressor 13-KC-701_RCC |  | 2026-02-20 |  |  | 16 | 28-Jul-25 A | 2027-01-20 | 15-Aug-25 A | 2026-02-20 | 2027-01-20
| A49080 | Design Calculation Report PSA-2 FeedGas Compressor 13-KC-701_IFA |  | 2026-02-20 |  |  | 3 | 18-Aug-25 A | 2027-01-20 | 22-Aug-25 A | 2026-02-20 | 2027-01-20
| A49090 | Design Calculation Report PSA-2 FeedGas Compressor 13-KC-701_RCA |  | 2026-02-20 |  |  | 16 | 19-Aug-25 A | 2027-01-20 | 29-Aug-25 A | 2026-02-20 | 2027-01-20
| A49100 | Design Calculation Report PSA-2 FeedGas Compressor 13-KC-701_IFD/IFC |  | 2026-02-20 |  |  | 2 | 09-Jan-26 A | 2027-01-20 | 13-Jan-26 A | 2026-02-20 | 2027-01-20
| Foundation drawing PSA-2 OffGas Compressor 13-KC-702 |  |  | 2026-02-20 |  |  | 57 | 30-Jun-25 A | 2026-02-21 | 05-Sep-25 A | 2026-02-20 | 2026-02-21
| A49110 | Foundation drawing PSA-2 OffGas Compressor 13-KC-702_RCC |  | 2026-02-20 |  |  | 16 | 11-Jul-25 A | 2026-02-21 | 15-Aug-25 A | 2026-02-20 | 2026-02-21
| A49120 | Foundation drawing PSA-2 OffGas Compressor 13-KC-702_IFA |  | 2026-02-20 |  |  | 3 | 16-Aug-25 A | 2026-02-21 | 22-Aug-25 A | 2026-02-20 | 2026-02-21
| A49130 | Foundation drawing PSA-2 OffGas Compressor 13-KC-702_RCA |  | 2026-02-20 |  |  | 16 | 23-Aug-25 A | 2026-02-21 | 29-Aug-25 A | 2026-02-20 | 2026-02-21
| A49140 | Foundation drawing PSA-2 OffGas Compressor 13-KC-702_IFD/IFC |  | 2026-02-20 |  |  | 2 | 30-Aug-25 A | 2026-02-21 | 05-Sep-25 A | 2026-02-20 | 2026-02-21
| Design Calculation Report PSA-2 OffGas Compressor 13-KC-702 |  |  | 2026-02-20 |  |  | 87 | 01-Sep-25 A | 2027-01-18 | 2026-02-24 | 2026-02-24 | 2027-01-20 | 237
| A18940 | Design Calculation Report PSA-2 OffGas Compressor 13-KC-702_RCC |  | 2026-02-20 |  |  | 16 | 05-Sep-25 A | 2027-01-18 | 20-Sep-25 A | 2026-02-20 | 2027-01-18
| A18950 | Design Calculation Report PSA-2 OffGas Compressor 13-KC-702_IFA |  | 2026-02-20 |  |  | 3 | 22-Sep-25 A | 2027-01-18 | 26-Sep-25 A | 2026-02-20 | 2027-01-18
| A18960 | Design Calculation Report PSA-2 OffGas Compressor 13-KC-702_RCA |  | 2026-02-20 |  |  | 16 | 24-Sep-25 A | 2027-01-18 | 04-Oct-25 A | 2026-02-20 | 2027-01-18
| A18970 | Design Calculation Report PSA-2 OffGas Compressor 13-KC-702_IFD/IFC |  | 2026-02-20 |  |  | 2 | 2026-02-20 | 2027-01-18 | 2026-02-24 | 2026-02-24 | 2027-01-20 | 237
| Foundation Drawing PSA-2 Unit - Hydrogen Purification 13-XA-710 |  |  | 2026-02-20 |  |  | 87 | 05-May-25 A | 2027-01-20 | 10-Jul-25 A | 2026-02-20 | 2027-01-20
| A49610 | Foundation Drawing PSA-2 Unit - Hydrogen Purification 13-XA-710_RCC |  | 2026-02-20 |  |  | 16 | 08-May-25 A | 2027-01-20 | 21-May-25 A | 2026-02-20 | 2027-01-20
| A20200 | Foundation Drawing PSA-2 Unit - Hydrogen Purification 13-XA-710_IFA |  | 2026-02-20 |  |  | 3 | 22-May-25 A | 2027-01-20 | 28-May-25 A | 2026-02-20 | 2027-01-20
| A20210 | Foundation Drawing PSA-2 Unit - Hydrogen Purification 13-XA-710_RCA |  | 2026-02-20 |  |  | 16 | 21-May-25 A | 2027-01-20 | 04-Jun-25 A | 2026-02-20 | 2027-01-20
| A20220 | Foundation Drawing PSA-2 Unit - Hydrogen Purification 13-XA-710_IFD/IFC |  | 2026-02-20 |  |  | 2 | 09-Jun-25 A | 2027-01-20 | 10-Jul-25 A | 2026-02-20 | 2027-01-20
| Design Calculation Report for foundation of PSA-2 Unit - Hydrogen Purification 13-XA-710 |  |  | 2026-02-20 |  |  | 87 | 26-May-25 A | 2027-01-20 | 05-Sep-25 A | 2026-02-20 | 2027-01-20
| A49630 | Design Calculation Report for foundation of PSA-2 Unit - Hydrogen Purification 13-XA-710_RCC |  | 2026-02-20 |  |  | 16 | 08-Jul-25 A | 2027-01-20 | 15-Aug-25 A | 2026-02-20 | 2027-01-20
| A49640 | Design Calculation Report for foundation of PSA-2 Unit - Hydrogen Purification 13-XA-710_IFA |  | 2026-02-20 |  |  | 3 | 18-Aug-25 A | 2027-01-20 | 22-Aug-25 A | 2026-02-20 | 2027-01-20
| A20260 | Design Calculation Report for foundation of PSA-2 Unit - Hydrogen Purification 13-XA-710_RCA |  | 2026-02-20 |  |  | 16 | 11-Aug-25 A | 2027-01-20 | 29-Aug-25 A | 2026-02-20 | 2027-01-20
| A20270 | Design Calculation Report for foundation of PSA-2 Unit - Hydrogen Purification 13-XA-710_IFD/IFC |  | 2026-02-20 |  |  | 2 | 01-Sep-25 A | 2027-01-20 | 05-Sep-25 A | 2026-02-20 | 2027-01-20
| Foundation drawing for Equipment 50-HE-1410 |  |  | 2026-02-20 |  |  | 215 | 02-May-25 A | 2026-03-29 | 2026-02-24 | 2026-02-24 | 2027-01-20 | 237
| A50350 | Foundation drawing for Equipment 50-HE-1410_RCC |  | 2026-02-20 |  |  | 16 | 24-May-25 A | 2027-01-18 | 29-May-25 A | 2026-02-20 | 2027-01-18
| A50360 | Foundation drawing for Equipment 50-HE-1410_IFA |  | 2026-02-20 |  |  | 3 | 01-Aug-25 A | 2027-01-18 | 22-Aug-25 A | 2026-02-20 | 2027-01-18
| A50370 | Foundation drawing for Equipment 50-HE-1410_RCA |  | 2026-02-20 |  |  | 16 | 11-Aug-25 A | 2027-01-18 | 29-Aug-25 A | 2026-02-20 | 2027-01-18
| A50380 | Foundation drawing for Equipment 50-HE-1410_IFD/IFC |  | 2026-02-20 |  |  | 2 | 2026-02-20 | 2027-01-18 | 2026-02-24 | 2026-02-24 | 2027-01-20 | 237
| Design calculation for foundation of Equipment 50-HE-1410 |  |  | 2026-02-20 |  |  | 123 | 02-May-25 A | 2027-01-20 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| A50400 | Design calculation for foundation of Equipment 50-HE-1410_RCC |  | 2026-02-20 |  |  | 16 | 24-May-25 A | 2027-01-20 | 21-Jun-25 A | 2026-02-20 | 2027-01-20
| A50410 | Design calculation for foundation of Equipment 50-HE-1410_IFA |  | 2026-02-20 |  |  | 3 | 15-Jul-25 A | 2027-01-20 | 22-Aug-25 A | 2026-02-20 | 2027-01-20
| A50420 | Design calculation for foundation of Equipment 50-HE-1410_RCA |  | 2026-02-20 |  |  | 16 | 29-Sep-25 A | 2027-01-20 | 24-Oct-25 A | 2026-02-20 | 2027-01-20
| A21870 | Design calculation for foundation of Equipment 50-HE-1410_IFD/IFC |  | 2026-02-20 |  |  | 2 | 19-Dec-25 A | 2027-01-20 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| Foundation Drawing PSA-2 OffGas Compressor Interstage Cooler 13-HE-708 |  |  | 2026-02-20 |  |  | 108 | 01-May-25 A | 2026-03-29 | 10-Oct-25 A | 2026-02-20 | 2026-03-29
| A20090 | Foundation Drawing PSA-2 OffGas Compressor Interstage Cooler 13-HE-708_RCC |  | 2026-02-20 |  |  | 16 | 16-May-25 A | 2026-03-29 | 22-May-25 A | 2026-02-20 | 2026-03-29
| A20100 | Foundation Drawing PSA-2 OffGas Compressor Interstage Cooler 13-HE-708_IFA |  | 2026-02-20 |  |  | 3 | 23-May-25 A | 2026-03-29 | 21-Jun-25 A | 2026-02-20 | 2026-03-29
| A49560 | Foundation Drawing PSA-2 OffGas Compressor Interstage Cooler 13-HE-708_RCA |  | 2026-02-20 |  |  | 16 | 01-Aug-25 A | 2026-03-29 | 21-Aug-25 A | 2026-02-20 | 2026-03-29
| A49570 | Foundation Drawing PSA-2 OffGas Compressor Interstage Cooler 13-HE-708_IFD/IFC |  | 2026-02-20 |  |  | 2 | 26-Sep-25 A | 2026-03-29 | 10-Oct-25 A | 2026-02-20 | 2026-03-29
| Design Calculation Report for foundation of PSA-2 OffGas Compressor Interstage Cooler 13-HE-708 |  |  | 2026-02-20 |  |  | 82 | 28-Apr-25 A | 2027-01-20 | 10-Oct-25 A | 2026-02-20 | 2027-01-20
| A20140 | Design Calculation Report for foundation of PSA-2 OffGas Compressor Interstage Cooler 13-HE-708_RCC |  | 2026-02-20 |  |  | 16 | 20-May-25 A | 2027-01-20 | 21-Jun-25 A | 2026-02-20 | 2027-01-20
| A20150 | Design Calculation Report for foundation of PSA-2 OffGas Compressor Interstage Cooler 13-HE-708_IFA |  | 2026-02-20 |  |  | 3 | 22-Jun-25 A | 2027-01-20 | 28-Jun-25 A | 2026-02-20 | 2027-01-20
| A20160 | Design Calculation Report for foundation of PSA-2 OffGas Compressor Interstage Cooler 13-HE-708_RCA |  | 2026-02-20 |  |  | 16 | 21-Jul-25 A | 2027-01-20 | 21-Aug-25 A | 2026-02-20 | 2027-01-20
| A49590 | Design Calculation Report for foundation of PSA-2 OffGas Compressor Interstage Cooler 13-HE-708_IFD/IFC |  | 2026-02-20 |  |  | 2 | 22-Sep-25 A | 2027-01-20 | 10-Oct-25 A | 2026-02-20 | 2027-01-20
| Foundation Drawing PSA-2 Feed Gas Compressor AfterCooler 13-HE-704 |  |  | 2026-02-20 |  |  | 111 | 28-Apr-25 A | 2026-05-03 | 25-Jul-25 A | 2026-02-20 | 2026-05-26
| A19280 | Foundation Drawing PSA-2 Feed Gas Compressor AfterCooler 13-HE-704_IFR |  | 2026-02-20 |  |  | 6 | 28-Apr-25 A | 2026-05-03 | 19-May-25 A | 2026-02-20 | 2026-05-03
| A19290 | Foundation Drawing PSA-2 Feed Gas Compressor AfterCooler 13-HE-704_RCC |  | 2026-02-20 |  |  | 16 | 20-May-25 A | 2026-05-26 | 21-Jun-25 A | 2026-02-20 | 2026-05-26
| A19300 | Foundation Drawing PSA-2 Feed Gas Compressor AfterCooler 13-HE-704_IFA |  | 2026-02-20 |  |  | 3 | 22-Jun-25 A | 2026-05-26 | 28-Jun-25 A | 2026-02-20 | 2026-05-26
| A19310 | Foundation Drawing PSA-2 Feed Gas Compressor AfterCooler 13-HE-704_RCA |  | 2026-02-20 |  |  | 16 | 30-Jun-25 A | 2026-05-26 | 18-Jul-25 A | 2026-02-20 | 2026-05-26
| A19320 | Foundation Drawing PSA-2 Feed Gas Compressor AfterCooler 13-HE-704_IFD/IFC |  | 2026-02-20 |  |  | 2 | 21-Jul-25 A | 2026-05-26 | 25-Jul-25 A | 2026-02-20 | 2026-05-26
| Design Calculation Report for foundation of PSA-2 Feed Gas Compressor AfterCooler 13-HE-704 |  |  | 2026-02-20 |  |  | 36 | 28-Apr-25 A | 2027-01-20 | 08-Sep-25 A | 2026-02-20 | 2027-01-20
| A19340 | Design Calculation Report for foundation of PSA-2 Feed Gas Compressor AfterCooler 13-HE-704_RCC |  | 2026-02-20 |  |  | 16 | 04-May-25 A | 2027-01-20 | 19-May-25 A | 2026-02-20 | 2027-01-20
| A49240 | Design Calculation Report for foundation of PSA-2 Feed Gas Compressor AfterCooler 13-HE-704_IFA |  | 2026-02-20 |  |  | 3 | 20-May-25 A | 2027-01-20 | 21-Jun-25 A | 2026-02-20 | 2027-01-20
| A49250 | Design Calculation Report for foundation of PSA-2 Feed Gas Compressor AfterCooler 13-HE-704_RCA |  | 2026-02-20 |  |  | 16 | 22-Jun-25 A | 2027-01-20 | 28-Jun-25 A | 2026-02-20 | 2027-01-20
| A49260 | Design Calculation Report for foundation of PSA-2 Feed Gas Compressor AfterCooler 13-HE-704_IFD/IFC |  | 2026-02-20 |  |  | 2 | 29-Jun-25 A | 2027-01-20 | 08-Sep-25 A | 2026-02-20 | 2027-01-20
| Foundation Drawing PSA-2 Feed Gas Compressor Interstage Cooler 13-HE-703 |  |  | 2026-02-20 |  |  | 103 | 24-Apr-25 A | 2026-05-03 | 15-Sep-25 A | 2026-02-20 | 2026-05-24
| A49320 | Foundation Drawing PSA-2 Feed Gas Compressor Interstage Cooler 13-HE-703_RCC |  | 2026-02-20 |  |  | 16 | 16-May-25 A | 2026-05-24 | 22-May-25 A | 2026-02-20 | 2026-05-24
| A19500 | Foundation Drawing PSA-2 Feed Gas Compressor Interstage Cooler 13-HE-703_IFA |  | 2026-02-20 |  |  | 3 | 23-May-25 A | 2026-05-24 | 01-Sep-25 A | 2026-02-20 | 2026-05-24
| A19510 | Foundation Drawing PSA-2 Feed Gas Compressor Interstage Cooler 13-HE-703_RCA |  | 2026-02-20 |  |  | 16 | 02-Sep-25 A | 2026-05-24 | 08-Sep-25 A | 2026-02-20 | 2026-05-24
| A19520 | Foundation Drawing PSA-2 Feed Gas Compressor Interstage Cooler 13-HE-703_IFD/IFC |  | 2026-02-20 |  |  | 2 | 09-Sep-25 A | 2026-05-24 | 15-Sep-25 A | 2026-02-20 | 2026-05-24
| Design Calculation Report for foundation of PSA-2 Feed Gas Compressor Interstage Cooler 13-HE-703 |  |  | 2026-02-20 |  |  | 53 | 24-Apr-25 A | 2027-01-20 | 15-Sep-25 A | 2026-02-20 | 2027-01-20
| A49340 | Design Calculation Report for foundation of PSA-2 Feed Gas Compressor Interstage Cooler 13-HE-703_RCC |  | 2026-02-20 |  |  | 16 | 16-May-25 A | 2027-01-20 | 22-May-25 A | 2026-02-20 | 2027-01-20
| A49350 | Design Calculation Report for foundation of PSA-2 Feed Gas Compressor Interstage Cooler 13-HE-703_IFA |  | 2026-02-20 |  |  | 3 | 23-May-25 A | 2027-01-20 | 01-Sep-25 A | 2026-02-20 | 2027-01-20
| A19560 | Design Calculation Report for foundation of PSA-2 Feed Gas Compressor Interstage Cooler 13-HE-703_RCA |  | 2026-02-20 |  |  | 16 | 02-Sep-25 A | 2027-01-20 | 09-Sep-25 A | 2026-02-20 | 2027-01-20
| A19570 | Design Calculation Report for foundation of PSA-2 Feed Gas Compressor Interstage Cooler 13-HE-703_IFD/IFC |  | 2026-02-20 |  |  | 2 | 10-Sep-25 A | 2027-01-20 | 15-Sep-25 A | 2026-02-20 | 2027-01-20
| Foundation Drawing PSA-2 OffGas Compressor AfterCooler 13-HE-709 |  |  | 2026-02-20 |  |  | 101 | 20-May-25 A | 2026-05-03 | 10-Oct-25 A | 2026-02-20 | 2026-05-07
| A49430 | Foundation Drawing PSA-2 OffGas Compressor AfterCooler 13-HE-709_IFR |  | 2026-02-20 |  |  | 6 | 30-May-25 A | 2026-05-03 | 13-Jun-25 A | 2026-02-20 | 2026-05-03
| A19790 | Foundation Drawing PSA-2 OffGas Compressor AfterCooler 13-HE-709_RCC |  | 2026-02-20 |  |  | 16 | 20-May-25 A | 2026-05-07 | 21-Jun-25 A | 2026-02-20 | 2026-05-07
| A19800 | Foundation Drawing PSA-2 OffGas Compressor AfterCooler 13-HE-709_IFA |  | 2026-02-20 |  |  | 3 | 22-Jun-25 A | 2026-05-07 | 28-Jun-25 A | 2026-02-20 | 2026-05-07
| A19810 | Foundation Drawing PSA-2 OffGas Compressor AfterCooler 13-HE-709_RCA |  | 2026-02-20 |  |  | 16 | 30-Jun-25 A | 2026-05-07 | 15-Sep-25 A | 2026-02-20 | 2026-05-07
| A19820 | Foundation Drawing PSA-2 OffGas Compressor AfterCooler 13-HE-709_IFD/IFC |  | 2026-02-20 |  |  | 2 | 16-Sep-25 A | 2026-05-07 | 10-Oct-25 A | 2026-02-20 | 2026-05-07
| Design Calculation Report for foundation of PSA-2 OffGas Compressor AfterCooler 13-HE-709 |  |  | 2026-02-20 |  |  | 36 | 28-Apr-25 A | 2027-01-20 | 08-Oct-25 A | 2026-02-20 | 2027-01-20
| A19840 | Design Calculation Report for foundation of PSA-2 OffGas Compressor AfterCooler 13-HE-709_RCC |  | 2026-02-20 |  |  | 16 | 20-May-25 A | 2027-01-20 | 21-Jun-25 A | 2026-02-20 | 2027-01-20
| A19850 | Design Calculation Report for foundation of PSA-2 OffGas Compressor AfterCooler 13-HE-709_IFA |  | 2026-02-20 |  |  | 3 | 22-Jun-25 A | 2027-01-20 | 28-Jun-25 A | 2026-02-20 | 2027-01-20
| A19860 | Design Calculation Report for foundation of PSA-2 OffGas Compressor AfterCooler 13-HE-709_RCA |  | 2026-02-20 |  |  | 16 | 29-Jun-25 A | 2027-01-20 | 08-Sep-25 A | 2026-02-20 | 2027-01-20
| A49440 | Design Calculation Report for foundation of PSA-2 OffGas Compressor AfterCooler 13-HE-709_IFD/IFC |  | 2026-02-20 |  |  | 2 | 09-Sep-25 A | 2027-01-20 | 08-Oct-25 A | 2026-02-20 | 2027-01-20
| Foundation Drawing PSA-2 OffGas Compressor Discharge Dripleg 13-SP-7004 |  |  | 2026-02-20 |  |  | 44 | 16-Apr-25 A | 2026-05-03 | 04-Sep-25 A | 2026-02-20 | 2026-05-03
| A49500 | Foundation Drawing PSA-2 OffGas Compressor Discharge Dripleg 13-SP-7004_RCC |  | 2026-02-20 |  |  | 16 | 08-May-25 A | 2026-05-03 | 14-May-25 A | 2026-02-20 | 2026-05-03
| A49510 | Foundation Drawing PSA-2 OffGas Compressor Discharge Dripleg 13-SP-7004_IFA |  | 2026-02-20 |  |  | 3 | 15-May-25 A | 2026-05-03 | 03-Jun-25 A | 2026-02-20 | 2026-05-03
| A49520 | Foundation Drawing PSA-2 OffGas Compressor Discharge Dripleg 13-SP-7004_RCA |  | 2026-02-20 |  |  | 16 | 04-Jun-25 A | 2026-05-03 | 21-Jun-25 A | 2026-02-20 | 2026-05-03
| A20020 | Foundation Drawing PSA-2 OffGas Compressor Discharge Dripleg 13-SP-7004_IFD/IFC |  | 2026-02-20 |  |  | 2 | 22-Jun-25 A | 2026-05-03 | 04-Sep-25 A | 2026-02-20 | 2026-05-03
| Design Calculation Report for foundation of PSA-2 OffGas Compressor Discharge Dripleg 13-SP-7004 |  |  | 2026-02-20 |  |  | 47 | 16-Apr-25 A | 2027-01-20 | 10-Oct-25 A | 2026-02-20 | 2027-01-20
| A20040 | Design Calculation Report for foundation of PSA-2 OffGas Compressor Discharge Dripleg 13-SP-7004_RCC |  | 2026-02-20 |  |  | 16 | 08-May-25 A | 2027-01-20 | 14-May-25 A | 2026-02-20 | 2027-01-20
| A49530 | Design Calculation Report for foundation of PSA-2 OffGas Compressor Discharge Dripleg 13-SP-7004_IFA |  | 2026-02-20 |  |  | 3 | 15-May-25 A | 2027-01-20 | 03-Jun-25 A | 2026-02-20 | 2027-01-20
| A49540 | Design Calculation Report for foundation of PSA-2 OffGas Compressor Discharge Dripleg 13-SP-7004_RCA |  | 2026-02-20 |  |  | 16 | 04-Jun-25 A | 2027-01-20 | 21-Jun-25 A | 2026-02-20 | 2027-01-20
| A49550 | Design Calculation Report for foundation of PSA-2 OffGas Compressor Discharge Dripleg 13-SP-7004_IFD/IFC |  | 2026-02-20 |  |  | 2 | 29-Sep-25 A | 2027-01-20 | 10-Oct-25 A | 2026-02-20 | 2027-01-20
| Foundation Drawing PSA-2 Slop Drum 70-VV-1415 |  |  | 2026-02-20 |  |  | 146 | 24-Apr-25 A | 2026-05-11 | 2026-03-23 | 2026-03-23 | 2027-01-20 | 218
| A20280 | Foundation Drawing PSA-2 Slop Drum 70-VV-1415_IFR |  | 2026-02-20 |  |  | 6 | 24-Apr-25 A | 2026-05-11 | 15-May-25 A | 2026-02-20 | 2026-05-11
| A49650 | Foundation Drawing PSA-2 Slop Drum 70-VV-1415_RCC |  | 2026-02-20 |  |  | 16 | 16-May-25 A | 2026-05-21 | 22-May-25 A | 2026-02-20 | 2026-05-21
| A49660 | Foundation Drawing PSA-2 Slop Drum 70-VV-1415_IFA |  | 2026-02-20 |  |  | 3 | 2026-02-20 | 2026-12-22 | 2026-02-25 | 2026-02-25 | 2026-12-25 | 218
| A49670 | Foundation Drawing PSA-2 Slop Drum 70-VV-1415_RCA |  | 2026-02-25 |  |  | 16 | 2026-02-25 | 2026-12-28 | 2026-03-19 | 2026-03-19 | 2027-01-18 | 218
| A20320 | Foundation Drawing PSA-2 Slop Drum 70-VV-1415_IFD/IFC |  | 2026-03-19 |  |  | 2 | 2026-03-19 | 2027-01-18 | 2026-03-23 | 2026-03-23 | 2027-01-20 | 218
| Design Calculation Report for foundation of PSA-2 Slop Drum 70-VV-1415 |  |  | 2026-02-20 |  |  | 74 | 01-Aug-25 A | 2027-01-20 | 19-Jan-26 A | 2026-02-20 | 2027-01-20
| A20340 | Design Calculation Report for foundation of PSA-2 Slop Drum 70-VV-1415_RCC |  | 2026-02-20 |  |  | 16 | 08-Aug-25 A | 2027-01-20 | 26-Aug-25 A | 2026-02-20 | 2027-01-20
| A49680 | Design Calculation Report for foundation of PSA-2 Slop Drum 70-VV-1415_IFA |  | 2026-02-20 |  |  | 3 | 27-Aug-25 A | 2027-01-20 | 02-Sep-25 A | 2026-02-20 | 2027-01-20
| A49690 | Design Calculation Report for foundation of PSA-2 Slop Drum 70-VV-1415_RCA |  | 2026-02-20 |  |  | 16 | 25-Aug-25 A | 2027-01-20 | 09-Sep-25 A | 2026-02-20 | 2027-01-20
| A49700 | Design Calculation Report for foundation of PSA-2 Slop Drum 70-VV-1415_IFD/IFC |  | 2026-02-20 |  |  | 2 | 15-Jan-26 A | 2027-01-20 | 19-Jan-26 A | 2026-02-20 | 2027-01-20
| Foundation Drawing PSA-2 Feed Gas Compressor 2nd Stage Discharge Drum 13-VV-707 |  |  | 2026-02-20 |  |  | 76 | 20-Apr-25 A | 2026-05-11 | 23-Dec-25 A | 2026-02-20 | 2026-05-11
| A49200 | Foundation Drawing PSA-2 Feed Gas Compressor 2nd Stage Discharge Drum 13-VV-707_RCC |  | 2026-02-20 |  |  | 16 | 12-May-25 A | 2026-05-11 | 18-May-25 A | 2026-02-20 | 2026-05-11
| A19200 | Foundation Drawing PSA-2 Feed Gas Compressor 2nd Stage Discharge Drum 13-VV-707_IFA |  | 2026-02-20 |  |  | 3 | 19-May-25 A | 2026-05-11 | 11-Jun-25 A | 2026-02-20 | 2026-05-11
| A19210 | Foundation Drawing PSA-2 Feed Gas Compressor 2nd Stage Discharge Drum 13-VV-707_RCA |  | 2026-02-20 |  |  | 16 | 22-Sep-25 A | 2026-05-11 | 10-Oct-25 A | 2026-02-20 | 2026-05-11
| A19220 | Foundation Drawing PSA-2 Feed Gas Compressor 2nd Stage Discharge Drum 13-VV-707_IFD/IFC |  | 2026-02-20 |  |  | 2 | 19-Dec-25 A | 2026-05-11 | 23-Dec-25 A | 2026-02-20 | 2026-05-11
| Design Calculation Report-Foundation of PSA-2 FeedGas Compressor 2ndStage DischargeDrum 13-VV-707 |  |  | 2026-02-20 |  |  | 76 | 20-Apr-25 A | 2027-01-20 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| A49220 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 FEED GAS COMPRESSOR 2ND STAGE DISCHARGE DRUM 13-VV-707_RCC |  | 2026-02-20 |  |  | 16 | 12-May-25 A | 2027-01-20 | 18-May-25 A | 2026-02-20 | 2027-01-20
| A49230 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 FEED GAS COMPRESSOR 2ND STAGE DISCHARGE DRUM 13-VV-707_IFA |  | 2026-02-20 |  |  | 3 | 19-May-25 A | 2027-01-20 | 11-Jun-25 A | 2026-02-20 | 2027-01-20
| A19260 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 FEED GAS COMPRESSOR 2ND STAGE DISCHARGE DRUM 13-VV-707_RCA |  | 2026-02-20 |  |  | 16 | 22-Sep-25 A | 2027-01-20 | 10-Oct-25 A | 2026-02-20 | 2027-01-20
| A19270 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 FEED GAS COMPRESSOR 2ND STAGE DISCHARGE DRUM 13-VV-707_IFD/IFC |  | 2026-02-20 |  |  | 2 | 19-Dec-25 A | 2027-01-20 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| Foundation Drawing PSA-2 Feed Gas Compressor 2nd Stage Suction Drum 13-VV-706 |  |  | 2026-02-20 |  |  | 43 | 16-Apr-25 A | 2026-05-14 | 16-Sep-25 A | 2026-02-20 | 2026-05-18
| A19390 | Foundation Drawing PSA-2 Feed Gas Compressor 2nd Stage Suction Drum 13-VV-706_RCC |  | 2026-02-20 |  |  | 16 | 04-May-25 A | 2026-05-18 | 10-May-25 A | 2026-02-20 | 2026-05-18
| A19400 | Foundation Drawing PSA-2 Feed Gas Compressor 2nd Stage Suction Drum 13-VV-706_IFA |  | 2026-02-20 |  |  | 3 | 11-May-25 A | 2026-05-18 | 11-Jun-25 A | 2026-02-20 | 2026-05-18
| A49270 | Foundation Drawing PSA-2 Feed Gas Compressor 2nd Stage Suction Drum 13-VV-706_RCA |  | 2026-02-20 |  |  | 16 | 12-Jun-25 A | 2026-05-18 | 01-Sep-25 A | 2026-02-20 | 2026-05-18
| A49280 | Foundation Drawing PSA-2 Feed Gas Compressor 2nd Stage Suction Drum 13-VV-706_IFD/IFC |  | 2026-02-20 |  |  | 2 | 02-Sep-25 A | 2026-05-18 | 16-Sep-25 A | 2026-02-20 | 2026-05-18
| Design Calculation Report Foundation of PSA-2 FeedGas Compressor 2ndStage Suction Drum 13-VV-706 |  |  | 2026-02-20 |  |  | 29 | 16-Apr-25 A | 2027-01-20 | 08-Sep-25 A | 2026-02-20 | 2027-01-20
| A19440 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 FEED GAS COMPRESSOR 2ND STAGE SUCTION DRUM 13-VV-706_RCC |  | 2026-02-20 |  |  | 16 | 04-May-25 A | 2027-01-20 | 10-May-25 A | 2026-02-20 | 2027-01-20
| A19450 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 FEED GAS COMPRESSOR 2ND STAGE SUCTION DRUM 13-VV-706_IFA |  | 2026-02-20 |  |  | 3 | 11-May-25 A | 2027-01-20 | 11-Jun-25 A | 2026-02-20 | 2027-01-20
| A19460 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 FEED GAS COMPRESSOR 2ND STAGE SUCTION DRUM 13-VV-706_RCA |  | 2026-02-20 |  |  | 16 | 12-Jun-25 A | 2027-01-20 | 21-Jun-25 A | 2026-02-20 | 2027-01-20
| A49300 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 FEED GAS COMPRESSOR 2ND STAGE SUCTION DRUM 13-VV-706_IFD/IFC |  | 2026-02-20 |  |  | 2 | 22-Jun-25 A | 2027-01-20 | 08-Sep-25 A | 2026-02-20 | 2027-01-20
| Foundation Drawing PSA-2 Feed Gas Compressor 1st Stage Suction Drum 13-VV-705 |  |  | 2026-02-20 |  |  | 66 | 24-Apr-25 A | 2026-05-14 | 23-Dec-25 A | 2026-02-20 | 2026-05-14
| A49360 | Foundation Drawing PSA-2 Feed Gas Compressor 1st Stage Suction Drum 13-VV-705_RCC |  | 2026-02-20 |  |  | 16 | 16-May-25 A | 2026-05-14 | 22-May-25 A | 2026-02-20 | 2026-05-14
| A49370 | Foundation Drawing PSA-2 Feed Gas Compressor 1st Stage Suction Drum 13-VV-705_IFA |  | 2026-02-20 |  |  | 3 | 23-May-25 A | 2026-05-14 | 04-Jun-25 A | 2026-02-20 | 2026-05-14
| A49380 | Foundation Drawing PSA-2 Feed Gas Compressor 1st Stage Suction Drum 13-VV-705_RCA |  | 2026-02-20 |  |  | 16 | 05-Jun-25 A | 2026-05-14 | 21-Jun-25 A | 2026-02-20 | 2026-05-14
| A19620 | Foundation Drawing PSA-2 Feed Gas Compressor 1st Stage Suction Drum 13-VV-705_IFD/IFC |  | 2026-02-20 |  |  | 2 | 19-Dec-25 A | 2026-05-14 | 23-Dec-25 A | 2026-02-20 | 2026-05-14
| Design Calculation Report Foundation of PSA-2 FeedGas Compressor 1stStage Suction Drum 13-VV-705 |  |  | 2026-02-20 |  |  | 66 | 24-Apr-25 A | 2027-01-20 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| A19630 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 FEED GAS COMPRESSOR 1ST STAGE SUCTION DRUM 13-VV-705_IFR |  | 2026-02-20 |  |  | 6 | 24-Apr-25 A | 2027-01-20 | 15-May-25 A | 2026-02-20 | 2027-01-20
| A19640 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 FEED GAS COMPRESSOR 1ST STAGE SUCTION DRUM 13-VV-705_RCC |  | 2026-02-20 |  |  | 16 | 16-May-25 A | 2027-01-20 | 22-May-25 A | 2026-02-20 | 2027-01-20
| A49390 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 FEED GAS COMPRESSOR 1ST STAGE SUCTION DRUM 13-VV-705_IFA |  | 2026-02-20 |  |  | 3 | 23-May-25 A | 2027-01-20 | 03-Jun-25 A | 2026-02-20 | 2027-01-20
| A49400 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 FEED GAS COMPRESSOR 1ST STAGE SUCTION DRUM 13-VV-705_RCA |  | 2026-02-20 |  |  | 16 | 04-Jun-25 A | 2027-01-20 | 21-Jun-25 A | 2026-02-20 | 2027-01-20
| A49410 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 FEED GAS COMPRESSOR 1ST STAGE SUCTION DRUM 13-VV-705_IFD/IFC |  | 2026-02-20 |  |  | 2 | 19-Dec-25 A | 2027-01-20 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| Foundation Drawing PSA-2 OffGas Compressor 2nd Stage Suction Drum 13-VV-713 |  |  | 2026-02-20 |  |  | 47 | 15-Apr-25 A | 2026-05-14 | 29-Jul-25 A | 2026-02-20 | 2026-06-22
| A19690 | Foundation Drawing PSA-2 OffGas Compressor 2nd Stage Suction Drum 13-VV-713_RCC |  | 2026-02-20 |  |  | 16 | 07-May-25 A | 2026-06-22 | 13-Jun-25 A | 2026-02-20 | 2026-06-22
| A19700 | Foundation Drawing PSA-2 OffGas Compressor 2nd Stage Suction Drum 13-VV-713_IFA |  | 2026-02-20 |  |  | 3 | 16-Jun-25 A | 2026-06-22 | 30-Jun-25 A | 2026-02-20 | 2026-06-22
| A19710 | Foundation Drawing PSA-2 OffGas Compressor 2nd Stage Suction Drum 13-VV-713_RCA |  | 2026-02-20 |  |  | 16 | 16-Jun-25 A | 2026-06-22 | 14-Jul-25 A | 2026-02-20 | 2026-06-22
| A19720 | Foundation Drawing PSA-2 OffGas Compressor 2nd Stage Suction Drum 13-VV-713_IFD/IFC |  | 2026-02-20 |  |  | 2 | 15-Jul-25 A | 2026-06-22 | 29-Jul-25 A | 2026-02-20 | 2026-06-22
| Design Calculation Report Foundation of PSA-2 OffGas Compressor 2ndStage Suction Drum 13-VV-713 |  |  | 2026-02-20 |  |  | 50 | 20-Apr-25 A | 2027-01-20 | 10-Oct-25 A | 2026-02-20 | 2027-01-20
| A19740 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 OFFGAS COMPRESSOR 2ND STAGE SUCTION DRUM 13-VV-713_RCC |  | 2026-02-20 |  |  | 16 | 12-May-25 A | 2027-01-20 | 21-Jun-25 A | 2026-02-20 | 2027-01-20
| A19750 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 OFFGAS COMPRESSOR 2ND STAGE SUCTION DRUM 13-VV-713_IFA |  | 2026-02-20 |  |  | 3 | 22-Jun-25 A | 2027-01-20 | 28-Jun-25 A | 2026-02-20 | 2027-01-20
| A19760 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 OFFGAS COMPRESSOR 2ND STAGE SUCTION DRUM 13-VV-713_RCA |  | 2026-02-20 |  |  | 16 | 01-Jul-25 A | 2027-01-20 | 04-Sep-25 A | 2026-02-20 | 2027-01-20
| A49420 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 OFFGAS COMPRESSOR 2ND STAGE SUCTION DRUM 13-VV-713_IFD/IFC |  | 2026-02-20 |  |  | 2 | 08-Sep-25 A | 2027-01-20 | 10-Oct-25 A | 2026-02-20 | 2027-01-20
| Foundation Drawing PSA-2 OffGas Buffer Drum 13-VV-712 |  |  | 2026-02-20 |  |  | 21 | 22-Apr-25 A | 2026-05-14 | 10-Oct-25 A | 2026-02-20 | 2026-05-14
| A49460 | Foundation Drawing PSA-2 OffGas Buffer Drum 13-VV-712_RCC |  | 2026-02-20 |  |  | 16 | 14-May-25 A | 2026-05-14 | 29-May-25 A | 2026-02-20 | 2026-05-14
| A19900 | Foundation Drawing PSA-2 OffGas Buffer Drum 13-VV-712_IFA |  | 2026-02-20 |  |  | 3 | 30-May-25 A | 2026-05-14 | 21-Jun-25 A | 2026-02-20 | 2026-05-14
| A19910 | Foundation Drawing PSA-2 OffGas Buffer Drum 13-VV-712_RCA |  | 2026-02-20 |  |  | 16 | 22-Jun-25 A | 2026-05-14 | 28-Jun-25 A | 2026-02-20 | 2026-05-14
| A19920 | Foundation Drawing PSA-2 OffGas Buffer Drum 13-VV-712_IFD/IFC |  | 2026-02-20 |  |  | 2 | 26-Sep-25 A | 2026-05-14 | 10-Oct-25 A | 2026-02-20 | 2026-05-14
| Design Calculation Report for foundation of PSA-2 OffGas Buffer Drum 13-VV-712 |  |  | 2026-02-20 |  |  | 47 | 22-Apr-25 A | 2027-01-20 | 10-Oct-25 A | 2026-02-20 | 2027-01-20
| A49480 | Design Calculation Report for foundation of PSA-2 OffGas Buffer Drum 13-VV-712_RCC |  | 2026-02-20 |  |  | 16 | 14-May-25 A | 2027-01-20 | 03-Jun-25 A | 2026-02-20 | 2027-01-20
| A49490 | Design Calculation Report for foundation of PSA-2 OffGas Buffer Drum 13-VV-712_IFA |  | 2026-02-20 |  |  | 3 | 04-Jun-25 A | 2027-01-20 | 21-Jun-25 A | 2026-02-20 | 2027-01-20
| A19960 | Design Calculation Report for foundation of PSA-2 OffGas Buffer Drum 13-VV-712_RCA |  | 2026-02-20 |  |  | 16 | 22-Jun-25 A | 2027-01-20 | 06-Sep-25 A | 2026-02-20 | 2027-01-20
| A19970 | Design Calculation Report for foundation of PSA-2 OffGas Buffer Drum 13-VV-712_IFD/IFC |  | 2026-02-20 |  |  | 2 | 26-Sep-25 A | 2027-01-20 | 10-Oct-25 A | 2026-02-20 | 2027-01-20
| Pile Layout Compressor Shelter & SR8001 |  |  | 2026-02-20 |  |  | 39 | 01-Jul-25 A | 2026-02-21 | 13-Sep-25 A | 2026-02-20 | 2026-02-21
| A17640 | Pile Layout Compressor Shelter & SR8001_RCC |  | 2026-02-20 |  |  | 16 | 14-Jul-25 A | 2026-02-21 | 22-Aug-25 A | 2026-02-20 | 2026-02-21
| A17650 | Pile Layout Compressor Shelter & SR8001_IFA |  | 2026-02-20 |  |  | 3 | 25-Aug-25 A | 2026-02-21 | 30-Aug-25 A | 2026-02-20 | 2026-02-21
| A17660 | Pile Layout Compressor Shelter & SR8001_RCA |  | 2026-02-20 |  |  | 16 | 25-Aug-25 A | 2026-02-21 | 06-Sep-25 A | 2026-02-20 | 2026-02-21
| A17670 | Pile Layout Compressor Shelter & SR8001_IFD/IFC |  | 2026-02-20 |  |  | 2 | 08-Sep-25 A | 2026-02-21 | 13-Sep-25 A | 2026-02-20 | 2026-02-21
| Pile Reinforcement Drawing |  |  | 2026-02-20 |  |  | 39 | 01-Jul-25 A | 2026-02-21 | 18-Jul-25 A | 2026-02-20 | 2027-01-20
| A17480 | Pile Reinforcement Drawing_IFR |  | 2026-02-20 |  |  | 6 | 01-Jul-25 A | 2026-02-21 | 18-Jul-25 A | 2026-02-20 | 2026-02-21
| A17490 | Pile Reinforcement Drawing_RCC |  | 2026-02-20 |  |  | 16 | 01-Jul-25 A | 2027-01-20 | 18-Jul-25 A | 2026-02-20 | 2027-01-20
| A17500 | Pile Reinforcement Drawing_IFA |  | 2026-02-20 |  |  | 3 | 01-Jul-25 A | 2027-01-20 | 18-Jul-25 A | 2026-02-20 | 2027-01-20
| A17510 | Pile Reinforcement Drawing_RCA |  | 2026-02-20 |  |  | 16 | 01-Jul-25 A | 2027-01-20 | 18-Jul-25 A | 2026-02-20 | 2027-01-20
| A17520 | Pile Reinforcement Drawing_IFD/IFC |  | 2026-02-20 |  |  | 2 | 01-Jul-25 A | 2027-01-20 | 18-Jul-25 A | 2026-02-20 | 2027-01-20
| Pile Layout PSA-2 FeedGas Compressor 13-KC-701 |  |  | 2026-02-20 |  |  | 149 | 10-Apr-25 A | 2026-02-21 | 15-Sep-25 A | 2026-02-20 | 2026-02-21
| A48320 | Pile Layout PSA-2 FeedGas Compressor 13-KC-701_RCC |  | 2026-02-20 |  |  | 16 | 16-Aug-25 A | 2026-02-21 | 22-Aug-25 A | 2026-02-20 | 2026-02-21
| A17550 | Pile Layout PSA-2 FeedGas Compressor 13-KC-701_IFA |  | 2026-02-20 |  |  | 3 | 22-Aug-25 A | 2026-02-21 | 29-Aug-25 A | 2026-02-20 | 2026-02-21
| A17560 | Pile Layout PSA-2 FeedGas Compressor 13-KC-701_RCA |  | 2026-02-20 |  |  | 16 | 18-Aug-25 A | 2026-02-21 | 05-Sep-25 A | 2026-02-20 | 2026-02-21
| A17570 | Pile Layout PSA-2 FeedGas Compressor 13-KC-701_IFD/IFC |  | 2026-02-20 |  |  | 2 | 08-Sep-25 A | 2026-02-21 | 15-Sep-25 A | 2026-02-20 | 2026-02-21
| Pile Layout PSA-2 OffGas Compressor 13-KC-702 |  |  | 2026-02-20 |  |  | 39 | 01-Jul-25 A | 2026-02-21 | 15-Sep-25 A | 2026-02-20 | 2026-02-21
| A17590 | Pile Layout PSA-2 OffGas Compressor 13-KC-702_RCC |  | 2026-02-20 |  |  | 16 | 14-Jul-25 A | 2026-02-21 | 22-Aug-25 A | 2026-02-20 | 2026-02-21
| A17600 | Pile Layout PSA-2 OffGas Compressor 13-KC-702_IFA |  | 2026-02-20 |  |  | 3 | 25-Aug-25 A | 2026-02-21 | 30-Aug-25 A | 2026-02-20 | 2026-02-21
| A17610 | Pile Layout PSA-2 OffGas Compressor 13-KC-702_RCA |  | 2026-02-20 |  |  | 16 | 01-Aug-25 A | 2026-02-21 | 06-Sep-25 A | 2026-02-20 | 2026-02-21
| A17620 | Pile Layout PSA-2 OffGas Compressor 13-KC-702_IFD/IFC |  | 2026-02-20 |  |  | 2 | 08-Sep-25 A | 2026-02-21 | 15-Sep-25 A | 2026-02-20 | 2026-02-21
| Pile Layout PSA-2 Unit - Hydrogen Purification 13-XA-710 |  |  | 2026-02-20 |  |  | 38 | 30-Jun-25 A | 2026-03-02 | 13-Sep-25 A | 2026-02-20 | 2026-03-02
| A48340 | Pile Layout PSA-2 Unit - Hydrogen Purification 13-XA-710_RCC |  | 2026-02-20 |  |  | 16 | 14-Jul-25 A | 2026-03-02 | 22-Aug-25 A | 2026-02-20 | 2026-03-02
| A48350 | Pile Layout PSA-2 Unit - Hydrogen Purification 13-XA-710_IFA |  | 2026-02-20 |  |  | 3 | 25-Aug-25 A | 2026-03-02 | 30-Aug-25 A | 2026-02-20 | 2026-03-02
| A48360 | Pile Layout PSA-2 Unit - Hydrogen Purification 13-XA-710_RCA |  | 2026-02-20 |  |  | 16 | 19-Aug-25 A | 2026-03-02 | 06-Sep-25 A | 2026-02-20 | 2026-03-02
| A48370 | Pile Layout PSA-2 Unit - Hydrogen Purification 13-XA-710_IFD/IFC |  | 2026-02-20 |  |  | 2 | 08-Sep-25 A | 2026-03-02 | 13-Sep-25 A | 2026-02-20 | 2026-03-02
| Pile Layout PSA-2 OffGas Buffer Drum 13-VV-712 |  |  | 2026-02-20 |  |  | 39 | 02-Jun-25 A | 2026-03-02 | 05-Jul-25 A | 2026-02-20 | 2026-03-02
| A17680 | Pile Layout PSA-2 OffGas Buffer Drum 13-VV-712_IFR |  | 2026-02-20 |  |  | 6 | 02-Jun-25 A | 2026-03-02 | 07-Jun-25 A | 2026-02-20 | 2026-03-02
| A17690 | Pile Layout PSA-2 OffGas Buffer Drum 13-VV-712_RCC |  | 2026-02-20 |  |  | 16 | 06-Jun-25 A | 2026-03-02 | 16-Jun-25 A | 2026-02-20 | 2026-03-02
| A17700 | Pile Layout PSA-2 OffGas Buffer Drum 13-VV-712_IFA |  | 2026-02-20 |  |  | 3 | 17-Jun-25 A | 2026-03-02 | 23-Jun-25 A | 2026-02-20 | 2026-03-02
| A17710 | Pile Layout PSA-2 OffGas Buffer Drum 13-VV-712_RCA |  | 2026-02-20 |  |  | 16 | 17-Jun-25 A | 2026-03-02 | 28-Jun-25 A | 2026-02-20 | 2026-03-02
| A17720 | Pile Layout PSA-2 OffGas Buffer Drum 13-VV-712_IFD/IFC |  | 2026-02-20 |  |  | 2 | 30-Jun-25 A | 2026-03-02 | 05-Jul-25 A | 2026-02-20 | 2026-03-02
| Structure & Foundation design - Buildings/Shelters/Electrical |  |  | 2026-02-20 |  |  | 321 | 05-Feb-25 A | 2026-03-14 | 2026-04-07 | 2026-04-07 | 2027-01-20 | 206
| Structural GA, Section and Details - Compressor Shelter |  |  | 2026-02-20 |  |  | 61 | 01-Oct-25 A | 2026-05-19 | 19-Jan-26 A | 2026-02-20 | 2026-05-19
| A48880 | Structural GA, Section and Details - Compressor Shelter_IFR |  | 2026-02-20 |  |  | 17 | 01-Oct-25 A | 2026-05-19 | 07-Oct-25 A | 2026-02-20 | 2026-05-19
| A48890 | Structural GA, Section and Details - Compressor Shelter_RCC |  | 2026-02-20 |  |  | 16 | 08-Oct-25 A | 2026-05-19 | 23-Oct-25 A | 2026-02-20 | 2026-05-19
| A48900 | Structural GA, Section and Details - Compressor Shelter_IFA |  | 2026-02-20 |  |  | 11 | 23-Oct-25 A | 2026-05-19 | 24-Oct-25 A | 2026-02-20 | 2026-05-19
| A48910 | Structural GA, Section and Details - Compressor Shelter_RCA |  | 2026-02-20 |  |  | 16 | 19-Dec-25 A | 2026-05-19 | 09-Jan-26 A | 2026-02-20 | 2026-05-19
| A48920 | Structural GA, Section and Details - Compressor Shelter_IFD/IFC |  | 2026-02-20 |  |  | 6 | 09-Jan-26 A | 2026-05-19 | 19-Jan-26 A | 2026-02-20 | 2026-05-19
| Design Calculation Report for structural steel- Compressor Shelter |  |  | 2026-02-20 |  |  | 118 | 01-Sep-25 A | 2026-12-07 | 2026-04-07 | 2026-04-07 | 2027-01-20 | 206
| A18690 | Design Calculation Report for structural steel- Compressor Shelter_RCC |  | 2026-02-20 |  |  | 16 | 10-Sep-25 A | 2026-12-07 | 01-Oct-25 A | 2026-02-20 | 2026-12-07
| A18700 | Design Calculation Report for structural steel- Compressor Shelter_IFA |  | 2026-02-20 |  |  | 11 | 2026-02-20 | 2026-12-07 | 2026-03-09 | 2026-03-09 | 2026-12-22 | 206
| A18710 | Design Calculation Report for structural steel- Compressor Shelter_RCA |  | 2026-03-09 |  |  | 16 | 2026-03-09 | 2026-12-22 | 2026-03-30 | 2026-03-30 | 2027-01-13 | 206
| A48960 | Design Calculation Report for structural steel- Compressor Shelter_IFD/IFC |  | 2026-03-31 |  |  | 6 | 2026-03-31 | 2027-01-13 | 2026-04-07 | 2026-04-07 | 2027-01-20 | 206
| Foundation Drawing- Compressor Shelter |  |  | 2026-02-20 |  |  | 107 | 01-Jul-25 A | 2027-01-20 | 21-Jan-26 A | 2026-02-20 | 2027-01-20
| A18640 | Foundation Drawing- Compressor Shelter_RCC |  | 2026-02-20 |  |  | 16 | 15-Jul-25 A | 2027-01-20 | 22-Aug-25 A | 2026-02-20 | 2027-01-20
| A18650 | Foundation Drawing- Compressor Shelter_IFA |  | 2026-02-20 |  |  | 3 | 20-Oct-25 A | 2027-01-20 | 30-Oct-25 A | 2026-02-20 | 2027-01-20
| A48930 | Foundation Drawing- Compressor Shelter_RCA |  | 2026-02-20 |  |  | 16 | 31-Oct-25 A | 2027-01-20 | 14-Nov-25 A | 2026-02-20 | 2027-01-20
| A48940 | Foundation Drawing- Compressor Shelter_IFD/IFC |  | 2026-02-20 |  |  | 2 | 19-Jan-26 A | 2027-01-20 | 21-Jan-26 A | 2026-02-20 | 2027-01-20
| Design Calculation Report for Foundations- Compressor Shelter |  |  | 2026-02-20 |  |  | 104 | 28-Jun-25 A | 2027-01-20 | 21-Jan-26 A | 2026-02-20 | 2027-01-20
| A48980 | Design Calculation Report for Foundations- Compressor Shelter_RCC |  | 2026-02-20 |  |  | 16 | 16-Jul-25 A | 2027-01-20 | 22-Aug-25 A | 2026-02-20 | 2027-01-20
| A48990 | Design Calculation Report for Foundations- Compressor Shelter_IFA |  | 2026-02-20 |  |  | 3 | 25-Aug-25 A | 2027-01-20 | 29-Aug-25 A | 2026-02-20 | 2027-01-20
| A49000 | Design Calculation Report for Foundations- Compressor Shelter_RCA |  | 2026-02-20 |  |  | 16 | 20-Aug-25 A | 2027-01-20 | 05-Sep-25 A | 2026-02-20 | 2027-01-20
| A49010 | Design Calculation Report for Foundations- Compressor Shelter_IFD/IFC |  | 2026-02-20 |  |  | 2 | 19-Jan-26 A | 2027-01-20 | 21-Jan-26 A | 2026-02-20 | 2027-01-20
| Architectural Drawing- Substation, SIS Building |  |  | 2026-02-20 |  |  | 218 | 05-Feb-25 A | 2026-03-14 | 18-Sep-25 A | 2026-02-20 | 2026-03-14
| A17790 | Architectural Drawing- Substation, SIS Building_RCC |  | 2026-02-20 |  |  | 16 | 12-Mar-25 A | 2026-03-14 | 20-Apr-25 A | 2026-02-20 | 2026-03-14
| A48390 | Architectural Drawing- Substation, SIS Building_IFA |  | 2026-02-20 |  |  | 6 | 21-Apr-25 A | 2026-03-14 | 19-Jun-25 A | 2026-02-20 | 2026-03-14
| A48400 | Architectural Drawing- Substation, SIS Building_RCA |  | 2026-02-20 |  |  | 16 | 20-Jun-25 A | 2026-03-14 | 04-Sep-25 A | 2026-02-20 | 2026-03-14
| A48410 | Architectural Drawing- Substation, SIS Building_IFD/IFC |  | 2026-02-20 |  |  | 2 | 08-Sep-25 A | 2026-03-14 | 18-Sep-25 A | 2026-02-20 | 2026-03-14
| Structural Concrete GA, Section and Details- Substation, SIS Building |  |  | 2026-02-20 |  |  | 80 | 21-Apr-25 A | 2026-03-14 | 29-Aug-25 A | 2026-02-20 | 2026-03-14
| A48430 | Structural Concrete GA, Section and Details- Substation, SIS Building_RCC |  | 2026-02-20 |  |  | 16 | 13-May-25 A | 2026-03-14 | 03-Jun-25 A | 2026-02-20 | 2026-03-14
| A48440 | Structural Concrete GA, Section and Details- Substation, SIS Building_IFA |  | 2026-02-20 |  |  | 6 | 04-Jun-25 A | 2026-03-14 | 15-Aug-25 A | 2026-02-20 | 2026-03-14
| A48450 | Structural Concrete GA, Section and Details- Substation, SIS Building_RCA |  | 2026-02-20 |  |  | 16 | 07-Aug-25 A | 2026-03-14 | 22-Aug-25 A | 2026-02-20 | 2026-03-14
| A48460 | Structural Concrete GA, Section and Details- Substation, SIS Building_IFD/IFC |  | 2026-02-20 |  |  | 2 | 22-Aug-25 A | 2026-03-14 | 29-Aug-25 A | 2026-02-20 | 2026-03-14
| Design Calculation report for Substation, SIS Building |  |  | 2026-02-20 |  |  | 105 | 20-Apr-25 A | 2026-03-14 | 29-Aug-25 A | 2026-02-20 | 2026-03-14
| A17940 | Design Calculation report for Substation, SIS Building_RCC |  | 2026-02-20 |  |  | 16 | 12-May-25 A | 2026-03-14 | 05-Jun-25 A | 2026-02-20 | 2026-03-14
| A48480 | Design Calculation report for Substation, SIS Building_IFA |  | 2026-02-20 |  |  | 6 | 06-Jun-25 A | 2026-03-14 | 15-Aug-25 A | 2026-02-20 | 2026-03-14
| A48490 | Design Calculation report for Substation, SIS Building_RCA |  | 2026-02-20 |  |  | 16 | 16-Jun-25 A | 2026-03-14 | 22-Aug-25 A | 2026-02-20 | 2026-03-14
| A48500 | Design Calculation report for Substation, SIS Building_IFD/IFC |  | 2026-02-20 |  |  | 2 | 25-Aug-25 A | 2026-03-14 | 29-Aug-25 A | 2026-02-20 | 2026-03-14
| Foundation Layout, Section and Details- Substation, SIS Building |  |  | 2026-02-20 |  |  | 107 | 21-Apr-25 A | 2026-03-14 | 29-Aug-25 A | 2026-02-20 | 2026-03-14
| A17840 | Foundation Layout, Section and Details- Substation, SIS Building_RCC |  | 2026-02-20 |  |  | 16 | 13-May-25 A | 2026-03-14 | 29-May-25 A | 2026-02-20 | 2026-03-14
| A17850 | Foundation Layout, Section and Details- Substation, SIS Building_IFA |  | 2026-02-20 |  |  | 6 | 30-May-25 A | 2026-03-14 | 21-Jun-25 A | 2026-02-20 | 2026-03-14
| A17860 | Foundation Layout, Section and Details- Substation, SIS Building_RCA |  | 2026-02-20 |  |  | 16 | 23-Jun-25 A | 2026-03-14 | 22-Aug-25 A | 2026-02-20 | 2026-03-14
| A17870 | Foundation Layout, Section and Details- Substation, SIS Building_IFD/IFC |  | 2026-02-20 |  |  | 2 | 25-Aug-25 A | 2026-03-14 | 29-Aug-25 A | 2026-02-20 | 2026-03-14
| Structure design - U/G facilities |  |  | 2026-02-20 |  |  | 190 | 10-Jun-25 A | 2026-03-19 | 2026-04-21 | 2026-04-21 | 2027-01-20 | 196
| Sump Pit plan and details Accidentally Oil contaminated water collection 70-TD-1407 |  |  | 2026-02-20 |  |  | 87 | 18-Aug-25 A | 2026-05-06 | 23-Dec-25 A | 2026-02-20 | 2026-05-06
| A20390 | Sump Pit plan and details Accidentally Oil contaminated water collection 70-TD-1407_RCC |  | 2026-02-20 |  |  | 16 | 20-Aug-25 A | 2026-05-06 | 27-Aug-25 A | 2026-02-20 | 2026-05-06
| A20400 | Sump Pit plan and details Accidentally Oil contaminated water collection 70-TD-1407_IFA |  | 2026-02-20 |  |  | 3 | 28-Aug-25 A | 2026-05-06 | 02-Sep-25 A | 2026-02-20 | 2026-05-06
| A49710 | Sump Pit plan and details Accidentally Oil contaminated water collection 70-TD-1407_RCA |  | 2026-02-20 |  |  | 16 | 27-Aug-25 A | 2026-05-06 | 09-Sep-25 A | 2026-02-20 | 2026-05-06
| A49720 | Sump Pit plan and details Accidentally Oil contaminated water collection 70-TD-1407_IFD/IFC |  | 2026-02-20 |  |  | 2 | 19-Dec-25 A | 2026-05-06 | 23-Dec-25 A | 2026-02-20 | 2026-05-06
| Design Calculation Report for Accidentally Oil contaminated water collection Sump Pit 70-TD-1407 |  |  | 2026-02-20 |  |  | 86 | 23-Aug-25 A | 2026-05-06 | 23-Dec-25 A | 2026-02-20 | 2026-05-06
| A20440 | Design Calculation Report for Accidentally Oil contaminated water collection Sump Pit 70-TD-1407_RCC |  | 2026-02-20 |  |  | 16 | 29-Aug-25 A | 2026-05-06 | 22-Sep-25 A | 2026-02-20 | 2026-05-06
| A20450 | Design Calculation Report for Accidentally Oil contaminated water collection Sump Pit 70-TD-1407_IFA |  | 2026-02-20 |  |  | 3 | 23-Sep-25 A | 2026-05-06 | 29-Sep-25 A | 2026-02-20 | 2026-05-06
| A20460 | Design Calculation Report for Accidentally Oil contaminated water collection Sump Pit 70-TD-1407_RCA |  | 2026-02-20 |  |  | 16 | 25-Sep-25 A | 2026-05-06 | 04-Oct-25 A | 2026-02-20 | 2026-05-06
| A49740 | Design Calculation Report for Accidentally Oil contaminated water collection Sump Pit 70-TD-1407_IFD/IFC |  | 2026-02-20 |  |  | 2 | 19-Dec-25 A | 2026-05-06 | 23-Dec-25 A | 2026-02-20 | 2026-05-06
| Sump Pit plan and details Oily Water 70-TD-1408 |  |  | 2026-02-20 |  |  | 98 | 01-Aug-25 A | 2026-05-06 | 13-Jan-26 A | 2026-02-20 | 2026-05-06
| A49760 | Sump Pit plan and details Oily Water 70-TD-1408_RCC |  | 2026-02-20 |  |  | 16 | 15-Aug-25 A | 2026-05-06 | 26-Aug-25 A | 2026-02-20 | 2026-05-06
| A20500 | Sump Pit plan and details Oily Water 70-TD-1408_IFA |  | 2026-02-20 |  |  | 3 | 29-Aug-25 A | 2026-05-06 | 02-Sep-25 A | 2026-02-20 | 2026-05-06
| A20510 | Sump Pit plan and details Oily Water 70-TD-1408_RCA |  | 2026-02-20 |  |  | 16 | 01-Sep-25 A | 2026-05-06 | 09-Sep-25 A | 2026-02-20 | 2026-05-06
| A20520 | Sump Pit plan and details Oily Water 70-TD-1408_IFD/IFC |  | 2026-02-20 |  |  | 2 | 09-Jan-26 A | 2026-05-06 | 13-Jan-26 A | 2026-02-20 | 2026-05-06
| Design Calculation Report for Oily Water Sump Pit 70-TD-1408 |  |  | 2026-02-20 |  |  | 102 | 23-Aug-25 A | 2026-05-06 | 13-Jan-26 A | 2026-02-20 | 2026-05-06
| A49780 | Design Calculation Report for Oily Water Sump Pit 70-TD-1408_RCC |  | 2026-02-20 |  |  | 16 | 15-Sep-25 A | 2026-05-06 | 16-Oct-25 A | 2026-02-20 | 2026-05-06
| A49790 | Design Calculation Report for Oily Water Sump Pit 70-TD-1408_IFA |  | 2026-02-20 |  |  | 3 | 17-Oct-25 A | 2026-05-06 | 23-Oct-25 A | 2026-02-20 | 2026-05-06
| A20560 | Design Calculation Report for Oily Water Sump Pit 70-TD-1408_RCA |  | 2026-02-20 |  |  | 16 | 19-Dec-25 A | 2026-05-06 | 09-Jan-26 A | 2026-02-20 | 2026-05-06
| A20570 | Design Calculation Report for Oily Water Sump Pit 70-TD-1408_IFD/IFC |  | 2026-02-20 |  |  | 2 | 09-Jan-26 A | 2026-05-06 | 13-Jan-26 A | 2026-02-20 | 2026-05-06
| Sump Pit plan and details Sanitary Waste Water 70-TD-1409 |  |  | 2026-02-20 |  |  | 82 | 23-Aug-25 A | 2026-10-26 | 23-Dec-25 A | 2026-02-20 | 2026-10-26
| A49800 | Sump Pit plan and details Sanitary Waste Water 70-TD-1409_RCC |  | 2026-02-20 |  |  | 16 | 01-Sep-25 A | 2026-10-26 | 24-Sep-25 A | 2026-02-20 | 2026-10-26
| A49810 | Sump Pit plan and details Sanitary Waste Water 70-TD-1409_IFA |  | 2026-02-20 |  |  | 3 | 25-Sep-25 A | 2026-10-26 | 01-Oct-25 A | 2026-02-20 | 2026-10-26
| A49820 | Sump Pit plan and details Sanitary Waste Water 70-TD-1409_RCA |  | 2026-02-20 |  |  | 16 | 29-Sep-25 A | 2026-10-26 | 08-Oct-25 A | 2026-02-20 | 2026-10-26
| A20620 | Sump Pit plan and details Sanitary Waste Water 70-TD-1409_IFD/IFC |  | 2026-02-20 |  |  | 2 | 19-Dec-25 A | 2026-10-26 | 23-Dec-25 A | 2026-02-20 | 2026-10-26
| Design Calculation Report for Sanitary Waste Water Sump Pit 70-TD-1409 |  |  | 2026-02-20 |  |  | 82 | 23-Aug-25 A | 2026-10-26 | 23-Dec-25 A | 2026-02-20 | 2026-10-26
| A20640 | Design Calculation Report for Sanitary Waste Water Sump Pit 70-TD-1409_RCC |  | 2026-02-20 |  |  | 16 | 15-Sep-25 A | 2026-10-26 | 13-Oct-25 A | 2026-02-20 | 2026-10-26
| A49830 | Design Calculation Report for Sanitary Waste Water Sump Pit 70-TD-1409_IFA |  | 2026-02-20 |  |  | 3 | 14-Oct-25 A | 2026-10-26 | 20-Oct-25 A | 2026-02-20 | 2026-10-26
| A49840 | Design Calculation Report for Sanitary Waste Water Sump Pit 70-TD-1409_RCA |  | 2026-02-20 |  |  | 16 | 15-Oct-25 A | 2026-10-26 | 24-Oct-25 A | 2026-02-20 | 2026-10-26
| A49850 | Design Calculation Report for Sanitary Waste Water Sump Pit 70-TD-1409_IFD/IFC |  | 2026-02-20 |  |  | 2 | 19-Dec-25 A | 2026-10-26 | 23-Dec-25 A | 2026-02-20 | 2026-10-26
| Transformer Foundation Drawing for Bay-A to Bay-E |  |  | 2026-02-20 |  |  | 43 | 2026-02-20 | 2026-11-23 | 2026-04-21 | 2026-04-21 | 2027-01-20 | 196
| A20690 | Transformer Foundation Drawing for Bay-A to Bay-E_RCC |  | 2026-02-27 |  |  | 16 | 2026-02-27 | 2026-11-30 | 2026-03-23 | 2026-03-23 | 2026-12-22 | 196
| A20700 | Transformer Foundation Drawing for Bay-A to Bay-E_IFA |  | 2026-03-23 |  |  | 3 | 2026-03-23 | 2026-12-22 | 2026-03-26 | 2026-03-26 | 2026-12-25 | 196
| A49860 | Transformer Foundation Drawing for Bay-A to Bay-E_RCA |  | 2026-03-26 |  |  | 16 | 2026-03-26 | 2026-12-28 | 2026-04-17 | 2026-04-17 | 2027-01-18 | 196
| A49870 | Transformer Foundation Drawing for Bay-A to Bay-E_IFD/IFC |  | 2026-04-17 |  |  | 2 | 2026-04-17 | 2027-01-18 | 2026-04-21 | 2026-04-21 | 2027-01-20 | 196
| Design Calculation Report for Foundation- Transformer for Bay-A to Bay-E |  |  | 2026-02-20 |  |  | 43 | 2026-02-20 | 2026-11-23 | 2026-04-21 | 2026-04-21 | 2027-01-20 | 196
| A49890 | Design Calculation Report for Foundation- Transformer for Bay-A to Bay-E_RCC |  | 2026-02-27 |  |  | 16 | 2026-02-27 | 2026-11-30 | 2026-03-23 | 2026-03-23 | 2026-12-22 | 196
| A20750 | Design Calculation Report for Foundation- Transformer for Bay-A to Bay-E_IFA |  | 2026-03-23 |  |  | 3 | 2026-03-23 | 2026-12-22 | 2026-03-26 | 2026-03-26 | 2026-12-25 | 196
| A20760 | Design Calculation Report for Foundation- Transformer for Bay-A to Bay-E_RCA |  | 2026-03-26 |  |  | 16 | 2026-03-26 | 2026-12-28 | 2026-04-17 | 2026-04-17 | 2027-01-18 | 196
| A20770 | Design Calculation Report for Foundation- Transformer for Bay-A to Bay-E_IFD/IFC |  | 2026-04-17 |  |  | 2 | 2026-04-17 | 2027-01-18 | 2026-04-21 | 2026-04-21 | 2027-01-20 | 196
| Firewater Valve Pit Plan, Section and Details |  |  | 2026-02-20 |  |  | 42 | 01-Oct-25 A | 2026-04-20 | 23-Dec-25 A | 2026-02-20 | 2026-04-20
| A21390 | Firewater Valve Pit Plan, Section and Details_RCC |  | 2026-02-20 |  |  | 16 | 06-Oct-25 A | 2026-04-20 | 17-Oct-25 A | 2026-02-20 | 2026-04-20
| A21400 | Firewater Valve Pit Plan, Section and Details_IFA |  | 2026-02-20 |  |  | 3 | 20-Oct-25 A | 2026-04-20 | 27-Oct-25 A | 2026-02-20 | 2026-04-20
| A50150 | Firewater Valve Pit Plan, Section and Details_RCA |  | 2026-02-20 |  |  | 16 | 28-Oct-25 A | 2026-04-20 | 21-Nov-25 A | 2026-02-20 | 2026-04-20
| A50160 | Firewater Valve Pit Plan, Section and Details_IFD/IFC |  | 2026-02-20 |  |  | 2 | 19-Dec-25 A | 2026-04-20 | 23-Dec-25 A | 2026-02-20 | 2026-04-20
| Cooling water Valve Pit Plan, Section and Details |  |  | 2026-02-20 |  |  | 55 | 01-Oct-25 A | 2026-06-28 | 23-Dec-25 A | 2026-02-20 | 2026-06-28
| A21440 | Cooling water Valve Pit Plan, Section and Details_RCC |  | 2026-02-20 |  |  | 16 | 11-Oct-25 A | 2026-06-28 | 24-Oct-25 A | 2026-02-20 | 2026-06-28
| A21450 | Cooling water Valve Pit Plan, Section and Details_IFA |  | 2026-02-20 |  |  | 3 | 25-Oct-25 A | 2026-06-28 | 20-Nov-25 A | 2026-02-20 | 2026-06-28
| A21460 | Cooling water Valve Pit Plan, Section and Details_RCA |  | 2026-02-20 |  |  | 16 | 31-Oct-25 A | 2026-06-28 | 21-Nov-25 A | 2026-02-20 | 2026-06-28
| A50180 | Cooling water Valve Pit Plan, Section and Details_IFD/IFC |  | 2026-02-20 |  |  | 2 | 19-Dec-25 A | 2026-06-28 | 23-Dec-25 A | 2026-02-20 | 2026-06-28
| Underground Layout |  |  | 2026-02-20 |  |  | 116 | 10-Jun-25 A | 2026-03-19 | 22-Oct-25 A | 2026-02-20 | 2026-03-27
| A50210 | Underground Layout_IFR |  | 2026-02-20 |  |  | 6 | 10-Jun-25 A | 2026-03-19 | 08-Jul-25 A | 2026-02-20 | 2026-03-19
| A50230 | Underground Layout_IFA |  | 2026-02-20 |  |  | 3 | 11-Aug-25 A | 2026-03-19 | 15-Aug-25 A | 2026-02-20 | 2026-03-19
| A50220 | Underground Layout_RCC |  | 2026-02-20 |  |  | 16 | 18-Aug-25 A | 2026-03-19 | 12-Sep-25 A | 2026-02-20 | 2026-03-19
| A50240 | Underground Layout_RCA |  | 2026-02-20 |  |  | 16 | 15-Sep-25 A | 2026-03-27 | 10-Oct-25 A | 2026-02-20 | 2026-03-27
| A21570 | Underground Layout_IFD/IFC |  | 2026-02-20 |  |  | 2 | 14-Oct-25 A | 2026-03-27 | 22-Oct-25 A | 2026-02-20 | 2026-03-27
| Composite Underground drawing |  |  | 2026-02-20 |  |  | 101 | 22-Sep-25 A | 2026-03-19 | 2026-03-23 | 2026-03-23 | 2026-04-17 | 20
| A21580 | Composite Underground drawing_IFR |  | 2026-02-20 |  |  | 6 | 22-Sep-25 A | 2026-03-19 | 30-Sep-25 A | 2026-02-20 | 2026-03-19
| A21590 | Composite Underground drawing_RCC |  | 2026-02-20 |  |  | 16 | 24-Sep-25 A | 2026-03-19 | 07-Oct-25 A | 2026-02-20 | 2026-03-19
| A21600 | Composite Underground drawing_IFA |  | 2026-02-20 |  |  | 3 | 2026-02-20 | 2026-03-19 | 2026-02-25 | 2026-02-25 | 2026-03-24 | 20
| A50250 | Composite Underground drawing_RCA |  | 2026-02-25 |  |  | 16 | 2026-02-25 | 2026-03-25 | 2026-03-19 | 2026-03-19 | 2026-04-15 | 20
| A50260 | Composite Underground drawing_IFD/IFC |  | 2026-03-19 |  |  | 2 | 2026-03-19 | 2026-04-15 | 2026-03-23 | 2026-03-23 | 2026-04-17 | 20
| Underground Trench Layout drawing and details |  |  | 2026-02-20 |  |  | 61 | 01-Oct-25 A | 2026-03-19 | 19-Jan-26 A | 2026-02-20 | 2026-04-11
| A50270 | Underground Trench Layout drawing and details_IFR |  | 2026-02-20 |  |  | 6 | 01-Oct-25 A | 2026-03-19 | 09-Oct-25 A | 2026-02-20 | 2026-03-19
| A50280 | Underground Trench Layout drawing and details_RCC |  | 2026-02-20 |  |  | 16 | 10-Oct-25 A | 2026-03-19 | 10-Nov-25 A | 2026-02-20 | 2026-03-19
| A21650 | Underground Trench Layout drawing and details_IFA |  | 2026-02-20 |  |  | 3 | 19-Dec-25 A | 2026-03-19 | 24-Dec-25 A | 2026-02-20 | 2026-03-19
| A21660 | Underground Trench Layout drawing and details_RCA |  | 2026-02-20 |  |  | 16 | 24-Dec-25 A | 2026-04-11 | 15-Jan-26 A | 2026-02-20 | 2026-04-11
| A21670 | Underground Trench Layout drawing and details_IFD/IFC |  | 2026-02-20 |  |  | 2 | 15-Jan-26 A | 2026-04-11 | 19-Jan-26 A | 2026-02-20 | 2026-04-11
| Design Calculation for Concrete Trenches and Duct Banks (If Required) |  |  | 2026-02-20 |  |  | 66 | 19-Dec-25 A | 2026-12-22 | 2026-03-23 | 2026-03-23 | 2027-01-20 | 218
| A21680 | Design Calculation for Concrete Trenches and Duct Banks (If Required)_IFR |  | 2026-02-20 |  |  | 6 | 19-Dec-25 A | 2026-12-22 | 26-Dec-25 A | 2026-02-20 | 2026-12-22
| A50290 | Design Calculation for Concrete Trenches and Duct Banks (If Required)_RCC |  | 2026-02-20 |  |  | 16 | 26-Dec-25 A | 2026-12-22 | 19-Jan-26 A | 2026-02-20 | 2026-12-22
| A50300 | Design Calculation for Concrete Trenches and Duct Banks (If Required)_IFA |  | 2026-02-20 |  |  | 3 | 2026-02-20 | 2026-12-22 | 2026-02-25 | 2026-02-25 | 2026-12-25 | 218
| A50310 | Design Calculation for Concrete Trenches and Duct Banks (If Required)_RCA |  | 2026-02-25 |  |  | 16 | 2026-02-25 | 2026-12-28 | 2026-03-19 | 2026-03-19 | 2027-01-18 | 218
| A50320 | Design Calculation for Concrete Trenches and Duct Banks (If Required)_IFD/IFC |  | 2026-03-19 |  |  | 2 | 2026-03-19 | 2027-01-18 | 2026-03-23 | 2026-03-23 | 2027-01-20 | 218
| Calculation for UG Hydraulics |  |  | 2026-02-20 |  |  | 99 | 10-Jun-25 A | 2027-01-20 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| A21730 | Calculation for UG Hydraulics_IFR |  | 2026-02-20 |  |  | 6 | 10-Jun-25 A | 2027-01-20 | 04-Jul-25 A | 2026-02-20 | 2027-01-20
| A21740 | Calculation for UG Hydraulics_RCC |  | 2026-02-20 |  |  | 16 | 07-Jul-25 A | 2027-01-20 | 15-Aug-25 A | 2026-02-20 | 2027-01-20
| A21750 | Calculation for UG Hydraulics_IFA |  | 2026-02-20 |  |  | 3 | 18-Aug-25 A | 2027-01-20 | 22-Aug-25 A | 2026-02-20 | 2027-01-20
| A21760 | Calculation for UG Hydraulics_RCA |  | 2026-02-20 |  |  | 16 | 20-Aug-25 A | 2027-01-20 | 29-Aug-25 A | 2026-02-20 | 2027-01-20
| A50330 | Calculation for UG Hydraulics_IFD/IFC |  | 2026-02-20 |  |  | 2 | 19-Dec-25 A | 2027-01-20 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| Other Civil deliverables |  |  | 2026-02-20 |  |  | 485 | 16-Jan-25 A | 2026-02-23 | 2026-04-21 | 2026-04-21 | 2027-01-20 | 196
| General notes for Civil and Concrete Works |  |  | 2026-02-20 |  |  | 112 | 30-Jan-25 A | 2027-01-20 | 10-May-25 A | 2026-02-20 | 2027-01-20
| A17190 | General notes for Civil and Concrete Works_RCC |  | 2026-02-20 |  |  | 16 | 21-Feb-25 A | 2027-01-20 | 19-Apr-25 A | 2026-02-20 | 2027-01-20
| A17200 | General notes for Civil and Concrete Works_IFA |  | 2026-02-20 |  |  | 3 | 20-Apr-25 A | 2027-01-20 | 26-Apr-25 A | 2026-02-20 | 2027-01-20
| A17210 | General notes for Civil and Concrete Works_RCA |  | 2026-02-20 |  |  | 16 | 27-Apr-25 A | 2027-01-20 | 03-May-25 A | 2026-02-20 | 2027-01-20
| A17220 | General notes for Civil and Concrete Works_IFD/IFC |  | 2026-02-20 |  |  | 2 | 04-May-25 A | 2027-01-20 | 10-May-25 A | 2026-02-20 | 2027-01-20
| Standard details for stair and ladder foundation |  |  | 2026-02-20 |  |  | 127 | 01-Jul-25 A | 2026-11-30 | 08-Oct-25 A | 2026-02-20 | 2027-01-20
| A48280 | Standard details for stair and ladder foundation_RCC |  | 2026-02-20 |  |  | 16 | 31-Jul-25 A | 2027-01-20 | 17-Sep-25 A | 2026-02-20 | 2027-01-20
| A17300 | Standard details for stair and ladder foundation_IFA |  | 2026-02-20 |  |  | 3 | 18-Sep-25 A | 2027-01-20 | 24-Sep-25 A | 2026-02-20 | 2027-01-20
| A17310 | Standard details for stair and ladder foundation_RCA |  | 2026-02-20 |  |  | 16 | 15-Sep-25 A | 2027-01-20 | 01-Oct-25 A | 2026-02-20 | 2027-01-20
| A17320 | Standard details for stair and ladder foundation_IFD/IFC |  | 2026-02-20 |  |  | 2 | 02-Oct-25 A | 2027-01-20 | 08-Oct-25 A | 2026-02-20 | 2027-01-20
| Site Grading Layout |  |  | 2026-02-20 |  |  | 42 | 03-Sep-25 A | 2027-01-20 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| A17440 | Site Grading Layout_RCC |  | 2026-02-20 |  |  | 16 | 06-Sep-25 A | 2027-01-20 | 22-Sep-25 A | 2026-02-20 | 2027-01-20
| A17450 | Site Grading Layout_IFA |  | 2026-02-20 |  |  | 3 | 31-Oct-25 A | 2027-01-20 | 06-Nov-25 A | 2026-02-20 | 2027-01-20
| A17460 | Site Grading Layout_RCA |  | 2026-02-20 |  |  | 16 | 07-Nov-25 A | 2027-01-20 | 20-Nov-25 A | 2026-02-20 | 2027-01-20
| A48310 | Site Grading Layout_IFD/IFC |  | 2026-02-20 |  |  | 2 | 19-Dec-25 A | 2027-01-20 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| General notes for Structural steel Works |  |  | 2026-02-20 |  |  | 95 | 16-Jan-25 A | 2026-11-30 | 03-May-25 A | 2026-02-20 | 2027-01-20
| A17240 | General notes for Structural steel Works_RCC |  | 2026-02-20 |  |  | 16 | 21-Feb-25 A | 2027-01-20 | 13-Mar-25 A | 2026-02-20 | 2027-01-20
| A17250 | General notes for Structural steel Works_IFA |  | 2026-02-20 |  |  | 3 | 14-Mar-25 A | 2027-01-20 | 19-Apr-25 A | 2026-02-20 | 2027-01-20
| A17260 | General notes for Structural steel Works_RCA |  | 2026-02-20 |  |  | 16 | 20-Apr-25 A | 2027-01-20 | 26-Apr-25 A | 2026-02-20 | 2027-01-20
| A17270 | General notes for Structural steel Works_IFD/IFC |  | 2026-02-20 |  |  | 2 | 27-Apr-25 A | 2027-01-20 | 03-May-25 A | 2026-02-20 | 2027-01-20
| Typical Road Details |  |  | 2026-02-20 |  |  | 206 | 02-Jul-25 A | 2026-11-30 | 2026-04-14 | 2026-04-14 | 2027-01-20 | 202
| A17330 | Typical Road Details_IFR |  | 2026-02-20 |  |  | 6 | 02-Jul-25 A | 2026-11-30 | 09-Jul-25 A | 2026-02-20 | 2026-11-30
| A17340 | Typical Road Details_RCC |  | 2026-02-20 |  |  | 16 | 2026-02-20 | 2026-11-30 | 2026-03-13 | 2026-03-13 | 2026-12-22 | 202
| A48290 | Typical Road Details_IFA |  | 2026-03-13 |  |  | 3 | 2026-03-13 | 2026-12-22 | 2026-03-19 | 2026-03-19 | 2026-12-25 | 202
| A17360 | Typical Road Details_RCA |  | 2026-03-19 |  |  | 16 | 2026-03-19 | 2026-12-28 | 2026-04-09 | 2026-04-09 | 2027-01-18 | 202
| A17370 | Typical Road Details_IFD/IFC |  | 2026-04-09 |  |  | 2 | 2026-04-09 | 2027-01-18 | 2026-04-14 | 2026-04-14 | 2027-01-20 | 202
| MTO for Civil Works |  |  | 2026-02-20 |  |  | 299 | 05-May-25 A | 2026-11-23 | 10-Jun-25 A | 2026-02-20 | 2027-01-20
| A22440 | MTO for Civil Works_RCC |  | 2026-02-20 |  |  | 16 | 19-May-25 A | 2027-01-20 | 05-Jun-25 A | 2026-02-20 | 2027-01-20
| A50770 | MTO for Civil Works_IFD/IFC |  | 2026-02-20 |  |  | 2 | 08-Jun-25 A | 2027-01-20 | 10-Jun-25 A | 2026-02-20 | 2027-01-20
| MTO for Structural Steel |  |  | 2026-02-20 |  |  | 21 | 25-Aug-25 A | 2026-02-23 | 12-Sep-25 A | 2026-02-20 | 2026-07-24
| A50780 | MTO for Structural Steel_IFR |  | 2026-02-20 |  |  | 6 | 25-Aug-25 A | 2026-02-23 | 29-Aug-25 A | 2026-02-20 | 2026-02-23
| A50790 | MTO for Structural Steel_RCC |  | 2026-02-20 |  |  | 16 | 01-Sep-25 A | 2026-07-24 | 05-Sep-25 A | 2026-02-20 | 2026-07-24
| A50800 | MTO for Structural Steel_IFD/IFC |  | 2026-02-20 |  |  | 2 | 08-Sep-25 A | 2026-07-24 | 12-Sep-25 A | 2026-02-20 | 2026-07-24
| Tie-in Manhole modification drawing |  |  | 2026-02-20 |  |  | 43 | 2026-02-20 | 2026-11-23 | 2026-04-21 | 2026-04-21 | 2027-01-20 | 196
| A50730 | Tie-in Manhole modification drawing_RCC |  | 2026-02-27 |  |  | 16 | 2026-02-27 | 2026-11-30 | 2026-03-23 | 2026-03-23 | 2026-12-22 | 196
| A50740 | Tie-in Manhole modification drawing_IFA |  | 2026-03-23 |  |  | 3 | 2026-03-23 | 2026-12-22 | 2026-03-26 | 2026-03-26 | 2026-12-25 | 196
| A50750 | Tie-in Manhole modification drawing_RCA |  | 2026-03-26 |  |  | 16 | 2026-03-26 | 2026-12-28 | 2026-04-17 | 2026-04-17 | 2027-01-18 | 196
| A50760 | Tie-in Manhole modification drawing_IFD/IFC |  | 2026-04-17 |  |  | 2 | 2026-04-17 | 2027-01-18 | 2026-04-21 | 2026-04-21 | 2027-01-20 | 196
| Fence and Gate Layout |  |  | 2026-02-20 |  |  | 199 | 01-May-25 A | 2027-01-20 | 23-Jan-26 A | 2026-02-20 | 2027-01-20
| A17380 | Fence and Gate Layout_IFR |  | 2026-02-20 |  |  | 6 | 01-May-25 A | 2027-01-20 | 22-May-25 A | 2026-02-20 | 2027-01-20
| A17390 | Fence and Gate Layout_RCC |  | 2026-02-20 |  |  | 16 | 23-May-25 A | 2027-01-20 | 17-Jun-25 A | 2026-02-20 | 2027-01-20
| A17400 | Fence and Gate Layout_IFA |  | 2026-02-20 |  |  | 3 | 18-Jun-25 A | 2027-01-20 | 24-Jun-25 A | 2026-02-20 | 2027-01-20
| A48300 | Fence and Gate Layout_RCA |  | 2026-02-20 |  |  | 16 | 25-Jun-25 A | 2027-01-20 | 16-Sep-25 A | 2026-02-20 | 2027-01-20
| A17420 | Fence and Gate Layout_IFD/IFC |  | 2026-02-20 |  |  | 2 | 30-Dec-25 A | 2027-01-20 | 23-Jan-26 A | 2026-02-20 | 2027-01-20
| Road and Paving Layout |  |  | 2026-02-20 |  |  | 45 | 02-Jun-25 A | 2026-07-29 | 23-Jan-26 A | 2026-02-20 | 2026-07-29
| A50200 | Road and Paving Layout_RCC |  | 2026-02-20 |  |  | 16 | 19-Dec-25 A | 2026-07-29 | 09-Jan-26 A | 2026-02-20 | 2026-07-29
| A56270 | Road and Paving Layout_IFA |  | 2026-02-20 |  |  | 3 | 09-Jan-26 A | 2026-07-29 | 15-Jan-26 A | 2026-02-20 | 2026-07-29
| A56280 | Road and Paving Layout_RCA |  | 2026-02-20 |  |  | 16 | 15-Jan-26 A | 2026-07-29 | 19-Jan-26 A | 2026-02-20 | 2026-07-29
| A21520 | Road and Paving Layout_IFD/IFC |  | 2026-02-20 |  |  | 2 | 19-Jan-26 A | 2026-07-29 | 23-Jan-26 A | 2026-02-20 | 2026-07-29
| Block Diagram For Process CCTV |  |  | 2026-02-20 |  |  | 196 | 30-Dec-24 A | 2026-03-19 | 19-Sep-25 A | 2026-02-20 | 2027-01-20
| A51070 | Block Diagram For Process CCTV_RCC |  | 2026-02-20 |  |  | 16 | 21-Jan-25 A | 2027-01-20 | 14-Feb-25 A | 2026-02-20 | 2027-01-20
| A51080 | Block Diagram For Process CCTV_IFA |  | 2026-02-20 |  |  | 3 | 15-Feb-25 A | 2027-01-20 | 22-Apr-25 A | 2026-02-20 | 2027-01-20
| A51090 | Block Diagram For Process CCTV_RCA |  | 2026-02-20 |  |  | 16 | 23-Apr-25 A | 2027-01-20 | 12-Sep-25 A | 2026-02-20 | 2027-01-20
| A51100 | Block Diagram For Process CCTV_IFD/IFC |  | 2026-02-20 |  |  | 2 | 13-Sep-25 A | 2027-01-20 | 19-Sep-25 A | 2026-02-20 | 2027-01-20
| Block Diagram For PAGA |  |  | 2026-02-20 |  |  | 221 | 30-Dec-24 A | 2026-03-19 | 15-Oct-25 A | 2026-02-20 | 2027-01-20
| A51120 | Block Diagram For PAGA_RCC |  | 2026-02-20 |  |  | 16 | 21-Jan-25 A | 2027-01-20 | 14-Feb-25 A | 2026-02-20 | 2027-01-20
| A51130 | Block Diagram For PAGA_IFA |  | 2026-02-20 |  |  | 3 | 15-Feb-25 A | 2027-01-20 | 22-Apr-25 A | 2026-02-20 | 2027-01-20
| A51140 | Block Diagram For PAGA_RCA |  | 2026-02-20 |  |  | 16 | 23-Apr-25 A | 2027-01-20 | 10-Sep-25 A | 2026-02-20 | 2027-01-20
| A51150 | Block Diagram For PAGA_IFD/IFC |  | 2026-02-20 |  |  | 2 | 15-Sep-25 A | 2027-01-20 | 15-Oct-25 A | 2026-02-20 | 2027-01-20
| Block Diagram For Digital Network And Telephone System |  |  | 2026-02-20 |  |  | 216 | 01-Aug-25 A | 2026-03-19 | 22-Oct-25 A | 2026-02-20 | 2027-01-20
| A51160 | Block Diagram For Digital Network And Telephone System_IFR |  | 2026-02-20 |  |  | 6 | 01-Aug-25 A | 2026-03-19 | 15-Aug-25 A | 2026-02-20 | 2026-03-19
| A51170 | Block Diagram For Digital Network And Telephone System_RCC |  | 2026-02-20 |  |  | 16 | 04-Aug-25 A | 2027-01-20 | 22-Aug-25 A | 2026-02-20 | 2027-01-20
| A51180 | Block Diagram For Digital Network And Telephone System_IFA |  | 2026-02-20 |  |  | 3 | 25-Aug-25 A | 2027-01-20 | 29-Aug-25 A | 2026-02-20 | 2027-01-20
| A51190 | Block Diagram For Digital Network And Telephone System_RCA |  | 2026-02-20 |  |  | 16 | 25-Aug-25 A | 2027-01-20 | 11-Sep-25 A | 2026-02-20 | 2027-01-20
| A51200 | Block Diagram For Digital Network And Telephone System_IFD/IFC |  | 2026-02-20 |  |  | 2 | 01-Oct-25 A | 2027-01-20 | 22-Oct-25 A | 2026-02-20 | 2027-01-20
| Block Diagram For Access Control System |  |  | 2026-02-20 |  |  | 165 | 30-Dec-24 A | 2026-03-19 | 19-Sep-25 A | 2026-02-20 | 2027-01-20
| A51220 | Block Diagram For Access Control System_RCC |  | 2026-02-20 |  |  | 16 | 21-Jan-25 A | 2027-01-20 | 14-Feb-25 A | 2026-02-20 | 2027-01-20
| A51230 | Block Diagram For Access Control System_IFA |  | 2026-02-20 |  |  | 3 | 15-Feb-25 A | 2027-01-20 | 22-Apr-25 A | 2026-02-20 | 2027-01-20
| A51240 | Block Diagram For Access Control System_RCA |  | 2026-02-20 |  |  | 16 | 23-Apr-25 A | 2027-01-20 | 21-Jun-25 A | 2026-02-20 | 2027-01-20
| A51250 | Block Diagram For Access Control System_IFD/IFC |  | 2026-02-20 |  |  | 2 | 22-Jun-25 A | 2027-01-20 | 19-Sep-25 A | 2026-02-20 | 2027-01-20
| Overall Telecom System Block Diagram |  |  | 2026-02-20 |  |  | 290 | 25-Jan-25 A | 2027-01-18 | 2026-02-24 | 2026-02-24 | 2027-01-20 | 237
| A51270 | Overall Telecom System Block Diagram_RCC |  | 2026-02-20 |  |  | 16 | 01-Jul-25 A | 2027-01-18 | 29-Jul-25 A | 2026-02-20 | 2027-01-18
| A51280 | Overall Telecom System Block Diagram_IFA |  | 2026-02-20 |  |  | 3 | 31-Jul-25 A | 2027-01-18 | 23-Sep-25 A | 2026-02-20 | 2027-01-18
| A51290 | Overall Telecom System Block Diagram_RCA |  | 2026-02-20 |  |  | 16 | 22-Sep-25 A | 2027-01-18 | 07-Oct-25 A | 2026-02-20 | 2027-01-18
| A51300 | Overall Telecom System Block Diagram_IFD/IFC |  | 2026-02-20 |  |  | 2 | 2026-02-20 | 2027-01-18 | 2026-02-24 | 2026-02-24 | 2027-01-20 | 237
| Telecom Tie-In Schedule |  |  | 2026-02-20 |  |  | 206 | 13-Mar-25 A | 2027-01-20 | 01-Sep-25 A | 2026-02-20 | 2027-01-20
| A51810 | Telecom Tie-In Schedule_RCC |  | 2026-02-20 |  |  | 16 | 28-Apr-25 A | 2027-01-20 | 04-May-25 A | 2026-02-20 | 2027-01-20
| A51820 | Telecom Tie-In Schedule_IFA |  | 2026-02-20 |  |  | 3 | 05-May-25 A | 2027-01-20 | 11-May-25 A | 2026-02-20 | 2027-01-20
| A23660 | Telecom Tie-In Schedule_RCA |  | 2026-02-20 |  |  | 16 | 12-May-25 A | 2027-01-20 | 25-Aug-25 A | 2026-02-20 | 2027-01-20
| A51830 | Telecom Tie-In Schedule_IFD/IFC |  | 2026-02-20 |  |  | 2 | 26-Aug-25 A | 2027-01-20 | 01-Sep-25 A | 2026-02-20 | 2027-01-20
| Datasheet For Fiber Optic Cable |  |  | 2026-02-20 |  |  | 116 | 30-Jan-25 A | 2026-03-19 | 11-May-25 A | 2026-02-20 | 2027-01-20
| A50820 | Datasheet For Fiber Optic Cable_RCC |  | 2026-02-20 |  |  | 16 | 21-Feb-25 A | 2027-01-20 | 20-Apr-25 A | 2026-02-20 | 2027-01-20
| A50830 | Datasheet For Fiber Optic Cable_IFA |  | 2026-02-20 |  |  | 3 | 21-Apr-25 A | 2027-01-20 | 27-Apr-25 A | 2026-02-20 | 2027-01-20
| A50840 | Datasheet For Fiber Optic Cable_RCA |  | 2026-02-20 |  |  | 16 | 28-Apr-25 A | 2027-01-20 | 04-May-25 A | 2026-02-20 | 2027-01-20
| A50850 | Datasheet For Fiber Optic Cable_IFD/IFC |  | 2026-02-20 |  |  | 2 | 05-May-25 A | 2027-01-20 | 11-May-25 A | 2026-02-20 | 2027-01-20
| Datasheet For Process CCTV |  |  | 2026-02-20 |  |  | 269 | 01-Aug-25 A | 2026-03-19 | 19-Jan-26 A | 2026-02-20 | 2026-03-19
| A50860 | Datasheet For Process CCTV_IFR |  | 2026-02-20 |  |  | 6 | 01-Aug-25 A | 2026-03-19 | 15-Aug-25 A | 2026-02-20 | 2026-03-19
| A50870 | Datasheet For Process CCTV_RCC |  | 2026-02-20 |  |  | 16 | 15-Sep-25 A | 2026-03-19 | 15-Oct-25 A | 2026-02-20 | 2026-03-19
| A50880 | Datasheet For Process CCTV_IFA |  | 2026-02-20 |  |  | 3 | 19-Dec-25 A | 2026-03-19 | 24-Dec-25 A | 2026-02-20 | 2026-03-19
| A50890 | Datasheet For Process CCTV_RCA |  | 2026-02-20 |  |  | 16 | 24-Dec-25 A | 2026-03-19 | 15-Jan-26 A | 2026-02-20 | 2026-03-19
| A50900 | Datasheet For Process CCTV_IFD/IFC |  | 2026-02-20 |  |  | 2 | 15-Jan-26 A | 2026-03-19 | 19-Jan-26 A | 2026-02-20 | 2026-03-19
| Datasheet For PAGA |  |  | 2026-02-20 |  |  | 250 | 10-Jan-25 A | 2026-03-19 | 23-Dec-25 A | 2026-02-20 | 2026-03-19
| A50920 | Datasheet For PAGA_RCC |  | 2026-02-20 |  |  | 16 | 21-Mar-25 A | 2026-03-19 | 20-Apr-25 A | 2026-02-20 | 2026-03-19
| A50930 | Datasheet For PAGA_IFA |  | 2026-02-20 |  |  | 3 | 21-Apr-25 A | 2026-03-19 | 30-May-25 A | 2026-02-20 | 2026-03-19
| A50940 | Datasheet For PAGA_RCA |  | 2026-02-20 |  |  | 16 | 01-Jun-25 A | 2026-03-19 | 21-Jun-25 A | 2026-02-20 | 2026-03-19
| A50950 | Datasheet For PAGA_IFD/IFC |  | 2026-02-20 |  |  | 2 | 19-Dec-25 A | 2026-03-19 | 23-Dec-25 A | 2026-02-20 | 2026-03-19
| Datasheet For Access Control System |  |  | 2026-02-20 |  |  | 245 | 15-Jan-25 A | 2026-03-19 | 23-Dec-25 A | 2026-02-20 | 2026-03-19
| A50970 | Datasheet For Access Control System_RCC |  | 2026-02-20 |  |  | 16 | 28-Apr-25 A | 2026-03-19 | 04-May-25 A | 2026-02-20 | 2026-03-19
| A50980 | Datasheet For Access Control System_IFA |  | 2026-02-20 |  |  | 3 | 05-May-25 A | 2026-03-19 | 09-Jun-25 A | 2026-02-20 | 2026-03-19
| A50990 | Datasheet For Access Control System_RCA |  | 2026-02-20 |  |  | 16 | 10-Jun-25 A | 2026-03-19 | 19-Sep-25 A | 2026-02-20 | 2026-03-19
| A51000 | Datasheet For Access Control System_IFD/IFC |  | 2026-02-20 |  |  | 2 | 19-Dec-25 A | 2026-03-19 | 23-Dec-25 A | 2026-02-20 | 2026-03-19
| Datasheet For Digital Network And Telephone System |  |  | 2026-02-20 |  |  | 245 | 15-Jan-25 A | 2026-03-19 | 23-Dec-25 A | 2026-02-20 | 2026-03-19
| A51020 | Datasheet For Digital Network And Telephone System_RCC |  | 2026-02-20 |  |  | 16 | 28-Apr-25 A | 2026-03-19 | 04-May-25 A | 2026-02-20 | 2026-03-19
| A51030 | Datasheet For Digital Network And Telephone System_IFA |  | 2026-02-20 |  |  | 3 | 05-May-25 A | 2026-03-19 | 10-Jun-25 A | 2026-02-20 | 2026-03-19
| A51040 | Datasheet For Digital Network And Telephone System_RCA |  | 2026-02-20 |  |  | 16 | 11-Jun-25 A | 2026-03-19 | 28-Aug-25 A | 2026-02-20 | 2026-03-19
| A51050 | Datasheet For Digital Network And Telephone System_IFD/IFC |  | 2026-02-20 |  |  | 2 | 19-Dec-25 A | 2026-03-19 | 23-Dec-25 A | 2026-02-20 | 2026-03-19
| Wiring Diagram For Process Cctv |  |  | 2026-02-20 |  |  | 261 | 08-Jan-25 A | 2027-01-20 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| A51320 | Wiring Diagram For Process Cctv_RCC |  | 2026-02-20 |  |  | 16 | 13-Feb-25 A | 2027-01-20 | 13-Mar-25 A | 2026-02-20 | 2027-01-20
| A51330 | Wiring Diagram For Process Cctv_IFA |  | 2026-02-20 |  |  | 3 | 27-Oct-25 A | 2027-01-20 | 03-Nov-25 A | 2026-02-20 | 2027-01-20
| A51340 | Wiring Diagram For Process Cctv_RCA |  | 2026-02-20 |  |  | 16 | 04-Nov-25 A | 2027-01-20 | 18-Nov-25 A | 2026-02-20 | 2027-01-20
| A51350 | Wiring Diagram For Process Cctv_IFD/IFC |  | 2026-02-20 |  |  | 2 | 19-Dec-25 A | 2027-01-20 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| Wiring Diagram For Paga |  |  | 2026-02-20 |  |  | 275 | 09-Jan-25 A | 2027-01-20 | 19-Jan-26 A | 2026-02-20 | 2027-01-20
| A51370 | Wiring Diagram For Paga_RCC |  | 2026-02-20 |  |  | 16 | 13-Feb-25 A | 2027-01-20 | 13-Mar-25 A | 2026-02-20 | 2027-01-20
| A51380 | Wiring Diagram For Paga_IFA |  | 2026-02-20 |  |  | 3 | 19-Dec-25 A | 2027-01-20 | 24-Dec-25 A | 2026-02-20 | 2027-01-20
| A51390 | Wiring Diagram For Paga_RCA |  | 2026-02-20 |  |  | 16 | 24-Dec-25 A | 2027-01-20 | 15-Jan-26 A | 2026-02-20 | 2027-01-20
| A51400 | Wiring Diagram For Paga_IFD/IFC |  | 2026-02-20 |  |  | 2 | 15-Jan-26 A | 2027-01-20 | 19-Jan-26 A | 2026-02-20 | 2027-01-20
| Wiring Diagram For Digital Network And Telephone System |  |  | 2026-02-20 |  |  | 336 | 22-Jan-25 A | 2026-11-23 | 2026-04-21 | 2026-04-21 | 2027-01-20 | 196
| A51420 | Wiring Diagram For Digital Network And Telephone System_RCC |  | 2026-02-27 |  |  | 16 | 2026-02-27 | 2026-11-30 | 2026-03-23 | 2026-03-23 | 2026-12-22 | 196
| A51430 | Wiring Diagram For Digital Network And Telephone System_IFA |  | 2026-03-23 |  |  | 3 | 2026-03-23 | 2026-12-22 | 2026-03-26 | 2026-03-26 | 2026-12-25 | 196
| A51440 | Wiring Diagram For Digital Network And Telephone System_RCA |  | 2026-03-26 |  |  | 16 | 2026-03-26 | 2026-12-28 | 2026-04-17 | 2026-04-17 | 2027-01-18 | 196
| A51450 | Wiring Diagram For Digital Network And Telephone System_IFD/IFC |  | 2026-04-17 |  |  | 2 | 2026-04-17 | 2027-01-18 | 2026-04-21 | 2026-04-21 | 2027-01-20 | 196
| Wiring Diagram For Access Control System |  |  | 2026-02-20 |  |  | 331 | 22-Jan-25 A | 2026-11-23 | 2026-04-21 | 2026-04-21 | 2027-01-20 | 196
| A51470 | Wiring Diagram For Access Control System_RCC |  | 2026-02-27 |  |  | 16 | 2026-02-27 | 2026-11-30 | 2026-03-23 | 2026-03-23 | 2026-12-22 | 196
| A51480 | Wiring Diagram For Access Control System_IFA |  | 2026-03-23 |  |  | 3 | 2026-03-23 | 2026-12-22 | 2026-03-26 | 2026-03-26 | 2026-12-25 | 196
| A51490 | Wiring Diagram For Access Control System_RCA |  | 2026-03-26 |  |  | 16 | 2026-03-26 | 2026-12-28 | 2026-04-17 | 2026-04-17 | 2027-01-18 | 196
| A51500 | Wiring Diagram For Access Control System_IFD/IFC |  | 2026-04-17 |  |  | 2 | 2026-04-17 | 2027-01-18 | 2026-04-21 | 2026-04-21 | 2027-01-20 | 196
| Material Requisitions For Telecom System (Paga, CCTV, ACS, Telephone & LAN System) |  |  | 2026-02-20 |  |  | 263 | 14-Mar-25 A | 2026-03-19 | 22-Jan-26 A | 2026-02-20 | 2026-03-19
| A23790 | Material Requisitions For Telecom System (Paga, Cctv, Acs, Telephone & Lan System)_RCC |  | 2026-02-20 |  |  | 16 | 01-Jul-25 A | 2026-03-19 | 29-Jul-25 A | 2026-02-20 | 2026-03-19
| A23800 | Material Requisitions For Telecom System (Paga, Cctv, Acs, Telephone & Lan System)_IFA |  | 2026-02-20 |  |  | 3 | 24-Dec-25 A | 2026-03-19 | 29-Dec-25 A | 2026-02-20 | 2026-03-19
| A23810 | Material Requisitions For Telecom System (Paga, Cctv, Acs, Telephone & Lan System)_RCA |  | 2026-02-20 |  |  | 16 | 29-Dec-25 A | 2026-03-19 | 20-Jan-26 A | 2026-02-20 | 2026-03-19
| A51910 | Material Requisitions For Telecom System (Paga, Cctv, Acs, Telephone & Lan System)_IFD/IFC |  | 2026-02-20 |  |  | 2 | 20-Jan-26 A | 2026-03-19 | 22-Jan-26 A | 2026-02-20 | 2026-03-19
| Material Requisitions For Telecom Cables |  |  | 2026-02-20 |  |  | 161 | 01-May-25 A | 2026-11-23 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| A51930 | Material Requisitions For Telecom Cables_RCC |  | 2026-02-20 |  |  | 16 | 01-Jul-25 A | 2027-01-20 | 29-Jul-25 A | 2026-02-20 | 2027-01-20
| A51940 | Material Requisitions For Telecom Cables_IFA |  | 2026-02-20 |  |  | 3 | 27-Oct-25 A | 2027-01-20 | 11-Nov-25 A | 2026-02-20 | 2027-01-20
| A23860 | Material Requisitions For Telecom Cables_RCA |  | 2026-02-20 |  |  | 16 | 12-Nov-25 A | 2027-01-20 | 21-Nov-25 A | 2026-02-20 | 2027-01-20
| A23870 | Material Requisitions For Telecom Cables_IFD/IFC |  | 2026-02-20 |  |  | 2 | 19-Dec-25 A | 2027-01-20 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| Telecom Equipment List |  |  | 2026-02-20 |  |  | 220 | 10-Mar-25 A | 2027-01-20 | 18-Dec-25 A | 2026-02-20 | 2027-01-20
| A51760 | Telecom Equipment List_RCC |  | 2026-02-20 |  |  | 16 | 28-Apr-25 A | 2027-01-20 | 04-May-25 A | 2026-02-20 | 2027-01-20
| A51770 | Telecom Equipment List_IFA |  | 2026-02-20 |  |  | 3 | 25-Aug-25 A | 2027-01-20 | 15-Sep-25 A | 2026-02-20 | 2027-01-20
| A51780 | Telecom Equipment List_RCA |  | 2026-02-20 |  |  | 16 | 10-Sep-25 A | 2027-01-20 | 29-Sep-25 A | 2026-02-20 | 2027-01-20
| A51790 | Telecom Equipment List_IFD/IFC |  | 2026-02-20 |  |  | 2 | 04-Dec-25 A | 2027-01-20 | 18-Dec-25 A | 2026-02-20 | 2027-01-20
| Telecom Cable Schedule |  |  | 2026-02-20 |  |  | 276 | 14-Apr-25 A | 2026-12-22 | 2026-03-23 | 2026-03-23 | 2027-01-20 | 218
| A51640 | Telecom Cable Schedule_IFR |  | 2026-02-20 |  |  | 6 | 14-Apr-25 A | 2026-12-22 | 05-May-25 A | 2026-02-20 | 2026-12-22
| A51650 | Telecom Cable Schedule_RCC |  | 2026-02-20 |  |  | 16 | 06-May-25 A | 2026-12-22 | 29-Jul-25 A | 2026-02-20 | 2026-12-22
| A51660 | Telecom Cable Schedule_IFA |  | 2026-02-20 |  |  | 3 | 2026-02-20 | 2026-12-22 | 2026-02-25 | 2026-02-25 | 2026-12-25 | 218
| A51670 | Telecom Cable Schedule_RCA |  | 2026-02-25 |  |  | 16 | 2026-02-25 | 2026-12-28 | 2026-03-19 | 2026-03-19 | 2027-01-18 | 218
| A51680 | Telecom Cable Schedule_IFD/IFC |  | 2026-03-19 |  |  | 2 | 2026-03-19 | 2027-01-18 | 2026-03-23 | 2026-03-23 | 2027-01-20 | 218
| Telecom Junction Box Schedule |  |  | 2026-02-20 |  |  | 143 | 01-Aug-25 A | 2027-01-20 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| A51690 | Telecom Junction Box Schedule_IFR |  | 2026-02-20 |  |  | 6 | 01-Aug-25 A | 2027-01-20 | 15-Aug-25 A | 2026-02-20 | 2027-01-20
| A51700 | Telecom Junction Box Schedule_RCC |  | 2026-02-20 |  |  | 16 | 04-Aug-25 A | 2027-01-20 | 22-Aug-25 A | 2026-02-20 | 2027-01-20
| A51710 | Telecom Junction Box Schedule_IFA |  | 2026-02-20 |  |  | 3 | 03-Nov-25 A | 2027-01-20 | 11-Nov-25 A | 2026-02-20 | 2027-01-20
| A51720 | Telecom Junction Box Schedule_RCA |  | 2026-02-20 |  |  | 16 | 12-Nov-25 A | 2027-01-20 | 21-Nov-25 A | 2026-02-20 | 2027-01-20
| A23520 | Telecom Junction Box Schedule_IFD/IFC |  | 2026-02-20 |  |  | 2 | 19-Dec-25 A | 2027-01-20 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| Voltage Drop Calculation For Paga System |  |  | 2026-02-20 |  |  | 43 | 2026-02-20 | 2026-11-23 | 2026-04-21 | 2026-04-21 | 2027-01-20 | 196
| A51740 | Voltage Drop Calculation For Paga System_RCC |  | 2026-02-27 |  |  | 16 | 2026-02-27 | 2026-11-30 | 2026-03-23 | 2026-03-23 | 2026-12-22 | 196
| A23550 | Voltage Drop Calculation For Paga System_IFA |  | 2026-03-23 |  |  | 3 | 2026-03-23 | 2026-12-22 | 2026-03-26 | 2026-03-26 | 2026-12-25 | 196
| A51750 | Voltage Drop Calculation For Paga System_RCA |  | 2026-03-26 |  |  | 16 | 2026-03-26 | 2026-12-28 | 2026-04-17 | 2026-04-17 | 2027-01-18 | 196
| A23570 | Voltage Drop Calculation For Paga System_IFD/IFC |  | 2026-04-17 |  |  | 2 | 2026-04-17 | 2027-01-18 | 2026-04-21 | 2026-04-21 | 2027-01-20 | 196
| Technical Bid Evaluation For Telecom Cables |  |  | 2026-02-20 |  |  | 43 | 2026-02-20 | 2026-11-23 | 2026-04-21 | 2026-04-21 | 2027-01-20 | 196
| A51990 | Technical Bid Evaluation For Telecom Cables_RCC |  | 2026-02-27 |  |  | 16 | 2026-02-27 | 2026-11-30 | 2026-03-23 | 2026-03-23 | 2026-12-22 | 196
| A52000 | Technical Bid Evaluation For Telecom Cables_IFA |  | 2026-03-23 |  |  | 3 | 2026-03-23 | 2026-12-22 | 2026-03-26 | 2026-03-26 | 2026-12-25 | 196
| A52010 | Technical Bid Evaluation For Telecom Cables_RCA |  | 2026-03-26 |  |  | 16 | 2026-03-26 | 2026-12-28 | 2026-04-17 | 2026-04-17 | 2027-01-18 | 196
| A52020 | Technical Bid Evaluation For Telecom Cables_IFD/IFC |  | 2026-04-17 |  |  | 2 | 2026-04-17 | 2027-01-18 | 2026-04-21 | 2026-04-21 | 2027-01-20 | 196
| Central Control Room Equipment Layout For Telecom |  |  | 2026-02-20 |  |  | 193 | 01-Jul-25 A | 2026-12-28 | 2026-03-17 | 2026-03-17 | 2027-01-20 | 221
| A51850 | Central Control Room Equipment Layout For Telecom_RCC |  | 2026-02-20 |  |  | 16 | 15-Aug-25 A | 2026-12-28 | 15-Sep-25 A | 2026-02-20 | 2026-12-28
| A51860 | Central Control Room Equipment Layout For Telecom_IFA |  | 2026-02-20 |  |  | 3 | 16-Sep-25 A | 2026-12-28 | 29-Sep-25 A | 2026-02-20 | 2026-12-28
| A51870 | Central Control Room Equipment Layout For Telecom_RCA |  | 2026-02-20 |  |  | 16 | 2026-02-20 | 2026-12-28 | 2026-03-13 | 2026-03-13 | 2027-01-18 | 221
| A51880 | Central Control Room Equipment Layout For Telecom_IFD/IFC |  | 2026-03-13 |  |  | 2 | 2026-03-13 | 2027-01-18 | 2026-03-17 | 2026-03-17 | 2027-01-20 | 221
| Telecommunication Core Allocation Drawing For Fiber Optic Cable |  |  | 2026-02-20 |  |  | 78 | 15-Apr-25 A | 2027-01-20 | 23-Jan-26 A | 2026-02-20 | 2027-01-20
| A51900 | Telecommunication Core Allocation Drawing For Fiber Optic Cable_RCC |  | 2026-02-20 |  |  | 16 | 29-Apr-25 A | 2027-01-20 | 21-Jul-25 A | 2026-02-20 | 2027-01-20
| A23750 | Telecommunication Core Allocation Drawing For Fiber Optic Cable_IFA |  | 2026-02-20 |  |  | 3 | 03-Nov-25 A | 2027-01-20 | 11-Nov-25 A | 2026-02-20 | 2027-01-20
| A23760 | Telecommunication Core Allocation Drawing For Fiber Optic Cable_RCA |  | 2026-02-20 |  |  | 16 | 10-Nov-25 A | 2027-01-20 | 21-Nov-25 A | 2026-02-20 | 2027-01-20
| A23770 | Telecommunication Core Allocation Drawing For Fiber Optic Cable_IFD/IFC |  | 2026-02-20 |  |  | 2 | 23-Dec-25 A | 2027-01-20 | 23-Jan-26 A | 2026-02-20 | 2027-01-20
| Overall Telecom Cable Routing Layout Drawing For H2 Extraction Unit |  |  | 2026-02-20 |  |  | 78 | 01-May-25 A | 2026-11-23 | 23-Jan-26 A | 2026-02-20 | 2027-01-20
| A51570 | Overall Telecom Cable Routing Layout Drawing For H2 Extraction Unit_RCC |  | 2026-02-20 |  |  | 16 | 19-Dec-25 A | 2027-01-20 | 25-Dec-25 A | 2026-02-20 | 2027-01-20
| A51580 | Overall Telecom Cable Routing Layout Drawing For H2 Extraction Unit_IFA |  | 2026-02-20 |  |  | 3 | 25-Dec-25 A | 2027-01-20 | 06-Jan-26 A | 2026-02-20 | 2027-01-20
| A51590 | Overall Telecom Cable Routing Layout Drawing For H2 Extraction Unit_RCA |  | 2026-02-20 |  |  | 16 | 06-Jan-26 A | 2027-01-20 | 14-Jan-26 A | 2026-02-20 | 2027-01-20
| A51600 | Overall Telecom Cable Routing Layout Drawing For H2 Extraction Unit_IFD/IFC |  | 2026-02-20 |  |  | 2 | 10-Jan-26 A | 2027-01-20 | 23-Jan-26 A | 2026-02-20 | 2027-01-20
| Overall Telecom Equipment Layout Drawing For H2 Extraction Unit |  |  | 2026-02-20 |  |  | 98 | 01-May-25 A | 2026-11-23 | 16-Jan-26 A | 2026-02-20 | 2027-01-20
| A51510 | Overall Telecom Equipment Layout Drawing For H2 Extraction Unit_IFR |  | 2026-02-20 |  |  | 11 | 01-May-25 A | 2026-11-23 | 20-May-25 A | 2026-02-20 | 2026-11-23
| A51520 | Overall Telecom Equipment Layout Drawing For H2 Extraction Unit_RCC |  | 2026-02-20 |  |  | 16 | 21-May-25 A | 2026-12-22 | 04-Jun-25 A | 2026-02-20 | 2026-12-22
| A51530 | Overall Telecom Equipment Layout Drawing For H2 Extraction Unit_IFA |  | 2026-02-20 |  |  | 3 | 10-Oct-25 A | 2026-12-22 | 16-Oct-25 A | 2026-02-20 | 2026-12-22
| A51540 | Overall Telecom Equipment Layout Drawing For H2 Extraction Unit_RCA |  | 2026-02-20 |  |  | 16 | 17-Oct-25 A | 2027-01-20 | 01-Nov-25 A | 2026-02-20 | 2027-01-20
| A51550 | Overall Telecom Equipment Layout Drawing For H2 Extraction Unit_IFD/IFC |  | 2026-02-20 |  |  | 2 | 31-Dec-25 A | 2027-01-20 | 16-Jan-26 A | 2026-02-20 | 2027-01-20
| Telecom System Material Take Off |  |  | 2026-02-20 |  |  | 116 | 02-Jul-25 A | 2027-01-20 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| A51610 | Telecom System Material Take Off_IFR |  | 2026-02-20 |  |  | 6 | 02-Jul-25 A | 2027-01-20 | 18-Jul-25 A | 2026-02-20 | 2027-01-20
| A51620 | Telecom System Material Take Off_RCC |  | 2026-02-20 |  |  | 16 | 07-Jul-25 A | 2027-01-20 | 29-Jul-25 A | 2026-02-20 | 2027-01-20
| A51630 | Telecom System Material Take Off_IFD/IFC |  | 2026-02-20 |  |  | 2 | 19-Dec-25 A | 2027-01-20 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| Material/Corrosion |  |  | 2026-02-20 |  |  | 320 | 15-Apr-25 A | 2026-12-22 | 2026-03-23 | 2026-03-23 | 2027-01-20 | 218
| Material Selection & Corrosion Control Report |  |  | 2026-02-20 |  |  | 320 | 15-Apr-25 A | 2026-12-22 | 2026-03-23 | 2026-03-23 | 2027-01-20 | 218
| A24040 | Material Selection & Corrosion Control Report_RCC |  | 2026-02-20 |  |  | 16 | 08-May-25 A | 2026-12-22 | 03-Jun-25 A | 2026-02-20 | 2026-12-22
| A24050 | Material Selection & Corrosion Control Report_IFA |  | 2026-02-20 |  |  | 3 | 2026-02-20 | 2026-12-22 | 2026-02-25 | 2026-02-25 | 2026-12-25 | 218
| A52080 | Material Selection & Corrosion Control Report_RCA |  | 2026-02-25 |  |  | 16 | 2026-02-25 | 2026-12-28 | 2026-03-19 | 2026-03-19 | 2027-01-18 | 218
| A52090 | Material Selection & Corrosion Control Report_IFD/IFC |  | 2026-03-19 |  |  | 2 | 2026-03-19 | 2027-01-18 | 2026-03-23 | 2026-03-23 | 2027-01-20 | 218
| Material Selection Diagrams (MSD) |  |  | 2026-02-20 |  |  | 311 | 16-Apr-25 A | 2026-12-28 | 2026-03-17 | 2026-03-17 | 2027-01-20 | 221
| A52040 | Material Selection Diagrams (MSD)_RCC |  | 2026-02-20 |  |  | 16 | 25-Jul-25 A | 2026-12-28 | 01-Aug-25 A | 2026-02-20 | 2026-12-28
| A52050 | Material Selection Diagrams (MSD)_IFA |  | 2026-02-20 |  |  | 3 | 29-Nov-25 A | 2026-12-28 | 18-Dec-25 A | 2026-02-20 | 2026-12-28
| A52060 | Material Selection Diagrams (MSD)_RCA |  | 2026-02-20 |  |  | 16 | 2026-02-20 | 2026-12-28 | 2026-03-13 | 2026-03-13 | 2027-01-18 | 221
| A24020 | Material Selection Diagrams (MSD)_IFD/IFC |  | 2026-03-13 |  |  | 2 | 2026-03-13 | 2027-01-18 | 2026-03-17 | 2026-03-17 | 2027-01-20 | 221
| HVAC Design Basis |  |  | 2026-02-20 |  |  | 137 | 13-Mar-25 A | 2027-01-20 | 24-May-25 A | 2026-02-20 | 2027-01-20
| A52110 | HVAC Design Basis_RCC |  | 2026-02-20 |  |  | 16 | 27-Apr-25 A | 2027-01-20 | 03-May-25 A | 2026-02-20 | 2027-01-20
| A52120 | HVAC Design Basis_IFA |  | 2026-02-20 |  |  | 3 | 04-May-25 A | 2027-01-20 | 10-May-25 A | 2026-02-20 | 2027-01-20
| A52130 | HVAC Design Basis_RCA |  | 2026-02-20 |  |  | 16 | 11-May-25 A | 2027-01-20 | 18-May-25 A | 2026-02-20 | 2027-01-20
| A52140 | HVAC Design Basis_IFD/IFC |  | 2026-02-20 |  |  | 2 | 19-May-25 A | 2027-01-20 | 24-May-25 A | 2026-02-20 | 2027-01-20
| HVAC Equipment And Accessories Specifications |  |  | 2026-02-20 |  |  | 133 | 23-Mar-25 A | 2027-01-20 | 19-May-25 A | 2026-02-20 | 2027-01-20
| A52160 | HVAC Equipment And Accessories Specifications_RCC |  | 2026-02-20 |  |  | 16 | 14-Apr-25 A | 2027-01-20 | 22-Apr-25 A | 2026-02-20 | 2027-01-20
| A52170 | HVAC Equipment And Accessories Specifications_IFA |  | 2026-02-20 |  |  | 3 | 23-Apr-25 A | 2027-01-20 | 05-May-25 A | 2026-02-20 | 2027-01-20
| A52180 | HVAC Equipment And Accessories Specifications_RCA |  | 2026-02-20 |  |  | 16 | 06-May-25 A | 2027-01-20 | 12-May-25 A | 2026-02-20 | 2027-01-20
| A52190 | HVAC Equipment And Accessories Specifications_IFD/IFC |  | 2026-02-20 |  |  | 2 | 13-May-25 A | 2027-01-20 | 19-May-25 A | 2026-02-20 | 2027-01-20
| HVAC Cooling Load Calculation And Equipment Sizing |  |  | 2026-02-20 |  |  | 66 | 20-Apr-25 A | 2026-03-19 | 03-Jun-25 A | 2026-02-20 | 2026-03-19
| A52210 | HVAC Cooling Load Calculation And Equipment Sizing_RCC |  | 2026-02-20 |  |  | 16 | 12-May-25 A | 2026-03-19 | 18-May-25 A | 2026-02-20 | 2026-03-19
| A52220 | HVAC Cooling Load Calculation And Equipment Sizing_IFA |  | 2026-02-20 |  |  | 3 | 23-May-25 A | 2026-03-19 | 25-May-25 A | 2026-02-20 | 2026-03-19
| A24210 | HVAC Cooling Load Calculation And Equipment Sizing_RCA |  | 2026-02-20 |  |  | 16 | 26-May-25 A | 2026-03-19 | 31-May-25 A | 2026-02-20 | 2026-03-19
| A24220 | HVAC Cooling Load Calculation And Equipment Sizing_IFD/IFC |  | 2026-02-20 |  |  | 2 | 01-Jun-25 A | 2026-03-19 | 03-Jun-25 A | 2026-02-20 | 2026-03-19
| HVAC Airflow Schematic Diagrams |  |  | 2026-02-20 |  |  | 67 | 25-Apr-25 A | 2026-11-02 | 25-Oct-25 A | 2026-02-20 | 2027-01-20
| A52550 | HVAC Airflow Schematic Diagrams_RCC |  | 2026-02-20 |  |  | 16 | 15-Jul-25 A | 2027-01-20 | 01-Aug-25 A | 2026-02-20 | 2027-01-20
| A52560 | HVAC Airflow Schematic Diagrams_IFA |  | 2026-02-20 |  |  | 3 | 29-Sep-25 A | 2027-01-20 | 07-Oct-25 A | 2026-02-20 | 2027-01-20
| A52570 | HVAC Airflow Schematic Diagrams_RCA |  | 2026-02-20 |  |  | 16 | 30-Sep-25 A | 2027-01-20 | 20-Oct-25 A | 2026-02-20 | 2027-01-20
| A52580 | HVAC Airflow Schematic Diagrams_IFD/IFC |  | 2026-02-20 |  |  | 2 | 21-Oct-25 A | 2027-01-20 | 25-Oct-25 A | 2026-02-20 | 2027-01-20
| HVAC Chilled Water Piping Schematic Diagrams |  |  | 2026-02-20 |  |  | 189 | 20-Jun-25 A | 2026-11-02 | 2026-04-14 | 2026-04-14 | 2027-01-20 | 202
| A52590 | HVAC Chilled Water Piping Schematic Diagrams_IFR |  | 2026-02-20 |  |  | 2 | 20-Jun-25 A | 2026-11-02 | 05-Jul-25 A | 2026-02-20 | 2026-11-02
| A52600 | HVAC Chilled Water Piping Schematic Diagrams_RCC |  | 2026-02-20 |  |  | 16 | 2026-02-20 | 2026-11-30 | 2026-03-13 | 2026-03-13 | 2026-12-22 | 202
| A52610 | HVAC Chilled Water Piping Schematic Diagrams_IFA |  | 2026-03-13 |  |  | 3 | 2026-03-13 | 2026-12-22 | 2026-03-19 | 2026-03-19 | 2026-12-25 | 202
| A52620 | HVAC Chilled Water Piping Schematic Diagrams_RCA |  | 2026-03-19 |  |  | 16 | 2026-03-19 | 2026-12-28 | 2026-04-09 | 2026-04-09 | 2027-01-18 | 202
| A52630 | HVAC Chilled Water Piping Schematic Diagrams_IFD/IFC |  | 2026-04-09 |  |  | 2 | 2026-04-09 | 2027-01-18 | 2026-04-14 | 2026-04-14 | 2027-01-20 | 202
| HVAC Chilled Water Piping And Instrumentation Diagrams |  |  | 2026-02-20 |  |  | 169 | 02-Jun-25 A | 2026-11-02 | 2026-02-24 | 2026-02-24 | 2027-01-20 | 237
| A52850 | HVAC Chilled Water Piping And Instrumentation Diagrams_RCC |  | 2026-02-20 |  |  | 16 | 11-Jul-25 A | 2027-01-18 | 15-Aug-25 A | 2026-02-20 | 2027-01-18
| A52860 | HVAC Chilled Water Piping And Instrumentation Diagrams_IFH |  | 2026-02-20 |  |  | 3 | 15-Aug-25 A | 2027-01-18 | 22-Aug-25 A | 2026-02-20 | 2027-01-18
| A52870 | HVAC Chilled Water Piping And Instrumentation Diagrams_RCA |  | 2026-02-20 |  |  | 16 | 25-Aug-25 A | 2027-01-18 | 07-Oct-25 A | 2026-02-20 | 2027-01-18
| A52880 | HVAC Chilled Water Piping And Instrumentation Diagrams_IFD/IFC |  | 2026-02-20 |  |  | 2 | 2026-02-20 | 2027-01-18 | 2026-02-24 | 2026-02-24 | 2027-01-20 | 237
| HVAC Ducting and Instrumentation Diagrams |  |  | 2026-02-20 |  |  | 114 | 17-Jun-25 A | 2026-11-02 | 14-Oct-25 A | 2026-02-20 | 2027-01-20
| A52800 | HVAC Ducting and Instrumentation Diagrams_RCC |  | 2026-02-20 |  |  | 16 | 09-Jul-25 A | 2027-01-20 | 15-Aug-25 A | 2026-02-20 | 2027-01-20
| A52810 | HVAC Ducting and Instrumentation Diagrams_IFH |  | 2026-02-20 |  |  | 3 | 18-Aug-25 A | 2027-01-20 | 22-Aug-25 A | 2026-02-20 | 2027-01-20
| A52820 | HVAC Ducting and Instrumentation Diagrams_RCA |  | 2026-02-20 |  |  | 16 | 29-Aug-25 A | 2027-01-20 | 07-Oct-25 A | 2026-02-20 | 2027-01-20
| A52830 | HVAC Ducting and Instrumentation Diagrams_IFD/IFC |  | 2026-02-20 |  |  | 2 | 08-Oct-25 A | 2027-01-20 | 14-Oct-25 A | 2026-02-20 | 2027-01-20
| HVAC Equipment Schedules |  |  | 2026-02-20 |  |  | 131 | 09-Jun-25 A | 2026-12-22 | 2026-03-23 | 2026-03-23 | 2027-01-20 | 218
| A52900 | HVAC Equipment Schedules_RCC |  | 2026-02-20 |  |  | 16 | 17-Jun-25 A | 2026-12-22 | 19-Jul-25 A | 2026-02-20 | 2026-12-22
| A52910 | HVAC Equipment Schedules_IFA |  | 2026-02-20 |  |  | 3 | 2026-02-20 | 2026-12-22 | 2026-02-25 | 2026-02-25 | 2026-12-25 | 218
| A52920 | HVAC Equipment Schedules_RCA |  | 2026-02-25 |  |  | 16 | 2026-02-25 | 2026-12-28 | 2026-03-19 | 2026-03-19 | 2027-01-18 | 218
| A52930 | HVAC Equipment Schedules_IFD/IFC |  | 2026-03-19 |  |  | 2 | 2026-03-19 | 2027-01-18 | 2026-03-23 | 2026-03-23 | 2027-01-20 | 218
| HVAC System Cause & Effect |  |  | 2026-02-20 |  |  | 38 | 21-Nov-25 A | 2027-01-20 | 13-Jan-26 A | 2026-02-20 | 2027-01-20
| A53000 | HVAC System Cause & Effect_RCC |  | 2026-02-20 |  |  | 16 | 27-Nov-25 A | 2027-01-20 | 18-Dec-25 A | 2026-02-20 | 2027-01-20
| A53010 | HVAC System Cause & Effect_IFA |  | 2026-02-20 |  |  | 3 | 18-Dec-25 A | 2027-01-20 | 19-Dec-25 A | 2026-02-20 | 2027-01-20
| A53020 | HVAC System Cause & Effect_RCA |  | 2026-02-20 |  |  | 16 | 19-Dec-25 A | 2027-01-20 | 09-Jan-26 A | 2026-02-20 | 2027-01-20
| A53030 | HVAC System Cause & Effect_IFD/IFC |  | 2026-02-20 |  |  | 2 | 09-Jan-26 A | 2027-01-20 | 13-Jan-26 A | 2026-02-20 | 2027-01-20
| HVAC Chilled Water Pump Head Calculation |  |  | 2026-02-20 |  |  | 61 | 01-Oct-25 A | 2027-01-20 | 10-Nov-25 A | 2026-02-20 | 2027-01-20
| A53100 | HVAC Chilled Water Pump Head Calculation_RCC |  | 2026-02-20 |  |  | 16 | 14-Oct-25 A | 2027-01-20 | 25-Oct-25 A | 2026-02-20 | 2027-01-20
| A53110 | HVAC Chilled Water Pump Head Calculation_IFA |  | 2026-02-20 |  |  | 3 | 24-Oct-25 A | 2027-01-20 | 28-Oct-25 A | 2026-02-20 | 2027-01-20
| A53120 | HVAC Chilled Water Pump Head Calculation_RCA |  | 2026-02-20 |  |  | 16 | 28-Oct-25 A | 2027-01-20 | 31-Oct-25 A | 2026-02-20 | 2027-01-20
| A53130 | HVAC Chilled Water Pump Head Calculation_IFD/IFC |  | 2026-02-20 |  |  | 2 | 01-Nov-25 A | 2027-01-20 | 10-Nov-25 A | 2026-02-20 | 2027-01-20
| HVAC Technical Data Sheet For Air Handling Unit |  |  | 2026-02-20 |  |  | 102 | 01-May-25 A | 2026-03-19 | 10-Oct-25 A | 2026-02-20 | 2026-03-19
| A52240 | HVAC Technical Data Sheet For Air Handling Unit_IFR |  | 2026-02-20 |  |  | 2 | 01-May-25 A | 2026-03-19 | 22-May-25 A | 2026-02-20 | 2026-03-19
| A52250 | HVAC Technical Data Sheet For Air Handling Unit_RCC |  | 2026-02-20 |  |  | 16 | 23-May-25 A | 2026-03-19 | 10-Jun-25 A | 2026-02-20 | 2026-03-19
| A52260 | HVAC Technical Data Sheet For Air Handling Unit_IFA |  | 2026-02-20 |  |  | 3 | 11-Jun-25 A | 2026-03-19 | 26-Jun-25 A | 2026-02-20 | 2026-03-19
| A52270 | HVAC Technical Data Sheet For Air Handling Unit_RCA |  | 2026-02-20 |  |  | 16 | 27-Jun-25 A | 2026-03-19 | 10-Sep-25 A | 2026-02-20 | 2026-03-19
| A52280 | HVAC Technical Data Sheet For Air Handling Unit_IFD/IFC |  | 2026-02-20 |  |  | 2 | 15-Sep-25 A | 2026-03-19 | 10-Oct-25 A | 2026-02-20 | 2026-03-19
| HVAC Technical Data Sheet For Air Cooled Chiller |  |  | 2026-02-20 |  |  | 53 | 26-May-25 A | 2026-03-19 | 10-Jun-25 A | 2026-02-20 | 2026-03-19
| A24230 | HVAC Technical Data Sheet For Air Cooled Chiller_IFR |  | 2026-02-20 |  |  | 2 | 26-May-25 A | 2026-03-19 | 28-May-25 A | 2026-02-20 | 2026-03-19
| A24240 | HVAC Technical Data Sheet For Air Cooled Chiller_RCC |  | 2026-02-20 |  |  | 16 | 29-May-25 A | 2026-03-19 | 31-May-25 A | 2026-02-20 | 2026-03-19
| A24250 | HVAC Technical Data Sheet For Air Cooled Chiller_IFA |  | 2026-02-20 |  |  | 3 | 01-Jun-25 A | 2026-03-19 | 04-Jun-25 A | 2026-02-20 | 2026-03-19
| A24260 | HVAC Technical Data Sheet For Air Cooled Chiller_RCA |  | 2026-02-20 |  |  | 16 | 05-Jun-25 A | 2026-03-19 | 07-Jun-25 A | 2026-02-20 | 2026-03-19
| A52230 | HVAC Technical Data Sheet For Air Cooled Chiller_IFD/IFC |  | 2026-02-20 |  |  | 2 | 08-Jun-25 A | 2026-03-19 | 10-Jun-25 A | 2026-02-20 | 2026-03-19
| HVAC Technical Data Sheet For Chilled Water Pump |  |  | 2026-02-20 |  |  | 84 | 26-May-25 A | 2026-03-19 | 10-Oct-25 A | 2026-02-20 | 2026-03-19
| A52290 | HVAC Technical Data Sheet For Chilled Water Pump_IFR |  | 2026-02-20 |  |  | 2 | 26-May-25 A | 2026-03-19 | 05-Jul-25 A | 2026-02-20 | 2026-03-19
| A52300 | HVAC Technical Data Sheet For Chilled Water Pump_RCC |  | 2026-02-20 |  |  | 16 | 06-Jul-25 A | 2026-03-19 | 01-Aug-25 A | 2026-02-20 | 2026-03-19
| A52310 | HVAC Technical Data Sheet For Chilled Water Pump_IFA |  | 2026-02-20 |  |  | 3 | 02-Aug-25 A | 2026-03-19 | 27-Aug-25 A | 2026-02-20 | 2026-03-19
| A52320 | HVAC Technical Data Sheet For Chilled Water Pump_RCA |  | 2026-02-20 |  |  | 16 | 28-Aug-25 A | 2026-03-19 | 10-Sep-25 A | 2026-02-20 | 2026-03-19
| A52330 | HVAC Technical Data Sheet For Chilled Water Pump_IFD/IFC |  | 2026-02-20 |  |  | 2 | 15-Sep-25 A | 2026-03-19 | 10-Oct-25 A | 2026-02-20 | 2026-03-19
| HVAC Technical Data Sheet For Chemical Filter Unit |  |  | 2026-02-20 |  |  | 82 | 26-May-25 A | 2026-03-19 | 10-Oct-25 A | 2026-02-20 | 2026-03-19
| A52350 | HVAC Technical Data Sheet For Chemical Filter Unit_RCC |  | 2026-02-20 |  |  | 16 | 06-Jul-25 A | 2026-03-19 | 01-Aug-25 A | 2026-02-20 | 2026-03-19
| A52360 | HVAC Technical Data Sheet For Chemical Filter Unit_IFA |  | 2026-02-20 |  |  | 3 | 02-Aug-25 A | 2026-03-19 | 29-Aug-25 A | 2026-02-20 | 2026-03-19
| A52370 | HVAC Technical Data Sheet For Chemical Filter Unit_RCA |  | 2026-02-20 |  |  | 16 | 30-Aug-25 A | 2026-03-19 | 12-Sep-25 A | 2026-02-20 | 2026-03-19
| A52380 | HVAC Technical Data Sheet For Chemical Filter Unit_IFD/IFC |  | 2026-02-20 |  |  | 2 | 15-Sep-25 A | 2026-03-19 | 10-Oct-25 A | 2026-02-20 | 2026-03-19
| HVAC Technical Data Sheet For Inertia Filter With Bleed Fan |  |  | 2026-02-20 |  |  | 100 | 26-May-25 A | 2026-03-19 | 21-Nov-25 A | 2026-02-20 | 2026-03-19
| A52400 | HVAC Technical Data Sheet For Inertia Filter With Bleed Fan_RCC |  | 2026-02-20 |  |  | 16 | 06-Jul-25 A | 2026-03-19 | 30-Jul-25 A | 2026-02-20 | 2026-03-19
| A52410 | HVAC Technical Data Sheet For Inertia Filter With Bleed Fan_IFA |  | 2026-02-20 |  |  | 3 | 31-Jul-25 A | 2026-03-19 | 22-Aug-25 A | 2026-02-20 | 2026-03-19
| A52420 | HVAC Technical Data Sheet For Inertia Filter With Bleed Fan_RCA |  | 2026-02-20 |  |  | 16 | 23-Aug-25 A | 2026-03-19 | 10-Sep-25 A | 2026-02-20 | 2026-03-19
| A52430 | HVAC Technical Data Sheet For Inertia Filter With Bleed Fan_IFD/IFC |  | 2026-02-20 |  |  | 2 | 17-Nov-25 A | 2026-03-19 | 21-Nov-25 A | 2026-02-20 | 2026-03-19
| HVAC Technical Data Sheet For Exhaust Air Fans |  |  | 2026-02-20 |  |  | 65 | 26-May-25 A | 2026-03-19 | 15-Sep-25 A | 2026-02-20 | 2026-03-19
| A52440 | HVAC Technical Data Sheet For Exhaust Air Fans_IFR |  | 2026-02-20 |  |  | 2 | 26-May-25 A | 2026-03-19 | 05-Jul-25 A | 2026-02-20 | 2026-03-19
| A52450 | HVAC Technical Data Sheet For Exhaust Air Fans_RCC |  | 2026-02-20 |  |  | 16 | 06-Jul-25 A | 2026-03-19 | 01-Aug-25 A | 2026-02-20 | 2026-03-19
| A52460 | HVAC Technical Data Sheet For Exhaust Air Fans_IFA |  | 2026-02-20 |  |  | 3 | 02-Aug-25 A | 2026-03-19 | 01-Sep-25 A | 2026-02-20 | 2026-03-19
| A52470 | HVAC Technical Data Sheet For Exhaust Air Fans_RCA |  | 2026-02-20 |  |  | 16 | 02-Sep-25 A | 2026-03-19 | 08-Sep-25 A | 2026-02-20 | 2026-03-19
| A52480 | HVAC Technical Data Sheet For Exhaust Air Fans_IFD/IFC |  | 2026-02-20 |  |  | 2 | 09-Sep-25 A | 2026-03-19 | 15-Sep-25 A | 2026-02-20 | 2026-03-19
| HVAC Technical Data Sheet For Electric Duct Heater |  |  | 2026-02-20 |  |  | 46 | 26-May-25 A | 2026-03-19 | 15-Sep-25 A | 2026-02-20 | 2026-03-19
| A52500 | HVAC Technical Data Sheet For Electric Duct Heater_RCC |  | 2026-02-20 |  |  | 16 | 02-Jun-25 A | 2026-03-19 | 15-Jun-25 A | 2026-02-20 | 2026-03-19
| A52510 | HVAC Technical Data Sheet For Electric Duct Heater_IFA |  | 2026-02-20 |  |  | 3 | 16-Jun-25 A | 2026-03-19 | 20-Jun-25 A | 2026-02-20 | 2026-03-19
| A52520 | HVAC Technical Data Sheet For Electric Duct Heater_RCA |  | 2026-02-20 |  |  | 16 | 21-Jun-25 A | 2026-03-19 | 08-Sep-25 A | 2026-02-20 | 2026-03-19
| A52530 | HVAC Technical Data Sheet For Electric Duct Heater_IFD/IFC |  | 2026-02-20 |  |  | 2 | 09-Sep-25 A | 2026-03-19 | 15-Sep-25 A | 2026-02-20 | 2026-03-19
| HVAC Chilled Water Piping Layouts & Sections |  |  | 2026-02-20 |  |  | 101 | 10-Jul-25 A | 2027-01-20 | 13-Jan-26 A | 2026-02-20 | 2027-01-20
| A52750 | HVAC Chilled Water Piping Layouts & Sections_RCC |  | 2026-02-20 |  |  | 16 | 08-Oct-25 A | 2027-01-20 | 31-Oct-25 A | 2026-02-20 | 2027-01-20
| A52760 | HVAC Chilled Water Piping Layouts & Sections_IFA |  | 2026-02-20 |  |  | 3 | 28-Nov-25 A | 2027-01-20 | 10-Dec-25 A | 2026-02-20 | 2027-01-20
| A52770 | HVAC Chilled Water Piping Layouts & Sections_RCA |  | 2026-02-20 |  |  | 16 | 19-Dec-25 A | 2027-01-20 | 09-Jan-26 A | 2026-02-20 | 2027-01-20
| A52780 | HVAC Chilled Water Piping Layouts & Sections_IFD/IFC |  | 2026-02-20 |  |  | 2 | 09-Jan-26 A | 2027-01-20 | 13-Jan-26 A | 2026-02-20 | 2027-01-20
| HVAC System Sequence Of Operation And Control Philosophy |  |  | 2026-02-20 |  |  | 110 | 01-Jul-25 A | 2027-01-20 | 04-Dec-25 A | 2026-02-20 | 2027-01-20
| A52950 | HVAC System Sequence Of Operation And Control Philosophy_RCC |  | 2026-02-20 |  |  | 16 | 17-Jul-25 A | 2027-01-20 | 22-Aug-25 A | 2026-02-20 | 2027-01-20
| A52960 | HVAC System Sequence Of Operation And Control Philosophy_IFA |  | 2026-02-20 |  |  | 3 | 01-Oct-25 A | 2027-01-20 | 28-Oct-25 A | 2026-02-20 | 2027-01-20
| A52970 | HVAC System Sequence Of Operation And Control Philosophy_RCA |  | 2026-02-20 |  |  | 16 | 29-Oct-25 A | 2027-01-20 | 17-Nov-25 A | 2026-02-20 | 2027-01-20
| A52980 | HVAC System Sequence Of Operation And Control Philosophy_IFD/IFC |  | 2026-02-20 |  |  | 2 | 24-Nov-25 A | 2027-01-20 | 04-Dec-25 A | 2026-02-20 | 2027-01-20
| Material Requisition For HVAC Equipments |  |  | 2026-02-20 |  |  | 97 | 02-Jun-25 A | 2026-03-19 | 19-Nov-25 A | 2026-02-20 | 2026-03-19
| A53200 | Material Requisition For HVAC Equipments_RCC |  | 2026-02-20 |  |  | 16 | 04-Jul-25 A | 2026-03-19 | 30-Jul-25 A | 2026-02-20 | 2026-03-19
| A53210 | Material Requisition For HVAC Equipments_IFA |  | 2026-02-20 |  |  | 3 | 29-Aug-25 A | 2026-03-19 | 01-Oct-25 A | 2026-02-20 | 2026-03-19
| A53220 | Material Requisition For HVAC Equipments_RCA |  | 2026-02-20 |  |  | 16 | 01-Oct-25 A | 2026-03-19 | 24-Oct-25 A | 2026-02-20 | 2026-03-19
| A53230 | Material Requisition For HVAC Equipments_IFD/IFC |  | 2026-02-20 |  |  | 2 | 27-Oct-25 A | 2026-03-19 | 19-Nov-25 A | 2026-02-20 | 2026-03-19
| Material Requisition for Fire Detection System & LFCP |  |  | 2026-02-20 |  |  | 137 | 09-Jun-25 A | 2026-03-19 | 25-Dec-25 A | 2026-02-20 | 2026-03-19
| A47790 | Material Requisition for Fire Detection System & LFCP_RCC |  | 2026-02-20 |  |  | 16 | 07-Jul-25 A | 2026-03-19 | 30-Jul-25 A | 2026-02-20 | 2026-03-19
| A47800 | Material Requisition for Fire Detection System & LFCP_IFA |  | 2026-02-20 |  |  | 3 | 31-Jul-25 A | 2026-03-19 | 26-Aug-25 A | 2026-02-20 | 2026-03-19
| A47810 | Material Requisition for Fire Detection System & LFCP_RCA |  | 2026-02-20 |  |  | 16 | 15-Aug-25 A | 2026-03-19 | 10-Sep-25 A | 2026-02-20 | 2026-03-19
| A15420 | Material Requisition for Fire Detection System & LFCP_IFD/IFC |  | 2026-02-20 |  |  | 2 | 23-Dec-25 A | 2026-03-19 | 25-Dec-25 A | 2026-02-20 | 2026-03-19
| HVAC Equipment And Ducting Layouts |  |  | 2026-02-20 |  |  | 94 | 29-Jun-25 A | 2026-11-02 | 18-Dec-25 A | 2026-02-20 | 2026-11-02
| A52650 | HVAC Equipment And Ducting Layouts_RCC |  | 2026-02-20 |  |  | 16 | 01-Aug-25 A | 2026-11-02 | 14-Oct-25 A | 2026-02-20 | 2026-11-02
| A52660 | HVAC Equipment And Ducting Layouts_IFA |  | 2026-02-20 |  |  | 3 | 01-Oct-25 A | 2026-11-02 | 24-Oct-25 A | 2026-02-20 | 2026-11-02
| A52670 | HVAC Equipment And Ducting Layouts_RCA |  | 2026-02-20 |  |  | 16 | 27-Oct-25 A | 2026-11-02 | 21-Nov-25 A | 2026-02-20 | 2026-11-02
| A52680 | HVAC Equipment And Ducting Layouts_IFD/IFC |  | 2026-02-20 |  |  | 2 | 02-Dec-25 A | 2026-11-02 | 18-Dec-25 A | 2026-02-20 | 2026-11-02
| HVAC Ducting Section Layout |  |  | 2026-02-20 |  |  | 95 | 03-Aug-25 A | 2027-01-20 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| A52700 | HVAC Ducting Section Layout_RCC |  | 2026-02-20 |  |  | 16 | 19-Aug-25 A | 2027-01-20 | 22-Aug-25 A | 2026-02-20 | 2027-01-20
| A52710 | HVAC Ducting Section Layout_IFA |  | 2026-02-20 |  |  | 3 | 25-Aug-25 A | 2027-01-20 | 26-Sep-25 A | 2026-02-20 | 2027-01-20
| A52720 | HVAC Ducting Section Layout_RCA |  | 2026-02-20 |  |  | 16 | 15-Sep-25 A | 2027-01-20 | 14-Oct-25 A | 2026-02-20 | 2027-01-20
| A52730 | HVAC Ducting Section Layout_IFD/IFC |  | 2026-02-20 |  |  | 2 | 19-Dec-25 A | 2027-01-20 | 23-Dec-25 A | 2026-02-20 | 2027-01-20
| HVAC External Static Pressure Calculation |  |  | 2026-02-20 |  |  | 43 | 2026-02-20 | 2026-11-23 | 2026-04-21 | 2026-04-21 | 2027-01-20 | 196
| A53050 | HVAC External Static Pressure Calculation_RCC |  | 2026-02-27 |  |  | 16 | 2026-02-27 | 2026-11-30 | 2026-03-23 | 2026-03-23 | 2026-12-22 | 196
| A53060 | HVAC External Static Pressure Calculation_IFA |  | 2026-03-23 |  |  | 3 | 2026-03-23 | 2026-12-22 | 2026-03-26 | 2026-03-26 | 2026-12-25 | 196
| A53070 | HVAC External Static Pressure Calculation_RCA |  | 2026-03-26 |  |  | 16 | 2026-03-26 | 2026-12-28 | 2026-04-17 | 2026-04-17 | 2027-01-18 | 196
| A53080 | HVAC External Static Pressure Calculation_IFD/IFC |  | 2026-04-17 |  |  | 2 | 2026-04-17 | 2027-01-18 | 2026-04-21 | 2026-04-21 | 2027-01-20 | 196
| HVAC Standard Installation Details |  |  | 2026-02-20 |  |  | 121 | 25-Apr-25 A | 2027-01-20 | 07-Oct-25 A | 2026-02-20 | 2027-01-20
| A53150 | HVAC Standard Installation Details_RCC |  | 2026-02-20 |  |  | 16 | 17-May-25 A | 2027-01-20 | 10-Jun-25 A | 2026-02-20 | 2027-01-20
| A53160 | HVAC Standard Installation Details_IFA |  | 2026-02-20 |  |  | 3 | 11-Jun-25 A | 2027-01-20 | 20-Jun-25 A | 2026-02-20 | 2027-01-20
| A53170 | HVAC Standard Installation Details_RCA |  | 2026-02-20 |  |  | 16 | 13-Jun-25 A | 2027-01-20 | 30-Jun-25 A | 2026-02-20 | 2027-01-20
| A53180 | HVAC Standard Installation Details_IFD/IFC |  | 2026-02-20 |  |  | 2 | 30-Jul-25 A | 2027-01-20 | 07-Oct-25 A | 2026-02-20 | 2027-01-20
| Technical Bid Evaluation for Fire Detection System & LFCP |  |  | 2026-02-20 |  |  | 61 | 01-Oct-25 A | 2026-03-19 | 19-Jan-26 A | 2026-02-20 | 2027-01-20
| A16940 | Technical Bid Evaluation for Fire Detection System & LFCP_RCC |  | 2026-02-20 |  |  | 11 | 20-Oct-25 A | 2026-03-19 | 06-Nov-25 A | 2026-02-20 | 2026-03-19
| A16950 | Technical Bid Evaluation for Fire Detection System & LFCP_IFA |  | 2026-02-20 |  |  | 3 | 19-Dec-25 A | 2026-03-19 | 24-Dec-25 A | 2026-02-20 | 2026-03-19
| A16960 | Technical Bid Evaluation for Fire Detection System & LFCP_RCA |  | 2026-02-20 |  |  | 16 | 24-Dec-25 A | 2027-01-20 | 15-Jan-26 A | 2026-02-20 | 2027-01-20
| A16970 | Technical Bid Evaluation for Fire Detection System & LFCP_IFD/IFC |  | 2026-02-20 |  |  | 2 | 15-Jan-26 A | 2027-01-20 | 19-Jan-26 A | 2026-02-20 | 2027-01-20
| Procurement - HO Services |  |  | 2026-02-20 |  |  | 399 | 01-Jan-25 A | 2026-02-23 | 2026-07-24 | 2026-07-24 | 2027-07-20 | 257
| Equipment Packages |  |  | 2026-02-20 |  |  | 210 | 01-Jan-25 A | 2026-03-19 | 15-Oct-25 A | 2026-02-20 | 2026-07-15 | 234
| Vessels |  |  | 2026-02-20 |  |  | 210 | 01-Jan-25 A | 2026-03-19 | 20-Jun-25 A | 2026-02-20 | 2026-07-15 | 100
| C4 Guard Adsorber Cooler - (BF) |  |  | 2026-02-20 |  |  | 68 | 01-Jan-25 A | 2026-03-19 | 20-Jun-25 A | 2026-02-20 | 2026-07-15
| A8310 | Issue RFQ to Bidders |  | 2026-02-20 |  |  | 20 | 01-Jan-25 A | 2026-03-19 | 14-Jan-25 A | 2026-02-20 | 2026-03-19
| A57200 | Technical Bid Evaluation for Pressure Vessels & Internals_RCC |  | 2026-02-20 |  |  | 16 | 04-May-25 A | 2026-03-19 | 03-Jun-25 A | 2026-02-20 | 2026-03-19
| A57210 | Technical Bid Evaluation for Pressure Vessels & Internals_IFA |  | 2026-02-20 |  |  | 3 | 04-Jun-25 A | 2026-03-19 | 08-Jun-25 A | 2026-02-20 | 2026-03-19
| A57220 | Technical Bid Evaluation for Pressure Vessels & Internals_RCA |  | 2026-02-20 |  |  | 16 | 09-Jun-25 A | 2026-07-15 | 14-Jun-25 A | 2026-02-20 | 2026-07-15
| A8340 | Issue Purchase Order to Vendor |  | 2026-02-20 |  |  | 30 | 20-Jun-25 A | 2026-07-15 | 20-Jun-25 A | 2026-02-20 | 2026-07-15
| A57230 | Technical Bid Evaluation for Pressure Vessels & Internals_IFD/IFC |  | 2026-02-20 |  |  | 11 | 15-Jun-25 A | 2026-07-15 | 20-Jun-25 A | 2026-02-20 | 2026-07-15
| Vessel's Internals (05 Dimister pads) |  |  | 2026-02-20 |  |  | 106 | 01-Jan-25 A | 2026-03-19 | 20-Jun-25 A | 2026-02-20 | 2026-05-14 | 59
| A15970 | Issue RFQ to Bidders |  | 2026-02-20 |  |  | 20 | 01-Jan-25 A | 2026-03-19 | 14-Jan-25 A | 2026-02-20 | 2026-03-19
| A56540 | Technical Bid Evaluation for Pressure Vessels & Internals_IFR |  | 2026-02-20 |  |  | 11 | 28-Apr-25 A | 2026-03-19 | 03-May-25 A | 2026-02-20 | 2026-03-19
| A56550 | Technical Bid Evaluation for Pressure Vessels & Internals_RCC |  | 2026-02-20 |  |  | 16 | 04-May-25 A | 2026-03-19 | 03-Jun-25 A | 2026-02-20 | 2026-03-19
| A56560 | Technical Bid Evaluation for Pressure Vessels & Internals_IFA |  | 2026-02-20 |  |  | 11 | 04-Jun-25 A | 2026-03-19 | 08-Jun-25 A | 2026-02-20 | 2026-03-19
| A56570 | Technical Bid Evaluation for Pressure Vessels & Internals_RCA |  | 2026-02-20 |  |  | 16 | 09-Jun-25 A | 2026-05-14 | 14-Jun-25 A | 2026-02-20 | 2026-05-14
| A56580 | Technical Bid Evaluation for Pressure Vessels & Internals_IFD/IFC |  | 2026-02-20 |  |  | 8 | 09-Jun-25 A | 2026-05-14 | 14-Jun-25 A | 2026-02-20 | 2026-05-14
| A18020 | Issue Purchase Order to Vendor |  | 2026-02-20 |  |  | 21 | 20-Jun-25 A | 2026-05-14 | 20-Jun-25 A | 2026-02-20 | 2026-05-14
| A18040 | Commercial Bid Evaluation(Completion) |  | 2026-02-20 |  |  | 30 | 15-Jun-25 A | 2026-05-14 | 20-Jun-25 A | 2026-02-20 | 2026-05-14
| Vessels/Drums |  |  | 2026-02-20 |  |  | 124 | 01-Jan-25 A | 2026-03-19 | 20-Jun-25 A | 2026-02-20 | 2026-05-26
| FG Comp. 2nd Stage Suc. Drum (13-VV-706) |  |  | 2026-02-20 |  |  | 104 | 01-Jan-25 A | 2026-03-19 | 20-Jun-25 A | 2026-02-20 | 2026-04-17 | 40
| A35900 | Issue RFQ to Bidders |  | 2026-02-20 |  |  | 15 | 01-Jan-25 A | 2026-03-19 | 14-Jan-25 A | 2026-02-20 | 2026-03-19
| A45970 | Technical Bid Evaluation for Pressure Vessels & Internals_RCC |  | 2026-02-20 |  |  | 16 | 25-Mar-25 A | 2026-03-19 | 27-Mar-25 A | 2026-02-20 | 2026-03-19
| A45980 | Technical Bid Evaluation for Pressure Vessels & Internals_IFA |  | 2026-02-20 |  |  | 11 | 28-Mar-25 A | 2026-03-19 | 29-Mar-25 A | 2026-02-20 | 2026-03-19
| A45990 | Technical Bid Evaluation for Pressure Vessels & Internals_RCA |  | 2026-02-20 |  |  | 16 | 30-Mar-25 A | 2026-04-17 | 31-Mar-25 A | 2026-02-20 | 2026-04-17
| A46000 | Technical Bid Evaluation for Pressure Vessels & Internals_IFD/IFC |  | 2026-02-20 |  |  | 8 | 31-Mar-25 A | 2026-04-17 | 01-Apr-25 A | 2026-02-20 | 2026-04-17
| A45960 | Technical Bid Evaluation for Pressure Vessels & Internals_IFR |  | 2026-02-20 |  |  | 11 | 28-Apr-25 A | 2026-03-19 | 03-May-25 A | 2026-02-20 | 2026-03-19
| A35930 | Issue Purchase Order to Vendor |  | 2026-02-20 |  |  | 10 | 20-Jun-25 A | 2026-04-17 | 20-Jun-25 A | 2026-02-20 | 2026-04-17
| A35920 | Commercial Bid Evaluation(Completion) |  | 2026-02-20 |  |  | 21 | 15-Jun-25 A | 2026-04-17 | 20-Jun-25 A | 2026-02-20 | 2026-04-17
| FG Comp.1st Stage Suc. Drum (13-VV-705) |  |  | 2026-02-20 |  |  | 104 | 01-Jan-25 A | 2026-03-19 | 07-Apr-25 A | 2026-02-20 | 2026-04-17 | 54
| A17540 | Issue RFQ to Bidders |  | 2026-02-20 |  |  | 15 | 01-Jan-25 A | 2026-03-19 | 14-Jan-25 A | 2026-02-20 | 2026-03-19
| A56290 | Technical Bid Evaluation for Pressure Vessels & Internals_IFR |  | 2026-02-20 |  |  | 11 | 23-Mar-25 A | 2026-03-19 | 24-Mar-25 A | 2026-02-20 | 2026-03-19
| A56300 | Technical Bid Evaluation for Pressure Vessels & Internals_RCC |  | 2026-02-20 |  |  | 16 | 25-Mar-25 A | 2026-03-19 | 27-Mar-25 A | 2026-02-20 | 2026-03-19
| A56310 | Technical Bid Evaluation for Pressure Vessels & Internals_IFA |  | 2026-02-20 |  |  | 11 | 28-Mar-25 A | 2026-03-19 | 29-Mar-25 A | 2026-02-20 | 2026-03-19
| A56320 | Technical Bid Evaluation for Pressure Vessels & Internals_RCA |  | 2026-02-20 |  |  | 16 | 30-Mar-25 A | 2026-04-17 | 31-Mar-25 A | 2026-02-20 | 2026-04-17
| A56330 | Technical Bid Evaluation for Pressure Vessels & Internals_IFD/IFC |  | 2026-02-20 |  |  | 8 | 01-Apr-25 A | 2026-04-17 | 02-Apr-25 A | 2026-02-20 | 2026-04-17
| A9220 | Commercial Bid Evaluation(Completion) |  | 2026-02-20 |  |  | 21 | 03-Apr-25 A | 2026-04-17 | 04-Apr-25 A | 2026-02-20 | 2026-04-17
| A9200 | Issue Purchase Order to Vendor |  | 2026-02-20 |  |  | 10 | 04-Apr-25 A | 2026-04-17 | 07-Apr-25 A | 2026-02-20 | 2026-04-17
| PSA2 Slop Drum (70-VV-1415) |  |  | 2026-02-20 |  |  | 124 | 01-Jan-25 A | 2026-03-19 | 12-Apr-25 A | 2026-02-20 | 2026-05-26 | 106
| A35940 | Issue RFQ to Bidders |  | 2026-02-20 |  |  | 15 | 01-Jan-25 A | 2026-03-19 | 14-Jan-25 A | 2026-02-20 | 2026-03-19
| A56340 | Technical Bid Evaluation for Pressure Vessels & Internals_IFR |  | 2026-02-20 |  |  | 11 | 23-Mar-25 A | 2026-03-19 | 24-Mar-25 A | 2026-02-20 | 2026-03-19
| A56350 | Technical Bid Evaluation for Pressure Vessels & Internals_RCC |  | 2026-02-20 |  |  | 16 | 25-Mar-25 A | 2026-03-19 | 27-Mar-25 A | 2026-02-20 | 2026-03-19
| A56360 | Technical Bid Evaluation for Pressure Vessels & Internals_IFA |  | 2026-02-20 |  |  | 11 | 28-Mar-25 A | 2026-03-19 | 29-Mar-25 A | 2026-02-20 | 2026-03-19
| A56370 | Technical Bid Evaluation for Pressure Vessels & Internals_RCA |  | 2026-02-20 |  |  | 16 | 30-Mar-25 A | 2026-05-26 | 31-Mar-25 A | 2026-02-20 | 2026-05-26
| A56380 | Technical Bid Evaluation for Pressure Vessels & Internals_IFD/IFC |  | 2026-02-20 |  |  | 8 | 31-Mar-25 A | 2026-05-26 | 01-Apr-25 A | 2026-02-20 | 2026-05-26
| A35960 | Commercial Bid Evaluation(Completion) |  | 2026-02-20 |  |  | 30 | 02-Apr-25 A | 2026-05-26 | 03-Apr-25 A | 2026-02-20 | 2026-05-26
| A35970 | Issue Purchase Order to Vendor |  | 2026-02-20 |  |  | 21 | 04-Apr-25 A | 2026-05-26 | 12-Apr-25 A | 2026-02-20 | 2026-05-26
| OG Comp. 2nd Stage Suc. Drum (13-VV-713) |  |  | 2026-02-20 |  |  | 97 | 01-Jan-25 A | 2026-03-19 | 12-Apr-25 A | 2026-02-20 | 2026-04-22 | 43
| A35980 | Issue RFQ to Bidders |  | 2026-02-20 |  |  | 15 | 01-Jan-25 A | 2026-03-19 | 14-Jan-25 A | 2026-02-20 | 2026-03-19
| A56390 | Technical Bid Evaluation for Pressure Vessels & Internals_IFR |  | 2026-02-20 |  |  | 11 | 23-Mar-25 A | 2026-03-19 | 24-Mar-25 A | 2026-02-20 | 2026-03-19
| A56400 | Technical Bid Evaluation for Pressure Vessels & Internals_RCC |  | 2026-02-20 |  |  | 16 | 25-Mar-25 A | 2026-03-19 | 27-Mar-25 A | 2026-02-20 | 2026-03-19
| A56410 | Technical Bid Evaluation for Pressure Vessels & Internals_IFA |  | 2026-02-20 |  |  | 11 | 28-Mar-25 A | 2026-03-19 | 29-Mar-25 A | 2026-02-20 | 2026-03-19
| A56420 | Technical Bid Evaluation for Pressure Vessels & Internals_RCA |  | 2026-02-20 |  |  | 16 | 30-Mar-25 A | 2026-04-22 | 31-Mar-25 A | 2026-02-20 | 2026-04-22
| A56430 | Technical Bid Evaluation for Pressure Vessels & Internals_IFD/IFC |  | 2026-02-20 |  |  | 8 | 31-Mar-25 A | 2026-04-22 | 01-Apr-25 A | 2026-02-20 | 2026-04-22
| A36000 | Commercial Bid Evaluation(Completion) |  | 2026-02-20 |  |  | 14 | 02-Apr-25 A | 2026-04-22 | 03-Apr-25 A | 2026-02-20 | 2026-04-22
| A36010 | Issue Purchase Order to Vendor |  | 2026-02-20 |  |  | 10 | 04-Apr-25 A | 2026-04-22 | 12-Apr-25 A | 2026-02-20 | 2026-04-22
| FG Comp. 2nd Stage Dis. Drum (13-VV-707) |  |  | 2026-02-20 |  |  | 100 | 01-Jan-25 A | 2026-03-19 | 12-Apr-25 A | 2026-02-20 | 2026-04-16 | 40
| A36020 | Issue RFQ to Bidders |  | 2026-02-20 |  |  | 14 | 01-Jan-25 A | 2026-03-19 | 14-Jan-25 A | 2026-02-20 | 2026-03-19
| A56440 | Technical Bid Evaluation for Pressure Vessels & Internals_IFR |  | 2026-02-20 |  |  | 11 | 23-Mar-25 A | 2026-03-19 | 24-Mar-25 A | 2026-02-20 | 2026-03-19
| A56450 | Technical Bid Evaluation for Pressure Vessels & Internals_RCC |  | 2026-02-20 |  |  | 16 | 25-Mar-25 A | 2026-03-19 | 27-Mar-25 A | 2026-02-20 | 2026-03-19
| A56460 | Technical Bid Evaluation for Pressure Vessels & Internals_IFA |  | 2026-02-20 |  |  | 11 | 28-Mar-25 A | 2026-03-19 | 29-Mar-25 A | 2026-02-20 | 2026-03-19
| A56470 | Technical Bid Evaluation for Pressure Vessels & Internals_RCA |  | 2026-02-20 |  |  | 16 | 30-Mar-25 A | 2026-04-16 | 31-Mar-25 A | 2026-02-20 | 2026-04-16
| A56480 | Technical Bid Evaluation for Pressure Vessels & Internals_IFD/IFC |  | 2026-02-20 |  |  | 8 | 31-Mar-25 A | 2026-04-16 | 01-Apr-25 A | 2026-02-20 | 2026-04-16
| A36040 | Commercial Bid Evaluation(Completion) |  | 2026-02-20 |  |  | 14 | 02-Apr-25 A | 2026-04-16 | 03-Apr-25 A | 2026-02-20 | 2026-04-16
| A36050 | Issue Purchase Order to Vendor |  | 2026-02-20 |  |  | 14 | 04-Apr-25 A | 2026-04-16 | 12-Apr-25 A | 2026-02-20 | 2026-04-16
| OG Buffer Drum (13-VV-712) |  |  | 2026-02-20 |  |  | 108 | 01-Jan-25 A | 2026-03-19 | 12-Apr-25 A | 2026-02-20 | 2026-05-26 | 72
| A36060 | Issue RFQ to Bidders |  | 2026-02-20 |  |  | 15 | 01-Jan-25 A | 2026-03-19 | 22-Mar-25 A | 2026-02-20 | 2026-03-19
| A56490 | Technical Bid Evaluation for Pressure Vessels & Internals_IFR |  | 2026-02-20 |  |  | 11 | 23-Mar-25 A | 2026-03-19 | 24-Mar-25 A | 2026-02-20 | 2026-03-19
| A56500 | Technical Bid Evaluation for Pressure Vessels & Internals_RCC |  | 2026-02-20 |  |  | 16 | 25-Mar-25 A | 2026-03-19 | 27-Mar-25 A | 2026-02-20 | 2026-03-19
| A56510 | Technical Bid Evaluation for Pressure Vessels & Internals_IFA |  | 2026-02-20 |  |  | 11 | 28-Mar-25 A | 2026-03-19 | 29-Mar-25 A | 2026-02-20 | 2026-03-19
| A56520 | Technical Bid Evaluation for Pressure Vessels & Internals_RCA |  | 2026-02-20 |  |  | 16 | 30-Mar-25 A | 2026-05-26 | 31-Mar-25 A | 2026-02-20 | 2026-05-26
| A56530 | Technical Bid Evaluation for Pressure Vessels & Internals_IFD/IFC |  | 2026-02-20 |  |  | 8 | 31-Mar-25 A | 2026-05-26 | 01-Apr-25 A | 2026-02-20 | 2026-05-26
| A36080 | Commercial Bid Evaluation(Completion) |  | 2026-02-20 |  |  | 21 | 02-Apr-25 A | 2026-05-26 | 03-Apr-25 A | 2026-02-20 | 2026-05-26
| A36090 | Issue Purchase Order to Vendor |  | 2026-02-20 |  |  | 14 | 04-Apr-25 A | 2026-05-26 | 12-Apr-25 A | 2026-02-20 | 2026-05-26
| Water Collection & Sanitary Wastewater Pumps |  |  | 2026-02-20 |  |  | 85 | 01-Apr-25 A | 2026-05-26 | 15-Oct-25 A | 2026-02-20 | 2026-05-26
| Sanitary Waste Water Sump Pump |  |  | 2026-02-20 |  |  | 83 | 01-Apr-25 A | 2026-05-26 | 15-Oct-25 A | 2026-02-20 | 2026-05-26 | 87
| A8430 | RFQs to Bid Receipt |  | 2026-02-20 |  |  | 21 | 01-Apr-25 A | 2026-05-26 | 10-Apr-25 A | 2026-02-20 | 2026-05-26
| A45820 | Technical Bid Evaluation for Centrifugal Pump_RCC |  | 2026-02-20 |  |  | 3 | 13-Jun-25 A | 2026-05-26 | 18-Jun-25 A | 2026-02-20 | 2026-05-26
| A45830 | Technical Bid Evaluation for Centrifugal Pump_IFA |  | 2026-02-20 |  |  | 7 | 04-Jul-25 A | 2026-05-26 | 23-Aug-25 A | 2026-02-20 | 2026-05-26
| A45840 | Technical Bid Evaluation for Centrifugal Pump_RCA |  | 2026-02-20 |  |  | 3 | 24-Aug-25 A | 2026-05-26 | 30-Aug-25 A | 2026-02-20 | 2026-05-26
| A19490 | Commercial Bid Evaluation(Completion) |  | 2026-02-20 |  |  | 3 | 08-Sep-25 A | 2026-05-26 | 12-Sep-25 A | 2026-02-20 | 2026-05-26
| A19470 | Issue Purchase Order to Vendor |  | 2026-02-20 |  |  | 3 | 15-Sep-25 A | 2026-05-26 | 17-Sep-25 A | 2026-02-20 | 2026-05-26
| A45850 | Technical Bid Evaluation for Centrifugal Pump_IFD/IFC |  | 2026-02-20 |  |  | 3 | 01-Sep-25 A | 2026-05-26 | 15-Oct-25 A | 2026-02-20 | 2026-05-26
| Water Collection Sump Pump ll |  |  | 2026-02-20 |  |  | 37 | 01-Apr-25 A | 2026-05-26 | 05-Aug-25 A | 2026-02-20 | 2026-05-26 | 95
| A8490 | RFQs to Bid Receipt |  | 2026-02-20 |  |  | 21 | 01-Apr-25 A | 2026-05-26 | 10-Apr-25 A | 2026-02-20 | 2026-05-26
| A56890 | Technical Bid Evaluation for Centrifugal Pump_IFR |  | 2026-02-20 |  |  | 3 | 10-Jun-25 A | 2026-05-26 | 12-Jun-25 A | 2026-02-20 | 2026-05-26
| A56900 | Technical Bid Evaluation for Centrifugal Pump_RCC |  | 2026-02-20 |  |  | 5 | 13-Jun-25 A | 2026-05-26 | 18-Jun-25 A | 2026-02-20 | 2026-05-26
| A56910 | Technical Bid Evaluation for Centrifugal Pump_IFA |  | 2026-02-20 |  |  | 3 | 19-Jun-25 A | 2026-05-26 | 23-Jun-25 A | 2026-02-20 | 2026-05-26
| A56920 | Technical Bid Evaluation for Centrifugal Pump_RCA |  | 2026-02-20 |  |  | 3 | 24-Jun-25 A | 2026-05-26 | 29-Jun-25 A | 2026-02-20 | 2026-05-26
| A56930 | Technical Bid Evaluation for Centrifugal Pump_IFD/IFC |  | 2026-02-20 |  |  | 3 | 30-Jun-25 A | 2026-05-26 | 03-Jul-25 A | 2026-02-20 | 2026-05-26
| A19430 | Commercial Bid Evaluation(Completion) |  | 2026-02-20 |  |  | 3 | 18-Jul-25 A | 2026-05-26 | 29-Jul-25 A | 2026-02-20 | 2026-05-26
| A19410 | Issue Purchase Order to Vendor |  | 2026-02-20 |  |  | 3 | 30-Jul-25 A | 2026-05-26 | 05-Aug-25 A | 2026-02-20 | 2026-05-26
| EOT Cranes |  |  | 2026-02-20 |  |  | 124 | 01-May-25 A | 2026-03-19 | 18-Sep-25 A | 2026-02-20 | 2026-04-28 | 243
| EOT Crane for FG Compressor (1 = 60 Ton) |  |  | 2026-02-20 |  |  | 92 | 01-May-25 A | 2026-03-19 | 13-Aug-25 A | 2026-02-20 | 2026-04-21 | 243
| A8370 | Issue RFQ to Bidders |  | 2026-02-20 |  |  | 21 | 01-May-25 A | 2026-03-19 | 15-May-25 A | 2026-02-20 | 2026-03-19
| A45860 | Technical Bid Evaluation for EOT Crane_IFR |  | 2026-02-20 |  |  | 11 | 20-Jun-25 A | 2026-03-19 | 24-Jun-25 A | 2026-02-20 | 2026-03-19
| A45870 | Technical Bid Evaluation for EOT Crane_RCC |  | 2026-02-20 |  |  | 5 | 25-Jun-25 A | 2026-03-19 | 30-Jun-25 A | 2026-02-20 | 2026-03-19
| A45880 | Technical Bid Evaluation for EOT Crane_IFA |  | 2026-02-20 |  |  | 6 | 30-Jun-25 A | 2026-03-19 | 06-Jul-25 A | 2026-02-20 | 2026-03-19
| A45890 | Technical Bid Evaluation for EOT Crane_RCA |  | 2026-02-20 |  |  | 6 | 06-Jul-25 A | 2026-04-21 | 12-Jul-25 A | 2026-02-20 | 2026-04-21
| A45900 | Technical Bid Evaluation for EOT Crane_IFD/IFC |  | 2026-02-20 |  |  | 6 | 13-Jul-25 A | 2026-04-21 | 22-Jul-25 A | 2026-02-20 | 2026-04-21
| A20490 | Commercial Bid Evaluation(Completion) |  | 2026-02-20 |  |  | 3 | 23-Jul-25 A | 2026-04-21 | 06-Aug-25 A | 2026-02-20 | 2026-04-21
| A20470 | Issue Purchase Order to Vendor |  | 2026-02-20 |  |  | 10 | 07-Aug-25 A | 2026-04-21 | 13-Aug-25 A | 2026-02-20 | 2026-04-21
| EOT Crane for OG Compressor (1 = 25 Ton) |  |  | 2026-02-20 |  |  | 98 | 01-May-25 A | 2026-03-19 | 18-Sep-25 A | 2026-02-20 | 2026-04-28 | 243
| A8250 | Issue RFQ to Bidders |  | 2026-02-20 |  |  | 21 | 01-May-25 A | 2026-03-19 | 20-Jun-25 A | 2026-02-20 | 2026-03-19
| A56940 | Technical Bid Evaluation for EOT Crane_IFR |  | 2026-02-20 |  |  | 11 | 20-Jun-25 A | 2026-03-19 | 15-Aug-25 A | 2026-02-20 | 2026-03-19
| A56950 | Technical Bid Evaluation for EOT Crane_RCC |  | 2026-02-20 |  |  | 5 | 16-Aug-25 A | 2026-03-19 | 22-Aug-25 A | 2026-02-20 | 2026-03-19
| A56960 | Technical Bid Evaluation for EOT Crane_IFA |  | 2026-02-20 |  |  | 6 | 23-Aug-25 A | 2026-03-19 | 30-Aug-25 A | 2026-02-20 | 2026-03-19
| A56970 | Technical Bid Evaluation for EOT Crane_RCA |  | 2026-02-20 |  |  | 6 | 01-Sep-25 A | 2026-04-28 | 05-Sep-25 A | 2026-02-20 | 2026-04-28
| A56980 | Technical Bid Evaluation for EOT Crane_IFD/IFC |  | 2026-02-20 |  |  | 6 | 01-Sep-25 A | 2026-04-28 | 12-Sep-25 A | 2026-02-20 | 2026-04-28
| A20550 | Commercial Bid Evaluation(Completion) |  | 2026-02-20 |  |  | 3 | 15-Sep-25 A | 2026-04-28 | 17-Sep-25 A | 2026-02-20 | 2026-04-28
| A20530 | Issue Purchase Order to Vendor |  | 2026-02-20 |  |  | 10 | 17-Sep-25 A | 2026-04-28 | 18-Sep-25 A | 2026-02-20 | 2026-04-28
| Heat Exchangers |  |  | 2026-02-20 |  |  | 36 | 01-Jun-25 A | 2026-05-14 | 02-Jul-25 A | 2026-02-20 | 2026-05-26 | 138
| Heat Exchanger (Type S & T = 06 Nos) |  |  | 2026-02-20 |  |  | 36 | 01-Jun-25 A | 2026-05-14 | 02-Jul-25 A | 2026-02-20 | 2026-05-26 | 138
| FG Comp. Interstage Cooler (BEM) - Tag# 13-HE-703 |  |  | 2026-02-20 |  |  | 26 | 01-Jun-25 A | 2026-05-14 | 27-Jun-25 A | 2026-02-20 | 2026-05-14 | 60
| A36100 | Issue RFQ to Bidders |  | 2026-02-20 |  |  | 6 | 01-Jun-25 A | 2026-05-14 | 03-Jun-25 A | 2026-02-20 | 2026-05-14
| A45460 | Technical Bid Evaluation for Heat Exchangers_IFR |  | 2026-02-20 |  |  | 6 | 04-Jun-25 A | 2026-05-14 | 07-Jun-25 A | 2026-02-20 | 2026-05-14
| A45470 | Technical Bid Evaluation for Heat Exchangers_RCC |  | 2026-02-20 |  |  | 5 | 08-Jun-25 A | 2026-05-14 | 11-Jun-25 A | 2026-02-20 | 2026-05-14
| A45480 | Technical Bid Evaluation for Heat Exchangers_IFA |  | 2026-02-20 |  |  | 6 | 12-Jun-25 A | 2026-05-14 | 14-Jun-25 A | 2026-02-20 | 2026-05-14
| A45490 | Technical Bid Evaluation for Heat Exchangers_RCA |  | 2026-02-20 |  |  | 6 | 15-Jun-25 A | 2026-05-14 | 17-Jun-25 A | 2026-02-20 | 2026-05-14
| A45500 | Technical Bid Evaluation for Heat Exchangers_IFD/IFC |  | 2026-02-20 |  |  | 3 | 18-Jun-25 A | 2026-05-14 | 20-Jun-25 A | 2026-02-20 | 2026-05-14
| A36120 | Commercial Bid Evaluation(Completion) |  | 2026-02-20 |  |  | 6 | 20-Jun-25 A | 2026-05-14 | 24-Jun-25 A | 2026-02-20 | 2026-05-14
| A36130 | Issue Purchase Order to Vendor |  | 2026-02-20 |  |  | 3 | 25-Jun-25 A | 2026-05-14 | 27-Jun-25 A | 2026-02-20 | 2026-05-14
| OG Comp. After Cooler (BEU) - Tag# 13-HE-709 |  |  | 2026-02-20 |  |  | 36 | 01-Jun-25 A | 2026-05-26 | 27-Jun-25 A | 2026-02-20 | 2026-05-26 | 87
| A36140 | Issue RFQ to Bidders |  | 2026-02-20 |  |  | 21 | 01-Jun-25 A | 2026-05-26 | 03-Jun-25 A | 2026-02-20 | 2026-05-26
| A56640 | Technical Bid Evaluation for Heat Exchangers_IFR |  | 2026-02-20 |  |  | 6 | 04-Jun-25 A | 2026-05-26 | 07-Jun-25 A | 2026-02-20 | 2026-05-26
| A56650 | Technical Bid Evaluation for Heat Exchangers_RCC |  | 2026-02-20 |  |  | 5 | 08-Jun-25 A | 2026-05-26 | 11-Jun-25 A | 2026-02-20 | 2026-05-26
| A56660 | Technical Bid Evaluation for Heat Exchangers_IFA |  | 2026-02-20 |  |  | 6 | 12-Jun-25 A | 2026-05-26 | 14-Jun-25 A | 2026-02-20 | 2026-05-26
| A56670 | Technical Bid Evaluation for Heat Exchangers_RCA |  | 2026-02-20 |  |  | 6 | 15-Jun-25 A | 2026-05-26 | 17-Jun-25 A | 2026-02-20 | 2026-05-26
| A56680 | Technical Bid Evaluation for Heat Exchangers_IFD/IFC |  | 2026-02-20 |  |  | 3 | 18-Jun-25 A | 2026-05-26 | 20-Jun-25 A | 2026-02-20 | 2026-05-26
| A36160 | Commercial Bid Evaluation(Completion) |  | 2026-02-20 |  |  | 6 | 20-Jun-25 A | 2026-05-26 | 24-Jun-25 A | 2026-02-20 | 2026-05-26
| A36170 | Issue Purchase Order to Vendor |  | 2026-02-20 |  |  | 3 | 25-Jun-25 A | 2026-05-26 | 27-Jun-25 A | 2026-02-20 | 2026-05-26
| FG Comp. After Cooler (BEM) - Tag# 13-HE-704 |  |  | 2026-02-20 |  |  | 35 | 01-Jun-25 A | 2026-05-17 | 27-Jun-25 A | 2026-02-20 | 2026-05-17 | 62
| A36950 | Issue RFQ to Bidders |  | 2026-02-20 |  |  | 20 | 01-Jun-25 A | 2026-05-17 | 03-Jun-25 A | 2026-02-20 | 2026-05-17
| A56690 | Technical Bid Evaluation for Heat Exchangers_IFR |  | 2026-02-20 |  |  | 6 | 04-Jun-25 A | 2026-05-17 | 07-Jun-25 A | 2026-02-20 | 2026-05-17
| A56700 | Technical Bid Evaluation for Heat Exchangers_RCC |  | 2026-02-20 |  |  | 5 | 08-Jun-25 A | 2026-05-17 | 11-Jun-25 A | 2026-02-20 | 2026-05-17
| A56710 | Technical Bid Evaluation for Heat Exchangers_IFA |  | 2026-02-20 |  |  | 6 | 12-Jun-25 A | 2026-05-17 | 14-Jun-25 A | 2026-02-20 | 2026-05-17
| A56720 | Technical Bid Evaluation for Heat Exchangers_RCA |  | 2026-02-20 |  |  | 6 | 15-Jun-25 A | 2026-05-17 | 17-Jun-25 A | 2026-02-20 | 2026-05-17
| A56730 | Technical Bid Evaluation for Heat Exchangers_IFD/IFC |  | 2026-02-20 |  |  | 3 | 18-Jun-25 A | 2026-05-17 | 20-Jun-25 A | 2026-02-20 | 2026-05-17
| A36970 | Commercial Bid Evaluation(Completion) |  | 2026-02-20 |  |  | 6 | 20-Jun-25 A | 2026-05-17 | 24-Jun-25 A | 2026-02-20 | 2026-05-17
| A36980 | Issue Purchase Order to Vendor |  | 2026-02-20 |  |  | 3 | 25-Jun-25 A | 2026-05-17 | 27-Jun-25 A | 2026-02-20 | 2026-05-17
| OG Comp. Interstage Cooler (BEU) (13-HE-708) |  |  | 2026-02-20 |  |  | 36 | 01-Jun-25 A | 2026-05-26 | 27-Jun-25 A | 2026-02-20 | 2026-05-26 | 87
| A36990 | Issue RFQ to Bidders |  | 2026-02-20 |  |  | 21 | 01-Jun-25 A | 2026-05-26 | 03-Jun-25 A | 2026-02-20 | 2026-05-26
| A56740 | Technical Bid Evaluation for Heat Exchangers_IFR |  | 2026-02-20 |  |  | 6 | 04-Jun-25 A | 2026-05-26 | 07-Jun-25 A | 2026-02-20 | 2026-05-26
| A56750 | Technical Bid Evaluation for Heat Exchangers_RCC |  | 2026-02-20 |  |  | 5 | 08-Jun-25 A | 2026-05-26 | 11-Jun-25 A | 2026-02-20 | 2026-05-26
| A56760 | Technical Bid Evaluation for Heat Exchangers_IFA |  | 2026-02-20 |  |  | 6 | 12-Jun-25 A | 2026-05-26 | 14-Jun-25 A | 2026-02-20 | 2026-05-26
| A56770 | Technical Bid Evaluation for Heat Exchangers_RCA |  | 2026-02-20 |  |  | 6 | 15-Jun-25 A | 2026-05-26 | 17-Jun-25 A | 2026-02-20 | 2026-05-26
| A56780 | Technical Bid Evaluation for Heat Exchangers_IFD/IFC |  | 2026-02-20 |  |  | 3 | 18-Jun-25 A | 2026-05-26 | 20-Jun-25 A | 2026-02-20 | 2026-05-26
| A37010 | Commercial Bid Evaluation(Completion) |  | 2026-02-20 |  |  | 6 | 20-Jun-25 A | 2026-05-26 | 24-Jun-25 A | 2026-02-20 | 2026-05-26
| A37020 | Issue Purchase Order to Vendor |  | 2026-02-20 |  |  | 3 | 25-Jun-25 A | 2026-05-26 | 27-Jun-25 A | 2026-02-20 | 2026-05-26
| C4 Guard Regen. Gas Cooler (BEU) (Tag#50-HE-1410) |  |  | 2026-02-20 |  |  | 36 | 01-Jun-25 A | 2026-05-26 | 02-Jul-25 A | 2026-02-20 | 2026-05-26 | 138
| A37030 | Issue RFQ to Bidders |  | 2026-02-20 |  |  | 21 | 01-Jun-25 A | 2026-05-26 | 03-Jun-25 A | 2026-02-20 | 2026-05-26
| A56790 | Technical Bid Evaluation for Heat Exchangers_IFR |  | 2026-02-20 |  |  | 6 | 04-Jun-25 A | 2026-05-26 | 07-Jun-25 A | 2026-02-20 | 2026-05-26
| A56800 | Technical Bid Evaluation for Heat Exchangers_RCC |  | 2026-02-20 |  |  | 5 | 08-Jun-25 A | 2026-05-26 | 11-Jun-25 A | 2026-02-20 | 2026-05-26
| A56810 | Technical Bid Evaluation for Heat Exchangers_IFA |  | 2026-02-20 |  |  | 6 | 12-Jun-25 A | 2026-05-26 | 14-Jun-25 A | 2026-02-20 | 2026-05-26
| A56820 | Technical Bid Evaluation for Heat Exchangers_RCA |  | 2026-02-20 |  |  | 6 | 15-Jun-25 A | 2026-05-26 | 17-Jun-25 A | 2026-02-20 | 2026-05-26
| A56830 | Technical Bid Evaluation for Heat Exchangers_IFD/IFC |  | 2026-02-20 |  |  | 3 | 18-Jun-25 A | 2026-05-26 | 20-Jun-25 A | 2026-02-20 | 2026-05-26
| A37050 | Commercial Bid Evaluation(Completion) |  | 2026-02-20 |  |  | 3 | 20-Jun-25 A | 2026-05-26 | 27-Jun-25 A | 2026-02-20 | 2026-05-26
| A37060 | Issue Purchase Order to Vendor |  | 2026-02-20 |  |  | 3 | 30-Jun-25 A | 2026-05-26 | 02-Jul-25 A | 2026-02-20 | 2026-05-26
| A16510 | Issue RFQ to Bidders |  | 2026-02-20 |  |  | 20 | 25-May-25 A | 2026-06-15 | 03-Jun-25 A | 2026-02-20 | 2026-06-15
| A53240 | Technical Bid Evaluation For HVAC Equipments_IFR |  | 2026-02-20 |  |  | 11 | 04-Jun-25 A | 2026-06-15 | 19-Jun-25 A | 2026-02-20 | 2026-06-15
| A25290 | Technical Bid Evaluation For HVAC Equipments_RCC |  | 2026-02-20 |  |  | 1 | 20-Jun-25 A | 2026-06-15 | 25-Jun-25 A | 2026-02-20 | 2026-06-15
| A25300 | Technical Bid Evaluation For HVAC Equipments_IFA |  | 2026-02-20 |  |  | 5 | 26-Jun-25 A | 2026-06-15 | 02-Jul-25 A | 2026-02-20 | 2026-06-15
| A25310 | Technical Bid Evaluation For HVAC Equipments_RCA |  | 2026-02-20 |  |  | 5 | 03-Jul-25 A | 2026-06-15 | 08-Jul-25 A | 2026-02-20 | 2026-06-15
| A25320 | Technical Bid Evaluation For HVAC Equipments_IFD/IFC |  | 2026-02-20 |  |  | 5 | 09-Jul-25 A | 2026-06-15 | 14-Jul-25 A | 2026-02-20 | 2026-06-15
| A19890 | Commercial Bid Evaluation(Completion) |  | 2026-02-20 |  |  | 1 | 15-Jul-25 A | 2026-06-15 | 31-Jul-25 A | 2026-02-20 | 2026-06-15
| A19870 | Issue Purchase Order to Vendor |  | 2026-02-20 |  |  | 1 | 20-Aug-25 A | 2026-06-15 | 29-Aug-25 A | 2026-02-20 | 2026-06-15
| Bulk Materials |  |  | 2026-02-20 |  |  | 326 | 15-Jan-25 A | 2026-02-23 | 2026-07-24 | 2026-07-24 | 2027-07-20 | 257
| Drip Leg |  |  | 2026-02-20 |  |  | 71 | 01-Aug-25 A | 2026-03-19 | 09-Sep-25 A | 2026-02-20 | 2026-03-31 | 27
| OG Comp. Dis. Drip leg (02 Nos) |  |  | 2026-02-20 |  |  | 71 | 01-Aug-25 A | 2026-03-19 | 09-Sep-25 A | 2026-02-20 | 2026-03-31 | 27
| A8790 | Issue RFQ to Bidders |  | 2026-02-20 |  |  | 15 | 01-Aug-25 A | 2026-03-19 | 05-Aug-25 A | 2026-02-20 | 2026-03-19
| A56840 | Technical Bid Evaluation for Pressure Vessels & Internals_IFR |  | 2026-02-20 |  |  | 8 | 06-Aug-25 A | 2026-03-19 | 07-Aug-25 A | 2026-02-20 | 2026-03-19
| A56850 | Technical Bid Evaluation for Pressure Vessels & Internals_RCC |  | 2026-02-20 |  |  | 8 | 08-Aug-25 A | 2026-03-19 | 13-Aug-25 A | 2026-02-20 | 2026-03-19
| A56860 | Technical Bid Evaluation for Pressure Vessels & Internals_IFA |  | 2026-02-20 |  |  | 8 | 14-Aug-25 A | 2026-03-19 | 19-Aug-25 A | 2026-02-20 | 2026-03-19
| A56870 | Technical Bid Evaluation for Pressure Vessels & Internals_RCA |  | 2026-02-20 |  |  | 8 | 20-Aug-25 A | 2026-03-31 | 25-Aug-25 A | 2026-02-20 | 2026-03-31
| A56880 | Technical Bid Evaluation for Pressure Vessels & Internals_IFD/IFC |  | 2026-02-20 |  |  | 8 | 26-Aug-25 A | 2026-03-31 | 29-Aug-25 A | 2026-02-20 | 2026-03-31
| A19370 | Commercial Bid Evaluation(Completion) |  | 2026-02-20 |  |  | 15 | 30-Aug-25 A | 2026-03-31 | 03-Sep-25 A | 2026-02-20 | 2026-03-31
| A19350 | Issue Purchase Order to Vendor |  | 2026-02-20 |  |  | 11 | 04-Sep-25 A | 2026-03-31 | 09-Sep-25 A | 2026-02-20 | 2026-03-31
| Fire Fighting Equipment |  |  | 2026-02-20 |  |  | 197 | 11-Feb-25 A | 2026-03-27 | 2026-03-19 | 2026-03-19 | 2026-06-18 | 65
| TA_Fire Alarm System Modification - SAFCO |  |  | 2026-02-20 |  |  | 48 | 11-Feb-25 A | 2026-03-27 | 31-Mar-25 A | 2026-02-20 | 2026-03-27
| A37120 | Issue RFQ to Bidders |  | 2026-02-20 |  |  | 20 | 11-Feb-25 A | 2026-03-27 | 28-Feb-25 A | 2026-02-20 | 2026-03-27
| A37150 | Issue Purchase Order to Vendor |  | 2026-02-20 |  |  | 10 | 03-Mar-25 A | 2026-03-27 | 21-Mar-25 A | 2026-02-20 | 2026-03-27
| A57240 | TBE for ICT System Modification_Free Issue Material |  | 2026-02-20 |  |  | 23 | 24-Mar-25 A | 2026-03-27 | 31-Mar-25 A | 2026-02-20 | 2026-03-27
| VESDA (Very Early Smoke Detection Apparatus) |  |  | 2026-02-20 |  |  | 127 | 01-May-25 A | 2026-06-02 | 01-Oct-25 A | 2026-02-20 | 2026-06-02 | 72
| A20710 | Issue RFQ to Bidders |  | 2026-02-20 |  |  | 21 | 01-May-25 A | 2026-06-02 | 20-Jun-25 A | 2026-02-20 | 2026-06-02
| A20730 | Bid Evaluation(Completion) |  | 2026-02-20 |  |  | 40 | 25-Aug-25 A | 2026-06-02 | 29-Aug-25 A | 2026-02-20 | 2026-06-02
| A20740 | Commercial Bid Evaluation(Completion) |  | 2026-02-20 |  |  | 20 | 01-Sep-25 A | 2026-06-02 | 12-Sep-25 A | 2026-02-20 | 2026-06-02
| A20720 | Issue Purchase Order to Vendor for VESDA |  | 2026-02-20 |  |  | 10 | 15-Sep-25 A | 2026-06-02 | 01-Oct-25 A | 2026-02-20 | 2026-06-02
| A17470 | Issue RFQ to Bidders |  | 2026-02-20 |  |  | 5 | 20-Oct-25 A | 2026-05-22 | 27-Oct-25 A | 2026-02-20 | 2026-05-22
| A18090 | Bid Evaluation(Completion) |  | 2026-02-20 |  |  | 15 | 01-Feb-26 A | 2026-05-22 | 11-Mar-26 A | 2026-02-20 | 2026-05-22
| A18100 | Commercial Bid Evaluation(Completion) |  | 2026-02-20 |  |  | 15 | 12-Feb-26 A | 2026-05-22 | 2026-03-12 | 2026-03-12 | 2026-06-11 | 65
| A18080 | Issue Purchase Order to Vendor for Fire Fighting Equipment |  | 2026-03-13 |  |  | 5 | 2026-03-13 | 2026-06-12 | 2026-03-19 | 2026-03-19 | 2026-06-18 | 65
| Tail Gas Filter/Silencer/Colesor |  |  | 2026-02-20 |  |  | 187 | 01-Apr-25 A | 2026-11-09 | 2026-03-02 | 2026-03-02 | 2026-11-18 | 186
| Coalescer - (BF) |  |  | 2026-02-20 |  |  | 187 | 01-Apr-25 A | 2026-11-09 | 2026-03-02 | 2026-03-02 | 2026-11-18 | 186
| A8130 | Issue RFQ to Bidders |  | 2026-02-20 |  |  | 20 | 01-Apr-25 A | 2026-11-09 | 10-Apr-25 A | 2026-02-20 | 2026-11-09
| A45520 | Technical Bid Evaluation for Coalscer_RCC |  | 2026-02-20 |  |  | 3 | 25-Jan-26 A | 2026-11-09 | 26-Jan-26 A | 2026-02-20 | 2026-11-09
| A45530 | Technical Bid Evaluation for Coalscer_IFA |  | 2026-02-20 |  |  | 3 | 27-Jan-26 A | 2026-11-09 | 28-Jan-26 A | 2026-02-20 | 2026-11-09
| A8160 | Issue Purchase Order to Vendor |  | 2026-02-20 |  |  | 3 | 29-Jan-26 A | 2026-11-18 | 29-Jan-26 A | 2026-02-20 | 2026-11-18
| A45540 | Technical Bid Evaluation for Coalscer_RCA |  | 2026-02-20 |  |  | 3 | 2026-02-20 | 2026-11-09 | 2026-02-25 | 2026-02-25 | 2026-11-12 | 186
| A45550 | Technical Bid Evaluation for Coalscer_IFD/IFC |  | 2026-02-25 |  |  | 3 | 2026-02-25 | 2026-11-12 | 2026-03-02 | 2026-03-02 | 2026-11-17 | 186
| Steel Structure (material +sandwitch Panel) |  |  | 2026-02-20 |  |  | 181 | 01-Mar-25 A | 2026-02-23 | 2026-03-09 | 2026-03-09 | 2026-11-23 | 185
| Civil Bulk Material |  |  | 2026-02-20 |  |  | 54 | 16-May-25 A | 2026-11-23 | 10-Jul-25 A | 2026-02-20 | 2026-11-23
| A9550 | Issue RFQ to Bidders |  | 2026-02-20 |  |  | 21 | 16-May-25 A | 2026-11-23 | 01-Jun-25 A | 2026-02-20 | 2026-11-23
| A9580 | Issue Purchase Order to Vendor |  | 2026-02-20 |  |  | 21 | 09-Jun-25 A | 2026-11-23 | 20-Jun-25 A | 2026-02-20 | 2026-11-23
| A9560 | Vendor Quote Received |  | 2026-02-20 |  |  | 30 | 02-Jun-25 A | 2026-11-23 | 01-Jul-25 A | 2026-02-20 | 2026-11-23
| A9570 | Technical Bid Evaluation |  | 2026-02-20 |  |  | 21 | 02-Jul-25 A | 2026-11-23 | 10-Jul-25 A | 2026-02-20 | 2026-11-23
| TA_Steel Structure (Additional Steel Structure required for BFW) |  |  | 2026-02-20 |  |  | 30 | 01-Mar-25 A | 2026-03-27 | 20-Mar-25 A | 2026-02-20 | 2026-03-27
| A21910 | Issue RFQs to Bidders (Remaining Steel Structure for TA) |  | 2026-02-20 |  |  | 5 | 01-Mar-25 A | 2026-03-27 | 05-Mar-25 A | 2026-02-20 | 2026-03-27
| A21920 | Vendor Quote Received |  | 2026-02-20 |  |  | 10 | 05-Mar-25 A | 2026-03-27 | 10-Mar-25 A | 2026-02-20 | 2026-03-27
| A21940 | TBE for Steel Structure (TA) |  | 2026-02-20 |  |  | 10 | 11-Mar-25 A | 2026-03-27 | 15-Mar-25 A | 2026-02-20 | 2026-03-27
| A21930 | Issue Purchase Order to Vendor |  | 2026-02-20 |  |  | 5 | 16-Mar-25 A | 2026-03-27 | 20-Mar-25 A | 2026-02-20 | 2026-03-27
| Steel Structure - Post TA |  |  | 2026-02-20 |  |  | 95 | 01-Jun-25 A | 2026-02-23 | 03-Oct-25 A | 2026-02-20 | 2026-07-24
| 122 | Issue RFQ to Bidders |  | 2026-02-20 |  |  | 10 | 01-Jun-25 A | 2026-02-23 | 25-Jul-25 A | 2026-02-20 | 2026-02-23
| A34530 | Bid Evaluation(Completion) |  | 2026-02-20 |  |  | 10 | 25-Aug-25 A | 2026-04-20 | 05-Sep-25 A | 2026-02-20 | 2026-04-20
| A34540 | Commercial Bid Evaluation(Completion) |  | 2026-02-20 |  |  | 10 | 08-Sep-25 A | 2026-04-20 | 22-Sep-25 A | 2026-02-20 | 2026-04-20
| A34550 | Issue Purchase Order to Vendor |  | 2026-02-20 |  |  | 10 | 23-Sep-25 A | 2026-07-24 | 03-Oct-25 A | 2026-02-20 | 2026-07-24
| Structural Steel |  |  | 2026-02-20 |  |  | 181 | 01-Jun-25 A | 2026-02-23 | 2026-03-09 | 2026-03-09 | 2026-03-13 | 5
| A23620 | Issue RFQ to Bidders |  | 2026-02-20 |  |  | 10 | 01-Jun-25 A | 2026-02-23 | 25-Jun-25 A | 2026-02-20 | 2026-02-23
| A23630 | Vendor Quote Received |  | 2026-02-20 |  |  | 10 | 25-Aug-25 A | 2026-02-23 | 05-Sep-25 A | 2026-02-20 | 2026-02-23
| A57960 | Technical Bid Evaluation for Structural Steel_IFR |  | 2026-02-20 |  |  | 6 | 08-Sep-25 A | 2026-02-23 | 12-Sep-25 A | 2026-02-20 | 2026-02-23
| A57970 | Technical Bid Evaluation for Structural Steel_RCC |  | 2026-02-20 |  |  | 6 | 15-Sep-25 A | 2026-02-23 | 19-Sep-25 A | 2026-02-20 | 2026-02-23
| A57980 | Technical Bid Evaluation for Structural Steel_IFA |  | 2026-02-20 |  |  | 6 | 19-Sep-25 A | 2026-02-23 | 01-Oct-25 A | 2026-02-20 | 2026-02-23
| A23640 | Issue Purchase Order to Vendor |  | 2026-02-20 |  |  | 10 | 15-Sep-25 A | 2026-02-23 | 03-Oct-25 A | 2026-02-20 | 2026-02-23
| A57990 | Technical Bid Evaluation for Structural Steel_RCA |  | 2026-02-20 |  |  | 6 | 2026-02-20 | 2026-02-26 | 2026-02-27 | 2026-02-27 | 2026-03-06 | 5
| A58000 | Technical Bid Evaluation for Structural Steel_IFD/IFC |  | 2026-02-27 |  |  | 6 | 2026-02-27 | 2026-03-06 | 2026-03-09 | 2026-03-09 | 2026-03-13 | 5
| Turbing Material [SS tubes, Connectors, unions, plugs etc.] |  |  | 2026-02-20 |  |  | 40 | 2026-02-20 | 2026-04-07 | 2026-04-16 | 2026-04-16 | 2026-06-01 | 32
| Turbing Material [SS tubes, Connectors, unions, plugs etc] |  |  | 2026-02-20 |  |  | 40 | 2026-02-20 | 2026-04-07 | 2026-04-16 | 2026-04-16 | 2026-06-01 | 32
| A17410 | Issue RFQ to Bidders |  | 2026-02-20 |  |  | 10 | 2026-02-20 | 2026-04-07 | 2026-03-05 | 2026-03-05 | 2026-04-20 | 32
| A18210 | Bid Evaluation(Completion) |  | 2026-03-06 |  |  | 10 | 2026-03-06 | 2026-04-21 | 2026-03-19 | 2026-03-19 | 2026-05-04 | 32
| A18220 | Commercial Bid Evaluation(Completion) |  | 2026-03-20 |  |  | 10 | 2026-03-20 | 2026-05-05 | 2026-04-02 | 2026-04-02 | 2026-05-18 | 32
| A18200 | Issue Purchase Order to Vendor |  | 2026-04-03 |  |  | 10 | 2026-04-03 | 2026-05-19 | 2026-04-16 | 2026-04-16 | 2026-06-01 | 32
| Telecom (ACS+LAN +CCTV+PAGA) |  |  | 2026-02-20 |  |  | 111 | 11-Mar-25 A | 2026-03-27 | 2026-02-27 | 2026-02-27 | 2027-01-20 | 233
| Acess Control System |  |  | 2026-02-20 |  |  | 91 | 01-Aug-25 A | 2026-04-08 | 2026-02-27 | 2026-02-27 | 2027-01-20 | 233
| A18720 | RFQs to Bid Receipt |  | 2026-02-20 |  |  | 3 | 01-Aug-25 A | 2026-04-08 | 06-Aug-25 A | 2026-02-20 | 2026-04-08
| A23880 | Technical Bid Evaluation For Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_IFR |  | 2026-02-20 |  |  | 3 | 31-Oct-25 A | 2026-04-08 | 14-Nov-25 A | 2026-02-20 | 2026-04-08
| A23890 | Technical Bid Evaluation For Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_RCC |  | 2026-02-20 |  |  | 3 | 26-Nov-25 A | 2026-04-08 | 28-Nov-25 A | 2026-02-20 | 2026-04-08
| A22340 | Commercial Bid Evaluation(Completion) |  | 2026-02-20 |  |  | 3 | 01-Dec-25 A | 2026-04-08 | 03-Dec-25 A | 2026-02-20 | 2026-04-08
| A51950 | Technical Bid Evaluation For Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_IFA |  | 2026-02-20 |  |  | 3 | 01-Dec-25 A | 2026-04-08 | 03-Dec-25 A | 2026-02-20 | 2026-04-08
| A22350 | Issue Purchase Order to Vendor for ACS |  | 2026-02-20 |  |  | 3 | 13-Dec-25 A | 2026-04-08 | 19-Dec-25 A | 2026-02-20 | 2026-04-08
| A51960 | Technical Bid Evaluation For Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_RCA |  | 2026-02-20 |  |  | 3 | 2026-02-20 | 2027-01-13 | 2026-02-24 | 2026-02-24 | 2027-01-15 | 233
| A51970 | Technical Bid Evaluation For Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_IFD/IFC |  | 2026-02-25 |  |  | 3 | 2026-02-25 | 2027-01-18 | 2026-02-27 | 2026-02-27 | 2027-01-20 | 233
| TA_LAN System Modification - CISCO |  |  | 2026-02-20 |  |  | 48 | 11-Mar-25 A | 2026-03-27 | 10-Apr-25 A | 2026-02-20 | 2026-03-27
| A37200 | Issue RFQ to Bidders |  | 2026-02-20 |  |  | 20 | 11-Mar-25 A | 2026-03-27 | 27-Mar-25 A | 2026-02-20 | 2026-03-27
| A57480 | TBE for Electrical System Modification_Free Issue Material |  | 2026-02-20 |  |  | 23 | 28-Mar-25 A | 2026-03-27 | 03-Apr-25 A | 2026-02-20 | 2026-03-27
| A37230 | Issue Purchase Order to Vendor |  | 2026-02-20 |  |  | 10 | 03-Apr-25 A | 2026-03-27 | 10-Apr-25 A | 2026-02-20 | 2026-03-27
| PAGA + Telephone |  |  | 2026-02-20 |  |  | 91 | 01-Aug-25 A | 2026-05-22 | 2026-02-27 | 2026-02-27 | 2027-01-20 | 233
| A18810 | RFQs to Bid Receipt |  | 2026-02-20 |  |  | 3 | 01-Aug-25 A | 2026-05-22 | 06-Aug-25 A | 2026-02-20 | 2026-05-22
| A56990 | Technical Bid Evaluation For Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_IFR |  | 2026-02-20 |  |  | 3 | 24-Nov-25 A | 2026-05-22 | 26-Nov-25 A | 2026-02-20 | 2026-05-22
| A57000 | Technical Bid Evaluation For Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_RCC |  | 2026-02-20 |  |  | 3 | 27-Nov-25 A | 2026-05-22 | 01-Dec-25 A | 2026-02-20 | 2026-05-22
| A57010 | Technical Bid Evaluation For Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_IFA |  | 2026-02-20 |  |  | 3 | 03-Dec-25 A | 2026-05-22 | 05-Dec-25 A | 2026-02-20 | 2026-05-22
| A19130 | Commercial Bid Evaluation(Completion) |  | 2026-02-20 |  |  | 3 | 11-Dec-25 A | 2026-05-22 | 15-Dec-25 A | 2026-02-20 | 2026-05-22
| A19110 | Issue Purchase Order to Vendor for PAGA + Telephone |  | 2026-02-20 |  |  | 3 | 11-Dec-25 A | 2026-05-22 | 19-Dec-25 A | 2026-02-20 | 2026-05-22
| A57020 | Technical Bid Evaluation For Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_RCA |  | 2026-02-20 |  |  | 3 | 2026-02-20 | 2027-01-13 | 2026-02-24 | 2026-02-24 | 2027-01-15 | 233
| A57030 | Technical Bid Evaluation For Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_IFD/IFC |  | 2026-02-25 |  |  | 3 | 2026-02-25 | 2027-01-18 | 2026-02-27 | 2026-02-27 | 2027-01-20 | 233
| CCTV |  |  | 2026-02-20 |  |  | 91 | 01-Aug-25 A | 2026-05-13 | 2026-02-27 | 2026-02-27 | 2027-01-20 | 233
| A18900 | RFQs to Bid Receipt |  | 2026-02-20 |  |  | 3 | 01-Aug-25 A | 2026-05-13 | 06-Aug-25 A | 2026-02-20 | 2026-05-13
| A57050 | Technical Bid Evaluation For Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_RCC |  | 2026-02-20 |  |  | 3 | 26-Nov-25 A | 2026-05-13 | 28-Nov-25 A | 2026-02-20 | 2026-05-13
| A57060 | Technical Bid Evaluation For Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_IFA |  | 2026-02-20 |  |  | 3 | 01-Dec-25 A | 2026-05-13 | 03-Dec-25 A | 2026-02-20 | 2026-05-13
| A19190 | Commercial Bid Evaluation(Completion) |  | 2026-02-20 |  |  | 3 | 11-Dec-25 A | 2026-05-13 | 15-Dec-25 A | 2026-02-20 | 2026-05-13
| A19170 | Issue Purchase Order to Vendor for CCTV |  | 2026-02-20 |  |  | 3 | 11-Dec-25 A | 2026-05-13 | 19-Dec-25 A | 2026-02-20 | 2026-05-13
| A57070 | Technical Bid Evaluation For Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_RCA |  | 2026-02-20 |  |  | 3 | 2026-02-20 | 2027-01-13 | 2026-02-24 | 2026-02-24 | 2027-01-15 | 233
| A57080 | Technical Bid Evaluation For Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_IFD/IFC |  | 2026-02-25 |  |  | 3 | 2026-02-25 | 2027-01-18 | 2026-02-27 | 2026-02-27 | 2027-01-20 | 233
| Telecom (ACS + CCTV + PAGA) Integration |  |  | 2026-02-20 |  |  | 48 | 01-Aug-25 A | 2026-06-11 | 19-Dec-25 A | 2026-02-20 | 2026-06-11 | 79
| A16990 | Issue RFQ to Bidders |  | 2026-02-20 |  |  | 3 | 01-Aug-25 A | 2026-06-11 | 06-Aug-25 A | 2026-02-20 | 2026-06-11
| A22270 | Bid Evaluation(Completion) |  | 2026-02-20 |  |  | 3 | 01-Dec-25 A | 2026-06-11 | 03-Dec-25 A | 2026-02-20 | 2026-06-11
| A22280 | Commercial Bid Evaluation(Completion) |  | 2026-02-20 |  |  | 3 | 02-Dec-25 A | 2026-06-11 | 04-Dec-25 A | 2026-02-20 | 2026-06-11
| A22290 | Issue Purchase Order to Vendor for Telecom (ACS+CCTV+PAGA) Integration |  | 2026-02-20 |  |  | 3 | 12-Dec-25 A | 2026-06-11 | 19-Dec-25 A | 2026-02-20 | 2026-06-11
| Lighting Fixtures |  |  | 2026-02-20 |  |  | 66 | 2026-02-20 | 2026-06-11 | 2026-05-22 | 2026-05-22 | 2026-09-10 | 79
| Lighting Fixtures (Almost 50% Exd = 354 Nos) |  |  | 2026-02-20 |  |  | 66 | 2026-02-20 | 2026-06-11 | 2026-05-22 | 2026-05-22 | 2026-09-10 | 79
| A16390 | Issue RFQ to Bidders |  | 2026-02-20 |  |  | 21 | 2026-02-20 | 2026-06-11 | 2026-03-20 | 2026-03-20 | 2026-07-09 | 79
| A19600 | Bid Evaluation(Completion) |  | 2026-03-23 |  |  | 15 | 2026-03-23 | 2026-07-10 | 2026-04-10 | 2026-04-10 | 2026-07-30 | 79
| A19610 | Commercial Bid Evaluation(Completion) |  | 2026-04-13 |  |  | 15 | 2026-04-13 | 2026-07-31 | 2026-05-01 | 2026-05-01 | 2026-08-20 | 79
| A19590 | Issue Purchase Order to Vendor for Lighting Fixtures |  | 2026-05-04 |  |  | 15 | 2026-05-04 | 2026-08-21 | 2026-05-22 | 2026-05-22 | 2026-09-10 | 79
| Manual Valve |  |  | 2026-02-20 |  |  | 152 | 20-May-25 A | 2026-05-15 | 21-Nov-25 A | 2026-02-20 | 2026-05-18 | 62
| Manual Valves (Gate 9 Nos, Check 6 Nos, Globe Valves 64 Nos) |  |  | 2026-02-20 |  |  | 152 | 20-May-25 A | 2026-05-15 | 21-Nov-25 A | 2026-02-20 | 2026-05-18 | 62
| A9270 | Issue RFQ to Bidders |  | 2026-02-20 |  |  | 21 | 20-May-25 A | 2026-05-15 | 24-Jul-25 A | 2026-02-20 | 2026-05-15
| A45030 | Technical Bid Evaluation (TBE) for Manual Valves_RCC |  | 2026-02-20 |  |  | 6 | 26-Sep-25 A | 2026-05-15 | 02-Oct-25 A | 2026-02-20 | 2026-05-15
| A45050 | Technical Bid Evaluation (TBE) for Manual Valves_RCA |  | 2026-02-20 |  |  | 6 | 08-Oct-25 A | 2026-05-18 | 10-Oct-25 A | 2026-02-20 | 2026-05-18
| A45060 | Technical Bid Evaluation (TBE) for Manual Valves_IFD/IFC |  | 2026-02-20 |  |  | 6 | 10-Oct-25 A | 2026-05-18 | 14-Oct-25 A | 2026-02-20 | 2026-05-18
| A18160 | Commercial Bid Evaluation(Completion) |  | 2026-02-20 |  |  | 6 | 15-Oct-25 A | 2026-05-18 | 24-Oct-25 A | 2026-02-20 | 2026-05-18
| A45040 | Technical Bid Evaluation (TBE) for Manual Valves_IFA |  | 2026-02-20 |  |  | 6 | 03-Oct-25 A | 2026-05-15 | 07-Nov-25 A | 2026-02-20 | 2026-05-15
| A18140 | Issue Purchase Order to Vendor for Manual Valves |  | 2026-02-20 |  |  | 21 | 27-Oct-25 A | 2026-05-18 | 21-Nov-25 A | 2026-02-20 | 2026-05-18
| Piping Bulk |  |  | 2026-02-20 |  |  | 241 | 01-Jul-25 A | 2026-03-30 | 2026-07-24 | 2026-07-24 | 2027-05-14 | 210
| Piping Lot for Post TA |  |  | 2026-02-20 |  |  | 80 | 01-Jul-25 A | 2026-04-22 | 17-Nov-25 A | 2026-02-20 | 2026-04-22 | 43
| 112 | Issue RFQ to Bidders |  | 2026-02-20 |  |  | 15 | 01-Jul-25 A | 2026-04-22 | 21-Jul-25 A | 2026-02-20 | 2026-04-22
| A23680 | Issue Purchase Order to Vendor |  | 2026-02-20 |  |  | 6 | 01-Sep-25 A | 2026-04-22 | 06-Sep-25 A | 2026-02-20 | 2026-04-22
| A57090 | Technical Bid Evaluation (TBE) for Piping Bulk_IFR |  | 2026-02-20 |  |  | 6 | 22-Jul-25 A | 2026-04-22 | 15-Sep-25 A | 2026-02-20 | 2026-04-22
| A57100 | Technical Bid Evaluation (TBE) for Piping Bulk_RCC |  | 2026-02-20 |  |  | 8 | 15-Sep-25 A | 2026-04-22 | 15-Oct-25 A | 2026-02-20 | 2026-04-22
| A23700 | Commercial Bid Evaluation(Completion) |  | 2026-02-20 |  |  | 6 | 15-Oct-25 A | 2026-04-22 | 24-Oct-25 A | 2026-02-20 | 2026-04-22
| A57110 | Technical Bid Evaluation (TBE) for Piping Bulk_IFA |  | 2026-02-20 |  |  | 7 | 25-Oct-25 A | 2026-04-22 | 29-Oct-25 A | 2026-02-20 | 2026-04-22
| A57120 | Technical Bid Evaluation (TBE) for Piping Bulk_RCA |  | 2026-02-20 |  |  | 8 | 30-Oct-25 A | 2026-04-22 | 14-Nov-25 A | 2026-02-20 | 2026-04-22
| A57130 | Technical Bid Evaluation (TBE) for Piping Bulk_IFD/IFC |  | 2026-02-20 |  |  | 6 | 14-Nov-25 A | 2026-04-22 | 17-Nov-25 A | 2026-02-20 | 2026-04-22
| Piping Supports (Swing Hangers) for Post TA |  |  | 2026-02-20 |  |  | 83 | 04-Aug-25 A | 2026-03-30 | 08-Sep-25 A | 2026-02-20 | 2026-05-25 | 38
| A23710 | Issue RFQ to Bidders |  | 2026-02-20 |  |  | 20 | 04-Aug-25 A | 2026-03-30 | 08-Aug-25 A | 2026-02-20 | 2026-03-30
| A57140 | Technical Bid Evaluation (TBE) for Spring Hangers_IFR |  | 2026-02-20 |  |  | 11 | 09-Aug-25 A | 2026-03-30 | 14-Aug-25 A | 2026-02-20 | 2026-03-30
| A57150 | Technical Bid Evaluation (TBE) for Spring Hangers_RCC |  | 2026-02-20 |  |  | 16 | 15-Aug-25 A | 2026-03-30 | 16-Aug-25 A | 2026-02-20 | 2026-03-30
| A57160 | Technical Bid Evaluation (TBE) for Spring Hangers_IFA |  | 2026-02-20 |  |  | 8 | 18-Aug-25 A | 2026-03-30 | 19-Aug-25 A | 2026-02-20 | 2026-03-30
| A57170 | Technical Bid Evaluation (TBE) for Spring Hangers_RCA |  | 2026-02-20 |  |  | 16 | 20-Aug-25 A | 2026-05-25 | 22-Aug-25 A | 2026-02-20 | 2026-05-25
| A57180 | Technical Bid Evaluation (TBE) for Spring Hangers_IFD/IFC |  | 2026-02-20 |  |  | 8 | 25-Aug-25 A | 2026-05-25 | 26-Aug-25 A | 2026-02-20 | 2026-05-25
| A23740 | Commercial Bid Evaluation(Completion) |  | 2026-02-20 |  |  | 21 | 06-Aug-25 A | 2026-03-30 | 30-Aug-25 A | 2026-02-20 | 2026-03-30
| A23720 | Issue Purchase Order to Vendor |  | 2026-02-20 |  |  | 7 | 01-Sep-25 A | 2026-03-30 | 08-Sep-25 A | 2026-02-20 | 2026-03-30
| Piping 1st Lot for GF |  |  | 2026-02-20 |  |  | 146 | 01-Jul-25 A | 2026-04-20 | 2026-03-13 | 2026-03-13 | 2027-01-20 | 223
| 100 | Issue RFQ to Bidders |  | 2026-02-20 |  |  | 21 | 01-Jul-25 A | 2026-04-20 | 21-Jul-25 A | 2026-02-20 | 2026-04-20
| A44970 | Technical Bid Evaluation (TBE) for Piping Bulk_IFR |  | 2026-02-20 |  |  | 8 | 19-Aug-25 A | 2026-04-20 | 29-Aug-25 A | 2026-02-20 | 2026-04-20
| A21370 | Commercial Bid Evaluation(Completion) |  | 2026-02-20 |  |  | 15 | 25-Aug-25 A | 2026-04-20 | 05-Sep-25 A | 2026-02-20 | 2026-04-20
| A44980 | Technical Bid Evaluation (TBE) for Piping Bulk_RCC |  | 2026-02-20 |  |  | 8 | 30-Aug-25 A | 2026-04-20 | 08-Sep-25 A | 2026-02-20 | 2026-04-20
| A44990 | Technical Bid Evaluation (TBE) for Piping Bulk_IFA |  | 2026-02-20 |  |  | 8 | 09-Sep-25 A | 2026-04-20 | 16-Sep-25 A | 2026-02-20 | 2026-04-20
| A21350 | Issue Purchase Order to Vendor |  | 2026-02-20 |  |  | 14 | 08-Sep-25 A | 2026-04-20 | 19-Sep-25 A | 2026-02-20 | 2026-04-20
| A45000 | Technical Bid Evaluation (TBE) for Piping Bulk_RCA |  | 2026-02-20 |  |  | 8 | 2026-02-20 | 2026-12-30 | 2026-03-03 | 2026-03-03 | 2027-01-11 | 223
| A45010 | Technical Bid Evaluation (TBE) for Piping Bulk_IFD/IFC |  | 2026-03-03 |  |  | 8 | 2026-03-03 | 2027-01-11 | 2026-03-13 | 2026-03-13 | 2027-01-20 | 223
| Piping 2nd Lot for GF (CS Material) |  |  | 2026-02-20 |  |  | 20 | 2026-02-20 | 2026-05-18 | 2026-03-19 | 2026-03-19 | 2026-06-12 | 61
| 101 | Issue RFQ to Bidders |  | 2026-02-20 |  |  | 5 | 2026-02-20 | 2026-05-18 | 2026-02-26 | 2026-02-26 | 2026-05-22 | 61
| A21420 | Bid Evaluation(Completion) |  | 2026-02-27 |  |  | 5 | 2026-02-27 | 2026-05-25 | 2026-03-05 | 2026-03-05 | 2026-05-29 | 61
| A21430 | Commercial Bid Evaluation(Completion) |  | 2026-03-06 |  |  | 5 | 2026-03-06 | 2026-06-01 | 2026-03-12 | 2026-03-12 | 2026-06-05 | 61
| A21410 | Issue Purchase Order to Vendor |  | 2026-03-13 |  |  | 5 | 2026-03-13 | 2026-06-08 | 2026-03-19 | 2026-03-19 | 2026-06-12 | 61
| Piping 3rd Lot GF (CS Material) |  |  | 2026-03-13 |  |  | 28 | 2026-03-13 | 2026-04-06 | 2026-04-22 | 2026-04-22 | 2026-05-13 | 15
| 102 | Issue RFQ to Bidders |  | 2026-03-13 |  |  | 7 | 2026-03-13 | 2026-04-06 | 2026-03-24 | 2026-03-24 | 2026-04-14 | 15
| A21480 | Bid Evaluation(Completion) |  | 2026-03-24 |  |  | 7 | 2026-03-24 | 2026-04-15 | 2026-04-02 | 2026-04-02 | 2026-04-23 | 15
| A21490 | Commercial Bid Evaluation(Completion) |  | 2026-04-02 |  |  | 7 | 2026-04-02 | 2026-04-24 | 2026-04-13 | 2026-04-13 | 2026-05-04 | 15
| A21470 | Issue Purchase Order to Vendor |  | 2026-04-13 |  |  | 7 | 2026-04-13 | 2026-05-05 | 2026-04-22 | 2026-04-22 | 2026-05-13 | 15
| Piping Supports (Swing Hangers) for GF |  |  | 2026-02-20 |  |  | 111 | 2026-02-20 | 2026-10-20 | 2026-07-24 | 2026-07-24 | 2027-05-14 | 210
| A21610 | Issue RFQ to Bidders |  | 2026-02-20 |  |  | 5 | 2026-02-20 | 2026-10-20 | 2026-02-26 | 2026-02-26 | 2026-10-27 | 172
| A45130 | Technical Bid Evaluation (TBE) for Spring Hangers_RCC |  | 2026-03-16 |  |  | 16 | 2026-03-16 | 2026-11-11 | 2026-04-06 | 2026-04-06 | 2026-12-03 | 172
| A45140 | Technical Bid Evaluation (TBE) for Spring Hangers_IFA |  | 2026-04-07 |  |  | 11 | 2026-04-07 | 2026-12-03 | 2026-04-22 | 2026-04-22 | 2026-12-18 | 172
| A45150 | Technical Bid Evaluation (TBE) for Spring Hangers_RCA |  | 2026-04-22 |  |  | 16 | 2026-04-22 | 2026-12-18 | 2026-05-13 | 2026-05-13 | 2027-01-11 | 172
| A45160 | Technical Bid Evaluation (TBE) for Spring Hangers_IFD/IFC |  | 2026-05-14 |  |  | 8 | 2026-05-14 | 2027-01-11 | 2026-05-25 | 2026-05-25 | 2027-01-20 | 172
| A21640 | Commercial Bid Evaluation(Completion) |  | 2026-05-25 |  |  | 30 | 2026-05-25 | 2027-03-16 | 2026-07-06 | 2026-07-06 | 2027-04-26 | 210
| A21620 | Issue Purchase Order to Vendor |  | 2026-07-06 |  |  | 14 | 2026-07-06 | 2027-04-27 | 2026-07-24 | 2026-07-24 | 2027-05-14 | 210
| HDPE Piping |  |  | 2026-02-20 |  |  | 59 | 01-Aug-25 A | 2026-04-09 | 19-Dec-25 A | 2026-02-20 | 2026-06-05 | 34
| HDPE Piping GF (Fire Water Lines) |  |  | 2026-02-20 |  |  | 59 | 01-Aug-25 A | 2026-04-09 | 19-Dec-25 A | 2026-02-20 | 2026-06-05 | 34
| A21530 | Issue RFQ to Bidders |  | 2026-02-20 |  |  | 10 | 01-Aug-25 A | 2026-04-09 | 08-Aug-25 A | 2026-02-20 | 2026-04-09
| A60280 | Technical Bid Evaluation (TBE) for Piping Bulk_RCC |  | 2026-02-20 |  |  | 16 | 13-Aug-25 A | 2026-04-09 | 15-Aug-25 A | 2026-02-20 | 2026-04-09
| A60290 | Technical Bid Evaluation (TBE) for Piping Bulk_IFA |  | 2026-02-20 |  |  | 8 | 16-Aug-25 A | 2026-04-09 | 18-Aug-25 A | 2026-02-20 | 2026-04-09
| A60300 | Technical Bid Evaluation (TBE) for Piping Bulk_RCA |  | 2026-02-20 |  |  | 8 | 18-Aug-25 A | 2026-06-05 | 19-Aug-25 A | 2026-02-20 | 2026-06-05
| A60310 | Technical Bid Evaluation (TBE) for Piping Bulk_IFD/IFC |  | 2026-02-20 |  |  | 8 | 19-Aug-25 A | 2026-06-05 | 21-Aug-25 A | 2026-02-20 | 2026-06-05
| A21560 | Commercial Bid Evaluation(Completion) |  | 2026-02-20 |  |  | 21 | 22-Aug-25 A | 2026-04-09 | 30-Aug-25 A | 2026-02-20 | 2026-04-09
| A21540 | Issue Purchase Order to Vendor |  | 2026-02-20 |  |  | 10 | 18-Dec-25 A | 2026-04-09 | 19-Dec-25 A | 2026-02-20 | 2026-04-09
| Piping SP Items (strainer, filters) |  |  | 2026-02-20 |  |  | 78 | 23-Jan-26 A | 2026-04-17 | 2026-04-09 | 2026-04-09 | 2026-07-24 | 76
| Specialized Items (Orifice Flanges) CS 300# 1" - 6" = 08 Nos |  |  | 2026-02-20 |  |  | 29 | 2026-02-20 | 2026-04-22 | 2026-04-01 | 2026-04-01 | 2026-07-20 | 79
| A18340 | Issue RFQ to Bidders |  | 2026-02-20 |  |  | 5 | 2026-02-20 | 2026-04-22 | 2026-02-26 | 2026-02-26 | 2026-04-29 | 44
| A45070 | Technical Bid Evaluation (TBE) for Piping Speciality Items_IFR |  | 2026-02-27 |  |  | 5 | 2026-02-27 | 2026-04-29 | 2026-03-05 | 2026-03-05 | 2026-05-05 | 44
| A45080 | Technical Bid Evaluation (TBE) for Piping Speciality Items_RCC |  | 2026-03-05 |  |  | 5 | 2026-03-05 | 2026-05-06 | 2026-03-11 | 2026-03-11 | 2026-05-12 | 44
| A45090 | Technical Bid Evaluation (TBE) for Piping Speciality Items_IFA |  | 2026-03-12 |  |  | 5 | 2026-03-12 | 2026-05-12 | 2026-03-18 | 2026-03-18 | 2026-05-18 | 44
| A45100 | Technical Bid Evaluation (TBE) for Piping Speciality Items_RCA |  | 2026-03-18 |  |  | 5 | 2026-03-18 | 2026-07-08 | 2026-03-24 | 2026-03-24 | 2026-07-14 | 80
| A18380 | Commercial Bid Evaluation(Completion) |  | 2026-03-18 |  |  | 5 | 2026-03-18 | 2026-05-19 | 2026-03-25 | 2026-03-25 | 2026-05-25 | 44
| A45110 | Technical Bid Evaluation (TBE) for Piping Speciality Items_IFD/IFC |  | 2026-03-25 |  |  | 5 | 2026-03-25 | 2026-07-14 | 2026-03-31 | 2026-03-31 | 2026-07-20 | 80
| A18360 | Issue Purchase Order to Vendor |  | 2026-03-25 |  |  | 5 | 2026-03-25 | 2026-05-26 | 2026-04-01 | 2026-04-01 | 2026-06-01 | 44
| Specialized Items (Strainer/Filter) CS & SS 150 # -300# 2" - 26" = 08 Nos |  |  | 2026-02-20 |  |  | 78 | 23-Jan-26 A | 2026-04-17 | 2026-04-09 | 2026-04-09 | 2026-07-24 | 76
| A15910 | Issue RFQ to Bidders |  | 2026-02-20 |  |  | 21 | 23-Jan-26 A | 2026-04-17 | 04-Feb-26 A | 2026-02-20 | 2026-04-17
| A56600 | Technical Bid Evaluation (TBE) for Piping Speciality Items_RCC |  | 2026-02-20 |  |  | 16 | 11-Feb-26 A | 2026-04-17 | 17-Feb-26 A | 2026-02-20 | 2026-04-17
| A18280 | Commercial Bid Evaluation(Completion) |  | 2026-02-20 |  |  | 30 | 17-Feb-26 A | 2026-04-17 | 2026-02-26 | 2026-02-26 | 2026-04-23 | 40
| A56610 | Technical Bid Evaluation (TBE) for Piping Speciality Items_IFA |  | 2026-02-20 |  |  | 11 | 2026-02-20 | 2026-06-08 | 2026-03-09 | 2026-03-09 | 2026-06-23 | 76
| A18260 | Issue Purchase Order to Vendor |  | 2026-02-27 |  |  | 21 | 2026-02-27 | 2026-04-24 | 2026-03-27 | 2026-03-27 | 2026-05-22 | 40
| A56620 | Technical Bid Evaluation (TBE) for Piping Speciality Items_RCA |  | 2026-03-09 |  |  | 16 | 2026-03-09 | 2026-06-23 | 2026-03-30 | 2026-03-30 | 2026-07-15 | 76
| A56630 | Technical Bid Evaluation (TBE) for Piping Speciality Items_IFD/IFC |  | 2026-03-31 |  |  | 8 | 2026-03-31 | 2026-07-15 | 2026-04-09 | 2026-04-09 | 2026-07-24 | 76
| Pressure / Temperature / Level Instruments, Flowmeters |  |  | 2026-02-20 |  |  | 235 | 18-Apr-25 A | 2026-04-30 | 2026-03-25 | 2026-03-25 | 2027-07-20 | 344
| Gauges (PG, TG, PDG) PG - 10bar & 40bar = 19 Nos, DP = 05 Nos, TG = 09 Nos |  |  | 2026-02-20 |  |  | 88 | 15-Aug-25 A | 2026-04-30 | 2026-03-25 | 2026-03-25 | 2026-06-02 | 50
| A17290 | RFQs to Bid Receipt |  | 2026-02-20 |  |  | 2 | 15-Aug-25 A | 2026-04-30 | 27-Aug-25 A | 2026-02-20 | 2026-04-30
| A16340 | Technical Bid Evaluation for Temperature Gauges / Pressure Gauges_RCC |  | 2026-02-20 |  |  | 6 | 26-Dec-25 A | 2026-04-30 | 23-Jan-26 A | 2026-02-20 | 2026-04-30
| A16350 | Technical Bid Evaluation for Temperature Gauges / Pressure Gauges_IFA |  | 2026-02-20 |  |  | 6 | 2026-02-20 | 2026-04-30 | 2026-02-27 | 2026-02-27 | 2026-05-08 | 50
| A19250 | Commercial Bid Evaluation(Completion) |  | 2026-02-27 |  |  | 6 | 2026-02-27 | 2026-05-08 | 2026-03-09 | 2026-03-09 | 2026-05-15 | 50
| A16360 | Technical Bid Evaluation for Temperature Gauges / Pressure Gauges_RCA |  | 2026-02-27 |  |  | 6 | 2026-02-27 | 2026-05-18 | 2026-03-09 | 2026-03-09 | 2026-05-26 | 56
| A16370 | Technical Bid Evaluation for Temperature Gauges / Pressure Gauges_IFD/IFC |  | 2026-03-09 |  |  | 6 | 2026-03-09 | 2026-05-26 | 2026-03-16 | 2026-03-16 | 2026-06-02 | 56
| A19230 | Issue Purchase Order to Vendor Guages (PG, TG, PDG) |  | 2026-03-09 |  |  | 12 | 2026-03-09 | 2026-05-18 | 2026-03-25 | 2026-03-25 | 2026-06-02 | 50
| Flow Elements Venturi |  |  | 2026-02-20 |  |  | 139 | 01-Jun-25 A | 2026-04-30 | 11-Dec-25 A | 2026-02-20 | 2026-04-30 | 49
| A57610 | Issue RFQ to Bidders |  | 2026-02-20 |  |  | 20 | 01-Jun-25 A | 2026-04-30 | 22-Jun-25 A | 2026-02-20 | 2026-04-30
| A16240 | Technical Bid Evaluation for Flow Element (Venturi Tube)_RCC |  | 2026-02-20 |  |  | 8 | 11-Sep-25 A | 2026-04-30 | 15-Sep-25 A | 2026-02-20 | 2026-04-30
| A16250 | Technical Bid Evaluation for Flow Element (Venturi Tube)_IFA |  | 2026-02-20 |  |  | 8 | 16-Sep-25 A | 2026-04-30 | 25-Sep-25 A | 2026-02-20 | 2026-04-30
| A16260 | Technical Bid Evaluation for Flow Element (Venturi Tube)_RCA |  | 2026-02-20 |  |  | 16 | 01-Oct-25 A | 2026-04-30 | 15-Oct-25 A | 2026-02-20 | 2026-04-30
| A48170 | Technical Bid Evaluation for Flow Element (Venturi Tube)_IFD/IFC |  | 2026-02-20 |  |  | 8 | 16-Oct-25 A | 2026-04-30 | 31-Oct-25 A | 2026-02-20 | 2026-04-30
| A57630 | Commercial Bid Evaluation |  | 2026-02-20 |  |  | 10 | 01-Nov-25 A | 2026-04-30 | 17-Nov-25 A | 2026-02-20 | 2026-04-30
| A57640 | Issue Purchase Order to Vendor |  | 2026-02-20 |  |  | 10 | 27-Nov-25 A | 2026-04-30 | 11-Dec-25 A | 2026-02-20 | 2026-04-30
| Flow Elements Orifice |  |  | 2026-02-20 |  |  | 235 | 01-May-25 A | 2026-06-04 | 2026-03-25 | 2026-03-25 | 2026-07-07 | 74
| A57920 | Issue RFQ to Bidders |  | 2026-02-20 |  |  | 20 | 01-May-25 A | 2026-06-04 | 15-May-25 A | 2026-02-20 | 2026-06-04
| A16190 | Technical Bid Evaluation for Flow Element (Orifice Plate)_RCC |  | 2026-02-20 |  |  | 8 | 19-Sep-25 A | 2026-06-04 | 30-Sep-25 A | 2026-02-20 | 2026-06-04
| A16200 | Technical Bid Evaluation for Flow Element (Orifice Plate)_IFA |  | 2026-02-20 |  |  | 8 | 27-Nov-25 A | 2026-06-04 | 02-Dec-25 A | 2026-02-20 | 2026-06-04
| A57950 | Commercial Bid Evaluation |  | 2026-02-20 |  |  | 10 | 01-Dec-25 A | 2026-07-03 | 12-Dec-25 A | 2026-02-20 | 2026-07-03
| A57930 | Issue Purchase Order to Vendor |  | 2026-02-20 |  |  | 10 | 16-Dec-25 A | 2026-07-03 | 18-Dec-25 A | 2026-02-20 | 2026-07-03
| A48160 | Technical Bid Evaluation for Flow Element (Orifice Plate)_RCA |  | 2026-02-20 |  |  | 16 | 2026-02-20 | 2026-06-04 | 2026-03-13 | 2026-03-13 | 2026-06-26 | 74
| A16220 | Technical Bid Evaluation for Flow Element (Orifice Plate)_IFD/IFC |  | 2026-03-13 |  |  | 8 | 2026-03-13 | 2026-06-26 | 2026-03-25 | 2026-03-25 | 2026-07-07 | 74
| PT, TT & DPT [PT 50 Nos, TT 33 Nos, DPT 20 Nos] |  |  | 2026-02-20 |  |  | 186 | 18-Apr-25 A | 2027-01-06 | 2026-03-23 | 2026-03-23 | 2027-07-20 | 347
| A21030 | Issue RFQ to Bidders |  | 2026-02-20 |  |  | 21 | 18-Apr-25 A | 2027-01-06 | 09-May-25 A | 2026-02-20 | 2027-01-06
| A16140 | Technical Bid Evaluation for Electronic Transmitters_RCC |  | 2026-02-20 |  |  | 3 | 24-Dec-25 A | 2027-01-06 | 17-Jan-26 A | 2026-02-20 | 2027-01-06
| A48150 | Technical Bid Evaluation for Electronic Transmitters_IFA |  | 2026-02-20 |  |  | 3 | 2026-02-20 | 2027-01-06 | 2026-02-25 | 2026-02-25 | 2027-01-12 | 229
| A16160 | Technical Bid Evaluation for Electronic Transmitters_RCA |  | 2026-02-25 |  |  | 3 | 2026-02-25 | 2027-01-12 | 2026-03-02 | 2026-03-02 | 2027-01-15 | 229
| A16170 | Technical Bid Evaluation for Electronic Transmitters_IFD/IFC |  | 2026-03-02 |  |  | 3 | 2026-03-02 | 2027-01-15 | 2026-03-06 | 2026-03-06 | 2027-01-20 | 229
| A21060 | Commercial Bid Evaluation(Completion) |  | 2026-03-06 |  |  | 3 | 2026-03-06 | 2027-07-05 | 2026-03-11 | 2026-03-11 | 2027-07-08 | 347
| A21040 | Issue Purchase Order to Vendor |  | 2026-03-11 |  |  | 8 | 2026-03-11 | 2027-07-09 | 2026-03-23 | 2026-03-23 | 2027-07-20 | 347
| Instrument Bulk Material |  |  | 2026-02-20 |  |  | 230 | 01-Feb-25 A | 2026-03-05 | 2026-03-12 | 2026-03-12 | 2027-01-20 | 224
| TA_Instrument Bulk Materia l(Single & Multicore = Approx. 78,130 Mtr, FO Cables JB & Cable Trays)) |  |  | 2026-02-20 |  |  | 53 | 01-Feb-25 A | 2026-03-27 | 19-Mar-25 A | 2026-02-20 | 2026-03-27
| A22030 | Issue RFQs to Bidders |  | 2026-02-20 |  |  | 21 | 01-Feb-25 A | 2026-03-27 | 11-Feb-25 A | 2026-02-20 | 2026-03-27
| A22050 | TBE for Instrument Bulk Material (TA) |  | 2026-02-20 |  |  | 15 | 12-Feb-25 A | 2026-03-27 | 21-Feb-25 A | 2026-02-20 | 2026-03-27
| A22040 | Vendor Quote Received |  | 2026-02-20 |  |  | 10 | 24-Feb-25 A | 2026-03-27 | 04-Mar-25 A | 2026-02-20 | 2026-03-27
| A22070 | Issue Purchase Order to Vendor |  | 2026-02-20 |  |  | 7 | 05-Mar-25 A | 2026-03-27 | 19-Mar-25 A | 2026-02-20 | 2026-03-27
| Analyzer |  |  | 2026-02-20 |  |  | 116 | 01-May-25 A | 2026-11-28 | 08-Jun-25 A | 2026-02-20 | 2026-11-28
| A48190 | Technical Bid Evaluation for Analyzers_RCC |  | 2026-02-20 |  |  | 19 | 01-May-25 A | 2026-11-28 | 23-May-25 A | 2026-02-20 | 2026-11-28
| A16400 | Technical Bid Evaluation for Analyzers_IFA |  | 2026-02-20 |  |  | 19 | 01-May-25 A | 2026-11-28 | 23-May-25 A | 2026-02-20 | 2026-11-28
| A16410 | Technical Bid Evaluation for Analyzers_RCA |  | 2026-02-20 |  |  | 19 | 01-May-25 A | 2026-11-28 | 23-May-25 A | 2026-02-20 | 2026-11-28
| A16420 | Technical Bid Evaluation for Analyzers_IFD/IFC |  | 2026-02-20 |  |  | 19 | 01-May-25 A | 2026-11-28 | 23-May-25 A | 2026-02-20 | 2026-11-28
| A57570 | Issue RFQ to Bidders |  | 2026-02-20 |  |  | 20 | 01-May-25 A | 2026-11-28 | 25-May-25 A | 2026-02-20 | 2026-11-28
| A57590 | Commercial Bid Evaluation |  | 2026-02-20 |  |  | 15 | 25-May-25 A | 2026-11-28 | 01-Jun-25 A | 2026-02-20 | 2026-11-28
| A57600 | Issue Purchase Order to Vendor |  | 2026-02-20 |  |  | 14 | 02-Jun-25 A | 2026-11-28 | 08-Jun-25 A | 2026-02-20 | 2026-11-28
| Cable Tray and Instrument Junction Box (Perforated Cable tray Heavy duty = 5982 Mtrs, JBs = 73 Nos) |  |  | 2026-02-20 |  |  | 168 | 20-Jul-25 A | 2026-03-05 | 2026-03-12 | 2026-03-12 | 2027-01-20 | 224
| A17230 | Issue RFQ to Bidders |  | 2026-02-20 |  |  | 21 | 20-Jul-25 A | 2026-03-05 | 25-Oct-25 A | 2026-02-20 | 2026-03-05
| A16840 | Technical Bid Evaluation for Junction Boxes_RCC |  | 2026-02-20 |  |  | 5 | 19-Dec-25 A | 2026-03-05 | 10-Jan-26 A | 2026-02-20 | 2026-03-05
| A20070 | Commercial Bid Evaluation(Completion) |  | 2026-02-26 |  |  | 5 | 05-Jan-26 A | 2026-03-12 | 14-Jan-26 A | 2026-02-26 | 2026-03-12
| A20050 | Issue Purchase Order to Vendor |  | 2026-02-26 |  |  | 5 | 15-Jan-26 A | 2026-03-12 | 21-Jan-26 A | 2026-02-26 | 2026-03-12
| A16850 | Technical Bid Evaluation for Junction Boxes_IFA |  | 2026-02-20 |  |  | 5 | 2026-02-20 | 2026-03-05 | 2026-02-26 | 2026-02-26 | 2026-03-11 | 9
| A16860 | Technical Bid Evaluation for Junction Boxes_RCA |  | 2026-02-27 |  |  | 5 | 2026-02-27 | 2027-01-07 | 2026-03-05 | 2026-03-05 | 2027-01-13 | 224
| A16870 | Technical Bid Evaluation for Junction Boxes_IFD/IFC |  | 2026-03-06 |  |  | 5 | 2026-03-06 | 2027-01-14 | 2026-03-12 | 2026-03-12 | 2027-01-20 | 224
| Magnetic Level Gauge ( 09 Nos) |  |  | 2026-02-20 |  |  | 160 | 18-Jul-25 A | 2026-03-25 | 2026-02-26 | 2026-02-26 | 2026-03-31 | 23
| A21270 | Issue RFQ to Bidders |  | 2026-02-20 |  |  | 3 | 18-Jul-25 A | 2026-03-25 | 06-Aug-25 A | 2026-02-20 | 2026-03-25
| A16440 | Technical Bid Evaluation for Level Gauges (Magnetic Type)_RCC |  | 2026-02-20 |  |  | 3 | 21-Aug-25 A | 2026-03-25 | 29-Aug-25 A | 2026-02-20 | 2026-03-25
| A48200 | Technical Bid Evaluation for Level Gauges (Magnetic Type)_IFA |  | 2026-02-20 |  |  | 3 | 30-Aug-25 A | 2026-03-25 | 15-Sep-25 A | 2026-02-20 | 2026-03-25
| A16460 | Technical Bid Evaluation for Level Gauges (Magnetic Type)_RCA |  | 2026-02-20 |  |  | 3 | 16-Sep-25 A | 2026-03-25 | 30-Sep-25 A | 2026-02-20 | 2026-03-25
| A16470 | Technical Bid Evaluation for Level Gauges (Magnetic Type)_IFD/IFC |  | 2026-02-20 |  |  | 3 | 01-Oct-25 A | 2026-03-25 | 30-Oct-25 A | 2026-02-20 | 2026-03-25
| A21300 | Commercial Bid Evaluation(Completion) |  | 2026-02-20 |  |  | 3 | 10-Nov-25 A | 2026-03-25 | 21-Nov-25 A | 2026-02-20 | 2026-03-25
| A21280 | Issue Purchase Order to Vendor |  | 2026-02-20 |  |  | 5 | 2026-02-20 | 2026-03-25 | 2026-02-26 | 2026-02-26 | 2026-03-31 | 23
| Fibre Optic Cable (Armoured, Telecom/IT/MAS) |  |  | 2026-02-20 |  |  | 56 | 01-Jun-25 A | 2026-03-19 | 18-Aug-25 A | 2026-02-20 | 2026-03-19 | 125
| A17170 | RFQs to Bid receipt |  | 2026-02-20 |  |  | 21 | 01-Jun-25 A | 2026-03-19 | 21-Jun-25 A | 2026-02-20 | 2026-03-19
| A57550 | Technical Bid Evaluation for Instrument Cables_IFD/IFC |  | 2026-02-20 |  |  | 6 | 30-Jul-25 A | 2026-03-19 | 31-Jul-25 A | 2026-02-20 | 2026-03-19
| A57520 | Technical Bid Evaluation for Instrument Cables_RCC |  | 2026-02-20 |  |  | 6 | 30-Jul-25 A | 2026-03-19 | 31-Jul-25 A | 2026-02-20 | 2026-03-19
| A57530 | Technical Bid Evaluation for Instrument Cables_IFA |  | 2026-02-20 |  |  | 6 | 30-Jul-25 A | 2026-03-19 | 31-Jul-25 A | 2026-02-20 | 2026-03-19
| A57540 | Technical Bid Evaluation for Instrument Cables_RCA |  | 2026-02-20 |  |  | 6 | 30-Jul-25 A | 2026-03-19 | 31-Jul-25 A | 2026-02-20 | 2026-03-19
| A18680 | Commercial Bid Evaluation(Completion) |  | 2026-02-20 |  |  | 6 | 01-Aug-25 A | 2026-03-19 | 08-Aug-25 A | 2026-02-20 | 2026-03-19
| A18660 | Issue Purchase Order to Vendor |  | 2026-02-20 |  |  | 6 | 09-Aug-25 A | 2026-03-19 | 18-Aug-25 A | 2026-02-20 | 2026-03-19
| Earthing & Power Cables |  |  | 2026-02-20 |  |  | 139 | 18-Jul-25 A | 2026-05-22 | 24-Oct-25 A | 2026-02-20 | 2026-07-13 | 65
| Power Cables ( 11kV & 33kV) |  |  | 2026-02-20 |  |  | 129 | 01-Aug-25 A | 2026-07-13 | 03-Sep-25 A | 2026-02-20 | 2026-07-13 | 112
| A58690 | Issue RFQ to Bidders |  | 2026-02-20 |  |  | 21 | 01-Aug-25 A | 2026-07-13 | 20-Aug-25 A | 2026-02-20 | 2026-07-13
| A58700 | Bid Evaluation(Completion) |  | 2026-02-20 |  |  | 30 | 04-Aug-25 A | 2026-07-13 | 25-Aug-25 A | 2026-02-20 | 2026-07-13
| A58710 | Commercial Bid Evaluation(Completion) |  | 2026-02-20 |  |  | 25 | 06-Aug-25 A | 2026-07-13 | 27-Aug-25 A | 2026-02-20 | 2026-07-13
| A58720 | Issue Purchase Order to Vendor |  | 2026-02-20 |  |  | 14 | 25-Aug-25 A | 2026-07-13 | 03-Sep-25 A | 2026-02-20 | 2026-07-13
| Earthing and Power Cables |  |  | 2026-02-20 |  |  | 100 | 18-Jul-25 A | 2026-05-22 | 24-Oct-25 A | 2026-02-20 | 2026-06-10 | 65
| A16450 | Issue RFQ to Bidders |  | 2026-02-20 |  |  | 21 | 18-Jul-25 A | 2026-05-22 | 20-Aug-25 A | 2026-02-20 | 2026-05-22
| A13230 | Technical Bid Evaluation For Power, Control And Earthing Cables_IFR |  | 2026-02-20 |  |  | 3 | 21-Aug-25 A | 2026-05-22 | 29-Aug-25 A | 2026-02-20 | 2026-05-22
| A13240 | Technical Bid Evaluation For Power, Control And Earthing Cables_RCC |  | 2026-02-20 |  |  | 3 | 30-Aug-25 A | 2026-05-22 | 10-Sep-25 A | 2026-02-20 | 2026-05-22
| A13250 | Technical Bid Evaluation For Power, Control And Earthing Cables_IFA |  | 2026-02-20 |  |  | 3 | 11-Sep-25 A | 2026-06-10 | 17-Sep-25 A | 2026-02-20 | 2026-06-10
| A13260 | Technical Bid Evaluation For Power, Control And Earthing Cables_RCA |  | 2026-02-20 |  |  | 3 | 19-Sep-25 A | 2026-06-10 | 30-Sep-25 A | 2026-02-20 | 2026-06-10
| A13270 | Technical Bid Evaluation For Power, Control And Earthing Cables_IFD/IFC |  | 2026-02-20 |  |  | 3 | 01-Oct-25 A | 2026-06-10 | 07-Oct-25 A | 2026-02-20 | 2026-06-10
| A20610 | Commercial Bid Evaluation(Completion) |  | 2026-02-20 |  |  | 3 | 07-Oct-25 A | 2026-05-22 | 14-Oct-25 A | 2026-02-20 | 2026-05-22
| A20590 | Issue Purchase Order to Vendor |  | 2026-02-20 |  |  | 3 | 15-Oct-25 A | 2026-05-22 | 24-Oct-25 A | 2026-02-20 | 2026-05-22
| Electrical Bulk |  |  | 2026-02-20 |  |  | 196 | 15-Jan-25 A | 2026-04-14 | 2026-05-29 | 2026-05-29 | 2026-07-27 | 41
| TA_Electrical Bulk Material (Earthing ,FO, Power Cables) |  |  | 2026-02-20 |  |  | 91 | 15-Jan-25 A | 2026-04-30 | 09-Mar-25 A | 2026-02-20 | 2026-04-30
| A17890 | Issue RFQ to Bidders |  | 2026-02-20 |  |  | 20 | 15-Jan-25 A | 2026-04-30 | 08-Feb-25 A | 2026-02-20 | 2026-04-30
| A17900 | Vendor Quote Received |  | 2026-02-20 |  |  | 30 | 10-Feb-25 A | 2026-04-30 | 19-Feb-25 A | 2026-02-20 | 2026-04-30
| A17920 | TBE |  | 2026-02-20 |  |  | 30 | 20-Feb-25 A | 2026-04-30 | 28-Feb-25 A | 2026-02-20 | 2026-04-30
| A17910 | Negotiations and PO Placement (33 KVA) |  | 2026-02-20 |  |  | 15 | 03-Mar-25 A | 2026-04-30 | 09-Mar-25 A | 2026-02-20 | 2026-04-30
| Cable Trays, JBs, Conduit Pipe, Cable Lugs, etc |  |  | 2026-02-20 |  |  | 59 | 2026-02-20 | 2026-04-14 | 2026-05-13 | 2026-05-13 | 2026-07-03 | 37
| A9450 | Issue RFQ to Bidders |  | 2026-02-20 |  |  | 15 | 2026-02-20 | 2026-04-14 | 2026-03-12 | 2026-03-12 | 2026-05-04 | 37
| A20660 | Bid Evaluation(Completion) |  | 2026-03-13 |  |  | 15 | 2026-03-13 | 2026-05-05 | 2026-04-02 | 2026-04-02 | 2026-05-25 | 37
| A20670 | Commercial Bid Evaluation(Completion) |  | 2026-04-03 |  |  | 15 | 2026-04-03 | 2026-05-26 | 2026-04-23 | 2026-04-23 | 2026-06-15 | 37
| A20650 | Issue Purchase Order to Vendor |  | 2026-04-24 |  |  | 14 | 2026-04-24 | 2026-06-16 | 2026-05-13 | 2026-05-13 | 2026-07-03 | 37
| LCS & Snap Switches |  |  | 2026-02-20 |  |  | 71 | 2026-02-20 | 2026-04-20 | 2026-05-29 | 2026-05-29 | 2026-07-27 | 41
| A21690 | Issue RFQ to Bidders |  | 2026-02-20 |  |  | 21 | 2026-02-20 | 2026-04-20 | 2026-03-20 | 2026-03-20 | 2026-05-18 | 41
| A21710 | Bid Evaluation(Completion) |  | 2026-03-23 |  |  | 21 | 2026-03-23 | 2026-05-19 | 2026-04-20 | 2026-04-20 | 2026-06-16 | 41
| A21720 | Commercial Bid Evaluation(Completion) |  | 2026-04-21 |  |  | 15 | 2026-04-21 | 2026-06-17 | 2026-05-11 | 2026-05-11 | 2026-07-07 | 41
| A21700 | Issue Purchase Order to Vendor |  | 2026-05-12 |  |  | 14 | 2026-05-12 | 2026-07-08 | 2026-05-29 | 2026-05-29 | 2026-07-27 | 41
| Main Automation Equipment |  |  | 2026-02-20 |  |  | 245 | 01-Feb-25 A | 2026-03-18 | 2026-04-02 | 2026-04-02 | 2026-07-15 | 73
| On Off Valve / Control Valves |  |  | 2026-02-20 |  |  | 181 | 10-Apr-25 A | 2026-03-25 | 20-Oct-25 A | 2026-02-20 | 2026-05-12 | 212
| ESD Valve |  |  | 2026-02-20 |  |  | 181 | 10-Apr-25 A | 2026-03-25 | 16-May-25 A | 2026-02-20 | 2026-04-18
| A59730 | Issue RFQ to Bidders |  | 2026-02-20 |  |  | 21 | 10-Apr-25 A | 2026-03-25 | 02-May-25 A | 2026-02-20 | 2026-03-25
| A59760 | Technical Bid Evaluation for ESD_IFR |  | 2026-02-20 |  |  | 11 | 02-May-25 A | 2026-03-25 | 05-May-25 A | 2026-02-20 | 2026-03-25
| A59770 | Technical Bid Evaluation for ESD_RCC |  | 2026-02-20 |  |  | 16 | 05-May-25 A | 2026-03-25 | 07-May-25 A | 2026-02-20 | 2026-03-25
| A59780 | Technical Bid Evaluation for ESD_IFA |  | 2026-02-20 |  |  | 11 | 08-May-25 A | 2026-03-25 | 09-May-25 A | 2026-02-20 | 2026-03-25
| A59790 | Technical Bid Evaluation for ESD_RCA |  | 2026-02-20 |  |  | 16 | 10-May-25 A | 2026-04-18 | 12-May-25 A | 2026-02-20 | 2026-04-18
| A59800 | Technical Bid Evaluation for ESD_IFD/IFC |  | 2026-02-20 |  |  | 8 | 13-May-25 A | 2026-04-18 | 14-May-25 A | 2026-02-20 | 2026-04-18
| A59750 | Commercial Bid Evaluation(Completion) |  | 2026-02-20 |  |  | 21 | 14-May-25 A | 2026-03-25 | 15-May-25 A | 2026-02-20 | 2026-03-25
| A59740 | Issue Purchase Order to Vendor for ESD |  | 2026-02-20 |  |  | 21 | 15-May-25 A | 2026-03-25 | 16-May-25 A | 2026-02-20 | 2026-03-25
| Control Valves (1" - 24" Rating 150, 300 & 2500 = 32 Nos) + SDV |  |  | 2026-02-20 |  |  | 171 | 21-Apr-25 A | 2026-03-25 | 20-Oct-25 A | 2026-02-20 | 2026-05-12 | 247
| A16750 | Issue RFQ to Bidders |  | 2026-02-20 |  |  | 21 | 21-Apr-25 A | 2026-03-25 | 15-May-25 A | 2026-02-20 | 2026-03-25
| A22100 | Commercial Bid Evaluation(Completion) |  | 2026-02-20 |  |  | 21 | 17-Sep-25 A | 2026-03-25 | 18-Sep-25 A | 2026-02-20 | 2026-03-25
| A16490 | Technical Bid Evaluation for Control Valves_RCC |  | 2026-02-20 |  |  | 8 | 23-Aug-25 A | 2026-03-25 | 18-Sep-25 A | 2026-02-20 | 2026-03-25
| A16500 | Technical Bid Evaluation for Control Valves_IFA |  | 2026-02-20 |  |  | 8 | 23-Aug-25 A | 2026-03-25 | 18-Sep-25 A | 2026-02-20 | 2026-03-25
| A48210 | Technical Bid Evaluation for Control Valves_RCA |  | 2026-02-20 |  |  | 8 | 23-Aug-25 A | 2026-03-25 | 18-Sep-25 A | 2026-02-20 | 2026-03-25
| A16520 | Technical Bid Evaluation for Control Valves_IFD/IFC |  | 2026-02-20 |  |  | 8 | 23-Aug-25 A | 2026-03-25 | 18-Sep-25 A | 2026-02-20 | 2026-03-25
| A22110 | Issue Purchase Order to Vendor for Control Valves |  | 2026-02-20 |  |  | 21 | 01-Oct-25 A | 2026-05-12 | 20-Oct-25 A | 2026-02-20 | 2026-05-12
| MOVs |  |  | 2026-02-20 |  |  | 121 | 21-Apr-25 A | 2026-05-11 | 10-Sep-25 A | 2026-02-20 | 2026-05-11 | 55
| MOVs [Ball Type 24" 150# = 01 No] |  |  | 2026-02-20 |  |  | 121 | 21-Apr-25 A | 2026-05-11 | 10-Sep-25 A | 2026-02-20 | 2026-05-11 | 55
| A17050 | RFQs to Bid Receipt |  | 2026-02-20 |  |  | 21 | 21-Apr-25 A | 2026-05-11 | 15-May-25 A | 2026-02-20 | 2026-05-11
| A16650 | Technical Bid Evaluation for Motor Operated Valves_IFA |  | 2026-02-20 |  |  | 8 | 19-Aug-25 A | 2026-05-11 | 29-Aug-25 A | 2026-02-20 | 2026-05-11
| A18620 | Commercial Bid Evaluation(Completion) |  | 2026-02-20 |  |  | 5 | 19-Aug-25 A | 2026-05-11 | 01-Sep-25 A | 2026-02-20 | 2026-05-11
| A18600 | Issue Purchase Order to Vendor for MOVs |  | 2026-02-20 |  |  | 14 | 26-Aug-25 A | 2026-05-11 | 02-Sep-25 A | 2026-02-20 | 2026-05-11
| A16640 | Technical Bid Evaluation for Motor Operated Valves_RCC |  | 2026-02-20 |  |  | 6 | 22-Aug-25 A | 2026-05-11 | 02-Sep-25 A | 2026-02-20 | 2026-05-11
| A16660 | Technical Bid Evaluation for Motor Operated Valves_RCA |  | 2026-02-20 |  |  | 6 | 30-Aug-25 A | 2026-05-11 | 06-Sep-25 A | 2026-02-20 | 2026-05-11
| A16670 | Technical Bid Evaluation for Motor Operated Valves_IFD/IFC |  | 2026-02-20 |  |  | 5 | 07-Sep-25 A | 2026-05-11 | 10-Sep-25 A | 2026-02-20 | 2026-05-11
| Machine Condition Monitoring System (MCMS) |  |  | 2026-02-20 |  |  | 117 | 01-Feb-25 A | 2026-03-27 | 01-Jun-25 A | 2026-02-20 | 2026-07-15 | 101
| TA_MCMS System Modification - Bently Nevada |  |  | 2026-02-20 |  |  | 48 | 01-Feb-25 A | 2026-03-27 | 15-Mar-25 A | 2026-02-20 | 2026-03-27
| A37160 | Issue RFQ to Bidders |  | 2026-02-20 |  |  | 20 | 01-Feb-25 A | 2026-03-27 | 22-Feb-25 A | 2026-02-20 | 2026-03-27
| A57450 | TBE for ICT System Modification_Free Issue Material |  | 2026-02-20 |  |  | 23 | 23-Feb-25 A | 2026-03-27 | 09-Mar-25 A | 2026-02-20 | 2026-03-27
| A37190 | Issue Purchase Order to Vendor |  | 2026-02-20 |  |  | 5 | 10-Mar-25 A | 2026-03-27 | 15-Mar-25 A | 2026-02-20 | 2026-03-27
| Machine Condition Monitoring System |  |  | 2026-02-20 |  |  | 99 | 01-Apr-25 A | 2026-07-15 | 01-Jun-25 A | 2026-02-20 | 2026-07-15 | 101
| A17110 | Issue RFQ to Bidders |  | 2026-02-20 |  |  | 20 | 01-Apr-25 A | 2026-07-15 | 20-Apr-25 A | 2026-02-20 | 2026-07-15
| A19930 | Issue Purchase Order to Vendor for MCMS |  | 2026-02-20 |  |  | 21 | 08-May-25 A | 2026-07-15 | 15-May-25 A | 2026-02-20 | 2026-07-15
| A58590 | Technical Bid Evaluation for MCMS System_IFR |  | 2026-02-20 |  |  | 11 | 01-May-25 A | 2026-07-15 | 15-May-25 A | 2026-02-20 | 2026-07-15
| A58600 | Technical Bid Evaluation for MCMS System_RCC |  | 2026-02-20 |  |  | 16 | 16-May-25 A | 2026-07-15 | 19-May-25 A | 2026-02-20 | 2026-07-15
| A58610 | Technical Bid Evaluation for MCMSSystem_IFA |  | 2026-02-20 |  |  | 11 | 16-May-25 A | 2026-07-15 | 19-May-25 A | 2026-02-20 | 2026-07-15
| A58620 | Technical Bid Evaluation for MCMS System_RCA |  | 2026-02-20 |  |  | 16 | 16-May-25 A | 2026-07-15 | 19-May-25 A | 2026-02-20 | 2026-07-15
| A58630 | Technical Bid Evaluation for MCMS System_IFD/IFC |  | 2026-02-20 |  |  | 8 | 20-May-25 A | 2026-07-15 | 25-May-25 A | 2026-02-20 | 2026-07-15
| A19950 | Commercial Bid Evaluation(Completion) |  | 2026-02-20 |  |  | 21 | 26-May-25 A | 2026-07-15 | 01-Jun-25 A | 2026-02-20 | 2026-07-15
| IPCS Modification (ABB) |  |  | 2026-02-20 |  |  | 94 | 01-Feb-25 A | 2026-03-27 | 25-Jul-25 A | 2026-02-20 | 2026-05-04 | 53
| TA_Integrated Protection and Control System - ABB/Hitachi |  |  | 2026-02-20 |  |  | 37 | 01-Feb-25 A | 2026-03-27 | 18-Mar-25 A | 2026-02-20 | 2026-03-27
| A20950 | Issue RFQ to Bidders |  | 2026-02-20 |  |  | 20 | 01-Feb-25 A | 2026-03-27 | 25-Feb-25 A | 2026-02-20 | 2026-03-27
| A57390 | TBE for Electrical System Modification_ Free Issue Material |  | 2026-02-20 |  |  | 8 | 26-Feb-25 A | 2026-03-27 | 09-Mar-25 A | 2026-02-20 | 2026-03-27
| A20960 | Issue Purchase Order to Vendor |  | 2026-02-20 |  |  | 7 | 10-Mar-25 A | 2026-03-27 | 18-Mar-25 A | 2026-02-20 | 2026-03-27
| Integrated Protection and Control System |  |  | 2026-02-20 |  |  | 82 | 10-Apr-25 A | 2026-05-04 | 25-Jul-25 A | 2026-02-20 | 2026-05-04
| A23820 | Issue RFQ to Bidders |  | 2026-02-20 |  |  | 20 | 10-Apr-25 A | 2026-05-04 | 01-May-25 A | 2026-02-20 | 2026-05-04
| A58540 | Technical Bid Evaluation for IPCS_IFR |  | 2026-02-20 |  |  | 8 | 02-May-25 A | 2026-05-04 | 10-May-25 A | 2026-02-20 | 2026-05-04
| A58550 | Technical Bid Evaluation for IPCS_RCC |  | 2026-02-20 |  |  | 16 | 11-May-25 A | 2026-05-04 | 20-May-25 A | 2026-02-20 | 2026-05-04
| A58560 | Technical Bid Evaluation for IPCS_IFA |  | 2026-02-20 |  |  | 11 | 21-May-25 A | 2026-05-04 | 26-May-25 A | 2026-02-20 | 2026-05-04
| A58570 | Technical Bid Evaluation for IPCS_RCA |  | 2026-02-20 |  |  | 16 | 27-May-25 A | 2026-05-04 | 31-May-25 A | 2026-02-20 | 2026-05-04
| A58580 | Technical Bid Evaluation for IPCS_IFD/IFC |  | 2026-02-20 |  |  | 8 | 01-Jun-25 A | 2026-05-04 | 04-Jun-25 A | 2026-02-20 | 2026-05-04
| A23850 | Commercial Bid Evaluation(Completion) |  | 2026-02-20 |  |  | 10 | 07-Jul-25 A | 2026-05-04 | 16-Jul-25 A | 2026-02-20 | 2026-05-04
| A23830 | Issue Purchase Order to Vendor for IPCS |  | 2026-02-20 |  |  | 5 | 17-Jul-25 A | 2026-05-04 | 25-Jul-25 A | 2026-02-20 | 2026-05-04
| OTS |  |  | 2026-02-20 |  |  | 98 | 01-Feb-25 A | 2026-03-20 | 20-Aug-25 A | 2026-02-20 | 2026-03-27 | 20
| TA_SCMS Modification - Siemens |  |  | 2026-02-20 |  |  | 27 | 01-Feb-25 A | 2026-03-27 | 03-Mar-25 A | 2026-02-20 | 2026-03-27
| A24190 | Issue RFQ to Bidders |  | 2026-02-20 |  |  | 10 | 01-Feb-25 A | 2026-03-27 | 10-Feb-25 A | 2026-02-20 | 2026-03-27
| A57360 | TBE for Electrical System Modification_ Free Issue Material |  | 2026-02-20 |  |  | 11 | 11-Feb-25 A | 2026-03-27 | 24-Feb-25 A | 2026-02-20 | 2026-03-27
| A24200 | Issue Purchase Order to Vendor |  | 2026-02-20 |  |  | 7 | 25-Feb-25 A | 2026-03-27 | 03-Mar-25 A | 2026-02-20 | 2026-03-27
| SCMS |  |  | 2026-02-20 |  |  | 98 | 19-Mar-25 A | 2026-03-20 | 20-Aug-25 A | 2026-02-20 | 2026-03-20
| A60190 | Issue RFQ to Bidders |  | 2026-02-20 |  |  | 21 | 19-Mar-25 A | 2026-03-20 | 20-May-25 A | 2026-02-20 | 2026-03-20
| A60220 | Technical Bid Evaluation for SCMS_IFR |  | 2026-02-20 |  |  | 11 | 21-May-25 A | 2026-03-20 | 01-Jun-25 A | 2026-02-20 | 2026-03-20
| A60230 | Technical Bid Evaluation for SCMS_RCC |  | 2026-02-20 |  |  | 6 | 02-Jun-25 A | 2026-03-20 | 12-Jun-25 A | 2026-02-20 | 2026-03-20
| A60240 | Technical Bid Evaluation for SCMS_IFA |  | 2026-02-20 |  |  | 6 | 13-Jun-25 A | 2026-03-20 | 19-Jun-25 A | 2026-02-20 | 2026-03-20
| A60250 | Technical Bid Evaluation for SCMS_RCA |  | 2026-02-20 |  |  | 6 | 20-Jun-25 A | 2026-03-20 | 26-Jun-25 A | 2026-02-20 | 2026-03-20
| A60260 | Technical Bid Evaluation for SCMS_IFD/IFC |  | 2026-02-20 |  |  | 6 | 27-Jun-25 A | 2026-03-20 | 03-Jul-25 A | 2026-02-20 | 2026-03-20
| A60210 | Commercial Bid Evaluation(Completion) |  | 2026-02-20 |  |  | 6 | 04-Jul-25 A | 2026-03-20 | 15-Jul-25 A | 2026-02-20 | 2026-03-20
| A60200 | Issue Purchase Order to Vendor for SCMS |  | 2026-02-20 |  |  | 6 | 16-Jul-25 A | 2026-03-20 | 20-Aug-25 A | 2026-02-20 | 2026-03-20
| ICSS (Integrated Control and Safety System) including sys. Modifications |  |  | 2026-02-20 |  |  | 128 | 07-Feb-25 A | 2026-03-18 | 20-Jun-25 A | 2026-02-20 | 2026-03-27 | 18
| Integrated Control and Safety System GF |  |  | 2026-02-20 |  |  | 105 | 15-May-25 A | 2026-03-18 | 20-Jun-25 A | 2026-02-20 | 2026-03-18 | 18
| A23940 | Issue RFQ to Bidders |  | 2026-02-20 |  |  | 14 | 15-May-25 A | 2026-03-18 | 30-May-25 A | 2026-02-20 | 2026-03-18
| A16890 | Technical Bid Evaluation for ICSS System_RCC |  | 2026-02-20 |  |  | 16 | 29-May-25 A | 2026-03-18 | 30-May-25 A | 2026-02-20 | 2026-03-18
| A16900 | Technical Bid Evaluation for ICSS System_IFA |  | 2026-02-20 |  |  | 11 | 30-May-25 A | 2026-03-18 | 31-May-25 A | 2026-02-20 | 2026-03-18
| A16910 | Technical Bid Evaluation for ICSS System_RCA |  | 2026-02-20 |  |  | 16 | 31-May-25 A | 2026-03-18 | 01-Jun-25 A | 2026-02-20 | 2026-03-18
| A16920 | Technical Bid Evaluation for ICSS System_IFD/IFC |  | 2026-02-20 |  |  | 8 | 01-Jun-25 A | 2026-03-18 | 06-Jun-25 A | 2026-02-20 | 2026-03-18
| A23970 | Commercial Bid Evaluation(Completion) |  | 2026-02-20 |  |  | 21 | 07-Jun-25 A | 2026-03-18 | 13-Jun-25 A | 2026-02-20 | 2026-03-18
| A23950 | Issue Purchase Order to Vendor for ICSS |  | 2026-02-20 |  |  | 14 | 14-Jun-25 A | 2026-03-18 | 20-Jun-25 A | 2026-02-20 | 2026-03-18
| TA_Integrated Control & Safety System BF - Honeywell |  |  | 2026-02-20 |  |  | 27 | 07-Feb-25 A | 2026-03-27 | 10-Mar-25 A | 2026-02-20 | 2026-03-27
| A19770 | Issue RFQ to Bidders |  | 2026-02-20 |  |  | 10 | 07-Feb-25 A | 2026-03-27 | 17-Feb-25 A | 2026-02-20 | 2026-03-27
| A56210 | TBE for ICT System Modification_Free Issue Material |  | 2026-02-20 |  |  | 11 | 18-Feb-25 A | 2026-03-27 | 28-Feb-25 A | 2026-02-20 | 2026-03-27
| A19780 | Issue Purchase Order to Vendor |  | 2026-02-20 |  |  | 7 | 01-Mar-25 A | 2026-03-27 | 10-Mar-25 A | 2026-02-20 | 2026-03-27
| Instrument Cables |  |  | 2026-02-20 |  |  | 80 | 01-Nov-25 A | 2026-03-23 | 2026-03-12 | 2026-03-12 | 2026-04-10 | 21
| Instrument Cable (Single & Multicore = Approx. 78,130 Mtr) |  |  | 2026-02-20 |  |  | 80 | 01-Nov-25 A | 2026-03-23 | 2026-03-12 | 2026-03-12 | 2026-04-10 | 21
| A21190 | Issue RFQ to Bidders |  | 2026-02-20 |  |  | 5 | 01-Nov-25 A | 2026-03-23 | 11-Nov-25 A | 2026-02-20 | 2026-03-23
| A16780 | Technical Bid Evaluation for Instrument Cables_IFR |  | 2026-02-20 |  |  | 5 | 26-Jan-26 A | 2026-03-23 | 31-Jan-26 A | 2026-02-20 | 2026-03-23
| A16790 | Technical Bid Evaluation for Instrument Cables_RCC |  | 2026-02-20 |  |  | 5 | 02-Feb-26 A | 2026-03-23 | 06-Feb-26 A | 2026-02-20 | 2026-03-23
| A16800 | Technical Bid Evaluation for Instrument Cables_IFA |  | 2026-02-20 |  |  | 5 | 06-Feb-26 A | 2026-03-23 | 2026-02-26 | 2026-02-26 | 2026-03-27 | 21
| A21220 | Commercial Bid Evaluation(Completion) |  | 2026-02-27 |  |  | 5 | 2026-02-27 | 2026-03-30 | 2026-03-05 | 2026-03-05 | 2026-04-03 | 21
| A16810 | Technical Bid Evaluation for Instrument Cables_RCA |  | 2026-02-27 |  |  | 5 | 2026-02-27 | 2026-03-30 | 2026-03-05 | 2026-03-05 | 2026-04-03 | 21
| A21200 | Issue Purchase Order to Vendor |  | 2026-03-06 |  |  | 5 | 2026-03-06 | 2026-04-06 | 2026-03-12 | 2026-03-12 | 2026-04-10 | 21
| A16820 | Technical Bid Evaluation for Instrument Cables_IFD/IFC |  | 2026-03-06 |  |  | 5 | 2026-03-06 | 2026-04-06 | 2026-03-12 | 2026-03-12 | 2026-04-10 | 21
| Local Fire Control Panel including F & G Detectors |  |  | 2026-02-20 |  |  | 173 | 20-Jun-25 A | 2026-05-05 | 12-Dec-25 A | 2026-02-20 | 2026-05-05
| Fire Detection Alarm System and Local Fire Control Panel (Clean Agent Unit) |  |  | 2026-02-20 |  |  | 173 | 20-Jun-25 A | 2026-05-05 | 12-Dec-25 A | 2026-02-20 | 2026-05-05 | 52
| A16930 | Issue RFQ to Bidders |  | 2026-02-20 |  |  | 20 | 20-Jun-25 A | 2026-05-05 | 14-Aug-25 A | 2026-02-20 | 2026-05-05
| A19660 | Bid Evaluation(Completion) |  | 2026-02-20 |  |  | 15 | 01-Nov-25 A | 2026-05-05 | 14-Nov-25 A | 2026-02-20 | 2026-05-05
| A19670 | Commercial Bid Evaluation(Completion) |  | 2026-02-20 |  |  | 18 | 28-Nov-25 A | 2026-05-05 | 10-Dec-25 A | 2026-02-20 | 2026-05-05
| A19650 | Issue Purchase Order to Vendor for Fire Detection, Local Fire Control and Clean Agent |  | 2026-02-20 |  |  | 6 | 01-Dec-25 A | 2026-05-05 | 12-Dec-25 A | 2026-02-20 | 2026-05-05
| PSVs |  |  | 2026-02-20 |  |  | 89 | 15-Oct-25 A | 2026-03-20 | 2026-03-25 | 2026-03-25 | 2026-04-22 | 20
| PSVs (1"x2" upto 8"x10" - CS Rating 150/150, 300/150 = 22 Nos) |  |  | 2026-02-20 |  |  | 89 | 15-Oct-25 A | 2026-03-20 | 2026-03-25 | 2026-03-25 | 2026-04-22 | 20
| A21110 | Issue RFQ to Bidders |  | 2026-02-20 |  |  | 5 | 15-Oct-25 A | 2026-03-20 | 27-Oct-25 A | 2026-02-20 | 2026-03-20
| A21130 | Bid Evaluation(Completion) |  | 2026-02-20 |  |  | 10 | 15-Feb-26 A | 2026-03-20 | 2026-03-05 | 2026-03-05 | 2026-04-02 | 20
| A21140 | Commercial Bid Evaluation(Completion) |  | 2026-03-06 |  |  | 7 | 2026-03-06 | 2026-04-03 | 2026-03-16 | 2026-03-16 | 2026-04-13 | 20
| A21120 | Issue Purchase Order to Vendor |  | 2026-03-17 |  |  | 7 | 2026-03-17 | 2026-04-14 | 2026-03-25 | 2026-03-25 | 2026-04-22 | 20
| Sampling System |  |  | 2026-02-20 |  |  | 53 | 12-Feb-25 A | 2026-03-27 | 18-Mar-25 A | 2026-02-20 | 2026-03-27
| TA_CGC Turbine Software Upgrade - HMI |  |  | 2026-02-20 |  |  | 31 | 15-Feb-25 A | 2026-03-27 | 18-Mar-25 A | 2026-02-20 | 2026-03-27
| A37240 | Issue RFQ to Bidders |  | 2026-02-20 |  |  | 10 | 15-Feb-25 A | 2026-03-27 | 25-Feb-25 A | 2026-02-20 | 2026-03-27
| A57300 | TBE for ICT System Modification_Free Issue Material |  | 2026-02-20 |  |  | 11 | 26-Feb-25 A | 2026-03-27 | 07-Mar-25 A | 2026-02-20 | 2026-03-27
| A37270 | Issue Purchase Order to Vendor |  | 2026-02-20 |  |  | 10 | 08-Mar-25 A | 2026-03-27 | 18-Mar-25 A | 2026-02-20 | 2026-03-27
| TA_SGM Replacement (Additional Item) |  |  | 2026-02-20 |  |  | 53 | 12-Feb-25 A | 2026-03-27 | 15-Mar-25 A | 2026-02-20 | 2026-03-27
| A37400 | Issue RFQ to Bidders |  | 2026-02-20 |  |  | 20 | 12-Feb-25 A | 2026-03-27 | 22-Feb-25 A | 2026-02-20 | 2026-03-27
| A57330 | TBE for ICT System Modification_Free Issue Material |  | 2026-02-20 |  |  | 23 | 23-Feb-25 A | 2026-03-27 | 04-Mar-25 A | 2026-02-20 | 2026-03-27
| A37410 | Issue Purchase Order to Vendor |  | 2026-02-20 |  |  | 10 | 05-Mar-25 A | 2026-03-27 | 15-Mar-25 A | 2026-02-20 | 2026-03-27
| F&G [324 Nos] Flame Detectors, MCP, Beacon, etc. |  |  | 2026-02-20 |  |  | 185 | 18-Jul-25 A | 2026-04-20 | 2026-04-02 | 2026-04-02 | 2026-05-29 | 41
| F&G Flame Detectors, MCP, Beacon (Nos 324) |  |  | 2026-02-20 |  |  | 185 | 18-Jul-25 A | 2026-04-20 | 2026-04-02 | 2026-04-02 | 2026-05-29 | 41
| A17350 | Issue RFQ to Bidders |  | 2026-02-20 |  |  | 4 | 18-Jul-25 A | 2026-04-20 | 14-Aug-25 A | 2026-02-20 | 2026-04-20
| A16540 | Technical Bid Evaluation for Fire & Gas Detectors_RCC |  | 2026-02-20 |  |  | 8 | 14-Feb-26 A | 2026-04-20 | 2026-03-03 | 2026-03-03 | 2026-04-29 | 41
| A16550 | Technical Bid Evaluation for Fire & Gas Detectors_IFA |  | 2026-03-03 |  |  | 6 | 2026-03-03 | 2026-05-04 | 2026-03-11 | 2026-03-11 | 2026-05-12 | 44
| A20130 | Commercial Bid Evaluation(Completion) |  | 2026-03-03 |  |  | 10 | 2026-03-03 | 2026-04-30 | 2026-03-17 | 2026-03-17 | 2026-05-13 | 41
| A16560 | Technical Bid Evaluation for Fire & Gas Detectors_RCA |  | 2026-03-11 |  |  | 6 | 2026-03-11 | 2026-05-12 | 2026-03-19 | 2026-03-19 | 2026-05-20 | 44
| A48220 | Technical Bid Evaluation for Fire & Gas Detectors_IFD/IFC |  | 2026-03-19 |  |  | 8 | 2026-03-19 | 2026-05-20 | 2026-03-30 | 2026-03-30 | 2026-05-29 | 44
| A20110 | Issue Purchase Order to Vendor F&G Flames Detectors, MCP, Beacon (nos 324) |  | 2026-03-17 |  |  | 12 | 2026-03-17 | 2026-05-14 | 2026-04-02 | 2026-04-02 | 2026-05-29 | 41
| Main Electrical Equipment |  |  | 2026-02-20 |  |  | 309 | 01-Feb-25 A | 2026-03-27 | 2026-05-13 | 2026-05-13 | 2026-09-29 | 98
| DG Set (750 KVA) |  |  | 2026-02-20 |  |  | 78 | 01-Feb-25 A | 2026-05-18 | 25-Sep-25 A | 2026-02-20 | 2026-05-18
| DG Set |  |  | 2026-02-20 |  |  | 78 | 01-Feb-25 A | 2026-05-18 | 25-Sep-25 A | 2026-02-20 | 2026-05-18 | 63
| A16030 | Issue RFQ to Bidders |  | 2026-02-20 |  |  | 21 | 01-Feb-25 A | 2026-05-18 | 07-Feb-25 A | 2026-02-20 | 2026-05-18
| A13330 | Technical Bid Evaluation For Emergency Diesel Generator Set_IFR |  | 2026-02-20 |  |  | 11 | 03-May-25 A | 2026-05-18 | 21-May-25 A | 2026-02-20 | 2026-05-18
| A20430 | Commercial Bid Evaluation(Completion) |  | 2026-02-20 |  |  | 5 | 18-Jul-25 A | 2026-05-18 | 08-Aug-25 A | 2026-02-20 | 2026-05-18
| A20410 | Issue Purchase Order to Vendor for DG Set |  | 2026-02-20 |  |  | 5 | 09-Aug-25 A | 2026-05-18 | 22-Aug-25 A | 2026-02-20 | 2026-05-18
| A13340 | Technical Bid Evaluation For Emergency Diesel Generator Set_RCC |  | 2026-02-20 |  |  | 16 | 14-Jul-25 A | 2026-05-18 | 22-Aug-25 A | 2026-02-20 | 2026-05-18
| A13350 | Technical Bid Evaluation For Emergency Diesel Generator Set_IFA |  | 2026-02-20 |  |  | 11 | 23-Aug-25 A | 2026-05-18 | 08-Sep-25 A | 2026-02-20 | 2026-05-18
| A13360 | Technical Bid Evaluation For Emergency Diesel Generator Set_RCA |  | 2026-02-20 |  |  | 16 | 20-Aug-25 A | 2026-05-18 | 15-Sep-25 A | 2026-02-20 | 2026-05-18
| A13370 | Technical Bid Evaluation For Emergency Diesel Generator Set_IFD/IFC |  | 2026-02-20 |  |  | 8 | 10-Sep-25 A | 2026-05-18 | 25-Sep-25 A | 2026-02-20 | 2026-05-18
| UPS (AC - 60 KVA, 20 KVA, DC-UPS 6.5 KVA) |  |  | 2026-02-20 |  |  | 226 | 12-Feb-25 A | 2026-03-27 | 2026-03-09 | 2026-03-09 | 2026-08-13 | 114
| TA_UPS Modification (Additional Item) - Chloride Technology |  |  | 2026-02-20 |  |  | 50 | 12-Feb-25 A | 2026-03-27 | 15-Mar-25 A | 2026-02-20 | 2026-03-27
| A37080 | Issue RFQs to Bidders |  | 2026-02-20 |  |  | 20 | 12-Feb-25 A | 2026-03-27 | 22-Feb-25 A | 2026-02-20 | 2026-03-27
| A57420 | TBE for Electrical System Modification_ Free Issue Material |  | 2026-02-20 |  |  | 23 | 23-Feb-25 A | 2026-03-27 | 04-Mar-25 A | 2026-02-20 | 2026-03-27
| A37090 | Issue Purchase Order to Vendor |  | 2026-02-20 |  |  | 7 | 05-Mar-25 A | 2026-03-27 | 15-Mar-25 A | 2026-02-20 | 2026-03-27
| UPS (AC - 60 KVA, 20 KVA, DC-UPS 6.5 KVA) Qty 1+1+1 = 03 Nos |  |  | 2026-02-20 |  |  | 177 | 07-Jul-25 A | 2026-05-28 | 2026-03-09 | 2026-03-09 | 2026-08-13 | 114
| A16090 | Issue RFQ to Bidders |  | 2026-02-20 |  |  | 21 | 07-Jul-25 A | 2026-05-28 | 04-Aug-25 A | 2026-02-20 | 2026-05-28
| A13080 | Technical Bid Evaluation For AC UPS_IFR |  | 2026-02-20 |  |  | 11 | 06-Sep-25 A | 2026-05-28 | 13-Sep-25 A | 2026-02-20 | 2026-05-28
| A13090 | Technical Bid Evaluation For AC UPS_RCC |  | 2026-02-20 |  |  | 6 | 14-Sep-25 A | 2026-05-28 | 20-Sep-25 A | 2026-02-20 | 2026-05-28
| A19550 | Commercial Bid Evaluation(Completion) |  | 2026-02-20 |  |  | 6 | 01-Sep-25 A | 2026-05-28 | 26-Sep-25 A | 2026-02-20 | 2026-05-28
| A19530 | Issue Purchase Order to Vendor for UPS (GF) |  | 2026-02-20 |  |  | 6 | 29-Sep-25 A | 2026-05-28 | 16-Oct-25 A | 2026-02-20 | 2026-05-28
| A13100 | Technical Bid Evaluation For AC UPS_IFA |  | 2026-02-20 |  |  | 6 | 20-Oct-25 A | 2026-07-29 | 03-Nov-25 A | 2026-02-20 | 2026-07-29
| A13110 | Technical Bid Evaluation For AC UPS_RCA |  | 2026-02-20 |  |  | 6 | 04-Nov-25 A | 2026-07-29 | 12-Nov-25 A | 2026-02-20 | 2026-07-29
| A13120 | Technical Bid Evaluation For AC UPS_IFD/IFC |  | 2026-02-20 |  |  | 11 | 2026-02-20 | 2026-07-29 | 2026-03-09 | 2026-03-09 | 2026-08-13 | 114
| Power Transformer |  |  | 2026-02-20 |  |  | 97 | 10-May-25 A | 2026-05-01 | 17-Sep-25 A | 2026-02-20 | 2026-05-01
| Power Transformers (Qty 05) |  |  | 2026-02-20 |  |  | 97 | 10-May-25 A | 2026-05-01 | 17-Sep-25 A | 2026-02-20 | 2026-05-01 | 50
| A12930 | Technical Bid Evaluation For Transformer (Power And Distribution)_IFR |  | 2026-02-20 |  |  | 11 | 10-May-25 A | 2026-05-01 | 22-May-25 A | 2026-02-20 | 2026-05-01
| A16150 | Issue RFQ to Bidders |  | 2026-02-20 |  |  | 20 | 15-May-25 A | 2026-05-01 | 25-May-25 A | 2026-02-20 | 2026-05-01
| A12970 | Technical Bid Evaluation For Transformer (Power And Distribution)_IFD/IFC |  | 2026-02-20 |  |  | 8 | 25-May-25 A | 2026-05-01 | 01-Jun-25 A | 2026-02-20 | 2026-05-01
| A12940 | Technical Bid Evaluation For Transformer (Power And Distribution)_RCC |  | 2026-02-20 |  |  | 16 | 15-May-25 A | 2026-05-01 | 03-Jun-25 A | 2026-02-20 | 2026-05-01
| A20190 | Commercial Bid Evaluation(Completion) |  | 2026-02-20 |  |  | 21 | 02-Jun-25 A | 2026-05-01 | 08-Jun-25 A | 2026-02-20 | 2026-05-01
| A20170 | Issue Purchase Order to Vendor for Power Transformers |  | 2026-02-20 |  |  | 5 | 09-Jun-25 A | 2026-05-01 | 29-Jul-25 A | 2026-02-20 | 2026-05-01
| A12950 | Technical Bid Evaluation For Transformer (Power And Distribution)_IFA |  | 2026-02-20 |  |  | 11 | 01-Aug-25 A | 2026-05-01 | 10-Sep-25 A | 2026-02-20 | 2026-05-01
| A12960 | Technical Bid Evaluation For Transformer (Power And Distribution)_RCA |  | 2026-02-20 |  |  | 16 | 30-Aug-25 A | 2026-05-01 | 17-Sep-25 A | 2026-02-20 | 2026-05-01
| Electrical Heat Tracing |  |  | 2026-02-20 |  |  | 59 | 2026-02-20 | 2026-04-21 | 2026-05-13 | 2026-05-13 | 2026-07-13 | 42
| Electrical Heat Tracing (53 Meter for piping + 340 Meter for instrumentation) |  |  | 2026-02-20 |  |  | 59 | 2026-02-20 | 2026-04-21 | 2026-05-13 | 2026-05-13 | 2026-07-13 | 42
| A16270 | Issue RFQ to Bidders |  | 2026-02-20 |  |  | 15 | 2026-02-20 | 2026-04-21 | 2026-03-12 | 2026-03-12 | 2026-05-12 | 42
| A22210 | Bid Evaluation(Completion) |  | 2026-03-13 |  |  | 15 | 2026-03-13 | 2026-05-12 | 2026-04-02 | 2026-04-02 | 2026-06-02 | 42
| A22220 | Commercial Bid Evaluation(Completion) |  | 2026-04-03 |  |  | 15 | 2026-04-03 | 2026-06-02 | 2026-04-23 | 2026-04-23 | 2026-06-23 | 42
| A22230 | Issue Purchase Order to Vendor |  | 2026-04-24 |  |  | 14 | 2026-04-24 | 2026-06-23 | 2026-05-13 | 2026-05-13 | 2026-07-13 | 42
| CP |  |  | 2026-02-20 |  |  | 155 | 21-Nov-25 A | 2026-05-15 | 2026-02-27 | 2026-02-27 | 2026-05-22 | 60
| Cathodic Protection (CP) Total CS Piping Length - 499 Meters |  |  | 2026-02-20 |  |  | 155 | 21-Nov-25 A | 2026-05-15 | 2026-02-27 | 2026-02-27 | 2026-05-22 | 60
| A16210 | Issue RFQ to Bidders |  | 2026-02-20 |  |  | 20 | 21-Nov-25 A | 2026-05-15 | 18-Dec-25 A | 2026-02-20 | 2026-05-15
| A22150 | Bid Evaluation(Completion) |  | 2026-02-20 |  |  | 45 | 24-Jan-26 A | 2026-05-15 | 31-Jan-26 A | 2026-02-20 | 2026-05-15
| A22160 | Commercial Bid Evaluation(Completion) |  | 2026-02-20 |  |  | 15 | 01-Feb-26 A | 2026-05-15 | 20-Feb-26 A | 2026-02-20 | 2026-05-15
| A22170 | Issue Purchase Order to Vendor |  | 2026-02-20 |  |  | 30 | 20-Feb-26 A | 2026-05-15 | 2026-02-27 | 2026-02-27 | 2026-05-22 | 60
| LV & MV Switchgears |  |  | 2026-02-20 |  |  | 125 | 18-Mar-25 A | 2026-04-22 | 01-Nov-25 A | 2026-02-20 | 2026-04-22 | 41
| Switchgear (LV, MV) |  |  | 2026-02-20 |  |  | 125 | 18-Mar-25 A | 2026-04-22 | 01-Nov-25 A | 2026-02-20 | 2026-04-22
| A16330 | Issue RFQ to Bidders |  | 2026-02-20 |  |  | 21 | 18-Mar-25 A | 2026-04-22 | 14-Apr-25 A | 2026-02-20 | 2026-04-22
| A13030 | Technical Bid Evaluation For LV Switchgear_IFR |  | 2026-02-20 |  |  | 11 | 15-Apr-25 A | 2026-04-22 | 20-Apr-25 A | 2026-02-20 | 2026-04-22
| A13040 | Technical Bid Evaluation For LV Switchgear_RCC |  | 2026-02-20 |  |  | 16 | 21-Apr-25 A | 2026-04-22 | 25-Apr-25 A | 2026-02-20 | 2026-04-22
| A13050 | Technical Bid Evaluation For LV Switchgear_IFA |  | 2026-02-20 |  |  | 5 | 28-Apr-25 A | 2026-04-22 | 01-May-25 A | 2026-02-20 | 2026-04-22
| A13060 | Technical Bid Evaluation For LV Switchgear_RCA |  | 2026-02-20 |  |  | 16 | 02-May-25 A | 2026-04-22 | 10-May-25 A | 2026-02-20 | 2026-04-22
| A13070 | Technical Bid Evaluation For LV Switchgear_IFD/IFC |  | 2026-02-20 |  |  | 8 | 30-May-25 A | 2026-04-22 | 18-Jul-25 A | 2026-02-20 | 2026-04-22
| A20250 | Commercial Bid Evaluation(Completion) |  | 2026-02-20 |  |  | 2 | 19-Jul-25 A | 2026-04-22 | 29-Jul-25 A | 2026-02-20 | 2026-04-22
| A20230 | Issue Purchase Order to Vendor for switchgear (LV, MV) |  | 2026-02-20 |  |  | 16 | 24-Sep-25 A | 2026-04-22 | 01-Nov-25 A | 2026-02-20 | 2026-04-22
| Switch Gear Modification (Siemens) |  |  | 2026-02-20 |  |  | 25 | 20-Feb-25 A | 2026-03-27 | 18-Mar-25 A | 2026-02-20 | 2026-03-27
| TA_Switchgear (MV Switchgear Modifications) - Siemens |  |  | 2026-02-20 |  |  | 25 | 20-Feb-25 A | 2026-03-27 | 18-Mar-25 A | 2026-02-20 | 2026-03-27
| A22400 | Issue RFQ to Bidders |  | 2026-02-20 |  |  | 5 | 20-Feb-25 A | 2026-03-27 | 25-Feb-25 A | 2026-02-20 | 2026-03-27
| A56240 | TBE for Electrical System Modification_Free Issue Material |  | 2026-02-20 |  |  | 11 | 26-Feb-25 A | 2026-03-27 | 09-Mar-25 A | 2026-02-20 | 2026-03-27
| A22420 | Issue Purchase Order to Vendor |  | 2026-02-20 |  |  | 7 | 10-Mar-25 A | 2026-03-27 | 18-Mar-25 A | 2026-02-20 | 2026-03-27
| MV & LV VFD's |  |  | 2026-02-20 |  |  | 105 | 18-Jul-25 A | 2026-09-22 | 12-Aug-25 A | 2026-02-20 | 2026-09-22 | 152
| Variable Fequency Drives (VFDs) LV Qty = 03 |  |  | 2026-02-20 |  |  | 105 | 18-Jul-25 A | 2026-09-22 | 12-Aug-25 A | 2026-02-20 | 2026-09-22
| A20790 | Issue RFQ to Bidders |  | 2026-02-20 |  |  | 20 | 18-Jul-25 A | 2026-09-22 | 20-Jul-25 A | 2026-02-20 | 2026-09-22
| A13380 | Technical Bid Evaluation For LV Variable Frequency Drive_IFR |  | 2026-02-20 |  |  | 11 | 21-Jul-25 A | 2026-09-22 | 23-Jul-25 A | 2026-02-20 | 2026-09-22
| A13390 | Technical Bid Evaluation For LV Variable Frequency Drive_RCC |  | 2026-02-20 |  |  | 16 | 24-Jul-25 A | 2026-09-22 | 25-Jul-25 A | 2026-02-20 | 2026-09-22
| A13400 | Technical Bid Evaluation For LV Variable Frequency Drive_IFA |  | 2026-02-20 |  |  | 11 | 28-Jul-25 A | 2026-09-22 | 30-Jul-25 A | 2026-02-20 | 2026-09-22
| A13410 | Technical Bid Evaluation For LV Variable Frequency Drive_RCA |  | 2026-02-20 |  |  | 16 | 31-Jul-25 A | 2026-09-22 | 01-Aug-25 A | 2026-02-20 | 2026-09-22
| A13420 | Technical Bid Evaluation For LV Variable Frequency Drive_IFD/IFC |  | 2026-02-20 |  |  | 8 | 04-Aug-25 A | 2026-09-22 | 06-Aug-25 A | 2026-02-20 | 2026-09-22
| A20820 | Commercial Bid Evaluation(Completion) |  | 2026-02-20 |  |  | 21 | 07-Aug-25 A | 2026-09-22 | 08-Aug-25 A | 2026-02-20 | 2026-09-22
| A20800 | Issue Purchase Order to Vendor for VFDs |  | 2026-02-20 |  |  | 14 | 11-Aug-25 A | 2026-09-22 | 12-Aug-25 A | 2026-02-20 | 2026-09-22
| HV Capacitor Bay |  |  | 2026-02-20 |  |  | 140 | 15-Apr-25 A | 2026-06-11 | 15-Oct-25 A | 2026-02-20 | 2026-08-06 | 79
| A16570 | Issue RFQ to Bidders |  | 2026-02-20 |  |  | 21 | 15-Apr-25 A | 2026-06-11 | 06-May-25 A | 2026-02-20 | 2026-06-11
| A13180 | Technical Bid Evaluation For Capacitor Bank_IFR |  | 2026-02-20 |  |  | 3 | 01-Sep-25 A | 2026-06-11 | 05-Sep-25 A | 2026-02-20 | 2026-06-11
| A13190 | Technical Bid Evaluation For Capacitor Bank_RCC |  | 2026-02-20 |  |  | 3 | 06-Sep-25 A | 2026-06-11 | 10-Sep-25 A | 2026-02-20 | 2026-06-11
| A13200 | Technical Bid Evaluation For Capacitor Bank_IFA |  | 2026-02-20 |  |  | 3 | 11-Sep-25 A | 2026-08-06 | 15-Sep-25 A | 2026-02-20 | 2026-08-06
| A13210 | Technical Bid Evaluation For Capacitor Bank_RCA |  | 2026-02-20 |  |  | 3 | 16-Sep-25 A | 2026-08-06 | 20-Sep-25 A | 2026-02-20 | 2026-08-06
| A13220 | Technical Bid Evaluation For Capacitor Bank_IFD/IFC |  | 2026-02-20 |  |  | 3 | 22-Sep-25 A | 2026-08-06 | 25-Sep-25 A | 2026-02-20 | 2026-08-06
| A20010 | Commercial Bid Evaluation(Completion) |  | 2026-02-20 |  |  | 3 | 01-Sep-25 A | 2026-06-11 | 29-Sep-25 A | 2026-02-20 | 2026-06-11
| A19990 | Issue Purchase Order to Vendor for HV Capacitor Bay |  | 2026-02-20 |  |  | 3 | 30-Sep-25 A | 2026-06-11 | 15-Oct-25 A | 2026-02-20 | 2026-06-11
| Power Distribution Panel and LCS, Battery & Safety Switch, Resister Bank |  |  | 2026-02-20 |  |  | 109 | 10-Apr-25 A | 2026-09-29 | 20-Jun-25 A | 2026-02-20 | 2026-09-29 | 157
| NGR Panel Qty 02 |  |  | 2026-02-20 |  |  | 109 | 10-Apr-25 A | 2026-09-29 | 20-Jun-25 A | 2026-02-20 | 2026-09-29 | 157
| A16630 | Issue RFQ to Bidders |  | 2026-02-20 |  |  | 21 | 10-Apr-25 A | 2026-09-29 | 01-May-25 A | 2026-02-20 | 2026-09-29
| A13280 | Technical Bid Evaluation For Neutral Grounding Resistor_IFR |  | 2026-02-20 |  |  | 11 | 02-May-25 A | 2026-09-29 | 13-May-25 A | 2026-02-20 | 2026-09-29
| A13290 | Technical Bid Evaluation For Neutral Grounding Resistor_RCC |  | 2026-02-20 |  |  | 16 | 14-May-25 A | 2026-09-29 | 15-May-25 A | 2026-02-20 | 2026-09-29
| A13300 | Technical Bid Evaluation For Neutral Grounding Resistor_IFA |  | 2026-02-20 |  |  | 11 | 14-May-25 A | 2026-09-29 | 15-May-25 A | 2026-02-20 | 2026-09-29
| A13310 | Technical Bid Evaluation For Neutral Grounding Resistor_RCA |  | 2026-02-20 |  |  | 16 | 14-May-25 A | 2026-09-29 | 15-May-25 A | 2026-02-20 | 2026-09-29
| A13320 | Technical Bid Evaluation For Neutral Grounding Resistor_IFD/IFC |  | 2026-02-20 |  |  | 8 | 15-May-25 A | 2026-09-29 | 20-May-25 A | 2026-02-20 | 2026-09-29
| A20310 | Commercial Bid Evaluation(Completion) |  | 2026-02-20 |  |  | 21 | 21-May-25 A | 2026-09-29 | 13-Jun-25 A | 2026-02-20 | 2026-09-29
| A20290 | Issue Purchase Order to Vendor for NGR Panel |  | 2026-02-20 |  |  | 14 | 14-Jun-25 A | 2026-09-29 | 20-Jun-25 A | 2026-02-20 | 2026-09-29
| Interposing Relay Panel (IRP) |  |  | 2026-02-20 |  |  | 19 | 2026-02-20 | 2026-04-28 | 2026-03-18 | 2026-03-18 | 2026-07-17 | 87
| Interposing Relay Panel |  |  | 2026-02-20 |  |  | 19 | 2026-02-20 | 2026-04-28 | 2026-03-18 | 2026-03-18 | 2026-07-17 | 87
| A16690 | Issue RFQ to Bidders |  | 2026-02-20 |  |  | 3 | 2026-02-20 | 2026-04-28 | 2026-02-24 | 2026-02-24 | 2026-04-30 | 47
| A58640 | Technical Bid Evaluation for Interposting Relay Panel_IFR |  | 2026-02-25 |  |  | 3 | 2026-02-25 | 2026-05-01 | 2026-02-27 | 2026-02-27 | 2026-05-05 | 47
| A58650 | Technical Bid Evaluation for Interposting Relay Panel_RCC |  | 2026-03-02 |  |  | 3 | 2026-03-02 | 2026-05-06 | 2026-03-04 | 2026-03-04 | 2026-05-08 | 47
| A58660 | Technical Bid Evaluation for Interposting Relay Panel_IFA |  | 2026-03-05 |  |  | 3 | 2026-03-05 | 2026-05-11 | 2026-03-09 | 2026-03-09 | 2026-05-13 | 47
| A20370 | Commercial Bid Evaluation(Completion) |  | 2026-03-10 |  |  | 3 | 2026-03-10 | 2026-05-14 | 2026-03-12 | 2026-03-12 | 2026-05-18 | 47
| A58670 | Technical Bid Evaluation for Interposting Relay Panel_RCA |  | 2026-03-10 |  |  | 3 | 2026-03-10 | 2026-07-10 | 2026-03-12 | 2026-03-12 | 2026-07-14 | 88
| A58680 | Technical Bid Evaluation for Interposting Relay Panel_IFD/IFC |  | 2026-03-13 |  |  | 3 | 2026-03-13 | 2026-07-15 | 2026-03-17 | 2026-03-17 | 2026-07-17 | 88
| A20350 | Issue Purchase Order to Vendor for Interposing Relay Panel |  | 2026-03-13 |  |  | 4 | 2026-03-13 | 2026-05-19 | 2026-03-18 | 2026-03-18 | 2026-05-22 | 47
| Subcontract Services |  |  | 2026-02-20 |  |  | 198 | 14-Nov-24 A | 2026-02-21 | 11-Jun-25 A | 2026-02-20 | 2026-03-27
| Detail Engineering Subcontract |  |  | 2026-02-20 |  |  | 12 | 14-Nov-24 A | 2026-02-21 | 06-Dec-24 A | 2026-02-20 | 2026-02-21
| A61090 | Issue RFQ to CONTRACTORs |  | 2026-02-20 |  |  | 3 | 14-Nov-24 A | 2026-02-21 | 15-Nov-24 A | 2026-02-20 | 2026-02-21
| A61100 | Technical Bid analysis and clarifications |  | 2026-02-20 |  |  | 3 | 19-Nov-24 A | 2026-02-21 | 22-Nov-24 A | 2026-02-20 | 2026-02-21
| A61110 | Bid analysis and clarifications |  | 2026-02-20 |  |  | 3 | 23-Nov-24 A | 2026-02-21 | 29-Nov-24 A | 2026-02-20 | 2026-02-21
| A61120 | Subcontract Awarded/Signed |  | 2026-02-20 |  |  | 3 | 29-Nov-24 A | 2026-02-21 | 06-Dec-24 A | 2026-02-20 | 2026-02-21
| TA Construction |  |  | 2026-02-20 |  |  | 85 | 09-Dec-24 A | 2026-03-11 | 07-Mar-25 A | 2026-02-20 | 2026-03-11
| A61130 | Issue RFQ to CONTRACTORs |  | 2026-02-20 |  |  | 21 | 09-Dec-24 A | 2026-03-11 | 09-Dec-24 A | 2026-02-20 | 2026-03-11
| A61140 | Technical Bid analysis and clarifications |  | 2026-02-20 |  |  | 21 | 08-Jan-25 A | 2026-03-11 | 08-Jan-25 A | 2026-02-20 | 2026-03-11
| A61150 | Bid analysis and clarifications |  | 2026-02-20 |  |  | 21 | 06-Feb-25 A | 2026-03-11 | 06-Feb-25 A | 2026-02-20 | 2026-03-11
| A61160 | Subcontract Awarded/Signed |  | 2026-02-20 |  |  | 21 | 07-Mar-25 A | 2026-03-11 | 07-Mar-25 A | 2026-02-20 | 2026-03-11
| Main Construction |  |  | 2026-02-20 |  |  | 85 | 09-Dec-24 A | 2026-02-21 | 10-Mar-25 A | 2026-02-20 | 2026-02-21
| A61170 | Issue RFQ to CONTRACTORs |  | 2026-02-20 |  |  | 21 | 09-Dec-24 A | 2026-02-21 | 01-Feb-25 A | 2026-02-20 | 2026-02-21
| A61180 | Technical Bid analysis and clarifications |  | 2026-02-20 |  |  | 21 | 02-Feb-25 A | 2026-02-21 | 15-Feb-25 A | 2026-02-20 | 2026-02-21
| A61190 | Bid analysis and clarifications |  | 2026-02-20 |  |  | 21 | 16-Feb-25 A | 2026-02-21 | 25-Feb-25 A | 2026-02-20 | 2026-02-21
| A61200 | Subcontract Awarded/Signed |  | 2026-02-20 |  |  | 21 | 07-Mar-25 A | 2026-02-21 | 10-Mar-25 A | 2026-02-20 | 2026-02-21
| Topgraphic |  |  | 2026-02-20 |  |  | 85 | 01-Jan-25 A | 2026-02-21 | 20-Mar-25 A | 2026-02-20 | 2026-02-21
| A61210 | Issue RFQ to CONTRACTORs |  | 2026-02-20 |  |  | 21 | 01-Jan-25 A | 2026-02-21 | 03-Jan-25 A | 2026-02-20 | 2026-02-21
| A61220 | Technical Bid analysis and clarifications |  | 2026-02-20 |  |  | 21 | 04-Jan-25 A | 2026-02-21 | 03-Feb-25 A | 2026-02-20 | 2026-02-21
| A61230 | Bid analysis and clarifications |  | 2026-02-20 |  |  | 21 | 04-Feb-25 A | 2026-02-21 | 01-Mar-25 A | 2026-02-20 | 2026-02-21
| A61240 | Subcontract Awarded/Signed |  | 2026-02-20 |  |  | 21 | 02-Mar-25 A | 2026-02-21 | 20-Mar-25 A | 2026-02-20 | 2026-02-21
| Piling |  |  | 2026-02-20 |  |  | 87 | 01-Apr-25 A | 2026-02-21 | 11-May-25 A | 2026-02-20 | 2026-02-21
| A61250 | Issue RFQ to CONTRACTORs |  | 2026-02-20 |  |  | 21 | 01-Apr-25 A | 2026-02-21 | 20-Apr-25 A | 2026-02-20 | 2026-02-21
| A61260 | Technical Bid analysis and clarifications |  | 2026-02-20 |  |  | 21 | 21-Apr-25 A | 2026-02-21 | 27-Apr-25 A | 2026-02-20 | 2026-02-21
| A61270 | Bid analysis and clarifications |  | 2026-02-20 |  |  | 21 | 28-Apr-25 A | 2026-02-21 | 04-May-25 A | 2026-02-20 | 2026-02-21
| A61280 | Subcontract Awarded/Signed |  | 2026-02-20 |  |  | 21 | 05-May-25 A | 2026-02-21 | 11-May-25 A | 2026-02-20 | 2026-02-21
| A61290 | Issue RFQ to CONTRACTORs |  | 2026-02-20 |  |  | 21 | 10-Feb-25 A | 2026-03-02 | 01-Mar-25 A | 2026-02-20 | 2026-03-02
| A61300 | Technical Bid analysis and clarifications |  | 2026-02-20 |  |  | 21 | 02-Mar-25 A | 2026-03-02 | 15-Mar-25 A | 2026-02-20 | 2026-03-02
| A61310 | Bid analysis and clarifications |  | 2026-02-20 |  |  | 21 | 16-Mar-25 A | 2026-03-02 | 18-Apr-25 A | 2026-02-20 | 2026-03-02
| A61320 | Subcontract Awarded/Signed |  | 2026-02-20 |  |  | 21 | 19-Apr-25 A | 2026-03-02 | 11-Jun-25 A | 2026-02-20 | 2026-03-02
| VSM Services Agreements |  |  | 2026-02-20 |  |  | 85 | 01-Feb-25 A | 2026-03-27 | 08-Mar-25 A | 2026-02-20 | 2026-03-27
| A61330 | Issue RFQ to CONTRACTORs |  | 2026-02-20 |  |  | 21 | 01-Feb-25 A | 2026-03-27 | 15-Feb-25 A | 2026-02-20 | 2026-03-27
| A61340 | Technical Bid analysis and clarifications |  | 2026-02-20 |  |  | 21 | 16-Feb-25 A | 2026-03-27 | 22-Feb-25 A | 2026-02-20 | 2026-03-27
| A61350 | Bid analysis and clarifications |  | 2026-02-20 |  |  | 21 | 23-Feb-25 A | 2026-03-27 | 01-Mar-25 A | 2026-02-20 | 2026-03-27
| A61360 | Subcontract Awarded/Signed |  | 2026-02-20 |  |  | 21 | 02-Mar-25 A | 2026-03-27 | 08-Mar-25 A | 2026-02-20 | 2026-03-27
| As-Built & Package handover |  |  | 2026-02-20 |  |  | 463 | 01-Jun-25 A | 2026-03-27 | 2027-07-14 | 2027-07-14 | 2027-07-20 | 4
| TA |  |  | 2026-02-20 |  |  | 30 | 01-Jun-25 A | 2026-03-27 | 15-Jul-25 A | 2026-02-20 | 2026-03-27
| A61430 | TA As-Built |  | 2026-02-20 |  |  | 30 | 01-Jun-25 A | 2026-03-27 | 15-Jul-25 A | 2026-02-20 | 2026-03-27
| Main Scope |  |  | 2027-04-22 |  |  | 60 | 2027-04-22 | 2027-04-28 | 2027-07-14 | 2027-07-14 | 2027-07-20 | 4
| A61440 | Main Scope As-Built |  | 2027-04-22 |  |  | 60 | 2027-04-22 | 2027-04-28 | 2027-07-14 | 2027-07-14 | 2027-07-20 | 4
| Manufacturing and Delivery |  |  | 2026-02-20 |  |  | 510 | 25-Feb-25 A | 2026-02-23 | 2026-09-29 | 2026-09-29 | 2027-07-20 | 210
| 51.C | Issue purchase orders for all remaining Mechanical / Rotating EQT. & EQT. Pkgs |  |  |  |  | 0 |  |  | 31-Dec-25 A
| 54.C | Issue purchase order for all major Instruments Control System |  |  |  |  | 0 |  |  | 07-Jan-26 A
| 52.C | Issue purchase orders for all major Electrical Equipments |  |  |  |  | 0 |  |  | 14-Jan-26 A
| 79.D | All major electrical Equipment delivered to Site |  |  |  |  | 0 |  |  | 2026-08-20 | 2026-08-20 | 2027-01-03 | 170
| Vessels / Drums (by Linde) |  |  | 2026-02-20 |  |  | 231 | 20-Jun-25 A | 2026-04-16 | 2026-06-12 | 2026-06-12 | 2026-10-30 | 100
| A35210 | Key Vendor Drawings / Data Approved |  | 2026-02-20 |  |  | 30 | 20-Jun-25 A | 2026-04-16 | 23-Aug-25 A | 2026-02-20 | 2026-04-16
| A35220 | Purchase Order for Major Sub-ordered Materials |  | 2026-02-20 |  |  | 5 | 25-Aug-25 A | 2026-04-16 | 02-Sep-25 A | 2026-02-20 | 2026-04-16
| A35230 | Major Sub-ordered Materials Received by Vendor and Verified |  | 2026-02-20 |  |  | 30 | 11-Aug-25 A | 2026-04-16 | 12-Sep-25 A | 2026-02-20 | 2026-04-16
| A35200 | Start Production (13-VV-707) |  |  |  |  | 0 | 19-Sep-25 A
| A35240 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  | 2026-02-20 |  |  | 1 | 15-Sep-25 A | 2026-04-16 | 26-Sep-25 A | 2026-02-20 | 2026-04-16
| A35250 | Manufacturing / Ex Works (India/UAE) |  | 2026-02-20 |  |  | 138 | 02-Dec-25 A | 2026-04-16 | 2026-04-10 | 2026-04-10 | 2026-06-05 | 70
| A35260 | Complete Manufacturing & ready for Final Inspection |  | 2026-04-13 |  |  | 7 | 2026-04-13 | 2026-06-05 | 2026-04-22 | 2026-04-22 | 2026-06-16 | 40
| A35270 | Materials Successfully Inspected, Tested / Ex Work |  | 2026-04-22 |  |  | 7 | 2026-04-22 | 2026-06-17 | 2026-05-01 | 2026-05-01 | 2026-06-25 | 40
| A35320 | Delivery of FG Comp. 2nd Stage Dis. Drum Tag# 13-VV-707 |  | 2026-05-11 |  |  | 35 | 2026-05-11 | 2026-07-05 | 2026-06-08 | 2026-06-08 | 2026-08-01 | 69
| A35060 | Start Production (13-VV-713) |  |  |  |  | 0 | 20-Jun-25 A
| A35070 | Key Vendor Drawings / Data Approved |  | 2026-02-20 |  |  | 30 | 20-Jun-25 A | 2026-04-22 | 23-Aug-25 A | 2026-02-20 | 2026-04-22
| A35080 | Purchase Order for Major Sub-ordered Materials |  | 2026-02-20 |  |  | 5 | 25-Aug-25 A | 2026-04-22 | 02-Sep-25 A | 2026-02-20 | 2026-04-22
| A35090 | Major Sub-ordered Materials Received by Vendor and Verified |  | 2026-02-20 |  |  | 30 | 11-Aug-25 A | 2026-04-22 | 12-Sep-25 A | 2026-02-20 | 2026-04-22
| A35100 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  | 2026-02-20 |  |  | 1 | 15-Sep-25 A | 2026-04-22 | 26-Oct-25 A | 2026-02-20 | 2026-04-22
| A35110 | Manufacturing / Ex Works (India/UAE) |  | 2026-02-20 |  |  | 138 | 21-Nov-25 A | 2026-04-22 | 2026-04-15 | 2026-04-15 | 2026-06-16 | 77
| A35120 | Complete Manufacturing & ready for Final Inspection |  | 2026-04-16 |  |  | 5 | 2026-04-16 | 2026-06-16 | 2026-04-22 | 2026-04-22 | 2026-06-23 | 43
| A35130 | Materials Successfully Inspected, Tested / Ex Work |  | 2026-04-23 |  |  | 7 | 2026-04-23 | 2026-06-23 | 2026-05-01 | 2026-05-01 | 2026-07-02 | 43
| A35170 | Delivery of OG Comp. 2nd Stage Suc. Drum Tag# 13-VV-713 |  | 2026-05-09 |  |  | 35 | 2026-05-09 | 2026-07-09 | 2026-06-05 | 2026-06-05 | 2026-08-06 | 77
| A35340 | Start Production (13-VV-712) |  |  |  |  | 0 | 20-Jun-25 A
| A35350 | Key Vendor Drawings / Data Approved |  | 2026-02-20 |  |  | 30 | 20-Jun-25 A | 2026-06-02 | 23-Aug-25 A | 2026-02-20 | 2026-06-02
| A35360 | Purchase Order for Major Sub-ordered Materials |  | 2026-02-20 |  |  | 5 | 25-Aug-25 A | 2026-06-02 | 02-Sep-25 A | 2026-02-20 | 2026-06-02
| A35370 | Major Sub-ordered Materials Received by Vendor and Verified |  | 2026-02-20 |  |  | 30 | 11-Aug-25 A | 2026-06-02 | 12-Sep-25 A | 2026-02-20 | 2026-06-02
| A35380 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  | 2026-02-20 |  |  | 1 | 15-Sep-25 A | 2026-06-02 | 26-Oct-25 A | 2026-02-20 | 2026-06-02
| A35390 | Manufacturing / Ex Works (India/UAE) |  | 2026-02-20 |  |  | 138 | 21-Nov-25 A | 2026-06-02 | 2026-04-15 | 2026-04-15 | 2026-07-27 | 128
| A35400 | Complete Manufacturing & ready for Final Inspection |  | 2026-04-16 |  |  | 5 | 2026-04-16 | 2026-07-27 | 2026-04-22 | 2026-04-22 | 2026-07-31 | 72
| A35410 | Materials Successfully Inspected, Tested / Ex Work |  | 2026-04-23 |  |  | 7 | 2026-04-23 | 2026-08-03 | 2026-05-01 | 2026-05-01 | 2026-08-11 | 72
| A35470 | Delivery of OG Buffer Drum - Tag# 13-VV-712 |  | 2026-05-16 |  |  | 35 | 2026-05-16 | 2026-08-26 | 2026-06-12 | 2026-06-12 | 2026-09-22 | 128
| A35480 | Start Production (70-VV-1415) |  |  |  |  | 0 | 20-Jun-25 A
| A35490 | Key Vendor Drawings / Data Approved |  | 2026-02-20 |  |  | 30 | 20-Jun-25 A | 2026-07-18 | 23-Aug-25 A | 2026-02-20 | 2026-07-18
| A35500 | Purchase Order for Major Sub-ordered Materials |  | 2026-02-20 |  |  | 5 | 25-Aug-25 A | 2026-07-18 | 02-Sep-25 A | 2026-02-20 | 2026-07-18
| A35510 | Major Sub-ordered Materials Received by Vendor and Verified |  | 2026-02-20 |  |  | 30 | 11-Aug-25 A | 2026-07-18 | 12-Sep-25 A | 2026-02-20 | 2026-07-18
| A35520 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  | 2026-02-20 |  |  | 1 | 15-Sep-25 A | 2026-07-18 | 26-Oct-25 A | 2026-02-20 | 2026-07-18
| A35530 | Manufacturing / Ex Works (India/UAE) |  | 2026-02-20 |  |  | 138 | 21-Nov-25 A | 2026-07-18 | 2026-04-15 | 2026-04-15 | 2026-09-11 | 185
| A35540 | Complete Manufacturing & ready for Final Inspection |  | 2026-04-16 |  |  | 5 | 2026-04-16 | 2026-09-11 | 2026-04-22 | 2026-04-22 | 2026-09-17 | 106
| A35550 | Materials Successfully Inspected, Tested / Ex Work |  | 2026-04-23 |  |  | 7 | 2026-04-23 | 2026-09-18 | 2026-05-01 | 2026-05-01 | 2026-09-28 | 106
| A35580 | Delivery of PSA2 Slop Drum Tag# 70-VV-1415 |  | 2026-05-08 |  |  | 35 | 2026-05-08 | 2026-10-03 | 2026-06-04 | 2026-06-04 | 2026-10-30 | 185
| A35620 | Start Production (13-VV-706) |  |  |  |  | 0 | 20-Jun-25 A
| A35630 | Key Vendor Drawings / Data Approved |  | 2026-02-20 |  |  | 30 | 20-Jun-25 A | 2026-04-17 | 23-Aug-25 A | 2026-02-20 | 2026-04-17
| A35640 | Purchase Order for Major Sub-ordered Materials |  | 2026-02-20 |  |  | 5 | 25-Aug-25 A | 2026-04-17 | 02-Sep-25 A | 2026-02-20 | 2026-04-17
| A35650 | Major Sub-ordered Materials Received by Vendor and Verified |  | 2026-02-20 |  |  | 30 | 11-Aug-25 A | 2026-04-17 | 12-Sep-25 A | 2026-02-20 | 2026-04-17
| A35660 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  | 2026-02-20 |  |  | 1 | 15-Sep-25 A | 2026-04-17 | 26-Oct-25 A | 2026-02-20 | 2026-04-17
| A35670 | Manufacturing / Ex Works (India/UAE) |  | 2026-02-20 |  |  | 138 | 21-Nov-25 A | 2026-04-17 | 2026-04-15 | 2026-04-15 | 2026-06-11 | 70
| A35680 | Complete Manufacturing & ready for Final Inspection |  | 2026-04-16 |  |  | 7 | 2026-04-16 | 2026-06-11 | 2026-04-24 | 2026-04-24 | 2026-06-19 | 40
| A35690 | Materials Successfully Inspected, Tested / Ex Work |  | 2026-04-27 |  |  | 7 | 2026-04-27 | 2026-06-22 | 2026-05-05 | 2026-05-05 | 2026-06-30 | 40
| A35710 | Delivery of FG Comp. 2nd Stage Suc. Drum Tag# 13-VV-706 |  | 2026-05-06 |  |  | 35 | 2026-05-06 | 2026-07-01 | 2026-06-02 | 2026-06-02 | 2026-07-28 | 70
| A35760 | Start Production (13-VV-705) |  |  |  |  | 0 | 20-Jun-25 A
| A35770 | Key Vendor Drawings / Data Approved |  | 2026-02-20 |  |  | 30 | 20-Jun-25 A | 2026-05-07 | 23-Aug-25 A | 2026-02-20 | 2026-05-07
| A35780 | Purchase Order for Major Sub-ordered Materials |  | 2026-02-20 |  |  | 5 | 25-Aug-25 A | 2026-05-07 | 02-Sep-25 A | 2026-02-20 | 2026-05-07
| A35790 | Major Sub-ordered Materials Received by Vendor and Verified |  | 2026-02-20 |  |  | 30 | 11-Aug-25 A | 2026-05-07 | 12-Sep-25 A | 2026-02-20 | 2026-05-07
| A35800 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  | 2026-02-20 |  |  | 26 | 15-Sep-25 A | 2026-05-07 | 26-Oct-25 A | 2026-02-20 | 2026-05-07
| A35810 | Manufacturing / Ex Works (India/UAE) |  | 2026-02-20 |  |  | 138 | 21-Nov-25 A | 2026-05-07 | 2026-04-15 | 2026-04-15 | 2026-07-01 | 95
| A35820 | Complete Manufacturing & ready for Final Inspection |  | 2026-04-16 |  |  | 6 | 2026-04-16 | 2026-07-01 | 2026-04-23 | 2026-04-23 | 2026-07-08 | 54
| A35830 | Materials Successfully Inspected, Tested / Ex Work |  | 2026-04-24 |  |  | 7 | 2026-04-24 | 2026-07-09 | 2026-05-04 | 2026-05-04 | 2026-07-17 | 54
| A35840 | Delivery of FG Comp.1st Stage Suc. Drum (13-VV-705) |  | 2026-05-05 |  |  | 35 | 2026-05-05 | 2026-07-19 | 2026-06-01 | 2026-06-01 | 2026-08-15 | 94
| A33660 | Start Production |  |  |  |  | 0 | 20-Jun-25 A
| A29960 | Key Vendor Drawings / Data Approved |  | 2026-02-20 |  |  | 30 | 20-Jun-25 A | 2026-05-14 | 23-Aug-25 A | 2026-02-20 | 2026-05-14
| A29970 | Purchase Order for Major Sub-ordered Materials |  | 2026-02-20 |  |  | 5 | 25-Aug-25 A | 2026-05-14 | 02-Sep-25 A | 2026-02-20 | 2026-05-14
| A29980 | Major Sub-ordered Materials Received by Vendor and Verified |  | 2026-02-20 |  |  | 20 | 11-Aug-25 A | 2026-05-14 | 12-Sep-25 A | 2026-02-20 | 2026-05-14
| A29990 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  | 2026-02-20 |  |  | 1 | 15-Sep-25 A | 2026-05-14 | 26-Oct-25 A | 2026-02-20 | 2026-05-14
| A30000 | Manufacturing / Ex Works (India/UAE) |  | 2026-02-20 |  |  | 138 | 21-Nov-25 A | 2026-05-14 | 2026-04-15 | 2026-04-15 | 2026-07-08 | 104
| A30010 | Complete Manufacturing & ready for Final Inspection |  | 2026-04-16 |  |  | 7 | 2026-04-16 | 2026-07-08 | 2026-04-24 | 2026-04-24 | 2026-07-16 | 59
| A30020 | Materials Successfully Inspected, Tested / Ex Work |  | 2026-04-27 |  |  | 7 | 2026-04-27 | 2026-07-17 | 2026-05-05 | 2026-05-05 | 2026-07-27 | 59
| A33670 | Delivery of Vessel's Internals (05 Dimister Pads) in Warehouse |  | 2026-05-06 |  |  | 35 | 2026-05-06 | 2026-07-28 | 2026-06-02 | 2026-06-02 | 2026-08-24 | 104
| C4 Guard Adsorber Cooler Dripleg - (BF) |  |  | 2026-02-20 |  |  | 200 | 20-Jun-25 A | 2026-07-15 | 2026-06-02 | 2026-06-02 | 2026-10-25 | 103
| A34660 | Start Production |  |  |  |  | 0 | 20-Jun-25 A
| A28160 | Key Vendor Drawings / Data Approved |  | 2026-02-20 |  |  | 60 | 20-Jun-25 A | 2026-07-15 | 23-Aug-25 A | 2026-02-20 | 2026-07-15
| A28170 | Purchase Order for Major Sub-ordered Materials |  | 2026-02-20 |  |  | 30 | 25-Aug-25 A | 2026-07-15 | 02-Sep-25 A | 2026-02-20 | 2026-07-15
| A28180 | Major Sub-ordered Materials Received by Vendor and Verified |  | 2026-02-20 |  |  | 21 | 11-Aug-25 A | 2026-07-15 | 12-Sep-25 A | 2026-02-20 | 2026-07-15
| A28190 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  | 2026-02-20 |  |  | 9 | 15-Sep-25 A | 2026-07-15 | 26-Oct-25 A | 2026-02-20 | 2026-07-15
| A28200 | Manufacturing / Ex Works (India/UAE) |  | 2026-02-20 |  |  | 150 | 21-Nov-25 A | 2026-07-15 | 2026-04-15 | 2026-04-15 | 2026-09-08 | 181
| A28210 | Complete Manufacturing & ready for Final Inspection |  | 2026-04-16 |  |  | 7 | 2026-04-16 | 2026-09-08 | 2026-04-24 | 2026-04-24 | 2026-09-16 | 103
| A28220 | Materials Successfully Inspected, Tested / Ex Work |  | 2026-04-27 |  |  | 7 | 2026-04-27 | 2026-09-17 | 2026-05-05 | 2026-05-05 | 2026-09-25 | 103
| A34670 | Delivery of C4 Guard Absorber Cooler Dripleg (Post - TA) |  | 2026-05-06 |  |  | 35 | 2026-05-06 | 2026-09-28 | 2026-06-02 | 2026-06-02 | 2026-10-25 | 181
| Water Collection & Sanitary Waste Water Pumps |  |  | 2026-02-20 |  |  | 248 | 10-Sep-25 A | 2026-06-20 | 2026-06-05 | 2026-06-05 | 2026-10-18 | 95
| A33850 | Start Production |  |  |  |  | 0 | 10-Sep-25 A
| A30680 | Key Vendor Drawings / Data Approved |  | 2026-02-20 |  |  | 30 | 21-Nov-25 A | 2026-06-20 | 04-Dec-25 A | 2026-02-20 | 2026-06-20
| A30690 | Purchase Order for Major Sub-ordered Materials |  | 2026-02-20 |  |  | 5 | 08-Dec-25 A | 2026-06-20 | 19-Dec-25 A | 2026-02-20 | 2026-06-20
| A30700 | Major Sub-ordered Materials Received by Vendor and Verified |  | 2026-02-20 |  |  | 40 | 19-Dec-25 A | 2026-06-20 | 02-Jan-26 A | 2026-02-20 | 2026-06-20
| A30710 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  | 2026-02-20 |  |  | 1 | 01-Jan-26 A | 2026-06-20 | 15-Jan-26 A | 2026-02-20 | 2026-06-20
| A30720 | Manufacturing / Ex Works (India/UAE) |  | 2026-02-20 |  |  | 175 | 01-Jan-26 A | 2026-06-20 | 2026-04-20 | 2026-04-20 | 2026-08-19 | 151
| A30730 | Complete Manufacturing & ready for Final Inspection |  | 2026-04-21 |  |  | 7 | 2026-04-21 | 2026-08-19 | 2026-04-29 | 2026-04-29 | 2026-08-28 | 87
| A30740 | Materials Successfully Inspected, Tested / Ex Work |  | 2026-04-30 |  |  | 7 | 2026-04-30 | 2026-08-28 | 2026-05-08 | 2026-05-08 | 2026-09-08 | 87
| A33860 | Delivery of Sanitary Waste Water Sump Pump (01) |  | 2026-05-09 |  |  | 35 | 2026-05-09 | 2026-09-08 | 2026-06-05 | 2026-06-05 | 2026-10-06 | 153
| A33870 | Start Production |  |  |  |  | 0 | 10-Sep-25 A
| A30770 | Key Vendor Drawings / Data Approved |  | 2026-02-20 |  |  | 30 | 21-Nov-25 A | 2026-07-03 | 10-Dec-25 A | 2026-02-20 | 2026-07-03
| A30780 | Purchase Order for Major Sub-ordered Materials |  | 2026-02-20 |  |  | 5 | 11-Dec-25 A | 2026-07-03 | 19-Dec-25 A | 2026-02-20 | 2026-07-03
| A30790 | Major Sub-ordered Materials Received by Vendor and Verified |  | 2026-02-20 |  |  | 40 | 19-Dec-25 A | 2026-07-03 | 02-Jan-26 A | 2026-02-20 | 2026-07-03
| A30800 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  | 2026-02-20 |  |  | 1 | 01-Jan-26 A | 2026-07-03 | 15-Jan-26 A | 2026-02-20 | 2026-07-03
| A30810 | Manufacturing / Ex Works (India/UAE) |  | 2026-02-20 |  |  | 75 | 01-Jan-26 A | 2026-07-03 | 2026-04-20 | 2026-04-20 | 2026-09-01 | 166
| A30820 | Complete Manufacturing & ready for Final Inspection |  | 2026-04-21 |  |  | 7 | 2026-04-21 | 2026-09-01 | 2026-04-29 | 2026-04-29 | 2026-09-09 | 95
| A30830 | Materials Successfully Inspected, Tested / Ex Work |  | 2026-04-30 |  |  | 7 | 2026-04-30 | 2026-09-10 | 2026-05-08 | 2026-05-08 | 2026-09-18 | 95
| A33880 | Delivery of Water Sump Pump (02) |  | 2026-05-09 |  |  | 35 | 2026-05-09 | 2026-09-21 | 2026-06-05 | 2026-06-05 | 2026-10-18 | 169
| A33910 | Start Production |  |  |  |  | 0 | 15-Aug-25 A
| A30960 | Purchase Order for Major Sub-ordered Materials |  | 2026-03-26 |  |  | 5 | 01-Feb-26 A | 2027-06-09 | 12-Feb-26 A | 2026-03-26 | 2027-06-09
| A30950 | Key Vendor Drawings / Data Approved |  | 2026-02-20 |  |  | 50 | 23-Jan-26 A | 2026-04-21 | 2026-03-26 | 2026-03-26 | 2026-05-25 | 42
| A30980 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  | 2026-03-26 |  |  | 1 | 2026-03-26 | 2026-05-26 | 2026-03-27 | 2026-03-27 | 2026-05-27 | 75
| A30970 | Major Sub-ordered Materials Received by Vendor and Verified |  | 2026-03-26 |  |  | 30 | 2026-03-26 | 2027-06-09 | 2026-05-07 | 2026-05-07 | 2027-07-20 | 313
| A30990 | Manufacturing / Ex Works (India/UAE) |  | 2026-03-27 |  |  | 125 | 2026-03-27 | 2026-05-27 | 2026-07-05 | 2026-07-05 | 2026-09-04 | 75
| A31000 | Complete Manufacturing & ready for Final Inspection |  | 2026-07-06 |  |  | 7 | 2026-07-06 | 2026-09-04 | 2026-07-14 | 2026-07-14 | 2026-09-14 | 44
| A31010 | Materials Successfully Inspected, Tested / Ex Work |  | 2026-07-15 |  |  | 7 | 2026-07-15 | 2026-09-15 | 2026-07-23 | 2026-07-23 | 2026-09-23 | 44
| A33920 | Delivery of Material in Warehouse (FG) Crane |  | 2026-07-24 |  |  | 26 | 2026-07-24 | 2026-09-24 | 2026-08-13 | 2026-08-13 | 2026-10-14 | 78
| A33930 | Start Production |  |  |  |  | 0 | 10-Sep-25 A
| A31050 | Purchase Order for Major Sub-ordered Materials |  | 2026-03-26 |  |  | 5 | 01-Feb-26 A | 2027-06-09 | 12-Feb-26 A | 2026-03-26 | 2027-06-09
| A31040 | Key Vendor Drawings / Data Approved |  | 2026-02-20 |  |  | 35 | 23-Jan-26 A | 2026-04-28 | 2026-03-26 | 2026-03-26 | 2026-06-01 | 47
| A31070 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  | 2026-03-26 |  |  | 1 | 2026-03-26 | 2026-06-02 | 2026-03-27 | 2026-03-27 | 2026-06-03 | 84
| A31060 | Major Sub-ordered Materials Received by Vendor and Verified |  | 2026-03-26 |  |  | 30 | 2026-03-26 | 2027-06-09 | 2026-05-07 | 2026-05-07 | 2027-07-20 | 313
| A31080 | Manufacturing / Ex Works (India/UAE) |  | 2026-03-27 |  |  | 125 | 2026-03-27 | 2026-06-03 | 2026-07-05 | 2026-07-05 | 2026-09-11 | 84
| A31090 | Complete Manufacturing & ready for Final Inspection |  | 2026-07-06 |  |  | 7 | 2026-07-06 | 2026-09-11 | 2026-07-14 | 2026-07-14 | 2026-09-21 | 49
| A31100 | Materials Successfully Inspected, Tested / Ex Work |  | 2026-07-15 |  |  | 7 | 2026-07-15 | 2026-09-22 | 2026-07-23 | 2026-07-23 | 2026-09-30 | 49
| A33940 | Delivery of (OG) Crane |  | 2026-07-24 |  |  | 26 | 2026-07-24 | 2026-10-01 | 2026-08-13 | 2026-08-13 | 2026-10-21 | 86
| A36300 | Start Production (13-HE-703) |  |  |  |  | 0 | 11-Jul-25 A
| A36310 | Key Vendor Drawings / Data Approved |  | 2026-02-20 |  |  | 30 | 18-Jul-25 A | 2026-05-14 | 28-Aug-25 A | 2026-02-20 | 2026-05-14
| A36320 | Purchase Order for Major Sub-ordered Materials |  | 2026-02-20 |  |  | 35 | 29-Aug-25 A | 2026-05-14 | 02-Sep-25 A | 2026-02-20 | 2026-05-14
| A36330 | Major Sub-ordered Materials Received by Vendor and Verified |  | 2026-02-20 |  |  | 35 | 11-Aug-25 A | 2026-05-14 | 12-Sep-25 A | 2026-02-20 | 2026-05-14
| A36340 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  | 2026-02-20 |  |  | 13 | 15-Sep-25 A | 2026-05-14 | 26-Oct-25 A | 2026-02-20 | 2026-05-14
| A36350 | Manufacturing / Ex Works (India/UAE) |  | 2026-02-20 |  |  | 188 | 21-Nov-25 A | 2026-05-14 | 2026-02-27 | 2026-02-27 | 2026-05-22 | 105
| A36360 | Complete Manufacturing & ready for Final Inspection |  | 2026-02-27 |  |  | 10 | 2026-02-27 | 2026-05-22 | 2026-03-13 | 2026-03-13 | 2026-06-04 | 60
| A36370 | Materials Successfully Inspected, Tested / Ex Work |  | 2026-03-13 |  |  | 11 | 2026-03-13 | 2026-06-05 | 2026-03-30 | 2026-03-30 | 2026-06-19 | 60
| A36380 | Delivery of FG Comp. Interstage Cooler (BEM) - Tag# 13-HE-703 |  | 2026-03-30 |  |  | 35 | 2026-03-30 | 2026-06-21 | 2026-04-27 | 2026-04-27 | 2026-07-18 | 103
| A36430 | Start Production (13-HE-709) |  |  |  |  | 0 | 11-Jul-25 A
| A36440 | Key Vendor Drawings / Data Approved |  | 2026-02-20 |  |  | 30 | 18-Jul-25 A | 2026-06-21 | 28-Aug-25 A | 2026-02-20 | 2026-06-21
| A36450 | Purchase Order for Major Sub-ordered Materials |  | 2026-02-20 |  |  | 35 | 29-Aug-25 A | 2026-06-21 | 02-Sep-25 A | 2026-02-20 | 2026-06-21
| A36460 | Major Sub-ordered Materials Received by Vendor and Verified |  | 2026-02-20 |  |  | 35 | 11-Aug-25 A | 2026-06-21 | 12-Sep-25 A | 2026-02-20 | 2026-06-21
| A36470 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  | 2026-02-20 |  |  | 13 | 15-Sep-25 A | 2026-06-21 | 26-Oct-25 A | 2026-02-20 | 2026-06-21
| A36480 | Manufacturing / Ex Works (India/UAE) |  | 2026-02-20 |  |  | 119 | 21-Nov-25 A | 2026-06-21 | 2026-02-24 | 2026-02-24 | 2026-06-26 | 152
| A36490 | Complete Manufacturing & ready for Final Inspection |  | 2026-02-24 |  |  | 10 | 2026-02-24 | 2026-06-26 | 2026-03-10 | 2026-03-10 | 2026-07-09 | 87
| A36500 | Materials Successfully Inspected, Tested / Ex Work |  | 2026-03-10 |  |  | 11 | 2026-03-10 | 2026-07-10 | 2026-03-25 | 2026-03-25 | 2026-07-24 | 87
| A36520 | Delivery of OG Comp. After Cooler (BEU) - Tag# 13-HE-709 |  | 2026-03-25 |  |  | 35 | 2026-03-25 | 2026-07-25 | 2026-04-22 | 2026-04-22 | 2026-08-22 | 152
| A36560 | Start Production (13-HE-704) |  |  |  |  | 0 | 11-Jul-25 A
| A36570 | Key Vendor Drawings / Data Approved |  | 2026-02-20 |  |  | 30 | 18-Jul-25 A | 2026-05-17 | 28-Aug-25 A | 2026-02-20 | 2026-05-17
| A36580 | Purchase Order for Major Sub-ordered Materials |  | 2026-02-20 |  |  | 35 | 29-Aug-25 A | 2026-05-17 | 02-Sep-25 A | 2026-02-20 | 2026-05-17
| A36590 | Major Sub-ordered Materials Received by Vendor and Verified |  | 2026-02-20 |  |  | 35 | 11-Aug-25 A | 2026-05-17 | 12-Sep-25 A | 2026-02-20 | 2026-05-17
| A36600 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  | 2026-02-20 |  |  | 13 | 15-Sep-25 A | 2026-05-17 | 26-Oct-25 A | 2026-02-20 | 2026-05-17
| A36610 | Manufacturing / Ex Works (India/UAE) |  | 2026-02-20 |  |  | 119 | 21-Nov-25 A | 2026-05-17 | 2026-02-24 | 2026-02-24 | 2026-05-22 | 108
| A36620 | Complete Manufacturing & ready for Final Inspection |  | 2026-02-24 |  |  | 10 | 2026-02-24 | 2026-05-22 | 2026-03-10 | 2026-03-10 | 2026-06-04 | 62
| A36630 | Materials Successfully Inspected, Tested / Ex Work |  | 2026-03-10 |  |  | 11 | 2026-03-10 | 2026-06-05 | 2026-03-25 | 2026-03-25 | 2026-06-19 | 62
| A36660 | Delivery of FG Comp. After Cooler (BEM) - Tag# 13-HE-704 |  | 2026-03-25 |  |  | 35 | 2026-03-25 | 2026-06-21 | 2026-04-22 | 2026-04-22 | 2026-07-18 | 109
| A36690 | Start Production (13-HE-708) |  |  |  |  | 0 | 11-Jul-25 A
| A36700 | Key Vendor Drawings / Data Approved |  | 2026-02-20 |  |  | 30 | 18-Jul-25 A | 2026-06-21 | 28-Aug-25 A | 2026-02-20 | 2026-06-21
| A36710 | Purchase Order for Major Sub-ordered Materials |  | 2026-02-20 |  |  | 35 | 29-Aug-25 A | 2026-06-21 | 02-Sep-25 A | 2026-02-20 | 2026-06-21
| A36720 | Major Sub-ordered Materials Received by Vendor and Verified |  | 2026-02-20 |  |  | 35 | 11-Aug-25 A | 2026-06-21 | 12-Sep-25 A | 2026-02-20 | 2026-06-21
| A36730 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  | 2026-02-20 |  |  | 13 | 15-Sep-25 A | 2026-06-21 | 26-Oct-25 A | 2026-02-20 | 2026-06-21
| A36740 | Manufacturing / Ex Works (India/UAE) |  | 2026-02-20 |  |  | 119 | 21-Nov-25 A | 2026-06-21 | 2026-02-24 | 2026-02-24 | 2026-06-26 | 152
| A36750 | Complete Manufacturing & ready for Final Inspection |  | 2026-02-24 |  |  | 10 | 2026-02-24 | 2026-06-26 | 2026-03-10 | 2026-03-10 | 2026-07-09 | 87
| A36760 | Materials Successfully Inspected, Tested / Ex Work |  | 2026-03-10 |  |  | 11 | 2026-03-10 | 2026-07-10 | 2026-03-25 | 2026-03-25 | 2026-07-24 | 87
| A36800 | Delivery of GG Comp. Interstage Cooler (BEU) (13-HE-708) |  | 2026-03-25 |  |  | 35 | 2026-03-25 | 2026-07-25 | 2026-04-22 | 2026-04-22 | 2026-08-22 | 152
| A36820 | Start Production (50-HE-1410) |  |  |  |  | 0 | 11-Jul-25 A
| A36830 | Key Vendor Drawings / Data Approved |  | 2026-02-20 |  |  | 30 | 18-Jul-25 A | 2026-08-29 | 28-Aug-25 A | 2026-02-20 | 2026-08-29
| A36840 | Purchase Order for Major Sub-ordered Materials |  | 2026-02-20 |  |  | 35 | 29-Aug-25 A | 2026-08-29 | 02-Sep-25 A | 2026-02-20 | 2026-08-29
| A36850 | Major Sub-ordered Materials Received by Vendor and Verified |  | 2026-02-20 |  |  | 35 | 11-Aug-25 A | 2026-08-29 | 12-Sep-25 A | 2026-02-20 | 2026-08-29
| A36860 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  | 2026-02-20 |  |  | 13 | 15-Sep-25 A | 2026-08-29 | 26-Oct-25 A | 2026-02-20 | 2026-08-29
| A36870 | Manufacturing / Ex Works (India/UAE) |  | 2026-02-20 |  |  | 100 | 21-Nov-25 A | 2026-08-29 | 2026-02-23 | 2026-02-23 | 2026-09-02 | 238
| A36880 | Complete Manufacturing & ready for Final Inspection |  | 2026-02-24 |  |  | 10 | 2026-02-24 | 2026-09-02 | 2026-03-09 | 2026-03-09 | 2026-09-15 | 136
| A36890 | Materials Successfully Inspected, Tested / Ex Work |  | 2026-03-10 |  |  | 11 | 2026-03-10 | 2026-09-16 | 2026-03-24 | 2026-03-24 | 2026-09-30 | 136
| A36940 | Delivery of C4 Guard Regen. Gas Cooler (BEU) (Tag#50-HE-1410) |  | 2026-04-03 |  |  | 30 | 2026-04-03 | 2026-10-12 | 2026-04-26 | 2026-04-26 | 2026-11-04 | 240
| A33890 | Start Production |  |  |  |  | 0 | 29-Aug-25 A
| A30860 | Key Vendor Drawings / Data Approved |  | 2026-02-20 |  |  | 60 | 03-Sep-25 A | 2026-06-15 | 01-Dec-25 A | 2026-02-20 | 2026-06-15
| A30870 | Purchase Order for Major Sub-ordered Materials |  | 2026-02-20 |  |  | 10 | 02-Dec-25 A | 2026-06-15 | 19-Dec-25 A | 2026-02-20 | 2026-06-15
| A30880 | Major Sub-ordered Materials Received by Vendor and Verified |  | 2026-02-20 |  |  | 45 | 19-Dec-25 A | 2026-06-15 | 01-Jan-26 A | 2026-02-20 | 2026-06-15
| A30890 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  | 2026-02-20 |  |  | 1 | 01-Jan-26 A | 2026-06-15 | 15-Jan-26 A | 2026-02-20 | 2026-06-15
| A30900 | Manufacturing / Ex Works (India/UAE) |  | 2026-02-20 |  |  | 175 | 2026-02-20 | 2026-06-15 | 2026-07-09 | 2026-07-09 | 2026-11-02 | 144
| A30910 | Complete Manufacturing & ready for Final Inspection |  | 2026-07-10 |  |  | 7 | 2026-07-10 | 2026-11-02 | 2026-07-20 | 2026-07-20 | 2026-11-10 | 81
| A30920 | Materials Successfully Inspected, Tested / Ex Work |  | 2026-07-21 |  |  | 7 | 2026-07-21 | 2026-11-11 | 2026-07-29 | 2026-07-29 | 2026-11-19 | 81
| A34770 | Delivery of HVAC Ducts, E&I Material , Clading, Piping, Insulation, Supports & Accessories |  | 2026-07-30 |  |  | 15 | 2026-07-30 | 2026-11-20 | 2026-08-10 | 2026-08-10 | 2026-12-01 | 141
| A33900 | Delivery of Material HVAC (Main Equipments) |  | 2026-07-30 |  |  | 35 | 2026-07-30 | 2026-11-21 | 2026-08-26 | 2026-08-26 | 2026-12-18 | 143
| A33830 | Start Production |  |  |  |  | 0 | 03-Sep-25 A
| A30590 | Key Vendor Drawings / Data Approved |  | 2026-02-20 |  |  | 60 | 01-Oct-25 A | 2026-03-31 | 03-Nov-25 A | 2026-02-20 | 2026-03-31
| A30600 | Purchase Order for Major Sub-ordered Materials |  | 2026-02-20 |  |  | 8 | 03-Nov-25 A | 2026-03-31 | 09-Nov-25 A | 2026-02-20 | 2026-03-31
| A30610 | Major Sub-ordered Materials Received by Vendor and Verified |  | 2026-02-20 |  |  | 25 | 10-Nov-25 A | 2026-03-31 | 17-Nov-25 A | 2026-02-20 | 2026-03-31
| A30620 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  | 2026-02-20 |  |  | 1 | 2026-02-20 | 2026-03-31 | 2026-02-20 | 2026-02-20 | 2026-04-01 | 49
| A30630 | Manufacturing / Ex Works (India/UAE) |  | 2026-02-21 |  |  | 113 | 2026-02-21 | 2026-04-01 | 2026-05-21 | 2026-05-21 | 2026-06-30 | 49
| A30640 | Complete Manufacturing & ready for Final Inspection |  | 2026-05-22 |  |  | 7 | 2026-05-22 | 2026-06-30 | 2026-06-01 | 2026-06-01 | 2026-07-08 | 27
| A30650 | Materials Successfully Inspected, Tested / Ex Work |  | 2026-06-02 |  |  | 7 | 2026-06-02 | 2026-07-09 | 2026-06-10 | 2026-06-10 | 2026-07-17 | 27
| A33840 | Delivery of OG Compressor Discharge Drip Leg (02) |  | 2026-06-11 |  |  | 53 | 2026-06-11 | 2026-07-19 | 2026-07-22 | 2026-07-22 | 2026-08-30 | 48
| A34190 | Start Production |  |  |  |  | 0 | 27-Oct-25 A
| A32210 | Key Vendor Drawings / Data Approved |  | 2026-02-20 |  |  | 50 | 19-Dec-25 A | 2026-06-02 | 26-Dec-25 A | 2026-02-20 | 2026-06-02
| A32230 | Major Sub-ordered Materials Received by Vendor and Verified |  | 2026-02-20 |  |  | 40 | 29-Dec-25 A | 2026-06-02 | 02-Jan-26 A | 2026-02-20 | 2026-06-02
| A32220 | Purchase Order for Major Sub-ordered Materials |  | 2026-02-20 |  |  | 10 | 23-Dec-25 A | 2026-06-02 | 04-Jan-26 A | 2026-02-20 | 2026-06-02
| A32240 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  | 2026-02-20 |  |  | 1 | 06-Jan-26 A | 2026-06-02 | 09-Jan-26 A | 2026-02-20 | 2026-06-02
| A32250 | Manufacturing / Ex Works (India/UAE) |  | 2026-02-20 |  |  | 131 | 2026-02-20 | 2026-06-02 | 2026-06-04 | 2026-06-04 | 2026-09-15 | 128
| A32260 | Complete Manufacturing & ready for Final Inspection |  | 2026-06-05 |  |  | 8 | 2026-06-05 | 2026-09-15 | 2026-06-16 | 2026-06-16 | 2026-09-24 | 72
| A32270 | Materials Successfully Inspected, Tested / Ex Work |  | 2026-06-16 |  |  | 8 | 2026-06-16 | 2026-09-24 | 2026-06-25 | 2026-06-25 | 2026-10-05 | 72
| A34200 | Delivery and Manufacturing VESDA |  | 2026-06-26 |  |  | 35 | 2026-06-26 | 2026-10-06 | 2026-07-23 | 2026-07-23 | 2026-11-02 | 128
| A33990 | Start Production |  | 2026-03-19 |  |  | 0 | 2026-03-19 | 2026-06-19 |  |  |  | 114
| A31310 | Key Vendor Drawings / Data Approved |  | 2026-03-20 |  |  | 15 | 2026-03-20 | 2026-06-19 | 2026-04-09 | 2026-04-09 | 2026-07-09 | 65
| A31320 | Purchase Order for Major Sub-ordered Materials |  | 2026-04-09 |  |  | 7 | 2026-04-09 | 2026-07-10 | 2026-04-20 | 2026-04-20 | 2026-07-20 | 65
| A31330 | Major Sub-ordered Materials Received by Vendor and Verified |  | 2026-04-20 |  |  | 15 | 2026-04-20 | 2026-07-21 | 2026-05-11 | 2026-05-11 | 2026-08-10 | 65
| A31340 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  | 2026-05-11 |  |  | 1 | 2026-05-11 | 2026-08-11 | 2026-05-12 | 2026-05-12 | 2026-08-12 | 114
| A31350 | Manufacturing / Ex Works (India/UAE) |  | 2026-05-12 |  |  | 44 | 2026-05-12 | 2026-08-12 | 2026-06-16 | 2026-06-16 | 2026-09-16 | 114
| A31360 | Complete Manufacturing & ready for Final Inspection |  | 2026-06-16 |  |  | 7 | 2026-06-16 | 2026-09-16 | 2026-06-25 | 2026-06-25 | 2026-09-24 | 65
| A31370 | Materials Successfully Inspected, Tested / Ex Work |  | 2026-06-25 |  |  | 7 | 2026-06-25 | 2026-09-25 | 2026-07-06 | 2026-07-06 | 2026-10-05 | 65
| A34000 | Delivery of Fire Fighting Equipments |  | 2026-07-06 |  |  | 26 | 2026-07-06 | 2026-10-06 | 2026-07-27 | 2026-07-27 | 2026-10-26 | 114
| A34680 | Start Production |  |  |  |  | 0 | 30-Jan-26 A
| A28250 | Key Vendor Drawings / Data Approved |  | 2026-02-20 |  |  | 50 | 30-Jan-26 A | 2026-11-18 | 31-Jan-26 A | 2026-02-20 | 2026-11-18
| A28260 | Purchase Order for Major Sub-ordered Materials |  | 2026-02-20 |  |  | 15 | 01-Feb-26 A | 2026-11-18 | 02-Feb-26 A | 2026-02-20 | 2026-11-18
| A28270 | Major Sub-ordered Materials Received by Vendor and Verified |  | 2026-02-20 |  |  | 45 | 03-Feb-26 A | 2026-11-18 | 04-Feb-26 A | 2026-02-20 | 2026-11-18
| A28280 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  | 2026-03-02 |  |  | 9 | 05-Feb-26 A | 2026-11-18 | 06-Feb-26 A | 2026-03-02 | 2026-11-18
| A28290 | Manufacturing / Ex Works (India/UAE) |  | 2026-03-02 |  |  | 125 | 07-Feb-26 A | 2026-11-18 | 08-Feb-26 A | 2026-03-02 | 2026-11-18
| A28300 | Complete Manufacturing & ready for Final Inspection |  | 2026-03-02 |  |  | 7 | 09-Feb-26 A | 2026-11-18 | 10-Feb-26 A | 2026-03-02 | 2026-11-18
| A28310 | Materials Successfully Inspected, Tested / Ex Work |  | 2026-03-02 |  |  | 7 | 11-Feb-26 A | 2026-11-18 | 12-Feb-26 A | 2026-03-02 | 2026-11-18
| A34690 | Delivery of Coalescer (Post TA) |  | 2026-03-02 |  |  | 38 | 13-Feb-26 A | 2026-11-18 | 14-Feb-26 A | 2026-03-02 | 2026-11-18
| Steel Structure Greenfield (material +sandwitch Panel) |  |  | 2026-02-20 |  |  | 146 | 21-Jun-25 A | 2026-02-23 | 2026-05-17 | 2026-05-17 | 2026-11-23 | 135
| A33330 | Start Production |  |  |  |  | 0 | 21-Jun-25 A
| A28430 | Key Vendor Drawings / Data Approved |  | 2026-02-20 |  |  | 25 | 23-Jun-25 A | 2026-11-23 | 28-Jul-25 A | 2026-02-20 | 2026-11-23
| A28440 | Purchase Order for Major Sub-ordered Materials |  | 2026-02-20 |  |  | 30 | 29-Jul-25 A | 2026-11-23 | 23-Aug-25 A | 2026-02-20 | 2026-11-23
| A28450 | Major Sub-ordered Materials Received by Vendor and Verified |  | 2026-02-20 |  |  | 15 | 25-Aug-25 A | 2026-11-23 | 30-Aug-25 A | 2026-02-20 | 2026-11-23
| A28460 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  | 2026-02-20 |  |  | 9 | 01-Sep-25 A | 2026-11-23 | 06-Sep-25 A | 2026-02-20 | 2026-11-23
| A28470 | Manufacturing / Ex Works (India/UAE) |  | 2026-02-20 |  |  | 38 | 18-Aug-25 A | 2026-11-23 | 15-Sep-25 A | 2026-02-20 | 2026-11-23
| A28480 | Complete Manufacturing & ready for Final Inspection |  | 2026-02-20 |  |  | 15 | 08-Sep-25 A | 2026-11-23 | 20-Sep-25 A | 2026-02-20 | 2026-11-23
| A28490 | Materials Successfully Inspected, Tested / Ex Work |  | 2026-02-20 |  |  | 7 | 22-Sep-25 A | 2026-11-23 | 29-Sep-25 A | 2026-02-20 | 2026-11-23
| A28500 | Delivery of Civil Bulk Material |  | 2026-02-20 |  |  | 19 | 30-Sep-25 A | 2026-11-23 | 06-Oct-25 A | 2026-02-20 | 2026-11-23
| A33350 | Start Production |  |  |  |  | 0 | 18-Sep-25 A
| A28590 | COMPANY Final decision on Compressor Shelter Height |  |  |  |  | 0 |  |  | 15-Dec-25 A
| A28520 | Key Vendor Drawings / Data Approved |  | 2026-02-20 |  |  | 20 | 19-Dec-25 A | 2026-02-23 | 24-Jan-26 A | 2026-02-20 | 2026-02-23
| A28530 | Purchase Order for Major Sub-ordered Materials |  | 2026-02-20 |  |  | 5 | 25-Jan-26 A | 2026-02-23 | 16-Feb-26 A | 2026-02-20 | 2026-02-23
| A28550 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  | 2026-03-12 |  |  | 9 | 17-Feb-26 A | 2026-03-14 | 17-Feb-26 A | 2026-03-12 | 2026-03-14
| A28540 | Major Sub-ordered Materials Received by Vendor and Verified |  | 2026-02-20 |  |  | 14 | 17-Feb-26 A | 2026-02-23 | 2026-03-12 | 2026-03-12 | 2026-03-13 | 1
| A28560 | Manufacturing / Ex Works |  | 2026-03-13 |  |  | 59 | 2026-03-13 | 2026-03-14 | 2026-04-28 | 2026-04-28 | 2026-04-30 | 1
| A28570 | Complete Manufacturing & ready for Final Inspection |  | 2026-04-29 |  |  | 5 | 2026-04-29 | 2026-04-30 | 2026-05-05 | 2026-05-05 | 2026-05-06 | 1
| A28580 | Materials Successfully Inspected, Tested / Ex Work |  | 2026-05-06 |  |  | 5 | 2026-05-06 | 2026-05-07 | 2026-05-12 | 2026-05-12 | 2026-05-13 | 1
| A33340 | Delivery of Structural Steel GF |  | 2026-05-13 |  |  | 6 | 2026-05-13 | 2026-05-14 | 2026-05-17 | 2026-05-17 | 2026-05-18 | 1
| Tubing Material [SS tubes, Connectors, unions, plugs etc.] |  |  | 2026-04-16 |  |  | 106 | 2026-04-16 | 2026-06-02 | 2026-09-13 | 2026-09-13 | 2026-10-30 | 35
| Tubing Material [SS tubes, Connectors, unions, plugs etc] |  |  | 2026-04-16 |  |  | 106 | 2026-04-16 | 2026-06-02 | 2026-09-13 | 2026-09-13 | 2026-10-30 | 35
| A33700 | Start Production |  | 2026-04-16 |  |  | 0 | 2026-04-16 | 2026-06-02 |  |  |  | 58
| A30140 | Key Vendor Drawings / Data Approved |  | 2026-04-17 |  |  | 20 | 2026-04-17 | 2026-06-02 | 2026-05-14 | 2026-05-14 | 2026-06-29 | 32
| A30150 | Purchase Order for Major Sub-ordered Materials |  | 2026-05-14 |  |  | 15 | 2026-05-14 | 2026-06-30 | 2026-06-04 | 2026-06-04 | 2026-07-20 | 32
| A30160 | Major Sub-ordered Materials Received by Vendor and Verified |  | 2026-06-04 |  |  | 15 | 2026-06-04 | 2026-07-21 | 2026-06-25 | 2026-06-25 | 2026-08-10 | 32
| A30170 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  | 2026-06-25 |  |  | 1 | 2026-06-25 | 2026-08-11 | 2026-06-26 | 2026-06-26 | 2026-08-12 | 58
| A30180 | Manufacturing / Ex Works (India/UAE) |  | 2026-06-26 |  |  | 63 | 2026-06-26 | 2026-08-12 | 2026-08-15 | 2026-08-15 | 2026-10-01 | 58
| A30190 | Complete Manufacturing & ready for Final Inspection |  | 2026-08-17 |  |  | 7 | 2026-08-17 | 2026-10-01 | 2026-08-25 | 2026-08-25 | 2026-10-09 | 33
| A30200 | Materials Successfully Inspected, Tested / Ex Work |  | 2026-08-26 |  |  | 7 | 2026-08-26 | 2026-10-12 | 2026-09-03 | 2026-09-03 | 2026-10-20 | 33
| A33710 | Delivery at site - (Tubing Material) |  | 2026-09-04 |  |  | 13 | 2026-09-04 | 2026-10-21 | 2026-09-13 | 2026-09-13 | 2026-10-30 | 59
| Steel Structure Brownfield |  |  | 2026-02-20 |  |  | 362 | 15-Mar-25 A | 2026-03-27 | 2026-04-19 | 2026-04-19 | 2026-09-20 | 110
| Steel Structure - Post TA - BF |  |  | 2026-02-20 |  |  | 163 | 18-Sep-25 A | 2026-07-24 | 2026-04-19 | 2026-04-19 | 2026-09-20 | 110
| A34560 | Start Production |  |  |  |  | 0 | 18-Sep-25 A
| A34570 | Key Vendor Drawings / Data Approved |  | 2026-02-20 |  |  | 20 | 01-Feb-26 A | 2026-07-24 | 06-Feb-26 A | 2026-02-20 | 2026-07-24
| A34580 | Purchase Order for Major Sub-ordered Materials |  | 2026-02-20 |  |  | 14 | 09-Feb-26 A | 2026-07-24 | 13-Feb-26 A | 2026-02-20 | 2026-07-24
| A34590 | Major Sub-ordered Materials Received by Vendor and Verified |  | 2026-02-20 |  |  | 21 | 16-Feb-26 A | 2026-07-24 | 16-Feb-26 A | 2026-02-20 | 2026-07-24
| A34600 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  | 2026-02-20 |  |  | 9 | 17-Feb-26 A | 2026-07-24 | 17-Feb-26 A | 2026-02-20 | 2026-07-24
| A34610 | Manufacturing / Ex Works |  | 2026-02-20 |  |  | 50 | 18-Feb-26 A | 2026-07-24 | 2026-03-31 | 2026-03-31 | 2026-09-02 | 193
| A34620 | Complete Manufacturing & ready for Final Inspection |  | 2026-04-01 |  |  | 5 | 2026-04-01 | 2026-09-02 | 2026-04-07 | 2026-04-07 | 2026-09-08 | 110
| A34630 | Materials Successfully Inspected, Tested / Ex Work |  | 2026-04-08 |  |  | 5 | 2026-04-08 | 2026-09-09 | 2026-04-14 | 2026-04-14 | 2026-09-15 | 110
| A34650 | Delivery of (Steel Structure - PostTA) |  | 2026-04-15 |  |  | 6 | 2026-04-15 | 2026-09-16 | 2026-04-19 | 2026-04-19 | 2026-09-20 | 193
| TA_Steel Structure ( Additional Steel Structure required for BFW) |  |  | 2026-02-20 |  |  | 102 | 15-Mar-25 A | 2026-03-27 | 09-May-25 A | 2026-02-20 | 2026-03-27
| A34490 | Start Production |  |  |  |  | 0 | 15-Mar-25 A
| A27800 | Key Vendor Drawings / Data Approved |  | 2026-02-20 |  |  | 5 | 15-Mar-25 A | 2026-03-27 | 20-Mar-25 A | 2026-02-20 | 2026-03-27
| A27810 | Purchase Order for Major Sub-ordered Materials |  | 2026-02-20 |  |  | 5 | 17-Mar-25 A | 2026-03-27 | 21-Mar-25 A | 2026-02-20 | 2026-03-27
| A27820 | Major Sub-ordered Materials Received by Vendor and Verified |  | 2026-02-20 |  |  | 5 | 22-Mar-25 A | 2026-03-27 | 28-Mar-25 A | 2026-02-20 | 2026-03-27
| A27830 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  | 2026-02-20 |  |  | 1 | 29-Mar-25 A | 2026-03-27 | 04-Apr-25 A | 2026-02-20 | 2026-03-27
| A27840 | Manufacturing / Ex Works (India/UAE) |  | 2026-02-20 |  |  | 56 | 05-Apr-25 A | 2026-03-27 | 11-Apr-25 A | 2026-02-20 | 2026-03-27
| A27850 | Complete Manufacturing & ready for Final Inspection |  | 2026-02-20 |  |  | 2 | 12-Apr-25 A | 2026-03-27 | 18-Apr-25 A | 2026-02-20 | 2026-03-27
| A27860 | Materials Successfully Inspected, Tested / Ex Work |  | 2026-02-20 |  |  | 5 | 19-Apr-25 A | 2026-03-27 | 25-Apr-25 A | 2026-02-20 | 2026-03-27
| A34450 | Delivery at Site by EPC ( Fabricated, Painted & Galvanized TA Steel Structure ) |  | 2026-02-20 |  |  | 5 | 26-Apr-25 A | 2026-03-27 | 09-May-25 A | 2026-02-20 | 2026-03-27
| A34010 | Start Production |  |  |  |  | 0 | 19-Dec-25 A
| A31400 | Key Vendor Drawings / Data Approved |  | 2026-02-20 |  |  | 40 | 20-Feb-26 A | 2026-06-11 | 2026-03-20 | 2026-03-20 | 2026-07-09 | 79
| A31410 | Purchase Order for Major Sub-ordered Materials |  | 2026-03-09 |  |  | 10 | 11-Dec-25 A | 2026-06-29 | 2026-03-20 | 2026-03-20 | 2026-07-09 | 79
| A31420 | Major Sub-ordered Materials Received by Vendor and Verified |  | 2026-03-20 |  |  | 21 | 2026-03-20 | 2026-07-10 | 2026-04-20 | 2026-04-20 | 2026-08-07 | 79
| A31430 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  | 2026-04-20 |  |  | 1 | 2026-04-20 | 2026-08-10 | 2026-04-21 | 2026-04-21 | 2026-08-11 | 139
| A31440 | Manufacturing / Ex Works (India/UAE) |  | 2026-04-21 |  |  | 113 | 2026-04-21 | 2026-08-11 | 2026-07-20 | 2026-07-20 | 2026-11-09 | 139
| A31450 | Complete Manufacturing & ready for Final Inspection |  | 2026-07-20 |  |  | 7 | 2026-07-20 | 2026-11-09 | 2026-07-29 | 2026-07-29 | 2026-11-17 | 79
| A31460 | Materials Successfully Inspected, Tested / Ex Work |  | 2026-07-29 |  |  | 7 | 2026-07-29 | 2026-11-18 | 2026-08-07 | 2026-08-07 | 2026-11-26 | 79
| A34020 | Delivery of Telecom (ACS + CCTV + PAGA) Integration |  | 2026-08-07 |  |  | 18 | 2026-08-07 | 2026-11-27 | 2026-08-21 | 2026-08-21 | 2026-12-10 | 139
| A34030 | Start Production |  |  |  |  | 0 | 12-Dec-25 A
| A31500 | Purchase Order for Major Sub-ordered Materials |  | 2026-04-09 |  |  | 10 | 12-Dec-25 A | 2026-05-27 | 25-Dec-25 A | 2026-04-09 | 2026-05-27
| A31490 | Key Vendor Drawings / Data Approved |  | 2026-02-20 |  |  | 50 | 20-Feb-26 A | 2026-04-08 | 2026-04-09 | 2026-04-09 | 2026-05-26 | 33
| A31510 | Major Sub-ordered Materials Received by Vendor and Verified |  | 2026-04-09 |  |  | 20 | 2026-04-09 | 2026-05-27 | 2026-05-07 | 2026-05-07 | 2026-06-23 | 33
| A31520 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  | 2026-05-07 |  |  | 1 | 2026-05-07 | 2026-06-24 | 2026-05-08 | 2026-05-08 | 2026-06-25 | 59
| A31530 | Manufacturing / Ex Works (India/UAE) |  | 2026-05-08 |  |  | 113 | 2026-05-08 | 2026-06-25 | 2026-08-06 | 2026-08-06 | 2026-09-23 | 59
| A31540 | Complete Manufacturing & ready for Final Inspection |  | 2026-08-06 |  |  | 7 | 2026-08-06 | 2026-09-23 | 2026-08-17 | 2026-08-17 | 2026-10-01 | 33
| A31550 | Materials Successfully Inspected, Tested / Ex Work |  | 2026-08-17 |  |  | 7 | 2026-08-17 | 2026-10-02 | 2026-08-26 | 2026-08-26 | 2026-10-12 | 33
| A34040 | Delivery of ACS |  | 2026-08-26 |  |  | 18 | 2026-08-26 | 2026-10-13 | 2026-09-09 | 2026-09-09 | 2026-10-26 | 59
| A34210 | Start Production |  |  |  |  | 0 | 19-Dec-25 A
| A32310 | Purchase Order for Major Sub-ordered Materials |  | 2026-03-19 |  |  | 10 | 2026-03-19 | 2026-06-10 | 2026-04-02 | 2026-04-02 | 2026-06-23 | 58
| A34220 | Key Vendor Drawings / Data Approved |  | 2026-02-20 |  |  | 30 | 2026-02-20 | 2026-05-13 | 2026-04-02 | 2026-04-02 | 2026-06-23 | 58
| A32320 | Major Sub-ordered Materials Received by Vendor and Verified |  | 2026-04-02 |  |  | 30 | 2026-04-02 | 2026-06-24 | 2026-05-14 | 2026-05-14 | 2026-08-04 | 58
| A32330 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  | 2026-05-14 |  |  | 1 | 2026-05-14 | 2026-08-05 | 2026-05-15 | 2026-05-15 | 2026-08-06 | 103
| A32340 | Manufacturing / Ex Works (India/UAE) |  | 2026-05-15 |  |  | 94 | 2026-05-15 | 2026-08-06 | 2026-07-29 | 2026-07-29 | 2026-10-20 | 103
| A32350 | Complete Manufacturing & ready for Final Inspection |  | 2026-07-29 |  |  | 7 | 2026-07-29 | 2026-10-20 | 2026-08-07 | 2026-08-07 | 2026-10-28 | 58
| A32360 | Materials Successfully Inspected, Tested / Ex Work |  | 2026-08-07 |  |  | 7 | 2026-08-07 | 2026-10-29 | 2026-08-18 | 2026-08-18 | 2026-11-06 | 58
| A34250 | Delivery of CCTV |  | 2026-08-18 |  |  | 9 | 2026-08-18 | 2026-11-09 | 2026-08-25 | 2026-08-25 | 2026-11-15 | 103
| A34050 | Start Production |  |  |  |  | 0 | 19-Dec-25 A
| A31580 | Key Vendor Drawings / Data Approved |  | 2026-02-20 |  |  | 50 | 19-Dec-25 A | 2026-05-22 | 2026-03-20 | 2026-03-20 | 2026-06-19 | 65
| A31590 | Purchase Order for Major Sub-ordered Materials |  | 2026-03-09 |  |  | 10 | 11-Dec-25 A | 2026-06-09 | 2026-03-20 | 2026-03-20 | 2026-06-19 | 65
| A31600 | Major Sub-ordered Materials Received by Vendor and Verified |  | 2026-03-20 |  |  | 21 | 2026-03-20 | 2026-06-22 | 2026-04-20 | 2026-04-20 | 2026-07-20 | 65
| A31610 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  | 2026-04-20 |  |  | 1 | 2026-04-20 | 2026-07-21 | 2026-04-21 | 2026-04-21 | 2026-07-22 | 114
| A31620 | Manufacturing / Ex Works (India/UAE) |  | 2026-04-21 |  |  | 113 | 2026-04-21 | 2026-07-22 | 2026-07-20 | 2026-07-20 | 2026-10-20 | 114
| A31630 | Complete Manufacturing & ready for Final Inspection |  | 2026-07-20 |  |  | 7 | 2026-07-20 | 2026-10-20 | 2026-07-29 | 2026-07-29 | 2026-10-28 | 65
| A31640 | Materials Successfully Inspected, Tested / Ex Work |  | 2026-07-29 |  |  | 7 | 2026-07-29 | 2026-10-29 | 2026-08-07 | 2026-08-07 | 2026-11-06 | 65
| A34060 | Delivery of PAGA + Telephone |  | 2026-08-07 |  |  | 18 | 2026-08-07 | 2026-11-09 | 2026-08-21 | 2026-08-21 | 2026-11-22 | 116
| A34230 | Start Production |  | 2026-05-22 |  |  | 0 | 2026-05-22 | 2026-09-11 |  |  |  | 139
| A32390 | Key Vendor Drawings / Data Approved |  | 2026-05-25 |  |  | 21 | 2026-05-25 | 2026-09-11 | 2026-06-22 | 2026-06-22 | 2026-10-09 | 79
| A32400 | Purchase Order for Major Sub-ordered Materials |  | 2026-06-22 |  |  | 10 | 2026-06-22 | 2026-10-12 | 2026-07-06 | 2026-07-06 | 2026-10-23 | 79
| A32410 | Major Sub-ordered Materials Received by Vendor and Verified |  | 2026-07-06 |  |  | 15 | 2026-07-06 | 2026-10-26 | 2026-07-27 | 2026-07-27 | 2026-11-13 | 79
| A32420 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  | 2026-07-27 |  |  | 1 | 2026-07-27 | 2026-11-15 | 2026-07-28 | 2026-07-28 | 2026-11-16 | 138
| A32430 | Manufacturing / Ex Works (India/UAE) |  | 2026-07-28 |  |  | 44 | 2026-07-28 | 2026-11-16 | 2026-09-01 | 2026-09-01 | 2026-12-21 | 138
| A32440 | Complete Manufacturing & ready for Final Inspection |  | 2026-09-01 |  |  | 5 | 2026-09-01 | 2026-12-21 | 2026-09-08 | 2026-09-08 | 2026-12-25 | 78
| A32450 | Materials Successfully Inspected, Tested / Ex Work |  | 2026-09-08 |  |  | 5 | 2026-09-08 | 2026-12-28 | 2026-09-15 | 2026-09-15 | 2027-01-01 | 78
| A34240 | Delivery of Material in Warehouse Lighting Fixtures |  | 2026-09-15 |  |  | 9 | 2026-09-15 | 2027-01-04 | 2026-09-22 | 2026-09-22 | 2027-01-10 | 138
| A33680 | Start Production |  |  |  |  | 0 | 20-Nov-25 A
| A30050 | Key Vendor Drawings / Data Approved |  | 2026-02-20 |  |  | 30 | 20-Feb-26 A | 2026-05-18 | 2026-03-05 | 2026-03-05 | 2026-05-29 | 61
| A30060 | Purchase Order for Major Sub-ordered Materials |  | 2026-03-05 |  |  | 5 | 2026-03-05 | 2026-06-01 | 2026-03-12 | 2026-03-12 | 2026-06-05 | 61
| A30080 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  | 2026-03-12 |  |  | 1 | 2026-03-12 | 2026-06-07 | 2026-03-13 | 2026-03-13 | 2026-06-08 | 108
| A30070 | Major Sub-ordered Materials Received by Vendor and Verified |  | 2026-03-12 |  |  | 30 | 2026-03-12 | 2026-06-05 | 2026-04-23 | 2026-04-23 | 2026-07-17 | 61
| A30090 | Manufacturing / Ex Works (India/UAE) |  | 2026-03-13 |  |  | 125 | 2026-03-13 | 2026-06-08 | 2026-06-21 | 2026-06-21 | 2026-09-16 | 108
| A30100 | Complete Manufacturing & ready for Final Inspection |  | 2026-06-22 |  |  | 7 | 2026-06-22 | 2026-09-16 | 2026-06-30 | 2026-06-30 | 2026-09-24 | 62
| A30110 | Materials Successfully Inspected, Tested / Ex Work |  | 2026-07-01 |  |  | 7 | 2026-07-01 | 2026-09-25 | 2026-07-09 | 2026-07-09 | 2026-10-05 | 62
| A33690 | Delivery at site warehouse for Manual Valves (Gate 9 Nos, Check 6 Nos, Globe Valves 64 Nos) |  | 2026-07-10 |  |  | 26 | 2026-07-10 | 2026-10-06 | 2026-07-30 | 2026-07-30 | 2026-10-26 | 110
| A34500 | Start Production |  |  |  |  | 0 | 01-Sep-25 A
| A27990 | Purchase Order for Major Sub-ordered Materials |  | 2026-02-20 |  |  | 5 | 02-Sep-25 A | 2026-04-22 | 08-Sep-25 A | 2026-02-20 | 2026-04-22
| A28000 | Major Sub-ordered Materials Received by Vendor and Verified |  | 2026-02-20 |  |  | 15 | 22-Oct-25 A | 2026-04-22 | 31-Oct-25 A | 2026-02-20 | 2026-04-22
| A28010 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  | 2026-02-20 |  |  | 9 | 03-Nov-25 A | 2026-04-22 | 25-Dec-25 A | 2026-02-20 | 2026-04-22
| A28020 | Manufacturing / Ex Works (India/UAE) |  | 2026-02-20 |  |  | 100 | 26-Dec-25 A | 2026-04-22 | 18-Jan-26 A | 2026-02-20 | 2026-04-22
| A28030 | Complete Manufacturing & ready for Final Inspection |  | 2026-02-20 |  |  | 7 | 26-Jan-26 A | 2026-04-22 | 30-Jan-26 A | 2026-02-20 | 2026-04-22
| A28040 | Materials Successfully Inspected, Tested / Ex Work |  | 2026-02-20 |  |  | 10 | 02-Feb-26 A | 2026-04-22 | 06-Feb-26 A | 2026-02-20 | 2026-04-22
| 84.D50 | Delivery of Piping Material in Warehouse (1st Lot, GF) |  | 2026-02-20 |  |  | 13 | 10-Feb-26 A | 2026-04-22 | 2026-03-06 | 2026-03-06 | 2026-05-06 | 76
| A34510 | Start Production |  | 2026-02-20 |  |  | 0 | 2026-02-20 | 2026-03-30 |  |  |  | 48
| A28070 | Key Vendor Drawings / Data Approved |  | 2026-02-20 |  |  | 20 | 2026-02-20 | 2026-03-30 | 2026-03-19 | 2026-03-19 | 2026-04-24 | 26
| A28080 | Purchase Order for Major Sub-ordered Materials |  | 2026-03-19 |  |  | 5 | 2026-03-19 | 2026-04-27 | 2026-03-26 | 2026-03-26 | 2026-05-01 | 26
| A28090 | Major Sub-ordered Materials Received by Vendor and Verified |  | 2026-03-26 |  |  | 15 | 2026-03-26 | 2026-05-04 | 2026-04-16 | 2026-04-16 | 2026-05-22 | 26
| A28100 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  | 2026-04-16 |  |  | 9 | 2026-04-16 | 2026-05-25 | 2026-04-23 | 2026-04-23 | 2026-06-01 | 48
| A28110 | Manufacturing / Ex Works |  | 2026-04-23 |  |  | 70 | 2026-04-23 | 2026-06-01 | 2026-06-18 | 2026-06-18 | 2026-07-27 | 48
| A28120 | Complete Manufacturing & ready for Final Inspection |  | 2026-06-18 |  |  | 10 | 2026-06-18 | 2026-07-27 | 2026-07-02 | 2026-07-02 | 2026-08-07 | 26
| A28130 | Materials Successfully Inspected, Tested / Ex Work |  | 2026-07-02 |  |  | 5 | 2026-07-02 | 2026-08-10 | 2026-07-09 | 2026-07-09 | 2026-08-14 | 26
| A34520 | Delivery of Material in Warehouse ( Piping Swing Hangers - PostTA) |  | 2026-07-09 |  |  | 9 | 2026-07-09 | 2026-09-02 | 2026-07-16 | 2026-07-16 | 2026-09-08 | 68
| A33360 | Start Production |  |  |  |  | 0 | 01-Sep-25 A
| A28620 | Purchase Order for Major Sub-ordered Materials |  | 2026-02-20 |  |  | 5 | 02-Sep-25 A | 2026-04-20 | 08-Sep-25 A | 2026-02-20 | 2026-04-20
| A28630 | Major Sub-ordered Materials Received by Vendor and Verified |  | 2026-02-20 |  |  | 10 | 03-Sep-25 A | 2026-04-20 | 15-Sep-25 A | 2026-02-20 | 2026-04-20
| A28640 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  | 2026-02-20 |  |  | 9 | 19-Dec-25 A | 2026-04-20 | 25-Dec-25 A | 2026-02-20 | 2026-04-20
| A28650 | Manufacturing / Ex Works (India/UAE) |  | 2026-02-20 |  |  | 75 | 26-Dec-25 A | 2026-04-20 | 18-Jan-26 A | 2026-02-20 | 2026-04-20
| A28660 | Complete Manufacturing & ready for Final Inspection |  | 2026-02-20 |  |  | 2 | 19-Jan-26 A | 2026-04-20 | 23-Jan-26 A | 2026-02-20 | 2026-04-20
| A28670 | Materials Successfully Inspected, Tested / Ex Work |  | 2026-02-20 |  |  | 5 | 19-Jan-26 A | 2026-04-20 | 23-Jan-26 A | 2026-02-20 | 2026-04-20
| 84.D40 | Delivery of Piping Material in Warehouse (1st Lot, GF) |  | 2026-02-20 |  |  | 9 | 26-Jan-26 A | 2026-04-20 | 31-Jan-26 A | 2026-02-20 | 2026-04-20
| A33370 | Start Production |  |  |  |  | 0 | 26-Dec-25 A
| A28710 | Purchase Order for Major Sub-ordered Materials |  | 2026-02-20 |  |  | 10 | 28-Dec-25 A | 2026-05-19 | 02-Jan-26 A | 2026-02-20 | 2026-05-19
| A28720 | Major Sub-ordered Materials Received by Vendor and Verified |  | 2026-02-20 |  |  | 15 | 26-Dec-25 A | 2026-05-19 | 09-Jan-26 A | 2026-02-20 | 2026-05-19
| A28730 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  | 2026-02-20 |  |  | 9 | 09-Jan-26 A | 2026-05-19 | 16-Jan-26 A | 2026-02-20 | 2026-05-19
| A28740 | Manufacturing / Ex Works (India/UAE) |  | 2026-02-20 |  |  | 75 | 15-Jan-26 A | 2026-05-19 | 2026-03-21 | 2026-03-21 | 2026-06-18 | 110
| A28750 | Complete Manufacturing & ready for Final Inspection |  | 2026-03-23 |  |  | 5 | 2026-03-23 | 2026-06-18 | 2026-03-27 | 2026-03-27 | 2026-06-24 | 63
| A28760 | Materials Successfully Inspected, Tested / Ex Work |  | 2026-03-30 |  |  | 5 | 2026-03-30 | 2026-06-25 | 2026-04-03 | 2026-04-03 | 2026-07-01 | 63
| 85.D10 | Delivery of Piping Material in Warehouse (2nd Lot) |  | 2026-04-04 |  |  | 18 | 2026-04-04 | 2026-07-02 | 2026-04-17 | 2026-04-17 | 2026-07-15 | 111
| A33380 | Start Production |  | 2026-04-22 |  |  | 0 | 2026-04-22 | 2026-05-14 |  |  |  | 27
| A28800 | Purchase Order for Major Sub-ordered Materials |  | 2026-04-22 |  |  | 5 | 2026-04-22 | 2026-05-14 | 2026-04-29 | 2026-04-29 | 2026-05-20 | 15
| A28810 | Major Sub-ordered Materials Received by Vendor and Verified |  | 2026-04-29 |  |  | 15 | 2026-04-29 | 2026-05-21 | 2026-05-20 | 2026-05-20 | 2026-06-10 | 15
| A28820 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  | 2026-05-20 |  |  | 4 | 2026-05-20 | 2026-06-11 | 2026-05-23 | 2026-05-23 | 2026-06-14 | 27
| A28830 | Manufacturing / Ex Works (India/UAE) |  | 2026-05-23 |  |  | 75 | 2026-05-23 | 2026-06-14 | 2026-07-22 | 2026-07-22 | 2026-08-13 | 27
| A28840 | Complete Manufacturing & ready for Final Inspection |  | 2026-07-22 |  |  | 5 | 2026-07-22 | 2026-08-13 | 2026-07-29 | 2026-07-29 | 2026-08-19 | 15
| A28850 | Materials Successfully Inspected, Tested / Ex Work |  | 2026-07-29 |  |  | 7 | 2026-07-29 | 2026-08-20 | 2026-08-07 | 2026-08-07 | 2026-08-28 | 15
| A28860 | Delivery of Piping Material in Warehouse (Final Lot) |  | 2026-08-07 |  |  | 18 | 2026-08-07 | 2026-08-29 | 2026-08-21 | 2026-08-21 | 2026-09-11 | 27
| A33400 | Start Production |  | 2026-07-24 |  |  | 0 | 2026-07-24 | 2027-05-17 |  |  |  | 370
| A28970 | Key Vendor Drawings / Data Approved |  | 2026-07-24 |  |  | 5 | 2026-07-24 | 2027-05-17 | 2026-07-31 | 2026-07-31 | 2027-05-21 | 210
| A28980 | Purchase Order for Major Sub-ordered Materials |  | 2026-07-31 |  |  | 5 | 2026-07-31 | 2027-05-24 | 2026-08-07 | 2026-08-07 | 2027-05-28 | 210
| A28990 | Major Sub-ordered Materials Received by Vendor and Verified |  | 2026-08-07 |  |  | 5 | 2026-08-07 | 2027-05-31 | 2026-08-14 | 2026-08-14 | 2027-06-04 | 210
| A29000 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  | 2026-08-14 |  |  | 6 | 2026-08-14 | 2027-06-06 | 2026-08-19 | 2026-08-19 | 2027-06-11 | 369
| A29010 | Manufacturing / Ex Works (India/UAE) |  | 2026-08-19 |  |  | 13 | 2026-08-19 | 2027-06-11 | 2026-08-29 | 2026-08-29 | 2027-06-21 | 369
| A29020 | Complete Manufacturing & ready for Final Inspection |  | 2026-08-31 |  |  | 5 | 2026-08-31 | 2027-06-21 | 2026-09-04 | 2026-09-04 | 2027-06-25 | 210
| A29030 | Materials Successfully Inspected, Tested / Ex Work |  | 2026-09-07 |  |  | 6 | 2026-09-07 | 2027-06-28 | 2026-09-14 | 2026-09-14 | 2027-07-05 | 210
| A29040 | Delivery of Pipng Supports |  | 2026-09-15 |  |  | 19 | 2026-09-15 | 2027-07-06 | 2026-09-29 | 2026-09-29 | 2027-07-20 | 368
| A33390 | Start Production |  | 2026-02-20 |  |  | 0 | 2026-02-20 | 2026-04-09 |  |  |  | 60
| A28880 | Key Vendor Drawings / Data Approved |  | 2026-02-20 |  |  | 20 | 2026-02-20 | 2026-04-09 | 2026-03-19 | 2026-03-19 | 2026-05-06 | 34
| A28890 | Purchase Order for Major Sub-ordered Materials |  | 2026-03-19 |  |  | 5 | 2026-03-19 | 2026-05-07 | 2026-03-26 | 2026-03-26 | 2026-05-13 | 34
| A28900 | Major Sub-ordered Materials Received by Vendor and Verified |  | 2026-03-26 |  |  | 15 | 2026-03-26 | 2026-05-14 | 2026-04-16 | 2026-04-16 | 2026-06-03 | 34
| A28910 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  | 2026-04-16 |  |  | 1 | 2026-04-16 | 2026-06-04 | 2026-04-17 | 2026-04-17 | 2026-06-05 | 60
| A28920 | Manufacturing / Ex Works |  | 2026-04-17 |  |  | 75 | 2026-04-17 | 2026-06-05 | 2026-06-16 | 2026-06-16 | 2026-08-04 | 60
| A28930 | Complete Manufacturing & ready for Final Inspection |  | 2026-06-16 |  |  | 5 | 2026-06-16 | 2026-08-04 | 2026-06-23 | 2026-06-23 | 2026-08-10 | 34
| A28940 | Materials Successfully Inspected, Tested / Ex Work |  | 2026-06-23 |  |  | 7 | 2026-06-23 | 2026-08-11 | 2026-07-02 | 2026-07-02 | 2026-08-19 | 34
| A28950 | Delivery of HDPE Piping GF (Fire Water Lines) |  | 2026-07-02 |  |  | 18 | 2026-07-02 | 2026-08-20 | 2026-07-16 | 2026-07-16 | 2026-09-02 | 60
| A33720 | Start Production |  | 2026-04-01 |  |  | 0 | 2026-04-01 | 2026-06-02 |  |  |  | 77
| A30230 | Key Vendor Drawings / Data Approved |  | 2026-04-01 |  |  | 15 | 2026-04-01 | 2026-06-02 | 2026-04-22 | 2026-04-22 | 2026-06-22 | 44
| A30240 | Purchase Order for Major Sub-ordered Materials |  | 2026-04-22 |  |  | 5 | 2026-04-22 | 2026-06-23 | 2026-04-29 | 2026-04-29 | 2026-06-29 | 44
| A30250 | Major Sub-ordered Materials Received by Vendor and Verified |  | 2026-04-29 |  |  | 15 | 2026-04-29 | 2026-06-30 | 2026-05-20 | 2026-05-20 | 2026-07-20 | 44
| A30260 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  | 2026-05-20 |  |  | 1 | 2026-05-20 | 2026-07-21 | 2026-05-21 | 2026-05-21 | 2026-07-22 | 77
| A30270 | Manufacturing / Ex Works (India/UAE) |  | 2026-05-21 |  |  | 94 | 2026-05-21 | 2026-07-22 | 2026-08-04 | 2026-08-04 | 2026-10-05 | 77
| A30280 | Complete Manufacturing & ready for Final Inspection |  | 2026-08-04 |  |  | 5 | 2026-08-04 | 2026-10-05 | 2026-08-11 | 2026-08-11 | 2026-10-09 | 44
| A30290 | Materials Successfully Inspected, Tested / Ex Work |  | 2026-08-11 |  |  | 5 | 2026-08-11 | 2026-10-12 | 2026-08-18 | 2026-08-18 | 2026-10-16 | 44
| A30300 | Delivery of Orifice Flanges |  | 2026-08-18 |  |  | 18 | 2026-08-18 | 2026-10-18 | 2026-09-01 | 2026-09-01 | 2026-10-31 | 76
| A33730 | Start Production |  | 2026-03-27 |  |  | 0 | 2026-03-27 | 2026-05-25 |  |  |  | 73
| A30320 | Key Vendor Drawings / Data Approved |  | 2026-03-30 |  |  | 20 | 2026-03-30 | 2026-05-25 | 2026-04-24 | 2026-04-24 | 2026-06-19 | 40
| A30330 | Purchase Order for Major Sub-ordered Materials |  | 2026-04-24 |  |  | 5 | 2026-04-24 | 2026-06-22 | 2026-05-01 | 2026-05-01 | 2026-06-26 | 40
| A30340 | Major Sub-ordered Materials Received by Vendor and Verified |  | 2026-05-01 |  |  | 20 | 2026-05-01 | 2026-06-29 | 2026-05-29 | 2026-05-29 | 2026-07-24 | 40
| A30350 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  | 2026-05-29 |  |  | 1 | 2026-05-29 | 2026-07-26 | 2026-05-30 | 2026-05-30 | 2026-07-27 | 72
| A30360 | Manufacturing / Ex Works (India/UAE) |  | 2026-05-30 |  |  | 70 | 2026-05-30 | 2026-07-27 | 2026-07-25 | 2026-07-25 | 2026-09-21 | 72
| A30370 | Complete Manufacturing & ready for Final Inspection |  | 2026-07-27 |  |  | 5 | 2026-07-27 | 2026-09-21 | 2026-07-31 | 2026-07-31 | 2026-09-25 | 40
| A30380 | Materials Successfully Inspected, Tested / Ex Work |  | 2026-08-03 |  |  | 5 | 2026-08-03 | 2026-09-28 | 2026-08-07 | 2026-08-07 | 2026-10-02 | 40
| A30390 | Delivery of Strainer/Filters Flanges |  | 2026-08-08 |  |  | 35 | 2026-08-08 | 2026-10-04 | 2026-09-04 | 2026-09-04 | 2026-10-31 | 71
| A33510 | Start Production |  |  |  |  | 0 | 20-Dec-25 A
| A29510 | Key Vendor Drawings / Data Approved |  | 2026-02-20 |  |  | 20 | 2026-02-20 | 2026-03-27 | 2026-03-19 | 2026-03-19 | 2026-04-23 | 25
| A29520 | Purchase Order for Major Sub-ordered Materials |  | 2026-03-19 |  |  | 20 | 2026-03-19 | 2026-04-24 | 2026-04-16 | 2026-04-16 | 2026-05-21 | 25
| A29530 | Major Sub-ordered Materials Received by Vendor and Verified |  | 2026-04-16 |  |  | 20 | 2026-04-16 | 2026-05-22 | 2026-05-14 | 2026-05-14 | 2026-06-18 | 25
| A29540 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  | 2026-05-14 |  |  | 1 | 2026-05-14 | 2026-06-19 | 2026-05-15 | 2026-05-15 | 2026-06-20 | 44
| A29550 | Manufacturing / Ex Works (India/UAE) |  | 2026-05-15 |  |  | 75 | 2026-05-15 | 2026-06-20 | 2026-07-14 | 2026-07-14 | 2026-08-19 | 44
| A29560 | Complete Manufacturing & ready for Final Inspection |  | 2026-07-14 |  |  | 15 | 2026-07-14 | 2026-08-19 | 2026-08-04 | 2026-08-04 | 2026-09-08 | 25
| A29570 | Materials Successfully Inspected, Tested / Ex Work |  | 2026-08-04 |  |  | 15 | 2026-08-04 | 2026-09-09 | 2026-08-25 | 2026-08-25 | 2026-09-29 | 25
| A33520 | Delivery of Material in Warehouse for PT,TT & DPT |  | 2026-08-25 |  |  | 10 | 2026-08-25 | 2026-09-30 | 2026-09-02 | 2026-09-02 | 2026-10-07 | 44
| A34340 | Start Production |  | 2026-03-25 |  |  | 0 | 2026-03-25 | 2026-06-03 |  |  |  | 87
| A32840 | Key Vendor Drawings / Data Approved |  | 2026-03-25 |  |  | 21 | 2026-03-25 | 2026-06-03 | 2026-04-23 | 2026-04-23 | 2026-07-01 | 50
| A32850 | Purchase Order for Major Sub-ordered Materials |  | 2026-04-23 |  |  | 15 | 2026-04-23 | 2026-07-02 | 2026-05-14 | 2026-05-14 | 2026-07-22 | 50
| A32860 | Major Sub-ordered Materials Received by Vendor and Verified |  | 2026-05-14 |  |  | 15 | 2026-05-14 | 2026-07-23 | 2026-06-04 | 2026-06-04 | 2026-08-12 | 50
| A32870 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  | 2026-06-04 |  |  | 9 | 2026-06-04 | 2026-08-13 | 2026-06-11 | 2026-06-11 | 2026-08-20 | 87
| A32880 | Manufacturing / Ex Works (India/UAE) |  | 2026-06-11 |  |  | 50 | 2026-06-11 | 2026-08-20 | 2026-07-21 | 2026-07-21 | 2026-09-29 | 87
| A32890 | Complete Manufacturing & ready for Final Inspection |  | 2026-07-21 |  |  | 7 | 2026-07-21 | 2026-09-29 | 2026-07-30 | 2026-07-30 | 2026-10-07 | 50
| A32900 | Materials Successfully Inspected, Tested / Ex Work |  | 2026-07-30 |  |  | 7 | 2026-07-30 | 2026-10-08 | 2026-08-10 | 2026-08-10 | 2026-10-16 | 50
| A34350 | Delivery of Magnetic Level Gauges, PG, TG, PDG |  | 2026-08-10 |  |  | 18 | 2026-08-10 | 2026-10-17 | 2026-08-24 | 2026-08-24 | 2026-10-30 | 85
| Analyzers |  |  | 2026-02-20 |  |  | 183 | 24-May-25 A | 2026-11-28 | 12-Jul-25 A | 2026-02-20 | 2026-11-28
| A57650 | Start Production |  |  |  |  | 0 | 24-May-25 A
| A57660 | Key Vendor Drawings / Data Approved |  | 2026-02-20 |  |  | 30 | 25-May-25 A | 2026-11-28 | 31-May-25 A | 2026-02-20 | 2026-11-28
| A57670 | Purchase Order for Major Sub-ordered Materials |  | 2026-02-20 |  |  | 15 | 01-Jun-25 A | 2026-11-28 | 07-Jun-25 A | 2026-02-20 | 2026-11-28
| A57680 | Major Sub-ordered Materials Received by Vendor and Verified |  | 2026-02-20 |  |  | 30 | 07-Jun-25 A | 2026-11-28 | 14-Jun-25 A | 2026-02-20 | 2026-11-28
| A57690 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  | 2026-02-20 |  |  | 1 | 15-Jun-25 A | 2026-11-28 | 21-Jun-25 A | 2026-02-20 | 2026-11-28
| A57700 | Manufacturing / Ex Works (India/UAE) |  | 2026-02-20 |  |  | 138 | 22-Jun-25 A | 2026-11-28 | 28-Jun-25 A | 2026-02-20 | 2026-11-28
| A57710 | Complete Manufacturing & ready for Final Inspection |  | 2026-02-20 |  |  | 7 | 29-Jun-25 A | 2026-11-28 | 05-Jul-25 A | 2026-02-20 | 2026-11-28
| A57720 | Materials Successfully Inspected, Tested / Ex Work |  | 2026-02-20 |  |  | 7 | 29-Jun-25 A | 2026-11-28 | 05-Jul-25 A | 2026-02-20 | 2026-11-28
| A57730 | Delivery of Material in Warehouse for Analyzer |  | 2026-02-20 |  |  | 26 | 06-Jul-25 A | 2026-11-28 | 12-Jul-25 A | 2026-02-20 | 2026-11-28
| A57900 | Start Production |  | 2026-02-20 |  |  | 0 | 2026-02-20 | 2026-04-30 |  |  |  | 86
| A57830 | Key Vendor Drawings / Data Approved |  | 2026-02-20 |  |  | 21 | 2026-02-20 | 2026-04-30 | 2026-03-20 | 2026-03-20 | 2026-05-28 | 49
| A57850 | Purchase Order for Major Sub-ordered Materials |  | 2026-02-27 |  |  | 15 | 11-Dec-25 A | 2026-05-08 | 2026-03-20 | 2026-03-20 | 2026-05-28 | 49
| A57860 | Major Sub-ordered Materials Received by Vendor and Verified |  | 2026-03-20 |  |  | 21 | 2026-03-20 | 2026-05-29 | 2026-04-20 | 2026-04-20 | 2026-06-26 | 49
| A57870 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  | 2026-04-20 |  |  | 9 | 2026-04-20 | 2026-06-27 | 2026-04-27 | 2026-04-27 | 2026-07-04 | 84
| A57840 | Manufacturing / Ex Works (India/UAE) |  | 2026-04-27 |  |  | 113 | 2026-04-27 | 2026-07-04 | 2026-07-26 | 2026-07-26 | 2026-10-02 | 84
| A57880 | Complete Manufacturing & ready for Final Inspection |  | 2026-07-27 |  |  | 7 | 2026-07-27 | 2026-10-02 | 2026-08-04 | 2026-08-04 | 2026-10-12 | 49
| A57890 | Materials Successfully Inspected, Tested / Ex Work |  | 2026-08-05 |  |  | 7 | 2026-08-05 | 2026-10-13 | 2026-08-13 | 2026-08-13 | 2026-10-21 | 49
| A57910 | Delivery of Material in Warehouse for Flow Elements Venturi |  | 2026-08-14 |  |  | 18 | 2026-08-14 | 2026-10-22 | 2026-08-27 | 2026-08-27 | 2026-11-04 | 86
| A57740 | Start Production |  |  |  |  | 0 | 18-Dec-25 A
| A57750 | Key Vendor Drawings / Data Approved |  | 2026-02-20 |  |  | 30 | 18-Dec-25 A | 2026-07-03 | 08-Jan-26 A | 2026-02-20 | 2026-07-03
| A57760 | Purchase Order for Major Sub-ordered Materials |  | 2026-02-20 |  |  | 15 | 09-Jan-26 A | 2026-07-03 | 22-Jan-26 A | 2026-02-20 | 2026-07-03
| A57770 | Major Sub-ordered Materials Received by Vendor and Verified |  | 2026-02-20 |  |  | 50 | 23-Jan-26 A | 2026-07-03 | 31-Jan-26 A | 2026-02-20 | 2026-07-03
| A57780 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  | 2026-02-20 |  |  | 6 | 01-Feb-26 A | 2026-07-03 | 2026-02-24 | 2026-02-24 | 2026-07-08 | 166
| A57790 | Manufacturing / Ex Works (India/UAE) |  | 2026-03-25 |  |  | 113 | 2026-03-25 | 2026-07-08 | 2026-06-23 | 2026-06-23 | 2026-10-06 | 131
| A57800 | Complete Manufacturing & ready for Final Inspection |  | 2026-06-23 |  |  | 7 | 2026-06-23 | 2026-10-06 | 2026-07-02 | 2026-07-02 | 2026-10-14 | 75
| A57810 | Materials Successfully Inspected, Tested / Ex Work |  | 2026-07-02 |  |  | 7 | 2026-07-02 | 2026-10-15 | 2026-07-13 | 2026-07-13 | 2026-10-23 | 75
| A57820 | Delivery of Material in Warehouse for Flow Elements Orifice |  | 2026-07-13 |  |  | 15 | 2026-07-13 | 2026-10-24 | 2026-07-25 | 2026-07-25 | 2026-11-04 | 128
| A33490 | Start Production |  | 2026-02-26 |  |  | 0 | 2026-02-26 | 2026-03-12 |  |  |  | 17
| A29420 | Key Vendor Drawings / Data Approved |  | 2026-02-27 |  |  | 40 | 2026-02-27 | 2026-03-12 | 2026-04-23 | 2026-04-23 | 2026-05-06 | 9
| A29430 | Purchase Order for Major Sub-ordered Materials |  | 2026-04-23 |  |  | 7 | 2026-04-23 | 2026-05-07 | 2026-05-04 | 2026-05-04 | 2026-05-15 | 9
| A29440 | Major Sub-ordered Materials Received by Vendor and Verified |  | 2026-05-04 |  |  | 30 | 2026-05-04 | 2026-05-18 | 2026-06-15 | 2026-06-15 | 2026-06-26 | 9
| A29450 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  | 2026-06-15 |  |  | 1 | 2026-06-15 | 2026-06-28 | 2026-06-16 | 2026-06-16 | 2026-06-29 | 15
| A29460 | Manufacturing / Ex Works (India/UAE) |  | 2026-06-16 |  |  | 75 | 2026-06-16 | 2026-06-29 | 2026-08-15 | 2026-08-15 | 2026-08-28 | 15
| A29470 | Complete Manufacturing & ready for Final Inspection |  | 2026-08-17 |  |  | 7 | 2026-08-17 | 2026-08-28 | 2026-08-25 | 2026-08-25 | 2026-09-07 | 9
| A29480 | Materials Successfully Inspected, Tested / Ex Work |  | 2026-08-26 |  |  | 7 | 2026-08-26 | 2026-09-08 | 2026-09-03 | 2026-09-03 | 2026-09-16 | 9
| A33500 | Delivery of Material in Warehouse for Cable Tray and Instrument Junction Box |  | 2026-09-04 |  |  | 26 | 2026-09-04 | 2026-09-17 | 2026-09-24 | 2026-09-24 | 2026-10-07 | 16
| A34320 | Start Production |  |  |  |  | 0 | 18-Aug-25 A
| A32750 | Key Vendor Drawings / Data Approved |  | 2026-02-20 |  |  | 20 | 21-Nov-25 A | 2026-03-19 | 10-Dec-25 A | 2026-02-20 | 2026-03-19
| A32760 | Purchase Order for Major Sub-ordered Materials |  | 2026-02-20 |  |  | 15 | 11-Dec-25 A | 2026-08-14 | 19-Dec-25 A | 2026-02-20 | 2026-08-14
| A32770 | Major Sub-ordered Materials Received by Vendor and Verified |  | 2026-02-20 |  |  | 30 | 19-Dec-25 A | 2026-08-14 | 26-Dec-25 A | 2026-02-20 | 2026-08-14
| A32780 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  | 2026-02-20 |  |  | 1 | 25-Dec-25 A | 2026-08-14 | 16-Jan-26 A | 2026-02-20 | 2026-08-14
| A32790 | Manufacturing / Ex Works (India/UAE) |  | 2026-02-20 |  |  | 125 | 25-Dec-25 A | 2026-08-14 | 23-Jan-26 A | 2026-02-20 | 2026-08-14
| A32800 | Complete Manufacturing & ready for Final Inspection |  | 2026-02-20 |  |  | 7 | 2026-02-20 | 2026-08-14 | 2026-03-02 | 2026-03-02 | 2026-08-24 | 125
| A32810 | Materials Successfully Inspected, Tested / Ex Work |  | 2026-03-03 |  |  | 7 | 2026-03-03 | 2026-08-25 | 2026-03-11 | 2026-03-11 | 2026-09-02 | 125
| A34330 | Delivery of Fibre Optic Cable |  | 2026-03-12 |  |  | 18 | 2026-03-12 | 2026-09-03 | 2026-03-25 | 2026-03-25 | 2026-09-16 | 219
| A33570 | Start Production |  | 2026-02-26 |  |  | 0 | 2026-02-26 | 2026-04-01 |  |  |  | 42
| A29780 | Key Vendor Drawings / Data Approved |  | 2026-02-27 |  |  | 21 | 2026-02-27 | 2026-04-01 | 2026-03-27 | 2026-03-27 | 2026-04-29 | 23
| A29790 | Purchase Order for Major Sub-ordered Materials |  | 2026-03-27 |  |  | 10 | 2026-03-27 | 2026-04-30 | 2026-04-10 | 2026-04-10 | 2026-05-13 | 23
| A29800 | Major Sub-ordered Materials Received by Vendor and Verified |  | 2026-04-10 |  |  | 21 | 2026-04-10 | 2026-05-14 | 2026-05-11 | 2026-05-11 | 2026-06-11 | 23
| A29810 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  | 2026-05-11 |  |  | 9 | 2026-05-11 | 2026-06-12 | 2026-05-18 | 2026-05-18 | 2026-06-19 | 39
| A29820 | Manufacturing / Ex Works (India/UAE) |  | 2026-05-18 |  |  | 88 | 2026-05-18 | 2026-06-19 | 2026-07-27 | 2026-07-27 | 2026-08-28 | 39
| A29830 | Complete Manufacturing & ready for Final Inspection |  | 2026-07-27 |  |  | 7 | 2026-07-27 | 2026-08-28 | 2026-08-05 | 2026-08-05 | 2026-09-07 | 23
| A29840 | Materials Successfully Inspected, Tested / Ex Work |  | 2026-08-05 |  |  | 7 | 2026-08-05 | 2026-09-08 | 2026-08-14 | 2026-08-14 | 2026-09-16 | 23
| A33580 | Delivery of Material in Warehouse for Magnetic Level Gauge |  | 2026-08-14 |  |  | 26 | 2026-08-14 | 2026-09-17 | 2026-09-04 | 2026-09-04 | 2026-10-07 | 41
| Instrument Bulk Materia l(Single & Multicore = Approx. 78,130 Mtr, FO Cables JB & Cable Trays)) |  |  | 2026-02-20 |  |  | 111 | 11-Dec-25 A | 2026-07-13 | 2026-05-22 | 2026-05-22 | 2026-10-09 | 100
| A34470 | Start Production |  | 2026-02-20 |  |  | 0 | 2026-02-20 | 2026-07-13 |  |  |  | 179
| A27890 | Key Vendor Drawings / Data Approved |  | 2026-02-20 |  |  | 20 | 2026-02-20 | 2026-07-13 | 2026-03-19 | 2026-03-19 | 2026-08-07 | 101
| A27900 | Purchase Order for Major Sub-ordered Materials |  | 2026-03-12 |  |  | 5 | 11-Dec-25 A | 2026-08-03 | 2026-03-19 | 2026-03-19 | 2026-08-07 | 101
| A27910 | Major Sub-ordered Materials Received by Vendor and Verified |  | 2026-03-19 |  |  | 5 | 2026-03-19 | 2026-08-10 | 2026-03-26 | 2026-03-26 | 2026-08-14 | 101
| A27920 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  | 2026-03-26 |  |  | 1 | 2026-03-26 | 2026-08-16 | 2026-03-27 | 2026-03-27 | 2026-08-17 | 178
| A27930 | Manufacturing / Ex Works (India/UAE) |  | 2026-03-27 |  |  | 26 | 2026-03-27 | 2026-08-17 | 2026-04-17 | 2026-04-17 | 2026-09-07 | 178
| A27940 | Complete Manufacturing & ready for Final Inspection |  | 2026-04-17 |  |  | 5 | 2026-04-17 | 2026-09-07 | 2026-04-24 | 2026-04-24 | 2026-09-11 | 100
| A27950 | Materials Successfully Inspected, Tested / Ex Work |  | 2026-04-24 |  |  | 5 | 2026-04-24 | 2026-09-14 | 2026-05-01 | 2026-05-01 | 2026-09-18 | 100
| A34460 | Delivery of Material in Warehouse Instrument Bulk (Post TA) |  | 2026-05-01 |  |  | 26 | 2026-05-01 | 2026-09-19 | 2026-05-22 | 2026-05-22 | 2026-10-09 | 175
| A33310 | Start Production |  |  |  |  | 0 | 05-Nov-25 A
| A28340 | Key Vendor Drawings / Data Approved |  | 2026-02-20 |  |  | 20 | 24-Jan-26 A | 2026-05-22 | 30-Jan-26 A | 2026-02-20 | 2026-05-22
| A28350 | Purchase Order for Major Sub-ordered Materials |  | 2026-02-20 |  |  | 30 | 31-Jan-26 A | 2026-05-22 | 12-Feb-26 A | 2026-02-20 | 2026-05-22
| A28360 | Major Sub-ordered Materials Received by Vendor and Verified |  | 2026-02-20 |  |  | 45 | 13-Feb-26 A | 2026-05-22 | 2026-03-10 | 2026-03-10 | 2026-06-09 | 65
| A28370 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  | 2026-03-11 |  |  | 9 | 2026-03-11 | 2026-06-10 | 2026-03-17 | 2026-03-17 | 2026-06-17 | 114
| A28380 | Manufacturing / Ex Works (India/UAE) |  | 2026-03-18 |  |  | 113 | 2026-03-18 | 2026-06-17 | 2026-06-15 | 2026-06-15 | 2026-09-15 | 114
| A28390 | Complete Manufacturing & ready for Final Inspection |  | 2026-06-16 |  |  | 7 | 2026-06-16 | 2026-09-15 | 2026-06-24 | 2026-06-24 | 2026-09-23 | 65
| A28400 | Materials Successfully Inspected, Tested / Ex Work |  | 2026-06-25 |  |  | 7 | 2026-06-25 | 2026-09-24 | 2026-07-03 | 2026-07-03 | 2026-10-02 | 65
| A33320 | Delivery of Earthing and Power Cables |  | 2026-07-04 |  |  | 18 | 2026-07-04 | 2026-10-05 | 2026-07-17 | 2026-07-17 | 2026-10-18 | 116
| A33430 | Start Production |  | 2026-05-13 |  |  | 0 | 2026-05-13 | 2026-07-06 |  |  |  | 67
| A29150 | Key Vendor Drawings / Data Approved |  | 2026-05-14 |  |  | 20 | 2026-05-14 | 2026-07-06 | 2026-06-10 | 2026-06-10 | 2026-07-31 | 37
| A29160 | Purchase Order for Major Sub-ordered Materials |  | 2026-06-10 |  |  | 5 | 2026-06-10 | 2026-08-03 | 2026-06-17 | 2026-06-17 | 2026-08-07 | 37
| A29170 | Major Sub-ordered Materials Received by Vendor and Verified |  | 2026-06-17 |  |  | 5 | 2026-06-17 | 2026-08-10 | 2026-06-24 | 2026-06-24 | 2026-08-14 | 37
| A29180 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  | 2026-06-24 |  |  | 1 | 2026-06-24 | 2026-08-15 | 2026-06-25 | 2026-06-25 | 2026-08-16 | 65
| A29190 | Manufacturing / Ex Works (India/UAE) |  | 2026-06-25 |  |  | 31 | 2026-06-25 | 2026-08-16 | 2026-07-20 | 2026-07-20 | 2026-09-10 | 65
| A29200 | Complete Manufacturing & ready for Final Inspection |  | 2026-07-20 |  |  | 5 | 2026-07-20 | 2026-09-10 | 2026-07-27 | 2026-07-27 | 2026-09-16 | 38
| A29210 | Materials Successfully Inspected, Tested / Ex Work |  | 2026-07-27 |  |  | 5 | 2026-07-27 | 2026-09-17 | 2026-08-03 | 2026-08-03 | 2026-09-23 | 38
| A33440 | Delivery of Material in Warehouse for Cable Trays, JBs, Conduit Pipe, Cable Lugs, etc |  | 2026-08-03 |  |  | 18 | 2026-08-03 | 2026-09-24 | 2026-08-17 | 2026-08-17 | 2026-10-07 | 65
| A61450 | Power Cables |  | 2026-02-20 |  |  | 5 | 10-Oct-25 A | 2026-07-27 | 17-Oct-25 A | 2026-02-20 | 2026-07-27
| A61460 | Key Vendor Drawings / Data Approved |  | 2026-02-20 |  |  | 20 | 03-Oct-25 A | 2026-07-27 | 23-Oct-25 A | 2026-02-20 | 2026-07-27
| A61470 | Start Production |  |  |  |  | 0 | 24-Oct-25 A
| A61480 | Purchase Order for Major Sub-ordered Materials |  | 2026-02-20 |  |  | 5 | 2026-02-20 | 2026-07-27 | 2026-02-26 | 2026-02-26 | 2026-07-31 | 111
| A61490 | Major Sub-ordered Materials Received by Vendor and Verified |  | 2026-02-27 |  |  | 5 | 2026-02-27 | 2026-08-03 | 2026-03-05 | 2026-03-05 | 2026-08-07 | 111
| A61500 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  | 2026-03-06 |  |  | 1 | 2026-03-06 | 2026-08-08 | 2026-03-06 | 2026-03-06 | 2026-08-09 | 195
| A61510 | Manufacturing / Ex Works (India/UAE) |  | 2026-03-07 |  |  | 31 | 2026-03-07 | 2026-08-09 | 2026-03-31 | 2026-03-31 | 2026-09-03 | 195
| A61520 | Complete Manufacturing & ready for Final Inspection |  | 2026-03-31 |  |  | 5 | 2026-03-31 | 2026-09-03 | 2026-04-07 | 2026-04-07 | 2026-09-09 | 112
| A61530 | Materials Successfully Inspected, Tested / Ex Work |  | 2026-04-07 |  |  | 5 | 2026-04-07 | 2026-09-10 | 2026-04-14 | 2026-04-14 | 2026-09-16 | 112
| A61540 | Delivery of Material in Warehouse for Cable Trays, JBs, Conduit Pipe, Cable Lugs, etc |  | 2026-04-14 |  |  | 26 | 2026-04-14 | 2026-09-17 | 2026-05-05 | 2026-05-05 | 2026-10-07 | 194
| A33470 | Start Production |  | 2026-05-29 |  |  | 0 | 2026-05-29 | 2026-07-28 |  |  |  | 74
| A29330 | Key Vendor Drawings / Data Approved |  | 2026-06-01 |  |  | 15 | 2026-06-01 | 2026-07-28 | 2026-06-19 | 2026-06-19 | 2026-08-17 | 41
| A29340 | Purchase Order for Major Sub-ordered Materials |  | 2026-06-19 |  |  | 5 | 2026-06-19 | 2026-08-17 | 2026-06-26 | 2026-06-26 | 2026-08-24 | 41
| A29350 | Major Sub-ordered Materials Received by Vendor and Verified |  | 2026-06-26 |  |  | 10 | 2026-06-26 | 2026-08-24 | 2026-07-10 | 2026-07-10 | 2026-09-07 | 41
| A29360 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  | 2026-07-10 |  |  | 1 | 2026-07-10 | 2026-09-07 | 2026-07-11 | 2026-07-11 | 2026-09-08 | 74
| A29370 | Manufacturing / Ex Works (India/UAE) |  | 2026-07-11 |  |  | 35 | 2026-07-11 | 2026-09-08 | 2026-08-08 | 2026-08-08 | 2026-10-06 | 74
| A29380 | Complete Manufacturing & ready for Final Inspection |  | 2026-08-10 |  |  | 4 | 2026-08-10 | 2026-10-06 | 2026-08-14 | 2026-08-14 | 2026-10-12 | 42
| A29390 | Materials Successfully Inspected, Tested / Ex Work |  | 2026-08-14 |  |  | 5 | 2026-08-14 | 2026-10-13 | 2026-08-21 | 2026-08-21 | 2026-10-19 | 42
| A33480 | Delivery of Material in Warehouse for LCS & snap Switches |  | 2026-08-21 |  |  | 9 | 2026-08-21 | 2026-10-20 | 2026-08-28 | 2026-08-28 | 2026-10-26 | 75
| Electrical Bulk Material ( Earthing ,FO, Power Cables) |  |  | 2026-02-20 |  |  | 178 | 21-Nov-25 A | 2026-04-30 | 2026-07-28 | 2026-07-28 | 2026-10-05 | 49
| A17930 | Start Production |  |  |  |  | 0 | 21-Nov-25 A
| A27440 | Key Vendor Drawings / Data Approved |  | 2026-02-20 |  |  | 75 | 21-Nov-25 A | 2026-04-30 | 28-Nov-25 A | 2026-02-20 | 2026-04-30
| A27450 | Purchase Order for Major Sub-ordered Materials |  | 2026-02-20 |  |  | 10 | 11-Dec-25 A | 2026-04-30 | 19-Dec-25 A | 2026-02-20 | 2026-04-30
| A27460 | Major Sub-ordered Materials Received by Vendor and Verified |  | 2026-02-20 |  |  | 30 | 2026-02-20 | 2026-04-30 | 2026-04-02 | 2026-04-02 | 2026-06-10 | 49
| A27470 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  | 2026-04-03 |  |  | 1 | 2026-04-03 | 2026-06-11 | 2026-04-03 | 2026-04-03 | 2026-06-12 | 86
| A27480 | Manufacturing / Ex Works (India/UAE) |  | 2026-04-04 |  |  | 94 | 2026-04-04 | 2026-06-12 | 2026-06-17 | 2026-06-17 | 2026-08-26 | 86
| A27490 | Complete Manufacturing & ready for Final Inspection |  | 2026-06-18 |  |  | 7 | 2026-06-18 | 2026-08-26 | 2026-06-26 | 2026-06-26 | 2026-09-03 | 49
| A27500 | Materials Successfully Inspected, Tested / Ex Work |  | 2026-06-29 |  |  | 7 | 2026-06-29 | 2026-09-04 | 2026-07-07 | 2026-07-07 | 2026-09-14 | 49
| A33300 | Delivery of Electrical Bulk Material (Earthing, FO, 11 KVA Cable) (Post TA) |  | 2026-07-08 |  |  | 26 | 2026-07-08 | 2026-09-15 | 2026-07-28 | 2026-07-28 | 2026-10-05 | 86
| ESD Valves |  |  | 2026-02-20 |  |  | 198 | 30-Oct-25 A | 2026-03-25 | 2026-09-27 | 2026-09-27 | 2026-10-30 | 25
| A59880 | Start Production |  |  |  |  | 0 | 30-Oct-25 A
| A59830 | Purchase Order for Major Sub-ordered Materials |  | 2026-02-20 |  |  | 10 | 2026-02-20 | 2026-03-25 | 2026-02-28 | 2026-02-28 | 2026-04-02 | 42
| A59850 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  | 2026-03-15 |  |  | 1 | 2026-03-15 | 2026-04-17 | 2026-03-16 | 2026-03-16 | 2026-04-18 | 42
| A59840 | Major Sub-ordered Materials Received by Vendor and Verified |  | 2026-02-28 |  |  | 31 | 2026-02-28 | 2026-04-02 | 2026-03-25 | 2026-03-25 | 2026-04-27 | 42
| A59810 | Key Vendor Drawings / Data Approved |  | 2026-02-20 |  |  | 45 | 2026-02-20 | 2026-03-25 | 2026-04-23 | 2026-04-23 | 2026-05-27 | 24
| A59820 | Manufacturing / Ex Works (India/UAE) |  | 2026-03-16 |  |  | 213 | 2026-03-16 | 2026-04-18 | 2026-09-02 | 2026-09-02 | 2026-10-05 | 42
| A59860 | Complete Manufacturing & ready for Final Inspection |  | 2026-09-02 |  |  | 7 | 2026-09-02 | 2026-10-05 | 2026-09-07 | 2026-09-07 | 2026-10-11 | 42
| A59870 | Materials Successfully Inspected, Tested / Ex Work |  | 2026-09-07 |  |  | 7 | 2026-09-07 | 2026-10-11 | 2026-09-13 | 2026-09-13 | 2026-10-16 | 42
| A59890 | Delivery of Control Valves |  | 2026-09-13 |  |  | 18 | 2026-09-13 | 2026-10-17 | 2026-09-27 | 2026-09-27 | 2026-10-30 | 42
| A33740 | Start Production |  |  |  |  | 0 | 27-Oct-25 A
| A30410 | Key Vendor Drawings / Data Approved |  | 2026-02-20 |  |  | 50 | 18-Dec-25 A | 2026-05-12 | 20-Feb-26 A | 2026-02-20 | 2026-05-12
| A30440 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  | 2026-02-20 |  |  | 9 | 2026-02-20 | 2026-05-12 | 2026-02-26 | 2026-02-26 | 2026-05-19 | 102
| A30420 | Purchase Order for Major Sub-ordered Materials |  | 2026-02-20 |  |  | 10 | 15-Feb-26 A | 2027-05-26 | 2026-03-05 | 2026-03-05 | 2027-06-08 | 328
| A30430 | Major Sub-ordered Materials Received by Vendor and Verified |  | 2026-03-06 |  |  | 30 | 2026-03-06 | 2027-06-09 | 2026-04-16 | 2026-04-16 | 2027-07-20 | 328
| A30450 | Manufacturing / Ex Works (India/UAE) |  | 2026-02-27 |  |  | 165 | 2026-02-27 | 2026-05-19 | 2026-07-08 | 2026-07-08 | 2026-09-28 | 102
| A30460 | Complete Manufacturing & ready for Final Inspection |  | 2026-07-09 |  |  | 7 | 2026-07-09 | 2026-09-28 | 2026-07-14 | 2026-07-14 | 2026-10-04 | 102
| A30470 | Materials Successfully Inspected, Tested / Ex Work |  | 2026-07-14 |  |  | 7 | 2026-07-14 | 2026-10-04 | 2026-07-20 | 2026-07-20 | 2026-10-09 | 102
| A33750 | Delivery of Control Valves |  | 2026-07-20 |  |  | 26 | 2026-07-20 | 2026-10-10 | 2026-08-10 | 2026-08-10 | 2026-10-30 | 102
| A34300 | Start Production |  |  |  |  | 0 | 02-Sep-25 A
| A32660 | Key Vendor Drawings / Data Approved |  | 2026-02-20 |  |  | 50 | 21-Nov-25 A | 2026-05-11 | 10-Dec-25 A | 2026-02-20 | 2026-05-11
| A32670 | Purchase Order for Major Sub-ordered Materials |  | 2026-02-20 |  |  | 10 | 10-Dec-25 A | 2026-05-11 | 18-Dec-25 A | 2026-02-20 | 2026-05-11
| A32680 | Major Sub-ordered Materials Received by Vendor and Verified |  | 2026-02-20 |  |  | 30 | 2026-02-20 | 2026-05-11 | 2026-04-02 | 2026-04-02 | 2026-06-19 | 56
| A32690 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  | 2026-04-03 |  |  | 1 | 2026-04-03 | 2026-06-21 | 2026-04-03 | 2026-04-03 | 2026-06-22 | 99
| A32700 | Manufacturing / Ex Works (India/UAE) |  | 2026-04-04 |  |  | 175 | 2026-04-04 | 2026-06-22 | 2026-08-21 | 2026-08-21 | 2026-11-09 | 99
| A32710 | Complete Manufacturing & ready for Final Inspection |  | 2026-08-24 |  |  | 7 | 2026-08-24 | 2026-11-09 | 2026-09-01 | 2026-09-01 | 2026-11-17 | 55
| A32720 | Materials Successfully Inspected, Tested / Ex Work |  | 2026-09-02 |  |  | 7 | 2026-09-02 | 2026-11-18 | 2026-09-10 | 2026-09-10 | 2026-11-26 | 55
| A34310 | Delivery of MOVs |  | 2026-09-11 |  |  | 18 | 2026-09-11 | 2026-11-27 | 2026-09-24 | 2026-09-24 | 2026-12-10 | 96
| A34130 | Start Production |  |  |  |  | 0 | 25-May-25 A
| A31940 | Key Vendor Drawings / Data Approved |  | 2026-02-20 |  |  | 50 | 19-Dec-25 A | 2026-07-15 | 19-Dec-25 A | 2026-02-20 | 2026-07-15
| A31950 | Purchase Order for Major Sub-ordered Materials |  | 2026-02-20 |  |  | 10 | 20-Dec-25 A | 2026-07-15 | 26-Dec-25 A | 2026-02-20 | 2026-07-15
| A31960 | Major Sub-ordered Materials Received by Vendor and Verified |  | 2026-02-20 |  |  | 30 | 27-Dec-25 A | 2026-07-15 | 02-Jan-26 A | 2026-02-20 | 2026-07-15
| A31970 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  | 2026-02-20 |  |  | 4 | 01-Jan-26 A | 2026-07-15 | 09-Jan-26 A | 2026-02-20 | 2026-07-15
| A31980 | Manufacturing / Ex Works (India/UAE) |  | 2026-02-20 |  |  | 94 | 2026-02-20 | 2026-07-15 | 2026-05-05 | 2026-05-05 | 2026-09-28 | 181
| A31990 | Complete Manufacturing & ready for Final Inspection |  | 2026-05-06 |  |  | 5 | 2026-05-06 | 2026-09-28 | 2026-05-12 | 2026-05-12 | 2026-10-02 | 103
| A32000 | Materials Successfully Inspected, Tested / Ex Work |  | 2026-05-13 |  |  | 5 | 2026-05-13 | 2026-10-05 | 2026-05-19 | 2026-05-19 | 2026-10-09 | 103
| A34140 | Delivery of MCMS |  | 2026-05-20 |  |  | 21 | 2026-05-20 | 2026-10-10 | 2026-06-05 | 2026-06-05 | 2026-10-26 | 179
| TA_Integrated Protection and Control System BF - ABB/Hitachi |  |  | 2026-02-20 |  |  | 41 | 21-Mar-25 A | 2026-03-27 | 16-May-25 A | 2026-02-20 | 2026-03-27
| A34480 | Start Production |  |  |  |  | 0 | 21-Mar-25 A
| A27710 | Key Vendor Drawings / Data Approved |  | 2026-02-20 |  |  | 5 | 21-Mar-25 A | 2026-03-27 | 28-Mar-25 A | 2026-02-20 | 2026-03-27
| A27720 | Purchase Order for Major Sub-ordered Materials |  | 2026-02-20 |  |  | 5 | 01-Apr-25 A | 2026-03-27 | 04-Apr-25 A | 2026-02-20 | 2026-03-27
| A27730 | Major Sub-ordered Materials Received by Vendor and Verified |  | 2026-02-20 |  |  | 5 | 05-Apr-25 A | 2026-03-27 | 11-Apr-25 A | 2026-02-20 | 2026-03-27
| A27740 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  | 2026-02-20 |  |  | 1 | 12-Apr-25 A | 2026-03-27 | 18-Apr-25 A | 2026-02-20 | 2026-03-27
| A27750 | Manufacturing / Ex Works (India/UAE) |  | 2026-02-20 |  |  | 18 | 19-Apr-25 A | 2026-03-27 | 25-Apr-25 A | 2026-02-20 | 2026-03-27
| A27760 | Complete Manufacturing & ready for Final Inspection |  | 2026-02-20 |  |  | 5 | 26-Apr-25 A | 2026-03-27 | 02-May-25 A | 2026-02-20 | 2026-03-27
| A27770 | Materials Successfully Inspected, Tested / Ex Work |  | 2026-02-20 |  |  | 5 | 03-May-25 A | 2026-03-27 | 09-May-25 A | 2026-02-20 | 2026-03-27
| A27780 | Delivery of FOPP (02 Nos) |  | 2026-02-20 |  |  | 9 | 10-May-25 A | 2026-03-27 | 16-May-25 A | 2026-02-20 | 2026-03-27
| Integrated Protection Control System |  |  | 2026-02-20 |  |  | 226 | 25-Jul-25 A | 2026-05-04 | 2026-07-31 | 2026-07-31 | 2026-10-14 | 53
| A24030 | Start Production |  |  |  |  | 0 | 25-Jul-25 A
| A31220 | Key Vendor Drawings / Data Approved |  | 2026-02-20 |  |  | 50 | 10-Sep-25 A | 2026-05-04 | 20-Dec-25 A | 2026-02-20 | 2026-05-04
| A31230 | Purchase Order for Major Sub-ordered Materials |  | 2026-02-20 |  |  | 10 | 21-Dec-25 A | 2026-05-04 | 27-Dec-25 A | 2026-02-20 | 2026-05-04
| A31240 | Major Sub-ordered Materials Received by Vendor and Verified |  | 2026-02-20 |  |  | 30 | 28-Dec-25 A | 2026-05-04 | 03-Jan-26 A | 2026-02-20 | 2026-05-04
| A31250 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  | 2026-02-20 |  |  | 4 | 10-Jan-26 A | 2026-05-04 | 2026-02-22 | 2026-02-22 | 2026-05-07 | 92
| A31260 | Manufacturing / Ex Works (India/UAE) |  | 2026-02-22 |  |  | 150 | 2026-02-22 | 2026-05-07 | 2026-06-22 | 2026-06-22 | 2026-09-04 | 92
| A31270 | Complete Manufacturing & ready for Final Inspection |  | 2026-06-22 |  |  | 7 | 2026-06-22 | 2026-09-04 | 2026-07-01 | 2026-07-01 | 2026-09-14 | 53
| A31280 | Materials Successfully Inspected, Tested / Ex Work |  | 2026-07-01 |  |  | 7 | 2026-07-01 | 2026-09-15 | 2026-07-10 | 2026-07-10 | 2026-09-23 | 53
| A33970 | Delivery of IPCS |  | 2026-07-10 |  |  | 26 | 2026-07-10 | 2026-09-24 | 2026-07-31 | 2026-07-31 | 2026-10-14 | 94
| TA_SCMS System - Siemens |  |  | 2026-02-20 |  |  | 19 | 13-Mar-25 A | 2026-03-27 | 11-May-25 A | 2026-02-20 | 2026-03-27
| A27620 | Key Vendor Drawings / Data Approved |  | 2026-02-20 |  |  | 3 | 13-Mar-25 A | 2026-03-27 | 16-Mar-25 A | 2026-02-20 | 2026-03-27
| A33290 | Start Production |  |  |  |  | 0 | 23-Mar-25 A
| A27630 | Purchase Order for Major Sub-ordered Materials |  | 2026-02-20 |  |  | 3 | 24-Mar-25 A | 2026-03-27 | 30-Mar-25 A | 2026-02-20 | 2026-03-27
| A27640 | Major Sub-ordered Materials Received by Vendor and Verified |  | 2026-02-20 |  |  | 3 | 31-Mar-25 A | 2026-03-27 | 06-Apr-25 A | 2026-02-20 | 2026-03-27
| A27650 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  | 2026-02-20 |  |  | 1 | 07-Apr-25 A | 2026-03-27 | 13-Apr-25 A | 2026-02-20 | 2026-03-27
| A27660 | Manufacturing / Ex Works (India/UAE) |  | 2026-02-20 |  |  | 4 | 14-Apr-25 A | 2026-03-27 | 20-Apr-25 A | 2026-02-20 | 2026-03-27
| A27670 | Complete Manufacturing & ready for Final Inspection |  | 2026-02-20 |  |  | 3 | 21-Apr-25 A | 2026-03-27 | 27-Apr-25 A | 2026-02-20 | 2026-03-27
| A27680 | Materials Successfully Inspected, Tested / Ex Work |  | 2026-02-20 |  |  | 2 | 28-Apr-25 A | 2026-03-27 | 04-May-25 A | 2026-02-20 | 2026-03-27
| A27690 | Delivery of SCMS |  | 2026-02-20 |  |  | 4 | 05-May-25 A | 2026-03-27 | 11-May-25 A | 2026-02-20 | 2026-03-27
| SCMS System |  |  | 2026-02-20 |  |  | 322 | 23-May-25 A | 2026-03-20 | 2026-09-16 | 2026-09-16 | 2026-10-14 | 20
| A60100 | Start Production |  |  |  |  | 0 | 23-May-25 A
| A60110 | Key Vendor Drawings / Data Approved |  | 2026-02-20 |  |  | 50 | 06-Jan-26 A | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-04-17 | 20
| A60130 | Purchase Order for Major Sub-ordered Materials |  | 2026-03-20 |  |  | 10 | 2026-03-20 | 2026-04-20 | 2026-04-03 | 2026-04-03 | 2026-05-01 | 20
| A60140 | Major Sub-ordered Materials Received by Vendor and Verified |  | 2026-04-03 |  |  | 21 | 2026-04-03 | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-06-01 | 20
| A60150 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  | 2026-05-04 |  |  | 1 | 2026-05-04 | 2026-06-02 | 2026-05-05 | 2026-05-05 | 2026-06-03 | 35
| A60120 | Manufacturing / Ex Works (India/UAE) |  | 2026-05-05 |  |  | 125 | 2026-05-05 | 2026-06-03 | 2026-08-13 | 2026-08-13 | 2026-09-11 | 35
| A60160 | Complete Manufacturing & ready for Final Inspection |  | 2026-08-13 |  |  | 7 | 2026-08-13 | 2026-09-11 | 2026-08-24 | 2026-08-24 | 2026-09-21 | 20
| A60170 | Materials Successfully Inspected, Tested / Ex Work |  | 2026-08-24 |  |  | 7 | 2026-08-24 | 2026-09-22 | 2026-09-02 | 2026-09-02 | 2026-09-30 | 20
| A60180 | Delivery of SCMS |  | 2026-09-02 |  |  | 18 | 2026-09-02 | 2026-10-01 | 2026-09-16 | 2026-09-16 | 2026-10-14 | 35
| TA_Integrated Control and Safety System BF - Honeywell |  |  | 2026-02-20 |  |  | 103 | 20-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A33280 | Start Production |  |  |  |  | 0 | 22-Mar-25 A
| A27530 | Key Vendor Drawings / Data Approved |  | 2026-02-20 |  |  | 5 | 20-Mar-25 A | 2026-03-27 | 29-Mar-25 A | 2026-02-20 | 2026-03-27
| A27540 | Purchase Order for Major Sub-ordered Materials |  | 2026-02-20 |  |  | 5 | 29-Mar-25 A | 2026-03-27 | 05-Apr-25 A | 2026-02-20 | 2026-03-27
| A27550 | Major Sub-ordered Materials Received by Vendor and Verified |  | 2026-02-20 |  |  | 5 | 06-Apr-25 A | 2026-03-27 | 12-Apr-25 A | 2026-02-20 | 2026-03-27
| A27560 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  | 2026-02-20 |  |  | 1 | 13-Apr-25 A | 2026-03-27 | 19-Apr-25 A | 2026-02-20 | 2026-03-27
| A27570 | Manufacturing / Ex Works (India/UAE) |  | 2026-02-20 |  |  | 9 | 20-Apr-25 A | 2026-03-27 | 26-Apr-25 A | 2026-02-20 | 2026-03-27
| A27580 | Complete Manufacturing & ready for Final Inspection |  | 2026-02-20 |  |  | 5 | 27-Apr-25 A | 2026-03-27 | 03-May-25 A | 2026-02-20 | 2026-03-27
| A27590 | Materials Successfully Inspected, Tested / Ex Work |  | 2026-02-20 |  |  | 5 | 04-May-25 A | 2026-03-27 | 10-May-25 A | 2026-02-20 | 2026-03-27
| A27600 | Delivery of loose Material for ICSS Modification |  | 2026-02-20 |  |  | 6 | 11-May-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A33950 | Start Production |  |  |  |  | 0 | 20-Jun-25 A
| A31130 | Key Vendor Drawings / Data Approved |  | 2026-02-20 |  |  | 50 | 05-Aug-25 A | 2026-03-18 | 20-Dec-25 A | 2026-02-20 | 2026-03-18
| A31140 | Purchase Order for Major Sub-ordered Materials |  | 2026-02-20 |  |  | 10 | 21-Dec-25 A | 2026-03-18 | 27-Dec-25 A | 2026-02-20 | 2026-03-18
| A31150 | Major Sub-ordered Materials Received by Vendor and Verified |  | 2026-02-20 |  |  | 30 | 27-Dec-25 A | 2026-03-18 | 03-Jan-26 A | 2026-02-20 | 2026-03-18
| A31160 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  | 2026-02-20 |  |  | 1 | 10-Jan-26 A | 2026-03-18 | 2026-02-20 | 2026-02-20 | 2026-03-19 | 33
| A31170 | Manufacturing / Ex Works (India/UAE) |  | 2026-02-20 |  |  | 225 | 2026-02-20 | 2026-03-19 | 2026-08-19 | 2026-08-19 | 2026-09-15 | 33
| A31180 | Complete Manufacturing & ready for Final Inspection |  | 2026-08-19 |  |  | 7 | 2026-08-19 | 2026-09-15 | 2026-08-28 | 2026-08-28 | 2026-09-23 | 18
| A31190 | Materials Successfully Inspected, Tested / Ex Work |  | 2026-08-28 |  |  | 7 | 2026-08-28 | 2026-09-24 | 2026-09-08 | 2026-09-08 | 2026-10-02 | 18
| A33960 | Delivery of Material in Warehouse ICSS |  | 2026-09-08 |  |  | 26 | 2026-09-08 | 2026-10-03 | 2026-09-29 | 2026-09-29 | 2026-10-23 | 30
| A33550 | Start Production |  | 2026-03-12 |  |  | 0 | 2026-03-12 | 2026-04-13 |  |  |  | 39
| A29690 | Key Vendor Drawings / Data Approved |  | 2026-03-13 |  |  | 30 | 2026-03-13 | 2026-04-13 | 2026-04-23 | 2026-04-23 | 2026-05-22 | 21
| A29700 | Purchase Order for Major Sub-ordered Materials |  | 2026-04-23 |  |  | 10 | 2026-04-23 | 2026-05-25 | 2026-05-07 | 2026-05-07 | 2026-06-05 | 21
| A29710 | Major Sub-ordered Materials Received by Vendor and Verified |  | 2026-05-07 |  |  | 15 | 2026-05-07 | 2026-06-08 | 2026-05-28 | 2026-05-28 | 2026-06-26 | 21
| A29720 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  | 2026-05-28 |  |  | 1 | 2026-05-28 | 2026-06-27 | 2026-05-29 | 2026-05-29 | 2026-06-28 | 37
| A29730 | Manufacturing / Ex Works (India/UAE) |  | 2026-05-29 |  |  | 94 | 2026-05-29 | 2026-06-28 | 2026-08-12 | 2026-08-12 | 2026-09-11 | 37
| A29740 | Complete Manufacturing & ready for Final Inspection |  | 2026-08-12 |  |  | 7 | 2026-08-12 | 2026-09-11 | 2026-08-21 | 2026-08-21 | 2026-09-21 | 21
| A29750 | Materials Successfully Inspected, Tested / Ex Work |  | 2026-08-21 |  |  | 7 | 2026-08-21 | 2026-09-22 | 2026-09-01 | 2026-09-01 | 2026-09-30 | 21
| A33560 | Delivery of Material in Warehouse for Instrument Cable |  | 2026-09-01 |  |  | 9 | 2026-09-01 | 2026-10-01 | 2026-09-08 | 2026-09-08 | 2026-10-07 | 36
| Local Fire Control Panel including F&G Detectors |  |  | 2026-02-20 |  |  | 112 | 12-Dec-25 A | 2026-05-05 | 2026-07-27 | 2026-07-27 | 2026-10-07 | 52
| A34090 | Start Production |  |  |  |  | 0 | 12-Dec-25 A
| A31760 | Key Vendor Drawings / Data Approved |  | 2026-02-20 |  |  | 30 | 24-Jan-26 A | 2026-05-05 | 2026-03-19 | 2026-03-19 | 2026-06-01 | 52
| A31770 | Purchase Order for Major Sub-ordered Materials |  | 2026-03-19 |  |  | 7 | 2026-03-19 | 2026-06-02 | 2026-03-30 | 2026-03-30 | 2026-06-10 | 52
| A31780 | Major Sub-ordered Materials Received by Vendor and Verified |  | 2026-03-30 |  |  | 7 | 2026-03-30 | 2026-06-11 | 2026-04-08 | 2026-04-08 | 2026-06-19 | 52
| A31790 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  | 2026-04-08 |  |  | 1 | 2026-04-08 | 2026-06-20 | 2026-04-09 | 2026-04-09 | 2026-06-21 | 90
| A31800 | Manufacturing / Ex Works |  | 2026-04-09 |  |  | 94 | 2026-04-09 | 2026-06-21 | 2026-06-23 | 2026-06-23 | 2026-09-04 | 90
| A31810 | Complete Manufacturing & ready for Final Inspection |  | 2026-06-23 |  |  | 7 | 2026-06-23 | 2026-09-04 | 2026-07-02 | 2026-07-02 | 2026-09-14 | 52
| A31820 | Materials Successfully Inspected, Tested / Ex Work |  | 2026-07-02 |  |  | 7 | 2026-07-02 | 2026-09-15 | 2026-07-13 | 2026-07-13 | 2026-09-23 | 52
| A34100 | Delivery of FDAS, LFCP, Clean Agent Unit |  | 2026-07-13 |  |  | 18 | 2026-07-13 | 2026-09-24 | 2026-07-27 | 2026-07-27 | 2026-10-07 | 90
| A33530 | Start Production |  | 2026-03-25 |  |  | 0 | 2026-03-25 | 2026-04-23 |  |  |  | 35
| A29600 | Key Vendor Drawings / Data Approved |  | 2026-03-26 |  |  | 30 | 2026-03-26 | 2026-04-23 | 2026-05-06 | 2026-05-06 | 2026-06-03 | 20
| A29610 | Purchase Order for Major Sub-ordered Materials |  | 2026-05-06 |  |  | 7 | 2026-05-06 | 2026-06-04 | 2026-05-15 | 2026-05-15 | 2026-06-12 | 20
| A29620 | Major Sub-ordered Materials Received by Vendor and Verified |  | 2026-05-15 |  |  | 15 | 2026-05-15 | 2026-06-15 | 2026-06-05 | 2026-06-05 | 2026-07-03 | 20
| A29630 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  | 2026-06-05 |  |  | 0 | 2026-06-05 | 2026-07-05 | 2026-06-05 | 2026-06-05 | 2026-07-05 | 37
| A29640 | Manufacturing / Ex Works (India/UAE) |  | 2026-06-05 |  |  | 94 | 2026-06-05 | 2026-07-05 | 2026-08-19 | 2026-08-19 | 2026-09-18 | 37
| A29650 | Complete Manufacturing & ready for Final Inspection |  | 2026-08-19 |  |  | 7 | 2026-08-19 | 2026-09-18 | 2026-08-28 | 2026-08-28 | 2026-09-28 | 21
| A29660 | Materials Successfully Inspected, Tested / Ex Work |  | 2026-08-28 |  |  | 7 | 2026-08-28 | 2026-09-29 | 2026-09-08 | 2026-09-08 | 2026-10-07 | 21
| A33540 | Delivery of Material in Warehouse for PSVs |  | 2026-09-08 |  |  | 18 | 2026-09-08 | 2026-10-07 | 2026-09-22 | 2026-09-22 | 2026-10-21 | 36
| A37420 | Start Production |  |  |  |  | 0 | 17-Mar-25 A
| A37430 | Key Vendor Drawings / Data Approved |  | 2026-02-20 |  |  | 10 | 26-Feb-25 A | 2026-12-01 | 24-Mar-25 A | 2026-02-20 | 2026-12-01
| A37440 | Purchase Order for Major Sub-ordered Materials |  | 2026-02-20 |  |  | 5 | 25-Mar-25 A | 2026-12-01 | 31-Mar-25 A | 2026-02-20 | 2026-12-01
| A37450 | Major Sub-ordered Materials Received by Vendor and Verified |  | 2026-02-20 |  |  | 5 | 01-Apr-25 A | 2026-12-01 | 07-Apr-25 A | 2026-02-20 | 2026-12-01
| A37460 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  | 2026-02-20 |  |  | 1 | 08-Apr-25 A | 2026-12-01 | 14-Apr-25 A | 2026-02-20 | 2026-12-01
| A37470 | Manufacturing / Ex Works (India/UAE) |  | 2026-02-20 |  |  | 35 | 15-Apr-25 A | 2026-12-01 | 21-Apr-25 A | 2026-02-20 | 2026-12-01
| A37480 | Complete Manufacturing & ready for Final Inspection |  | 2026-02-20 |  |  | 5 | 22-Apr-25 A | 2026-12-01 | 28-Apr-25 A | 2026-02-20 | 2026-12-01
| A37490 | Materials Successfully Inspected, Tested / Ex Work |  | 2026-02-20 |  |  | 5 | 29-Apr-25 A | 2026-12-01 | 05-May-25 A | 2026-02-20 | 2026-12-01
| A37500 | Delivery of Additional Material to be Procured |  | 2026-02-20 |  |  | 18 | 06-May-25 A | 2026-12-01 | 12-May-25 A | 2026-02-20 | 2026-12-01
| F&G Flame Detectors, MCP, Beacon, etc. |  |  | 2026-04-02 |  |  | 109 | 2026-04-02 | 2026-06-01 | 2026-09-02 | 2026-09-02 | 2026-10-31 | 42
| A34170 | Start Production |  | 2026-04-02 |  |  | 0 | 2026-04-02 | 2026-06-01 |  |  |  | 74
| A32120 | Key Vendor Drawings / Data Approved |  | 2026-04-02 |  |  | 15 | 2026-04-02 | 2026-06-01 | 2026-04-23 | 2026-04-23 | 2026-06-19 | 41
| A32130 | Purchase Order for Major Sub-ordered Materials |  | 2026-04-23 |  |  | 10 | 2026-04-23 | 2026-06-22 | 2026-05-07 | 2026-05-07 | 2026-07-03 | 41
| A32140 | Major Sub-ordered Materials Received by Vendor and Verified |  | 2026-05-07 |  |  | 15 | 2026-05-07 | 2026-07-06 | 2026-05-28 | 2026-05-28 | 2026-07-24 | 41
| A32150 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  | 2026-05-28 |  |  | 1 | 2026-05-28 | 2026-07-25 | 2026-05-29 | 2026-05-29 | 2026-07-26 | 72
| A32160 | Manufacturing / Ex Works (India/UAE) |  | 2026-05-29 |  |  | 75 | 2026-05-29 | 2026-07-26 | 2026-07-28 | 2026-07-28 | 2026-09-24 | 72
| A32170 | Complete Manufacturing & ready for Final Inspection |  | 2026-07-28 |  |  | 7 | 2026-07-28 | 2026-09-24 | 2026-08-06 | 2026-08-06 | 2026-10-02 | 41
| A32180 | Materials Successfully Inspected, Tested / Ex Work |  | 2026-08-06 |  |  | 5 | 2026-08-06 | 2026-10-05 | 2026-08-13 | 2026-08-13 | 2026-10-09 | 41
| A34180 | Delivery of F&G Detectors |  | 2026-08-13 |  |  | 25 | 2026-08-13 | 2026-10-12 | 2026-09-02 | 2026-09-02 | 2026-10-31 | 74
| DG Set (750 KVA) 01 Nos |  |  | 2026-02-20 |  |  | 270 | 22-Aug-25 A | 2026-05-18 | 2026-08-06 | 2026-08-06 | 2026-11-03 | 63
| A34420 | Start Production |  |  |  |  | 0 | 22-Aug-25 A
| A33200 | Key Vendor Drawings / Data Approved |  | 2026-02-20 |  |  | 90 | 01-Sep-25 A | 2026-05-18 | 27-Nov-25 A | 2026-02-20 | 2026-05-18
| A33220 | Major Sub-ordered Materials Received by Vendor and Verified |  | 2026-02-20 |  |  | 30 | 26-Nov-25 A | 2026-05-18 | 01-Dec-25 A | 2026-02-20 | 2026-05-18
| A33230 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  | 2026-02-20 |  |  | 3 | 02-Dec-25 A | 2026-05-18 | 09-Dec-25 A | 2026-02-20 | 2026-05-18
| A33210 | Purchase Order for Major Sub-ordered Materials |  | 2026-02-20 |  |  | 10 | 30-Nov-25 A | 2026-05-18 | 19-Dec-25 A | 2026-02-20 | 2026-05-18
| A33240 | Manufacturing / Ex Works (India/UAE) |  | 2026-02-20 |  |  | 194 | 10-Dec-25 A | 2026-05-18 | 2026-06-29 | 2026-06-29 | 2026-09-25 | 109
| A33250 | Complete Manufacturing & ready for Final Inspection |  | 2026-06-30 |  |  | 7 | 2026-06-30 | 2026-09-25 | 2026-07-08 | 2026-07-08 | 2026-10-05 | 63
| A33260 | Materials Successfully Inspected, Tested / Ex Work |  | 2026-07-09 |  |  | 7 | 2026-07-09 | 2026-10-06 | 2026-07-17 | 2026-07-17 | 2026-10-14 | 63
| A34430 | Delivery of Material in Warehouse DG Set |  | 2026-07-18 |  |  | 25 | 2026-07-18 | 2026-10-15 | 2026-08-06 | 2026-08-06 | 2026-11-03 | 111
| UPS (AC - 60 KVA, 20 KVA, DC-UPS 6.5 KVA) 03 Nos. |  |  | 2026-02-20 |  |  | 412 | 25-Feb-25 A | 2026-03-27 | 2026-09-28 | 2026-09-28 | 2027-01-03 | 69
| TA_UPS Modification - Chloride Technology |  |  | 2026-02-20 |  |  | 99 | 25-Feb-25 A | 2026-03-27 | 03-May-25 A | 2026-02-20 | 2026-03-27
| A37280 | Start Production |  |  |  |  | 0 | 25-Feb-25 A
| A37290 | Key Vendor Drawings / Data Approved |  | 2026-02-20 |  |  | 5 | 27-Feb-25 A | 2026-03-27 | 04-Mar-25 A | 2026-02-20 | 2026-03-27
| A37300 | Purchase Order for Major Sub-ordered Materials |  | 2026-02-20 |  |  | 5 | 06-Mar-25 A | 2026-03-27 | 22-Mar-25 A | 2026-02-20 | 2026-03-27
| A37310 | Major Sub-ordered Materials Received by Vendor and Verified |  | 2026-02-20 |  |  | 5 | 23-Mar-25 A | 2026-03-27 | 29-Mar-25 A | 2026-02-20 | 2026-03-27
| A37320 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  | 2026-02-20 |  |  | 1 | 30-Mar-25 A | 2026-03-27 | 05-Apr-25 A | 2026-02-20 | 2026-03-27
| A37330 | Manufacturing / Ex Works (India/UAE) |  | 2026-02-20 |  |  | 26 | 06-Apr-25 A | 2026-03-27 | 12-Apr-25 A | 2026-02-20 | 2026-03-27
| A37340 | Complete Manufacturing & ready for Final Inspection |  | 2026-02-20 |  |  | 1 | 13-Apr-25 A | 2026-03-27 | 19-Apr-25 A | 2026-02-20 | 2026-03-27
| A37350 | Materials Successfully Inspected, Tested / Ex Work |  | 2026-02-20 |  |  | 5 | 20-Apr-25 A | 2026-03-27 | 26-Apr-25 A | 2026-02-20 | 2026-03-27
| A37360 | Delivery of Material for UPS Modification |  | 2026-02-20 |  |  | 6 | 27-Apr-25 A | 2026-03-27 | 03-May-25 A | 2026-02-20 | 2026-03-27
| A34070 | Start Production |  |  |  |  | 0 | 16-Oct-25 A
| A31670 | Key Vendor Drawings / Data Approved |  | 2026-02-20 |  |  | 16 | 2026-02-20 | 2026-05-28 | 2026-03-13 | 2026-03-13 | 2026-06-18 | 69
| A31680 | Purchase Order for Major Sub-ordered Materials |  | 2026-03-13 |  |  | 10 | 2026-03-13 | 2026-06-19 | 2026-03-27 | 2026-03-27 | 2026-07-02 | 69
| A31690 | Major Sub-ordered Materials Received by Vendor and Verified |  | 2026-03-27 |  |  | 30 | 2026-03-27 | 2026-07-03 | 2026-05-08 | 2026-05-08 | 2026-08-13 | 69
| A31700 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  | 2026-05-08 |  |  | 3 | 2026-05-08 | 2026-08-14 | 2026-05-10 | 2026-05-10 | 2026-08-16 | 122
| A31710 | Manufacturing / Ex Works (India/UAE) |  | 2026-05-10 |  |  | 125 | 2026-05-10 | 2026-08-16 | 2026-08-18 | 2026-08-18 | 2026-11-24 | 122
| A31720 | Complete Manufacturing & ready for Final Inspection |  | 2026-08-18 |  |  | 7 | 2026-08-18 | 2026-11-24 | 2026-08-27 | 2026-08-27 | 2026-12-02 | 69
| A31730 | Materials Successfully Inspected, Tested / Ex Work |  | 2026-08-27 |  |  | 7 | 2026-08-27 | 2026-12-03 | 2026-09-07 | 2026-09-07 | 2026-12-11 | 69
| A34080 | Delivery of Material in Warehouse UPS |  | 2026-09-07 |  |  | 26 | 2026-09-07 | 2026-12-14 | 2026-09-28 | 2026-09-28 | 2027-01-03 | 121
| Power Transformer (05 Nos) |  |  | 2026-02-20 |  |  | 256 | 10-Sep-25 A | 2026-05-01 | 2026-08-14 | 2026-08-14 | 2026-10-23 | 50
| A34110 | Start Production |  |  |  |  | 0 | 10-Sep-25 A
| A31850 | Key Vendor Drawings / Data Approved |  | 2026-02-20 |  |  | 60 | 21-Nov-25 A | 2026-05-01 | 02-Dec-25 A | 2026-02-20 | 2026-05-01
| A31860 | Purchase Order for Major Sub-ordered Materials |  | 2026-02-20 |  |  | 10 | 02-Dec-25 A | 2026-05-01 | 19-Dec-25 A | 2026-02-20 | 2026-05-01
| A31870 | Major Sub-ordered Materials Received by Vendor and Verified |  | 2026-02-20 |  |  | 30 | 19-Dec-25 A | 2026-05-01 | 03-Jan-26 A | 2026-02-20 | 2026-05-01
| A31880 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  | 2026-02-20 |  |  | 1 | 01-Jan-26 A | 2026-05-01 | 11-Jan-26 A | 2026-02-20 | 2026-05-01
| A31890 | Manufacturing / Ex Works (India/UAE) |  | 2026-02-20 |  |  | 163 | 2026-02-20 | 2026-05-01 | 2026-06-29 | 2026-06-29 | 2026-09-08 | 88
| A31900 | Complete Manufacturing & ready for Final Inspection |  | 2026-06-30 |  |  | 7 | 2026-06-30 | 2026-09-08 | 2026-07-08 | 2026-07-08 | 2026-09-16 | 50
| A31910 | Materials Successfully Inspected, Tested / Ex Work |  | 2026-07-09 |  |  | 7 | 2026-07-09 | 2026-09-17 | 2026-07-17 | 2026-07-17 | 2026-09-25 | 50
| A34120 | Delivery of Material in Warehouse Power Transformers |  | 2026-07-18 |  |  | 35 | 2026-07-18 | 2026-09-26 | 2026-08-14 | 2026-08-14 | 2026-10-23 | 88
| A33410 | Start Production |  | 2026-05-13 |  |  | 0 | 2026-05-13 | 2026-07-13 |  |  |  | 76
| A29060 | Key Vendor Drawings / Data Approved |  | 2026-05-14 |  |  | 30 | 2026-05-14 | 2026-07-13 | 2026-06-24 | 2026-06-24 | 2026-08-24 | 42
| A29070 | Purchase Order for Major Sub-ordered Materials |  | 2026-06-24 |  |  | 3 | 2026-06-24 | 2026-08-24 | 2026-06-29 | 2026-06-29 | 2026-08-27 | 43
| A29080 | Major Sub-ordered Materials Received by Vendor and Verified |  | 2026-06-29 |  |  | 5 | 2026-06-29 | 2026-08-27 | 2026-07-06 | 2026-07-06 | 2026-09-03 | 43
| A29090 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  | 2026-07-06 |  |  | 1 | 2026-07-06 | 2026-09-03 | 2026-07-07 | 2026-07-07 | 2026-09-04 | 73
| A29100 | Manufacturing / Ex Works (India/UAE) |  | 2026-07-07 |  |  | 31 | 2026-07-07 | 2026-09-04 | 2026-08-01 | 2026-08-01 | 2026-09-28 | 73
| A29110 | Complete Manufacturing & ready for Final Inspection |  | 2026-08-03 |  |  | 3 | 2026-08-03 | 2026-09-28 | 2026-08-06 | 2026-08-06 | 2026-10-01 | 41
| A29120 | Materials Successfully Inspected, Tested / Ex Work |  | 2026-08-06 |  |  | 7 | 2026-08-06 | 2026-10-02 | 2026-08-17 | 2026-08-17 | 2026-10-12 | 41
| A33420 | Delivery of Material in Warehouse for Electrical Heat Tracing |  | 2026-08-17 |  |  | 18 | 2026-08-17 | 2026-10-13 | 2026-08-31 | 2026-08-31 | 2026-10-26 | 71
| A33450 | Start Production |  | 2026-02-27 |  |  | 0 | 2026-02-27 | 2026-05-25 |  |  |  | 108
| A29240 | Key Vendor Drawings / Data Approved |  | 2026-03-02 |  |  | 30 | 2026-03-02 | 2026-05-25 | 2026-04-10 | 2026-04-10 | 2026-07-03 | 60
| A29250 | Purchase Order for Major Sub-ordered Materials |  | 2026-04-10 |  |  | 5 | 2026-04-10 | 2026-07-06 | 2026-04-17 | 2026-04-17 | 2026-07-10 | 60
| A29260 | Major Sub-ordered Materials Received by Vendor and Verified |  | 2026-04-17 |  |  | 20 | 2026-04-17 | 2026-07-13 | 2026-05-15 | 2026-05-15 | 2026-08-07 | 60
| A29270 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  | 2026-05-15 |  |  | 1 | 2026-05-15 | 2026-08-08 | 2026-05-16 | 2026-05-16 | 2026-08-09 | 105
| A29280 | Manufacturing / Ex Works |  | 2026-05-16 |  |  | 56 | 2026-05-16 | 2026-08-09 | 2026-06-30 | 2026-06-30 | 2026-09-23 | 105
| A29290 | Complete Manufacturing & ready for Final Inspection |  | 2026-06-30 |  |  | 7 | 2026-06-30 | 2026-09-23 | 2026-07-09 | 2026-07-09 | 2026-10-01 | 60
| A29300 | Materials Successfully Inspected, Tested / Ex Work |  | 2026-07-09 |  |  | 7 | 2026-07-09 | 2026-10-02 | 2026-07-20 | 2026-07-20 | 2026-10-12 | 60
| A33460 | Delivery of Material in Warehouse for Cathodic Protection |  | 2026-07-20 |  |  | 18 | 2026-07-20 | 2026-10-13 | 2026-08-03 | 2026-08-03 | 2026-10-26 | 105
| Switchgear (MV & LV) |  |  | 2026-02-20 |  |  | 244 | 12-Sep-25 A | 2026-04-22 | 2026-08-20 | 2026-08-20 | 2026-10-18 | 41
| A34260 | Start Production |  |  |  |  | 0 | 12-Sep-25 A
| A32480 | Key Vendor Drawings / Data Approved |  | 2026-02-20 |  |  | 50 | 21-Nov-25 A | 2026-04-22 | 02-Dec-25 A | 2026-02-20 | 2026-04-22
| A32490 | Purchase Order for Major Sub-ordered Materials |  | 2026-02-20 |  |  | 10 | 11-Dec-25 A | 2026-04-22 | 19-Dec-25 A | 2026-02-20 | 2026-04-22
| A32500 | Major Sub-ordered Materials Received by Vendor and Verified |  | 2026-02-20 |  |  | 35 | 20-Jan-26 A | 2026-04-22 | 2026-02-24 | 2026-02-24 | 2026-04-24 | 43
| A32510 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  | 2026-02-25 |  |  | 1 | 2026-02-25 | 2026-04-25 | 2026-02-25 | 2026-02-25 | 2026-04-26 | 74
| A32520 | Manufacturing / Ex Works (India/UAE) |  | 2026-02-26 |  |  | 169 | 2026-02-26 | 2026-04-26 | 2026-07-10 | 2026-07-10 | 2026-09-08 | 74
| A32530 | Complete Manufacturing & ready for Final Inspection |  | 2026-07-13 |  |  | 7 | 2026-07-13 | 2026-09-08 | 2026-07-21 | 2026-07-21 | 2026-09-16 | 41
| A32540 | Materials Successfully Inspected, Tested / Ex Work |  | 2026-07-22 |  |  | 7 | 2026-07-22 | 2026-09-17 | 2026-07-30 | 2026-07-30 | 2026-09-25 | 41
| A34270 | Delivery of Switchgear (MV & LV) |  | 2026-07-31 |  |  | 26 | 2026-07-31 | 2026-09-28 | 2026-08-20 | 2026-08-20 | 2026-10-18 | 74
| A22450 | Start Production |  |  |  |  | 0 | 17-Mar-25 A
| A22460 | Key Vendor Drawings / Data Approved |  | 2026-02-20 |  |  | 2 | 18-Mar-25 A | 2026-03-27 | 24-Mar-25 A | 2026-02-20 | 2026-03-27
| A22740 | Purchase Order for Major Sub-ordered Materials |  | 2026-02-20 |  |  | 2 | 25-Mar-25 A | 2026-03-27 | 31-Mar-25 A | 2026-02-20 | 2026-03-27
| A22760 | Major Sub-ordered Materials Received by Vendor and Verified |  | 2026-02-20 |  |  | 2 | 01-Apr-25 A | 2026-03-27 | 07-Apr-25 A | 2026-02-20 | 2026-03-27
| A24280 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  | 2026-02-20 |  |  | 3 | 08-Apr-25 A | 2026-03-27 | 14-Apr-25 A | 2026-02-20 | 2026-03-27
| A22470 | Manufacturing / Ex Works (India/UAE) |  | 2026-02-20 |  |  | 3 | 15-Apr-25 A | 2026-03-27 | 21-Apr-25 A | 2026-02-20 | 2026-03-27
| A22770 | Complete Manufacturing & ready for Final Inspection |  | 2026-02-20 |  |  | 2 | 22-Apr-25 A | 2026-03-27 | 28-Apr-25 A | 2026-02-20 | 2026-03-27
| A22780 | Materials Successfully Inspected, Tested / Ex Work |  | 2026-02-20 |  |  | 2 | 29-Apr-25 A | 2026-03-27 | 05-May-25 A | 2026-02-20 | 2026-03-27
| A22410 | Delivery of Material For Switchgear Modification |  | 2026-02-20 |  |  | 3 | 06-May-25 A | 2026-03-27 | 12-May-25 A | 2026-02-20 | 2026-03-27
| Variable Fequency Drives (VFDs) LV Qty = 03 |  |  | 2026-02-20 |  |  | 169 | 13-Aug-25 A | 2026-09-22 | 2026-03-19 | 2026-03-19 | 2026-10-19 | 152
| A34280 | Start Production |  |  |  |  | 0 | 13-Aug-25 A
| A32570 | Key Vendor Drawings / Data Approved |  | 2026-02-20 |  |  | 50 | 13-Aug-25 A | 2026-09-22 | 14-Aug-25 A | 2026-02-20 | 2026-09-22
| A32580 | Purchase Order for Major Sub-ordered Materials |  | 2026-02-20 |  |  | 10 | 15-Aug-25 A | 2026-09-22 | 16-Aug-25 A | 2026-02-20 | 2026-09-22
| A32590 | Major Sub-ordered Materials Received by Vendor and Verified |  | 2026-02-20 |  |  | 30 | 17-Aug-25 A | 2026-09-22 | 18-Aug-25 A | 2026-02-20 | 2026-09-22
| A32600 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  | 2026-02-20 |  |  | 1 | 19-Aug-25 A | 2026-09-22 | 19-Aug-25 A | 2026-02-20 | 2026-09-22
| A32610 | Manufacturing / Ex Works (India/UAE) |  | 2026-02-20 |  |  | 150 | 20-Aug-25 A | 2026-09-22 | 20-Aug-25 A | 2026-02-20 | 2026-09-22
| A32620 | Complete Manufacturing & ready for Final Inspection |  | 2026-02-20 |  |  | 7 | 20-Aug-25 A | 2026-09-22 | 21-Aug-25 A | 2026-02-20 | 2026-09-22
| A32630 | Materials Successfully Inspected, Tested / Ex Work |  | 2026-02-20 |  |  | 7 | 22-Aug-25 A | 2026-09-22 | 22-Aug-25 A | 2026-02-20 | 2026-09-22
| A34290 | Delivery of VFDs |  | 2026-02-20 |  |  | 35 | 2026-02-20 | 2026-09-22 | 2026-03-19 | 2026-03-19 | 2026-10-19 | 268
| A34150 | Start Production |  |  |  |  | 0 | 27-Oct-25 A
| A32030 | Key Vendor Drawings / Data Approved |  | 2026-02-20 |  |  | 50 | 19-Dec-25 A | 2026-06-11 | 26-Feb-26 A | 2026-02-20 | 2026-06-11
| A32040 | Purchase Order for Major Sub-ordered Materials |  | 2026-02-20 |  |  | 10 | 2026-02-20 | 2026-06-11 | 2026-03-05 | 2026-03-05 | 2026-06-24 | 79
| A32050 | Major Sub-ordered Materials Received by Vendor and Verified |  | 2026-03-06 |  |  | 30 | 2026-03-06 | 2026-06-25 | 2026-04-16 | 2026-04-16 | 2026-08-05 | 79
| A32060 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  | 2026-04-17 |  |  | 1 | 2026-04-17 | 2026-08-06 | 2026-04-17 | 2026-04-17 | 2026-08-07 | 139
| A32070 | Manufacturing / Ex Works (India/UAE) |  | 2026-04-18 |  |  | 94 | 2026-04-18 | 2026-08-07 | 2026-07-01 | 2026-07-01 | 2026-10-21 | 139
| A32080 | Complete Manufacturing & ready for Final Inspection |  | 2026-07-02 |  |  | 7 | 2026-07-02 | 2026-10-21 | 2026-07-10 | 2026-07-10 | 2026-10-29 | 79
| A32090 | Materials Successfully Inspected, Tested / Ex Work |  | 2026-07-13 |  |  | 7 | 2026-07-13 | 2026-10-30 | 2026-07-21 | 2026-07-21 | 2026-11-09 | 79
| A34160 | Delivery of Material in Warehouse HV Capacitor Bay |  | 2026-07-22 |  |  | 9 | 2026-07-22 | 2026-11-10 | 2026-07-28 | 2026-07-28 | 2026-11-16 | 139
| A34380 | Start Production |  |  |  |  | 0 | 06-Jun-25 A
| A33020 | Key Vendor Drawings / Data Approved |  | 2026-02-20 |  |  | 50 | 19-Dec-25 A | 2026-09-29 | 20-Dec-25 A | 2026-02-20 | 2026-09-29
| A33030 | Purchase Order for Major Sub-ordered Materials |  | 2026-02-20 |  |  | 10 | 22-Dec-25 A | 2026-09-29 | 27-Dec-25 A | 2026-02-20 | 2026-09-29
| A33040 | Major Sub-ordered Materials Received by Vendor and Verified |  | 2026-02-20 |  |  | 30 | 28-Dec-25 A | 2026-09-29 | 03-Jan-26 A | 2026-02-20 | 2026-09-29
| A33050 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  | 2026-02-20 |  |  | 1 | 02-Jan-26 A | 2026-09-29 | 10-Jan-26 A | 2026-02-20 | 2026-09-29
| A33060 | Manufacturing / Ex Works (India/UAE) |  | 2026-02-20 |  |  | 150 | 01-Jan-26 A | 2026-09-29 | 17-Jan-26 A | 2026-02-20 | 2026-09-29
| A33070 | Complete Manufacturing & ready for Final Inspection |  | 2026-02-20 |  |  | 7 | 2026-02-20 | 2026-09-29 | 2026-03-02 | 2026-03-02 | 2026-10-07 | 157
| A33080 | Materials Successfully Inspected, Tested / Ex Work |  | 2026-03-03 |  |  | 7 | 2026-03-03 | 2026-10-08 | 2026-03-11 | 2026-03-11 | 2026-10-16 | 157
| A34390 | Delivery of NGR Panel |  | 2026-03-12 |  |  | 35 | 2026-03-12 | 2026-10-17 | 2026-04-08 | 2026-04-08 | 2026-11-13 | 274
| A34400 | Start Production |  | 2026-03-18 |  |  | 0 | 2026-03-18 | 2026-05-25 |  |  |  | 84
| A33110 | Key Vendor Drawings / Data Approved |  | 2026-03-19 |  |  | 15 | 2026-03-19 | 2026-05-25 | 2026-04-08 | 2026-04-08 | 2026-06-12 | 47
| A33120 | Purchase Order for Major Sub-ordered Materials |  | 2026-04-08 |  |  | 10 | 2026-04-08 | 2026-06-15 | 2026-04-22 | 2026-04-22 | 2026-06-26 | 47
| A33130 | Major Sub-ordered Materials Received by Vendor and Verified |  | 2026-04-22 |  |  | 15 | 2026-04-22 | 2026-06-29 | 2026-05-13 | 2026-05-13 | 2026-07-17 | 47
| A33140 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  | 2026-05-13 |  |  | 1 | 2026-05-13 | 2026-07-18 | 2026-05-14 | 2026-05-14 | 2026-07-19 | 82
| A33150 | Manufacturing / Ex Works (India/UAE) |  | 2026-05-14 |  |  | 125 | 2026-05-14 | 2026-07-19 | 2026-08-22 | 2026-08-22 | 2026-10-27 | 82
| A33160 | Complete Manufacturing & ready for Final Inspection |  | 2026-08-24 |  |  | 7 | 2026-08-24 | 2026-10-27 | 2026-09-01 | 2026-09-01 | 2026-11-04 | 46
| A33170 | Materials Successfully Inspected, Tested / Ex Work |  | 2026-09-02 |  |  | 7 | 2026-09-02 | 2026-11-05 | 2026-09-10 | 2026-09-10 | 2026-11-13 | 46
| A34410 | Delivery of Interposing relay Panel |  | 2026-09-11 |  |  | 9 | 2026-09-11 | 2026-11-16 | 2026-09-17 | 2026-09-17 | 2026-11-22 | 83
| Construction and Pre-Commissioning |  |  | 2026-02-20 |  |  | 651 | 09-Jan-25 A | 2026-02-21 | 2027-07-01 | 2027-07-01 | 2027-07-20 | 13
| Construction/Pre-Commissioning |  |  | 2026-02-20 |  |  | 326 | 10-Jun-25 A | 2026-06-02 | 2026-12-21 | 2026-12-21 | 2027-01-03 | 9
| Green Field Works |  |  | 2026-02-20 |  |  | 326 | 10-Jun-25 A | 2026-06-02 | 2026-12-21 | 2026-12-21 | 2027-01-03 | 9
| A3250 | Complete Site Preparation and Grading works |  |  |  |  | 0 |  |  | 16-Jun-25 A
| CONS10 | Installation of Isolation Fence Plant Site |  | 2026-02-20 |  |  | 30 | 10-Jun-25 A | 2026-08-22 | 13-Aug-25 A | 2026-02-20 | 2026-08-22
| CONS | TSF Construction / Commence on SITE |  | 2026-02-20 |  |  | 100 | 01-Jul-25 A | 2026-08-22 | 15-Oct-25 A | 2026-02-20 | 2026-08-22
| Electrical & Instrumentation Works |  |  | 2026-05-09 |  |  | 161 | 2026-05-09 | 2026-06-02 | 2026-12-21 | 2026-12-21 | 2027-01-03 | 9
| A18510 | Cable Laying - Trenches |  | 2026-05-09 |  |  | 64 | 2026-05-09 | 2026-06-02 | 2026-07-21 | 2026-07-21 | 2026-08-15 | 21
| A3709 | E&I Bulk & Equipment Deliveries - Plant Site |  |  |  |  | 0 |  |  | 2026-09-24 | 2026-09-24 | 2026-10-26 | 40
| A3739 | Complete E&I Equipment / Panels Installation CCB &SIS |  |  |  |  | 0 |  |  | 2026-10-18 | 2026-10-18 | 2027-01-03 | 67
| A3889 | Electrical Works Plant Site (Cable trays, cable laying, termination, DBs, Jbs etc) |  | 2026-08-26 |  |  | 64 | 2026-08-26 | 2026-09-28 | 2026-11-08 | 2026-11-08 | 2026-12-10 | 28
| A3759 | Complete E&I Work at plant site |  |  |  |  | 0 |  |  | 2026-11-17 | 2026-11-17 | 2026-12-20 | 29
| A3909 | Instrumentation Works Plant Site (Control/Manual Valves, Gauges, TT, PT, DPT, PSVs, Switches etc) |  | 2026-09-27 |  |  | 44 | 2026-09-27 | 2026-10-31 | 2026-11-17 | 2026-11-17 | 2026-12-20 | 29
| A3719 | E&I Works (CCB & SIS) For cable trays and cable laying |  | 2026-09-26 |  |  | 75 | 2026-09-26 | 2026-10-08 | 2026-12-21 | 2026-12-21 | 2027-01-03 | 11
| A3749 | Complete Cable termination and loop test - Overall |  |  |  |  | 0 |  |  | 2026-12-21 | 2026-12-21 | 2027-01-03 | 11
| Accommodation and Messing |  |  | 2026-02-20 |  |  | 112 | 15-Apr-25 A | 2026-03-11 | 24-Jul-25 A | 2026-02-20 | 2026-03-11
| Mobilisation of Camp (Accommodation and Messing) |  |  | 2026-02-20 |  |  | 112 | 15-Apr-25 A | 2026-03-11 | 24-Jul-25 A | 2026-02-20 | 2026-03-11
| A61550 | TA - Mobilisation of Camp (Accommodation and messing) |  | 2026-02-20 |  |  | 4 | 15-Apr-25 A | 2026-03-11 | 20-Apr-25 A | 2026-02-20 | 2026-03-11
| A62210 | Main Scope - Mobilisation of Camp (Accommodation and messing) |  | 2026-02-20 |  |  | 4 | 22-Apr-25 A | 2026-03-11 | 24-Jul-25 A | 2026-02-20 | 2026-03-11
| Fabrication, Storage, Workshops (Temporary Facilities) |  |  | 2026-02-20 |  |  | 636 | 01-Apr-25 A | 2026-03-11 | 2027-07-01 | 2027-07-01 | 2027-07-20 | 16
| Mobilisation of Temporary Facilities |  |  | 2026-02-20 |  |  | 54 | 01-Apr-25 A | 2026-03-11 | 24-Oct-25 A | 2026-02-20 | 2026-03-11
| A61560 | Mobilisation of Temporary Facilities - TA |  | 2026-02-20 |  |  | 24 | 01-Apr-25 A | 2026-03-11 | 31-May-25 A | 2026-02-20 | 2026-03-11
| A62230 | Mobilisation of Temporary Facilities - Main Scope |  | 2026-02-20 |  |  | 24 | 01-Aug-25 A | 2026-03-11 | 24-Oct-25 A | 2026-02-20 | 2026-03-11
| Maintenance of Temporary Facilities |  |  | 2026-02-20 |  |  | 336 | 01-Nov-25 A | 2026-03-11 | 2027-03-18 | 2027-03-18 | 2027-04-06 | 16
| A62240 | Maintenance of Temporary Facilities - Q1 |  | 2026-02-20 |  |  | 24 | 01-Nov-25 A | 2026-03-11 | 18-Nov-25 A | 2026-02-20 | 2026-03-11
| A61570 | Maintenance of Temporary Facilities - Q2 |  | 2026-02-20 |  |  | 24 | 01-Jan-26 A | 2026-03-11 | 24-Jan-26 A | 2026-02-20 | 2026-03-11
| A62250 | Maintenance of Temporary Facilities - Q3 |  | 2026-04-11 |  |  | 24 | 2026-04-11 | 2026-04-29 | 2026-05-07 | 2026-05-07 | 2026-05-26 | 16
| A62260 | Maintenance of Temporary Facilities - Q4 |  | 2026-07-25 |  |  | 24 | 2026-07-25 | 2026-08-12 | 2026-08-20 | 2026-08-20 | 2026-09-08 | 16
| A62270 | Maintenance of Temporary Facilities - Q5 |  | 2026-11-07 |  |  | 24 | 2026-11-07 | 2026-11-25 | 2026-12-03 | 2026-12-03 | 2026-12-22 | 16
| A62280 | Maintenance of Temporary Facilities - Q6 |  | 2027-02-20 |  |  | 24 | 2027-02-20 | 2027-03-10 | 2027-03-18 | 2027-03-18 | 2027-04-06 | 16
| Demobilisation of Temporary Facilities |  |  | 2026-02-20 |  |  | 636 | 25-Jun-25 A | 2027-06-23 | 2027-07-01 | 2027-07-01 | 2027-07-20 | 16
| A61580 | Demobiisation of Temporary Facilities - TA |  | 2026-02-20 |  |  | 24 | 25-Jun-25 A | 2027-06-23 | 11-Jul-25 A | 2026-02-20 | 2027-06-23
| A62290 | Demobiisation of Temporary Facilities - Main Scope |  | 2027-06-05 |  |  | 24 | 2027-06-05 | 2027-06-23 | 2027-07-01 | 2027-07-01 | 2027-07-20 | 16
| Civil Construction |  |  | 2026-02-20 |  |  | 461 | 09-Jan-25 A | 2026-02-21 | 2027-01-11 | 2027-01-11 | 2027-01-20 | 7
| Site Preparation |  |  | 2026-02-20 |  |  | 78 | 01-Apr-25 A | 2026-03-11 | 15-Sep-25 A | 2026-02-20 | 2026-03-11
| A61590 | Site Preparation - TA |  | 2026-02-20 |  |  | 24 | 01-Apr-25 A | 2026-03-11 | 21-Jun-25 A | 2026-02-20 | 2026-03-11
| A62220 | Site Preparation - Main Scope |  | 2026-02-20 |  |  | 24 | 22-Aug-25 A | 2026-03-11 | 15-Sep-25 A | 2026-02-20 | 2026-03-11
| Fencing |  |  | 2026-02-20 |  |  | 24 | 17-Apr-25 A | 2026-03-11 | 22-Aug-25 A | 2026-02-20 | 2026-03-11
| A61600 | Fencing |  | 2026-02-20 |  |  | 24 | 17-Apr-25 A | 2026-03-11 | 22-Aug-25 A | 2026-02-20 | 2026-03-11
| Excavation and trenching |  |  | 2026-03-02 |  |  | 143 | 2026-03-02 | 2026-04-11 | 2026-08-15 | 2026-08-15 | 2026-10-04 | 43
| GF Sumps and Pits |  |  | 2026-03-07 |  |  | 136 | 2026-03-07 | 2026-05-06 | 2026-08-11 | 2026-08-11 | 2026-09-01 | 18
| Accidentally Oily Water Sump 70-TD-1407 |  |  | 2026-03-07 |  |  | 72 | 2026-03-07 | 2026-05-06 | 2026-05-28 | 2026-05-28 | 2026-07-28 | 52
| A26600 | Excavation |  | 2026-03-07 |  |  | 10 | 2026-03-07 | 2026-05-06 | 2026-03-17 | 2026-03-17 | 2026-05-17 | 52
| A26610 | Surface leveling and compaction |  | 2026-03-18 |  |  | 2 | 2026-03-18 | 2026-05-18 | 2026-03-19 | 2026-03-19 | 2026-05-19 | 52
| A26620 | Lean concrete |  | 2026-03-21 |  |  | 2 | 2026-03-21 | 2026-05-20 | 2026-03-22 | 2026-03-22 | 2026-05-21 | 52
| A26630 | Water proofing and bitumen coating/sheet |  | 2026-03-30 |  |  | 4 | 2026-03-30 | 2026-05-30 | 2026-04-02 | 2026-04-02 | 2026-06-02 | 52
| A26640 | Formworks |  | 2026-04-04 |  |  | 10 | 2026-04-04 | 2026-06-03 | 2026-04-14 | 2026-04-14 | 2026-06-14 | 52
| A26650 | Rebar works |  | 2026-04-04 |  |  | 10 | 2026-04-04 | 2026-06-03 | 2026-04-14 | 2026-04-14 | 2026-06-14 | 52
| A26660 | Concrete pouring |  | 2026-04-18 |  |  | 10 | 2026-04-18 | 2026-06-17 | 2026-04-28 | 2026-04-28 | 2026-06-28 | 52
| A26670 | Concrete Curing |  | 2026-04-19 |  |  | 14 | 2026-04-19 | 2026-06-18 | 2026-05-04 | 2026-05-04 | 2026-07-04 | 52
| A26680 | Formwork removal |  | 2026-04-21 |  |  | 14 | 2026-04-21 | 2026-06-21 | 2026-05-06 | 2026-05-06 | 2026-07-06 | 52
| A26690 | Protective Coating |  | 2026-05-07 |  |  | 12 | 2026-05-07 | 2026-07-07 | 2026-05-20 | 2026-05-20 | 2026-07-20 | 52
| A26700 | Back filling and compaction in layers |  | 2026-05-21 |  |  | 7 | 2026-05-21 | 2026-07-21 | 2026-05-28 | 2026-05-28 | 2026-07-28 | 52
| Oil Contaminated Water Sump 70-TD-1408 |  |  | 2026-03-25 |  |  | 72 | 2026-03-25 | 2026-05-06 | 2026-06-16 | 2026-06-16 | 2026-07-28 | 36
| A26710 | Excavation |  | 2026-03-25 |  |  | 10 | 2026-03-25 | 2026-05-06 | 2026-04-05 | 2026-04-05 | 2026-05-17 | 36
| A26720 | Surface leveling and compaction |  | 2026-04-06 |  |  | 2 | 2026-04-06 | 2026-05-18 | 2026-04-07 | 2026-04-07 | 2026-05-19 | 36
| A26730 | Lean concrete |  | 2026-04-08 |  |  | 2 | 2026-04-08 | 2026-05-20 | 2026-04-09 | 2026-04-09 | 2026-05-21 | 36
| A26740 | Water proofing and bitumen coating/sheet |  | 2026-04-18 |  |  | 4 | 2026-04-18 | 2026-05-30 | 2026-04-21 | 2026-04-21 | 2026-06-02 | 36
| A26750 | Formworks |  | 2026-04-22 |  |  | 10 | 2026-04-22 | 2026-06-03 | 2026-05-03 | 2026-05-03 | 2026-06-14 | 36
| A26760 | Rebar works |  | 2026-04-22 |  |  | 10 | 2026-04-22 | 2026-06-03 | 2026-05-03 | 2026-05-03 | 2026-06-14 | 36
| A26770 | Concrete pouring |  | 2026-05-06 |  |  | 10 | 2026-05-06 | 2026-06-17 | 2026-05-17 | 2026-05-17 | 2026-06-28 | 36
| A26780 | Concrete Curing |  | 2026-05-07 |  |  | 14 | 2026-05-07 | 2026-06-18 | 2026-05-23 | 2026-05-23 | 2026-07-04 | 36
| A26790 | Formwork removal |  | 2026-05-10 |  |  | 14 | 2026-05-10 | 2026-06-21 | 2026-05-25 | 2026-05-25 | 2026-07-06 | 36
| A26800 | Protective Coating |  | 2026-05-26 |  |  | 12 | 2026-05-26 | 2026-07-07 | 2026-06-08 | 2026-06-08 | 2026-07-20 | 36
| A26810 | Back filling and compaction in layers |  | 2026-06-09 |  |  | 7 | 2026-06-09 | 2026-07-21 | 2026-06-16 | 2026-06-16 | 2026-07-28 | 36
| Sanitary Waste Water Sump 70-TD-1409 |  |  | 2026-05-10 |  |  | 47 | 2026-05-10 | 2026-06-04 | 2026-07-02 | 2026-07-02 | 2026-07-28 | 22
| A26820 | Excavation |  | 2026-05-10 |  |  | 7 | 2026-05-10 | 2026-06-04 | 2026-05-17 | 2026-05-17 | 2026-06-11 | 22
| A26830 | Surface leveling and compaction |  | 2026-05-18 |  |  | 1 | 2026-05-18 | 2026-06-13 | 2026-05-18 | 2026-05-18 | 2026-06-13 | 22
| A26840 | Lean concrete |  | 2026-05-19 |  |  | 1 | 2026-05-19 | 2026-06-14 | 2026-05-19 | 2026-05-19 | 2026-06-14 | 22
| A26850 | Water proofing and bitumen coating/sheet |  | 2026-05-27 |  |  | 2 | 2026-05-27 | 2026-06-22 | 2026-05-28 | 2026-05-28 | 2026-06-23 | 22
| A26860 | Formworks |  | 2026-05-30 |  |  | 10 | 2026-05-30 | 2026-06-24 | 2026-06-09 | 2026-06-09 | 2026-07-05 | 22
| A26870 | Rebar works |  | 2026-05-30 |  |  | 10 | 2026-05-30 | 2026-06-24 | 2026-06-09 | 2026-06-09 | 2026-07-05 | 22
| A26880 | Concrete pouring |  | 2026-06-06 |  |  | 7 | 2026-06-06 | 2026-07-01 | 2026-06-13 | 2026-06-13 | 2026-07-08 | 22
| A26900 | Formwork removal |  | 2026-06-09 |  |  | 7 | 2026-06-09 | 2026-07-05 | 2026-06-16 | 2026-06-16 | 2026-07-12 | 22
| A26890 | Concrete Curing |  | 2026-06-07 |  |  | 14 | 2026-06-07 | 2026-07-02 | 2026-06-22 | 2026-06-22 | 2026-07-18 | 22
| A26910 | Protective Coating |  | 2026-06-17 |  |  | 7 | 2026-06-17 | 2026-07-13 | 2026-06-24 | 2026-06-24 | 2026-07-20 | 22
| A26920 | Back filling and compaction in layers |  | 2026-06-25 |  |  | 7 | 2026-06-25 | 2026-07-21 | 2026-07-02 | 2026-07-02 | 2026-07-28 | 22
| PSA2 Slope Drum Pit |  |  | 2026-03-15 |  |  | 60 | 2026-03-15 | 2026-05-20 | 2026-05-23 | 2026-05-23 | 2026-07-28 | 57
| A26930 | Excavation |  | 2026-03-15 |  |  | 7 | 2026-03-15 | 2026-05-20 | 2026-03-22 | 2026-03-22 | 2026-05-27 | 57
| A26940 | Surface leveling and compaction |  | 2026-03-23 |  |  | 2 | 2026-03-23 | 2026-05-28 | 2026-03-24 | 2026-03-24 | 2026-05-30 | 57
| A26950 | Lean concrete |  | 2026-03-25 |  |  | 2 | 2026-03-25 | 2026-05-31 | 2026-03-26 | 2026-03-26 | 2026-06-01 | 57
| A26960 | Water proofing and bitumen coating/sheet |  | 2026-04-04 |  |  | 4 | 2026-04-04 | 2026-06-09 | 2026-04-07 | 2026-04-07 | 2026-06-13 | 57
| A26970 | Formworks |  | 2026-04-08 |  |  | 7 | 2026-04-08 | 2026-06-14 | 2026-04-15 | 2026-04-15 | 2026-06-21 | 57
| A26980 | Rebar works |  | 2026-04-08 |  |  | 7 | 2026-04-08 | 2026-06-14 | 2026-04-15 | 2026-04-15 | 2026-06-21 | 57
| A26990 | Concrete pouring |  | 2026-04-22 |  |  | 7 | 2026-04-22 | 2026-06-28 | 2026-04-29 | 2026-04-29 | 2026-07-05 | 57
| A27010 | Formwork removal |  | 2026-04-26 |  |  | 10 | 2026-04-26 | 2026-07-01 | 2026-05-06 | 2026-05-06 | 2026-07-12 | 57
| A27000 | Concrete Curing |  | 2026-04-23 |  |  | 14 | 2026-04-23 | 2026-06-29 | 2026-05-09 | 2026-05-09 | 2026-07-14 | 57
| A27020 | Protective Coating |  | 2026-05-07 |  |  | 7 | 2026-05-07 | 2026-07-13 | 2026-05-14 | 2026-05-14 | 2026-07-20 | 57
| A27030 | Back filling and compaction in layers |  | 2026-05-16 |  |  | 7 | 2026-05-16 | 2026-07-21 | 2026-05-23 | 2026-05-23 | 2026-07-28 | 57
| Cooling Water Valve Pit |  |  | 2026-06-07 |  |  | 57 | 2026-06-07 | 2026-06-28 | 2026-08-11 | 2026-08-11 | 2026-09-01 | 18
| A27040 | Excavation |  | 2026-06-07 |  |  | 7 | 2026-06-07 | 2026-06-28 | 2026-06-14 | 2026-06-14 | 2026-07-05 | 18
| A27050 | Surface leveling and compaction |  | 2026-06-15 |  |  | 2 | 2026-06-15 | 2026-07-06 | 2026-06-16 | 2026-06-16 | 2026-07-07 | 18
| A27060 | Lean concrete |  | 2026-06-17 |  |  | 2 | 2026-06-17 | 2026-07-08 | 2026-06-18 | 2026-06-18 | 2026-07-09 | 18
| A27070 | Water proofing and bitumen coating/sheet |  | 2026-06-27 |  |  | 4 | 2026-06-27 | 2026-07-18 | 2026-06-30 | 2026-06-30 | 2026-07-21 | 18
| A27080 | Formworks |  | 2026-07-01 |  |  | 10 | 2026-07-01 | 2026-07-22 | 2026-07-12 | 2026-07-12 | 2026-08-02 | 18
| A27090 | Rebar works |  | 2026-07-01 |  |  | 10 | 2026-07-01 | 2026-07-22 | 2026-07-12 | 2026-07-12 | 2026-08-02 | 18
| A27100 | Concrete pouring |  | 2026-07-15 |  |  | 7 | 2026-07-15 | 2026-08-05 | 2026-07-22 | 2026-07-22 | 2026-08-12 | 18
| A27120 | Formwork removal |  | 2026-07-19 |  |  | 7 | 2026-07-19 | 2026-08-09 | 2026-07-26 | 2026-07-26 | 2026-08-16 | 18
| A27110 | Concrete Curing |  | 2026-07-16 |  |  | 14 | 2026-07-16 | 2026-08-06 | 2026-08-01 | 2026-08-01 | 2026-08-22 | 18
| A27130 | Protective Coating |  | 2026-07-27 |  |  | 7 | 2026-07-27 | 2026-08-17 | 2026-08-03 | 2026-08-03 | 2026-08-24 | 18
| A27140 | Back filling and compaction in layers |  | 2026-08-04 |  |  | 7 | 2026-08-04 | 2026-08-25 | 2026-08-11 | 2026-08-11 | 2026-09-01 | 18
| GF UG Piping and Trenches |  |  | 2026-03-17 |  |  | 130 | 2026-03-17 | 2026-04-11 | 2026-08-15 | 2026-08-15 | 2026-09-08 | 21
| A3440 | Trenching for UG Piping |  | 2026-04-11 |  |  | 27 | 2026-04-11 | 2026-04-20 | 2026-05-11 | 2026-05-11 | 2026-05-20 | 8
| A18530 | Excavation and Valve Pits for Fire Water Line |  | 2026-04-11 |  |  | 59 | 2026-04-11 | 2026-04-20 | 2026-06-17 | 2026-06-17 | 2026-06-27 | 8
| A3450 | Complete UG Piping & Backfilling |  | 2026-05-12 |  |  | 59 | 2026-05-12 | 2026-05-21 | 2026-07-19 | 2026-07-19 | 2026-07-28 | 8
| Cables |  |  | 2026-03-17 |  |  | 130 | 2026-03-17 | 2026-04-11 | 2026-08-15 | 2026-08-15 | 2026-09-08 | 21
| A18460 | Direct Buried Trenches for Power and Instrumentation cables |  | 2026-04-11 |  |  | 21 | 2026-04-11 | 2026-05-16 | 2026-05-04 | 2026-05-04 | 2026-06-08 | 30
| A3460 | Concrete Trenches for Electrical and Instrumentation Cable |  | 2026-03-17 |  |  | 45 | 2026-03-17 | 2026-04-11 | 2026-05-07 | 2026-05-07 | 2026-06-01 | 21
| A18480 | Backfilling of E&I trenches |  | 2026-07-22 |  |  | 21 | 2026-07-22 | 2026-08-16 | 2026-08-15 | 2026-08-15 | 2026-09-08 | 21
| BF Trenches |  |  | 2026-03-02 |  |  | 70 | 2026-03-02 | 2026-07-08 | 2026-05-23 | 2026-05-23 | 2026-10-04 | 116
| A21800 | Duct Banks/Road Crossing |  | 2026-03-02 |  |  | 35 | 2026-03-02 | 2026-07-08 | 2026-04-12 | 2026-04-12 | 2026-08-18 | 110
| A21770 | Direct buried trenches - BF |  | 2026-04-12 |  |  | 35 | 2026-04-12 | 2026-08-25 | 2026-05-23 | 2026-05-23 | 2026-10-04 | 116
| Foundations |  |  | 2026-02-20 |  |  | 324 | 03-Jul-25 A | 2026-02-21 | 2027-01-11 | 2027-01-11 | 2027-01-20 | 7
| A62510 | New Activity |  |  |  |  | 5 | 2026-02-20 |  | 2026-02-26
| GF SIS Building Structure Works |  |  | 2026-02-20 |  |  | 163 | 02-Sep-25 A | 2026-03-14 | 2026-05-02 | 2026-05-02 | 2026-05-23 | 18
| Sub-Structure |  |  | 2026-02-20 |  |  | 114 | 02-Sep-25 A | 2026-03-14 | 2026-03-09 | 2026-03-09 | 2026-03-30 | 18
| A1590 | Foundation Works (Excavation, PCC & RCC) |  | 2026-02-20 |  |  | 30 | 02-Sep-25 A | 2026-03-14 | 01-Jan-26 A | 2026-02-20 | 2026-03-14
| A1600 | RCC Columns and Walls Upto FFL |  | 2026-02-20 |  |  | 48 | 16-Dec-25 A | 2026-03-14 | 16-Jan-26 A | 2026-02-20 | 2026-03-14
| A1610 | Waterproofing & Backfilling |  | 2026-02-21 |  |  | 27 | 16-Dec-25 A | 2026-03-14 | 2026-02-28 | 2026-02-28 | 2026-03-21 | 18
| A1620 | Plinth Beams |  | 2026-02-21 |  |  | 15 | 16-Dec-25 A | 2026-03-14 | 2026-03-09 | 2026-03-09 | 2026-03-30 | 18
| Super-Structure |  |  | 2026-03-10 |  |  | 46 | 2026-03-10 | 2026-03-31 | 2026-05-02 | 2026-05-02 | 2026-05-23 | 18
| A1500 | RCC Columns and Walls Upto First Slab |  | 2026-03-10 |  |  | 30 | 2026-03-10 | 2026-03-31 | 2026-04-13 | 2026-04-13 | 2026-05-04 | 18
| A1510 | First Slab and Beams |  | 2026-03-29 |  |  | 30 | 2026-03-29 | 2026-04-19 | 2026-05-02 | 2026-05-02 | 2026-05-23 | 18
| GF Sub-Station Sub-Structure |  |  | 2026-02-20 |  |  | 383 | 25-Aug-25 A | 2026-03-14 | 2027-01-04 | 2027-01-04 | 2027-01-20 | 14
| A26360 | Foundation Works (Excavation, PCC & RCC) |  | 2026-02-20 |  |  | 21 | 25-Aug-25 A | 2026-03-14 | 16-Sep-25 A | 2026-02-20 | 2026-03-14
| A26380 | Waterproofing & Backfilling (handingover to Precast) |  | 2026-02-20 |  |  | 20 | 15-Sep-25 A | 2026-03-18 | 22-Sep-25 A | 2026-02-20 | 2026-03-18
| A26370 | RCC Base & Columns Upto FFL |  | 2026-02-20 |  |  | 20 | 21-Nov-25 A | 2026-03-18 | 10-Feb-26 A | 2026-02-20 | 2026-03-18
| A1030 | Plinth Beams (Casting Suti) |  | 2026-02-28 |  |  | 24 | 15-Dec-25 A | 2026-05-07 | 2026-03-26 | 2026-03-26 | 2026-06-03 | 59
| GF Sub-Station Super-Structure |  |  | 2026-02-21 |  |  | 273 | 24-Jan-26 A | 2026-03-18 | 2027-01-04 | 2027-01-04 | 2027-01-20 | 14
| Ground Floor - Cellar Area |  |  | 2026-02-21 |  |  | 30 | 24-Jan-26 A | 2026-03-18 | 2026-03-26 | 2026-03-26 | 2026-04-21 | 22
| A26390 | RCC Columns and Walls Upto First Slab |  | 2026-02-21 |  |  | 30 | 24-Jan-26 A | 2026-03-18 | 2026-03-26 | 2026-03-26 | 2026-04-21 | 22
| A26400 | First Slab and Beams |  | 2026-02-21 |  |  | 30 | 2026-02-21 | 2026-03-18 | 2026-03-26 | 2026-03-26 | 2026-04-21 | 22
| First Floor |  |  | 2026-03-11 |  |  | 257 | 2026-03-11 | 2026-04-06 | 2027-01-04 | 2027-01-04 | 2027-01-20 | 14
| A26410 | RCC Columns Upto 2nd Slab |  | 2026-03-11 |  |  | 27 | 2026-03-11 | 2026-04-06 | 2026-04-11 | 2026-04-11 | 2026-05-06 | 22
| A26420 | 2nd Slab and Beams |  | 2026-03-26 |  |  | 38 | 2026-03-26 | 2026-04-21 | 2026-05-09 | 2026-05-09 | 2026-06-03 | 22
| C1059 | Punch List Close Out (Construction / Mechanical) |  | 2026-12-22 |  |  | 12 | 2026-12-22 | 2027-01-07 | 2027-01-04 | 2027-01-04 | 2027-01-20 | 14
| GF Transformers Structure Works |  |  | 2026-02-21 |  |  | 91 | 2026-02-21 | 2026-03-17 | 2026-06-06 | 2026-06-06 | 2026-06-27 | 18
| A26460 | Foundation Works (Excavation, PCC & RCC) |  | 2026-02-21 |  |  | 30 | 2026-02-21 | 2026-03-17 | 2026-03-26 | 2026-03-26 | 2026-04-20 | 21
| A1150 | RCC Walls Upto FFL |  | 2026-03-25 |  |  | 30 | 2026-03-25 | 2026-04-19 | 2026-04-28 | 2026-04-28 | 2026-05-23 | 21
| A26470 | Waterproofing & Backfilling |  | 2026-04-08 |  |  | 30 | 2026-04-08 | 2026-05-24 | 2026-05-12 | 2026-05-12 | 2026-06-27 | 39
| A1190 | RCC Walls above Ground |  | 2026-05-03 |  |  | 30 | 2026-05-03 | 2026-05-24 | 2026-06-06 | 2026-06-06 | 2026-06-27 | 18
| Roads and Pavement Construction |  |  | 2026-07-20 |  |  | 151 | 2026-07-20 | 2026-07-29 | 2027-01-11 | 2027-01-11 | 2027-01-20 | 8
| A6860 | Subgarde and Sub-Base for Road |  | 2026-07-20 |  |  | 51 | 2026-07-20 | 2026-07-29 | 2026-09-16 | 2026-09-16 | 2026-09-26 | 8
| A6880 | Concrete Flooring on Plant Side |  | 2026-09-17 |  |  | 49 | 2026-09-17 | 2026-09-27 | 2026-11-12 | 2026-11-12 | 2026-11-22 | 8
| A6870 | Base Course and Asphalt working |  | 2026-11-14 |  |  | 51 | 2026-11-14 | 2026-11-23 | 2027-01-11 | 2027-01-11 | 2027-01-20 | 8
| BF Foundation |  |  | 2026-02-21 |  |  | 90 | 2026-02-21 | 2026-07-23 | 2026-06-04 | 2026-06-04 | 2026-11-04 | 131
| BFW3000 | General Civil Work - Equipment Foundations & Pipe Support (TBC) |  | 2026-02-21 |  |  | 90 | 2026-02-21 | 2026-07-23 | 2026-06-04 | 2026-06-04 | 2026-11-04 | 131
| GF Foundations |  |  | 2026-02-20 |  |  | 210 | 03-Jul-25 A | 2026-02-21 | 2026-06-25 | 2026-06-25 | 2026-08-22 | 48
| FG/OG Compressor and Shleter Foundation including shelter concrete trench |  |  | 2026-02-20 |  |  | 129 | 31-Jul-25 A | 2026-02-21 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 0
| A15660 | Excavation |  | 2026-02-20 |  |  | 18 | 31-Jul-25 A | 2026-02-21 | 23-Aug-25 A | 2026-02-20 | 2026-02-21
| A15670 | Surface leveling and compaction |  | 2026-02-20 |  |  | 18 | 11-Aug-25 A | 2026-02-21 | 25-Aug-25 A | 2026-02-20 | 2026-02-21
| A15740 | Lean concrete |  | 2026-02-20 |  |  | 18 | 25-Aug-25 A | 2026-02-21 | 30-Aug-25 A | 2026-02-20 | 2026-02-21
| A15750 | Water proofing and bitumen coating/sheet |  | 2026-02-21 |  |  | 18 | 15-Oct-25 A | 2026-02-21 | 2026-02-28 | 2026-02-28 | 2026-02-28 | 0
| A15790 | Formworks |  | 2026-02-21 |  |  | 36 | 19-Dec-25 A | 2026-02-21 | 2026-02-28 | 2026-02-28 | 2026-02-28 | 0
| A15840 | Rebar works |  | 2026-02-21 |  |  | 36 | 15-Dec-25 A | 2026-02-21 | 2026-02-28 | 2026-02-28 | 2026-02-28 | 0
| A15860 | Concrete Curing |  | 2026-02-21 |  |  | 42 | 27-Dec-25 A | 2026-02-21 | 2026-03-04 | 2026-03-04 | 2026-03-04 | 0
| A15850 | Concrete pouring |  | 2026-02-21 |  |  | 36 | 19-Dec-25 A | 2026-02-21 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 0
| A15870 | Formwork removal |  | 2026-02-21 |  |  | 15 | 2026-02-21 | 2026-02-21 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 0
| A15880 | Protective Coating |  | 2026-02-28 |  |  | 15 | 2026-02-28 | 2026-02-28 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 0
| A15890 | Back filling and compaction in layers |  | 2026-03-07 |  |  | 15 | 2026-03-07 | 2026-03-07 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 0
| Pipe Rack (Primary SR81 & Secondary SR80) Foundation |  |  | 2026-02-20 |  |  | 93 | 23-Dec-25 A | 2026-03-02 | 2026-04-09 | 2026-04-09 | 2026-04-19 | 8
| A26240 | Excavation - Pipe Rack (SR81 & SR80) |  | 2026-02-20 |  |  | 24 | 23-Dec-25 A | 2026-03-02 | 20-Jan-26 A | 2026-02-20 | 2026-03-02
| A26250 | Surface leveling and compaction |  | 2026-02-21 |  |  | 24 | 30-Dec-25 A | 2026-03-02 | 2026-02-26 | 2026-02-26 | 2026-03-08 | 8
| A26260 | Lean concrete |  | 2026-02-21 |  |  | 24 | 06-Jan-26 A | 2026-03-02 | 2026-02-26 | 2026-02-26 | 2026-03-08 | 8
| A26270 | Water proofing and bitumen coating/sheet |  | 2026-02-21 |  |  | 24 | 13-Jan-26 A | 2026-03-02 | 2026-03-05 | 2026-03-05 | 2026-03-15 | 8
| A26280 | Formworks |  | 2026-02-21 |  |  | 21 | 2026-02-21 | 2026-03-02 | 2026-03-16 | 2026-03-16 | 2026-03-25 | 8
| A26290 | Rebar works |  | 2026-02-21 |  |  | 21 | 2026-02-21 | 2026-03-02 | 2026-03-16 | 2026-03-16 | 2026-03-25 | 8
| A26300 | Concrete Pouring |  | 2026-02-28 |  |  | 21 | 2026-02-28 | 2026-03-09 | 2026-03-23 | 2026-03-23 | 2026-04-01 | 8
| A26310 | Concrete Curing |  | 2026-03-01 |  |  | 21 | 2026-03-01 | 2026-03-10 | 2026-03-24 | 2026-03-24 | 2026-04-02 | 8
| A26320 | Formwork removal |  | 2026-03-03 |  |  | 21 | 2026-03-03 | 2026-03-12 | 2026-03-26 | 2026-03-26 | 2026-04-05 | 8
| A26330 | Protective Coating |  | 2026-03-10 |  |  | 21 | 2026-03-10 | 2026-03-19 | 2026-04-02 | 2026-04-02 | 2026-04-12 | 8
| A26340 | Back filling and compaction in layers |  | 2026-03-17 |  |  | 21 | 2026-03-17 | 2026-03-26 | 2026-04-09 | 2026-04-09 | 2026-04-19 | 8
| OG Compressor Discharge Drip Leg (13-SP-7004) |  |  | 2026-03-28 |  |  | 49 | 2026-03-28 | 2026-05-03 | 2026-05-23 | 2026-05-23 | 2026-08-16 | 72
| A24810 | Excavation |  | 2026-03-28 |  |  | 4 | 2026-03-28 | 2026-05-03 | 2026-03-31 | 2026-03-31 | 2026-05-06 | 31
| A24820 | Surface leveling and compaction |  | 2026-04-01 |  |  | 4 | 2026-04-01 | 2026-06-24 | 2026-04-05 | 2026-04-05 | 2026-06-29 | 72
| A24830 | Lean concrete |  | 2026-04-06 |  |  | 4 | 2026-04-06 | 2026-06-29 | 2026-04-09 | 2026-04-09 | 2026-07-04 | 72
| A24840 | Water proofing and bitumen coating/sheet |  | 2026-04-11 |  |  | 8 | 2026-04-11 | 2026-07-04 | 2026-04-19 | 2026-04-19 | 2026-07-13 | 72
| A24850 | Formworks |  | 2026-04-20 |  |  | 7 | 2026-04-20 | 2026-07-13 | 2026-04-27 | 2026-04-27 | 2026-07-21 | 72
| A24860 | Rebar works |  | 2026-04-20 |  |  | 7 | 2026-04-20 | 2026-07-13 | 2026-04-27 | 2026-04-27 | 2026-07-21 | 72
| A24870 | Concrete pouring |  | 2026-04-28 |  |  | 4 | 2026-04-28 | 2026-07-21 | 2026-05-02 | 2026-05-02 | 2026-07-26 | 72
| A24890 | Formwork removal |  | 2026-04-30 |  |  | 4 | 2026-04-30 | 2026-07-23 | 2026-05-04 | 2026-05-04 | 2026-07-28 | 72
| A24880 | Concrete Curing |  | 2026-04-28 |  |  | 14 | 2026-04-28 | 2026-07-21 | 2026-05-13 | 2026-05-13 | 2026-08-06 | 72
| A24900 | Protective Coating |  | 2026-05-05 |  |  | 8 | 2026-05-05 | 2026-07-28 | 2026-05-13 | 2026-05-13 | 2026-08-06 | 72
| A24910 | Back filling and compaction in layers |  | 2026-05-14 |  |  | 8 | 2026-05-14 | 2026-08-06 | 2026-05-23 | 2026-05-23 | 2026-08-16 | 72
| PSA2 Package by Linde ( 10 Vessels) |  |  | 2026-02-20 |  |  | 151 | 03-Jul-25 A | 2026-05-24 | 20-Feb-26 A | 2026-02-20 | 2026-05-26
| A24920 | Excavation |  | 2026-02-20 |  |  | 6 | 03-Jul-25 A | 2026-05-24 | 15-Jul-25 A | 2026-02-20 | 2026-05-24
| A24930 | Surface leveling and compaction |  | 2026-02-20 |  |  | 12 | 11-Jul-25 A | 2026-05-24 | 25-Jul-25 A | 2026-02-20 | 2026-05-24
| A24940 | Lean concrete |  | 2026-02-20 |  |  | 6 | 01-Sep-25 A | 2026-05-24 | 18-Sep-25 A | 2026-02-20 | 2026-05-24
| A24950 | Water proofing and bitumen coating/sheet |  | 2026-02-20 |  |  | 6 | 19-Sep-25 A | 2026-05-24 | 26-Sep-25 A | 2026-02-20 | 2026-05-24
| A24960 | Formworks |  | 2026-02-20 |  |  | 24 | 27-Sep-25 A | 2026-05-26 | 01-Feb-26 A | 2026-02-20 | 2026-05-26
| A24980 | Concrete pouring |  | 2026-02-20 |  |  | 2 | 04-Nov-25 A | 2026-05-26 | 03-Feb-26 A | 2026-02-20 | 2026-05-26
| A24970 | Rebar works |  | 2026-02-20 |  |  | 24 | 22-Oct-25 A | 2026-05-24 | 05-Feb-26 A | 2026-02-20 | 2026-05-24
| A25000 | Formwork removal |  | 2026-02-20 |  |  | 10 | 05-Feb-26 A | 2026-05-26 | 05-Feb-26 A | 2026-02-20 | 2026-05-26
| A25010 | Protective Coating |  | 2026-02-20 |  |  | 12 | 01-Jan-26 A | 2026-05-26 | 15-Feb-26 A | 2026-02-20 | 2026-05-26
| A24990 | Concrete Curing |  | 2026-02-20 |  |  | 6 | 19-Dec-25 A | 2026-05-26 | 16-Feb-26 A | 2026-02-20 | 2026-05-26
| A25020 | Back filling and compaction in layers |  | 2026-02-20 |  |  | 21 | 01-Feb-26 A | 2026-05-26 | 20-Feb-26 A | 2026-02-20 | 2026-05-26
| OG Comp After Cooler ( 13-HE-709) |  |  | 2026-04-01 |  |  | 39 | 2026-04-01 | 2026-05-07 | 2026-05-16 | 2026-05-16 | 2026-08-08 | 71
| A25030 | Excavation |  | 2026-04-01 |  |  | 3 | 2026-04-01 | 2026-05-07 | 2026-04-04 | 2026-04-04 | 2026-05-10 | 31
| A25040 | Surface leveling and compaction |  | 2026-04-05 |  |  | 2 | 2026-04-05 | 2026-06-27 | 2026-04-06 | 2026-04-06 | 2026-06-29 | 71
| A25050 | Lean concrete |  | 2026-04-07 |  |  | 2 | 2026-04-07 | 2026-06-29 | 2026-04-08 | 2026-04-08 | 2026-07-01 | 71
| A25060 | Water proofing and bitumen coating/sheet |  | 2026-04-16 |  |  | 2 | 2026-04-16 | 2026-07-08 | 2026-04-18 | 2026-04-18 | 2026-07-11 | 71
| A25070 | Formworks |  | 2026-04-19 |  |  | 7 | 2026-04-19 | 2026-07-11 | 2026-04-26 | 2026-04-26 | 2026-07-19 | 71
| A25080 | Rebar works |  | 2026-04-19 |  |  | 7 | 2026-04-19 | 2026-07-12 | 2026-04-26 | 2026-04-26 | 2026-07-20 | 72
| A25090 | Concrete pouring |  | 2026-04-27 |  |  | 7 | 2026-04-27 | 2026-07-19 | 2026-05-04 | 2026-05-04 | 2026-07-27 | 71
| A25110 | Formwork removal |  | 2026-04-30 |  |  | 7 | 2026-04-30 | 2026-07-22 | 2026-05-07 | 2026-05-07 | 2026-07-30 | 71
| A25120 | Protective Coating |  | 2026-05-05 |  |  | 4 | 2026-05-05 | 2026-07-27 | 2026-05-09 | 2026-05-09 | 2026-08-01 | 71
| A25100 | Concrete Curing |  | 2026-04-28 |  |  | 14 | 2026-04-28 | 2026-07-20 | 2026-05-13 | 2026-05-13 | 2026-08-05 | 71
| A25130 | Back filling and compaction in layers |  | 2026-05-10 |  |  | 6 | 2026-05-10 | 2026-08-01 | 2026-05-16 | 2026-05-16 | 2026-08-08 | 71
| FG Comp 2nd Stage Discharge Drum(13-VV-707) |  |  | 2026-04-05 |  |  | 51 | 2026-04-05 | 2026-05-11 | 2026-06-02 | 2026-06-02 | 2026-07-23 | 44
| A25140 | Excavation |  | 2026-04-05 |  |  | 3 | 2026-04-05 | 2026-05-11 | 2026-04-07 | 2026-04-07 | 2026-05-13 | 31
| A25150 | Surface leveling and compaction |  | 2026-04-08 |  |  | 2 | 2026-04-08 | 2026-05-30 | 2026-04-09 | 2026-04-09 | 2026-05-31 | 44
| A25160 | Lean concrete |  | 2026-04-11 |  |  | 1 | 2026-04-11 | 2026-06-01 | 2026-04-11 | 2026-04-11 | 2026-06-01 | 44
| A25170 | Water proofing and bitumen coating/sheet |  | 2026-04-19 |  |  | 4 | 2026-04-19 | 2026-06-09 | 2026-04-22 | 2026-04-22 | 2026-06-13 | 44
| A25180 | Formworks |  | 2026-04-23 |  |  | 7 | 2026-04-23 | 2026-06-14 | 2026-04-30 | 2026-04-30 | 2026-06-21 | 44
| A25190 | Rebar works |  | 2026-04-23 |  |  | 7 | 2026-04-23 | 2026-06-14 | 2026-04-30 | 2026-04-30 | 2026-06-21 | 44
| A25200 | Concrete pouring |  | 2026-05-07 |  |  | 7 | 2026-05-07 | 2026-06-28 | 2026-05-14 | 2026-05-14 | 2026-07-05 | 44
| A25220 | Formwork removal |  | 2026-05-11 |  |  | 7 | 2026-05-11 | 2026-07-01 | 2026-05-18 | 2026-05-18 | 2026-07-08 | 44
| A25210 | Concrete Curing |  | 2026-05-09 |  |  | 14 | 2026-05-09 | 2026-06-29 | 2026-05-24 | 2026-05-24 | 2026-07-14 | 44
| A25230 | Protective Coating |  | 2026-05-19 |  |  | 6 | 2026-05-19 | 2026-07-09 | 2026-05-25 | 2026-05-25 | 2026-07-15 | 44
| A25240 | Back filling and compaction in layers |  | 2026-05-26 |  |  | 7 | 2026-05-26 | 2026-07-16 | 2026-06-02 | 2026-06-02 | 2026-07-23 | 44
| FG Comp 1st Stage Suction Drum(13-VV-705) |  |  | 2026-04-08 |  |  | 52 | 2026-04-08 | 2026-05-14 | 2026-06-07 | 2026-06-07 | 2026-08-01 | 47
| A25360 | Excavation |  | 2026-04-08 |  |  | 3 | 2026-04-08 | 2026-05-14 | 2026-04-11 | 2026-04-11 | 2026-05-17 | 31
| A25370 | Surface leveling and compaction |  | 2026-04-12 |  |  | 2 | 2026-04-12 | 2026-06-06 | 2026-04-13 | 2026-04-13 | 2026-06-07 | 47
| A25380 | Lean concrete |  | 2026-04-14 |  |  | 2 | 2026-04-14 | 2026-06-08 | 2026-04-15 | 2026-04-15 | 2026-06-09 | 47
| A25390 | Water proofing and bitumen coating/sheet |  | 2026-04-23 |  |  | 4 | 2026-04-23 | 2026-06-17 | 2026-04-27 | 2026-04-27 | 2026-06-21 | 47
| A25400 | Formworks |  | 2026-04-28 |  |  | 7 | 2026-04-28 | 2026-06-22 | 2026-05-05 | 2026-05-05 | 2026-06-29 | 47
| A25410 | Rebar works |  | 2026-04-28 |  |  | 7 | 2026-04-28 | 2026-06-22 | 2026-05-05 | 2026-05-05 | 2026-06-29 | 47
| A25420 | Concrete pouring |  | 2026-05-12 |  |  | 7 | 2026-05-12 | 2026-07-06 | 2026-05-19 | 2026-05-19 | 2026-07-13 | 47
| A25440 | Formwork removal |  | 2026-05-16 |  |  | 7 | 2026-05-16 | 2026-07-09 | 2026-05-23 | 2026-05-23 | 2026-07-16 | 47
| A25430 | Concrete Curing |  | 2026-05-13 |  |  | 14 | 2026-05-13 | 2026-07-07 | 2026-05-28 | 2026-05-28 | 2026-07-22 | 47
| A25450 | Protective Coating |  | 2026-05-24 |  |  | 6 | 2026-05-24 | 2026-07-18 | 2026-05-30 | 2026-05-30 | 2026-07-23 | 47
| A25460 | Back filling and compaction in layers |  | 2026-05-31 |  |  | 7 | 2026-05-31 | 2026-07-25 | 2026-06-07 | 2026-06-07 | 2026-08-01 | 47
| FG Comp 2nd Stage Suction Drum(13-VV-706) |  |  | 2026-04-12 |  |  | 52 | 2026-04-12 | 2026-05-18 | 2026-06-10 | 2026-06-10 | 2026-07-19 | 33
| A25470 | Excavation |  | 2026-04-12 |  |  | 3 | 2026-04-12 | 2026-05-18 | 2026-04-14 | 2026-04-14 | 2026-05-20 | 31
| A25480 | Surface leveling and compaction |  | 2026-04-15 |  |  | 2 | 2026-04-15 | 2026-05-24 | 2026-04-16 | 2026-04-16 | 2026-05-25 | 33
| A25490 | Lean concrete |  | 2026-04-18 |  |  | 2 | 2026-04-18 | 2026-05-26 | 2026-04-19 | 2026-04-19 | 2026-05-27 | 33
| A25500 | Water proofing and bitumen coating/sheet |  | 2026-04-27 |  |  | 4 | 2026-04-27 | 2026-06-04 | 2026-04-30 | 2026-04-30 | 2026-06-08 | 33
| A25510 | Formworks |  | 2026-05-02 |  |  | 7 | 2026-05-02 | 2026-06-09 | 2026-05-09 | 2026-05-09 | 2026-06-16 | 33
| A25520 | Rebar works |  | 2026-05-02 |  |  | 7 | 2026-05-02 | 2026-06-09 | 2026-05-09 | 2026-05-09 | 2026-06-16 | 33
| A25530 | Concrete pouring |  | 2026-05-16 |  |  | 7 | 2026-05-16 | 2026-06-23 | 2026-05-23 | 2026-05-23 | 2026-06-30 | 33
| A25550 | Formwork removal |  | 2026-05-19 |  |  | 7 | 2026-05-19 | 2026-06-27 | 2026-05-26 | 2026-05-26 | 2026-07-04 | 33
| A25540 | Concrete Curing |  | 2026-05-17 |  |  | 14 | 2026-05-17 | 2026-06-24 | 2026-06-01 | 2026-06-01 | 2026-07-09 | 33
| A25560 | Protective Coating |  | 2026-05-27 |  |  | 6 | 2026-05-27 | 2026-07-05 | 2026-06-02 | 2026-06-02 | 2026-07-11 | 33
| A25570 | Back filling and compaction in layers |  | 2026-06-03 |  |  | 7 | 2026-06-03 | 2026-07-12 | 2026-06-10 | 2026-06-10 | 2026-07-19 | 33
| PSA2 Slope Drum ( 70-VV-1415) |  |  | 2026-04-15 |  |  | 46 | 2026-04-15 | 2026-05-21 | 2026-06-07 | 2026-06-07 | 2026-08-22 | 64
| A25580 | Excavation |  | 2026-04-15 |  |  | 4 | 2026-04-15 | 2026-05-21 | 2026-04-19 | 2026-04-19 | 2026-05-25 | 31
| A25590 | Surface leveling and compaction |  | 2026-04-20 |  |  | 4 | 2026-04-20 | 2026-07-04 | 2026-04-23 | 2026-04-23 | 2026-07-08 | 64
| A25600 | Lean concrete |  | 2026-04-25 |  |  | 4 | 2026-04-25 | 2026-07-08 | 2026-04-28 | 2026-04-28 | 2026-07-13 | 64
| A25610 | Water proofing and bitumen coating/sheet |  | 2026-04-29 |  |  | 7 | 2026-04-29 | 2026-07-13 | 2026-05-06 | 2026-05-06 | 2026-07-21 | 64
| A25620 | Formworks |  | 2026-05-07 |  |  | 7 | 2026-05-07 | 2026-07-21 | 2026-05-14 | 2026-05-14 | 2026-07-29 | 64
| A25630 | Rebar works |  | 2026-05-07 |  |  | 7 | 2026-05-07 | 2026-07-21 | 2026-05-14 | 2026-05-14 | 2026-07-29 | 64
| A25640 | Concrete pouring |  | 2026-05-16 |  |  | 4 | 2026-05-16 | 2026-07-29 | 2026-05-19 | 2026-05-19 | 2026-08-03 | 64
| A25660 | Formwork removal |  | 2026-05-18 |  |  | 4 | 2026-05-18 | 2026-08-01 | 2026-05-21 | 2026-05-21 | 2026-08-05 | 64
| A25670 | Protective Coating |  | 2026-05-23 |  |  | 7 | 2026-05-23 | 2026-08-05 | 2026-05-30 | 2026-05-30 | 2026-08-13 | 64
| A25650 | Concrete Curing |  | 2026-05-16 |  |  | 14 | 2026-05-16 | 2026-07-29 | 2026-05-31 | 2026-05-31 | 2026-08-15 | 64
| A25680 | Back filling and compaction in layers |  | 2026-05-31 |  |  | 7 | 2026-05-31 | 2026-08-13 | 2026-06-07 | 2026-06-07 | 2026-08-22 | 64
| FG Comp After Cooler ( 13-HE-704) |  |  | 2026-04-20 |  |  | 40 | 2026-04-20 | 2026-05-26 | 2026-06-04 | 2026-06-04 | 2026-07-11 | 31
| A25690 | Excavation |  | 2026-04-20 |  |  | 3 | 2026-04-20 | 2026-05-26 | 2026-04-22 | 2026-04-22 | 2026-05-28 | 31
| A25700 | Surface leveling and compaction |  | 2026-04-23 |  |  | 2 | 2026-04-23 | 2026-05-30 | 2026-04-25 | 2026-04-25 | 2026-05-31 | 31
| A25710 | Lean concrete |  | 2026-04-26 |  |  | 2 | 2026-04-26 | 2026-06-01 | 2026-04-27 | 2026-04-27 | 2026-06-02 | 31
| A25720 | Water proofing and bitumen coating/sheet |  | 2026-05-05 |  |  | 2 | 2026-05-05 | 2026-06-10 | 2026-05-06 | 2026-05-06 | 2026-06-11 | 31
| A25730 | Formworks |  | 2026-05-07 |  |  | 7 | 2026-05-07 | 2026-06-13 | 2026-05-14 | 2026-05-14 | 2026-06-20 | 31
| A25740 | Rebar works |  | 2026-05-07 |  |  | 7 | 2026-05-07 | 2026-06-13 | 2026-05-14 | 2026-05-14 | 2026-06-20 | 31
| A25750 | Concrete pouring |  | 2026-05-14 |  |  | 7 | 2026-05-14 | 2026-06-20 | 2026-05-21 | 2026-05-21 | 2026-06-27 | 31
| A25770 | Formwork removal |  | 2026-05-18 |  |  | 7 | 2026-05-18 | 2026-06-23 | 2026-05-25 | 2026-05-25 | 2026-06-30 | 31
| A25780 | Protective Coating |  | 2026-05-21 |  |  | 8 | 2026-05-21 | 2026-06-27 | 2026-05-30 | 2026-05-30 | 2026-07-05 | 31
| A25760 | Concrete Curing |  | 2026-05-16 |  |  | 14 | 2026-05-16 | 2026-06-21 | 2026-05-31 | 2026-05-31 | 2026-07-06 | 31
| A25790 | Back filling and compaction in layers |  | 2026-05-31 |  |  | 5 | 2026-05-31 | 2026-07-06 | 2026-06-04 | 2026-06-04 | 2026-07-11 | 31
| FG Comp Interstage Cooler ( 13-HE-703) |  |  | 2026-04-23 |  |  | 40 | 2026-04-23 | 2026-06-09 | 2026-06-08 | 2026-06-08 | 2026-07-25 | 40
| A26490 | Excavation |  | 2026-04-23 |  |  | 3 | 2026-04-23 | 2026-06-09 | 2026-04-26 | 2026-04-26 | 2026-06-11 | 40
| A26500 | Surface leveling and compaction |  | 2026-04-27 |  |  | 2 | 2026-04-27 | 2026-06-13 | 2026-04-28 | 2026-04-28 | 2026-06-14 | 40
| A26510 | Lean concrete |  | 2026-04-29 |  |  | 2 | 2026-04-29 | 2026-06-15 | 2026-04-30 | 2026-04-30 | 2026-06-16 | 40
| A26520 | Water proofing and bitumen coating/sheet |  | 2026-05-09 |  |  | 2 | 2026-05-09 | 2026-06-24 | 2026-05-10 | 2026-05-10 | 2026-06-25 | 40
| A26530 | Formworks |  | 2026-05-11 |  |  | 7 | 2026-05-11 | 2026-06-27 | 2026-05-18 | 2026-05-18 | 2026-07-04 | 40
| A26540 | Rebar works |  | 2026-05-11 |  |  | 7 | 2026-05-11 | 2026-06-27 | 2026-05-18 | 2026-05-18 | 2026-07-04 | 40
| A26550 | Concrete pouring |  | 2026-05-18 |  |  | 7 | 2026-05-18 | 2026-07-04 | 2026-05-25 | 2026-05-25 | 2026-07-11 | 40
| A26570 | Formwork removal |  | 2026-05-21 |  |  | 7 | 2026-05-21 | 2026-07-08 | 2026-05-28 | 2026-05-28 | 2026-07-15 | 41
| A26580 | Protective Coating |  | 2026-05-26 |  |  | 7 | 2026-05-26 | 2026-07-12 | 2026-06-02 | 2026-06-02 | 2026-07-19 | 40
| A26560 | Concrete Curing |  | 2026-05-19 |  |  | 14 | 2026-05-19 | 2026-07-05 | 2026-06-03 | 2026-06-03 | 2026-07-20 | 40
| A26590 | Back filling and compaction in layers |  | 2026-06-03 |  |  | 5 | 2026-06-03 | 2026-07-20 | 2026-06-08 | 2026-06-08 | 2026-07-25 | 40
| OG Comp 2nd Stage Suction Drum(13-VV-713) |  |  | 2026-04-27 |  |  | 52 | 2026-04-27 | 2026-06-22 | 2026-06-25 | 2026-06-25 | 2026-08-22 | 48
| A25800 | Excavation |  | 2026-04-27 |  |  | 3 | 2026-04-27 | 2026-06-22 | 2026-04-29 | 2026-04-29 | 2026-06-25 | 48
| A25810 | Surface leveling and compaction |  | 2026-04-30 |  |  | 2 | 2026-04-30 | 2026-06-25 | 2026-05-02 | 2026-05-02 | 2026-06-28 | 48
| A25820 | Lean concrete |  | 2026-05-03 |  |  | 2 | 2026-05-03 | 2026-06-28 | 2026-05-04 | 2026-05-04 | 2026-06-30 | 48
| A25830 | Water proofing and bitumen coating/sheet |  | 2026-05-12 |  |  | 4 | 2026-05-12 | 2026-07-07 | 2026-05-16 | 2026-05-16 | 2026-07-12 | 48
| A25840 | Formworks |  | 2026-05-17 |  |  | 7 | 2026-05-17 | 2026-07-12 | 2026-05-24 | 2026-05-24 | 2026-07-20 | 48
| A25850 | Rebar works |  | 2026-05-17 |  |  | 7 | 2026-05-17 | 2026-07-12 | 2026-05-24 | 2026-05-24 | 2026-07-20 | 48
| A25860 | Concrete pouring |  | 2026-05-31 |  |  | 7 | 2026-05-31 | 2026-07-26 | 2026-06-07 | 2026-06-07 | 2026-08-03 | 48
| A25880 | Formwork removal |  | 2026-06-03 |  |  | 7 | 2026-06-03 | 2026-07-29 | 2026-06-10 | 2026-06-10 | 2026-08-06 | 48
| A25870 | Concrete Curing |  | 2026-06-01 |  |  | 14 | 2026-06-01 | 2026-07-27 | 2026-06-16 | 2026-06-16 | 2026-08-12 | 48
| A25890 | Protective Coating |  | 2026-06-11 |  |  | 6 | 2026-06-11 | 2026-08-06 | 2026-06-17 | 2026-06-17 | 2026-08-13 | 48
| A25900 | Back filling and compaction in layers |  | 2026-06-18 |  |  | 7 | 2026-06-18 | 2026-08-13 | 2026-06-25 | 2026-06-25 | 2026-08-22 | 48
| A26020 | Excavation |  | 2026-02-20 |  |  | 3 | 31-Dec-25 A | 2026-05-14 | 15-Jan-26 A | 2026-02-20 | 2026-05-14
| A26030 | Surface leveling and compaction |  | 2026-02-20 |  |  | 2 | 10-Jan-26 A | 2026-06-27 | 17-Jan-26 A | 2026-02-20 | 2026-06-27
| A26040 | Lean concrete |  | 2026-02-20 |  |  | 2 | 19-Jan-26 A | 2026-06-27 | 21-Jan-26 A | 2026-02-20 | 2026-06-27
| A26050 | Water proofing and bitumen coating/sheet |  | 2026-02-21 |  |  | 4 | 22-Jan-26 A | 2026-06-27 | 2026-02-24 | 2026-02-24 | 2026-07-01 | 109
| A26060 | Formworks |  | 2026-02-24 |  |  | 15 | 2026-02-24 | 2026-07-01 | 2026-03-14 | 2026-03-14 | 2026-07-19 | 109
| A26070 | Rebar works |  | 2026-02-24 |  |  | 15 | 2026-02-24 | 2026-07-01 | 2026-03-14 | 2026-03-14 | 2026-07-19 | 109
| A26080 | Concrete pouring |  | 2026-03-14 |  |  | 7 | 2026-03-14 | 2026-07-19 | 2026-03-22 | 2026-03-22 | 2026-07-27 | 109
| A26090 | Concrete Curing |  | 2026-03-14 |  |  | 14 | 2026-03-14 | 2026-07-19 | 2026-03-30 | 2026-03-30 | 2026-08-04 | 109
| A26100 | Formwork removal |  | 2026-03-16 |  |  | 14 | 2026-03-16 | 2026-07-21 | 2026-04-01 | 2026-04-01 | 2026-08-06 | 109
| A26110 | Protective Coating |  | 2026-04-01 |  |  | 6 | 2026-04-01 | 2026-08-06 | 2026-04-08 | 2026-04-08 | 2026-08-13 | 109
| A26120 | Back filling and compaction in layers |  | 2026-04-08 |  |  | 7 | 2026-04-08 | 2026-08-13 | 2026-04-16 | 2026-04-16 | 2026-08-22 | 109
| OG Compressor Interstage Cooler (13-HE-708) |  |  | 2026-02-20 |  |  | 40 | 01-Jan-26 A | 2026-03-29 | 2026-04-02 | 2026-04-02 | 2026-08-09 | 109
| A26130 | Excavation |  | 2026-02-20 |  |  | 3 | 01-Jan-26 A | 2026-03-29 | 23-Jan-26 A | 2026-02-20 | 2026-03-29
| A26140 | Surface leveling and compaction |  | 2026-02-21 |  |  | 2 | 2026-02-21 | 2026-03-29 | 2026-02-22 | 2026-02-22 | 2026-03-30 | 31
| A26150 | Lean concrete |  | 2026-02-23 |  |  | 2 | 2026-02-23 | 2026-03-31 | 2026-02-24 | 2026-02-24 | 2026-04-01 | 31
| A26160 | Water proofing and bitumen coating/sheet |  | 2026-03-04 |  |  | 2 | 2026-03-04 | 2026-04-09 | 2026-03-05 | 2026-03-05 | 2026-04-11 | 31
| A26170 | Formworks |  | 2026-03-07 |  |  | 15 | 2026-03-07 | 2026-04-12 | 2026-03-23 | 2026-03-23 | 2026-04-28 | 31
| A26180 | Rebar works |  | 2026-03-07 |  |  | 15 | 2026-03-07 | 2026-04-12 | 2026-03-23 | 2026-03-23 | 2026-04-28 | 31
| A26190 | Concrete pouring |  | 2026-03-14 |  |  | 12 | 2026-03-14 | 2026-04-19 | 2026-03-26 | 2026-03-26 | 2026-05-02 | 31
| A26220 | Protective Coating |  | 2026-03-22 |  |  | 6 | 2026-03-22 | 2026-07-27 | 2026-03-28 | 2026-03-28 | 2026-08-03 | 109
| A26210 | Formwork removal |  | 2026-03-17 |  |  | 12 | 2026-03-17 | 2026-07-23 | 2026-03-30 | 2026-03-30 | 2026-08-06 | 110
| A26230 | Back filling and compaction in layers |  | 2026-03-29 |  |  | 4 | 2026-03-29 | 2026-08-03 | 2026-04-01 | 2026-04-01 | 2026-08-08 | 109
| A26200 | Concrete Curing |  | 2026-03-15 |  |  | 17 | 2026-03-15 | 2026-07-20 | 2026-04-02 | 2026-04-02 | 2026-08-09 | 109
| Structural Steel and Shades |  |  | 2026-02-20 |  |  | 451 | 09-Mar-25 A | 2026-03-27 | 2026-09-26 | 2026-09-26 | 2027-01-06 | 88
| TA Prefabrication of Steel Structure for BFW |  |  | 2026-02-20 |  |  | 24 | 09-Mar-25 A | 2026-03-27 | 18-May-25 A | 2026-02-20 | 2026-03-27
| A61610 | TA prefabrication of steel structure for BFW |  | 2026-02-20 |  |  | 24 | 09-Mar-25 A | 2026-03-27 | 18-May-25 A | 2026-02-20 | 2026-03-27
| TA Erection of Steel Structure for BFW |  |  | 2026-02-20 |  |  | 20 | 19-Apr-25 A | 2026-03-27 | 24-May-25 A | 2026-02-20 | 2026-03-27
| A23330 | Erection of Steel Structure of BFW Preheater - Pre TA ( By external Subcontractor) |  | 2026-02-20 |  |  | 20 | 19-Apr-25 A | 2026-03-27 | 24-May-25 A | 2026-02-20 | 2026-03-27
| BF Structure Steel |  |  | 2026-04-29 |  |  | 39 | 2026-04-29 | 2026-09-21 | 2026-06-14 | 2026-06-14 | 2026-11-04 | 124
| BFW4020 | Structure Installation (Platform on the existing Piperack + strengthen) |  | 2026-04-29 |  |  | 39 | 2026-04-29 | 2026-09-21 | 2026-06-14 | 2026-06-14 | 2026-11-04 | 124
| GF Steel Works |  |  | 2026-05-19 |  |  | 112 | 2026-05-19 | 2026-05-19 | 2026-09-26 | 2026-09-26 | 2027-01-06 | 88
| A17820 | Pipe Rack SR81 - Structure Installation |  | 2026-06-28 |  |  | 65 | 2026-06-28 | 2026-06-28 | 2026-09-10 | 2026-09-10 | 2026-09-10 | 0
| A17810 | Compressors Area- Steel Structure Erection |  | 2026-05-19 |  |  | 99 | 2026-05-19 | 2026-05-19 | 2026-09-10 | 2026-09-10 | 2026-09-10 | 0
| A18420 | Secondary Pipe Rack (SR80) Structure installation |  | 2026-08-15 |  |  | 24 | 2026-08-15 | 2026-11-04 | 2026-09-10 | 2026-09-10 | 2026-12-01 | 70
| A23500 | Piping Platforms |  | 2026-08-12 |  |  | 26 | 2026-08-12 | 2026-08-12 | 2026-09-10 | 2026-09-10 | 2026-09-10 | 0
| A23510 | Transformer Shed - Sub Station Building |  | 2026-09-01 |  |  | 22 | 2026-09-01 | 2026-12-13 | 2026-09-26 | 2026-09-26 | 2027-01-06 | 88
| External Finishes |  |  | 2026-07-18 |  |  | 72 | 2026-07-18 | 2026-10-29 | 2026-10-08 | 2026-10-08 | 2027-01-20 | 89
| A61620 | External Finishing |  | 2026-07-18 |  |  | 72 | 2026-07-18 | 2026-10-29 | 2026-10-08 | 2026-10-08 | 2027-01-20 | 89
| Internal Finishes |  |  | 2026-02-21 |  |  | 209 | 2026-02-21 | 2026-06-25 | 2026-10-21 | 2026-10-21 | 2027-01-20 | 78
| GF SIS Building Architectural Works |  |  | 2026-02-21 |  |  | 141 | 2026-02-21 | 2026-07-07 | 2026-08-03 | 2026-08-03 | 2026-10-07 | 56
| A1580 | PCC Flooring Works |  | 2026-02-21 |  |  | 26 | 2026-02-21 | 2026-07-14 | 2026-03-22 | 2026-03-22 | 2026-08-12 | 123
| A1660 | Floor Finshes (Tiling, Skirting & Dado etc.) |  | 2026-03-23 |  |  | 48 | 2026-03-23 | 2026-08-13 | 2026-05-17 | 2026-05-17 | 2026-10-07 | 123
| A1540 | Block Works and E&I Conduiting Works |  | 2026-05-03 |  |  | 35 | 2026-05-03 | 2026-07-07 | 2026-06-11 | 2026-06-11 | 2026-08-16 | 56
| A1570 | Roof Treatments |  | 2026-05-17 |  |  | 29 | 2026-05-17 | 2026-09-05 | 2026-06-18 | 2026-06-18 | 2026-10-07 | 95
| A1550 | Plaster Works |  | 2026-05-24 |  |  | 47 | 2026-05-24 | 2026-07-28 | 2026-07-16 | 2026-07-16 | 2026-09-20 | 56
| A1560 | Painting Works |  | 2026-06-16 |  |  | 42 | 2026-06-16 | 2026-08-20 | 2026-08-03 | 2026-08-03 | 2026-10-07 | 56
| GF Transformers Architectural Works |  |  | 2026-05-20 |  |  | 133 | 2026-05-20 | 2026-08-18 | 2026-10-21 | 2026-10-21 | 2027-01-20 | 78
| A1260 | Installation of Fence and Doors |  | 2026-06-07 |  |  | 22 | 2026-06-07 | 2026-09-13 | 2026-07-01 | 2026-07-01 | 2026-10-07 | 84
| A1240 | Painting External Works |  | 2026-05-20 |  |  | 44 | 2026-05-20 | 2026-08-18 | 2026-07-09 | 2026-07-09 | 2026-10-07 | 77
| A1250 | Foundation for E&I Support Structure |  | 2026-06-07 |  |  | 32 | 2026-06-07 | 2026-09-01 | 2026-07-13 | 2026-07-13 | 2026-10-07 | 74
| A1270 | Steel Structure / Corrugated Sheet Installation |  | 2026-09-24 |  |  | 24 | 2026-09-24 | 2026-12-24 | 2026-10-21 | 2026-10-21 | 2027-01-20 | 78
| GF Sub-Station Architectural Works |  |  | 2026-03-28 |  |  | 102 | 2026-03-28 | 2026-06-25 | 2026-07-23 | 2026-07-23 | 2027-01-20 | 155
| A1630 | E&I Support Structure |  | 2026-03-28 |  |  | 23 | 2026-03-28 | 2026-10-31 | 2026-04-22 | 2026-04-22 | 2026-11-25 | 186
| A1640 | Flooring works |  | 2026-04-23 |  |  | 30 | 2026-04-23 | 2026-11-26 | 2026-05-27 | 2026-05-27 | 2026-12-30 | 186
| A1650 | Installation of Fence and Doors |  | 2026-05-28 |  |  | 18 | 2026-05-28 | 2026-12-31 | 2026-06-17 | 2026-06-17 | 2027-01-20 | 186
| A26430 | Block Works and E&I Conduiting Works |  | 2026-04-11 |  |  | 48 | 2026-04-11 | 2026-06-25 | 2026-06-04 | 2026-06-04 | 2026-08-19 | 65
| A1180 | PCC Flooring Works |  | 2026-05-16 |  |  | 27 | 2026-05-16 | 2026-08-09 | 2026-06-15 | 2026-06-15 | 2026-09-08 | 73
| A1090 | Plaster Works |  | 2026-04-26 |  |  | 48 | 2026-04-26 | 2026-07-11 | 2026-06-20 | 2026-06-20 | 2026-09-03 | 65
| A26440 | Roof Treatments |  | 2026-05-23 |  |  | 34 | 2026-05-23 | 2026-08-30 | 2026-06-30 | 2026-06-30 | 2026-10-07 | 85
| A1200 | Floor Finshes (Tiling, Skirting & Dado etc.) |  | 2026-06-16 |  |  | 25 | 2026-06-16 | 2026-09-09 | 2026-07-14 | 2026-07-14 | 2026-10-07 | 73
| A26450 | Painting Works (Release for Electrical Equipments) |  | 2026-06-04 |  |  | 43 | 2026-06-04 | 2026-08-19 | 2026-07-23 | 2026-07-23 | 2026-10-07 | 65
| Topographic |  |  | 2026-02-20 |  |  | 71 | 09-Jan-25 A | 2026-02-21 | 23-May-25 A | 2026-02-20 | 2026-02-21
| Topographic/UG Survey |  |  | 2026-02-20 |  |  | 71 | 09-Jan-25 A | 2026-02-21 | 22-May-25 A | 2026-02-20 | 2026-02-21
| A56190 | TBE for Topo,UG & Getechnical Survey_IFR |  | 2026-02-20 |  |  | 5 | 09-Jan-25 A | 2026-02-21 | 15-Jan-25 A | 2026-02-20 | 2026-02-21
| A56200 | TBE for Topo,UG & Getechnical Survey_RCC |  | 2026-02-20 |  |  | 13 | 16-Jan-25 A | 2026-02-21 | 10-Feb-25 A | 2026-02-20 | 2026-02-21
| A28960 | TBE for Topo,UG & Getechnical Survey_IFD/IFC |  | 2026-02-20 |  |  | 5 | 11-Feb-25 A | 2026-02-21 | 01-Mar-25 A | 2026-02-20 | 2026-02-21
| E1080 | TBE & PO issuance of Geotech / UG Scanning |  | 2026-02-20 |  |  | 6 | 02-Mar-25 A | 2026-02-21 | 20-Mar-25 A | 2026-02-20 | 2026-02-21
| E1110 | CICPA Passes for Geotech Sub Contractor |  | 2026-02-20 |  |  | 8 | 21-Mar-25 A | 2026-02-21 | 17-Apr-25 A | 2026-02-20 | 2026-02-21
| E1070 | Topo/ UG Scanning Survey |  | 2026-02-20 |  |  | 4 | 18-Apr-25 A | 2026-02-21 | 30-Apr-25 A | 2026-02-20 | 2026-02-21
| E1090 | Mobilization of Geotech / UG Scanning |  | 2026-02-20 |  |  | 4 | 01-May-25 A | 2026-02-21 | 08-May-25 A | 2026-02-20 | 2026-02-21
| E1060 | Geotech / Survery of Site |  | 2026-02-20 |  |  | 4 | 09-May-25 A | 2026-02-21 | 15-May-25 A | 2026-02-20 | 2026-02-21
| E1100 | Reports of Getech Investigation / UG Scanning |  | 2026-02-20 |  |  | 4 | 16-May-25 A | 2026-02-21 | 22-May-25 A | 2026-02-20 | 2026-02-21
| Geotech/ Topographic/UG Survey |  |  | 2026-02-20 |  |  | 60 | 11-Feb-25 A | 2026-02-21 | 23-May-25 A | 2026-02-20 | 2026-02-21
| E1000 | RFQ of Geotech / UG Scanning |  | 2026-02-20 |  |  | 4 | 11-Feb-25 A | 2026-02-21 | 01-Mar-25 A | 2026-02-20 | 2026-02-21
| E1010 | TBE & PO issuance of Geotech / UG Scanning |  | 2026-02-20 |  |  | 6 | 02-Mar-25 A | 2026-02-21 | 20-Mar-25 A | 2026-02-20 | 2026-02-21
| E1050 | CICPA Passes for Geotech Sub Contractor |  | 2026-02-20 |  |  | 12 | 21-Mar-25 A | 2026-02-21 | 17-Apr-25 A | 2026-02-20 | 2026-02-21
| E1020 | Mobilization of Geotech / UG Scanning |  | 2026-02-20 |  |  | 4 | 01-May-25 A | 2026-02-21 | 08-May-25 A | 2026-02-20 | 2026-02-21
| E1030 | Geotech / Survery of Site |  | 2026-02-20 |  |  | 8 | 10-May-25 A | 2026-02-21 | 16-May-25 A | 2026-02-20 | 2026-02-21
| E1040 | Reports of Getech Investigation / UG Scanning |  | 2026-02-20 |  |  | 8 | 17-May-25 A | 2026-02-21 | 23-May-25 A | 2026-02-20 | 2026-02-21
| Piling (No required) |  |  | 2026-02-20 |  |  | 196 | 20-Jun-25 A | 2026-02-21 | 20-Jun-25 A | 2026-02-20 | 2026-03-02
| Piling Works |  |  | 2026-02-20 |  |  | 196 | 20-Jun-25 A | 2026-02-21 | 20-Jun-25 A | 2026-02-20 | 2026-03-02
| A15550 | Piling Work (Compressors, Sheds & Equipment) |  | 2026-02-20 |  |  | 69 | 20-Jun-25 A | 2026-02-21 | 20-Jun-25 A | 2026-02-20 | 2026-02-21
| A15570 | Piling Works - Pipe Racks and OG Buffer Drum |  | 2026-02-20 |  |  | 28 | 20-Jun-25 A | 2026-03-02 | 20-Jun-25 A | 2026-02-20 | 2026-03-02
| A15610 | Piling work PSA2 Unit (10 Vessels) |  | 2026-02-20 |  |  | 22 | 20-Jun-25 A | 2026-03-02 | 20-Jun-25 A | 2026-02-20 | 2026-03-02
| A15650 | Test Piles (including curing time) |  | 2026-02-20 |  |  | 23 | 20-Jun-25 A | 2026-02-21 | 20-Jun-25 A | 2026-02-20 | 2026-02-21
| A15690 | Data for Test pile |  |  |  |  | 0 |  |  | 20-Jun-25 A
| A15720 | PO for Piling Contractor |  | 2026-02-20 |  |  | 12 | 20-Jun-25 A | 2026-02-21 | 20-Jun-25 A | 2026-02-20 | 2026-02-21
| A15730 | Mobilization of piling contractor |  | 2026-02-20 |  |  | 16 | 20-Jun-25 A | 2026-02-21 | 20-Jun-25 A | 2026-02-20 | 2026-02-21
| A23610 | Mobilization for Production Piles |  | 2026-02-20 |  |  | 12 | 20-Jun-25 A | 2026-02-21 | 20-Jun-25 A | 2026-02-20 | 2026-02-21
| Mechanical Construction |  |  | 2026-02-20 |  |  | 509 | 05-Mar-25 A | 2026-03-24 | 2027-01-17 | 2027-01-17 | 2027-07-20 | 132
| Equipment erection and installation |  |  | 2026-02-20 |  |  | 354 | 19-Apr-25 A | 2026-03-24 | 2026-12-01 | 2026-12-01 | 2027-01-20 | 36
| HVAC Works |  |  | 2026-07-12 |  |  | 69 | 2026-07-12 | 2026-11-02 | 2026-09-29 | 2026-09-29 | 2027-01-20 | 97
| A18570 | Fabrication and installation of ductwork inside the building |  | 2026-07-12 |  |  | 26 | 2026-07-12 | 2026-11-02 | 2026-08-10 | 2026-08-10 | 2026-12-01 | 97
| A18770 | Installation of piping inside and outside the building |  | 2026-07-12 |  |  | 26 | 2026-07-12 | 2026-11-02 | 2026-08-10 | 2026-08-10 | 2026-12-01 | 97
| A18580 | Fabrication and installation of ductwork outside the building |  | 2026-07-16 |  |  | 26 | 2026-07-16 | 2026-11-17 | 2026-08-15 | 2026-08-15 | 2026-12-16 | 106
| A18760 | Installation of electrical works inside the building (excluding installation of HVAC power control panel) |  | 2026-07-19 |  |  | 26 | 2026-07-19 | 2026-11-18 | 2026-08-17 | 2026-08-17 | 2026-12-17 | 105
| A18780 | Pressure testing of pipes |  | 2026-08-11 |  |  | 12 | 2026-08-11 | 2026-12-02 | 2026-08-24 | 2026-08-24 | 2026-12-15 | 97
| A18790 | Flushing, cleaning, air blowing of Piping |  | 2026-08-18 |  |  | 12 | 2026-08-18 | 2026-12-09 | 2026-08-31 | 2026-08-31 | 2026-12-22 | 97
| A18590 | Insulation of ductwork outside the building |  | 2026-07-30 |  |  | 30 | 2026-07-30 | 2026-12-01 | 2026-09-02 | 2026-09-02 | 2027-01-04 | 106
| A18820 | Assembly of Air Handling Unit (AHU) |  | 2026-09-01 |  |  | 5 | 2026-09-01 | 2026-12-23 | 2026-09-06 | 2026-09-06 | 2026-12-28 | 97
| A18890 | Insulation of refrigerant pipework outside the building |  | 2026-08-20 |  |  | 15 | 2026-08-20 | 2026-12-19 | 2026-09-06 | 2026-09-06 | 2027-01-04 | 103
| A18830 | Installation and alignment of air handling units (AHU) |  | 2026-09-07 |  |  | 6 | 2026-09-07 | 2026-12-29 | 2026-09-13 | 2026-09-13 | 2027-01-04 | 97
| A18840 | Installation of Exhaust Fan |  | 2026-09-07 |  |  | 6 | 2026-09-07 | 2027-01-05 | 2026-09-13 | 2026-09-13 | 2027-01-11 | 103
| A18860 | Installation and alignment of refrigerant cycle and chiller |  | 2026-09-07 |  |  | 6 | 2026-09-07 | 2026-12-29 | 2026-09-13 | 2026-09-13 | 2027-01-04 | 97
| A18870 | Installation of buffer tank |  | 2026-09-07 |  |  | 6 | 2026-09-07 | 2026-12-29 | 2026-09-13 | 2026-09-13 | 2027-01-04 | 97
| A18910 | Installation of electrical / power system and HVAC control system |  | 2026-08-27 |  |  | 15 | 2026-08-27 | 2026-12-19 | 2026-09-13 | 2026-09-13 | 2027-01-04 | 97
| A18850 | Complete Duct Connection to AHU & Fan |  | 2026-09-08 |  |  | 10 | 2026-09-08 | 2027-01-05 | 2026-09-19 | 2026-09-19 | 2027-01-16 | 102
| A18920 | HVAC Testing and Commissioning works |  | 2026-09-14 |  |  | 14 | 2026-09-14 | 2027-01-05 | 2026-09-29 | 2026-09-29 | 2027-01-20 | 97
| GF Sanitary Water Sump Pump (01 No) (70-PC-1409) |  |  | 2026-07-04 |  |  | 40 | 2026-07-04 | 2026-10-26 | 2026-08-18 | 2026-08-18 | 2026-12-10 | 99
| A22600 | Installation of Sanitary Water Sump Pump (70-PC-1409) |  | 2026-07-04 |  |  | 12 | 2026-07-04 | 2026-10-26 | 2026-07-16 | 2026-07-16 | 2026-11-09 | 99
| A22830 | Alignment of Sanitary Water Sump Pump (70-PC-1409) |  | 2026-07-18 |  |  | 18 | 2026-07-18 | 2026-11-09 | 2026-08-06 | 2026-08-06 | 2026-11-30 | 99
| A22840 | Grouting of Sanitary Water Sump Pump (70-PC-1409) |  | 2026-08-08 |  |  | 10 | 2026-08-08 | 2026-11-30 | 2026-08-18 | 2026-08-18 | 2026-12-10 | 99
| GF Feed Gas Compressor and Auxilary Equipment Errection |  |  | 2026-03-24 |  |  | 217 | 2026-03-24 | 2026-03-24 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 0
| A22480 | Delivery inspection, Unpacked and Installation of FG Comp 1st Stage Suction Drum(13-VV-705) |  | 2026-06-22 |  |  | 7 | 2026-06-22 | 2026-08-16 | 2026-06-29 | 2026-06-29 | 2026-08-23 | 47
| A23020 | Alignment of FG Comp 1st Stage Suction Drum(13-VV-705) |  | 2026-06-30 |  |  | 7 | 2026-06-30 | 2026-08-24 | 2026-07-07 | 2026-07-07 | 2026-08-31 | 47
| A23030 | Grouting of FG Comp 1st Stage Suction Drum(13-VV-705) |  | 2026-07-08 |  |  | 5 | 2026-07-08 | 2026-09-01 | 2026-07-13 | 2026-07-13 | 2026-09-06 | 47
| A23080 | Internals (Demister) of FG Comp 1st Stage Suction Drum(13-VV-705) |  | 2026-07-14 |  |  | 15 | 2026-07-14 | 2026-09-07 | 2026-07-30 | 2026-07-30 | 2026-09-23 | 47
| A23230 | Insulation of FG Comp 1st Stage Suction Drum(13-VV-705) |  | 2026-08-01 |  |  | 14 | 2026-08-01 | 2026-09-24 | 2026-08-16 | 2026-08-16 | 2026-10-10 | 47
| FG Compressor Interstage Cooler (13-HE-703) |  |  | 2026-06-09 |  |  | 51 | 2026-06-09 | 2026-07-26 | 2026-08-06 | 2026-08-06 | 2026-09-22 | 40
| A23600 | Intallation of FG Compressor Interstage Cooler (13-HE-703) |  | 2026-06-09 |  |  | 10 | 2026-06-09 | 2026-07-26 | 2026-06-20 | 2026-06-20 | 2026-08-05 | 40
| A23910 | Alignment of FG Compressor Interstage Cooler (13-HE-703) |  | 2026-06-21 |  |  | 10 | 2026-06-21 | 2026-08-06 | 2026-07-01 | 2026-07-01 | 2026-08-17 | 40
| A23920 | Grouting of FG Compressor Interstage Cooler (13-HE-703) |  | 2026-07-02 |  |  | 10 | 2026-07-02 | 2026-08-18 | 2026-07-13 | 2026-07-13 | 2026-08-29 | 40
| A23980 | Insulation of FG Compressor Interstage Cooler (13-HE-703) |  | 2026-07-14 |  |  | 21 | 2026-07-14 | 2026-08-30 | 2026-08-06 | 2026-08-06 | 2026-09-22 | 40
| A22540 | Installation of FG Comp After Cooler ( 13-HE-704) |  | 2026-06-20 |  |  | 10 | 2026-06-20 | 2026-07-26 | 2026-06-30 | 2026-06-30 | 2026-08-05 | 31
| A23240 | Alignment of FG Comp After Cooler ( 13-HE-704) |  | 2026-07-01 |  |  | 10 | 2026-07-01 | 2026-08-06 | 2026-07-12 | 2026-07-12 | 2026-08-17 | 31
| A23250 | Grouting of FG Comp After Cooler ( 13-HE-704) |  | 2026-07-13 |  |  | 10 | 2026-07-13 | 2026-08-18 | 2026-07-23 | 2026-07-23 | 2026-08-29 | 31
| A23370 | Insulation of FG Comp After Cooler ( 13-HE-704) |  | 2026-07-25 |  |  | 21 | 2026-07-25 | 2026-08-30 | 2026-08-17 | 2026-08-17 | 2026-09-22 | 31
| A22530 | Installation of FG Comp 2nd Stage Discharge Drum (13-VV-707) |  | 2026-07-14 |  |  | 5 | 2026-07-14 | 2026-08-08 | 2026-07-19 | 2026-07-19 | 2026-08-12 | 21
| A23380 | Alignment of FG Comp 2nd Stage Discharge Drum (13-VV-707) |  | 2026-07-20 |  |  | 5 | 2026-07-20 | 2026-08-13 | 2026-07-25 | 2026-07-25 | 2026-08-18 | 21
| A23390 | Grouting of FG Comp 2nd Stage Discharge Drum (13-VV-707) |  | 2026-07-26 |  |  | 5 | 2026-07-26 | 2026-08-19 | 2026-07-30 | 2026-07-30 | 2026-08-24 | 21
| A23400 | Internals (Demister Pad) of FG Comp 2nd Stage Discharge Drum (13-VV-707) |  | 2026-08-01 |  |  | 10 | 2026-08-01 | 2026-08-25 | 2026-08-11 | 2026-08-11 | 2026-09-05 | 21
| A23410 | Insulation of FG Comp 2nd Stage Discharge Drum (13-VV-707) |  | 2026-08-12 |  |  | 15 | 2026-08-12 | 2026-09-06 | 2026-08-29 | 2026-08-29 | 2026-09-22 | 21
| A22490 | Delivery inspection, Unpacked and Installation of FG Comp 2nd Stage Suction Drum (13-VV-706) |  | 2026-06-25 |  |  | 10 | 2026-06-25 | 2026-08-03 | 2026-07-06 | 2026-07-06 | 2026-08-13 | 33
| A23420 | Alignment of FG Comp 2nd Stage Suction Drum (13-VV-706) |  | 2026-07-07 |  |  | 5 | 2026-07-07 | 2026-08-15 | 2026-07-12 | 2026-07-12 | 2026-08-19 | 33
| A23430 | Grouting of FG Comp 2nd Stage Suction Drum (13-VV-706) |  | 2026-07-13 |  |  | 5 | 2026-07-13 | 2026-08-20 | 2026-07-18 | 2026-07-18 | 2026-08-25 | 33
| A23440 | Internals (Demister Pad) of FG Comp 2nd Stage Suction Drum (13-VV-706) |  | 2026-07-19 |  |  | 10 | 2026-07-19 | 2026-08-26 | 2026-07-29 | 2026-07-29 | 2026-09-06 | 33
| A23450 | Insulation of FG Comp 2nd Stage Suction Drum (13-VV-706) |  | 2026-07-30 |  |  | 14 | 2026-07-30 | 2026-09-07 | 2026-08-15 | 2026-08-15 | 2026-09-22 | 33
| Feed Gas (FG) Compressor Installation |  |  | 2026-03-24 |  |  | 217 | 2026-03-24 | 2026-03-24 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 0
| C1000 | FG Foundation Plan - Foundation Check & Dimensional Examination - FG Compressor |  | 2026-03-24 |  |  | 15 | 2026-03-24 | 2026-03-24 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 0
| C1002 | Setting of FG Compressor Base Plate (Temporary settng, Elevation, Level, Tolerance, Position) |  | 2026-04-11 |  |  | 21 | 2026-04-11 | 2026-04-11 | 2026-05-04 | 2026-05-04 | 2026-05-04 | 0
| C1001 | Installation of FG Compressor (Setting of Pad, Preparation, Position and Leveling) |  | 2026-05-05 |  |  | 12 | 2026-05-05 | 2026-05-05 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 0
| C1031 | Installation of FG Compressor Main Driver Motor |  | 2026-05-19 |  |  | 10 | 2026-05-19 | 2026-07-02 | 2026-05-30 | 2026-05-30 | 2026-07-13 | 38
| C1004 | Pre-alignment of FG Compressor |  | 2026-05-30 |  |  | 15 | 2026-05-30 | 2026-07-14 | 2026-06-16 | 2026-06-16 | 2026-07-30 | 38
| C1003 | Grouting - FG Compressor |  | 2026-06-16 |  |  | 10 | 2026-06-16 | 2026-08-01 | 2026-06-28 | 2026-06-28 | 2026-08-11 | 38
| C1005 | Coupling Alignment - FG Compressor |  | 2026-06-28 |  |  | 20 | 2026-06-28 | 2026-08-19 | 2026-07-21 | 2026-07-21 | 2026-09-10 | 44
| C1006 | Installation of Auxiliary Equipment - FG Compressor |  |  |  |  | 0 |  |  | 2026-09-15 | 2026-09-15 | 2026-10-10 | 21
| C1007 | Installation of Piping - FG Compressor |  | 2026-09-12 |  |  | 45 | 2026-09-12 | 2026-09-12 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 0
| C1008 | E&I Installation - FG Compressor |  | 2026-10-05 |  |  | 40 | 2026-10-05 | 2026-10-05 | 2026-11-19 | 2026-11-19 | 2026-11-19 | 0
| C1009 | Punch List Close Out FG Compressor |  | 2026-11-21 |  |  | 10 | 2026-11-21 | 2026-11-21 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 0
| GF Off Gas Compressor and Auxilary Equipment Errection |  |  | 2026-03-24 |  |  | 210 | 2026-03-24 | 2026-06-04 | 2026-11-23 | 2026-11-23 | 2026-12-10 | 15
| Off Gas (OG) Compressor Installation |  |  | 2026-03-24 |  |  | 210 | 2026-03-24 | 2026-06-04 | 2026-11-23 | 2026-11-23 | 2026-12-01 | 7
| C1069 | OG Foundation Plan - Foundation Check & Dimensional Examination |  | 2026-03-24 |  |  | 15 | 2026-03-24 | 2026-06-04 | 2026-04-09 | 2026-04-09 | 2026-06-22 | 62
| C1089 | Setting of OG Compressor Base Plate (Temporary setting, Elevation, Level, Tolerance, Position) |  | 2026-04-11 |  |  | 21 | 2026-04-11 | 2026-06-22 | 2026-05-04 | 2026-05-04 | 2026-07-16 | 62
| C1079 | Installation of OG Compressor (Setting of Pad, Preparation, Position and Leveling) |  | 2026-05-05 |  |  | 12 | 2026-05-05 | 2026-07-16 | 2026-05-18 | 2026-05-18 | 2026-07-30 | 62
| C1169 | Installation of OG Compressor Main Driver Motor |  | 2026-05-19 |  |  | 8 | 2026-05-19 | 2026-07-30 | 2026-05-27 | 2026-05-27 | 2026-08-09 | 62
| C1109 | Pre-alignment of OG Compressor |  | 2026-05-28 |  |  | 15 | 2026-05-28 | 2026-08-09 | 2026-06-14 | 2026-06-14 | 2026-08-26 | 62
| C1099 | Grouting - OG Compressor |  | 2026-06-15 |  |  | 10 | 2026-06-15 | 2026-08-26 | 2026-06-25 | 2026-06-25 | 2026-09-07 | 62
| C1119 | Coupling and Alignment - OG Compressor |  | 2026-06-27 |  |  | 20 | 2026-06-27 | 2026-09-07 | 2026-07-19 | 2026-07-19 | 2026-09-30 | 62
| C1129 | Installation of Auxiliary Equipment - OG Compressor |  |  |  |  | 0 |  |  | 2026-08-29 | 2026-08-29 | 2026-10-06 | 32
| C1139 | Installation of Piping - OG Compressor |  | 2026-09-22 |  |  | 35 | 2026-09-22 | 2026-09-30 | 2026-11-01 | 2026-11-01 | 2026-11-10 | 7
| C1149 | E&I Installation - OG Compressor |  | 2026-09-28 |  |  | 35 | 2026-09-28 | 2026-10-07 | 2026-11-08 | 2026-11-08 | 2026-11-16 | 7
| C1159 | Punch List Close Out (Mechanical) - OG Compressor |  | 2026-11-08 |  |  | 13 | 2026-11-08 | 2026-11-17 | 2026-11-23 | 2026-11-23 | 2026-12-01 | 7
| A25270 | Ground Preparatory Works for Crane |  | 2026-06-13 |  |  | 12 | 2026-06-13 | 2026-09-30 | 2026-06-25 | 2026-06-25 | 2026-10-13 | 94
| A22500 | Installation of OG Buffer Drum (13-VV-712) |  | 2026-07-04 |  |  | 6 | 2026-07-04 | 2026-10-14 | 2026-07-09 | 2026-07-09 | 2026-10-20 | 88
| A22790 | Alignment of OG Buffer Drum (13-VV-712) |  | 2026-07-11 |  |  | 6 | 2026-07-11 | 2026-10-28 | 2026-07-16 | 2026-07-16 | 2026-11-03 | 94
| A22800 | Grouting of OG Buffer Drum (13-VV-712) |  | 2026-07-18 |  |  | 6 | 2026-07-18 | 2026-11-04 | 2026-07-23 | 2026-07-23 | 2026-11-10 | 94
| A25280 | Scafolding Works |  | 2026-07-11 |  |  | 18 | 2026-07-11 | 2026-10-21 | 2026-07-30 | 2026-07-30 | 2026-11-10 | 88
| A22810 | Internals (Demister) of OG Buffer Drum (13-VV-712) |  | 2026-08-01 |  |  | 12 | 2026-08-01 | 2026-11-11 | 2026-08-13 | 2026-08-13 | 2026-11-24 | 88
| A22820 | Insulation of OG Buffer Drum (13-VV-712) |  | 2026-08-15 |  |  | 14 | 2026-08-15 | 2026-11-25 | 2026-08-30 | 2026-08-30 | 2026-12-10 | 88
| A22570 | Intallation of OG Compressor Interstage Cooler (13-HE-708) |  | 2026-04-22 |  |  | 4 | 2026-04-22 | 2026-08-22 | 2026-04-27 | 2026-04-27 | 2026-08-26 | 104
| A23460 | Alignment of OG Compressor Interstage Cooler (13-HE-708) |  | 2026-04-27 |  |  | 5 | 2026-04-27 | 2026-08-26 | 2026-05-03 | 2026-05-03 | 2026-09-01 | 104
| A23470 | Grouting of OG Compressor Interstage Cooler (13-HE-708) |  | 2026-05-03 |  |  | 10 | 2026-05-03 | 2026-09-01 | 2026-05-14 | 2026-05-14 | 2026-09-13 | 104
| A23480 | Insulation of OG Compressor Interstage Cooler (13-HE-708) |  | 2026-05-14 |  |  | 20 | 2026-05-14 | 2026-09-13 | 2026-06-07 | 2026-06-07 | 2026-10-06 | 104
| A22550 | Installation of OG Comp After Cooler ( 13-HE-709) |  | 2026-06-27 |  |  | 5 | 2026-06-27 | 2026-08-22 | 2026-07-01 | 2026-07-01 | 2026-08-27 | 48
| A23490 | Alignment of OG Comp After Cooler ( 13-HE-709) |  | 2026-07-02 |  |  | 4 | 2026-07-02 | 2026-08-27 | 2026-07-06 | 2026-07-06 | 2026-09-01 | 48
| A23930 | Grouting of OG Comp After Cooler ( 13-HE-709) |  | 2026-07-07 |  |  | 10 | 2026-07-07 | 2026-09-01 | 2026-07-18 | 2026-07-18 | 2026-09-13 | 48
| A23990 | Insulation of OG Comp After Cooler ( 13-HE-709) |  | 2026-07-19 |  |  | 20 | 2026-07-19 | 2026-09-13 | 2026-08-10 | 2026-08-10 | 2026-10-06 | 48
| A3490 | Installation of OG Compressor Discharge Drip Leg |  | 2026-07-23 |  |  | 4 | 2026-07-23 | 2026-08-30 | 2026-07-27 | 2026-07-27 | 2026-09-03 | 32
| A3500 | Alignment of OG Compressor Discharge Drip Leg |  | 2026-07-28 |  |  | 4 | 2026-07-28 | 2026-09-03 | 2026-08-01 | 2026-08-01 | 2026-09-08 | 32
| A3510 | Grouting of OG Compressor Discharge Drip Leg |  | 2026-08-02 |  |  | 4 | 2026-08-02 | 2026-09-08 | 2026-08-05 | 2026-08-05 | 2026-09-13 | 32
| A3520 | Internals of OG Compressor Discharge Drip Leg |  | 2026-08-06 |  |  | 10 | 2026-08-06 | 2026-09-13 | 2026-08-17 | 2026-08-17 | 2026-09-24 | 32
| A3530 | Insulation of OG Compressor Discharge Drip Leg |  | 2026-08-18 |  |  | 10 | 2026-08-18 | 2026-09-24 | 2026-08-29 | 2026-08-29 | 2026-10-06 | 32
| A22510 | Installation of OG Comp 2nd Stage Suction Drum (13-VV-713) |  | 2026-06-21 |  |  | 5 | 2026-06-21 | 2026-08-20 | 2026-06-25 | 2026-06-25 | 2026-08-26 | 52
| A24000 | Alignment of OG Comp 2nd Stage Suction Drum (13-VV-713) |  | 2026-06-27 |  |  | 5 | 2026-06-27 | 2026-08-26 | 2026-07-01 | 2026-07-01 | 2026-09-01 | 52
| A24010 | Grouting of OG Comp 2nd Stage Suction Drum (13-VV-713) |  | 2026-07-02 |  |  | 5 | 2026-07-02 | 2026-09-01 | 2026-07-07 | 2026-07-07 | 2026-09-07 | 52
| A25250 | Internals (Demster Pad) of OG Comp 2nd Stage Suction Drum (13-VV-713) |  | 2026-07-08 |  |  | 10 | 2026-07-08 | 2026-09-07 | 2026-07-19 | 2026-07-19 | 2026-09-19 | 52
| A25260 | Insulation of OG Comp 2nd Stage Suction Drum (13-VV-713) |  | 2026-07-20 |  |  | 15 | 2026-07-20 | 2026-09-19 | 2026-08-05 | 2026-08-05 | 2026-10-06 | 52
| TA Boiler Feed Water Installation |  |  | 2026-02-20 |  |  | 3 | 19-Apr-25 A | 2026-03-27 | 24-May-25 A | 2026-02-20 | 2026-03-27
| A3787 | Installation of BFW Preheater |  | 2026-02-20 |  |  | 3 | 19-Apr-25 A | 2026-03-27 | 24-May-25 A | 2026-02-20 | 2026-03-27
| BF Mechanical Equipments |  |  | 2026-06-14 |  |  | 40 | 2026-06-14 | 2026-11-05 | 2026-07-30 | 2026-07-30 | 2027-01-03 | 135
| A9650 | Installation of Dripleg (1 No) |  | 2026-06-14 |  |  | 40 | 2026-06-14 | 2026-11-05 | 2026-07-30 | 2026-07-30 | 2026-12-21 | 124
| A9660 | Installation of Coalescer (1 No) |  | 2026-06-14 |  |  | 40 | 2026-06-14 | 2026-11-18 | 2026-07-30 | 2026-07-30 | 2027-01-03 | 135
| A22560 | Installation of C4 Guard Regeneration Cooler (50-HE-1410) |  | 2026-06-14 |  |  | 40 | 2026-06-14 | 2026-11-05 | 2026-07-30 | 2026-07-30 | 2026-12-21 | 124
| GF PSA2 Package by Linde ( 10 Vessels) |  |  | 2026-03-22 |  |  | 183 | 2026-03-22 | 2026-05-26 | 2026-10-20 | 2026-10-20 | 2026-12-10 | 44
| A22610 | Installation of PSA2 Package by Linde ( 10 Vessels) |  | 2026-03-22 |  |  | 60 | 2026-03-22 | 2026-05-26 | 2026-05-30 | 2026-05-30 | 2026-08-03 | 56
| A22850 | Alignment of PSA2 Package by Linde ( 10 Vessels) |  | 2026-05-31 |  |  | 45 | 2026-05-31 | 2026-08-04 | 2026-07-21 | 2026-07-21 | 2026-09-24 | 56
| A22860 | Grouting of PSA2 Package by Linde ( 10 Vessels) |  | 2026-06-24 |  |  | 45 | 2026-06-24 | 2026-08-29 | 2026-08-15 | 2026-08-15 | 2026-10-19 | 56
| A22870 | Internals of PSA2 Package by Linde ( 10 Vessels) |  | 2026-08-30 |  |  | 45 | 2026-08-30 | 2026-10-20 | 2026-10-20 | 2026-10-20 | 2026-12-10 | 44
| GF Water Sump Pump (02 Nos) (70-PC-1407) |  |  | 2026-06-17 |  |  | 40 | 2026-06-17 | 2026-10-26 | 2026-08-02 | 2026-08-02 | 2026-12-10 | 112
| A22590 | Installation of Water Sump Pump (70-PC-1407) |  | 2026-06-17 |  |  | 12 | 2026-06-17 | 2026-10-26 | 2026-06-30 | 2026-06-30 | 2026-11-08 | 112
| A22880 | Alignment of Water Sump Pump (70-PC-1407) |  | 2026-07-01 |  |  | 18 | 2026-07-01 | 2026-11-09 | 2026-07-21 | 2026-07-21 | 2026-11-29 | 112
| A22890 | Grouting of Water Sump Pump (70-PC-1407) |  | 2026-07-22 |  |  | 10 | 2026-07-22 | 2026-11-30 | 2026-08-02 | 2026-08-02 | 2026-12-10 | 112
| GF PSA2 Slope Drum ( 70-VV-1415) |  |  | 2026-07-20 |  |  | 36 | 2026-07-20 | 2026-10-31 | 2026-08-30 | 2026-08-30 | 2026-12-10 | 88
| A22520 | Installation of PSA2 Slope Drum ( 70-VV-1415) |  | 2026-07-20 |  |  | 5 | 2026-07-20 | 2026-10-31 | 2026-07-25 | 2026-07-25 | 2026-11-04 | 88
| A22930 | Alignment of PSA2 Slope Drum ( 70-VV-1415) |  | 2026-07-26 |  |  | 5 | 2026-07-26 | 2026-11-05 | 2026-07-30 | 2026-07-30 | 2026-11-10 | 88
| A22960 | Grouting of PSA2 Slope Drum ( 70-VV-1415) |  | 2026-08-01 |  |  | 5 | 2026-08-01 | 2026-11-11 | 2026-08-05 | 2026-08-05 | 2026-11-16 | 88
| A22990 | Internals of PSA2 Slope Drum ( 70-VV-1415) |  | 2026-08-06 |  |  | 10 | 2026-08-06 | 2026-11-17 | 2026-08-17 | 2026-08-17 | 2026-11-28 | 88
| A23010 | Insulation of PSA2 Slope Drum ( 70-VV-1415) |  | 2026-08-18 |  |  | 11 | 2026-08-18 | 2026-11-29 | 2026-08-30 | 2026-08-30 | 2026-12-10 | 88
| GF EOT Crane for FG Compressor |  |  | 2026-09-12 |  |  | 27 | 2026-09-12 | 2026-10-15 | 2026-10-12 | 2026-10-12 | 2026-11-19 | 33
| C1339 | Installation of electrical equipment |  | 2026-09-12 |  |  | 4 | 2026-09-12 | 2026-10-27 | 2026-09-15 | 2026-09-15 | 2026-10-31 | 39
| C1319 | LT rail line installation |  | 2026-09-12 |  |  | 10 | 2026-09-12 | 2026-10-15 | 2026-09-22 | 2026-09-22 | 2026-10-26 | 29
| C1329 | Assembly of main girders at ground level |  | 2026-09-12 |  |  | 10 | 2026-09-12 | 2026-10-20 | 2026-09-22 | 2026-09-22 | 2026-10-31 | 33
| C1349 | Installation of end carriage & main girder |  | 2026-09-23 |  |  | 4 | 2026-09-23 | 2026-11-01 | 2026-09-27 | 2026-09-27 | 2026-11-04 | 33
| C1359 | Crab erection |  | 2026-09-28 |  |  | 3 | 2026-09-28 | 2026-11-05 | 2026-09-30 | 2026-09-30 | 2026-11-08 | 33
| C1369 | Installation of the platform, hand railing, cabin, ladder, DSL cage and DSL guard |  | 2026-10-01 |  |  | 10 | 2026-10-01 | 2026-11-09 | 2026-10-12 | 2026-10-12 | 2026-11-19 | 33
| GF EOT Crane for OG Compressor |  |  | 2026-09-19 |  |  | 22 | 2026-09-19 | 2026-10-22 | 2026-10-13 | 2026-10-13 | 2026-11-16 | 29
| C1309 | Installation of electrical equipment |  | 2026-09-19 |  |  | 4 | 2026-09-19 | 2026-10-29 | 2026-09-22 | 2026-09-22 | 2026-11-02 | 35
| C1259 | LT rail line installation |  | 2026-09-19 |  |  | 10 | 2026-09-19 | 2026-10-22 | 2026-09-29 | 2026-09-29 | 2026-11-02 | 29
| C1269 | Assembly of main girders at ground level |  | 2026-09-19 |  |  | 10 | 2026-09-19 | 2026-10-22 | 2026-09-29 | 2026-09-29 | 2026-11-02 | 29
| C1279 | Installation of end carriage & main girder |  | 2026-09-30 |  |  | 4 | 2026-09-30 | 2026-11-03 | 2026-10-04 | 2026-10-04 | 2026-11-07 | 29
| C1289 | Cran erection |  | 2026-10-05 |  |  | 2 | 2026-10-05 | 2026-11-08 | 2026-10-06 | 2026-10-06 | 2026-11-09 | 29
| C1299 | Installation of the platform, hand railing, cabin, ladder, DSL cage and DSL guard |  | 2026-10-05 |  |  | 8 | 2026-10-05 | 2026-11-08 | 2026-10-13 | 2026-10-13 | 2026-11-16 | 29
| Piping Fabrication |  |  | 2026-02-20 |  |  | 138 | 05-Mar-25 A | 2026-03-27 | 18-Apr-25 A | 2026-02-20 | 2026-03-27
| TA Piping Work |  |  | 2026-02-20 |  |  | 138 | 05-Mar-25 A | 2026-03-27 | 18-Apr-25 A | 2026-02-20 | 2026-03-27
| BFW4000 | Prefabrication of Tie-ins Spools |  | 2026-02-20 |  |  | 36 | 28-Mar-25 A | 2026-03-27 | 04-Apr-25 A | 2026-02-20 | 2026-03-27
| A17730 | Installation of Scaffolding |  | 2026-02-20 |  |  | 24 | 05-Mar-25 A | 2026-03-27 | 08-Apr-25 A | 2026-02-20 | 2026-03-27
| BFW4050 | Sand blastinfg and painting |  | 2026-02-20 |  |  | 45 | 01-Apr-25 A | 2026-03-27 | 15-Apr-25 A | 2026-02-20 | 2026-03-27
| BFW4010 | Prefabrication of Piping Spools for the BFW |  | 2026-02-20 |  |  | 36 | 11-Apr-25 A | 2026-03-27 | 18-Apr-25 A | 2026-02-20 | 2026-03-27
| Piping and Valves Installation |  |  | 2026-02-20 |  |  | 461 | 29-Mar-25 A | 2026-03-27 | 2027-01-17 | 2027-01-17 | 2027-03-11 | 39
| BF Piping Works |  |  | 2026-02-21 |  |  | 214 | 2026-02-21 | 2026-03-29 | 2026-10-27 | 2026-10-27 | 2026-12-02 | 31
| A18520 | Scaffolding for Piping errection on Piperack |  | 2026-02-21 |  |  | 34 | 2026-02-21 | 2026-03-29 | 2026-03-31 | 2026-03-31 | 2026-05-06 | 31
| A9670 | Piping Erection / Installation in Brown Field |  | 2026-04-01 |  |  | 120 | 2026-04-01 | 2026-05-07 | 2026-08-18 | 2026-08-18 | 2026-09-23 | 31
| BFW4030 | Piping Hydrotesting - BF |  | 2026-08-08 |  |  | 40 | 2026-08-08 | 2026-09-13 | 2026-09-22 | 2026-09-22 | 2026-10-28 | 31
| BFW4040 | Piping connections with tie-ins |  | 2026-09-10 |  |  | 41 | 2026-09-10 | 2026-10-17 | 2026-10-27 | 2026-10-27 | 2026-12-02 | 31
| TA Tie-In Execution - A/G Tie-Ins |  |  | 2026-02-20 |  |  | 127 | 29-Mar-25 A | 2026-03-27 | 24-May-25 A | 2026-02-20 | 2026-03-27
| Package 1 |  |  | 2026-02-20 |  |  | 125 | 11-Apr-25 A | 2026-03-27 | 24-May-25 A | 2026-02-20 | 2026-03-27
| Tailgas from Tie In point EU3 to EU3 H2 Tag # IP-B-B3-H3-L-2010 |  |  | 2026-02-20 |  |  | 88 | 11-Apr-25 A | 2026-03-27 | 24-May-25 A | 2026-02-20 | 2026-03-27
| A9730 | Full welding of joints & installation of Tie-In spool 45076 |  | 2026-02-20 |  |  | 0 | 25-Apr-25 A | 2026-03-27 | 26-Apr-25 A | 2026-02-20 | 2026-03-27
| A9740 | Inspection NDT / RT of selected joints |  | 2026-02-20 |  |  | 0 | 25-Apr-25 A | 2026-03-27 | 26-Apr-25 A | 2026-02-20 | 2026-03-27
| A38420 | Install pipe supports (if any) |  | 2026-02-20 |  |  | 0 | 25-Apr-25 A | 2026-03-27 | 26-Apr-25 A | 2026-02-20 | 2026-03-27
| A38430 | Prepare and hydrotest up to XX BarG (if required) |  | 2026-02-20 |  |  | 0 | 25-Apr-25 A | 2026-03-27 | 26-Apr-25 A | 2026-02-20 | 2026-03-27
| A38440 | Hydrotest witness inspection (if required) |  | 2026-02-20 |  |  | 0 | 25-Apr-25 A | 2026-03-27 | 26-Apr-25 A | 2026-02-20 | 2026-03-27
| A9780 | Reinstall back piping components (TW/TE, TG, PT, PG if any) |  | 2026-02-20 |  |  | 0 | 25-Apr-25 A | 2026-03-27 | 26-Apr-25 A | 2026-02-20 | 2026-03-27
| A9790 | Touch-up painting works |  | 2026-02-20 |  |  | 0 | 25-Apr-25 A | 2026-03-27 | 15-May-25 A | 2026-02-20 | 2026-03-27
| A9800 | Deblinding, remove temporary support / scaffolds |  | 2026-02-20 |  |  | 0 | 25-Apr-25 A | 2026-03-27 | 15-May-25 A | 2026-02-20 | 2026-03-27
| A9810 | Reinstall insulation (if any) |  | 2026-02-20 |  |  | 0 | 25-Apr-25 A | 2026-03-27 | 15-May-25 A | 2026-02-20 | 2026-03-27
| A9820 | Torquing / flange management & hand-over to Ops |  | 2026-02-20 |  |  | 0 | 25-Apr-25 A | 2026-03-27 | 15-May-25 A | 2026-02-20 | 2026-03-27
| A9830 | End of Work |  | 2026-02-20 |  |  | 1 | 16-May-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A38390 | Start of Work |  | 2026-02-20 |  |  | 1 | 11-Apr-25 A | 2026-03-27 | 24-May-25 A | 2026-02-20 | 2026-03-27
| A9680 | Obtain Work Permit |  | 2026-02-20 |  |  | 0 | 11-Apr-25 A | 2026-03-27 | 24-May-25 A | 2026-02-20 | 2026-03-27
| A38400 | Removal of insulation & Wallthickness measurement |  | 2026-02-20 |  |  | 0 | 11-Apr-25 A | 2026-03-27 | 24-May-25 A | 2026-02-20 | 2026-03-27
| A38410 | Drilling one hole (cold drilling, airdriven) & Gas measurement |  | 2026-02-20 |  |  | 0 | 11-Apr-25 A | 2026-03-27 | 24-May-25 A | 2026-02-20 | 2026-03-27
| A9710 | Cut old piping (existing line 45024), haul to ground level |  | 2026-02-20 |  |  | 0 | 11-Apr-25 A | 2026-03-27 | 24-May-25 A | 2026-02-20 | 2026-03-27
| A9720 | Grinding, bevelling of old piping & fit-up with new spool |  | 2026-02-20 |  |  | 0 | 11-Apr-25 A | 2026-03-27 | 24-May-25 A | 2026-02-20 | 2026-03-27
| Tailgas Tag # IP-B-B3-M3-L-3010 |  |  | 2026-02-20 |  |  | 88 | 11-Apr-25 A | 2026-03-27 | 24-May-25 A | 2026-02-20 | 2026-03-27
| A38340 | Full welding of joints & installation of Tie-In spool 45024 |  | 2026-02-20 |  |  | 0 | 25-Apr-25 A | 2026-03-27 | 26-Apr-25 A | 2026-02-20 | 2026-03-27
| A38350 | Inspection NDT / RT of selected joints |  | 2026-02-20 |  |  | 0 | 25-Apr-25 A | 2026-03-27 | 26-Apr-25 A | 2026-02-20 | 2026-03-27
| A38360 | Install pipe supports (if any) |  | 2026-02-20 |  |  | 0 | 25-Apr-25 A | 2026-03-27 | 26-Apr-25 A | 2026-02-20 | 2026-03-27
| A9590 | Prepare and hydrotest up to XX BarG (if required) |  | 2026-02-20 |  |  | 0 | 25-Apr-25 A | 2026-03-27 | 26-Apr-25 A | 2026-02-20 | 2026-03-27
| A9600 | Hydrotest witness inspection (if required) |  | 2026-02-20 |  |  | 0 | 25-Apr-25 A | 2026-03-27 | 26-Apr-25 A | 2026-02-20 | 2026-03-27
| A9610 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) |  | 2026-02-20 |  |  | 0 | 25-Apr-25 A | 2026-03-27 | 26-Apr-25 A | 2026-02-20 | 2026-03-27
| A9620 | Touch-up painting works |  | 2026-02-20 |  |  | 0 | 25-Apr-25 A | 2026-03-27 | 15-May-25 A | 2026-02-20 | 2026-03-27
| A9630 | Deblinding, remove temporary support / scaffolds |  | 2026-02-20 |  |  | 0 | 25-Apr-25 A | 2026-03-27 | 15-May-25 A | 2026-02-20 | 2026-03-27
| A9640 | Reinstall insulation (if any) |  | 2026-02-20 |  |  | 0 | 25-Apr-25 A | 2026-03-27 | 15-May-25 A | 2026-02-20 | 2026-03-27
| A38370 | Torquing / flange management & hand-over to Ops |  | 2026-02-20 |  |  | 0 | 25-Apr-25 A | 2026-03-27 | 15-May-25 A | 2026-02-20 | 2026-03-27
| A38380 | End of Work |  | 2026-02-20 |  |  | 1 | 16-May-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A38280 | Start of Work |  | 2026-02-20 |  |  | 1 | 11-Apr-25 A | 2026-03-27 | 24-May-25 A | 2026-02-20 | 2026-03-27
| A38290 | Obtain Work Permit |  | 2026-02-20 |  |  | 0 | 11-Apr-25 A | 2026-03-27 | 24-May-25 A | 2026-02-20 | 2026-03-27
| A38300 | Removal of insulation & Wallthickness measurement |  | 2026-02-20 |  |  | 0 | 11-Apr-25 A | 2026-03-27 | 24-May-25 A | 2026-02-20 | 2026-03-27
| A38310 | Drilling one hole (cold drilling, airdriven) & Gas measurement |  | 2026-02-20 |  |  | 0 | 11-Apr-25 A | 2026-03-27 | 24-May-25 A | 2026-02-20 | 2026-03-27
| A38320 | Cut old piping (existing line 45024), haul to ground level |  | 2026-02-20 |  |  | 0 | 11-Apr-25 A | 2026-03-27 | 24-May-25 A | 2026-02-20 | 2026-03-27
| A38330 | Grinding, bevelling of old piping & fit-up with new spool |  | 2026-02-20 |  |  | 0 | 11-Apr-25 A | 2026-03-27 | 24-May-25 A | 2026-02-20 | 2026-03-27
| Tailgas Tag # IP-B-M3-B3-L-3020 |  |  | 2026-02-20 |  |  | 88 | 11-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A9330 | Start of Work |  | 2026-02-20 |  |  | 1 | 11-Apr-25 A | 2026-03-27 | 11-Apr-25 A | 2026-02-20 | 2026-03-27
| A9340 | Obtain Work Permit |  | 2026-02-20 |  |  | 0 | 11-Apr-25 A | 2026-03-27 | 11-Apr-25 A | 2026-02-20 | 2026-03-27
| A9350 | Removal of insulation & Wallthickness measurement |  | 2026-02-20 |  |  | 0 | 11-Apr-25 A | 2026-03-27 | 11-Apr-25 A | 2026-02-20 | 2026-03-27
| A9360 | Drilling one hole (cold drilling, airdriven) & Gas measurement |  | 2026-02-20 |  |  | 0 | 11-Apr-25 A | 2026-03-27 | 11-Apr-25 A | 2026-02-20 | 2026-03-27
| A9370 | Cut old piping (existing line 45024), haul to ground level |  | 2026-02-20 |  |  | 0 | 11-Apr-25 A | 2026-03-27 | 11-Apr-25 A | 2026-02-20 | 2026-03-27
| A9380 | Grinding, bevelling of old piping & fit-up with new spool |  | 2026-02-20 |  |  | 0 | 11-Apr-25 A | 2026-03-27 | 11-Apr-25 A | 2026-02-20 | 2026-03-27
| A9390 | Full welding of joints & installation of Tie-In spool 45024 |  | 2026-02-20 |  |  | 0 | 11-Apr-25 A | 2026-03-27 | 11-Apr-25 A | 2026-02-20 | 2026-03-27
| A9400 | Inspection NDT / RT of selected joints |  | 2026-02-20 |  |  | 0 | 11-Apr-25 A | 2026-03-27 | 11-Apr-25 A | 2026-02-20 | 2026-03-27
| A9410 | Install pipe supports (if any) |  | 2026-02-20 |  |  | 0 | 11-Apr-25 A | 2026-03-27 | 11-Apr-25 A | 2026-02-20 | 2026-03-27
| A9420 | Prepare and hydrotest up to XX BarG (if required) |  | 2026-02-20 |  |  | 0 | 16-May-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A9430 | Hydrotest witness inspection (if required) |  | 2026-02-20 |  |  | 0 | 16-May-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A9440 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) |  | 2026-02-20 |  |  | 0 | 16-May-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A38270 | Touch-up painting works |  | 2026-02-20 |  |  | 0 | 16-May-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A9460 | Deblinding, remove temporary support / scaffolds |  | 2026-02-20 |  |  | 0 | 16-May-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A9470 | Reinstall insulation (if any) |  | 2026-02-20 |  |  | 0 | 16-May-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A9480 | Torquing / flange management & hand-over to Ops |  | 2026-02-20 |  |  | 0 | 16-May-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A9490 | End of Work |  | 2026-02-20 |  |  | 1 | 16-May-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| Tailgas Tag # IP-B-B3-M3-L-3030 |  |  | 2026-02-20 |  |  | 88 | 11-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A9160 | Start of Work |  | 2026-02-20 |  |  | 1 | 11-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A9170 | Obtain Work Permit |  | 2026-02-20 |  |  | 0 | 11-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A9180 | Removal of insulation & Wall thickness measurement |  | 2026-02-20 |  |  | 0 | 11-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A9190 | Drilling one hole (cold drilling, airdriven) & Gas measurement |  | 2026-02-20 |  |  | 0 | 11-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A38230 | Cut old piping (existing line 45024), haul to ground level |  | 2026-02-20 |  |  | 0 | 11-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A38240 | Grinding, bevelling of old piping & fit-up with new spool |  | 2026-02-20 |  |  | 0 | 11-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A38250 | Full welding of joints & installation of Tie-In spool 45075 |  | 2026-02-20 |  |  | 0 | 11-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A9230 | Inspection NDT / RT of selected joints |  | 2026-02-20 |  |  | 0 | 11-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A9240 | Install pipe supports (if any) |  | 2026-02-20 |  |  | 0 | 11-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A9250 | Prepare and hydrotest up to XX BarG |  | 2026-02-20 |  |  | 0 | 11-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A9260 | Hydrotest witness inspection |  | 2026-02-20 |  |  | 0 | 11-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A38260 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) |  | 2026-02-20 |  |  | 0 | 11-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A9280 | Touch-up painting works |  | 2026-02-20 |  |  | 0 | 11-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A9290 | Deblinding, remove temporary support / scaffolds |  | 2026-02-20 |  |  | 0 | 11-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A9300 | Reinstall insulation (if any) |  | 2026-02-20 |  |  | 0 | 11-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A9310 | Torquing / flange management & hand-over to Ops |  | 2026-02-20 |  |  | 0 | 11-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A9320 | End of Work |  | 2026-02-20 |  |  | 1 | 11-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| Tailgas Tag # IP-B-B3-M3-L-3050 |  |  | 2026-02-20 |  |  | 86 | 11-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A8990 | Start of Work |  | 2026-02-20 |  |  | 1 | 11-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A9000 | Obtain Work Permit |  | 2026-02-20 |  |  | 0 | 11-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A9010 | Removal of existing valve |  | 2026-02-20 |  |  | 0 | 11-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A9020 | Installation of new valve |  | 2026-02-20 |  |  | 0 | 11-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A9030 | Gas measurement |  | 2026-02-20 |  |  | 0 | 11-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A9120 | Deblinding, remove temporary support / scaffolds |  | 2026-02-20 |  |  | 0 | 11-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A9130 | Reinstall insulation (if any) |  | 2026-02-20 |  |  | 0 | 11-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A9140 | Torquing / flange management & hand-over to Ops |  | 2026-02-20 |  |  | 0 | 11-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A9150 | End of Work |  | 2026-02-20 |  |  | 1 | 11-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| Regeneration gas from 50-HE-1402 Tag # IP-B-B3-M3-L-3090 |  |  | 2026-02-20 |  |  | 88 | 11-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A8820 | Start of Work |  | 2026-02-20 |  |  | 0 | 11-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A8830 | Obtain Work Permit |  | 2026-02-20 |  |  | 0 | 11-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A8840 | Wallthickness measurement |  | 2026-02-20 |  |  | 0 | 11-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A8850 | Drilling one hole (cold drilling, airdriven) & Gas measurement |  | 2026-02-20 |  |  | 0 | 11-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A8860 | Cut old piping (existing line 140025), haul to ground level |  | 2026-02-20 |  |  | 0 | 11-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A8870 | Grinding, bevelling of old piping & fit-up with new spool |  | 2026-02-20 |  |  | 0 | 11-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A8880 | Full welding of joints & installation of Tie-In spool 140068 |  | 2026-02-20 |  |  | 0 | 11-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A8890 | Inspection NDT / RT of selected joints |  | 2026-02-20 |  |  | 0 | 11-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A8900 | Install pipe supports (if any) |  | 2026-02-20 |  |  | 0 | 11-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A8910 | Prepare and hydrotest up to XX BarG |  | 2026-02-20 |  |  | 0 | 11-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A8920 | Hydrotest witness inspection |  | 2026-02-20 |  |  | 0 | 11-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A8930 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) |  | 2026-02-20 |  |  | 0 | 11-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A8940 | Touch-up painting works |  | 2026-02-20 |  |  | 0 | 11-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A8950 | Deblinding, remove temporary support / scaffolds |  | 2026-02-20 |  |  | 0 | 11-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A8960 | Reinstall insulation (if any) |  | 2026-02-20 |  |  | 0 | 11-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A8970 | Torquing / flange management & hand-over to Ops |  | 2026-02-20 |  |  | 0 | 11-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A8980 | End of Work |  | 2026-02-20 |  |  | 0 | 11-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| Tailgas from 13-KX-402 Tag # IP-B-B3-M3-L-3100 |  |  | 2026-02-20 |  |  | 88 | 11-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A8650 | Start of Work |  | 2026-02-20 |  |  | 1 | 11-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A8660 | Obtain Work Permit |  | 2026-02-20 |  |  | 0 | 11-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A8670 | Removal of insulation & Wallthickness measurement |  | 2026-02-20 |  |  | 0 | 11-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A8680 | Drilling one hole (cold drilling, airdriven) & Gas measurement |  | 2026-02-20 |  |  | 0 | 11-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A8690 | Cut old piping (existing line 45024), haul to ground level |  | 2026-02-20 |  |  | 0 | 11-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A8700 | Grinding, bevelling of old piping & fit-up with new spool |  | 2026-02-20 |  |  | 0 | 11-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A8710 | Full welding of joints & installation of Tie-In spool 45024 |  | 2026-02-20 |  |  | 0 | 11-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A8720 | Inspection NDT / RT of selected joints |  | 2026-02-20 |  |  | 0 | 11-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A8730 | Install pipe supports (if any) |  | 2026-02-20 |  |  | 0 | 11-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A8740 | Prepare and hydrotest up to XX BarG (if required) |  | 2026-02-20 |  |  | 0 | 11-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A8750 | Hydrotest witness inspection (if required) |  | 2026-02-20 |  |  | 0 | 11-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A8760 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) |  | 2026-02-20 |  |  | 0 | 11-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A8770 | Touch-up painting works |  | 2026-02-20 |  |  | 0 | 11-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A8780 | Deblinding, remove temporary support / scaffolds |  | 2026-02-20 |  |  | 0 | 11-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A38220 | Reinstall insulation (if any) |  | 2026-02-20 |  |  | 0 | 11-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A8800 | Torquing / flange management & hand-over to Ops |  | 2026-02-20 |  |  | 0 | 11-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A8810 | End of Work |  | 2026-02-20 |  |  | 1 | 11-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| Cooling Water from EU3 Tie In Point to 50-HE-1410 Tag # IP-B-B3-M3-L-3120 |  |  | 2026-02-20 |  |  | 88 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A8480 | Start of Work |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A38210 | Obtain Work Permit |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A8500 | Wallthickness measurement |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A8510 | Drilling one hole (cold drilling, airdriven) & Gas measurement |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A8520 | Cut old piping (existing line 140036) , haul to ground level |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A8530 | Grinding, bevelling of old piping & fit-up with new spool |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A8540 | Full welding of joints & installation of Tie-In spool 140033 |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A8550 | Inspection NDT / RT of selected joints |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A8560 | Install pipe supports (if any) |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A8570 | Prepare and hydrotest up to XX BarG (if required) |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A8580 | Hydrotest witness inspection (if required) |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A8590 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A8600 | Touch-up painting works |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A8610 | Deblinding, remove temporary support / scaffolds |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A8620 | Reinstall insulation (if any) |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A8630 | Torquing / flange management & hand-over to Ops |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A8640 | End of Work |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| Regeneration Gas C4 Hydrogenation from 13-VA-804A/B Tag # IP-B-B3-M3-L-3170 |  |  | 2026-02-20 |  |  | 88 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A38150 | Start of Work |  | 2026-02-20 |  |  | 1 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A38160 | Obtain Work Permit |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A38170 | Removal of insulation & Wallthickness measurement |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A38180 | Drilling one hole (cold drilling, airdriven) & Gas measurement |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A8350 | Cut old piping (existing line 41022), haul to ground level |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A8360 | Grinding, bevelling of old piping & fit-up with new spool |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A38190 | Full welding of joints & installation of Tie-In spool 81142 |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A8380 | Inspection NDT / RT of selected joints |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A8390 | Install pipe supports (if any) |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A8400 | Prepare and hydrotest up to XX BarG (if required) |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A8410 | Hydrotest witness inspection (if required) |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A8420 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A38200 | Touch-up painting works |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A8440 | Deblinding, remove temporary support / scaffolds |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A8450 | Reinstall insulation (if any) |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A8460 | Torquing / flange management & hand-over to Ops |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A8470 | End of Work |  | 2026-02-20 |  |  | 1 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| Tailgas line bleed Tag # IP-B-B3-M3-L-3180 |  |  | 2026-02-20 |  |  | 88 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A38110 | Start of Work |  | 2026-02-20 |  |  | 1 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A38120 | Obtain Work Permit |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A38130 | Removal of insulation & Wallthickness measurement |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A8170 | Drilling one hole (cold drilling, airdriven) & Gas measurement |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A8180 | Cut old piping (existing line 45024), haul to ground level |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A8190 | Grinding, bevelling of old piping & fit-up with new spool |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A8200 | Full welding of joints & installation of Tie-In spool 45024 |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A8210 | Inspection NDT / RT of selected joints |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A8220 | Install pipe supports (if any) |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A8230 | Prepare and hydrotest up to XX BarG (if required) |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A8240 | Hydrotest witness inspection (if required) |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A38140 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A8260 | Touch-up painting works |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A8270 | Deblinding, remove temporary support / scaffolds |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A8280 | Reinstall insulation (if any) |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A8290 | Torquing / flange management & hand-over to Ops |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A8300 | End of Work |  | 2026-02-20 |  |  | 1 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| Treated VHP BFW Preheater 52-HE-1402 bypass valve Tag # IP-B-B3-M3-L-3190 |  |  | 2026-02-20 |  |  | 88 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7970 | Start of Work |  | 2026-02-20 |  |  | 1 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7980 | Obtain Work Permit |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7990 | Removal of insulation & Wallthickness measurement |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A8000 | Drilling one hole (cold drilling, airdriven) & Gas measurement |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A8010 | Cut old piping (existing line 140025), haul to ground level |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A8020 | Grinding, bevelling & fit-up of valve with new spool |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A8030 | Welding of gate valve & installation of Tie-In spool 140025 |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A8040 | Inspection NDT / RT of selected joints |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A8050 | Install pipe supports (if any) |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A8060 | Prepare and hydrotest up to XX BarG (if required) |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A8070 | Hydrotest witness inspection (if required) |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A8080 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A8090 | Touch-up painting works |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A8100 | Deblinding, remove temporary support / scaffolds |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A8110 | Reinstall insulation (if any) |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A8120 | Torquing / flange management & hand-over to Ops |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A38100 | End of Work |  | 2026-02-20 |  |  | 1 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| Treated VHP BFW from EU3 to 52-HE-1402 Tag # IP-B-B3-M3-L-3210 |  |  | 2026-02-20 |  |  | 88 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7800 | Start of Work |  | 2026-02-20 |  |  | 1 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7810 | Obtain Work Permit |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7820 | Removal of insulation & Wallthickness measurement |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7830 | Drilling one hole (cold drilling, airdriven) & Gas measurement |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7840 | Cut old piping (existing line 140025), haul to ground level |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7850 | Grinding, bevelling of old piping & fit-up with new spool |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7860 | Full welding of joints & installation of Tie-In spool 140219 |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7870 | Inspection NDT / RT of selected joints |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7880 | Install pipe supports (if any) |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7890 | Prepare and hydrotest up to XX BarG |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7900 | Hydrotest witness inspection |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7910 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7920 | Touch-up painting works |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7930 | Deblinding, remove temporary support / scaffolds |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7940 | Reinstall insulation (if any) |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7950 | Torquing / flange management & hand-over to Ops |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7960 | End of Work |  | 2026-02-20 |  |  | 1 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| LP- Steam from EU3 Tie In Point to 52-HE-1402 Tag # IP-B-B3-M3-L-3230 |  |  | 2026-02-20 |  |  | 88 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7630 | Start of Work |  | 2026-02-20 |  |  | 1 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7640 | Obtain Work Permit |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7650 | Removal of insulation & Wallthickness measurement |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7660 | Drilling one hole (cold drilling, airdriven) & Gas measurement |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7670 | Cut old piping (existing line 140472), haul to ground level |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7680 | Grinding, bevelling of old piping & fit-up with new spool |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7690 | Welding of weldolet and installation of Tie-In spool 140489 |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7700 | Inspection NDT / RT of selected joints |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7710 | Install pipe supports (if any) |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7720 | Prepare and hydrotest up to XX BarG Iif required) |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7730 | Hydrotest witness inspection Iif required) |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7740 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7750 | Touch-up painting works |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7760 | Deblinding, remove temporary support / scaffolds |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7770 | Reinstall insulation (if any) |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7780 | Torquing / flange management & hand-over to Ops |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7790 | End of Work |  | 2026-02-20 |  |  | 1 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| Package 2 |  |  | 2026-02-20 |  |  | 127 | 29-Mar-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| Regeneration Gas from 50-HE-1402 Tag # IP-B-B3-M3-L-3260 |  |  | 2026-02-20 |  |  | 88 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7460 | Start of Work |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7470 | Obtain Work Permit |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7480 | Wallthickness measurement |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7490 | Drilling one hole (cold drilling, airdriven) & Gas measurement |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7500 | Cut old piping (existing line 140025), haul to ground level |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7510 | Grinding, bevelling of old piping & fit-up with new spool |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7520 | Full welding of joints & installation of Tie-In spool 140025 |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7530 | Inspection NDT / RT of selected joints |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7540 | Install pipe supports (if any) |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7550 | Prepare and hydrotest up to XX BarG (if required) |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7560 | Hydrotest witness inspection (if required) |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7570 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7580 | Touch-up painting works |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7590 | Deblinding, remove temporary support / scaffolds |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7600 | Reinstall insulation (if any) |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7610 | Torquing / flange management & hand-over to Ops |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7620 | End of Work |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| Nitrogen from EU3 to 64PSV14001 Tag # IP-B-B3-M3-L-3380 |  |  | 2026-02-20 |  |  | 88 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7290 | Start of Work |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7300 | Obtain Work Permit |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7310 | Wallthickness measurement |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7320 | Drilling one hole (cold drilling, airdriven) & Gas measurement |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7330 | Cut old piping (existing line 140148) , haul to ground level |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7340 | Grinding, bevelling of old piping & fit-up with new spool |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7350 | Full welding of joints & installation of Tie-In spool 140038 |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7360 | Inspection NDT / RT of selected joints |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7370 | Install pipe supports (if any) |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7380 | Prepare and hydrotest up to XX BarG |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7390 | Hydrotest witness inspection |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7400 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7410 | Touch-up painting works |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7420 | Deblinding, remove temporary support / scaffolds |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7430 | Reinstall insulation (if any) |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7440 | Torquing / flange management & hand-over to Ops |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7450 | End of Work |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| Regeneration Gas C4 Hydrogenation Tag # IP-B-B3-M3-L-3390 |  |  | 2026-02-20 |  |  | 88 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7120 | Start of Work |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7130 | Obtain Work Permit |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7140 | Removal of insulation & Wallthickness measurement |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7150 | Drilling one hole (cold drilling, airdriven) & Gas measurement |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7160 | Cut old piping (existing line 81142), haul to ground level |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7170 | Grinding, bevelling of old piping & fit-up with new spool |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7180 | Full welding of joints & installation of Tie-In spool 81184 |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7190 | Inspection NDT / RT of selected joints & Additional Testing of Tie-in Valve |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7200 | Install pipe supports (if any) |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7210 | Prepare and hydrotest up to XX BarG (if required) |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7220 | Hydrotest witness inspection (if required) |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7230 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7240 | Touch-up painting works |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7250 | Deblinding, remove temporary support / scaffolds |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7260 | Reinstall insulation (if any) |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7270 | Torquing / flange management & hand-over to Ops |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7280 | End of Work |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| 50AT-14101A sample tap Tag # IP-B-B3-M3-L-3430 |  |  | 2026-02-20 |  |  | 88 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A6950 | Start of Work |  | 2026-02-20 |  |  | 1 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A6960 | Obtain Work Permit |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A6970 | Removal of insulation & Wallthickness measurement |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A6980 | Drilling one hole (cold drilling, airdriven) & Gas measurement |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A6990 | Cut old piping & support, haul to ground level |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7000 | Grinding, bevelling of old piping & fit-up with new spool |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7010 | Full welding of joints including weldolet & installation of Tie-In spool |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7020 | Inspection NDT / RT of selected joints |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7030 | Install pipe supports (if any) |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7040 | Prepare and hydrotest up to XX BarG (if required) |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7050 | Hydrotest witness inspection (if required) |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7060 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7070 | Touch-up painting works |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7080 | Deblinding, remove temporary support / scaffolds |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7090 | Reinstall insulation (if any) |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7100 | Torquing / flange management & hand-over to Ops |  | 2026-02-20 |  |  | 0 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| A7110 | End of Work |  | 2026-02-20 |  |  | 1 | 15-Apr-25 A | 2026-03-27 | 20-May-25 A | 2026-02-20 | 2026-03-27
| Regeneration Gas C4 Hydrogenation vent point Tag # P-B-B3-M3-L-3500 |  |  | 2026-02-20 |  |  | 88 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6780 | Start of Work |  | 2026-02-20 |  |  | 1 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6790 | Obtain Work Permit |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6800 | Removal of Insulation & Wallthickness measurement |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6810 | Drilling one hole (cold drilling, airdriven) & Gas measurement |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6820 | Cut old piping (existing line 81142), haul to ground level |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6830 | Grinding, bevelling of old piping & fit-up with new spool |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6840 | Welding of 8x1" weldolet and flange with valve and instrument |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6850 | Inspection NDT / RT of selected joints |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A38070 | Install pipe supports (if any) |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A38080 | Prepare and hydrotest up to XX BarG (if required) |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A38090 | Hydrotest witness inspection (if required) |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6890 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6900 | Touch-up painting works |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6910 | Deblinding, remove temporary support / scaffolds |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6920 | Reinstall insulation (if any) |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6930 | Torquing / flange management & hand-over to Ops |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6940 | End of Work |  | 2026-02-20 |  |  | 1 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| Sample point in Regeneration gas cooler outlet Tag # IP-B-B3-M3-L-3510 |  |  | 2026-02-20 |  |  | 88 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6610 | Start of Work |  | 2026-02-20 |  |  | 1 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6620 | Obtain Work Permit |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6630 | Wallthickness measurement |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6640 | Drilling one hole (cold drilling, airdriven) & Gas measurement |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6650 | Cut old piping (existing line 140024), haul to ground level |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6660 | Grinding, bevelling of old piping & fit-up with new spool |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6670 | Welding of 20x1" weldolet and flange with valve and instrument 50S-14161L |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6680 | Inspection NDT / RT of selected joints |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6690 | Install pipe supports (if any) |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6700 | Prepare and hydrotest up to XX BarG (if required) |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6710 | Hydrotest witness inspection (if required) |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6720 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6730 | Touch-up painting works |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6740 | Deblinding, remove temporary support / scaffolds |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6750 | Reinstall insulation (if any) |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6760 | Torquing / flange management & hand-over to Ops |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6770 | End of Work |  | 2026-02-20 |  |  | 1 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| Reinforced Branch connection for WG flare (Installation of 5 Tie Ins) Tag # IP-B-B3-M3-L-3520 |  |  | 2026-02-20 |  |  | 88 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6440 | Start of Work |  | 2026-02-20 |  |  | 1 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6450 | Obtain Work Permit |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6460 | Wallthickness measurement |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6470 | Drilling one hole (cold drilling, airdriven) & Gas measurement |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6480 | Cut old piping (existing line 140301), haul to ground level |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6490 | Grinding, bevelling of old piping & fit-up with new spool |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6500 | Full welding of joints (tie in Tee piece, than the tie in spools) |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6510 | Inspection NDT / RT of selected joints |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6520 | Install pipe supports (if any) |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6530 | Prepare and hydrotest up to XX BarG (if required) |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6540 | Hydrotest witness inspection (if required) |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6550 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6560 | Touch-up painting works |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6570 | Deblinding, remove temporary support / scaffolds |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6580 | Reinstall insulation (if any) |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6590 | Torquing / flange management & hand-over to Ops |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6600 | End of Work |  | 2026-02-20 |  |  | 1 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| Reinforced Branch connection pipe specification break for WG flare Tag # P-B-B3-M3-L-3530 |  |  | 2026-02-20 |  |  | 88 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6270 | Start of Work |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6280 | Obtain Work Permit |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6290 | Wallthickness measurement |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6300 | Drilling one hole (cold drilling, airdriven) & Gas measurement |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6310 | Cut old piping (existing line 140301), haul to ground level |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6320 | Grinding, bevelling of old piping & fit-up with new spool |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6330 | Full welding of joints |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6340 | Inspection NDT / RT of selected joints |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6350 | Install pipe supports (if any) |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6360 | Prepare and hydrotest up to XX BarG (if required) |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6370 | Hydrotest witness inspection (if required) |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6380 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6390 | Touch-up painting works |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6400 | Deblinding, remove temporary support / scaffolds |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6410 | Reinstall insulation (if any) |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6420 | Torquing / flange management & hand-over to Ops |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6430 | End of Work |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| PSA2 Off Gas from EU3 to EU3 Tie In point Tag # IP-B-H3-B3-L-2022 |  |  | 2026-02-20 |  |  | 88 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6100 | Start of Work |  | 2026-02-20 |  |  | 1 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6110 | Obtain Work Permit |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6120 | Removal of insulation & Wallthickness measurement |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6130 | Drilling one hole (cold drilling, airdriven) & Gas measurement |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6140 | Cut old piping (existing line 45024) , haul to ground level |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6150 | Grinding, bevelling of old piping & fit-up with new spool |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6160 | Full welding of joints, Tee & installation of Tie-In spool 72069 |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6170 | Inspection NDT / RT of selected joints |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6180 | Install pipe supports (if any) |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6190 | Prepare and hydrotest up to XX BarG (if required) |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6200 | Hydrotest witness inspection (if required) |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6210 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6220 | Touch-up painting works |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6230 | Deblinding, remove temporary support / scaffolds |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6240 | Reinstall insulation (if any) |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6250 | Torquing / flange management & hand-over to Ops |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6260 | End of Work |  | 2026-02-20 |  |  | 1 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| Process Water from EU3 H2 to EU3 Tie In Point Tag # IP-B-H3-B3-L-2042 |  |  | 2026-02-20 |  |  | 88 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5930 | Start of Work |  | 2026-02-20 |  |  | 1 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5940 | Obtain Work Permit |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5950 | Wallthickness measurement |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5960 | Drilling one hole (cold drilling, airdriven) & Gas measurement |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5970 | Cut old piping (existing line 20002), haul to ground level |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5980 | Grinding, bevelling of old piping & fit-up with new spool |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5990 | Welding of Tie-in spool weldolet |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6000 | Inspection NDT / RT of selected joints |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6010 | Install pipe supports (if any) |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6020 | Prepare and hydrotest up to XX BarG (if required) |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6030 | Hydrotest witness inspection (if required) |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6040 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6050 | Touch-up painting works |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6060 | Deblinding, remove temporary support / scaffolds |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6070 | Reinstall insulation (if any) |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6080 | Torquing / flange management & hand-over to Ops |  | 2026-02-20 |  |  | 0 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A6090 | End of Work |  | 2026-02-20 |  |  | 1 | 29-Mar-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| Warm Liquid Flare from EU3 to EU3 Tie In point Tag # IP-B-H3-B3-L-2052 |  |  | 2026-02-20 |  |  | 88 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5760 | Start of Work |  | 2026-02-20 |  |  | 1 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5770 | Obtain Work Permit |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5780 | Wallthickness measurement |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5790 | Drilling one hole (cold drilling, airdriven) & Gas measurement |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5800 | Cut old piping (existing line 140301), haul to ground level |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5810 | Grinding, bevelling of old piping & fit-up with new spool |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5820 | Full welding of joints & installation of Tie-In spool 140382 |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5830 | Inspection NDT / RT of selected joints |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5840 | Install pipe supports (if any) |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5850 | Prepare and hydrotest up to XX BarG |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5860 | Hydrotest witness inspection |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5870 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5880 | Touch-up painting works |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5890 | Deblinding, remove temporary support / scaffolds |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5900 | Reinstall insulation (if any) |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5910 | Torquing / flange management & hand-over to Ops |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5920 | End of Work |  | 2026-02-20 |  |  | 1 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| Warm Gas Flare from EU3 to EU3 Tie In point Tag # IP-B-H3-B3-L-2062 |  |  | 2026-02-20 |  |  | 88 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5590 | Start of Work |  | 2026-02-20 |  |  | 1 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5600 | Obtain Work Permit |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5610 | Wallthickness measurement |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5620 | Drilling one hole (cold drilling, airdriven) & Gas measurement |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5630 | Cut old piping (existing line 140301), haul to ground level |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5640 | Grinding, bevelling of old piping & fit-up with new spool |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5650 | Full welding of joints & installation of Tie-In spool 140381 |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5660 | Inspection NDT / RT of selected joints |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5670 | Install pipe supports (if any) |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5680 | Prepare and hydrotest up to XX BarG |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5690 | Hydrotest witness inspection |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5700 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5710 | Touch-up painting works |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5720 | Deblinding, remove temporary support / scaffolds |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5730 | Reinstall insulation (if any) |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5740 | Torquing / flange management & hand-over to Ops |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5750 | End of Work |  | 2026-02-20 |  |  | 1 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| LP Condensate from EU3 H2 to EU3 Tie In point Tag # IP-B-H3-B3-L-2072 |  |  | 2026-02-20 |  |  | 88 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5420 | Start of Work |  | 2026-02-20 |  |  | 1 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5430 | Obtain Work Permit |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5440 | Removal of insulation & Wallthickness measurement |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5450 | Drilling one hole (cold drilling, airdriven) & Gas measurement |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5460 | Cut old piping (existing line 140101), haul to ground level |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5470 | Grinding, bevelling of old piping & fit-up with new spool |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5480 | Full welding of joints including weldolet & installation of Tie-In spool 140434 |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5490 | Inspection NDT / RT of selected joints |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5500 | Install pipe supports (if any) |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5510 | Prepare and hydrotest up to XX BarG (if required) |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5520 | Hydrotest witness inspection (if required) |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5530 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5540 | Touch-up painting works |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5550 | Deblinding, remove temporary support / scaffolds |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5560 | Reinstall insulation (if any) |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5570 | Torquing / flange management & hand-over to Ops |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5580 | End of Work |  | 2026-02-20 |  |  | 1 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| Cooling Water Return from EU3 H2 to U&O3 Tie In point Tag # IP-B-H3-U3-L-1101 |  |  | 2026-02-20 |  |  | 88 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5250 | Start of Work |  | 2026-02-20 |  |  | 1 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5260 | Obtain Work Permit |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5270 | Wall thickness measurement |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5280 | Drilling one hole (cold drilling, airdriven) & Gas measurement |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5290 | Cut old piping (existing line '00018), haul to ground level |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5300 | Grinding, bevelling of old piping & fit-up with new spool |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5310 | Full welding of joints including weldolet & installation of Tie-In spool 00215 |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5320 | Inspection NDT / RT of selected joints |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5330 | Install pipe supports (if any) |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5340 | Prepare and hydrotest up to XX BarG (if required) |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5350 | Hydrotest witness inspection (if required) |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5360 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5370 | Touch-up painting works |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5380 | Deblinding, remove temporary support / scaffolds |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5390 | Reinstall insulation (if any) |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5400 | Torquing / flange management & hand-over to Ops |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5410 | End of Work |  | 2026-02-20 |  |  | 1 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| PSA2 Off Gas Recycle to CGC Tag # IP-B-M3-B3-L-3040 |  |  | 2026-02-20 |  |  | 88 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5080 | Start of Work |  | 2026-02-20 |  |  | 3 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5090 | Obtain Work Permit |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5100 | Removal of insulation & Wall thickness measurement |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5110 | Drilling one hole (cold drilling, airdriven) & Gas measurement |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5120 | Cut old piping & support, haul to ground level |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5130 | Grinding, bevelling of old piping & fit-up with new spool |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5140 | Full welding of weldolet & installation of Tie-In spool 72068 |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5150 | Inspection NDT / RT of selected joints |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A38010 | Install pipe supports (if any) |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A38020 | Prepare and hydrotest up to XX BarG (if required) |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A38030 | Hydrotest witness inspection (if required) |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A38040 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A38050 | Touch-up painting works |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A38060 | Deblinding, remove temporary support / scaffolds |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5220 | Reinstall insulation (if any) |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5230 | Torquing / flange management & hand-over to Ops |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5240 | End of Work |  | 2026-02-20 |  |  | 1 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| Regeneration Gas from 50-HE-1410 to 50-VV-1401 Tag # IP-B-M3-B3-L-3070 |  |  | 2026-02-20 |  |  | 88 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4910 | Start of Work |  | 2026-02-20 |  |  | 1 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4920 | Obtain Work Permit |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4930 | Removal of insulation & Wall thickness measurement |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4940 | Drilling one hole (cold drilling, airdriven) & Gas measurement |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4950 | Cut old piping (existing line 45024), haul to ground level |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4960 | Grinding, bevelling of old piping & fit-up with new spool |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4970 | Full welding of joints & installation of Tie-In spool 140489 |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4980 | Inspection NDT / RT of selected joints |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4990 | Install pipe supports (if any) |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5000 | Prepare and hydrotest up to XX BarG (if required) |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5010 | Hydrotest witness inspection (if required) |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5020 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5030 | Touch-up painting works |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5040 | Deblinding, remove temporary support / scaffolds |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5050 | Reinstall insulation (if any) |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5060 | Torquing / flange management & hand-over to Ops |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A5070 | End of Work |  | 2026-02-20 |  |  | 1 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| Regeneration Gas to 50-VV-1401 Tag # IP-B-M3-B3-L-3110 |  |  | 2026-02-20 |  |  | 88 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4740 | Start of Work |  | 2026-02-20 |  |  | 1 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4750 | Obtain Work Permit |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4760 | Wall thickness measurement |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4770 | Drilling one hole (cold drilling, airdriven) & Gas measurement |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4780 | Cut old piping (existing line 140025) , haul to ground level |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4790 | Grinding, bevelling of old piping & fit-up with new spool |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4800 | Full welding of joints |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4810 | Inspection NDT / RT of selected joints |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4820 | Install pipe supports (if any) |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4830 | Prepare and hydrotest up to XX BarG (if required) |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4840 | Hydrotest witness inspection (if required) |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4850 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4860 | Touch-up painting works |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4870 | Deblinding, remove temporary support / scaffolds |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4880 | Reinstall insulation (if any) |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4890 | Torquing / flange management & hand-over to Ops |  | 2026-02-20 |  |  | 0 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4900 | End of Work |  | 2026-02-20 |  |  | 1 | 02-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| Cooling Water from 50-HE-1410 to EU3 Tie-In Point Tag # IP-B-M3-B3-L-3130 |  |  | 2026-02-20 |  |  | 88 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4570 | Start of Work |  | 2026-02-20 |  |  | 1 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4580 | Obtain Work Permit |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4590 | Wall thickness measurement |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4600 | Drilling one hole (cold drilling, airdriven) & Gas measurement |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4610 | Cut old piping (existing line 140034) & support, haul to ground level |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4620 | Grinding, bevelling of old piping & fit-up with new spool |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4630 | Full welding of joints & installation of Tie-In spool 140065 |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4640 | Inspection NDT / RT of selected joints |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4650 | Install pipe supports (if any) |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4660 | Prepare and hydrotest up to XX BarG (if required) |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4670 | Hydrotest witness inspection (if required) |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4680 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4690 | Touch-up painting works |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4700 | Deblinding, remove temporary support / scaffolds |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4710 | Reinstall insulation (if any) |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4720 | Torquing / flange management & hand-over to Ops |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4730 | End of Work |  | 2026-02-20 |  |  | 1 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| Warm Gas Flare from 50-HE-1410 to EU3 Tie In Point Tag # IP-B-M3-B3-L-3140 |  |  | 2026-02-20 |  |  | 88 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4400 | Start of Work |  | 2026-02-20 |  |  | 1 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4410 | Obtain Work Permit |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4420 | Wall thickness measurement |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4430 | Drilling one hole (cold drilling, airdriven) & Gas measurement |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4440 | Cut old piping (existing line 140301), haul to ground level |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4450 | Grinding, bevelling of old piping & fit-up with new spool |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4460 | Full welding of joints & installation of Tie-In spool 140379 |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4470 | Inspection NDT / RT of selected joints |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4480 | Install pipe supports (if any) |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4490 | Prepare and hydrotest up to XX BarG (if required) |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4500 | Hydrotest witness inspection (if required) |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4510 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4520 | Touch-up painting works |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4530 | Deblinding, remove temporary support / scaffolds |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4540 | Reinstall insulation (if any) |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4550 | Torquing / flange management & hand-over to Ops |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4560 | End of Work |  | 2026-02-20 |  |  | 1 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| Treated VHP BFW from 52-HE-1402 to EU3 Tag # IP-B-M3-B3-L-3220 |  |  | 2026-02-20 |  |  | 88 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4230 | Start of Work |  | 2026-02-20 |  |  | 1 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4240 | Obtain Work Permit |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4250 | Removal of insulation and wall thickness measurement |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4260 | Drilling one hole (cold drilling, airdriven) & Gas measurement |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4270 | Cut old piping (existing line 140025) & support, haul to ground level |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4280 | Grinding, bevelling of old piping & fit-up with new spool |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4290 | Full welding of joints (Tee-piece) & installation of Tie-In spool 140218 |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4300 | Inspection NDT / RT of selected joints |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4310 | Install pipe supports (if any) |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4320 | Prepare and hydrotest up to XX BarG (if required) |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4330 | Hydrotest witness inspection (if required) |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4340 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4350 | Touch-up painting works |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4360 | Deblinding, remove temporary support / scaffolds |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4370 | Reinstall insulation (if any) |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4380 | Torquing / flange management & hand-over to Ops |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4390 | End of Work |  | 2026-02-20 |  |  | 1 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| LP- Condensate from 52-HE-1402 to 54-VV-1402 Tag # IP-B-M3-B3-L-3240 |  |  | 2026-02-20 |  |  | 87 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4060 | Start of Work |  | 2026-02-20 |  |  | 1 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4070 | Obtain Work Permit |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4080 | Removal of insulation |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4090 | Removal of blind flange 54-VV-1402, N02 & Gas measurement |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4100 | Check of cleanliness of vessel and new pipe |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4110 | Connection of tie in spool |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4190 | Deblinding, remove temporary support / scaffolds |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4200 | Reinstall insulation (if any) |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4210 | Torquing / flange management & hand-over to Ops |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4220 | End of Work |  | 2026-02-20 |  |  | 1 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| Tailgas to 50-VV-1401 Tag # IP-B-M3-B3-L-3250 |  |  | 2026-02-20 |  |  | 88 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A3890 | Start of Work |  | 2026-02-20 |  |  | 1 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A3900 | Obtain Work Permit |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A3910 | Removal of insulation and wall thickness measurement |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A3920 | Drilling one hole (cold drilling, airdriven) & Gas measurement |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A3930 | Cut old piping (existing line 45024), haul to ground level |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A3940 | Grinding, bevelling of old piping & fit-up with new spool |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A3950 | Full welding of joints & installation of Tie-In spool 45024 |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A3960 | Inspection NDT / RT of selected joints |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A3970 | Install pipe supports (if any) |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A3980 | Prepare and hydrotest up to XX BarG (if required) |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A3990 | Hydrotest witness inspection (if required) |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4000 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4010 | Touch-up painting works |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4020 | Deblinding, remove temporary support / scaffolds |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4030 | Reinstall insulation (if any) |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A4040 | Torquing / flange management & hand-over to Ops |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A38000 | End of Work |  | 2026-02-20 |  |  | 1 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| Regeneration Gas C4 Hydrogenation to 50-HE-1402 Tag # IP-B-M3-B3-L-3280 |  |  | 2026-02-20 |  |  | 89 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A3720 | Start of Work |  | 2026-02-20 |  |  | 1 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A3730 | Obtain Work Permit |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A3740 | Removal of insulation and wall thickness measurement |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A3750 | Drilling one hole (cold drilling, airdriven) & Gas measurement |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A3760 | Cut old piping (existing line 41022), haul to ground level |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A3770 | Grinding, bevelling of old piping & fit-up with new spool |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A3780 | Full welding of joints & installation of Tie-In spool 81142 |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A3790 | Inspection NDT / RT of selected joints |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A3800 | Install pipe supports (if any) |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A3810 | Prepare and hydrotest up to XX BarG (if required) |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A3820 | Hydrotest witness inspection (if required) |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A3830 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A3840 | Touch-up painting works |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A3850 | Deblinding, remove temporary support / scaffolds |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A3860 | Reinstall insulation (if any) |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A3870 | Torquing / flange management & hand-over to Ops |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A3880 | End of Work |  | 2026-02-20 |  |  | 1 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| Regeneration Gas C4 Hydrogenation Condensate Tag # IP-B-M3-B3-L-3290 |  |  | 2026-02-20 |  |  | 88 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A3550 | Start of Work |  | 2026-02-20 |  |  | 1 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A37970 | Obtain Work Permit |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A3570 | Wall thickness measurement |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A37980 | Drilling one hole (cold drilling, airdriven) & Gas measurement |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A37990 | Cut old piping (existing line 140028) , haul to ground level |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A3600 | Grinding, bevelling of old piping & fit-up with new spool |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A3610 | Full welding of joints & installation of Tie-In spool 140066 |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A3620 | Inspection NDT / RT of selected joints |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A3630 | Install pipe supports (if any) |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A3640 | Prepare and hydrotest up to XX BarG (if any) |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A3650 | Hydrotest witness inspection (if any) |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A3660 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A3670 | Touch-up painting works |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A3680 | Deblinding, remove temporary support / scaffolds |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A3690 | Reinstall insulation (if any) |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A3700 | Torquing / flange management & hand-over to Ops |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A3710 | End of Work |  | 2026-02-20 |  |  | 1 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| Warm Gas Flare from 13-KX-402/50-HE-1402 to EU3 Tie In Point Tag # P-B-M3-B3-L-3300 |  |  | 2026-02-20 |  |  | 88 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A37820 | Start of Work |  | 2026-02-20 |  |  | 1 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A3390 | Obtain Work Permit |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A37830 | Wall thickness measurement |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A37840 | Drilling one hole (cold drilling, airdriven) & Gas measurement |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A37850 | Cut old piping (existing line 140301) , haul to ground level |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A37860 | Grinding, bevelling of old piping & fit-up with new spool |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A37870 | Full welding of joints & installation of Tie-In spool 140301 |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A37880 | Inspection NDT / RT of selected joints |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A37890 | Install pipe supports (if any) |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A37900 | Prepare and hydrotest up to XX BarG |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A37910 | Hydrotest witness inspection |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A37920 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A37930 | Touch-up painting works |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A37940 | Deblinding, remove temporary support / scaffolds |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A37950 | Reinstall insulation (if any) |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A37960 | Torquing / flange management & hand-over to Ops |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A3540 | End of Work |  | 2026-02-20 |  |  | 1 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| Cold Gas from 13-PSV-4508 to EU3 Tie In Tag # P-B-M3-B3-L-3410 |  |  | 2026-02-20 |  |  | 88 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A3210 | Start of Work |  | 2026-02-20 |  |  | 1 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A3220 | Obtain Work Permit |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A3230 | Wall thickness measurement |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A3240 | Drilling one hole (cold drilling, airdriven) & Gas measurement |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A37800 | Cut old piping (existing line 140321) & support, haul to ground level |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A3260 | Grinding, bevelling of old piping & fit-up with new spool |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A3270 | Purge with 24" balloons & welding of Tie-In spool 144564 |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A3280 | Inspection NDT / RT of selected joints |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A3290 | Install pipe supports (if any) |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A3300 | Prepare and hydrotest up to XX BarG (if required) |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A3310 | Hydrotest witness inspection (if required) |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A3320 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A3330 | Touch-up painting works |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A3340 | Deblinding, remove temporary support / scaffolds |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A37810 | Reinstall insulation (if any) |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A3360 | Torquing / flange management & hand-over to Ops |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A3370 | End of Work |  | 2026-02-20 |  |  | 1 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| Package 4 |  |  | 2026-02-20 |  |  | 110 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| 50AT-14101A sample tap vent return to process Tag # IP-B-M3-B3-L-3420 |  |  | 2026-02-20 |  |  | 87 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A3040 | Start of Work |  | 2026-02-20 |  |  | 2 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A3050 | Obtain Work Permit |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A3060 | Gas measurement |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A3070 | Making tubing connection |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A3170 | Deblinding, remove temporary support / scaffolds |  | 2026-02-20 |  |  | 0 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A3200 | End of Work |  | 2026-02-20 |  |  | 2 | 10-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| Instrument Air from U&O3 Tie In point to EU3 H2 Tag # IP-B-U3-H3-L-1020 |  |  | 2026-02-20 |  |  | 94 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A2870 | Start of Work |  | 2026-02-20 |  |  | 10 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A2880 | Obtain Work Permit |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A3030 | End of Work |  | 2026-02-20 |  |  | 10 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| Plant Air from U&O3 Tie In point to EU3 H2 Tag # IP-B-U3-H3-L-1030 |  |  | 2026-02-20 |  |  | 94 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A2700 | Start of Work |  | 2026-02-20 |  |  | 10 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A2710 | Obtain Work Permit |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A2860 | End of Work |  | 2026-02-20 |  |  | 10 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| Nitrogen from U&O3 Tie In point to EU3 H2 Tag # IP-B-U3-H3-L-1040 |  |  | 2026-02-20 |  |  | 94 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A2530 | Start of Work |  | 2026-02-20 |  |  | 10 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A2540 | Obtain Work Permit |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A2690 | End of Work |  | 2026-02-20 |  |  | 10 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| LP Steam from U&O3 Tie In point to EU3 H2 Tag # IP-B-U3-H3-L-1050 |  |  | 2026-02-20 |  |  | 88 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A2360 | Start of Work |  | 2026-02-20 |  |  | 1 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A2370 | Obtain Work Permit |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A2380 | Wall thickness measurement |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A2390 | Drilling one hole (cold drilling, airdriven) & Gas measurement |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A2400 | Cut old piping (existing line 00271) & support, haul to ground level |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A2410 | Grinding, bevelling of old piping & fit-up with new spool |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A2420 | Full welding of joints & Installation of Tie-In spool '0005 |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A2430 | Inspection NDT / RT of selected joints |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A2440 | Install pipe supports (if any) |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A2450 | Prepare and hydrotest up to XX BarG |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A2460 | Hydrotest witness inspection |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A2470 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A2480 | Touch-up painting works |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A2490 | Deblinding, remove temporary support / scaffolds |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A2500 | Reinstall insulation (if any) |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A2510 | Torquing / flange management & hand-over to Ops |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A2520 | End of Work |  | 2026-02-20 |  |  | 1 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| Service water from U&O3 Tie In point to to EU3 H2 Tag # IP-B-U3-H3-L-1060 |  |  | 2026-02-20 |  |  | 88 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A2190 | Start of Work |  | 2026-02-20 |  |  | 1 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A2200 | Obtain Work Permit |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A2210 | Removal of insulation and wall thickness measurement |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A2220 | Drilling one hole (cold drilling, airdriven) & Gas measurement |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A2230 | Cut old piping (existing line '00061) & support, haul to ground level |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A2240 | Grinding, bevelling of old piping & fit-up with new spool |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A2250 | Full welding of joints |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A2260 | Inspection NDT / RT of selected joints |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A2270 | Install pipe supports (if any) |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A2280 | Prepare and hydrotest up to XX BarG |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A2290 | Hydrotest witness inspection |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A2300 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A2310 | Touch-up painting works |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A2320 | Deblinding, remove temporary support / scaffolds |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A2330 | Reinstall insulation (if any) |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A2340 | Torquing / flange management & hand-over to Ops |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A2350 | End of Work |  | 2026-02-20 |  |  | 1 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| Potable water from U&O3 Tie In point to EU3 H2 Tag # IP-B-U3-H3-L-1070 |  |  | 2026-02-20 |  |  | 88 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A2020 | Start of Work |  | 2026-02-20 |  |  | 1 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A2030 | Obtain Work Permit |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A2040 | Wall thickness measurement |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A2050 | Drilling one hole (cold drilling, airdriven) & Gas measurement |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A2060 | Cut old piping & support, haul to ground level |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A2070 | Grinding, bevelling of old piping & fit-up with new spool |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A2080 | Full welding of joints |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A2090 | Inspection NDT / RT of selected joints |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A2100 | Install pipe supports (if any) |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A2110 | Prepare and hydrotest up to XX BarG |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A2120 | Hydrotest witness inspection |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A2130 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A2140 | Touch-up painting works |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A2150 | Deblinding, remove temporary support / scaffolds |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A2160 | Reinstall insulation (if any) |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A2170 | Torquing / flange management & hand-over to Ops |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A2180 | End of Work |  | 2026-02-20 |  |  | 1 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| Cooling Water Supply from U&O3 Tie In Point to EU3 H2 Tag # P-B-U3-H3-L-1090 |  |  | 2026-02-20 |  |  | 88 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A1340 | Start of Work |  | 2026-02-20 |  |  | 1 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A1350 | Obtain Work Permit |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A1360 | Removal of insulation (if any) & measurement of wall thickness |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A1370 | Pull-out piping components (Valves, TW/TE, TG, PT, PG if any) |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A1380 | Cut old piping (existing line '00234) & support, haul to ground level |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A1390 | Grinding, bevelling of old piping & fit-up with new spool |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A1400 | Welding of weldolet |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A1410 | Inspection NDT / RT of selected joints |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A1420 | Install pipe supports (if any) |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A1430 | Prepare and hydrotest up to XX BarG (if required) |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A1440 | Hydrotest witness inspection (if required) |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A1450 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A1460 | Touch-up painting works (if any) |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A1470 | Deblinding, remove temporary support / scaffolds |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A1480 | Reinstall insulation (if any) |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A1490 | Torquing / flange management & hand-over to Ops |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A37650 | End of Work |  | 2026-02-20 |  |  | 1 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| Oily water from EU3 H2 to U&O3 Tie In point Tag # IP-B-U3-H3-L-1121 |  |  | 2026-02-20 |  |  | 88 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A37570 | Start of Work |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A37580 | Obtain Work Permit |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A37590 | Removal of insulation & measurement of wall thickness |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A37600 | Drilling one hole (cold drilling, air-driven) & Gas measurement |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A1210 | Cut old piping (existing line '00018), haul to ground level |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A1220 | Grinding, bevelling of old piping & fit-up with new spool |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A1230 | Full welding of joints |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A37610 | Inspection NDT / RT of selected joints |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A37620 | Install pipe supports (if any) |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A37630 | Prepare and hydrotest up to XX BarG (if required) |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A37640 | Hydrotest witness inspection (if required) |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A1280 | Reinstall back piping components (TW/TE, TG, PT, PG if any) |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A1290 | Touch-up painting works |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A1300 | Deblinding, remove temporary support / scaffolds |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A1310 | Reinstall insulation (if any) |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A1320 | Torquing / flange management & hand-over to Ops |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A1330 | End of Work |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| TA Tie-In Execution - U/G Tie-Ins |  |  | 2026-02-20 |  |  | 94 | 03-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| Fire Water from U&O3 Tie point to EU3 H2 (South west) Tag # IP-B-U3-H3-L-1080 |  |  | 2026-02-20 |  |  | 86 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A1850 | Start of Work |  | 2026-02-20 |  |  | 1 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A1860 | Obtain Work Permit |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A1870 | Install temporary support / scaffolds as site |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A1880 | Install isolation balloon |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A1980 | Deblinding, remove temporary support / scaffolds |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A1990 | Reinstall insulation (if any) |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A2000 | Torquing / flange management & hand-over to Ops |  | 2026-02-20 |  |  | 0 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A2010 | End of Work |  | 2026-02-20 |  |  | 1 | 08-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| Fire Water from U&O3 Tie point to EU3 H2 (south east) Tag # IP-B-U3-H3-L-1082 |  |  | 2026-02-20 |  |  | 90 | 03-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A1680 | Start of Work |  | 2026-02-20 |  |  | 2 | 03-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A1690 | Obtain Work Permit |  | 2026-02-20 |  |  | 0 | 03-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A1700 | Removal of insulation & wall thickness measurement |  | 2026-02-20 |  |  | 0 | 03-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A1710 | Drilling one hole (cold drilling, airdriven) & Gas measurement |  | 2026-02-20 |  |  | 0 | 03-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A1720 | Cut old piping & support, haul to ground level |  | 2026-02-20 |  |  | 0 | 03-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A1730 | Grinding, bevelling of old piping & fit-up with new spool |  | 2026-02-20 |  |  | 0 | 03-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A1740 | Full welding of joints |  | 2026-02-20 |  |  | 0 | 03-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A1750 | Inspection NDT / RT of selected joints |  | 2026-02-20 |  |  | 0 | 03-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A1760 | Install pipe supports (if any) |  | 2026-02-20 |  |  | 0 | 03-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A1770 | Prepare and hydrotest up to XX BarG |  | 2026-02-20 |  |  | 0 | 03-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A1780 | Hydrotest witness inspection |  | 2026-02-20 |  |  | 0 | 03-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A1790 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) |  | 2026-02-20 |  |  | 0 | 03-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A1800 | Touch-up painting works |  | 2026-02-20 |  |  | 0 | 03-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A1810 | Deblinding, remove temporary support / scaffolds |  | 2026-02-20 |  |  | 0 | 03-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A1820 | Reinstall insulation (if any) |  | 2026-02-20 |  |  | 0 | 03-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A1830 | Torquing / flange management & hand-over to Ops |  | 2026-02-20 |  |  | 0 | 03-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A1840 | End of Work |  | 2026-02-20 |  |  | 2 | 03-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| Fire Water from U&O3 Tie point to EU3 H2 (North east) Tag # IP-B-U3-H3-L-1086 |  |  | 2026-02-20 |  |  | 90 | 03-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A37660 | Start of Work |  | 2026-02-20 |  |  | 2 | 03-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A1520 | Obtain Work Permit |  | 2026-02-20 |  |  | 0 | 03-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A1530 | Install temporary support / scaffolds as site |  | 2026-02-20 |  |  | 0 | 03-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A37670 | Pull-out piping components (Valves, TW/TE, TG, PT, PG if any) |  | 2026-02-20 |  |  | 0 | 03-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A37680 | Cut old piping (20" HDPE Line), haul to ground level |  | 2026-02-20 |  |  | 0 | 03-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A37690 | Grinding, bevelling of old piping & fit-up with new spool (new HDPE TEE) |  | 2026-02-20 |  |  | 0 | 03-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A37700 | Installation, alignment and welding of HDPE Tee to existing header 18011 & install. of tie-in spools 18481 & welding |  | 2026-02-20 |  |  | 0 | 03-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A37710 | Inspection (all required HDPE welding examinations) of selected joints |  | 2026-02-20 |  |  | 0 | 03-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A37720 | Install pipe supports (if any) |  | 2026-02-20 |  |  | 0 | 03-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A37730 | Prepare and hydrotest up to XX BarG (if any) |  | 2026-02-20 |  |  | 0 | 03-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A37740 | Hydrotest witness inspection (if any) |  | 2026-02-20 |  |  | 0 | 03-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A37750 | Reinstall back piping components (TW/TE, TG, PT, PG if any) |  | 2026-02-20 |  |  | 0 | 03-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A37760 | Touch-up painting works |  | 2026-02-20 |  |  | 0 | 03-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A37770 | Deblinding, remove temporary support / scaffolds |  | 2026-02-20 |  |  | 0 | 03-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A37780 | Reinstall insulation (if any) |  | 2026-02-20 |  |  | 0 | 03-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A37790 | Torquing / flange management & hand-over to Ops |  | 2026-02-20 |  |  | 0 | 03-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| A1670 | End of Work |  | 2026-02-20 |  |  | 2 | 03-Apr-25 A | 2026-03-27 | 17-May-25 A | 2026-02-20 | 2026-03-27
| GF Piping Works |  |  | 2026-03-28 |  |  | 254 | 2026-03-28 | 2026-04-20 | 2027-01-17 | 2027-01-17 | 2027-03-11 | 46
| AG |  |  | 2026-03-28 |  |  | 254 | 2026-03-28 | 2026-04-20 | 2027-01-17 | 2027-01-17 | 2027-03-11 | 46
| A60800 | Piping - Pre-Fabrication Shop |  | 2026-03-28 |  |  | 150 | 2026-03-28 | 2026-04-20 | 2026-09-17 | 2026-09-17 | 2026-10-11 | 20
| A3400 | Painting Piping - Fabrication Shop |  | 2026-04-14 |  |  | 150 | 2026-04-14 | 2026-05-07 | 2026-10-05 | 2026-10-05 | 2026-10-28 | 20
| A3380 | Piping Eection at Site |  | 2026-05-02 |  |  | 150 | 2026-05-02 | 2026-05-25 | 2026-10-22 | 2026-10-22 | 2026-11-15 | 20
| A3430 | Hydro testing and reinstatment |  | 2026-09-20 |  |  | 50 | 2026-09-20 | 2026-11-12 | 2026-11-16 | 2026-11-16 | 2027-01-09 | 46
| A3420 | Final Touch up and painting of joints |  | 2026-10-01 |  |  | 50 | 2026-10-01 | 2026-11-24 | 2026-11-28 | 2026-11-28 | 2027-01-20 | 46
| A3410 | Piping Insulation |  | 2026-10-10 |  |  | 86 | 2026-10-10 | 2026-12-02 | 2027-01-17 | 2027-01-17 | 2027-03-11 | 46
| UG |  |  | 2026-06-06 |  |  | 156 | 2026-06-06 | 2026-08-16 | 2026-12-03 | 2026-12-03 | 2027-01-20 | 41
| A3480 | U/G Piping Erection Oily Water (CS) |  | 2026-08-16 |  |  | 21 | 2026-08-16 | 2026-12-28 | 2026-09-08 | 2026-09-08 | 2027-01-20 | 115
| A3470 | U/G Piping Erection & Hydrotesting Cooling Water Lines (CS) |  | 2026-06-06 |  |  | 100 | 2026-06-06 | 2026-08-16 | 2026-09-29 | 2026-09-29 | 2026-12-09 | 61
| A23540 | Piping Erection of Fire water piping (HDPE) UG including hydrotesting |  | 2026-07-16 |  |  | 120 | 2026-07-16 | 2026-09-03 | 2026-12-03 | 2026-12-03 | 2027-01-20 | 41
| Insulation |  |  | 2026-06-23 |  |  | 90 | 2026-06-23 | 2026-10-08 | 2026-10-05 | 2026-10-05 | 2027-01-20 | 92
| A3580 | Complete Insulation, Fire-Proofing and Painting works |  | 2026-06-23 |  |  | 90 | 2026-06-23 | 2026-10-08 | 2026-10-05 | 2026-10-05 | 2027-01-20 | 92
| Painting |  |  | 2026-08-09 |  |  | 96 | 2026-08-09 | 2027-03-27 | 2026-11-28 | 2026-11-28 | 2027-07-15 | 197
| A61630 | Painting |  | 2026-08-09 |  |  | 96 | 2026-08-09 | 2027-03-27 | 2026-11-28 | 2026-11-28 | 2027-07-15 | 197
| A61640 | Painting punch clearing |  | 2026-11-29 |  |  | 4 | 2026-11-29 | 2027-07-17 | 2026-12-02 | 2026-12-02 | 2027-07-20 | 197
| Electrical Construction |  |  | 2026-02-20 |  |  | 501 | 01-Mar-25 A | 2026-03-27 | 2026-12-28 | 2026-12-28 | 2027-01-20 | 17
| Equipment Installation |  |  | 2026-02-20 |  |  | 451 | 03-Apr-25 A | 2026-03-27 | 2026-12-28 | 2026-12-28 | 2027-01-20 | 17
| System and Panels Installation |  |  | 2026-04-16 |  |  | 48 | 2026-04-16 | 2026-11-26 | 2026-06-10 | 2026-06-10 | 2027-01-20 | 192
| A61650 | System and Panels Installations |  | 2026-04-16 |  |  | 48 | 2026-04-16 | 2026-11-26 | 2026-06-10 | 2026-06-10 | 2027-01-20 | 192
| GF Interposing Relay Panel |  |  | 2026-09-19 |  |  | 51 | 2026-09-19 | 2026-11-23 | 2026-11-16 | 2026-11-16 | 2027-01-20 | 56
| A24070 | Installation of Interposting Relay Panel |  | 2026-09-19 |  |  | 12 | 2026-09-19 | 2026-11-23 | 2026-10-01 | 2026-10-01 | 2026-12-06 | 56
| A24580 | Cable terminations and loop testing - IRP |  | 2026-10-03 |  |  | 21 | 2026-10-03 | 2026-12-07 | 2026-10-26 | 2026-10-26 | 2026-12-30 | 56
| A24790 | IRP - Pre Comm |  | 2026-10-27 |  |  | 18 | 2026-10-27 | 2026-12-31 | 2026-11-16 | 2026-11-16 | 2027-01-20 | 56
| GF DG Set |  |  | 2026-08-08 |  |  | 67 | 2026-08-08 | 2026-11-04 | 2026-10-24 | 2026-10-24 | 2027-01-20 | 76
| A3829 | Installation of DG Set |  | 2026-08-08 |  |  | 27 | 2026-08-08 | 2026-11-04 | 2026-09-07 | 2026-09-07 | 2026-12-05 | 76
| A24590 | Cable terminations and loop testing - DG Set |  | 2026-09-08 |  |  | 22 | 2026-09-08 | 2026-12-06 | 2026-10-03 | 2026-10-03 | 2026-12-30 | 76
| A24800 | DG Set - Pre Comm |  | 2026-10-04 |  |  | 18 | 2026-10-04 | 2026-12-31 | 2026-10-24 | 2026-10-24 | 2027-01-20 | 76
| GF Electrical Heat Tracing (53 Meter for piping + 340 Meter for instrumentation) |  |  | 2026-08-31 |  |  | 62 | 2026-08-31 | 2026-11-10 | 2026-11-11 | 2026-11-11 | 2027-01-20 | 61
| A24090 | Electrical Heat Tracing works |  | 2026-08-31 |  |  | 20 | 2026-08-31 | 2026-11-10 | 2026-09-23 | 2026-09-23 | 2026-12-02 | 61
| A24410 | Cable terminations and loop testing - Electric Heat Tracing |  | 2026-09-23 |  |  | 24 | 2026-09-23 | 2026-12-03 | 2026-10-21 | 2026-10-21 | 2026-12-30 | 61
| A24660 | Electric Heat Tracing - Pre Comm |  | 2026-10-21 |  |  | 18 | 2026-10-21 | 2026-12-31 | 2026-11-11 | 2026-11-11 | 2027-01-20 | 61
| GF Power Transformers (Qty 05) |  |  | 2026-08-15 |  |  | 77 | 2026-08-15 | 2026-10-24 | 2026-11-11 | 2026-11-11 | 2027-01-20 | 60
| A24120 | Installation of Power Transformers |  | 2026-08-15 |  |  | 35 | 2026-08-15 | 2026-10-24 | 2026-09-23 | 2026-09-23 | 2026-12-02 | 60
| A24470 | Cable terminations and loop testing - Power Transformers |  | 2026-09-24 |  |  | 24 | 2026-09-24 | 2026-12-03 | 2026-10-21 | 2026-10-21 | 2026-12-30 | 60
| A24680 | Power Transformers - Pre Comm |  | 2026-10-22 |  |  | 18 | 2026-10-22 | 2026-12-31 | 2026-11-11 | 2026-11-11 | 2027-01-20 | 60
| GF HV Capacitor Bay |  |  | 2026-08-04 |  |  | 56 | 2026-08-04 | 2026-11-17 | 2026-10-07 | 2026-10-07 | 2027-01-20 | 90
| A24080 | Installation of Capacitor Bay |  | 2026-08-04 |  |  | 18 | 2026-08-04 | 2026-11-17 | 2026-08-24 | 2026-08-24 | 2026-12-07 | 90
| A24490 | Cable terminations and HV Capacitor Bay |  | 2026-08-25 |  |  | 21 | 2026-08-25 | 2026-12-08 | 2026-09-17 | 2026-09-17 | 2026-12-31 | 90
| A24700 | HV Capacitor Bay - Pre Comm |  | 2026-09-19 |  |  | 17 | 2026-09-19 | 2027-01-02 | 2026-10-07 | 2026-10-07 | 2027-01-20 | 90
| GF Switchgear (LV, MV) |  |  | 2026-08-22 |  |  | 81 | 2026-08-22 | 2026-10-19 | 2026-11-23 | 2026-11-23 | 2027-01-20 | 50
| A3839 | Installation of Switchgear |  | 2026-08-22 |  |  | 30 | 2026-08-22 | 2026-10-19 | 2026-09-24 | 2026-09-24 | 2026-11-22 | 50
| A24530 | Cable terminations and loop testing - Switchgear (LV, MV) |  | 2026-09-26 |  |  | 30 | 2026-09-26 | 2026-11-23 | 2026-10-29 | 2026-10-29 | 2026-12-27 | 50
| A24740 | Switchgear (LV, MV) - Pre Comm |  | 2026-10-31 |  |  | 21 | 2026-10-31 | 2026-12-28 | 2026-11-23 | 2026-11-23 | 2027-01-20 | 50
| GF Variable Fequency Drives (VFDs) LV Qty = 03 |  |  | 2026-08-04 |  |  | 80 | 2026-08-04 | 2026-10-20 | 2026-11-04 | 2026-11-04 | 2027-01-20 | 66
| A24140 | Installation of VFD |  | 2026-08-04 |  |  | 24 | 2026-08-04 | 2026-10-20 | 2026-08-31 | 2026-08-31 | 2026-11-16 | 66
| A24540 | Cable terminations and loop testing - VFD |  | 2026-09-01 |  |  | 32 | 2026-09-01 | 2026-11-17 | 2026-10-07 | 2026-10-07 | 2026-12-23 | 66
| A24750 | VFDs - Pre Comm |  | 2026-10-08 |  |  | 24 | 2026-10-08 | 2026-12-24 | 2026-11-04 | 2026-11-04 | 2027-01-20 | 66
| GF NGR Panel Qty 02 |  |  | 2026-08-04 |  |  | 50 | 2026-08-04 | 2026-11-24 | 2026-09-30 | 2026-09-30 | 2027-01-20 | 96
| A3869 | Installation of NGR Panel |  | 2026-08-04 |  |  | 12 | 2026-08-04 | 2026-11-24 | 2026-08-17 | 2026-08-17 | 2026-12-07 | 96
| A24570 | Cable terminations and loop testing NGR Panel |  | 2026-08-18 |  |  | 21 | 2026-08-18 | 2026-12-08 | 2026-09-10 | 2026-09-10 | 2026-12-31 | 96
| A24780 | NGR Panel - Pre Comm |  | 2026-09-12 |  |  | 17 | 2026-09-12 | 2027-01-02 | 2026-09-30 | 2026-09-30 | 2027-01-20 | 96
| GF Cathodic Protection (CP) Total CS Piping Length - 499 Meters |  |  | 2026-10-04 |  |  | 74 | 2026-10-04 | 2026-10-27 | 2026-12-28 | 2026-12-28 | 2027-01-20 | 20
| A24100 | Cathodic Protection for complete CS Piping |  | 2026-10-04 |  |  | 32 | 2026-10-04 | 2026-10-27 | 2026-11-09 | 2026-11-09 | 2026-12-02 | 20
| A24420 | Cable terminations and loop testing - Cathodic Protection |  | 2026-11-10 |  |  | 24 | 2026-11-10 | 2026-12-03 | 2026-12-07 | 2026-12-07 | 2026-12-30 | 20
| A24670 | Cathodic Protection - Pre Comm |  | 2026-12-08 |  |  | 18 | 2026-12-08 | 2026-12-31 | 2026-12-28 | 2026-12-28 | 2027-01-20 | 20
| GF UPS (AC - 60 KVA, 20 KVA, DC-UPS 6.5 KVA) Qty 1+1+1 = 03 Nos |  |  | 2026-08-15 |  |  | 62 | 2026-08-15 | 2026-11-10 | 2026-10-25 | 2026-10-25 | 2027-01-20 | 75
| A24060 | Installation of UPS |  | 2026-08-15 |  |  | 24 | 2026-08-15 | 2026-11-10 | 2026-09-10 | 2026-09-10 | 2026-12-07 | 75
| A24450 | Cable terminations and loop testing - UPS |  | 2026-09-12 |  |  | 20 | 2026-09-12 | 2026-12-08 | 2026-10-04 | 2026-10-04 | 2026-12-30 | 75
| A24640 | UPS - Pre Comm |  | 2026-10-05 |  |  | 18 | 2026-10-05 | 2026-12-31 | 2026-10-25 | 2026-10-25 | 2027-01-20 | 75
| TA IPCS Modification by ABB |  |  | 2026-02-20 |  |  | 5 | 03-Apr-25 A | 2026-03-27 | 10-May-25 A | 2026-02-20 | 2026-03-27
| A34830 | Installation of FOPP (02 )in existing CCB |  | 2026-02-20 |  |  | 5 | 03-Apr-25 A | 2026-03-27 | 10-May-25 A | 2026-02-20 | 2026-03-27
| TA Switchgear Modification by SIEMENS |  |  | 2026-02-20 |  |  | 11 | 03-Apr-25 A | 2026-03-27 | 10-May-25 A | 2026-02-20 | 2026-03-27
| A17970 | Bus-bar differential testing Bus-A - feeder H01 (TA) |  | 2026-02-20 |  |  | 5 | 03-Apr-25 A | 2026-03-27 | 10-May-25 A | 2026-02-20 | 2026-03-27
| A17980 | Bus-bar differential testing Bus-B - feeder H16 (TA) |  | 2026-02-20 |  |  | 3 | 03-Apr-25 A | 2026-03-27 | 10-May-25 A | 2026-02-20 | 2026-03-27
| A34440 | Switchgear Modifications - Siemens |  | 2026-02-20 |  |  | 5 | 03-Apr-25 A | 2026-03-27 | 10-May-25 A | 2026-02-20 | 2026-03-27
| A34800 | Installation of Surge Arersstor |  | 2026-02-20 |  |  | 5 | 03-Apr-25 A | 2026-03-27 | 10-May-25 A | 2026-02-20 | 2026-03-27
| A34810 | Installation of Dummy Plugs |  | 2026-02-20 |  |  | 5 | 03-Apr-25 A | 2026-03-27 | 10-May-25 A | 2026-02-20 | 2026-03-27
| A34820 | Installation of Castle key interlock and key exchange box |  | 2026-02-20 |  |  | 5 | 03-Apr-25 A | 2026-03-27 | 10-May-25 A | 2026-02-20 | 2026-03-27
| TA SCMS Modification by SIEMENS |  |  | 2026-02-20 |  |  | 10 | 14-Apr-25 A | 2026-03-27 | 14-May-25 A | 2026-02-20 | 2026-03-27
| A17990 | SCMS FOPP Modifications - Siemens (By Client) |  | 2026-02-20 |  |  | 5 | 14-Apr-25 A | 2026-03-27 | 25-Apr-25 A | 2026-02-20 | 2026-03-27
| A34780 | Mapping of SCMS in IPCS |  | 2026-02-20 |  |  | 3 | 26-Apr-25 A | 2026-03-27 | 30-Apr-25 A | 2026-02-20 | 2026-03-27
| A34840 | Annuciator Panel Modification |  | 2026-02-20 |  |  | 5 | 01-May-25 A | 2026-03-27 | 09-May-25 A | 2026-02-20 | 2026-03-27
| A34850 | HMI Graphics Update |  | 2026-02-20 |  |  | 3 | 10-May-25 A | 2026-03-27 | 14-May-25 A | 2026-02-20 | 2026-03-27
| TA UPS Modification |  |  | 2026-02-20 |  |  | 5 | 15-Apr-25 A | 2026-03-27 | 13-May-25 A | 2026-02-20 | 2026-03-27
| A17960 | Modification in DC power supply arrangmeent- UPS |  | 2026-02-20 |  |  | 5 | 15-Apr-25 A | 2026-03-27 | 13-May-25 A | 2026-02-20 | 2026-03-27
| Cabling Work |  |  | 2026-07-29 |  |  | 92 | 2026-07-29 | 2026-10-06 | 2026-11-12 | 2026-11-12 | 2027-01-20 | 59
| BF Electrical Works |  |  | 2026-07-29 |  |  | 92 | 2026-07-29 | 2026-10-06 | 2026-11-12 | 2026-11-12 | 2027-01-20 | 59
| A17740 | Power Cables Laying |  | 2026-07-29 |  |  | 36 | 2026-07-29 | 2026-10-06 | 2026-09-08 | 2026-09-08 | 2026-11-16 | 59
| A18750 | FO Cable laying for IPCSS and SCMS |  | 2026-07-29 |  |  | 36 | 2026-07-29 | 2026-10-14 | 2026-09-08 | 2026-09-08 | 2026-11-25 | 67
| A18740 | Termination of Power cables and Loop Testing |  | 2026-09-09 |  |  | 26 | 2026-09-09 | 2026-11-17 | 2026-10-08 | 2026-10-08 | 2026-12-16 | 59
| A21980 | FO Cable termination for IPCSS and SCMS |  | 2026-09-21 |  |  | 26 | 2026-09-21 | 2026-11-29 | 2026-10-20 | 2026-10-20 | 2026-12-28 | 59
| BFW4080 | Other Electrical Works |  | 2026-10-21 |  |  | 20 | 2026-10-21 | 2026-12-29 | 2026-11-12 | 2026-11-12 | 2027-01-20 | 59
| Earthing System Installation |  |  | 2026-07-28 |  |  | 72 | 2026-07-28 | 2026-10-29 | 2026-10-19 | 2026-10-19 | 2027-01-20 | 80
| A61660 | Earthing System Installation |  | 2026-07-28 |  |  | 60 | 2026-07-28 | 2026-10-29 | 2026-10-05 | 2026-10-05 | 2027-01-06 | 80
| A61670 | Earthing System Testing |  | 2026-10-06 |  |  | 12 | 2026-10-06 | 2027-01-07 | 2026-10-19 | 2026-10-19 | 2027-01-20 | 80
| Lightning System Installation |  |  | 2026-09-15 |  |  | 15 | 2026-09-15 | 2027-01-04 | 2026-10-03 | 2026-10-03 | 2027-01-20 | 94
| GF Lighting Fixtures (Almost 50% Exd = 354 Nos) |  |  | 2026-09-15 |  |  | 15 | 2026-09-15 | 2027-01-04 | 2026-10-03 | 2026-10-03 | 2027-01-20 | 94
| A3590 | Complete Street lighting |  | 2026-09-15 |  |  | 15 | 2026-09-15 | 2027-01-04 | 2026-10-03 | 2026-10-03 | 2027-01-20 | 94
| TA Site Survey AC & DC UPS(Chloride Terchnology) |  |  | 2026-02-20 |  |  | 10 | 01-Mar-25 A | 2026-03-27 | 15-Mar-25 A | 2026-02-20 | 2026-03-27
| A35010 | Site Survey for UPS Modification |  | 2026-02-20 |  |  | 4 | 01-Mar-25 A | 2026-03-27 | 07-Mar-25 A | 2026-02-20 | 2026-03-27
| A37540 | Site Survey Report for UPS Modification |  | 2026-02-20 |  |  | 4 | 08-Mar-25 A | 2026-03-27 | 15-Mar-25 A | 2026-02-20 | 2026-03-27
| TA Site Survey MCMS System (Bently Nevada) |  |  | 2026-02-20 |  |  | 10 | 01-Mar-25 A | 2026-03-27 | 15-Mar-25 A | 2026-02-20 | 2026-03-27
| A35020 | Site Survey for MCMS Modification |  | 2026-02-20 |  |  | 4 | 01-Mar-25 A | 2026-03-27 | 07-Mar-25 A | 2026-02-20 | 2026-03-27
| A37550 | Site Survey Report for MCMS Modification |  | 2026-02-20 |  |  | 4 | 08-Mar-25 A | 2026-03-27 | 15-Mar-25 A | 2026-02-20 | 2026-03-27
| For Switchgear & SCMS(Siemens) |  |  | 2026-02-20 |  |  | 10 | 01-Mar-25 A | 2026-03-27 | 15-Mar-25 A | 2026-02-20 | 2026-03-27
| A34980 | Site Survey for SG & SCMS Modification |  | 2026-02-20 |  |  | 4 | 01-Mar-25 A | 2026-03-27 | 07-Mar-25 A | 2026-02-20 | 2026-03-27
| A35140 | Health Check / Site Survey Report |  | 2026-02-20 |  |  | 4 | 08-Mar-25 A | 2026-03-27 | 15-Mar-25 A | 2026-02-20 | 2026-03-27
| Instrumentation/Telecom Construction |  |  | 2026-02-20 |  |  | 518 | 11-Feb-25 A | 2026-03-27 | 2026-12-28 | 2026-12-28 | 2027-01-20 | 17
| MCMS/DCS/ESD/F&G Modification / Installation (as applicable) |  |  | 2026-02-20 |  |  | 359 | 01-May-25 A | 2026-03-27 | 2026-11-23 | 2026-11-23 | 2027-01-20 | 42
| GF Fire Fighting Equipment |  |  | 2026-08-04 |  |  | 71 | 2026-08-04 | 2026-10-31 | 2026-10-25 | 2026-10-25 | 2027-01-20 | 75
| A3849 | Installation of Fire Fighting Equipment |  | 2026-08-04 |  |  | 36 | 2026-08-04 | 2026-10-31 | 2026-09-14 | 2026-09-14 | 2026-12-10 | 75
| A24400 | Cable terminations and loop testing - Fire Fighting Equipment |  | 2026-09-15 |  |  | 17 | 2026-09-15 | 2026-12-12 | 2026-10-04 | 2026-10-04 | 2026-12-30 | 75
| A24610 | Fire Fighting Equip - Pre Comm |  | 2026-10-05 |  |  | 18 | 2026-10-05 | 2026-12-31 | 2026-10-25 | 2026-10-25 | 2027-01-20 | 75
| BF DCS/ESD Modification by Honeywell |  |  | 2026-05-23 |  |  | 35 | 2026-05-23 | 2026-10-21 | 2026-07-02 | 2026-07-02 | 2026-11-30 | 130
| A17750 | DCS modification for integration between brownfield and greenfield |  | 2026-05-23 |  |  | 35 | 2026-05-23 | 2026-10-21 | 2026-07-02 | 2026-07-02 | 2026-11-30 | 130
| GF Fire Detection Alarm System, Local Fire Control Panel & Clean Agent Unit |  |  | 2026-08-04 |  |  | 90 | 2026-08-04 | 2026-10-08 | 2026-11-16 | 2026-11-16 | 2027-01-20 | 56
| A24110 | Installation of Fire Detection Alarm System, LFCP and Clean Agent Unit |  | 2026-08-04 |  |  | 36 | 2026-08-04 | 2026-10-08 | 2026-09-14 | 2026-09-14 | 2026-11-18 | 56
| A24460 | Cable terminations and loop testing - FDAS, LFCP and Clean Agent Unit |  | 2026-09-15 |  |  | 30 | 2026-09-15 | 2026-11-19 | 2026-10-19 | 2026-10-19 | 2026-12-23 | 56
| A24650 | FDAS, LFCP & CAU - Pre Comm |  | 2026-10-20 |  |  | 24 | 2026-10-20 | 2026-12-24 | 2026-11-16 | 2026-11-16 | 2027-01-20 | 56
| TA EU3 ICSS(DCS/ESD/GDS) Modifications by HONEYWELL |  |  | 2026-02-20 |  |  | 24 | 01-May-25 A | 2026-03-27 | 15-May-25 A | 2026-02-20 | 2026-03-27
| A21970 | Cross wiring between existing marshalling racks ( Instrument Tie-in No 6,7) |  | 2026-02-20 |  |  | 3 | 01-May-25 A | 2026-03-27 | 15-May-25 A | 2026-02-20 | 2026-03-27
| A34910 | Installation of New Non-IS ESD Cabinet (83-JM3021-D) (Intrument Tie-In-8) |  | 2026-02-20 |  |  | 8 | 01-May-25 A | 2026-03-27 | 15-May-25 A | 2026-02-20 | 2026-03-27
| A34920 | Non-UPS Power &earthing for New Non-IS ESD Cabinet (Intrument Tie-In- 9) |  | 2026-02-20 |  |  | 5 | 01-May-25 A | 2026-03-27 | 15-May-25 A | 2026-02-20 | 2026-03-27
| A34930 | (OEM) Vendor (Honeywell) loose supplied (Intrument Tie-In- 9.1) |  | 2026-02-20 |  |  | 8 | 01-May-25 A | 2026-03-27 | 15-May-25 A | 2026-02-20 | 2026-03-27
| A34940 | COLD Section ESD shutdown console switches (Intrument Tie-In- 11) |  | 2026-02-20 |  |  | 8 | 01-May-25 A | 2026-03-27 | 15-May-25 A | 2026-02-20 | 2026-03-27
| A34950 | OEM) Vendor loose supplied material installation Including Honeywell, Safetec (Instrument Tie-12) |  | 2026-02-20 |  |  | 8 | 01-May-25 A | 2026-03-27 | 15-May-25 A | 2026-02-20 | 2026-03-27
| A34960 | Change in the Existing DCS configuration for BF added/ Modified Field Tag (Instrument TieIn-14) |  | 2026-02-20 |  |  | 3 | 01-May-25 A | 2026-03-27 | 15-May-25 A | 2026-02-20 | 2026-03-27
| A34970 | Change in the Existing ESD configuration for BF added/ Modified Field Tag(Instrument TieIn-14.1) |  | 2026-02-20 |  |  | 3 | 01-May-25 A | 2026-03-27 | 15-May-25 A | 2026-02-20 | 2026-03-27
| GF F&G Flame Detectors, MCP, Beacon (Nos 324) |  |  | 2026-09-02 |  |  | 70 | 2026-09-02 | 2026-11-01 | 2026-11-23 | 2026-11-23 | 2027-01-20 | 50
| A24130 | Installation of F&G Detectors, MCP,Beacon |  | 2026-09-02 |  |  | 29 | 2026-09-02 | 2026-11-01 | 2026-10-06 | 2026-10-06 | 2026-12-03 | 50
| A24500 | Cable terminations and loop testing - F&G Detectors, MCP, Beacon |  | 2026-10-06 |  |  | 23 | 2026-10-06 | 2026-12-05 | 2026-11-02 | 2026-11-02 | 2026-12-30 | 50
| A24710 | F&G, MCP, Beacon - Pre Comm |  | 2026-11-02 |  |  | 18 | 2026-11-02 | 2026-12-31 | 2026-11-23 | 2026-11-23 | 2027-01-20 | 50
| TA Fire Alarm System Modification by SAFCO+HONEYWELL |  |  | 2026-02-20 |  |  | 11 | 15-May-25 A | 2026-03-27 | 25-May-25 A | 2026-02-20 | 2026-03-27
| A34740 | Existing Deluge Console switches shall be relocated including retesting of existing loops on new dual tier Console |  | 2026-02-20 |  |  | 11 | 15-May-25 A | 2026-03-27 | 25-May-25 A | 2026-02-20 | 2026-03-27
| TA Modification in MCMS System by BENTLY NAVEDA |  |  | 2026-02-20 |  |  | 13 | 01-May-25 A | 2026-12-01 | 15-May-25 A | 2026-02-20 | 2026-12-01
| A34710 | Existing MCMS system 1 will be upgraded with new EVO series servers for EU3 existing network |  | 2026-02-20 |  |  | 13 | 01-May-25 A | 2026-12-01 | 15-May-25 A | 2026-02-20 | 2026-12-01
| Field Instrument Installation |  |  | 2026-02-20 |  |  | 442 | 01-May-25 A | 2026-03-27 | 2026-12-28 | 2026-12-28 | 2027-01-20 | 17
| GF Machine Condition Monitoring System |  |  | 2026-08-04 |  |  | 74 | 2026-08-04 | 2026-10-27 | 2026-10-28 | 2026-10-28 | 2027-01-20 | 72
| A3789 | Installation of MCMS |  | 2026-08-04 |  |  | 36 | 2026-08-04 | 2026-10-27 | 2026-09-14 | 2026-09-14 | 2026-12-07 | 72
| A24480 | Cable terminations and loop testing - MCMS |  | 2026-09-15 |  |  | 21 | 2026-09-15 | 2026-12-08 | 2026-10-08 | 2026-10-08 | 2026-12-31 | 72
| A24690 | MCMS - Pre Comm |  | 2026-10-10 |  |  | 17 | 2026-10-10 | 2027-01-02 | 2026-10-28 | 2026-10-28 | 2027-01-20 | 72
| TA Replacement of Existing Air Distribution Pot |  |  | 2026-02-20 |  |  | 7 | 01-May-25 A | 2026-03-27 | 15-May-25 A | 2026-02-20 | 2026-03-27
| A34860 | Replacoment of existing ADP (E3-SP-0146) from 6-ways to 10-ways (Intrument Tie-In- 1.1) |  | 2026-02-20 |  |  | 1 | 01-May-25 A | 2026-03-27 | 15-May-25 A | 2026-02-20 | 2026-03-27
| A34870 | Replacoment of existing ADP (E3-SP-0322) from 6-ways to 10-ways (Intrument Tie-In- 1) |  | 2026-02-20 |  |  | 1 | 01-May-25 A | 2026-03-27 | 15-May-25 A | 2026-02-20 | 2026-03-27
| A34880 | Replacoment of existing ADP (E3-SP-0149) from 6-ways to 10-ways (Intrument Tie-In- 2) |  | 2026-02-20 |  |  | 1 | 01-May-25 A | 2026-03-27 | 15-May-25 A | 2026-02-20 | 2026-03-27
| GF Acess Control System |  |  | 2026-09-09 |  |  | 74 | 2026-09-09 | 2026-10-27 | 2026-12-05 | 2026-12-05 | 2027-01-20 | 40
| A3859 | Installation of Access Control System |  | 2026-09-09 |  |  | 24 | 2026-09-09 | 2026-10-27 | 2026-10-07 | 2026-10-07 | 2026-11-23 | 40
| A24430 | Cable terminations and loop testing - ACS |  | 2026-10-07 |  |  | 32 | 2026-10-07 | 2026-11-24 | 2026-11-14 | 2026-11-14 | 2026-12-30 | 40
| A24620 | ACS - Pre Comm |  | 2026-11-14 |  |  | 18 | 2026-11-14 | 2026-12-31 | 2026-12-05 | 2026-12-05 | 2027-01-20 | 40
| GF VESDA (Very Early Smoke Detection Apparatus) |  |  | 2026-08-04 |  |  | 68 | 2026-08-04 | 2026-11-03 | 2026-10-21 | 2026-10-21 | 2027-01-20 | 78
| A3799 | Installation of VESDA |  | 2026-08-04 |  |  | 27 | 2026-08-04 | 2026-11-03 | 2026-09-03 | 2026-09-03 | 2026-12-03 | 78
| A24510 | Cable terminations and loop testing VESDA |  | 2026-09-05 |  |  | 23 | 2026-09-05 | 2026-12-05 | 2026-09-30 | 2026-09-30 | 2026-12-30 | 78
| A24720 | VESDA - Pre Comm |  | 2026-10-01 |  |  | 18 | 2026-10-01 | 2026-12-31 | 2026-10-21 | 2026-10-21 | 2027-01-20 | 78
| GF MOVs [Ball Type 24" 150# = 01 No] |  |  | 2026-09-26 |  |  | 29 | 2026-09-26 | 2026-12-15 | 2026-10-28 | 2026-10-28 | 2027-01-20 | 72
| A24160 | Installatrion of MOV |  | 2026-09-26 |  |  | 5 | 2026-09-26 | 2026-12-15 | 2026-09-30 | 2026-09-30 | 2026-12-20 | 69
| A24550 | Cable terminations and lop termination - MOVs |  | 2026-09-30 |  |  | 12 | 2026-09-30 | 2026-12-21 | 2026-10-14 | 2026-10-14 | 2027-01-03 | 69
| A24760 | MOVS - Pre Comm |  | 2026-10-14 |  |  | 12 | 2026-10-14 | 2027-01-07 | 2026-10-28 | 2026-10-28 | 2027-01-20 | 72
| TA Compresoor CGC Turbine by MHI |  |  | 2026-02-20 |  |  | 8 | 01-Sep-25 A | 2026-03-27 | 10-Sep-25 A | 2026-02-20 | 2026-03-27
| A21840 | Turbine Governor Software modification by MHI (Intrument Tie-In- 15) |  | 2026-02-20 |  |  | 8 | 01-Sep-25 A | 2026-03-27 | 10-Sep-25 A | 2026-02-20 | 2026-03-27
| TA SGM Replacement (EMERSON) |  |  | 2026-02-20 |  |  | 7 | 01-May-25 A | 2026-12-01 | 15-May-25 A | 2026-02-20 | 2026-12-01
| A34720 | Existing Gas density Meter to replaced by SGM (EMERSON) (Intrument Tie-In- 3) |  | 2026-02-20 |  |  | 2 | 01-May-25 A | 2026-12-01 | 15-May-25 A | 2026-02-20 | 2026-12-01
| A34890 | SGM meter connection to nearest Power Distruribution Board (Intrument Tie-In- 3.1) |  | 2026-02-20 |  |  | 1 | 01-May-25 A | 2026-12-01 | 15-May-25 A | 2026-02-20 | 2026-12-01
| A34900 | New Tubing for Votex cooling of sgm Cabinet SGM (EMERSON) ((Intrument Tie-In- 2) |  | 2026-02-20 |  |  | 2 | 01-May-25 A | 2026-12-01 | 15-May-25 A | 2026-02-20 | 2026-12-01
| GF Integrated Control and Safety System GF |  |  | 2026-09-29 |  |  | 77 | 2026-09-29 | 2026-10-24 | 2026-12-28 | 2026-12-28 | 2027-01-20 | 20
| A3729 | Installation of ICSS System |  | 2026-09-29 |  |  | 35 | 2026-09-29 | 2026-10-24 | 2026-11-09 | 2026-11-09 | 2026-12-02 | 20
| A3879 | Cable terminations and loop testing ICSS - GF |  | 2026-11-09 |  |  | 21 | 2026-11-09 | 2026-12-03 | 2026-12-03 | 2026-12-03 | 2026-12-27 | 20
| A3899 | ICSS - Pre Comm |  | 2026-12-03 |  |  | 21 | 2026-12-03 | 2026-12-28 | 2026-12-28 | 2026-12-28 | 2027-01-20 | 20
| GF Gauges (PG, TG, PDG, Analzer, FE) PG - 10bar & 40bar = 19 Nos, DP = 05 Nos, TG = 09 Nos |  |  | 2026-08-29 |  |  | 66 | 2026-08-29 | 2026-11-05 | 2026-11-12 | 2026-11-12 | 2027-01-20 | 59
| A24150 | Installation of Field Instruments |  | 2026-08-29 |  |  | 24 | 2026-08-29 | 2026-11-05 | 2026-09-24 | 2026-09-24 | 2026-12-02 | 59
| A24560 | Cable terminations and loop testing - Gauges (PG, TG, PDG) |  | 2026-09-26 |  |  | 24 | 2026-09-26 | 2026-12-03 | 2026-10-22 | 2026-10-22 | 2026-12-30 | 59
| A24770 | Guages (PG, TG, PDG) - Pre Comm (Calibration/Testing) |  | 2026-10-24 |  |  | 18 | 2026-10-24 | 2026-12-31 | 2026-11-12 | 2026-11-12 | 2027-01-20 | 59
| TA Field Instrument Modification |  |  | 2026-02-20 |  |  | 10 | 01-May-25 A | 2026-12-01 | 15-May-25 A | 2026-02-20 | 2026-12-01
| A21850 | Dp Flow Transmitters to be re-calibrated ( approx qty- 20 nos.) in existing EU3 plant area |  | 2026-02-20 |  |  | 3 | 01-May-25 A | 2026-12-01 | 15-May-25 A | 2026-02-20 | 2026-12-01
| A21860 | Replacement of 13-PV-4515 and stroke calibration, loop Testing (Intrument Tie-In- 4) |  | 2026-02-20 |  |  | 10 | 01-May-25 A | 2026-12-01 | 15-May-25 A | 2026-02-20 | 2026-12-01
| A34700 | Flow Element to be re-calibrated ( approx qty- 19 nos.) in existing EU3 plant area |  | 2026-02-20 |  |  | 3 | 01-May-25 A | 2026-12-01 | 15-May-25 A | 2026-02-20 | 2026-12-01
| GF Integrated Protection Control System |  |  | 2026-09-16 |  |  | 84 | 2026-09-16 | 2026-10-15 | 2026-12-23 | 2026-12-23 | 2027-01-20 | 24
| A3769 | Installation of IPCS |  | 2026-09-16 |  |  | 30 | 2026-09-16 | 2026-10-15 | 2026-10-21 | 2026-10-21 | 2026-11-18 | 24
| A24390 | Cable terminations and loop testing - IPCS |  | 2026-10-21 |  |  | 30 | 2026-10-21 | 2026-11-19 | 2026-11-25 | 2026-11-25 | 2026-12-23 | 24
| A24600 | IPCS - Pre Comm |  | 2026-11-25 |  |  | 24 | 2026-11-25 | 2026-12-24 | 2026-12-23 | 2026-12-23 | 2027-01-20 | 24
| TA Instrumentation Work |  |  | 2026-02-20 |  |  | 25 | 01-May-25 A | 2026-11-02 | 15-May-25 A | 2026-02-20 | 2026-12-01
| A18330 | Instrument Air Tubing from existing Spare ADP connections to new valves in Brown Field area- @ 7 nos. |  | 2026-02-20 |  |  | 14 | 01-May-25 A | 2026-12-01 | 15-May-25 A | 2026-02-20 | 2026-12-01
| A23560 | Heath Check for ICSS Report |  | 2026-02-20 |  |  | 25 | 01-May-25 A | 2026-11-02 | 15-May-25 A | 2026-02-20 | 2026-11-02
| Cabling work |  |  | 2026-03-26 |  |  | 204 | 2026-03-26 | 2026-09-17 | 2026-11-18 | 2026-11-18 | 2027-01-20 | 54
| GF Cable Tray and Instrument Junction Box (Perforated Cable tray Heavy duty= 5982 Mtrs, JBs= 73 Nos) |  |  | 2026-07-29 |  |  | 96 | 2026-07-29 | 2026-10-01 | 2026-11-18 | 2026-11-18 | 2027-01-20 | 54
| A61680 | GF Cable Tray and Junction Box |  | 2026-07-29 |  |  | 96 | 2026-07-29 | 2026-10-01 | 2026-11-18 | 2026-11-18 | 2027-01-20 | 54
| GF Fibre Optic Cable (Armoured, Telecom/IT/MAS) |  |  | 2026-03-26 |  |  | 96 | 2026-03-26 | 2026-09-17 | 2026-07-15 | 2026-07-15 | 2027-01-06 | 150
| A61690 | GF Fiber Optic cable |  | 2026-03-26 |  |  | 96 | 2026-03-26 | 2026-09-17 | 2026-07-15 | 2026-07-15 | 2027-01-06 | 150
| BF Instrumentation Works |  |  | 2026-05-23 |  |  | 98 | 2026-05-23 | 2026-09-28 | 2026-09-14 | 2026-09-14 | 2027-01-20 | 111
| A21790 | Cable tray in EU3 SIS and H2 Extraction Plant SIS |  | 2026-05-23 |  |  | 11 | 2026-05-23 | 2026-11-12 | 2026-06-04 | 2026-06-04 | 2026-11-25 | 149
| A18730 | Laying UTP/CAT5 cable from B3-CCB Network cabinet (82-JS- 4844) located Ethernet swtich to B3-CCB located SOE PC |  | 2026-07-29 |  |  | 19 | 2026-07-29 | 2026-10-14 | 2026-08-20 | 2026-08-20 | 2026-11-05 | 67
| FO Cable Laying |  |  | 2026-05-23 |  |  | 26 | 2026-05-23 | 2026-10-14 | 2026-06-22 | 2026-06-22 | 2026-12-09 | 147
| A17760 | Laying FO cables inside existing trenches/pipe/conduit between EU3 SIS &new H2 Plant SIS |  | 2026-05-23 |  |  | 24 | 2026-05-23 | 2026-11-12 | 2026-06-20 | 2026-06-20 | 2026-12-09 | 149
| A21880 | Laying PU ASC PLC (TRICONEX) FO cable between new SIS at H2 Green Field area and B3-CCB for TRICONEX PLC |  | 2026-06-06 |  |  | 12 | 2026-06-06 | 2026-10-19 | 2026-06-20 | 2026-06-20 | 2026-11-01 | 116
| A21780 | Laying FO cables inside existing trenches/pipe/conduit between B3 CCB to new H2 Plant SIS |  | 2026-06-01 |  |  | 18 | 2026-06-01 | 2026-10-14 | 2026-06-22 | 2026-06-22 | 2026-11-03 | 116
| Hardwired Cable Laying |  |  | 2026-05-23 |  |  | 35 | 2026-05-23 | 2026-09-28 | 2026-07-02 | 2026-07-02 | 2027-01-20 | 174
| A18320 | Hardwired multicore/pair cable laying between EU3 SIS to H2 Extraction Plant SIS |  | 2026-05-23 |  |  | 24 | 2026-05-23 | 2026-09-28 | 2026-06-20 | 2026-06-20 | 2026-10-26 | 110
| A17770 | Trench & cable laying |  | 2026-05-23 |  |  | 35 | 2026-05-23 | 2026-12-12 | 2026-07-02 | 2026-07-02 | 2027-01-20 | 174
| Termination |  |  | 2026-05-23 |  |  | 98 | 2026-05-23 | 2026-10-10 | 2026-09-14 | 2026-09-14 | 2026-11-30 | 67
| A17780 | FO Patch cord laying |  | 2026-05-23 |  |  | 24 | 2026-05-23 | 2026-10-10 | 2026-06-18 | 2026-06-18 | 2026-11-05 | 120
| A21830 | Termination of Hardwiring multicore/pair cable inside existing/new marshalling cabinets |  | 2026-06-20 |  |  | 18 | 2026-06-20 | 2026-10-26 | 2026-07-11 | 2026-07-11 | 2026-11-15 | 110
| A21890 | Termination at Green Field H2 SIS of' PU ASC PLC (TRICONEX) FO cable between new SIS at H2 Green Field area and B3-CCB |  | 2026-06-27 |  |  | 25 | 2026-06-27 | 2026-11-02 | 2026-07-26 | 2026-07-26 | 2026-11-30 | 110
| A21810 | Termination & Testing of various FO cables laid between EU3 SIS to new H2 Plant SIS |  | 2026-08-20 |  |  | 21 | 2026-08-20 | 2026-11-07 | 2026-09-14 | 2026-09-14 | 2026-11-30 | 67
| A21820 | Termination & Testing of FO cables laid between B3-CCB to new H2 Plant SIS |  | 2026-08-20 |  |  | 21 | 2026-08-20 | 2026-11-07 | 2026-09-14 | 2026-09-14 | 2026-11-30 | 67
| Telecommunication System Installation |  |  | 2026-02-20 |  |  | 343 | 01-May-25 A | 2026-03-27 | 2026-10-31 | 2026-10-31 | 2027-01-20 | 58
| GF PAGA + Telephone |  |  | 2026-08-22 |  |  | 51 | 2026-08-22 | 2026-11-23 | 2026-10-19 | 2026-10-19 | 2027-01-20 | 80
| A3809 | Installation of PAGA+Telephone |  | 2026-08-22 |  |  | 21 | 2026-08-22 | 2026-11-23 | 2026-09-14 | 2026-09-14 | 2026-12-16 | 80
| A24440 | Cable terminations and loop testing - PAGA + Telephone |  | 2026-09-15 |  |  | 15 | 2026-09-15 | 2026-12-17 | 2026-10-01 | 2026-10-01 | 2027-01-03 | 80
| A24630 | PAGA + Telephone - Pre Comm |  | 2026-10-03 |  |  | 15 | 2026-10-03 | 2027-01-04 | 2026-10-19 | 2026-10-19 | 2027-01-20 | 80
| GF CCTV |  |  | 2026-08-25 |  |  | 57 | 2026-08-25 | 2026-11-16 | 2026-10-31 | 2026-10-31 | 2027-01-20 | 70
| A3819 | Installation of CCTV |  | 2026-08-25 |  |  | 21 | 2026-08-25 | 2026-11-16 | 2026-09-19 | 2026-09-19 | 2026-12-09 | 70
| A24520 | Cable terminations and loop testing - CCTV |  | 2026-09-19 |  |  | 21 | 2026-09-19 | 2026-12-10 | 2026-10-13 | 2026-10-13 | 2027-01-03 | 70
| A24730 | CCTV - Pre Comm |  | 2026-10-13 |  |  | 15 | 2026-10-13 | 2027-01-04 | 2026-10-31 | 2026-10-31 | 2027-01-20 | 70
| TA Telecom Related |  |  | 2026-02-20 |  |  | 13 | 01-May-25 A | 2026-03-27 | 15-May-25 A | 2026-02-20 | 2026-03-27
| A18010 | Installation of 08 Nos of Cards in existing system |  | 2026-02-20 |  |  | 13 | 01-May-25 A | 2026-03-27 | 15-May-25 A | 2026-02-20 | 2026-03-27
| A37380 | Installation of SFP in existing distribution switch (Hemal / Rommel). |  | 2026-02-20 |  |  | 13 | 01-May-25 A | 2026-03-27 | 15-May-25 A | 2026-02-20 | 2026-03-27
| Testing |  |  | 2026-06-20 |  |  | 36 | 2026-06-20 | 2026-12-10 | 2026-08-01 | 2026-08-01 | 2027-01-20 | 149
| A61700 | Fiber Optical Testing |  | 2026-06-20 |  |  | 36 | 2026-06-20 | 2026-12-10 | 2026-08-01 | 2026-08-01 | 2027-01-20 | 149
| TA Site Survey For IPCS (ABB) |  |  | 2026-02-20 |  |  | 10 | 20-Feb-25 A | 2026-03-27 | 18-Mar-25 A | 2026-02-20 | 2026-03-27
| A34990 | Site Survey for IPCS Modification |  | 2026-02-20 |  |  | 4 | 20-Feb-25 A | 2026-03-27 | 25-Feb-25 A | 2026-02-20 | 2026-03-27
| A35150 | Health Check / Site Survey Report |  | 2026-02-20 |  |  | 4 | 26-Feb-25 A | 2026-03-27 | 18-Mar-25 A | 2026-02-20 | 2026-03-27
| TA Site Survey For ICSS (Honeywell) |  |  | 2026-02-20 |  |  | 10 | 20-Feb-25 A | 2026-03-27 | 18-Mar-25 A | 2026-02-20 | 2026-03-27
| A35000 | Site Survey for ICSS Modification |  | 2026-02-20 |  |  | 4 | 20-Feb-25 A | 2026-03-27 | 25-Feb-25 A | 2026-02-20 | 2026-03-27
| A37510 | Health Check / Site Survey Report |  | 2026-02-20 |  |  | 4 | 26-Feb-25 A | 2026-03-27 | 18-Mar-25 A | 2026-02-20 | 2026-03-27
| TA Site Survey For LAN System (CISCO) |  |  | 2026-02-20 |  |  | 10 | 19-Apr-25 A | 2026-03-27 | 26-Apr-25 A | 2026-02-20 | 2026-03-27
| A37370 | Site Survey for LAN System Modification |  | 2026-02-20 |  |  | 4 | 19-Apr-25 A | 2026-03-27 | 22-Apr-25 A | 2026-02-20 | 2026-03-27
| A37520 | Health Check / Site Survey Report |  | 2026-02-20 |  |  | 4 | 23-Apr-25 A | 2026-03-27 | 26-Apr-25 A | 2026-02-20 | 2026-03-27
| TA Site Survey For CGC Turbine Software Upgarde |  |  | 2026-02-20 |  |  | 10 | 11-Feb-25 A | 2026-03-27 | 21-Feb-25 A | 2026-02-20 | 2026-03-27
| A37390 | Site Survey for CGC Turbine Software Upgrade |  | 2026-02-20 |  |  | 4 | 11-Feb-25 A | 2026-03-27 | 14-Feb-25 A | 2026-02-20 | 2026-03-27
| A37530 | Site Survey Report for CGC Turbine Software Upgrade |  | 2026-02-20 |  |  | 4 | 17-Feb-25 A | 2026-03-27 | 21-Feb-25 A | 2026-02-20 | 2026-03-27
| TA Site Survey Fire Alarm System (SAFCO) |  |  | 2026-02-20 |  |  | 10 | 19-Apr-25 A | 2026-03-27 | 26-Apr-25 A | 2026-02-20 | 2026-03-27
| A35030 | Site Survey for Fire Alaram System Modification |  | 2026-02-20 |  |  | 4 | 19-Apr-25 A | 2026-03-27 | 22-Apr-25 A | 2026-02-20 | 2026-03-27
| A37560 | Site Survey Report for Fire Alaram System Modification |  | 2026-02-20 |  |  | 4 | 23-Apr-25 A | 2026-03-27 | 26-Apr-25 A | 2026-02-20 | 2026-03-27
| Pre-commissioning |  |  | 2026-07-30 |  |  | 150 | 2026-07-30 | 2026-12-01 | 2027-01-20 | 2027-01-20 | 2027-01-20 | 0
| GF Pre Commissioning FG/OG Compressor |  |  | 2026-12-02 |  |  | 43 | 2026-12-02 | 2026-12-02 | 2027-01-20 | 2027-01-20 | 2027-01-20 | 0
| C1011 | Lube Oil Flushing |  | 2026-12-02 |  |  | 10 | 2026-12-02 | 2026-12-02 | 2026-12-13 | 2026-12-13 | 2026-12-13 | 0
| C1010 | Flushing/Airblowing and inspection of piping |  | 2026-12-02 |  |  | 15 | 2026-12-02 | 2026-12-02 | 2026-12-19 | 2026-12-19 | 2026-12-19 | 0
| C1013 | Final compressor/driver alignment |  | 2026-12-14 |  |  | 18 | 2026-12-14 | 2026-12-14 | 2027-01-03 | 2027-01-03 | 2027-01-03 | 0
| C1014 | Pre-commissioning punchlist clearing |  | 2027-01-04 |  |  | 15 | 2027-01-04 | 2027-01-04 | 2027-01-20 | 2027-01-20 | 2027-01-20 | 0
| GF Pre-Comm |  |  | 2026-10-06 |  |  | 81 | 2026-10-06 | 2026-12-10 | 2027-01-07 | 2027-01-07 | 2027-01-20 | 11
| A3560 | Piping Cleaning, Flushing & Blowing (Pre Comm) |  | 2026-10-06 |  |  | 36 | 2026-10-06 | 2026-12-10 | 2026-11-16 | 2026-11-16 | 2027-01-20 | 56
| A23900 | CCB/SIS systems overall Pre-commissioning |  |  |  |  | 0 |  |  | 2026-12-28 | 2026-12-28 | 2027-01-20 | 20
| A17800 | Overall Plant & CCB/SIS Building Pre-Commissioning |  |  |  |  | 0 |  |  | 2027-01-07 | 2027-01-07 | 2027-01-20 | 11
| A23590 | Plant Equipments Pre Commissionning |  | 2026-11-29 |  |  | 35 | 2026-11-29 | 2026-12-12 | 2027-01-07 | 2027-01-07 | 2027-01-20 | 11
| BF Pre Commissioning |  |  | 2026-07-30 |  |  | 130 | 2026-07-30 | 2026-12-01 | 2026-12-28 | 2026-12-28 | 2027-01-20 | 20
| BFW4100 | Equipment pre commissioning |  | 2026-07-30 |  |  | 26 | 2026-07-30 | 2026-12-22 | 2026-08-30 | 2026-08-30 | 2027-01-20 | 124
| BFW4070 | Pre Commissioning works - Instrumentation & Control |  | 2026-09-14 |  |  | 29 | 2026-09-14 | 2026-12-01 | 2026-10-18 | 2026-10-18 | 2027-01-03 | 67
| BFW4090 | Piping Cleaning, Flushing & Blowing (Pre Comm) |  | 2026-11-10 |  |  | 42 | 2026-11-10 | 2026-12-03 | 2026-12-28 | 2026-12-28 | 2027-01-20 | 20
| Commissioning, RFSU, Start-Up |  |  | 2026-05-23 |  |  | 293 | 2026-05-23 | 2027-02-08 | 2027-04-28 | 2027-04-28 | 2027-07-20 | 71
| Commissioning and Start-up |  |  | 2026-05-23 |  |  | 281 | 2026-05-23 | 2027-02-08 | 2027-04-15 | 2027-04-15 | 2027-07-20 | 83
| A27180 | Industrial Buildings (MCC / Control Room including HVAC System / Building Fire Alarm System / Clean Agent etc) |  | 2027-01-21 |  |  | 12 | 2027-01-21 | 2027-02-08 | 2027-02-03 | 2027-02-03 | 2027-02-22 | 16
| A27310 | Fire Water & Fire Suppression System |  | 2027-01-24 |  |  | 10 | 2027-01-24 | 2027-02-10 | 2027-02-03 | 2027-02-03 | 2027-02-22 | 16
| A27160 | Potable & Service Water System |  | 2027-01-30 |  |  | 7 | 2027-01-30 | 2027-02-16 | 2027-02-06 | 2027-02-06 | 2027-02-24 | 16
| A27290 | Instrument & Plant Air System |  | 2027-01-26 |  |  | 10 | 2027-01-26 | 2027-02-13 | 2027-02-06 | 2027-02-06 | 2027-02-24 | 16
| A27300 | Inert Gas / Nitrogen System |  | 2027-01-27 |  |  | 12 | 2027-01-27 | 2027-02-14 | 2027-02-09 | 2027-02-09 | 2027-02-28 | 16
| A27170 | Sanitary Waste Water System |  | 2027-02-06 |  |  | 5 | 2027-02-06 | 2027-02-23 | 2027-02-10 | 2027-02-10 | 2027-03-01 | 16
| A27320 | LP Steam System |  | 2027-02-01 |  |  | 10 | 2027-02-01 | 2027-02-18 | 2027-02-11 | 2027-02-11 | 2027-03-02 | 16
| A27360 | LP Condensate Collection System |  | 2027-02-03 |  |  | 10 | 2027-02-03 | 2027-02-21 | 2027-02-14 | 2027-02-14 | 2027-03-04 | 16
| A27150 | Emergency Diesel Storage & Power Generation System |  | 2027-02-08 |  |  | 10 | 2027-02-08 | 2027-02-25 | 2027-02-18 | 2027-02-18 | 2027-03-09 | 16
| A27200 | Power Supply System (Existing 33 KVA) |  | 2027-02-10 |  |  | 10 | 2027-02-10 | 2027-02-28 | 2027-02-21 | 2027-02-21 | 2027-03-11 | 16
| A27240 | MCC |  | 2027-02-13 |  |  | 12 | 2027-02-13 | 2027-03-02 | 2027-02-25 | 2027-02-25 | 2027-03-16 | 16
| A27250 | UPS System |  | 2027-02-15 |  |  | 10 | 2027-02-15 | 2027-03-04 | 2027-02-25 | 2027-02-25 | 2027-03-16 | 16
| A27190 | Plant Lighting System |  | 2027-02-17 |  |  | 10 | 2027-02-17 | 2027-03-07 | 2027-02-28 | 2027-02-28 | 2027-03-18 | 16
| A27340 | Slop / Drainage System |  | 2027-03-01 |  |  | 5 | 2027-03-01 | 2027-03-18 | 2027-03-06 | 2027-03-06 | 2027-03-24 | 16
| A27270 | Anti-Surge Protection System/ PSA2 PLC Control System / Plant F&G System / Deluge Fire Suppression System / Analyzers |  | 2027-02-22 |  |  | 12 | 2027-02-22 | 2027-03-11 | 2027-03-07 | 2027-03-07 | 2027-03-25 | 16
| A27280 | CP System / Heat Tracing System |  | 2027-02-24 |  |  | 10 | 2027-02-24 | 2027-03-14 | 2027-03-07 | 2027-03-07 | 2027-03-25 | 16
| A27330 | Oily Water System |  | 2027-03-03 |  |  | 5 | 2027-03-03 | 2027-03-21 | 2027-03-08 | 2027-03-08 | 2027-03-27 | 16
| A26480 | Telecom (PAGA / PABX / LAN / CCTV) |  | 2027-02-27 |  |  | 10 | 2027-02-27 | 2027-03-16 | 2027-03-09 | 2027-03-09 | 2027-03-28 | 16
| A27260 | DCS / ESD / Compressor Control Systems / Machine Monitoring Systems (MMS) |  | 2027-02-20 |  |  | 18 | 2027-02-20 | 2027-03-09 | 2027-03-11 | 2027-03-11 | 2027-03-30 | 16
| A27370 | Cooling Water Distribution System |  | 2027-03-06 |  |  | 7 | 2027-03-06 | 2027-03-23 | 2027-03-13 | 2027-03-13 | 2027-03-31 | 16
| A27350 | Warm & Cold Flare Blowdown System |  | 2027-03-08 |  |  | 12 | 2027-03-08 | 2027-03-25 | 2027-03-21 | 2027-03-21 | 2027-04-08 | 16
| A27380 | C4 Guard Bed Adsorber Regeneration Gas Cooler & Drip Leg to Existing Fuel Gas System |  | 2027-03-10 |  |  | 12 | 2027-03-10 | 2027-03-28 | 2027-03-23 | 2027-03-23 | 2027-04-11 | 16
| A27390 | Feed Gas from Existing Fuel Gas, C1/C2 Separation Tail Gas Expander Booster Interface Battery Limits |  | 2027-03-13 |  |  | 12 | 2027-03-13 | 2027-03-30 | 2027-03-25 | 2027-03-25 | 2027-04-13 | 16
| A27400 | PSA2 Feed Gas Compressor |  | 2027-03-16 |  |  | 12 | 2027-03-16 | 2027-04-03 | 2027-03-29 | 2027-03-29 | 2027-04-17 | 16
| A27410 | PSA2 H2 Extraction Unit, Closed Sampling & Onwards to Interface Battery Limits |  | 2027-03-20 |  |  | 12 | 2027-03-20 | 2027-04-06 | 2027-04-01 | 2027-04-01 | 2027-04-20 | 16
| A27420 | PSA2 Off Gas Compression (including all drums & coolers), Drip Leg & Onwards to Interface Battery Limits |  | 2027-03-23 |  |  | 10 | 2027-03-23 | 2027-04-10 | 2027-04-04 | 2027-04-04 | 2027-04-21 | 16
| Commissioning & Handover |  |  | 2026-05-23 |  |  | 233 | 2026-05-23 | 2027-02-23 | 2027-02-17 | 2027-02-17 | 2027-07-20 | 131
| A9915 | As BuiltUpdation of UG Composite Layouts in B3/U3 areas, Substation Layouts (B3/ U3) under revamp / modification scope |  | 2026-05-23 |  |  | 96 | 2026-05-23 | 2027-03-30 | 2026-09-12 | 2026-09-12 | 2027-07-20 | 268
| C1039 | PSSR |  | 2027-01-21 |  |  | 24 | 2027-01-21 | 2027-02-23 | 2027-02-17 | 2027-02-17 | 2027-03-22 | 28
| FG & OG Compressor - Commissioing |  |  | 2027-01-21 |  |  | 42 | 2027-01-21 | 2027-02-17 | 2027-03-10 | 2027-03-10 | 2027-04-06 | 23
| C1015 | Compressor UCP Pre-Check / Power |  | 2027-01-21 |  |  | 18 | 2027-01-21 | 2027-02-17 | 2027-02-10 | 2027-02-10 | 2027-03-09 | 23
| C1016 | Hot Loop Testing |  | 2027-01-27 |  |  | 18 | 2027-01-27 | 2027-02-23 | 2027-02-16 | 2027-02-16 | 2027-03-15 | 23
| C1017 | Energization and Motor Solo Run |  | 2027-02-01 |  |  | 18 | 2027-02-01 | 2027-02-28 | 2027-02-21 | 2027-02-21 | 2027-03-20 | 23
| C1020 | Compressor Oil Lubrication System Check |  | 2027-02-18 |  |  | 5 | 2027-02-18 | 2027-03-17 | 2027-02-23 | 2027-02-23 | 2027-03-22 | 23
| C1018 | Interlock and Emergency Shutdown Tests - Part of Dry Commissioning (C&E Check) |  | 2027-02-09 |  |  | 18 | 2027-02-09 | 2027-03-08 | 2027-03-01 | 2027-03-01 | 2027-03-28 | 23
| C1021 | PSSR |  | 2027-02-24 |  |  | 6 | 2027-02-24 | 2027-03-23 | 2027-03-02 | 2027-03-02 | 2027-03-29 | 23
| C1019 | Control system sequence checks - Part of Dry Commissioning |  | 2027-02-18 |  |  | 18 | 2027-02-18 | 2027-03-17 | 2027-03-10 | 2027-03-10 | 2027-04-06 | 23
| RFSU & Handover |  |  | 2027-02-18 |  |  | 48 | 2027-02-18 | 2027-03-30 | 2027-04-15 | 2027-04-15 | 2027-07-20 | 83
| PC1010 | Ready for Start-Up |  |  |  |  | 0 |  |  | 2027-04-04 | 2027-04-04 | 2027-04-21 | 16
| PC1050 | Project Close Out ( Handover of Care, Custody & Control of Plant ) |  |  |  |  | 0 |  |  | 2027-04-14 | 2027-04-14 | 2027-07-20 | 83
| PC1030 | Issue "AS BUILT STATUS" Maintenance & Safety Manual |  | 2027-02-18 |  |  | 48 | 2027-02-18 | 2027-05-26 | 2027-04-15 | 2027-04-15 | 2027-07-20 | 83
| FG & OG Compressor - RFSU |  |  | 2027-03-03 |  |  | 20 | 2027-03-03 | 2027-03-30 | 2027-03-25 | 2027-03-25 | 2027-04-21 | 23
| C1022 | Surge Testing |  | 2027-03-03 |  |  | 18 | 2027-03-03 | 2027-03-30 | 2027-03-23 | 2027-03-23 | 2027-04-19 | 23
| C1023 | For motor drives, motor current readings shall be obtained. |  | 2027-03-03 |  |  | 18 | 2027-03-03 | 2027-03-30 | 2027-03-23 | 2027-03-23 | 2027-04-19 | 23
| C1024 | Vibration signatures shall be obtained for all bearings |  | 2027-03-03 |  |  | 18 | 2027-03-03 | 2027-03-30 | 2027-03-23 | 2027-03-23 | 2027-04-19 | 23
| C1025 | Equipment performance data - Mapping |  | 2027-03-06 |  |  | 18 | 2027-03-06 | 2027-04-01 | 2027-03-25 | 2027-03-25 | 2027-04-21 | 23
| A61710 | Commissioning |  | 2027-01-21 |  |  | 48 | 2027-01-21 | 2027-04-14 | 2027-03-17 | 2027-03-17 | 2027-06-08 | 71
| Start-up |  |  | 2027-03-18 |  |  | 12 | 2027-03-18 | 2027-06-23 | 2027-03-31 | 2027-03-31 | 2027-07-07 | 84
| A61720 | Start-Up |  | 2027-03-18 |  |  | 12 | 2027-03-18 | 2027-06-23 | 2027-03-31 | 2027-03-31 | 2027-07-07 | 84
| Initial Operations |  |  | 2027-04-01 |  |  | 6 | 2027-04-01 | 2027-07-07 | 2027-04-07 | 2027-04-07 | 2027-07-14 | 84
| A61730 | Intial Operations |  | 2027-04-01 |  |  | 6 | 2027-04-01 | 2027-07-07 | 2027-04-07 | 2027-04-07 | 2027-07-14 | 84
| Performance Test Run |  |  | 2027-04-07 |  |  | 6 | 2027-04-07 | 2027-07-14 | 2027-04-14 | 2027-04-14 | 2027-07-20 | 84
| A61740 | Performance test Run |  | 2027-04-07 |  |  | 6 | 2027-04-07 | 2027-07-14 | 2027-04-14 | 2027-04-14 | 2027-07-20 | 84
| Training |  |  | 2027-03-18 |  |  | 36 | 2027-03-18 | 2027-06-09 | 2027-04-28 | 2027-04-28 | 2027-07-20 | 71
| A61750 | Training |  | 2027-03-18 |  |  | 36 | 2027-03-18 | 2027-06-09 | 2027-04-28 | 2027-04-28 | 2027-07-20 | 71
| Optional Item’s Prices | [5 empty] | 0 | 10-Sep-25 A |  | 10-Sep-25 A
| Furnace Modification – Optional Scope | [5 empty] | 0 | 10-Sep-25 A |  | 10-Sep-25 A
| A61080 | COMPANY Activation for Optional Scope |  |  |  |  | 0 |  |  | 10-Sep-25 A
| Reimbursable Items (Provisional Sums) |  |  | 2027-01-21 |  |  | 48 | 2027-01-21 | 2027-06-03 | 2027-03-09 | 2027-03-09 | 2027-07-20 | 133
| Provisional Sum for Two Year Operating Spares |  |  | 2027-01-21 |  |  | 48 | 2027-01-21 | 2027-06-03 | 2027-03-09 | 2027-03-09 | 2027-07-20 | 133
| A61760 | Provisional Sum for Two Year Operating Spares |  | 2027-01-21 |  |  | 60 | 2027-01-21 | 2027-06-03 | 2027-03-09 | 2027-03-09 | 2027-07-20 | 166
| Provisional Sum for Additional Assistance to Company IPMT’s |  |  | 2027-01-21 |  |  | 48 | 2027-01-21 | 2027-06-03 | 2027-03-09 | 2027-03-09 | 2027-07-20 | 133
| A61770 | Provisional Sum for Additional Assistance to Company IPMT’s |  | 2027-01-21 |  |  | 60 | 2027-01-21 | 2027-06-03 | 2027-03-09 | 2027-03-09 | 2027-07-20 | 166
| Provisional Sum for Additional Start Up Assistance to COMPANY |  |  | 2027-01-21 |  |  | 48 | 2027-01-21 | 2027-06-03 | 2027-03-09 | 2027-03-09 | 2027-07-20 | 133
| A61780 | Provisional Sum for Additional Start Up Assistance to COMPANY |  | 2027-01-21 |  |  | 60 | 2027-01-21 | 2027-06-03 | 2027-03-09 | 2027-03-09 | 2027-07-20 | 166
| Training of COMPANY personnel |  |  | 2027-01-21 |  |  | 48 | 2027-01-21 | 2027-06-03 | 2027-03-09 | 2027-03-09 | 2027-07-20 | 133
| A61790 | Training of COMPANY personnel |  | 2027-01-21 |  |  | 60 | 2027-01-21 | 2027-06-03 | 2027-03-09 | 2027-03-09 | 2027-07-20 | 166
| Initial Fills and / or One (1) full Spare Charge (refer to Addendum to Scope |  |  | 2027-01-21 |  |  | 48 | 2027-01-21 | 2027-06-03 | 2027-03-09 | 2027-03-09 | 2027-07-20 | 133
| A61800 | Initial Fills and / or One (1) full Spare Charge (refer to Addendum to Scope |  | 2027-01-21 |  |  | 60 | 2027-01-21 | 2027-06-03 | 2027-03-09 | 2027-03-09 | 2027-07-20 | 166
| Feed-gas Compressor Final design configuration (3 Casing design) |  |  | 2027-01-21 |  |  | 48 | 2027-01-21 | 2027-06-03 | 2027-03-09 | 2027-03-09 | 2027-07-20 | 133
| A61810 | Feed-gas Compressor Final design configuration (3 Casing design) |  | 2027-01-21 |  |  | 60 | 2027-01-21 | 2027-06-03 | 2027-03-09 | 2027-03-09 | 2027-07-20 | 166
| Accommodation for IPMT (Site) |  |  | 2027-01-21 |  |  | 48 | 2027-01-21 | 2027-06-03 | 2027-03-09 | 2027-03-09 | 2027-07-20 | 133
| A61820 | Accommodation for IPMT (Site) |  | 2027-01-21 |  |  | 60 | 2027-01-21 | 2027-06-03 | 2027-03-09 | 2027-03-09 | 2027-07-20 | 166
| Unforeseen development during Execution for additional services over and above |  |  | 2027-01-21 |  |  | 48 | 2027-01-21 | 2027-06-03 | 2027-03-09 | 2027-03-09 | 2027-07-20 | 133
| A61830 | Unforeseen development during Execution for additional services over and above |  | 2027-01-21 |  |  | 60 | 2027-01-21 | 2027-06-03 | 2027-03-09 | 2027-03-09 | 2027-07-20 | 166