## APRIL 26
ActivityID | Activity Name | Start | Finish | Late Start | Late Finish | Early Start | Early Finish | Phase Definition | MS Definition | CP (LF) | CP (BL)
BorougeEU3H2ExtractionEPCProject-MPR-APR-2026 |  | 07-Nov-24 A | 2027-09-20 | 2026-04-17 | 2027-09-20 | 20-Nov-24 A | 2027-07-20
COMPANY/PKG1&2Interfaces |  | 20-Nov-24 A | 2027-03-23 | 2026-04-17 | 2027-09-20 | 20-Nov-24 A | 2027-01-20
Engineering |  | 20-Nov-24 A | 2026-05-28 | 2026-06-09 | 2027-09-20 | 20-Nov-24 A | 2026-05-06
RequiredInputsfromCOMPANY/Pkg1&2 |  | 20-Nov-24 A | 2026-04-17 | 2026-06-09 | 2027-09-20 | 20-Nov-24 A | 2026-02-20
A5200 | TA Construction Dossier (IFC) - Pkg 1&2 |  | 04-Apr-25 A |  | 2026-06-15 |  | 04-Apr-25 A
A60660 | Receipt of SPI database login |  | 11-Feb-25 A |  | 2026-06-09 |  | 11-Feb-25 A
A60690 | Receipt of Unit Plot Plan Native File - Pkg 1&2 |  | 25-Mar-25 A |  | 2026-06-09 |  | 25-Mar-25 A
A60700 | Receipt of Drawings for all UG systems |  | 20-Nov-24 A |  | 2026-06-09 |  | 20-Nov-24 A
A60710 | Receipt of Native files of 3D model building & structural design (FEED stage) - Pkg 1&2 |  | 20-May-25 A |  | 2026-06-16 |  | 20-May-25 A
A60720 | Receipt of Native files of 3D model, STAAD model, calculations for brown field - Pkg 1&2 |  | 15-Jan-25 A |  | 2026-06-11 |  | 15-Jan-25 A
A60730 | Receipt of PSCAD native files for electrical studies - Pkg 1&2 |  | 15-Jan-25 A |  | 2027-01-22 |  | 15-Jan-25 A
A60740 | Receipt of System architecture & cable block diagram for MCMS, compressor control |  | 13-Feb-25 A |  | 2027-01-29 |  | 13-Feb-25 A
A60750 | Receipt of FEED datasheets for all telecom systems - Pkg 1&2 |  | 15-Jan-25 A |  | 2026-06-16 |  | 15-Jan-25 A
A60760 | Receipt of Piping TA MTO |  | 20-Feb-25 A |  | 2026-06-16 |  | 20-Feb-25 A
A60770 | Receipt of Approved Vendor data - GAD for PSA-2 unit |  | 17-Mar-25 A |  | 2026-06-12 |  | 17-Mar-25 A
A60780 | Receipt of Approved vendor data for FG & OG compressor |  | 24-Apr-25 A |  | 2026-06-12 |  | 24-Apr-25 A
A60790 | Receipt of Design parameters within received line list - Pkg 1&2 |  | 15-Jun-25 A |  | 2027-02-26 |  | 15-Jun-25 A
P&IDsStatus |  | 19-Jun-25 A | 2026-04-17 | 2026-06-09 | 2027-09-20 | 19-Jun-25 A | 2026-02-20
A60670 | Receipt of Updated P&ID's - Pkg 1&2 - Pre-HAZOP |  | 19-Jun-25 A |  | 2026-06-09 |  | 19-Jun-25 A
A60680 | Receipt of Updated P&ID's Updated Line List (Tie-in list, PDS etc) - Pkg 1&2 - Pre-60% Model Review |  | 05-Sep-25 A |  | 2026-06-09 |  | 05-Sep-25 A
A61020 | Receipt of Final P&ID's - Pkg 1&2 - IFC |  | 2026-04-17 |  | 2026-07-13 |  | 2026-02-20
A61030 | Latest Path of Mark-up P&ID by Pkg 3 |  | 12-Dec-25 A |  | 2026-06-15 |  | 12-Dec-25 A
A62490 | Receipt of Final Process Data for Piping Line list - Pkg 1&2 - IFC |  | 2026-04-17 |  | 2027-09-20 |  | 2026-02-20
SP3DDatabaseStatus |  | 25-Apr-25 A | 19-Nov-25 A | 2026-06-09 | 2026-07-22 | 25-Apr-25 A | 19-Nov-25 A
A60650 | Receipt of SP3D database from COMPANY (Not correct) |  | 25-Apr-25 A |  | 2026-06-09 |  | 25-Apr-25 A
A61010 | Receipt of corrected SP3D database from COMPANY |  | 19-Nov-25 A |  | 2026-07-22 |  | 19-Nov-25 A
RequiredInputsfromPkg3toPkg1&2 |  | 04-Mar-25 A | 2026-05-28 | 2026-06-12 | 2026-11-27 | 04-Mar-25 A | 2026-05-06
A60810 | All EPC Contractor G status input (detail refer Main Activities for P&ID) |  | 13-Mar-25 A |  | 2026-06-12 |  | 13-Mar-25 A
A60820 | All EPC Contractor H status input (detail refer Main Activities for P&ID) |  | 18-Jun-25 A |  | 2026-08-28 |  | 18-Jun-25 A
A60830 | Piping isos for main process piping and 3D model |  | 31-Jul-25 A |  | 2026-06-16 |  | 31-Jul-25 A
A60840 | Mechanical data sheet (vendor data sheet) of vessels and exchangers |  | 20-Jun-25 A |  | 2026-06-16 |  | 20-Jun-25 A
A60850 | Data sheet of control valve, shut down, PSV, check valve and flow element (vendor data sheet) |  | 2026-05-28 |  | 2026-11-27 |  | 2026-05-06
A60860 | Cause and effect update |  | 13-Mar-25 A |  | 2026-06-12 |  | 13-Mar-25 A
A60870 | Instrument data sheet for level, pressure and temperature |  | 2026-05-07 |  | 2026-11-27 |  | 2026-03-19
A60880 | Review & Confirmation on compressor GAD, Foundation plan & Anchor bolt locations |  | 20-Mar-25 A |  | 2026-06-12 |  | 20-Mar-25 A
A60890 | Review and Confirmation by Pkg -3 contractor as per issue 02 for EICT Cables |  | 15-May-25 A |  | 2026-06-16 |  | 15-May-25 A
A60900 | List of inputs required in compressor process loop |  | 23-Apr-25 A |  | 2026-06-16 |  | 23-Apr-25 A
A60910 | By-pass line sizing and routing and hot gas bypass valve details |  | 23-Apr-25 A |  | 2026-06-16 |  | 23-Apr-25 A
A60920 | GF Balance of Plant maturity w.r.t. Compressor & PSA2 model integration |  | 27-Mar-25 A |  | 2026-06-12 |  | 27-Mar-25 A
A60930 | H2-SIS layout required + power cable details. |  | 16-Apr-25 A |  | 2026-06-16 |  | 16-Apr-25 A
A60940 | Homerun cable length with its datasheet required for UCP signal IS calculation |  | 04-Apr-25 A |  | 2026-06-12 |  | 04-Apr-25 A
A60950 | Vendor manuals package to be provided by EPC Contractor for Linde's review |  | 2026-05-28 |  | 2026-11-27 |  | 2026-05-06
A60960 | Follow up HAZOP/LOPA Recommendations report - 13-KC-701 - PSA2 Feed Gas Compressor - Pkg 3 related |  | 23-Apr-25 A |  | 2026-06-16 |  | 23-Apr-25 A
A60970 | HSE Action Tracking Register - Pkg 3 Actions |  | 20-May-25 A |  | 2026-11-05 |  | 20-May-25 A
A60980 | Safty Follow up HAZOP/LOPA Recommendations Package 1c - Pkg 3 related |  | 23-Apr-25 A |  | 2026-06-16 |  | 23-Apr-25 A
A60990 | Selection for Option of MV motor (650% or 500% of rated current) or Starting VFD for Off Comp. |  | 04-Mar-25 A |  | 2026-06-12 |  | 04-Mar-25 A
A61000 | Compressor Motor VDDR Motor datasheet - Electrical Cable list |  | 20-Mar-25 A |  | 2026-06-12 |  | 20-Mar-25 A
Procurement |  | 15-Apr-25 A | 2026-12-31 | 2026-04-17 | 2027-03-23 | 15-Apr-25 A | 2026-10-07
76.D | FG Compressor - Delivery |  | 2026-06-22 |  | 2026-06-22 |  | 2026-03-03 |  |  | CP | CP
78.D | OG Compressor - Delivery |  | 2026-04-17 |  | 2026-08-05 |  | 2026-03-01
A5170 | Key Vendor Data (LLI, Package Details and Design Data) |  | 2026-04-17 |  | 2026-06-22 |  | 2026-02-20
A5190 | Free Issue TA Material latest delivery |  | 15-Apr-25 A |  | 2026-06-16 |  | 15-Apr-25 A
A5210 | BFW Preheater - Delivery |  | 15-Apr-25 A |  | 2026-06-16 |  | 15-Apr-25 A
A61070 | Approved Key Vendor Data (LLI, Package Details and Design Data) |  | 2026-04-17 |  | 2026-06-22 |  | 2026-02-20
A9950 | PSA Unit Delivery - Delivery |  | 2026-04-17 |  | 2026-10-16 |  | 2026-02-20
FeedGasCompressor-Delivery |  | 10-Feb-26 A | 2026-09-15 | 2026-04-17 | 2027-03-23 | 13-Feb-26 A | 2026-05-25
A62300 | Feed Gas Compressor (incl. Baseplate, Gear, Gas seal module & Booster) |  | 2026-06-22 |  | 2026-06-22 |  | 2026-03-03 |  | MS | CP | CP
A62310 | LO Console |  | 2026-07-05 |  | 2026-10-23 |  | 2026-03-16
A62320 | Anti-surge valve |  | 2026-07-17 |  | 2026-11-28 |  | 2026-05-25
A62330 | Capital Spares |  | 2026-06-28 |  | 2027-03-23 |  | 2026-03-09
A62340 | Main Driver (Motor) for FGC |  | 2026-06-28 |  | 2026-08-25 |  | 2026-03-09
A62350 | UCP |  | 10-Feb-26 A |  | 2026-04-17 |  | 2026-02-20
A62360 | VSD |  | 13-Feb-26 A |  | 2026-04-17 |  | 13-Feb-26 A
A62370 | Transformer |  | 2026-09-15 |  | 2026-10-23 |  | 2026-04-27
A64630 | UCP - Part 2 |  | 2026-04-30 |  | 2026-10-23
OffGasCompressor:Vendor-Delivery |  | 27-Jan-26 A | 2026-06-30 | 2026-08-05 | 2026-12-07 | 2026-02-20 | 2026-03-07
A62380 | Off Gas Compressor |  | 06-Feb-26 A |  | 2026-08-05 |  | 2026-03-01 |  | MS
A62390 | Capital Spares |  | 30-Jan-26 A |  | 2026-08-05 |  | 2026-02-22
A62400 | Main Driver (Motor) for OGC |  | 09-Feb-26 A |  | 2026-09-30 |  | 2026-03-04
A62410 | UCP |  | 27-Jan-26 A |  | 2026-08-05 |  | 2026-02-20
A62420 | Lube Oil Unit |  | 06-Feb-26 A |  | 2026-09-30 |  | 2026-03-01
A62430 | Seal Gas Unit |  | 12-Feb-26 A |  | 2026-12-07 |  | 2026-03-07
A64640 | Anti-surge valve |  | 2026-06-30 |  | 2026-12-06
PSAUnit:Vendor-Delivery |  | 03-Sep-25 A | 2026-12-31 | 2026-06-08 | 2027-02-21 | 03-Sep-25 A | 2026-10-07
A62440 | PSA Pressure vessels |  | 03-Sep-25 A |  | 2026-06-08 |  | 03-Sep-25 A
A62450 | PSA Valve Skid |  | 16-Feb-26 A |  | 2026-07-05 |  | 2026-02-20
A62460 | PLC Cabinet |  | 03-Sep-25 A |  | 2026-11-16 |  | 03-Sep-25 A
A62470 | Adsorbent Material (PO pending) |  | 2026-09-24 |  | 2026-12-12 |  | 2026-08-21
A62480 | Analyzer (PO pending) |  | 2026-12-31 |  | 2027-02-21 |  | 2026-10-07 |  | MS
Construction&Commissioning |  | 2027-03-23 | 2027-03-23 | 2027-06-28 | 2027-06-28 | 2027-01-20 | 2027-01-20
A40220 | Potable Water and Service water (Needs) |  | 2027-03-23 |  | 2027-06-28 |  | 2027-01-20
A40230 | SANITARY Water system (Needs) |  | 2027-03-23 |  | 2027-06-28 |  | 2027-01-20
A40240 | Chilled Water for Safety Shower |  | 2027-03-23 |  | 2027-06-28 |  | 2027-01-20
A40250 | Instrument Air (Needs) for Boiler RFSU |  | 2027-03-23 |  | 2027-06-28 |  | 2027-01-20
A40260 | Fire Water (Needs) |  | 2027-03-23 |  | 2027-06-28 |  | 2027-01-20
A40270 | ETP (Effluent Treatment Package) System (Needs) |  | 2027-03-23 |  | 2027-06-28 |  | 2027-01-20
A40280 | Demin water (Needs) |  | 2027-03-23 |  | 2027-06-28 |  | 2027-01-20
A40290 | Nitrogen (Needs) |  | 2027-03-23 |  | 2027-06-28 |  | 2027-01-20
ProjectManagement |  | 07-Nov-24 A | 2027-09-20 | 2026-04-17 | 2027-09-20 | 07-Nov-24 A | 2027-07-20
ProjectManagement |  | 07-Nov-24 A | 2027-05-31 | 2026-04-17 | 2027-09-20 | 07-Nov-24 A | 2027-07-20
ProjectManagementDeliverables |  | 22-Mar-25 A | 2026-05-12 | 2026-06-15 | 2027-09-20 | 22-Mar-25 A | 2026-03-17
A1-PM-PMD-0001 | PM-001-Job Bulletins | 25-May-25 A | 15-Aug-25 A | 2026-06-15 | 2026-06-15 | 25-May-25 A | 15-Aug-25 A
A1-PM-PMD-0002 | PM-002-Project Coordination Procedure |  | 18-Apr-25 A |  | 2026-06-15 |  | 18-Apr-25 A
A1-PM-PMD-0003 | PM-003-Code of accounts | 25-May-25 A | 15-Aug-25 A | 2026-08-12 | 2026-08-12 | 25-May-25 A | 15-Aug-25 A
A1-PM-PMD-0004 | PM-004-PDS / Smart3D 3D Modeling Guideline for End User | 25-May-25 A | 25-Aug-25 A | 2026-08-12 | 2026-08-12 | 25-May-25 A | 25-Aug-25 A
A1-PM-PMD-0005 | PM-005-SPI (Smart Plant Instrumentation) INtoos Guideline for End User | 25-May-25 A | 26-Aug-25 A | 2026-08-12 | 2026-08-12 | 25-May-25 A | 26-Aug-25 A
A1-PM-PMD-0006 | PM-006-SP PID (Smart Plant P&ID ) Guideline for End User | 25-May-25 A | 30-Aug-25 A | 2026-08-12 | 2026-08-12 | 25-May-25 A | 30-Aug-25 A
A1-PM-PMD-0007 | PM-007-SPEL (Smart Plant Electrical) Guideline for End Users | 25-May-25 A | 02-Sep-25 A | 2026-08-12 | 2026-08-12 | 25-May-25 A | 02-Sep-25 A
A1-PM-PMD-0008 | PM-008-PDS / Smart3D CADD Area/Model Index/ Plan | 25-May-25 A | 08-Sep-25 A | 2026-08-12 | 2026-08-12 | 25-May-25 A | 08-Sep-25 A
A1-PM-PMD-0009 | PM-009-CADD Project Hierarchy & Setup Guideline (PDS /Intools/ SP PID/ SPEL) | 25-May-25 A | 12-Sep-25 A | 2026-08-12 | 2026-08-12 | 25-May-25 A | 12-Sep-25 A
A1-PM-PMD-0010 | PM-010-PDS / Smart3D Physical Support Modeling Guideline for End Users | 25-May-25 A | 16-Sep-25 A | 2026-08-12 | 2026-08-12 | 25-May-25 A | 16-Sep-25 A
A1-PM-PMD-0011 | PM-011-Project Engineering CADD Applications & Deliverables Guideline | 25-May-25 A | 21-Aug-25 A | 2026-08-12 | 2026-08-12 | 25-May-25 A | 21-Aug-25 A
A1-PM-PMD-0012 | PM-012-PDS / Smart3D Raceways Guideline | 25-May-25 A | 23-Aug-25 A | 2026-08-12 | 2026-08-12 | 25-May-25 A | 23-Aug-25 A
A1-PM-PMD-0013 | PM-013-PDS / Smart3D Generated List of Drawings / Documents | 25-May-25 A | 27-Aug-25 A | 2026-08-12 | 2026-08-12 | 25-May-25 A | 27-Aug-25 A
A1-PM-PMD-0014 | PM-014-Documentation and CADD Systems / Database Handover Schedule | 25-May-25 A | 01-Sep-25 A | 2026-08-12 | 2026-08-12 | 25-May-25 A | 01-Sep-25 A
A1-PM-PMD-0015 | PM-015-CADD Systems As-built Database and System integrated Deliverables (PDS/IN Tools/SP PID/SPEL/ETAP/ Caesar-II / STA | 25-May-25 A | 05-Sep-25 A | 2026-08-12 | 2026-08-12 | 25-May-25 A | 05-Sep-25 A
A1-PM-PMD-0016 | PM-016-Site Mobilization Plan | 25-May-25 A | 07-Sep-25 A | 2026-08-12 | 2026-08-12 | 25-May-25 A | 07-Sep-25 A
A1-PM-PMD-0017 | PM-017-HSE Training plan & procedure | 21-Jun-25 A | 12-Jul-25 A | 2026-08-12 | 2026-08-12 | 21-Jun-25 A | 12-Jul-25 A
A1-PM-PMD-0018 | PM-028-Project Organization Charts | 25-May-25 A | 27-Aug-25 A | 2026-08-12 | 2026-08-12 | 25-May-25 A | 27-Aug-25 A
A1-PM-PMD-0019 | PM-029-Recovery Plan | 25-May-25 A | 12-Jul-25 A | 2026-08-12 | 2026-08-12 | 25-May-25 A | 12-Jul-25 A
A1-PM-PMD-0020 | PM-030-Worksite HSE Plan | 25-May-25 A | 28-May-25 A | 2026-08-12 | 2026-08-12 | 25-May-25 A | 28-May-25 A
A1-PM-PMD-0021 | PM-031-Temporary Site Establishment plan | 25-May-25 A | 25-Aug-25 A | 2026-08-12 | 2026-08-12 | 25-May-25 A | 25-Aug-25 A
A1-PM-PMD-0022 | PM-032-Tie-in & Interface Matrix | 25-May-25 A | 26-Aug-25 A | 2026-08-12 | 2026-08-12 | 25-May-25 A | 26-Aug-25 A
A1-PM-PMD-0023 | PM-037-Document/Drawing Index | 25-May-25 A | 30-Aug-25 A | 2026-08-12 | 2026-08-12 | 25-May-25 A | 30-Aug-25 A
A1-PM-PMD-0024 | PM-038-Documentation List | 25-May-25 A | 04-Sep-25 A | 2026-08-12 | 2026-08-12 | 25-May-25 A | 04-Sep-25 A
A1-PM-PMD-0025 | PM-039-List of Claims for Damage | 25-May-25 A | 12-Jul-25 A | 2026-08-12 | 2026-08-12 | 25-May-25 A | 12-Jul-25 A
A1-PM-PMD-0026 | PM-040-List of Commissioning Spares | 30-Jul-25 A | 2026-04-21 | 2027-09-07 | 2027-09-09 | 30-Jul-25 A | 2026-02-24
A1-PM-PMD-0027 | PM-041-List of startup spares | 25-Aug-25 A | 2026-04-23 | 2027-09-07 | 2027-09-13 | 25-Aug-25 A | 2026-02-26
A1-PM-PMD-0028 | PM-045-Project Close out Report | 2026-04-24 | 2026-04-30 | 2027-09-14 | 2027-09-20 | 2026-02-27 | 2026-03-05
A1-PM-PMD-0029 | PM-046-Procurement Status Report | 25-May-25 A | 25-Jul-25 A | 2026-08-12 | 2026-08-12 | 25-May-25 A | 25-Jul-25 A
A1-PM-PMD-0030 | PM-047-Project Execution Plan |  | 12-Nov-25 A |  | 2026-08-27 |  | 12-Nov-25 A
A1-PM-PMD-0031 | PM-048-HSE Audit Procedure | 21-Jun-25 A | 12-Jul-25 A | 2026-08-12 | 2026-08-12 | 21-Jun-25 A | 12-Jul-25 A
A1-PM-PMD-0032 | PM-049-Risk Analysis | 25-May-25 A | 17-Sep-25 A | 2026-08-12 | 2026-08-12 | 25-May-25 A | 17-Sep-25 A
A1-PM-PMD-0033 | PM-050-Acceptance Certificate | 2026-05-08 | 2026-05-12 | 2027-09-17 | 2027-09-20 | 2026-03-13 | 2026-03-17
A1-PM-PMD-0034 | PM-052-Contract Trending procedure | 25-May-25 A | 26-Aug-25 A | 2026-08-12 | 2026-08-12 | 25-May-25 A | 26-Aug-25 A
A1-PM-PMD-0035 | PM-053-Contract Trend notice / Log | 22-Mar-25 A | 27-Aug-25 A | 2026-08-12 | 2026-08-12 | 22-Mar-25 A | 27-Aug-25 A
A1-PM-PMD-0036 | PM-054-Master Document schedule and Status Report | 25-May-25 A | 25-Jul-25 A | 2026-08-12 | 2026-08-12 | 25-May-25 A | 25-Jul-25 A
A1-PM-PMD-0037 | PM-057-Project Specification | 25-May-25 A | 25-Aug-25 A | 2026-08-12 | 2026-08-12 | 25-May-25 A | 25-Aug-25 A
A1-PM-PMD-0038 | PM-061-Insurance Policies | 25-May-25 A | 01-Sep-25 A | 2026-08-12 | 2026-08-12 | 25-May-25 A | 01-Sep-25 A
A1-PM-PMD-0039 | PM-062-Insurance Claims | 25-Aug-25 A | 05-Sep-25 A | 2026-08-12 | 2026-08-12 | 25-Aug-25 A | 05-Sep-25 A
A1-PM-PMD-0040 | PM-063-Insurance claim status report | 23-Aug-25 A | 26-Aug-25 A | 2026-08-12 | 2026-08-12 | 23-Aug-25 A | 26-Aug-25 A
A1-PM-PMD-0041 | PM-064-Claims | 27-Aug-25 A | 30-Aug-25 A | 2026-08-12 | 2026-08-12 | 27-Aug-25 A | 30-Aug-25 A
A1-PM-PMD-0042 | PM-065-Requests for Variation | 01-Sep-25 A | 04-Sep-25 A | 2026-08-12 | 2026-08-12 | 01-Sep-25 A | 04-Sep-25 A
A1-PM-PMD-0043 | PM-073-Feed Documents | 25-May-25 A | 08-Sep-25 A | 2026-08-12 | 2026-08-12 | 25-May-25 A | 08-Sep-25 A
A1-PM-PMD-0044 | PM-074-Asset Integrated Management System (AIMS) / Project Integrity Management Plan | 08-Aug-25 A | 18-Dec-25 A | 2027-08-26 | 2027-08-26 | 08-Aug-25 A | 18-Dec-25 A
A1-PM-PMD-0045 | PM-075-Constructability Action Closeout Report | 28-Oct-25 A | 2026-04-17 | 2027-08-26 | 2027-08-26 | 28-Oct-25 A | 2026-02-20
A1-PM-PMD-0046 | PM-076-Project Training Requirements and Training Plan | 2026-04-17 | 2026-04-24 | 2027-08-27 | 2027-09-02 | 2026-02-20 | 2026-02-27
A1-PM-PMD-0047 | PM-077-Operating Procedure/Guidelines | 2026-04-24 | 2026-05-01 | 2027-09-03 | 2027-09-09 | 2026-02-27 | 2026-03-06
A1-PM-PMD-0048 | PM-078-Guidelines for Acceptance of Work | 2026-05-01 | 2026-05-08 | 2027-09-10 | 2027-09-16 | 2026-03-06 | 2026-03-13
A1-PM-PMD-0049 | PM-079-Synergies Study Report | 08-Sep-25 A | 2026-04-21 | 2026-08-12 | 2026-08-17 | 08-Sep-25 A | 2026-02-24
A1-PM-PMD-0050 | PM-080-Project IT/EDMS Requirements | 25-May-25 A | 16-Sep-25 A | 2026-08-12 | 2026-08-12 | 25-May-25 A | 16-Sep-25 A
A1-PM-PMD-0051 | PM-081-Interface Management Plan - EPC | 25-May-25 A | 10-Sep-25 A | 2026-08-12 | 2026-08-12 | 25-May-25 A | 10-Sep-25 A
A1-PM-PMD-0052 | PM-082-Interface Responsibility Philosophy | 21-Jun-25 A | 12-Jul-25 A | 2026-08-12 | 2026-08-12 | 21-Jun-25 A | 12-Jul-25 A
A1-PM-PMD-0053 | PM-083-EPC Responsibility Matrix for Control Systems | 25-Jul-25 A | 19-Dec-25 A | 2026-08-12 | 2026-08-12 | 25-Jul-25 A | 19-Dec-25 A
A1-PM-PMD-0054 | PM-084-EPC Responsibility Matrix for ICT & IT/OT | 08-Aug-25 A | 18-Dec-25 A | 2026-08-12 | 2026-08-12 | 08-Aug-25 A | 18-Dec-25 A
A1-PM-PMD-0055 | PM-085-Interface Point Registers | 08-Aug-25 A | 19-Dec-25 A | 2026-08-12 | 2026-08-12 | 08-Aug-25 A | 19-Dec-25 A
A1-PM-PMD-0056 | PM-086-Interface Dependency Table | 14-Jul-25 A | 19-Dec-25 A | 2026-08-12 | 2026-08-12 | 14-Jul-25 A | 19-Dec-25 A
A1-PM-PMD-0057 | PM-087-Master Boundary Interface Layout Drawing | 20-Jun-25 A | 19-Dec-25 A | 2026-08-12 | 2026-08-12 | 20-Jun-25 A | 19-Dec-25 A
A1-PM-PMD-0058 | PM-088-Process and Utilities Overall Block Flow Diagram Borouge-4 Facilities | 21-Jul-25 A | 19-Dec-25 A | 2026-08-12 | 2026-08-12 | 21-Jul-25 A | 19-Dec-25 A
A1-PM-PMD-0059 | PM-089-Process and Utilities Block Flow Diagram Interconnecting | 08-Aug-25 A | 2026-04-17 | 2026-08-11 | 2026-08-12 | 08-Aug-25 A | 2026-02-20
A1-PM-PMD-0060 | PM-090-Piping External/Internal Connections Layout drawings | 08-Aug-25 A | 19-Dec-25 A | 2026-08-11 | 2026-08-11 | 08-Aug-25 A | 19-Dec-25 A
A1-PM-PMD-0061 | PM-091-MRB Index | 01-Aug-25 A | 2026-04-21 | 2026-08-07 | 2026-08-11 | 01-Aug-25 A | 2026-02-24
A1-PM-PMD-0062 | PM-092-Material Record Book (MRB) | 01-Aug-25 A | 2026-04-30 | 2026-08-19 | 2026-08-20 | 01-Aug-25 A | 2026-03-05
A1-PM-PMD-0063 | PM-093-QA/QC Dossiers | 01-Aug-25 A | 2026-05-11 | 2026-08-27 | 2026-08-31 | 01-Aug-25 A | 2026-03-16
A1-PM-PMD-0064 | PM-094-Package 1 Deliverables IFC | 15-May-25 A | 12-Jul-25 A | 2026-08-27 | 2026-08-27 | 15-May-25 A | 12-Jul-25 A
ProjectControlDeliverables |  | 15-Feb-25 A | 2026-04-24 | 2026-06-16 | 2027-01-07 | 15-Feb-25 A | 2026-02-27
A1-PM-PCD-0001 | PC-001-Procedures | 15-Feb-25 A | 17-Nov-25 A | 2026-06-16 | 2026-06-16 | 15-Feb-25 A | 17-Nov-25 A
A1-PM-PCD-0002 | PC-002-Distribution Matrix | 04-Mar-25 A | 03-Nov-25 A | 2026-06-16 | 2026-06-16 | 04-Mar-25 A | 03-Nov-25 A
A1-PM-PCD-0003 | PC-003-Time Schedule / Program | 15-Feb-25 A | 17-Nov-25 A | 2026-06-16 | 2026-06-16 | 15-Feb-25 A | 17-Nov-25 A
A1-PM-PCD-0004 | PC-004-Overall Project Schedule | 15-Feb-25 A | 17-Nov-25 A | 2026-06-16 | 2026-06-16 | 15-Feb-25 A | 17-Nov-25 A
A1-PM-PCD-0005 | PC-005-Detailed Procurement schedule | 15-Feb-25 A | 14-Nov-25 A | 2026-06-16 | 2026-06-16 | 15-Feb-25 A | 14-Nov-25 A
A1-PM-PCD-0006 | PC-006-Detailed Engineering Schedule | 15-Feb-25 A | 17-Nov-25 A | 2026-06-16 | 2026-06-16 | 15-Feb-25 A | 17-Nov-25 A
A1-PM-PCD-0007 | PC-007-Detailed Construction Schedule | 15-Feb-25 A | 17-Nov-25 A | 2026-06-16 | 2026-06-16 | 15-Feb-25 A | 17-Nov-25 A
A1-PM-PCD-0008 | PC-008-Detailed Control Log / Schedule | 15-Feb-25 A | 08-Nov-25 A | 2026-06-16 | 2026-06-16 | 15-Feb-25 A | 08-Nov-25 A
A1-PM-PCD-0009 | PC-009-Detailed Commissioning and Pre Commissioning Schedule | 15-Feb-25 A | 17-Jun-25 A | 2026-06-16 | 2026-06-16 | 15-Feb-25 A | 17-Jun-25 A
A1-PM-PCD-0010 | PC-010-Variations | 21-Jun-25 A | 12-Jul-25 A | 2026-06-16 | 2026-06-16 | 21-Jun-25 A | 12-Jul-25 A
A1-PM-PCD-0011 | PC-011-Document/Drawing Index | 21-Jun-25 A | 12-Jul-25 A | 2026-06-16 | 2026-06-16 | 21-Jun-25 A | 12-Jul-25 A
A1-PM-PCD-0012 | PC-012-Specialty Item List | 21-Jun-25 A | 21-Aug-25 A | 2026-06-16 | 2026-06-16 | 21-Jun-25 A | 21-Aug-25 A
A1-PM-PCD-0013 | PC-013-Spares Lists | 21-Jun-25 A | 12-Jul-25 A | 2026-06-16 | 2026-06-16 | 21-Jun-25 A | 12-Jul-25 A
A1-PM-PCD-0014 | PC-014-Suppliers Lists | 19-Aug-25 A | 20-Aug-25 A | 2026-06-16 | 2026-06-16 | 19-Aug-25 A | 20-Aug-25 A
A1-PM-PCD-0015 | PC-015-Annual Reports | 15-May-25 A | 23-May-25 A | 2026-06-16 | 2026-06-16 | 15-May-25 A | 23-May-25 A
A1-PM-PCD-0016 | PC-016-Monthly Reports | 26-May-25 A | 20-Jul-25 A | 2026-06-16 | 2026-06-16 | 26-May-25 A | 20-Jul-25 A
A1-PM-PCD-0017 | PC-017-Weekly Reports | 25-May-25 A | 19-Aug-25 A | 2026-06-16 | 2026-06-16 | 25-May-25 A | 19-Aug-25 A
A1-PM-PCD-0018 | PC-018-Forecasts for Completion | 25-May-25 A | 21-Aug-25 A | 2026-06-16 | 2026-06-16 | 25-May-25 A | 21-Aug-25 A
A1-PM-PCD-0019 | PC-019-Project Execution Plan |  | 17-Nov-25 A |  | 2026-08-27 |  | 17-Nov-25 A
A1-PM-PCD-0020 | PC-020-FAT Procedures | 15-Feb-25 A | 17-Nov-25 A | 2026-12-31 | 2026-12-31 | 15-Feb-25 A | 17-Nov-25 A
A1-PM-PCD-0021 | PC-021-FAT Reports | 2026-04-17 | 2026-04-20 | 2026-12-31 | 2027-01-01 | 2026-02-20 | 2026-02-23
A1-PM-PCD-0022 | PC-022-SAT Procedures | 2026-04-21 | 2026-04-22 | 2027-01-04 | 2027-01-05 | 2026-02-24 | 2026-02-25
A1-PM-PCD-0023 | PC-023-SAT Reports | 2026-04-23 | 2026-04-24 | 2027-01-06 | 2027-01-07 | 2026-02-26 | 2026-02-27
A1-PM-PCD-0024 | PC-024-P&ID change notes | 06-Sep-25 A | 07-Sep-25 A | 2026-06-16 | 2026-06-16 | 06-Sep-25 A | 07-Sep-25 A
A1-PM-PCD-0025 | PC-025-Engineering Document Change Note | 25-May-25 A | 02-Sep-25 A | 2026-06-16 | 2026-06-16 | 25-May-25 A | 02-Sep-25 A
A1-PM-PCD-0026 | PC-026-Query Form | 25-May-25 A | 09-Sep-25 A | 2026-06-16 | 2026-06-16 | 25-May-25 A | 09-Sep-25 A
A1-PM-PCD-0027 | PC-027-Change Orders | 25-Aug-25 A | 29-Aug-25 A | 2026-06-16 | 2026-06-16 | 25-Aug-25 A | 29-Aug-25 A
A1-PM-PCD-0028 | PC-028-Field Queries | 01-Sep-25 A | 08-Sep-25 A | 2026-06-16 | 2026-06-16 | 01-Sep-25 A | 08-Sep-25 A
A1-PM-PCD-0029 | PC-029-Site Queries | 27-Aug-25 A | 29-Aug-25 A | 2026-06-16 | 2026-06-16 | 27-Aug-25 A | 29-Aug-25 A
A1-PM-PCD-0030 | PC-030-Technical Queries | 25-May-25 A | 27-Aug-25 A | 2026-06-16 | 2026-06-16 | 25-May-25 A | 27-Aug-25 A
A1-PM-PCD-0031 | PC-031-Invoices | 25-May-25 A | 20-Nov-25 A | 2026-06-16 | 2026-06-16 | 25-May-25 A | 20-Nov-25 A
A1-PM-PCD-0032 | PC-032-Invoices Status Report | 25-May-25 A | 20-Nov-25 A | 2026-06-16 | 2026-06-16 | 25-May-25 A | 20-Nov-25 A
A1-PM-PCD-0033 | PC-033-Bank Bonds and Guarantees | 25-May-25 A | 26-Aug-25 A | 2026-06-16 | 2026-06-16 | 25-May-25 A | 26-Aug-25 A
A1-PM-PCD-0034 | PC-034-Cash Flow Forecast | 25-May-25 A | 14-Oct-25 A | 2026-06-16 | 2026-06-16 | 25-May-25 A | 14-Oct-25 A
A1-PM-PCD-0035 | PC-035-Back charges Status Report | 21-Jun-25 A | 12-Jul-25 A | 2026-06-16 | 2026-06-16 | 21-Jun-25 A | 12-Jul-25 A
A1-PM-PCD-0036 | PC-036-Progress Review and Certification Procedure | 15-Feb-25 A | 10-Sep-25 A | 2026-06-16 | 2026-06-16 | 15-Feb-25 A | 10-Sep-25 A
A1-PM-PCD-0037 | PC-037-Schedule Risk Analysis Reports | 15-Feb-25 A | 28-Jun-25 A | 2026-06-16 | 2026-06-16 | 15-Feb-25 A | 28-Jun-25 A
A1-PM-PCD-0038 | PC-038-Manpower Mobilization Plan | 15-Feb-25 A | 19-Nov-25 A | 2026-06-16 | 2026-06-16 | 15-Feb-25 A | 19-Nov-25 A
A1-PM-PCD-0039 | PC-039-Equipment Deployment Plan | 15-Feb-25 A | 15-Nov-25 A | 2026-06-16 | 2026-06-16 | 15-Feb-25 A | 15-Nov-25 A
A1-PM-PCD-0040 | PC-040-Planning Package | 15-Feb-25 A | 15-Nov-25 A | 2026-06-16 | 2026-06-16 | 15-Feb-25 A | 15-Nov-25 A
ProjectRiskAnalysisWorkshops |  | 25-May-25 A | 2027-05-20 | 2026-08-20 | 2027-09-09 | 25-May-25 A | 2027-03-25
A1-PM-PRA-0001 | PRA01-Project Risk Analysis - Risk Identifications Workshop |  | 25-May-25 A |  | 2026-08-20 |  | 25-May-25 A
A1-PM-PRA-0002 | PRA02-Project Risk Analysis Workshop - Update - Q01 |  | 21-Jun-25 A |  | 2026-08-20 |  | 21-Jun-25 A
A1-PM-PRA-0003 | PRA03-Project Risk Analysis Workshop - Update - Q02 |  | 20-Aug-25 A |  | 2026-08-20 |  | 20-Aug-25 A
A1-PM-PRA-0004 | PRA04-Project Risk Analysis Workshop - Update - Q03 |  | 24-Oct-25 A |  | 2026-08-27 |  | 24-Oct-25 A
A1-PM-PRA-0005 | PRA05-Project Risk Analysis Workshop - Update - Q04 |  | 2026-05-07 |  | 2026-08-27 |  | 2026-03-12
A1-PM-PRA-0006 | PRA06-Project Risk Analysis Workshop - Update - Q05 |  | 2026-09-10 |  | 2026-12-31 |  | 2026-07-16
A1-PM-PRA-0007 | PRA07-Project Risk Analysis Workshop - Update - Q06 |  | 2027-01-14 |  | 2027-05-06 |  | 2026-11-19
A1-PM-PRA-0008 | PRA08-Project Risk Analysis Workshop - Update - Q07 |  | 2027-05-20 |  | 2027-09-09 |  | 2027-03-25
ScheduleRiskAnalysisWorkshops |  | 15-May-25 A | 2027-05-31 | 2026-08-20 | 2027-09-20 | 15-May-25 A | 2027-04-05
A1-PM-SRA-0001 | SRA01-Schedule Risk Analysis Workshop - Baseline Schedule |  | 15-May-25 A |  | 2026-08-20 |  | 15-May-25 A
A1-PM-SRA-0002 | SRA02-Schedule Risk Analysis Workshop - UpdatedSchedule - Q01 |  | 10-Jul-25 A |  | 2026-08-20 |  | 10-Jul-25 A
A1-PM-SRA-0003 | SRA03-Schedule Risk Analysis Workshop - Updated Schedule - Q02 |  | 17-Sep-25 A |  | 2026-08-20 |  | 17-Sep-25 A
A1-PM-SRA-0004 | SRA04-Schedule Risk Analysis Workshop - Updated Schedule - Q03 |  | 2026-04-17 |  | 2026-08-20 |  | 2026-02-20
A1-PM-SRA-0005 | SRA05-Schedule Risk Analysis Workshop - Updated Schedule - Q04 |  | 2026-08-20 |  | 2026-12-24 |  | 2026-06-25
A1-PM-SRA-0006 | SRA06-Schedule Risk Analysis Workshop - Updated Schedule - Q05 |  | 2026-12-24 |  | 2027-04-29 |  | 2026-10-29
A1-PM-SRA-0007 | SRA07-Schedule Risk Analysis Workshop - Updated Schedule - Q06 |  | 2027-04-29 |  | 2027-09-02 |  | 2027-03-04
A1-PM-SRA-0008 | SRA08-Schedule Risk Analysis Workshop - Updated Schedule - Q07 |  | 2027-05-31 |  | 2027-09-20 |  | 2027-04-05
ProjectLessonLearnWorkshops |  | 25-May-25 A | 2027-05-25 | 2026-09-07 | 2027-09-20 | 25-May-25 A | 2027-03-30
A1-PM-LLW-0001 | PRA01-Project Lesson Learn Workshop - Lesson Learn Identifications |  | 25-May-25 A |  | 2026-09-07 |  | 25-May-25 A
A1-PM-LLW-0002 | PRA02-Project Lesson Learn Workshop - Update - Q01 |  | 21-Jun-25 A |  | 2026-09-07 |  | 21-Jun-25 A
A1-PM-LLW-0003 | PRA03-Project Lesson Learn Workshop - Update - Q02 |  | 15-Sep-25 A |  | 2026-09-07 |  | 15-Sep-25 A
A1-PM-LLW-0004 | PRA04-Project Lesson Learn Workshop - Update - Q03 |  | 01-Oct-25 A |  | 2026-09-07 |  | 01-Oct-25 A
A1-PM-LLW-0005 | PRA05-Project Lesson Learn Workshop - Update - Q04 |  | 2026-05-12 |  | 2026-09-07 |  | 2026-03-17
A1-PM-LLW-0006 | PRA06-Project Lesson Learn Workshop - Update - Q05 |  | 2026-09-15 |  | 2027-01-11 |  | 2026-07-21
A1-PM-LLW-0007 | PRA07-Project Lesson Learn Workshop - Update - Q06 |  | 2027-01-19 |  | 2027-05-17 |  | 2026-11-24
A1-PM-LLW-0008 | PRA08-Project Lesson Learn Workshop - Update - Q07 |  | 2027-05-25 |  | 2027-09-20 |  | 2027-03-30
ProjectManagementInterimMilestones |  | 07-Nov-24 A | 30-Oct-25 A | 2026-04-17 | 2027-02-09 | 07-Nov-24 A | 30-Oct-25 A
A1-PM-PMM-0001 | Letter of Award (LOA) Recieved - Project Commencement Date |  | 07-Nov-24 A |  | 2026-04-17 |  | 07-Nov-24 A |  | MS
A1-PM-PMM-0002 | 10.A-Kick-off Meeting Completed |  | 06-Dec-24 A |  | 2026-06-15 |  | 06-Dec-24 A |  | MS
A1-PM-PMM-0003 | 1.A*-Issue Overall Project Execution Plan |  | 30-Oct-25 A |  | 2026-12-31 |  | 30-Oct-25 A
A1-PM-PMM-0004 | 1.A*-Issue Coordination Procedure |  | 30-Apr-25 A |  | 2026-06-15 |  | 30-Apr-25 A
QAQCInterimMilestones |  | 26-May-25 A | 26-May-25 A | 2027-02-09 | 2027-02-09 | 26-May-25 A | 26-May-25 A
GeneralProjectManagement |  | 26-May-25 A | 26-May-25 A | 2027-02-09 | 2027-02-09 | 26-May-25 A | 26-May-25 A
A1-PM-QCM-0001 | 1.A*-Issue Project Quality Procedures (Final Issue). |  | 26-May-25 A |  | 2027-02-09 |  | 26-May-25 A
HSEInterimMilestones |  | 30-Apr-25 A | 30-Apr-25 A | 2027-02-09 | 2027-02-09 | 30-Apr-25 A | 30-Apr-25 A
GeneralProjectManagement |  | 30-Apr-25 A | 30-Apr-25 A | 2027-02-09 | 2027-02-09 | 26-May-25 A | 26-May-25 A
A1-PM-HSM-0001 | 1.A*-Issue Project HSE Procedure. |  | 30-Apr-25 A |  | 2027-02-09 |  | 30-Apr-25 A
ProjectControlInterimMilestones |  | 24-Mar-25 A | 24-Mar-25 A | 2026-06-12 | 2026-06-12 | 24-Mar-25 A | 24-Mar-25 A
A1-PM-PCM-0001 | 2.A-Issue Project Control Propcedures |  | 24-Mar-25 A |  | 2026-06-12 |  | 24-Mar-25 A
A1-PM-PCM-0002 | 2.A-Issue Progress Measurement & Reporting System |  | 24-Mar-25 A |  | 2026-06-12 |  | 24-Mar-25 A
A1-PM-PCM-0003 | 2.A-Issue Cost Control Procedure |  | 24-Mar-25 A |  | 2026-06-12 |  | 24-Mar-25 A
A1-PM-PCM-0004 | 2.A-Issue Planning Docs |  | 24-Mar-25 A |  | 2026-06-12 |  | 24-Mar-25 A
MoblizationofKeyPersonnel |  | 15-Nov-24 A | 13-Nov-25 A | 2026-06-09 | 2026-06-16 | 15-Nov-24 A | 13-Nov-25 A
A1-PM-KPM-0001 | Moblization of Project Director or Project Manager * |  | 18-Dec-24 A |  | 2026-06-09 |  | 18-Dec-24 A
A1-PM-KPM-0002 | Moblization of Project Turnaround Manager * |  | 21-Nov-24 A |  | 2026-06-09 |  | 21-Nov-24 A
A1-PM-KPM-0003 | Moblization of Engineering Manager * |  | 15-Feb-25 A |  | 2026-06-09 |  | 15-Feb-25 A
A1-PM-KPM-0004 | Moblization of Quality Assurance and Quality Control Manager (Home Office/SITE) |  | 20-Feb-25 A |  | 2026-06-09 |  | 20-Feb-25 A
A1-PM-KPM-0005 | Moblization of Lead Discipline and Supervisory Engineers * - RAD |  | 01-Dec-24 A |  | 2026-06-12 |  | 01-Dec-24 A
A1-PM-KPM-0006 | Moblization of Process Manager (s) * |  | 01-Feb-25 A |  | 2026-06-12 |  | 01-Feb-25 A
A1-PM-KPM-0007 | Moblization of Procurement Manager (s) * |  | 15-Nov-24 A |  | 2026-06-12 |  | 15-Nov-24 A
A1-PM-KPM-0008 | Moblization of Project Commercial/Prime Contracts Manager |  | 01-Jan-25 A |  | 2026-06-12 |  | 01-Jan-25 A
A1-PM-KPM-0009 | Moblization of Project Traffic and Logistics Manager |  | 01-Dec-24 A |  | 2026-06-12 |  | 01-Dec-24 A
A1-PM-KPM-0010 | Moblization of Project Control Manager* |  | 15-Nov-24 A |  | 2026-06-12 |  | 15-Nov-24 A
A1-PM-KPM-0011 | Moblization of Lead Planner |  | 21-Jun-25 A |  | 2026-06-12 |  | 21-Jun-25 A
A1-PM-KPM-0012 | Moblization of Construction Planner |  | 27-Mar-25 A |  | 2026-06-12 |  | 27-Mar-25 A
A1-PM-KPM-0013 | Moblization of Project Contracts/Subcontracts Manager* |  | 01-Jun-25 A |  | 2026-06-16 |  | 01-Jun-25 A
A1-PM-KPM-0014 | Moblization of Project Construction Director/Manager(s)* |  | 14-Apr-25 A |  | 2026-06-12 |  | 14-Apr-25 A
A1-PM-KPM-0015 | Moblization of Project Construction Chief Field Engineer |  | 01-Mar-25 A |  | 2026-06-12 |  | 01-Mar-25 A
A1-PM-KPM-0016 | Moblization of Project Construction Field Superintendent |  | 15-Apr-25 A |  | 2026-06-16 |  | 15-Apr-25 A
A1-PM-KPM-0017 | Moblization of Project HSE Manager(s) (Home Office/Construction) |  | 20-Dec-24 A |  | 2026-06-12 |  | 20-Dec-24 A
A1-PM-KPM-0018 | Moblization of Lead Cost Engineer / Estimator |  | 01-Apr-25 A |  | 2026-06-12 |  | 01-Apr-25 A
A1-PM-KPM-0019 | Moblization of Project Commissioning Manager* |  | 13-Nov-25 A |  | 2026-06-16 |  | 13-Nov-25 A
A1-PM-KPM-0020 | Moblization of Project Training Manager* |  | 13-Nov-25 A |  | 2026-06-16 |  | 13-Nov-25 A
A1-PM-KPM-0021 | Moblization of Project IT Manager |  | 15-May-25 A |  | 2026-06-12 |  | 15-May-25 A
A1-PM-KPM-0022 | Moblization of Field Engineering Manager |  | 22-Aug-25 A |  | 2026-06-16 |  | 22-Aug-25 A
DetailedDesignandEngineering |  | 02-Apr-25 A | 2027-03-24 | 2026-06-11 | 2027-09-20 | 02-Apr-25 A | 2027-01-21
EngineeringWorkshops |  | 25-May-25 A | 15-Mar-26 A | 2026-06-11 | 2026-06-16 | 25-May-25 A | 2026-03-06
A1-PM-EWS-0001 | Engineering Workshops - 30% Model Review |  | 25-May-25 A |  | 2026-06-11 |  | 25-May-25 A |  | MS
A1-PM-EWS-0002 | Engineering Workshops - 60% Model Review |  | 19-Sep-25 A |  | 2026-06-12 |  | 19-Sep-25 A |  | MS
A1-PM-EWS-0003 | Engineering Workshops - 90% Model Review |  | 15-Mar-26 A |  | 2026-06-16 |  | 2026-03-06 |  | MS
EngineeringInterimMilestones |  | 02-Apr-25 A | 2027-03-24 | 2026-06-11 | 2027-09-20 | 02-Apr-25 A | 2027-01-21
GeneralProjectManagement |  | 30-Apr-25 A | 2027-03-24 | 2026-06-15 | 2027-09-20 | 26-May-25 A | 26-May-25 A
A1-PM-EIM-0001 | 1.A*-Issue Engineering Procedure. |  | 30-Apr-25 A |  | 2026-06-15 |  | 30-Apr-25 A |  | MS
A1-PM-EIM-0002 | 8.A*-As Built drawings handover to COMPANY |  | 2027-03-24 |  | 2027-09-20 |  | 2027-01-21 |  | MS
DetailEngineering |  | 02-Apr-25 A | 2026-06-16 | 2026-06-11 | 2027-03-23 | 02-Apr-25 A | 2026-06-04
A1-PM-EIM-0003 | 9.B*-Issue Utility demands, associated line sizes and electrical load data and equipment ratings final. |  | 2026-04-17 |  | 2026-06-15 |  | 2026-02-20
A1-PM-EIM-0004 | 10.B-Issue for COMPANY approval all documents for HAZOP / SIL review |  | 21-Jun-25 A |  | 2026-06-15 |  | 21-Jun-25 A
A1-PM-EIM-0005 | 11.B-Complete HAZOP/ SIL Review and submit Close Out Report with all actions closed. |  | 05-Sep-25 A |  | 2026-06-16 |  | 05-Sep-25 A
A1-PM-EIM-0006 | 12.B-Process design frozen |  | 18-Aug-25 A |  | 2027-03-23 |  | 18-Aug-25 A
A1-PM-EIM-0007 | 13.B*-Issue IFC PFDs, P&IDs, Data Sheets, Equipment Lists, Line Lists complete incorporating HAZOP comments |  | 2026-04-17 |  | 2027-03-19 |  | 2026-04-14
A1-PM-EIM-0008 | 14.B*-Issue IFC Plot Plans, Equipment Layouts etc. complete |  | 06-May-25 A |  | 2026-12-16 |  | 06-May-25 A
A1-PM-EIM-0009 | 15.B-Utility Consumption Issued for U&O |  | 20-Jun-25 A |  | 2026-06-15 |  | 20-Jun-25 A
A1-PM-EIM-0010 | 16.B-Effluent Summary & Flare Loads Frozen for U&O |  | 2026-04-17 |  | 2026-06-15 |  | 2026-02-24
A1-PM-EIM-0011 | 17.B-Steam Balance Frozen for U&O |  | 2026-04-17 |  | 2026-06-15 |  | 2026-02-24
A1-PM-EIM-0012 | 18.B-Issue IFC all Single Line Diagrams, Hazardous Area classification details for all facilities (complete). |  | 2026-06-09 |  | 2027-03-05 |  | 2026-04-14
A1-PM-EIM-0013 | 19.B*-Issue MRs for all Major Equipment & Packages for purchase. |  | 16-Sep-25 A |  | 2026-07-06 |  | 16-Sep-25 A
A1-PM-EIM-0014 | 20.B*-Receipt of key VENDOR data (by major equipment) |  | 2026-05-21 |  | 2026-10-16 |  | 2026-04-23
A1-PM-EIM-0015 | 21.B*-Issue IFC all underground services drawings |  | 15-Nov-25 A |  | 2026-06-16 |  | 15-Nov-25 A
A1-PM-EIM-0016 | 22.B*-Issue IFC all foundation & superstructure drawings for all Equipment & Packages |  | 2026-05-18 |  | 2027-01-01 |  | 2026-03-23
A1-PM-EIM-0017 | 23.B-Issue IFC 95% of Civil / Structural drawings for pipe supports, pipe trestles, sleepers etc. complete. |  | 17-Apr-26 A |  | 2026-08-29 |  | 2026-05-14
A1-PM-EIM-0018 | 24.B-Issue IFC 95% of Civil / Structural drawings etc. for all Buildings. |  | 01-Sep-25 A |  | 2026-12-16 |  | 01-Sep-25 A
A1-PM-EIM-0019 | 25.B-Complete 30% 3D-CAD model review |  | 25-May-25 A |  | 2026-06-11 |  | 25-May-25 A
A1-PM-EIM-0020 | 26.B*-Complete 60% 3D-CAD model review |  | 18-Sep-25 A |  | 2026-06-16 |  | 18-Sep-25 A
A1-PM-EIM-0021 | 27.B-Complete 90% 3D-CAD model review |  | 2026-04-23 |  | 2026-07-07 |  | 2026-03-06
A1-PM-EIM-0022 | 28.B*-Start issue piping isometrics IFC |  | 2026-04-17 |  | 2026-06-15 |  | 2026-02-20
A1-PM-EIM-0023 | 29.B-Issue 50% Piping Isometrics IFC |  | 2026-05-22 |  | 2027-03-19 |  | 2026-06-04
A1-PM-EIM-0024 | 30.B-Complete Piping Isometrics IFC |  | 2026-05-19 |  | 2026-07-24 |  | 2026-05-01
A1-PM-EIM-0025 | 31.B*-Issue 1st MTO and MRs for piping bulk materials |  | 21-Jun-25 A |  | 2026-06-15 |  | 21-Jun-25 A
A1-PM-EIM-0026 | 32.B-Issue Intermediate MTO and MR’s for piping bulk materials |  | 2026-04-17 |  | 2026-06-15 |  | 2026-02-24
A1-PM-EIM-0027 | 33.B-Issue final MTO and MRs for piping bulk materials |  | 2026-06-03 |  | 2026-08-24 |  | 2026-04-08
A1-PM-EIM-0028 | 34.B-Establish piping interface details and finalize procedures with COMPANY |  | 2026-05-12 |  | 2026-12-16 |  | 2026-04-21
A1-PM-EIM-0029 | 35.B*-Issue IFC Electrical cable schedules, cable layouts, equipment layouts earthing layouts, lighting layouts, JB deta |  | 2026-06-09 |  | 2026-12-04 |  | 2026-05-06
A1-PM-EIM-0030 | 36.B-Issue first MTO and MRs for electrical bulk materials |  | 21-Jun-25 A |  | 2026-08-17 |  | 21-Jun-25 A
A1-PM-EIM-0031 | 38.B*-Issue IFC Instrument cable schedules, cable layouts, equipment layouts, JB details, trench details etc. complete |  | 2026-06-09 |  | 2027-03-19 |  | 2026-06-03
A1-PM-EIM-0032 | 39.B-Issue first MTO and MRs for instrument bulk materials |  | 21-Jun-25 A |  | 2026-06-12 |  | 21-Jun-25 A
A1-PM-EIM-0033 | 41.B*-Issue IFC Electrical/Instrument layouts, interconnection diagrams etc. including all building control SYSTEMS, HVA |  | 2026-06-16 |  | 2027-03-05 |  | 2026-04-21
A1-PM-EIM-0034 | 42.B-Finalize and issue IFC all instrumentation loop diagrams. |  | 2026-06-16 |  | 2027-03-05 |  | 2026-05-06
A1-PM-EIM-0035 | 44.B-Issue Operating, Maintenance and Safety Manual. |  | 2026-06-09 |  | 2027-03-23 |  | 2026-04-21
A1-PM-EIM-0036 | 45.B-Design for Turnaround Works |  | 02-Apr-25 A |  | 2026-06-16 |  | 02-Apr-25 A
Procurement |  | 21-Feb-25 A | 2027-03-23 | 2026-06-15 | 2027-09-20 | 15-Apr-25 A | 2026-10-07
ProcurementDeliverables |  | 03-Mar-25 A | 2026-04-21 | 2026-09-11 | 2026-09-15 | 03-Mar-25 A | 2026-02-24
A1-PM-PRD-0001 | PM-018-Equipment Delivery and storage Plan | 25-May-25 A | 25-Aug-25 A | 2026-09-11 | 2026-09-11 | 25-May-25 A | 25-Aug-25 A
A1-PM-PRD-0002 | PM-019-Subcontracting Procedure | 25-May-25 A | 02-Sep-25 A | 2026-09-11 | 2026-09-11 | 25-May-25 A | 02-Sep-25 A
A1-PM-PRD-0003 | PM-020-Procurement Procedures | 01-Jun-25 A | 25-Aug-25 A | 2026-09-11 | 2026-09-11 | 01-Jun-25 A | 25-Aug-25 A
A1-PM-PRD-0004 | PM-021-Procurement Plan | 25-May-25 A | 15-Jun-25 A | 2026-09-11 | 2026-09-11 | 25-May-25 A | 15-Jun-25 A
A1-PM-PRD-0005 | PM-022-Procurement Control Log | 21-Jun-25 A | 12-Jul-25 A | 2026-09-11 | 2026-09-11 | 21-Jun-25 A | 12-Jul-25 A
A1-PM-PRD-0006 | PM-023-Transportation Plan & Procedure | 24-May-25 A | 25-Aug-25 A | 2026-09-11 | 2026-09-11 | 24-May-25 A | 25-Aug-25 A
A1-PM-PRD-0007 | PM-024-Shipping Forecast | 21-Jun-25 A | 12-Jul-25 A | 2026-09-11 | 2026-09-11 | 21-Jun-25 A | 12-Jul-25 A
A1-PM-PRD-0008 | PM-025-Copy of priced and unpriced Purchase Order | 21-Jun-25 A | 12-Jul-25 A | 2026-09-11 | 2026-09-11 | 21-Jun-25 A | 12-Jul-25 A
A1-PM-PRD-0009 | PM-026-Vendor Schedules | 21-Jun-25 A | 12-Jul-25 A | 2026-09-11 | 2026-09-11 | 21-Jun-25 A | 12-Jul-25 A
A1-PM-PRD-0010 | PM-027-Shipping Progress Report | 21-Jun-25 A | 12-Jul-25 A | 2026-09-11 | 2026-09-11 | 21-Jun-25 A | 12-Jul-25 A
A1-PM-PRD-0011 | PM-033-Commercial Bid Analysis | 21-Jun-25 A | 12-Jul-25 A | 2026-09-11 | 2026-09-11 | 21-Jun-25 A | 12-Jul-25 A
A1-PM-PRD-0012 | PM-034-Subcontract Award Recommendation | 21-Jun-25 A | 12-Jul-25 A | 2026-09-11 | 2026-09-11 | 21-Jun-25 A | 12-Jul-25 A
A1-PM-PRD-0013 | PM-035-Vendor Prequalification's | 21-Jun-25 A | 12-Jul-25 A | 2026-09-11 | 2026-09-11 | 21-Jun-25 A | 12-Jul-25 A
A1-PM-PRD-0014 | PM-036-Vendor Technical Queries /Answers | 21-Jun-25 A | 12-Jul-25 A | 2026-09-11 | 2026-09-11 | 21-Jun-25 A | 12-Jul-25 A
A1-PM-PRD-0015 | PM-042-Subcontract Bidders List | 21-Jun-25 A | 12-Jul-25 A | 2026-09-11 | 2026-09-11 | 21-Jun-25 A | 12-Jul-25 A
A1-PM-PRD-0016 | PM-043-Vendors List / Bidders Lists | 21-Jun-25 A | 12-Jul-25 A | 2026-09-11 | 2026-09-11 | 21-Jun-25 A | 12-Jul-25 A
A1-PM-PRD-0017 | PM-044-Vendor List | 12-Jun-25 A | 25-Aug-25 A | 2026-09-11 | 2026-09-11 | 12-Jun-25 A | 25-Aug-25 A
A1-PM-PRD-0018 | PM-051-Copy of unpriced sub contract agreement | 19-Jun-25 A | 02-Sep-25 A | 2026-09-11 | 2026-09-11 | 19-Jun-25 A | 02-Sep-25 A
A1-PM-PRD-0019 | PM-055-Subcontract Pre Qualification | 19-Jun-25 A | 25-Aug-25 A | 2026-09-11 | 2026-09-11 | 19-Jun-25 A | 25-Aug-25 A
A1-PM-PRD-0020 | PM-056-Vendor Manufacturing Quality Plan | 21-Jun-25 A | 23-Jul-25 A | 2026-09-11 | 2026-09-11 | 21-Jun-25 A | 23-Jul-25 A
A1-PM-PRD-0021 | PM-058-Subcontract technical & commercial bid evaluation | 03-Mar-25 A | 28-May-25 A | 2026-09-11 | 2026-09-11 | 03-Mar-25 A | 28-May-25 A
A1-PM-PRD-0022 | PM-059-Subcontract control log | 21-Jun-25 A | 12-Jul-25 A | 2026-09-11 | 2026-09-11 | 21-Jun-25 A | 12-Jul-25 A
A1-PM-PRD-0023 | PM-060-Award Recommendation | 21-Jun-25 A | 12-Jul-25 A | 2026-09-11 | 2026-09-11 | 21-Jun-25 A | 12-Jul-25 A
A1-PM-PRD-0024 | PM-066-Copy of Bill of Loading | 21-Jun-25 A | 12-Jul-25 A | 2026-09-11 | 2026-09-11 | 21-Jun-25 A | 12-Jul-25 A
A1-PM-PRD-0025 | PM-067-Delivery Certificate on Site | 21-Jun-25 A | 12-Jul-25 A | 2026-09-11 | 2026-09-11 | 21-Jun-25 A | 12-Jul-25 A
A1-PM-PRD-0026 | PM-068-Subcontract status report | 21-Jun-25 A | 12-Jul-25 A | 2026-09-11 | 2026-09-11 | 21-Jun-25 A | 12-Jul-25 A
A1-PM-PRD-0027 | PM-069-Sub contractor performance feed back report | 21-Jun-25 A | 12-Jul-25 A | 2026-09-11 | 2026-09-11 | 21-Jun-25 A | 12-Jul-25 A
A1-PM-PRD-0028 | PM-070-Material Status Report | 21-Jun-25 A | 12-Jul-25 A | 2026-09-11 | 2026-09-11 | 21-Jun-25 A | 12-Jul-25 A
A1-PM-PRD-0029 | PM-071-Purchasing Status Report | 21-Jun-25 A | 12-Jul-25 A | 2026-09-11 | 2026-09-11 | 21-Jun-25 A | 12-Jul-25 A
A1-PM-PRD-0030 | PM-072-Vendor Performance feed back report | 25-Oct-25 A | 2026-04-21 | 2026-09-11 | 2026-09-15 | 25-Oct-25 A | 2026-02-24
ProcurementInterimMilestones |  | 21-Feb-25 A | 2027-03-23 | 2026-06-15 | 2027-09-20 | 21-Feb-25 A | 2027-01-20
GeneralProjectManagement |  | 28-Mar-25 A | 2026-11-25 | 2026-10-22 | 2027-03-06 | 26-May-25 A | 26-May-25 A
A1-PM-PRM-0001 | 1.A*-Issue Procurement Procedures. |  | 28-Mar-25 A |  | 2026-10-22 |  | 28-Mar-25 A
A1-PM-PRM-0002 | 7.A-VENDOR training and visits planned |  | 2026-11-25 |  | 2027-03-06 |  | 2026-10-18
ProcurementEquipment&Materials |  | 21-Feb-25 A | 2026-06-17 | 2026-06-16 | 2027-03-23 | 21-Feb-25 A | 2026-05-13
A1-PM-PRM-0003 | 49.C*-Issue purchase order for Compressors Centrifugal / Reciprocating |  | 30-May-25 A |  | 2026-09-08 |  | 30-May-25 A
A1-PM-PRM-0004 | 50.C*-Issue purchase orders for Furnaces |  | 21-Jun-25 A |  | 2026-06-16 |  | 21-Jun-25 A
A1-PM-PRM-0005 | 51.C*-Issue purchase orders for all remaining Mechanical / Rotating Equipment & Equipment Packages |  | 01-Sep-25 A |  | 2026-12-11 |  | 01-Sep-25 A
A1-PM-PRM-0006 | 52.C*-Issue purchase orders for all major electrical Equipment |  | 2026-05-08 |  | 2027-03-23 |  | 2026-05-13
A1-PM-PRM-0007 | 54.C*-Issue purchase order for all major instrument control SYSTEMS |  | 21-Nov-25 A |  | 2026-12-10 |  | 21-Nov-25 A
A1-PM-PRM-0008 | 55.C*-Issue first purchase order for piping bulk materials |  | 19-Sep-25 A |  | 2026-08-02 |  | 19-Sep-25 A
A1-PM-PRM-0009 | 56.C-Issue intermediate purchase order for piping bulk materials |  | 2026-04-17 |  | 2026-08-24 |  | 2026-03-19
A1-PM-PRM-0010 | 57.C-Issue final purchase order for piping bulk materials |  | 2026-06-17 |  | 2026-08-24 |  | 2026-04-22
A1-PM-PRM-0011 | 58.C-Issue purchase orders for all field instrument tagged items |  | 2026-04-17 |  | 2027-03-23 |  | 2026-03-25
A1-PM-PRM-0012 | 59.C*-Issue first purchase orders for bulk electrical materials |  | 21-Jun-25 A |  | 2026-10-01 |  | 21-Jun-25 A
A1-PM-PRM-0013 | 60.C-Issue purchase orders for all Shut Down Materials (Piping, Electrical and Instrumentation |  | 28-Mar-25 A |  | 2026-06-16 |  | 28-Mar-25 A
A1-PM-PRM-0014 | 61.C*-Issue first purchase orders for bulk instrument materials |  | 21-Jun-25 A |  | 2027-03-23 |  | 21-Jun-25 A
A1-PM-PRM-0015 | 62.C-Issue purchase order Piping MTO for Shut Down Works |  | 21-Feb-25 A |  | 2026-06-16 |  | 21-Feb-25 A
Subcontracts |  | 30-May-25 A | 01-Sep-25 A | 2026-06-15 | 2027-03-06 | 30-May-25 A | 01-Sep-25 A
A1-PM-PRM-0016 | 63.C-Piling subcontract award |  | 01-Jun-25 A |  | 2026-06-15 |  | 01-Jun-25 A
A1-PM-PRM-0017 | 64.C*-Civil subcontract award |  | 15-Jun-25 A |  | 2026-06-21 |  | 15-Jun-25 A
A1-PM-PRM-0018 | 65.C-Steel fabrication/erection subcontract award |  | 01-Sep-25 A |  | 2026-06-25 |  | 01-Sep-25 A
A1-PM-PRM-0019 | 66.C*-Mechanical subcontract award |  | 15-Jun-25 A |  | 2026-11-16 |  | 15-Jun-25 A
A1-PM-PRM-0020 | 67.C-Insulation subcontract award |  | 15-Jun-25 A |  | 2026-12-09 |  | 15-Jun-25 A
A1-PM-PRM-0021 | 68.C-Painting subcontract award |  | 15-Jun-25 A |  | 2026-12-09 |  | 15-Jun-25 A
A1-PM-PRM-0022 | 69.C*-Electrical subcontract award |  | 15-Jun-25 A |  | 2026-12-20 |  | 15-Jun-25 A
A1-PM-PRM-0023 | 70.C*-Instrument subcontract award |  | 15-Jun-25 A |  | 2027-03-06 |  | 15-Jun-25 A
A1-PM-PRM-0024 | 71.C*-Buildings subcontract award |  | 30-May-25 A |  | 2026-06-21 |  | 30-May-25 A
Manufacturing&Delivery |  | 20-Mar-25 A | 2027-03-23 | 2026-06-16 | 2027-09-20 | 20-Mar-25 A | 2027-01-20
A1-PM-PRM-0025 | 76.D*-Compressors Centrifugal / Reciprocating delivered to SITE |  | 2026-06-22 |  | 2026-07-05 |  | 2026-03-03 |  | MS
A1-PM-PRM-0026 | 77.D*-Furnaces delivered to SITE |  | 10-Sep-25 A |  | 2027-03-23 |  | 10-Sep-25 A
A1-PM-PRM-0027 | 78.D*-Remaining Mechanical / Rotating Equipment & Equipment Packages delivered to SITE |  | 2026-09-30 |  | 2026-12-11 |  | 2026-09-13
A1-PM-PRM-0028 | 79.D*-All major electrical Equipment delivered to SITE |  | 2026-10-30 |  | 2027-03-06 |  | 2026-09-29 |  | MS
A1-PM-PRM-0029 | 80.D*-HVAC, Fire Detection and Fire Fighting SYSTEMS for all buildings delivered to SITE |  | 2026-08-13 |  | 2027-02-28 |  | 2026-08-26
A1-PM-PRM-0030 | 81.D*-Major instrument control SYSTEMS delivered to SITE |  | 2026-11-06 |  | 2027-02-10 |  | 2026-09-29 |  | MS
A1-PM-PRM-0031 | 82.D-Instrument Control SYSTEMS for CCB delivered to SITE |  | 2026-10-30 |  | 2027-02-10 |  | 2026-09-29 |  | MS
A1-PM-PRM-0032 | 83.D-Field instrument tagged items delivered to SITE |  | 2026-11-06 |  | 2027-02-10 |  | 2026-09-27 |  | MS
A1-PM-PRM-0033 | 84.D*-Bulk piping materials initial MTO delivered to SITE |  | 31-Jan-26 A |  | 2026-07-08 |  | 2026-02-20
A1-PM-PRM-0034 | 85.D*-Bulk piping materials intermediate MTO delivered to SITE |  | 2026-05-31 |  | 2026-09-15 |  | 2026-04-18
A1-PM-PRM-0035 | 86.D*-Bulk piping materials final MTO delivered to SITE |  | 2026-09-17 |  | 2027-03-06 |  | 2026-08-22 |  | MS
A1-PM-PRM-0036 | 88.D-Bulk electrical materials final MTO delivered to SITE |  | 2026-09-28 |  | 2027-02-10 |  | 2026-08-31 |  | MS
A1-PM-PRM-0037 | 90.D-Bulk instrument materials final MTO delivered to SITE |  | 2026-10-19 |  | 2027-03-06 |  | 2026-09-24 | End of Procurement | MS
A1-PM-PRM-0038 | 91.D-Insurance spares for all equipment & packages arrival at SITE and handover to COMPANY |  | 2027-03-23 |  | 2027-09-20 |  | 2027-01-20
A1-PM-PRM-0039 | 92.D*-Operating Spares for all item’s arrival at SITE and handover to COMPANY. |  | 2027-03-23 |  | 2027-09-20 |  | 2027-01-20
A1-PM-PRM-0040 | 93.D*-All VENDOR Documentation Handed over to COMPANY |  | 2027-03-23 |  | 2027-09-20 |  | 2027-01-20
A1-PM-PRM-0041 | 94.D-Piping MTO for Shut Down Works Delivered to SITE |  | 20-Mar-25 A |  | 2026-06-16 |  | 20-Mar-25 A
Construction |  | 10-Mar-25 A | 2027-05-11 | 2026-06-16 | 2027-09-20 | 10-Mar-25 A | 2027-03-10
ConstructionDeliverables |  | 10-Mar-25 A | 2027-05-11 | 2026-10-22 | 2027-06-22 | 10-Mar-25 A | 2027-03-10
A1-PM-COD-0001 | CS-001-QC Dossier | 2027-03-24 | 2027-03-30 | 2027-05-05 | 2027-05-11 | 2027-01-21 | 2027-01-27
A1-PM-COD-0002 | CS-002-Construction Handover Dossier ( ALL Discipline wise) | 22-Jun-25 A | 2027-05-11 | 2027-06-18 | 2027-06-22 | 22-Jun-25 A | 2027-03-10
A1-PM-COD-0003 | CS-003-Execution Plan | 25-May-25 A | 15-Nov-25 A | 2026-10-22 | 2026-10-22 | 25-May-25 A | 15-Nov-25 A
A1-PM-COD-0004 | CS-004-Procedures | 21-Jun-25 A | 12-Jul-25 A | 2026-10-22 | 2026-10-22 | 21-Jun-25 A | 12-Jul-25 A
A1-PM-COD-0005 | CS-005-Field instructions | 01-Sep-25 A | 2026-04-17 | 2026-10-22 | 2026-10-23 | 01-Sep-25 A | 2026-02-20
A1-PM-COD-0006 | CS-006-Method Statements | 21-Jun-25 A | 12-Jul-25 A | 2026-10-22 | 2026-10-22 | 21-Jun-25 A | 12-Jul-25 A
A1-PM-COD-0007 | CS-007-Time Schedule / Programme | 19-Mar-25 A | 19-Jun-25 A | 2026-10-22 | 2026-10-22 | 19-Mar-25 A | 19-Jun-25 A
A1-PM-COD-0008 | CS-008-Lifting | 21-Jun-25 A | 12-Jul-25 A | 2026-10-22 | 2026-10-22 | 21-Jun-25 A | 12-Jul-25 A
A1-PM-COD-0009 | CS-009-Site plans | 21-Jun-25 A | 12-Jul-25 A | 2026-10-22 | 2026-10-22 | 21-Jun-25 A | 12-Jul-25 A
A1-PM-COD-0010 | CS-010-Demolition plan | 21-Jun-25 A | 12-Jul-25 A | 2026-10-22 | 2026-10-22 | 21-Jun-25 A | 12-Jul-25 A
A1-PM-COD-0011 | CS-011-Temporary Works | 21-Jun-25 A | 12-Jul-25 A | 2026-10-22 | 2026-10-22 | 21-Jun-25 A | 12-Jul-25 A
A1-PM-COD-0012 | CS-012-label | 21-Jun-25 A | 12-Jul-25 A | 2026-10-22 | 2026-10-22 | 21-Jun-25 A | 12-Jul-25 A
A1-PM-COD-0013 | CS-013-Locking List | 02-Jun-25 A | 20-Jun-25 A | 2026-10-22 | 2026-10-22 | 02-Jun-25 A | 20-Jun-25 A
A1-PM-COD-0014 | CS-014-Technical Bid Analysis | 21-Jun-25 A | 12-Jul-25 A | 2026-10-22 | 2026-10-22 | 21-Jun-25 A | 12-Jul-25 A
A1-PM-COD-0015 | CS-015-Insulation / Painting / Fire Proofing | 01-Apr-25 A | 2026-04-23 | 2026-10-22 | 2026-10-29 | 01-Apr-25 A | 2026-02-26
A1-PM-COD-0016 | CS-016-Punch List | 21-Jun-25 A | 2026-04-17 | 2026-10-22 | 2026-10-23 | 21-Jun-25 A | 2026-02-20
A1-PM-COD-0017 | CS-017-Check List | 15-Oct-25 A | 19-Dec-25 A | 2026-10-22 | 2026-10-22 | 15-Oct-25 A | 19-Dec-25 A
A1-PM-COD-0018 | CS-018-Quality Assurance Docs | 02-Jun-25 A | 19-Jun-25 A | 2026-10-22 | 2026-10-22 | 02-Jun-25 A | 19-Jun-25 A
A1-PM-COD-0019 | CS-019-HSE | 01-Oct-25 A | 18-Dec-25 A | 2026-10-22 | 2026-10-22 | 01-Oct-25 A | 18-Dec-25 A
A1-PM-COD-0020 | CS-020-Test Certificate | 10-Mar-25 A | 26-Mar-25 A | 2026-10-22 | 2026-10-22 | 10-Mar-25 A | 26-Mar-25 A
A1-PM-COD-0021 | CS-021-Quality Control Procedure | 01-Oct-25 A | 19-Dec-25 A | 2026-10-22 | 2026-10-22 | 01-Oct-25 A | 19-Dec-25 A
A1-PM-COD-0022 | CS-022-Construction Strategies | 21-Jun-25 A | 19-Dec-25 A | 2026-10-22 | 2026-10-22 | 21-Jun-25 A | 19-Dec-25 A
A1-PM-COD-0023 | CS-023-Concession Requests | 01-Sep-25 A | 19-Dec-25 A | 2026-10-22 | 2026-10-22 | 01-Sep-25 A | 19-Dec-25 A
A1-PM-COD-0024 | CS-024-Non-Conformance Requests | 01-Sep-25 A | 19-Dec-25 A | 2026-10-22 | 2026-10-22 | 01-Sep-25 A | 19-Dec-25 A
A1-PM-COD-0025 | CS-025-Electrical Specifications | 21-Jun-25 A | 20-Aug-25 A | 2026-10-22 | 2026-10-22 | 21-Jun-25 A | 20-Aug-25 A
A1-PM-COD-0026 | CS-026-Civil Specifications | 21-Jun-25 A | 31-Jul-25 A | 2026-10-22 | 2026-10-22 | 21-Jun-25 A | 31-Jul-25 A
A1-PM-COD-0027 | CS-027-Temporary facilities plan | 21-Jun-25 A | 30-Jun-25 A | 2026-10-22 | 2026-10-22 | 21-Jun-25 A | 30-Jun-25 A
A1-PM-COD-0028 | CS-028-Construction execution methodologies (work methods) | 01-Apr-25 A | 07-Apr-25 A | 2026-10-22 | 2026-10-22 | 01-Apr-25 A | 07-Apr-25 A
A1-PM-COD-0029 | CS-029-Logistics plan | 21-Jun-25 A | 30-Jun-25 A | 2026-10-22 | 2026-10-22 | 21-Jun-25 A | 30-Jun-25 A
A1-PM-COD-0030 | CS-030-mobilisation/demobilisation plan | 01-Jul-25 A | 19-Dec-25 A | 2026-10-22 | 2026-10-22 | 01-Jul-25 A | 19-Dec-25 A
A1-PM-COD-0031 | CS-031-Construction Cleanliness Plant | 01-Aug-25 A | 2026-04-21 | 2026-10-22 | 2026-10-27 | 01-Aug-25 A | 2026-02-24
A1-PM-COD-0032 | CS-032-Camp and Accommodation Plan | 21-Jun-25 A | 12-Jul-25 A | 2026-10-22 | 2026-10-22 | 21-Jun-25 A | 12-Jul-25 A
A1-PM-COD-0033 | CS-033-Construction logistic plan | 01-Aug-25 A | 2026-04-20 | 2026-10-22 | 2026-10-23 | 01-Aug-25 A | 2026-02-23
A1-PM-COD-0034 | CS-034-Field Construction Execution plan | 08-Apr-25 A | 19-Dec-25 A | 2027-04-09 | 2027-04-09 | 08-Apr-25 A | 19-Dec-25 A
ConstructionInterimMilestones |  | 25-Mar-25 A | 2027-04-24 | 2026-06-16 | 2027-09-20 | 25-Mar-25 A | 2027-02-21
GeneralProjectManagement |  | 31-May-25 A | 2026-04-17 | 2026-06-16 | 2027-04-09 | 26-May-25 A | 26-May-25 A
A1-PM-CIM-0001 | 3.A-Issue Construction Execution Plan (Excluding Hydrotesting, Drying, Purging, PRE-COMMISSIONING and COMMISSIONING Proc |  | 21-Jun-25 A |  | 2026-06-16 |  | 21-Jun-25 A
A1-PM-CIM-0002 | 3.A-Issue Construction Execution Procedures (Excluding Hydrotesting, Drying, Purging, PRE-COMMISSIONING and COMMISSIONIN |  | 21-Jun-25 A |  | 2026-06-16 |  | 21-Jun-25 A
A1-PM-CIM-0003 | 3.A-Issue Construction Execution Method Statements (Excluding Hydrotesting, Drying, Purging, PRE-COMMISSIONING and COMMI |  | 21-Jun-25 A |  | 2026-06-16 |  | 21-Jun-25 A
A1-PM-CIM-0004 | 3.A-Tie-in/Shutdown philosophy etc. (Excluding Hydrotesting, Drying, Purging, PRE-COMMISSIONING and COMMISSIONING Proced |  | 31-May-25 A |  | 2026-06-16 |  | 31-May-25 A
A1-PM-CIM-0005 | 4.A-Issue Hydrotesting Procedures and plan (Final). |  | 2026-04-17 |  | 2027-04-09 |  | 2026-04-14
A1-PM-CIM-0006 | 4.A-Issue Drying Procedures and plan (Final). |  | 2026-04-17 |  | 2027-04-09 |  | 2026-04-14
A1-PM-CIM-0007 | 4.A-Issue Purging Procedures and plan (Final). |  | 2026-04-17 |  | 2027-04-09 |  | 2026-04-14
A1-PM-CIM-0008 | 4.A-Issue PRECOMMISSIONING Procedures and plan (Final). |  | 2026-04-17 |  | 2027-04-09 |  | 2026-04-14
A1-PM-CIM-0009 | 4.A-Issue COMMISSIONING Procedures and plan (Final). |  | 2026-04-17 |  | 2027-04-09 |  | 2026-04-14
A1-PM-CIM-0010 | 4.A-Issue Handover Procedures and plan (Final). |  | 2026-04-17 |  | 2027-02-09 |  | 2026-04-14
Construction&Commissioning |  | 25-Mar-25 A | 2027-01-03 | 2026-06-16 | 2027-03-23 | 2027-01-20 | 2027-01-20
A1-PM-CIM-0011 | 94.E*-Commence on SITE |  | 31-May-25 A |  | 2026-10-22 |  | 31-May-25 A |  | MS
A1-PM-CIM-0012 | 95.E-Complete Construction of Temporary Facilities at SITE. |  | 15-Nov-25 A |  | 2026-10-22 |  | 15-Nov-25 A
A1-PM-CIM-0013 | 96.E-Complete SITE preparation and grading works |  | 21-Jun-25 A |  | 2026-10-22 |  | 21-Jun-25 A
A1-PM-CIM-0014 | 100.E-Complete construction of foundations for all remaining mechanical, rotating & packaged equipment |  | 2026-07-19 |  | 2026-10-22 |  | 2026-06-25
A1-PM-CIM-0015 | 101.E-Complete all Piperack foundations |  | 2026-05-25 |  | 2027-03-23 |  | 2026-04-09 |  | MS
A1-PM-CIM-0016 | 102.E-Complete all underground piping |  | 2026-08-19 |  | 2027-03-23 |  | 2026-07-19 |  | MS
A1-PM-CIM-0017 | 103.E-Complete installation of all underground electrical cabling |  | 2026-06-11 |  | 2027-02-09 |  | 2026-05-07
A1-PM-CIM-0018 | 104.E-Complete installation of all underground instrument cabling |  | 2026-09-28 |  | 2027-02-09 |  | 2026-06-20
A1-PM-CIM-0019 | 105.E-Trench for data highway cables SIS to Control Building available |  | 2026-06-11 |  | 2027-03-23 |  | 2026-05-07
A1-PM-CIM-0020 | 106.E-Complete installation of steel structural works for shelters, and Package Units etc. |  | 2026-11-11 |  | 2027-03-23 |  | 2026-09-10 |  | MS
A1-PM-CIM-0021 | 110.E-Complete installation of Turbines/Compressors |  | 2026-07-19 |  | 2027-03-23 |  | 2026-05-18 |  | MS
A1-PM-CIM-0022 | 111.E-Complete installation of all remaining mechanical, rotating & packaged equipment |  | 2027-01-03 |  | 2027-03-23 |  | 2026-11-02
A1-PM-CIM-0023 | 112.E-Completion of Heavy Lifts |  | 2026-07-19 |  | 2026-09-30 |  | 2026-05-18
A1-PM-CIM-0024 | 113.E-Start Piping Prefabrication |  | 25-Mar-25 A |  | 2026-06-16 |  | 25-Mar-25 A |  | MS
A1-PM-CIM-0025 | 114.E-Complete prefabrication 50% piping. |  | 2026-10-08 |  | 2027-03-23 |  | 2026-09-17
A1-PM-CIM-0026 | 115.E-Complete prefabrication 98% piping |  | 2026-10-26 |  | 2027-03-23 |  | 2026-10-05 |  | MS
A1-PM-CIM-0027 | 116.E-Complete installation of pipe supports, sleepers, trestles etc. |  | 2026-11-14 |  | 2027-03-23 |  | 2026-10-22
A1-PM-CIM-0028 | 117.E-Start Piping erection |  | 15-Apr-25 A |  | 2027-03-23 |  | 15-Apr-25 A |  | MS
A1-PM-CIM-0029 | 118.E-Piping erection 50% Complete |  | 2026-11-14 |  | 2027-03-23 |  | 2026-10-22
A1-PM-CIM-0030 | 119.E-Piping Erection 100% complete |  | 2026-11-14 |  | 2027-03-23 |  | 2026-10-22 |  | MS
A1-PM-CIM-0031 | 120.E-Commence hydrotesting of Pipework |  | 2026-12-07 |  | 2027-03-23 |  | 2026-11-16
A1-PM-CIM-0032 | 121.E-Piping Hydrotesting 50% complete |  | 2026-12-07 |  | 2027-03-23 |  | 2026-11-16
A1-PM-CIM-0033 | 122.E-Piping Hydrotesting 100% complete |  | 2026-12-07 |  | 2027-03-23 |  | 2026-12-03 |  | MS
A1-PM-CIM-0034 | 123.E-Complete all piping tie-ins (Including Interface Tie-Ins) |  | 20-May-25 A |  | 2026-06-16 |  | 20-May-25 A
A1-PM-CIM-0035 | 124.E-Complete Fire Water System including tanks, pumps and piping works up to Mechanical Completion. |  | 2026-11-05 |  | 2027-03-23 |  | 2026-12-03
A1-PM-CIM-0036 | 125.E-Complete Heat Tracing, Insulation, Fire Proofing and Painting works |  | 2026-11-07 |  | 2027-03-23 |  | 2026-10-05 |  | MS
A1-PM-CIM-0037 | 126.E-Complete installation of platforms, walkways, crossovers etc. |  | 2026-11-11 |  | 2027-03-23 |  | 2026-09-10
A1-PM-CIM-0038 | 127.E-Complete installation of all Substation electrical equipment |  | 2026-12-10 |  | 2027-03-23 |  | 2026-10-18
A1-PM-CIM-0039 | 128.E-Trench for Main Electrical Feeder cables Main to Unit Substations available |  | 2026-06-18 |  | 2026-10-15 |  | 2026-05-07
A1-PM-CIM-0040 | 129.E-Complete electrical cabling and termination works (field works) for all plant facilities including continuity chec |  | 2026-12-28 |  | 2027-03-23 |  | 2026-12-21 |  | MS
A1-PM-CIM-0041 | 130.E-Complete Street lighting |  | 2026-10-04 |  | 2027-03-23 |  | 2026-10-03
Eelectrical |  | 2027-03-23 | 2027-04-24 | 2027-06-22 | 2027-09-20 | 2027-01-20 | 2027-02-21
A1-PM-CIM-0042 | 131.E-Power from TRANSCO (Needs) |  | 2027-03-23 |  | 2027-09-20 |  | 2027-01-20
A1-PM-CIM-0043 | 134.E-Complete motor run |  | 2027-04-24 |  | 2027-06-22 |  | 2027-02-21
Instrumentation |  | 2026-12-09 | 2026-12-28 | 2027-06-22 | 2027-06-22 | 2026-11-08 | 2026-12-21
A1-PM-CIM-0044 | 135.E-Control System Cables including Fiber opticinstalled and tested |  | 2026-12-09 |  | 2027-06-22 |  | 2026-11-08
A1-PM-CIM-0045 | 136.E-Complete instrumentation system loop checks and other PRE-COMMISSIONING checks |  | 2026-12-28 |  | 2027-06-22 |  | 2026-12-21 |  | MS
MechanicalCompletion&ReadyforSTARTUP |  | 2027-03-23 | 2027-03-23 | 2027-09-20 | 2027-09-20 | 2027-01-20 | 2027-01-20
A1-PM-CIM-0046 | 138.F-Mechanical Completion |  | 2027-03-23 |  | 2027-09-20 |  | 2027-01-20 | End of Construction | MS
ConstructionWorkshops |  | 27-Aug-25 A | 29-Aug-25 A | 2027-02-22 | 2027-02-22 | 27-Aug-25 A | 29-Aug-25 A
A1-PM-CWS-0001 | Constructabilty Workshop | 27-Aug-25 A | 27-Aug-25 A | 2027-02-22 | 2027-02-22 | 27-Aug-25 A | 27-Aug-25 A
A1-PM-CWS-0002 | SIMOPS Workshop | 28-Aug-25 A | 29-Aug-25 A | 2027-02-22 | 2027-02-22 | 28-Aug-25 A | 29-Aug-25 A
Commissioning |  | 01-Aug-25 A | 2027-09-20 | 2026-10-13 | 2027-09-20 | 01-Aug-25 A | 2027-07-20
CommissioningDeliverables |  | 01-Aug-25 A | 2026-09-04 | 2026-10-13 | 2027-03-02 | 01-Aug-25 A | 2026-07-10
A1-PM-CMD-0001 | CM-001-Performance Test Run Procedure | 01-Aug-25 A | 2026-05-01 | 2026-10-13 | 2026-10-27 | 01-Aug-25 A | 2026-03-06
A1-PM-CMD-0002 | CM-002-Performance Test Run Report | 2026-05-01 | 2026-05-22 | 2026-10-28 | 2026-11-17 | 2026-03-06 | 2026-03-27
A1-PM-CMD-0003 | CM-003-Commissioning Procedures | 2026-05-22 | 2026-06-12 | 2026-11-18 | 2026-12-08 | 2026-03-27 | 2026-04-17
A1-PM-CMD-0004 | CM-004-Pre-Commisioning & Commissioning Schedule | 2026-06-12 | 2026-07-03 | 2026-12-09 | 2026-12-29 | 2026-04-17 | 2026-05-08
A1-PM-CMD-0005 | CM-005-Pre-Commisioning & Commissioning systems identification drawings (P&IDs, single line diagram, etc) | 2026-07-03 | 2026-07-24 | 2026-12-30 | 2027-01-19 | 2026-05-08 | 2026-05-29
A1-PM-CMD-0006 | CM-006-Pre- Commissioning Procedure | 2026-07-24 | 2026-08-14 | 2027-01-20 | 2027-02-09 | 2026-05-29 | 2026-06-19
A1-PM-CMD-0007 | CM-007-Pre-Commisioning & Commissioning Method of Statements | 2026-08-14 | 2026-09-04 | 2027-02-10 | 2027-03-02 | 2026-06-19 | 2026-07-10
CommissioningInterimMilestones |  | 2026-10-28 | 2027-09-20 | 2027-06-22 | 2027-09-20 | 2026-09-14 | 2027-07-20
GeneralProjectManagement |  | 2027-03-23 | 2027-03-24 | 2027-06-22 | 2027-06-22 | 26-May-25 A | 26-May-25 A
A1-PM-CMM-0001 | 6.A-Training program for COMPANY staff issued to COMPANY for APPROVAL |  | 2027-03-23 |  | 2027-06-22 |  | 2027-01-20
A1-PM-CMM-0006 | 5.A-Issue SYSTEMS definition IFC & SYSTEMS completion Schedule |  | 2027-03-24 |  | 2027-06-22 |  | 2027-01-21
MechanicalCompletion&ReadyforSTARTUP |  | 2026-10-28 | 2027-09-20 | 2027-09-20 | 2027-09-20 | 2027-01-20 | 2027-01-20
A1-PM-CMM-0002 | 145.F-Ready for Start-Up |  | 2027-06-23 |  | 2027-09-20 |  | 2027-04-22
A1-PM-CMM-0003 | 142.F-Commercial Production |  | 2027-06-15 |  | 2027-09-20 |  | 2027-04-14
A1-PM-CMM-0004 | 143.F-Issue "AS BUILT STATUS”
operating/Maintenance&SafetyManual |  | 2026-10-28 |  | 2027-09-20 |  | 2026-09-14
A1-PM-CMM-0005 | 144.F-PROVISIONAL ACCEPTANCE CERTIFICATE |  | 2027-09-20 |  | 2027-09-20 |  | 2027-07-20 |  |  | CP | CP
HSEManagement |  | 17-Feb-25 A | 2026-11-13 | 2026-06-11 | 2027-03-23 | 17-Feb-25 A | 2026-09-25
HSEDeliverables |  | 17-Feb-25 A | 2026-06-16 | 2026-06-15 | 2027-02-09 | 17-Feb-25 A | 2026-04-21
A1-PM-HSD-0001 | S-001-Procedures & Management of Change | 17-Feb-25 A | 03-Mar-25 A | 2026-06-22 | 2026-06-22 | 17-Feb-25 A | 03-Mar-25 A
A1-PM-HSD-0002 | S-002-Requisition / Supply Specifications/ Technical Specifications | 01-Aug-25 A | 2026-04-17 | 2026-10-22 | 2026-10-22 | 01-Aug-25 A | 2026-02-20
A1-PM-HSD-0003 | S-003-HSE Requirements | 03-Mar-25 A | 06-Sep-25 A | 2026-11-05 | 2026-11-05 | 03-Mar-25 A | 06-Sep-25 A
A1-PM-HSD-0004 | S-004-Fire Fighting Diagram / Fire Protection Diagram | 01-Aug-25 A | 2026-04-17 | 2026-11-05 | 2026-11-05 | 01-Aug-25 A | 2026-02-20
A1-PM-HSD-0005 | S-005-Site Plans / Plot Plans / Key Plans | 21-Jun-25 A | 12-Jul-25 A | 2026-11-05 | 2026-11-05 | 21-Jun-25 A | 12-Jul-25 A
A1-PM-HSD-0006 | S-006-Overall Fire Water & Ringman Header Layout | 21-Jun-25 A | 12-Jul-25 A | 2026-11-05 | 2026-11-05 | 21-Jun-25 A | 12-Jul-25 A
A1-PM-HSD-0007 | S-007-Project Construction HSE Plan / House Keeping Plan | 10-Jun-25 A | 11-Jul-25 A | 2027-02-09 | 2027-02-09 | 10-Jun-25 A | 11-Jul-25 A
A1-PM-HSD-0008 | S-008-Fire Proofing Zone layout (Plant / Area Wise) | 01-Aug-25 A | 2026-04-17 | 2026-11-05 | 2026-11-05 | 01-Aug-25 A | 2026-02-20
A1-PM-HSD-0009 | S-009-HSE Layouts | 21-Jun-25 A | 12-Jul-25 A | 2026-11-05 | 2026-11-05 | 21-Jun-25 A | 12-Jul-25 A
A1-PM-HSD-0010 | S-010-Hazardous area Layouts | 22-Jul-25 A | 2026-04-17 | 2026-11-05 | 2026-11-05 | 22-Jul-25 A | 2026-02-20
A1-PM-HSD-0011 | S-011-Fire Exposure Envelop Drawings / Heat Flux Boundary Drawings | 01-Aug-25 A | 2026-04-17 | 2026-11-05 | 2026-11-05 | 01-Aug-25 A | 2026-02-20
A1-PM-HSD-0012 | S-012-Fire Alarm Drawings (Plant) | 01-Aug-25 A | 2026-04-17 | 2026-11-05 | 2026-11-05 | 01-Aug-25 A | 2026-02-20
A1-PM-HSD-0013 | S-013-Fire Alarm Drawings (Building) | 01-Aug-25 A | 2026-04-17 | 2026-11-05 | 2026-11-05 | 01-Aug-25 A | 2026-02-20
A1-PM-HSD-0014 | S-014-Bill of material | 02-Jun-25 A | 09-Jun-25 A | 2026-10-22 | 2026-10-22 | 02-Jun-25 A | 09-Jun-25 A
A1-PM-HSD-0015 | S-015-Safety Schedule / Sheets | 09-Jun-25 A | 20-Jun-25 A | 2026-11-05 | 2026-11-05 | 09-Jun-25 A | 20-Jun-25 A
A1-PM-HSD-0016 | S-016-Technical Bid Analysis | 21-Jun-25 A | 12-Jul-25 A | 2026-11-05 | 2026-11-05 | 21-Jun-25 A | 12-Jul-25 A
A1-PM-HSD-0017 | S-017-Hazard and Effect Register / HSECES Register/ HSE Critical Activities | 01-Aug-25 A | 2026-04-17 | 2026-11-05 | 2026-11-05 | 01-Aug-25 A | 2026-02-20
A1-PM-HSD-0018 | S-018-Equipment List | 21-Jun-25 A | 21-Jul-25 A | 2026-11-05 | 2026-11-05 | 21-Jun-25 A | 21-Jul-25 A
A1-PM-HSD-0019 | S-019-Fire and Safety Calculations / Explosion Over Pressure Calculations / Hydraulic Calculation | 01-Aug-25 A | 2026-04-20 | 2026-11-05 | 2026-11-06 | 01-Aug-25 A | 2026-02-23
A1-PM-HSD-0020 | S-020-Hydraulic Calculations Report | 04-Aug-25 A | 2026-04-20 | 2026-11-05 | 2026-11-06 | 04-Aug-25 A | 2026-02-23
A1-PM-HSD-0021 | S-021-HAZOP / SIL (LOPA) Reports |  | 18-Jul-25 A |  | 2026-06-15 |  | 18-Jul-25 A
A1-PM-HSD-0022 | S-022-Hazard Study / Fire Protection Design Study / Noise Vibration Study/ SIMOPS Study | 11-Aug-25 A | 29-Aug-25 A | 2026-11-05 | 2026-11-05 | 11-Aug-25 A | 29-Aug-25 A
A1-PM-HSD-0023 | S-023-Quality Assurance Docs | 05-Aug-25 A | 2026-04-17 | 2026-11-05 | 2026-11-05 | 05-Aug-25 A | 2026-02-20
A1-PM-HSD-0024 | S-024-Manufacturing Data Report | 04-Aug-25 A | 2026-04-21 | 2026-11-05 | 2026-11-09 | 04-Aug-25 A | 2026-02-24
A1-PM-HSD-0025 | S-025-Installation, Operation and Maintenance | 01-Aug-25 A | 2026-04-21 | 2026-11-05 | 2026-11-09 | 01-Aug-25 A | 2026-02-24
A1-PM-HSD-0026 | S-026-Environmental / Effluent Disposal System/ Gas Dispersion /Environmental Pollution Reports / Fugitive Emissions Rep | 04-Aug-25 A | 2026-04-20 | 2026-11-05 | 2026-11-06 | 04-Aug-25 A | 2026-02-23
A1-PM-HSD-0027 | S-027-HSE Report / Close out Report/Atmospheric Relief System Report/ HSE- Safety Reviews | 05-Aug-25 A | 2026-04-21 | 2026-11-05 | 2026-11-09 | 05-Aug-25 A | 2026-02-24
A1-PM-HSD-0028 | S-028-QRA Reports | 05-Aug-25 A | 2026-04-20 | 2026-11-05 | 2026-11-06 | 05-Aug-25 A | 2026-02-23
A1-PM-HSD-0029 | S-029-COSHH Assessments | 01-Aug-25 A | 25-Sep-25 A | 2026-11-05 | 2026-11-05 | 01-Aug-25 A | 25-Sep-25 A
A1-PM-HSD-0030 | S-030-Risk Assessment | 21-Jun-25 A | 12-Jul-25 A | 2026-10-22 | 2026-10-22 | 21-Jun-25 A | 12-Jul-25 A
A1-PM-HSD-0031 | S-031-Process Philosophies & HSE Plan | 14-Jul-25 A | 13-Aug-25 A | 2027-02-09 | 2027-02-09 | 14-Jul-25 A | 13-Aug-25 A
A1-PM-HSD-0032 | S-032-Philosophies | 14-Aug-25 A | 19-Aug-25 A | 2026-10-22 | 2026-10-22 | 14-Aug-25 A | 19-Aug-25 A
A1-PM-HSD-0033 | S-033-Data sheets (ALL Type of Safety Data sheets) | 20-Aug-25 A | 26-Aug-25 A | 2026-10-22 | 2026-10-22 | 20-Aug-25 A | 26-Aug-25 A
A1-PM-HSD-0034 | S-034-Specifications | 21-Jun-25 A | 12-Jul-25 A | 2026-10-22 | 2026-10-22 | 21-Jun-25 A | 12-Jul-25 A
A1-PM-HSD-0035 | S-035-Ergonomic Study/ Human Factor Engineering / Assessment | 02-Aug-25 A | 2026-04-21 | 2026-10-22 | 2026-10-26 | 02-Aug-25 A | 2026-02-24
A1-PM-HSD-0036 | S-036-Safety Equipment and safety Routes Layout | 04-Aug-25 A | 2026-04-20 | 2026-10-22 | 2026-10-23 | 04-Aug-25 A | 2026-02-23
A1-PM-HSD-0037 | S-037-PHSER and Close Out Report | 2026-04-21 | 2026-04-27 | 2026-10-26 | 2026-10-30 | 2026-02-24 | 2026-03-02
A1-PM-HSD-0038 | S-038-List of Applicable Regulatory Requirements | 2026-04-28 | 2026-05-04 | 2026-11-02 | 2026-11-06 | 2026-03-03 | 2026-03-09
A1-PM-HSD-0039 | S-039-Waste Management Plan | 25-May-25 A | 06-Jan-26 A | 2026-06-22 | 2026-06-22 | 25-May-25 A | 06-Jan-26 A
A1-PM-HSD-0040 | S-040-HSEIA Screening/ HSEIA Report/ HSEIA Dossier | 2026-06-09 | 2026-06-16 | 2026-11-02 | 2026-11-06 | 2026-04-14 | 2026-04-21
A1-PM-HSD-0041 | S-041-HSE deliverables as per HSE-RM-ST02 EPC deliverable requirements; not limited to : Building Fire and Safety revie | 01-Aug-25 A | 2026-06-16 | 2026-11-05 | 2026-11-06 | 01-Aug-25 A | 2026-04-21
HSEStudies |  | 01-May-25 A | 2026-11-13 | 2026-06-11 | 2027-03-23 | 01-May-25 A | 2026-09-25
HAZID/ENVID/OHID |  | 01-May-25 A | 2026-05-11 | 2026-06-11 | 2026-10-30 | 01-May-25 A | 2026-03-16
A58780 | HAZID / ENVID / OHID Workshop | 01-May-25 A | 10-May-25 A | 2026-06-11 | 2026-06-11 | 01-May-25 A | 10-May-25 A
A58790 | HAZID / ENVID / OHID /_RCC | 26-May-25 A | 01-Sep-25 A | 2026-10-08 | 2026-10-08 | 26-May-25 A | 01-Sep-25 A
A58800 | HAZID / ENVID / OHID /_IFA | 02-Sep-25 A | 08-Sep-25 A | 2026-10-08 | 2026-10-08 | 02-Sep-25 A | 08-Sep-25 A
A58810 | HAZID / ENVID / OHID /_RCA | 15-Dec-25 A | 22-Dec-25 A | 2026-10-08 | 2026-10-08 | 15-Dec-25 A | 22-Dec-25 A
A58820 | HAZID / ENVID / OHID /_IFD/IFC | 2026-04-17 | 2026-05-11 | 2026-10-08 | 2026-10-30 | 2026-02-20 | 2026-03-16
A60330 | HAZID / ENVID / OHID /_IFR | 11-May-25 A | 20-May-25 A | 2026-10-08 | 2026-10-08 | 11-May-25 A | 20-May-25 A
InherentSaferDesignReview |  | 23-Jul-25 A | 2026-06-03 | 2027-02-04 | 2027-03-23 | 23-Jul-25 A | 2026-04-08
A59430 | Inherent Safer Design Review Preparation | 23-Jul-25 A | 31-Jul-25 A | 2027-02-04 | 2027-02-04 | 23-Jul-25 A | 31-Jul-25 A
A59440 | Inherent Safer Design Review_RCC | 28-Aug-25 A | 04-Sep-25 A | 2027-02-04 | 2027-02-04 | 28-Aug-25 A | 04-Sep-25 A
A59450 | Inherent Safer Design Review_IFA | 05-Sep-25 A | 11-Sep-25 A | 2027-02-04 | 2027-02-04 | 05-Sep-25 A | 11-Sep-25 A
A59460 | Inherent Safer Design Review_RCA | 2026-04-17 | 2026-05-11 | 2027-02-04 | 2027-03-01 | 2026-02-20 | 2026-03-16
A59470 | Inherent Safer Design Review_IFD/IFC | 2026-05-11 | 2026-06-03 | 2027-03-01 | 2027-03-23 | 2026-03-16 | 2026-04-08
A60460 | Inherent Safer Design Review_IFR | 01-Aug-25 A | 28-Aug-25 A | 2027-02-04 | 2027-02-04 | 01-Aug-25 A | 28-Aug-25 A
Bow-tieDevelopment&HSECriticalEquipment&SystemsandPerformanceStandards |  | 25-Jul-25 A | 2026-06-03 | 2026-06-11 | 2026-10-30 | 25-Jul-25 A | 2026-04-08
A59280 | Bow-tie Development & HSE Critical Equipment & Systems and Performance Standards_Workshop | 25-Jul-25 A | 31-Jul-25 A | 2026-06-11 | 2026-06-11 | 25-Jul-25 A | 31-Jul-25 A
A59290 | Bow-tie Development & HSE Critical Equipment & Systems and Performance Standards_RCC | 26-Aug-25 A | 04-Sep-25 A | 2026-09-15 | 2026-09-15 | 26-Aug-25 A | 04-Sep-25 A
A59300 | Bow-tie Development & HSE Critical Equipment & Systems and Performance Standards_IFA | 05-Sep-25 A | 11-Sep-25 A | 2026-09-15 | 2026-09-15 | 05-Sep-25 A | 11-Sep-25 A
A59310 | Bow-tie Development & HSE Critical Equipment & Systems and Performance Standards_RCA | 2026-04-17 | 2026-05-11 | 2026-09-15 | 2026-10-08 | 2026-02-20 | 2026-03-16
A59320 | Bow-tie Development & HSE Critical Equipment & Systems and Performance Standards_IFD/IFC | 2026-05-11 | 2026-06-03 | 2026-10-08 | 2026-10-30 | 2026-03-16 | 2026-04-08
A60430 | Bow-tie Development & HSE Critical Equipment & Systems and Performance Standards_IFR | 01-Aug-25 A | 25-Aug-25 A | 2026-09-15 | 2026-09-15 | 01-Aug-25 A | 25-Aug-25 A
HSECESandPerformanceStandards |  | 23-Jul-25 A | 2026-07-21 | 2026-12-18 | 2027-03-23 | 23-Jul-25 A | 2026-05-26
A61970 | HSE Critical Equipment & Systems and Performance Standards_Preparation | 23-Jul-25 A | 31-Jul-25 A | 2026-12-18 | 2026-12-18 | 23-Jul-25 A | 31-Jul-25 A
A61980 | HSE Critical Equipment & Systems and Performance Standards_IFR | 01-Aug-25 A | 28-Aug-25 A | 2026-12-18 | 2026-12-18 | 01-Aug-25 A | 28-Aug-25 A
A61990 | HSE Critical Equipment & Systems and Performance Standards_RCC | 2026-04-17 | 2026-05-11 | 2026-12-18 | 2027-01-12 | 2026-02-20 | 2026-03-16
A62000 | HSE Critical Equipment & Systems and Performance Standards_IFA | 2026-05-11 | 2026-06-03 | 2027-01-12 | 2027-02-04 | 2026-03-16 | 2026-04-08
A62010 | HSE Critical Equipment & Systems and Performance Standards_RCA | 2026-06-03 | 2026-06-26 | 2027-02-04 | 2027-03-01 | 2026-04-08 | 2026-05-01
A62020 | HSE Critical Equipment & Systems and Performance Standards_IFD/IFC | 2026-06-26 | 2026-07-21 | 2027-03-01 | 2027-03-23 | 2026-05-01 | 2026-05-26
HAZOP |  | 01-Jul-25 A | 22-Sep-25 A | 2026-06-15 | 2026-06-22 | 01-Jul-25 A | 22-Sep-25 A
A62030 | HAZOP_Workshop | 01-Jul-25 A | 11-Jul-25 A | 2026-06-15 | 2026-06-15 | 01-Jul-25 A | 11-Jul-25 A
A62040 | HAZOP_IFR | 12-Jul-25 A | 25-Aug-25 A | 2026-06-22 | 2026-06-22 | 12-Jul-25 A | 25-Aug-25 A
A62050 | HAZOP_RCC | 26-Aug-25 A | 01-Sep-25 A | 2026-06-22 | 2026-06-22 | 26-Aug-25 A | 01-Sep-25 A
A62060 | HAZOP_IFA | 02-Sep-25 A | 08-Sep-25 A | 2026-06-22 | 2026-06-22 | 02-Sep-25 A | 08-Sep-25 A
A62070 | HAZOP_RCA | 09-Sep-25 A | 15-Sep-25 A | 2026-06-22 | 2026-06-22 | 09-Sep-25 A | 15-Sep-25 A
A62080 | HAZOP_IFD/IFC | 16-Sep-25 A | 22-Sep-25 A | 2026-06-22 | 2026-06-22 | 16-Sep-25 A | 22-Sep-25 A
SIL |  | 15-Aug-25 A | 25-Sep-25 A | 2026-06-15 | 2026-06-22 | 15-Aug-25 A | 25-Sep-25 A
A23200 | SIL Review Workshop | 15-Aug-25 A | 17-Aug-25 A | 2026-06-15 | 2026-06-15 | 15-Aug-25 A | 17-Aug-25 A
A23210 | Issue for Company Approval | 05-Sep-25 A | 11-Sep-25 A | 2026-06-22 | 2026-06-22 | 05-Sep-25 A | 11-Sep-25 A
A23220 | Issue for Construction | 12-Sep-25 A | 25-Sep-25 A | 2026-06-22 | 2026-06-22 | 12-Sep-25 A | 25-Sep-25 A
A60510 | Issue for Company Review | 18-Aug-25 A | 28-Aug-25 A | 2026-06-22 | 2026-06-22 | 18-Aug-25 A | 28-Aug-25 A
FireandExplosionRiskAssessment(FERA) |  | 01-Aug-25 A | 2026-06-09 | 2026-09-09 | 2026-10-30 | 01-Aug-25 A | 2026-04-14
A59480 | Fire and Explosion Risk Assessment (FERA)_Preparation | 01-Aug-25 A | 20-Aug-25 A | 2026-09-09 | 2026-09-09 | 01-Aug-25 A | 20-Aug-25 A
A59490 | Fire and Explosion Risk Assessment (FERA)_RCC | 2026-04-17 | 2026-05-08 | 2026-09-09 | 2026-10-01 | 2026-02-20 | 2026-03-13
A59500 | Fire and Explosion Risk Assessment (FERA)_IFA | 2026-05-08 | 2026-05-14 | 2026-10-01 | 2026-10-06 | 2026-03-13 | 2026-03-19
A59510 | Fire and Explosion Risk Assessment (FERA)_RCA | 2026-05-14 | 2026-06-04 | 2026-10-07 | 2026-10-28 | 2026-03-19 | 2026-04-09
A59520 | Fire and Explosion Risk Assessment (FERA)_IFD/IFC | 2026-06-04 | 2026-06-09 | 2026-10-28 | 2026-10-30 | 2026-04-09 | 2026-04-14
A60470 | Fire and Explosion Risk Assessment (FERA)_IFR | 22-Aug-25 A | 31-Oct-25 A | 2026-09-09 | 2026-09-09 | 22-Aug-25 A | 31-Oct-25 A
QRA |  | 07-Jul-25 A | 2026-06-09 | 2026-06-11 | 2026-10-30 | 07-Jul-25 A | 2026-04-14
A60590 | Workshop - QRA | 07-Jul-25 A | 15-Jul-25 A | 2026-06-11 | 2026-06-11 | 07-Jul-25 A | 15-Jul-25 A
A60600 | QRA Report_IFR | 16-Jul-25 A | 28-Aug-25 A | 2026-09-09 | 2026-09-09 | 16-Jul-25 A | 28-Aug-25 A
A60610 | QRA Report_RCC | 2026-04-17 | 2026-05-08 | 2026-09-09 | 2026-10-01 | 2026-02-20 | 2026-03-13
A60620 | QRA Report_IFA | 2026-05-08 | 2026-05-14 | 2026-10-01 | 2026-10-06 | 2026-03-13 | 2026-03-19
A60630 | QRA Report_RCA | 2026-05-14 | 2026-06-04 | 2026-10-07 | 2026-10-28 | 2026-03-19 | 2026-04-09
A60640 | QRA Report_IFD/IFC | 2026-06-04 | 2026-06-09 | 2026-10-28 | 2026-10-30 | 2026-04-09 | 2026-04-14
BRA |  | 07-Jul-25 A | 2026-06-09 | 2027-01-29 | 2027-03-23 | 07-Jul-25 A | 2026-04-14
A23290 | Workshop - BRA | 07-Jul-25 A | 15-Jul-25 A | 2027-01-29 | 2027-01-29 | 07-Jul-25 A | 15-Jul-25 A
A60540 | BRA Report_IFR | 16-Jul-25 A | 28-Aug-25 A | 2027-01-29 | 2027-01-29 | 16-Jul-25 A | 28-Aug-25 A
A60550 | BRA Report_RCC | 2026-04-17 | 2026-05-08 | 2027-01-29 | 2027-02-22 | 2026-02-20 | 2026-03-13
A60560 | BRA Report_IFA | 2026-05-08 | 2026-05-14 | 2027-02-22 | 2027-02-25 | 2026-03-13 | 2026-03-19
A60570 | BRA Report_RCA | 2026-05-14 | 2026-06-04 | 2027-02-26 | 2027-03-19 | 2026-03-19 | 2026-04-09
A60580 | BRA Report_IFD/IFC | 2026-06-04 | 2026-06-09 | 2027-03-19 | 2027-03-23 | 2026-04-09 | 2026-04-14
EscapeEvacuationandRescueAssessment(EERA) |  | 01-Aug-25 A | 2026-06-09 | 2026-09-09 | 2026-10-30 | 01-Aug-25 A | 2026-04-14
A59530 | Escape Evacuation and Rescue Assessment (EERA)_Preparation | 01-Aug-25 A | 15-Aug-25 A | 2026-09-09 | 2026-09-09 | 01-Aug-25 A | 15-Aug-25 A
A59540 | Escape Evacuation and Rescue Assessment (EERA)_RCC | 2026-04-17 | 2026-05-08 | 2026-09-09 | 2026-10-01 | 2026-02-20 | 2026-03-13
A59550 | Escape Evacuation and Rescue Assessment (EERA)_IFA | 2026-05-08 | 2026-05-14 | 2026-10-01 | 2026-10-06 | 2026-03-13 | 2026-03-19
A59560 | Escape Evacuation and Rescue Assessment (EERA)_RCA | 2026-05-14 | 2026-06-04 | 2026-10-07 | 2026-10-28 | 2026-03-19 | 2026-04-09
A59570 | Escape Evacuation and Rescue Assessment (EERA)_IFD/IFC | 2026-06-04 | 2026-06-09 | 2026-10-28 | 2026-10-30 | 2026-04-09 | 2026-04-14
A60480 | Escape Evacuation and Rescue Assessment (EERA)_IFR | 16-Aug-25 A | 31-Oct-25 A | 2026-09-09 | 2026-09-09 | 16-Aug-25 A | 31-Oct-25 A
EmergencySystemsSurvivabilityAnalysis(ESSA) |  | 01-Aug-25 A | 2026-06-09 | 2026-09-09 | 2026-10-30 | 01-Aug-25 A | 2026-04-14
A58830 | Emergency Systems Survivability Analysis (ESSA)_IFR | 18-Aug-25 A | 31-Oct-25 A | 2026-09-09 | 2026-09-09 | 18-Aug-25 A | 31-Oct-25 A
A58840 | Emergency Systems Survivability Analysis (ESSA)_RCC | 2026-04-17 | 2026-05-08 | 2026-09-09 | 2026-10-01 | 2026-02-20 | 2026-03-13
A58850 | Emergency Systems Survivability Analysis (ESSA)_IFA | 2026-05-08 | 2026-05-14 | 2026-10-01 | 2026-10-06 | 2026-03-13 | 2026-03-19
A58860 | Emergency Systems Survivability Analysis (ESSA)_RCA | 2026-05-14 | 2026-06-04 | 2026-10-07 | 2026-10-28 | 2026-03-19 | 2026-04-09
A58870 | Emergency Systems Survivability Analysis (ESSA)_IFD/IFC | 2026-06-04 | 2026-06-09 | 2026-10-28 | 2026-10-30 | 2026-04-09 | 2026-04-14
A60340 | Emergency Systems Survivability Analysis (ESSA)_Preparation | 01-Aug-25 A | 15-Aug-25 A | 2026-09-09 | 2026-09-09 | 01-Aug-25 A | 15-Aug-25 A
RiskReductionALARPWorkshop |  | 28-Jul-25 A | 2026-06-10 | 2027-01-28 | 2027-03-23 | 28-Jul-25 A | 2026-04-15
A59130 | Risk Reduction ALARP Workshop | 28-Jul-25 A | 07-Aug-25 A | 2027-01-28 | 2027-01-28 | 28-Jul-25 A | 07-Aug-25 A
A59140 | Risk Reduction ALARP Workshop_Report RCC | 2026-04-24 | 2026-05-11 | 2027-02-05 | 2027-02-22 | 2026-02-27 | 2026-03-16
A59150 | Risk Reduction ALARP Workshop Report_IFA | 2026-05-11 | 2026-05-15 | 2027-02-22 | 2027-02-25 | 2026-03-16 | 2026-03-20
A59160 | Risk Reduction ALARP Workshop Report_RCA | 2026-05-15 | 2026-06-05 | 2027-02-26 | 2027-03-19 | 2026-03-20 | 2026-04-10
A59170 | Risk Reduction ALARP Workshop Report_IFD/IFC | 2026-06-08 | 2026-06-10 | 2027-03-19 | 2027-03-23 | 2026-04-13 | 2026-04-15
A60400 | Risk Reduction ALARP Workshop Report_IFR | 2026-04-17 | 2026-04-24 | 2027-01-28 | 2027-02-05 | 2026-02-20 | 2026-02-27
AirEmissionDispersionAssessment |  | 01-Aug-25 A | 2026-06-09 | 2026-09-09 | 2026-10-30 | 01-Aug-25 A | 2026-04-14
A59080 | Air Emission Dispersion Assessment_IFR | 16-Aug-25 A | 25-Sep-25 A | 2026-09-09 | 2026-09-09 | 16-Aug-25 A | 25-Sep-25 A
A59090 | Air Emission Dispersion Assessment_RCC | 2026-04-17 | 2026-05-08 | 2026-09-09 | 2026-10-01 | 2026-02-20 | 2026-03-13
A59100 | Air Emission Dispersion Assessment_IFA | 2026-05-08 | 2026-05-14 | 2026-10-01 | 2026-10-06 | 2026-03-13 | 2026-03-19
A59110 | Air Emission Dispersion Assessment_RCA | 2026-05-14 | 2026-06-04 | 2026-10-07 | 2026-10-28 | 2026-03-19 | 2026-04-09
A59120 | Air Emission Dispersion Assessment_IFD/IFC | 2026-06-04 | 2026-06-09 | 2026-10-28 | 2026-10-30 | 2026-04-09 | 2026-04-14
A60390 | Air Emission Dispersion Assessment_Preparation | 01-Aug-25 A | 15-Aug-25 A | 2026-09-09 | 2026-09-09 | 01-Aug-25 A | 15-Aug-25 A
NoiseStudy&ContoursReport |  | 01-Aug-25 A | 2026-06-03 | 2026-06-11 | 2026-10-30 | 01-Aug-25 A | 2026-04-08
A62090 | Noise study & control report_Preparation | 01-Aug-25 A | 15-Aug-25 A | 2026-06-11 | 2026-06-11 | 01-Aug-25 A | 15-Aug-25 A
A62100 | Noise study & control report_IFR | 16-Aug-25 A | 25-Sep-25 A | 2026-09-15 | 2026-09-15 | 16-Aug-25 A | 25-Sep-25 A
A62110 | Noise study & control report_RCC | 2026-04-17 | 2026-05-06 | 2026-09-15 | 2026-10-05 | 2026-02-20 | 2026-03-11
A62120 | Noise study & control report_IFA | 2026-05-07 | 2026-05-12 | 2026-10-05 | 2026-10-08 | 2026-03-12 | 2026-03-17
A62130 | Noise study & control report_RCA | 2026-05-12 | 2026-06-01 | 2026-10-08 | 2026-10-28 | 2026-03-17 | 2026-04-06
A62140 | Noise study & control report_IFD/IFC | 2026-06-01 | 2026-06-03 | 2026-10-28 | 2026-10-30 | 2026-04-06 | 2026-04-08
BestAvailableTechniquesStudy(BAT) |  | 01-Aug-25 A | 2026-05-18 | 2026-06-11 | 2026-10-30 | 01-Aug-25 A | 2026-03-23
A58930 | Best Available Techniques Study_IFR | 21-Aug-25 A | 18-Sep-25 A | 2026-06-11 | 2026-06-11 | 21-Aug-25 A | 18-Sep-25 A
A58940 | Best Available Techniques Study_RCC | 21-Aug-25 A | 29-Aug-25 A | 2026-06-16 | 2026-06-16 | 21-Aug-25 A | 29-Aug-25 A
A58950 | Best Available Techniques Study_IFA | 2026-04-17 | 2026-04-22 | 2026-10-01 | 2026-10-06 | 2026-02-20 | 2026-02-25
A58960 | Best Available Techniques Study_RCA | 2026-04-22 | 2026-05-14 | 2026-10-07 | 2026-10-28 | 2026-02-25 | 2026-03-19
A58970 | Best Available Techniques Study_IFD/IFC | 2026-05-14 | 2026-05-18 | 2026-10-28 | 2026-10-30 | 2026-03-19 | 2026-03-23
A60360 | Best Available Techniques Study_Workshop | 01-Aug-25 A | 20-Aug-25 A | 2026-06-11 | 2026-06-11 | 01-Aug-25 A | 20-Aug-25 A
EnergyReviewWorkshop&Report |  | 01-Sep-25 A | 2026-06-16 | 2026-06-16 | 2027-03-23 | 01-Sep-25 A | 2026-04-21
A59380 | Energy Review Workshop | 01-Sep-25 A | 19-Sep-25 A | 2026-06-16 | 2026-06-16 | 01-Sep-25 A | 19-Sep-25 A
A59390 | Energy Review Workshop & Report_RCC | 2026-04-24 | 2026-05-18 | 2027-01-29 | 2027-02-22 | 2026-02-27 | 2026-03-23
A59400 | Energy Review Workshop & Report_IFA | 2026-05-18 | 2026-05-21 | 2027-02-22 | 2027-02-25 | 2026-03-23 | 2026-03-26
A59410 | Energy Review Workshop & Report_RCA | 2026-05-21 | 2026-06-12 | 2027-02-26 | 2027-03-19 | 2026-03-26 | 2026-04-17
A59420 | Energy Review Workshop & Report_IFD/IFC | 2026-06-12 | 2026-06-16 | 2027-03-19 | 2027-03-23 | 2026-04-17 | 2026-04-21
A60450 | Energy Review Workshop & Report_IFR | 2026-04-17 | 2026-04-24 | 2027-01-22 | 2027-01-29 | 2026-02-20 | 2026-02-27
Vent&FlareDispersionandRadiationStudy |  | 01-Oct-25 A | 2026-06-09 | 2026-06-16 | 2027-03-23 | 01-Oct-25 A | 2026-04-14
A59630 | Vent & Flare Dispersion and Radiation Study Preparation ---- | 01-Oct-25 A | 15-Oct-25 A | 2026-06-16 | 2026-06-16 | 01-Oct-25 A | 15-Oct-25 A
A59640 | Vent & Flare Dispersion and Radiation Study_RCC | 2026-04-17 | 2026-05-08 | 2027-01-29 | 2027-02-22 | 2026-02-20 | 2026-03-13
A59650 | Vent & Flare Dispersion and Radiation Study_IFA | 2026-05-08 | 2026-05-14 | 2027-02-22 | 2027-02-25 | 2026-03-13 | 2026-03-19
A59660 | Vent & Flare Dispersion and Radiation Study_RCA | 2026-05-14 | 2026-06-04 | 2027-02-26 | 2027-03-19 | 2026-03-19 | 2026-04-09
A59670 | Vent & Flare Dispersion and Radiation Study_IFD/IFC | 2026-06-04 | 2026-06-09 | 2027-03-19 | 2027-03-23 | 2026-04-09 | 2026-04-14
A60500 | Vent & Flare Dispersion and Radiation Study_IFR | 16-Oct-25 A | 31-Oct-25 A | 2026-06-16 | 2026-06-16 | 16-Oct-25 A | 31-Oct-25 A
EnvironmentImpactAssessment |  | 28-Aug-25 A | 2026-06-03 | 2026-09-15 | 2026-10-30 | 28-Aug-25 A | 2026-04-08
A59030 | Environment Impact Assessment_IFR | 06-Sep-25 A | 18-Sep-25 A | 2026-09-15 | 2026-09-15 | 06-Sep-25 A | 18-Sep-25 A
A59040 | Environment Impact Assessment_RCC | 2026-04-17 | 2026-05-06 | 2026-09-15 | 2026-10-05 | 2026-02-20 | 2026-03-11
A59050 | Environment Impact Assessment_IFA | 2026-05-07 | 2026-05-12 | 2026-10-05 | 2026-10-08 | 2026-03-12 | 2026-03-17
A59060 | Environment Impact Assessment_RCA | 2026-05-12 | 2026-06-01 | 2026-10-08 | 2026-10-28 | 2026-03-17 | 2026-04-06
A59070 | Environment Impact Assessment_IFD/IFC | 2026-06-01 | 2026-06-03 | 2026-10-28 | 2026-10-30 | 2026-04-06 | 2026-04-08
A60380 | Environment Impact Assessment_Workshop ---- | 28-Aug-25 A | 05-Sep-25 A | 2026-09-15 | 2026-09-15 | 28-Aug-25 A | 05-Sep-25 A
ErgonomicsandHumanFactorEngineeringStudy |  | 25-Aug-25 A | 2026-08-26 | 2026-11-12 | 2027-03-23 | 25-Aug-25 A | 2026-07-01
A58730 | Ergonomics and Human Factor Engineering Study_IFR | 2026-04-17 | 2026-04-24 | 2026-11-12 | 2026-11-20 | 2026-02-20 | 2026-02-27
A58740 | Ergonomics and Human Factor Engineering Study_RCC | 2026-04-24 | 2026-05-28 | 2026-11-20 | 2026-12-23 | 2026-02-27 | 2026-04-02
A58750 | Ergonomics and Human Factor Engineering Study_IFA | 2026-05-28 | 2026-06-30 | 2026-12-23 | 2027-01-26 | 2026-04-02 | 2026-05-05
A58760 | Ergonomics and Human Factor Engineering Study_RCA | 2026-06-30 | 2026-08-03 | 2027-01-26 | 2027-03-01 | 2026-05-05 | 2026-06-08
A58770 | Ergonomics and Human Factor Engineering Study_IFD/IFC | 2026-08-03 | 2026-08-26 | 2027-03-01 | 2027-03-23 | 2026-06-08 | 2026-07-01
A60320 | Ergonomics and Human Factor Engineering Study Workshop | 25-Aug-25 A | 01-Sep-25 A | 2026-11-12 | 2026-11-12 | 25-Aug-25 A | 01-Sep-25 A
DroppedObjectsStudy(DOS) |  | 2026-04-17 | 2026-07-14 | 2026-12-25 | 2027-03-23 | 2026-02-20 | 2026-05-19
A58880 | Dropped Objects Study (DOS)_IFR | 2026-04-24 | 2026-05-22 | 2027-01-01 | 2027-01-29 | 2026-02-27 | 2026-03-27
A58890 | Dropped Objects Study (DOS)_RCC | 2026-05-22 | 2026-06-15 | 2027-01-29 | 2027-02-22 | 2026-03-27 | 2026-04-20
A58900 | Dropped Objects Study (DOS)_IFA | 2026-06-15 | 2026-06-18 | 2027-02-22 | 2027-02-25 | 2026-04-20 | 2026-04-23
A58910 | Dropped Objects Study (DOS)_RCA | 2026-06-19 | 2026-07-10 | 2027-02-26 | 2027-03-19 | 2026-04-24 | 2026-05-15
A58920 | Dropped Objects Study (DOS)_IFD/IFC | 2026-07-10 | 2026-07-14 | 2027-03-19 | 2027-03-23 | 2026-05-15 | 2026-05-19
A60350 | Dropped Objects Study (DOS)_Workshop | 2026-04-17 | 2026-04-24 | 2026-12-25 | 2027-01-01 | 2026-02-20 | 2026-02-27
3DF&Gmappingstudy |  | 2026-04-17 | 2026-06-24 | 2027-01-14 | 2027-03-23 | 2026-02-20 | 2026-04-29
A58980 | 3D F&G mapping study_IFR | 2026-04-24 | 2026-05-04 | 2027-01-22 | 2027-01-29 | 2026-02-27 | 2026-03-09
A58990 | 3D F&G mapping study_RCC | 2026-05-04 | 2026-05-25 | 2027-01-29 | 2027-02-22 | 2026-03-09 | 2026-03-30
A59000 | 3D F&G mapping study_IFA | 2026-05-26 | 2026-05-29 | 2027-02-22 | 2027-02-25 | 2026-03-31 | 2026-04-03
A59010 | 3D F&G mapping study_RCA | 2026-05-29 | 2026-06-22 | 2027-02-26 | 2027-03-19 | 2026-04-03 | 2026-04-27
A59020 | 3D F&G mapping study_IFD/IFC | 2026-06-22 | 2026-06-24 | 2027-03-19 | 2027-03-23 | 2026-04-27 | 2026-04-29
A60370 | 3D F&G mapping study_Preparation | 2026-04-17 | 2026-04-24 | 2027-01-14 | 2027-01-22 | 2026-02-20 | 2026-02-27
E-HAZOP |  | 25-Aug-25 A | 2026-06-16 | 2026-06-11 | 2027-03-23 | 25-Aug-25 A | 2026-04-21
A62150 | E-HAZOP_Workshop | 25-Aug-25 A | 01-Sep-25 A | 2026-06-11 | 2026-06-11 | 25-Aug-25 A | 01-Sep-25 A
A62160 | E-HAZOP_IFR | 2026-04-17 | 2026-04-24 | 2027-01-22 | 2027-01-29 | 2026-02-20 | 2026-02-27
A62170 | E-HAZOP_RCC | 2026-04-24 | 2026-05-18 | 2027-01-29 | 2027-02-22 | 2026-02-27 | 2026-03-23
A62180 | E-HAZOP_IFA | 2026-05-18 | 2026-05-21 | 2027-02-22 | 2027-02-25 | 2026-03-23 | 2026-03-26
A62190 | E-HAZOP_RCA | 2026-05-21 | 2026-06-12 | 2027-02-26 | 2027-03-19 | 2026-03-26 | 2026-04-17
A62200 | E-HAZOP_IFD/IFC | 2026-06-12 | 2026-06-16 | 2027-03-19 | 2027-03-23 | 2026-04-17 | 2026-04-21
ConstructabilityReview |  | 27-Aug-25 A | 2026-05-18 | 2027-02-22 | 2027-03-23 | 27-Aug-25 A | 2026-03-23
A59180 | Constructability Review Workshop | 27-Aug-25 A | 27-Aug-25 A | 2027-02-22 | 2027-02-22 | 27-Aug-25 A | 27-Aug-25 A
A59190 | Constructability Review_RCC | 01-Dec-25 A | 10-Dec-25 A | 2027-02-22 | 2027-02-22 | 01-Dec-25 A | 10-Dec-25 A
A59200 | Constructability Review_IFA | 2026-04-17 | 2026-04-22 | 2027-02-22 | 2027-02-25 | 2026-02-20 | 2026-02-25
A59210 | Constructability Review_RCA | 2026-04-22 | 2026-05-14 | 2027-02-26 | 2027-03-19 | 2026-02-25 | 2026-03-19
A59220 | Constructability Review_IFD/IFC | 2026-05-14 | 2026-05-18 | 2027-03-19 | 2027-03-23 | 2026-03-19 | 2026-03-23
A60410 | Constructability Review_IFR | 17-Nov-25 A | 30-Nov-25 A | 2027-02-22 | 2027-02-22 | 17-Nov-25 A | 30-Nov-25 A
SIMPOS |  | 25-Aug-25 A | 2026-05-18 | 2027-02-22 | 2027-03-23 | 25-Aug-25 A | 2026-03-23
A59680 | SIMOPS Workshop | 25-Aug-25 A | 28-Aug-25 A | 2027-02-22 | 2027-02-22 | 25-Aug-25 A | 28-Aug-25 A
A59690 | SIMOPS Report_RCC | 08-Dec-25 A | 16-Dec-25 A | 2027-02-22 | 2027-02-22 | 08-Dec-25 A | 16-Dec-25 A
A59700 | SIMOPS Report_IFA | 2026-04-17 | 2026-04-22 | 2027-02-22 | 2027-02-25 | 2026-02-20 | 2026-02-25
A59710 | SIMOPS Report_RCA | 2026-04-22 | 2026-05-14 | 2027-02-26 | 2027-03-19 | 2026-02-25 | 2026-03-19
A59720 | SIMOPS Report_IFD/IFC | 2026-05-14 | 2026-05-18 | 2027-03-19 | 2027-03-23 | 2026-03-19 | 2026-03-23
A60520 | SIMOPS Report_IFR | 11-Nov-25 A | 30-Nov-25 A | 2027-02-22 | 2027-02-22 | 11-Nov-25 A | 30-Nov-25 A
HSEIA |  | 24-Dec-25 A | 2026-05-21 | 2026-06-22 | 2027-03-23 | 24-Dec-25 A | 2026-03-26
A61370 | HSEIA Report Preparation | 24-Dec-25 A | 31-Dec-25 A | 2026-06-22 | 2026-06-22 | 24-Dec-25 A | 31-Dec-25 A
A61380 | HSEIA Report_IFR | 01-Jan-26 A | 06-Jan-26 A | 2026-06-22 | 2026-06-22 | 01-Jan-26 A | 06-Jan-26 A
A61390 | HSEIA Report_RCC | 07-Jan-26 A | 23-Jan-26 A | 2027-03-01 | 2027-03-01 | 07-Jan-26 A | 23-Jan-26 A
A61400 | HSEIA Report_IFA | 2026-04-27 | 2026-04-30 | 2027-03-09 | 2027-03-12 | 2026-03-02 | 2026-03-05
A61410 | HSEIA Report_RCA | 2026-04-30 | 2026-05-07 | 2027-03-12 | 2027-03-19 | 2026-03-05 | 2026-03-12
A61420 | HSEIA Report_IFD/IFC | 2026-05-07 | 2026-05-11 | 2027-03-19 | 2027-03-23 | 2026-03-12 | 2026-03-16
A61840 | HSEIA Report ADNOC Approval | 2026-04-17 | 2026-05-21 | 2026-06-22 | 2026-07-24 | 2026-02-20 | 2026-03-26
A62500 | Assesemnt on new requirements by COMPANY | 13-Feb-26 A | 2026-04-24 | 2027-03-01 | 2027-03-09 | 13-Feb-26 A | 2026-02-27
PHSERIII |  | 2026-04-24 | 2026-07-01 | 2026-09-01 | 2026-11-09 | 2026-03-06 | 2026-05-13
A59330 | PHSER III_Workshop | 2026-04-24 | 2026-05-01 | 2026-09-01 | 2026-09-09 | 2026-03-06 | 2026-03-13
A59340 | PHSER III_RCC | 2026-05-11 | 2026-06-01 | 2026-09-17 | 2026-10-08 | 2026-03-23 | 2026-04-14
A59350 | PHSER III_IFA | 2026-06-02 | 2026-06-05 | 2026-10-08 | 2026-10-14 | 2026-04-14 | 2026-04-17
A59360 | PHSER III_RCA | 2026-06-05 | 2026-06-29 | 2026-10-14 | 2026-11-04 | 2026-04-17 | 2026-05-11
A59370 | PHSER III_IFD/IFC | 2026-06-29 | 2026-07-01 | 2026-11-05 | 2026-11-09 | 2026-05-11 | 2026-05-13
A60440 | PHSER III_IFR | 2026-05-01 | 2026-05-11 | 2026-09-09 | 2026-09-17 | 2026-03-13 | 2026-03-23
PHSERIV |  | 2026-07-01 | 2026-09-07 | 2026-11-09 | 2027-01-14 | 2026-05-13 | 2026-07-20
A61850 | PHSER IV_Workshop | 2026-07-01 | 2026-07-08 | 2026-11-09 | 2026-11-16 | 2026-05-13 | 2026-05-21
A61860 | PHSER IV_RCC | 2026-07-16 | 2026-08-07 | 2026-11-24 | 2026-12-16 | 2026-05-28 | 2026-06-19
A61870 | PHSER IV_IFA | 2026-08-07 | 2026-08-12 | 2026-12-16 | 2026-12-21 | 2026-06-19 | 2026-06-24
A61880 | PHSER IV_RCA | 2026-08-12 | 2026-09-03 | 2026-12-21 | 2027-01-12 | 2026-06-24 | 2026-07-16
A61890 | PHSER IV_IFD/IFC | 2026-09-03 | 2026-09-07 | 2027-01-12 | 2027-01-14 | 2026-07-16 | 2026-07-20
A61900 | PHSER IV_IFR | 2026-07-09 | 2026-07-16 | 2026-11-16 | 2026-11-24 | 2026-05-21 | 2026-05-28
PHSERV |  | 2026-09-07 | 2026-11-13 | 2027-01-14 | 2027-03-23 | 2026-07-20 | 2026-09-25
A61910 | PHSER V_Workshop | 2026-09-07 | 2026-09-15 | 2027-01-14 | 2027-01-22 | 2026-07-20 | 2026-07-28
A61920 | PHSER V_RCC | 2026-09-23 | 2026-10-14 | 2027-01-29 | 2027-02-22 | 2026-08-05 | 2026-08-26
A61930 | PHSER V_FA | 2026-10-14 | 2026-10-20 | 2027-02-22 | 2027-02-25 | 2026-08-26 | 2026-09-01
A61940 | PHSER V_RCA | 2026-10-20 | 2026-11-10 | 2027-02-26 | 2027-03-19 | 2026-09-01 | 2026-09-22
A61950 | PHSER V_IFD/IFC | 2026-11-10 | 2026-11-13 | 2027-03-19 | 2027-03-23 | 2026-09-23 | 2026-09-25
A61960 | PHSER V_IFR | 2026-09-15 | 2026-09-22 | 2027-01-22 | 2027-01-29 | 2026-07-28 | 2026-08-05
QA/QCManagement |  | 12-May-25 A | 2026-08-06 | 2026-06-09 | 2027-09-20 | 12-May-25 A | 2026-06-11
QAQCDeliverables |  | 25-May-25 A | 2026-08-06 | 2026-06-09 | 2027-06-22 | 25-May-25 A | 2026-06-11
A1-PM-QCD-0001 | PCQ-001-Inspection Record | 08-Aug-25 A | 2026-04-23 | 2026-06-09 | 2026-06-15 | 08-Aug-25 A | 2026-02-26
A1-PM-QCD-0002 | PCQ-002-Inspection Check List | 08-Aug-25 A | 2026-05-04 | 2027-03-12 | 2027-03-18 | 08-Aug-25 A | 2026-03-09
A1-PM-QCD-0003 | PCQ-003-Test Certificate | 14-Aug-25 A | 2026-05-13 | 2027-03-23 | 2027-03-29 | 14-Aug-25 A | 2026-03-18
A1-PM-QCD-0004 | PCQ-004-Inspection and Test Plan Vendor | 14-Aug-25 A | 2026-05-22 | 2027-04-01 | 2027-04-07 | 14-Aug-25 A | 2026-03-27
A1-PM-QCD-0005 | PCQ-005-Inspection and Test Plan Site | 16-Jun-25 A | 2026-06-02 | 2027-04-16 | 2027-04-16 | 16-Jun-25 A | 2026-04-07
A1-PM-QCD-0006 | PCQ-006-Inspection and Test Plan | 16-Jun-25 A | 2026-06-11 | 2027-04-27 | 2027-04-27 | 16-Jun-25 A | 2026-04-16
A1-PM-QCD-0007 | PCQ-007-Quality Assurance Docs | 15-Aug-25 A | 2026-06-22 | 2027-05-06 | 2027-05-06 | 15-Aug-25 A | 2026-04-27
A1-PM-QCD-0008 | PCQ-008-Inspection Guidelines (Source and Field) | 15-Aug-25 A | 2026-07-01 | 2027-05-17 | 2027-05-17 | 15-Aug-25 A | 2026-05-06
A1-PM-QCD-0009 | PCQ-009-Inspection / Expediting / Reports | 15-Aug-25 A | 2026-07-10 | 2027-05-26 | 2027-05-26 | 15-Aug-25 A | 2026-05-15
A1-PM-QCD-0010 | PCQ-010-Vendor Shop Inspection & Quality Control Plans | 18-Aug-25 A | 2026-07-21 | 2027-06-04 | 2027-06-04 | 18-Aug-25 A | 2026-05-26
A1-PM-QCD-0011 | PCQ-011-Site Contractors Quality Plans | 25-May-25 A | 03-Sep-25 A | 2026-06-16 | 2026-06-16 | 25-May-25 A | 03-Sep-25 A
A1-PM-QCD-0012 | PCQ-012-Worksite Quality Plan | 03-Sep-25 A | 15-Sep-25 A | 2026-12-31 | 2026-12-31 | 03-Sep-25 A | 15-Sep-25 A
A1-PM-QCD-0013 | PCQ-013-Inspection Plan and Schedule | 15-Aug-25 A | 2026-07-30 | 2027-06-15 | 2027-06-15 | 15-Aug-25 A | 2026-06-04
A1-PM-QCD-0014 | PCQ-014-Inspection Release Report | 2026-07-31 | 2026-08-06 | 2027-06-16 | 2027-06-22 | 2026-06-05 | 2026-06-11
QAQCAuditPlan |  | 12-May-25 A | 25-May-25 A | 2027-09-20 | 2027-09-20 | 12-May-25 A | 25-May-25 A
A1-PM-QAP-0001 | QAQC Audit Plan | 12-May-25 A | 25-May-25 A | 2027-09-20 | 2027-09-20 | 12-May-25 A | 25-May-25 A
Contractor'sTemporaryFacilities |  | 20-Jan-25 A | 20-Jan-25 A | 2026-10-08 | 2026-10-08 | 20-Jan-25 A | 20-Jan-25 A
HomeOffice |  | 20-Jan-25 A | 20-Jan-25 A | 2026-10-08 | 2026-10-08 | 20-Jan-25 A | 20-Jan-25 A
A1-PM-CTF-0001 | Home Office Ready for IPMT Moblization |  | 20-Jan-25 A |  | 2026-10-08 |  | 20-Jan-25 A
Others |  | 20-Dec-24 A | 2027-09-20 | 2026-06-16 | 2027-09-20 | 20-Dec-24 A | 2027-07-20
ProjectKeyMilestones |  | 12-Apr-25 A | 2027-09-20 | 2026-06-16 | 2027-09-20 | 12-Apr-25 A | 2027-07-20
A1-PM-PKM-0001 | Turnaround Scope Completion (TA) | 12-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 12-Apr-25 A | 17-May-25 A |  | MS
A1-PM-PKM-0002 | Mechanical Completion (MC) |  | 2027-03-23 |  | 2027-03-23 |  | 2027-01-20 | Start of Commissioning |  | CP | CP
A1-PM-PKM-0003 | Ready for Start-up (RFSU) |  | 2027-06-22 |  | 2027-06-22 |  | 2027-04-21 | End of Commissioning |  | CP | CP
A1-PM-PKM-0004 | Provisional Acceptance Certificate (PAC) |  | 2027-09-20 |  | 2027-09-20 |  | 2027-07-20 | End of Start up |  | CP | CP
WeeklyProgressReport |  | 03-Jan-25 A | 2027-03-30 | 2026-10-08 | 2027-09-20 | 03-Jan-25 A | 2027-02-24
A1-PM-WPR-0001 | Weekly Progress Report Issuance - WPR0001 |  | 03-Jan-25 A |  | 2026-10-08 |  | 03-Jan-25 A
A1-PM-WPR-0002 | Weekly Progress Report Issuance - WPR0002 |  | 10-Jan-25 A |  | 2026-10-08 |  | 10-Jan-25 A
A1-PM-WPR-0003 | Weekly Progress Report Issuance - WPR0003 |  | 17-Jan-25 A |  | 2026-10-08 |  | 17-Jan-25 A
A1-PM-WPR-0004 | Weekly Progress Report Issuance - WPR0004 |  | 24-Jan-25 A |  | 2026-10-08 |  | 24-Jan-25 A
A1-PM-WPR-0005 | Weekly Progress Report Issuance - WPR0005 |  | 31-Jan-25 A |  | 2026-10-08 |  | 31-Jan-25 A
A1-PM-WPR-0006 | Weekly Progress Report Issuance - WPR0006 |  | 07-Feb-25 A |  | 2026-10-08 |  | 07-Feb-25 A
A1-PM-WPR-0007 | Weekly Progress Report Issuance - WPR0007 |  | 14-Feb-25 A |  | 2026-10-08 |  | 14-Feb-25 A
A1-PM-WPR-0008 | Weekly Progress Report Issuance - WPR0008 |  | 21-Feb-25 A |  | 2026-10-08 |  | 21-Feb-25 A
A1-PM-WPR-0009 | Weekly Progress Report Issuance - WPR0009 |  | 28-Feb-25 A |  | 2026-10-08 |  | 28-Feb-25 A
A1-PM-WPR-0010 | Weekly Progress Report Issuance - WPR0010 |  | 06-May-25 A |  | 2026-10-08 |  | 06-May-25 A
A1-PM-WPR-0011 | Weekly Progress Report Issuance - WPR0011 |  | 06-May-25 A |  | 2026-10-08 |  | 06-May-25 A
A1-PM-WPR-0012 | Weekly Progress Report Issuance - WPR0012 |  | 06-May-25 A |  | 2026-10-08 |  | 06-May-25 A
A1-PM-WPR-0013 | Weekly Progress Report Issuance - WPR0013 |  | 06-May-25 A |  | 2026-10-08 |  | 06-May-25 A
A1-PM-WPR-0014 | Weekly Progress Report Issuance - WPR0014 |  | 06-May-25 A |  | 2026-10-08 |  | 06-May-25 A
A1-PM-WPR-0015 | Weekly Progress Report Issuance - WPR0015 |  | 06-May-25 A |  | 2026-10-08 |  | 06-May-25 A
A1-PM-WPR-0016 | Weekly Progress Report Issuance - WPR0016 |  | 18-Apr-25 A |  | 2026-10-08 |  | 18-Apr-25 A
A1-PM-WPR-0017 | Weekly Progress Report Issuance - WPR0017 |  | 09-May-25 A |  | 2026-10-08 |  | 09-May-25 A
A1-PM-WPR-0018 | Weekly Progress Report Issuance - WPR0018 |  | 09-May-25 A |  | 2026-10-08 |  | 09-May-25 A
A1-PM-WPR-0019 | Weekly Progress Report Issuance - WPR0019 |  | 13-May-25 A |  | 2026-10-08 |  | 13-May-25 A
A1-PM-WPR-0020 | Weekly Progress Report Issuance - WPR0020 |  | 21-May-25 A |  | 2026-10-08 |  | 21-May-25 A
A1-PM-WPR-0021 | Weekly Progress Report Issuance - WPR0021 |  | 28-May-25 A |  | 2026-10-08 |  | 28-May-25 A
A1-PM-WPR-0022 | Weekly Progress Report Issuance - WPR0022 |  | 08-Jun-25 A |  | 2026-10-08 |  | 08-Jun-25 A
A1-PM-WPR-0023 | Weekly Progress Report Issuance - WPR0023 |  | 06-Jun-25 A |  | 2026-10-08 |  | 06-Jun-25 A
A1-PM-WPR-0024 | Weekly Progress Report Issuance - WPR0024 |  | 13-Jun-25 A |  | 2026-10-08 |  | 13-Jun-25 A
A1-PM-WPR-0025 | Weekly Progress Report Issuance - WPR0025 |  | 21-Jun-25 A |  | 2026-10-08 |  | 21-Jun-25 A
A1-PM-WPR-0026 | Weekly Progress Report Issuance - WPR0026 |  | 30-Jun-25 A |  | 2026-10-08 |  | 30-Jun-25 A
A1-PM-WPR-0027 | Weekly Progress Report Issuance - WPR0027 |  | 10-Jul-25 A |  | 2026-10-08 |  | 10-Jul-25 A
A1-PM-WPR-0028 | Weekly Progress Report Issuance - WPR0028 |  | 18-Jul-25 A |  | 2026-10-08 |  | 18-Jul-25 A
A1-PM-WPR-0029 | Weekly Progress Report Issuance - WPR0029 |  | 22-Aug-25 A |  | 2026-10-08 |  | 22-Aug-25 A
A1-PM-WPR-0030 | Weekly Progress Report Issuance - WPR0030 |  | 27-Aug-25 A |  | 2026-10-08 |  | 27-Aug-25 A
A1-PM-WPR-0031 | Weekly Progress Report Issuance - WPR0031 |  | 02-Sep-25 A |  | 2026-10-08 |  | 02-Sep-25 A
A1-PM-WPR-0032 | Weekly Progress Report Issuance - WPR0032 |  | 07-Sep-25 A |  | 2026-10-08 |  | 07-Sep-25 A
A1-PM-WPR-0033 | Weekly Progress Report Issuance - WPR0033 |  | 13-Sep-25 A |  | 2026-10-08 |  | 13-Sep-25 A
A1-PM-WPR-0034 | Weekly Progress Report Issuance - WPR0034 |  | 27-Aug-25 A |  | 2026-10-08 |  | 27-Aug-25 A
A1-PM-WPR-0035 | Weekly Progress Report Issuance - WPR0035 |  | 15-Sep-25 A |  | 2026-10-08 |  | 15-Sep-25 A
A1-PM-WPR-0036 | Weekly Progress Report Issuance - WPR0036 |  | 15-Sep-25 A |  | 2026-10-08 |  | 15-Sep-25 A
A1-PM-WPR-0037 | Weekly Progress Report Issuance - WPR0037 |  | 12-Sep-25 A |  | 2026-10-08 |  | 12-Sep-25 A
A1-PM-WPR-0038 | Weekly Progress Report Issuance - WPR0038 |  | 19-Sep-25 A |  | 2026-10-08 |  | 19-Sep-25 A
A1-PM-WPR-0039 | Weekly Progress Report Issuance - WPR0039 |  | 03-Oct-25 A |  | 2026-10-08 |  | 03-Oct-25 A
A1-PM-WPR-0040 | Weekly Progress Report Issuance - WPR0040 |  | 10-Oct-25 A |  | 2026-10-08 |  | 10-Oct-25 A
A1-PM-WPR-0041 | Weekly Progress Report Issuance - WPR0041 |  | 17-Oct-25 A |  | 2026-10-08 |  | 17-Oct-25 A
A1-PM-WPR-0042 | Weekly Progress Report Issuance - WPR0042 |  | 24-Oct-25 A |  | 2026-10-08 |  | 24-Oct-25 A
A1-PM-WPR-0043 | Weekly Progress Report Issuance - WPR0043 |  | 30-Oct-25 A |  | 2026-10-08 |  | 30-Oct-25 A
A1-PM-WPR-0044 | Weekly Progress Report Issuance - WPR0044 |  | 04-Nov-25 A |  | 2026-10-08 |  | 04-Nov-25 A
A1-PM-WPR-0045 | Weekly Progress Report Issuance - WPR0045 |  | 12-Nov-25 A |  | 2026-10-08 |  | 12-Nov-25 A
A1-PM-WPR-0046 | Weekly Progress Report Issuance - WPR0046 |  | 18-Nov-25 A |  | 2026-10-08 |  | 18-Nov-25 A
A1-PM-WPR-0047 | Weekly Progress Report Issuance - WPR0047 |  | 20-Feb-26 A |  | 2026-10-08 |  | 2026-02-20
A1-PM-WPR-0048 | Weekly Progress Report Issuance - WPR0048 |  | 25-Feb-26 A |  | 2026-10-08 |  | 2026-02-25
A1-PM-WPR-0049 | Weekly Progress Report Issuance - WPR0049 |  | 03-Mar-26 A |  | 2026-10-08 |  | 2026-03-03
A1-PM-WPR-0050 | Weekly Progress Report Issuance - WPR0050 |  | 08-Mar-26 A |  | 2026-10-08 |  | 2026-03-08
A1-PM-WPR-0051 | Weekly Progress Report Issuance - WPR0051 |  | 2026-04-17 |  | 2026-10-08 |  | 2026-03-14
A1-PM-WPR-0052 | Weekly Progress Report Issuance - WPR0052 |  | 2026-04-22 |  | 2026-10-14 |  | 2026-03-19
A1-PM-WPR-0053 | Weekly Progress Report Issuance - WPR0053 |  | 2026-04-28 |  | 2026-10-19 |  | 2026-03-25
A1-PM-WPR-0054 | Weekly Progress Report Issuance - WPR0054 |  | 2026-05-03 |  | 2026-10-25 |  | 2026-03-31
A1-PM-WPR-0055 | Weekly Progress Report Issuance - WPR0055 |  | 2026-05-09 |  | 2026-10-31 |  | 2026-04-05
A1-PM-WPR-0056 | Weekly Progress Report Issuance - WPR0056 |  | 2026-05-14 |  | 2026-11-05 |  | 2026-04-11
A1-PM-WPR-0057 | Weekly Progress Report Issuance - WPR0057 |  | 2026-05-20 |  | 2026-11-11 |  | 2026-04-16
A1-PM-WPR-0058 | Weekly Progress Report Issuance - WPR0058 |  | 2026-05-26 |  | 2026-11-16 |  | 2026-04-22
A1-PM-WPR-0059 | Weekly Progress Report Issuance - WPR0059 |  | 2026-05-31 |  | 2026-11-22 |  | 2026-04-28
A1-PM-WPR-0060 | Weekly Progress Report Issuance - WPR0060 |  | 2026-06-06 |  | 2026-11-28 |  | 2026-05-03
A1-PM-WPR-0061 | Weekly Progress Report Issuance - WPR0061 |  | 2026-06-11 |  | 2026-12-03 |  | 2026-05-09
A1-PM-WPR-0062 | Weekly Progress Report Issuance - WPR0062 |  | 2026-06-17 |  | 2026-12-09 |  | 2026-05-14
A1-PM-WPR-0063 | Weekly Progress Report Issuance - WPR0063 |  | 2026-06-23 |  | 2026-12-14 |  | 2026-05-20
A1-PM-WPR-0064 | Weekly Progress Report Issuance - WPR0064 |  | 2026-06-28 |  | 2026-12-20 |  | 2026-05-26
A1-PM-WPR-0065 | Weekly Progress Report Issuance - WPR0065 |  | 2026-07-04 |  | 2026-12-26 |  | 2026-05-31
A1-PM-WPR-0066 | Weekly Progress Report Issuance - WPR0066 |  | 2026-07-09 |  | 2026-12-31 |  | 2026-06-06
A1-PM-WPR-0067 | Weekly Progress Report Issuance - WPR0067 |  | 2026-07-15 |  | 2027-01-06 |  | 2026-06-11
A1-PM-WPR-0068 | Weekly Progress Report Issuance - WPR0068 |  | 2026-07-21 |  | 2027-01-11 |  | 2026-06-17
A1-PM-WPR-0069 | Weekly Progress Report Issuance - WPR0069 |  | 2026-07-26 |  | 2027-01-17 |  | 2026-06-23
A1-PM-WPR-0070 | Weekly Progress Report Issuance - WPR0070 |  | 2026-08-01 |  | 2027-01-23 |  | 2026-06-28
A1-PM-WPR-0071 | Weekly Progress Report Issuance - WPR0071 |  | 2026-08-06 |  | 2027-01-28 |  | 2026-07-04
A1-PM-WPR-0072 | Weekly Progress Report Issuance - WPR0072 |  | 2026-08-12 |  | 2027-02-03 |  | 2026-07-09
A1-PM-WPR-0073 | Weekly Progress Report Issuance - WPR0073 |  | 2026-08-18 |  | 2027-02-08 |  | 2026-07-15
A1-PM-WPR-0074 | Weekly Progress Report Issuance - WPR0074 |  | 2026-08-23 |  | 2027-02-14 |  | 2026-07-21
A1-PM-WPR-0075 | Weekly Progress Report Issuance - WPR0075 |  | 2026-08-29 |  | 2027-02-20 |  | 2026-07-26
A1-PM-WPR-0076 | Weekly Progress Report Issuance - WPR0076 |  | 2026-09-03 |  | 2027-02-25 |  | 2026-08-01
A1-PM-WPR-0077 | Weekly Progress Report Issuance - WPR0077 |  | 2026-09-09 |  | 2027-03-03 |  | 2026-08-06
A1-PM-WPR-0078 | Weekly Progress Report Issuance - WPR0078 |  | 2026-09-15 |  | 2027-03-08 |  | 2026-08-12
A1-PM-WPR-0079 | Weekly Progress Report Issuance - WPR0079 |  | 2026-09-20 |  | 2027-03-14 |  | 2026-08-18
A1-PM-WPR-0080 | Weekly Progress Report Issuance - WPR0080 |  | 2026-09-26 |  | 2027-03-20 |  | 2026-08-23
A1-PM-WPR-0081 | Weekly Progress Report Issuance - WPR0081 |  | 2026-10-01 |  | 2027-03-25 |  | 2026-08-29
A1-PM-WPR-0082 | Weekly Progress Report Issuance - WPR0082 |  | 2026-10-07 |  | 2027-03-31 |  | 2026-09-03
A1-PM-WPR-0083 | Weekly Progress Report Issuance - WPR0083 |  | 2026-10-13 |  | 2027-04-05 |  | 2026-09-09
A1-PM-WPR-0084 | Weekly Progress Report Issuance - WPR0084 |  | 2026-10-18 |  | 2027-04-11 |  | 2026-09-15
A1-PM-WPR-0085 | Weekly Progress Report Issuance - WPR0085 |  | 2026-10-24 |  | 2027-04-17 |  | 2026-09-20
A1-PM-WPR-0086 | Weekly Progress Report Issuance - WPR0086 |  | 2026-10-29 |  | 2027-04-22 |  | 2026-09-26
A1-PM-WPR-0087 | Weekly Progress Report Issuance - WPR0087 |  | 2026-11-04 |  | 2027-04-28 |  | 2026-10-01
A1-PM-WPR-0088 | Weekly Progress Report Issuance - WPR0088 |  | 2026-11-10 |  | 2027-05-03 |  | 2026-10-07
A1-PM-WPR-0089 | Weekly Progress Report Issuance - WPR0089 |  | 2026-11-15 |  | 2027-05-09 |  | 2026-10-13
A1-PM-WPR-0090 | Weekly Progress Report Issuance - WPR0090 |  | 2026-11-21 |  | 2027-05-15 |  | 2026-10-18
A1-PM-WPR-0091 | Weekly Progress Report Issuance - WPR0091 |  | 2026-11-26 |  | 2027-05-20 |  | 2026-10-24
A1-PM-WPR-0092 | Weekly Progress Report Issuance - WPR0092 |  | 2026-12-02 |  | 2027-05-26 |  | 2026-10-29
A1-PM-WPR-0093 | Weekly Progress Report Issuance - WPR0093 |  | 2026-12-08 |  | 2027-05-31 |  | 2026-11-04
A1-PM-WPR-0094 | Weekly Progress Report Issuance - WPR0094 |  | 2026-12-13 |  | 2027-06-06 |  | 2026-11-10
A1-PM-WPR-0095 | Weekly Progress Report Issuance - WPR0095 |  | 2026-12-19 |  | 2027-06-12 |  | 2026-11-15
A1-PM-WPR-0096 | Weekly Progress Report Issuance - WPR0096 |  | 2026-12-24 |  | 2027-06-17 |  | 2026-11-21
A1-PM-WPR-0097 | Weekly Progress Report Issuance - WPR0097 |  | 2026-12-30 |  | 2027-06-23 |  | 2026-11-26
A1-PM-WPR-0098 | Weekly Progress Report Issuance - WPR0098 |  | 2027-01-05 |  | 2027-06-28 |  | 2026-12-02
A1-PM-WPR-0099 | Weekly Progress Report Issuance - WPR0099 |  | 2027-01-10 |  | 2027-07-04 |  | 2026-12-08
A1-PM-WPR-0100 | Weekly Progress Report Issuance - WPR0100 |  | 2027-01-16 |  | 2027-07-10 |  | 2026-12-13
A1-PM-WPR-0101 | Weekly Progress Report Issuance - WPR0101 |  | 2027-01-21 |  | 2027-07-15 |  | 2026-12-19
A1-PM-WPR-0102 | Weekly Progress Report Issuance - WPR0102 |  | 2027-01-27 |  | 2027-07-21 |  | 2026-12-24
A1-PM-WPR-0103 | Weekly Progress Report Issuance - WPR0103 |  | 2027-02-02 |  | 2027-07-26 |  | 2026-12-30
A1-PM-WPR-0104 | Weekly Progress Report Issuance - WPR0104 |  | 2027-02-07 |  | 2027-08-01 |  | 2027-01-05
A1-PM-WPR-0105 | Weekly Progress Report Issuance - WPR0105 |  | 2027-02-13 |  | 2027-08-07 |  | 2027-01-10
A1-PM-WPR-0106 | Weekly Progress Report Issuance - WPR0106 |  | 2027-02-18 |  | 2027-08-12 |  | 2027-01-16
A1-PM-WPR-0107 | Weekly Progress Report Issuance - WPR0107 |  | 2027-02-24 |  | 2027-08-18 |  | 2027-01-21
A1-PM-WPR-0108 | Weekly Progress Report Issuance - WPR0108 |  | 2027-03-02 |  | 2027-08-23 |  | 2027-01-27
A1-PM-WPR-0109 | Weekly Progress Report Issuance - WPR0109 |  | 2027-03-07 |  | 2027-08-29 |  | 2027-02-02
A1-PM-WPR-0110 | Weekly Progress Report Issuance - WPR0110 |  | 2027-03-13 |  | 2027-09-04 |  | 2027-02-07
A1-PM-WPR-0111 | Weekly Progress Report Issuance - WPR0111 |  | 2027-03-18 |  | 2027-09-09 |  | 2027-02-13
A1-PM-WPR-0112 | Weekly Progress Report Issuance - WPR0112 |  | 2027-03-24 |  | 2027-09-15 |  | 2027-02-18
A1-PM-WPR-0113 | Weekly Progress Report Issuance - WPR0113 |  | 2027-03-30 |  | 2027-09-20 |  | 2027-02-24
MonthlyProgressReport |  | 20-Dec-24 A | 2027-02-24 | 2026-11-11 | 2027-09-20 | 20-Dec-24 A | 2027-02-18
A1-PM-MPR-0001 | Monthly Progress Report Issuance - MPR001 |  | 20-Dec-24 A |  | 2026-11-11 |  | 20-Dec-24 A
A1-PM-MPR-0002 | Monthly Progress Report Issuance - MPR002 |  | 24-Jan-25 A |  | 2026-11-11 |  | 24-Jan-25 A
A1-PM-MPR-0003 | Monthly Progress Report Issuance - MPR003 |  | 17-Jun-25 A |  | 2026-11-11 |  | 17-Jun-25 A
A1-PM-MPR-0004 | Monthly Progress Report Issuance - MPR004 |  | 14-Apr-25 A |  | 2026-11-11 |  | 14-Apr-25 A
A1-PM-MPR-0005 | Monthly Progress Report Issuance - MPR005 |  | 13-May-25 A |  | 2026-11-11 |  | 13-May-25 A
A1-PM-MPR-0006 | Monthly Progress Report Issuance - MPR006 |  | 17-Jun-25 A |  | 2026-11-11 |  | 17-Jun-25 A
A1-PM-MPR-0007 | Monthly Progress Report Issuance - MPR007 |  | 01-Jul-25 A |  | 2026-11-11 |  | 01-Jul-25 A
A1-PM-MPR-0008 | Monthly Progress Report Issuance - MPR008 |  | 22-Aug-25 A |  | 2026-11-11 |  | 22-Aug-25 A
A1-PM-MPR-0009 | Monthly Progress Report Issuance - MPR009 |  | 10-Sep-25 A |  | 2026-11-11 |  | 10-Sep-25 A
A1-PM-MPR-0010 | Monthly Progress Report Issuance - MPR010 |  | 30-Oct-25 A |  | 2026-11-11 |  | 30-Oct-25 A
A1-PM-MPR-0011 | Monthly Progress Report Issuance - MPR011 |  | 21-Nov-25 A |  | 2026-11-11 |  | 21-Nov-25 A
A1-PM-MPR-0012 | Monthly Progress Report Issuance - MPR012 |  | 20-Feb-26 A |  | 2026-11-11 |  | 2026-02-20
A1-PM-MPR-0013 | Monthly Progress Report Issuance - MPR013 |  | 14-Mar-26 A |  | 2026-11-11 |  | 2026-03-14
A1-PM-MPR-0014 | Monthly Progress Report Issuance - MPR014 |  | 2026-04-17 |  | 2026-11-11 |  | 2026-04-11
A1-PM-MPR-0015 | Monthly Progress Report Issuance - MPR015 |  | 2026-05-09 |  | 2026-12-03 |  | 2026-05-03
A1-PM-MPR-0016 | Monthly Progress Report Issuance - MPR016 |  | 2026-05-31 |  | 2026-12-26 |  | 2026-05-26
A1-PM-MPR-0017 | Monthly Progress Report Issuance - MPR017 |  | 2026-06-23 |  | 2027-01-17 |  | 2026-06-17
A1-PM-MPR-0018 | Monthly Progress Report Issuance - MPR018 |  | 2026-07-21 |  | 2027-02-14 |  | 2026-07-15
A1-PM-MPR-0019 | Monthly Progress Report Issuance - MPR019 |  | 2026-08-12 |  | 2027-03-08 |  | 2026-08-06
A1-PM-MPR-0020 | Monthly Progress Report Issuance - MPR020 |  | 2026-09-09 |  | 2027-04-05 |  | 2026-09-03
A1-PM-MPR-0021 | Monthly Progress Report Issuance - MPR021 |  | 2026-10-01 |  | 2027-04-28 |  | 2026-09-26
A1-PM-MPR-0022 | Monthly Progress Report Issuance - MPR022 |  | 2026-10-24 |  | 2027-05-20 |  | 2026-10-18
A1-PM-MPR-0023 | Monthly Progress Report Issuance - MPR023 |  | 2026-11-21 |  | 2027-06-17 |  | 2026-11-15
A1-PM-MPR-0024 | Monthly Progress Report Issuance - MPR024 |  | 2026-12-13 |  | 2027-07-10 |  | 2026-12-08
A1-PM-MPR-0025 | Monthly Progress Report Issuance - MPR025 |  | 2027-01-05 |  | 2027-08-01 |  | 2026-12-30
A1-PM-MPR-0026 | Monthly Progress Report Issuance - MPR026 |  | 2027-02-02 |  | 2027-08-29 |  | 2027-01-27
A1-PM-MPR-0027 | Monthly Progress Report Issuance - MPR027 |  | 2027-02-24 |  | 2027-09-20 |  | 2027-02-18
TeamBuildingWorkshops |  | 06-Mar-25 A | 2026-12-04 | 2027-02-01 | 2027-09-20 | 06-Mar-25 A | 2026-12-04
A1-PM-TBW-0001 | TBW01-Team Building Event-001 |  | 06-Mar-25 A |  | 2027-02-01 |  | 06-Mar-25 A
A1-PM-TBW-0002 | TBW01-Team Building Event-002 |  | 21-Jun-25 A |  | 2027-02-01 |  | 21-Jun-25 A
A1-PM-TBW-0003 | TBW01-Team Building Event-003 |  | 12-Aug-25 A |  | 2027-02-01 |  | 12-Aug-25 A
A1-PM-TBW-0004 | TBW01-Team Building Event-004 |  | 20-Feb-26 A |  | 2027-02-01 |  | 2026-02-20
A1-PM-TBW-0005 | TBW01-Team Building Event-005 |  | 2026-05-26 |  | 2027-03-12 |  | 2026-05-26
A1-PM-TBW-0006 | TBW01-Team Building Event-006 |  | 2026-08-30 |  | 2027-06-16 |  | 2026-08-30
A1-PM-TBW-0007 | TBW01-Team Building Event-007 |  | 2026-12-04 |  | 2027-09-20 |  | 2026-12-04
InvoicingPlan |  | 07-Feb-25 A | 2027-04-16 | 2026-09-20 | 2027-09-20 | 07-Feb-25 A | 2027-04-05
A1-PM-MIP-0001 | Monthly Invoicing Plan - MIP001 (Advanced Payment) |  | 07-Feb-25 A |  | 2026-09-20 |  | 07-Feb-25 A
A1-PM-MIP-0002 | Monthly Invoicing Plan - MIP002 |  | 07-Mar-25 A |  | 2026-09-20 |  | 07-Mar-25 A
A1-PM-MIP-0003 | Monthly Invoicing Plan - MIP003 |  | 10-Apr-25 A |  | 2026-09-20 |  | 10-Apr-25 A
A1-PM-MIP-0004 | Monthly Invoicing Plan - MIP004 |  | 10-May-25 A |  | 2026-09-20 |  | 10-May-25 A
A1-PM-MIP-0005 | Monthly Invoicing Plan - MIP005 |  | 21-Jun-25 A |  | 2026-09-20 |  | 21-Jun-25 A
A1-PM-MIP-0006 | Monthly Invoicing Plan - MIP006 |  | 21-Jun-25 A |  | 2026-09-20 |  | 21-Jun-25 A
A1-PM-MIP-0007 | Monthly Invoicing Plan - MIP007 |  | 21-Jun-25 A |  | 2026-09-20 |  | 21-Jun-25 A
A1-PM-MIP-0008 | Monthly Invoicing Plan - MIP008 |  | 29-Aug-25 A |  | 2026-09-20 |  | 29-Aug-25 A
A1-PM-MIP-0009 | Monthly Invoicing Plan - MIP009 |  | 19-Sep-25 A |  | 2026-09-20 |  | 19-Sep-25 A
A1-PM-MIP-0010 | Monthly Invoicing Plan - MIP010 |  | 24-Oct-25 A |  | 2026-09-20 |  | 24-Oct-25 A
A1-PM-MIP-0011 | Monthly Invoicing Plan - MIP011 |  | 11-Nov-25 A |  | 2026-09-20 |  | 11-Nov-25 A
A1-PM-MIP-0012 | Monthly Invoicing Plan - MIP012 |  | 20-Feb-26 A |  | 2026-09-20 |  | 2026-02-20
A1-PM-MIP-0013 | Monthly Invoicing Plan - MIP013 |  | 08-Mar-26 A |  | 2026-09-20 |  | 2026-03-08
A1-PM-MIP-0014 | Monthly Invoicing Plan - MIP014 |  | 2026-04-17 |  | 2026-09-20 |  | 2026-04-05
A1-PM-MIP-0015 | Monthly Invoicing Plan - MIP015 |  | 2026-05-17 |  | 2026-10-21 |  | 2026-05-06
A1-PM-MIP-0016 | Monthly Invoicing Plan - MIP016 |  | 2026-06-16 |  | 2026-11-20 |  | 2026-06-05
A1-PM-MIP-0017 | Monthly Invoicing Plan - MIP017 |  | 2026-07-17 |  | 2026-12-21 |  | 2026-07-06
A1-PM-MIP-0018 | Monthly Invoicing Plan - MIP018 |  | 2026-08-16 |  | 2027-01-20 |  | 2026-08-05
A1-PM-MIP-0019 | Monthly Invoicing Plan - MIP019 |  | 2026-08-16 |  | 2027-01-20 |  | 2026-08-05
A1-PM-MIP-0020 | Monthly Invoicing Plan - MIP020 |  | 2026-09-16 |  | 2027-02-20 |  | 2026-09-05
A1-PM-MIP-0021 | Monthly Invoicing Plan - MIP021 |  | 2026-10-17 |  | 2027-03-23 |  | 2026-10-06
A1-PM-MIP-0022 | Monthly Invoicing Plan - MIP022 |  | 2026-11-16 |  | 2027-04-22 |  | 2026-11-05
A1-PM-MIP-0023 | Monthly Invoicing Plan - MIP023 |  | 2026-12-17 |  | 2027-05-23 |  | 2026-12-06
A1-PM-MIP-0024 | Monthly Invoicing Plan - MIP024 |  | 2027-01-16 |  | 2027-06-22 |  | 2027-01-05
A1-PM-MIP-0025 | Monthly Invoicing Plan - MIP025 |  | 2027-02-16 |  | 2027-07-23 |  | 2027-02-05
A1-PM-MIP-0026 | Monthly Invoicing Plan - MIP026 |  | 2027-03-19 |  | 2027-08-23 |  | 2027-03-08
A1-PM-MIP-0027 | Monthly Invoicing Plan - MIP027 |  | 2027-04-16 |  | 2027-09-20 |  | 2027-04-05
HomeOfficeServices |  | 14-Nov-24 A | 2027-09-14 | 2026-06-09 | 2027-09-20 | 14-Nov-24 A | 2027-07-14
DetailedDesign-EDDR |  | 27-Nov-24 A | 2026-11-13 | 2026-06-09 | 2027-09-20 | 27-Nov-24 A | 2026-09-25
Package1&2 |  | 01-Aug-25 A | 22-Aug-25 A | 2026-06-22 | 2026-06-22 | 01-Aug-25 A | 22-Aug-25 A
DeliverablestobeRecievedfromPkg1&2 |  | 01-Aug-25 A | 22-Aug-25 A | 2026-06-22 | 2026-06-22 | 01-Aug-25 A | 22-Aug-25 A
1B-DE-P12-0001 | Civil / Architecture / Structure - 63 Deleverables |  | 01-Aug-25 A |  | 2026-06-22 |  | 01-Aug-25 A
1B-DE-P12-0011 | Construction - 30 Deleverables |  | 04-Aug-25 A |  | 2026-06-22 |  | 04-Aug-25 A
1B-DE-P12-0021 | Electrical Engineering - 73 Deleverables |  | 05-Aug-25 A |  | 2026-06-22 |  | 05-Aug-25 A
1B-DE-P12-0031 | HVAC - 26 Deleverables |  | 06-Aug-25 A |  | 2026-06-22 |  | 06-Aug-25 A
1B-DE-P12-0041 | Instrument and Control System - 90 Deleverables |  | 07-Aug-25 A |  | 2026-06-22 |  | 07-Aug-25 A
1B-DE-P12-0051 | IT/TELECOM - 69 Deleverables |  | 08-Aug-25 A |  | 2026-06-22 |  | 08-Aug-25 A
1B-DE-P12-0061 | Material and Corrosion - 24 Deleverables |  | 11-Aug-25 A |  | 2026-06-22 |  | 11-Aug-25 A
1B-DE-P12-0071 | Mechanical Rotating - 19 Deleverables |  | 12-Aug-25 A |  | 2026-06-22 |  | 12-Aug-25 A
1B-DE-P12-0081 | Mechanical Rotating/Package - 9 Deleverables |  | 13-Aug-25 A |  | 2026-06-22 |  | 13-Aug-25 A
1B-DE-P12-0091 | MS-Mechanical Static - 9 Deleverables |  | 14-Aug-25 A |  | 2026-06-22 |  | 14-Aug-25 A
1B-DE-P12-0101 | Piping Engineering - 43 Deleverables |  | 15-Aug-25 A |  | 2026-06-22 |  | 15-Aug-25 A
1B-DE-P12-0111 | Process and Safety Engineering - 38 Deleverables |  | 18-Aug-25 A |  | 2026-06-22 |  | 18-Aug-25 A
1B-DE-P12-0121 | Project Control - 29 Deleverables |  | 19-Aug-25 A |  | 2026-06-22 |  | 19-Aug-25 A
1B-DE-P12-0131 | Project Control Quality - 14 Deleverables |  | 20-Aug-25 A |  | 2026-06-22 |  | 20-Aug-25 A
1B-DE-P12-0141 | Project Management - 86 Deleverables |  | 21-Aug-25 A |  | 2026-06-22 |  | 21-Aug-25 A
1B-DE-P12-0151 | Safety - 11 Deleverables |  | 22-Aug-25 A |  | 2026-06-22 |  | 22-Aug-25 A
Package3 |  | 27-Nov-24 A | 2026-11-13 | 2026-06-09 | 2027-09-20 | 27-Nov-24 A | 2026-09-25
Milestone |  | 11-Dec-24 A | 2026-11-13 | 2026-06-11 | 2027-03-23 | 11-Dec-24 A | 2026-09-25
General |  | 11-Dec-24 A | 2026-11-13 | 2026-06-11 | 2027-03-23 | 11-Dec-24 A | 2026-09-25
Turnaround |  | 11-Dec-24 A | 11-Dec-24 A | 2026-06-15 | 2026-06-15 | 11-Dec-24 A | 11-Dec-24 A
A40690 | Commencement of TA Engginering Works | 11-Dec-24 A |  | 2026-06-15 |  | 11-Dec-24 A
BalanceofPlant |  | 11-Dec-24 A | 2026-11-13 | 2026-06-11 | 2027-03-23 | 11-Dec-24 A | 2026-09-25
A120 | Commencement of BOP Engineering Works | 11-Dec-24 A |  | 2026-06-11 |  | 11-Dec-24 A
A40320 | Completion of Engineering | 2026-11-13 |  | 2027-03-23 |  | 2026-09-25 |  | End of Engineering
General/Common |  | 27-Nov-24 A | 21-Jan-25 A | 2026-06-16 | 2026-06-16 | 27-Nov-24 A | 21-Jan-25 A
MSE1300 | Site Survey & Data Collection / FEED Verification | 27-Nov-24 A | 21-Jan-25 A | 2026-06-16 | 2026-06-16 | 27-Nov-24 A | 21-Jan-25 A | Start of Engineering
ProjectManagement |  | 04-Dec-24 A | 2026-05-14 | 2026-06-09 | 2027-09-20 | 07-Nov-24 A | 2027-07-20
Preliminaries |  | 04-Dec-24 A | 23-May-25 A | 2026-06-09 | 2026-06-16 | 04-Dec-24 A | 23-May-25 A
A40350 | Site Visit for TA Activities (CSA, Piping) | 09-Jan-25 A | 16-Jan-25 A | 2026-06-16 | 2026-06-16 | 09-Jan-25 A | 16-Jan-25 A
A40360 | Site Visit Report Before TA | 09-Jan-25 A | 16-Jan-25 A | 2026-06-16 | 2026-06-16 | 09-Jan-25 A | 16-Jan-25 A
A53280 | Engineering Subcontractor KOM | 04-Dec-24 A | 04-Dec-24 A | 2026-06-09 | 2026-06-09 | 04-Dec-24 A | 04-Dec-24 A
A53290 | LOA Request | 05-Dec-24 A | 13-Dec-24 A | 2026-06-09 | 2026-06-09 | 05-Dec-24 A | 13-Dec-24 A
A53320 | Receipt of Source Data | 05-Dec-24 A | 23-May-25 A | 2026-06-09 | 2026-06-09 | 05-Dec-24 A | 23-May-25 A
A53330 | Medicals and CICPA Passes | 05-Dec-24 A | 24-Dec-24 A | 2026-06-09 | 2026-06-09 | 05-Dec-24 A | 24-Dec-24 A
A53340 | Site Visit for BOP | 25-Dec-24 A | 31-Dec-24 A | 2026-06-09 | 2026-06-09 | 25-Dec-24 A | 31-Dec-24 A
TArelatedInputs |  | 12-Dec-24 A | 2026-05-14 | 2026-06-09 | 2027-09-20 | 12-Dec-24 A | 2026-06-16
TAPhase |  | 12-Dec-24 A | 22-Apr-25 A | 2026-06-09 | 2026-06-16 | 12-Dec-24 A | 22-Apr-25 A
A28140 | Receipt of Approved Topo, UG & geotechnical investigation report | 08-Apr-25 A | 22-Apr-25 A | 2026-06-15 | 2026-06-15 | 08-Apr-25 A | 22-Apr-25 A
A40330 | Receipt of Approved ICT Site Adequacy Report | 12-Feb-25 A | 13-Feb-25 A | 2026-06-16 | 2026-06-16 | 12-Feb-25 A | 13-Feb-25 A
A40340 | Receipt of Approved Electrical Site Adequacy Report | 12-Feb-25 A | 13-Feb-25 A | 2026-06-16 | 2026-06-16 | 12-Feb-25 A | 13-Feb-25 A
A55740 | Receipt of HSE third party offers by RAD (Descon) | 12-Dec-24 A | 12-Dec-24 A | 2026-06-09 | 2026-06-09 | 12-Dec-24 A | 12-Dec-24 A
VendorOfferReceipt(toenableEngSubcontoperformTBE) |  | 09-Jan-25 A | 15-Jul-25 A | 2026-06-12 | 2027-03-23 | 09-Jan-25 A | 15-Jul-25 A
Piping |  | 03-Feb-25 A | 24-Feb-25 A | 2026-06-12 | 2026-07-20 | 03-Feb-25 A | 24-Feb-25 A
A53550 | Piping Bulk_All Technical Vendor Offers Receipt |  | 03-Feb-25 A |  | 2026-06-16 |  | 03-Feb-25 A
A53560 | Manual Valves_All Technical Vendor Offers Receipt |  | 11-Feb-25 A |  | 2026-07-20 |  | 11-Feb-25 A
A53570 | Piping Speciality Items_All Technical Vendor Offers Receipt |  | 24-Feb-25 A |  | 2026-07-20 |  | 24-Feb-25 A
A53580 | Spring Hangers_All Technical Vendor Offers Receipt |  | 21-Feb-25 A |  | 2026-06-12 |  | 21-Feb-25 A
A53590 | Rigid Struts_All Technical Vendor Offers Receipt |  | 17-Feb-25 A |  | 2026-06-15 |  | 17-Feb-25 A
Mechanical |  | 07-Feb-25 A | 07-May-25 A | 2026-06-15 | 2027-01-19 | 07-Feb-25 A | 07-May-25 A
A53400 | Heat Exchangers_All Technical Vendor Offers Receipt |  | 14-Mar-25 A |  | 2026-08-05 |  | 14-Mar-25 A
A53410 | Centrifugal Pump_All Technical Vendor Offers Receipt |  | 21-Mar-25 A |  | 2026-09-26 |  | 21-Mar-25 A
A53420 | EOT Crane_All Technical Vendor Offers Receipt |  | 07-May-25 A |  | 2026-06-15 |  | 07-May-25 A
A53430 | Coalscer_All Technical Vendor Offers Receipt |  | 21-Mar-25 A |  | 2027-01-19 |  | 21-Mar-25 A
A53440 | Pressure Vessels & Internals_All Technical Vendor Offers Receipt |  | 07-Feb-25 A |  | 2026-06-16 |  | 07-Feb-25 A
Electrical |  | 09-Jan-25 A | 13-May-25 A | 2026-06-15 | 2026-12-21 | 09-Jan-25 A | 13-May-25 A
A53600 | Transformer (Power And Distribution)_All Technical Vendor Offers Receipt |  | 09-Jan-25 A |  | 2026-09-07 |  | 09-Jan-25 A
A53610 | 11KV Switchgear_All Technical Vendor Offers Receipt |  | 06-Mar-25 A |  | 2026-12-21 |  | 06-Mar-25 A
A53620 | LV Switchgear_All Technical Vendor Offers Receipt |  | 28-Feb-25 A |  | 2026-07-28 |  | 28-Feb-25 A
A53630 | AC UPS_All Technical Vendor Offers Receipt |  | 22-Jan-25 A |  | 2026-09-23 |  | 22-Jan-25 A
A53640 | DC UPS_All Technical Vendor Offers Receipt |  | 21-Feb-25 A |  | 2026-06-15 |  | 21-Feb-25 A
A53650 | Capacitor Bank_All Technical Vendor Offers Receipt |  | 21-Apr-25 A |  | 2026-11-03 |  | 21-Apr-25 A
A53660 | Power, Control And Earthing Cables_All Technical Vendor Offers Receipt |  | 13-May-25 A |  | 2026-08-23 |  | 13-May-25 A
A53670 | Neutral Grounding Resistor_All Technical Vendor Offers Receipt |  | 17-Jan-25 A |  | 2026-12-01 |  | 17-Jan-25 A
A53680 | Emergency Diesel Generator Set_All Technical Vendor Offers Receipt |  | 22-Jan-25 A |  | 2026-07-11 |  | 22-Jan-25 A
A53690 | LV Variable Frequency Drive_All Technical Vendor Offers Receipt |  | 21-Feb-25 A |  | 2026-12-21 |  | 21-Feb-25 A
Instrumentation&Controls |  | 23-Apr-25 A | 15-Jul-25 A | 2026-06-15 | 2027-03-23 | 23-Apr-25 A | 15-Jul-25 A
A25910 | Flow Element (Venturi Tube)_All Technical Vendor Offers Receipt |  | 30-Apr-25 A |  | 2026-07-23 |  | 30-Apr-25 A
A25920 | Temperature Element / Thermowell_All Technical Vendor Offers Receipt |  | 07-May-25 A |  | 2027-02-22 |  | 07-May-25 A
A25930 | Temperature Gauges / Pressure Gauges_All Technical Vendor Offers Receipt |  | 30-Apr-25 A |  | 2026-08-15 |  | 30-Apr-25 A
A25940 | Analyzers_All Technical Vendor Offers Receipt |  | 15-Jul-25 A |  | 2027-01-28 |  | 15-Jul-25 A
A25950 | Level Gauges (Magnetic Type)_All Technical Vendor Offers Receipt |  | 23-Apr-25 A |  | 2026-07-17 |  | 23-Apr-25 A
A25960 | Control Valves_All Technical Vendor Offers Receipt |  | 27-Apr-25 A |  | 2026-07-13 |  | 27-Apr-25 A
A25970 | Fire & Gas Detectors_All Technical Vendor Offers Receipt |  | 05-Jul-25 A |  | 2026-07-10 |  | 05-Jul-25 A
A25980 | Level Transmitters (GWR type)_All Technical Vendor Offers Receipt |  | 28-Apr-25 A |  | 2027-03-23 |  | 28-Apr-25 A
A25990 | Motor Operated Valves_All Technical Vendor Offers Receipt |  | 27-Apr-25 A |  | 2026-10-28 |  | 27-Apr-25 A
A26000 | ESD Valves_All Technical Vendor Offers Receipt |  | 30-Apr-25 A |  | 2027-02-26 |  | 30-Apr-25 A
A26010 | Rotameter_All Technical Vendor Offers Receipt |  | 01-May-25 A |  | 2027-02-22 |  | 01-May-25 A
A53700 | Electronic Transmitters_All Technical Vendor Offers Receipt |  | 28-Apr-25 A |  | 2026-07-17 |  | 28-Apr-25 A
A53710 | Flow Element (Orifice Plate)_All Technical Vendor Offers Receipt |  | 29-Apr-25 A |  | 2026-07-23 |  | 29-Apr-25 A
A53720 | Instrument Cables_All Technical Vendor Offers Receipt |  | 05-Jul-25 A |  | 2026-06-15 |  | 05-Jul-25 A
A53730 | Junction Boxes_All Technical Vendor Offers Receipt |  | 05-Jul-25 A |  | 2026-08-31 |  | 05-Jul-25 A
A53740 | ICSS System_All Technical Vendor Offers Receipt |  | 24-Apr-25 A |  | 2026-07-30 |  | 24-Apr-25 A
A53750 | Fire Detection System & LFCP_All Technical Vendor Offers Receipt |  | 12-Jun-25 A |  | 2026-06-15 |  | 12-Jun-25 A
Telecom |  | 26-Apr-25 A | 22-May-25 A | 2026-07-09 | 2027-02-24 | 26-Apr-25 A | 22-May-25 A
A53760 | Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_All Technical Vendor Offers Receipt |  | 26-Apr-25 A |  | 2026-07-09 |  | 26-Apr-25 A
A53770 | Telecom Cables_All Technical Vendor Offers Receipt |  | 22-May-25 A |  | 2027-02-24 |  | 22-May-25 A
HVAC |  | 03-Jun-25 A | 03-Jun-25 A | 2026-06-15 | 2026-06-15 | 03-Jun-25 A | 03-Jun-25 A
A53780 | HVAC Equipments_All Technical Vendor Offers Receipt |  | 03-Jun-25 A |  | 2026-06-15 |  | 03-Jun-25 A
IstIssuanceofVendorDataReceipt-1 |  | 03-Feb-25 A | 2026-04-21 | 2026-06-09 | 2027-09-06 | 03-Feb-25 A | 2026-05-22
Piping |  | 24-Mar-25 A | 2026-04-21 | 2026-06-09 | 2026-08-14 | 03-Feb-25 A | 24-Feb-25 A
A53790 | Piping Bulk_1st issuance of Vendor Data Receipt |  | 30-Oct-25 A |  | 2026-06-09 |  | 2026-02-20
A53800 | Manual Valves_1st issuance of Vendor Data Receipt |  | 2026-04-17 |  | 2026-07-20 |  | 2026-02-20
A53810 | Piping Speciality Items_1st issuance of Vendor Data Receipt |  | 05-Aug-25 A |  | 2026-06-16 |  | 05-Aug-25 A
A53820 | Spring Hangers_1st issuance of Vendor Data Receipt |  | 2026-04-21 |  | 2026-08-14 |  | 2026-05-22
A53830 | Rigid Struts_1st issuance of Vendor Data Receipt |  | 24-Mar-25 A |  | 2026-06-15 |  | 24-Mar-25 A
Mechanical |  | 27-Aug-25 A | 20-Feb-26 A | 2026-06-11 | 2027-01-19 | 07-Feb-25 A | 07-May-25 A
A28770 | Compressors (FG & OG)_1st issuance of Vendor Data Receipt |  | 27-Aug-25 A |  | 2026-06-11 |  | 27-Aug-25 A
A28780 | PSA Unit_1st issuance of Vendor Data Receipt |  | 09-Sep-25 A |  | 2026-06-15 |  | 09-Sep-25 A
A53500 | Heat Exchangers_1st issuance of Vendor Data Receipt |  | 02-Sep-25 A |  | 2026-06-16 |  | 02-Sep-25 A
A53510 | Centrifugal Pump_1st issuance of Vendor Data Receipt |  | 30-Oct-25 A |  | 2026-06-15 |  | 30-Oct-25 A
A53520 | EOT Crane_1st issuance of Vendor Data Receipt |  | 04-Nov-25 A |  | 2026-06-15 |  | 04-Nov-25 A
A53530 | Coalscer_1st issuance of Vendor Data Receipt |  | 20-Feb-26 A |  | 2027-01-19 |  | 2026-02-27
A53540 | Pressure Vessels & Internals_1st issuance of Vendor Data Receipt |  | 02-Sep-25 A |  | 2026-06-16 |  | 02-Sep-25 A
Electrical |  | 11-Aug-25 A | 2026-04-17 | 2026-06-15 | 2027-08-27 | 09-Jan-25 A | 13-May-25 A
A53840 | Transformer (Power And Distribution)_1st issuance of Vendor Data Receipt |  | 2026-04-17 |  | 2027-01-22 |  | 2026-02-20
A53850 | 11KV Switchgear_1st issuance of Vendor Data Receipt |  | 11-Aug-25 A |  | 2026-12-21 |  | 2026-02-20
A53860 | LV Switchgear_1st issuance of Vendor Data Receipt |  | 11-Aug-25 A |  | 2026-12-21 |  | 2026-02-20
A53870 | AC UPS_1st issuance of Vendor Data Receipt |  | 06-Feb-26 A |  | 2026-09-23 |  | 2026-02-20
A53880 | DC UPS_1st issuance of Vendor Data Receipt |  | 2026-04-17 |  | 2026-06-15 |  | 2026-02-20
A53890 | Capacitor Bank_1st issuance of Vendor Data Receipt |  | 19-Dec-25 A |  | 2026-11-03 |  | 2026-02-20
A53900 | Power, Control And Earthing Cables_1st issuance of Vendor Data Receipt |  | 21-Nov-25 A |  | 2026-08-23 |  | 2026-02-20
A53910 | Neutral Grounding Resistor_1st issuance of Vendor Data Receipt |  | 19-Dec-25 A |  | 2026-12-01 |  | 2026-02-20
A53920 | Emergency Diesel Generator Set_1st issuance of Vendor Data Receipt |  | 2026-04-17 |  | 2027-03-23 |  | 2026-02-20
A53930 | LV Variable Frequency Drive_1st issuance of Vendor Data Receipt |  | 2026-04-17 |  | 2027-08-27 |  | 2026-02-20
Instrumentation&Controls |  | 03-Feb-25 A | 2026-04-21 | 2026-06-15 | 2027-09-06 | 23-Apr-25 A | 15-Jul-25 A
A53940 | Electronic Transmitters_1st issuance of Vendor Data Receipt |  | 2026-04-21 |  | 2027-08-27 |  | 2026-03-27
A53950 | Flow Element (Orifice Plate)_1st issuance of Vendor Data Receipt |  | 2026-04-17 |  | 2027-08-27 |  | 2026-02-20
A53960 | Flow Element (Venturi Tube)_1st issuance of Vendor Data Receipt |  | 2026-04-17 |  | 2027-08-27 |  | 2026-02-20
A53970 | Temperature Element / Thermowell_1st issuance of Vendor Data Receipt |  | 18-Mar-25 A |  | 2026-06-15 |  | 18-Mar-25 A
A53980 | Temperature Gauges / Pressure Gauges_1st issuance of Vendor Data Receipt |  | 29-May-25 A |  | 2026-06-16 |  | 29-May-25 A
A53990 | Analyzers_1st issuance of Vendor Data Receipt |  | 03-Feb-25 A |  | 2026-06-15 |  | 03-Feb-25 A
A54000 | Level Gauges (Magnetic Type)_1st issuance of Vendor Data Receipt |  | 2026-04-17 |  | 2027-08-27 |  | 2026-02-20
A54010 | Control Valves_1st issuance of Vendor Data Receipt |  | 2026-04-17 |  | 2027-08-27 |  | 2026-02-20
A54020 | Fire & Gas Detectors_1st issuance of Vendor Data Receipt |  | 17-Mar-25 A |  | 2026-06-16 |  | 17-Mar-25 A
A54030 | Level Transmitters (GWR type)_1st issuance of Vendor Data Receipt |  | 2026-04-17 |  | 2027-08-27 |  | 2026-02-20
A54040 | Motor Operated Valves_1st issuance of Vendor Data Receipt |  | 2026-04-17 |  | 2027-08-27 |  | 2026-02-20
A54050 | ESD Valves_1st issuance of Vendor Data Receipt |  | 2026-04-17 |  | 2027-08-27 |  | 2026-02-20
A54060 | Rotameter_1st issuance of Vendor Data Receipt |  | 29-May-25 A |  | 2026-06-16 |  | 29-May-25 A
A54070 | Instrument Cables_1st issuance of Vendor Data Receipt |  | 30-Nov-25 A |  | 2026-06-15 |  | 30-Nov-25 A
A54080 | Junction Boxes_1st issuance of Vendor Data Receipt |  | 2026-04-17 |  | 2027-09-06 |  | 2026-03-12
A54090 | ICSS System_1st issuance of Vendor Data Receipt |  | 2026-04-17 |  | 2027-08-27 |  | 2026-02-20
A54100 | Fire Detection System & LFCP_1st issuance of Vendor Data Receipt |  | 2026-04-17 |  | 2026-06-15 |  | 2026-02-20
Telecom |  | 18-Mar-25 A | 2026-04-17 | 2026-06-15 | 2027-08-27 | 26-Apr-25 A | 22-May-25 A
A54110 | Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_1st issuance of Vendor Data Receipt |  | 2026-04-17 |  | 2027-08-27 |  | 2026-02-20
A54120 | Telecom Cables_1st issuance of Vendor Data Receipt |  | 18-Mar-25 A |  | 2026-06-15 |  | 18-Mar-25 A
HVAC |  | 2026-04-17 | 2026-04-17 | 2027-08-27 | 2027-08-27 | 03-Jun-25 A | 03-Jun-25 A
A54130 | HVAC Equipments_1st issuance of Vendor Data Receipt |  | 2026-04-17 |  | 2027-08-27 |  | 2026-02-20
ApprovedVenderDataReceipt |  | 04-Mar-25 A | 2026-05-14 | 2026-06-09 | 2027-09-20 | 04-Mar-25 A | 2026-06-16
Piping |  | 26-Aug-25 A | 2026-05-14 | 2026-06-09 | 2026-09-07 | 03-Feb-25 A | 24-Feb-25 A
A54140 | Piping Bulk_Approved Vendor Data Receipt |  | 21-Oct-25 A |  | 2026-06-09 |  | 2026-03-16
A54150 | Manual Valves_Approved Vendor Data Receipt |  | 2026-04-30 |  | 2026-08-03 |  | 2026-03-05
A54160 | Piping Speciality Items_Approved Vendor Data Receipt |  | 26-Aug-25 A |  | 2026-06-16 |  | 26-Aug-25 A
A54170 | Spring Hangers_Approved Vendor Data Receipt |  | 2026-05-14 |  | 2026-09-07 |  | 2026-06-16
A54180 | Rigid Struts_Approved Vendor Data Receipt |  | 2026-04-17 |  | 2026-06-15 |  | 2026-02-20
Mechanical |  | 10-Jun-25 A | 2026-04-17 | 2026-06-15 | 2027-01-19 | 07-Feb-25 A | 07-May-25 A
A28150 | Compressors (FG & OG)_Approved Vendor Data Receipt |  | 19-Sep-25 A |  | 2026-06-15 |  | 19-Sep-25 A
A53450 | Heat Exchangers_Approved Vendor Data Receipt |  | 02-Sep-25 A |  | 2026-06-16 |  | 02-Sep-25 A
A53460 | Centrifugal Pump_Approved Vendor Data Receipt |  | 2026-04-17 |  | 2026-06-15 |  | 2026-02-20
A53470 | EOT Crane_Approved Vendor Data Receipt |  | 2026-04-17 |  | 2026-06-15 |  | 2026-02-20
A53480 | Coalscer_Approved Vendor Data Receipt |  | 30-Jan-26 A |  | 2027-01-19 |  | 2026-03-24
A53490 | Pressure Vessels & Internals_Approved Vendor Data Receipt |  | 02-Sep-25 A |  | 2026-06-16 |  | 02-Sep-25 A
A55640 | PSA Unit_Approved Vendor Data Receipt |  | 10-Jun-25 A |  | 2026-06-15 |  | 10-Jun-25 A
Electrical |  | 11-Aug-25 A | 2026-05-11 | 2026-06-15 | 2027-09-20 | 09-Jan-25 A | 13-May-25 A
A54190 | Transformer (Power And Distribution)_Approved Vendor Data Receipt |  | 2026-05-11 |  | 2027-02-22 |  | 2026-03-16
A54200 | 11KV Switchgear_Approved Vendor Data Receipt |  | 12-Aug-25 A |  | 2026-12-21 |  | 2026-03-16
A54210 | LV Switchgear_Approved Vendor Data Receipt |  | 11-Aug-25 A |  | 2026-12-21 |  | 2026-03-16
A54220 | AC UPS_Approved Vendor Data Receipt |  | 20-Feb-26 A |  | 2026-09-23 |  | 2026-03-16
A54230 | DC UPS_Approved Vendor Data Receipt |  | 2026-04-17 |  | 2026-06-15 |  | 2026-02-20
A54240 | Capacitor Bank_Approved Vendor Data Receipt |  | 26-Feb-26 A |  | 2026-11-03 |  | 2026-03-16
A54250 | Power, Control And Earthing Cables_Approved Vendor Data Receipt |  | 28-Nov-25 A |  | 2026-08-23 |  | 2026-03-16
A54260 | Neutral Grounding Resistor_Approved Vendor Data Receipt |  | 20-Dec-25 A |  | 2026-12-01 |  | 2026-03-16
A54270 | Emergency Diesel Generator Set_Approved Vendor Data Receipt |  | 2026-04-17 |  | 2027-03-23 |  | 2026-02-20
A54280 | LV Variable Frequency Drive_Approved Vendor Data Receipt |  | 2026-05-11 |  | 2027-09-20 |  | 2026-03-16
A55650 | Notice to proceed - All Electrical equipment footprint & load data to freeze Electrical building Equipment layout |  | 2026-04-17 |  | 2027-09-20 |  | 2026-02-20
Instrumentation&Controls |  | 04-Mar-25 A | 2026-05-14 | 2026-06-15 | 2027-09-20 | 23-Apr-25 A | 15-Jul-25 A
A54290 | Electronic Transmitters_Approved Vendor Data Receipt |  | 2026-05-14 |  | 2027-09-20 |  | 2026-04-21
A54300 | Flow Element (Orifice Plate)_Approved Vendor Data Receipt |  | 2026-05-11 |  | 2027-09-20 |  | 2026-03-16
A54310 | Flow Element (Venturi Tube)_Approved Vendor Data Receipt |  | 2026-05-11 |  | 2027-09-20 |  | 2026-03-16
A54320 | Temperature Element / Thermowell_Approved Vendor Data Receipt |  | 2026-04-17 |  | 2026-06-15 |  | 2026-02-20
A54330 | Temperature Gauges / Pressure Gauges_Approved Vendor Data Receipt |  | 29-May-25 A |  | 2026-06-16 |  | 29-May-25 A
A54340 | Analyzers_Approved Vendor Data Receipt |  | 04-Mar-25 A |  | 2026-06-16 |  | 04-Mar-25 A
A54350 | Level Gauges (Magnetic Type)_Approved Vendor Data Receipt |  | 2026-05-11 |  | 2027-09-20 |  | 2026-03-16
A54360 | Control Valves_Approved Vendor Data Receipt |  | 2026-05-11 |  | 2027-09-20 |  | 2026-03-16
A54370 | Fire & Gas Detectors_Approved Vendor Data Receipt |  | 09-Apr-25 A |  | 2026-06-16 |  | 09-Apr-25 A
A54380 | Level Transmitters (GWR type)_Approved Vendor Data Receipt |  | 2026-05-11 |  | 2027-09-20 |  | 2026-03-16
A54390 | Motor Operated Valves_Approved Vendor Data Receipt |  | 2026-05-11 |  | 2027-09-20 |  | 2026-03-16
A54400 | ESD Valves_Approved Vendor Data Receipt |  | 2026-05-11 |  | 2027-09-20 |  | 2026-03-16
A54410 | Rotameter_Approved Vendor Data Receipt |  | 23-May-25 A |  | 2026-06-16 |  | 23-May-25 A
A54420 | Instrument Cables_Approved Vendor Data Receipt |  | 2026-04-17 |  | 2026-06-15 |  | 2026-02-20
A54430 | Junction Boxes_Approved Vendor Data Receipt |  | 2026-04-30 |  | 2027-09-20 |  | 2026-03-26
A54440 | ICSS System_Approved Vendor Data Receipt |  | 2026-05-11 |  | 2027-09-20 |  | 2026-03-16
A54450 | Fire Detection System & LFCP_Approved Vendor Data Receipt |  | 2026-04-17 |  | 2026-06-15 |  | 2026-02-20
A55660 | Notice to proceed - All ICT equipment footprint & load data to freeze SIS Equipment layout |  | 23-Jun-25 A |  | 2026-06-21 |  | 23-Jun-25 A
Telecom |  | 2026-04-17 | 2026-05-11 | 2026-06-15 | 2027-09-20 | 26-Apr-25 A | 22-May-25 A
A54460 | Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_Approved Vendor Data Receipt |  | 2026-05-11 |  | 2027-09-20 |  | 2026-03-16
A54470 | Telecom Cables_Approved Vendor Data Receipt |  | 2026-04-17 |  | 2026-06-15 |  | 2026-02-20
HVAC |  | 2026-05-11 | 2026-05-11 | 2027-09-20 | 2027-09-20 | 03-Jun-25 A | 03-Jun-25 A
A54480 | HVAC Equipments_Approved Vendor Data Receipt |  | 2026-05-11 |  | 2027-09-20 |  | 2026-03-16
Workshops/Studies/ModelReviews |  | 05-May-25 A | 2026-04-27 | 2026-06-09 | 2027-03-23 | 05-May-25 A | 2026-03-16
A25330 | PHA (HAZID/ENVID/OHID) | 03-Jul-25 A | 03-Jul-25 A | 2026-06-11 | 2026-06-11 | 03-Jul-25 A | 03-Jul-25 A
A25340 | ISD Workshop | 04-Jul-25 A | 04-Jul-25 A | 2026-06-22 | 2026-06-22 | 04-Jul-25 A | 04-Jul-25 A
A25350 | HAZOP | 08-Jul-25 A | 20-Jul-25 A | 2026-06-11 | 2026-06-11 | 08-Jul-25 A | 20-Jul-25 A
A53250 | PHSER-3 | 2026-04-24 | 2026-04-27 | 2027-03-22 | 2027-03-23 | 2026-03-13 | 2026-03-16
A53260 | SIL/LOPA | 17-Aug-25 A | 20-Aug-25 A | 2026-06-11 | 2026-06-11 | 17-Aug-25 A | 20-Aug-25 A
A53270 | Energy Review | 2026-04-20 | 2026-04-21 | 2026-06-12 | 2026-06-15 | 2026-02-23 | 2026-02-24
A53350 | Design Review | 05-May-25 A | 09-May-25 A | 2026-06-09 | 2026-06-09 | 05-May-25 A | 09-May-25 A
A53360 | Plot Plan Review | 13-May-25 A | 21-May-25 A | 2026-06-09 | 2026-06-09 | 13-May-25 A | 21-May-25 A
A53370 | 30% Model Review | 13-May-25 A | 16-May-25 A | 2026-06-09 | 2026-06-09 | 13-May-25 A | 16-May-25 A
A53380 | 60% Model Review | 08-Sep-25 A | 18-Sep-25 A | 2026-06-11 | 2026-06-11 | 08-Sep-25 A | 18-Sep-25 A
A53390 | 90% Model Review | 09-Mar-26 A | 15-Mar-26 A | 2026-06-16 | 2026-06-16 | 2026-02-26 | 2026-03-06
A55680 | HSEIA Screening | 01-Jan-26 A | 06-Jan-26 A | 2026-06-22 | 2026-06-22 | 01-Jan-26 A | 06-Jan-26 A
A55690 | Bow-Tie | 12-Aug-25 A | 12-Aug-25 A | 2026-06-11 | 2026-06-11 | 12-Aug-25 A | 12-Aug-25 A
A55700 | E-HAZOP | 2026-04-17 | 2026-04-20 | 2026-06-11 | 2026-06-12 | 2026-02-20 | 2026-02-23
A55710 | ALARP Demonstration | 2026-04-17 | 2026-04-20 | 2026-06-12 | 2026-06-15 | 2026-02-20 | 2026-02-23
A55720 | SIMOPS | 28-Aug-25 A | 28-Aug-25 A | 2026-06-16 | 2026-06-16 | 28-Aug-25 A | 28-Aug-25 A
A55730 | Constructability Review | 27-Aug-25 A | 27-Aug-25 A | 2026-06-16 | 2026-06-16 | 27-Aug-25 A | 27-Aug-25 A
Turnaround(TA) |  | 27-Nov-24 A | 21-Jun-25 A | 2026-06-11 | 2026-06-16 | 27-Nov-24 A | 21-Jun-25 A
TA-EngineeringWorkpack |  | 27-Nov-24 A | 12-Apr-25 A | 2026-06-16 | 2026-06-16 | 27-Nov-24 A | 12-Apr-25 A
B1-DE-TA-TAD-0001 | Verify TA Dossier & Provid List of Missing Materials to EPC Contractor | 07-Jan-25 A | 27-Mar-25 A | 2026-06-16 | 2026-06-16 | 07-Jan-25 A | 27-Mar-25 A
B1-DE-TA-TAD-0002 | Engineering Support During Pre-TA & TA Phase | 17-Jan-25 A | 12-Apr-25 A |  |  | 17-Jan-25 A | 12-Apr-25 A
PipingDriven-Workpack |  | 27-Nov-24 A | 10-Feb-25 A | 2026-06-16 | 2026-06-16 | 27-Nov-24 A | 10-Feb-25 A
PreliminaryWorkpack |  | 27-Nov-24 A | 13-Jan-25 A | 2026-06-16 | 2026-06-16 | 27-Nov-24 A | 13-Jan-25 A
B1-DE-TA-PIP-0001 | Workpack Piping Nos. 0001 Preliminary Issuance | 27-Nov-24 A | 18-Dec-24 A | 2026-06-16 | 2026-06-16 | 27-Nov-24 A | 18-Dec-24 A
B1-DE-TA-PIP-0002 | Workpack Piping Nos. 0002 Preliminary Issuance | 27-Nov-24 A | 18-Dec-24 A | 2026-06-16 | 2026-06-16 | 27-Nov-24 A | 18-Dec-24 A
B1-DE-TA-PIP-0003 | Workpack Piping Nos. 0003 Preliminary Issuance | 27-Nov-24 A | 18-Dec-24 A | 2026-06-16 | 2026-06-16 | 27-Nov-24 A | 18-Dec-24 A
B1-DE-TA-PIP-0004 | Workpack Piping Nos. 0004 Preliminary Issuance | 27-Nov-24 A | 18-Dec-24 A | 2026-06-16 | 2026-06-16 | 27-Nov-24 A | 18-Dec-24 A
B1-DE-TA-PIP-0005 | Workpack Piping Nos. 0005 Preliminary Issuance | 27-Nov-24 A | 18-Dec-24 A | 2026-06-16 | 2026-06-16 | 27-Nov-24 A | 18-Dec-24 A
B1-DE-TA-PIP-0006 | Workpack Piping Nos. 0006 Preliminary Issuance | 27-Nov-24 A | 18-Dec-24 A | 2026-06-16 | 2026-06-16 | 27-Nov-24 A | 18-Dec-24 A
B1-DE-TA-PIP-0007 | Workpack Piping Nos. 0007 Preliminary Issuance | 27-Nov-24 A | 18-Dec-24 A | 2026-06-16 | 2026-06-16 | 27-Nov-24 A | 18-Dec-24 A
B1-DE-TA-PIP-0008 | Workpack Piping Nos. 0008 Preliminary Issuance | 27-Nov-24 A | 18-Dec-24 A | 2026-06-16 | 2026-06-16 | 27-Nov-24 A | 18-Dec-24 A
B1-DE-TA-PIP-0009 | Workpack Piping Nos. 0009 Preliminary Issuance | 27-Nov-24 A | 18-Dec-24 A | 2026-06-16 | 2026-06-16 | 27-Nov-24 A | 18-Dec-24 A
B1-DE-TA-PIP-0010 | Workpack Piping Nos. 0010 Preliminary Issuance | 27-Nov-24 A | 18-Dec-24 A | 2026-06-16 | 2026-06-16 | 27-Nov-24 A | 18-Dec-24 A
B1-DE-TA-PIP-0011 | Workpack Piping Nos. 0011 Preliminary Issuance | 27-Nov-24 A | 18-Dec-24 A | 2026-06-16 | 2026-06-16 | 27-Nov-24 A | 18-Dec-24 A
B1-DE-TA-PIP-0012 | Workpack Piping Nos. 0012 Preliminary Issuance | 27-Nov-24 A | 18-Dec-24 A | 2026-06-16 | 2026-06-16 | 27-Nov-24 A | 18-Dec-24 A
B1-DE-TA-PIP-0013 | Workpack Piping Nos. 0013 Preliminary Issuance | 27-Nov-24 A | 18-Dec-24 A | 2026-06-16 | 2026-06-16 | 27-Nov-24 A | 18-Dec-24 A
B1-DE-TA-PIP-0014 | Workpack Piping Nos. 0014 Preliminary Issuance | 27-Nov-24 A | 18-Dec-24 A | 2026-06-16 | 2026-06-16 | 27-Nov-24 A | 18-Dec-24 A
B1-DE-TA-PIP-0015 | Workpack Piping Nos. 0015 Preliminary Issuance | 27-Nov-24 A | 18-Dec-24 A | 2026-06-16 | 2026-06-16 | 27-Nov-24 A | 18-Dec-24 A
B1-DE-TA-PIP-0016 | Workpack Piping Nos. 0016 Preliminary Issuance | 27-Nov-24 A | 18-Dec-24 A | 2026-06-16 | 2026-06-16 | 27-Nov-24 A | 18-Dec-24 A
B1-DE-TA-PIP-0017 | Workpack Piping Nos. 0017 Preliminary Issuance | 27-Nov-24 A | 18-Dec-24 A | 2026-06-16 | 2026-06-16 | 27-Nov-24 A | 18-Dec-24 A
B1-DE-TA-PIP-0018 | Workpack Piping Nos. 0018 Preliminary Issuance | 27-Nov-24 A | 18-Dec-24 A | 2026-06-16 | 2026-06-16 | 27-Nov-24 A | 18-Dec-24 A
B1-DE-TA-PIP-0019 | Workpack Piping Nos. 0019 Preliminary Issuance | 27-Nov-24 A | 18-Dec-24 A | 2026-06-16 | 2026-06-16 | 27-Nov-24 A | 18-Dec-24 A
B1-DE-TA-PIP-0020 | Workpack Piping Nos. 0020 Preliminary Issuance | 27-Nov-24 A | 18-Dec-24 A | 2026-06-16 | 2026-06-16 | 27-Nov-24 A | 18-Dec-24 A
B1-DE-TA-PIP-0021 | Workpack Piping Nos. 0021 Preliminary Issuance | 27-Nov-24 A | 18-Dec-24 A | 2026-06-16 | 2026-06-16 | 27-Nov-24 A | 18-Dec-24 A
B1-DE-TA-PIP-0022 | Workpack Piping Nos. 0022 Preliminary Issuance | 27-Nov-24 A | 18-Dec-24 A | 2026-06-16 | 2026-06-16 | 27-Nov-24 A | 18-Dec-24 A
B1-DE-TA-PIP-0023 | Workpack Piping Nos. 0023 Preliminary Issuance | 27-Nov-24 A | 18-Dec-24 A | 2026-06-16 | 2026-06-16 | 27-Nov-24 A | 18-Dec-24 A
B1-DE-TA-PIP-0024 | Workpack Piping Nos. 0024 Preliminary Issuance | 27-Nov-24 A | 18-Dec-24 A | 2026-06-16 | 2026-06-16 | 27-Nov-24 A | 18-Dec-24 A
B1-DE-TA-PIP-0025 | Workpack Piping Nos. 0025 Preliminary Issuance | 27-Nov-24 A | 18-Dec-24 A | 2026-06-16 | 2026-06-16 | 27-Nov-24 A | 18-Dec-24 A
B1-DE-TA-PIP-0026 | Workpack Piping Nos. 0026 Preliminary Issuance | 27-Nov-24 A | 18-Dec-24 A | 2026-06-16 | 2026-06-16 | 27-Nov-24 A | 18-Dec-24 A
B1-DE-TA-PIP-0027 | Workpack Piping Nos. 0025 Preliminary Issuance | 27-Nov-24 A | 18-Dec-24 A | 2026-06-16 | 2026-06-16 | 27-Nov-24 A | 18-Dec-24 A
B1-DE-TA-PIP-0028 | Workpack Piping Nos. 0026 Preliminary Issuance | 27-Nov-24 A | 18-Dec-24 A | 2026-06-16 | 2026-06-16 | 27-Nov-24 A | 18-Dec-24 A
B1-DE-TA-PIP-0029 | Workpack Piping Nos. 0027 Preliminary Issuance | 27-Nov-24 A | 18-Dec-24 A | 2026-06-16 | 2026-06-16 | 27-Nov-24 A | 18-Dec-24 A
B1-DE-TA-PIP-0030 | Workpack Piping Nos. 0028 Preliminary Issuance | 27-Nov-24 A | 18-Dec-24 A | 2026-06-16 | 2026-06-16 | 27-Nov-24 A | 18-Dec-24 A
B1-DE-TA-PIP-0031 | Workpack Piping Nos. 0029 Preliminary Issuance | 27-Nov-24 A | 18-Dec-24 A | 2026-06-16 | 2026-06-16 | 27-Nov-24 A | 18-Dec-24 A
B1-DE-TA-PIP-0032 | Workpack Piping Nos. 0030 Preliminary Issuance | 17-Dec-24 A | 07-Jan-25 A | 2026-06-16 | 2026-06-16 | 17-Dec-24 A | 07-Jan-25 A
B1-DE-TA-PIP-0033 | Workpack Piping Nos. 0031 Preliminary Issuance | 17-Dec-24 A | 07-Jan-25 A | 2026-06-16 | 2026-06-16 | 17-Dec-24 A | 07-Jan-25 A
B1-DE-TA-PIP-0034 | Workpack Piping Nos. 0032 Preliminary Issuance | 17-Dec-24 A | 07-Jan-25 A | 2026-06-16 | 2026-06-16 | 17-Dec-24 A | 07-Jan-25 A
B1-DE-TA-PIP-0035 | Workpack Piping Nos. 0033 Preliminary Issuance | 17-Dec-24 A | 07-Jan-25 A | 2026-06-16 | 2026-06-16 | 17-Dec-24 A | 07-Jan-25 A
B1-DE-TA-PIP-0036 | Workpack Piping Nos. 0034 Preliminary Issuance | 17-Dec-24 A | 07-Jan-25 A | 2026-06-16 | 2026-06-16 | 17-Dec-24 A | 07-Jan-25 A
B1-DE-TA-PIP-0037 | Workpack Piping Nos. 0035 Preliminary Issuance | 17-Dec-24 A | 07-Jan-25 A | 2026-06-16 | 2026-06-16 | 17-Dec-24 A | 07-Jan-25 A
B1-DE-TA-PIP-0038 | Workpack Piping Nos. 0036 Preliminary Issuance | 17-Dec-24 A | 07-Jan-25 A | 2026-06-16 | 2026-06-16 | 17-Dec-24 A | 07-Jan-25 A
B1-DE-TA-PIP-0039 | Workpack Piping Nos. 0037 Preliminary Issuance | 17-Dec-24 A | 07-Jan-25 A | 2026-06-16 | 2026-06-16 | 17-Dec-24 A | 07-Jan-25 A
B1-DE-TA-PIP-0040 | Workpack Piping Nos. 0038 Preliminary Issuance | 17-Dec-24 A | 07-Jan-25 A | 2026-06-16 | 2026-06-16 | 17-Dec-24 A | 07-Jan-25 A
B1-DE-TA-PIP-0041 | Workpack Piping Nos. 0039 Preliminary Issuance | 17-Dec-24 A | 07-Jan-25 A | 2026-06-16 | 2026-06-16 | 17-Dec-24 A | 07-Jan-25 A
B1-DE-TA-PIP-0042 | Workpack Piping Nos. 0040 Preliminary Issuance | 17-Dec-24 A | 07-Jan-25 A | 2026-06-16 | 2026-06-16 | 17-Dec-24 A | 07-Jan-25 A
B1-DE-TA-PIP-0043 | Workpack Piping Nos. 0041 Preliminary Issuance | 23-Dec-24 A | 13-Jan-25 A | 2026-06-16 | 2026-06-16 | 23-Dec-24 A | 13-Jan-25 A
B1-DE-TA-PIP-0044 | Workpack Piping Nos. 0042 Preliminary Issuance | 23-Dec-24 A | 13-Jan-25 A | 2026-06-16 | 2026-06-16 | 23-Dec-24 A | 13-Jan-25 A
B1-DE-TA-PIP-0045 | Workpack Piping Nos. 0003 Preliminary Issuance | 23-Dec-24 A | 13-Jan-25 A | 2026-06-16 | 2026-06-16 | 23-Dec-24 A | 13-Jan-25 A
B1-DE-TA-PIP-0046 | Workpack Nos. 41 to 52 - Preliminary Issuance | 23-Dec-24 A | 13-Jan-25 A | 2026-06-16 | 2026-06-16 | 23-Dec-24 A | 13-Jan-25 A
B1-DE-TA-PIP-0047 | Workpack Nos. 41 to 52 - Preliminary Issuance | 23-Dec-24 A | 13-Jan-25 A | 2026-06-16 | 2026-06-16 | 23-Dec-24 A | 13-Jan-25 A
B1-DE-TA-PIP-0048 | Workpack Nos. 41 to 52 - Preliminary Issuance | 23-Dec-24 A | 13-Jan-25 A | 2026-06-16 | 2026-06-16 | 23-Dec-24 A | 13-Jan-25 A
B1-DE-TA-PIP-0049 | Workpack Nos. 41 to 52 - Preliminary Issuance | 23-Dec-24 A | 13-Jan-25 A | 2026-06-16 | 2026-06-16 | 23-Dec-24 A | 13-Jan-25 A
B1-DE-TA-PIP-0050 | Workpack Nos. 41 to 52 - Preliminary Issuance | 23-Dec-24 A | 13-Jan-25 A | 2026-06-16 | 2026-06-16 | 23-Dec-24 A | 13-Jan-25 A
B1-DE-TA-PIP-0051 | Workpack Nos. 41 to 52 - Preliminary Issuance | 23-Dec-24 A | 13-Jan-25 A | 2026-06-16 | 2026-06-16 | 23-Dec-24 A | 13-Jan-25 A
B1-DE-TA-PIP-0052 | Workpack Nos. 41 to 52 - Preliminary Issuance | 23-Dec-24 A | 13-Jan-25 A | 2026-06-16 | 2026-06-16 | 23-Dec-24 A | 13-Jan-25 A
FinalWorkpack |  | 19-Dec-24 A | 10-Feb-25 A | 2026-06-16 | 2026-06-16 | 19-Dec-24 A | 10-Feb-25 A
A40430 | Workpack Nos. 1 to 10 - Final Issuance | 19-Dec-24 A | 15-Jan-25 A | 2026-06-16 | 2026-06-16 | 19-Dec-24 A | 15-Jan-25 A
A40440 | Workpack Nos. 11 to 20 - Final Issuance | 19-Dec-24 A | 15-Jan-25 A | 2026-06-16 | 2026-06-16 | 19-Dec-24 A | 15-Jan-25 A
A40450 | Workpack Nos. 21 to 30 - Final Issuance | 08-Jan-25 A | 06-Feb-25 A | 2026-06-16 | 2026-06-16 | 08-Jan-25 A | 06-Feb-25 A
A40460 | Workpack Nos. 31 to 40 - Final Issuance | 08-Jan-25 A | 06-Feb-25 A | 2026-06-16 | 2026-06-16 | 08-Jan-25 A | 06-Feb-25 A
A40470 | Workpack Nos. 41 to 52 - Final Issuance | 24-Dec-24 A | 10-Feb-25 A | 2026-06-16 | 2026-06-16 | 24-Dec-24 A | 10-Feb-25 A
ICTDriven-Workpack |  | 02-Jan-25 A | 20-Jan-25 A | 2026-06-16 | 2026-06-16 | 02-Jan-25 A | 20-Jan-25 A
PreliminaryWorkpack |  | 02-Jan-25 A | 16-Jan-25 A | 2026-06-16 | 2026-06-16 | 27-Nov-24 A | 13-Jan-25 A
A40480 | Workpack Nos. 53 to 56 - Preliminary Issuance | 02-Jan-25 A | 07-Jan-25 A | 2026-06-16 | 2026-06-16 | 02-Jan-25 A | 07-Jan-25 A
A40490 | Workpack Nos. 57 to 59 - Preliminary Issuance | 02-Jan-25 A | 07-Jan-25 A | 2026-06-16 | 2026-06-16 | 02-Jan-25 A | 07-Jan-25 A
A40500 | Workpack Nos. 60 to 63 - Preliminary Issuance | 02-Jan-25 A | 07-Jan-25 A | 2026-06-16 | 2026-06-16 | 02-Jan-25 A | 07-Jan-25 A
A40510 | Workpack Nos. 64 to 67 - Preliminary Issuance | 06-Jan-25 A | 16-Jan-25 A | 2026-06-16 | 2026-06-16 | 06-Jan-25 A | 16-Jan-25 A
A40520 | Workpack Nos. 68 to 70 - Preliminary Issuance | 06-Jan-25 A | 16-Jan-25 A | 2026-06-16 | 2026-06-16 | 06-Jan-25 A | 16-Jan-25 A
FinalWorkpack |  | 08-Jan-25 A | 20-Jan-25 A | 2026-06-16 | 2026-06-16 | 19-Dec-24 A | 10-Feb-25 A
A40530 | Workpack Nos. 53 to 56 - Final Issuance | 08-Jan-25 A | 16-Jan-25 A | 2026-06-16 | 2026-06-16 | 08-Jan-25 A | 16-Jan-25 A
A40540 | Workpack Nos. 57 to 59 - Final Issuance | 08-Jan-25 A | 16-Jan-25 A | 2026-06-16 | 2026-06-16 | 08-Jan-25 A | 16-Jan-25 A
A40550 | Workpack Nos. 60 to 63 - Final Issuance | 08-Jan-25 A | 16-Jan-25 A | 2026-06-16 | 2026-06-16 | 08-Jan-25 A | 16-Jan-25 A
A40560 | Workpack Nos. 64 to 67 - Final Issuance | 17-Jan-25 A | 20-Jan-25 A | 2026-06-16 | 2026-06-16 | 17-Jan-25 A | 20-Jan-25 A
A40570 | Workpack Nos. 68 to 70 - Final Issuance | 17-Jan-25 A | 20-Jan-25 A | 2026-06-16 | 2026-06-16 | 17-Jan-25 A | 20-Jan-25 A
Civil/Structural/ArchitecturalDriven-Workpack |  | 31-Dec-24 A | 29-Jan-25 A | 2026-06-16 | 2026-06-16 | 31-Dec-24 A | 29-Jan-25 A
PreliminaryWorkpack |  | 31-Dec-24 A | 06-Jan-25 A | 2026-06-16 | 2026-06-16 | 27-Nov-24 A | 13-Jan-25 A
A40580 | Workpack No. 71 - Preliminary Issuance | 31-Dec-24 A | 03-Jan-25 A | 2026-06-16 | 2026-06-16 | 31-Dec-24 A | 03-Jan-25 A
A40590 | Workpack Nos. 72 - Preliminary Issuance | 01-Jan-25 A | 06-Jan-25 A | 2026-06-16 | 2026-06-16 | 01-Jan-25 A | 06-Jan-25 A
FinalWorkpack |  | 04-Jan-25 A | 29-Jan-25 A | 2026-06-16 | 2026-06-16 | 19-Dec-24 A | 10-Feb-25 A
A40600 | Workpack No. 71 - Final Issuance | 04-Jan-25 A | 16-Jan-25 A | 2026-06-16 | 2026-06-16 | 04-Jan-25 A | 16-Jan-25 A
A40610 | Workpack No. 72 - Final Issuance | 29-Jan-25 A | 29-Jan-25 A | 2026-06-16 | 2026-06-16 | 29-Jan-25 A | 29-Jan-25 A
ElectricalDriven-Workpack |  | 27-Dec-24 A | 17-Jan-25 A | 2026-06-16 | 2026-06-16 | 27-Dec-24 A | 17-Jan-25 A
PreliminaryWorkpack |  | 27-Dec-24 A | 02-Jan-25 A | 2026-06-16 | 2026-06-16 | 27-Nov-24 A | 13-Jan-25 A
A40650 | Workpack Nos. 73 - Preliminary Issuance | 27-Dec-24 A | 02-Jan-25 A | 2026-06-16 | 2026-06-16 | 27-Dec-24 A | 02-Jan-25 A
A40660 | Workpack Nos. 74 - Preliminary Issuance | 27-Dec-24 A | 02-Jan-25 A | 2026-06-16 | 2026-06-16 | 27-Dec-24 A | 02-Jan-25 A
A40670 | Workpack Nos. 75 - Preliminary Issuance | 27-Dec-24 A | 02-Jan-25 A | 2026-06-16 | 2026-06-16 | 27-Dec-24 A | 02-Jan-25 A
FinalWorkpack |  | 03-Jan-25 A | 17-Jan-25 A | 2026-06-16 | 2026-06-16 | 19-Dec-24 A | 10-Feb-25 A
A40620 | Workpack No. 73 - Final Issuance | 03-Jan-25 A | 17-Jan-25 A | 2026-06-16 | 2026-06-16 | 03-Jan-25 A | 17-Jan-25 A
A40630 | Workpack No. 74 - Final Issuance | 03-Jan-25 A | 17-Jan-25 A | 2026-06-16 | 2026-06-16 | 03-Jan-25 A | 17-Jan-25 A
A40640 | Workpack No. 75 - Final Issuance | 03-Jan-25 A | 17-Jan-25 A | 2026-06-16 | 2026-06-16 | 03-Jan-25 A | 17-Jan-25 A
SubcontractingSupport |  | 01-Jan-25 A | 21-Jun-25 A | 2026-06-11 | 2026-06-16 | 01-Jan-25 A | 21-Jun-25 A
SOW&RequisitionforICTSystemModification |  | 15-Jan-25 A | 28-Feb-25 A | 2026-06-16 | 2026-06-16 | 15-Jan-25 A | 28-Feb-25 A
A56050 | SOW & Requisition for ICT System Modification_IFR | 15-Jan-25 A | 30-Jan-25 A | 2026-06-16 | 2026-06-16 | 15-Jan-25 A | 30-Jan-25 A
A56060 | SOW & Requisition for ICT System Modification_RCC | 31-Jan-25 A | 12-Feb-25 A | 2026-06-16 | 2026-06-16 | 31-Jan-25 A | 12-Feb-25 A
A56070 | SOW & Requisition for ICT System Modification_IFD/IFC | 13-Feb-25 A | 28-Feb-25 A | 2026-06-16 | 2026-06-16 | 13-Feb-25 A | 28-Feb-25 A
SOW&RequisitionforElectricalSystemModification |  | 07-Jan-25 A | 14-Feb-25 A | 2026-06-16 | 2026-06-16 | 07-Jan-25 A | 14-Feb-25 A
A56080 | SOW & Requisition for Electrical System Modification_IFR | 07-Jan-25 A | 22-Jan-25 A | 2026-06-16 | 2026-06-16 | 07-Jan-25 A | 22-Jan-25 A
A56090 | SOW & Requisition for Electrical System Modification_RCC | 23-Jan-25 A | 31-Jan-25 A | 2026-06-16 | 2026-06-16 | 23-Jan-25 A | 31-Jan-25 A
A56100 | SOW & Requisition for Electrical System Modification_IFD/IFC | 03-Feb-25 A | 14-Feb-25 A | 2026-06-16 | 2026-06-16 | 03-Feb-25 A | 14-Feb-25 A
SOW&RequisitionforTopo&UGsurvey |  | 01-Jan-25 A | 05-Feb-25 A | 2026-06-15 | 2026-06-15 | 01-Jan-25 A | 05-Feb-25 A
A28870 | SOW & Requisition for Topo & UG survey_IFD/IFC | 27-Jan-25 A | 05-Feb-25 A | 2026-06-15 | 2026-06-15 | 27-Jan-25 A | 05-Feb-25 A
A56110 | SOW & Requisition for Topo & UG survey_IFR | 01-Jan-25 A | 09-Jan-25 A | 2026-06-15 | 2026-06-15 | 01-Jan-25 A | 09-Jan-25 A
A56120 | SOW & Requisition for Topo & UG survey_RCC | 13-Jan-25 A | 24-Jan-25 A | 2026-06-15 | 2026-06-15 | 13-Jan-25 A | 24-Jan-25 A
SOW&RequisitionforGeotechnicalinvestigation |  | 01-Jan-25 A | 05-Feb-25 A | 2026-06-15 | 2026-06-15 | 01-Jan-25 A | 05-Feb-25 A
A56130 | SOW & Requisition for Geotechnical investigation_IFR | 01-Jan-25 A | 09-Jan-25 A | 2026-06-15 | 2026-06-15 | 01-Jan-25 A | 09-Jan-25 A
A56140 | SOW & Requisition for Geotechnical investigation_RCC | 13-Jan-25 A | 24-Jan-25 A | 2026-06-15 | 2026-06-15 | 13-Jan-25 A | 24-Jan-25 A
A56150 | SOW & Requisition for Geotechnical investigation_IFD/IFC | 27-Jan-25 A | 05-Feb-25 A | 2026-06-15 | 2026-06-15 | 27-Jan-25 A | 05-Feb-25 A
SOW&RequisitionforThirdpartyHSEstudies |  | 30-Jan-25 A | 01-Jun-25 A | 2026-06-11 | 2026-06-11 | 30-Jan-25 A | 01-Jun-25 A
A56160 | SOW & Requisition for HSE third party studies_IFR | 30-Jan-25 A | 20-Feb-25 A | 2026-06-11 | 2026-06-11 | 30-Jan-25 A | 20-Feb-25 A
A56170 | SOW & Requisition for HSE third party studies_RCC | 21-Feb-25 A | 27-Feb-25 A | 2026-06-11 | 2026-06-11 | 21-Feb-25 A | 27-Feb-25 A
A56180 | SOW & Requisition for HSE third party studies_IFD/IFC | 28-Feb-25 A | 01-Jun-25 A | 2026-06-11 | 2026-06-11 | 28-Feb-25 A | 01-Jun-25 A
TechnicalBidEvaluationforThirdPartyHSEStudies |  | 25-Feb-25 A | 21-Jun-25 A | 2026-06-11 | 2026-06-11 | 25-Feb-25 A | 21-Jun-25 A
A55950 | Technical Bid Evaluation for Third Party HSE Studies_IFR | 25-Feb-25 A | 18-Mar-25 A | 2026-06-11 | 2026-06-11 | 25-Feb-25 A | 18-Mar-25 A
A55960 | Technical Bid Evaluation for Third Party HSE Studies_RCA | 19-Mar-25 A | 04-Jun-25 A | 2026-06-11 | 2026-06-11 | 19-Mar-25 A | 04-Jun-25 A
A55970 | Technical Bid Evaluation for Third Party HSE Studies_IFD/IFC | 05-Jun-25 A | 21-Jun-25 A | 2026-06-11 | 2026-06-11 | 05-Jun-25 A | 21-Jun-25 A
MTOSupport |  | 01-Feb-25 A | 07-Mar-25 A | 2026-06-15 | 2026-06-16 | 01-Feb-25 A | 07-Mar-25 A
A40710 | Issue Preliminary MTO for Piping Bulks | 18-Feb-25 A | 28-Feb-25 A | 2026-06-16 | 2026-06-16 | 18-Feb-25 A | 28-Feb-25 A
A40720 | Issue Preliminary MTO for Structural Steel Bulks | 17-Feb-25 A | 28-Feb-25 A | 2026-06-15 | 2026-06-15 | 17-Feb-25 A | 28-Feb-25 A
A40730 | Issue Preliminary MTO for ICT Bulks | 01-Feb-25 A | 07-Feb-25 A | 2026-06-16 | 2026-06-16 | 01-Feb-25 A | 07-Feb-25 A
A40740 | Issue Preliminary MTO for Electrical Bulks | 13-Feb-25 A | 26-Feb-25 A | 2026-06-16 | 2026-06-16 | 13-Feb-25 A | 26-Feb-25 A
A40750 | Issue Final MTO for Piping Bulks | 10-Feb-25 A | 19-Feb-25 A | 2026-06-16 | 2026-06-16 | 10-Feb-25 A | 19-Feb-25 A
A40760 | Issue Final MTO for Structural Steel Bulks | 24-Feb-25 A | 28-Feb-25 A | 2026-06-16 | 2026-06-16 | 24-Feb-25 A | 28-Feb-25 A
A40770 | Issue Final MTO for ICT Bulks | 14-Feb-25 A | 07-Mar-25 A | 2026-06-16 | 2026-06-16 | 14-Feb-25 A | 07-Mar-25 A
A40780 | Issue Final MTO for Electrical Bulks | 17-Feb-25 A | 27-Feb-25 A | 2026-06-16 | 2026-06-16 | 17-Feb-25 A | 27-Feb-25 A
BalanceofPlant |  | 28-Nov-24 A | 2026-06-26 | 2026-06-09 | 2027-03-23 | 11-Dec-24 A | 2026-09-25
General |  | 28-Nov-24 A | 20-Mar-26 A | 2026-06-11 | 2027-03-23 | 11-Dec-24 A | 2026-09-25
MasterDeliverableRegister(MDR) |  | 28-Nov-24 A | 16-Jan-25 A | 2026-06-11 | 2027-03-23 | 28-Nov-24 A | 16-Jan-25 A
A40790 | Master Deliverable Register (MDR)_IFR | 28-Nov-24 A | 19-Dec-24 A | 2026-06-11 | 2026-06-11 | 28-Nov-24 A | 19-Dec-24 A
A40800 | Master Deliverable Register (MDR)_RCC | 19-Dec-24 A | 26-Dec-24 A | 2027-03-23 | 2027-03-23 | 19-Dec-24 A | 26-Dec-24 A
A40810 | Master Deliverable Register (MDR)_IFA | 27-Dec-24 A | 02-Jan-25 A | 2027-03-23 | 2027-03-23 | 27-Dec-24 A | 02-Jan-25 A
A40820 | Master Deliverable Register (MDR)_RCA | 03-Jan-25 A | 09-Jan-25 A | 2027-03-23 | 2027-03-23 | 03-Jan-25 A | 09-Jan-25 A
A40830 | Master Deliverable Register (MDR)_IFD/IFC | 10-Jan-25 A | 16-Jan-25 A | 2027-03-23 | 2027-03-23 | 10-Jan-25 A | 16-Jan-25 A
PlanningPackage/EDDR |  | 01-Jan-25 A | 13-Apr-25 A | 2027-03-23 | 2027-03-23 | 01-Jan-25 A | 13-Apr-25 A
A40840 | Planning Package / EDDR_IFR | 01-Jan-25 A | 22-Jan-25 A | 2027-03-23 | 2027-03-23 | 01-Jan-25 A | 22-Jan-25 A
A40850 | Planning Package / EDDR_RCC | 23-Jan-25 A | 21-Mar-25 A | 2027-03-23 | 2027-03-23 | 23-Jan-25 A | 21-Mar-25 A
A40860 | Planning Package / EDDR_IFA | 22-Mar-25 A | 29-Mar-25 A | 2027-03-23 | 2027-03-23 | 22-Mar-25 A | 29-Mar-25 A
A40870 | Planning Package / EDDR_RCA | 30-Mar-25 A | 04-Apr-25 A | 2027-03-23 | 2027-03-23 | 30-Mar-25 A | 04-Apr-25 A
A40880 | Planning Package / EDDR_IFD/IFC | 07-Apr-25 A | 13-Apr-25 A | 2027-03-23 | 2027-03-23 | 07-Apr-25 A | 13-Apr-25 A
ProjectExecutionPlan |  | 03-Mar-25 A | 01-Sep-25 A | 2026-08-27 | 2026-08-27 | 03-Mar-25 A | 01-Sep-25 A
A40890 | Project Execution Plan_IFR | 03-Mar-25 A | 22-Mar-25 A | 2026-08-27 | 2026-08-27 | 03-Mar-25 A | 22-Mar-25 A
A40900 | Project Execution Plan_RCC | 23-Mar-25 A | 29-Mar-25 A | 2026-08-27 | 2026-08-27 | 23-Mar-25 A | 29-Mar-25 A
A40910 | Project Execution Plan_IFA | 30-Mar-25 A | 05-Apr-25 A | 2026-08-27 | 2026-08-27 | 30-Mar-25 A | 05-Apr-25 A
A40920 | Project Execution Plan_RCA | 31-Mar-25 A | 06-Apr-25 A | 2026-08-27 | 2026-08-27 | 31-Mar-25 A | 06-Apr-25 A
A40930 | Project Execution Plan_IFD/IFC | 31-Aug-25 A | 01-Sep-25 A | 2026-08-27 | 2026-08-27 | 31-Aug-25 A | 01-Sep-25 A
FEEDVerificationReport |  | 27-Mar-25 A | 15-May-25 A | 2026-06-11 | 2027-03-23 | 27-Mar-25 A | 15-May-25 A
A40940 | FEED Verification Report_IFR | 27-Mar-25 A | 04-Apr-25 A | 2026-06-11 | 2026-06-11 | 27-Mar-25 A | 04-Apr-25 A
A40950 | FEED Verification Report_RCC | 07-Apr-25 A | 18-Apr-25 A | 2026-06-11 | 2026-06-11 | 07-Apr-25 A | 18-Apr-25 A
A40960 | FEED Verification Report_IFA | 21-Apr-25 A | 30-Apr-25 A | 2027-03-23 | 2027-03-23 | 21-Apr-25 A | 30-Apr-25 A
A40970 | FEED Verification Report_RCA | 01-May-25 A | 08-May-25 A | 2027-03-23 | 2027-03-23 | 01-May-25 A | 08-May-25 A
A40980 | FEED Verification Report_IFD/IFC | 02-May-25 A | 15-May-25 A | 2027-03-23 | 2027-03-23 | 02-May-25 A | 15-May-25 A
SiteVisitReportforBOP |  | 15-Mar-25 A | 20-Jun-25 A | 2026-06-12 | 2026-06-12 | 15-Mar-25 A | 20-Jun-25 A
A40990 | Site Visit Report for BOP_IFR | 15-Mar-25 A | 22-Mar-25 A | 2026-06-12 | 2026-06-12 | 15-Mar-25 A | 22-Mar-25 A
A41000 | Site Visit Report for BOP_RCC | 23-Mar-25 A | 29-Mar-25 A | 2026-06-12 | 2026-06-12 | 23-Mar-25 A | 29-Mar-25 A
A41010 | Site Visit Report for BOP_IFA | 30-Mar-25 A | 05-Apr-25 A | 2026-06-12 | 2026-06-12 | 30-Mar-25 A | 05-Apr-25 A
A41020 | Site Visit Report for BOP_RCA | 06-Apr-25 A | 13-Jun-25 A | 2026-06-12 | 2026-06-12 | 06-Apr-25 A | 13-Jun-25 A
A41030 | Site Visit Report for BOP_IFD/IFC | 14-Jun-25 A | 20-Jun-25 A | 2026-06-12 | 2026-06-12 | 14-Jun-25 A | 20-Jun-25 A
ProjectRiskRegister |  | 21-Feb-25 A | 13-Sep-25 A | 2027-03-23 | 2027-03-23 | 21-Feb-25 A | 13-Sep-25 A
A41040 | Project Risk Register_IFR | 21-Feb-25 A | 10-Jun-25 A | 2027-03-23 | 2027-03-23 | 21-Feb-25 A | 10-Jun-25 A
A41050 | Project Risk Register_RCC | 30-Jul-25 A | 24-Aug-25 A | 2027-03-23 | 2027-03-23 | 30-Jul-25 A | 24-Aug-25 A
A41060 | Project Risk Register_IFA | 13-Aug-25 A | 31-Aug-25 A | 2027-03-23 | 2027-03-23 | 13-Aug-25 A | 31-Aug-25 A
A41070 | Project Risk Register_RCA | 20-Aug-25 A | 06-Sep-25 A | 2027-03-23 | 2027-03-23 | 20-Aug-25 A | 06-Sep-25 A
A41080 | Project Risk Register_IFD/IFC | 26-Aug-25 A | 13-Sep-25 A | 2027-03-23 | 2027-03-23 | 26-Aug-25 A | 13-Sep-25 A
ProjectLessonLearntRegister |  | 09-Jan-25 A | 14-Sep-25 A | 2027-03-23 | 2027-03-23 | 09-Jan-25 A | 14-Sep-25 A
A1890 | Project Lesson Learnt Register_RCC | 01-Aug-25 A | 24-Aug-25 A | 2027-03-23 | 2027-03-23 | 01-Aug-25 A | 24-Aug-25 A
A1900 | Project Lesson Learnt Register_IFA | 08-Aug-25 A | 30-Aug-25 A | 2027-03-23 | 2027-03-23 | 08-Aug-25 A | 30-Aug-25 A
A1910 | Project Lesson Learnt Register_RCA | 28-Aug-25 A | 06-Sep-25 A | 2027-03-23 | 2027-03-23 | 28-Aug-25 A | 06-Sep-25 A
A1920 | Project Lesson Learnt Register_IFD/IFC | 10-Sep-25 A | 14-Sep-25 A | 2027-03-23 | 2027-03-23 | 10-Sep-25 A | 14-Sep-25 A
A41090 | Project Lesson Learnt Register_IFR | 09-Jan-25 A | 10-Jun-25 A | 2027-03-23 | 2027-03-23 | 09-Jan-25 A | 10-Jun-25 A
CriticalityRatingReport |  | 21-Jun-25 A | 13-Sep-25 A | 2027-03-23 | 2027-03-23 | 21-Jun-25 A | 13-Sep-25 A
A1930 | Criticality Rating Report_IFR | 21-Jun-25 A | 12-Jul-25 A | 2027-03-23 | 2027-03-23 | 21-Jun-25 A | 12-Jul-25 A
A1940 | Criticality Rating Report_RCC | 08-Aug-25 A | 24-Aug-25 A | 2027-03-23 | 2027-03-23 | 08-Aug-25 A | 24-Aug-25 A
A1950 | Criticality Rating Report_IFA | 21-Aug-25 A | 30-Aug-25 A | 2027-03-23 | 2027-03-23 | 21-Aug-25 A | 30-Aug-25 A
A1960 | Criticality Rating Report_RCA | 20-Aug-25 A | 06-Sep-25 A | 2027-03-23 | 2027-03-23 | 20-Aug-25 A | 06-Sep-25 A
A1970 | Criticality Rating Report_IFD/IFC | 10-Sep-25 A | 13-Sep-25 A | 2027-03-23 | 2027-03-23 | 10-Sep-25 A | 13-Sep-25 A
ProjectCloseOutReport |  | 01-Feb-26 A | 20-Mar-26 A | 2027-03-23 | 2027-03-23 | 2026-03-23 | 2026-05-14
A41100 | Project Close Out Report_IFR | 01-Feb-26 A | 28-Feb-26 A | 2027-03-23 | 2027-03-23 | 2026-03-23 | 2026-03-25
A41110 | Project Close Out Report_RCC | 01-Mar-26 A | 10-Mar-26 A | 2027-03-23 | 2027-03-23 | 2026-03-25 | 2026-04-16
A41120 | Project Close Out Report_IFA | 03-Mar-26 A | 17-Mar-26 A | 2027-03-23 | 2027-03-23 | 2026-04-16 | 2026-04-21
A41130 | Project Close Out Report_RCA | 11-Mar-26 A | 20-Mar-26 A | 2027-03-23 | 2027-03-23 | 2026-04-21 | 2026-05-13
A41140 | Project Close Out Report_IFD/IFC | 17-Mar-26 A | 20-Mar-26 A | 2027-03-23 | 2027-03-23 | 2026-05-13 | 2026-05-14
EnergyReviewCloseoutReport |  | 01-Feb-26 A | 20-Mar-26 A | 2027-03-23 | 2027-03-23 | 2026-02-24 | 2026-05-01
A41150 | Energy Review Closeout Report_IFR | 01-Feb-26 A | 28-Feb-26 A | 2027-03-23 | 2027-03-23 | 2026-02-24 | 2026-03-11
A41160 | Energy Review Closeout Report_RCC | 04-Feb-26 A | 28-Feb-26 A | 2027-03-23 | 2027-03-23 | 2026-03-11 | 2026-04-02
A41170 | Energy Review Closeout Report_IFA | 28-Feb-26 A | 05-Mar-26 A | 2027-03-23 | 2027-03-23 | 2026-04-02 | 2026-04-07
A41180 | Energy Review Closeout Report_RCA | 01-Mar-26 A | 19-Mar-26 A | 2027-03-23 | 2027-03-23 | 2026-04-07 | 2026-04-29
A41190 | Energy Review Closeout Report_IFD/IFC | 11-Mar-26 A | 20-Mar-26 A | 2027-03-23 | 2027-03-23 | 2026-04-29 | 2026-05-01
Process |  | 27-Dec-24 A | 2026-06-09 | 2026-06-09 | 2027-03-23 | 27-Dec-24 A | 2026-04-23
UtilityDesignBasis |  | 27-Dec-24 A | 18-Aug-25 A | 2026-06-15 | 2027-03-23 | 27-Dec-24 A | 18-Aug-25 A
A41200 | Utility Design Basis_IFR | 27-Dec-24 A | 17-Jan-25 A | 2026-06-15 | 2026-06-15 | 27-Dec-24 A | 17-Jan-25 A
A41210 | Utility Design Basis_RCC | 18-Jan-25 A | 31-Jan-25 A | 2027-03-23 | 2027-03-23 | 18-Jan-25 A | 31-Jan-25 A
A41220 | Utility Design Basis_IFA | 01-Aug-25 A | 04-Aug-25 A | 2027-03-23 | 2027-03-23 | 01-Aug-25 A | 04-Aug-25 A
A41230 | Utility Design Basis_RCA | 05-Aug-25 A | 12-Aug-25 A | 2027-03-23 | 2027-03-23 | 05-Aug-25 A | 12-Aug-25 A
A41240 | Utility Design Basis_IFD/IFC | 13-Aug-25 A | 18-Aug-25 A | 2027-03-23 | 2027-03-23 | 13-Aug-25 A | 18-Aug-25 A
CriticalityRatingofSystem |  | 10-Jan-25 A | 13-Mar-26 A | 2027-03-23 | 2027-03-23 | 10-Jan-25 A | 2026-04-14
A41250 | Criticality Rating of System_IFR | 10-Jan-25 A | 06-Jun-25 A | 2027-03-23 | 2027-03-23 | 10-Jan-25 A | 06-Jun-25 A
A41260 | Criticality Rating of System_RCC | 14-Nov-25 A | 14-Nov-25 A | 2027-03-23 | 2027-03-23 | 2026-02-20 | 2026-03-13
A41270 | Criticality Rating of System_IFA | 14-Nov-25 A | 29-Nov-25 A | 2027-03-23 | 2027-03-23 | 2026-03-13 | 2026-03-19
A41280 | Criticality Rating of System_RCA | 29-Nov-25 A | 25-Dec-25 A | 2027-03-23 | 2027-03-23 | 2026-03-19 | 2026-04-09
A41290 | Criticality Rating of System_IFD/IFC | 25-Dec-25 A | 13-Mar-26 A | 2027-03-23 | 2027-03-23 | 2026-04-09 | 2026-04-14
ListOfProcessSimulationCases |  | 27-Dec-24 A | 12-Jul-25 A | 2027-03-23 | 2027-03-23 | 27-Dec-24 A | 12-Jul-25 A
A41300 | List Of Process Simulation Cases_IFR | 27-Dec-24 A | 17-Jan-25 A | 2027-03-23 | 2027-03-23 | 27-Dec-24 A | 17-Jan-25 A
A41310 | List Of Process Simulation Cases_RCC | 03-Jun-25 A | 21-Jun-25 A | 2027-03-23 | 2027-03-23 | 03-Jun-25 A | 21-Jun-25 A
A41320 | List Of Process Simulation Cases_IFA | 23-Jun-25 A | 28-Jun-25 A | 2027-03-23 | 2027-03-23 | 23-Jun-25 A | 28-Jun-25 A
A41330 | List Of Process Simulation Cases_RCA | 20-Jun-25 A | 05-Jul-25 A | 2027-03-23 | 2027-03-23 | 20-Jun-25 A | 05-Jul-25 A
A41340 | List Of Process Simulation Cases_IFD/IFC | 09-Jul-25 A | 12-Jul-25 A | 2027-03-23 | 2027-03-23 | 09-Jul-25 A | 12-Jul-25 A
IsolationPhilosophy |  | 03-Jan-25 A | 23-Dec-25 A | 2027-01-29 | 2027-03-23 | 03-Jan-25 A | 23-Dec-25 A
A3180 | Isolation Philosophy_IFR | 03-Jan-25 A | 24-Jan-25 A | 2027-01-29 | 2027-01-29 | 03-Jan-25 A | 24-Jan-25 A
A3190 | Isolation Philosophy_RCC | 18-Apr-25 A | 19-Apr-25 A | 2027-03-23 | 2027-03-23 | 18-Apr-25 A | 19-Apr-25 A
A41790 | Isolation Philosophy_IFA | 20-Apr-25 A | 13-Jun-25 A | 2027-03-23 | 2027-03-23 | 20-Apr-25 A | 13-Jun-25 A
A41800 | Isolation Philosophy_RCA | 14-Jun-25 A | 21-Jun-25 A | 2027-03-23 | 2027-03-23 | 14-Jun-25 A | 21-Jun-25 A
A41810 | Isolation Philosophy_IFD/IFC | 19-Dec-25 A | 23-Dec-25 A | 2027-03-23 | 2027-03-23 | 19-Dec-25 A | 23-Dec-25 A
ReliefandBlowdownPhilosophy |  | 09-Jan-25 A | 31-Dec-25 A | 2027-01-29 | 2027-03-23 | 09-Jan-25 A | 2026-03-17
A41820 | Relief and Blowdown Philosophy_IFR | 09-Jan-25 A | 30-Jan-25 A | 2027-01-29 | 2027-01-29 | 09-Jan-25 A | 30-Jan-25 A
A41830 | Relief and Blowdown Philosophy_RCC | 31-Jan-25 A | 20-Apr-25 A | 2027-03-23 | 2027-03-23 | 31-Jan-25 A | 20-Apr-25 A
A41840 | Relief and Blowdown Philosophy_IFA | 10-Dec-25 A | 19-Dec-25 A | 2027-03-23 | 2027-03-23 | 10-Dec-25 A | 19-Dec-25 A
A41850 | Relief and Blowdown Philosophy_RCA | 08-Apr-25 A | 08-Apr-25 A | 2027-03-23 | 2027-03-23 | 2026-02-20 | 2026-03-13
A41860 | Relief and Blowdown Philosophy_IFD/IFC | 31-Dec-25 A | 31-Dec-25 A | 2027-03-23 | 2027-03-23 | 2026-03-13 | 2026-03-17
VentandDrainPhilosophy |  | 03-Jan-25 A | 15-Feb-26 A | 2027-01-29 | 2027-03-23 | 03-Jan-25 A | 2026-04-23
A41870 | Vent and Drain Philosophy_IFR | 03-Jan-25 A | 24-Jan-25 A | 2027-01-29 | 2027-01-29 | 03-Jan-25 A | 24-Jan-25 A
A41880 | Vent and Drain Philosophy_RCC | 25-Jan-25 A | 20-Apr-25 A | 2027-03-23 | 2027-03-23 | 25-Jan-25 A | 20-Apr-25 A
A41890 | Vent and Drain Philosophy_IFA | 21-Apr-25 A | 17-Jun-25 A | 2027-03-23 | 2027-03-23 | 21-Apr-25 A | 17-Jun-25 A
A41900 | Vent and Drain Philosophy_RCA | 31-Jul-25 A | 15-Aug-25 A | 2027-03-23 | 2027-03-23 | 31-Jul-25 A | 15-Aug-25 A
A41910 | Vent and Drain Philosophy_IFD/IFC | 30-Jan-26 A | 15-Feb-26 A | 2027-03-23 | 2027-03-23 | 2026-04-21 | 2026-04-23
Operatingmanualincludingoperatingprocedure/guidelinesincludingstartupandshutdownprocedure |  | 01-Mar-26 A | 2026-06-09 | 2027-01-29 | 2027-03-23 | 2026-02-20 | 2026-04-21
A55980 | Operating manual including operating procedure/guidelines including startup and shutdown procedure_IFR | 01-Mar-26 A | 12-Mar-26 A | 2027-01-29 | 2027-01-29 | 2026-02-20 | 2026-02-27
A55990 | Operating manual including operating procedure/guidelines including startup and shutdown procedure_RCC | 2026-04-17 | 2026-05-08 | 2027-01-29 | 2027-02-22 | 2026-02-27 | 2026-03-23
A56000 | Operating manual including operating procedure/guidelines including startup and shutdown procedure_IFA | 2026-05-08 | 2026-05-14 | 2027-02-22 | 2027-02-25 | 2026-03-23 | 2026-03-26
A56010 | Operating manual including operating procedure/guidelines including startup and shutdown procedure_RCA | 2026-05-14 | 2026-06-04 | 2027-02-26 | 2027-03-19 | 2026-03-26 | 2026-04-17
A56020 | Operating manual including operating procedure/guidelines including startup and shutdown procedure_IFD/IFC | 2026-06-04 | 2026-06-09 | 2027-03-19 | 2027-03-23 | 2026-04-17 | 2026-04-21
ProcessSafeguardingDiagram:List |  | 04-Jan-25 A | 28-Jun-25 A | 2026-06-09 | 2027-01-29 | 04-Jan-25 A | 28-Jun-25 A
A41920 | Process Safeguarding Diagram: List_IFR | 04-Jan-25 A | 25-Jan-25 A | 2026-06-09 | 2026-06-09 | 04-Jan-25 A | 25-Jan-25 A
A41930 | Process Safeguarding Diagram: List_RCC | 26-Jan-25 A | 20-Feb-25 A | 2026-06-11 | 2026-06-11 | 26-Jan-25 A | 20-Feb-25 A
A41940 | Process Safeguarding Diagram: List_IFH | 21-Feb-25 A | 27-May-25 A | 2026-06-11 | 2026-06-11 | 21-Feb-25 A | 27-May-25 A
A41950 | Process Safeguarding Diagram: List_RCA | 28-May-25 A | 21-Jun-25 A | 2027-01-29 | 2027-01-29 | 28-May-25 A | 21-Jun-25 A
A41960 | Process Safeguarding Diagram: List_IFD/IFC | 22-Jun-25 A | 28-Jun-25 A | 2027-01-29 | 2027-01-29 | 22-Jun-25 A | 28-Jun-25 A
ProcessSafeguardingDiagram:FeedPretreatment |  | 04-Jan-25 A | 28-Jun-25 A | 2026-06-09 | 2027-03-23 | 04-Jan-25 A | 28-Jun-25 A
A41970 | Process Safeguarding Diagram: Feed Pretreatment_IFR | 04-Jan-25 A | 25-Jan-25 A | 2026-06-09 | 2026-06-09 | 04-Jan-25 A | 25-Jan-25 A
A41980 | Process Safeguarding Diagram: Feed Pretreatment_RCC | 26-Jan-25 A | 20-Feb-25 A | 2026-06-11 | 2026-06-11 | 26-Jan-25 A | 20-Feb-25 A
A41990 | Process Safeguarding Diagram: Feed Pretreatment_IFH | 21-Feb-25 A | 27-May-25 A | 2026-06-11 | 2026-06-11 | 21-Feb-25 A | 27-May-25 A
A42000 | Process Safeguarding Diagram: Feed Pretreatment_RCA | 28-May-25 A | 21-Jun-25 A | 2027-03-23 | 2027-03-23 | 28-May-25 A | 21-Jun-25 A
A42010 | Process Safeguarding Diagram: Feed Pretreatment_IFD/IFC | 22-Jun-25 A | 28-Jun-25 A | 2027-03-23 | 2027-03-23 | 22-Jun-25 A | 28-Jun-25 A
ProcessSafeguardingDiagram:WashWaterSystem |  | 04-Jan-25 A | 28-Jun-25 A | 2026-06-09 | 2027-03-23 | 04-Jan-25 A | 28-Jun-25 A
A42020 | Process Safeguarding Diagram: Wash Water System_IFR | 04-Jan-25 A | 25-Jan-25 A | 2026-06-09 | 2026-06-09 | 04-Jan-25 A | 25-Jan-25 A
A42030 | Process Safeguarding Diagram: Wash Water System_RCC | 26-Jan-25 A | 20-Feb-25 A | 2026-06-11 | 2026-06-11 | 26-Jan-25 A | 20-Feb-25 A
A42040 | Process Safeguarding Diagram: Wash Water System_IFH | 21-Feb-25 A | 27-May-25 A | 2026-06-11 | 2026-06-11 | 21-Feb-25 A | 27-May-25 A
A42050 | Process Safeguarding Diagram: Wash Water System_RCA | 28-May-25 A | 21-Jun-25 A | 2027-03-23 | 2027-03-23 | 28-May-25 A | 21-Jun-25 A
A42060 | Process Safeguarding Diagram: Wash Water System_IFD/IFC | 22-Jun-25 A | 28-Jun-25 A | 2027-03-23 | 2027-03-23 | 22-Jun-25 A | 28-Jun-25 A
ProcessSafeguardingDiagram:CrackedGasCompression |  | 04-Jan-25 A | 28-Jun-25 A | 2026-06-09 | 2027-03-23 | 04-Jan-25 A | 28-Jun-25 A
A42070 | Process Safeguarding Diagram: Cracked Gas Compression_IFR | 04-Jan-25 A | 25-Jan-25 A | 2026-06-09 | 2026-06-09 | 04-Jan-25 A | 25-Jan-25 A
A42080 | Process Safeguarding Diagram: Cracked Gas Compression_RCC | 26-Jan-25 A | 20-Feb-25 A | 2026-06-11 | 2026-06-11 | 26-Jan-25 A | 20-Feb-25 A
A42090 | Process Safeguarding Diagram: Cracked Gas Compression_IFH | 21-Feb-25 A | 27-May-25 A | 2026-06-11 | 2026-06-11 | 21-Feb-25 A | 27-May-25 A
A42100 | Process Safeguarding Diagram: Cracked Gas Compression_RCA | 28-May-25 A | 21-Jun-25 A | 2027-03-23 | 2027-03-23 | 28-May-25 A | 21-Jun-25 A
A42110 | Process Safeguarding Diagram: Cracked Gas Compression_IFD/IFC | 22-Jun-25 A | 28-Jun-25 A | 2027-03-23 | 2027-03-23 | 22-Jun-25 A | 28-Jun-25 A
ProcessSafeguardingDiagram:C1/C2Separation |  | 04-Jan-25 A | 28-Jun-25 A | 2026-06-09 | 2027-03-23 | 04-Jan-25 A | 28-Jun-25 A
A42120 | Process Safeguarding Diagram: C1/C2 Separation_IFR | 04-Jan-25 A | 25-Jan-25 A | 2026-06-09 | 2026-06-09 | 04-Jan-25 A | 25-Jan-25 A
A42130 | Process Safeguarding Diagram: C1/C2 Separation_RCC | 26-Jan-25 A | 20-Feb-25 A | 2026-06-11 | 2026-06-11 | 26-Jan-25 A | 20-Feb-25 A
A42140 | Process Safeguarding Diagram: C1/C2 Separation_IFH | 21-Feb-25 A | 27-May-25 A | 2026-06-11 | 2026-06-11 | 21-Feb-25 A | 27-May-25 A
A42150 | Process Safeguarding Diagram: C1/C2 Separation_RCA | 28-May-25 A | 21-Jun-25 A | 2027-03-23 | 2027-03-23 | 28-May-25 A | 21-Jun-25 A
A42160 | Process Safeguarding Diagram: C1/C2 Separation_IFD/IFC | 22-Jun-25 A | 28-Jun-25 A | 2027-03-23 | 2027-03-23 | 22-Jun-25 A | 28-Jun-25 A
ProcessSafeguardingDiagram:H2ExtractionUnit |  | 04-Jan-25 A | 28-Jun-25 A | 2026-06-09 | 2027-03-23 | 04-Jan-25 A | 28-Jun-25 A
A42170 | Process Safeguarding Diagram: H2 Extraction Unit_IFR | 04-Jan-25 A | 25-Jan-25 A | 2026-06-09 | 2026-06-09 | 04-Jan-25 A | 25-Jan-25 A
A42180 | Process Safeguarding Diagram: H2 Extraction Unit_RCC | 26-Jan-25 A | 20-Feb-25 A | 2026-06-11 | 2026-06-11 | 26-Jan-25 A | 20-Feb-25 A
A42190 | Process Safeguarding Diagram: H2 Extraction Unit_IFH | 21-Feb-25 A | 27-May-25 A | 2026-06-11 | 2026-06-11 | 21-Feb-25 A | 27-May-25 A
A42200 | Process Safeguarding Diagram: H2 Extraction Unit_RCA | 28-May-25 A | 21-Jun-25 A | 2027-03-23 | 2027-03-23 | 28-May-25 A | 21-Jun-25 A
A42210 | Process Safeguarding Diagram: H2 Extraction Unit_IFD/IFC | 22-Jun-25 A | 28-Jun-25 A | 2027-03-23 | 2027-03-23 | 22-Jun-25 A | 28-Jun-25 A
ProcessSafeguardingDiagram:H2ExtractionUnitII |  | 04-Jan-25 A | 28-Jun-25 A | 2026-06-09 | 2027-03-23 | 04-Jan-25 A | 28-Jun-25 A
A42220 | Process Safeguarding Diagram: H2 Extraction Unit II_IFR | 04-Jan-25 A | 25-Jan-25 A | 2026-06-09 | 2026-06-09 | 04-Jan-25 A | 25-Jan-25 A
A42230 | Process Safeguarding Diagram: H2 Extraction Unit II_RCC | 26-Jan-25 A | 20-Feb-25 A | 2026-06-11 | 2026-06-11 | 26-Jan-25 A | 20-Feb-25 A
A42240 | Process Safeguarding Diagram: H2 Extraction Unit II_IFH | 21-Feb-25 A | 27-May-25 A | 2026-06-11 | 2026-06-11 | 21-Feb-25 A | 27-May-25 A
A42250 | Process Safeguarding Diagram: H2 Extraction Unit II_RCA | 28-May-25 A | 21-Jun-25 A | 2027-03-23 | 2027-03-23 | 28-May-25 A | 21-Jun-25 A
A42260 | Process Safeguarding Diagram: H2 Extraction Unit II_IFD/IFC | 22-Jun-25 A | 28-Jun-25 A | 2027-03-23 | 2027-03-23 | 22-Jun-25 A | 28-Jun-25 A
ProcessSafeguardingDiagram:C4SelectiveHydrogenationIV |  | 04-Jan-25 A | 28-Jun-25 A | 2026-06-09 | 2027-03-23 | 04-Jan-25 A | 28-Jun-25 A
A42270 | Process Safeguarding Diagram: C4 Selective Hydrogenation IV_IFR | 04-Jan-25 A | 25-Jan-25 A | 2026-06-09 | 2026-06-09 | 04-Jan-25 A | 25-Jan-25 A
A42280 | Process Safeguarding Diagram: C4 Selective Hydrogenation IV_RCC | 26-Jan-25 A | 20-Feb-25 A | 2026-06-11 | 2026-06-11 | 26-Jan-25 A | 20-Feb-25 A
A42290 | Process Safeguarding Diagram: C4 Selective Hydrogenation IV_IFH | 21-Feb-25 A | 27-May-25 A | 2026-06-11 | 2026-06-11 | 21-Feb-25 A | 27-May-25 A
A42300 | Process Safeguarding Diagram: C4 Selective Hydrogenation IV_RCA | 28-May-25 A | 21-Jun-25 A | 2027-03-23 | 2027-03-23 | 28-May-25 A | 21-Jun-25 A
A42310 | Process Safeguarding Diagram: C4 Selective Hydrogenation IV_IFD/IFC | 22-Jun-25 A | 28-Jun-25 A | 2027-03-23 | 2027-03-23 | 22-Jun-25 A | 28-Jun-25 A
ProcessSafeguardingDiagram:FuelGasSystem |  | 04-Jan-25 A | 28-Jun-25 A | 2026-06-09 | 2027-03-23 | 04-Jan-25 A | 28-Jun-25 A
A42320 | Process Safeguarding Diagram: Fuel Gas System_IFR | 04-Jan-25 A | 25-Jan-25 A | 2026-06-09 | 2026-06-09 | 04-Jan-25 A | 25-Jan-25 A
A42330 | Process Safeguarding Diagram: Fuel Gas System_RCC | 26-Jan-25 A | 20-Feb-25 A | 2026-06-11 | 2026-06-11 | 26-Jan-25 A | 20-Feb-25 A
A42340 | Process Safeguarding Diagram: Fuel Gas System_IFH | 21-Feb-25 A | 27-May-25 A | 2026-06-11 | 2026-06-11 | 21-Feb-25 A | 27-May-25 A
A42350 | Process Safeguarding Diagram: Fuel Gas System_RCA | 28-May-25 A | 21-Jun-25 A | 2027-03-23 | 2027-03-23 | 28-May-25 A | 21-Jun-25 A
A42360 | Process Safeguarding Diagram: Fuel Gas System_IFD/IFC | 22-Jun-25 A | 28-Jun-25 A | 2027-03-23 | 2027-03-23 | 22-Jun-25 A | 28-Jun-25 A
ProcessSafeguardingDiagram:RegenerationSystem |  | 04-Jan-25 A | 28-Jun-25 A | 2026-06-09 | 2027-03-23 | 04-Jan-25 A | 28-Jun-25 A
A42370 | Process Safeguarding Diagram: Regeneration System_IFR | 04-Jan-25 A | 25-Jan-25 A | 2026-06-09 | 2026-06-09 | 04-Jan-25 A | 25-Jan-25 A
A42380 | Process Safeguarding Diagram: Regeneration System_RCC | 26-Jan-25 A | 20-Feb-25 A | 2026-06-11 | 2026-06-11 | 26-Jan-25 A | 20-Feb-25 A
A42390 | Process Safeguarding Diagram: Regeneration System_IFH | 21-Feb-25 A | 27-May-25 A | 2026-06-11 | 2026-06-11 | 21-Feb-25 A | 27-May-25 A
A42400 | Process Safeguarding Diagram: Regeneration System_RCA | 28-May-25 A | 21-Jun-25 A | 2027-03-23 | 2027-03-23 | 28-May-25 A | 21-Jun-25 A
A42410 | Process Safeguarding Diagram: Regeneration System_IFD/IFC | 22-Jun-25 A | 28-Jun-25 A | 2027-03-23 | 2027-03-23 | 22-Jun-25 A | 28-Jun-25 A
ProcessSafeguardingDiagram:BoilerFeedWaterSystem |  | 04-Jan-25 A | 28-Jun-25 A | 2026-06-09 | 2027-03-23 | 04-Jan-25 A | 28-Jun-25 A
A42420 | Process Safeguarding Diagram: Boiler Feed Water System_IFR | 04-Jan-25 A | 25-Jan-25 A | 2026-06-09 | 2026-06-09 | 04-Jan-25 A | 25-Jan-25 A
A42430 | Process Safeguarding Diagram: Boiler Feed Water System_RCC | 26-Jan-25 A | 20-Feb-25 A | 2026-06-11 | 2026-06-11 | 26-Jan-25 A | 20-Feb-25 A
A42440 | Process Safeguarding Diagram: Boiler Feed Water System_IFH | 21-Feb-25 A | 27-May-25 A | 2026-06-11 | 2026-06-11 | 21-Feb-25 A | 27-May-25 A
A42450 | Process Safeguarding Diagram: Boiler Feed Water System_RCA | 28-May-25 A | 21-Jun-25 A | 2027-03-23 | 2027-03-23 | 28-May-25 A | 21-Jun-25 A
A42460 | Process Safeguarding Diagram: Boiler Feed Water System_IFD/IFC | 22-Jun-25 A | 28-Jun-25 A | 2027-03-23 | 2027-03-23 | 22-Jun-25 A | 28-Jun-25 A
ProcessSafeguardingDiagram:CondensateCollectionSystem |  | 04-Jan-25 A | 28-Jun-25 A | 2026-06-09 | 2027-03-23 | 04-Jan-25 A | 28-Jun-25 A
A42470 | Process Safeguarding Diagram: Condensate Collection System_IFR | 04-Jan-25 A | 25-Jan-25 A | 2026-06-09 | 2026-06-09 | 04-Jan-25 A | 25-Jan-25 A
A42480 | Process Safeguarding Diagram: Condensate Collection System_RCC | 26-Jan-25 A | 20-Feb-25 A | 2026-06-11 | 2026-06-11 | 26-Jan-25 A | 20-Feb-25 A
A42490 | Process Safeguarding Diagram: Condensate Collection System_IFH | 21-Feb-25 A | 27-May-25 A | 2026-06-11 | 2026-06-11 | 21-Feb-25 A | 27-May-25 A
A42500 | Process Safeguarding Diagram: Condensate Collection System_RCA | 28-May-25 A | 21-Jun-25 A | 2027-03-23 | 2027-03-23 | 28-May-25 A | 21-Jun-25 A
A42510 | Process Safeguarding Diagram: Condensate Collection System_IFD/IFC | 22-Jun-25 A | 28-Jun-25 A | 2027-03-23 | 2027-03-23 | 22-Jun-25 A | 28-Jun-25 A
ProcessSafeguardingDiagram:CoolingWaterSystem |  | 04-Jan-25 A | 28-Jun-25 A | 2026-06-09 | 2027-03-23 | 04-Jan-25 A | 28-Jun-25 A
A42520 | Process Safeguarding Diagram: Cooling Water System_IFR | 04-Jan-25 A | 25-Jan-25 A | 2026-06-09 | 2026-06-09 | 04-Jan-25 A | 25-Jan-25 A
A42530 | Process Safeguarding Diagram: Cooling Water System_RCC | 26-Jan-25 A | 20-Feb-25 A | 2026-06-11 | 2026-06-11 | 26-Jan-25 A | 20-Feb-25 A
A42540 | Process Safeguarding Diagram: Cooling Water System_IFH | 21-Feb-25 A | 27-May-25 A | 2026-06-11 | 2026-06-11 | 21-Feb-25 A | 27-May-25 A
A42550 | Process Safeguarding Diagram: Cooling Water System_RCA | 28-May-25 A | 21-Jun-25 A | 2027-03-23 | 2027-03-23 | 28-May-25 A | 21-Jun-25 A
A42560 | Process Safeguarding Diagram: Cooling Water System_IFD/IFC | 22-Jun-25 A | 28-Jun-25 A | 2027-03-23 | 2027-03-23 | 22-Jun-25 A | 28-Jun-25 A
ProcessSafeguardingDiagram:UtilitySystemForH2ExtractionUnit |  | 04-Jan-25 A | 28-Jun-25 A | 2026-06-09 | 2027-03-23 | 04-Jan-25 A | 28-Jun-25 A
A42570 | Process Safeguarding Diagram: Utility System For H2 Extraction Unit_IFR | 04-Jan-25 A | 25-Jan-25 A | 2026-06-09 | 2026-06-09 | 04-Jan-25 A | 25-Jan-25 A
A42580 | Process Safeguarding Diagram: Utility System For H2 Extraction Unit_RCC | 26-Jan-25 A | 20-Feb-25 A | 2026-06-11 | 2026-06-11 | 26-Jan-25 A | 20-Feb-25 A
A42590 | Process Safeguarding Diagram: Utility System For H2 Extraction Unit_IFH | 21-Feb-25 A | 27-May-25 A | 2026-06-11 | 2026-06-11 | 21-Feb-25 A | 27-May-25 A
A42600 | Process Safeguarding Diagram: Utility System For H2 Extraction Unit_RCA | 28-May-25 A | 21-Jun-25 A | 2027-03-23 | 2027-03-23 | 28-May-25 A | 21-Jun-25 A
A42610 | Process Safeguarding Diagram: Utility System For H2 Extraction Unit_IFD/IFC | 22-Jun-25 A | 28-Jun-25 A | 2027-03-23 | 2027-03-23 | 22-Jun-25 A | 28-Jun-25 A
ProcessSafeguardingDiagram:BlowdownVesselsAndAcidGasFlare |  | 04-Jan-25 A | 28-Jun-25 A | 2026-06-09 | 2027-03-23 | 04-Jan-25 A | 28-Jun-25 A
A42620 | Process Safeguarding Diagram: Blowdown Vessels And Acid Gas Flare_IFR | 04-Jan-25 A | 25-Jan-25 A | 2026-06-09 | 2026-06-09 | 04-Jan-25 A | 25-Jan-25 A
A42630 | Process Safeguarding Diagram: Blowdown Vessels And Acid Gas Flare_RCC | 26-Jan-25 A | 20-Feb-25 A | 2026-06-11 | 2026-06-11 | 26-Jan-25 A | 20-Feb-25 A
A42640 | Process Safeguarding Diagram: Blowdown Vessels And Acid Gas Flare_IFH | 21-Feb-25 A | 27-May-25 A | 2026-06-11 | 2026-06-11 | 21-Feb-25 A | 27-May-25 A
A42650 | Process Safeguarding Diagram: Blowdown Vessels And Acid Gas Flare_RCA | 28-May-25 A | 21-Jun-25 A | 2027-03-23 | 2027-03-23 | 28-May-25 A | 21-Jun-25 A
A42660 | Process Safeguarding Diagram: Blowdown Vessels And Acid Gas Flare_IFD/IFC | 22-Jun-25 A | 28-Jun-25 A | 2027-03-23 | 2027-03-23 | 22-Jun-25 A | 28-Jun-25 A
ProcessSafeguardingDiagram:Slop,SewerAndDrainageSystem |  | 04-Jan-25 A | 28-Jun-25 A | 2026-06-09 | 2027-03-23 | 04-Jan-25 A | 28-Jun-25 A
A42670 | Process Safeguarding Diagram: Slop,Sewer And Drainage System_IFR | 04-Jan-25 A | 25-Jan-25 A | 2026-06-09 | 2026-06-09 | 04-Jan-25 A | 25-Jan-25 A
A42680 | Process Safeguarding Diagram: Slop,Sewer And Drainage System_RCC | 26-Jan-25 A | 20-Feb-25 A | 2026-06-11 | 2026-06-11 | 26-Jan-25 A | 20-Feb-25 A
A42690 | Process Safeguarding Diagram: Slop,Sewer And Drainage System_IFH | 21-Feb-25 A | 27-May-25 A | 2026-06-11 | 2026-06-11 | 21-Feb-25 A | 27-May-25 A
A42700 | Process Safeguarding Diagram: Slop,Sewer And Drainage System_RCA | 28-May-25 A | 21-Jun-25 A | 2027-03-23 | 2027-03-23 | 28-May-25 A | 21-Jun-25 A
A42710 | Process Safeguarding Diagram: Slop,Sewer And Drainage System_IFD/IFC | 22-Jun-25 A | 28-Jun-25 A | 2027-03-23 | 2027-03-23 | 22-Jun-25 A | 28-Jun-25 A
ProcessSafeguardingDiagram:Slop,SewerAndDrainageSystemII |  | 04-Jan-25 A | 28-Jun-25 A | 2026-06-09 | 2027-03-23 | 04-Jan-25 A | 28-Jun-25 A
A4130 | Process Safeguarding Diagram: Slop,Sewer And Drainage System II_IFR | 04-Jan-25 A | 25-Jan-25 A | 2026-06-09 | 2026-06-09 | 04-Jan-25 A | 25-Jan-25 A
A4140 | Process Safeguarding Diagram: Slop,Sewer And Drainage System II_RCC | 26-Jan-25 A | 20-Feb-25 A | 2026-06-11 | 2026-06-11 | 26-Jan-25 A | 20-Feb-25 A
A4150 | Process Safeguarding Diagram: Slop,Sewer And Drainage System II_IFH | 21-Feb-25 A | 27-May-25 A | 2026-06-11 | 2026-06-11 | 21-Feb-25 A | 27-May-25 A
A4160 | Process Safeguarding Diagram: Slop,Sewer And Drainage System II_RCA | 28-May-25 A | 21-Jun-25 A | 2026-06-12 | 2026-06-12 | 28-May-25 A | 21-Jun-25 A
A4170 | Process Safeguarding Diagram: Slop,Sewer And Drainage System II_IFD/IFC | 22-Jun-25 A | 28-Jun-25 A | 2027-03-23 | 2027-03-23 | 22-Jun-25 A | 28-Jun-25 A
UtilityConsumption |  | 21-Jun-25 A | 13-Feb-26 A | 2026-06-15 | 2026-06-15 | 21-Jun-25 A | 2026-02-24
A42760 | Utility Consumption_IFR | 21-Jun-25 A | 12-Jul-25 A | 2026-06-15 | 2026-06-15 | 21-Jun-25 A | 12-Jul-25 A
A42770 | Utility Consumption_RCC | 02-Oct-25 A | 22-Oct-25 A | 2026-06-15 | 2026-06-15 | 02-Oct-25 A | 22-Oct-25 A
A42780 | Utility Consumption_IFA | 16-Dec-25 A | 26-Dec-25 A | 2026-06-15 | 2026-06-15 | 16-Dec-25 A | 26-Dec-25 A
A42790 | Utility Consumption_RCA | 16-Dec-25 A | 26-Dec-25 A | 2026-06-15 | 2026-06-15 | 16-Dec-25 A | 26-Dec-25 A
A42800 | Utility Consumption_IFD/IFC | 02-Feb-26 A | 13-Feb-26 A | 2026-06-15 | 2026-06-15 | 2026-02-20 | 2026-02-24
SafeguardingMemorendum |  | 02-Sep-25 A | 23-Feb-26 A | 2027-03-23 | 2027-03-23 | 02-Sep-25 A | 2026-02-24
A4180 | Safeguarding Memorandum_IFR | 02-Sep-25 A | 13-Sep-25 A | 2027-03-23 | 2027-03-23 | 02-Sep-25 A | 13-Sep-25 A
A42720 | Safeguarding Memorandum_RCC | 17-Sep-25 A | 06-Oct-25 A | 2027-03-23 | 2027-03-23 | 17-Sep-25 A | 06-Oct-25 A
A42730 | Safeguarding Memorandum_IFA | 06-Oct-25 A | 25-Nov-25 A | 2027-03-23 | 2027-03-23 | 06-Oct-25 A | 25-Nov-25 A
A42740 | Safeguarding Memorandum_RCA | 25-Nov-25 A | 29-Dec-25 A | 2027-03-23 | 2027-03-23 | 25-Nov-25 A | 29-Dec-25 A
A42750 | Safeguarding Memorandum_IFD/IFC | 04-Feb-26 A | 23-Feb-26 A | 2027-03-23 | 2027-03-23 | 2026-02-20 | 2026-02-24
ProcessUtilityAdequacyCheckReport |  | 10-Oct-25 A | 19-Jan-26 A | 2026-06-15 | 2026-06-15 | 10-Oct-25 A | 19-Jan-26 A
A43210 | Process Utility Adequacy Check Report_IFR | 10-Oct-25 A | 17-Oct-25 A | 2026-06-15 | 2026-06-15 | 10-Oct-25 A | 17-Oct-25 A
A43220 | Process Utility Adequacy Check Report_RCC | 11-Oct-25 A | 24-Oct-25 A | 2026-06-15 | 2026-06-15 | 11-Oct-25 A | 24-Oct-25 A
A43230 | Process Utility Adequacy Check Report_IFA | 19-Dec-25 A | 24-Dec-25 A | 2026-06-15 | 2026-06-15 | 19-Dec-25 A | 24-Dec-25 A
A43240 | Process Utility Adequacy Check Report_RCA | 24-Dec-25 A | 15-Jan-26 A | 2026-06-15 | 2026-06-15 | 24-Dec-25 A | 15-Jan-26 A
A43250 | Process Utility Adequacy Check Report_IFD/IFC | 15-Jan-26 A | 19-Jan-26 A | 2026-06-15 | 2026-06-15 | 15-Jan-26 A | 19-Jan-26 A
ProcessDatasheetforPSA2FeedGasCompressor1stStageSuctionDrum |  | 31-Dec-24 A | 21-May-25 A | 2026-06-12 | 2027-03-23 | 31-Dec-24 A | 21-May-25 A
A41350 | Process Datasheet for PSA2 Feed Gas Compressor 1st Stage Suction Drum_IFR | 31-Dec-24 A | 24-Jan-25 A | 2026-06-12 | 2026-06-12 | 31-Dec-24 A | 24-Jan-25 A
A41360 | Process Datasheet for PSA2 Feed Gas Compressor 1st Stage Suction Drum_RCC | 25-Jan-25 A | 18-Mar-25 A | 2027-03-23 | 2027-03-23 | 25-Jan-25 A | 18-Mar-25 A
A41370 | Process Datasheet for PSA2 Feed Gas Compressor 1st Stage Suction Drum_IFA | 19-Mar-25 A | 19-Apr-25 A | 2027-03-23 | 2027-03-23 | 19-Mar-25 A | 19-Apr-25 A
A41380 | Process Datasheet for PSA2 Feed Gas Compressor 1st Stage Suction Drum_RCA | 20-Apr-25 A | 14-May-25 A | 2027-03-23 | 2027-03-23 | 20-Apr-25 A | 14-May-25 A
A41390 | Process Datasheet for PSA2 Feed Gas Compressor 1st Stage Suction Drum_IFD/IFC | 15-May-25 A | 21-May-25 A | 2027-03-23 | 2027-03-23 | 15-May-25 A | 21-May-25 A
ProcessDatasheetforPSA2FeedGasCompressor1stStageCooler |  | 01-Jan-25 A | 21-Jun-25 A | 2026-06-12 | 2027-03-23 | 01-Jan-25 A | 21-Jun-25 A
A41400 | Process Datasheet for PSA2 Feed Gas Compressor 1st Stage Cooler_IFR | 01-Jan-25 A | 26-Jan-25 A | 2026-06-12 | 2026-06-12 | 01-Jan-25 A | 26-Jan-25 A
A41410 | Process Datasheet for PSA2 Feed Gas Compressor 1st Stage Cooler_RCC | 27-Jan-25 A | 19-Mar-25 A | 2027-03-23 | 2027-03-23 | 27-Jan-25 A | 19-Mar-25 A
A41420 | Process Datasheet for PSA2 Feed Gas Compressor 1st Stage Cooler_IFA | 20-Mar-25 A | 20-May-25 A | 2027-03-23 | 2027-03-23 | 20-Mar-25 A | 20-May-25 A
A41430 | Process Datasheet for PSA2 Feed Gas Compressor 1st Stage Cooler_RCA | 21-May-25 A | 02-Jun-25 A | 2027-03-23 | 2027-03-23 | 21-May-25 A | 02-Jun-25 A
A41440 | Process Datasheet for PSA2 Feed Gas Compressor 1st Stage Cooler_IFD/IFC | 03-Jun-25 A | 21-Jun-25 A | 2027-03-23 | 2027-03-23 | 03-Jun-25 A | 21-Jun-25 A
ProcessDatasheetforPSA2FeedGasCompressor2ndStageSuctionDrum |  | 31-Dec-24 A | 21-May-25 A | 2026-06-12 | 2027-03-23 | 31-Dec-24 A | 21-May-25 A
A41450 | Process Datasheet for PSA2 Feed Gas Compressor 2nd Stage Suction Drum_IFR | 31-Dec-24 A | 24-Jan-25 A | 2026-06-12 | 2026-06-12 | 31-Dec-24 A | 24-Jan-25 A
A41460 | Process Datasheet for PSA2 Feed Gas Compressor 2nd Stage Suction Drum_RCC | 25-Jan-25 A | 18-Mar-25 A | 2027-03-23 | 2027-03-23 | 25-Jan-25 A | 18-Mar-25 A
A41470 | Process Datasheet for PSA2 Feed Gas Compressor 2nd Stage Suction Drum_IFA | 19-Mar-25 A | 19-Apr-25 A | 2027-03-23 | 2027-03-23 | 19-Mar-25 A | 19-Apr-25 A
A41480 | Process Datasheet for PSA2 Feed Gas Compressor 2nd Stage Suction Drum_RCA | 20-Apr-25 A | 14-May-25 A | 2027-03-23 | 2027-03-23 | 20-Apr-25 A | 14-May-25 A
A41490 | Process Datasheet for PSA2 Feed Gas Compressor 2nd Stage Suction Drum_IFD/IFC | 15-May-25 A | 21-May-25 A | 2027-03-23 | 2027-03-23 | 15-May-25 A | 21-May-25 A
ProcessDatasheetforPSA2FeedGasCompressor2ndStageCooler |  | 01-Jan-25 A | 21-Jun-25 A | 2026-06-12 | 2027-03-23 | 01-Jan-25 A | 21-Jun-25 A
A41500 | Process Datasheet for PSA2 Feed Gas Compressor 2nd Stage Cooler_IFR | 01-Jan-25 A | 26-Jan-25 A | 2026-06-12 | 2026-06-12 | 01-Jan-25 A | 26-Jan-25 A
A41510 | Process Datasheet for PSA2 Feed Gas Compressor 2nd Stage Cooler_RCC | 27-Jan-25 A | 19-Mar-25 A | 2027-03-23 | 2027-03-23 | 27-Jan-25 A | 19-Mar-25 A
A41520 | Process Datasheet for PSA2 Feed Gas Compressor 2nd Stage Cooler_IFA | 20-Mar-25 A | 20-May-25 A | 2027-03-23 | 2027-03-23 | 20-Mar-25 A | 20-May-25 A
A41530 | Process Datasheet for PSA2 Feed Gas Compressor 2nd Stage Cooler_RCA | 21-May-25 A | 02-Jun-25 A | 2027-03-23 | 2027-03-23 | 21-May-25 A | 02-Jun-25 A
A41540 | Process Datasheet for PSA2 Feed Gas Compressor 2nd Stage Cooler_IFD/IFC | 03-Jun-25 A | 21-Jun-25 A | 2027-03-23 | 2027-03-23 | 03-Jun-25 A | 21-Jun-25 A
ProcessDatasheetforPSA2FeedGasCompressor3rdStageSuctionDrum |  | 31-Dec-24 A | 20-May-25 A | 2026-06-12 | 2027-03-23 | 31-Dec-24 A | 20-May-25 A
A41550 | Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Suction Drum_IFR | 31-Dec-24 A | 24-Jan-25 A | 2026-06-12 | 2026-06-12 | 31-Dec-24 A | 24-Jan-25 A
A41560 | Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Suction Drum_RCC | 25-Jan-25 A | 18-Mar-25 A | 2027-03-23 | 2027-03-23 | 25-Jan-25 A | 18-Mar-25 A
A41570 | Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Suction Drum_IFA | 19-Mar-25 A | 19-Apr-25 A | 2027-03-23 | 2027-03-23 | 19-Mar-25 A | 19-Apr-25 A
A41580 | Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Suction Drum_RCA | 20-Apr-25 A | 13-May-25 A | 2027-03-23 | 2027-03-23 | 20-Apr-25 A | 13-May-25 A
A41590 | Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Suction Drum_IFD/IFC | 14-May-25 A | 20-May-25 A | 2027-03-23 | 2027-03-23 | 14-May-25 A | 20-May-25 A
ProcessDatasheetforPSA2FeedGasCompressor3rdStageCooler |  | 01-Jan-25 A | 20-Jul-25 A | 2026-06-12 | 2027-03-23 | 01-Jan-25 A | 20-Jul-25 A
A41600 | Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Cooler_IFR | 01-Jan-25 A | 26-Jan-25 A | 2026-06-12 | 2026-06-12 | 01-Jan-25 A | 26-Jan-25 A
A41610 | Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Cooler_RCC | 27-Jan-25 A | 19-Mar-25 A | 2027-03-23 | 2027-03-23 | 27-Jan-25 A | 19-Mar-25 A
A41620 | Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Cooler_IFA | 20-Mar-25 A | 21-Jun-25 A | 2027-03-23 | 2027-03-23 | 20-Mar-25 A | 21-Jun-25 A
A41630 | Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Cooler_RCA | 28-Jun-25 A | 14-Jul-25 A | 2027-03-23 | 2027-03-23 | 28-Jun-25 A | 14-Jul-25 A
A41640 | Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Cooler_IFD/IFC | 16-Jul-25 A | 20-Jul-25 A | 2027-03-23 | 2027-03-23 | 16-Jul-25 A | 20-Jul-25 A
ProcessDatasheetforPSA2FeedGasCompressor3rdStageDischargeDrum |  | 31-Dec-24 A | 20-May-25 A | 2026-06-12 | 2027-03-23 | 31-Dec-24 A | 20-May-25 A
A2550 | Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Discharge Drum_IFA | 19-Mar-25 A | 19-Apr-25 A | 2027-03-23 | 2027-03-23 | 19-Mar-25 A | 19-Apr-25 A
A2560 | Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Discharge Drum_RCA | 20-Apr-25 A | 13-May-25 A | 2027-03-23 | 2027-03-23 | 20-Apr-25 A | 13-May-25 A
A2570 | Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Discharge Drum_IFD/IFC | 14-May-25 A | 20-May-25 A | 2027-03-23 | 2027-03-23 | 14-May-25 A | 20-May-25 A
A41650 | Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Discharge Drum_IFR | 31-Dec-24 A | 24-Jan-25 A | 2026-06-12 | 2026-06-12 | 31-Dec-24 A | 24-Jan-25 A
A41660 | Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Discharge Drum_RCC | 25-Jan-25 A | 18-Mar-25 A | 2027-03-23 | 2027-03-23 | 25-Jan-25 A | 18-Mar-25 A
ProcessDatasheetforPSA2OffGasBufferDrum-13-VV-712 |  | 31-Dec-24 A | 12-Jun-25 A | 2026-06-12 | 2027-03-23 | 31-Dec-24 A | 12-Jun-25 A
A2580 | Process Datasheet for PSA2 Off Gas Buffer Drum - 13-VV-712_IFR | 31-Dec-24 A | 24-Jan-25 A | 2026-06-12 | 2026-06-12 | 31-Dec-24 A | 24-Jan-25 A
A2590 | Process Datasheet for PSA2 Off Gas Buffer Drum - 13-VV-712_RCC | 25-Jan-25 A | 14-May-25 A | 2027-03-23 | 2027-03-23 | 25-Jan-25 A | 14-May-25 A
A2600 | Process Datasheet for PSA2 Off Gas Buffer Drum - 13-VV-712_IFA | 15-May-25 A | 21-May-25 A | 2027-03-23 | 2027-03-23 | 15-May-25 A | 21-May-25 A
A2610 | Process Datasheet for PSA2 Off Gas Buffer Drum - 13-VV-712_RCA | 22-May-25 A | 02-Jun-25 A | 2027-03-23 | 2027-03-23 | 22-May-25 A | 02-Jun-25 A
A2620 | Process Datasheet for PSA2 Off Gas Buffer Drum - 13-VV-712_IFD/IFC | 03-Jun-25 A | 12-Jun-25 A | 2027-03-23 | 2027-03-23 | 03-Jun-25 A | 12-Jun-25 A
ProcessDatasheetforPSA2OffGasCompressorInterstageCooler-13-HE-708 |  | 01-Jan-25 A | 21-Jun-25 A | 2026-06-12 | 2027-03-23 | 01-Jan-25 A | 21-Jun-25 A
A2630 | Process Datasheet for PSA2 Off Gas Compressor Interstage Cooler - 13-HE-708_IFR | 01-Jan-25 A | 26-Jan-25 A | 2026-06-12 | 2026-06-12 | 01-Jan-25 A | 26-Jan-25 A
A2640 | Process Datasheet for PSA2 Off Gas Compressor Interstage Cooler - 13-HE-708_RCC | 27-Jan-25 A | 19-Mar-25 A | 2027-03-23 | 2027-03-23 | 27-Jan-25 A | 19-Mar-25 A
A2650 | Process Datasheet for PSA2 Off Gas Compressor Interstage Cooler - 13-HE-708_IFA | 20-Mar-25 A | 20-May-25 A | 2027-03-23 | 2027-03-23 | 20-Mar-25 A | 20-May-25 A
A2660 | Process Datasheet for PSA2 Off Gas Compressor Interstage Cooler - 13-HE-708_RCA | 21-May-25 A | 11-Jun-25 A | 2027-03-23 | 2027-03-23 | 21-May-25 A | 11-Jun-25 A
A2670 | Process Datasheet for PSA2 Off Gas Compressor Interstage Cooler - 13-HE-708_IFD/IFC | 12-Jun-25 A | 21-Jun-25 A | 2027-03-23 | 2027-03-23 | 12-Jun-25 A | 21-Jun-25 A
ProcessDatasheetforPSA2OffGasCompressor2NdStageSuctionDrum13-VV-713 |  | 31-Dec-24 A | 13-Jun-25 A | 2026-06-12 | 2027-03-23 | 31-Dec-24 A | 13-Jun-25 A
A2680 | Process Datasheet for PSA2 Off Gas Compressor 2Nd Stage Suction Drum 13-VV-713_IFR | 31-Dec-24 A | 24-Jan-25 A | 2026-06-12 | 2026-06-12 | 31-Dec-24 A | 24-Jan-25 A
A2720 | Process Datasheet for PSA2 Off Gas Compressor 2Nd Stage Suction Drum 13-VV-713_IFD/IFC | 03-Jun-25 A | 13-Jun-25 A | 2027-03-23 | 2027-03-23 | 03-Jun-25 A | 13-Jun-25 A
A41670 | Process Datasheet for PSA2 Off Gas Compressor 2Nd Stage Suction Drum 13-VV-713_RCC | 25-Jan-25 A | 14-May-25 A | 2027-03-23 | 2027-03-23 | 25-Jan-25 A | 14-May-25 A
A41680 | Process Datasheet for PSA2 Off Gas Compressor 2Nd Stage Suction Drum 13-VV-713_IFA | 15-May-25 A | 21-May-25 A | 2027-03-23 | 2027-03-23 | 15-May-25 A | 21-May-25 A
A41690 | Process Datasheet for PSA2 Off Gas Compressor 2Nd Stage Suction Drum 13-VV-713_RCA | 22-May-25 A | 02-Jun-25 A | 2027-03-23 | 2027-03-23 | 22-May-25 A | 02-Jun-25 A
ProcessDatasheetforPSA2OffGasCompressorAftercooler-13-HE-709 |  | 01-Jan-25 A | 09-Feb-26 A | 2026-06-12 | 2027-03-23 | 01-Jan-25 A | 2026-02-24
A2730 | Process Datasheet for PSA2 Off Gas Compressor Aftercooler - 13-HE-709_IFR | 01-Jan-25 A | 26-Jan-25 A | 2026-06-12 | 2026-06-12 | 01-Jan-25 A | 26-Jan-25 A
A2740 | Process Datasheet for PSA2 Off Gas Compressor Aftercooler - 13-HE-709_RCC | 27-Jan-25 A | 19-Mar-25 A | 2027-03-23 | 2027-03-23 | 27-Jan-25 A | 19-Mar-25 A
A2750 | Process Datasheet for PSA2 Off Gas Compressor Aftercooler - 13-HE-709_IFA | 20-Mar-25 A | 20-May-25 A | 2027-03-23 | 2027-03-23 | 20-Mar-25 A | 20-May-25 A
A2760 | Process Datasheet for PSA2 Off Gas Compressor Aftercooler - 13-HE-709_RCA | 21-May-25 A | 11-Jun-25 A | 2027-03-23 | 2027-03-23 | 21-May-25 A | 11-Jun-25 A
A2770 | Process Datasheet for PSA2 Off Gas Compressor Aftercooler - 13-HE-709_IFD/IFC | 03-Feb-26 A | 09-Feb-26 A | 2027-03-23 | 2027-03-23 | 2026-02-20 | 2026-02-24
ProcessDatasheetforPSA2OffGasCompressorDischargeDripleg-13-SP-7004* |  | 01-Jan-25 A | 25-Jun-25 A | 2026-06-12 | 2027-03-19 | 01-Jan-25 A | 25-Jun-25 A
A2780 | Process Datasheet for PSA2 Off Gas Compressor Discharge Dripleg - 13-SP-7004_IFR | 01-Jan-25 A | 24-Jan-25 A | 2026-06-12 | 2026-06-12 | 01-Jan-25 A | 24-Jan-25 A
A2790 | Process Datasheet for PSA2 Off Gas Compressor Discharge Dripleg - 13-SP-7004_RCC | 25-Jan-25 A | 05-May-25 A | 2027-03-19 | 2027-03-19 | 25-Jan-25 A | 05-May-25 A
A2800 | Process Datasheet for PSA2 Off Gas Compressor Discharge Dripleg - 13-SP-7004_IFA | 06-May-25 A | 11-Jun-25 A | 2027-03-19 | 2027-03-19 | 06-May-25 A | 11-Jun-25 A
A2810 | Process Datasheet for PSA2 Off Gas Compressor Discharge Dripleg - 13-SP-7004_RCA | 12-Jun-25 A | 21-Jun-25 A | 2027-03-19 | 2027-03-19 | 12-Jun-25 A | 21-Jun-25 A
A55750 | Process Datasheet for PSA2 Off Gas Compressor Discharge Dripleg - 13-SP-7004_IFD/IFC | 23-Jun-25 A | 25-Jun-25 A | 2027-03-19 | 2027-03-19 | 23-Jun-25 A | 25-Jun-25 A
ProcessDatasheetfor52-SP-14067VhpBoilerFeedWaterPreheaterDripleg |  | 01-Jan-25 A | 2026-06-05 | 2026-06-12 | 2027-03-23 | 01-Jan-25 A | 2026-04-10
A2830 | Process Datasheet for 52-SP-14067 Vhp Boiler Feed Water Preheater Dripleg_IFR | 01-Jan-25 A | 06-Jun-25 A | 2026-06-12 | 2026-06-12 | 01-Jan-25 A | 06-Jun-25 A
A2840 | Process Datasheet for 52-SP-14067 Vhp Boiler Feed Water Preheater Dripleg_RCC | 2026-04-17 | 2026-05-08 | 2027-02-02 | 2027-02-23 | 2026-02-20 | 2026-03-13
A2850 | Process Datasheet for 52-SP-14067 Vhp Boiler Feed Water Preheater Dripleg_IFA | 2026-05-08 | 2026-05-12 | 2027-02-23 | 2027-02-25 | 2026-03-13 | 2026-03-17
A41700 | Process Datasheet for 52-SP-14067 Vhp Boiler Feed Water Preheater Dripleg_RCA | 2026-05-13 | 2026-06-03 | 2027-02-26 | 2027-03-19 | 2026-03-18 | 2026-04-08
A41710 | Process Datasheet for 52-SP-14067 Vhp Boiler Feed Water Preheater Dripleg_IFD/IFC | 2026-06-03 | 2026-06-05 | 2027-03-19 | 2027-03-23 | 2026-04-08 | 2026-04-10
ProcessDatasheetfor50-HE-1410C4GuardAdsorberRegenerationGasCooler |  | 01-Jan-25 A | 20-Jan-26 A | 2026-06-12 | 2027-03-23 | 01-Jan-25 A | 2026-02-24
A2890 | Process Datasheet for 50-HE-1410 C4 Guard Adsorber Regeneration Gas Cooler_RCC | 28-Apr-25 A | 04-May-25 A | 2027-03-23 | 2027-03-23 | 28-Apr-25 A | 04-May-25 A
A2900 | Process Datasheet for 50-HE-1410 C4 Guard Adsorber Regeneration Gas Cooler_IFA | 05-May-25 A | 30-May-25 A | 2027-03-23 | 2027-03-23 | 05-May-25 A | 30-May-25 A
A2910 | Process Datasheet for 50-HE-1410 C4 Guard Adsorber Regeneration Gas Cooler_RCA | 01-Jun-25 A | 21-Jun-25 A | 2027-03-23 | 2027-03-23 | 01-Jun-25 A | 21-Jun-25 A
A2920 | Process Datasheet for 50-HE-1410 C4 Guard Adsorber Regeneration Gas Cooler_IFD/IFC | 13-Jan-26 A | 20-Jan-26 A | 2027-03-23 | 2027-03-23 | 2026-02-20 | 2026-02-24
A41720 | Process Datasheet for 50-HE-1410 C4 Guard Adsorber Regeneration Gas Cooler_IFR | 01-Jan-25 A | 27-Apr-25 A | 2026-06-12 | 2026-06-12 | 01-Jan-25 A | 27-Apr-25 A
ProcessDatasheetfor50-VV-1403C4GuardAdsorberRegenerationGasCoalescer |  | 01-Jan-25 A | 2026-05-15 | 2026-06-12 | 2027-03-23 | 01-Jan-25 A | 2026-03-20
A2980 | Process Datasheet for 50-VV-1403 C4 Guard Adsorber Regeneration Gas Coalescer_IFR | 01-Jan-25 A | 30-Jan-25 A | 2026-06-12 | 2026-06-12 | 01-Jan-25 A | 30-Jan-25 A
A2990 | Process Datasheet for 50-VV-1403 C4 Guard Adsorber Regeneration Gas Coalescer_RCC | 31-Jan-25 A | 20-Apr-25 A | 2027-02-23 | 2027-02-23 | 31-Jan-25 A | 20-Apr-25 A
A3000 | Process Datasheet for 50-VV-1403 C4 Guard Adsorber Regeneration Gas Coalescer_IFA | 2026-04-17 | 2026-04-21 | 2027-02-23 | 2027-02-25 | 2026-02-20 | 2026-02-24
A3010 | Process Datasheet for 50-VV-1403 C4 Guard Adsorber Regeneration Gas Coalescer_RCA | 2026-04-21 | 2026-05-12 | 2027-02-26 | 2027-03-19 | 2026-02-24 | 2026-03-17
A3020 | Process Datasheet for 50-VV-1403 C4 Guard Adsorber Regeneration Gas Coalescer_IFD/IFC | 2026-05-13 | 2026-05-15 | 2027-03-19 | 2027-03-23 | 2026-03-18 | 2026-03-20
ProcessDatasheetfor70-PC-1407WaterCollectionSumpPumpII |  | 01-Jan-25 A | 13-Jan-26 A | 2026-06-12 | 2027-03-23 | 01-Jan-25 A | 13-Jan-26 A
A41730 | Process Datasheet for 70-PC-1407 Water Collection Sump Pump II_IFR | 01-Jan-25 A | 24-Jan-25 A | 2026-06-12 | 2026-06-12 | 01-Jan-25 A | 24-Jan-25 A
A41740 | Process Datasheet for 70-PC-1407 Water Collection Sump Pump II_RCC | 25-Jan-25 A | 02-May-25 A | 2027-03-23 | 2027-03-23 | 25-Jan-25 A | 02-May-25 A
A41750 | Process Datasheet for 70-PC-1407 Water Collection Sump Pump II_IFA | 03-May-25 A | 19-Sep-25 A | 2027-03-23 | 2027-03-23 | 03-May-25 A | 19-Sep-25 A
A41760 | Process Datasheet for 70-PC-1407 Water Collection Sump Pump II_RCA | 19-Dec-25 A | 09-Jan-26 A | 2027-03-23 | 2027-03-23 | 19-Dec-25 A | 09-Jan-26 A
A41770 | Process Datasheet for 70-PC-1407 Water Collection Sump Pump II_IFD/IFC | 09-Jan-26 A | 13-Jan-26 A | 2027-03-23 | 2027-03-23 | 09-Jan-26 A | 13-Jan-26 A
ProcessDatasheetfor70-PC-1409A/BSanitaryWasteWaterSumpPump |  | 01-Jan-25 A | 12-Nov-25 A | 2026-06-12 | 2027-03-23 | 01-Jan-25 A | 12-Nov-25 A
A3080 | Process Datasheet for 70-PC-1409 A/B Sanitary Waste Water Sump Pump_IFR | 01-Jan-25 A | 24-Jan-25 A | 2026-06-12 | 2026-06-12 | 01-Jan-25 A | 24-Jan-25 A
A3090 | Process Datasheet for 70-PC-1409 A/B Sanitary Waste Water Sump Pump_RCC | 25-Jan-25 A | 02-May-25 A | 2027-03-23 | 2027-03-23 | 25-Jan-25 A | 02-May-25 A
A3100 | Process Datasheet for 70-PC-1409 A/B Sanitary Waste Water Sump Pump_IFA | 01-Aug-25 A | 05-Aug-25 A | 2027-03-23 | 2027-03-23 | 01-Aug-25 A | 05-Aug-25 A
A3110 | Process Datasheet for 70-PC-1409 A/B Sanitary Waste Water Sump Pump_RCA | 05-Aug-25 A | 25-Aug-25 A | 2027-03-23 | 2027-03-23 | 05-Aug-25 A | 25-Aug-25 A
A3120 | Process Datasheet for 70-PC-1409 A/B Sanitary Waste Water Sump Pump_IFD/IFC | 02-Sep-25 A | 12-Nov-25 A | 2027-03-23 | 2027-03-23 | 02-Sep-25 A | 12-Nov-25 A
ProcessDatasheetfor70-VV-1415PSA2SlopDrum |  | 01-Jan-25 A | 03-Nov-25 A | 2026-06-12 | 2027-03-23 | 01-Jan-25 A | 03-Nov-25 A
A3130 | Process Datasheet for 70-VV-1415 PSA2 Slop Drum_IFR | 01-Jan-25 A | 24-Jan-25 A | 2026-06-12 | 2026-06-12 | 01-Jan-25 A | 24-Jan-25 A
A3140 | Process Datasheet for 70-VV-1415 PSA2 Slop Drum_RCC | 25-Jan-25 A | 05-May-25 A | 2027-03-23 | 2027-03-23 | 25-Jan-25 A | 05-May-25 A
A3150 | Process Datasheet for 70-VV-1415 PSA2 Slop Drum_IFA | 06-May-25 A | 11-Jun-25 A | 2027-03-23 | 2027-03-23 | 06-May-25 A | 11-Jun-25 A
A3160 | Process Datasheet for 70-VV-1415 PSA2 Slop Drum_RCA | 12-Jun-25 A | 21-Jun-25 A | 2027-03-23 | 2027-03-23 | 12-Jun-25 A | 21-Jun-25 A
A41780 | Process Datasheet for 70-VV-1415 PSA2 Slop Drum_IFD/IFC | 24-Oct-25 A | 03-Nov-25 A | 2027-03-23 | 2027-03-23 | 24-Oct-25 A | 03-Nov-25 A
ProcessDatasheetofOff-GasCompressorCoalescer |  | 05-Jun-25 A | 12-Jul-25 A | 2027-03-23 | 2027-03-23 | 05-Jun-25 A | 12-Jul-25 A
A28230 | Process Datasheet of Off-Gas Compressor Coalescer_IFR | 18-Jun-25 A | 21-Jun-25 A | 2027-03-23 | 2027-03-23 | 18-Jun-25 A | 21-Jun-25 A
A28240 | Process Datasheet of Off-Gas Compressor Coalescer_RCC | 05-Jun-25 A | 25-Jun-25 A | 2027-03-23 | 2027-03-23 | 05-Jun-25 A | 25-Jun-25 A
A55760 | Process Datasheet of Off-Gas Compressor Coalescer_IFA | 26-Jun-25 A | 28-Jun-25 A | 2027-03-23 | 2027-03-23 | 26-Jun-25 A | 28-Jun-25 A
A55770 | Process Datasheet of Off-Gas Compressor Coalescer_RCA | 20-Jun-25 A | 05-Jul-25 A | 2027-03-23 | 2027-03-23 | 20-Jun-25 A | 05-Jul-25 A
A55780 | Process Datasheet of Off-Gas Compressor Coalescer_IFD/IFC | 10-Jul-25 A | 12-Jul-25 A | 2027-03-23 | 2027-03-23 | 10-Jul-25 A | 12-Jul-25 A
SamplePoint/ConnectionLists |  | 21-Jun-25 A | 05-Feb-26 A | 2027-03-23 | 2027-03-23 | 21-Jun-25 A | 2026-02-24
A43060 | Sample Point /Connection Lists_IFR | 21-Jun-25 A | 12-Jul-25 A | 2027-03-23 | 2027-03-23 | 21-Jun-25 A | 12-Jul-25 A
A43070 | Sample Point /Connection Lists_RCC | 01-Oct-25 A | 27-Oct-25 A | 2027-03-23 | 2027-03-23 | 01-Oct-25 A | 27-Oct-25 A
A43080 | Sample Point /Connection Lists_IFA | 28-Oct-25 A | 31-Oct-25 A | 2027-03-23 | 2027-03-23 | 28-Oct-25 A | 31-Oct-25 A
A43090 | Sample Point /Connection Lists_RCA | 01-Nov-25 A | 05-Nov-25 A | 2027-03-23 | 2027-03-23 | 01-Nov-25 A | 05-Nov-25 A
A43100 | Sample Point /Connection Lists_IFD/IFC | 29-Jan-26 A | 05-Feb-26 A | 2027-03-23 | 2027-03-23 | 2026-02-20 | 2026-02-24
ProcessCalculationReport |  | 20-Feb-25 A | 2026-05-18 | 2027-02-22 | 2027-03-23 | 20-Feb-25 A | 2026-03-23
A42960 | Process Calculation Report_IFR | 20-Feb-25 A | 26-Dec-25 A | 2027-02-22 | 2027-02-22 | 20-Feb-25 A | 26-Dec-25 A
A42970 | Process Calculation Report_RCC | 26-Dec-25 A | 10-Jan-26 A | 2027-02-22 | 2027-02-22 | 26-Dec-25 A | 10-Jan-26 A
A42980 | Process Calculation Report_IFA | 2026-04-17 | 2026-04-22 | 2027-02-22 | 2027-02-25 | 2026-02-20 | 2026-02-25
A42990 | Process Calculation Report_RCA | 2026-04-22 | 2026-05-14 | 2027-02-26 | 2027-03-19 | 2026-02-25 | 2026-03-19
A43000 | Process Calculation Report_IFD/IFC | 2026-05-14 | 2026-05-18 | 2027-03-19 | 2027-03-23 | 2026-03-19 | 2026-03-23
ProcessDatasheetforControlValve |  | 20-Feb-25 A | 12-Jul-25 A | 2026-06-12 | 2027-03-23 | 20-Feb-25 A | 12-Jul-25 A
A42810 | Process Datasheet for Control Valve_IFR | 20-Feb-25 A | 27-Apr-25 A | 2026-06-12 | 2026-06-12 | 20-Feb-25 A | 27-Apr-25 A
A42820 | Process Datasheet for Control Valve_RCC | 28-Apr-25 A | 21-Jun-25 A | 2027-03-23 | 2027-03-23 | 28-Apr-25 A | 21-Jun-25 A
A42830 | Process Datasheet for Control Valve_IFA | 22-Jun-25 A | 28-Jun-25 A | 2027-03-23 | 2027-03-23 | 22-Jun-25 A | 28-Jun-25 A
A42840 | Process Datasheet for Control Valve_RCA | 29-Jun-25 A | 05-Jul-25 A | 2027-03-23 | 2027-03-23 | 29-Jun-25 A | 05-Jul-25 A
A42850 | Process Datasheet for Control Valve_IFD/IFC | 06-Jul-25 A | 12-Jul-25 A | 2027-03-23 | 2027-03-23 | 06-Jul-25 A | 12-Jul-25 A
ProcessDatasheetforReliefValve |  | 25-Jan-25 A | 19-Jan-26 A | 2026-06-12 | 2027-03-23 | 25-Jan-25 A | 19-Jan-26 A
A42860 | Process Datasheet for Relief Valve_IFR | 25-Jan-25 A | 20-Apr-25 A | 2026-06-12 | 2026-06-12 | 25-Jan-25 A | 20-Apr-25 A
A42870 | Process Datasheet for Relief Valve_RCC | 16-Jul-25 A | 01-Aug-25 A | 2027-03-23 | 2027-03-23 | 16-Jul-25 A | 01-Aug-25 A
A42880 | Process Datasheet for Relief Valve_IFA | 19-Dec-25 A | 24-Dec-25 A | 2027-03-23 | 2027-03-23 | 19-Dec-25 A | 24-Dec-25 A
A42890 | Process Datasheet for Relief Valve_RCA | 24-Dec-25 A | 15-Jan-26 A | 2027-03-23 | 2027-03-23 | 24-Dec-25 A | 15-Jan-26 A
A42900 | Process Datasheet for Relief Valve_IFD/IFC | 15-Jan-26 A | 19-Jan-26 A | 2027-03-23 | 2027-03-23 | 15-Jan-26 A | 19-Jan-26 A
ProcessDatasheetforFlowInstrument |  | 20-Feb-25 A | 2026-04-21 | 2026-06-12 | 2027-03-23 | 20-Feb-25 A | 2026-03-23
A42910 | Process Datasheet for Flow Instrument_IFR | 20-Feb-25 A | 25-Apr-25 A | 2026-06-12 | 2026-06-12 | 20-Feb-25 A | 25-Apr-25 A
A42920 | Process Datasheet for Flow Instrument_RCC | 26-Apr-25 A | 26-May-25 A | 2027-03-19 | 2027-03-19 | 26-Apr-25 A | 26-May-25 A
A42930 | Process Datasheet for Flow Instrument_IFA | 03-Nov-25 A | 16-Nov-25 A | 2027-03-19 | 2027-03-19 | 2026-02-20 | 2026-02-25
A42940 | Process Datasheet for Flow Instrument_RCA | 16-Nov-25 A | 27-Nov-25 A | 2027-03-19 | 2027-03-19 | 2026-02-25 | 2026-03-19
A42950 | Process Datasheet for Flow Instrument_IFD/IFC | 2026-04-17 | 2026-04-21 | 2027-03-19 | 2027-03-23 | 2026-03-19 | 2026-03-23
FlareReliefLoadSummary |  | 31-Jan-25 A | 20-Mar-26 A | 2026-06-15 | 2026-06-15 | 31-Jan-25 A | 2026-02-24
A43160 | Flare Relief Load Summary_IFR | 31-Jan-25 A | 11-Mar-25 A | 2026-06-15 | 2026-06-15 | 31-Jan-25 A | 11-Mar-25 A
A43170 | Flare Relief Load Summary_RCC | 12-Mar-25 A | 20-Apr-25 A | 2026-06-15 | 2026-06-15 | 12-Mar-25 A | 20-Apr-25 A
A43180 | Flare Relief Load Summary_IFA | 09-Dec-25 A | 19-Dec-25 A | 2026-06-15 | 2026-06-15 | 09-Dec-25 A | 19-Dec-25 A
A43190 | Flare Relief Load Summary_RCA | 16-Dec-25 A | 13-Feb-26 A | 2026-06-15 | 2026-06-15 | 16-Dec-25 A | 13-Feb-26 A
A43200 | Flare Relief Load Summary_IFD/IFC | 18-Mar-26 A | 20-Mar-26 A | 2026-06-15 | 2026-06-15 | 2026-02-20 | 2026-02-24
FlareRelief&BlowdownReport |  | 03-May-25 A | 20-Mar-26 A | 2027-02-22 | 2027-03-23 | 03-May-25 A | 2026-03-17
A43110 | Flare Relief & Blowdown Report_IFR | 03-May-25 A | 11-May-25 A | 2027-02-22 | 2027-02-22 | 03-May-25 A | 11-May-25 A
A43120 | Flare Relief & Blowdown Report_RCC | 05-May-25 A | 18-May-25 A | 2027-03-23 | 2027-03-23 | 05-May-25 A | 18-May-25 A
A43130 | Flare Relief & Blowdown Report_IFA | 05-Dec-25 A | 19-Dec-25 A | 2027-03-23 | 2027-03-23 | 05-Dec-25 A | 19-Dec-25 A
A43140 | Flare Relief & Blowdown Report_RCA | 04-Feb-26 A | 17-Feb-26 A | 2027-03-23 | 2027-03-23 | 2026-02-20 | 2026-03-13
A43150 | Flare Relief & Blowdown Report_IFD/IFC | 18-Mar-26 A | 20-Mar-26 A | 2027-03-23 | 2027-03-23 | 2026-03-13 | 2026-03-17
DynamicFlareSimulationStudy |  | 20-Mar-26 A | 2026-05-18 | 2027-02-22 | 2027-03-23 | 2026-02-20 | 2026-04-21
A43010 | Dynamic Flare Simulation Study_IFR | 20-Mar-26 A | 27-Mar-26 A | 2027-02-22 | 2027-02-22 | 2026-02-20 | 2026-02-27
A43020 | Dynamic Flare Simulation Study_RCC | 27-Mar-26 A | 17-Apr-26 A | 2027-02-22 | 2027-02-22 | 2026-02-27 | 2026-03-23
A43030 | Dynamic Flare Simulation Study_IFA | 2026-04-17 | 2026-04-22 | 2027-02-22 | 2027-02-25 | 2026-03-23 | 2026-03-26
A43040 | Dynamic Flare Simulation Study_RCA | 2026-04-22 | 2026-05-14 | 2027-02-26 | 2027-03-19 | 2026-03-26 | 2026-04-17
A43050 | Dynamic Flare Simulation Study_IFD/IFC | 2026-05-14 | 2026-05-18 | 2027-03-19 | 2027-03-23 | 2026-04-17 | 2026-04-21
Piping |  | 16-Jan-25 A | 2026-06-26 | 2026-06-09 | 2027-03-23 | 03-Feb-25 A | 24-Feb-25 A
3DModellingProcedure |  | 01-Mar-25 A | 15-Oct-25 A | 2026-06-09 | 2027-03-23 | 01-Mar-25 A | 15-Oct-25 A
A43260 | 3D Modelling Procedure_IFR | 01-Mar-25 A | 20-Apr-25 A | 2026-06-09 | 2026-06-09 | 01-Mar-25 A | 20-Apr-25 A
A43270 | 3D Modelling Procedure_RCC | 21-Apr-25 A | 28-Apr-25 A | 2027-03-23 | 2027-03-23 | 21-Apr-25 A | 28-Apr-25 A
A43280 | 3D Modelling Procedure_IFA | 29-Apr-25 A | 21-Jun-25 A | 2027-03-23 | 2027-03-23 | 29-Apr-25 A | 21-Jun-25 A
A43290 | 3D Modelling Procedure_RCA | 01-Aug-25 A | 23-Aug-25 A | 2027-03-23 | 2027-03-23 | 01-Aug-25 A | 23-Aug-25 A
A43300 | 3D Modelling Procedure_IFD/IFC | 12-Oct-25 A | 15-Oct-25 A | 2027-03-23 | 2027-03-23 | 12-Oct-25 A | 15-Oct-25 A
3DModelExecutionPhilosophy |  | 25-Mar-25 A | 14-Oct-25 A | 2027-02-09 | 2027-03-23 | 25-Mar-25 A | 14-Oct-25 A
A55400 | 3D Model Execution Philosophy_IFR | 25-Mar-25 A | 15-Apr-25 A | 2027-02-09 | 2027-02-09 | 25-Mar-25 A | 15-Apr-25 A
A55410 | 3D Model Execution Philosophy_RCC | 16-Apr-25 A | 28-Apr-25 A | 2027-03-23 | 2027-03-23 | 16-Apr-25 A | 28-Apr-25 A
A55420 | 3D Model Execution Philosophy_IFA | 29-Apr-25 A | 21-Jun-25 A | 2027-03-23 | 2027-03-23 | 29-Apr-25 A | 21-Jun-25 A
A55430 | 3D Model Execution Philosophy_RCA | 20-Jul-25 A | 08-Aug-25 A | 2027-03-23 | 2027-03-23 | 20-Jul-25 A | 08-Aug-25 A
A55440 | 3D Model Execution Philosophy_IFD/IFC | 11-Oct-25 A | 14-Oct-25 A | 2027-03-23 | 2027-03-23 | 11-Oct-25 A | 14-Oct-25 A
3DModelReviewProcedure |  | 25-Mar-25 A | 23-Dec-25 A | 2027-03-23 | 2027-03-23 | 25-Mar-25 A | 23-Dec-25 A
A43310 | 3D Model Review Procedure_IFR | 25-Mar-25 A | 15-Apr-25 A | 2027-03-23 | 2027-03-23 | 25-Mar-25 A | 15-Apr-25 A
A43320 | 3D Model Review Procedure_RCC | 16-Apr-25 A | 28-Apr-25 A | 2027-03-23 | 2027-03-23 | 16-Apr-25 A | 28-Apr-25 A
A43330 | 3D Model Review Procedure_IFA | 29-Apr-25 A | 21-Jun-25 A | 2027-03-23 | 2027-03-23 | 29-Apr-25 A | 21-Jun-25 A
A43340 | 3D Model Review Procedure_RCA | 22-Jun-25 A | 05-Sep-25 A | 2027-03-23 | 2027-03-23 | 22-Jun-25 A | 05-Sep-25 A
A43350 | 3D Model Review Procedure_IFD/IFC | 19-Dec-25 A | 23-Dec-25 A | 2027-03-23 | 2027-03-23 | 19-Dec-25 A | 23-Dec-25 A
ClashCheckProcedure |  | 22-Mar-25 A | 11-May-25 A | 2027-02-09 | 2027-03-23 | 22-Mar-25 A | 11-May-25 A
A27870 | Clash Check Procedure_RCC | 13-Apr-25 A | 20-Apr-25 A | 2027-03-23 | 2027-03-23 | 13-Apr-25 A | 20-Apr-25 A
A27880 | Clash Check Procedure_IFA | 21-Apr-25 A | 27-Apr-25 A | 2027-03-23 | 2027-03-23 | 21-Apr-25 A | 27-Apr-25 A
A55450 | Clash Check Procedure_IFR | 22-Mar-25 A | 12-Apr-25 A | 2027-02-09 | 2027-02-09 | 22-Mar-25 A | 12-Apr-25 A
A55460 | Clash Check Procedure_RCA | 28-Apr-25 A | 04-May-25 A | 2027-03-23 | 2027-03-23 | 28-Apr-25 A | 04-May-25 A
A55470 | Clash Check Procedure_IFD/IFC | 05-May-25 A | 11-May-25 A | 2027-03-23 | 2027-03-23 | 05-May-25 A | 11-May-25 A
DeliverablesExtractionProcedure |  | 23-Jan-25 A | 12-Mar-25 A | 2027-02-09 | 2027-03-23 | 23-Jan-25 A | 12-Mar-25 A
A55480 | Deliverables Extraction Procedure_IFR | 23-Jan-25 A | 12-Feb-25 A | 2027-02-09 | 2027-02-09 | 23-Jan-25 A | 12-Feb-25 A
A55490 | Deliverables Extraction Procedure_RCC | 13-Feb-25 A | 19-Feb-25 A | 2027-03-23 | 2027-03-23 | 13-Feb-25 A | 19-Feb-25 A
A55500 | Deliverables Extraction Procedure_IFA | 20-Feb-25 A | 26-Feb-25 A | 2027-03-23 | 2027-03-23 | 20-Feb-25 A | 26-Feb-25 A
A55510 | Deliverables Extraction Procedure_RCA | 27-Feb-25 A | 05-Mar-25 A | 2027-03-23 | 2027-03-23 | 27-Feb-25 A | 05-Mar-25 A
A55520 | Deliverables Extraction Procedure_IFD/IFC | 06-Mar-25 A | 12-Mar-25 A | 2027-03-23 | 2027-03-23 | 06-Mar-25 A | 12-Mar-25 A
DataHandoverProcedure |  | 21-Jun-25 A | 12-Jul-25 A | 2027-02-09 | 2027-02-09 | 21-Jun-25 A | 2026-04-14
A27960 | Data Handover Procedure_IFR | 21-Jun-25 A | 12-Jul-25 A | 2027-02-09 | 2027-02-09 | 21-Jun-25 A | 12-Jul-25 A
A27970 | Data Handover Procedure_RCC | 25-Jun-25 A | 25-Jun-25 A | 2027-02-09 | 2027-02-09 | 2026-02-20 | 2026-03-13
A55530 | Data Handover Procedure_IFA | 26-Jun-25 A | 26-Jun-25 A | 2027-02-09 | 2027-02-09 | 2026-03-13 | 2026-03-19
A55540 | Data Handover Procedure_RCA | 27-Jun-25 A | 27-Jun-25 A | 2027-02-09 | 2027-02-09 | 2026-03-19 | 2026-04-09
A55550 | Data Handover Procedure_IFD/IFC | 30-Jun-25 A | 30-Jun-25 A | 2027-02-09 | 2027-02-09 | 2026-04-09 | 2026-04-14
StressCriticalLineList |  | 15-Apr-25 A | 2026-05-12 | 2027-02-26 | 2027-03-23 | 15-Apr-25 A | 2026-03-17
A43460 | Stress Critical Line List_IFR | 15-Apr-25 A | 06-May-25 A | 2027-02-26 | 2027-02-26 | 15-Apr-25 A | 06-May-25 A
A43470 | Stress Critical Line List_RCC | 07-May-25 A | 13-May-25 A | 2027-02-26 | 2027-02-26 | 07-May-25 A | 13-May-25 A
A43480 | Stress Critical Line List_IFA | 04-Dec-25 A | 19-Dec-25 A | 2027-02-26 | 2027-02-26 | 04-Dec-25 A | 19-Dec-25 A
A43490 | Stress Critical Line List_RCA | 2026-04-17 | 2026-05-08 | 2027-02-26 | 2027-03-19 | 2026-02-20 | 2026-03-13
A43500 | Stress Critical Line List_IFD/IFC | 2026-05-08 | 2026-05-12 | 2027-03-19 | 2027-03-23 | 2026-03-13 | 2026-03-17
DatasheetsforBallValves |  | 16-Jan-25 A | 21-Nov-25 A | 2026-06-11 | 2026-06-11 | 16-Jan-25 A | 21-Nov-25 A
A43660 | Datasheets for Ball Valves_IFR | 16-Jan-25 A | 14-May-25 A | 2026-06-11 | 2026-06-11 | 16-Jan-25 A | 14-May-25 A
A43670 | Datasheets for Ball Valves_RCC | 01-Aug-25 A | 25-Aug-25 A | 2026-06-11 | 2026-06-11 | 01-Aug-25 A | 25-Aug-25 A
A43680 | Datasheets for Ball Valves_IFA | 22-Oct-25 A | 30-Oct-25 A | 2026-06-11 | 2026-06-11 | 22-Oct-25 A | 30-Oct-25 A
A43690 | Datasheets for Ball Valves_RCA | 31-Oct-25 A | 07-Nov-25 A | 2026-06-11 | 2026-06-11 | 31-Oct-25 A | 07-Nov-25 A
A43700 | Datasheets for Ball Valves_IFD/IFC | 10-Nov-25 A | 21-Nov-25 A | 2026-06-11 | 2026-06-11 | 10-Nov-25 A | 21-Nov-25 A
DatasheetsforDoubleBlock&BleedValves |  | 27-Jan-25 A | 22-Aug-25 A | 2026-06-11 | 2026-06-16 | 27-Jan-25 A | 22-Aug-25 A
A43760 | Datasheets for Double Block & Bleed Valves_IFR | 27-Jan-25 A | 01-Aug-25 A | 2026-06-11 | 2026-06-11 | 27-Jan-25 A | 01-Aug-25 A
A43770 | Datasheets for Double Block & Bleed Valves_RCC | 02-Aug-25 A | 10-Aug-25 A | 2026-06-16 | 2026-06-16 | 02-Aug-25 A | 10-Aug-25 A
A43780 | Datasheets for Double Block & Bleed Valves_IFA | 11-Aug-25 A | 15-Aug-25 A | 2026-06-16 | 2026-06-16 | 11-Aug-25 A | 15-Aug-25 A
A43790 | Datasheets for Double Block & Bleed Valves_RCA | 16-Aug-25 A | 20-Aug-25 A | 2026-06-16 | 2026-06-16 | 16-Aug-25 A | 20-Aug-25 A
A43800 | Datasheets for Double Block & Bleed Valves_IFD/IFC | 21-Aug-25 A | 22-Aug-25 A | 2026-06-16 | 2026-06-16 | 21-Aug-25 A | 22-Aug-25 A
DatasheetsforCheckValves |  | 23-Jan-25 A | 17-Nov-25 A | 2026-06-11 | 2026-06-16 | 23-Jan-25 A | 17-Nov-25 A
A43710 | Datasheets for Check Valves_IFR | 23-Jan-25 A | 14-May-25 A | 2026-06-11 | 2026-06-11 | 23-Jan-25 A | 14-May-25 A
A43720 | Datasheets for Check Valves_RCC | 15-May-25 A | 21-Jun-25 A | 2026-06-16 | 2026-06-16 | 15-May-25 A | 21-Jun-25 A
A43730 | Datasheets for Check Valves_IFA | 06-Aug-25 A | 12-Aug-25 A | 2026-06-16 | 2026-06-16 | 06-Aug-25 A | 12-Aug-25 A
A43740 | Datasheets for Check Valves_RCA | 02-Sep-25 A | 03-Nov-25 A | 2026-06-16 | 2026-06-16 | 02-Sep-25 A | 03-Nov-25 A
A43750 | Datasheets for Check Valves_IFD/IFC | 04-Nov-25 A | 17-Nov-25 A | 2026-06-16 | 2026-06-16 | 04-Nov-25 A | 17-Nov-25 A
DatasheetsforButterflyValves |  | 16-Jan-25 A | 20-Nov-25 A | 2026-06-11 | 2026-06-16 | 16-Jan-25 A | 20-Nov-25 A
A43810 | Datasheets for Butterfly Valves_IFR | 16-Jan-25 A | 12-Jun-25 A | 2026-06-11 | 2026-06-11 | 16-Jan-25 A | 12-Jun-25 A
A43820 | Datasheets for Butterfly Valves_RCC | 04-Aug-25 A | 27-Aug-25 A | 2026-06-16 | 2026-06-16 | 04-Aug-25 A | 27-Aug-25 A
A43830 | Datasheets for Butterfly Valves_IFA | 31-Aug-25 A | 03-Sep-25 A | 2026-06-16 | 2026-06-16 | 31-Aug-25 A | 03-Sep-25 A
A43840 | Datasheets for Butterfly Valves_RCA | 20-Sep-25 A | 13-Oct-25 A | 2026-06-16 | 2026-06-16 | 20-Sep-25 A | 13-Oct-25 A
A43850 | Datasheets for Butterfly Valves_IFD/IFC | 10-Nov-25 A | 20-Nov-25 A | 2026-06-16 | 2026-06-16 | 10-Nov-25 A | 20-Nov-25 A
DatasheetsforNeedleValves |  | 01-Aug-25 A | 22-Aug-25 A | 2026-06-11 | 2026-06-16 | 01-Aug-25 A | 22-Aug-25 A
A43860 | Datasheets for Needle Valves_IFR | 01-Aug-25 A | 05-Aug-25 A | 2026-06-11 | 2026-06-11 | 01-Aug-25 A | 05-Aug-25 A
A43870 | Datasheets for Needle Valves_RCC | 06-Aug-25 A | 12-Aug-25 A | 2026-06-16 | 2026-06-16 | 06-Aug-25 A | 12-Aug-25 A
A43880 | Datasheets for Needle Valves_IFA | 13-Aug-25 A | 15-Aug-25 A | 2026-06-16 | 2026-06-16 | 13-Aug-25 A | 15-Aug-25 A
A43890 | Datasheets for Needle Valves_RCA | 16-Aug-25 A | 20-Aug-25 A | 2026-06-16 | 2026-06-16 | 16-Aug-25 A | 20-Aug-25 A
A43900 | Datasheets for Needle Valves_IFD/IFC | 20-Aug-25 A | 22-Aug-25 A | 2026-06-16 | 2026-06-16 | 20-Aug-25 A | 22-Aug-25 A
DatasheetsforInsulatingGaskets |  | 22-Sep-25 A | 13-Jan-26 A | 2026-06-11 | 2026-06-11 | 22-Sep-25 A | 13-Jan-26 A
A43910 | Datasheets for Insulating Gaskets_IFR | 22-Sep-25 A | 29-Sep-25 A | 2026-06-11 | 2026-06-11 | 22-Sep-25 A | 29-Sep-25 A
A43920 | Datasheets for Insulating Gaskets_RCC | 23-Sep-25 A | 06-Oct-25 A | 2026-06-11 | 2026-06-11 | 23-Sep-25 A | 06-Oct-25 A
A43930 | Datasheets for Insulating Gaskets_IFA | 03-Dec-25 A | 18-Dec-25 A | 2026-06-11 | 2026-06-11 | 03-Dec-25 A | 18-Dec-25 A
A43940 | Datasheets for Insulating Gaskets_RCA | 19-Dec-25 A | 09-Jan-26 A | 2026-06-11 | 2026-06-11 | 19-Dec-25 A | 09-Jan-26 A
A43950 | Datasheets for Insulating Gaskets_IFD/IFC | 09-Jan-26 A | 13-Jan-26 A | 2026-06-11 | 2026-06-11 | 09-Jan-26 A | 13-Jan-26 A
DatasheetsforFlameArrestors |  | 20-Apr-25 A | 23-Dec-25 A | 2026-07-20 | 2027-03-23 | 20-Apr-25 A | 23-Dec-25 A
A43960 | Datasheets for Flame Arrestors_IFR | 20-Apr-25 A | 11-May-25 A | 2026-07-20 | 2026-07-20 | 20-Apr-25 A | 11-May-25 A
A43970 | Datasheets for Flame Arrestors_RCC | 12-May-25 A | 18-May-25 A | 2027-03-23 | 2027-03-23 | 12-May-25 A | 18-May-25 A
A43980 | Datasheets for Flame Arrestors_IFA | 19-May-25 A | 25-May-25 A | 2027-03-23 | 2027-03-23 | 19-May-25 A | 25-May-25 A
A43990 | Datasheets for Flame Arrestors_RCA | 26-May-25 A | 14-Oct-25 A | 2027-03-23 | 2027-03-23 | 26-May-25 A | 14-Oct-25 A
A44000 | Datasheets for Flame Arrestors_IFD/IFC | 19-Dec-25 A | 23-Dec-25 A | 2027-03-23 | 2027-03-23 | 19-Dec-25 A | 23-Dec-25 A
DatasheetsforFlameBirdScreen |  | 15-Apr-25 A | 23-Dec-25 A | 2026-07-20 | 2027-03-23 | 15-Apr-25 A | 23-Dec-25 A
A44010 | Datasheets for Flame Bird Screen_IFR | 15-Apr-25 A | 06-May-25 A | 2026-07-20 | 2026-07-20 | 15-Apr-25 A | 06-May-25 A
A44020 | Datasheets for Flame Bird Screen_RCC | 07-May-25 A | 13-May-25 A | 2027-03-23 | 2027-03-23 | 07-May-25 A | 13-May-25 A
A44030 | Datasheets for Flame Bird Screen_IFA | 20-Aug-25 A | 27-Aug-25 A | 2027-03-23 | 2027-03-23 | 20-Aug-25 A | 27-Aug-25 A
A44040 | Datasheets for Flame Bird Screen_RCA | 01-Oct-25 A | 27-Oct-25 A | 2027-03-23 | 2027-03-23 | 01-Oct-25 A | 27-Oct-25 A
A44050 | Datasheets for Flame Bird Screen_IFD/IFC | 19-Dec-25 A | 23-Dec-25 A | 2027-03-23 | 2027-03-23 | 19-Dec-25 A | 23-Dec-25 A
DatasheetsforHoseCoupling |  | 01-Jul-25 A | 23-Dec-25 A | 2026-06-09 | 2026-06-11 | 01-Jul-25 A | 23-Dec-25 A
A44060 | Datasheets for Hose Coupling_IFR | 01-Jul-25 A | 12-Jul-25 A | 2026-06-09 | 2026-06-09 | 01-Jul-25 A | 12-Jul-25 A
A44070 | Datasheets for Hose Coupling_RCC | 05-Jul-25 A | 25-Jul-25 A | 2026-06-11 | 2026-06-11 | 05-Jul-25 A | 25-Jul-25 A
A44080 | Datasheets for Hose Coupling_IFA | 05-Aug-25 A | 12-Aug-25 A | 2026-06-11 | 2026-06-11 | 05-Aug-25 A | 12-Aug-25 A
A44090 | Datasheets for Hose Coupling_RCA | 09-Aug-25 A | 27-Aug-25 A | 2026-06-11 | 2026-06-11 | 09-Aug-25 A | 27-Aug-25 A
A44100 | Datasheets for Hose Coupling_IFD/IFC | 19-Dec-25 A | 23-Dec-25 A | 2026-06-11 | 2026-06-11 | 19-Dec-25 A | 23-Dec-25 A
DatasheetsforStrainers |  | 14-Apr-25 A | 23-Dec-25 A | 2026-07-20 | 2027-03-23 | 14-Apr-25 A | 23-Dec-25 A
A44110 | Datasheets for Strainers_IFR | 14-Apr-25 A | 05-May-25 A | 2026-07-20 | 2026-07-20 | 14-Apr-25 A | 05-May-25 A
A44120 | Datasheets for Strainers_RCC | 06-May-25 A | 12-May-25 A | 2027-03-23 | 2027-03-23 | 06-May-25 A | 12-May-25 A
A44130 | Datasheets for Strainers_IFA | 13-May-25 A | 01-Sep-25 A | 2027-03-23 | 2027-03-23 | 13-May-25 A | 01-Sep-25 A
A44140 | Datasheets for Strainers_RCA | 02-Sep-25 A | 08-Sep-25 A | 2027-03-23 | 2027-03-23 | 02-Sep-25 A | 08-Sep-25 A
A44150 | Datasheets for Strainers_IFD/IFC | 19-Dec-25 A | 23-Dec-25 A | 2027-03-23 | 2027-03-23 | 19-Dec-25 A | 23-Dec-25 A
DatasheetsforSpringHangers |  | 25-Apr-25 A | 2026-05-12 | 2026-06-12 | 2027-03-19 | 25-Apr-25 A | 2026-03-23
A44160 | Datasheets for Spring Hangers_IFR | 25-Apr-25 A | 30-Apr-25 A | 2026-06-12 | 2026-06-12 | 25-Apr-25 A | 30-Apr-25 A
A44170 | Datasheets for Spring Hangers_RCC | 01-May-25 A | 15-May-25 A | 2027-02-23 | 2027-02-23 | 01-May-25 A | 15-May-25 A
A44180 | Datasheets for Spring Hangers_IFA | 20-Mar-26 A | 17-Apr-26 A | 2027-02-23 | 2027-02-23 | 2026-02-20 | 2026-02-25
A44190 | Datasheets for Spring Hangers_RCA | 2026-04-17 | 2026-05-08 | 2027-02-23 | 2027-03-17 | 2026-02-25 | 2026-03-19
A44200 | Datasheets for Spring Hangers_IFD/IFC | 2026-05-08 | 2026-05-12 | 2027-03-17 | 2027-03-19 | 2026-03-19 | 2026-03-23
DatasheetsforRigidStruts |  | 15-Apr-25 A | 2026-05-12 | 2027-02-23 | 2027-03-19 | 15-Apr-25 A | 2026-03-17
A44210 | Datasheets for Rigid Struts_IFR | 15-Apr-25 A | 06-May-25 A | 2027-02-23 | 2027-02-23 | 15-Apr-25 A | 06-May-25 A
A44220 | Datasheets for Rigid Struts_RCC | 07-May-25 A | 13-May-25 A | 2027-02-23 | 2027-02-23 | 07-May-25 A | 13-May-25 A
A44230 | Datasheets for Rigid Struts_IFA | 10-Dec-25 A | 17-Dec-25 A | 2027-02-23 | 2027-02-23 | 10-Dec-25 A | 17-Dec-25 A
A44240 | Datasheets for Rigid Struts_RCA | 2026-04-17 | 2026-05-08 | 2027-02-23 | 2027-03-17 | 2026-02-20 | 2026-03-13
A44250 | Datasheets for Rigid Struts_IFD/IFC | 2026-05-08 | 2026-05-12 | 2027-03-17 | 2027-03-19 | 2026-03-13 | 2026-03-17
DatasheetforPipingSpecialityItems |  | 01-Sep-25 A | 23-Dec-25 A | 2026-07-20 | 2027-03-23 | 01-Sep-25 A | 2026-03-23
A54490 | Datasheet for Piping Speciality Items_IFR | 01-Sep-25 A | 12-Sep-25 A | 2026-07-20 | 2026-07-20 | 01-Sep-25 A | 12-Sep-25 A
A54500 | Datasheet for Piping Speciality Items_RCC | 15-Sep-25 A | 19-Sep-25 A | 2027-03-23 | 2027-03-23 | 15-Sep-25 A | 19-Sep-25 A
A54510 | Datasheet for Piping Speciality Items_IFA | 19-Dec-25 A | 19-Dec-25 A | 2027-03-23 | 2027-03-23 | 2026-02-20 | 2026-02-25
A54520 | Datasheet for Piping Speciality Items_RCA | 22-Dec-25 A | 22-Dec-25 A | 2027-03-23 | 2027-03-23 | 2026-02-25 | 2026-03-19
A54530 | Datasheet for Piping Speciality Items_IFD/IFC | 23-Dec-25 A | 23-Dec-25 A | 2027-03-23 | 2027-03-23 | 2026-03-19 | 2026-03-23
MaterialRequisitionforPipingBulk |  | 15-Apr-25 A | 16-Jan-26 A | 2026-06-09 | 2026-06-16 | 15-Apr-25 A | 16-Jan-26 A
A44720 | Material Requisition for Piping Bulk_IFR | 15-Apr-25 A | 06-May-25 A | 2026-06-09 | 2026-06-09 | 15-Apr-25 A | 06-May-25 A
A44730 | Material Requisition for Piping Bulk_RCC | 20-Jul-25 A | 10-Aug-25 A | 2026-06-16 | 2026-06-16 | 20-Jul-25 A | 10-Aug-25 A
A44740 | Material Requisition for Piping Bulk_IFA | 15-Oct-25 A | 29-Oct-25 A | 2026-06-16 | 2026-06-16 | 15-Oct-25 A | 29-Oct-25 A
A44750 | Material Requisition for Piping Bulk_RCA | 30-Oct-25 A | 10-Nov-25 A | 2026-06-16 | 2026-06-16 | 30-Oct-25 A | 10-Nov-25 A
A44760 | Material Requisition for Piping Bulk_IFD/IFC | 14-Jan-26 A | 16-Jan-26 A | 2026-06-16 | 2026-06-16 | 14-Jan-26 A | 16-Jan-26 A
MaterialRequisitionforHDPEPipingBulk |  | 15-Oct-25 A | 2026-04-21 | 2026-06-11 | 2026-06-15 | 15-Oct-25 A | 2026-02-24
A60050 | Material Requisition for HDPE Piping Bulk_IFR | 15-Oct-25 A | 26-Oct-25 A | 2026-06-11 | 2026-06-11 | 15-Oct-25 A | 26-Oct-25 A
A60060 | Material Requisition for HDPE Piping Bulk_RCC | 26-Oct-25 A | 10-Nov-25 A | 2026-06-11 | 2026-06-11 | 26-Oct-25 A | 10-Nov-25 A
A60070 | Material Requisition for HDPE Piping Bulk_IFA | 10-Nov-25 A | 27-Nov-25 A | 2026-06-11 | 2026-06-11 | 10-Nov-25 A | 27-Nov-25 A
A60080 | Material Requisition for HDPE Piping Bulk_RCA | 27-Nov-25 A | 16-Dec-25 A | 2026-06-11 | 2026-06-11 | 27-Nov-25 A | 16-Dec-25 A
A60090 | Material Requisition for HDPE Piping Bulk_IFD/IFC | 2026-04-17 | 2026-04-21 | 2026-06-11 | 2026-06-15 | 2026-02-20 | 2026-02-24
MaterialRequisitionforManualValves |  | 01-Jul-25 A | 10-Oct-25 A | 2026-06-16 | 2026-06-16 | 01-Jul-25 A | 10-Oct-25 A
A44770 | Material Requisition for Manual Valves_IFR | 01-Jul-25 A | 12-Jul-25 A | 2026-06-16 | 2026-06-16 | 01-Jul-25 A | 12-Jul-25 A
A44780 | Material Requisition for Manual Valves_RCC | 21-Aug-25 A | 31-Aug-25 A | 2026-06-16 | 2026-06-16 | 21-Aug-25 A | 31-Aug-25 A
A44790 | Material Requisition for Manual Valves_IFA | 01-Sep-25 A | 10-Sep-25 A | 2026-06-16 | 2026-06-16 | 01-Sep-25 A | 10-Sep-25 A
A44800 | Material Requisition for Manual Valves_RCA | 11-Sep-25 A | 15-Sep-25 A | 2026-06-16 | 2026-06-16 | 11-Sep-25 A | 15-Sep-25 A
A44810 | Material Requisition for Manual Valves_IFD/IFC | 22-Sep-25 A | 10-Oct-25 A | 2026-06-16 | 2026-06-16 | 22-Sep-25 A | 10-Oct-25 A
MaterialRequisitionforPipingSpecialityItems |  | 15-Sep-25 A | 23-Sep-25 A | 2026-07-20 | 2027-03-23 | 15-Sep-25 A | 2026-04-14
A44820 | Material Requisition for Piping Speciality Items_IFR | 15-Sep-25 A | 16-Sep-25 A | 2026-07-20 | 2026-07-20 | 15-Sep-25 A | 16-Sep-25 A
A44830 | Material Requisition for Piping Speciality Items_RCC | 19-Sep-25 A | 19-Sep-25 A | 2027-03-23 | 2027-03-23 | 2026-02-20 | 2026-03-13
A44840 | Material Requisition for Piping Speciality Items_IFA | 19-Sep-25 A | 19-Sep-25 A | 2027-03-23 | 2027-03-23 | 2026-03-13 | 2026-03-19
A44850 | Material Requisition for Piping Speciality Items_RCA | 22-Sep-25 A | 22-Sep-25 A | 2027-03-23 | 2027-03-23 | 2026-03-19 | 2026-04-09
A44860 | Material Requisition for Piping Speciality Items_IFD/IFC | 23-Sep-25 A | 23-Sep-25 A | 2027-03-23 | 2027-03-23 | 2026-04-09 | 2026-04-14
MaterialRequisitionforSpringHangers |  | 22-Apr-25 A | 2026-05-15 | 2026-06-12 | 2027-03-23 | 22-Apr-25 A | 2026-03-25
A44870 | Material Requisition for Spring Hangers_IFR | 22-Apr-25 A | 13-May-25 A | 2026-06-12 | 2026-06-12 | 22-Apr-25 A | 13-May-25 A
A44880 | Material Requisition for Spring Hangers_RCC | 14-May-25 A | 20-May-25 A | 2026-06-12 | 2026-06-12 | 14-May-25 A | 20-May-25 A
A44890 | Material Requisition for Spring Hangers_IFA | 04-Dec-25 A | 18-Dec-25 A | 2027-02-26 | 2027-02-26 | 04-Dec-25 A | 18-Dec-25 A
A44900 | Material Requisition for Spring Hangers_RCA | 2026-04-17 | 2026-05-08 | 2027-02-26 | 2027-03-19 | 2026-02-20 | 2026-03-13
A44910 | Material Requisition for Spring Hangers_IFD/IFC | 2026-05-13 | 2026-05-15 | 2027-03-19 | 2027-03-23 | 2026-03-23 | 2026-03-25
MaterialRequisitionforRigidStruts |  | 22-Apr-25 A | 2026-05-15 | 2027-02-26 | 2027-03-23 | 22-Apr-25 A | 2026-03-20
A44920 | Material Requisition for Rigid Struts_IFR | 22-Apr-25 A | 13-May-25 A | 2027-02-26 | 2027-02-26 | 22-Apr-25 A | 13-May-25 A
A44930 | Material Requisition for Rigid Struts_RCC | 14-May-25 A | 20-May-25 A | 2027-02-26 | 2027-02-26 | 14-May-25 A | 20-May-25 A
A44940 | Material Requisition for Rigid Struts_IFA | 01-Dec-25 A | 12-Dec-25 A | 2027-02-26 | 2027-02-26 | 01-Dec-25 A | 12-Dec-25 A
A44950 | Material Requisition for Rigid Struts_RCA | 2026-04-17 | 2026-05-08 | 2027-02-26 | 2027-03-19 | 2026-02-20 | 2026-03-13
A44960 | Material Requisition for Rigid Struts_IFD/IFC | 2026-05-13 | 2026-05-15 | 2027-03-19 | 2027-03-23 | 2026-03-18 | 2026-03-20
UtilityStationLocationPlan |  | 15-Apr-25 A | 19-Jan-26 A | 2027-03-23 | 2027-03-23 | 15-Apr-25 A | 19-Jan-26 A
A43510 | Utility Station Location Plan_IFR | 15-Apr-25 A | 06-May-25 A | 2027-03-23 | 2027-03-23 | 15-Apr-25 A | 06-May-25 A
A43520 | Utility Station Location Plan_RCC | 20-Jul-25 A | 08-Aug-25 A | 2027-03-23 | 2027-03-23 | 20-Jul-25 A | 08-Aug-25 A
A43530 | Utility Station Location Plan_IFA | 19-Dec-25 A | 24-Dec-25 A | 2027-03-23 | 2027-03-23 | 19-Dec-25 A | 24-Dec-25 A
A43540 | Utility Station Location Plan_RCA | 24-Dec-25 A | 15-Jan-26 A | 2027-03-23 | 2027-03-23 | 24-Dec-25 A | 15-Jan-26 A
A43550 | Utility Station Location Plan_IFD/IFC | 15-Jan-26 A | 19-Jan-26 A | 2027-03-23 | 2027-03-23 | 15-Jan-26 A | 19-Jan-26 A
30%3DModelReviewReport |  | 25-Apr-25 A | 21-Aug-25 A | 2026-06-11 | 2026-06-11 | 25-Apr-25 A | 21-Aug-25 A
A43560 | 30% 3D Model Review Report_IFR | 25-Apr-25 A | 16-May-25 A | 2026-06-11 | 2026-06-11 | 25-Apr-25 A | 16-May-25 A
A43570 | 30% 3D Model Review Report_RCC | 17-May-25 A | 23-May-25 A | 2026-06-11 | 2026-06-11 | 17-May-25 A | 23-May-25 A
A43580 | 30% 3D Model Review Report_IFA | 24-May-25 A | 10-Aug-25 A | 2026-06-11 | 2026-06-11 | 24-May-25 A | 10-Aug-25 A
A43590 | 30% 3D Model Review Report_RCA | 11-Aug-25 A | 15-Aug-25 A | 2026-06-11 | 2026-06-11 | 11-Aug-25 A | 15-Aug-25 A
A43600 | 30% 3D Model Review Report_IFD/IFC | 16-Aug-25 A | 21-Aug-25 A | 2026-06-11 | 2026-06-11 | 16-Aug-25 A | 21-Aug-25 A
30%3DModelReviewCloseoutReport |  | 01-Jul-25 A | 19-Dec-25 A | 2026-06-12 | 2026-06-12 | 01-Jul-25 A | 19-Dec-25 A
A43610 | 30% 3D Model Review Closeout Report_IFR | 01-Jul-25 A | 12-Jul-25 A | 2026-06-12 | 2026-06-12 | 01-Jul-25 A | 12-Jul-25 A
A43620 | 30% 3D Model Review Closeout Report_RCC | 27-Aug-25 A | 27-Nov-25 A | 2026-06-12 | 2026-06-12 | 27-Aug-25 A | 27-Nov-25 A
A43630 | 30% 3D Model Review Closeout Report_IFA | 27-Nov-25 A | 02-Dec-25 A | 2026-06-12 | 2026-06-12 | 27-Nov-25 A | 02-Dec-25 A
A43640 | 30% 3D Model Review Closeout Report_RCA | 02-Dec-25 A | 15-Dec-25 A | 2026-06-12 | 2026-06-12 | 02-Dec-25 A | 15-Dec-25 A
A43650 | 30% 3D Model Review Closeout Report_IFD/IFC | 10-Dec-25 A | 19-Dec-25 A | 2026-06-12 | 2026-06-12 | 10-Dec-25 A | 19-Dec-25 A
PlotPlan |  | 09-Mar-25 A | 25-Oct-25 A | 2026-06-09 | 2026-12-16 | 09-Mar-25 A | 25-Oct-25 A
A45220 | Plot Plan_IFR | 14-Mar-25 A | 27-Apr-25 A | 2026-06-11 | 2026-06-11 | 14-Mar-25 A | 27-Apr-25 A
A45230 | Plot Plan_RCC | 28-Apr-25 A | 11-Jun-25 A | 2026-06-16 | 2026-06-16 | 28-Apr-25 A | 11-Jun-25 A
A45240 | Plot Plan_IFA | 03-Oct-25 A | 10-Oct-25 A | 2026-06-16 | 2026-06-16 | 03-Oct-25 A | 10-Oct-25 A
A45250 | Plot Plan_RCA | 02-Oct-25 A | 24-Oct-25 A | 2026-12-16 | 2026-12-16 | 02-Oct-25 A | 24-Oct-25 A
A45260 | Plot Plan_IFD/IFC | 23-Oct-25 A | 25-Oct-25 A | 2026-12-16 | 2026-12-16 | 23-Oct-25 A | 25-Oct-25 A
A55670 | Plot Plan_Preliminary issuance for Plot plan workshop | 09-Mar-25 A | 12-Mar-25 A | 2026-06-09 | 2026-06-09 | 09-Mar-25 A | 12-Mar-25 A
PlotPlanReviewReport |  | 19-Apr-25 A | 16-Oct-25 A | 2027-03-23 | 2027-03-23 | 19-Apr-25 A | 16-Oct-25 A
A43360 | Plot Plan Review Report_IFR | 19-Apr-25 A | 10-May-25 A | 2027-03-23 | 2027-03-23 | 19-Apr-25 A | 10-May-25 A
A43370 | Plot Plan Review Report_RCC | 11-May-25 A | 17-May-25 A | 2027-03-23 | 2027-03-23 | 11-May-25 A | 17-May-25 A
A43380 | Plot Plan Review Report_IFA | 18-May-25 A | 21-Jun-25 A | 2027-03-23 | 2027-03-23 | 18-May-25 A | 21-Jun-25 A
A43390 | Plot Plan Review Report_RCA | 22-Jun-25 A | 28-Jun-25 A | 2027-03-23 | 2027-03-23 | 22-Jun-25 A | 28-Jun-25 A
A43400 | Plot Plan Review Report_IFD/IFC | 10-Oct-25 A | 16-Oct-25 A | 2027-03-23 | 2027-03-23 | 10-Oct-25 A | 16-Oct-25 A
FirstMaterialTakeOff |  | 02-Jun-25 A | 27-Jun-25 A | 2026-06-09 | 2026-06-09 | 02-Jun-25 A | 27-Jun-25 A
A45270 | First Material Take Off_IFR | 02-Jun-25 A | 06-Jun-25 A | 2026-06-09 | 2026-06-09 | 02-Jun-25 A | 06-Jun-25 A
A45280 | First Material Take Off_RCC | 09-Jun-25 A | 20-Jun-25 A | 2026-06-09 | 2026-06-09 | 09-Jun-25 A | 20-Jun-25 A
A45290 | First Material Take Off_IFD/IFC | 23-Jun-25 A | 27-Jun-25 A | 2026-06-09 | 2026-06-09 | 23-Jun-25 A | 27-Jun-25 A
PlotPlanCloseOutReport |  | 19-Apr-25 A | 18-Dec-25 A | 2027-03-23 | 2027-03-23 | 19-Apr-25 A | 18-Dec-25 A
A43410 | Plot Plan Close Out report_IFR | 19-Apr-25 A | 10-May-25 A | 2027-03-23 | 2027-03-23 | 19-Apr-25 A | 10-May-25 A
A43420 | Plot Plan Close Out report_RCC | 11-May-25 A | 17-May-25 A | 2027-03-23 | 2027-03-23 | 11-May-25 A | 17-May-25 A
A43430 | Plot Plan Close Out report_IFA | 10-Oct-25 A | 14-Oct-25 A | 2027-03-23 | 2027-03-23 | 10-Oct-25 A | 14-Oct-25 A
A43440 | Plot Plan Close Out report_RCA | 10-Oct-25 A | 27-Oct-25 A | 2027-03-23 | 2027-03-23 | 10-Oct-25 A | 27-Oct-25 A
A43450 | Plot Plan Close Out report_IFD/IFC | 15-Dec-25 A | 18-Dec-25 A | 2027-03-23 | 2027-03-23 | 15-Dec-25 A | 18-Dec-25 A
ManualValvesList(ValvesMTOs) |  | 25-Feb-25 A | 23-Dec-25 A | 2027-03-23 | 2027-03-23 | 25-Feb-25 A | 23-Dec-25 A
A44690 | Manual Valves List (Valves MTOs)_IFR | 25-Feb-25 A | 10-Apr-25 A | 2027-03-23 | 2027-03-23 | 25-Feb-25 A | 10-Apr-25 A
A44700 | Manual Valves List (Valves MTOs)_RCC | 02-Aug-25 A | 25-Aug-25 A | 2027-03-23 | 2027-03-23 | 02-Aug-25 A | 25-Aug-25 A
A44710 | Manual Valves List (Valves MTOs)_IFD/IFC | 19-Dec-25 A | 23-Dec-25 A | 2027-03-23 | 2027-03-23 | 19-Dec-25 A | 23-Dec-25 A
TechnicalBidEvaluation(TBE)forRigidStruts |  | 2026-04-17 | 2026-06-16 | 2027-01-22 | 2027-03-23 | 2026-02-20 | 2026-04-21
A45170 | Technical Bid Evaluation (TBE) for Rigid Struts_IFR | 2026-04-17 | 2026-04-24 | 2027-01-22 | 2027-01-29 | 2026-02-20 | 2026-02-27
A45180 | Technical Bid Evaluation (TBE) for Rigid Struts_RCC | 2026-04-24 | 2026-05-18 | 2027-01-29 | 2027-02-22 | 2026-02-27 | 2026-03-23
A45190 | Technical Bid Evaluation (TBE) for Rigid Struts_IFA | 2026-05-18 | 2026-05-21 | 2027-02-22 | 2027-02-25 | 2026-03-23 | 2026-03-26
A45200 | Technical Bid Evaluation (TBE) for Rigid Struts_RCA | 2026-05-21 | 2026-06-12 | 2027-02-26 | 2027-03-19 | 2026-03-26 | 2026-04-17
A45210 | Technical Bid Evaluation (TBE) for Rigid Struts_IFD/IFC | 2026-06-12 | 2026-06-16 | 2027-03-19 | 2027-03-23 | 2026-04-17 | 2026-04-21
60%3DModelReviewReport |  | 26-Sep-25 A | 21-Jan-26 A | 2026-06-16 | 2027-03-23 | 26-Sep-25 A | 21-Jan-26 A
A44260 | 60% 3D Model Review Report_IFR | 26-Sep-25 A | 02-Oct-25 A | 2026-06-16 | 2026-06-16 | 26-Sep-25 A | 02-Oct-25 A
A44270 | 60% 3D Model Review Report_RCC | 13-Oct-25 A | 04-Nov-25 A | 2027-03-23 | 2027-03-23 | 13-Oct-25 A | 04-Nov-25 A
A44280 | 60% 3D Model Review Report_IFA | 19-Dec-25 A | 24-Dec-25 A | 2027-03-23 | 2027-03-23 | 19-Dec-25 A | 24-Dec-25 A
A44290 | 60% 3D Model Review Report_RCA | 24-Dec-25 A | 15-Jan-26 A | 2027-03-23 | 2027-03-23 | 24-Dec-25 A | 15-Jan-26 A
A44300 | 60% 3D Model Review Report_IFD/IFC | 19-Jan-26 A | 21-Jan-26 A | 2027-03-23 | 2027-03-23 | 19-Jan-26 A | 21-Jan-26 A
60%3DModelReviewCloseoutReport |  | 24-Nov-25 A | 10-Mar-26 A | 2026-10-14 | 2027-03-23 | 2026-02-20 | 2026-04-29
A44310 | 60% 3D Model Review Closeout Report_IFR | 24-Nov-25 A | 04-Feb-26 A | 2026-10-14 | 2026-10-14 | 2026-02-20 | 2026-03-09
A44320 | 60% 3D Model Review Closeout Report_RCC | 04-Feb-26 A | 23-Feb-26 A | 2027-02-18 | 2027-02-18 | 2026-03-09 | 2026-03-30
A44330 | 60% 3D Model Review Closeout Report_IFA | 21-Feb-26 A | 02-Mar-26 A | 2027-02-18 | 2027-02-18 | 2026-03-31 | 2026-04-03
A44340 | 60% 3D Model Review Closeout Report_RCA | 03-Mar-26 A | 03-Mar-26 A | 2027-03-23 | 2027-03-23 | 2026-04-03 | 2026-04-27
A44350 | 60% 3D Model Review Closeout Report_IFD/IFC | 04-Mar-26 A | 10-Mar-26 A | 2027-03-23 | 2027-03-23 | 2026-04-27 | 2026-04-29
PipingStressAnalysisReports |  | 06-Jul-25 A | 23-Jan-26 A | 2026-07-22 | 2026-07-22 | 06-Jul-25 A | 23-Jan-26 A
A44640 | Piping Stress Analysis Reports_IFR | 06-Jul-25 A | 31-Jul-25 A | 2026-07-22 | 2026-07-22 | 06-Jul-25 A | 31-Jul-25 A
A44650 | Piping Stress Analysis Reports_RCC | 20-Jul-25 A | 07-Aug-25 A | 2026-07-22 | 2026-07-22 | 20-Jul-25 A | 07-Aug-25 A
A44660 | Piping Stress Analysis Reports_IFA | 19-Dec-25 A | 05-Jan-26 A | 2026-07-22 | 2026-07-22 | 19-Dec-25 A | 05-Jan-26 A
A44670 | Piping Stress Analysis Reports_RCA | 05-Jan-26 A | 14-Jan-26 A | 2026-07-22 | 2026-07-22 | 05-Jan-26 A | 14-Jan-26 A
A44680 | Piping Stress Analysis Reports_IFD/IFC | 15-Jan-26 A | 23-Jan-26 A | 2026-07-22 | 2026-07-22 | 15-Jan-26 A | 23-Jan-26 A
PipingGADrawings&KeyPlanforPipingGADs |  | 01-Dec-25 A | 17-Apr-26 A | 2026-06-16 | 2027-03-23 | 01-Dec-25 A | 2026-04-07
A44540 | Piping GA Drawings & Key Plan for Piping GADs_IFR | 05-Dec-25 A | 18-Dec-25 A | 2026-06-16 | 2026-06-16 | 05-Dec-25 A | 18-Dec-25 A
A44550 | Piping GA Drawings & Key Plan for Piping GADs_RCC | 01-Dec-25 A | 02-Dec-25 A | 2026-06-16 | 2026-06-16 | 01-Dec-25 A | 02-Dec-25 A
A44560 | Piping GA Drawings & Key Plan for Piping GADs_IFA | 20-Mar-26 A | 06-Apr-26 A | 2027-03-23 | 2027-03-23 | 2026-02-20 | 2026-03-09
A44570 | Piping GA Drawings & Key Plan for Piping GADs_RCA | 06-Apr-26 A | 10-Apr-26 A | 2027-03-23 | 2027-03-23 | 2026-03-09 | 2026-03-30
A44580 | Piping GA Drawings & Key Plan for Piping GADs_IFD/IFC | 13-Apr-26 A | 17-Apr-26 A | 2027-03-23 | 2027-03-23 | 2026-03-31 | 2026-04-07
PipingIsometrics(largebore) |  | 14-Jan-26 A | 2026-05-22 | 2026-06-15 | 2026-11-30 | 14-Jan-26 A | 2026-06-04
A44360 | Piping Isometrics (large bore)_IFR | 14-Jan-26 A | 2026-05-22 | 2026-06-15 | 2026-07-21 | 14-Jan-26 A | 2026-03-27
A44370 | Piping Isometrics (large bore)_RCC | 20-Jan-26 A | 01-Mar-26 A | 2026-11-30 | 2026-11-30 | 2026-03-30 | 2026-04-20
A44380 | Piping Isometrics (large bore)_IFA | 27-Jan-26 A | 03-Mar-26 A | 2026-11-30 | 2026-11-30 | 2026-04-20 | 2026-05-05
A44390 | Piping Isometrics (large bore)_RCA | 09-Feb-26 A | 05-Mar-26 A | 2026-11-30 | 2026-11-30 | 2026-05-06 | 2026-05-27
A44400 | Piping Isometrics (large bore)_IFD/IFC | 23-Feb-26 A | 20-Mar-26 A | 2026-11-30 | 2026-11-30 | 2026-05-27 | 2026-06-04
SecondMaterialTakeOff |  | 23-Dec-25 A | 20-Mar-26 A | 2026-06-15 | 2026-06-15 | 23-Dec-25 A | 2026-02-24
A45300 | Second Material Take Off_IFR | 23-Dec-25 A | 15-Jan-26 A | 2026-06-15 | 2026-06-15 | 23-Dec-25 A | 15-Jan-26 A
A45310 | Second Material Take Off_RCC | 16-Jan-26 A | 23-Jan-26 A | 2026-06-15 | 2026-06-15 | 16-Jan-26 A | 23-Jan-26 A
A45320 | Second Material Take Off_IFD/IFC | 23-Jan-26 A | 20-Mar-26 A | 2026-06-15 | 2026-06-15 | 23-Jan-26 A | 2026-02-24
90%3DModelReviewReport |  | 18-Mar-26 A | 2026-06-26 | 2027-01-22 | 2027-03-23 | 2026-03-06 | 2026-06-08
A44410 | 90% 3D Model Review Report_IFR | 18-Mar-26 A | 20-Mar-26 A | 2027-01-22 | 2027-01-22 | 2026-03-06 | 2026-03-13
A44420 | 90% 3D Model Review Report_RCC | 2026-04-24 | 2026-05-15 | 2027-01-29 | 2027-02-22 | 2026-03-13 | 2026-04-06
A44430 | 90% 3D Model Review Report_IFA | 2026-05-15 | 2026-05-21 | 2027-02-22 | 2027-02-25 | 2026-04-06 | 2026-04-09
A44440 | 90% 3D Model Review Report_RCA | 2026-05-21 | 2026-06-11 | 2027-02-26 | 2027-03-19 | 2026-04-09 | 2026-05-01
A44450 | 90% 3D Model Review Report_IFD/IFC | 2026-06-24 | 2026-06-26 | 2027-03-19 | 2027-03-23 | 2026-06-04 | 2026-06-08
PipingIsometrics(SmallBore) |  | 19-Mar-26 A | 2026-05-19 | 2026-07-01 | 2026-07-24 | 2026-03-06 | 2026-05-01
A44510 | Piping Isometrics(Small Bore)_IFR | 19-Mar-26 A | 20-Mar-26 A | 2026-07-01 | 2026-07-01 | 2026-03-06 | 2026-04-07
A44520 | Piping Isometrics(Small Bore)_RCC | 2026-04-23 | 2026-05-15 | 2026-07-01 | 2026-07-22 | 2026-04-07 | 2026-04-29
A44530 | Piping Isometrics(Small Bore)_IFD/IFC | 2026-05-15 | 2026-05-19 | 2026-07-22 | 2026-07-24 | 2026-04-29 | 2026-05-01
PipingTie-InsSchedule |  | 11-Feb-26 A | 2026-05-12 | 2026-11-23 | 2026-12-16 | 2026-02-20 | 2026-04-21
A44590 | Piping Tie-Ins Schedule_IFR | 11-Feb-26 A | 24-Feb-26 A | 2026-11-23 | 2026-11-23 | 2026-02-20 | 2026-02-27
A44600 | Piping Tie-Ins Schedule_RCC | 24-Feb-26 A | 16-Mar-26 A | 2026-11-23 | 2026-11-23 | 2026-02-27 | 2026-03-23
A44610 | Piping Tie-Ins Schedule_IFA | 19-Mar-26 A | 20-Mar-26 A | 2026-11-23 | 2026-11-23 | 2026-03-23 | 2026-03-26
A44620 | Piping Tie-Ins Schedule_RCA | 2026-04-17 | 2026-05-08 | 2026-11-23 | 2026-12-14 | 2026-03-26 | 2026-04-17
A44630 | Piping Tie-Ins Schedule_IFD/IFC | 2026-05-08 | 2026-05-12 | 2026-12-14 | 2026-12-16 | 2026-04-17 | 2026-04-21
90%3DModelReviewCloseoutReport |  | 2026-04-24 | 2026-06-23 | 2027-01-22 | 2027-03-23 | 2026-03-13 | 2026-05-13
A44460 | 90% 3D Model Review Closeout Report_IFR | 2026-04-24 | 2026-05-01 | 2027-01-22 | 2027-01-29 | 2026-03-13 | 2026-03-23
A44470 | 90% 3D Model Review Closeout Report_RCC | 2026-05-01 | 2026-05-25 | 2027-01-29 | 2027-02-22 | 2026-03-23 | 2026-04-14
A44480 | 90% 3D Model Review Closeout Report_IFA | 2026-05-25 | 2026-05-28 | 2027-02-22 | 2027-02-25 | 2026-04-14 | 2026-04-17
A44490 | 90% 3D Model Review Closeout Report_RCA | 2026-05-28 | 2026-06-19 | 2027-02-26 | 2027-03-19 | 2026-04-17 | 2026-05-11
A44500 | 90% 3D Model Review Closeout Report_IFD/IFC | 2026-06-19 | 2026-06-23 | 2027-03-19 | 2027-03-23 | 2026-05-11 | 2026-05-13
FinalMaterialTakeOff |  | 10-Mar-26 A | 2026-06-03 | 2026-06-16 | 2026-07-29 | 2026-03-06 | 2026-04-08
A45330 | Final Material Take Off_IFR | 10-Mar-26 A | 2026-05-08 | 2026-06-16 | 2026-06-30 | 2026-03-06 | 2026-03-13
A45340 | Final Material Take Off_RCC | 2026-05-11 | 2026-06-01 | 2026-07-06 | 2026-07-27 | 2026-03-13 | 2026-04-06
A45350 | Final Material Take Off_IFD/IFC | 2026-06-01 | 2026-06-03 | 2026-07-27 | 2026-07-29 | 2026-04-06 | 2026-04-08
Mechanical |  | 31-Dec-24 A | 2026-06-09 | 2026-06-11 | 2027-03-23 | 07-Feb-25 A | 07-May-25 A
MechanicalStatic |  | 31-Dec-24 A | 2026-06-09 | 2026-06-11 | 2027-03-23 | 31-Dec-24 A | 2026-04-14
MechanicalDatasheetForPsa2FeedGasCompressor1StStageSuctionDrum(TagNo.13-Vv-705) |  | 31-Dec-24 A | 10-May-25 A | 2026-06-11 | 2027-03-23 | 31-Dec-24 A | 10-May-25 A
A54590 | Mechanical Datasheet For Psa2 Feed Gas Compressor 1St Stage Suction Drum (Tag No. 13-Vv-705)_IFR | 31-Dec-24 A | 06-Feb-25 A | 2026-06-11 | 2026-06-11 | 31-Dec-24 A | 06-Feb-25 A
A54600 | Mechanical Datasheet For Psa2 Feed Gas Compressor 1St Stage Suction Drum (Tag No. 13-Vv-705)_RCC | 07-Feb-25 A | 19-Apr-25 A | 2027-03-23 | 2027-03-23 | 07-Feb-25 A | 19-Apr-25 A
A54610 | Mechanical Datasheet For Psa2 Feed Gas Compressor 1St Stage Suction Drum (Tag No. 13-Vv-705)_IFA | 20-Apr-25 A | 26-Apr-25 A | 2027-03-23 | 2027-03-23 | 20-Apr-25 A | 26-Apr-25 A
A54620 | Mechanical Datasheet For Psa2 Feed Gas Compressor 1St Stage Suction Drum (Tag No. 13-Vv-705)_RCA | 27-Apr-25 A | 03-May-25 A | 2027-03-23 | 2027-03-23 | 27-Apr-25 A | 03-May-25 A
A54630 | Mechanical Datasheet For Psa2 Feed Gas Compressor 1St Stage Suction Drum (Tag No. 13-Vv-705)_IFD/IFC | 04-May-25 A | 10-May-25 A | 2027-03-23 | 2027-03-23 | 04-May-25 A | 10-May-25 A
MechanicalDatasheetForPsa2FeedGasCompressor2NdStageSuctionDrum(TagNo.13-Vv-706) |  | 31-Dec-24 A | 10-May-25 A | 2026-06-11 | 2027-03-23 | 31-Dec-24 A | 10-May-25 A
A54640 | Mechanical Datasheet For Psa2 Feed Gas Compressor 2Nd Stage Suction Drum (Tag No. 13-Vv-706)_IFR | 31-Dec-24 A | 06-Feb-25 A | 2026-06-11 | 2026-06-11 | 31-Dec-24 A | 06-Feb-25 A
A54650 | Mechanical Datasheet For Psa2 Feed Gas Compressor 2Nd Stage Suction Drum (Tag No. 13-Vv-706)_RCC | 07-Feb-25 A | 19-Apr-25 A | 2027-03-23 | 2027-03-23 | 07-Feb-25 A | 19-Apr-25 A
A54660 | Mechanical Datasheet For Psa2 Feed Gas Compressor 2Nd Stage Suction Drum (Tag No. 13-Vv-706)_IFA | 20-Apr-25 A | 26-Apr-25 A | 2027-03-23 | 2027-03-23 | 20-Apr-25 A | 26-Apr-25 A
A54670 | Mechanical Datasheet For Psa2 Feed Gas Compressor 2Nd Stage Suction Drum (Tag No. 13-Vv-706)_RCA | 27-Apr-25 A | 03-May-25 A | 2027-03-23 | 2027-03-23 | 27-Apr-25 A | 03-May-25 A
A54680 | Mechanical Datasheet For Psa2 Feed Gas Compressor 2Nd Stage Suction Drum (Tag No. 13-Vv-706)_IFD/IFC | 04-May-25 A | 10-May-25 A | 2027-03-23 | 2027-03-23 | 04-May-25 A | 10-May-25 A
MechanicalDatasheetForPsa2FeedGasCompressor3RdStageSuctionDrum(TagNo.13-Vv-707) |  | 31-Dec-24 A | 10-May-25 A | 2026-06-11 | 2027-03-23 | 31-Dec-24 A | 10-May-25 A
A54690 | Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Suction Drum (Tag No. 13-Vv-707)_IFR | 31-Dec-24 A | 06-Feb-25 A | 2026-06-11 | 2026-06-11 | 31-Dec-24 A | 06-Feb-25 A
A54700 | Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Suction Drum (Tag No. 13-Vv-707)_RCC | 07-Feb-25 A | 19-Apr-25 A | 2027-03-23 | 2027-03-23 | 07-Feb-25 A | 19-Apr-25 A
A54710 | Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Suction Drum (Tag No. 13-Vv-707)_IFA | 20-Apr-25 A | 26-Apr-25 A | 2027-03-23 | 2027-03-23 | 20-Apr-25 A | 26-Apr-25 A
A54720 | Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Suction Drum (Tag No. 13-Vv-707)_RCA | 27-Apr-25 A | 03-May-25 A | 2027-03-23 | 2027-03-23 | 27-Apr-25 A | 03-May-25 A
A54730 | Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Suction Drum (Tag No. 13-Vv-707)_IFD/IFC | 04-May-25 A | 10-May-25 A | 2027-03-23 | 2027-03-23 | 04-May-25 A | 10-May-25 A
MechanicalDatasheetForPsa2FeedGasCompressor3RdStageDischargeDrum(TagNo.13-Vv-Xxx) |  | 31-Dec-24 A | 05-Jul-25 A | 2026-06-11 | 2027-03-23 | 31-Dec-24 A | 05-Jul-25 A
A54740 | Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Discharge Drum (Tag No. 13-Vv-Xxx)_IFR | 31-Dec-24 A | 24-Jan-25 A | 2026-06-11 | 2026-06-11 | 31-Dec-24 A | 24-Jan-25 A
A54750 | Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Discharge Drum (Tag No. 13-Vv-Xxx)_RCC | 25-Jan-25 A | 19-Apr-25 A | 2027-03-23 | 2027-03-23 | 25-Jan-25 A | 19-Apr-25 A
A54760 | Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Discharge Drum (Tag No. 13-Vv-Xxx)_IFA | 20-Apr-25 A | 21-Jun-25 A | 2027-03-23 | 2027-03-23 | 20-Apr-25 A | 21-Jun-25 A
A54770 | Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Discharge Drum (Tag No. 13-Vv-Xxx)_RCA | 22-Jun-25 A | 28-Jun-25 A | 2027-03-23 | 2027-03-23 | 22-Jun-25 A | 28-Jun-25 A
A54780 | Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Discharge Drum (Tag No. 13-Vv-Xxx)_IFD/IFC | 29-Jun-25 A | 05-Jul-25 A | 2027-03-23 | 2027-03-23 | 29-Jun-25 A | 05-Jul-25 A
MechanicalDatasheetForPsa2OffGasBufferDrum(TagNo.13-Vv-712) |  | 31-Dec-24 A | 10-May-25 A | 2026-06-11 | 2027-03-23 | 31-Dec-24 A | 10-May-25 A
A54790 | Mechanical Datasheet For Psa2 Off Gas Buffer Drum (Tag No. 13-Vv-712)_IFR | 31-Dec-24 A | 06-Feb-25 A | 2026-06-11 | 2026-06-11 | 31-Dec-24 A | 06-Feb-25 A
A54800 | Mechanical Datasheet For Psa2 Off Gas Buffer Drum (Tag No. 13-Vv-712)_RCC | 07-Feb-25 A | 19-Apr-25 A | 2027-03-23 | 2027-03-23 | 07-Feb-25 A | 19-Apr-25 A
A54810 | Mechanical Datasheet For Psa2 Off Gas Buffer Drum (Tag No. 13-Vv-712)_IFA | 20-Apr-25 A | 26-Apr-25 A | 2027-03-23 | 2027-03-23 | 20-Apr-25 A | 26-Apr-25 A
A54820 | Mechanical Datasheet For Psa2 Off Gas Buffer Drum (Tag No. 13-Vv-712)_RCA | 27-Apr-25 A | 03-May-25 A | 2027-03-23 | 2027-03-23 | 27-Apr-25 A | 03-May-25 A
A54830 | Mechanical Datasheet For Psa2 Off Gas Buffer Drum (Tag No. 13-Vv-712)_IFD/IFC | 04-May-25 A | 10-May-25 A | 2027-03-23 | 2027-03-23 | 04-May-25 A | 10-May-25 A
MechanicalDatasheetForPsa2OffGasCompressor2NdStageSuctionDrum(TagNo.13-Vv-713) |  | 31-Dec-24 A | 10-May-25 A | 2026-06-11 | 2027-03-23 | 31-Dec-24 A | 10-May-25 A
A54840 | Mechanical Datasheet For Psa2 Off Gas Compressor 2Nd Stage Suction Drum (Tag No. 13-Vv-713)_IFR | 31-Dec-24 A | 06-Feb-25 A | 2026-06-11 | 2026-06-11 | 31-Dec-24 A | 06-Feb-25 A
A54850 | Mechanical Datasheet For Psa2 Off Gas Compressor 2Nd Stage Suction Drum (Tag No. 13-Vv-713)_RCC | 07-Feb-25 A | 19-Apr-25 A | 2027-03-23 | 2027-03-23 | 07-Feb-25 A | 19-Apr-25 A
A54860 | Mechanical Datasheet For Psa2 Off Gas Compressor 2Nd Stage Suction Drum (Tag No. 13-Vv-713)_IFA | 20-Apr-25 A | 26-Apr-25 A | 2027-03-23 | 2027-03-23 | 20-Apr-25 A | 26-Apr-25 A
A54870 | Mechanical Datasheet For Psa2 Off Gas Compressor 2Nd Stage Suction Drum (Tag No. 13-Vv-713)_RCA | 27-Apr-25 A | 03-May-25 A | 2027-03-23 | 2027-03-23 | 27-Apr-25 A | 03-May-25 A
A54880 | Mechanical Datasheet For Psa2 Off Gas Compressor 2Nd Stage Suction Drum (Tag No. 13-Vv-713)_IFD/IFC | 04-May-25 A | 10-May-25 A | 2027-03-23 | 2027-03-23 | 04-May-25 A | 10-May-25 A
MechanicalDatasheetForPsa2SlopDrum(TagNo.70-Vv-1415) |  | 01-Jan-25 A | 10-May-25 A | 2026-06-11 | 2027-03-23 | 01-Jan-25 A | 10-May-25 A
A27210 | Mechanical Datasheet For Psa2 Slop Drum (Tag No. 70-Vv-1415)_IFR | 01-Jan-25 A | 06-Feb-25 A | 2026-06-11 | 2026-06-11 | 01-Jan-25 A | 06-Feb-25 A
A27220 | Mechanical Datasheet For Psa2 Slop Drum (Tag No. 70-Vv-1415)_RCC | 07-Feb-25 A | 19-Apr-25 A | 2027-03-23 | 2027-03-23 | 07-Feb-25 A | 19-Apr-25 A
A27230 | Mechanical Datasheet For Psa2 Slop Drum (Tag No. 70-Vv-1415)_IFA | 20-Apr-25 A | 26-Apr-25 A | 2027-03-23 | 2027-03-23 | 20-Apr-25 A | 26-Apr-25 A
A54890 | Mechanical Datasheet For Psa2 Slop Drum (Tag No. 70-Vv-1415)_RCA | 27-Apr-25 A | 03-May-25 A | 2027-03-23 | 2027-03-23 | 27-Apr-25 A | 03-May-25 A
A54900 | Mechanical Datasheet For Psa2 Slop Drum (Tag No. 70-Vv-1415)_IFD/IFC | 04-May-25 A | 10-May-25 A | 2027-03-23 | 2027-03-23 | 04-May-25 A | 10-May-25 A
MechanicalDatasheetForPsa2FeedGasCompressor1StStageCooler(TagNo.13-He-703) |  | 07-Jan-25 A | 10-May-25 A | 2026-06-11 | 2026-06-11 | 07-Jan-25 A | 10-May-25 A
A54910 | Mechanical Datasheet For Psa2 Feed Gas Compressor 1St Stage Cooler (Tag No. 13-He-703)_IFR | 07-Jan-25 A | 06-Feb-25 A | 2026-06-11 | 2026-06-11 | 07-Jan-25 A | 06-Feb-25 A
A54920 | Mechanical Datasheet For Psa2 Feed Gas Compressor 1St Stage Cooler (Tag No. 13-He-703)_RCC | 07-Feb-25 A | 19-Apr-25 A | 2026-06-11 | 2026-06-11 | 07-Feb-25 A | 19-Apr-25 A
A54930 | Mechanical Datasheet For Psa2 Feed Gas Compressor 1St Stage Cooler (Tag No. 13-He-703)_IFA | 20-Apr-25 A | 26-Apr-25 A | 2026-06-11 | 2026-06-11 | 20-Apr-25 A | 26-Apr-25 A
A54940 | Mechanical Datasheet For Psa2 Feed Gas Compressor 1St Stage Cooler (Tag No. 13-He-703)_RCA | 27-Apr-25 A | 03-May-25 A | 2026-06-11 | 2026-06-11 | 27-Apr-25 A | 03-May-25 A
A54950 | Mechanical Datasheet For Psa2 Feed Gas Compressor 1St Stage Cooler (Tag No. 13-He-703)_IFD/IFC | 04-May-25 A | 10-May-25 A | 2026-06-11 | 2026-06-11 | 04-May-25 A | 10-May-25 A
MechanicalDatasheetForPsa2FeedGasCompressor2NdStageCooler(TagNo.13-He-704) |  | 14-Feb-25 A | 03-May-25 A | 2026-06-11 | 2026-06-11 | 14-Feb-25 A | 03-May-25 A
A54960 | Mechanical Datasheet For Psa2 Feed Gas Compressor 2Nd Stage Cooler (Tag No. 13-He-704)_IFR | 14-Feb-25 A | 07-Mar-25 A | 2026-06-11 | 2026-06-11 | 14-Feb-25 A | 07-Mar-25 A
A54970 | Mechanical Datasheet For Psa2 Feed Gas Compressor 2Nd Stage Cooler (Tag No. 13-He-704)_RCC | 08-Mar-25 A | 14-Mar-25 A | 2026-06-11 | 2026-06-11 | 08-Mar-25 A | 14-Mar-25 A
A54980 | Mechanical Datasheet For Psa2 Feed Gas Compressor 2Nd Stage Cooler (Tag No. 13-He-704)_IFA | 15-Mar-25 A | 21-Mar-25 A | 2026-06-11 | 2026-06-11 | 15-Mar-25 A | 21-Mar-25 A
A54990 | Mechanical Datasheet For Psa2 Feed Gas Compressor 2Nd Stage Cooler (Tag No. 13-He-704)_RCA | 22-Mar-25 A | 30-Apr-25 A | 2026-06-11 | 2026-06-11 | 22-Mar-25 A | 30-Apr-25 A
A55000 | Mechanical Datasheet For Psa2 Feed Gas Compressor 2Nd Stage Cooler (Tag No. 13-He-704)_IFD/IFC | 01-May-25 A | 03-May-25 A | 2026-06-11 | 2026-06-11 | 01-May-25 A | 03-May-25 A
MechanicalDatasheetForPsa2FeedGasCompressor3RdStageCooler(TagNo.13-He-703) |  | 20-Jan-25 A | 14-Jun-25 A | 2026-06-11 | 2026-06-11 | 20-Jan-25 A | 14-Jun-25 A
A55010 | Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Cooler (Tag No. 13-He-703)_IFR | 20-Jan-25 A | 26-Feb-25 A | 2026-06-11 | 2026-06-11 | 20-Jan-25 A | 26-Feb-25 A
A55020 | Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Cooler (Tag No. 13-He-703)_RCC | 27-Feb-25 A | 19-Apr-25 A | 2026-06-11 | 2026-06-11 | 27-Feb-25 A | 19-Apr-25 A
A55030 | Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Cooler (Tag No. 13-He-703)_IFA | 20-Apr-25 A | 26-Apr-25 A | 2026-06-11 | 2026-06-11 | 20-Apr-25 A | 26-Apr-25 A
A55040 | Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Cooler (Tag No. 13-He-703)_RCA | 08-Jun-25 A | 10-Jun-25 A | 2026-06-11 | 2026-06-11 | 08-Jun-25 A | 10-Jun-25 A
A55050 | Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Cooler (Tag No. 13-He-703)_IFD/IFC | 11-Jun-25 A | 14-Jun-25 A | 2026-06-11 | 2026-06-11 | 11-Jun-25 A | 14-Jun-25 A
MechanicalDatasheetForPsa2OffGasCompressorInterstageCooler(TagNo.13-He-708) |  | 25-Feb-25 A | 09-May-25 A | 2026-06-11 | 2026-06-11 | 25-Feb-25 A | 09-May-25 A
A27430 | Mechanical Datasheet For Psa2 Off Gas Compressor Interstage Cooler(Tag No. 13-He-708)_IFA | 05-Mar-25 A | 25-Apr-25 A | 2026-06-11 | 2026-06-11 | 05-Mar-25 A | 25-Apr-25 A
A55060 | Mechanical Datasheet For Psa2 Off Gas Compressor Interstage Cooler(Tag No. 13-He-708)_IFR | 25-Feb-25 A | 26-Feb-25 A | 2026-06-11 | 2026-06-11 | 25-Feb-25 A | 26-Feb-25 A
A55070 | Mechanical Datasheet For Psa2 Off Gas Compressor Interstage Cooler(Tag No. 13-He-708)_RCC | 27-Feb-25 A | 04-Mar-25 A | 2026-06-11 | 2026-06-11 | 27-Feb-25 A | 04-Mar-25 A
A55080 | Mechanical Datasheet For Psa2 Off Gas Compressor Interstage Cooler(Tag No. 13-He-708)_RCA | 26-Apr-25 A | 02-May-25 A | 2026-06-11 | 2026-06-11 | 26-Apr-25 A | 02-May-25 A
A55090 | Mechanical Datasheet For Psa2 Off Gas Compressor Interstage Cooler(Tag No. 13-He-708)_IFD/IFC | 03-May-25 A | 09-May-25 A | 2026-06-11 | 2026-06-11 | 03-May-25 A | 09-May-25 A
MechanicalDatasheetForPsa2OffGasCompressorAftercooler(TagNo.13-He-709) |  | 25-Feb-25 A | 09-May-25 A | 2026-06-11 | 2026-06-11 | 25-Feb-25 A | 09-May-25 A
A55100 | Mechanical Datasheet For Psa2 Off Gas Compressor Aftercooler(Tag No. 13-He-709)_IFR | 25-Feb-25 A | 26-Feb-25 A | 2026-06-11 | 2026-06-11 | 25-Feb-25 A | 26-Feb-25 A
A55110 | Mechanical Datasheet For Psa2 Off Gas Compressor Aftercooler(Tag No. 13-He-709)_RCC | 27-Feb-25 A | 04-Mar-25 A | 2026-06-11 | 2026-06-11 | 27-Feb-25 A | 04-Mar-25 A
A55120 | Mechanical Datasheet For Psa2 Off Gas Compressor Aftercooler(Tag No. 13-He-709)_IFA | 05-Mar-25 A | 25-Apr-25 A | 2026-06-11 | 2026-06-11 | 05-Mar-25 A | 25-Apr-25 A
A55130 | Mechanical Datasheet For Psa2 Off Gas Compressor Aftercooler(Tag No. 13-He-709)_RCA | 26-Apr-25 A | 02-May-25 A | 2026-06-11 | 2026-06-11 | 26-Apr-25 A | 02-May-25 A
A55140 | Mechanical Datasheet For Psa2 Off Gas Compressor Aftercooler(Tag No. 13-He-709)_IFD/IFC | 03-May-25 A | 09-May-25 A | 2026-06-11 | 2026-06-11 | 03-May-25 A | 09-May-25 A
MechanicalDatasheetForPsa2OffGasCompressorDischargeDripleg-13-Sp-7004 |  | 01-Jan-25 A | 10-May-25 A | 2026-06-11 | 2027-03-23 | 01-Jan-25 A | 10-May-25 A
A27510 | Mechanical Datasheet For Psa2 Off Gas Compressor Discharge Dripleg -13-Sp-7004_IFR | 01-Jan-25 A | 24-Jan-25 A | 2026-06-11 | 2026-06-11 | 01-Jan-25 A | 24-Jan-25 A
A27520 | Mechanical Datasheet For Psa2 Off Gas Compressor Discharge Dripleg -13-Sp-7004_RCC | 25-Jan-25 A | 19-Apr-25 A | 2027-03-23 | 2027-03-23 | 25-Jan-25 A | 19-Apr-25 A
A55150 | Mechanical Datasheet For Psa2 Off Gas Compressor Discharge Dripleg -13-Sp-7004_IFA | 20-Apr-25 A | 26-Apr-25 A | 2027-03-23 | 2027-03-23 | 20-Apr-25 A | 26-Apr-25 A
A55160 | Mechanical Datasheet For Psa2 Off Gas Compressor Discharge Dripleg -13-Sp-7004_RCA | 27-Apr-25 A | 03-May-25 A | 2027-03-23 | 2027-03-23 | 27-Apr-25 A | 03-May-25 A
A55170 | Mechanical Datasheet For Psa2 Off Gas Compressor Discharge Dripleg -13-Sp-7004_IFD/IFC | 04-May-25 A | 10-May-25 A | 2027-03-23 | 2027-03-23 | 04-May-25 A | 10-May-25 A
MechanicalDatasheetForC4GuardAdsorberRegenerationGasCooler(TagNo.50-He-1410) |  | 27-Feb-25 A | 10-May-25 A | 2026-06-11 | 2026-06-11 | 27-Feb-25 A | 10-May-25 A
A55180 | Mechanical Datasheet For C4 Guard Adsorber Regeneration Gas Cooler(Tag No. 50-He-1410)_IFR | 27-Feb-25 A | 20-Mar-25 A | 2026-06-11 | 2026-06-11 | 27-Feb-25 A | 20-Mar-25 A
A55190 | Mechanical Datasheet For C4 Guard Adsorber Regeneration Gas Cooler(Tag No. 50-He-1410)_RCC | 21-Mar-25 A | 19-Apr-25 A | 2026-06-11 | 2026-06-11 | 21-Mar-25 A | 19-Apr-25 A
A55200 | Mechanical Datasheet For C4 Guard Adsorber Regeneration Gas Cooler(Tag No. 50-He-1410)_IFA | 20-Apr-25 A | 26-Apr-25 A | 2026-06-11 | 2026-06-11 | 20-Apr-25 A | 26-Apr-25 A
A55210 | Mechanical Datasheet For C4 Guard Adsorber Regeneration Gas Cooler(Tag No. 50-He-1410)_RCA | 27-Apr-25 A | 03-May-25 A | 2026-06-11 | 2026-06-11 | 27-Apr-25 A | 03-May-25 A
A55220 | Mechanical Datasheet For C4 Guard Adsorber Regeneration Gas Cooler(Tag No. 50-He-1410)_IFD/IFC | 04-May-25 A | 10-May-25 A | 2026-06-11 | 2026-06-11 | 04-May-25 A | 10-May-25 A
MechanicalDatasheetForVhpBoilerFeedWaterPreheaterDripleg |  | 01-Jul-25 A | 20-Mar-26 A | 2026-06-11 | 2027-03-23 | 01-Jul-25 A | 2026-04-14
A27610 | Mechanical Datasheet For Vhp Boiler Feed Water Preheater Dripleg_IFR | 01-Jul-25 A | 12-Jul-25 A | 2026-06-11 | 2026-06-11 | 01-Jul-25 A | 12-Jul-25 A
A55230 | Mechanical Datasheet For Vhp Boiler Feed Water Preheater Dripleg_RCC | 01-Mar-26 A | 10-Mar-26 A | 2027-03-23 | 2027-03-23 | 2026-02-20 | 2026-03-13
A55240 | Mechanical Datasheet For Vhp Boiler Feed Water Preheater Dripleg_IFA | 03-Mar-26 A | 11-Mar-26 A | 2027-03-23 | 2027-03-23 | 2026-03-13 | 2026-03-19
A55250 | Mechanical Datasheet For Vhp Boiler Feed Water Preheater Dripleg_RCA | 08-Mar-26 A | 14-Mar-26 A | 2027-03-23 | 2027-03-23 | 2026-03-19 | 2026-04-09
A55260 | Mechanical Datasheet For Vhp Boiler Feed Water Preheater Dripleg_IFD/IFC | 19-Mar-26 A | 20-Mar-26 A | 2027-03-23 | 2027-03-23 | 2026-04-09 | 2026-04-14
MechanicalDatasheetForOff-GasCompressorCoalescer |  | 13-Jan-25 A | 03-Mar-25 A | 2026-06-11 | 2026-06-11 | 13-Jan-25 A | 03-Mar-25 A
A27700 | Mechanical Datasheet For Off-Gas Compressor Coalescer_IFD/IFC | 25-Feb-25 A | 03-Mar-25 A | 2026-06-11 | 2026-06-11 | 25-Feb-25 A | 03-Mar-25 A
A55270 | Mechanical Datasheet For Off-Gas Compressor Coalescer_IFR | 13-Jan-25 A | 03-Feb-25 A | 2026-06-11 | 2026-06-11 | 13-Jan-25 A | 03-Feb-25 A
A55280 | Mechanical Datasheet For Off-Gas Compressor Coalescer_RCC | 04-Feb-25 A | 10-Feb-25 A | 2026-06-11 | 2026-06-11 | 04-Feb-25 A | 10-Feb-25 A
A55290 | Mechanical Datasheet For Off-Gas Compressor Coalescer_IFA | 11-Feb-25 A | 17-Feb-25 A | 2026-06-11 | 2026-06-11 | 11-Feb-25 A | 17-Feb-25 A
A55300 | Mechanical Datasheet For Off-Gas Compressor Coalescer_RCA | 18-Feb-25 A | 24-Feb-25 A | 2026-06-11 | 2026-06-11 | 18-Feb-25 A | 24-Feb-25 A
MechanicalDatasheetForGuardAdsorberRegenerationGasCoalescer |  | 06-Jan-25 A | 10-May-25 A | 2026-06-11 | 2026-06-11 | 06-Jan-25 A | 10-May-25 A
A55310 | Mechanical Datasheet For Guard Adsorber Regeneration Gas Coalescer_IFR | 06-Jan-25 A | 14-Mar-25 A | 2026-06-11 | 2026-06-11 | 06-Jan-25 A | 14-Mar-25 A
A55320 | Mechanical Datasheet For Guard Adsorber Regeneration Gas Coalescer_RCC | 15-Mar-25 A | 19-Apr-25 A | 2026-06-11 | 2026-06-11 | 15-Mar-25 A | 19-Apr-25 A
A55330 | Mechanical Datasheet For Guard Adsorber Regeneration Gas Coalescer_IFA | 20-Apr-25 A | 26-Apr-25 A | 2026-06-11 | 2026-06-11 | 20-Apr-25 A | 26-Apr-25 A
A55340 | Mechanical Datasheet For Guard Adsorber Regeneration Gas Coalescer_RCA | 27-Apr-25 A | 03-May-25 A | 2026-06-11 | 2026-06-11 | 27-Apr-25 A | 03-May-25 A
A55350 | Mechanical Datasheet For Guard Adsorber Regeneration Gas Coalescer_IFD/IFC | 04-May-25 A | 10-May-25 A | 2026-06-11 | 2026-06-11 | 04-May-25 A | 10-May-25 A
MechanicalDatasheetForTailGasSilencer |  | 01-Jul-25 A | 2026-06-09 | 2027-01-29 | 2027-03-23 | 01-Jul-25 A | 2026-04-14
A27790 | Mechanical Datasheet For Tail Gas Silencer_RCA | 2026-05-14 | 2026-06-04 | 2027-02-26 | 2027-03-19 | 2026-03-19 | 2026-04-09
A55360 | Mechanical Datasheet For Tail Gas Silencer_IFR | 01-Jul-25 A | 12-Jul-25 A | 2027-01-29 | 2027-01-29 | 01-Jul-25 A | 12-Jul-25 A
A55370 | Mechanical Datasheet For Tail Gas Silencer_RCC | 2026-04-17 | 2026-05-08 | 2027-01-29 | 2027-02-22 | 2026-02-20 | 2026-03-13
A55380 | Mechanical Datasheet For Tail Gas Silencer_IFA | 2026-05-08 | 2026-05-14 | 2027-02-22 | 2027-02-25 | 2026-03-13 | 2026-03-19
A55390 | Mechanical Datasheet For Tail Gas Silencer_IFD/IFC | 2026-06-04 | 2026-06-09 | 2027-03-19 | 2027-03-23 | 2026-04-09 | 2026-04-14
MaterialRequisitonforCoalscer |  | 28-Feb-25 A | 14-May-25 A | 2026-06-11 | 2026-06-11 | 28-Feb-25 A | 14-May-25 A
A45410 | Material Requisiton for Coalscer_IFR | 28-Feb-25 A | 21-Mar-25 A | 2026-06-11 | 2026-06-11 | 28-Feb-25 A | 21-Mar-25 A
A45420 | Material Requisiton for Coalscer_RCC | 22-Mar-25 A | 21-Apr-25 A | 2026-06-11 | 2026-06-11 | 22-Mar-25 A | 21-Apr-25 A
A45430 | Material Requisiton for Coalscer_IFA | 22-Apr-25 A | 30-Apr-25 A | 2026-06-11 | 2026-06-11 | 22-Apr-25 A | 30-Apr-25 A
A45440 | Material Requisiton for Coalscer_RCA | 01-May-25 A | 07-May-25 A | 2026-06-11 | 2026-06-11 | 01-May-25 A | 07-May-25 A
A45450 | Material Requisiton for Coalscer_IFD/IFC | 08-May-25 A | 14-May-25 A | 2026-06-11 | 2026-06-11 | 08-May-25 A | 14-May-25 A
MaterialRequisitonforShellandTubeHeatExchangers |  | 21-Feb-25 A | 20-Jun-25 A | 2026-06-11 | 2026-06-11 | 21-Feb-25 A | 20-Jun-25 A
A45360 | Material Requisiton for Heat Exchangers_IFR | 21-Feb-25 A | 14-Mar-25 A | 2026-06-11 | 2026-06-11 | 21-Feb-25 A | 14-Mar-25 A
A45370 | Material Requisiton for Heat Exchangers_RCC | 01-Jun-25 A | 05-Jun-25 A | 2026-06-11 | 2026-06-11 | 01-Jun-25 A | 05-Jun-25 A
A45380 | Material Requisiton for Heat Exchangers_IFA | 06-Jun-25 A | 10-Jun-25 A | 2026-06-11 | 2026-06-11 | 06-Jun-25 A | 10-Jun-25 A
A45390 | Material Requisiton for Heat Exchangers_RCA | 11-Jun-25 A | 15-Jun-25 A | 2026-06-11 | 2026-06-11 | 11-Jun-25 A | 15-Jun-25 A
A45400 | Material Requisiton for Heat Exchangers_IFD/IFC | 16-Jun-25 A | 20-Jun-25 A | 2026-06-11 | 2026-06-11 | 16-Jun-25 A | 20-Jun-25 A
MaterialRequisitonforPressureVessels&Internals |  | 17-Jan-25 A | 09-May-25 A | 2026-06-11 | 2026-06-11 | 17-Jan-25 A | 09-May-25 A
A45910 | Material Requisiton for Pressure Vessels & Internals_IFR | 17-Jan-25 A | 07-Feb-25 A | 2026-06-11 | 2026-06-11 | 17-Jan-25 A | 07-Feb-25 A
A45920 | Material Requisiton for Pressure Vessels & Internals_RCC | 08-Feb-25 A | 14-Feb-25 A | 2026-06-11 | 2026-06-11 | 08-Feb-25 A | 14-Feb-25 A
A45930 | Material Requisiton for Pressure Vessels & Internals_IFA | 15-Feb-25 A | 25-Apr-25 A | 2026-06-11 | 2026-06-11 | 15-Feb-25 A | 25-Apr-25 A
A45940 | Material Requisiton for Pressure Vessels & Internals_RCA | 26-Apr-25 A | 02-May-25 A | 2026-06-11 | 2026-06-11 | 26-Apr-25 A | 02-May-25 A
A45950 | Material Requisiton for Pressure Vessels & Internals_IFD/IFC | 03-May-25 A | 09-May-25 A | 2026-06-11 | 2026-06-11 | 03-May-25 A | 09-May-25 A
MechanicalRotating |  | 04-Jan-25 A | 28-Jun-25 A | 2026-06-11 | 2026-06-11 | 04-Jan-25 A | 28-Jun-25 A
MechanicalDatasheetForSanitaryWaterCollectionPump |  | 05-Feb-25 A | 10-May-25 A | 2026-06-11 | 2026-06-11 | 05-Feb-25 A | 10-May-25 A
A54540 | Mechanical Datasheet For Sanitary Water Collection Pump_IFR | 05-Feb-25 A | 26-Feb-25 A | 2026-06-11 | 2026-06-11 | 05-Feb-25 A | 26-Feb-25 A
A54550 | Mechanical Datasheet For Sanitary Water Collection Pump_RCC | 27-Feb-25 A | 19-Apr-25 A | 2026-06-11 | 2026-06-11 | 27-Feb-25 A | 19-Apr-25 A
A54560 | Mechanical Datasheet For Sanitary Water Collection Pump_IFA | 20-Apr-25 A | 26-Apr-25 A | 2026-06-11 | 2026-06-11 | 20-Apr-25 A | 26-Apr-25 A
A54570 | Mechanical Datasheet For Sanitary Water Collection Pump_RCA | 27-Apr-25 A | 03-May-25 A | 2026-06-11 | 2026-06-11 | 27-Apr-25 A | 03-May-25 A
A54580 | Mechanical Datasheet For Sanitary Water Collection Pump_IFD/IFC | 04-May-25 A | 10-May-25 A | 2026-06-11 | 2026-06-11 | 04-May-25 A | 10-May-25 A
MechanicalDataSheetforEOTCraneforFeedGasCompressor |  | 27-Jan-25 A | 28-Jun-25 A | 2026-06-11 | 2026-06-11 | 27-Jan-25 A | 28-Jun-25 A
A45610 | Mechanical Data Sheet for EOT Crane for Feed Gas Compressor_IFR | 27-Jan-25 A | 26-Feb-25 A | 2026-06-11 | 2026-06-11 | 27-Jan-25 A | 26-Feb-25 A
A45620 | Mechanical Data Sheet for EOT Crane for Feed Gas Compressor_RCC | 27-Feb-25 A | 19-Apr-25 A | 2026-06-11 | 2026-06-11 | 27-Feb-25 A | 19-Apr-25 A
A45630 | Mechanical Data Sheet for EOT Crane for Feed Gas Compressor_IFA | 20-Apr-25 A | 10-Jun-25 A | 2026-06-11 | 2026-06-11 | 20-Apr-25 A | 10-Jun-25 A
A45640 | Mechanical Data Sheet for EOT Crane for Feed Gas Compressor_RCA | 11-Jun-25 A | 21-Jun-25 A | 2026-06-11 | 2026-06-11 | 11-Jun-25 A | 21-Jun-25 A
A45650 | Mechanical Data Sheet for EOT Crane for Feed Gas Compressor_IFD/IFC | 22-Jun-25 A | 28-Jun-25 A | 2026-06-11 | 2026-06-11 | 22-Jun-25 A | 28-Jun-25 A
MechanicalDataSheetEOTCraneforOffGasCompressor |  | 27-Jan-25 A | 28-Jun-25 A | 2026-06-11 | 2026-06-11 | 27-Jan-25 A | 28-Jun-25 A
A45660 | Mechanical Data Sheet EOT Crane for Off Gas Compressor_IFR | 27-Jan-25 A | 26-Feb-25 A | 2026-06-11 | 2026-06-11 | 27-Jan-25 A | 26-Feb-25 A
A45670 | Mechanical Data Sheet EOT Crane for Off Gas Compressor_RCC | 27-Feb-25 A | 18-Mar-25 A | 2026-06-11 | 2026-06-11 | 27-Feb-25 A | 18-Mar-25 A
A45680 | Mechanical Data Sheet EOT Crane for Off Gas Compressor_IFA | 19-Mar-25 A | 10-Jun-25 A | 2026-06-11 | 2026-06-11 | 19-Mar-25 A | 10-Jun-25 A
A45690 | Mechanical Data Sheet EOT Crane for Off Gas Compressor_RCA | 11-Jun-25 A | 21-Jun-25 A | 2026-06-11 | 2026-06-11 | 11-Jun-25 A | 21-Jun-25 A
A45700 | Mechanical Data Sheet EOT Crane for Off Gas Compressor_IFD/IFC | 22-Jun-25 A | 28-Jun-25 A | 2026-06-11 | 2026-06-11 | 22-Jun-25 A | 28-Jun-25 A
MechanicalDatasheetforWaterCollectionSumpPump |  | 04-Jan-25 A | 10-May-25 A | 2026-06-11 | 2026-06-11 | 04-Jan-25 A | 10-May-25 A
A45560 | Mechanical Datasheet for Water Collection Sump Pump_IFR | 04-Jan-25 A | 25-Jan-25 A | 2026-06-11 | 2026-06-11 | 04-Jan-25 A | 25-Jan-25 A
A45570 | Mechanical Datasheet for Water Collection Sump Pump_RCC | 26-Jan-25 A | 19-Apr-25 A | 2026-06-11 | 2026-06-11 | 26-Jan-25 A | 19-Apr-25 A
A45580 | Mechanical Datasheet for Water Collection Sump Pump_IFA | 20-Apr-25 A | 26-Apr-25 A | 2026-06-11 | 2026-06-11 | 20-Apr-25 A | 26-Apr-25 A
A45590 | Mechanical Datasheet for Water Collection Sump Pump_RCA | 27-Apr-25 A | 03-May-25 A | 2026-06-11 | 2026-06-11 | 27-Apr-25 A | 03-May-25 A
A45600 | Mechanical Datasheet for Water Collection Sump Pump_IFD/IFC | 04-May-25 A | 10-May-25 A | 2026-06-11 | 2026-06-11 | 04-May-25 A | 10-May-25 A
MaterialRequisitonforEOTCrane |  | 15-Apr-25 A | 13-Jun-25 A | 2026-06-11 | 2026-06-11 | 15-Apr-25 A | 13-Jun-25 A
A45760 | Material Requisiton for EOT Crane_IFR | 15-Apr-25 A | 06-May-25 A | 2026-06-11 | 2026-06-11 | 15-Apr-25 A | 06-May-25 A
A45770 | Material Requisiton for EOT Crane_RCC | 07-May-25 A | 13-May-25 A | 2026-06-11 | 2026-06-11 | 07-May-25 A | 13-May-25 A
A45780 | Material Requisiton for EOT Crane_IFA | 14-May-25 A | 20-May-25 A | 2026-06-11 | 2026-06-11 | 14-May-25 A | 20-May-25 A
A45790 | Material Requisiton for EOT Crane_RCA | 21-May-25 A | 02-Jun-25 A | 2026-06-11 | 2026-06-11 | 21-May-25 A | 02-Jun-25 A
A45800 | Material Requisiton for EOT Crane_IFD/IFC | 03-Jun-25 A | 13-Jun-25 A | 2026-06-11 | 2026-06-11 | 03-Jun-25 A | 13-Jun-25 A
MaterialRequisitonforCentrifugalPump |  | 27-Jan-25 A | 21-Jun-25 A | 2026-06-11 | 2026-06-11 | 27-Jan-25 A | 21-Jun-25 A
A45710 | Material Requisiton for Centrifugal Pump_IFR | 27-Jan-25 A | 21-Mar-25 A | 2026-06-11 | 2026-06-11 | 27-Jan-25 A | 21-Mar-25 A
A45720 | Material Requisiton for Centrifugal Pump_RCC | 22-Mar-25 A | 19-Apr-25 A | 2026-06-11 | 2026-06-11 | 22-Mar-25 A | 19-Apr-25 A
A45730 | Material Requisiton for Centrifugal Pump_IFA | 20-Apr-25 A | 01-May-25 A | 2026-06-11 | 2026-06-11 | 20-Apr-25 A | 01-May-25 A
A45740 | Material Requisiton for Centrifugal Pump_RCA | 02-May-25 A | 26-May-25 A | 2026-06-11 | 2026-06-11 | 02-May-25 A | 26-May-25 A
A45750 | Material Requisiton for Centrifugal Pump_IFD/IFC | 27-May-25 A | 21-Jun-25 A | 2026-06-11 | 2026-06-11 | 27-May-25 A | 21-Jun-25 A
Safety |  | 31-Dec-24 A | 2026-06-16 | 2026-06-11 | 2027-03-23 | 31-Dec-24 A | 2026-05-14
EngineeringHSEPlan |  | 30-Jan-25 A | 19-May-25 A | 2026-06-11 | 2027-03-23 | 30-Jan-25 A | 19-May-25 A
A46010 | Engineering HSE Plan_IFR | 30-Jan-25 A | 20-Feb-25 A | 2026-06-11 | 2026-06-11 | 30-Jan-25 A | 20-Feb-25 A
A46020 | Engineering HSE Plan_RCC | 21-Feb-25 A | 27-Feb-25 A | 2027-03-23 | 2027-03-23 | 21-Feb-25 A | 27-Feb-25 A
A46030 | Engineering HSE Plan_IFA | 28-Feb-25 A | 06-Mar-25 A | 2027-03-23 | 2027-03-23 | 28-Feb-25 A | 06-Mar-25 A
A46040 | Engineering HSE Plan_RCA | 07-Mar-25 A | 12-May-25 A | 2027-03-23 | 2027-03-23 | 07-Mar-25 A | 12-May-25 A
A46050 | Engineering HSE Plan_IFD/IFC | 13-May-25 A | 19-May-25 A | 2027-03-23 | 2027-03-23 | 13-May-25 A | 19-May-25 A
ProjectHSEPhilosophy |  | 31-Dec-24 A | 20-May-25 A | 2026-06-11 | 2027-03-23 | 31-Dec-24 A | 20-May-25 A
A46060 | Project HSE Philosophy_IFR | 31-Dec-24 A | 23-Jan-25 A | 2026-06-11 | 2026-06-11 | 31-Dec-24 A | 23-Jan-25 A
A46070 | Project HSE Philosophy_RCC | 24-Jan-25 A | 03-Mar-25 A | 2026-06-22 | 2026-06-22 | 24-Jan-25 A | 03-Mar-25 A
A46080 | Project HSE Philosophy_IFA | 04-Mar-25 A | 10-Mar-25 A | 2026-06-22 | 2026-06-22 | 04-Mar-25 A | 10-Mar-25 A
A46090 | Project HSE Philosophy_RCA | 11-Mar-25 A | 13-Mar-25 A | 2027-03-23 | 2027-03-23 | 11-Mar-25 A | 13-Mar-25 A
A46100 | Project HSE Philosophy_IFD/IFC | 14-Mar-25 A | 20-May-25 A | 2027-03-23 | 2027-03-23 | 14-Mar-25 A | 20-May-25 A
FireProtectionandDetectionPhilosophy |  | 07-Feb-25 A | 19-Nov-25 A | 2026-06-11 | 2027-03-23 | 07-Feb-25 A | 19-Nov-25 A
A46110 | Fire Protection and Detection Philosophy_IFR | 07-Feb-25 A | 28-Feb-25 A | 2026-06-11 | 2026-06-11 | 07-Feb-25 A | 28-Feb-25 A
A46120 | Fire Protection and Detection Philosophy_RCC | 01-Mar-25 A | 21-Jun-25 A | 2027-03-23 | 2027-03-23 | 01-Mar-25 A | 21-Jun-25 A
A46130 | Fire Protection and Detection Philosophy_IFA | 22-Jun-25 A | 28-Jun-25 A | 2027-03-23 | 2027-03-23 | 22-Jun-25 A | 28-Jun-25 A
A46140 | Fire Protection and Detection Philosophy_RCA | 28-Aug-25 A | 16-Oct-25 A | 2027-03-23 | 2027-03-23 | 28-Aug-25 A | 16-Oct-25 A
A46150 | Fire Protection and Detection Philosophy_IFD/IFC | 10-Nov-25 A | 19-Nov-25 A | 2027-03-23 | 2027-03-23 | 10-Nov-25 A | 19-Nov-25 A
HazardousAreaClassificationSchedule |  | 17-Jan-25 A | 23-Dec-25 A | 2026-06-15 | 2027-03-23 | 17-Jan-25 A | 23-Dec-25 A
A46160 | Hazardous Area Classification Schedule_IFR | 17-Jan-25 A | 07-Feb-25 A | 2026-06-15 | 2026-06-15 | 17-Jan-25 A | 07-Feb-25 A
A46170 | Hazardous Area Classification Schedule_RCC | 08-Feb-25 A | 06-May-25 A | 2026-06-15 | 2026-06-15 | 08-Feb-25 A | 06-May-25 A
A46180 | Hazardous Area Classification Schedule_IFA | 07-May-25 A | 20-May-25 A | 2026-06-15 | 2026-06-15 | 07-May-25 A | 20-May-25 A
A46190 | Hazardous Area Classification Schedule_RCA | 23-Jun-25 A | 22-Aug-25 A | 2027-03-23 | 2027-03-23 | 23-Jun-25 A | 22-Aug-25 A
A46200 | Hazardous Area Classification Schedule_IFD/IFC | 19-Dec-25 A | 23-Dec-25 A | 2027-03-23 | 2027-03-23 | 19-Dec-25 A | 23-Dec-25 A
FireProtectionandSafetyEquipmentLayouts(Building) |  | 27-Feb-25 A | 23-Dec-25 A | 2026-07-06 | 2027-03-23 | 27-Feb-25 A | 23-Dec-25 A
A46360 | Fire Protection and Safety Equipment Layouts (Building)_IFR | 27-Feb-25 A | 20-Mar-25 A | 2026-07-06 | 2026-07-06 | 27-Feb-25 A | 20-Mar-25 A
A46370 | Fire Protection and Safety Equipment Layouts (Building)_RCC | 21-Mar-25 A | 21-Jun-25 A | 2027-03-23 | 2027-03-23 | 21-Mar-25 A | 21-Jun-25 A
A46380 | Fire Protection and Safety Equipment Layouts (Building)_IFA | 22-Jun-25 A | 28-Jul-25 A | 2027-03-23 | 2027-03-23 | 22-Jun-25 A | 28-Jul-25 A
A46390 | Fire Protection and Safety Equipment Layouts (Building)_RCA | 29-Jul-25 A | 27-Aug-25 A | 2027-03-23 | 2027-03-23 | 29-Jul-25 A | 27-Aug-25 A
A46400 | Fire Protection and Safety Equipment Layouts (Building)_IFD/IFC | 19-Dec-25 A | 23-Dec-25 A | 2027-03-23 | 2027-03-23 | 19-Dec-25 A | 23-Dec-25 A
EscapeRouteandSafetySignsLayouts(Building) |  | 27-Feb-25 A | 23-Dec-25 A | 2026-07-06 | 2027-03-23 | 27-Feb-25 A | 23-Dec-25 A
A46460 | Escape Route and Safety Signs Layouts (Building)_IFR | 27-Feb-25 A | 20-Mar-25 A | 2026-07-06 | 2026-07-06 | 27-Feb-25 A | 20-Mar-25 A
A46470 | Escape Route and Safety Signs Layouts (Building)_RCC | 21-Mar-25 A | 21-Jun-25 A | 2027-03-23 | 2027-03-23 | 21-Mar-25 A | 21-Jun-25 A
A46480 | Escape Route and Safety Signs Layouts (Building)_IFA | 01-Oct-25 A | 07-Oct-25 A | 2027-03-23 | 2027-03-23 | 01-Oct-25 A | 07-Oct-25 A
A46490 | Escape Route and Safety Signs Layouts (Building)_RCA | 03-Oct-25 A | 14-Oct-25 A | 2027-03-23 | 2027-03-23 | 03-Oct-25 A | 14-Oct-25 A
A46500 | Escape Route and Safety Signs Layouts (Building)_IFD/IFC | 19-Dec-25 A | 23-Dec-25 A | 2027-03-23 | 2027-03-23 | 19-Dec-25 A | 23-Dec-25 A
Fire&GasDetectorsLayouts(Building) |  | 27-Feb-25 A | 23-Dec-25 A | 2026-07-06 | 2027-03-23 | 27-Feb-25 A | 23-Dec-25 A
A46560 | Fire & Gas Detectors Layouts (Building)_IFR | 27-Feb-25 A | 20-Mar-25 A | 2026-07-06 | 2026-07-06 | 27-Feb-25 A | 20-Mar-25 A
A46570 | Fire & Gas Detectors Layouts (Building)_RCC | 21-Mar-25 A | 21-Jun-25 A | 2027-03-23 | 2027-03-23 | 21-Mar-25 A | 21-Jun-25 A
A46580 | Fire & Gas Detectors Layouts (Building)_IFA | 22-Jun-25 A | 16-Jul-25 A | 2027-03-23 | 2027-03-23 | 22-Jun-25 A | 16-Jul-25 A
A46590 | Fire & Gas Detectors Layouts (Building)_RCA | 08-Sep-25 A | 07-Oct-25 A | 2027-03-23 | 2027-03-23 | 08-Sep-25 A | 07-Oct-25 A
A46600 | Fire & Gas Detectors Layouts (Building)_IFD/IFC | 19-Dec-25 A | 23-Dec-25 A | 2027-03-23 | 2027-03-23 | 19-Dec-25 A | 23-Dec-25 A
F&GCauseandEffectsMatrix |  | 2026-04-17 | 2026-06-16 | 2027-01-22 | 2027-03-23 | 2026-02-20 | 2026-04-21
A46610 | F&G Cause and Effects Matrix_IFR | 2026-04-17 | 2026-04-24 | 2027-01-22 | 2027-01-29 | 2026-02-20 | 2026-02-27
A46620 | F&G Cause and Effects Matrix_RCC | 2026-04-24 | 2026-05-18 | 2027-01-29 | 2027-02-22 | 2026-02-27 | 2026-03-23
A46630 | F&G Cause and Effects Matrix_IFA | 2026-05-18 | 2026-05-21 | 2027-02-22 | 2027-02-25 | 2026-03-23 | 2026-03-26
A46640 | F&G Cause and Effects Matrix_RCA | 2026-05-21 | 2026-06-12 | 2027-02-26 | 2027-03-19 | 2026-03-26 | 2026-04-17
A46650 | F&G Cause and Effects Matrix_IFD/IFC | 2026-06-12 | 2026-06-16 | 2027-03-19 | 2027-03-23 | 2026-04-17 | 2026-04-21
SpecificationforFireProtectionandSafetyEquipment |  | 07-Feb-25 A | 23-Dec-25 A | 2026-06-30 | 2027-03-23 | 07-Feb-25 A | 23-Dec-25 A
A46760 | Specification for Fire Protection and Safety Equipment_IFR | 07-Feb-25 A | 28-Feb-25 A | 2026-06-30 | 2026-06-30 | 07-Feb-25 A | 28-Feb-25 A
A46770 | Specification for Fire Protection and Safety Equipment_RCC | 01-Mar-25 A | 31-Jul-25 A | 2027-03-23 | 2027-03-23 | 01-Mar-25 A | 31-Jul-25 A
A46780 | Specification for Fire Protection and Safety Equipment_IFA | 01-Oct-25 A | 07-Oct-25 A | 2027-03-23 | 2027-03-23 | 01-Oct-25 A | 07-Oct-25 A
A46790 | Specification for Fire Protection and Safety Equipment_RCA | 03-Oct-25 A | 14-Oct-25 A | 2027-03-23 | 2027-03-23 | 03-Oct-25 A | 14-Oct-25 A
A46800 | Specification for Fire Protection and Safety Equipment_IFD/IFC | 19-Dec-25 A | 23-Dec-25 A | 2027-03-23 | 2027-03-23 | 19-Dec-25 A | 23-Dec-25 A
SpecificationforCleanAgentSystem |  | 11-Feb-25 A | 10-Oct-25 A | 2026-06-30 | 2027-03-23 | 11-Feb-25 A | 10-Oct-25 A
A46810 | Specification for Clean Agent System_IFR | 11-Feb-25 A | 04-Mar-25 A | 2026-06-30 | 2026-06-30 | 11-Feb-25 A | 04-Mar-25 A
A46820 | Specification for Clean Agent System_RCC | 05-Mar-25 A | 21-Jun-25 A | 2027-03-23 | 2027-03-23 | 05-Mar-25 A | 21-Jun-25 A
A46830 | Specification for Clean Agent System_IFA | 22-Jun-25 A | 30-Jun-25 A | 2027-03-23 | 2027-03-23 | 22-Jun-25 A | 30-Jun-25 A
A46840 | Specification for Clean Agent System_RCA | 12-Jul-25 A | 30-Jul-25 A | 2027-03-23 | 2027-03-23 | 12-Jul-25 A | 30-Jul-25 A
A46850 | Specification for Clean Agent System_IFD/IFC | 01-Oct-25 A | 10-Oct-25 A | 2027-03-23 | 2027-03-23 | 01-Oct-25 A | 10-Oct-25 A
MRforCleanAgentSystem |  | 28-Feb-25 A | 10-Oct-25 A | 2026-06-30 | 2026-06-30 | 28-Feb-25 A | 10-Oct-25 A
A47230 | MR for Clean Agent System_IFR | 28-Feb-25 A | 21-Mar-25 A | 2026-06-30 | 2026-06-30 | 28-Feb-25 A | 21-Mar-25 A
A47240 | MR for Clean Agent System_RCC | 22-Mar-25 A | 21-Jun-25 A | 2026-06-30 | 2026-06-30 | 22-Mar-25 A | 21-Jun-25 A
A47250 | MR for Clean Agent System_IFA | 22-Jun-25 A | 23-Aug-25 A | 2026-06-30 | 2026-06-30 | 22-Jun-25 A | 23-Aug-25 A
A47260 | MR for Clean Agent System_RCA | 24-Aug-25 A | 30-Aug-25 A | 2026-06-30 | 2026-06-30 | 24-Aug-25 A | 30-Aug-25 A
A47270 | MR for Clean Agent System_IFD/IFC | 01-Oct-25 A | 10-Oct-25 A | 2026-06-30 | 2026-06-30 | 01-Oct-25 A | 10-Oct-25 A
FirewaterLineList |  | 28-Feb-25 A | 2026-06-09 | 2027-01-29 | 2027-03-23 | 28-Feb-25 A | 2026-04-17
A47130 | Firewater Line List_IFR | 28-Feb-25 A | 21-Mar-25 A | 2027-01-29 | 2027-01-29 | 28-Feb-25 A | 21-Mar-25 A
A47140 | Firewater Line List_RCC | 2026-04-17 | 2026-05-08 | 2027-01-29 | 2027-02-22 | 2026-02-20 | 2026-03-13
A47150 | Firewater Line List_IFA | 2026-05-08 | 2026-05-14 | 2027-02-22 | 2027-02-25 | 2026-03-19 | 2026-03-24
A47160 | Firewater Line List_RCA | 2026-05-14 | 2026-06-04 | 2027-02-26 | 2027-03-19 | 2026-03-24 | 2026-04-15
A47170 | Firewater Line List_IFD/IFC | 2026-06-04 | 2026-06-09 | 2027-03-19 | 2027-03-23 | 2026-04-15 | 2026-04-17
PassiveFireProtectionschedule |  | 28-Feb-25 A | 23-Dec-25 A | 2027-03-23 | 2027-03-23 | 28-Feb-25 A | 23-Dec-25 A
A46660 | Passive Fire Protection schedule_IFR | 28-Feb-25 A | 21-Mar-25 A | 2027-03-23 | 2027-03-23 | 28-Feb-25 A | 21-Mar-25 A
A46670 | Passive Fire Protection schedule_RCC | 22-Mar-25 A | 21-Jun-25 A | 2027-03-23 | 2027-03-23 | 22-Mar-25 A | 21-Jun-25 A
A46680 | Passive Fire Protection schedule_IFA | 22-Jun-25 A | 18-Jul-25 A | 2027-03-23 | 2027-03-23 | 22-Jun-25 A | 18-Jul-25 A
A46690 | Passive Fire Protection schedule_RCA | 08-Sep-25 A | 07-Oct-25 A | 2027-03-23 | 2027-03-23 | 08-Sep-25 A | 07-Oct-25 A
A46700 | Passive Fire Protection schedule_IFD/IFC | 19-Dec-25 A | 23-Dec-25 A | 2027-03-23 | 2027-03-23 | 19-Dec-25 A | 23-Dec-25 A
FirewaterDemandReport |  | 17-Jan-25 A | 03-Nov-25 A | 2027-01-29 | 2027-03-23 | 17-Jan-25 A | 03-Nov-25 A
A47070 | Firewater Demand Report_IFD/IFC | 30-Oct-25 A | 03-Nov-25 A | 2027-03-23 | 2027-03-23 | 30-Oct-25 A | 03-Nov-25 A
A9080 | Firewater Demand Report_IFR | 17-Jan-25 A | 11-Mar-25 A | 2027-01-29 | 2027-01-29 | 17-Jan-25 A | 11-Mar-25 A
A9090 | Firewater Demand Report_RCC | 12-Mar-25 A | 21-Jul-25 A | 2027-03-23 | 2027-03-23 | 12-Mar-25 A | 21-Jul-25 A
A9100 | Firewater Demand Report_IFA | 22-Jul-25 A | 06-Sep-25 A | 2027-03-23 | 2027-03-23 | 22-Jul-25 A | 06-Sep-25 A
A9110 | Firewater Demand Report_RCA | 07-Sep-25 A | 13-Sep-25 A | 2027-03-23 | 2027-03-23 | 07-Sep-25 A | 13-Sep-25 A
HAZIDENVIDOHIDCloseoutReport |  | 01-Sep-25 A | 2026-05-12 | 2026-06-22 | 2027-03-23 | 01-Sep-25 A | 2026-03-17
A47330 | HAZID ENVID OHID Closeout Report_IFR | 01-Sep-25 A | 12-Sep-25 A | 2026-06-22 | 2026-06-22 | 01-Sep-25 A | 12-Sep-25 A
A47340 | HAZID ENVID OHID Closeout Report_RCC | 05-Sep-25 A | 20-Sep-25 A | 2027-02-26 | 2027-02-26 | 05-Sep-25 A | 20-Sep-25 A
A47350 | HAZID ENVID OHID Closeout Report_IFA | 28-Nov-25 A | 19-Dec-25 A | 2027-02-26 | 2027-02-26 | 28-Nov-25 A | 19-Dec-25 A
A47360 | HAZID ENVID OHID Closeout Report_RCA | 2026-04-17 | 2026-05-08 | 2027-02-26 | 2027-03-19 | 2026-02-20 | 2026-03-13
A47370 | HAZID ENVID OHID Closeout Report_IFD/IFC | 2026-05-08 | 2026-05-12 | 2027-03-19 | 2027-03-23 | 2026-03-13 | 2026-03-17
EscapeRouteandSafetySignsLayouts(Plant) |  | 16-Apr-25 A | 23-Dec-25 A | 2026-07-06 | 2027-03-23 | 16-Apr-25 A | 23-Dec-25 A
A46410 | Escape Route and Safety Signs Layouts (Plant)_IFR | 16-Apr-25 A | 07-May-25 A | 2026-07-06 | 2026-07-06 | 16-Apr-25 A | 07-May-25 A
A46420 | Escape Route and Safety Signs Layouts (Plant)_RCC | 08-May-25 A | 21-Jun-25 A | 2027-03-23 | 2027-03-23 | 08-May-25 A | 21-Jun-25 A
A46430 | Escape Route and Safety Signs Layouts (Plant)_IFA | 22-Jun-25 A | 28-Jul-25 A | 2027-03-23 | 2027-03-23 | 22-Jun-25 A | 28-Jul-25 A
A46440 | Escape Route and Safety Signs Layouts (Plant)_RCA | 29-Jul-25 A | 30-Aug-25 A | 2027-03-23 | 2027-03-23 | 29-Jul-25 A | 30-Aug-25 A
A46450 | Escape Route and Safety Signs Layouts (Plant)_IFD/IFC | 19-Dec-25 A | 23-Dec-25 A | 2027-03-23 | 2027-03-23 | 19-Dec-25 A | 23-Dec-25 A
Fire&GasDetectorsLayouts(Plant) |  | 06-Apr-25 A | 23-Dec-25 A | 2026-07-06 | 2027-03-23 | 06-Apr-25 A | 23-Dec-25 A
A46510 | Fire & Gas Detectors Layouts (Plant)_IFR | 06-Apr-25 A | 27-Apr-25 A | 2026-07-06 | 2026-07-06 | 06-Apr-25 A | 27-Apr-25 A
A46520 | Fire & Gas Detectors Layouts (Plant)_RCC | 28-Apr-25 A | 21-Jun-25 A | 2027-03-23 | 2027-03-23 | 28-Apr-25 A | 21-Jun-25 A
A46530 | Fire & Gas Detectors Layouts (Plant)_IFA | 22-Jun-25 A | 28-Jun-25 A | 2027-03-23 | 2027-03-23 | 22-Jun-25 A | 28-Jun-25 A
A46540 | Fire & Gas Detectors Layouts (Plant)_RCA | 01-Sep-25 A | 07-Oct-25 A | 2027-03-23 | 2027-03-23 | 01-Sep-25 A | 07-Oct-25 A
A46550 | Fire & Gas Detectors Layouts (Plant)_IFD/IFC | 19-Dec-25 A | 23-Dec-25 A | 2027-03-23 | 2027-03-23 | 19-Dec-25 A | 23-Dec-25 A
PassiveFireProtectionLayouts |  | 08-Apr-25 A | 23-Dec-25 A | 2027-03-23 | 2027-03-23 | 08-Apr-25 A | 23-Dec-25 A
A46710 | Passive Fire Protection Layouts_IFR | 08-Apr-25 A | 29-Apr-25 A | 2027-03-23 | 2027-03-23 | 08-Apr-25 A | 29-Apr-25 A
A46720 | Passive Fire Protection Layouts_RCC | 30-Apr-25 A | 21-Jun-25 A | 2027-03-23 | 2027-03-23 | 30-Apr-25 A | 21-Jun-25 A
A46730 | Passive Fire Protection Layouts_IFA | 22-Jun-25 A | 29-Jul-25 A | 2027-03-23 | 2027-03-23 | 22-Jun-25 A | 29-Jul-25 A
A46740 | Passive Fire Protection Layouts_RCA | 08-Sep-25 A | 07-Oct-25 A | 2027-03-23 | 2027-03-23 | 08-Sep-25 A | 07-Oct-25 A
A46750 | Passive Fire Protection Layouts_IFD/IFC | 19-Dec-25 A | 23-Dec-25 A | 2027-03-23 | 2027-03-23 | 19-Dec-25 A | 23-Dec-25 A
HAZOPCloseoutReport |  | 01-Aug-25 A | 04-Sep-25 A | 2026-06-15 | 2026-06-15 | 01-Aug-25 A | 04-Sep-25 A
A47430 | HAZOP Closeout Report_IFR | 01-Aug-25 A | 16-Aug-25 A | 2026-06-15 | 2026-06-15 | 01-Aug-25 A | 16-Aug-25 A
A47440 | HAZOP Closeout Report_RCC | 04-Aug-25 A | 25-Aug-25 A | 2026-06-15 | 2026-06-15 | 04-Aug-25 A | 25-Aug-25 A
A47450 | HAZOP Closeout Report_IFA | 25-Aug-25 A | 28-Aug-25 A | 2026-06-15 | 2026-06-15 | 25-Aug-25 A | 28-Aug-25 A
A47460 | HAZOP Closeout Report_RCA | 29-Aug-25 A | 31-Aug-25 A | 2026-06-15 | 2026-06-15 | 29-Aug-25 A | 31-Aug-25 A
A47470 | HAZOP Closeout Report_IFD/IFC | 01-Sep-25 A | 04-Sep-25 A | 2026-06-15 | 2026-06-15 | 01-Sep-25 A | 04-Sep-25 A
FireProtectionandSafetyEquipmentLayouts(Plant) |  | 28-Mar-25 A | 20-Mar-26 A | 2026-07-06 | 2027-03-23 | 28-Mar-25 A | 2026-02-24
A46310 | Fire Protection and Safety Equipment Layouts (Plant)_IFR | 28-Mar-25 A | 21-Apr-25 A | 2026-07-06 | 2026-07-06 | 28-Mar-25 A | 21-Apr-25 A
A46320 | Fire Protection and Safety Equipment Layouts (Plant)_RCC | 22-Apr-25 A | 21-Jun-25 A | 2027-03-23 | 2027-03-23 | 22-Apr-25 A | 21-Jun-25 A
A46330 | Fire Protection and Safety Equipment Layouts (Plant)_IFA | 22-Jun-25 A | 28-Jul-25 A | 2027-03-23 | 2027-03-23 | 22-Jun-25 A | 28-Jul-25 A
A46340 | Fire Protection and Safety Equipment Layouts (Plant)_RCA | 29-Jul-25 A | 30-Aug-25 A | 2027-03-23 | 2027-03-23 | 29-Jul-25 A | 30-Aug-25 A
A46350 | Fire Protection and Safety Equipment Layouts (Plant)_IFD/IFC | 17-Mar-26 A | 20-Mar-26 A | 2027-03-23 | 2027-03-23 | 2026-02-20 | 2026-02-24
FirewaterHydraulicReport |  | 02-Jul-25 A | 2026-06-09 | 2027-01-29 | 2027-03-23 | 02-Jul-25 A | 2026-04-14
A47080 | Firewater Hydraulic Report_IFR | 02-Jul-25 A | 11-Jul-25 A | 2027-01-29 | 2027-01-29 | 02-Jul-25 A | 11-Jul-25 A
A47090 | Firewater Hydraulic Report_RCC | 2026-04-17 | 2026-05-08 | 2027-01-29 | 2027-02-22 | 2026-02-20 | 2026-03-13
A47100 | Firewater Hydraulic Report_IFA | 2026-05-08 | 2026-05-14 | 2027-02-22 | 2027-02-25 | 2026-03-13 | 2026-03-19
A47110 | Firewater Hydraulic Report_RCA | 2026-05-14 | 2026-06-04 | 2027-02-26 | 2027-03-19 | 2026-03-19 | 2026-04-09
A47120 | Firewater Hydraulic Report_IFD/IFC | 2026-06-04 | 2026-06-09 | 2027-03-19 | 2027-03-23 | 2026-04-09 | 2026-04-14
DatasheetsforFireProtectionandSafetyEquipment |  | 17-Apr-25 A | 23-Dec-25 A | 2026-07-06 | 2026-07-06 | 17-Apr-25 A | 23-Dec-25 A
A46860 | Datasheets for Fire Protection and Safety Equipment_IFR | 17-Apr-25 A | 08-May-25 A | 2026-07-06 | 2026-07-06 | 17-Apr-25 A | 08-May-25 A
A46870 | Datasheets for Fire Protection and Safety Equipment_RCC | 09-May-25 A | 21-Jun-25 A | 2026-07-06 | 2026-07-06 | 09-May-25 A | 21-Jun-25 A
A46880 | Datasheets for Fire Protection and Safety Equipment_IFA | 18-Aug-25 A | 25-Aug-25 A | 2026-07-06 | 2026-07-06 | 18-Aug-25 A | 25-Aug-25 A
A46890 | Datasheets for Fire Protection and Safety Equipment_RCA | 01-Sep-25 A | 07-Oct-25 A | 2026-07-06 | 2026-07-06 | 01-Sep-25 A | 07-Oct-25 A
A46900 | Datasheets for Fire Protection and Safety Equipment_IFD/IFC | 19-Dec-25 A | 23-Dec-25 A | 2026-07-06 | 2026-07-06 | 19-Dec-25 A | 23-Dec-25 A
FireZoneLayout |  | 02-Apr-25 A | 10-Sep-25 A | 2027-03-23 | 2027-03-23 | 02-Apr-25 A | 10-Sep-25 A
A46260 | Fire Zone Layout_IFR | 02-Apr-25 A | 23-Apr-25 A | 2027-03-23 | 2027-03-23 | 02-Apr-25 A | 23-Apr-25 A
A46270 | Fire Zone Layout_RCC | 24-Apr-25 A | 12-Aug-25 A | 2027-03-23 | 2027-03-23 | 24-Apr-25 A | 12-Aug-25 A
A46280 | Fire Zone Layout_IFA | 13-Aug-25 A | 15-Aug-25 A | 2027-03-23 | 2027-03-23 | 13-Aug-25 A | 15-Aug-25 A
A46290 | Fire Zone Layout_RCA | 16-Aug-25 A | 07-Sep-25 A | 2027-03-23 | 2027-03-23 | 16-Aug-25 A | 07-Sep-25 A
A46300 | Fire Zone Layout_IFD/IFC | 08-Sep-25 A | 10-Sep-25 A | 2027-03-23 | 2027-03-23 | 08-Sep-25 A | 10-Sep-25 A
HazardousAreaClassificationLayouts |  | 06-Apr-25 A | 13-Jan-26 A | 2027-03-23 | 2027-03-23 | 06-Apr-25 A | 13-Jan-26 A
A46210 | Hazardous Area Classification Layouts_IFR | 06-Apr-25 A | 27-Apr-25 A | 2027-03-23 | 2027-03-23 | 06-Apr-25 A | 27-Apr-25 A
A46220 | Hazardous Area Classification Layouts_RCC | 28-Apr-25 A | 21-Jun-25 A | 2027-03-23 | 2027-03-23 | 28-Apr-25 A | 21-Jun-25 A
A46230 | Hazardous Area Classification Layouts_IFA | 22-Jun-25 A | 29-Aug-25 A | 2027-03-23 | 2027-03-23 | 22-Jun-25 A | 29-Aug-25 A
A46240 | Hazardous Area Classification Layouts_RCA | 19-Dec-25 A | 09-Jan-26 A | 2027-03-23 | 2027-03-23 | 19-Dec-25 A | 09-Jan-26 A
A46250 | Hazardous Area Classification Layouts_IFD/IFC | 09-Jan-26 A | 13-Jan-26 A | 2027-03-23 | 2027-03-23 | 09-Jan-26 A | 13-Jan-26 A
MRforFireProtectionandSafetyEquipment |  | 14-May-25 A | 25-Dec-25 A | 2026-07-06 | 2026-07-06 | 14-May-25 A | 25-Dec-25 A
A47180 | MR for Fire Protection and Safety Equipment_IFR | 04-Jun-25 A | 13-Jun-25 A | 2026-07-06 | 2026-07-06 | 04-Jun-25 A | 13-Jun-25 A
A47190 | MR for Fire Protection and Safety Equipment_RCC | 14-May-25 A | 21-Jun-25 A | 2026-07-06 | 2026-07-06 | 14-May-25 A | 21-Jun-25 A
A47200 | MR for Fire Protection and Safety Equipment_IFA | 23-Jun-25 A | 21-Jul-25 A | 2026-07-06 | 2026-07-06 | 23-Jun-25 A | 21-Jul-25 A
A47210 | MR for Fire Protection and Safety Equipment_RCA | 01-Jul-25 A | 28-Jul-25 A | 2026-07-06 | 2026-07-06 | 01-Jul-25 A | 28-Jul-25 A
A47220 | MR for Fire Protection and Safety Equipment_IFD/IFC | 23-Dec-25 A | 25-Dec-25 A | 2026-07-06 | 2026-07-06 | 23-Dec-25 A | 25-Dec-25 A
FireWaterLayout |  | 17-Apr-25 A | 23-Dec-25 A | 2027-03-23 | 2027-03-23 | 17-Apr-25 A | 23-Dec-25 A
A46910 | Fire Water Layout_IFR | 17-Apr-25 A | 08-May-25 A | 2027-03-23 | 2027-03-23 | 17-Apr-25 A | 08-May-25 A
A46920 | Fire Water Layout_RCC | 09-May-25 A | 21-Jun-25 A | 2027-03-23 | 2027-03-23 | 09-May-25 A | 21-Jun-25 A
A46930 | Fire Water Layout_IFA | 27-Jun-25 A | 21-Jul-25 A | 2027-03-23 | 2027-03-23 | 27-Jun-25 A | 21-Jul-25 A
A46940 | Fire Water Layout_RCA | 01-Jul-25 A | 28-Jul-25 A | 2027-03-23 | 2027-03-23 | 01-Jul-25 A | 28-Jul-25 A
A46950 | Fire Water Layout_IFD/IFC | 19-Dec-25 A | 23-Dec-25 A | 2027-03-23 | 2027-03-23 | 19-Dec-25 A | 23-Dec-25 A
P&ID-FirewaterNetwork |  | 21-Feb-25 A | 20-Mar-26 A | 2027-01-29 | 2027-03-19 | 21-Feb-25 A | 2026-04-14
A46960 | P&ID - Firewater Network_IFR | 21-Feb-25 A | 14-Mar-25 A | 2027-01-29 | 2027-01-29 | 21-Feb-25 A | 14-Mar-25 A
A46970 | P&ID - Firewater Network_RCC | 02-Mar-26 A | 10-Mar-26 A | 2027-02-22 | 2027-02-22 | 2026-02-20 | 2026-03-13
A46980 | P&ID - Firewater Network_IFA | 08-Mar-26 A | 11-Mar-26 A | 2027-02-22 | 2027-02-22 | 2026-03-13 | 2026-03-19
A46990 | P&ID - Firewater Network_RCA | 10-Mar-26 A | 18-Mar-26 A | 2027-03-19 | 2027-03-19 | 2026-03-19 | 2026-04-09
A47000 | P&ID - Firewater Network_IFD/IFC | 11-Mar-26 A | 20-Mar-26 A | 2027-03-19 | 2027-03-19 | 2026-04-09 | 2026-04-14
P&ID-DelugeSpraySystem |  | 19-Apr-25 A | 20-Mar-26 A | 2027-03-19 | 2027-03-19 | 19-Apr-25 A | 2026-04-14
A47010 | P&ID - Deluge Spray System_IFR | 19-Apr-25 A | 10-May-25 A | 2027-03-19 | 2027-03-19 | 19-Apr-25 A | 10-May-25 A
A47020 | P&ID - Deluge Spray System_RCC | 01-Feb-26 A | 18-Feb-26 A | 2027-03-19 | 2027-03-19 | 2026-02-20 | 2026-03-13
A47030 | P&ID - Deluge Spray System_IFA | 18-Feb-26 A | 28-Feb-26 A | 2027-03-19 | 2027-03-19 | 2026-03-13 | 2026-03-19
A47040 | P&ID - Deluge Spray System_RCA | 27-Feb-26 A | 03-Mar-26 A | 2027-03-19 | 2027-03-19 | 2026-03-19 | 2026-04-09
A47050 | P&ID - Deluge Spray System_IFD/IFC | 04-Mar-26 A | 20-Mar-26 A | 2027-03-19 | 2027-03-19 | 2026-04-09 | 2026-04-14
P&ID-CleanAgentSystem |  | 21-Feb-25 A | 20-Mar-26 A | 2027-03-19 | 2027-03-19 | 21-Feb-25 A | 2026-04-14
A47060 | P&ID - Clean Agent System_IFR | 21-Feb-25 A | 14-Mar-25 A | 2027-03-19 | 2027-03-19 | 21-Feb-25 A | 14-Mar-25 A
A9040 | P&ID - Clean Agent System_RCC | 01-Mar-26 A | 03-Mar-26 A | 2027-03-19 | 2027-03-19 | 2026-02-20 | 2026-03-13
A9050 | P&ID - Clean Agent System_IFA | 03-Mar-26 A | 16-Mar-26 A | 2027-03-19 | 2027-03-19 | 2026-03-13 | 2026-03-19
A9060 | P&ID - Clean Agent System_RCA | 16-Mar-26 A | 18-Mar-26 A | 2027-03-19 | 2027-03-19 | 2026-03-19 | 2026-04-09
A9070 | P&ID - Clean Agent System_IFD/IFC | 18-Mar-26 A | 20-Mar-26 A | 2027-03-19 | 2027-03-19 | 2026-04-09 | 2026-04-14
ISDCloseoutReport |  | 01-Oct-25 A | 20-Mar-26 A | 2027-03-23 | 2027-03-23 | 01-Oct-25 A | 2026-03-23
A47380 | ISD Closeout Report_IFR | 01-Oct-25 A | 09-Oct-25 A | 2027-03-23 | 2027-03-23 | 01-Oct-25 A | 09-Oct-25 A
A47390 | ISD Closeout Report_RCC | 20-Oct-25 A | 17-Nov-25 A | 2027-03-23 | 2027-03-23 | 20-Oct-25 A | 17-Nov-25 A
A47400 | ISD Closeout Report_IFA | 01-Mar-26 A | 10-Mar-26 A | 2027-03-23 | 2027-03-23 | 2026-02-20 | 2026-02-25
A47410 | ISD Closeout Report_RCA | 10-Mar-26 A | 18-Mar-26 A | 2027-03-23 | 2027-03-23 | 2026-02-25 | 2026-03-19
A47420 | ISD Closeout Report_IFD/IFC | 11-Mar-26 A | 20-Mar-26 A | 2027-03-23 | 2027-03-23 | 2026-03-19 | 2026-03-23
PHSER3CloseoutReport |  | 01-Feb-26 A | 20-Mar-26 A | 2027-03-23 | 2027-03-23 | 2026-03-16 | 2026-05-14
A47480 | PHSER 3 Closeout Report_IFR | 01-Feb-26 A | 26-Feb-26 A | 2027-03-23 | 2027-03-23 | 2026-03-16 | 2026-03-24
A47490 | PHSER 3 Closeout Report_RCC | 25-Feb-26 A | 28-Feb-26 A | 2027-03-23 | 2027-03-23 | 2026-03-24 | 2026-04-15
A47500 | PHSER 3 Closeout Report_IFA | 28-Feb-26 A | 04-Mar-26 A | 2027-03-23 | 2027-03-23 | 2026-04-15 | 2026-04-20
A47510 | PHSER 3 Closeout Report_RCA | 05-Mar-26 A | 18-Mar-26 A | 2027-03-23 | 2027-03-23 | 2026-04-20 | 2026-05-12
A47520 | PHSER 3 Closeout Report_IFD/IFC | 06-Mar-26 A | 20-Mar-26 A | 2027-03-23 | 2027-03-23 | 2026-05-12 | 2026-05-14
HSEActionTrackingRegister |  | 03-Nov-25 A | 20-Mar-26 A | 2027-03-23 | 2027-03-23 | 03-Nov-25 A | 2026-03-23
A47280 | HSE Action Tracking Register_IFR | 03-Nov-25 A | 17-Nov-25 A | 2027-03-23 | 2027-03-23 | 03-Nov-25 A | 17-Nov-25 A
A47290 | HSE Action Tracking Register_RCC | 19-Dec-25 A | 09-Jan-26 A | 2027-03-23 | 2027-03-23 | 19-Dec-25 A | 09-Jan-26 A
A47300 | HSE Action Tracking Register_IFA | 01-Mar-26 A | 04-Mar-26 A | 2027-03-23 | 2027-03-23 | 2026-02-20 | 2026-02-25
A47310 | HSE Action Tracking Register_RCA | 10-Mar-26 A | 15-Mar-26 A | 2027-03-23 | 2027-03-23 | 2026-02-25 | 2026-03-19
A47320 | HSE Action Tracking Register_IFD/IFC | 16-Mar-26 A | 20-Mar-26 A | 2027-03-23 | 2027-03-23 | 2026-03-19 | 2026-03-23
Electrical |  | 13-Dec-24 A | 2026-06-22 | 2026-06-11 | 2027-03-23 | 09-Jan-25 A | 13-May-25 A
ScopeOfWorkForCathodicProtection |  | 08-Aug-25 A | 23-Dec-25 A | 2026-08-14 | 2027-03-23 | 08-Aug-25 A | 23-Dec-25 A
A10630 | Scope Of Work For Cathodic Protection_IFR | 08-Aug-25 A | 14-Aug-25 A | 2026-08-14 | 2026-08-14 | 08-Aug-25 A | 14-Aug-25 A
A10640 | Scope Of Work For Cathodic Protection_RCC | 15-Aug-25 A | 19-Sep-25 A | 2026-08-14 | 2026-08-14 | 15-Aug-25 A | 19-Sep-25 A
A10650 | Scope Of Work For Cathodic Protection_IFA | 03-Nov-25 A | 10-Nov-25 A | 2026-08-14 | 2026-08-14 | 03-Nov-25 A | 10-Nov-25 A
A10660 | Scope Of Work For Cathodic Protection_RCA | 11-Nov-25 A | 20-Nov-25 A | 2027-03-23 | 2027-03-23 | 11-Nov-25 A | 20-Nov-25 A
A10670 | Scope Of Work For Cathodic Protection_IFD/IFC | 19-Dec-25 A | 23-Dec-25 A | 2027-03-23 | 2027-03-23 | 19-Dec-25 A | 23-Dec-25 A
ElectricalSystemOperatingPhilosophy |  | 2026-04-17 | 2026-06-16 | 2027-01-22 | 2027-03-23 | 2026-02-20 | 2026-04-21
A47530 | Electrical System Operating Philosophy_IFR | 2026-04-17 | 2026-04-24 | 2027-01-22 | 2027-01-29 | 2026-02-20 | 2026-02-27
A47540 | Electrical System Operating Philosophy_RCC | 2026-04-24 | 2026-05-18 | 2027-01-29 | 2027-02-22 | 2026-02-27 | 2026-03-23
A47550 | Electrical System Operating Philosophy_IFA | 2026-05-18 | 2026-05-21 | 2027-02-22 | 2027-02-25 | 2026-03-23 | 2026-03-26
A47560 | Electrical System Operating Philosophy_RCA | 2026-05-21 | 2026-06-12 | 2027-02-26 | 2027-03-19 | 2026-03-26 | 2026-04-17
A47570 | Electrical System Operating Philosophy_IFD/IFC | 2026-06-12 | 2026-06-16 | 2027-03-19 | 2027-03-23 | 2026-04-17 | 2026-04-21
TechnicalDataSheetForTransformer(PowerandDistribution) |  | 23-Dec-24 A | 03-Jul-25 A | 2026-06-11 | 2026-06-11 | 23-Dec-24 A | 03-Jul-25 A
A47580 | Technical Data Sheet For Transformer (Power and Distribution)_IFR | 23-Dec-24 A | 13-Jan-25 A | 2026-06-11 | 2026-06-11 | 23-Dec-24 A | 13-Jan-25 A
A47590 | Technical Data Sheet For Transformer (Power and Distribution)_RCC | 14-Jan-25 A | 06-May-25 A | 2026-06-11 | 2026-06-11 | 14-Jan-25 A | 06-May-25 A
A47600 | Technical Data Sheet For Transformer (Power and Distribution)_IFA | 07-May-25 A | 19-Jun-25 A | 2026-06-11 | 2026-06-11 | 07-May-25 A | 19-Jun-25 A
A47610 | Technical Data Sheet For Transformer (Power and Distribution)_RCA | 20-Jun-25 A | 26-Jun-25 A | 2026-06-11 | 2026-06-11 | 20-Jun-25 A | 26-Jun-25 A
A47620 | Technical Data Sheet For Transformer (Power and Distribution)_IFD/IFC | 27-Jun-25 A | 03-Jul-25 A | 2026-06-11 | 2026-06-11 | 27-Jun-25 A | 03-Jul-25 A
TechnicalDataSheetForLVMotors |  | 01-Jan-25 A | 03-May-25 A | 2026-06-11 | 2027-03-23 | 01-Jan-25 A | 03-May-25 A
A47630 | Technical Data Sheet For LV Motors_IFR | 01-Jan-25 A | 22-Jan-25 A | 2026-06-11 | 2026-06-11 | 01-Jan-25 A | 22-Jan-25 A
A9840 | Technical Data Sheet For LV Motors_RCC | 23-Jan-25 A | 28-Feb-25 A | 2027-03-23 | 2027-03-23 | 23-Jan-25 A | 28-Feb-25 A
A9850 | Technical Data Sheet For LV Motors_IFA | 01-Mar-25 A | 19-Apr-25 A | 2027-03-23 | 2027-03-23 | 01-Mar-25 A | 19-Apr-25 A
A9860 | Technical Data Sheet For LV Motors_RCA | 20-Apr-25 A | 26-Apr-25 A | 2027-03-23 | 2027-03-23 | 20-Apr-25 A | 26-Apr-25 A
A9870 | Technical Data Sheet For LV Motors_IFD/IFC | 27-Apr-25 A | 03-May-25 A | 2027-03-23 | 2027-03-23 | 27-Apr-25 A | 03-May-25 A
TechnicalDataSheetForEmergencyDieselGenerator |  | 09-Jan-25 A | 10-Sep-25 A | 2026-06-11 | 2026-06-11 | 09-Jan-25 A | 10-Sep-25 A
A9880 | Technical Data Sheet For Emergency Diesel Generator_IFR | 09-Jan-25 A | 02-Mar-25 A | 2026-06-11 | 2026-06-11 | 09-Jan-25 A | 02-Mar-25 A
A9890 | Technical Data Sheet For Emergency Diesel Generator_RCC | 03-Mar-25 A | 02-May-25 A | 2026-06-11 | 2026-06-11 | 03-Mar-25 A | 02-May-25 A
A9900 | Technical Data Sheet For Emergency Diesel Generator_IFA | 03-May-25 A | 16-May-25 A | 2026-06-11 | 2026-06-11 | 03-May-25 A | 16-May-25 A
A9910 | Technical Data Sheet For Emergency Diesel Generator_RCA | 19-Aug-25 A | 08-Sep-25 A | 2026-06-11 | 2026-06-11 | 19-Aug-25 A | 08-Sep-25 A
A9920 | Technical Data Sheet For Emergency Diesel Generator_IFD/IFC | 09-Sep-25 A | 10-Sep-25 A | 2026-06-11 | 2026-06-11 | 09-Sep-25 A | 10-Sep-25 A
TechnicalDataSheetForIntergratedProtectionControlPanel |  | 01-May-25 A | 06-Jun-25 A | 2026-06-11 | 2026-06-11 | 01-May-25 A | 06-Jun-25 A
A58390 | Technical Data Sheet For IPCS_IFR | 01-May-25 A | 05-May-25 A | 2026-06-11 | 2026-06-11 | 01-May-25 A | 05-May-25 A
A58400 | Technical Data Sheet For IPCS_RCC | 06-May-25 A | 16-May-25 A | 2026-06-11 | 2026-06-11 | 06-May-25 A | 16-May-25 A
A58410 | Technical Data Sheet For IPCS_IFA | 19-May-25 A | 23-May-25 A | 2026-06-11 | 2026-06-11 | 19-May-25 A | 23-May-25 A
A58420 | Technical Data Sheet For IPCS_RCA | 26-May-25 A | 30-May-25 A | 2026-06-11 | 2026-06-11 | 26-May-25 A | 30-May-25 A
A58430 | Technical Data Sheet For IPCS_IFD/IFC | 02-Jun-25 A | 06-Jun-25 A | 2026-06-11 | 2026-06-11 | 02-Jun-25 A | 06-Jun-25 A
TechnicalDataSheetForSCMS |  | 05-May-25 A | 13-Jun-25 A | 2026-06-11 | 2026-06-11 | 05-May-25 A | 13-Jun-25 A
A59900 | Technical Data Sheet For SCMS_IFR | 05-May-25 A | 09-May-25 A | 2026-06-11 | 2026-06-11 | 05-May-25 A | 09-May-25 A
A59910 | Technical Data Sheet For SCMS_RCC | 12-May-25 A | 23-May-25 A | 2026-06-11 | 2026-06-11 | 12-May-25 A | 23-May-25 A
A59920 | Technical Data Sheet For SCMS_IFA | 26-May-25 A | 30-May-25 A | 2026-06-11 | 2026-06-11 | 26-May-25 A | 30-May-25 A
A59930 | Technical Data Sheet For SCMS_RCA | 02-Jun-25 A | 06-Jun-25 A | 2026-06-11 | 2026-06-11 | 02-Jun-25 A | 06-Jun-25 A
A59940 | Technical Data Sheet For SCMS_IFD/IFC | 09-Jun-25 A | 13-Jun-25 A | 2026-06-11 | 2026-06-11 | 09-Jun-25 A | 13-Jun-25 A
TechnicalDataSheetFor11KVSwitchgear |  | 19-Dec-24 A | 21-Jun-25 A | 2026-06-11 | 2026-06-11 | 19-Dec-24 A | 21-Jun-25 A
A47640 | Technical Data Sheet For 11KV Switchgear_IFA | 15-Feb-25 A | 21-Mar-25 A | 2026-06-11 | 2026-06-11 | 15-Feb-25 A | 21-Mar-25 A
A9930 | Technical Data Sheet For 11KV Switchgear_IFR | 19-Dec-24 A | 09-Jan-25 A | 2026-06-11 | 2026-06-11 | 19-Dec-24 A | 09-Jan-25 A
A9940 | Technical Data Sheet For 11KV Switchgear_RCC | 10-Jan-25 A | 14-Feb-25 A | 2026-06-11 | 2026-06-11 | 10-Jan-25 A | 14-Feb-25 A
A9960 | Technical Data Sheet For 11KV Switchgear_RCA | 22-Mar-25 A | 02-Jun-25 A | 2026-06-11 | 2026-06-11 | 22-Mar-25 A | 02-Jun-25 A
A9970 | Technical Data Sheet For 11KV Switchgear_IFD/IFC | 03-Jun-25 A | 21-Jun-25 A | 2026-06-11 | 2026-06-11 | 03-Jun-25 A | 21-Jun-25 A
TechnicalDataSheetForLVSwitchgear |  | 27-Dec-24 A | 11-May-25 A | 2026-06-11 | 2026-06-12 | 27-Dec-24 A | 11-May-25 A
A10000 | Technical Data Sheet For LV Switchgear_IFA | 21-Apr-25 A | 27-Apr-25 A | 2026-06-12 | 2026-06-12 | 21-Apr-25 A | 27-Apr-25 A
A10010 | Technical Data Sheet For LV Switchgear_RCA | 28-Apr-25 A | 04-May-25 A | 2026-06-12 | 2026-06-12 | 28-Apr-25 A | 04-May-25 A
A10020 | Technical Data Sheet For LV Switchgear_IFD/IFC | 06-May-25 A | 11-May-25 A | 2026-06-12 | 2026-06-12 | 06-May-25 A | 11-May-25 A
A9980 | Technical Data Sheet For LV Switchgear_IFR | 27-Dec-24 A | 17-Jan-25 A | 2026-06-11 | 2026-06-11 | 27-Dec-24 A | 17-Jan-25 A
A9990 | Technical Data Sheet For LV Switchgear_RCC | 18-Jan-25 A | 20-Apr-25 A | 2026-06-12 | 2026-06-12 | 18-Jan-25 A | 20-Apr-25 A
TechnicalDataSheetForLVVariableFrequencyDrive |  | 31-Jan-25 A | 05-Jul-25 A | 2026-06-11 | 2026-06-11 | 31-Jan-25 A | 05-Jul-25 A
A10030 | Technical Data Sheet For LV Variable Frequency Drive_IFR | 31-Jan-25 A | 21-Feb-25 A | 2026-06-11 | 2026-06-11 | 31-Jan-25 A | 21-Feb-25 A
A10040 | Technical Data Sheet For LV Variable Frequency Drive_RCC | 22-Feb-25 A | 20-Apr-25 A | 2026-06-11 | 2026-06-11 | 22-Feb-25 A | 20-Apr-25 A
A10050 | Technical Data Sheet For LV Variable Frequency Drive_IFA | 21-Apr-25 A | 21-Jun-25 A | 2026-06-11 | 2026-06-11 | 21-Apr-25 A | 21-Jun-25 A
A10060 | Technical Data Sheet For LV Variable Frequency Drive_RCA | 22-Jun-25 A | 28-Jun-25 A | 2026-06-11 | 2026-06-11 | 22-Jun-25 A | 28-Jun-25 A
A10070 | Technical Data Sheet For LV Variable Frequency Drive_IFD/IFC | 29-Jun-25 A | 05-Jul-25 A | 2026-06-11 | 2026-06-11 | 29-Jun-25 A | 05-Jul-25 A
TechnicalDataSheetForNeutralEarthingResistor |  | 19-Dec-24 A | 21-Jun-25 A | 2026-06-11 | 2026-06-11 | 19-Dec-24 A | 21-Jun-25 A
A10080 | Technical Data Sheet For Neutral Earthing Resistor_IFR | 19-Dec-24 A | 09-Jan-25 A | 2026-06-11 | 2026-06-11 | 19-Dec-24 A | 09-Jan-25 A
A10090 | Technical Data Sheet For Neutral Earthing Resistor_RCC | 10-Jan-25 A | 21-Feb-25 A | 2026-06-11 | 2026-06-11 | 10-Jan-25 A | 21-Feb-25 A
A10100 | Technical Data Sheet For Neutral Earthing Resistor_IFA | 22-Feb-25 A | 06-Mar-25 A | 2026-06-11 | 2026-06-11 | 22-Feb-25 A | 06-Mar-25 A
A10110 | Technical Data Sheet For Neutral Earthing Resistor_RCA | 07-Mar-25 A | 29-May-25 A | 2026-06-11 | 2026-06-11 | 07-Mar-25 A | 29-May-25 A
A10120 | Technical Data Sheet For Neutral Earthing Resistor_IFD/IFC | 30-May-25 A | 21-Jun-25 A | 2026-06-11 | 2026-06-11 | 30-May-25 A | 21-Jun-25 A
TechnicalDataSheetForInterpostingRelayPanel |  | 01-Aug-25 A | 17-Sep-25 A | 2026-07-20 | 2027-03-23 | 01-Aug-25 A | 17-Sep-25 A
A58240 | Technical Data Sheet For Interpopsting Relay Panel _IFR | 01-Aug-25 A | 08-Aug-25 A | 2026-07-20 | 2026-07-20 | 01-Aug-25 A | 08-Aug-25 A
A58250 | Technical Data Sheet For Interpopsting Relay Panel_RCC | 11-Aug-25 A | 22-Aug-25 A | 2027-03-23 | 2027-03-23 | 11-Aug-25 A | 22-Aug-25 A
A58260 | Technical Data Sheet For Interpopsting Relay Panel_IFA | 25-Aug-25 A | 29-Aug-25 A | 2027-03-23 | 2027-03-23 | 25-Aug-25 A | 29-Aug-25 A
A58270 | Technical Data Sheet For Interpopsting Relay Panel_RCA | 01-Sep-25 A | 12-Sep-25 A | 2027-03-23 | 2027-03-23 | 01-Sep-25 A | 12-Sep-25 A
A58280 | Technical Data Sheet For Interpopsting Relay Panel_IFD/IFC | 15-Sep-25 A | 17-Sep-25 A | 2027-03-23 | 2027-03-23 | 15-Sep-25 A | 17-Sep-25 A
TechnicalDataSheetForPower,ControlAndEarthingCables |  | 10-Jan-25 A | 05-Sep-25 A | 2026-06-16 | 2026-06-16 | 10-Jan-25 A | 05-Sep-25 A
A10130 | Technical Data Sheet For Power, Control And Earthing Cables_IFR | 10-Jan-25 A | 20-Apr-25 A | 2026-06-16 | 2026-06-16 | 10-Jan-25 A | 20-Apr-25 A
A10140 | Technical Data Sheet For Power, Control And Earthing Cables_RCC | 21-Apr-25 A | 19-May-25 A | 2026-06-16 | 2026-06-16 | 21-Apr-25 A | 19-May-25 A
A10150 | Technical Data Sheet For Power, Control And Earthing Cables_IFA | 20-May-25 A | 11-Jun-25 A | 2026-06-16 | 2026-06-16 | 20-May-25 A | 11-Jun-25 A
A10160 | Technical Data Sheet For Power, Control And Earthing Cables_RCA | 25-Aug-25 A | 29-Aug-25 A | 2026-06-16 | 2026-06-16 | 25-Aug-25 A | 29-Aug-25 A
A10170 | Technical Data Sheet For Power, Control And Earthing Cables_IFD/IFC | 01-Sep-25 A | 05-Sep-25 A | 2026-06-16 | 2026-06-16 | 01-Sep-25 A | 05-Sep-25 A
TechnicalDataSheetForDirectCurrentUPSSystem |  | 01-Jan-25 A | 21-Jun-25 A | 2026-06-11 | 2026-06-11 | 01-Jan-25 A | 21-Jun-25 A
A10180 | Technical Data Sheet For Direct Current UPS System_IFR | 01-Jan-25 A | 22-Jan-25 A | 2026-06-11 | 2026-06-11 | 01-Jan-25 A | 22-Jan-25 A
A10190 | Technical Data Sheet For Direct Current UPS System_RCC | 23-Jan-25 A | 07-Mar-25 A | 2026-06-11 | 2026-06-11 | 23-Jan-25 A | 07-Mar-25 A
A10200 | Technical Data Sheet For Direct Current UPS System_IFA | 08-Mar-25 A | 21-Mar-25 A | 2026-06-11 | 2026-06-11 | 08-Mar-25 A | 21-Mar-25 A
A10210 | Technical Data Sheet For Direct Current UPS System_RCA | 22-Mar-25 A | 02-Jun-25 A | 2026-06-11 | 2026-06-11 | 22-Mar-25 A | 02-Jun-25 A
A10220 | Technical Data Sheet For Direct Current UPS System_IFD/IFC | 03-Jun-25 A | 21-Jun-25 A | 2026-06-11 | 2026-06-11 | 03-Jun-25 A | 21-Jun-25 A
TechnicalDataSheetForStaticACUPSSystem |  | 27-Dec-24 A | 28-Jun-25 A | 2026-06-12 | 2026-06-12 | 27-Dec-24 A | 28-Jun-25 A
A10230 | Technical Data Sheet For Static AC UPS System_IFR | 27-Dec-24 A | 17-Jan-25 A | 2026-06-12 | 2026-06-12 | 27-Dec-24 A | 17-Jan-25 A
A10240 | Technical Data Sheet For Static AC UPS System_RCC | 18-Jan-25 A | 18-Feb-25 A | 2026-06-12 | 2026-06-12 | 18-Jan-25 A | 18-Feb-25 A
A10250 | Technical Data Sheet For Static AC UPS System_IFA | 19-Feb-25 A | 12-Jun-25 A | 2026-06-12 | 2026-06-12 | 19-Feb-25 A | 12-Jun-25 A
A10260 | Technical Data Sheet For Static AC UPS System_RCA | 13-Jun-25 A | 21-Jun-25 A | 2026-06-12 | 2026-06-12 | 13-Jun-25 A | 21-Jun-25 A
A10270 | Technical Data Sheet For Static AC UPS System_IFD/IFC | 22-Jun-25 A | 28-Jun-25 A | 2026-06-12 | 2026-06-12 | 22-Jun-25 A | 28-Jun-25 A
TechnicalDataSheetForPowerFactorCorrectionCapacitor |  | 20-Jan-25 A | 28-Aug-25 A | 2026-06-11 | 2026-06-12 | 20-Jan-25 A | 28-Aug-25 A
A10280 | Technical Data Sheet For Power Factor Correction Capacitor_IFR | 20-Jan-25 A | 21-Feb-25 A | 2026-06-11 | 2026-06-11 | 20-Jan-25 A | 21-Feb-25 A
A10290 | Technical Data Sheet For Power Factor Correction Capacitor_RCC | 19-Jul-25 A | 08-Aug-25 A | 2026-06-12 | 2026-06-12 | 19-Jul-25 A | 08-Aug-25 A
A10300 | Technical Data Sheet For Power Factor Correction Capacitor_IFA | 09-Aug-25 A | 12-Aug-25 A | 2026-06-12 | 2026-06-12 | 09-Aug-25 A | 12-Aug-25 A
A10310 | Technical Data Sheet For Power Factor Correction Capacitor_RCA | 12-Aug-25 A | 26-Aug-25 A | 2026-06-12 | 2026-06-12 | 12-Aug-25 A | 26-Aug-25 A
A10320 | Technical Data Sheet For Power Factor Correction Capacitor_IFD/IFC | 26-Aug-25 A | 28-Aug-25 A | 2026-06-12 | 2026-06-12 | 26-Aug-25 A | 28-Aug-25 A
NeutralEarthingResistorSizingCalculation |  | 13-Dec-24 A | 13-May-25 A | 2026-06-22 | 2027-03-23 | 13-Dec-24 A | 13-May-25 A
A10380 | Neutral Earthing Resistor Sizing Calculation_IFR | 13-Dec-24 A | 09-Jan-25 A | 2026-06-22 | 2026-06-22 | 13-Dec-24 A | 09-Jan-25 A
A10390 | Neutral Earthing Resistor Sizing Calculation_RCC | 10-Jan-25 A | 21-Feb-25 A | 2027-03-23 | 2027-03-23 | 10-Jan-25 A | 21-Feb-25 A
A10400 | Neutral Earthing Resistor Sizing Calculation_IFA | 22-Feb-25 A | 12-Mar-25 A | 2027-03-23 | 2027-03-23 | 22-Feb-25 A | 12-Mar-25 A
A10410 | Neutral Earthing Resistor Sizing Calculation_RCA | 13-Mar-25 A | 06-May-25 A | 2027-03-23 | 2027-03-23 | 13-Mar-25 A | 06-May-25 A
A10420 | Neutral Earthing Resistor Sizing Calculation_IFD/IFC | 07-May-25 A | 13-May-25 A | 2027-03-23 | 2027-03-23 | 07-May-25 A | 13-May-25 A
InterpostingRelayPanelSizingCalculation |  | 2026-04-17 | 2026-06-16 | 2026-07-31 | 2027-03-23 | 2026-02-20 | 2026-04-21
A58290 | Interpopsting Relay Panel Sizing Calculation_IFR | 2026-04-17 | 2026-04-24 | 2026-07-31 | 2026-08-10 | 2026-02-20 | 2026-02-27
A58300 | Interpopsting Relay Panel Sizing Calculation_RCC | 2026-04-24 | 2026-05-18 | 2026-08-10 | 2026-09-01 | 2026-02-27 | 2026-03-23
A58310 | Interpopsting Relay Panel Sizing Calculation_IFA | 2026-05-18 | 2026-05-21 | 2026-09-01 | 2026-09-04 | 2026-03-23 | 2026-03-26
A58320 | Interpopsting Relay Panel Sizing Calculation_RCA | 2026-05-21 | 2026-06-12 | 2027-02-26 | 2027-03-19 | 2026-03-26 | 2026-04-17
A58330 | Interpopsting Relay Panel Sizing Calculation_IFD/IFC | 2026-06-12 | 2026-06-16 | 2027-03-19 | 2027-03-23 | 2026-04-17 | 2026-04-21
TransformerSizingCalculation |  | 29-Mar-25 A | 28-Jun-25 A | 2026-06-11 | 2027-03-23 | 29-Mar-25 A | 28-Jun-25 A
A10680 | Transformer Sizing Calculation_IFR | 29-Mar-25 A | 06-Apr-25 A | 2026-06-11 | 2026-06-11 | 29-Mar-25 A | 06-Apr-25 A
A10690 | Transformer Sizing Calculation_RCC | 30-Mar-25 A | 13-Apr-25 A | 2027-03-23 | 2027-03-23 | 30-Mar-25 A | 13-Apr-25 A
A10700 | Transformer Sizing Calculation_IFA | 14-Apr-25 A | 20-Apr-25 A | 2027-03-23 | 2027-03-23 | 14-Apr-25 A | 20-Apr-25 A
A10710 | Transformer Sizing Calculation_RCA | 21-Apr-25 A | 21-Jun-25 A | 2027-03-23 | 2027-03-23 | 21-Apr-25 A | 21-Jun-25 A
A10720 | Transformer Sizing Calculation_IFD/IFC | 22-Jun-25 A | 28-Jun-25 A | 2027-03-23 | 2027-03-23 | 22-Jun-25 A | 28-Jun-25 A
ElectricalLoadList-EU3H2ExtractionUnit |  | 19-Dec-24 A | 30-Apr-25 A | 2026-06-11 | 2026-06-15 | 19-Dec-24 A | 30-Apr-25 A
A10330 | Electrical Load List - EU3 H2 Extraction Unit_IFR | 19-Dec-24 A | 09-Jan-25 A | 2026-06-11 | 2026-06-11 | 19-Dec-24 A | 09-Jan-25 A
A10340 | Electrical Load List - EU3 H2 Extraction Unit_RCC | 10-Jan-25 A | 18-Feb-25 A | 2026-06-11 | 2026-06-11 | 10-Jan-25 A | 18-Feb-25 A
A10350 | Electrical Load List - EU3 H2 Extraction Unit_IFA | 25-Feb-25 A | 13-Mar-25 A | 2026-06-15 | 2026-06-15 | 25-Feb-25 A | 13-Mar-25 A
A10360 | Electrical Load List - EU3 H2 Extraction Unit_RCA | 14-Mar-25 A | 29-Apr-25 A | 2026-06-15 | 2026-06-15 | 14-Mar-25 A | 29-Apr-25 A
A10370 | Electrical Load List - EU3 H2 Extraction Unit_IFD/IFC | 30-Apr-25 A | 30-Apr-25 A | 2026-06-15 | 2026-06-15 | 30-Apr-25 A | 30-Apr-25 A
ElectricalLoadSummaryforUtilities&OffsitesArea |  | 14-Feb-25 A | 19-Jan-26 A | 2026-06-15 | 2026-06-15 | 14-Feb-25 A | 19-Jan-26 A
A28320 | Electrical Load Summary for Utilities & Offsites Area_IFD/IFC | 15-Jan-26 A | 19-Jan-26 A | 2026-06-15 | 2026-06-15 | 15-Jan-26 A | 19-Jan-26 A
A55790 | Electrical Load Summary for Utilities & Offsites Area_IFR | 14-Feb-25 A | 20-Mar-25 A | 2026-06-15 | 2026-06-15 | 14-Feb-25 A | 20-Mar-25 A
A55800 | Electrical Load Summary for Utilities & Offsites Area_RCC | 30-Sep-25 A | 16-Oct-25 A | 2026-06-15 | 2026-06-15 | 30-Sep-25 A | 16-Oct-25 A
A55810 | Electrical Load Summary for Utilities & Offsites Area_IFA | 19-Dec-25 A | 24-Dec-25 A | 2026-06-15 | 2026-06-15 | 19-Dec-25 A | 24-Dec-25 A
A55820 | Electrical Load Summary for Utilities & Offsites Area_RCA | 24-Dec-25 A | 15-Jan-26 A | 2026-06-15 | 2026-06-15 | 24-Dec-25 A | 15-Jan-26 A
ACUPSSizingCalculation |  | 01-Aug-25 A | 23-Dec-25 A | 2026-06-22 | 2027-03-23 | 01-Aug-25 A | 23-Dec-25 A
A10930 | AC UPS Sizing Calculation_IFR | 01-Aug-25 A | 15-Aug-25 A | 2026-06-22 | 2026-06-22 | 01-Aug-25 A | 15-Aug-25 A
A10940 | AC UPS Sizing Calculation_RCC | 04-Aug-25 A | 22-Aug-25 A | 2027-03-23 | 2027-03-23 | 04-Aug-25 A | 22-Aug-25 A
A10950 | AC UPS Sizing Calculation_IFA | 17-Sep-25 A | 09-Oct-25 A | 2027-03-23 | 2027-03-23 | 17-Sep-25 A | 09-Oct-25 A
A10960 | AC UPS Sizing Calculation_RCA | 24-Sep-25 A | 16-Oct-25 A | 2027-03-23 | 2027-03-23 | 24-Sep-25 A | 16-Oct-25 A
A10970 | AC UPS Sizing Calculation_IFD/IFC | 19-Dec-25 A | 23-Dec-25 A | 2027-03-23 | 2027-03-23 | 19-Dec-25 A | 23-Dec-25 A
DCUPSSizingCalculation |  | 30-Mar-25 A | 23-Dec-25 A | 2026-06-22 | 2027-03-23 | 30-Mar-25 A | 23-Dec-25 A
A10980 | DC UPS Sizing Calculation_IFR | 30-Mar-25 A | 13-Apr-25 A | 2026-06-22 | 2026-06-22 | 30-Mar-25 A | 13-Apr-25 A
A10990 | DC UPS Sizing Calculation_RCC | 01-Apr-25 A | 20-Apr-25 A | 2027-03-23 | 2027-03-23 | 01-Apr-25 A | 20-Apr-25 A
A11000 | DC UPS Sizing Calculation_IFA | 21-Apr-25 A | 27-Apr-25 A | 2027-03-23 | 2027-03-23 | 21-Apr-25 A | 27-Apr-25 A
A11010 | DC UPS Sizing Calculation_RCA | 15-May-25 A | 21-Jun-25 A | 2027-03-23 | 2027-03-23 | 15-May-25 A | 21-Jun-25 A
A11020 | DC UPS Sizing Calculation_IFD/IFC | 19-Dec-25 A | 23-Dec-25 A | 2027-03-23 | 2027-03-23 | 19-Dec-25 A | 23-Dec-25 A
EDGSizingCalculation |  | 19-Dec-24 A | 28-Jun-25 A | 2026-06-11 | 2027-03-23 | 19-Dec-24 A | 28-Jun-25 A
A11030 | EDG Sizing Calculation_IFR | 19-Dec-24 A | 09-Jan-25 A | 2026-06-11 | 2026-06-11 | 19-Dec-24 A | 09-Jan-25 A
A11040 | EDG Sizing Calculation_RCC | 10-Jan-25 A | 20-Feb-25 A | 2027-03-23 | 2027-03-23 | 10-Jan-25 A | 20-Feb-25 A
A11050 | EDG Sizing Calculation_IFA | 21-Feb-25 A | 20-Apr-25 A | 2027-03-23 | 2027-03-23 | 21-Feb-25 A | 20-Apr-25 A
A11060 | EDG Sizing Calculation_RCA | 21-Apr-25 A | 21-Jun-25 A | 2027-03-23 | 2027-03-23 | 21-Apr-25 A | 21-Jun-25 A
A11070 | EDG Sizing Calculation_IFD/IFC | 22-Jun-25 A | 28-Jun-25 A | 2027-03-23 | 2027-03-23 | 22-Jun-25 A | 28-Jun-25 A
IOListForIPCS |  | 29-Mar-25 A | 18-Sep-25 A | 2027-03-23 | 2027-03-23 | 29-Mar-25 A | 18-Sep-25 A
A11080 | IO List For IPCS_IFR | 29-Mar-25 A | 06-Apr-25 A | 2027-03-23 | 2027-03-23 | 29-Mar-25 A | 06-Apr-25 A
A11090 | IO List For IPCS_RCC | 01-Apr-25 A | 13-Apr-25 A | 2027-03-23 | 2027-03-23 | 01-Apr-25 A | 13-Apr-25 A
A11100 | IO List For IPCS_IFA | 14-Apr-25 A | 20-Apr-25 A | 2027-03-23 | 2027-03-23 | 14-Apr-25 A | 20-Apr-25 A
A11110 | IO List For IPCS_RCA | 30-Apr-25 A | 21-Jun-25 A | 2027-03-23 | 2027-03-23 | 30-Apr-25 A | 21-Jun-25 A
A11120 | IO List For IPCS_IFD/IFC | 22-Jun-25 A | 18-Sep-25 A | 2027-03-23 | 2027-03-23 | 22-Jun-25 A | 18-Sep-25 A
IOListForSCMS |  | 24-Jan-25 A | 23-Dec-25 A | 2027-03-23 | 2027-03-23 | 24-Jan-25 A | 23-Dec-25 A
A11130 | IO List For SCMS_IFR | 24-Jan-25 A | 24-Feb-25 A | 2027-03-23 | 2027-03-23 | 24-Jan-25 A | 24-Feb-25 A
A11140 | IO List For SCMS_RCC | 25-Feb-25 A | 20-Apr-25 A | 2027-03-23 | 2027-03-23 | 25-Feb-25 A | 20-Apr-25 A
A11150 | IO List For SCMS_IFA | 21-Apr-25 A | 27-Apr-25 A | 2027-03-23 | 2027-03-23 | 21-Apr-25 A | 27-Apr-25 A
A11160 | IO List For SCMS_RCA | 21-Apr-25 A | 21-Jun-25 A | 2027-03-23 | 2027-03-23 | 21-Apr-25 A | 21-Jun-25 A
A11170 | IO List For SCMS_IFD/IFC | 22-Jun-25 A | 23-Dec-25 A | 2027-03-23 | 2027-03-23 | 22-Jun-25 A | 23-Dec-25 A
PowerSystemStudyReport-ARCFlash,HarmonicsResonance |  | 18-Jul-25 A | 23-Dec-25 A | 2026-06-11 | 2027-03-23 | 18-Jul-25 A | 23-Dec-25 A
A11230 | Power System Study Report - ARC Flash, Harmonics Resonance_IFR | 18-Jul-25 A | 11-Aug-25 A | 2026-06-11 | 2026-06-11 | 18-Jul-25 A | 11-Aug-25 A
A11240 | Power System Study Report - ARC Flash, Harmonics Resonance_RCC | 12-Aug-25 A | 28-Aug-25 A | 2027-03-23 | 2027-03-23 | 12-Aug-25 A | 28-Aug-25 A
A11250 | Power System Study Report - ARC Flash, Harmonics Resonance_IFA | 04-Sep-25 A | 10-Oct-25 A | 2027-03-23 | 2027-03-23 | 04-Sep-25 A | 10-Oct-25 A
A11260 | Power System Study Report - ARC Flash, Harmonics Resonance_RCA | 20-Sep-25 A | 17-Oct-25 A | 2027-03-23 | 2027-03-23 | 20-Sep-25 A | 17-Oct-25 A
A11270 | Power System Study Report - ARC Flash, Harmonics Resonance_IFD/IFC | 19-Dec-25 A | 23-Dec-25 A | 2027-03-23 | 2027-03-23 | 19-Dec-25 A | 23-Dec-25 A
PowerSystemStudyReport-LoadFlow,ShortCircuitandMotorStarting |  | 28-Apr-25 A | 23-Dec-25 A | 2026-06-11 | 2027-03-23 | 28-Apr-25 A | 23-Dec-25 A
A11180 | Power System Study Report - Load Flow, Short Circuit and Motor Starting_IFR | 28-Apr-25 A | 19-May-25 A | 2026-06-11 | 2026-06-11 | 28-Apr-25 A | 19-May-25 A
A11190 | Power System Study Report - Load Flow, Short Circuit and Motor Starting_RCC | 25-Jun-25 A | 25-Jul-25 A | 2027-03-23 | 2027-03-23 | 25-Jun-25 A | 25-Jul-25 A
A11200 | Power System Study Report - Load Flow, Short Circuit and Motor Starting_IFA | 26-Jul-25 A | 28-Aug-25 A | 2027-03-23 | 2027-03-23 | 26-Jul-25 A | 28-Aug-25 A
A11210 | Power System Study Report - Load Flow, Short Circuit and Motor Starting_RCA | 20-Aug-25 A | 04-Sep-25 A | 2027-03-23 | 2027-03-23 | 20-Aug-25 A | 04-Sep-25 A
A11220 | Power System Study Report - Load Flow, Short Circuit and Motor Starting_IFD/IFC | 19-Dec-25 A | 23-Dec-25 A | 2027-03-23 | 2027-03-23 | 19-Dec-25 A | 23-Dec-25 A
PSCADStudyReport-TransientStabilityAndInsulationCoordination |  | 01-May-25 A | 23-Dec-25 A | 2027-01-22 | 2027-03-23 | 01-May-25 A | 23-Dec-25 A
A11280 | Pscad Study Report - Transient Stability And Insulation Coordination_IFR | 01-May-25 A | 22-May-25 A | 2027-01-22 | 2027-01-22 | 01-May-25 A | 22-May-25 A
A11290 | Pscad Study Report - Transient Stability And Insulation Coordination_RCC | 11-Jun-25 A | 25-Jul-25 A | 2027-03-23 | 2027-03-23 | 11-Jun-25 A | 25-Jul-25 A
A11300 | Pscad Study Report - Transient Stability And Insulation Coordination_IFA | 31-Jul-25 A | 26-Sep-25 A | 2027-03-23 | 2027-03-23 | 31-Jul-25 A | 26-Sep-25 A
A11310 | Pscad Study Report - Transient Stability And Insulation Coordination_RCA | 10-Sep-25 A | 03-Oct-25 A | 2027-03-23 | 2027-03-23 | 10-Sep-25 A | 03-Oct-25 A
A11320 | Pscad Study Report - Transient Stability And Insulation Coordination_IFD/IFC | 19-Dec-25 A | 23-Dec-25 A | 2027-03-23 | 2027-03-23 | 19-Dec-25 A | 23-Dec-25 A
PowerSystemStudyReport-ProtectionCoordinationandRelaySetting |  | 2026-04-17 | 2026-06-16 | 2027-01-22 | 2027-03-23 | 2026-02-20 | 2026-04-21
A11330 | Power System Study Report - Protection Coordination and Relay Setting_IFR | 2026-04-17 | 2026-04-24 | 2027-01-22 | 2027-01-29 | 2026-02-20 | 2026-02-27
A11340 | Power System Study Report - Protection Coordination and Relay Setting_RCC | 2026-04-24 | 2026-05-18 | 2027-01-29 | 2027-02-22 | 2026-02-27 | 2026-03-23
A11350 | Power System Study Report - Protection Coordination and Relay Setting_IFA | 2026-05-18 | 2026-05-21 | 2027-02-22 | 2027-02-25 | 2026-03-23 | 2026-03-26
A11360 | Power System Study Report - Protection Coordination and Relay Setting_RCA | 2026-05-21 | 2026-06-12 | 2027-02-26 | 2027-03-19 | 2026-03-26 | 2026-04-17
A11370 | Power System Study Report - Protection Coordination and Relay Setting_IFD/IFC | 2026-06-12 | 2026-06-16 | 2027-03-19 | 2027-03-23 | 2026-04-17 | 2026-04-21
MaterialRequisitionForTransformer(PowerAndDistribution) |  | 19-Dec-24 A | 28-Jun-25 A | 2026-06-11 | 2026-06-11 | 19-Dec-24 A | 28-Jun-25 A
A12430 | Material Requisition For Transformer (Power And Distribution)_IFR | 19-Dec-24 A | 09-Jan-25 A | 2026-06-11 | 2026-06-11 | 19-Dec-24 A | 09-Jan-25 A
A12440 | Material Requisition For Transformer (Power And Distribution)_RCC | 10-Jan-25 A | 18-Feb-25 A | 2026-06-11 | 2026-06-11 | 10-Jan-25 A | 18-Feb-25 A
A12450 | Material Requisition For Transformer (Power And Distribution)_IFA | 19-Feb-25 A | 21-Mar-25 A | 2026-06-11 | 2026-06-11 | 19-Feb-25 A | 21-Mar-25 A
A12460 | Material Requisition For Transformer (Power And Distribution)_RCA | 22-Mar-25 A | 21-Jun-25 A | 2026-06-11 | 2026-06-11 | 22-Mar-25 A | 21-Jun-25 A
A12470 | Material Requisition For Transformer (Power And Distribution)_IFD/IFC | 22-Jun-25 A | 28-Jun-25 A | 2026-06-11 | 2026-06-11 | 22-Jun-25 A | 28-Jun-25 A
MaterialRequisitionFor11KVSwitchgear |  | 13-Feb-25 A | 12-May-25 A | 2026-06-11 | 2026-06-11 | 13-Feb-25 A | 12-May-25 A
A12480 | Material Requisition For 11KV Switchgear_IFR | 13-Feb-25 A | 06-Mar-25 A | 2026-06-11 | 2026-06-11 | 13-Feb-25 A | 06-Mar-25 A
A12490 | Material Requisition For 11KV Switchgear_RCC | 07-Mar-25 A | 21-Apr-25 A | 2026-06-11 | 2026-06-11 | 07-Mar-25 A | 21-Apr-25 A
A12500 | Material Requisition For 11KV Switchgear_IFA | 22-Apr-25 A | 28-Apr-25 A | 2026-06-11 | 2026-06-11 | 22-Apr-25 A | 28-Apr-25 A
A12510 | Material Requisition For 11KV Switchgear_RCA | 29-Apr-25 A | 05-May-25 A | 2026-06-11 | 2026-06-11 | 29-Apr-25 A | 05-May-25 A
A12520 | Material Requisition For 11KV Switchgear_IFD/IFC | 06-May-25 A | 12-May-25 A | 2026-06-11 | 2026-06-11 | 06-May-25 A | 12-May-25 A
MaterialRequisitionForLVSwitchgear |  | 20-Jan-25 A | 11-Jul-25 A | 2026-06-12 | 2026-06-12 | 20-Jan-25 A | 11-Jul-25 A
A12530 | Material Requisition For LV Switchgear_IFR | 20-Jan-25 A | 28-Feb-25 A | 2026-06-12 | 2026-06-12 | 20-Jan-25 A | 28-Feb-25 A
A12540 | Material Requisition For LV Switchgear_RCC | 01-Mar-25 A | 06-May-25 A | 2026-06-12 | 2026-06-12 | 01-Mar-25 A | 06-May-25 A
A12550 | Material Requisition For LV Switchgear_IFA | 07-May-25 A | 21-Jun-25 A | 2026-06-12 | 2026-06-12 | 07-May-25 A | 21-Jun-25 A
A12560 | Material Requisition For LV Switchgear_RCA | 23-Jun-25 A | 04-Jul-25 A | 2026-06-12 | 2026-06-12 | 23-Jun-25 A | 04-Jul-25 A
A12570 | Material Requisition For LV Switchgear_IFD/IFC | 07-Jul-25 A | 11-Jul-25 A | 2026-06-12 | 2026-06-12 | 07-Jul-25 A | 11-Jul-25 A
MaterialRequisitionForCapacitorBank |  | 03-Mar-25 A | 04-Sep-25 A | 2026-06-12 | 2026-06-12 | 03-Mar-25 A | 04-Sep-25 A
A12580 | Material Requisition For Capacitor Bank_IFR | 03-Mar-25 A | 27-Apr-25 A | 2026-06-12 | 2026-06-12 | 03-Mar-25 A | 27-Apr-25 A
A12590 | Material Requisition For Capacitor Bank_RCC | 28-Apr-25 A | 04-May-25 A | 2026-06-12 | 2026-06-12 | 28-Apr-25 A | 04-May-25 A
A12600 | Material Requisition For Capacitor Bank_IFA | 05-May-25 A | 21-Jun-25 A | 2026-06-12 | 2026-06-12 | 05-May-25 A | 21-Jun-25 A
A12610 | Material Requisition For Capacitor Bank_RCA | 22-Jun-25 A | 28-Aug-25 A | 2026-06-12 | 2026-06-12 | 22-Jun-25 A | 28-Aug-25 A
A12620 | Material Requisition For Capacitor Bank_IFD/IFC | 29-Aug-25 A | 04-Sep-25 A | 2026-06-12 | 2026-06-12 | 29-Aug-25 A | 04-Sep-25 A
MaterialRequisitionForPower,ControlAndEarthingCables |  | 22-Apr-25 A | 20-Mar-26 A | 2026-06-16 | 2026-06-16 | 22-Apr-25 A | 2026-02-20
A12630 | Material Requisition For Power, Control And Earthing Cables_IFR | 22-Apr-25 A | 13-May-25 A | 2026-06-16 | 2026-06-16 | 22-Apr-25 A | 13-May-25 A
A12640 | Material Requisition For Power, Control And Earthing Cables_RCC | 26-May-25 A | 31-Jul-25 A | 2026-06-16 | 2026-06-16 | 26-May-25 A | 31-Jul-25 A
A12650 | Material Requisition For Power, Control And Earthing Cables_IFA | 01-Aug-25 A | 20-Aug-25 A | 2026-06-16 | 2026-06-16 | 01-Aug-25 A | 20-Aug-25 A
A12660 | Material Requisition For Power, Control And Earthing Cables_RCA | 15-Sep-25 A | 15-Oct-25 A | 2026-06-16 | 2026-06-16 | 15-Sep-25 A | 15-Oct-25 A
A12670 | Material Requisition For Power, Control And Earthing Cables_IFD/IFC | 20-Sep-25 A | 20-Mar-26 A | 2026-06-16 | 2026-06-16 | 20-Sep-25 A | 2026-02-20
MaterialRequisitionForEmergencyDieselGenerator |  | 01-Jan-25 A | 28-Jun-25 A | 2026-06-11 | 2026-06-11 | 01-Jan-25 A | 28-Jun-25 A
A12680 | Material Requisition For Emergency Diesel Generator_IFR | 01-Jan-25 A | 22-Jan-25 A | 2026-06-11 | 2026-06-11 | 01-Jan-25 A | 22-Jan-25 A
A12690 | Material Requisition For Emergency Diesel Generator_RCC | 23-Jan-25 A | 07-Mar-25 A | 2026-06-11 | 2026-06-11 | 23-Jan-25 A | 07-Mar-25 A
A12700 | Material Requisition For Emergency Diesel Generator_IFA | 08-Mar-25 A | 20-Apr-25 A | 2026-06-11 | 2026-06-11 | 08-Mar-25 A | 20-Apr-25 A
A12710 | Material Requisition For Emergency Diesel Generator_RCA | 21-Apr-25 A | 21-Jun-25 A | 2026-06-11 | 2026-06-11 | 21-Apr-25 A | 21-Jun-25 A
A12720 | Material Requisition For Emergency Diesel Generator_IFD/IFC | 22-Jun-25 A | 28-Jun-25 A | 2026-06-11 | 2026-06-11 | 22-Jun-25 A | 28-Jun-25 A
MaterialRequisitionForACUPS |  | 01-Jan-25 A | 30-Apr-25 A | 2026-06-12 | 2026-06-12 | 01-Jan-25 A | 30-Apr-25 A
A12730 | Material Requisition For AC UPS_IFR | 01-Jan-25 A | 22-Jan-25 A | 2026-06-12 | 2026-06-12 | 01-Jan-25 A | 22-Jan-25 A
A12740 | Material Requisition For AC UPS_RCC | 25-Feb-25 A | 07-Mar-25 A | 2026-06-12 | 2026-06-12 | 25-Feb-25 A | 07-Mar-25 A
A12750 | Material Requisition For AC UPS_IFA | 10-Mar-25 A | 21-Mar-25 A | 2026-06-12 | 2026-06-12 | 10-Mar-25 A | 21-Mar-25 A
A12760 | Material Requisition For AC UPS_RCA | 24-Mar-25 A | 04-Apr-25 A | 2026-06-12 | 2026-06-12 | 24-Mar-25 A | 04-Apr-25 A
A12770 | Material Requisition For AC UPS_IFD/IFC | 07-Apr-25 A | 30-Apr-25 A | 2026-06-12 | 2026-06-12 | 07-Apr-25 A | 30-Apr-25 A
MaterialRequisitionForDCUPS |  | 31-Jan-25 A | 28-Jun-25 A | 2026-06-11 | 2026-06-11 | 31-Jan-25 A | 28-Jun-25 A
A12780 | Material Requisition For DC UPS_IFR | 31-Jan-25 A | 21-Feb-25 A | 2026-06-11 | 2026-06-11 | 31-Jan-25 A | 21-Feb-25 A
A12790 | Material Requisition For DC UPS_RCC | 21-Feb-25 A | 14-Mar-25 A | 2026-06-11 | 2026-06-11 | 21-Feb-25 A | 14-Mar-25 A
A12800 | Material Requisition For DC UPS_IFA | 13-Mar-25 A | 21-Mar-25 A | 2026-06-11 | 2026-06-11 | 13-Mar-25 A | 21-Mar-25 A
A12810 | Material Requisition For DC UPS_RCA | 22-Mar-25 A | 21-Jun-25 A | 2026-06-11 | 2026-06-11 | 22-Mar-25 A | 21-Jun-25 A
A12820 | Material Requisition For DC UPS_IFD/IFC | 22-Jun-25 A | 28-Jun-25 A | 2026-06-11 | 2026-06-11 | 22-Jun-25 A | 28-Jun-25 A
MaterialRequisitionForLVVariableFrequencyDrive |  | 31-Jan-25 A | 12-Jul-25 A | 2026-06-11 | 2026-06-11 | 31-Jan-25 A | 12-Jul-25 A
A12830 | Material Requisition For LV Variable Frequency Drive_IFR | 31-Jan-25 A | 21-Feb-25 A | 2026-06-11 | 2026-06-11 | 31-Jan-25 A | 21-Feb-25 A
A12840 | Material Requisition For LV Variable Frequency Drive_RCC | 22-Feb-25 A | 21-Jun-25 A | 2026-06-11 | 2026-06-11 | 22-Feb-25 A | 21-Jun-25 A
A12850 | Material Requisition For LV Variable Frequency Drive_IFA | 22-Jun-25 A | 28-Jun-25 A | 2026-06-11 | 2026-06-11 | 22-Jun-25 A | 28-Jun-25 A
A12860 | Material Requisition For LV Variable Frequency Drive_RCA | 27-Jun-25 A | 05-Jul-25 A | 2026-06-11 | 2026-06-11 | 27-Jun-25 A | 05-Jul-25 A
A12870 | Material Requisition For LV Variable Frequency Drive_IFD/IFC | 06-Jul-25 A | 12-Jul-25 A | 2026-06-11 | 2026-06-11 | 06-Jul-25 A | 12-Jul-25 A
MaterialRequisitionForNeutralGroundingResistor |  | 13-Dec-24 A | 15-Oct-25 A | 2026-06-11 | 2026-06-11 | 13-Dec-24 A | 15-Oct-25 A
A12880 | Material Requisition For Neutral Grounding Resistor_IFR | 13-Dec-24 A | 17-Jan-25 A | 2026-06-11 | 2026-06-11 | 13-Dec-24 A | 17-Jan-25 A
A12890 | Material Requisition For Neutral Grounding Resistor_RCC | 08-Jan-25 A | 10-Feb-25 A | 2026-06-11 | 2026-06-11 | 08-Jan-25 A | 10-Feb-25 A
A12900 | Material Requisition For Neutral Grounding Resistor_IFA | 11-Feb-25 A | 14-Mar-25 A | 2026-06-11 | 2026-06-11 | 11-Feb-25 A | 14-Mar-25 A
A12910 | Material Requisition For Neutral Grounding Resistor_RCA | 15-Mar-25 A | 06-May-25 A | 2026-06-11 | 2026-06-11 | 15-Mar-25 A | 06-May-25 A
A12920 | Material Requisition For Neutral Grounding Resistor_IFD/IFC | 01-Sep-25 A | 15-Oct-25 A | 2026-06-11 | 2026-06-11 | 01-Sep-25 A | 15-Oct-25 A
MaterialRequisitionForInterpostingRelayPanel |  | 01-Sep-25 A | 2026-06-22 | 2026-07-20 | 2026-10-05 | 01-Sep-25 A | 2026-04-27
A58340 | Material Requisition For Interpopsting Relay Panel_IFR | 01-Sep-25 A | 05-Sep-25 A | 2026-07-20 | 2026-07-20 | 01-Sep-25 A | 05-Sep-25 A
A58350 | Material Requisition For Interpopsting Relay Panel_RCC | 2026-04-17 | 2026-05-08 | 2026-08-13 | 2026-09-04 | 2026-02-20 | 2026-03-13
A58360 | Material Requisition For Interpopsting Relay Panel_IFA | 2026-05-21 | 2026-05-27 | 2026-09-04 | 2026-09-09 | 2026-03-26 | 2026-04-01
A58370 | Material Requisition For Interpopsting Relay Panel_RCA | 2026-05-27 | 2026-06-17 | 2026-09-10 | 2026-10-01 | 2026-04-01 | 2026-04-22
A58380 | Material Requisition For Interpopsting Relay Panel_IFD/IFC | 2026-06-17 | 2026-06-22 | 2026-10-01 | 2026-10-05 | 2026-04-22 | 2026-04-27
MaterialRequisitionForIntegratedProtectionControlPanel |  | 19-Jul-25 A | 04-Sep-25 A | 2026-09-01 | 2027-03-23 | 19-Jul-25 A | 04-Sep-25 A
A58140 | Material Requisition For IPCS_IFR | 19-Jul-25 A | 25-Jul-25 A | 2026-09-01 | 2026-09-01 | 19-Jul-25 A | 25-Jul-25 A
A58150 | Material Requisition For IPCS_RCC | 26-Jul-25 A | 14-Aug-25 A | 2027-03-23 | 2027-03-23 | 26-Jul-25 A | 14-Aug-25 A
A58160 | Material Requisition For IPCS_IFA | 14-Aug-25 A | 17-Aug-25 A | 2027-03-23 | 2027-03-23 | 14-Aug-25 A | 17-Aug-25 A
A58170 | Material Requisition For IPCS_RCA | 17-Aug-25 A | 30-Aug-25 A | 2027-03-23 | 2027-03-23 | 17-Aug-25 A | 30-Aug-25 A
A58180 | Material Requisition For IPCS_IFD/IFC | 30-Aug-25 A | 04-Sep-25 A | 2027-03-23 | 2027-03-23 | 30-Aug-25 A | 04-Sep-25 A
MaterialRequisitionForSCMS |  | 19-Jul-25 A | 04-Sep-25 A | 2026-09-01 | 2026-09-01 | 19-Jul-25 A | 04-Sep-25 A
A59950 | Material Requisition For SCMS_IFR | 19-Jul-25 A | 25-Jul-25 A | 2026-09-01 | 2026-09-01 | 19-Jul-25 A | 25-Jul-25 A
A59960 | Material Requisition For SCMS_RCC | 26-Jul-25 A | 14-Aug-25 A | 2026-09-01 | 2026-09-01 | 26-Jul-25 A | 14-Aug-25 A
A59970 | Material Requisition For SCMS_IFA | 14-Aug-25 A | 17-Aug-25 A | 2026-09-01 | 2026-09-01 | 14-Aug-25 A | 17-Aug-25 A
A59980 | Material Requisition For SCMS_RCA | 17-Aug-25 A | 30-Aug-25 A | 2026-09-01 | 2026-09-01 | 17-Aug-25 A | 30-Aug-25 A
A59990 | Material Requisition For SCMS_IFD/IFC | 30-Aug-25 A | 04-Sep-25 A | 2026-09-01 | 2026-09-01 | 30-Aug-25 A | 04-Sep-25 A
KeySingleLineDiagram-HydrogenExtractionUnit |  | 28-May-25 A | 23-Dec-25 A | 2026-06-11 | 2027-03-23 | 28-May-25 A | 23-Dec-25 A
A11380 | Key Single Line Diagram - Hydrogen Extraction Unit_IFR | 28-May-25 A | 07-Jun-25 A | 2026-06-11 | 2026-06-11 | 28-May-25 A | 07-Jun-25 A
A11390 | Key Single Line Diagram - Hydrogen Extraction Unit_RCC | 30-May-25 A | 14-Jun-25 A | 2027-03-23 | 2027-03-23 | 30-May-25 A | 14-Jun-25 A
A11400 | Key Single Line Diagram - Hydrogen Extraction Unit_IFA | 15-Jun-25 A | 21-Jun-25 A | 2027-03-23 | 2027-03-23 | 15-Jun-25 A | 21-Jun-25 A
A11410 | Key Single Line Diagram - Hydrogen Extraction Unit_RCA | 01-Jul-25 A | 10-Sep-25 A | 2027-03-23 | 2027-03-23 | 01-Jul-25 A | 10-Sep-25 A
A11420 | Key Single Line Diagram - Hydrogen Extraction Unit_IFD/IFC | 19-Dec-25 A | 23-Dec-25 A | 2027-03-23 | 2027-03-23 | 19-Dec-25 A | 23-Dec-25 A
SingleLineDiagramForIntegratedProtectionControlPanel |  | 19-Aug-25 A | 2026-06-09 | 2026-09-01 | 2027-03-05 | 19-Aug-25 A | 2026-04-14
A58440 | Single Line Diagram For IPCS_IFR | 19-Aug-25 A | 25-Aug-25 A | 2026-09-01 | 2026-09-01 | 19-Aug-25 A | 25-Aug-25 A
A58450 | Single Line Diagram For IPCS_RCC | 2026-04-17 | 2026-05-08 | 2027-01-13 | 2027-02-04 | 2026-02-20 | 2026-03-13
A58460 | Single Line Diagram For IPCS_IFA | 2026-05-08 | 2026-05-14 | 2027-02-04 | 2027-02-09 | 2026-03-13 | 2026-03-19
A58470 | Single Line Diagram For IPCS_RCA | 2026-05-14 | 2026-06-04 | 2027-02-10 | 2027-03-03 | 2026-03-19 | 2026-04-09
A58480 | Single Line Diagram For IPCS_IFD/IFC | 2026-06-04 | 2026-06-09 | 2027-03-03 | 2027-03-05 | 2026-04-09 | 2026-04-14
SingleLineDiagramForSCMS |  | 19-Aug-25 A | 2026-06-09 | 2026-09-01 | 2027-03-05 | 19-Aug-25 A | 2026-04-14
A60000 | Single Line Diagram For SCMS_IFR | 19-Aug-25 A | 25-Aug-25 A | 2026-09-01 | 2026-09-01 | 19-Aug-25 A | 25-Aug-25 A
A60010 | Single Line Diagram For SCMS_RCC | 2026-04-17 | 2026-05-08 | 2027-01-13 | 2027-02-04 | 2026-02-20 | 2026-03-13
A60020 | Single Line Diagram For SCMS_IFA | 2026-05-08 | 2026-05-14 | 2027-02-04 | 2027-02-09 | 2026-03-13 | 2026-03-19
A60030 | Single Line Diagram For SCMS_RCA | 2026-05-14 | 2026-06-04 | 2027-02-10 | 2027-03-03 | 2026-03-19 | 2026-04-09
A60040 | Single Line Diagram For SCMS_IFD/IFC | 2026-06-04 | 2026-06-09 | 2027-03-03 | 2027-03-05 | 2026-04-09 | 2026-04-14
SingleLineDiagramFor11KVSwitchgear |  | 31-Jan-25 A | 23-Aug-25 A | 2026-06-11 | 2027-03-05 | 31-Jan-25 A | 23-Aug-25 A
A11530 | Single Line Diagram For 11KV Switchgear_IFR | 31-Jan-25 A | 21-Feb-25 A | 2026-06-11 | 2026-06-11 | 31-Jan-25 A | 21-Feb-25 A
A11540 | Single Line Diagram For 11KV Switchgear_RCC | 22-Feb-25 A | 20-Apr-25 A | 2027-03-05 | 2027-03-05 | 22-Feb-25 A | 20-Apr-25 A
A11550 | Single Line Diagram For 11KV Switchgear_IFA | 21-Apr-25 A | 27-Apr-25 A | 2027-03-05 | 2027-03-05 | 21-Apr-25 A | 27-Apr-25 A
A11560 | Single Line Diagram For 11KV Switchgear_RCA | 28-Apr-25 A | 21-Jun-25 A | 2027-03-05 | 2027-03-05 | 28-Apr-25 A | 21-Jun-25 A
A11570 | Single Line Diagram For 11KV Switchgear_IFD/IFC | 22-Jun-25 A | 23-Aug-25 A | 2027-03-05 | 2027-03-05 | 22-Jun-25 A | 23-Aug-25 A
SingleLineDiagramForACUPS |  | 26-Aug-25 A | 23-Dec-25 A | 2027-02-09 | 2027-03-05 | 26-Aug-25 A | 23-Dec-25 A
A11580 | Single Line Diagram For AC UPS_IFR | 26-Aug-25 A | 02-Sep-25 A | 2027-02-09 | 2027-02-09 | 26-Aug-25 A | 02-Sep-25 A
A11590 | Single Line Diagram For AC UPS_RCC | 02-Sep-25 A | 05-Sep-25 A | 2027-03-05 | 2027-03-05 | 02-Sep-25 A | 05-Sep-25 A
A11600 | Single Line Diagram For AC UPS_IFA | 08-Sep-25 A | 12-Sep-25 A | 2027-03-05 | 2027-03-05 | 08-Sep-25 A | 12-Sep-25 A
A11610 | Single Line Diagram For AC UPS_RCA | 01-Nov-25 A | 21-Nov-25 A | 2027-03-05 | 2027-03-05 | 01-Nov-25 A | 21-Nov-25 A
A11620 | Single Line Diagram For AC UPS_IFD/IFC | 19-Dec-25 A | 23-Dec-25 A | 2027-03-05 | 2027-03-05 | 19-Dec-25 A | 23-Dec-25 A
SingleLineDiagramForDCUPS |  | 03-Feb-25 A | 25-Dec-25 A | 2027-02-09 | 2027-03-05 | 03-Feb-25 A | 25-Dec-25 A
A11630 | Single Line Diagram For DC UPS_IFR | 03-Feb-25 A | 24-Feb-25 A | 2027-02-09 | 2027-02-09 | 03-Feb-25 A | 24-Feb-25 A
A11640 | Single Line Diagram For DC UPS_RCC | 25-Feb-25 A | 18-Mar-25 A | 2027-02-09 | 2027-02-09 | 25-Feb-25 A | 18-Mar-25 A
A11650 | Single Line Diagram For DC UPS_IFA | 19-Mar-25 A | 29-Apr-25 A | 2027-03-05 | 2027-03-05 | 19-Mar-25 A | 29-Apr-25 A
A11660 | Single Line Diagram For DC UPS_RCA | 30-Apr-25 A | 02-Jun-25 A | 2027-03-05 | 2027-03-05 | 30-Apr-25 A | 02-Jun-25 A
A11670 | Single Line Diagram For DC UPS_IFD/IFC | 23-Dec-25 A | 25-Dec-25 A | 2027-03-05 | 2027-03-05 | 23-Dec-25 A | 25-Dec-25 A
SingleLineDiagramForLVSwitchgear |  | 20-Jan-25 A | 23-Dec-25 A | 2027-03-05 | 2027-03-05 | 20-Jan-25 A | 23-Dec-25 A
A11680 | Single Line Diagram For LV Switchgear_IFR | 20-Jan-25 A | 21-Feb-25 A | 2027-03-05 | 2027-03-05 | 20-Jan-25 A | 21-Feb-25 A
A11690 | Single Line Diagram For LV Switchgear_RCC | 22-Feb-25 A | 06-May-25 A | 2027-03-05 | 2027-03-05 | 22-Feb-25 A | 06-May-25 A
A11700 | Single Line Diagram For LV Switchgear_IFA | 07-May-25 A | 21-Jun-25 A | 2027-03-05 | 2027-03-05 | 07-May-25 A | 21-Jun-25 A
A11710 | Single Line Diagram For LV Switchgear_RCA | 15-Jul-25 A | 10-Sep-25 A | 2027-03-05 | 2027-03-05 | 15-Jul-25 A | 10-Sep-25 A
A11720 | Single Line Diagram For LV Switchgear_IFD/IFC | 19-Dec-25 A | 23-Dec-25 A | 2027-03-05 | 2027-03-05 | 19-Dec-25 A | 23-Dec-25 A
SingleLineDiagramForLightingAndSmallPower |  | 28-Oct-25 A | 2026-05-12 | 2027-02-09 | 2027-03-05 | 28-Oct-25 A | 2026-03-17
A11730 | Single Line Diagram For Lighting And Small Power_IFR | 28-Oct-25 A | 05-Nov-25 A | 2027-02-09 | 2027-02-09 | 28-Oct-25 A | 05-Nov-25 A
A11740 | Single Line Diagram For Lighting And Small Power_RCC | 05-Nov-25 A | 14-Nov-25 A | 2027-02-09 | 2027-02-09 | 05-Nov-25 A | 14-Nov-25 A
A11750 | Single Line Diagram For Lighting And Small Power_IFA | 23-Jan-26 A | 2026-04-17 | 2027-02-09 | 2027-02-09 | 23-Jan-26 A | 2026-02-20
A11760 | Single Line Diagram For Lighting And Small Power_RCA | 2026-04-17 | 2026-05-08 | 2027-02-10 | 2027-03-03 | 2026-02-20 | 2026-03-13
A11770 | Single Line Diagram For Lighting And Small Power_IFD/IFC | 2026-05-08 | 2026-05-12 | 2027-03-03 | 2027-03-05 | 2026-03-13 | 2026-03-17
OneLineDiagram220/33KVMainSubstation(UnitNo-80)-Update |  | 25-Mar-25 A | 28-Jun-25 A | 2027-03-23 | 2027-03-23 | 25-Mar-25 A | 28-Jun-25 A
A28330 | One Line Diagram 220/33 KV Main Substation (Unit No-80) - Update_IFR | 25-Mar-25 A | 28-Apr-25 A | 2027-03-23 | 2027-03-23 | 25-Mar-25 A | 28-Apr-25 A
A55830 | One Line Diagram 220/33 KV Main Substation (Unit No-80) - Update_RCC | 29-Apr-25 A | 15-May-25 A | 2027-03-23 | 2027-03-23 | 29-Apr-25 A | 15-May-25 A
A55840 | One Line Diagram 220/33 KV Main Substation (Unit No-80) - Update_IFA | 16-May-25 A | 04-Jun-25 A | 2027-03-23 | 2027-03-23 | 16-May-25 A | 04-Jun-25 A
A55850 | One Line Diagram 220/33 KV Main Substation (Unit No-80) - Update_RCA | 05-Jun-25 A | 21-Jun-25 A | 2027-03-23 | 2027-03-23 | 05-Jun-25 A | 21-Jun-25 A
A55860 | One Line Diagram 220/33 KV Main Substation (Unit No-80) - Update_IFD/IFC | 22-Jun-25 A | 28-Jun-25 A | 2027-03-23 | 2027-03-23 | 22-Jun-25 A | 28-Jun-25 A
ProtectionandMeteringOneLineDiagram220/33KVMainSubstation33KVSwitchgear80-ES-1802-Upd |  | 18-Feb-25 A | 13-Jan-26 A | 2027-03-23 | 2027-03-23 | 18-Feb-25 A | 13-Jan-26 A
A28410 | Protection and Metering One Line Diagram 220/33 KV Main Substation 33 KV Switchgear 80-ES-1802 - Update_RCA | 19-Dec-25 A | 09-Jan-26 A | 2027-03-23 | 2027-03-23 | 19-Dec-25 A | 09-Jan-26 A
A28420 | Protection and Metering One Line Diagram 220/33 KV Main Substation 33 KV Switchgear 80-ES-1802 - Update_IFD/IFC | 09-Jan-26 A | 13-Jan-26 A | 2027-03-23 | 2027-03-23 | 09-Jan-26 A | 13-Jan-26 A
A55870 | Protection and Metering One Line Diagram 220/33 KV Main Substation 33 KV Switchgear 80-ES-1802 - Update_IFR | 18-Feb-25 A | 11-Mar-25 A | 2027-03-23 | 2027-03-23 | 18-Feb-25 A | 11-Mar-25 A
A55880 | Protection and Metering One Line Diagram 220/33 KV Main Substation 33 KV Switchgear 80-ES-1802 - Update_RCC | 12-Mar-25 A | 18-Mar-25 A | 2027-03-23 | 2027-03-23 | 12-Mar-25 A | 18-Mar-25 A
A55890 | Protection and Metering One Line Diagram 220/33 KV Main Substation 33 KV Switchgear 80-ES-1802 - Update_IFA | 16-May-25 A | 21-Jun-25 A | 2027-03-23 | 2027-03-23 | 16-May-25 A | 21-Jun-25 A
ElectricalLegendSheet |  | 28-Mar-25 A | 28-Jun-25 A | 2027-01-29 | 2027-03-23 | 28-Mar-25 A | 28-Jun-25 A
A12130 | Electrical Legend Sheet_IFR | 28-Mar-25 A | 06-Apr-25 A | 2027-01-29 | 2027-01-29 | 28-Mar-25 A | 06-Apr-25 A
A12140 | Electrical Legend Sheet_RCC | 31-Mar-25 A | 13-Apr-25 A | 2027-03-23 | 2027-03-23 | 31-Mar-25 A | 13-Apr-25 A
A12150 | Electrical Legend Sheet_IFA | 14-Apr-25 A | 20-Apr-25 A | 2027-03-23 | 2027-03-23 | 14-Apr-25 A | 20-Apr-25 A
A12160 | Electrical Legend Sheet_RCA | 21-Apr-25 A | 21-Jun-25 A | 2027-03-23 | 2027-03-23 | 21-Apr-25 A | 21-Jun-25 A
A12170 | Electrical Legend Sheet_IFD/IFC | 22-Jun-25 A | 28-Jun-25 A | 2027-03-23 | 2027-03-23 | 22-Jun-25 A | 28-Jun-25 A
ElectricalEquipmentAndMotorList |  | 28-Mar-25 A | 04-May-25 A | 2027-01-29 | 2027-03-23 | 28-Mar-25 A | 04-May-25 A
A12230 | Electrical Equipment And Motor List_IFR | 28-Mar-25 A | 06-Apr-25 A | 2027-01-29 | 2027-01-29 | 28-Mar-25 A | 06-Apr-25 A
A12240 | Electrical Equipment And Motor List_RCC | 31-Mar-25 A | 13-Apr-25 A | 2027-03-23 | 2027-03-23 | 31-Mar-25 A | 13-Apr-25 A
A12250 | Electrical Equipment And Motor List_IFA | 14-Apr-25 A | 20-Apr-25 A | 2027-03-23 | 2027-03-23 | 14-Apr-25 A | 20-Apr-25 A
A12260 | Electrical Equipment And Motor List_RCA | 18-Apr-25 A | 27-Apr-25 A | 2027-03-23 | 2027-03-23 | 18-Apr-25 A | 27-Apr-25 A
A12270 | Electrical Equipment And Motor List_IFD/IFC | 28-Apr-25 A | 04-May-25 A | 2027-03-23 | 2027-03-23 | 28-Apr-25 A | 04-May-25 A
SystemArchitectureDiagramForIPCS |  | 12-Feb-25 A | 23-Dec-25 A | 2027-03-23 | 2027-03-23 | 12-Feb-25 A | 23-Dec-25 A
A12280 | System Architecture Diagram For IPCS_IFR | 12-Feb-25 A | 05-Mar-25 A | 2027-03-23 | 2027-03-23 | 12-Feb-25 A | 05-Mar-25 A
A12290 | System Architecture Diagram For IPCS_RCC | 06-Mar-25 A | 20-Apr-25 A | 2027-03-23 | 2027-03-23 | 06-Mar-25 A | 20-Apr-25 A
A12300 | System Architecture Diagram For IPCS_IFA | 21-Apr-25 A | 27-Apr-25 A | 2027-03-23 | 2027-03-23 | 21-Apr-25 A | 27-Apr-25 A
A12310 | System Architecture Diagram For IPCS_RCA | 15-Aug-25 A | 04-Sep-25 A | 2027-03-23 | 2027-03-23 | 15-Aug-25 A | 04-Sep-25 A
A12320 | System Architecture Diagram For IPCS_IFD/IFC | 19-Dec-25 A | 23-Dec-25 A | 2027-03-23 | 2027-03-23 | 19-Dec-25 A | 23-Dec-25 A
SystemArchitectureDiagramForSCMS-Update |  | 01-Jul-25 A | 08-Sep-25 A | 2027-03-23 | 2027-03-23 | 01-Jul-25 A | 08-Sep-25 A
A12330 | System Architecture Diagram For SCMS - Update_IFR | 01-Jul-25 A | 08-Jul-25 A | 2027-03-23 | 2027-03-23 | 01-Jul-25 A | 08-Jul-25 A
A12340 | System Architecture Diagram For SCMS - Update_RCC | 09-Jul-25 A | 30-Jul-25 A | 2027-03-23 | 2027-03-23 | 09-Jul-25 A | 30-Jul-25 A
A12350 | System Architecture Diagram For SCMS - Update_IFA | 31-Jul-25 A | 20-Aug-25 A | 2027-03-23 | 2027-03-23 | 31-Jul-25 A | 20-Aug-25 A
A12360 | System Architecture Diagram For SCMS - Update_RCA | 21-Aug-25 A | 01-Sep-25 A | 2027-03-23 | 2027-03-23 | 21-Aug-25 A | 01-Sep-25 A
A12370 | System Architecture Diagram For SCMS - Update_IFD/IFC | 02-Sep-25 A | 08-Sep-25 A | 2027-03-23 | 2027-03-23 | 02-Sep-25 A | 08-Sep-25 A
CapacitorBankSizingCalculation |  | 22-Mar-25 A | 16-Oct-25 A | 2026-06-11 | 2027-03-23 | 22-Mar-25 A | 16-Oct-25 A
A10780 | Capacitor Bank Sizing Calculation_IFR | 30-Apr-25 A | 19-May-25 A | 2026-06-11 | 2026-06-11 | 30-Apr-25 A | 19-May-25 A
A10790 | Capacitor Bank Sizing Calculation_RCC | 22-Mar-25 A | 26-May-25 A | 2027-03-23 | 2027-03-23 | 22-Mar-25 A | 26-May-25 A
A10800 | Capacitor Bank Sizing Calculation_IFA | 27-May-25 A | 21-Jun-25 A | 2027-03-23 | 2027-03-23 | 27-May-25 A | 21-Jun-25 A
A10810 | Capacitor Bank Sizing Calculation_RCA | 20-Jul-25 A | 22-Aug-25 A | 2027-03-23 | 2027-03-23 | 20-Jul-25 A | 22-Aug-25 A
A10820 | Capacitor Bank Sizing Calculation_IFD/IFC | 10-Oct-25 A | 16-Oct-25 A | 2027-03-23 | 2027-03-23 | 10-Oct-25 A | 16-Oct-25 A
TechnicalBidEvaluationFor11KVSwitchgear |  | 01-Jul-25 A | 23-Dec-25 A | 2026-12-21 | 2027-03-23 | 01-Jul-25 A | 23-Dec-25 A
A12980 | Technical Bid Evaluation For 11KV Switchgear_IFR | 01-Jul-25 A | 18-Jul-25 A | 2026-12-21 | 2026-12-21 | 01-Jul-25 A | 18-Jul-25 A
A12990 | Technical Bid Evaluation For 11KV Switchgear_RCC | 21-Jul-25 A | 22-Aug-25 A | 2026-12-21 | 2026-12-21 | 21-Jul-25 A | 22-Aug-25 A
A13000 | Technical Bid Evaluation For 11KV Switchgear_IFA | 27-Oct-25 A | 05-Nov-25 A | 2026-12-21 | 2026-12-21 | 27-Oct-25 A | 05-Nov-25 A
A13010 | Technical Bid Evaluation For 11KV Switchgear_RCA | 06-Nov-25 A | 17-Nov-25 A | 2027-03-23 | 2027-03-23 | 06-Nov-25 A | 17-Nov-25 A
A13020 | Technical Bid Evaluation For 11KV Switchgear_IFD/IFC | 19-Dec-25 A | 23-Dec-25 A | 2027-03-23 | 2027-03-23 | 19-Dec-25 A | 23-Dec-25 A
TechnicalBidEvaluationForDCUPS |  | 01-Oct-25 A | 19-Jan-26 A | 2026-06-15 | 2027-03-23 | 01-Oct-25 A | 19-Jan-26 A
A13130 | Technical Bid Evaluation For DC UPS_IFR | 01-Oct-25 A | 10-Oct-25 A | 2026-06-15 | 2026-06-15 | 01-Oct-25 A | 10-Oct-25 A
A13140 | Technical Bid Evaluation For DC UPS_RCC | 08-Oct-25 A | 24-Oct-25 A | 2026-06-15 | 2026-06-15 | 08-Oct-25 A | 24-Oct-25 A
A13150 | Technical Bid Evaluation For DC UPS_IFA | 19-Dec-25 A | 24-Dec-25 A | 2026-06-15 | 2026-06-15 | 19-Dec-25 A | 24-Dec-25 A
A13160 | Technical Bid Evaluation For DC UPS_RCA | 24-Dec-25 A | 15-Jan-26 A | 2027-03-23 | 2027-03-23 | 24-Dec-25 A | 15-Jan-26 A
A13170 | Technical Bid Evaluation For DC UPS_IFD/IFC | 15-Jan-26 A | 19-Jan-26 A | 2027-03-23 | 2027-03-23 | 15-Jan-26 A | 19-Jan-26 A
Cable(MVandLV)SizingCalculation |  | 19-Feb-25 A | 16-Oct-25 A | 2026-12-04 | 2027-03-23 | 19-Feb-25 A | 16-Oct-25 A
A10730 | Cable (MV and LV) Sizing Calculation_IFR | 19-Feb-25 A | 12-Mar-25 A | 2026-12-04 | 2026-12-04 | 19-Feb-25 A | 12-Mar-25 A
A10740 | Cable (MV and LV) Sizing Calculation_RCC | 13-Mar-25 A | 06-May-25 A | 2027-03-23 | 2027-03-23 | 13-Mar-25 A | 06-May-25 A
A10750 | Cable (MV and LV) Sizing Calculation_IFA | 07-May-25 A | 19-Jun-25 A | 2027-03-23 | 2027-03-23 | 07-May-25 A | 19-Jun-25 A
A10760 | Cable (MV and LV) Sizing Calculation_RCA | 20-Jun-25 A | 26-Jun-25 A | 2027-03-23 | 2027-03-23 | 20-Jun-25 A | 26-Jun-25 A
A10770 | Cable (MV and LV) Sizing Calculation_IFD/IFC | 10-Oct-25 A | 16-Oct-25 A | 2027-03-23 | 2027-03-23 | 10-Oct-25 A | 16-Oct-25 A
LightingDesignCalculation |  | 31-Jul-25 A | 23-Dec-25 A | 2027-03-23 | 2027-03-23 | 31-Jul-25 A | 23-Dec-25 A
A10830 | Lighting Design Calculation_IFR | 31-Jul-25 A | 15-Aug-25 A | 2027-03-23 | 2027-03-23 | 31-Jul-25 A | 15-Aug-25 A
A10840 | Lighting Design Calculation_RCC | 02-Aug-25 A | 22-Aug-25 A | 2027-03-23 | 2027-03-23 | 02-Aug-25 A | 22-Aug-25 A
A10850 | Lighting Design Calculation_IFA | 01-Oct-25 A | 09-Oct-25 A | 2027-03-23 | 2027-03-23 | 01-Oct-25 A | 09-Oct-25 A
A10860 | Lighting Design Calculation_RCA | 01-Oct-25 A | 17-Oct-25 A | 2027-03-23 | 2027-03-23 | 01-Oct-25 A | 17-Oct-25 A
A10870 | Lighting Design Calculation_IFD/IFC | 19-Dec-25 A | 23-Dec-25 A | 2027-03-23 | 2027-03-23 | 19-Dec-25 A | 23-Dec-25 A
EarthingandLightningProtectionCalculation |  | 31-Jul-25 A | 2026-04-21 | 2026-11-02 | 2027-03-23 | 31-Jul-25 A | 2026-02-24
A10880 | Earthing and Lightning Protection Calculation_IFR | 31-Jul-25 A | 11-Aug-25 A | 2026-11-02 | 2026-11-02 | 31-Jul-25 A | 11-Aug-25 A
A10890 | Earthing and Lightning Protection Calculation_RCC | 10-Aug-25 A | 30-Aug-25 A | 2027-03-19 | 2027-03-19 | 10-Aug-25 A | 30-Aug-25 A
A10900 | Earthing and Lightning Protection Calculation_IFA | 24-Sep-25 A | 09-Oct-25 A | 2027-03-19 | 2027-03-19 | 24-Sep-25 A | 09-Oct-25 A
A10910 | Earthing and Lightning Protection Calculation_RCA | 28-Sep-25 A | 16-Oct-25 A | 2027-03-19 | 2027-03-19 | 28-Sep-25 A | 16-Oct-25 A
A10920 | Earthing and Lightning Protection Calculation_IFD/IFC | 2026-04-17 | 2026-04-21 | 2027-03-19 | 2027-03-23 | 2026-02-20 | 2026-02-24
PowerAndControlCableSchedule |  | 01-Aug-25 A | 19-Jan-26 A | 2026-12-04 | 2026-12-04 | 01-Aug-25 A | 19-Jan-26 A
A12180 | Power And Control Cable Schedule_IFR | 01-Aug-25 A | 15-Aug-25 A | 2026-12-04 | 2026-12-04 | 01-Aug-25 A | 15-Aug-25 A
A12190 | Power And Control Cable Schedule_RCC | 08-Aug-25 A | 22-Aug-25 A | 2026-12-04 | 2026-12-04 | 08-Aug-25 A | 22-Aug-25 A
A12200 | Power And Control Cable Schedule_IFA | 19-Dec-25 A | 24-Dec-25 A | 2026-12-04 | 2026-12-04 | 19-Dec-25 A | 24-Dec-25 A
A12210 | Power And Control Cable Schedule_RCA | 24-Dec-25 A | 15-Jan-26 A | 2026-12-04 | 2026-12-04 | 24-Dec-25 A | 15-Jan-26 A
A12220 | Power And Control Cable Schedule_IFD/IFC | 15-Jan-26 A | 19-Jan-26 A | 2026-12-04 | 2026-12-04 | 15-Jan-26 A | 19-Jan-26 A
InterconnectionSchedule |  | 2026-04-17 | 2026-06-16 | 2027-01-06 | 2027-03-05 | 2026-02-20 | 2026-04-21
A12380 | Interconnection Schedule_IFR | 2026-04-17 | 2026-04-24 | 2027-01-06 | 2027-01-13 | 2026-02-20 | 2026-02-27
A12390 | Interconnection Schedule_RCC | 2026-04-24 | 2026-05-18 | 2027-01-13 | 2027-02-04 | 2026-02-27 | 2026-03-23
A12400 | Interconnection Schedule_IFA | 2026-05-18 | 2026-05-21 | 2027-02-04 | 2027-02-09 | 2026-03-23 | 2026-03-26
A12410 | Interconnection Schedule_RCA | 2026-05-21 | 2026-06-12 | 2027-02-10 | 2027-03-03 | 2026-03-26 | 2026-04-17
A12420 | Interconnection Schedule_IFD/IFC | 2026-06-12 | 2026-06-16 | 2027-03-03 | 2027-03-05 | 2026-04-17 | 2026-04-21
ElectricalSubstationBuildingLayout |  | 03-Jan-25 A | 30-Dec-25 A | 2026-06-15 | 2027-03-23 | 03-Jan-25 A | 30-Dec-25 A
A11930 | Electrical Substation Building Layout_IFR | 03-Jan-25 A | 24-Jan-25 A | 2026-06-15 | 2026-06-15 | 03-Jan-25 A | 24-Jan-25 A
A11940 | Electrical Substation Building Layout_RCC | 25-Jan-25 A | 15-May-25 A | 2026-06-15 | 2026-06-15 | 25-Jan-25 A | 15-May-25 A
A11950 | Electrical Substation Building Layout_IFA | 16-May-25 A | 23-Aug-25 A | 2026-06-15 | 2026-06-15 | 16-May-25 A | 23-Aug-25 A
A11960 | Electrical Substation Building Layout_RCA | 24-Aug-25 A | 30-Aug-25 A | 2027-03-23 | 2027-03-23 | 24-Aug-25 A | 30-Aug-25 A
A11970 | Electrical Substation Building Layout_IFD/IFC | 26-Dec-25 A | 30-Dec-25 A | 2027-03-23 | 2027-03-23 | 26-Dec-25 A | 30-Dec-25 A
CableandTrayRoutingLayout-Outdoor |  | 01-Oct-25 A | 20-Apr-26 A | 2026-11-11 | 2026-12-04 | 01-Oct-25 A | 2026-04-15
A11830 | Cable and Tray Routing Layout - Outdoor_IFR | 01-Oct-25 A | 10-Oct-25 A | 2026-11-11 | 2026-11-11 | 01-Oct-25 A | 10-Oct-25 A
A11840 | Cable and Tray Routing Layout - Outdoor_RCC | 19-Dec-25 A | 21-Jan-26 A | 2026-12-04 | 2026-12-04 | 19-Dec-25 A | 21-Jan-26 A
A11850 | Cable and Tray Routing Layout - Outdoor_IFA | 01-Mar-26 A | 05-Mar-26 A | 2026-12-04 | 2026-12-04 | 2026-02-20 | 2026-02-25
A11860 | Cable and Tray Routing Layout - Outdoor_RCA | 03-Mar-26 A | 10-Apr-26 A | 2026-12-04 | 2026-12-04 | 2026-02-25 | 2026-03-19
A11870 | Cable and Tray Routing Layout - Outdoor_IFD/IFC | 11-Mar-26 A | 20-Apr-26 A | 2026-12-04 | 2026-12-04 | 2026-04-07 | 2026-04-15
Underground33KVCableRoutingLayoutOverall-Update |  | 17-Oct-25 A | 2026-05-12 | 2026-11-11 | 2026-12-04 | 17-Oct-25 A | 2026-04-15
A55900 | Underground 33KV Cable Routing Layout Overall - Update_IFR | 17-Oct-25 A | 25-Oct-25 A | 2026-11-11 | 2026-11-11 | 17-Oct-25 A | 25-Oct-25 A
A55910 | Underground 33KV Cable Routing Layout Overall - Update_RCC | 27-Oct-25 A | 06-Nov-25 A | 2026-11-11 | 2026-11-11 | 27-Oct-25 A | 06-Nov-25 A
A55920 | Underground 33KV Cable Routing Layout Overall - Update_IFA | 10-Dec-25 A | 19-Dec-25 A | 2026-11-11 | 2026-11-11 | 10-Dec-25 A | 19-Dec-25 A
A55930 | Underground 33KV Cable Routing Layout Overall - Update_RCA | 2026-04-17 | 2026-05-08 | 2026-11-11 | 2026-12-02 | 2026-02-20 | 2026-03-13
A55940 | Underground 33KV Cable Routing Layout Overall - Update_IFD/IFC | 2026-05-08 | 2026-05-12 | 2026-12-02 | 2026-12-04 | 2026-04-13 | 2026-04-15
CableandTrayRoutingLayout-Indoor |  | 17-Mar-26 A | 2026-06-09 | 2026-10-14 | 2026-12-04 | 2026-03-09 | 2026-05-06
A11880 | Cable and Tray Routing Layout - Indoor_IFR | 17-Mar-26 A | 20-Mar-26 A | 2026-10-14 | 2026-10-14 | 2026-03-09 | 2026-03-16
A11890 | Cable and Tray Routing Layout - Indoor_RCC | 2026-04-17 | 2026-05-08 | 2026-10-14 | 2026-11-05 | 2026-03-16 | 2026-04-07
A11900 | Cable and Tray Routing Layout - Indoor_IFA | 2026-05-08 | 2026-05-14 | 2026-11-05 | 2026-11-10 | 2026-04-07 | 2026-04-10
A11910 | Cable and Tray Routing Layout - Indoor_RCA | 2026-05-14 | 2026-06-04 | 2026-11-11 | 2026-12-02 | 2026-04-13 | 2026-05-04
A11920 | Cable and Tray Routing Layout - Indoor_IFD/IFC | 2026-06-04 | 2026-06-09 | 2026-12-02 | 2026-12-04 | 2026-05-04 | 2026-05-06
OverallLighting&SmallPowerLayout |  | 23-Aug-25 A | 23-Jan-26 A | 2026-12-04 | 2026-12-04 | 23-Aug-25 A | 23-Jan-26 A
A11980 | Overall Lighting & Small Power Layout_IFR | 23-Aug-25 A | 13-Sep-25 A | 2026-12-04 | 2026-12-04 | 23-Aug-25 A | 13-Sep-25 A
A11990 | Overall Lighting & Small Power Layout_RCC | 28-Aug-25 A | 20-Sep-25 A | 2026-12-04 | 2026-12-04 | 28-Aug-25 A | 20-Sep-25 A
A12000 | Overall Lighting & Small Power Layout_IFA | 19-Dec-25 A | 24-Dec-25 A | 2026-12-04 | 2026-12-04 | 19-Dec-25 A | 24-Dec-25 A
A12010 | Overall Lighting & Small Power Layout_RCA | 24-Dec-25 A | 15-Jan-26 A | 2026-12-04 | 2026-12-04 | 24-Dec-25 A | 15-Jan-26 A
A12020 | Overall Lighting & Small Power Layout_IFD/IFC | 15-Jan-26 A | 23-Jan-26 A | 2026-12-04 | 2026-12-04 | 15-Jan-26 A | 23-Jan-26 A
EarthingAndLightningProtectionSystemLayout |  | 20-Dec-25 A | 2026-05-21 | 2026-11-02 | 2026-12-04 | 20-Dec-25 A | 2026-03-26
A12030 | Earthing And Lightning Protection System Layout_IFR | 20-Dec-25 A | 12-Jan-26 A | 2026-11-02 | 2026-11-02 | 20-Dec-25 A | 12-Jan-26 A
A12040 | Earthing And Lightning Protection System Layout_RCC | 12-Jan-26 A | 17-Jan-26 A | 2026-11-02 | 2026-11-02 | 12-Jan-26 A | 17-Jan-26 A
A12050 | Earthing And Lightning Protection System Layout_IFA | 2026-04-17 | 2026-04-22 | 2026-11-02 | 2026-11-05 | 2026-02-20 | 2026-02-25
A12060 | Earthing And Lightning Protection System Layout_RCA | 2026-04-22 | 2026-05-14 | 2026-11-05 | 2026-11-27 | 2026-02-25 | 2026-03-19
A12070 | Earthing And Lightning Protection System Layout_IFD/IFC | 2026-05-14 | 2026-05-21 | 2026-11-27 | 2026-12-04 | 2026-03-19 | 2026-03-26
UpdationofEarthingLayoutButene1,EU3,B3/EU3 |  | 10-Sep-25 A | 2026-06-12 | 2026-07-23 | 2027-03-23 | 10-Sep-25 A | 2026-04-17
A12080 | Updation of Earthing Layout Butene 1, EU3, B3/EU3_IFR | 10-Sep-25 A | 15-Sep-25 A | 2026-07-23 | 2026-07-23 | 10-Sep-25 A | 15-Sep-25 A
A12090 | Updation of Earthing Layout Butene 1, EU3, B3/EU3_RCC | 2026-04-17 | 2026-05-08 | 2027-01-26 | 2027-02-17 | 2026-02-20 | 2026-03-13
A12100 | Updation of Earthing Layout Butene 1, EU3, B3/EU3_IFA | 2026-05-08 | 2026-05-14 | 2027-02-17 | 2027-02-22 | 2026-03-13 | 2026-03-19
A12110 | Updation of Earthing Layout Butene 1, EU3, B3/EU3_RCA | 2026-05-14 | 2026-06-04 | 2027-02-22 | 2027-03-16 | 2026-03-19 | 2026-04-09
A12120 | Updation of Earthing Layout Butene 1, EU3, B3/EU3_IFD/IFC | 2026-06-04 | 2026-06-12 | 2027-03-16 | 2027-03-23 | 2026-04-09 | 2026-04-17
ElectricalBulkMTO |  | 20-Apr-25 A | 25-May-25 A | 2026-07-23 | 2026-08-17 | 20-Apr-25 A | 25-May-25 A
A13430 | Electrical Bulk MTO_IFR | 20-Apr-25 A | 11-May-25 A | 2026-07-23 | 2026-07-23 | 20-Apr-25 A | 11-May-25 A
A13440 | Electrical Bulk MTO_RCC | 12-May-25 A | 18-May-25 A | 2026-07-23 | 2026-07-23 | 12-May-25 A | 18-May-25 A
A13470 | Electrical Bulk MTO_IFD/IFC | 19-May-25 A | 25-May-25 A | 2026-08-17 | 2026-08-17 | 19-May-25 A | 25-May-25 A
Instrumentation |  | 31-Dec-24 A | 2026-06-16 | 2026-06-09 | 2027-03-23 | 2026-11-08 | 2026-12-21
ScopeofWorkfortheICSSSystem |  | 01-Jul-25 A | 2026-06-09 | 2026-06-16 | 2027-03-23 | 01-Jul-25 A | 2026-04-14
A14530 | Scope of Work for the ICSS System_IFR | 01-Jul-25 A | 12-Jul-25 A | 2026-06-16 | 2026-06-16 | 01-Jul-25 A | 12-Jul-25 A
A14540 | Scope of Work for the ICSS System_RCC | 2026-04-17 | 2026-05-08 | 2027-01-29 | 2027-02-22 | 2026-02-20 | 2026-03-13
A14550 | Scope of Work for the ICSS System_IFA | 2026-05-08 | 2026-05-14 | 2027-02-22 | 2027-02-25 | 2026-03-13 | 2026-03-19
A14560 | Scope of Work for the ICSS System_RCA | 2026-05-14 | 2026-06-04 | 2027-02-26 | 2027-03-19 | 2026-03-19 | 2026-04-09
A14570 | Scope of Work for the ICSS System_IFD/IFC | 2026-06-04 | 2026-06-09 | 2027-03-19 | 2027-03-23 | 2026-04-09 | 2026-04-14
ScopeofWorkfortheMCMSSystem |  | 01-Mar-25 A | 2026-06-09 | 2026-06-16 | 2027-03-23 | 01-Mar-25 A | 2026-04-14
A58490 | Scope of Work for the MCMS System_IFR | 01-Mar-25 A | 10-Mar-25 A | 2026-06-16 | 2026-06-16 | 01-Mar-25 A | 10-Mar-25 A
A58500 | Scope of Work for the MCMS System_RCC | 2026-04-17 | 2026-05-08 | 2027-01-29 | 2027-02-22 | 2026-02-20 | 2026-03-13
A58510 | Scope of Work for the MCMS System_IFA | 2026-05-08 | 2026-05-14 | 2027-02-22 | 2027-02-25 | 2026-03-13 | 2026-03-19
A58520 | Scope of Work for the MCMSSystem_RCA | 2026-05-14 | 2026-06-04 | 2027-02-26 | 2027-03-19 | 2026-03-19 | 2026-04-09
A58530 | Scope of Work for the MCMS System_IFD/IFC | 2026-06-04 | 2026-06-09 | 2027-03-19 | 2027-03-23 | 2026-04-09 | 2026-04-14
InstrumentDatasheetforESDValves |  | 13-Mar-25 A | 20-Mar-26 A | 2026-06-12 | 2026-06-16 | 13-Mar-25 A | 2026-02-24
A14430 | Instrument Datasheet for ESD Valves_IFR | 13-Mar-25 A | 27-Apr-25 A | 2026-06-12 | 2026-06-12 | 13-Mar-25 A | 27-Apr-25 A
A14440 | Instrument Datasheet for ESD Valves_RCC | 28-Apr-25 A | 13-Jun-25 A | 2026-06-16 | 2026-06-16 | 28-Apr-25 A | 13-Jun-25 A
A14450 | Instrument Datasheet for ESD Valves_IFA | 14-Jun-25 A | 21-Jun-25 A | 2026-06-16 | 2026-06-16 | 14-Jun-25 A | 21-Jun-25 A
A14460 | Instrument Datasheet for ESD Valves_RCA | 24-Nov-25 A | 22-Jan-26 A | 2026-06-16 | 2026-06-16 | 24-Nov-25 A | 22-Jan-26 A
A14470 | Instrument Datasheet for ESD Valves_IFD/IFC | 17-Mar-26 A | 20-Mar-26 A | 2026-06-16 | 2026-06-16 | 2026-02-20 | 2026-02-24
InstrumentDatasheetforControlValves |  | 13-Mar-25 A | 10-Sep-25 A | 2026-06-16 | 2026-06-16 | 13-Mar-25 A | 10-Sep-25 A
A14280 | Instrument Datasheet for Control Valves_IFR | 13-Mar-25 A | 27-Apr-25 A | 2026-06-16 | 2026-06-16 | 13-Mar-25 A | 27-Apr-25 A
A14290 | Instrument Datasheet for Control Valves_RCC | 28-Apr-25 A | 21-Jun-25 A | 2026-06-16 | 2026-06-16 | 28-Apr-25 A | 21-Jun-25 A
A14300 | Instrument Datasheet for Control Valves_IFA | 22-Jun-25 A | 28-Jun-25 A | 2026-06-16 | 2026-06-16 | 22-Jun-25 A | 28-Jun-25 A
A14310 | Instrument Datasheet for Control Valves_RCA | 19-Aug-25 A | 08-Sep-25 A | 2026-06-16 | 2026-06-16 | 19-Aug-25 A | 08-Sep-25 A
A14320 | Instrument Datasheet for Control Valves_IFD/IFC | 09-Sep-25 A | 10-Sep-25 A | 2026-06-16 | 2026-06-16 | 09-Sep-25 A | 10-Sep-25 A
InstrumentDatasheetforMotorOperatedValves |  | 13-Mar-25 A | 10-Sep-25 A | 2026-06-16 | 2026-06-16 | 13-Mar-25 A | 10-Sep-25 A
A14330 | Instrument Datasheet for Motor Operated Valves_IFR | 13-Mar-25 A | 27-Apr-25 A | 2026-06-16 | 2026-06-16 | 13-Mar-25 A | 27-Apr-25 A
A14340 | Instrument Datasheet for Motor Operated Valves_RCC | 28-Apr-25 A | 13-Jun-25 A | 2026-06-16 | 2026-06-16 | 28-Apr-25 A | 13-Jun-25 A
A14350 | Instrument Datasheet for Motor Operated Valves_IFA | 14-Jun-25 A | 21-Jun-25 A | 2026-06-16 | 2026-06-16 | 14-Jun-25 A | 21-Jun-25 A
A14360 | Instrument Datasheet for Motor Operated Valves_RCA | 19-Aug-25 A | 08-Sep-25 A | 2026-06-16 | 2026-06-16 | 19-Aug-25 A | 08-Sep-25 A
A14370 | Instrument Datasheet for Motor Operated Valves_IFD/IFC | 09-Sep-25 A | 10-Sep-25 A | 2026-06-16 | 2026-06-16 | 09-Sep-25 A | 10-Sep-25 A
InstrumentDatasheetforAnalyzers |  | 01-Jul-25 A | 2026-04-21 | 2026-06-09 | 2026-06-11 | 01-Jul-25 A | 2026-02-24
A14130 | Instrument Datasheet for Analyzers_IFR | 01-Jul-25 A | 12-Jul-25 A | 2026-06-09 | 2026-06-09 | 01-Jul-25 A | 12-Jul-25 A
A14140 | Instrument Datasheet for Analyzers_RCC | 04-Aug-25 A | 25-Aug-25 A | 2026-06-09 | 2026-06-09 | 04-Aug-25 A | 25-Aug-25 A
A14150 | Instrument Datasheet for Analyzers_IFA | 22-Aug-25 A | 30-Aug-25 A | 2026-06-09 | 2026-06-09 | 22-Aug-25 A | 30-Aug-25 A
A14160 | Instrument Datasheet for Analyzers_RCA | 25-Aug-25 A | 06-Sep-25 A | 2026-06-09 | 2026-06-09 | 25-Aug-25 A | 06-Sep-25 A
A14170 | Instrument Datasheet for Analyzers_IFD/IFC | 2026-04-17 | 2026-04-21 | 2026-06-09 | 2026-06-11 | 2026-02-20 | 2026-02-24
InstrumentDatasheetforFlowElement(OrificePlate) |  | 07-Apr-25 A | 23-Dec-25 A | 2026-06-12 | 2027-03-23 | 07-Apr-25 A | 23-Dec-25 A
A13830 | Instrument Datasheet for Flow Element (Orifice Plate)_IFR | 07-Apr-25 A | 28-Apr-25 A | 2026-06-12 | 2026-06-12 | 07-Apr-25 A | 28-Apr-25 A
A13840 | Instrument Datasheet for Flow Element (Orifice Plate)_RCC | 29-Apr-25 A | 21-Jun-25 A | 2027-03-23 | 2027-03-23 | 29-Apr-25 A | 21-Jun-25 A
A13850 | Instrument Datasheet for Flow Element (Orifice Plate)_IFA | 22-Jun-25 A | 28-Jun-25 A | 2027-03-23 | 2027-03-23 | 22-Jun-25 A | 28-Jun-25 A
A13860 | Instrument Datasheet for Flow Element (Orifice Plate)_RCA | 29-Jun-25 A | 05-Jul-25 A | 2027-03-23 | 2027-03-23 | 29-Jun-25 A | 05-Jul-25 A
A13870 | Instrument Datasheet for Flow Element (Orifice Plate)_IFD/IFC | 19-Dec-25 A | 23-Dec-25 A | 2027-03-23 | 2027-03-23 | 19-Dec-25 A | 23-Dec-25 A
InstrumentDatasheetforFlowElement(VenturiTube) |  | 13-Mar-25 A | 22-Aug-25 A | 2026-06-12 | 2026-06-12 | 13-Mar-25 A | 22-Aug-25 A
A13880 | Instrument Datasheet for Flow Element (Venturi Tube)_IFR | 13-Mar-25 A | 27-Apr-25 A | 2026-06-12 | 2026-06-12 | 13-Mar-25 A | 27-Apr-25 A
A13890 | Instrument Datasheet for Flow Element (Venturi Tube)_RCC | 28-Apr-25 A | 13-Jun-25 A | 2026-06-12 | 2026-06-12 | 28-Apr-25 A | 13-Jun-25 A
A13900 | Instrument Datasheet for Flow Element (Venturi Tube)_IFA | 14-Jun-25 A | 21-Jun-25 A | 2026-06-12 | 2026-06-12 | 14-Jun-25 A | 21-Jun-25 A
A13910 | Instrument Datasheet for Flow Element (Venturi Tube)_RCA | 22-Jun-25 A | 28-Jun-25 A | 2026-06-12 | 2026-06-12 | 22-Jun-25 A | 28-Jun-25 A
A13920 | Instrument Datasheet for Flow Element (Venturi Tube)_IFD/IFC | 19-Aug-25 A | 22-Aug-25 A | 2026-06-12 | 2026-06-12 | 19-Aug-25 A | 22-Aug-25 A
InstrumentDatasheetforRotameter |  | 13-Mar-25 A | 21-Nov-25 A | 2026-06-12 | 2026-06-16 | 13-Mar-25 A | 21-Nov-25 A
A14480 | Instrument Datasheet for Rotameter_IFR | 13-Mar-25 A | 27-Apr-25 A | 2026-06-12 | 2026-06-12 | 13-Mar-25 A | 27-Apr-25 A
A14490 | Instrument Datasheet for Rotameter_RCC | 28-Apr-25 A | 13-Jun-25 A | 2026-06-16 | 2026-06-16 | 28-Apr-25 A | 13-Jun-25 A
A14500 | Instrument Datasheet for Rotameter_IFA | 14-Jun-25 A | 21-Jun-25 A | 2026-06-16 | 2026-06-16 | 14-Jun-25 A | 21-Jun-25 A
A14510 | Instrument Datasheet for Rotameter_RCA | 22-Jun-25 A | 08-Sep-25 A | 2026-06-16 | 2026-06-16 | 22-Jun-25 A | 08-Sep-25 A
A14520 | Instrument Datasheet for Rotameter_IFD/IFC | 14-Nov-25 A | 21-Nov-25 A | 2026-06-16 | 2026-06-16 | 14-Nov-25 A | 21-Nov-25 A
InstrumentDatasheetforElectronicTransmitters(Pressure/Level/DP) |  | 26-Mar-25 A | 23-Dec-25 A | 2026-06-12 | 2026-06-16 | 26-Mar-25 A | 23-Dec-25 A
A13680 | Instrument Datasheet for Electronic Transmitters (Pressure / Level / DP)_IFR | 26-Mar-25 A | 16-Apr-25 A | 2026-06-12 | 2026-06-12 | 26-Mar-25 A | 16-Apr-25 A
A13690 | Instrument Datasheet for Electronic Transmitters (Pressure / Level / DP)_RCC | 17-Apr-25 A | 02-May-25 A | 2026-06-16 | 2026-06-16 | 17-Apr-25 A | 02-May-25 A
A13700 | Instrument Datasheet for Electronic Transmitters (Pressure / Level / DP)_IFA | 19-Aug-25 A | 23-Aug-25 A | 2026-06-16 | 2026-06-16 | 19-Aug-25 A | 23-Aug-25 A
A13710 | Instrument Datasheet for Electronic Transmitters (Pressure / Level / DP)_RCA | 16-Aug-25 A | 30-Aug-25 A | 2026-06-16 | 2026-06-16 | 16-Aug-25 A | 30-Aug-25 A
A13720 | Instrument Datasheet for Electronic Transmitters (Pressure / Level / DP)_IFD/IFC | 19-Dec-25 A | 23-Dec-25 A | 2026-06-16 | 2026-06-16 | 19-Dec-25 A | 23-Dec-25 A
InstrumentDatasheetforElectronicTransmitters(Flow) |  | 13-Mar-25 A | 23-Dec-25 A | 2026-06-12 | 2026-06-16 | 13-Mar-25 A | 23-Dec-25 A
A13730 | Instrument Datasheet for Electronic Transmitters (Flow)_IFR | 13-Mar-25 A | 27-Apr-25 A | 2026-06-12 | 2026-06-12 | 13-Mar-25 A | 27-Apr-25 A
A13740 | Instrument Datasheet for Electronic Transmitters (Flow)_RCC | 28-Apr-25 A | 04-May-25 A | 2026-06-16 | 2026-06-16 | 28-Apr-25 A | 04-May-25 A
A13750 | Instrument Datasheet for Electronic Transmitters (Flow)_IFA | 05-May-25 A | 21-Jun-25 A | 2026-06-16 | 2026-06-16 | 05-May-25 A | 21-Jun-25 A
A13760 | Instrument Datasheet for Electronic Transmitters (Flow)_RCA | 22-Jun-25 A | 10-Sep-25 A | 2026-06-16 | 2026-06-16 | 22-Jun-25 A | 10-Sep-25 A
A13770 | Instrument Datasheet for Electronic Transmitters (Flow)_IFD/IFC | 19-Dec-25 A | 23-Dec-25 A | 2026-06-16 | 2026-06-16 | 19-Dec-25 A | 23-Dec-25 A
InstrumentDatasheetforTemperatureTransmitters(Headmounted) |  | 25-Mar-25 A | 2026-04-21 | 2026-06-12 | 2027-03-23 | 25-Mar-25 A | 2026-02-24
A14380 | Instrument Datasheet for Temperature Transmitters (Head mounted)_IFR | 25-Mar-25 A | 21-Jun-25 A | 2026-06-12 | 2026-06-12 | 25-Mar-25 A | 21-Jun-25 A
A14390 | Instrument Datasheet for Temperature Transmitters (Head mounted)_RCC | 22-Jun-25 A | 28-Jun-25 A | 2027-03-19 | 2027-03-19 | 22-Jun-25 A | 28-Jun-25 A
A14400 | Instrument Datasheet for Temperature Transmitters (Head mounted)_IFA | 29-Jun-25 A | 05-Jul-25 A | 2027-03-19 | 2027-03-19 | 29-Jun-25 A | 05-Jul-25 A
A14410 | Instrument Datasheet for Temperature Transmitters (Head mounted)_RCA | 06-Jul-25 A | 12-Jul-25 A | 2027-03-19 | 2027-03-19 | 06-Jul-25 A | 12-Jul-25 A
A14420 | Instrument Datasheet for Temperature Transmitters (Head mounted)_IFD/IFC | 2026-04-17 | 2026-04-21 | 2027-03-19 | 2027-03-23 | 2026-02-20 | 2026-02-24
InstrumentDatasheetforLevelTransmitters(GWRtype) |  | 13-Mar-25 A | 18-Dec-25 A | 2026-06-12 | 2027-03-23 | 13-Mar-25 A | 18-Dec-25 A
A14080 | Instrument Datasheet for Level Transmitters (GWR type)_IFR | 13-Mar-25 A | 27-Apr-25 A | 2026-06-12 | 2026-06-12 | 13-Mar-25 A | 27-Apr-25 A
A14090 | Instrument Datasheet for Level Transmitters (GWR type)_RCC | 28-Apr-25 A | 23-Jun-25 A | 2026-06-16 | 2026-06-16 | 28-Apr-25 A | 23-Jun-25 A
A14100 | Instrument Datasheet for Level Transmitters (GWR type)_IFA | 19-Aug-25 A | 23-Aug-25 A | 2026-06-16 | 2026-06-16 | 19-Aug-25 A | 23-Aug-25 A
A14110 | Instrument Datasheet for Level Transmitters (GWR type)_RCA | 03-Nov-25 A | 21-Nov-25 A | 2027-03-23 | 2027-03-23 | 03-Nov-25 A | 21-Nov-25 A
A14120 | Instrument Datasheet for Level Transmitters (GWR type)_IFD/IFC | 08-Dec-25 A | 18-Dec-25 A | 2027-03-23 | 2027-03-23 | 08-Dec-25 A | 18-Dec-25 A
InstrumentDatasheetforTemperatureElement/Thermowell |  | 29-May-25 A | 23-Dec-25 A | 2026-06-12 | 2026-06-16 | 29-May-25 A | 23-Dec-25 A
A13930 | Instrument Datasheet for Temperature Element / Thermowell_IFR | 29-May-25 A | 20-Jun-25 A | 2026-06-12 | 2026-06-12 | 29-May-25 A | 20-Jun-25 A
A13940 | Instrument Datasheet for Temperature Element / Thermowell_RCC | 30-May-25 A | 28-Jun-25 A | 2026-06-16 | 2026-06-16 | 30-May-25 A | 28-Jun-25 A
A13950 | Instrument Datasheet for Temperature Element / Thermowell_IFA | 30-Jun-25 A | 07-Jul-25 A | 2026-06-16 | 2026-06-16 | 30-Jun-25 A | 07-Jul-25 A
A13960 | Instrument Datasheet for Temperature Element / Thermowell_RCA | 02-Jul-25 A | 18-Jul-25 A | 2026-06-16 | 2026-06-16 | 02-Jul-25 A | 18-Jul-25 A
A13970 | Instrument Datasheet for Temperature Element / Thermowell_IFD/IFC | 19-Dec-25 A | 23-Dec-25 A | 2026-06-16 | 2026-06-16 | 19-Dec-25 A | 23-Dec-25 A
InstrumentDatasheetforTemperatureGauges/Thermowell |  | 13-Mar-25 A | 23-Dec-25 A | 2026-06-12 | 2027-03-23 | 13-Mar-25 A | 23-Dec-25 A
A14030 | Instrument Datasheet for Temperature Gauges / Thermowell_IFR | 13-Mar-25 A | 28-Apr-25 A | 2026-06-12 | 2026-06-12 | 13-Mar-25 A | 28-Apr-25 A
A14040 | Instrument Datasheet for Temperature Gauges / Thermowell_RCC | 19-Apr-25 A | 13-Jun-25 A | 2027-03-23 | 2027-03-23 | 19-Apr-25 A | 13-Jun-25 A
A14050 | Instrument Datasheet for Temperature Gauges / Thermowell_IFA | 11-Jul-25 A | 28-Jul-25 A | 2027-03-23 | 2027-03-23 | 11-Jul-25 A | 28-Jul-25 A
A14060 | Instrument Datasheet for Temperature Gauges / Thermowell_RCA | 20-Oct-25 A | 12-Nov-25 A | 2027-03-23 | 2027-03-23 | 20-Oct-25 A | 12-Nov-25 A
A14070 | Instrument Datasheet for Temperature Gauges / Thermowell_IFD/IFC | 19-Dec-25 A | 23-Dec-25 A | 2027-03-23 | 2027-03-23 | 19-Dec-25 A | 23-Dec-25 A
InstrumentDatasheetforPressureGauges |  | 21-Apr-25 A | 23-Dec-25 A | 2026-06-12 | 2027-03-19 | 21-Apr-25 A | 23-Dec-25 A
A13980 | Instrument Datasheet for Pressure Gauges_IFR | 21-Apr-25 A | 27-Apr-25 A | 2026-06-12 | 2026-06-12 | 21-Apr-25 A | 27-Apr-25 A
A13990 | Instrument Datasheet for Pressure Gauges_RCC | 26-Jun-25 A | 20-Jul-25 A | 2027-02-22 | 2027-02-22 | 26-Jun-25 A | 20-Jul-25 A
A14000 | Instrument Datasheet for Pressure Gauges_IFA | 31-Jul-25 A | 13-Aug-25 A | 2027-02-22 | 2027-02-22 | 31-Jul-25 A | 13-Aug-25 A
A14010 | Instrument Datasheet for Pressure Gauges_RCA | 01-Nov-25 A | 21-Nov-25 A | 2027-03-19 | 2027-03-19 | 01-Nov-25 A | 21-Nov-25 A
A14020 | Instrument Datasheet for Pressure Gauges_IFD/IFC | 19-Dec-25 A | 23-Dec-25 A | 2027-03-19 | 2027-03-19 | 19-Dec-25 A | 23-Dec-25 A
InstrumentDatasheetforLevelGauges(MagneticType) |  | 13-Mar-25 A | 22-Aug-25 A | 2026-06-12 | 2026-06-12 | 13-Mar-25 A | 22-Aug-25 A
A14180 | Instrument Datasheet for Level Gauges (Magnetic Type)_IFR | 13-Mar-25 A | 27-Apr-25 A | 2026-06-12 | 2026-06-12 | 13-Mar-25 A | 27-Apr-25 A
A14190 | Instrument Datasheet for Level Gauges (Magnetic Type)_RCC | 24-Apr-25 A | 13-Jun-25 A | 2026-06-12 | 2026-06-12 | 24-Apr-25 A | 13-Jun-25 A
A14200 | Instrument Datasheet for Level Gauges (Magnetic Type)_IFA | 14-Jun-25 A | 21-Jun-25 A | 2026-06-12 | 2026-06-12 | 14-Jun-25 A | 21-Jun-25 A
A14210 | Instrument Datasheet for Level Gauges (Magnetic Type)_RCA | 22-Jun-25 A | 28-Jun-25 A | 2026-06-12 | 2026-06-12 | 22-Jun-25 A | 28-Jun-25 A
A14220 | Instrument Datasheet for Level Gauges (Magnetic Type)_IFD/IFC | 19-Aug-25 A | 22-Aug-25 A | 2026-06-12 | 2026-06-12 | 19-Aug-25 A | 22-Aug-25 A
InstrumentDatasheetforFire&GasDetectors |  | 26-May-25 A | 23-Dec-25 A | 2026-06-15 | 2026-06-16 | 26-May-25 A | 23-Dec-25 A
A14230 | Instrument Datasheet for Fire & Gas Detectors_IFR | 26-May-25 A | 05-Jul-25 A | 2026-06-15 | 2026-06-15 | 26-May-25 A | 05-Jul-25 A
A14240 | Instrument Datasheet for Fire & Gas Detectors_RCC | 07-Aug-25 A | 01-Sep-25 A | 2026-06-16 | 2026-06-16 | 07-Aug-25 A | 01-Sep-25 A
A14250 | Instrument Datasheet for Fire & Gas Detectors_IFA | 26-Sep-25 A | 13-Oct-25 A | 2026-06-16 | 2026-06-16 | 26-Sep-25 A | 13-Oct-25 A
A14260 | Instrument Datasheet for Fire & Gas Detectors_RCA | 10-Oct-25 A | 25-Oct-25 A | 2026-06-16 | 2026-06-16 | 10-Oct-25 A | 25-Oct-25 A
A14270 | Instrument Datasheet for Fire & Gas Detectors_IFD/IFC | 19-Dec-25 A | 23-Dec-25 A | 2026-06-16 | 2026-06-16 | 19-Dec-25 A | 23-Dec-25 A
InstrumentDatasheetforLoopPoweredIndicator |  | 07-Apr-25 A | 05-Jul-25 A | 2027-03-23 | 2027-03-23 | 07-Apr-25 A | 05-Jul-25 A
A13780 | Instrument Datasheet for Loop Powered Indicator_IFR | 07-Apr-25 A | 28-Apr-25 A | 2027-03-23 | 2027-03-23 | 07-Apr-25 A | 28-Apr-25 A
A13790 | Instrument Datasheet for Loop Powered Indicator_RCC | 29-Apr-25 A | 30-May-25 A | 2027-03-23 | 2027-03-23 | 29-Apr-25 A | 30-May-25 A
A13800 | Instrument Datasheet for Loop Powered Indicator_IFA | 01-Jun-25 A | 21-Jun-25 A | 2027-03-23 | 2027-03-23 | 01-Jun-25 A | 21-Jun-25 A
A13810 | Instrument Datasheet for Loop Powered Indicator_RCA | 22-Jun-25 A | 28-Jun-25 A | 2027-03-23 | 2027-03-23 | 22-Jun-25 A | 28-Jun-25 A
A13820 | Instrument Datasheet for Loop Powered Indicator_IFD/IFC | 29-Jun-25 A | 05-Jul-25 A | 2027-03-23 | 2027-03-23 | 29-Jun-25 A | 05-Jul-25 A
MaterialRequisitionforESDValves |  | 24-Mar-25 A | 03-Sep-25 A | 2026-06-12 | 2026-06-16 | 24-Mar-25 A | 03-Sep-25 A
A15130 | Material Requisition for ESD Valves_IFR | 24-Mar-25 A | 30-Apr-25 A | 2026-06-12 | 2026-06-12 | 24-Mar-25 A | 30-Apr-25 A
A15140 | Material Requisition for ESD Valves_RCC | 01-May-25 A | 21-Jun-25 A | 2026-06-16 | 2026-06-16 | 01-May-25 A | 21-Jun-25 A
A15150 | Material Requisition for ESD Valves_IFA | 22-Jun-25 A | 28-Jun-25 A | 2026-06-16 | 2026-06-16 | 22-Jun-25 A | 28-Jun-25 A
A15160 | Material Requisition for ESD Valves_RCA | 29-Jun-25 A | 27-Aug-25 A | 2026-06-16 | 2026-06-16 | 29-Jun-25 A | 27-Aug-25 A
A15170 | Material Requisition for ESD Valves_IFD/IFC | 28-Aug-25 A | 03-Sep-25 A | 2026-06-16 | 2026-06-16 | 28-Aug-25 A | 03-Sep-25 A
MaterialRequisitionforControlValves |  | 13-Mar-25 A | 19-Sep-25 A | 2026-06-16 | 2026-06-16 | 13-Mar-25 A | 19-Sep-25 A
A14980 | Material Requisition for Control Valves_IFR | 13-Mar-25 A | 27-Apr-25 A | 2026-06-16 | 2026-06-16 | 13-Mar-25 A | 27-Apr-25 A
A14990 | Material Requisition for Control Valves_RCC | 28-Apr-25 A | 21-Jun-25 A | 2026-06-16 | 2026-06-16 | 28-Apr-25 A | 21-Jun-25 A
A15000 | Material Requisition for Control Valves_IFA | 22-Jun-25 A | 28-Jun-25 A | 2026-06-16 | 2026-06-16 | 22-Jun-25 A | 28-Jun-25 A
A15010 | Material Requisition for Control Valves_RCA | 29-Jun-25 A | 02-Sep-25 A | 2026-06-16 | 2026-06-16 | 29-Jun-25 A | 02-Sep-25 A
A15020 | Material Requisition for Control Valves_IFD/IFC | 10-Sep-25 A | 19-Sep-25 A | 2026-06-16 | 2026-06-16 | 10-Sep-25 A | 19-Sep-25 A
MaterialRequisitionforMotorOperatedValves |  | 24-Mar-25 A | 13-Sep-25 A | 2026-06-16 | 2026-06-16 | 24-Mar-25 A | 13-Sep-25 A
A15080 | Material Requisition for Motor Operated Valves_IFR | 24-Mar-25 A | 27-Apr-25 A | 2026-06-16 | 2026-06-16 | 24-Mar-25 A | 27-Apr-25 A
A15090 | Material Requisition for Motor Operated Valves_RCC | 28-Apr-25 A | 13-Jun-25 A | 2026-06-16 | 2026-06-16 | 28-Apr-25 A | 13-Jun-25 A
A15100 | Material Requisition for Motor Operated Valves_IFA | 14-Jun-25 A | 21-Jun-25 A | 2026-06-16 | 2026-06-16 | 14-Jun-25 A | 21-Jun-25 A
A15110 | Material Requisition for Motor Operated Valves_RCA | 22-Jun-25 A | 08-Sep-25 A | 2026-06-16 | 2026-06-16 | 22-Jun-25 A | 08-Sep-25 A
A15120 | Material Requisition for Motor Operated Valves_IFD/IFC | 11-Sep-25 A | 13-Sep-25 A | 2026-06-16 | 2026-06-16 | 11-Sep-25 A | 13-Sep-25 A
MaterialRequisitionforAnalyzers |  | 01-Jul-25 A | 2026-04-23 | 2026-06-11 | 2026-06-15 | 01-Jul-25 A | 2026-02-26
A14830 | Material Requisition for Analyzers_IFR | 01-Jul-25 A | 15-Jul-25 A | 2026-06-11 | 2026-06-11 | 01-Jul-25 A | 15-Jul-25 A
A14840 | Material Requisition for Analyzers_RCC | 01-Aug-25 A | 25-Aug-25 A | 2026-06-11 | 2026-06-11 | 01-Aug-25 A | 25-Aug-25 A
A14850 | Material Requisition for Analyzers_IFA | 26-Aug-25 A | 30-Aug-25 A | 2026-06-11 | 2026-06-11 | 26-Aug-25 A | 30-Aug-25 A
A14860 | Material Requisition for Analyzers_RCA | 20-Aug-25 A | 11-Sep-25 A | 2026-06-11 | 2026-06-11 | 20-Aug-25 A | 11-Sep-25 A
A14870 | Material Requisition for Analyzers_IFD/IFC | 2026-04-21 | 2026-04-23 | 2026-06-11 | 2026-06-15 | 2026-02-24 | 2026-02-26
MaterialRequisitionforFlowElement(OrificePlate) |  | 14-Mar-25 A | 25-Dec-25 A | 2026-07-23 | 2027-03-23 | 14-Mar-25 A | 25-Dec-25 A
A14630 | Material Requisition for Flow Element (Orifice Plate)_IFR | 14-Mar-25 A | 29-Apr-25 A | 2026-07-23 | 2026-07-23 | 14-Mar-25 A | 29-Apr-25 A
A14640 | Material Requisition for Flow Element (Orifice Plate)_RCC | 30-Apr-25 A | 21-Jun-25 A | 2027-03-23 | 2027-03-23 | 30-Apr-25 A | 21-Jun-25 A
A14650 | Material Requisition for Flow Element (Orifice Plate)_IFA | 22-Jun-25 A | 28-Jun-25 A | 2027-03-23 | 2027-03-23 | 22-Jun-25 A | 28-Jun-25 A
A14660 | Material Requisition for Flow Element (Orifice Plate)_RCA | 29-Jun-25 A | 05-Jul-25 A | 2027-03-23 | 2027-03-23 | 29-Jun-25 A | 05-Jul-25 A
A14670 | Material Requisition for Flow Element (Orifice Plate)_IFD/IFC | 23-Dec-25 A | 25-Dec-25 A | 2027-03-23 | 2027-03-23 | 23-Dec-25 A | 25-Dec-25 A
MaterialRequisitionforFlowElement(VenturiTube) |  | 13-Mar-25 A | 15-Sep-25 A | 2026-06-12 | 2026-06-12 | 13-Mar-25 A | 15-Sep-25 A
A14680 | Material Requisition for Flow Element (Venturi Tube)_IFR | 13-Mar-25 A | 30-Apr-25 A | 2026-06-12 | 2026-06-12 | 13-Mar-25 A | 30-Apr-25 A
A14690 | Material Requisition for Flow Element (Venturi Tube)_RCC | 01-May-25 A | 21-Jun-25 A | 2026-06-12 | 2026-06-12 | 01-May-25 A | 21-Jun-25 A
A14700 | Material Requisition for Flow Element (Venturi Tube)_IFA | 22-Jun-25 A | 28-Jun-25 A | 2026-06-12 | 2026-06-12 | 22-Jun-25 A | 28-Jun-25 A
A14710 | Material Requisition for Flow Element (Venturi Tube)_RCA | 22-Aug-25 A | 11-Sep-25 A | 2026-06-12 | 2026-06-12 | 22-Aug-25 A | 11-Sep-25 A
A14720 | Material Requisition for Flow Element (Venturi Tube)_IFD/IFC | 12-Sep-25 A | 15-Sep-25 A | 2026-06-12 | 2026-06-12 | 12-Sep-25 A | 15-Sep-25 A
MaterialRequisitionforRotameter |  | 25-Mar-25 A | 04-Oct-25 A | 2026-06-16 | 2026-06-16 | 25-Mar-25 A | 04-Oct-25 A
A15180 | Material Requisition for Rotameter_IFR | 25-Mar-25 A | 01-May-25 A | 2026-06-16 | 2026-06-16 | 25-Mar-25 A | 01-May-25 A
A15190 | Material Requisition for Rotameter_RCC | 02-May-25 A | 21-Jun-25 A | 2026-06-16 | 2026-06-16 | 02-May-25 A | 21-Jun-25 A
A15200 | Material Requisition for Rotameter_IFA | 14-Jun-25 A | 28-Jun-25 A | 2026-06-16 | 2026-06-16 | 14-Jun-25 A | 28-Jun-25 A
A15210 | Material Requisition for Rotameter_RCA | 22-Jun-25 A | 07-Jul-25 A | 2026-06-16 | 2026-06-16 | 22-Jun-25 A | 07-Jul-25 A
A15220 | Material Requisition for Rotameter_IFD/IFC | 26-Sep-25 A | 04-Oct-25 A | 2026-06-16 | 2026-06-16 | 26-Sep-25 A | 04-Oct-25 A
MaterialRequisitionforElectronicTransmitters |  | 25-Mar-25 A | 25-Dec-25 A | 2026-06-16 | 2026-06-16 | 25-Mar-25 A | 25-Dec-25 A
A14580 | Material Requisition for Electronic Transmitters_IFR | 25-Mar-25 A | 28-Apr-25 A | 2026-06-16 | 2026-06-16 | 25-Mar-25 A | 28-Apr-25 A
A14590 | Material Requisition for Electronic Transmitters_RCC | 29-Apr-25 A | 30-Jul-25 A | 2026-06-16 | 2026-06-16 | 29-Apr-25 A | 30-Jul-25 A
A14600 | Material Requisition for Electronic Transmitters_IFA | 31-Jul-25 A | 23-Aug-25 A | 2026-06-16 | 2026-06-16 | 31-Jul-25 A | 23-Aug-25 A
A14610 | Material Requisition for Electronic Transmitters_RCA | 24-Aug-25 A | 06-Sep-25 A | 2026-06-16 | 2026-06-16 | 24-Aug-25 A | 06-Sep-25 A
A14620 | Material Requisition for Electronic Transmitters_IFD/IFC | 23-Dec-25 A | 25-Dec-25 A | 2026-06-16 | 2026-06-16 | 23-Dec-25 A | 25-Dec-25 A
MaterialRequisitionforLevelTransmitters(GWRtype) |  | 26-Mar-25 A | 28-Aug-25 A | 2026-06-16 | 2026-06-16 | 26-Mar-25 A | 28-Aug-25 A
A14880 | Material Requisition for Level Transmitters (GWR type)_IFR | 26-Mar-25 A | 28-Apr-25 A | 2026-06-16 | 2026-06-16 | 26-Mar-25 A | 28-Apr-25 A
A14890 | Material Requisition for Level Transmitters (GWR type)_RCC | 04-Jul-25 A | 28-Jul-25 A | 2026-06-16 | 2026-06-16 | 04-Jul-25 A | 28-Jul-25 A
A14900 | Material Requisition for Level Transmitters (GWR type)_IFA | 31-Jul-25 A | 11-Aug-25 A | 2026-06-16 | 2026-06-16 | 31-Jul-25 A | 11-Aug-25 A
A14910 | Material Requisition for Level Transmitters (GWR type)_RCA | 01-Aug-25 A | 19-Aug-25 A | 2026-06-16 | 2026-06-16 | 01-Aug-25 A | 19-Aug-25 A
A14920 | Material Requisition for Level Transmitters (GWR type)_IFD/IFC | 20-Aug-25 A | 28-Aug-25 A | 2026-06-16 | 2026-06-16 | 20-Aug-25 A | 28-Aug-25 A
MaterialRequisitionforTemperatureElement/Thermowell |  | 13-Mar-25 A | 23-Jan-26 A | 2026-06-16 | 2026-06-16 | 13-Mar-25 A | 23-Jan-26 A
A14730 | Material Requisition for Temperature Element / Thermowell_IFR | 13-Mar-25 A | 07-May-25 A | 2026-06-16 | 2026-06-16 | 13-Mar-25 A | 07-May-25 A
A14740 | Material Requisition for Temperature Element / Thermowell_RCC | 19-Dec-25 A | 09-Jan-26 A | 2026-06-16 | 2026-06-16 | 19-Dec-25 A | 09-Jan-26 A
A14750 | Material Requisition for Temperature Element / Thermowell_IFA | 09-Jan-26 A | 15-Jan-26 A | 2026-06-16 | 2026-06-16 | 09-Jan-26 A | 15-Jan-26 A
A14760 | Material Requisition for Temperature Element / Thermowell_RCA | 15-Jan-26 A | 20-Jan-26 A | 2026-06-16 | 2026-06-16 | 15-Jan-26 A | 20-Jan-26 A
A14770 | Material Requisition for Temperature Element / Thermowell_IFD/IFC | 20-Jan-26 A | 23-Jan-26 A | 2026-06-16 | 2026-06-16 | 20-Jan-26 A | 23-Jan-26 A
MaterialRequisitionforTemperatureGauges/PressureGauges |  | 25-Mar-25 A | 2026-05-18 | 2026-06-16 | 2027-03-23 | 25-Mar-25 A | 2026-03-23
A14780 | Material Requisition for Temperature Gauges / Pressure Gauges_IFR | 25-Mar-25 A | 30-Apr-25 A | 2026-06-16 | 2026-06-16 | 25-Mar-25 A | 30-Apr-25 A
A14790 | Material Requisition for Temperature Gauges / Pressure Gauges_RCC | 01-May-25 A | 21-Jun-25 A | 2026-06-16 | 2026-06-16 | 01-May-25 A | 21-Jun-25 A
A14800 | Material Requisition for Temperature Gauges / Pressure Gauges_IFA | 2026-04-17 | 2026-04-22 | 2027-02-22 | 2027-02-25 | 2026-02-20 | 2026-02-25
A14810 | Material Requisition for Temperature Gauges / Pressure Gauges_RCA | 2026-04-22 | 2026-05-14 | 2027-02-26 | 2027-03-19 | 2026-02-25 | 2026-03-19
A14820 | Material Requisition for Temperature Gauges / Pressure Gauges_IFD/IFC | 2026-05-14 | 2026-05-18 | 2027-03-19 | 2027-03-23 | 2026-03-19 | 2026-03-23
MaterialRequisitionforLevelGauges(MagneticType) |  | 25-Mar-25 A | 17-Sep-25 A | 2026-06-12 | 2026-06-12 | 25-Mar-25 A | 17-Sep-25 A
A14930 | Material Requisition for Level Gauges (Magnetic Type)_IFR | 25-Mar-25 A | 23-Apr-25 A | 2026-06-12 | 2026-06-12 | 25-Mar-25 A | 23-Apr-25 A
A14940 | Material Requisition for Level Gauges (Magnetic Type)_RCC | 24-Apr-25 A | 30-Jul-25 A | 2026-06-12 | 2026-06-12 | 24-Apr-25 A | 30-Jul-25 A
A14950 | Material Requisition for Level Gauges (Magnetic Type)_IFA | 31-Jul-25 A | 26-Aug-25 A | 2026-06-12 | 2026-06-12 | 31-Jul-25 A | 26-Aug-25 A
A14960 | Material Requisition for Level Gauges (Magnetic Type)_RCA | 27-Aug-25 A | 02-Sep-25 A | 2026-06-12 | 2026-06-12 | 27-Aug-25 A | 02-Sep-25 A
A14970 | Material Requisition for Level Gauges (Magnetic Type)_IFD/IFC | 03-Sep-25 A | 17-Sep-25 A | 2026-06-12 | 2026-06-12 | 03-Sep-25 A | 17-Sep-25 A
MaterialRequisitionforFire&GasDetectors |  | 27-May-25 A | 25-Dec-25 A | 2026-06-16 | 2026-06-16 | 27-May-25 A | 25-Dec-25 A
A15030 | Material Requisition for Fire & Gas Detectors_IFR | 27-May-25 A | 05-Jul-25 A | 2026-06-16 | 2026-06-16 | 27-May-25 A | 05-Jul-25 A
A15040 | Material Requisition for Fire & Gas Detectors_RCC | 07-Jul-25 A | 30-Jul-25 A | 2026-06-16 | 2026-06-16 | 07-Jul-25 A | 30-Jul-25 A
A15050 | Material Requisition for Fire & Gas Detectors_IFA | 26-Sep-25 A | 06-Oct-25 A | 2026-06-16 | 2026-06-16 | 26-Sep-25 A | 06-Oct-25 A
A15060 | Material Requisition for Fire & Gas Detectors_RCA | 29-Sep-25 A | 20-Oct-25 A | 2026-06-16 | 2026-06-16 | 29-Sep-25 A | 20-Oct-25 A
A15070 | Material Requisition for Fire & Gas Detectors_IFD/IFC | 23-Dec-25 A | 25-Dec-25 A | 2026-06-16 | 2026-06-16 | 23-Dec-25 A | 25-Dec-25 A
MaterialRequisitionforInstrumentCables |  | 27-May-25 A | 08-Aug-25 A | 2026-06-15 | 2026-06-16 | 27-May-25 A | 08-Aug-25 A
A15230 | Material Requisition for Instrument Cables_IFR | 27-May-25 A | 05-Jul-25 A | 2026-06-15 | 2026-06-15 | 27-May-25 A | 05-Jul-25 A
A47650 | Material Requisition for Instrument Cables_RCC | 07-Jul-25 A | 18-Jul-25 A | 2026-06-15 | 2026-06-15 | 07-Jul-25 A | 18-Jul-25 A
A47660 | Material Requisition for Instrument Cables_IFA | 02-Jun-25 A | 06-Jun-25 A | 2026-06-15 | 2026-06-15 | 02-Jun-25 A | 06-Jun-25 A
A47670 | Material Requisition for Instrument Cables_RCA | 21-Jul-25 A | 01-Aug-25 A | 2026-06-16 | 2026-06-16 | 21-Jul-25 A | 01-Aug-25 A
A47680 | Material Requisition for Instrument Cables_IFD/IFC | 04-Aug-25 A | 08-Aug-25 A | 2026-06-16 | 2026-06-16 | 04-Aug-25 A | 08-Aug-25 A
MaterialRequisitionforJunctionBoxes |  | 27-May-25 A | 19-Dec-25 A | 2026-06-16 | 2026-06-16 | 27-May-25 A | 19-Dec-25 A
A47690 | Material Requisition for Junction Boxes_IFR | 27-May-25 A | 05-Jul-25 A | 2026-06-16 | 2026-06-16 | 27-May-25 A | 05-Jul-25 A
A47700 | Material Requisition for Junction Boxes_RCC | 22-Sep-25 A | 09-Oct-25 A | 2026-06-16 | 2026-06-16 | 22-Sep-25 A | 09-Oct-25 A
A47710 | Material Requisition for Junction Boxes_IFA | 21-Oct-25 A | 03-Nov-25 A | 2026-06-16 | 2026-06-16 | 21-Oct-25 A | 03-Nov-25 A
A47720 | Material Requisition for Junction Boxes_RCA | 03-Nov-25 A | 13-Nov-25 A | 2026-06-16 | 2026-06-16 | 03-Nov-25 A | 13-Nov-25 A
A47730 | Material Requisition for Junction Boxes_IFD/IFC | 30-Nov-25 A | 19-Dec-25 A | 2026-06-16 | 2026-06-16 | 30-Nov-25 A | 19-Dec-25 A
MaterialRequisitionforICSSSystem |  | 31-Dec-24 A | 14-Aug-25 A | 2026-06-11 | 2026-06-11 | 31-Dec-24 A | 14-Aug-25 A
A15370 | Material Requisition for ICSS System_IFD/IFC | 04-Aug-25 A | 14-Aug-25 A | 2026-06-11 | 2026-06-11 | 04-Aug-25 A | 14-Aug-25 A
A47740 | Material Requisition for ICSS System_IFR | 31-Dec-24 A | 23-Jan-25 A | 2026-06-11 | 2026-06-11 | 31-Dec-24 A | 23-Jan-25 A
A47750 | Material Requisition for ICSS System_RCC | 01-May-25 A | 30-May-25 A | 2026-06-11 | 2026-06-11 | 01-May-25 A | 30-May-25 A
A47760 | Material Requisition for ICSS System_IFA | 02-Jun-25 A | 21-Jun-25 A | 2026-06-11 | 2026-06-11 | 02-Jun-25 A | 21-Jun-25 A
A47770 | Material Requisition for ICSS System_RCA | 22-Jun-25 A | 28-Jun-25 A | 2026-06-11 | 2026-06-11 | 22-Jun-25 A | 28-Jun-25 A
MaterialRequisitionforMCMSSystem |  | 20-Apr-25 A | 07-May-25 A | 2026-06-11 | 2026-06-11 | 20-Apr-25 A | 07-May-25 A
A58190 | Material Requisition for MCMS System_IFR | 20-Apr-25 A | 24-Apr-25 A | 2026-06-11 | 2026-06-11 | 20-Apr-25 A | 24-Apr-25 A
A58200 | Material Requisition for MCMS System_RCC | 25-Apr-25 A | 27-Apr-25 A | 2026-06-11 | 2026-06-11 | 25-Apr-25 A | 27-Apr-25 A
A58210 | Material Requisition for MCMS System_IFA | 28-Apr-25 A | 01-May-25 A | 2026-06-11 | 2026-06-11 | 28-Apr-25 A | 01-May-25 A
A58220 | Material Requisition for MCMS System_RCA | 02-May-25 A | 05-May-25 A | 2026-06-11 | 2026-06-11 | 02-May-25 A | 05-May-25 A
A58230 | Material Requisition for MCMS System_IFD/IFC | 05-May-25 A | 07-May-25 A | 2026-06-11 | 2026-06-11 | 05-May-25 A | 07-May-25 A
TechnicalBidEvaluationforESDValves |  | 01-Oct-25 A | 2026-05-12 | 2027-02-26 | 2027-03-23 | 01-Oct-25 A | 2026-03-17
A16680 | Technical Bid Evaluation for ESD Valves_IFR | 01-Oct-25 A | 07-Oct-25 A | 2027-02-26 | 2027-02-26 | 01-Oct-25 A | 07-Oct-25 A
A16700 | Technical Bid Evaluation for ESD Valves_IFA | 28-Nov-25 A | 11-Dec-25 A | 2027-02-26 | 2027-02-26 | 28-Nov-25 A | 11-Dec-25 A
A16710 | Technical Bid Evaluation for ESD Valves_RCA | 2026-04-17 | 2026-05-08 | 2027-02-26 | 2027-03-19 | 2026-02-20 | 2026-03-13
A16720 | Technical Bid Evaluation for ESD Valves_IFD/IFC | 2026-05-08 | 2026-05-12 | 2027-03-19 | 2027-03-23 | 2026-03-13 | 2026-03-17
A48240 | Technical Bid Evaluation for ESD Valves_RCC | 03-Oct-25 A | 14-Oct-25 A | 2027-02-26 | 2027-02-26 | 03-Oct-25 A | 14-Oct-25 A
TechnicalBidEvaluationforRotameter |  | 30-Nov-25 A | 2026-05-18 | 2027-02-22 | 2027-03-23 | 30-Nov-25 A | 2026-03-23
A16730 | Technical Bid Evaluation for Rotameter_IFR | 30-Nov-25 A | 08-Dec-25 A | 2027-02-22 | 2027-02-22 | 30-Nov-25 A | 08-Dec-25 A
A16740 | Technical Bid Evaluation for Rotameter_RCC | 19-Dec-25 A | 09-Jan-26 A | 2027-02-22 | 2027-02-22 | 19-Dec-25 A | 09-Jan-26 A
A16760 | Technical Bid Evaluation for Rotameter_RCA | 2026-04-22 | 2026-05-14 | 2027-02-26 | 2027-03-19 | 2026-02-25 | 2026-03-19
A16770 | Technical Bid Evaluation for Rotameter_IFD/IFC | 2026-05-14 | 2026-05-18 | 2027-03-19 | 2027-03-23 | 2026-03-19 | 2026-03-23
A48250 | Technical Bid Evaluation for Rotameter_IFA | 2026-04-17 | 2026-04-22 | 2027-02-22 | 2027-02-25 | 2026-02-20 | 2026-02-25
TechnicalBidEvaluationforLevelTransmitters(GWRtype) |  | 23-Aug-25 A | 13-Jan-26 A | 2027-03-23 | 2027-03-23 | 23-Aug-25 A | 13-Jan-26 A
A16580 | Technical Bid Evaluation for Level Transmitters (GWR type)_IFR | 23-Aug-25 A | 18-Sep-25 A | 2027-03-23 | 2027-03-23 | 23-Aug-25 A | 18-Sep-25 A
A16590 | Technical Bid Evaluation for Level Transmitters (GWR type)_RCC | 05-Sep-25 A | 29-Sep-25 A | 2027-03-23 | 2027-03-23 | 05-Sep-25 A | 29-Sep-25 A
A16600 | Technical Bid Evaluation for Level Transmitters (GWR type)_IFA | 28-Nov-25 A | 18-Dec-25 A | 2027-03-23 | 2027-03-23 | 28-Nov-25 A | 18-Dec-25 A
A16610 | Technical Bid Evaluation for Level Transmitters (GWR type)_RCA | 19-Dec-25 A | 09-Jan-26 A | 2027-03-23 | 2027-03-23 | 19-Dec-25 A | 09-Jan-26 A
A16620 | Technical Bid Evaluation for Level Transmitters (GWR type)_IFD/IFC | 09-Jan-26 A | 13-Jan-26 A | 2027-03-23 | 2027-03-23 | 09-Jan-26 A | 13-Jan-26 A
TechnicalBidEvaluationforTemperatureElement/Thermowell |  | 19-Dec-25 A | 2026-05-18 | 2027-02-22 | 2027-03-23 | 19-Dec-25 A | 2026-03-23
A16280 | Technical Bid Evaluation for Temperature Element / Thermowell_IFR | 19-Dec-25 A | 26-Dec-25 A | 2027-02-22 | 2027-02-22 | 19-Dec-25 A | 26-Dec-25 A
A16290 | Technical Bid Evaluation for Temperature Element / Thermowell_RCC | 26-Dec-25 A | 19-Jan-26 A | 2027-02-22 | 2027-02-22 | 26-Dec-25 A | 19-Jan-26 A
A16300 | Technical Bid Evaluation for Temperature Element / Thermowell_IFA | 2026-04-17 | 2026-04-22 | 2027-02-22 | 2027-02-25 | 2026-02-20 | 2026-02-25
A16310 | Technical Bid Evaluation for Temperature Element / Thermowell_RCA | 2026-04-22 | 2026-05-14 | 2027-02-26 | 2027-03-19 | 2026-02-25 | 2026-03-19
A16320 | Technical Bid Evaluation for Temperature Element / Thermowell_IFD/IFC | 2026-05-14 | 2026-05-18 | 2027-03-19 | 2027-03-23 | 2026-03-19 | 2026-03-23
SIL/LOPACLoseoutReport |  | 01-Feb-26 A | 20-Apr-26 A | 2027-03-22 | 2027-03-23 | 2026-02-20 | 2026-04-21
A13480 | SIL/LOPA Closeout Report_IFR | 01-Feb-26 A | 25-Feb-26 A | 2027-03-22 | 2027-03-22 | 2026-02-20 | 2026-02-27
A13490 | SIL/LOPA Closeout Report_RCC | 10-Feb-26 A | 28-Feb-26 A | 2027-03-23 | 2027-03-23 | 2026-02-27 | 2026-03-23
A13500 | SIL/LOPA Closeout Report_IFA | 27-Feb-26 A | 12-Mar-26 A | 2027-03-23 | 2027-03-23 | 2026-03-23 | 2026-03-26
A13510 | SIL/LOPA Closeout Report_RCA | 04-Mar-26 A | 20-Apr-26 A | 2027-03-23 | 2027-03-23 | 2026-03-26 | 2026-04-17
A13520 | SIL/LOPA Closeout Report_IFD/IFC | 12-Mar-26 A | 20-Mar-26 A | 2027-03-23 | 2027-03-23 | 2026-04-17 | 2026-04-21
OverallControlSystemArchitectureDrawing |  | 09-Jun-25 A | 23-Dec-25 A | 2027-01-29 | 2027-03-23 | 09-Jun-25 A | 23-Dec-25 A
A15430 | Overall Control System Architecture Drawing_IFR | 09-Jun-25 A | 05-Jul-25 A | 2027-01-29 | 2027-01-29 | 09-Jun-25 A | 05-Jul-25 A
A15440 | Overall Control System Architecture Drawing_RCC | 06-Jul-25 A | 30-Jul-25 A | 2027-03-23 | 2027-03-23 | 06-Jul-25 A | 30-Jul-25 A
A15450 | Overall Control System Architecture Drawing_IFA | 31-Jul-25 A | 09-Sep-25 A | 2027-03-23 | 2027-03-23 | 31-Jul-25 A | 09-Sep-25 A
A15460 | Overall Control System Architecture Drawing_RCA | 10-Sep-25 A | 16-Sep-25 A | 2027-03-23 | 2027-03-23 | 10-Sep-25 A | 16-Sep-25 A
A15470 | Overall Control System Architecture Drawing_IFD/IFC | 19-Dec-25 A | 23-Dec-25 A | 2027-03-23 | 2027-03-23 | 19-Dec-25 A | 23-Dec-25 A
InstrumentIndex |  | 10-Jun-25 A | 2026-05-12 | 2027-01-29 | 2027-03-23 | 10-Jun-25 A | 2026-03-17
A15480 | Instrument Index_IFR | 10-Jun-25 A | 05-Jul-25 A | 2027-01-29 | 2027-01-29 | 10-Jun-25 A | 05-Jul-25 A
A15490 | Instrument Index_RCC | 01-Aug-25 A | 25-Aug-25 A | 2027-02-26 | 2027-02-26 | 01-Aug-25 A | 25-Aug-25 A
A15500 | Instrument Index_IFA | 22-Aug-25 A | 30-Aug-25 A | 2027-02-26 | 2027-02-26 | 22-Aug-25 A | 30-Aug-25 A
A15510 | Instrument Index_RCA | 2026-04-17 | 2026-05-08 | 2027-02-26 | 2027-03-19 | 2026-02-20 | 2026-03-13
A15520 | Instrument Index_IFD/IFC | 2026-05-08 | 2026-05-12 | 2027-03-19 | 2027-03-23 | 2026-03-13 | 2026-03-17
Instrument&F&GI/Olist |  | 26-May-25 A | 23-Dec-25 A | 2027-01-29 | 2027-03-23 | 26-May-25 A | 23-Dec-25 A
A15530 | Instrument & F&G I/O list_IFR | 26-May-25 A | 05-Jul-25 A | 2027-01-29 | 2027-01-29 | 26-May-25 A | 05-Jul-25 A
A15540 | Instrument & F&G I/O list_RCC | 06-Jul-25 A | 10-Aug-25 A | 2027-03-23 | 2027-03-23 | 06-Jul-25 A | 10-Aug-25 A
A47820 | Instrument & F&G I/O list_IFA | 11-Aug-25 A | 20-Aug-25 A | 2027-03-23 | 2027-03-23 | 11-Aug-25 A | 20-Aug-25 A
A47830 | Instrument & F&G I/O list_RCA | 21-Aug-25 A | 01-Sep-25 A | 2027-03-23 | 2027-03-23 | 21-Aug-25 A | 01-Sep-25 A
A47840 | Instrument & F&G I/O list_IFD/IFC | 19-Dec-25 A | 23-Dec-25 A | 2027-03-23 | 2027-03-23 | 19-Dec-25 A | 23-Dec-25 A
CableBlockDiagram |  | 08-May-25 A | 2026-04-21 | 2027-01-29 | 2027-03-23 | 08-May-25 A | 2026-02-24
A15580 | Cable Block Diagram_IFR | 08-May-25 A | 06-Aug-25 A | 2027-01-29 | 2027-01-29 | 08-May-25 A | 06-Aug-25 A
A15590 | Cable Block Diagram_RCC | 07-Aug-25 A | 13-Sep-25 A | 2027-03-19 | 2027-03-19 | 07-Aug-25 A | 13-Sep-25 A
A15600 | Cable Block Diagram_IFA | 14-Aug-25 A | 20-Aug-25 A | 2027-03-19 | 2027-03-19 | 14-Aug-25 A | 20-Aug-25 A
A15620 | Cable Block Diagram_IFD/IFC | 2026-04-17 | 2026-04-21 | 2027-03-19 | 2027-03-23 | 2026-02-20 | 2026-02-24
A47850 | Cable Block Diagram_RCA | 21-Aug-25 A | 01-Sep-25 A | 2027-03-19 | 2027-03-19 | 21-Aug-25 A | 01-Sep-25 A
Process&PneumaticHookupDrawings |  | 01-Mar-26 A | 2026-06-09 | 2027-01-29 | 2027-03-23 | 2026-02-20 | 2026-04-21
A15630 | Process & Pneumatic Hookup Drawings_IFR | 01-Mar-26 A | 02-Mar-26 A | 2027-01-29 | 2027-01-29 | 2026-02-20 | 2026-02-27
A47860 | Process & Pneumatic Hookup Drawings_RCC | 2026-04-17 | 2026-05-08 | 2027-01-29 | 2027-02-22 | 2026-02-27 | 2026-03-23
A47870 | Process & Pneumatic Hookup Drawings_IFA | 2026-05-08 | 2026-05-14 | 2027-02-22 | 2027-02-25 | 2026-03-23 | 2026-03-26
A47880 | Process & Pneumatic Hookup Drawings_RCA | 2026-05-14 | 2026-06-04 | 2027-02-26 | 2027-03-19 | 2026-03-26 | 2026-04-17
A47890 | Process & Pneumatic Hookup Drawings_IFD/IFC | 2026-06-04 | 2026-06-09 | 2027-03-19 | 2027-03-23 | 2026-04-17 | 2026-04-21
JunctionBoxSchedule |  | 26-May-25 A | 2026-06-09 | 2027-01-27 | 2027-03-23 | 26-May-25 A | 2026-04-14
A15680 | Junction Box Schedule_IFR | 26-May-25 A | 07-Jul-25 A | 2027-01-27 | 2027-01-27 | 26-May-25 A | 07-Jul-25 A
A47900 | Junction Box Schedule_RCC | 2026-04-17 | 2026-05-08 | 2027-01-29 | 2027-02-22 | 2026-02-20 | 2026-03-13
A47910 | Junction Box Schedule_IFA | 2026-05-08 | 2026-05-14 | 2027-02-22 | 2027-02-25 | 2026-03-13 | 2026-03-19
A47920 | Junction Box Schedule_RCA | 2026-05-14 | 2026-06-04 | 2027-02-26 | 2027-03-19 | 2026-03-19 | 2026-04-09
A47930 | Junction Box Schedule_IFD/IFC | 2026-06-04 | 2026-06-09 | 2027-03-19 | 2027-03-23 | 2026-04-09 | 2026-04-14
InstrumentCableSchedule |  | 27-Jun-25 A | 2026-06-09 | 2027-01-27 | 2027-03-19 | 27-Jun-25 A | 2026-04-14
A47940 | Instrument Cable Schedule_IFR | 27-Jun-25 A | 05-Jul-25 A | 2027-01-27 | 2027-01-27 | 27-Jun-25 A | 05-Jul-25 A
A47950 | Instrument Cable Schedule_RCC | 2026-04-17 | 2026-05-08 | 2027-01-27 | 2027-02-18 | 2026-02-20 | 2026-03-13
A47960 | Instrument Cable Schedule_IFA | 2026-05-08 | 2026-05-14 | 2027-02-18 | 2027-02-23 | 2026-03-13 | 2026-03-19
A47970 | Instrument Cable Schedule_RCA | 2026-05-14 | 2026-06-04 | 2027-02-23 | 2027-03-17 | 2026-03-19 | 2026-04-09
A47980 | Instrument Cable Schedule_IFD/IFC | 2026-06-04 | 2026-06-09 | 2027-03-17 | 2027-03-19 | 2026-04-09 | 2026-04-14
SISBuildingEquipmentLayout |  | 08-Apr-25 A | 27-Jun-25 A | 2026-06-15 | 2026-06-21 | 08-Apr-25 A | 27-Jun-25 A
A48040 | SIS Building Equipment Layout_IFR | 08-Apr-25 A | 29-Apr-25 A | 2026-06-15 | 2026-06-15 | 08-Apr-25 A | 29-Apr-25 A
A48050 | SIS Building Equipment Layout_RCC | 30-Apr-25 A | 30-May-25 A | 2026-06-15 | 2026-06-15 | 30-Apr-25 A | 30-May-25 A
A48060 | SIS Building Equipment Layout_IFA | 02-Jun-25 A | 06-Jun-25 A | 2026-06-15 | 2026-06-15 | 02-Jun-25 A | 06-Jun-25 A
A48070 | SIS Building Equipment Layout_RCA | 09-Jun-25 A | 20-Jun-25 A | 2026-06-21 | 2026-06-21 | 09-Jun-25 A | 20-Jun-25 A
A48080 | SIS Building Equipment Layout_IFD/IFC | 23-Jun-25 A | 27-Jun-25 A | 2026-06-21 | 2026-06-21 | 23-Jun-25 A | 27-Jun-25 A
Instrument&JBWiringDiagram |  | 20-Dec-25 A | 2026-05-18 | 2027-02-18 | 2027-03-19 | 20-Dec-25 A | 2026-03-23
A47990 | Instrument & JB wiring Diagram_IFR | 20-Dec-25 A | 12-Jan-26 A | 2027-02-18 | 2027-02-18 | 20-Dec-25 A | 12-Jan-26 A
A48000 | Instrument & JB wiring Diagram_RCC | 12-Jan-26 A | 17-Jan-26 A | 2027-02-18 | 2027-02-18 | 12-Jan-26 A | 17-Jan-26 A
A48010 | Instrument & JB wiring Diagram_IFA | 2026-04-17 | 2026-04-22 | 2027-02-18 | 2027-02-23 | 2026-02-20 | 2026-02-25
A48020 | Instrument & JB wiring Diagram_RCA | 2026-04-22 | 2026-05-14 | 2027-02-23 | 2027-03-17 | 2026-02-25 | 2026-03-19
A48030 | Instrument & JB wiring Diagram_IFD/IFC | 2026-05-14 | 2026-05-18 | 2027-03-17 | 2027-03-19 | 2026-03-19 | 2026-03-23
InstrumentLoopDiagram |  | 2026-04-17 | 2026-06-16 | 2027-01-06 | 2027-03-05 | 2026-03-09 | 2026-05-06
A16080 | Instrument Loop Diagram_IFR | 2026-04-17 | 2026-04-24 | 2027-01-06 | 2027-01-13 | 2026-03-09 | 2026-03-16
A16100 | Instrument Loop Diagram_IFA | 2026-05-18 | 2026-05-21 | 2027-02-04 | 2027-02-09 | 2026-04-07 | 2026-04-10
A16110 | Instrument Loop Diagram_RCA | 2026-05-21 | 2026-06-12 | 2027-02-10 | 2027-03-03 | 2026-04-13 | 2026-05-04
A16120 | Instrument Loop Diagram_IFD/IFC | 2026-06-12 | 2026-06-16 | 2027-03-03 | 2027-03-05 | 2026-05-04 | 2026-05-06
A48140 | Instrument Loop Diagram_RCC | 2026-04-24 | 2026-05-18 | 2027-01-13 | 2027-02-04 | 2026-03-16 | 2026-04-07
InstrumentLocationLayout |  | 01-Mar-26 A | 2026-05-18 | 2027-02-18 | 2027-03-19 | 2026-04-03 | 2026-06-03
A15900 | Instrument Location Layout_IFA | 2026-04-17 | 2026-04-22 | 2027-02-18 | 2027-02-23 | 2026-05-04 | 2026-05-08
A15920 | Instrument Location Layout_IFD/IFC | 2026-05-14 | 2026-05-18 | 2027-03-17 | 2027-03-19 | 2026-05-29 | 2026-06-03
A48090 | Instrument Location Layout_IFR | 01-Mar-26 A | 10-Mar-26 A | 2027-02-18 | 2027-02-18 | 2026-04-03 | 2026-04-10
A48100 | Instrument Location Layout_RCC | 10-Mar-26 A | 20-Mar-26 A | 2027-02-18 | 2027-02-18 | 2026-04-13 | 2026-05-04
A48110 | Instrument Location Layout_RCA | 2026-04-22 | 2026-05-14 | 2027-02-23 | 2027-03-17 | 2026-05-08 | 2026-05-29
InstrumentCable&trenchroutinglayout |  | 20-Dec-25 A | 2026-05-18 | 2027-02-18 | 2027-03-19 | 20-Dec-25 A | 2026-03-23
A15930 | Instrument Cable & trench routing layout_IFR | 20-Dec-25 A | 01-Jan-26 A | 2027-02-18 | 2027-02-18 | 20-Dec-25 A | 01-Jan-26 A
A15940 | Instrument Cable & trench routing layout_RCC | 01-Jan-26 A | 17-Jan-26 A | 2027-02-18 | 2027-02-18 | 01-Jan-26 A | 17-Jan-26 A
A15950 | Instrument Cable & trench routing layout_IFA | 2026-04-17 | 2026-04-22 | 2027-02-18 | 2027-02-23 | 2026-02-20 | 2026-02-25
A15960 | Instrument Cable & trench routing layout_RCA | 2026-04-22 | 2026-05-14 | 2027-02-23 | 2027-03-17 | 2026-02-25 | 2026-03-19
A48120 | Instrument Cable & trench routing layout_IFD/IFC | 2026-05-14 | 2026-05-18 | 2027-03-17 | 2027-03-19 | 2026-03-19 | 2026-03-23
MCTInstallationDrawing |  | 10-Nov-25 A | 2026-05-18 | 2027-02-22 | 2027-03-23 | 10-Nov-25 A | 2026-03-23
A15980 | MCT Installation Drawing_IFR | 10-Nov-25 A | 21-Nov-25 A | 2027-02-22 | 2027-02-22 | 10-Nov-25 A | 21-Nov-25 A
A15990 | MCT Installation Drawing_RCC | 19-Dec-25 A | 09-Jan-26 A | 2027-02-22 | 2027-02-22 | 19-Dec-25 A | 09-Jan-26 A
A16000 | MCT Installation Drawing_IFA | 2026-04-17 | 2026-04-22 | 2027-02-22 | 2027-02-25 | 2026-02-20 | 2026-02-25
A16010 | MCT Installation Drawing_RCA | 2026-04-22 | 2026-05-14 | 2027-02-26 | 2027-03-19 | 2026-02-25 | 2026-03-19
A16020 | MCT Installation Drawing_IFD/IFC | 2026-05-14 | 2026-05-18 | 2027-03-19 | 2027-03-23 | 2026-03-19 | 2026-03-23
Instrumentation&ControlMaterialTakeOff |  | 19-Dec-25 A | 2026-04-21 | 2026-07-17 | 2027-03-23 | 19-Dec-25 A | 2026-02-24
A16040 | Instrumentation & Control Material Take Off_RCC | 26-Dec-25 A | 19-Jan-26 A | 2027-03-19 | 2027-03-19 | 26-Dec-25 A | 19-Jan-26 A
A16070 | Instrumentation & Control Material Take Off_IFD/IFC | 2026-04-17 | 2026-04-21 | 2027-03-19 | 2027-03-23 | 2026-02-20 | 2026-02-24
A48130 | Instrumentation & Control Material Take Off_IFR | 19-Dec-25 A | 26-Dec-25 A | 2026-07-17 | 2026-07-17 | 19-Dec-25 A | 26-Dec-25 A
SPI |  | 02-Mar-25 A | 20-Mar-26 A | 2027-03-23 | 2027-03-23 | 25-Mar-25 A | 2026-04-14
SPIExecutionPhiloshpy |  | 02-Mar-25 A | 20-Mar-26 A | 2027-03-23 | 2027-03-23 | 25-Mar-25 A | 2026-04-14
A28050 | SPI Execution Philoshpy_IFD/IFC | 17-Mar-26 A | 20-Mar-26 A | 2027-03-23 | 2027-03-23 | 2026-04-09 | 2026-04-14
A55560 | SPI Execution Philoshpy_IFR | 02-Mar-25 A | 05-Mar-25 A | 2027-03-23 | 2027-03-23 | 25-Mar-25 A | 28-Apr-25 A
A55570 | SPI Execution Philoshpy_RCC | 02-Mar-26 A | 10-Mar-26 A | 2027-03-23 | 2027-03-23 | 2026-02-20 | 2026-03-13
A55580 | SPI Execution Philoshpy_IFA | 10-Mar-26 A | 15-Mar-26 A | 2027-03-23 | 2027-03-23 | 2026-03-13 | 2026-03-19
A55590 | SPI Execution Philoshpy_RCA | 10-Mar-26 A | 19-Mar-26 A | 2027-03-23 | 2027-03-23 | 2026-03-19 | 2026-04-09
SPIExtractionProcedure |  | 01-Jul-25 A | 20-Mar-26 A | 2027-03-23 | 2027-03-23 | 01-Jul-25 A | 2026-04-14
A28060 | SPI Extraction Procedure_IFR | 01-Jul-25 A | 12-Jul-25 A | 2027-03-23 | 2027-03-23 | 01-Jul-25 A | 12-Jul-25 A
A55600 | SPI Extraction Procedure_RCC | 01-Mar-26 A | 10-Mar-26 A | 2027-03-23 | 2027-03-23 | 2026-02-20 | 2026-03-13
A55610 | SPI Extraction Procedure_IFA | 10-Mar-26 A | 17-Mar-26 A | 2027-03-23 | 2027-03-23 | 2026-03-13 | 2026-03-19
A55620 | SPI Extraction Procedure_RCA | 16-Mar-26 A | 19-Mar-26 A | 2027-03-23 | 2027-03-23 | 2026-03-19 | 2026-04-09
A55630 | SPI Extraction Procedure_IFD/IFC | 01-Mar-26 A | 20-Mar-26 A | 2027-03-23 | 2027-03-23 | 2026-04-09 | 2026-04-14
Civil/Structural/Architectural |  | 16-Jan-25 A | 2026-06-25 | 2026-06-15 | 2027-03-23 | 16-Jan-25 A | 2026-05-14
Structure&Foundationdesign-Piperack&otherpipesupports |  | 21-Apr-25 A | 2026-06-25 | 2026-06-15 | 2027-03-23 | 21-Apr-25 A | 2026-05-14
StructuralGA,SectionandDetails-PipeRackSR8001 |  | 02-Jun-25 A | 08-Aug-25 A | 2026-06-15 | 2026-06-15 | 02-Jun-25 A | 08-Aug-25 A
A18000 | Structural GA, Section and Details - Pipe Rack SR8001_IFA | 07-Jul-25 A | 18-Jul-25 A | 2026-06-15 | 2026-06-15 | 07-Jul-25 A | 18-Jul-25 A
A48510 | Structural GA, Section and Details - Pipe Rack SR8001_IFR | 02-Jun-25 A | 20-Jun-25 A | 2026-06-15 | 2026-06-15 | 02-Jun-25 A | 20-Jun-25 A
A48520 | Structural GA, Section and Details - Pipe Rack SR8001_RCC | 23-Jun-25 A | 04-Jul-25 A | 2026-06-15 | 2026-06-15 | 23-Jun-25 A | 04-Jul-25 A
A48530 | Structural GA, Section and Details - Pipe Rack SR8001_RCA | 21-Jul-25 A | 01-Aug-25 A | 2026-06-15 | 2026-06-15 | 21-Jul-25 A | 01-Aug-25 A
A48540 | Structural GA, Section and Details - Pipe Rack SR8001_IFD/IFC | 04-Aug-25 A | 08-Aug-25 A | 2026-06-15 | 2026-06-15 | 04-Aug-25 A | 08-Aug-25 A
DesignCalculationReportforStructuralSteel-PipeRackSR8001 |  | 02-Jun-25 A | 01-Aug-25 A | 2026-06-15 | 2027-03-23 | 02-Jun-25 A | 01-Aug-25 A
A18050 | Design Calculation Report for Structural Steel - Pipe Rack SR8001_IFA | 30-Jun-25 A | 11-Jul-25 A | 2027-03-23 | 2027-03-23 | 30-Jun-25 A | 11-Jul-25 A
A18060 | Design Calculation Report for Structural Steel - Pipe Rack SR8001_RCA | 14-Jul-25 A | 25-Jul-25 A | 2027-03-23 | 2027-03-23 | 14-Jul-25 A | 25-Jul-25 A
A18070 | Design Calculation Report for Structural Steel - Pipe Rack SR8001_IFD/IFC | 28-Jul-25 A | 01-Aug-25 A | 2027-03-23 | 2027-03-23 | 28-Jul-25 A | 01-Aug-25 A
A48550 | Design Calculation Report for Structural Steel - Pipe Rack SR8001_IFR | 02-Jun-25 A | 13-Jun-25 A | 2026-06-15 | 2026-06-15 | 02-Jun-25 A | 13-Jun-25 A
A48560 | Design Calculation Report for Structural Steel - Pipe Rack SR8001_RCC | 16-Jun-25 A | 27-Jun-25 A | 2027-03-23 | 2027-03-23 | 16-Jun-25 A | 27-Jun-25 A
Foundationlayout,SectionandDetails-PipeRackSR8001 |  | 25-Jun-25 A | 23-Dec-25 A | 2026-06-15 | 2026-06-15 | 25-Jun-25 A | 23-Dec-25 A
A18110 | Foundation layout, Section and Details - Pipe Rack SR8001_RCA | 13-Nov-25 A | 21-Nov-25 A | 2026-06-15 | 2026-06-15 | 13-Nov-25 A | 21-Nov-25 A
A18120 | Foundation layout, Section and Details - Pipe Rack SR8001_IFD/IFC | 19-Dec-25 A | 23-Dec-25 A | 2026-06-15 | 2026-06-15 | 19-Dec-25 A | 23-Dec-25 A
A48570 | Foundation layout, Section and Details - Pipe Rack SR8001_IFR | 25-Jun-25 A | 12-Jul-25 A | 2026-06-15 | 2026-06-15 | 25-Jun-25 A | 12-Jul-25 A
A48580 | Foundation layout, Section and Details - Pipe Rack SR8001_RCC | 14-Jul-25 A | 22-Aug-25 A | 2026-06-15 | 2026-06-15 | 14-Jul-25 A | 22-Aug-25 A
A48590 | Foundation layout, Section and Details - Pipe Rack SR8001_IFA | 31-Oct-25 A | 11-Nov-25 A | 2026-06-15 | 2026-06-15 | 31-Oct-25 A | 11-Nov-25 A
DesignCalculationReportforFoundations-PipeRackSR8001 |  | 01-Jul-25 A | 23-Dec-25 A | 2027-03-23 | 2027-03-23 | 01-Jul-25 A | 23-Dec-25 A
A18130 | Design Calculation Report for Foundations - Pipe Rack SR8001_IFR | 01-Jul-25 A | 12-Jul-25 A | 2027-03-23 | 2027-03-23 | 01-Jul-25 A | 12-Jul-25 A
A18170 | Design Calculation Report for Foundations - Pipe Rack SR8001_IFD/IFC | 19-Dec-25 A | 23-Dec-25 A | 2027-03-23 | 2027-03-23 | 19-Dec-25 A | 23-Dec-25 A
A48600 | Design Calculation Report for Foundations - Pipe Rack SR8001_RCC | 14-Jul-25 A | 22-Aug-25 A | 2027-03-23 | 2027-03-23 | 14-Jul-25 A | 22-Aug-25 A
A48610 | Design Calculation Report for Foundations - Pipe Rack SR8001_IFA | 31-Oct-25 A | 11-Nov-25 A | 2027-03-23 | 2027-03-23 | 31-Oct-25 A | 11-Nov-25 A
A48620 | Design Calculation Report for Foundations - Pipe Rack SR8001_RCA | 12-Nov-25 A | 21-Nov-25 A | 2027-03-23 | 2027-03-23 | 12-Nov-25 A | 21-Nov-25 A
StructuralGA,SectionandDetails-PipeRack13-I-08001 |  | 01-Aug-25 A | 24-Dec-25 A | 2026-06-15 | 2026-08-29 | 01-Aug-25 A | 24-Dec-25 A
A18180 | Structural GA, Section and Details - Pipe Rack 13-I-08001_IFR | 01-Aug-25 A | 15-Aug-25 A | 2026-06-15 | 2026-06-15 | 01-Aug-25 A | 15-Aug-25 A
A18190 | Structural GA, Section and Details - Pipe Rack 13-I-08001_RCC | 04-Aug-25 A | 22-Aug-25 A | 2026-06-15 | 2026-06-15 | 04-Aug-25 A | 22-Aug-25 A
A48630 | Structural GA, Section and Details - Pipe Rack 13-I-08001_IFA | 25-Aug-25 A | 29-Aug-25 A | 2026-06-15 | 2026-06-15 | 25-Aug-25 A | 29-Aug-25 A
A48640 | Structural GA, Section and Details - Pipe Rack 13-I-08001_RCA | 01-Sep-25 A | 22-Oct-25 A | 2026-08-29 | 2026-08-29 | 01-Sep-25 A | 22-Oct-25 A
A48650 | Structural GA, Section and Details - Pipe Rack 13-I-08001_IFD/IFC | 19-Dec-25 A | 24-Dec-25 A | 2026-08-29 | 2026-08-29 | 19-Dec-25 A | 24-Dec-25 A
DesignCalculationReportforStructuralSteel-PipeRack13-I-08001 |  | 07-Jul-25 A | 12-Sep-25 A | 2026-06-15 | 2026-06-15 | 07-Jul-25 A | 12-Sep-25 A
A18230 | Design Calculation Report for Structural Steel - Pipe Rack 13-I-08001_IFR | 07-Jul-25 A | 18-Jul-25 A | 2026-06-15 | 2026-06-15 | 07-Jul-25 A | 18-Jul-25 A
A18240 | Design Calculation Report for Structural Steel - Pipe Rack 13-I-08001_RCC | 21-Jul-25 A | 08-Aug-25 A | 2026-06-15 | 2026-06-15 | 21-Jul-25 A | 08-Aug-25 A
A18250 | Design Calculation Report for Structural Steel - Pipe Rack 13-I-08001_IFA | 11-Aug-25 A | 19-Aug-25 A | 2026-06-15 | 2026-06-15 | 11-Aug-25 A | 19-Aug-25 A
A48660 | Design Calculation Report for Structural Steel - Pipe Rack 13-I-08001_RCA | 20-Aug-25 A | 05-Sep-25 A | 2026-06-15 | 2026-06-15 | 20-Aug-25 A | 05-Sep-25 A
A48670 | Design Calculation Report for Structural Steel - Pipe Rack 13-I-08001_IFD/IFC | 08-Sep-25 A | 12-Sep-25 A | 2026-06-15 | 2026-06-15 | 08-Sep-25 A | 12-Sep-25 A
Foundationlayout,SectionandDetails-PipeRack13-I-08001 |  | 30-Jun-25 A | 23-Dec-25 A | 2026-06-15 | 2026-06-15 | 30-Jun-25 A | 23-Dec-25 A
A18290 | Foundation layout, Section and Details - Pipe Rack 13-I-08001_RCC | 16-Jul-25 A | 22-Aug-25 A | 2026-06-15 | 2026-06-15 | 16-Jul-25 A | 22-Aug-25 A
A18300 | Foundation layout, Section and Details - Pipe Rack 13-I-08001_IFA | 25-Aug-25 A | 29-Aug-25 A | 2026-06-15 | 2026-06-15 | 25-Aug-25 A | 29-Aug-25 A
A18310 | Foundation layout, Section and Details - Pipe Rack 13-I-08001_RCA | 11-Aug-25 A | 05-Sep-25 A | 2026-06-15 | 2026-06-15 | 11-Aug-25 A | 05-Sep-25 A
A48680 | Foundation layout, Section and Details - Pipe Rack 13-I-08001_IFR | 30-Jun-25 A | 15-Jul-25 A | 2026-06-15 | 2026-06-15 | 30-Jun-25 A | 15-Jul-25 A
A48690 | Foundation layout, Section and Details - Pipe Rack 13-I-08001_IFD/IFC | 19-Dec-25 A | 23-Dec-25 A | 2026-06-15 | 2026-06-15 | 19-Dec-25 A | 23-Dec-25 A
DesignCalculationReportforFoundations-PipeRack13-I-08001 |  | 02-Jul-25 A | 23-Dec-25 A | 2026-06-15 | 2026-06-15 | 02-Jul-25 A | 23-Dec-25 A
A18350 | Design Calculation Report for Foundations - Pipe Rack 13-I-08001_IFA | 25-Aug-25 A | 29-Aug-25 A | 2026-06-15 | 2026-06-15 | 25-Aug-25 A | 29-Aug-25 A
A48700 | Design Calculation Report for Foundations - Pipe Rack 13-I-08001_IFR | 02-Jul-25 A | 12-Jul-25 A | 2026-06-15 | 2026-06-15 | 02-Jul-25 A | 12-Jul-25 A
A48710 | Design Calculation Report for Foundations - Pipe Rack 13-I-08001_RCC | 14-Jul-25 A | 22-Aug-25 A | 2026-06-15 | 2026-06-15 | 14-Jul-25 A | 22-Aug-25 A
A48720 | Design Calculation Report for Foundations - Pipe Rack 13-I-08001_RCA | 18-Aug-25 A | 05-Sep-25 A | 2026-06-15 | 2026-06-15 | 18-Aug-25 A | 05-Sep-25 A
A48730 | Design Calculation Report for Foundations - Pipe Rack 13-I-08001_IFD/IFC | 19-Dec-25 A | 23-Dec-25 A | 2026-06-15 | 2026-06-15 | 19-Dec-25 A | 23-Dec-25 A
StructralsteelGAanddetailsFieldSupportsSF8200 |  | 03-Jul-25 A | 2026-05-18 | 2026-07-30 | 2026-08-28 | 03-Jul-25 A | 2026-03-23
A20980 | Structral steel GA and details Field Supports SF8200_IFR | 03-Jul-25 A | 20-Jul-25 A | 2026-07-30 | 2026-07-30 | 03-Jul-25 A | 20-Jul-25 A
A20990 | Structral steel GA and details Field Supports SF8200_RCC | 19-Dec-25 A | 09-Jan-26 A | 2026-07-30 | 2026-07-30 | 19-Dec-25 A | 09-Jan-26 A
A21000 | Structral steel GA and details Field Supports SF8200_IFA | 2026-04-17 | 2026-04-22 | 2026-07-30 | 2026-08-04 | 2026-02-20 | 2026-02-25
A21010 | Structral steel GA and details Field Supports SF8200_RCA | 2026-04-22 | 2026-05-14 | 2026-08-05 | 2026-08-26 | 2026-02-25 | 2026-03-19
A21020 | Structral steel GA and details Field Supports SF8200_IFD/IFC | 2026-05-14 | 2026-05-18 | 2026-08-26 | 2026-08-28 | 2026-03-19 | 2026-03-23
DesignCalculationReportforstructuralsteelFieldSupportsSF8200 |  | 19-Aug-25 A | 2026-05-18 | 2026-06-25 | 2026-08-24 | 19-Aug-25 A | 2026-03-23
A21070 | Design Calculation Report for structural steel Field Supports SF8200_IFD/IFC | 2026-05-14 | 2026-05-18 | 2026-08-20 | 2026-08-24 | 2026-03-19 | 2026-03-23
A49960 | Design Calculation Report for structural steel Field Supports SF8200_IFR | 19-Aug-25 A | 25-Aug-25 A | 2026-06-25 | 2026-06-25 | 19-Aug-25 A | 25-Aug-25 A
A49970 | Design Calculation Report for structural steel Field Supports SF8200_RCC | 19-Dec-25 A | 09-Jan-26 A | 2026-07-21 | 2026-07-21 | 19-Dec-25 A | 09-Jan-26 A
A49980 | Design Calculation Report for structural steel Field Supports SF8200_IFA | 2026-04-17 | 2026-04-22 | 2026-07-21 | 2026-07-27 | 2026-02-20 | 2026-02-25
A49990 | Design Calculation Report for structural steel Field Supports SF8200_RCA | 2026-04-22 | 2026-05-14 | 2026-07-29 | 2026-08-20 | 2026-02-25 | 2026-03-19
FoundationLayout,SectionanddetailsFieldSupportsSF8200 |  | 19-Dec-25 A | 2026-05-21 | 2027-02-22 | 2027-03-23 | 19-Dec-25 A | 2026-03-26
A21080 | Foundation Layout, Section and details Field Supports SF8200_IFR | 19-Dec-25 A | 26-Dec-25 A | 2027-02-22 | 2027-02-22 | 19-Dec-25 A | 26-Dec-25 A
A21090 | Foundation Layout, Section and details Field Supports SF8200_RCC | 26-Dec-25 A | 19-Jan-26 A | 2027-02-22 | 2027-02-22 | 26-Dec-25 A | 19-Jan-26 A
A21100 | Foundation Layout, Section and details Field Supports SF8200_IFA | 2026-04-22 | 2026-04-27 | 2027-02-22 | 2027-02-25 | 2026-02-25 | 2026-03-02
A50000 | Foundation Layout, Section and details Field Supports SF8200_RCA | 2026-04-27 | 2026-05-19 | 2027-02-26 | 2027-03-19 | 2026-03-02 | 2026-03-24
A50010 | Foundation Layout, Section and details Field Supports SF8200_IFD/IFC | 2026-05-19 | 2026-05-21 | 2027-03-19 | 2027-03-23 | 2026-03-24 | 2026-03-26
DesignCalculationReportforFoundationsFieldSupportsSF8200 |  | 19-Dec-25 A | 2026-05-21 | 2027-02-22 | 2027-03-23 | 19-Dec-25 A | 2026-03-26
A21150 | Design Calculation Report for Foundations Field Supports SF8200_IFA | 2026-04-22 | 2026-04-27 | 2027-02-22 | 2027-02-25 | 2026-02-25 | 2026-03-02
A21160 | Design Calculation Report for Foundations Field Supports SF8200_RCA | 2026-04-27 | 2026-05-19 | 2027-02-26 | 2027-03-19 | 2026-03-02 | 2026-03-24
A21170 | Design Calculation Report for Foundations Field Supports SF8200_IFD/IFC | 2026-05-19 | 2026-05-21 | 2027-03-19 | 2027-03-23 | 2026-03-24 | 2026-03-26
A50020 | Design Calculation Report for Foundations Field Supports SF8200_IFR | 19-Dec-25 A | 26-Dec-25 A | 2027-02-22 | 2027-02-22 | 19-Dec-25 A | 26-Dec-25 A
A50030 | Design Calculation Report for Foundations Field Supports SF8200_RCC | 26-Dec-25 A | 19-Jan-26 A | 2027-02-22 | 2027-02-22 | 26-Dec-25 A | 19-Jan-26 A
StructuralGAandDetails,FieldsupportsinCA37 |  | 2026-04-17 | 2026-06-16 | 2026-06-25 | 2026-08-26 | 2026-02-20 | 2026-04-21
A21900 | Structural GA and Details, Field supports in CA37_IFA | 2026-05-18 | 2026-05-21 | 2026-07-27 | 2026-07-30 | 2026-03-23 | 2026-03-26
A50430 | Structural GA and Details, Field supports in CA37_IFR | 2026-04-17 | 2026-04-24 | 2026-06-25 | 2026-07-03 | 2026-02-20 | 2026-02-27
A50440 | Structural GA and Details, Field supports in CA37_RCC | 2026-04-24 | 2026-05-18 | 2026-07-03 | 2026-07-27 | 2026-02-27 | 2026-03-23
A50450 | Structural GA and Details, Field supports in CA37_RCA | 2026-05-21 | 2026-06-12 | 2026-07-31 | 2026-08-24 | 2026-03-26 | 2026-04-17
A50460 | Structural GA and Details, Field supports in CA37_IFD/IFC | 2026-06-12 | 2026-06-16 | 2026-08-24 | 2026-08-26 | 2026-04-17 | 2026-04-21
DesignCalculationreportofstructuralsteelFieldsupportsCA37 |  | 2026-04-17 | 2026-06-16 | 2026-06-25 | 2026-08-26 | 2026-02-20 | 2026-04-21
A21990 | Design Calculation report of structural steel Field supports CA37_RCC | 2026-04-24 | 2026-05-18 | 2026-07-03 | 2026-07-27 | 2026-02-27 | 2026-03-23
A22020 | Design Calculation report of structural steel Field supports CA37_IFD/IFC | 2026-06-12 | 2026-06-16 | 2026-08-24 | 2026-08-26 | 2026-04-17 | 2026-04-21
A50500 | Design Calculation report of structural steel Field supports CA37_IFR | 2026-04-17 | 2026-04-24 | 2026-06-25 | 2026-07-03 | 2026-02-20 | 2026-02-27
A50510 | Design Calculation report of structural steel Field supports CA37_IFA | 2026-05-18 | 2026-05-21 | 2026-07-27 | 2026-07-30 | 2026-03-23 | 2026-03-26
A50520 | Design Calculation report of structural steel Field supports CA37_RCA | 2026-05-21 | 2026-06-12 | 2026-07-31 | 2026-08-24 | 2026-03-26 | 2026-04-17
DesignCalculationreportofFoundationsFieldsupportsCA37 |  | 2026-04-24 | 2026-06-24 | 2027-01-22 | 2027-03-23 | 2026-02-27 | 2026-04-29
A22060 | Design Calculation report of Foundations Field supports CA37_RCA | 2026-05-29 | 2026-06-22 | 2027-02-26 | 2027-03-19 | 2026-04-03 | 2026-04-27
A50530 | Design Calculation report of Foundations Field supports CA37_IFR | 2026-04-24 | 2026-05-04 | 2027-01-22 | 2027-01-29 | 2026-02-27 | 2026-03-09
A50540 | Design Calculation report of Foundations Field supports CA37_RCC | 2026-05-04 | 2026-05-25 | 2027-01-29 | 2027-02-22 | 2026-03-09 | 2026-03-30
A50550 | Design Calculation report of Foundations Field supports CA37_IFA | 2026-05-26 | 2026-05-29 | 2027-02-22 | 2027-02-25 | 2026-03-31 | 2026-04-03
A50560 | Design Calculation report of Foundations Field supports CA37_IFD/IFC | 2026-06-22 | 2026-06-24 | 2027-03-19 | 2027-03-23 | 2026-04-27 | 2026-04-29
Foundationlayoutanddetails,FieldsupportsinCA37 |  | 2026-04-24 | 2026-06-24 | 2027-01-22 | 2027-03-23 | 2026-02-27 | 2026-04-29
A21950 | Foundation layout and details, Field supports in CA37_IFA | 2026-05-26 | 2026-05-29 | 2027-02-22 | 2027-02-25 | 2026-03-31 | 2026-04-03
A21960 | Foundation layout and details, Field supports in CA37_RCA | 2026-05-29 | 2026-06-22 | 2027-02-26 | 2027-03-19 | 2026-04-03 | 2026-04-27
A50470 | Foundation layout and details, Field supports in CA37_IFR | 2026-04-24 | 2026-05-04 | 2027-01-22 | 2027-01-29 | 2026-02-27 | 2026-03-09
A50480 | Foundation layout and details, Field supports in CA37_RCC | 2026-05-04 | 2026-05-25 | 2027-01-29 | 2027-02-22 | 2026-03-09 | 2026-03-30
A50490 | Foundation layout and details, Field supports in CA37_IFD/IFC | 2026-06-22 | 2026-06-24 | 2027-03-19 | 2027-03-23 | 2026-04-27 | 2026-04-29
StructuralGA,SectionandDetails-PipeBridgeSR81 |  | 23-Jun-25 A | 14-Aug-25 A | 2026-06-15 | 2026-06-15 | 23-Jun-25 A | 14-Aug-25 A
A18390 | Structural GA, Section and Details - Pipe Bridge SR81_RCC | 03-Jul-25 A | 18-Jul-25 A | 2026-06-15 | 2026-06-15 | 03-Jul-25 A | 18-Jul-25 A
A18400 | Structural GA, Section and Details - Pipe Bridge SR81_IFA | 21-Jul-25 A | 25-Jul-25 A | 2026-06-15 | 2026-06-15 | 21-Jul-25 A | 25-Jul-25 A
A18410 | Structural GA, Section and Details - Pipe Bridge SR81_RCA | 28-Jul-25 A | 08-Aug-25 A | 2026-06-15 | 2026-06-15 | 28-Jul-25 A | 08-Aug-25 A
A48740 | Structural GA, Section and Details - Pipe Bridge SR81_IFR | 23-Jun-25 A | 02-Jul-25 A | 2026-06-15 | 2026-06-15 | 23-Jun-25 A | 02-Jul-25 A
A48750 | Structural GA, Section and Details - Pipe Bridge SR81_IFD/IFC | 11-Aug-25 A | 14-Aug-25 A | 2026-06-15 | 2026-06-15 | 11-Aug-25 A | 14-Aug-25 A
DesignCalculationReportforStructuralSteel-PipeBridgeSR81 |  | 03-Jul-25 A | 12-Sep-25 A | 2026-06-15 | 2026-06-15 | 03-Jul-25 A | 12-Sep-25 A
A18440 | Design Calculation Report for Structural Steel - Pipe Bridge SR81_RCC | 21-Jul-25 A | 08-Aug-25 A | 2026-06-15 | 2026-06-15 | 21-Jul-25 A | 08-Aug-25 A
A18450 | Design Calculation Report for Structural Steel - Pipe Bridge SR81_IFA | 11-Aug-25 A | 15-Aug-25 A | 2026-06-15 | 2026-06-15 | 11-Aug-25 A | 15-Aug-25 A
A18470 | Design Calculation Report for Structural Steel - Pipe Bridge SR81_IFD/IFC | 08-Sep-25 A | 12-Sep-25 A | 2026-06-15 | 2026-06-15 | 08-Sep-25 A | 12-Sep-25 A
A48760 | Design Calculation Report for Structural Steel - Pipe Bridge SR81_IFR | 03-Jul-25 A | 20-Jul-25 A | 2026-06-15 | 2026-06-15 | 03-Jul-25 A | 20-Jul-25 A
A48770 | Design Calculation Report for Structural Steel - Pipe Bridge SR81_RCA | 18-Aug-25 A | 05-Sep-25 A | 2026-06-15 | 2026-06-15 | 18-Aug-25 A | 05-Sep-25 A
DesignCalculationReportforFoundations-PipeBridgeSR81 |  | 21-Apr-25 A | 17-Jul-25 A | 2026-06-15 | 2026-06-15 | 21-Apr-25 A | 17-Jul-25 A
A48830 | Design Calculation Report for Foundations - Pipe Bridge SR81_IFR | 21-Apr-25 A | 12-May-25 A | 2026-06-15 | 2026-06-15 | 21-Apr-25 A | 12-May-25 A
A48840 | Design Calculation Report for Foundations - Pipe Bridge SR81_RCC | 13-May-25 A | 19-May-25 A | 2026-06-15 | 2026-06-15 | 13-May-25 A | 19-May-25 A
A48850 | Design Calculation Report for Foundations - Pipe Bridge SR81_IFA | 20-May-25 A | 20-Jun-25 A | 2026-06-15 | 2026-06-15 | 20-May-25 A | 20-Jun-25 A
A48860 | Design Calculation Report for Foundations - Pipe Bridge SR81_RCA | 23-Jun-25 A | 11-Jul-25 A | 2026-06-15 | 2026-06-15 | 23-Jun-25 A | 11-Jul-25 A
A48870 | Design Calculation Report for Foundations - Pipe Bridge SR81_IFD/IFC | 14-Jul-25 A | 17-Jul-25 A | 2026-06-15 | 2026-06-15 | 14-Jul-25 A | 17-Jul-25 A
Foundationlayout,SectionandDetails-PipeBridgeSR81 |  | 21-Apr-25 A | 13-Sep-25 A | 2026-06-15 | 2026-06-15 | 21-Apr-25 A | 13-Sep-25 A
A48780 | Foundation layout, Section and Details - Pipe Bridge SR81_IFR | 21-Apr-25 A | 12-May-25 A | 2026-06-15 | 2026-06-15 | 21-Apr-25 A | 12-May-25 A
A48790 | Foundation layout, Section and Details - Pipe Bridge SR81_RCC | 13-May-25 A | 19-May-25 A | 2026-06-15 | 2026-06-15 | 13-May-25 A | 19-May-25 A
A48800 | Foundation layout, Section and Details - Pipe Bridge SR81_IFA | 20-May-25 A | 20-Jun-25 A | 2026-06-15 | 2026-06-15 | 20-May-25 A | 20-Jun-25 A
A48810 | Foundation layout, Section and Details - Pipe Bridge SR81_RCA | 21-Jun-25 A | 06-Sep-25 A | 2026-06-15 | 2026-06-15 | 21-Jun-25 A | 06-Sep-25 A
A48820 | Foundation layout, Section and Details - Pipe Bridge SR81_IFD/IFC | 08-Sep-25 A | 13-Sep-25 A | 2026-06-15 | 2026-06-15 | 08-Sep-25 A | 13-Sep-25 A
StructralsteelGAanddetailsFieldSupportsSF8300 |  | 02-Feb-26 A | 20-Mar-26 A | 2026-07-30 | 2026-08-26 | 2026-02-27 | 2026-04-29
A21180 | Structral steel GA and details Field Supports SF8300_IFR | 02-Feb-26 A | 01-Mar-26 A | 2026-07-30 | 2026-07-30 | 2026-02-27 | 2026-03-09
A50040 | Structral steel GA and details Field Supports SF8300_RCC | 01-Mar-26 A | 03-Mar-26 A | 2026-07-30 | 2026-07-30 | 2026-03-09 | 2026-03-30
A50050 | Structral steel GA and details Field Supports SF8300_IFA | 02-Mar-26 A | 10-Mar-26 A | 2026-07-30 | 2026-07-30 | 2026-03-31 | 2026-04-03
A50060 | Structral steel GA and details Field Supports SF8300_RCA | 01-Mar-26 A | 11-Mar-26 A | 2026-08-26 | 2026-08-26 | 2026-04-03 | 2026-04-27
A50070 | Structral steel GA and details Field Supports SF8300_IFD/IFC | 04-Mar-26 A | 20-Mar-26 A | 2026-08-26 | 2026-08-26 | 2026-04-27 | 2026-04-29
DesignCalculationReportforstructuralsteelFieldSupportsSF8300 |  | 01-Mar-26 A | 20-Mar-26 A | 2026-07-30 | 2027-03-23 | 2026-02-27 | 2026-04-29
A21230 | Design Calculation Report for structural steel Field Supports SF8300_IFR | 01-Mar-26 A | 06-Mar-26 A | 2026-07-30 | 2026-07-30 | 2026-02-27 | 2026-03-09
A21240 | Design Calculation Report for structural steel Field Supports SF8300_RCC | 06-Mar-26 A | 13-Mar-26 A | 2027-03-23 | 2027-03-23 | 2026-03-09 | 2026-03-30
A21250 | Design Calculation Report for structural steel Field Supports SF8300_IFA | 10-Mar-26 A | 12-Mar-26 A | 2027-03-23 | 2027-03-23 | 2026-03-31 | 2026-04-03
A21260 | Design Calculation Report for structural steel Field Supports SF8300_RCA | 11-Mar-26 A | 18-Mar-26 A | 2027-03-23 | 2027-03-23 | 2026-04-03 | 2026-04-27
A50080 | Design Calculation Report for structural steel Field Supports SF8300_IFD/IFC | 18-Mar-26 A | 20-Mar-26 A | 2027-03-23 | 2027-03-23 | 2026-04-27 | 2026-04-29
DesignCalculationReportforFoundationsFieldSupportsSF8300 |  | 20-Dec-25 A | 2026-06-22 | 2027-02-22 | 2027-03-23 | 20-Dec-25 A | 2026-05-04
A21330 | Design Calculation Report for Foundations Field Supports SF8300_IFR | 20-Dec-25 A | 01-Jan-26 A | 2027-02-22 | 2027-02-22 | 20-Dec-25 A | 01-Jan-26 A
A21340 | Design Calculation Report for Foundations Field Supports SF8300_RCC | 01-Jan-26 A | 16-Jan-26 A | 2027-02-22 | 2027-02-22 | 01-Jan-26 A | 16-Jan-26 A
A50120 | Design Calculation Report for Foundations Field Supports SF8300_IFA | 2026-05-21 | 2026-05-27 | 2027-02-22 | 2027-02-25 | 2026-04-03 | 2026-04-08
A50130 | Design Calculation Report for Foundations Field Supports SF8300_RCA | 2026-05-27 | 2026-06-17 | 2027-02-26 | 2027-03-19 | 2026-04-08 | 2026-04-30
A50140 | Design Calculation Report for Foundations Field Supports SF8300_IFD/IFC | 2026-06-17 | 2026-06-22 | 2027-03-19 | 2027-03-23 | 2026-04-30 | 2026-05-04
FoundationLayout,SectionanddetailsFieldSupportsSF8300 |  | 20-Dec-25 A | 2026-06-22 | 2027-02-22 | 2027-03-23 | 20-Dec-25 A | 2026-05-04
A21310 | Foundation Layout, Section and details Field Supports SF8300_RCA | 2026-05-27 | 2026-06-17 | 2027-02-26 | 2027-03-19 | 2026-04-08 | 2026-04-30
A21320 | Foundation Layout, Section and details Field Supports SF8300_IFD/IFC | 2026-06-17 | 2026-06-22 | 2027-03-19 | 2027-03-23 | 2026-04-30 | 2026-05-04
A50090 | Foundation Layout, Section and details Field Supports SF8300_IFR | 20-Dec-25 A | 01-Jan-26 A | 2027-02-22 | 2027-02-22 | 20-Dec-25 A | 01-Jan-26 A
A50100 | Foundation Layout, Section and details Field Supports SF8300_RCC | 01-Jan-26 A | 15-Jan-26 A | 2027-02-22 | 2027-02-22 | 01-Jan-26 A | 15-Jan-26 A
A50110 | Foundation Layout, Section and details Field Supports SF8300_IFA | 2026-05-21 | 2026-05-27 | 2027-02-22 | 2027-02-25 | 2026-04-03 | 2026-04-08
StructralsteelGAanddetailsFieldSupportsSF8100 |  | 20-Dec-25 A | 2026-06-22 | 2026-07-30 | 2026-08-28 | 20-Dec-25 A | 2026-05-04
A20780 | Structral steel GA and details Field Supports SF8100_IFR | 20-Dec-25 A | 12-Jan-26 A | 2026-07-30 | 2026-07-30 | 20-Dec-25 A | 12-Jan-26 A
A49900 | Structral steel GA and details Field Supports SF8100_RCC | 12-Jan-26 A | 15-Jan-26 A | 2026-07-30 | 2026-07-30 | 12-Jan-26 A | 15-Jan-26 A
A49910 | Structral steel GA and details Field Supports SF8100_IFA | 2026-05-21 | 2026-05-27 | 2026-07-30 | 2026-08-04 | 2026-04-03 | 2026-04-08
A49920 | Structral steel GA and details Field Supports SF8100_RCA | 2026-05-27 | 2026-06-17 | 2026-08-05 | 2026-08-26 | 2026-04-08 | 2026-04-30
A49930 | Structral steel GA and details Field Supports SF8100_IFD/IFC | 2026-06-17 | 2026-06-22 | 2026-08-26 | 2026-08-28 | 2026-04-30 | 2026-05-04
DesignCalculationReportforstructuralsteelFieldSupportsSF8100 |  | 20-Dec-25 A | 2026-06-22 | 2027-02-22 | 2027-03-23 | 20-Dec-25 A | 2026-05-04
A20830 | Design Calculation Report for structural steel Field Supports SF8100_IFR | 20-Dec-25 A | 12-Jan-26 A | 2027-02-22 | 2027-02-22 | 20-Dec-25 A | 12-Jan-26 A
A20840 | Design Calculation Report for structural steel Field Supports SF8100_RCC | 12-Jan-26 A | 15-Jan-26 A | 2027-02-22 | 2027-02-22 | 12-Jan-26 A | 15-Jan-26 A
A20850 | Design Calculation Report for structural steel Field Supports SF8100_IFA | 01-Mar-26 A | 20-Mar-26 A | 2027-02-22 | 2027-02-22 | 2026-04-03 | 2026-04-08
A20860 | Design Calculation Report for structural steel Field Supports SF8100_RCA | 2026-05-27 | 2026-06-17 | 2027-02-26 | 2027-03-19 | 2026-04-08 | 2026-04-30
A20870 | Design Calculation Report for structural steel Field Supports SF8100_IFD/IFC | 2026-06-17 | 2026-06-22 | 2027-03-19 | 2027-03-23 | 2026-04-30 | 2026-05-04
DesignCalculationReportforFoundationsFieldSupportsSF8100 |  | 20-Dec-25 A | 2026-06-23 | 2027-02-22 | 2027-03-23 | 20-Dec-25 A | 2026-05-08
A20930 | Design Calculation Report for Foundations Field Supports SF8100_IFR | 20-Dec-25 A | 01-Jan-26 A | 2027-02-22 | 2027-02-22 | 20-Dec-25 A | 01-Jan-26 A
A20940 | Design Calculation Report for Foundations Field Supports SF8100_RCC | 01-Jan-26 A | 15-Jan-26 A | 2027-02-22 | 2027-02-22 | 01-Jan-26 A | 15-Jan-26 A
A20970 | Design Calculation Report for Foundations Field Supports SF8100_IFD/IFC | 13-Apr-26 A | 17-Apr-26 A | 2027-03-23 | 2027-03-23 | 2026-05-05 | 2026-05-08
A49940 | Design Calculation Report for Foundations Field Supports SF8100_IFA | 2026-05-27 | 2026-06-01 | 2027-02-22 | 2027-02-25 | 2026-04-08 | 2026-04-14
A49950 | Design Calculation Report for Foundations Field Supports SF8100_RCA | 2026-06-01 | 2026-06-23 | 2027-03-02 | 2027-03-23 | 2026-04-14 | 2026-05-05
FoundationLayout,SectionanddetailsFieldSupportsSF8100 |  | 20-Dec-25 A | 2026-06-25 | 2027-02-26 | 2027-03-23 | 20-Dec-25 A | 2026-05-08
A20880 | Foundation Layout, Section and details Field Supports SF8100_IFR | 20-Dec-25 A | 01-Jan-26 A | 2027-02-26 | 2027-02-26 | 20-Dec-25 A | 01-Jan-26 A
A20890 | Foundation Layout, Section and details Field Supports SF8100_RCC | 01-Jan-26 A | 15-Jan-26 A | 2027-02-26 | 2027-02-26 | 01-Jan-26 A | 15-Jan-26 A
A20900 | Foundation Layout, Section and details Field Supports SF8100_IFA | 10-Apr-26 A | 17-Apr-26 A | 2027-02-26 | 2027-02-26 | 2026-04-08 | 2026-04-14
A20910 | Foundation Layout, Section and details Field Supports SF8100_RCA | 2026-06-01 | 2026-06-23 | 2027-02-26 | 2027-03-19 | 2026-04-14 | 2026-05-05
A20920 | Foundation Layout, Section and details Field Supports SF8100_IFD/IFC | 2026-06-23 | 2026-06-25 | 2027-03-19 | 2027-03-23 | 2026-05-05 | 2026-05-08
AdequacycheckofPiperackSR70 |  | 01-Apr-26 A | 16-Apr-26 A | 2026-06-23 | 2026-08-24 | 2026-02-20 | 2026-04-21
A22130 | Adequacy check of Pipe rack SR70_IFR | 01-Apr-26 A | 03-Apr-26 A | 2026-06-23 | 2026-06-23 | 2026-02-20 | 2026-02-27
A22140 | Adequacy check of Pipe rack SR70_RCC | 10-Apr-26 A | 13-Apr-26 A | 2026-07-27 | 2026-07-27 | 2026-02-27 | 2026-03-23
A50610 | Adequacy check of Pipe rack SR70_IFA | 06-Apr-26 A | 09-Apr-26 A | 2026-07-27 | 2026-07-27 | 2026-03-23 | 2026-03-26
A50620 | Adequacy check of Pipe rack SR70_RCA | 10-Apr-26 A | 13-Apr-26 A | 2026-08-24 | 2026-08-24 | 2026-03-26 | 2026-04-17
A50630 | Adequacy check of Pipe rack SR70_IFD/IFC | 13-Apr-26 A | 16-Apr-26 A | 2026-08-24 | 2026-08-24 | 2026-04-17 | 2026-04-21
StructuralGAandDetails,PipeRackSR70 |  | 2026-04-17 | 2026-06-16 | 2026-07-01 | 2026-08-28 | 2026-02-27 | 2026-04-29
A22120 | Structural GA and Details, Pipe Rack SR70_IFD/IFC | 2026-06-12 | 2026-06-16 | 2026-08-26 | 2026-08-28 | 2026-04-27 | 2026-04-29
A50570 | Structural GA and Details, Pipe Rack SR70_IFR | 2026-04-17 | 2026-04-24 | 2026-07-01 | 2026-07-08 | 2026-02-27 | 2026-03-09
A50580 | Structural GA and Details, Pipe Rack SR70_RCC | 2026-04-24 | 2026-05-18 | 2026-07-08 | 2026-07-30 | 2026-03-09 | 2026-03-30
A50590 | Structural GA and Details, Pipe Rack SR70_IFA | 2026-05-18 | 2026-05-21 | 2026-07-30 | 2026-08-04 | 2026-03-31 | 2026-04-03
A50600 | Structural GA and Details, Pipe Rack SR70_RCA | 2026-05-21 | 2026-06-12 | 2026-08-05 | 2026-08-26 | 2026-04-03 | 2026-04-27
AdequacycheckofPiperackSR73 |  | 01-Apr-26 A | 16-Apr-26 A | 2026-06-23 | 2026-08-24 | 2026-02-27 | 2026-04-29
A22240 | Adequacy check of Pipe rack SR73_RCC | 03-Apr-26 A | 07-Apr-26 A | 2026-07-27 | 2026-07-27 | 2026-03-09 | 2026-03-30
A22250 | Adequacy check of Pipe rack SR73_IFA | 08-Apr-26 A | 10-Apr-26 A | 2026-07-27 | 2026-07-27 | 2026-03-31 | 2026-04-03
A22260 | Adequacy check of Pipe rack SR73_RCA | 13-Apr-26 A | 16-Apr-26 A | 2026-08-24 | 2026-08-24 | 2026-04-03 | 2026-04-27
A50660 | Adequacy check of Pipe rack SR73_IFR | 01-Apr-26 A | 03-Apr-26 A | 2026-06-23 | 2026-06-23 | 2026-02-27 | 2026-03-09
A50670 | Adequacy check of Pipe rack SR73_IFD/IFC | 10-Apr-26 A | 13-Apr-26 A | 2026-08-24 | 2026-08-24 | 2026-04-27 | 2026-04-29
StructuralGAandDetails,PipeRackSR73 |  | 2026-04-17 | 2026-04-23 | 2026-08-24 | 2026-08-28 | 2026-03-16 | 2026-05-14
A22180 | Structural GA and Details, Pipe Rack SR73_IFR | 2026-04-17 | 2026-04-17 | 2026-08-24 | 2026-08-24 | 2026-03-16 | 2026-03-24
A22190 | Structural GA and Details, Pipe Rack SR73_RCC | 2026-04-20 | 2026-04-20 | 2026-08-25 | 2026-08-25 | 2026-03-24 | 2026-04-15
A22200 | Structural GA and Details, Pipe Rack SR73_IFA | 2026-04-21 | 2026-04-21 | 2026-08-26 | 2026-08-26 | 2026-04-15 | 2026-04-20
A50640 | Structural GA and Details, Pipe Rack SR73_RCA | 2026-04-22 | 2026-04-22 | 2026-08-27 | 2026-08-27 | 2026-04-20 | 2026-05-12
A50650 | Structural GA and Details, Pipe Rack SR73_IFD/IFC | 2026-04-23 | 2026-04-23 | 2026-08-28 | 2026-08-28 | 2026-05-12 | 2026-05-14
AdequacycheckofU&ORackSR37 |  | 2026-04-17 | 2026-06-16 | 2026-06-23 | 2026-08-26 | 2026-03-09 | 2026-05-06
A22360 | Adequacy check of U&O Rack SR37_RCA | 2026-05-21 | 2026-06-12 | 2026-07-31 | 2026-08-24 | 2026-04-13 | 2026-05-04
A22370 | Adequacy check of U&O Rack SR37_IFD/IFC | 2026-06-12 | 2026-06-16 | 2026-08-24 | 2026-08-26 | 2026-05-04 | 2026-05-06
A50700 | Adequacy check of U&O Rack SR37_IFR | 2026-04-17 | 2026-04-24 | 2026-06-23 | 2026-07-01 | 2026-03-09 | 2026-03-16
A50710 | Adequacy check of U&O Rack SR37_RCC | 2026-04-24 | 2026-05-18 | 2026-07-03 | 2026-07-27 | 2026-03-16 | 2026-04-07
A50720 | Adequacy check of U&O Rack SR37_IFA | 2026-05-18 | 2026-05-21 | 2026-07-27 | 2026-07-30 | 2026-04-07 | 2026-04-10
StructuralGAandDetails,U&ORackSR37 |  | 2026-04-24 | 2026-06-24 | 2026-07-01 | 2026-08-28 | 2026-03-16 | 2026-05-14
A22300 | Structural GA and Details, U&O Rack SR37_IFA | 2026-05-26 | 2026-05-29 | 2026-07-30 | 2026-08-04 | 2026-04-15 | 2026-04-20
A22310 | Structural GA and Details, U&O Rack SR37_RCA | 2026-05-29 | 2026-06-22 | 2026-08-05 | 2026-08-26 | 2026-04-20 | 2026-05-12
A22320 | Structural GA and Details, U&O Rack SR37_IFD/IFC | 2026-06-22 | 2026-06-24 | 2026-08-26 | 2026-08-28 | 2026-05-12 | 2026-05-14
A50680 | Structural GA and Details, U&O Rack SR37_IFR | 2026-04-24 | 2026-05-04 | 2026-07-01 | 2026-07-08 | 2026-03-16 | 2026-03-24
A50690 | Structural GA and Details, U&O Rack SR37_RCC | 2026-05-04 | 2026-05-25 | 2026-07-08 | 2026-07-30 | 2026-03-24 | 2026-04-15
Structure&Foundationdesign-Mechanical |  | 10-Apr-25 A | 2026-05-18 | 2026-06-15 | 2027-03-23 | 10-Apr-25 A | 2026-03-23
FoundationDrawing-LubeOilunitforPSA-2FeedGasCompressor |  | 12-Apr-25 A | 23-Dec-25 A | 2027-01-01 | 2027-01-01 | 12-Apr-25 A | 23-Dec-25 A
A18980 | Foundation Drawing- Lube Oil unit for PSA-2 FeedGas Compressor_IFR | 12-Apr-25 A | 03-May-25 A | 2027-01-01 | 2027-01-01 | 12-Apr-25 A | 03-May-25 A
A18990 | Foundation Drawing- Lube Oil unit for PSA-2 FeedGas Compressor_RCC | 04-May-25 A | 10-May-25 A | 2027-01-01 | 2027-01-01 | 04-May-25 A | 10-May-25 A
A19000 | Foundation Drawing- Lube Oil unit for PSA-2 FeedGas Compressor_IFA | 11-May-25 A | 21-Jun-25 A | 2027-01-01 | 2027-01-01 | 11-May-25 A | 21-Jun-25 A
A19010 | Foundation Drawing- Lube Oil unit for PSA-2 FeedGas Compressor_RCA | 27-Jun-25 A | 15-Aug-25 A | 2027-01-01 | 2027-01-01 | 27-Jun-25 A | 15-Aug-25 A
A19020 | Foundation Drawing- Lube Oil unit for PSA-2 FeedGas Compressor_IFD/IFC | 19-Dec-25 A | 23-Dec-25 A | 2027-01-01 | 2027-01-01 | 19-Dec-25 A | 23-Dec-25 A
DesignCalculationreportforfoundationofLubeOilunitforPSA-2FeedGasCompressor |  | 13-Apr-25 A | 23-Dec-25 A | 2027-03-23 | 2027-03-23 | 13-Apr-25 A | 23-Dec-25 A
A19030 | Design Calculation report for foundation of Lube Oil unit for PSA-2 FeedGas Compressor_IFR | 13-Apr-25 A | 03-May-25 A | 2027-03-23 | 2027-03-23 | 13-Apr-25 A | 03-May-25 A
A19040 | Design Calculation report for foundation of Lube Oil unit for PSA-2 FeedGas Compressor_RCC | 04-May-25 A | 10-May-25 A | 2027-03-23 | 2027-03-23 | 04-May-25 A | 10-May-25 A
A19050 | Design Calculation report for foundation of Lube Oil unit for PSA-2 FeedGas Compressor_IFA | 11-May-25 A | 21-Jun-25 A | 2027-03-23 | 2027-03-23 | 11-May-25 A | 21-Jun-25 A
A19060 | Design Calculation report for foundation of Lube Oil unit for PSA-2 FeedGas Compressor_RCA | 27-Jun-25 A | 15-Aug-25 A | 2027-03-23 | 2027-03-23 | 27-Jun-25 A | 15-Aug-25 A
A19070 | Design Calculation report for foundation of Lube Oil unit for PSA-2 FeedGas Compressor_IFD/IFC | 19-Dec-25 A | 23-Dec-25 A | 2027-03-23 | 2027-03-23 | 19-Dec-25 A | 23-Dec-25 A
FoundationDrawing-LubeOilunitforPSA-2OffGasCompressor |  | 26-May-25 A | 23-Dec-25 A | 2027-01-01 | 2027-01-01 | 26-May-25 A | 23-Dec-25 A
A19080 | Foundation Drawing- Lube Oil unit for PSA-2 OffGas Compressor_IFR | 26-May-25 A | 05-Jul-25 A | 2027-01-01 | 2027-01-01 | 26-May-25 A | 05-Jul-25 A
A19090 | Foundation Drawing- Lube Oil unit for PSA-2 OffGas Compressor_RCC | 07-Jul-25 A | 01-Aug-25 A | 2027-01-01 | 2027-01-01 | 07-Jul-25 A | 01-Aug-25 A
A19100 | Foundation Drawing- Lube Oil unit for PSA-2 OffGas Compressor_IFA | 04-Aug-25 A | 08-Aug-25 A | 2027-01-01 | 2027-01-01 | 04-Aug-25 A | 08-Aug-25 A
A49150 | Foundation Drawing- Lube Oil unit for PSA-2 OffGas Compressor_RCA | 07-Aug-25 A | 15-Aug-25 A | 2027-01-01 | 2027-01-01 | 07-Aug-25 A | 15-Aug-25 A
A49160 | Foundation Drawing- Lube Oil unit for PSA-2 OffGas Compressor_IFD/IFC | 19-Dec-25 A | 23-Dec-25 A | 2027-01-01 | 2027-01-01 | 19-Dec-25 A | 23-Dec-25 A
DesignCalculationreportforfoundationofLubeOilunitforPSA-2OffGasCompressor |  | 26-May-25 A | 23-Dec-25 A | 2027-03-23 | 2027-03-23 | 26-May-25 A | 23-Dec-25 A
A19140 | Design Calculation report for foundation of Lube Oil unit for PSA-2 OffGas Compressor_RCC | 07-Jul-25 A | 01-Aug-25 A | 2027-03-23 | 2027-03-23 | 07-Jul-25 A | 01-Aug-25 A
A19150 | Design Calculation report for foundation of Lube Oil unit for PSA-2 OffGas Compressor_IFA | 04-Aug-25 A | 08-Aug-25 A | 2027-03-23 | 2027-03-23 | 04-Aug-25 A | 08-Aug-25 A
A19160 | Design Calculation report for foundation of Lube Oil unit for PSA-2 OffGas Compressor_RCA | 07-Aug-25 A | 15-Aug-25 A | 2027-03-23 | 2027-03-23 | 07-Aug-25 A | 15-Aug-25 A
A49170 | Design Calculation report for foundation of Lube Oil unit for PSA-2 OffGas Compressor_IFR | 26-May-25 A | 05-Jul-25 A | 2027-03-23 | 2027-03-23 | 26-May-25 A | 05-Jul-25 A
A49180 | Design Calculation report for foundation of Lube Oil unit for PSA-2 OffGas Compressor_IFD/IFC | 19-Dec-25 A | 23-Dec-25 A | 2027-03-23 | 2027-03-23 | 19-Dec-25 A | 23-Dec-25 A
FoundationdrawingPSA-2FeedGasCompressor13-KC-701 |  | 19-Jul-25 A | 20-Mar-26 A | 2026-06-15 | 2027-01-01 | 19-Jul-25 A | 2026-03-17
A18800 | Foundation drawing PSA-2 FeedGas Compressor 13-KC-701_IFA | 01-Sep-25 A | 05-Sep-25 A | 2027-01-01 | 2027-01-01 | 01-Sep-25 A | 05-Sep-25 A
A49020 | Foundation drawing PSA-2 FeedGas Compressor 13-KC-701_IFR | 19-Jul-25 A | 22-Aug-25 A | 2026-06-15 | 2026-06-15 | 19-Jul-25 A | 22-Aug-25 A
A49030 | Foundation drawing PSA-2 FeedGas Compressor 13-KC-701_RCC | 01-Aug-25 A | 29-Aug-25 A | 2027-01-01 | 2027-01-01 | 01-Aug-25 A | 29-Aug-25 A
A49040 | Foundation drawing PSA-2 FeedGas Compressor 13-KC-701_RCA | 09-Mar-26 A | 18-Mar-26 A | 2027-01-01 | 2027-01-01 | 2026-02-20 | 2026-03-13
A49050 | Foundation drawing PSA-2 FeedGas Compressor 13-KC-701_IFD/IFC | 11-Mar-26 A | 20-Mar-26 A | 2027-01-01 | 2027-01-01 | 2026-03-13 | 2026-03-17
DesignCalculationReportPSA-2FeedGasCompressor13-KC-701 |  | 12-Apr-25 A | 13-Jan-26 A | 2027-03-23 | 2027-03-23 | 12-Apr-25 A | 13-Jan-26 A
A49060 | Design Calculation Report PSA-2 FeedGas Compressor 13-KC-701_IFR | 12-Apr-25 A | 27-Jul-25 A | 2027-03-23 | 2027-03-23 | 12-Apr-25 A | 27-Jul-25 A
A49070 | Design Calculation Report PSA-2 FeedGas Compressor 13-KC-701_RCC | 28-Jul-25 A | 15-Aug-25 A | 2027-03-23 | 2027-03-23 | 28-Jul-25 A | 15-Aug-25 A
A49080 | Design Calculation Report PSA-2 FeedGas Compressor 13-KC-701_IFA | 18-Aug-25 A | 22-Aug-25 A | 2027-03-23 | 2027-03-23 | 18-Aug-25 A | 22-Aug-25 A
A49090 | Design Calculation Report PSA-2 FeedGas Compressor 13-KC-701_RCA | 19-Aug-25 A | 29-Aug-25 A | 2027-03-23 | 2027-03-23 | 19-Aug-25 A | 29-Aug-25 A
A49100 | Design Calculation Report PSA-2 FeedGas Compressor 13-KC-701_IFD/IFC | 09-Jan-26 A | 13-Jan-26 A | 2027-03-23 | 2027-03-23 | 09-Jan-26 A | 13-Jan-26 A
FoundationdrawingPSA-2OffGasCompressor13-KC-702 |  | 30-Jun-25 A | 05-Sep-25 A | 2026-06-15 | 2026-06-15 | 30-Jun-25 A | 05-Sep-25 A
A18880 | Foundation drawing PSA-2 OffGas Compressor 13-KC-702_IFR | 30-Jun-25 A | 10-Jul-25 A | 2026-06-15 | 2026-06-15 | 30-Jun-25 A | 10-Jul-25 A
A49110 | Foundation drawing PSA-2 OffGas Compressor 13-KC-702_RCC | 11-Jul-25 A | 15-Aug-25 A | 2026-06-15 | 2026-06-15 | 11-Jul-25 A | 15-Aug-25 A
A49120 | Foundation drawing PSA-2 OffGas Compressor 13-KC-702_IFA | 16-Aug-25 A | 22-Aug-25 A | 2026-06-15 | 2026-06-15 | 16-Aug-25 A | 22-Aug-25 A
A49130 | Foundation drawing PSA-2 OffGas Compressor 13-KC-702_RCA | 23-Aug-25 A | 29-Aug-25 A | 2026-06-15 | 2026-06-15 | 23-Aug-25 A | 29-Aug-25 A
A49140 | Foundation drawing PSA-2 OffGas Compressor 13-KC-702_IFD/IFC | 30-Aug-25 A | 05-Sep-25 A | 2026-06-15 | 2026-06-15 | 30-Aug-25 A | 05-Sep-25 A
DesignCalculationReportPSA-2OffGasCompressor13-KC-702 |  | 01-Sep-25 A | 2026-04-21 | 2027-03-19 | 2027-03-23 | 01-Sep-25 A | 2026-02-24
A18930 | Design Calculation Report PSA-2 OffGas Compressor 13-KC-702_IFR | 01-Sep-25 A | 13-Sep-25 A | 2027-03-19 | 2027-03-19 | 01-Sep-25 A | 13-Sep-25 A
A18940 | Design Calculation Report PSA-2 OffGas Compressor 13-KC-702_RCC | 05-Sep-25 A | 20-Sep-25 A | 2027-03-19 | 2027-03-19 | 05-Sep-25 A | 20-Sep-25 A
A18950 | Design Calculation Report PSA-2 OffGas Compressor 13-KC-702_IFA | 22-Sep-25 A | 26-Sep-25 A | 2027-03-19 | 2027-03-19 | 22-Sep-25 A | 26-Sep-25 A
A18960 | Design Calculation Report PSA-2 OffGas Compressor 13-KC-702_RCA | 24-Sep-25 A | 04-Oct-25 A | 2027-03-19 | 2027-03-19 | 24-Sep-25 A | 04-Oct-25 A
A18970 | Design Calculation Report PSA-2 OffGas Compressor 13-KC-702_IFD/IFC | 2026-04-17 | 2026-04-21 | 2027-03-19 | 2027-03-23 | 2026-02-20 | 2026-02-24
FoundationDrawingPSA-2Unit-HydrogenPurification13-XA-710 |  | 05-May-25 A | 10-Jul-25 A | 2027-01-01 | 2027-01-01 | 05-May-25 A | 10-Jul-25 A
A20200 | Foundation Drawing PSA-2 Unit - Hydrogen Purification 13-XA-710_IFA | 22-May-25 A | 28-May-25 A | 2027-01-01 | 2027-01-01 | 22-May-25 A | 28-May-25 A
A20210 | Foundation Drawing PSA-2 Unit - Hydrogen Purification 13-XA-710_RCA | 21-May-25 A | 04-Jun-25 A | 2027-01-01 | 2027-01-01 | 21-May-25 A | 04-Jun-25 A
A20220 | Foundation Drawing PSA-2 Unit - Hydrogen Purification 13-XA-710_IFD/IFC | 09-Jun-25 A | 10-Jul-25 A | 2027-01-01 | 2027-01-01 | 09-Jun-25 A | 10-Jul-25 A
A49600 | Foundation Drawing PSA-2 Unit - Hydrogen Purification 13-XA-710_IFR | 05-May-25 A | 14-May-25 A | 2027-01-01 | 2027-01-01 | 05-May-25 A | 14-May-25 A
A49610 | Foundation Drawing PSA-2 Unit - Hydrogen Purification 13-XA-710_RCC | 08-May-25 A | 21-May-25 A | 2027-01-01 | 2027-01-01 | 08-May-25 A | 21-May-25 A
DesignCalculationReportforfoundationofPSA-2Unit-HydrogenPurification13-XA-710 |  | 26-May-25 A | 05-Sep-25 A | 2027-03-23 | 2027-03-23 | 26-May-25 A | 05-Sep-25 A
A20260 | Design Calculation Report for foundation of PSA-2 Unit - Hydrogen Purification 13-XA-710_RCA | 11-Aug-25 A | 29-Aug-25 A | 2027-03-23 | 2027-03-23 | 11-Aug-25 A | 29-Aug-25 A
A20270 | Design Calculation Report for foundation of PSA-2 Unit - Hydrogen Purification 13-XA-710_IFD/IFC | 01-Sep-25 A | 05-Sep-25 A | 2027-03-23 | 2027-03-23 | 01-Sep-25 A | 05-Sep-25 A
A49620 | Design Calculation Report for foundation of PSA-2 Unit - Hydrogen Purification 13-XA-710_IFR | 26-May-25 A | 07-Jul-25 A | 2027-03-23 | 2027-03-23 | 26-May-25 A | 07-Jul-25 A
A49630 | Design Calculation Report for foundation of PSA-2 Unit - Hydrogen Purification 13-XA-710_RCC | 08-Jul-25 A | 15-Aug-25 A | 2027-03-23 | 2027-03-23 | 08-Jul-25 A | 15-Aug-25 A
A49640 | Design Calculation Report for foundation of PSA-2 Unit - Hydrogen Purification 13-XA-710_IFA | 18-Aug-25 A | 22-Aug-25 A | 2027-03-23 | 2027-03-23 | 18-Aug-25 A | 22-Aug-25 A
FoundationdrawingforEquipment50-HE-1410 |  | 02-May-25 A | 20-Mar-26 A | 2026-06-25 | 2027-01-01 | 02-May-25 A | 2026-02-24
A50340 | Foundation drawing for Equipment 50-HE-1410_IFR | 02-May-25 A | 23-May-25 A | 2026-06-25 | 2026-06-25 | 02-May-25 A | 23-May-25 A
A50350 | Foundation drawing for Equipment 50-HE-1410_RCC | 24-May-25 A | 29-May-25 A | 2027-01-01 | 2027-01-01 | 24-May-25 A | 29-May-25 A
A50360 | Foundation drawing for Equipment 50-HE-1410_IFA | 01-Aug-25 A | 22-Aug-25 A | 2027-01-01 | 2027-01-01 | 01-Aug-25 A | 22-Aug-25 A
A50370 | Foundation drawing for Equipment 50-HE-1410_RCA | 11-Aug-25 A | 29-Aug-25 A | 2027-01-01 | 2027-01-01 | 11-Aug-25 A | 29-Aug-25 A
A50380 | Foundation drawing for Equipment 50-HE-1410_IFD/IFC | 17-Mar-26 A | 20-Mar-26 A | 2027-01-01 | 2027-01-01 | 2026-02-20 | 2026-02-24
DesigncalculationforfoundationofEquipment50-HE-1410 |  | 02-May-25 A | 23-Dec-25 A | 2027-03-23 | 2027-03-23 | 02-May-25 A | 23-Dec-25 A
A21870 | Design calculation for foundation of Equipment 50-HE-1410_IFD/IFC | 19-Dec-25 A | 23-Dec-25 A | 2027-03-23 | 2027-03-23 | 19-Dec-25 A | 23-Dec-25 A
A50390 | Design calculation for foundation of Equipment 50-HE-1410_IFR | 02-May-25 A | 23-May-25 A | 2027-03-23 | 2027-03-23 | 02-May-25 A | 23-May-25 A
A50400 | Design calculation for foundation of Equipment 50-HE-1410_RCC | 24-May-25 A | 21-Jun-25 A | 2027-03-23 | 2027-03-23 | 24-May-25 A | 21-Jun-25 A
A50410 | Design calculation for foundation of Equipment 50-HE-1410_IFA | 15-Jul-25 A | 22-Aug-25 A | 2027-03-23 | 2027-03-23 | 15-Jul-25 A | 22-Aug-25 A
A50420 | Design calculation for foundation of Equipment 50-HE-1410_RCA | 29-Sep-25 A | 24-Oct-25 A | 2027-03-23 | 2027-03-23 | 29-Sep-25 A | 24-Oct-25 A
FoundationDrawingPSA-2OffGasCompressorInterstageCooler13-HE-708 |  | 01-May-25 A | 10-Oct-25 A | 2026-06-25 | 2026-06-25 | 01-May-25 A | 10-Oct-25 A
A20080 | Foundation Drawing PSA-2 OffGas Compressor Interstage Cooler 13-HE-708_IFR | 01-May-25 A | 15-May-25 A | 2026-06-25 | 2026-06-25 | 01-May-25 A | 15-May-25 A
A20090 | Foundation Drawing PSA-2 OffGas Compressor Interstage Cooler 13-HE-708_RCC | 16-May-25 A | 22-May-25 A | 2026-06-25 | 2026-06-25 | 16-May-25 A | 22-May-25 A
A20100 | Foundation Drawing PSA-2 OffGas Compressor Interstage Cooler 13-HE-708_IFA | 23-May-25 A | 21-Jun-25 A | 2026-06-25 | 2026-06-25 | 23-May-25 A | 21-Jun-25 A
A49560 | Foundation Drawing PSA-2 OffGas Compressor Interstage Cooler 13-HE-708_RCA | 01-Aug-25 A | 21-Aug-25 A | 2026-06-25 | 2026-06-25 | 01-Aug-25 A | 21-Aug-25 A
A49570 | Foundation Drawing PSA-2 OffGas Compressor Interstage Cooler 13-HE-708_IFD/IFC | 26-Sep-25 A | 10-Oct-25 A | 2026-06-25 | 2026-06-25 | 26-Sep-25 A | 10-Oct-25 A
DesignCalculationReportforfoundationofPSA-2OffGasCompressorInterstageCooler13-HE-708 |  | 28-Apr-25 A | 10-Oct-25 A | 2027-03-23 | 2027-03-23 | 28-Apr-25 A | 10-Oct-25 A
A20140 | Design Calculation Report for foundation of PSA-2 OffGas Compressor Interstage Cooler 13-HE-708_RCC | 20-May-25 A | 21-Jun-25 A | 2027-03-23 | 2027-03-23 | 20-May-25 A | 21-Jun-25 A
A20150 | Design Calculation Report for foundation of PSA-2 OffGas Compressor Interstage Cooler 13-HE-708_IFA | 22-Jun-25 A | 28-Jun-25 A | 2027-03-23 | 2027-03-23 | 22-Jun-25 A | 28-Jun-25 A
A20160 | Design Calculation Report for foundation of PSA-2 OffGas Compressor Interstage Cooler 13-HE-708_RCA | 21-Jul-25 A | 21-Aug-25 A | 2027-03-23 | 2027-03-23 | 21-Jul-25 A | 21-Aug-25 A
A49580 | Design Calculation Report for foundation of PSA-2 OffGas Compressor Interstage Cooler 13-HE-708_IFR | 28-Apr-25 A | 19-May-25 A | 2027-03-23 | 2027-03-23 | 28-Apr-25 A | 19-May-25 A
A49590 | Design Calculation Report for foundation of PSA-2 OffGas Compressor Interstage Cooler 13-HE-708_IFD/IFC | 22-Sep-25 A | 10-Oct-25 A | 2027-03-23 | 2027-03-23 | 22-Sep-25 A | 10-Oct-25 A
FoundationDrawingPSA-2FeedGasCompressorAfterCooler13-HE-704 |  | 28-Apr-25 A | 25-Jul-25 A | 2026-07-16 | 2026-08-09 | 28-Apr-25 A | 25-Jul-25 A
A19280 | Foundation Drawing PSA-2 Feed Gas Compressor AfterCooler 13-HE-704_IFR | 28-Apr-25 A | 19-May-25 A | 2026-07-16 | 2026-07-16 | 28-Apr-25 A | 19-May-25 A
A19290 | Foundation Drawing PSA-2 Feed Gas Compressor AfterCooler 13-HE-704_RCC | 20-May-25 A | 21-Jun-25 A | 2026-08-09 | 2026-08-09 | 20-May-25 A | 21-Jun-25 A
A19300 | Foundation Drawing PSA-2 Feed Gas Compressor AfterCooler 13-HE-704_IFA | 22-Jun-25 A | 28-Jun-25 A | 2026-08-09 | 2026-08-09 | 22-Jun-25 A | 28-Jun-25 A
A19310 | Foundation Drawing PSA-2 Feed Gas Compressor AfterCooler 13-HE-704_RCA | 30-Jun-25 A | 18-Jul-25 A | 2026-08-09 | 2026-08-09 | 30-Jun-25 A | 18-Jul-25 A
A19320 | Foundation Drawing PSA-2 Feed Gas Compressor AfterCooler 13-HE-704_IFD/IFC | 21-Jul-25 A | 25-Jul-25 A | 2026-08-09 | 2026-08-09 | 21-Jul-25 A | 25-Jul-25 A
DesignCalculationReportforfoundationofPSA-2FeedGasCompressorAfterCooler13-HE-704 |  | 28-Apr-25 A | 08-Sep-25 A | 2027-03-23 | 2027-03-23 | 28-Apr-25 A | 08-Sep-25 A
A19330 | Design Calculation Report for foundation of PSA-2 Feed Gas Compressor AfterCooler 13-HE-704_IFR | 28-Apr-25 A | 03-May-25 A | 2027-03-23 | 2027-03-23 | 28-Apr-25 A | 03-May-25 A
A19340 | Design Calculation Report for foundation of PSA-2 Feed Gas Compressor AfterCooler 13-HE-704_RCC | 04-May-25 A | 19-May-25 A | 2027-03-23 | 2027-03-23 | 04-May-25 A | 19-May-25 A
A49240 | Design Calculation Report for foundation of PSA-2 Feed Gas Compressor AfterCooler 13-HE-704_IFA | 20-May-25 A | 21-Jun-25 A | 2027-03-23 | 2027-03-23 | 20-May-25 A | 21-Jun-25 A
A49250 | Design Calculation Report for foundation of PSA-2 Feed Gas Compressor AfterCooler 13-HE-704_RCA | 22-Jun-25 A | 28-Jun-25 A | 2027-03-23 | 2027-03-23 | 22-Jun-25 A | 28-Jun-25 A
A49260 | Design Calculation Report for foundation of PSA-2 Feed Gas Compressor AfterCooler 13-HE-704_IFD/IFC | 29-Jun-25 A | 08-Sep-25 A | 2027-03-23 | 2027-03-23 | 29-Jun-25 A | 08-Sep-25 A
FoundationDrawingPSA-2FeedGasCompressorInterstageCooler13-HE-703 |  | 24-Apr-25 A | 15-Sep-25 A | 2026-07-16 | 2026-08-24 | 24-Apr-25 A | 15-Sep-25 A
A19500 | Foundation Drawing PSA-2 Feed Gas Compressor Interstage Cooler 13-HE-703_IFA | 23-May-25 A | 01-Sep-25 A | 2026-08-24 | 2026-08-24 | 23-May-25 A | 01-Sep-25 A
A19510 | Foundation Drawing PSA-2 Feed Gas Compressor Interstage Cooler 13-HE-703_RCA | 02-Sep-25 A | 08-Sep-25 A | 2026-08-24 | 2026-08-24 | 02-Sep-25 A | 08-Sep-25 A
A19520 | Foundation Drawing PSA-2 Feed Gas Compressor Interstage Cooler 13-HE-703_IFD/IFC | 09-Sep-25 A | 15-Sep-25 A | 2026-08-24 | 2026-08-24 | 09-Sep-25 A | 15-Sep-25 A
A49310 | Foundation Drawing PSA-2 Feed Gas Compressor Interstage Cooler 13-HE-703_IFR | 24-Apr-25 A | 15-May-25 A | 2026-07-16 | 2026-07-16 | 24-Apr-25 A | 15-May-25 A
A49320 | Foundation Drawing PSA-2 Feed Gas Compressor Interstage Cooler 13-HE-703_RCC | 16-May-25 A | 22-May-25 A | 2026-08-24 | 2026-08-24 | 16-May-25 A | 22-May-25 A
DesignCalculationReportforfoundationofPSA-2FeedGasCompressorInterstageCooler13-HE-703 |  | 24-Apr-25 A | 15-Sep-25 A | 2027-03-23 | 2027-03-23 | 24-Apr-25 A | 15-Sep-25 A
A19560 | Design Calculation Report for foundation of PSA-2 Feed Gas Compressor Interstage Cooler 13-HE-703_RCA | 02-Sep-25 A | 09-Sep-25 A | 2027-03-23 | 2027-03-23 | 02-Sep-25 A | 09-Sep-25 A
A19570 | Design Calculation Report for foundation of PSA-2 Feed Gas Compressor Interstage Cooler 13-HE-703_IFD/IFC | 10-Sep-25 A | 15-Sep-25 A | 2027-03-23 | 2027-03-23 | 10-Sep-25 A | 15-Sep-25 A
A49330 | Design Calculation Report for foundation of PSA-2 Feed Gas Compressor Interstage Cooler 13-HE-703_IFR | 24-Apr-25 A | 15-May-25 A | 2027-03-23 | 2027-03-23 | 24-Apr-25 A | 15-May-25 A
A49340 | Design Calculation Report for foundation of PSA-2 Feed Gas Compressor Interstage Cooler 13-HE-703_RCC | 16-May-25 A | 22-May-25 A | 2027-03-23 | 2027-03-23 | 16-May-25 A | 22-May-25 A
A49350 | Design Calculation Report for foundation of PSA-2 Feed Gas Compressor Interstage Cooler 13-HE-703_IFA | 23-May-25 A | 01-Sep-25 A | 2027-03-23 | 2027-03-23 | 23-May-25 A | 01-Sep-25 A
FoundationDrawingPSA-2OffGasCompressorAfterCooler13-HE-709 |  | 20-May-25 A | 10-Oct-25 A | 2026-07-16 | 2026-07-21 | 20-May-25 A | 10-Oct-25 A
A19790 | Foundation Drawing PSA-2 OffGas Compressor AfterCooler 13-HE-709_RCC | 20-May-25 A | 21-Jun-25 A | 2026-07-21 | 2026-07-21 | 20-May-25 A | 21-Jun-25 A
A19800 | Foundation Drawing PSA-2 OffGas Compressor AfterCooler 13-HE-709_IFA | 22-Jun-25 A | 28-Jun-25 A | 2026-07-21 | 2026-07-21 | 22-Jun-25 A | 28-Jun-25 A
A19810 | Foundation Drawing PSA-2 OffGas Compressor AfterCooler 13-HE-709_RCA | 30-Jun-25 A | 15-Sep-25 A | 2026-07-21 | 2026-07-21 | 30-Jun-25 A | 15-Sep-25 A
A19820 | Foundation Drawing PSA-2 OffGas Compressor AfterCooler 13-HE-709_IFD/IFC | 16-Sep-25 A | 10-Oct-25 A | 2026-07-21 | 2026-07-21 | 16-Sep-25 A | 10-Oct-25 A
A49430 | Foundation Drawing PSA-2 OffGas Compressor AfterCooler 13-HE-709_IFR | 30-May-25 A | 13-Jun-25 A | 2026-07-16 | 2026-07-16 | 30-May-25 A | 13-Jun-25 A
DesignCalculationReportforfoundationofPSA-2OffGasCompressorAfterCooler13-HE-709 |  | 28-Apr-25 A | 08-Oct-25 A | 2027-03-23 | 2027-03-23 | 28-Apr-25 A | 08-Oct-25 A
A19830 | Design Calculation Report for foundation of PSA-2 OffGas Compressor AfterCooler 13-HE-709_IFR | 28-Apr-25 A | 19-May-25 A | 2027-03-23 | 2027-03-23 | 28-Apr-25 A | 19-May-25 A
A19840 | Design Calculation Report for foundation of PSA-2 OffGas Compressor AfterCooler 13-HE-709_RCC | 20-May-25 A | 21-Jun-25 A | 2027-03-23 | 2027-03-23 | 20-May-25 A | 21-Jun-25 A
A19850 | Design Calculation Report for foundation of PSA-2 OffGas Compressor AfterCooler 13-HE-709_IFA | 22-Jun-25 A | 28-Jun-25 A | 2027-03-23 | 2027-03-23 | 22-Jun-25 A | 28-Jun-25 A
A19860 | Design Calculation Report for foundation of PSA-2 OffGas Compressor AfterCooler 13-HE-709_RCA | 29-Jun-25 A | 08-Sep-25 A | 2027-03-23 | 2027-03-23 | 29-Jun-25 A | 08-Sep-25 A
A49440 | Design Calculation Report for foundation of PSA-2 OffGas Compressor AfterCooler 13-HE-709_IFD/IFC | 09-Sep-25 A | 08-Oct-25 A | 2027-03-23 | 2027-03-23 | 09-Sep-25 A | 08-Oct-25 A
FoundationDrawingPSA-2OffGasCompressorDischargeDripleg13-SP-7004 |  | 16-Apr-25 A | 04-Sep-25 A | 2026-07-16 | 2026-07-16 | 16-Apr-25 A | 04-Sep-25 A
A19980 | Foundation Drawing PSA-2 OffGas Compressor Discharge Dripleg 13-SP-7004_IFR | 16-Apr-25 A | 07-May-25 A | 2026-07-16 | 2026-07-16 | 16-Apr-25 A | 07-May-25 A
A20020 | Foundation Drawing PSA-2 OffGas Compressor Discharge Dripleg 13-SP-7004_IFD/IFC | 22-Jun-25 A | 04-Sep-25 A | 2026-07-16 | 2026-07-16 | 22-Jun-25 A | 04-Sep-25 A
A49500 | Foundation Drawing PSA-2 OffGas Compressor Discharge Dripleg 13-SP-7004_RCC | 08-May-25 A | 14-May-25 A | 2026-07-16 | 2026-07-16 | 08-May-25 A | 14-May-25 A
A49510 | Foundation Drawing PSA-2 OffGas Compressor Discharge Dripleg 13-SP-7004_IFA | 15-May-25 A | 03-Jun-25 A | 2026-07-16 | 2026-07-16 | 15-May-25 A | 03-Jun-25 A
A49520 | Foundation Drawing PSA-2 OffGas Compressor Discharge Dripleg 13-SP-7004_RCA | 04-Jun-25 A | 21-Jun-25 A | 2026-07-16 | 2026-07-16 | 04-Jun-25 A | 21-Jun-25 A
DesignCalculationReportforfoundationofPSA-2OffGasCompressorDischargeDripleg13-SP-7004 |  | 16-Apr-25 A | 10-Oct-25 A | 2027-03-23 | 2027-03-23 | 16-Apr-25 A | 10-Oct-25 A
A20030 | Design Calculation Report for foundation of PSA-2 OffGas Compressor Discharge Dripleg 13-SP-7004_IFR | 16-Apr-25 A | 07-May-25 A | 2027-03-23 | 2027-03-23 | 16-Apr-25 A | 07-May-25 A
A20040 | Design Calculation Report for foundation of PSA-2 OffGas Compressor Discharge Dripleg 13-SP-7004_RCC | 08-May-25 A | 14-May-25 A | 2027-03-23 | 2027-03-23 | 08-May-25 A | 14-May-25 A
A49530 | Design Calculation Report for foundation of PSA-2 OffGas Compressor Discharge Dripleg 13-SP-7004_IFA | 15-May-25 A | 03-Jun-25 A | 2027-03-23 | 2027-03-23 | 15-May-25 A | 03-Jun-25 A
A49540 | Design Calculation Report for foundation of PSA-2 OffGas Compressor Discharge Dripleg 13-SP-7004_RCA | 04-Jun-25 A | 21-Jun-25 A | 2027-03-23 | 2027-03-23 | 04-Jun-25 A | 21-Jun-25 A
A49550 | Design Calculation Report for foundation of PSA-2 OffGas Compressor Discharge Dripleg 13-SP-7004_IFD/IFC | 29-Sep-25 A | 10-Oct-25 A | 2027-03-23 | 2027-03-23 | 29-Sep-25 A | 10-Oct-25 A
FoundationDrawingPSA-2SlopDrum70-VV-1415 |  | 24-Apr-25 A | 2026-05-18 | 2026-07-25 | 2027-01-01 | 24-Apr-25 A | 2026-03-23
A20280 | Foundation Drawing PSA-2 Slop Drum 70-VV-1415_IFR | 24-Apr-25 A | 15-May-25 A | 2026-07-25 | 2026-07-25 | 24-Apr-25 A | 15-May-25 A
A20320 | Foundation Drawing PSA-2 Slop Drum 70-VV-1415_IFD/IFC | 2026-05-14 | 2026-05-18 | 2026-12-30 | 2027-01-01 | 2026-03-19 | 2026-03-23
A49650 | Foundation Drawing PSA-2 Slop Drum 70-VV-1415_RCC | 16-May-25 A | 22-May-25 A | 2026-08-04 | 2026-08-04 | 16-May-25 A | 22-May-25 A
A49660 | Foundation Drawing PSA-2 Slop Drum 70-VV-1415_IFA | 2026-04-17 | 2026-04-22 | 2026-12-03 | 2026-12-08 | 2026-02-20 | 2026-02-25
A49670 | Foundation Drawing PSA-2 Slop Drum 70-VV-1415_RCA | 2026-04-22 | 2026-05-14 | 2026-12-09 | 2026-12-30 | 2026-02-25 | 2026-03-19
DesignCalculationReportforfoundationofPSA-2SlopDrum70-VV-1415 |  | 01-Aug-25 A | 19-Jan-26 A | 2027-03-23 | 2027-03-23 | 01-Aug-25 A | 19-Jan-26 A
A20330 | Design Calculation Report for foundation of PSA-2 Slop Drum 70-VV-1415_IFR | 01-Aug-25 A | 22-Aug-25 A | 2027-03-23 | 2027-03-23 | 01-Aug-25 A | 22-Aug-25 A
A20340 | Design Calculation Report for foundation of PSA-2 Slop Drum 70-VV-1415_RCC | 08-Aug-25 A | 26-Aug-25 A | 2027-03-23 | 2027-03-23 | 08-Aug-25 A | 26-Aug-25 A
A49680 | Design Calculation Report for foundation of PSA-2 Slop Drum 70-VV-1415_IFA | 27-Aug-25 A | 02-Sep-25 A | 2027-03-23 | 2027-03-23 | 27-Aug-25 A | 02-Sep-25 A
A49690 | Design Calculation Report for foundation of PSA-2 Slop Drum 70-VV-1415_RCA | 25-Aug-25 A | 09-Sep-25 A | 2027-03-23 | 2027-03-23 | 25-Aug-25 A | 09-Sep-25 A
A49700 | Design Calculation Report for foundation of PSA-2 Slop Drum 70-VV-1415_IFD/IFC | 15-Jan-26 A | 19-Jan-26 A | 2027-03-23 | 2027-03-23 | 15-Jan-26 A | 19-Jan-26 A
FoundationDrawingPSA-2FeedGasCompressor2ndStageDischargeDrum13-VV-707 |  | 20-Apr-25 A | 23-Dec-25 A | 2026-07-25 | 2026-07-25 | 20-Apr-25 A | 23-Dec-25 A
A19200 | Foundation Drawing PSA-2 Feed Gas Compressor 2nd Stage Discharge Drum 13-VV-707_IFA | 19-May-25 A | 11-Jun-25 A | 2026-07-25 | 2026-07-25 | 19-May-25 A | 11-Jun-25 A
A19210 | Foundation Drawing PSA-2 Feed Gas Compressor 2nd Stage Discharge Drum 13-VV-707_RCA | 22-Sep-25 A | 10-Oct-25 A | 2026-07-25 | 2026-07-25 | 22-Sep-25 A | 10-Oct-25 A
A19220 | Foundation Drawing PSA-2 Feed Gas Compressor 2nd Stage Discharge Drum 13-VV-707_IFD/IFC | 19-Dec-25 A | 23-Dec-25 A | 2026-07-25 | 2026-07-25 | 19-Dec-25 A | 23-Dec-25 A
A49190 | Foundation Drawing PSA-2 Feed Gas Compressor 2nd Stage Discharge Drum 13-VV-707_IFR | 20-Apr-25 A | 11-May-25 A | 2026-07-25 | 2026-07-25 | 20-Apr-25 A | 11-May-25 A
A49200 | Foundation Drawing PSA-2 Feed Gas Compressor 2nd Stage Discharge Drum 13-VV-707_RCC | 12-May-25 A | 18-May-25 A | 2026-07-25 | 2026-07-25 | 12-May-25 A | 18-May-25 A
DesignCalculationReport-FoundationofPSA-2FeedGasCompressor2ndStageDischargeDrum13-VV-707 |  | 20-Apr-25 A | 23-Dec-25 A | 2027-03-23 | 2027-03-23 | 20-Apr-25 A | 23-Dec-25 A
A19260 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 FEED GAS COMPRESSOR 2ND STAGE DISCHARGE DRUM 13-VV-707_RCA | 22-Sep-25 A | 10-Oct-25 A | 2027-03-23 | 2027-03-23 | 22-Sep-25 A | 10-Oct-25 A
A19270 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 FEED GAS COMPRESSOR 2ND STAGE DISCHARGE DRUM 13-VV-707_IFD/IFC | 19-Dec-25 A | 23-Dec-25 A | 2027-03-23 | 2027-03-23 | 19-Dec-25 A | 23-Dec-25 A
A49210 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 FEED GAS COMPRESSOR 2ND STAGE DISCHARGE DRUM 13-VV-707_IFR | 20-Apr-25 A | 11-May-25 A | 2027-03-23 | 2027-03-23 | 20-Apr-25 A | 11-May-25 A
A49220 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 FEED GAS COMPRESSOR 2ND STAGE DISCHARGE DRUM 13-VV-707_RCC | 12-May-25 A | 18-May-25 A | 2027-03-23 | 2027-03-23 | 12-May-25 A | 18-May-25 A
A49230 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 FEED GAS COMPRESSOR 2ND STAGE DISCHARGE DRUM 13-VV-707_IFA | 19-May-25 A | 11-Jun-25 A | 2027-03-23 | 2027-03-23 | 19-May-25 A | 11-Jun-25 A
FoundationDrawingPSA-2FeedGasCompressor2ndStageSuctionDrum13-VV-706 |  | 16-Apr-25 A | 16-Sep-25 A | 2026-07-28 | 2026-08-01 | 16-Apr-25 A | 16-Sep-25 A
A19380 | Foundation Drawing PSA-2 Feed Gas Compressor 2nd Stage Suction Drum 13-VV-706_IFR | 16-Apr-25 A | 03-May-25 A | 2026-07-28 | 2026-07-28 | 16-Apr-25 A | 03-May-25 A
A19390 | Foundation Drawing PSA-2 Feed Gas Compressor 2nd Stage Suction Drum 13-VV-706_RCC | 04-May-25 A | 10-May-25 A | 2026-08-01 | 2026-08-01 | 04-May-25 A | 10-May-25 A
A19400 | Foundation Drawing PSA-2 Feed Gas Compressor 2nd Stage Suction Drum 13-VV-706_IFA | 11-May-25 A | 11-Jun-25 A | 2026-08-01 | 2026-08-01 | 11-May-25 A | 11-Jun-25 A
A49270 | Foundation Drawing PSA-2 Feed Gas Compressor 2nd Stage Suction Drum 13-VV-706_RCA | 12-Jun-25 A | 01-Sep-25 A | 2026-08-01 | 2026-08-01 | 12-Jun-25 A | 01-Sep-25 A
A49280 | Foundation Drawing PSA-2 Feed Gas Compressor 2nd Stage Suction Drum 13-VV-706_IFD/IFC | 02-Sep-25 A | 16-Sep-25 A | 2026-08-01 | 2026-08-01 | 02-Sep-25 A | 16-Sep-25 A
DesignCalculationReportFoundationofPSA-2FeedGasCompressor2ndStageSuctionDrum13-VV-706 |  | 16-Apr-25 A | 08-Sep-25 A | 2027-03-23 | 2027-03-23 | 16-Apr-25 A | 08-Sep-25 A
A19440 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 FEED GAS COMPRESSOR 2ND STAGE SUCTION DRUM 13-VV-706_RCC | 04-May-25 A | 10-May-25 A | 2027-03-23 | 2027-03-23 | 04-May-25 A | 10-May-25 A
A19450 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 FEED GAS COMPRESSOR 2ND STAGE SUCTION DRUM 13-VV-706_IFA | 11-May-25 A | 11-Jun-25 A | 2027-03-23 | 2027-03-23 | 11-May-25 A | 11-Jun-25 A
A19460 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 FEED GAS COMPRESSOR 2ND STAGE SUCTION DRUM 13-VV-706_RCA | 12-Jun-25 A | 21-Jun-25 A | 2027-03-23 | 2027-03-23 | 12-Jun-25 A | 21-Jun-25 A
A49290 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 FEED GAS COMPRESSOR 2ND STAGE SUCTION DRUM 13-VV-706_IFR | 16-Apr-25 A | 03-May-25 A | 2027-03-23 | 2027-03-23 | 16-Apr-25 A | 03-May-25 A
A49300 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 FEED GAS COMPRESSOR 2ND STAGE SUCTION DRUM 13-VV-706_IFD/IFC | 22-Jun-25 A | 08-Sep-25 A | 2027-03-23 | 2027-03-23 | 22-Jun-25 A | 08-Sep-25 A
FoundationDrawingPSA-2FeedGasCompressor1stStageSuctionDrum13-VV-705 |  | 24-Apr-25 A | 23-Dec-25 A | 2026-07-28 | 2026-07-28 | 24-Apr-25 A | 23-Dec-25 A
A19580 | Foundation Drawing PSA-2 Feed Gas Compressor 1st Stage Suction Drum 13-VV-705_IFR | 24-Apr-25 A | 15-May-25 A | 2026-07-28 | 2026-07-28 | 24-Apr-25 A | 15-May-25 A
A19620 | Foundation Drawing PSA-2 Feed Gas Compressor 1st Stage Suction Drum 13-VV-705_IFD/IFC | 19-Dec-25 A | 23-Dec-25 A | 2026-07-28 | 2026-07-28 | 19-Dec-25 A | 23-Dec-25 A
A49360 | Foundation Drawing PSA-2 Feed Gas Compressor 1st Stage Suction Drum 13-VV-705_RCC | 16-May-25 A | 22-May-25 A | 2026-07-28 | 2026-07-28 | 16-May-25 A | 22-May-25 A
A49370 | Foundation Drawing PSA-2 Feed Gas Compressor 1st Stage Suction Drum 13-VV-705_IFA | 23-May-25 A | 04-Jun-25 A | 2026-07-28 | 2026-07-28 | 23-May-25 A | 04-Jun-25 A
A49380 | Foundation Drawing PSA-2 Feed Gas Compressor 1st Stage Suction Drum 13-VV-705_RCA | 05-Jun-25 A | 21-Jun-25 A | 2026-07-28 | 2026-07-28 | 05-Jun-25 A | 21-Jun-25 A
DesignCalculationReportFoundationofPSA-2FeedGasCompressor1stStageSuctionDrum13-VV-705 |  | 24-Apr-25 A | 23-Dec-25 A | 2027-03-23 | 2027-03-23 | 24-Apr-25 A | 23-Dec-25 A
A19630 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 FEED GAS COMPRESSOR 1ST STAGE SUCTION DRUM 13-VV-705_IFR | 24-Apr-25 A | 15-May-25 A | 2027-03-23 | 2027-03-23 | 24-Apr-25 A | 15-May-25 A
A19640 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 FEED GAS COMPRESSOR 1ST STAGE SUCTION DRUM 13-VV-705_RCC | 16-May-25 A | 22-May-25 A | 2027-03-23 | 2027-03-23 | 16-May-25 A | 22-May-25 A
A49390 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 FEED GAS COMPRESSOR 1ST STAGE SUCTION DRUM 13-VV-705_IFA | 23-May-25 A | 03-Jun-25 A | 2027-03-23 | 2027-03-23 | 23-May-25 A | 03-Jun-25 A
A49400 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 FEED GAS COMPRESSOR 1ST STAGE SUCTION DRUM 13-VV-705_RCA | 04-Jun-25 A | 21-Jun-25 A | 2027-03-23 | 2027-03-23 | 04-Jun-25 A | 21-Jun-25 A
A49410 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 FEED GAS COMPRESSOR 1ST STAGE SUCTION DRUM 13-VV-705_IFD/IFC | 19-Dec-25 A | 23-Dec-25 A | 2027-03-23 | 2027-03-23 | 19-Dec-25 A | 23-Dec-25 A
FoundationDrawingPSA-2OffGasCompressor2ndStageSuctionDrum13-VV-713 |  | 15-Apr-25 A | 29-Jul-25 A | 2026-07-28 | 2026-09-16 | 15-Apr-25 A | 29-Jul-25 A
A19680 | Foundation Drawing PSA-2 OffGas Compressor 2nd Stage Suction Drum 13-VV-713_IFR | 15-Apr-25 A | 06-May-25 A | 2026-07-28 | 2026-07-28 | 15-Apr-25 A | 06-May-25 A
A19690 | Foundation Drawing PSA-2 OffGas Compressor 2nd Stage Suction Drum 13-VV-713_RCC | 07-May-25 A | 13-Jun-25 A | 2026-09-16 | 2026-09-16 | 07-May-25 A | 13-Jun-25 A
A19700 | Foundation Drawing PSA-2 OffGas Compressor 2nd Stage Suction Drum 13-VV-713_IFA | 16-Jun-25 A | 30-Jun-25 A | 2026-09-16 | 2026-09-16 | 16-Jun-25 A | 30-Jun-25 A
A19710 | Foundation Drawing PSA-2 OffGas Compressor 2nd Stage Suction Drum 13-VV-713_RCA | 16-Jun-25 A | 14-Jul-25 A | 2026-09-16 | 2026-09-16 | 16-Jun-25 A | 14-Jul-25 A
A19720 | Foundation Drawing PSA-2 OffGas Compressor 2nd Stage Suction Drum 13-VV-713_IFD/IFC | 15-Jul-25 A | 29-Jul-25 A | 2026-09-16 | 2026-09-16 | 15-Jul-25 A | 29-Jul-25 A
DesignCalculationReportFoundationofPSA-2OffGasCompressor2ndStageSuctionDrum13-VV-713 |  | 20-Apr-25 A | 10-Oct-25 A | 2027-03-23 | 2027-03-23 | 20-Apr-25 A | 10-Oct-25 A
A19730 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 OFFGAS COMPRESSOR 2ND STAGE SUCTION DRUM 13-VV-713_IFR | 20-Apr-25 A | 11-May-25 A | 2027-03-23 | 2027-03-23 | 20-Apr-25 A | 11-May-25 A
A19740 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 OFFGAS COMPRESSOR 2ND STAGE SUCTION DRUM 13-VV-713_RCC | 12-May-25 A | 21-Jun-25 A | 2027-03-23 | 2027-03-23 | 12-May-25 A | 21-Jun-25 A
A19750 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 OFFGAS COMPRESSOR 2ND STAGE SUCTION DRUM 13-VV-713_IFA | 22-Jun-25 A | 28-Jun-25 A | 2027-03-23 | 2027-03-23 | 22-Jun-25 A | 28-Jun-25 A
A19760 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 OFFGAS COMPRESSOR 2ND STAGE SUCTION DRUM 13-VV-713_RCA | 01-Jul-25 A | 04-Sep-25 A | 2027-03-23 | 2027-03-23 | 01-Jul-25 A | 04-Sep-25 A
A49420 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 OFFGAS COMPRESSOR 2ND STAGE SUCTION DRUM 13-VV-713_IFD/IFC | 08-Sep-25 A | 10-Oct-25 A | 2027-03-23 | 2027-03-23 | 08-Sep-25 A | 10-Oct-25 A
FoundationDrawingPSA-2OffGasBufferDrum13-VV-712 |  | 22-Apr-25 A | 10-Oct-25 A | 2026-07-28 | 2026-07-28 | 22-Apr-25 A | 10-Oct-25 A
A19900 | Foundation Drawing PSA-2 OffGas Buffer Drum 13-VV-712_IFA | 30-May-25 A | 21-Jun-25 A | 2026-07-28 | 2026-07-28 | 30-May-25 A | 21-Jun-25 A
A19910 | Foundation Drawing PSA-2 OffGas Buffer Drum 13-VV-712_RCA | 22-Jun-25 A | 28-Jun-25 A | 2026-07-28 | 2026-07-28 | 22-Jun-25 A | 28-Jun-25 A
A19920 | Foundation Drawing PSA-2 OffGas Buffer Drum 13-VV-712_IFD/IFC | 26-Sep-25 A | 10-Oct-25 A | 2026-07-28 | 2026-07-28 | 26-Sep-25 A | 10-Oct-25 A
A49450 | Foundation Drawing PSA-2 OffGas Buffer Drum 13-VV-712_IFR | 22-Apr-25 A | 13-May-25 A | 2026-07-28 | 2026-07-28 | 22-Apr-25 A | 13-May-25 A
A49460 | Foundation Drawing PSA-2 OffGas Buffer Drum 13-VV-712_RCC | 14-May-25 A | 29-May-25 A | 2026-07-28 | 2026-07-28 | 14-May-25 A | 29-May-25 A
DesignCalculationReportforfoundationofPSA-2OffGasBufferDrum13-VV-712 |  | 22-Apr-25 A | 10-Oct-25 A | 2027-03-23 | 2027-03-23 | 22-Apr-25 A | 10-Oct-25 A
A19960 | Design Calculation Report for foundation of PSA-2 OffGas Buffer Drum 13-VV-712_RCA | 22-Jun-25 A | 06-Sep-25 A | 2027-03-23 | 2027-03-23 | 22-Jun-25 A | 06-Sep-25 A
A19970 | Design Calculation Report for foundation of PSA-2 OffGas Buffer Drum 13-VV-712_IFD/IFC | 26-Sep-25 A | 10-Oct-25 A | 2027-03-23 | 2027-03-23 | 26-Sep-25 A | 10-Oct-25 A
A49470 | Design Calculation Report for foundation of PSA-2 OffGas Buffer Drum 13-VV-712_IFR | 22-Apr-25 A | 13-May-25 A | 2027-03-23 | 2027-03-23 | 22-Apr-25 A | 13-May-25 A
A49480 | Design Calculation Report for foundation of PSA-2 OffGas Buffer Drum 13-VV-712_RCC | 14-May-25 A | 03-Jun-25 A | 2027-03-23 | 2027-03-23 | 14-May-25 A | 03-Jun-25 A
A49490 | Design Calculation Report for foundation of PSA-2 OffGas Buffer Drum 13-VV-712_IFA | 04-Jun-25 A | 21-Jun-25 A | 2027-03-23 | 2027-03-23 | 04-Jun-25 A | 21-Jun-25 A
PileLayoutCompressorShelter&SR8001 |  | 01-Jul-25 A | 13-Sep-25 A | 2026-06-15 | 2026-06-15 | 01-Jul-25 A | 13-Sep-25 A
A17630 | Pile Layout Compressor Shelter & SR8001_IFR | 01-Jul-25 A | 12-Jul-25 A | 2026-06-15 | 2026-06-15 | 01-Jul-25 A | 12-Jul-25 A
A17640 | Pile Layout Compressor Shelter & SR8001_RCC | 14-Jul-25 A | 22-Aug-25 A | 2026-06-15 | 2026-06-15 | 14-Jul-25 A | 22-Aug-25 A
A17650 | Pile Layout Compressor Shelter & SR8001_IFA | 25-Aug-25 A | 30-Aug-25 A | 2026-06-15 | 2026-06-15 | 25-Aug-25 A | 30-Aug-25 A
A17660 | Pile Layout Compressor Shelter & SR8001_RCA | 25-Aug-25 A | 06-Sep-25 A | 2026-06-15 | 2026-06-15 | 25-Aug-25 A | 06-Sep-25 A
A17670 | Pile Layout Compressor Shelter & SR8001_IFD/IFC | 08-Sep-25 A | 13-Sep-25 A | 2026-06-15 | 2026-06-15 | 08-Sep-25 A | 13-Sep-25 A
PileReinforcementDrawing |  | 01-Jul-25 A | 18-Jul-25 A | 2026-06-15 | 2027-03-23 | 01-Jul-25 A | 18-Jul-25 A
A17480 | Pile Reinforcement Drawing_IFR | 01-Jul-25 A | 18-Jul-25 A | 2026-06-15 | 2026-06-15 | 01-Jul-25 A | 18-Jul-25 A
A17490 | Pile Reinforcement Drawing_RCC | 01-Jul-25 A | 18-Jul-25 A | 2027-03-23 | 2027-03-23 | 01-Jul-25 A | 18-Jul-25 A
A17500 | Pile Reinforcement Drawing_IFA | 01-Jul-25 A | 18-Jul-25 A | 2027-03-23 | 2027-03-23 | 01-Jul-25 A | 18-Jul-25 A
A17510 | Pile Reinforcement Drawing_RCA | 01-Jul-25 A | 18-Jul-25 A | 2027-03-23 | 2027-03-23 | 01-Jul-25 A | 18-Jul-25 A
A17520 | Pile Reinforcement Drawing_IFD/IFC | 01-Jul-25 A | 18-Jul-25 A | 2027-03-23 | 2027-03-23 | 01-Jul-25 A | 18-Jul-25 A
PileLayoutPSA-2FeedGasCompressor13-KC-701 |  | 10-Apr-25 A | 15-Sep-25 A | 2026-06-15 | 2026-06-15 | 10-Apr-25 A | 15-Sep-25 A
A17530 | Pile Layout PSA-2 FeedGas Compressor 13-KC-701_IFR | 10-Apr-25 A | 15-Aug-25 A | 2026-06-15 | 2026-06-15 | 10-Apr-25 A | 15-Aug-25 A
A17550 | Pile Layout PSA-2 FeedGas Compressor 13-KC-701_IFA | 22-Aug-25 A | 29-Aug-25 A | 2026-06-15 | 2026-06-15 | 22-Aug-25 A | 29-Aug-25 A
A17560 | Pile Layout PSA-2 FeedGas Compressor 13-KC-701_RCA | 18-Aug-25 A | 05-Sep-25 A | 2026-06-15 | 2026-06-15 | 18-Aug-25 A | 05-Sep-25 A
A17570 | Pile Layout PSA-2 FeedGas Compressor 13-KC-701_IFD/IFC | 08-Sep-25 A | 15-Sep-25 A | 2026-06-15 | 2026-06-15 | 08-Sep-25 A | 15-Sep-25 A
A48320 | Pile Layout PSA-2 FeedGas Compressor 13-KC-701_RCC | 16-Aug-25 A | 22-Aug-25 A | 2026-06-15 | 2026-06-15 | 16-Aug-25 A | 22-Aug-25 A
PileLayoutPSA-2OffGasCompressor13-KC-702 |  | 01-Jul-25 A | 15-Sep-25 A | 2026-06-15 | 2026-06-15 | 01-Jul-25 A | 15-Sep-25 A
A17580 | Pile Layout PSA-2 OffGas Compressor 13-KC-702_IFR | 01-Jul-25 A | 11-Jul-25 A | 2026-06-15 | 2026-06-15 | 01-Jul-25 A | 11-Jul-25 A
A17590 | Pile Layout PSA-2 OffGas Compressor 13-KC-702_RCC | 14-Jul-25 A | 22-Aug-25 A | 2026-06-15 | 2026-06-15 | 14-Jul-25 A | 22-Aug-25 A
A17600 | Pile Layout PSA-2 OffGas Compressor 13-KC-702_IFA | 25-Aug-25 A | 30-Aug-25 A | 2026-06-15 | 2026-06-15 | 25-Aug-25 A | 30-Aug-25 A
A17610 | Pile Layout PSA-2 OffGas Compressor 13-KC-702_RCA | 01-Aug-25 A | 06-Sep-25 A | 2026-06-15 | 2026-06-15 | 01-Aug-25 A | 06-Sep-25 A
A17620 | Pile Layout PSA-2 OffGas Compressor 13-KC-702_IFD/IFC | 08-Sep-25 A | 15-Sep-25 A | 2026-06-15 | 2026-06-15 | 08-Sep-25 A | 15-Sep-25 A
PileLayoutPSA-2Unit-HydrogenPurification13-XA-710 |  | 30-Jun-25 A | 13-Sep-25 A | 2026-06-15 | 2026-06-15 | 30-Jun-25 A | 13-Sep-25 A
A48330 | Pile Layout PSA-2 Unit - Hydrogen Purification 13-XA-710_IFR | 30-Jun-25 A | 11-Jul-25 A | 2026-06-15 | 2026-06-15 | 30-Jun-25 A | 11-Jul-25 A
A48340 | Pile Layout PSA-2 Unit - Hydrogen Purification 13-XA-710_RCC | 14-Jul-25 A | 22-Aug-25 A | 2026-06-15 | 2026-06-15 | 14-Jul-25 A | 22-Aug-25 A
A48350 | Pile Layout PSA-2 Unit - Hydrogen Purification 13-XA-710_IFA | 25-Aug-25 A | 30-Aug-25 A | 2026-06-15 | 2026-06-15 | 25-Aug-25 A | 30-Aug-25 A
A48360 | Pile Layout PSA-2 Unit - Hydrogen Purification 13-XA-710_RCA | 19-Aug-25 A | 06-Sep-25 A | 2026-06-15 | 2026-06-15 | 19-Aug-25 A | 06-Sep-25 A
A48370 | Pile Layout PSA-2 Unit - Hydrogen Purification 13-XA-710_IFD/IFC | 08-Sep-25 A | 13-Sep-25 A | 2026-06-15 | 2026-06-15 | 08-Sep-25 A | 13-Sep-25 A
PileLayoutPSA-2OffGasBufferDrum13-VV-712 |  | 02-Jun-25 A | 05-Jul-25 A | 2026-06-15 | 2026-06-15 | 02-Jun-25 A | 05-Jul-25 A
A17680 | Pile Layout PSA-2 OffGas Buffer Drum 13-VV-712_IFR | 02-Jun-25 A | 07-Jun-25 A | 2026-06-15 | 2026-06-15 | 02-Jun-25 A | 07-Jun-25 A
A17690 | Pile Layout PSA-2 OffGas Buffer Drum 13-VV-712_RCC | 06-Jun-25 A | 16-Jun-25 A | 2026-06-15 | 2026-06-15 | 06-Jun-25 A | 16-Jun-25 A
A17700 | Pile Layout PSA-2 OffGas Buffer Drum 13-VV-712_IFA | 17-Jun-25 A | 23-Jun-25 A | 2026-06-15 | 2026-06-15 | 17-Jun-25 A | 23-Jun-25 A
A17710 | Pile Layout PSA-2 OffGas Buffer Drum 13-VV-712_RCA | 17-Jun-25 A | 28-Jun-25 A | 2026-06-15 | 2026-06-15 | 17-Jun-25 A | 28-Jun-25 A
A17720 | Pile Layout PSA-2 OffGas Buffer Drum 13-VV-712_IFD/IFC | 30-Jun-25 A | 05-Jul-25 A | 2026-06-15 | 2026-06-15 | 30-Jun-25 A | 05-Jul-25 A
Structure&Foundationdesign-Buildings/Shelters/Electrical |  | 05-Feb-25 A | 20-Mar-26 A | 2026-06-15 | 2027-03-23 | 05-Feb-25 A | 2026-04-07
StructuralGA,SectionandDetails-CompressorShelter |  | 01-Oct-25 A | 19-Jan-26 A | 2026-07-20 | 2026-07-20 | 01-Oct-25 A | 19-Jan-26 A
A48880 | Structural GA, Section and Details - Compressor Shelter_IFR | 01-Oct-25 A | 07-Oct-25 A | 2026-07-20 | 2026-07-20 | 01-Oct-25 A | 07-Oct-25 A
A48890 | Structural GA, Section and Details - Compressor Shelter_RCC | 08-Oct-25 A | 23-Oct-25 A | 2026-07-20 | 2026-07-20 | 08-Oct-25 A | 23-Oct-25 A
A48900 | Structural GA, Section and Details - Compressor Shelter_IFA | 23-Oct-25 A | 24-Oct-25 A | 2026-07-20 | 2026-07-20 | 23-Oct-25 A | 24-Oct-25 A
A48910 | Structural GA, Section and Details - Compressor Shelter_RCA | 19-Dec-25 A | 09-Jan-26 A | 2026-07-20 | 2026-07-20 | 19-Dec-25 A | 09-Jan-26 A
A48920 | Structural GA, Section and Details - Compressor Shelter_IFD/IFC | 09-Jan-26 A | 19-Jan-26 A | 2026-07-20 | 2026-07-20 | 09-Jan-26 A | 19-Jan-26 A
DesignCalculationReportforstructuralsteel-CompressorShelter |  | 01-Sep-25 A | 20-Mar-26 A | 2027-03-23 | 2027-03-23 | 01-Sep-25 A | 2026-04-07
A18690 | Design Calculation Report for structural steel- Compressor Shelter_RCC | 10-Sep-25 A | 01-Oct-25 A | 2027-03-23 | 2027-03-23 | 10-Sep-25 A | 01-Oct-25 A
A18700 | Design Calculation Report for structural steel- Compressor Shelter_IFA | 02-Mar-26 A | 11-Mar-26 A | 2027-03-23 | 2027-03-23 | 2026-02-20 | 2026-03-09
A18710 | Design Calculation Report for structural steel- Compressor Shelter_RCA | 04-Mar-26 A | 11-Mar-26 A | 2027-03-23 | 2027-03-23 | 2026-03-09 | 2026-03-30
A48950 | Design Calculation Report for structural steel- Compressor Shelter_IFR | 01-Sep-25 A | 13-Sep-25 A | 2027-03-23 | 2027-03-23 | 01-Sep-25 A | 13-Sep-25 A
A48960 | Design Calculation Report for structural steel- Compressor Shelter_IFD/IFC | 02-Mar-26 A | 20-Mar-26 A | 2027-03-23 | 2027-03-23 | 2026-03-31 | 2026-04-07
FoundationDrawing-CompressorShelter |  | 01-Jul-25 A | 21-Jan-26 A | 2027-03-23 | 2027-03-23 | 01-Jul-25 A | 21-Jan-26 A
A18630 | Foundation Drawing- Compressor Shelter_IFR | 01-Jul-25 A | 12-Jul-25 A | 2027-03-23 | 2027-03-23 | 01-Jul-25 A | 12-Jul-25 A
A18640 | Foundation Drawing- Compressor Shelter_RCC | 15-Jul-25 A | 22-Aug-25 A | 2027-03-23 | 2027-03-23 | 15-Jul-25 A | 22-Aug-25 A
A18650 | Foundation Drawing- Compressor Shelter_IFA | 20-Oct-25 A | 30-Oct-25 A | 2027-03-23 | 2027-03-23 | 20-Oct-25 A | 30-Oct-25 A
A48930 | Foundation Drawing- Compressor Shelter_RCA | 31-Oct-25 A | 14-Nov-25 A | 2027-03-23 | 2027-03-23 | 31-Oct-25 A | 14-Nov-25 A
A48940 | Foundation Drawing- Compressor Shelter_IFD/IFC | 19-Jan-26 A | 21-Jan-26 A | 2027-03-23 | 2027-03-23 | 19-Jan-26 A | 21-Jan-26 A
DesignCalculationReportforFoundations-CompressorShelter |  | 28-Jun-25 A | 21-Jan-26 A | 2027-03-23 | 2027-03-23 | 28-Jun-25 A | 21-Jan-26 A
A48970 | Design Calculation Report for Foundations- Compressor Shelter_IFR | 28-Jun-25 A | 15-Jul-25 A | 2027-03-23 | 2027-03-23 | 28-Jun-25 A | 15-Jul-25 A
A48980 | Design Calculation Report for Foundations- Compressor Shelter_RCC | 16-Jul-25 A | 22-Aug-25 A | 2027-03-23 | 2027-03-23 | 16-Jul-25 A | 22-Aug-25 A
A48990 | Design Calculation Report for Foundations- Compressor Shelter_IFA | 25-Aug-25 A | 29-Aug-25 A | 2027-03-23 | 2027-03-23 | 25-Aug-25 A | 29-Aug-25 A
A49000 | Design Calculation Report for Foundations- Compressor Shelter_RCA | 20-Aug-25 A | 05-Sep-25 A | 2027-03-23 | 2027-03-23 | 20-Aug-25 A | 05-Sep-25 A
A49010 | Design Calculation Report for Foundations- Compressor Shelter_IFD/IFC | 19-Jan-26 A | 21-Jan-26 A | 2027-03-23 | 2027-03-23 | 19-Jan-26 A | 21-Jan-26 A
ArchitecturalDrawing-Substation,SISBuilding |  | 05-Feb-25 A | 18-Sep-25 A | 2026-06-15 | 2026-06-21 | 05-Feb-25 A | 18-Sep-25 A
A17790 | Architectural Drawing- Substation, SIS Building_RCC | 12-Mar-25 A | 20-Apr-25 A | 2026-06-16 | 2026-06-16 | 12-Mar-25 A | 20-Apr-25 A
A48380 | Architectural Drawing- Substation, SIS Building_IFR | 05-Feb-25 A | 11-Mar-25 A | 2026-06-15 | 2026-06-15 | 05-Feb-25 A | 11-Mar-25 A
A48390 | Architectural Drawing- Substation, SIS Building_IFA | 21-Apr-25 A | 19-Jun-25 A | 2026-06-16 | 2026-06-16 | 21-Apr-25 A | 19-Jun-25 A
A48400 | Architectural Drawing- Substation, SIS Building_RCA | 20-Jun-25 A | 04-Sep-25 A | 2026-06-21 | 2026-06-21 | 20-Jun-25 A | 04-Sep-25 A
A48410 | Architectural Drawing- Substation, SIS Building_IFD/IFC | 08-Sep-25 A | 18-Sep-25 A | 2026-06-21 | 2026-06-21 | 08-Sep-25 A | 18-Sep-25 A
StructuralConcreteGA,SectionandDetails-Substation,SISBuilding |  | 21-Apr-25 A | 29-Aug-25 A | 2026-06-16 | 2026-06-21 | 21-Apr-25 A | 29-Aug-25 A
A17880 | Structural Concrete GA, Section and Details- Substation, SIS Building_IFR | 21-Apr-25 A | 12-May-25 A | 2026-06-16 | 2026-06-16 | 21-Apr-25 A | 12-May-25 A
A48430 | Structural Concrete GA, Section and Details- Substation, SIS Building_RCC | 13-May-25 A | 03-Jun-25 A | 2026-06-16 | 2026-06-16 | 13-May-25 A | 03-Jun-25 A
A48440 | Structural Concrete GA, Section and Details- Substation, SIS Building_IFA | 04-Jun-25 A | 15-Aug-25 A | 2026-06-16 | 2026-06-16 | 04-Jun-25 A | 15-Aug-25 A
A48450 | Structural Concrete GA, Section and Details- Substation, SIS Building_RCA | 07-Aug-25 A | 22-Aug-25 A | 2026-06-21 | 2026-06-21 | 07-Aug-25 A | 22-Aug-25 A
A48460 | Structural Concrete GA, Section and Details- Substation, SIS Building_IFD/IFC | 22-Aug-25 A | 29-Aug-25 A | 2026-06-21 | 2026-06-21 | 22-Aug-25 A | 29-Aug-25 A
DesignCalculationreportforSubstation,SISBuilding |  | 20-Apr-25 A | 29-Aug-25 A | 2026-06-21 | 2026-06-21 | 20-Apr-25 A | 29-Aug-25 A
A17940 | Design Calculation report for Substation, SIS Building_RCC | 12-May-25 A | 05-Jun-25 A | 2026-06-21 | 2026-06-21 | 12-May-25 A | 05-Jun-25 A
A48470 | Design Calculation report for Substation, SIS Building_IFR | 20-Apr-25 A | 11-May-25 A | 2026-06-21 | 2026-06-21 | 20-Apr-25 A | 11-May-25 A
A48480 | Design Calculation report for Substation, SIS Building_IFA | 06-Jun-25 A | 15-Aug-25 A | 2026-06-21 | 2026-06-21 | 06-Jun-25 A | 15-Aug-25 A
A48490 | Design Calculation report for Substation, SIS Building_RCA | 16-Jun-25 A | 22-Aug-25 A | 2026-06-21 | 2026-06-21 | 16-Jun-25 A | 22-Aug-25 A
A48500 | Design Calculation report for Substation, SIS Building_IFD/IFC | 25-Aug-25 A | 29-Aug-25 A | 2026-06-21 | 2026-06-21 | 25-Aug-25 A | 29-Aug-25 A
FoundationLayout,SectionandDetails-Substation,SISBuilding |  | 21-Apr-25 A | 29-Aug-25 A | 2026-06-21 | 2026-06-21 | 21-Apr-25 A | 29-Aug-25 A
A17840 | Foundation Layout, Section and Details- Substation, SIS Building_RCC | 13-May-25 A | 29-May-25 A | 2026-06-21 | 2026-06-21 | 13-May-25 A | 29-May-25 A
A17850 | Foundation Layout, Section and Details- Substation, SIS Building_IFA | 30-May-25 A | 21-Jun-25 A | 2026-06-21 | 2026-06-21 | 30-May-25 A | 21-Jun-25 A
A17860 | Foundation Layout, Section and Details- Substation, SIS Building_RCA | 23-Jun-25 A | 22-Aug-25 A | 2026-06-21 | 2026-06-21 | 23-Jun-25 A | 22-Aug-25 A
A17870 | Foundation Layout, Section and Details- Substation, SIS Building_IFD/IFC | 25-Aug-25 A | 29-Aug-25 A | 2026-06-21 | 2026-06-21 | 25-Aug-25 A | 29-Aug-25 A
A48420 | Foundation Layout, Section and Details- Substation, SIS Building_IFR | 21-Apr-25 A | 12-May-25 A | 2026-06-21 | 2026-06-21 | 21-Apr-25 A | 12-May-25 A
Structuredesign-U/Gfacilities |  | 10-Jun-25 A | 2026-06-16 | 2026-06-16 | 2027-03-23 | 10-Jun-25 A | 2026-04-21
SumpPitplananddetailsAccidentallyOilcontaminatedwatercollection70-TD-1407 |  | 18-Aug-25 A | 23-Dec-25 A | 2026-07-07 | 2026-07-08 | 18-Aug-25 A | 23-Dec-25 A
A20380 | Sump Pit plan and details Accidentally Oil contaminated water collection 70-TD-1407_IFR | 18-Aug-25 A | 22-Aug-25 A | 2026-07-07 | 2026-07-07 | 18-Aug-25 A | 22-Aug-25 A
A20390 | Sump Pit plan and details Accidentally Oil contaminated water collection 70-TD-1407_RCC | 20-Aug-25 A | 27-Aug-25 A | 2026-07-08 | 2026-07-08 | 20-Aug-25 A | 27-Aug-25 A
A20400 | Sump Pit plan and details Accidentally Oil contaminated water collection 70-TD-1407_IFA | 28-Aug-25 A | 02-Sep-25 A | 2026-07-08 | 2026-07-08 | 28-Aug-25 A | 02-Sep-25 A
A49710 | Sump Pit plan and details Accidentally Oil contaminated water collection 70-TD-1407_RCA | 27-Aug-25 A | 09-Sep-25 A | 2026-07-08 | 2026-07-08 | 27-Aug-25 A | 09-Sep-25 A
A49720 | Sump Pit plan and details Accidentally Oil contaminated water collection 70-TD-1407_IFD/IFC | 19-Dec-25 A | 23-Dec-25 A | 2026-07-08 | 2026-07-08 | 19-Dec-25 A | 23-Dec-25 A
DesignCalculationReportforAccidentallyOilcontaminatedwatercollectionSumpPit70-TD-1407 |  | 23-Aug-25 A | 23-Dec-25 A | 2026-07-07 | 2026-07-08 | 23-Aug-25 A | 23-Dec-25 A
A20440 | Design Calculation Report for Accidentally Oil contaminated water collection Sump Pit 70-TD-1407_RCC | 29-Aug-25 A | 22-Sep-25 A | 2026-07-08 | 2026-07-08 | 29-Aug-25 A | 22-Sep-25 A
A20450 | Design Calculation Report for Accidentally Oil contaminated water collection Sump Pit 70-TD-1407_IFA | 23-Sep-25 A | 29-Sep-25 A | 2026-07-08 | 2026-07-08 | 23-Sep-25 A | 29-Sep-25 A
A20460 | Design Calculation Report for Accidentally Oil contaminated water collection Sump Pit 70-TD-1407_RCA | 25-Sep-25 A | 04-Oct-25 A | 2026-07-08 | 2026-07-08 | 25-Sep-25 A | 04-Oct-25 A
A49730 | Design Calculation Report for Accidentally Oil contaminated water collection Sump Pit 70-TD-1407_IFR | 23-Aug-25 A | 13-Sep-25 A | 2026-07-07 | 2026-07-07 | 23-Aug-25 A | 13-Sep-25 A
A49740 | Design Calculation Report for Accidentally Oil contaminated water collection Sump Pit 70-TD-1407_IFD/IFC | 19-Dec-25 A | 23-Dec-25 A | 2026-07-08 | 2026-07-08 | 19-Dec-25 A | 23-Dec-25 A
SumpPitplananddetailsOilyWater70-TD-1408 |  | 01-Aug-25 A | 13-Jan-26 A | 2026-07-07 | 2026-07-07 | 01-Aug-25 A | 13-Jan-26 A
A20500 | Sump Pit plan and details Oily Water 70-TD-1408_IFA | 29-Aug-25 A | 02-Sep-25 A | 2026-07-07 | 2026-07-07 | 29-Aug-25 A | 02-Sep-25 A
A20510 | Sump Pit plan and details Oily Water 70-TD-1408_RCA | 01-Sep-25 A | 09-Sep-25 A | 2026-07-07 | 2026-07-07 | 01-Sep-25 A | 09-Sep-25 A
A20520 | Sump Pit plan and details Oily Water 70-TD-1408_IFD/IFC | 09-Jan-26 A | 13-Jan-26 A | 2026-07-07 | 2026-07-07 | 09-Jan-26 A | 13-Jan-26 A
A49750 | Sump Pit plan and details Oily Water 70-TD-1408_IFR | 01-Aug-25 A | 22-Aug-25 A | 2026-07-07 | 2026-07-07 | 01-Aug-25 A | 22-Aug-25 A
A49760 | Sump Pit plan and details Oily Water 70-TD-1408_RCC | 15-Aug-25 A | 26-Aug-25 A | 2026-07-07 | 2026-07-07 | 15-Aug-25 A | 26-Aug-25 A
DesignCalculationReportforOilyWaterSumpPit70-TD-1408 |  | 23-Aug-25 A | 13-Jan-26 A | 2026-07-07 | 2026-07-07 | 23-Aug-25 A | 13-Jan-26 A
A20560 | Design Calculation Report for Oily Water Sump Pit 70-TD-1408_RCA | 19-Dec-25 A | 09-Jan-26 A | 2026-07-07 | 2026-07-07 | 19-Dec-25 A | 09-Jan-26 A
A20570 | Design Calculation Report for Oily Water Sump Pit 70-TD-1408_IFD/IFC | 09-Jan-26 A | 13-Jan-26 A | 2026-07-07 | 2026-07-07 | 09-Jan-26 A | 13-Jan-26 A
A49770 | Design Calculation Report for Oily Water Sump Pit 70-TD-1408_IFR | 23-Aug-25 A | 13-Sep-25 A | 2026-07-07 | 2026-07-07 | 23-Aug-25 A | 13-Sep-25 A
A49780 | Design Calculation Report for Oily Water Sump Pit 70-TD-1408_RCC | 15-Sep-25 A | 16-Oct-25 A | 2026-07-07 | 2026-07-07 | 15-Sep-25 A | 16-Oct-25 A
A49790 | Design Calculation Report for Oily Water Sump Pit 70-TD-1408_IFA | 17-Oct-25 A | 23-Oct-25 A | 2026-07-07 | 2026-07-07 | 17-Oct-25 A | 23-Oct-25 A
SumpPitplananddetailsSanitaryWasteWater70-TD-1409 |  | 23-Aug-25 A | 23-Dec-25 A | 2026-12-27 | 2026-12-27 | 23-Aug-25 A | 23-Dec-25 A
A20580 | Sump Pit plan and details Sanitary Waste Water 70-TD-1409_IFR | 23-Aug-25 A | 13-Sep-25 A | 2026-12-27 | 2026-12-27 | 23-Aug-25 A | 13-Sep-25 A
A20620 | Sump Pit plan and details Sanitary Waste Water 70-TD-1409_IFD/IFC | 19-Dec-25 A | 23-Dec-25 A | 2026-12-27 | 2026-12-27 | 19-Dec-25 A | 23-Dec-25 A
A49800 | Sump Pit plan and details Sanitary Waste Water 70-TD-1409_RCC | 01-Sep-25 A | 24-Sep-25 A | 2026-12-27 | 2026-12-27 | 01-Sep-25 A | 24-Sep-25 A
A49810 | Sump Pit plan and details Sanitary Waste Water 70-TD-1409_IFA | 25-Sep-25 A | 01-Oct-25 A | 2026-12-27 | 2026-12-27 | 25-Sep-25 A | 01-Oct-25 A
A49820 | Sump Pit plan and details Sanitary Waste Water 70-TD-1409_RCA | 29-Sep-25 A | 08-Oct-25 A | 2026-12-27 | 2026-12-27 | 29-Sep-25 A | 08-Oct-25 A
DesignCalculationReportforSanitaryWasteWaterSumpPit70-TD-1409 |  | 23-Aug-25 A | 23-Dec-25 A | 2026-12-27 | 2026-12-27 | 23-Aug-25 A | 23-Dec-25 A
A20630 | Design Calculation Report for Sanitary Waste Water Sump Pit 70-TD-1409_IFR | 23-Aug-25 A | 13-Sep-25 A | 2026-12-27 | 2026-12-27 | 23-Aug-25 A | 13-Sep-25 A
A20640 | Design Calculation Report for Sanitary Waste Water Sump Pit 70-TD-1409_RCC | 15-Sep-25 A | 13-Oct-25 A | 2026-12-27 | 2026-12-27 | 15-Sep-25 A | 13-Oct-25 A
A49830 | Design Calculation Report for Sanitary Waste Water Sump Pit 70-TD-1409_IFA | 14-Oct-25 A | 20-Oct-25 A | 2026-12-27 | 2026-12-27 | 14-Oct-25 A | 20-Oct-25 A
A49840 | Design Calculation Report for Sanitary Waste Water Sump Pit 70-TD-1409_RCA | 15-Oct-25 A | 24-Oct-25 A | 2026-12-27 | 2026-12-27 | 15-Oct-25 A | 24-Oct-25 A
A49850 | Design Calculation Report for Sanitary Waste Water Sump Pit 70-TD-1409_IFD/IFC | 19-Dec-25 A | 23-Dec-25 A | 2026-12-27 | 2026-12-27 | 19-Dec-25 A | 23-Dec-25 A
TransformerFoundationDrawingforBay-AtoBay-E |  | 01-Mar-26 A | 2026-06-04 | 2027-01-22 | 2027-03-23 | 2026-02-20 | 2026-04-21
A20680 | Transformer Foundation Drawing for Bay-A to Bay-E_IFR | 01-Mar-26 A | 06-Mar-26 A | 2027-01-22 | 2027-01-22 | 2026-02-20 | 2026-02-27
A20690 | Transformer Foundation Drawing for Bay-A to Bay-E_RCC | 06-Mar-26 A | 20-Mar-26 A | 2027-02-22 | 2027-02-22 | 2026-02-27 | 2026-03-23
A20700 | Transformer Foundation Drawing for Bay-A to Bay-E_IFA | 13-Apr-26 A | 17-Apr-26 A | 2027-02-22 | 2027-02-22 | 2026-03-23 | 2026-03-26
A49860 | Transformer Foundation Drawing for Bay-A to Bay-E_RCA | 2026-05-11 | 2026-06-02 | 2027-02-26 | 2027-03-19 | 2026-03-26 | 2026-04-17
A49870 | Transformer Foundation Drawing for Bay-A to Bay-E_IFD/IFC | 2026-06-02 | 2026-06-04 | 2027-03-19 | 2027-03-23 | 2026-04-17 | 2026-04-21
DesignCalculationReportforFoundation-TransformerforBay-AtoBay-E |  | 2026-04-17 | 2026-06-16 | 2027-01-22 | 2027-03-23 | 2026-02-20 | 2026-04-21
A20750 | Design Calculation Report for Foundation- Transformer for Bay-A to Bay-E_IFA | 2026-05-18 | 2026-05-21 | 2027-02-22 | 2027-02-25 | 2026-03-23 | 2026-03-26
A20760 | Design Calculation Report for Foundation- Transformer for Bay-A to Bay-E_RCA | 2026-05-21 | 2026-06-12 | 2027-02-26 | 2027-03-19 | 2026-03-26 | 2026-04-17
A20770 | Design Calculation Report for Foundation- Transformer for Bay-A to Bay-E_IFD/IFC | 2026-06-12 | 2026-06-16 | 2027-03-19 | 2027-03-23 | 2026-04-17 | 2026-04-21
A49880 | Design Calculation Report for Foundation- Transformer for Bay-A to Bay-E_IFR | 2026-04-17 | 2026-04-24 | 2027-01-22 | 2027-01-29 | 2026-02-20 | 2026-02-27
A49890 | Design Calculation Report for Foundation- Transformer for Bay-A to Bay-E_RCC | 2026-04-24 | 2026-05-18 | 2027-01-29 | 2027-02-22 | 2026-02-27 | 2026-03-23
FirewaterValvePitPlan,SectionandDetails |  | 01-Oct-25 A | 23-Dec-25 A | 2026-07-29 | 2026-07-29 | 01-Oct-25 A | 23-Dec-25 A
A21380 | Firewater Valve Pit Plan, Section and Details_IFR | 01-Oct-25 A | 10-Oct-25 A | 2026-07-29 | 2026-07-29 | 01-Oct-25 A | 10-Oct-25 A
A21390 | Firewater Valve Pit Plan, Section and Details_RCC | 06-Oct-25 A | 17-Oct-25 A | 2026-07-29 | 2026-07-29 | 06-Oct-25 A | 17-Oct-25 A
A21400 | Firewater Valve Pit Plan, Section and Details_IFA | 20-Oct-25 A | 27-Oct-25 A | 2026-07-29 | 2026-07-29 | 20-Oct-25 A | 27-Oct-25 A
A50150 | Firewater Valve Pit Plan, Section and Details_RCA | 28-Oct-25 A | 21-Nov-25 A | 2026-07-29 | 2026-07-29 | 28-Oct-25 A | 21-Nov-25 A
A50160 | Firewater Valve Pit Plan, Section and Details_IFD/IFC | 19-Dec-25 A | 23-Dec-25 A | 2026-07-29 | 2026-07-29 | 19-Dec-25 A | 23-Dec-25 A
CoolingwaterValvePitPlan,SectionandDetails |  | 01-Oct-25 A | 23-Dec-25 A | 2026-08-29 | 2026-08-29 | 01-Oct-25 A | 23-Dec-25 A
A21440 | Cooling water Valve Pit Plan, Section and Details_RCC | 11-Oct-25 A | 24-Oct-25 A | 2026-08-29 | 2026-08-29 | 11-Oct-25 A | 24-Oct-25 A
A21450 | Cooling water Valve Pit Plan, Section and Details_IFA | 25-Oct-25 A | 20-Nov-25 A | 2026-08-29 | 2026-08-29 | 25-Oct-25 A | 20-Nov-25 A
A21460 | Cooling water Valve Pit Plan, Section and Details_RCA | 31-Oct-25 A | 21-Nov-25 A | 2026-08-29 | 2026-08-29 | 31-Oct-25 A | 21-Nov-25 A
A50170 | Cooling water Valve Pit Plan, Section and Details_IFR | 01-Oct-25 A | 10-Oct-25 A | 2026-08-29 | 2026-08-29 | 01-Oct-25 A | 10-Oct-25 A
A50180 | Cooling water Valve Pit Plan, Section and Details_IFD/IFC | 19-Dec-25 A | 23-Dec-25 A | 2026-08-29 | 2026-08-29 | 19-Dec-25 A | 23-Dec-25 A
UndergroundLayout |  | 10-Jun-25 A | 22-Oct-25 A | 2026-06-16 | 2026-06-16 | 10-Jun-25 A | 22-Oct-25 A
A21570 | Underground Layout_IFD/IFC | 14-Oct-25 A | 22-Oct-25 A | 2026-06-16 | 2026-06-16 | 14-Oct-25 A | 22-Oct-25 A
A50210 | Underground Layout_IFR | 10-Jun-25 A | 08-Jul-25 A | 2026-06-16 | 2026-06-16 | 10-Jun-25 A | 08-Jul-25 A
A50220 | Underground Layout_RCC | 18-Aug-25 A | 12-Sep-25 A | 2026-06-16 | 2026-06-16 | 18-Aug-25 A | 12-Sep-25 A
A50230 | Underground Layout_IFA | 11-Aug-25 A | 15-Aug-25 A | 2026-06-16 | 2026-06-16 | 11-Aug-25 A | 15-Aug-25 A
A50240 | Underground Layout_RCA | 15-Sep-25 A | 10-Oct-25 A | 2026-06-16 | 2026-06-16 | 15-Sep-25 A | 10-Oct-25 A
CompositeUndergrounddrawing |  | 22-Sep-25 A | 2026-05-18 | 2026-06-29 | 2026-07-28 | 22-Sep-25 A | 2026-03-23
A21580 | Composite Underground drawing_IFR | 22-Sep-25 A | 30-Sep-25 A | 2026-06-29 | 2026-06-29 | 22-Sep-25 A | 30-Sep-25 A
A21590 | Composite Underground drawing_RCC | 24-Sep-25 A | 07-Oct-25 A | 2026-06-29 | 2026-06-29 | 24-Sep-25 A | 07-Oct-25 A
A21600 | Composite Underground drawing_IFA | 2026-04-17 | 2026-04-22 | 2026-06-29 | 2026-07-02 | 2026-02-20 | 2026-02-25
A50250 | Composite Underground drawing_RCA | 2026-04-22 | 2026-05-14 | 2026-07-03 | 2026-07-24 | 2026-02-25 | 2026-03-19
A50260 | Composite Underground drawing_IFD/IFC | 2026-05-14 | 2026-05-18 | 2026-07-24 | 2026-07-28 | 2026-03-19 | 2026-03-23
UndergroundTrenchLayoutdrawinganddetails |  | 01-Oct-25 A | 19-Jan-26 A | 2026-06-29 | 2026-07-24 | 01-Oct-25 A | 19-Jan-26 A
A21650 | Underground Trench Layout drawing and details_IFA | 19-Dec-25 A | 24-Dec-25 A | 2026-06-29 | 2026-06-29 | 19-Dec-25 A | 24-Dec-25 A
A21660 | Underground Trench Layout drawing and details_RCA | 24-Dec-25 A | 15-Jan-26 A | 2026-07-24 | 2026-07-24 | 24-Dec-25 A | 15-Jan-26 A
A21670 | Underground Trench Layout drawing and details_IFD/IFC | 15-Jan-26 A | 19-Jan-26 A | 2026-07-24 | 2026-07-24 | 15-Jan-26 A | 19-Jan-26 A
A50270 | Underground Trench Layout drawing and details_IFR | 01-Oct-25 A | 09-Oct-25 A | 2026-06-29 | 2026-06-29 | 01-Oct-25 A | 09-Oct-25 A
A50280 | Underground Trench Layout drawing and details_RCC | 10-Oct-25 A | 10-Nov-25 A | 2026-06-29 | 2026-06-29 | 10-Oct-25 A | 10-Nov-25 A
DesignCalculationforConcreteTrenchesandDuctBanks(IfRequired) |  | 19-Dec-25 A | 2026-05-12 | 2027-02-26 | 2027-03-23 | 19-Dec-25 A | 2026-03-23
A21680 | Design Calculation for Concrete Trenches and Duct Banks (If Required)_IFR | 19-Dec-25 A | 26-Dec-25 A | 2027-02-26 | 2027-02-26 | 19-Dec-25 A | 26-Dec-25 A
A50290 | Design Calculation for Concrete Trenches and Duct Banks (If Required)_RCC | 26-Dec-25 A | 19-Jan-26 A | 2027-02-26 | 2027-02-26 | 26-Dec-25 A | 19-Jan-26 A
A50300 | Design Calculation for Concrete Trenches and Duct Banks (If Required)_IFA | 20-Mar-26 A | 25-Mar-26 A | 2027-02-26 | 2027-02-26 | 2026-02-20 | 2026-02-25
A50310 | Design Calculation for Concrete Trenches and Duct Banks (If Required)_RCA | 2026-04-17 | 2026-05-08 | 2027-02-26 | 2027-03-19 | 2026-02-25 | 2026-03-19
A50320 | Design Calculation for Concrete Trenches and Duct Banks (If Required)_IFD/IFC | 2026-05-08 | 2026-05-12 | 2027-03-19 | 2027-03-23 | 2026-03-19 | 2026-03-23
CalculationforUGHydraulics |  | 10-Jun-25 A | 23-Dec-25 A | 2027-03-23 | 2027-03-23 | 10-Jun-25 A | 23-Dec-25 A
A21730 | Calculation for UG Hydraulics_IFR | 10-Jun-25 A | 04-Jul-25 A | 2027-03-23 | 2027-03-23 | 10-Jun-25 A | 04-Jul-25 A
A21740 | Calculation for UG Hydraulics_RCC | 07-Jul-25 A | 15-Aug-25 A | 2027-03-23 | 2027-03-23 | 07-Jul-25 A | 15-Aug-25 A
A21750 | Calculation for UG Hydraulics_IFA | 18-Aug-25 A | 22-Aug-25 A | 2027-03-23 | 2027-03-23 | 18-Aug-25 A | 22-Aug-25 A
A21760 | Calculation for UG Hydraulics_RCA | 20-Aug-25 A | 29-Aug-25 A | 2027-03-23 | 2027-03-23 | 20-Aug-25 A | 29-Aug-25 A
A50330 | Calculation for UG Hydraulics_IFD/IFC | 19-Dec-25 A | 23-Dec-25 A | 2027-03-23 | 2027-03-23 | 19-Dec-25 A | 23-Dec-25 A
OtherCivildeliverables |  | 16-Jan-25 A | 2026-06-09 | 2026-06-21 | 2027-03-23 | 16-Jan-25 A | 2026-04-21
GeneralnotesforCivilandConcreteWorks |  | 30-Jan-25 A | 10-May-25 A | 2027-03-23 | 2027-03-23 | 30-Jan-25 A | 10-May-25 A
A17180 | General notes for Civil and Concrete Works_IFR | 30-Jan-25 A | 20-Feb-25 A | 2027-03-23 | 2027-03-23 | 30-Jan-25 A | 20-Feb-25 A
A17190 | General notes for Civil and Concrete Works_RCC | 21-Feb-25 A | 19-Apr-25 A | 2027-03-23 | 2027-03-23 | 21-Feb-25 A | 19-Apr-25 A
A17200 | General notes for Civil and Concrete Works_IFA | 20-Apr-25 A | 26-Apr-25 A | 2027-03-23 | 2027-03-23 | 20-Apr-25 A | 26-Apr-25 A
A17210 | General notes for Civil and Concrete Works_RCA | 27-Apr-25 A | 03-May-25 A | 2027-03-23 | 2027-03-23 | 27-Apr-25 A | 03-May-25 A
A17220 | General notes for Civil and Concrete Works_IFD/IFC | 04-May-25 A | 10-May-25 A | 2027-03-23 | 2027-03-23 | 04-May-25 A | 10-May-25 A
Standarddetailsforstairandladderfoundation |  | 01-Jul-25 A | 08-Oct-25 A | 2027-01-29 | 2027-03-23 | 01-Jul-25 A | 08-Oct-25 A
A17280 | Standard details for stair and ladder foundation_IFR | 01-Jul-25 A | 11-Jul-25 A | 2027-01-29 | 2027-01-29 | 01-Jul-25 A | 11-Jul-25 A
A17300 | Standard details for stair and ladder foundation_IFA | 18-Sep-25 A | 24-Sep-25 A | 2027-03-23 | 2027-03-23 | 18-Sep-25 A | 24-Sep-25 A
A17310 | Standard details for stair and ladder foundation_RCA | 15-Sep-25 A | 01-Oct-25 A | 2027-03-23 | 2027-03-23 | 15-Sep-25 A | 01-Oct-25 A
A17320 | Standard details for stair and ladder foundation_IFD/IFC | 02-Oct-25 A | 08-Oct-25 A | 2027-03-23 | 2027-03-23 | 02-Oct-25 A | 08-Oct-25 A
A48280 | Standard details for stair and ladder foundation_RCC | 31-Jul-25 A | 17-Sep-25 A | 2027-03-23 | 2027-03-23 | 31-Jul-25 A | 17-Sep-25 A
SiteGradingLayout |  | 03-Sep-25 A | 23-Dec-25 A | 2027-03-23 | 2027-03-23 | 03-Sep-25 A | 23-Dec-25 A
A17430 | Site Grading Layout_IFR | 03-Sep-25 A | 15-Sep-25 A | 2027-03-23 | 2027-03-23 | 03-Sep-25 A | 15-Sep-25 A
A17440 | Site Grading Layout_RCC | 06-Sep-25 A | 22-Sep-25 A | 2027-03-23 | 2027-03-23 | 06-Sep-25 A | 22-Sep-25 A
A17450 | Site Grading Layout_IFA | 31-Oct-25 A | 06-Nov-25 A | 2027-03-23 | 2027-03-23 | 31-Oct-25 A | 06-Nov-25 A
A17460 | Site Grading Layout_RCA | 07-Nov-25 A | 20-Nov-25 A | 2027-03-23 | 2027-03-23 | 07-Nov-25 A | 20-Nov-25 A
A48310 | Site Grading Layout_IFD/IFC | 19-Dec-25 A | 23-Dec-25 A | 2027-03-23 | 2027-03-23 | 19-Dec-25 A | 23-Dec-25 A
GeneralnotesforStructuralsteelWorks |  | 16-Jan-25 A | 03-May-25 A | 2027-01-29 | 2027-03-23 | 16-Jan-25 A | 03-May-25 A
A17240 | General notes for Structural steel Works_RCC | 21-Feb-25 A | 13-Mar-25 A | 2027-03-23 | 2027-03-23 | 21-Feb-25 A | 13-Mar-25 A
A17250 | General notes for Structural steel Works_IFA | 14-Mar-25 A | 19-Apr-25 A | 2027-03-23 | 2027-03-23 | 14-Mar-25 A | 19-Apr-25 A
A17260 | General notes for Structural steel Works_RCA | 20-Apr-25 A | 26-Apr-25 A | 2027-03-23 | 2027-03-23 | 20-Apr-25 A | 26-Apr-25 A
A17270 | General notes for Structural steel Works_IFD/IFC | 27-Apr-25 A | 03-May-25 A | 2027-03-23 | 2027-03-23 | 27-Apr-25 A | 03-May-25 A
A48270 | General notes for Structural steel Works_IFR | 16-Jan-25 A | 20-Feb-25 A | 2027-01-29 | 2027-01-29 | 16-Jan-25 A | 20-Feb-25 A
TypicalRoadDetails |  | 02-Jul-25 A | 2026-06-09 | 2027-01-29 | 2027-03-23 | 02-Jul-25 A | 2026-04-14
A17330 | Typical Road Details_IFR | 02-Jul-25 A | 09-Jul-25 A | 2027-01-29 | 2027-01-29 | 02-Jul-25 A | 09-Jul-25 A
A17340 | Typical Road Details_RCC | 2026-04-17 | 2026-05-08 | 2027-01-29 | 2027-02-22 | 2026-02-20 | 2026-03-13
A17360 | Typical Road Details_RCA | 2026-05-14 | 2026-06-04 | 2027-02-26 | 2027-03-19 | 2026-03-19 | 2026-04-09
A17370 | Typical Road Details_IFD/IFC | 2026-06-04 | 2026-06-09 | 2027-03-19 | 2027-03-23 | 2026-04-09 | 2026-04-14
A48290 | Typical Road Details_IFA | 2026-05-08 | 2026-05-14 | 2027-02-22 | 2027-02-25 | 2026-03-13 | 2026-03-19
MTOforCivilWorks |  | 05-May-25 A | 10-Jun-25 A | 2027-01-24 | 2027-03-23 | 05-May-25 A | 10-Jun-25 A
A22430 | MTO for Civil Works_IFR | 05-May-25 A | 16-May-25 A | 2027-01-24 | 2027-01-24 | 05-May-25 A | 16-May-25 A
A22440 | MTO for Civil Works_RCC | 19-May-25 A | 05-Jun-25 A | 2027-03-23 | 2027-03-23 | 19-May-25 A | 05-Jun-25 A
A50770 | MTO for Civil Works_IFD/IFC | 08-Jun-25 A | 10-Jun-25 A | 2027-03-23 | 2027-03-23 | 08-Jun-25 A | 10-Jun-25 A
MTOforStructuralSteel |  | 25-Aug-25 A | 12-Sep-25 A | 2026-06-21 | 2026-11-01 | 25-Aug-25 A | 12-Sep-25 A
A50780 | MTO for Structural Steel_IFR | 25-Aug-25 A | 29-Aug-25 A | 2026-06-21 | 2026-06-21 | 25-Aug-25 A | 29-Aug-25 A
A50790 | MTO for Structural Steel_RCC | 01-Sep-25 A | 05-Sep-25 A | 2026-11-01 | 2026-11-01 | 01-Sep-25 A | 05-Sep-25 A
A50800 | MTO for Structural Steel_IFD/IFC | 08-Sep-25 A | 12-Sep-25 A | 2026-11-01 | 2026-11-01 | 08-Sep-25 A | 12-Sep-25 A
Tie-inManholemodificationdrawing |  | 20-Mar-26 A | 17-Apr-26 A | 2027-03-23 | 2027-03-23 | 2026-02-20 | 2026-04-21
A22380 | Tie-in Manhole modification drawing_IFR | 20-Mar-26 A | 21-Mar-26 A | 2027-03-23 | 2027-03-23 | 2026-02-20 | 2026-02-27
A50730 | Tie-in Manhole modification drawing_RCC | 25-Mar-26 A | 30-Mar-26 A | 2027-03-23 | 2027-03-23 | 2026-02-27 | 2026-03-23
A50740 | Tie-in Manhole modification drawing_IFA | 01-Apr-26 A | 07-Apr-26 A | 2027-03-23 | 2027-03-23 | 2026-03-23 | 2026-03-26
A50750 | Tie-in Manhole modification drawing_RCA | 08-Apr-26 A | 11-Apr-26 A | 2027-03-23 | 2027-03-23 | 2026-03-26 | 2026-04-17
A50760 | Tie-in Manhole modification drawing_IFD/IFC | 14-Apr-26 A | 17-Apr-26 A | 2027-03-23 | 2027-03-23 | 2026-04-17 | 2026-04-21
FenceandGateLayout |  | 01-May-25 A | 23-Jan-26 A | 2027-03-23 | 2027-03-23 | 01-May-25 A | 23-Jan-26 A
A17380 | Fence and Gate Layout_IFR | 01-May-25 A | 22-May-25 A | 2027-03-23 | 2027-03-23 | 01-May-25 A | 22-May-25 A
A17390 | Fence and Gate Layout_RCC | 23-May-25 A | 17-Jun-25 A | 2027-03-23 | 2027-03-23 | 23-May-25 A | 17-Jun-25 A
A17400 | Fence and Gate Layout_IFA | 18-Jun-25 A | 24-Jun-25 A | 2027-03-23 | 2027-03-23 | 18-Jun-25 A | 24-Jun-25 A
A17420 | Fence and Gate Layout_IFD/IFC | 30-Dec-25 A | 23-Jan-26 A | 2027-03-23 | 2027-03-23 | 30-Dec-25 A | 23-Jan-26 A
A48300 | Fence and Gate Layout_RCA | 25-Jun-25 A | 16-Sep-25 A | 2027-03-23 | 2027-03-23 | 25-Jun-25 A | 16-Sep-25 A
RoadandPavingLayout |  | 02-Jun-25 A | 23-Jan-26 A | 2026-09-29 | 2026-09-29 | 02-Jun-25 A | 23-Jan-26 A
A21520 | Road and Paving Layout_IFD/IFC | 19-Jan-26 A | 23-Jan-26 A | 2026-09-29 | 2026-09-29 | 19-Jan-26 A | 23-Jan-26 A
A50190 | Road and Paving Layout_IFR | 02-Jun-25 A | 07-Jul-25 A | 2026-09-29 | 2026-09-29 | 02-Jun-25 A | 07-Jul-25 A
A50200 | Road and Paving Layout_RCC | 19-Dec-25 A | 09-Jan-26 A | 2026-09-29 | 2026-09-29 | 19-Dec-25 A | 09-Jan-26 A
A56270 | Road and Paving Layout_IFA | 09-Jan-26 A | 15-Jan-26 A | 2026-09-29 | 2026-09-29 | 09-Jan-26 A | 15-Jan-26 A
A56280 | Road and Paving Layout_RCA | 15-Jan-26 A | 19-Jan-26 A | 2026-09-29 | 2026-09-29 | 15-Jan-26 A | 19-Jan-26 A
Telecom |  | 30-Dec-24 A | 2026-06-16 | 2026-06-16 | 2027-03-23 | 26-Apr-25 A | 22-May-25 A
BlockDiagramForProcessCCTV |  | 30-Dec-24 A | 19-Sep-25 A | 2026-06-16 | 2027-03-23 | 30-Dec-24 A | 19-Sep-25 A
A51060 | Block Diagram For Process CCTV_IFR | 30-Dec-24 A | 20-Jan-25 A | 2026-06-16 | 2026-06-16 | 30-Dec-24 A | 20-Jan-25 A
A51070 | Block Diagram For Process CCTV_RCC | 21-Jan-25 A | 14-Feb-25 A | 2027-03-23 | 2027-03-23 | 21-Jan-25 A | 14-Feb-25 A
A51080 | Block Diagram For Process CCTV_IFA | 15-Feb-25 A | 22-Apr-25 A | 2027-03-23 | 2027-03-23 | 15-Feb-25 A | 22-Apr-25 A
A51090 | Block Diagram For Process CCTV_RCA | 23-Apr-25 A | 12-Sep-25 A | 2027-03-23 | 2027-03-23 | 23-Apr-25 A | 12-Sep-25 A
A51100 | Block Diagram For Process CCTV_IFD/IFC | 13-Sep-25 A | 19-Sep-25 A | 2027-03-23 | 2027-03-23 | 13-Sep-25 A | 19-Sep-25 A
BlockDiagramForPAGA |  | 30-Dec-24 A | 15-Oct-25 A | 2026-06-16 | 2027-03-23 | 30-Dec-24 A | 15-Oct-25 A
A51110 | Block Diagram For PAGA_IFR | 30-Dec-24 A | 20-Jan-25 A | 2026-06-16 | 2026-06-16 | 30-Dec-24 A | 20-Jan-25 A
A51120 | Block Diagram For PAGA_RCC | 21-Jan-25 A | 14-Feb-25 A | 2027-03-23 | 2027-03-23 | 21-Jan-25 A | 14-Feb-25 A
A51130 | Block Diagram For PAGA_IFA | 15-Feb-25 A | 22-Apr-25 A | 2027-03-23 | 2027-03-23 | 15-Feb-25 A | 22-Apr-25 A
A51140 | Block Diagram For PAGA_RCA | 23-Apr-25 A | 10-Sep-25 A | 2027-03-23 | 2027-03-23 | 23-Apr-25 A | 10-Sep-25 A
A51150 | Block Diagram For PAGA_IFD/IFC | 15-Sep-25 A | 15-Oct-25 A | 2027-03-23 | 2027-03-23 | 15-Sep-25 A | 15-Oct-25 A
BlockDiagramForDigitalNetworkAndTelephoneSystem |  | 01-Aug-25 A | 22-Oct-25 A | 2026-06-16 | 2027-03-23 | 01-Aug-25 A | 22-Oct-25 A
A51160 | Block Diagram For Digital Network And Telephone System_IFR | 01-Aug-25 A | 15-Aug-25 A | 2026-06-16 | 2026-06-16 | 01-Aug-25 A | 15-Aug-25 A
A51170 | Block Diagram For Digital Network And Telephone System_RCC | 04-Aug-25 A | 22-Aug-25 A | 2027-03-23 | 2027-03-23 | 04-Aug-25 A | 22-Aug-25 A
A51180 | Block Diagram For Digital Network And Telephone System_IFA | 25-Aug-25 A | 29-Aug-25 A | 2027-03-23 | 2027-03-23 | 25-Aug-25 A | 29-Aug-25 A
A51190 | Block Diagram For Digital Network And Telephone System_RCA | 25-Aug-25 A | 11-Sep-25 A | 2027-03-23 | 2027-03-23 | 25-Aug-25 A | 11-Sep-25 A
A51200 | Block Diagram For Digital Network And Telephone System_IFD/IFC | 01-Oct-25 A | 22-Oct-25 A | 2027-03-23 | 2027-03-23 | 01-Oct-25 A | 22-Oct-25 A
BlockDiagramForAccessControlSystem |  | 30-Dec-24 A | 19-Sep-25 A | 2026-06-16 | 2027-03-23 | 30-Dec-24 A | 19-Sep-25 A
A51210 | Block Diagram For Access Control System_IFR | 30-Dec-24 A | 20-Jan-25 A | 2026-06-16 | 2026-06-16 | 30-Dec-24 A | 20-Jan-25 A
A51220 | Block Diagram For Access Control System_RCC | 21-Jan-25 A | 14-Feb-25 A | 2027-03-23 | 2027-03-23 | 21-Jan-25 A | 14-Feb-25 A
A51230 | Block Diagram For Access Control System_IFA | 15-Feb-25 A | 22-Apr-25 A | 2027-03-23 | 2027-03-23 | 15-Feb-25 A | 22-Apr-25 A
A51240 | Block Diagram For Access Control System_RCA | 23-Apr-25 A | 21-Jun-25 A | 2027-03-23 | 2027-03-23 | 23-Apr-25 A | 21-Jun-25 A
A51250 | Block Diagram For Access Control System_IFD/IFC | 22-Jun-25 A | 19-Sep-25 A | 2027-03-23 | 2027-03-23 | 22-Jun-25 A | 19-Sep-25 A
OverallTelecomSystemBlockDiagram |  | 25-Jan-25 A | 2026-04-21 | 2027-03-19 | 2027-03-23 | 25-Jan-25 A | 2026-02-24
A51260 | Overall Telecom System Block Diagram_IFR | 25-Jan-25 A | 27-Apr-25 A | 2027-03-19 | 2027-03-19 | 25-Jan-25 A | 27-Apr-25 A
A51270 | Overall Telecom System Block Diagram_RCC | 01-Jul-25 A | 29-Jul-25 A | 2027-03-19 | 2027-03-19 | 01-Jul-25 A | 29-Jul-25 A
A51280 | Overall Telecom System Block Diagram_IFA | 31-Jul-25 A | 23-Sep-25 A | 2027-03-19 | 2027-03-19 | 31-Jul-25 A | 23-Sep-25 A
A51290 | Overall Telecom System Block Diagram_RCA | 22-Sep-25 A | 07-Oct-25 A | 2027-03-19 | 2027-03-19 | 22-Sep-25 A | 07-Oct-25 A
A51300 | Overall Telecom System Block Diagram_IFD/IFC | 2026-04-17 | 2026-04-21 | 2027-03-19 | 2027-03-23 | 2026-02-20 | 2026-02-24
TelecomTie-InSchedule |  | 13-Mar-25 A | 01-Sep-25 A | 2027-03-23 | 2027-03-23 | 13-Mar-25 A | 01-Sep-25 A
A23660 | Telecom Tie-In Schedule_RCA | 12-May-25 A | 25-Aug-25 A | 2027-03-23 | 2027-03-23 | 12-May-25 A | 25-Aug-25 A
A51800 | Telecom Tie-In Schedule_IFR | 13-Mar-25 A | 27-Apr-25 A | 2027-03-23 | 2027-03-23 | 13-Mar-25 A | 27-Apr-25 A
A51810 | Telecom Tie-In Schedule_RCC | 28-Apr-25 A | 04-May-25 A | 2027-03-23 | 2027-03-23 | 28-Apr-25 A | 04-May-25 A
A51820 | Telecom Tie-In Schedule_IFA | 05-May-25 A | 11-May-25 A | 2027-03-23 | 2027-03-23 | 05-May-25 A | 11-May-25 A
A51830 | Telecom Tie-In Schedule_IFD/IFC | 26-Aug-25 A | 01-Sep-25 A | 2027-03-23 | 2027-03-23 | 26-Aug-25 A | 01-Sep-25 A
DatasheetForFiberOpticCable |  | 30-Jan-25 A | 11-May-25 A | 2026-06-16 | 2027-03-23 | 30-Jan-25 A | 11-May-25 A
A50810 | Datasheet For Fiber Optic Cable_IFR | 30-Jan-25 A | 20-Feb-25 A | 2026-06-16 | 2026-06-16 | 30-Jan-25 A | 20-Feb-25 A
A50820 | Datasheet For Fiber Optic Cable_RCC | 21-Feb-25 A | 20-Apr-25 A | 2027-03-23 | 2027-03-23 | 21-Feb-25 A | 20-Apr-25 A
A50830 | Datasheet For Fiber Optic Cable_IFA | 21-Apr-25 A | 27-Apr-25 A | 2027-03-23 | 2027-03-23 | 21-Apr-25 A | 27-Apr-25 A
A50840 | Datasheet For Fiber Optic Cable_RCA | 28-Apr-25 A | 04-May-25 A | 2027-03-23 | 2027-03-23 | 28-Apr-25 A | 04-May-25 A
A50850 | Datasheet For Fiber Optic Cable_IFD/IFC | 05-May-25 A | 11-May-25 A | 2027-03-23 | 2027-03-23 | 05-May-25 A | 11-May-25 A
DatasheetForProcessCCTV |  | 01-Aug-25 A | 19-Jan-26 A | 2026-06-16 | 2026-06-16 | 01-Aug-25 A | 19-Jan-26 A
A50860 | Datasheet For Process CCTV_IFR | 01-Aug-25 A | 15-Aug-25 A | 2026-06-16 | 2026-06-16 | 01-Aug-25 A | 15-Aug-25 A
A50870 | Datasheet For Process CCTV_RCC | 15-Sep-25 A | 15-Oct-25 A | 2026-06-16 | 2026-06-16 | 15-Sep-25 A | 15-Oct-25 A
A50880 | Datasheet For Process CCTV_IFA | 19-Dec-25 A | 24-Dec-25 A | 2026-06-16 | 2026-06-16 | 19-Dec-25 A | 24-Dec-25 A
A50890 | Datasheet For Process CCTV_RCA | 24-Dec-25 A | 15-Jan-26 A | 2026-06-16 | 2026-06-16 | 24-Dec-25 A | 15-Jan-26 A
A50900 | Datasheet For Process CCTV_IFD/IFC | 15-Jan-26 A | 19-Jan-26 A | 2026-06-16 | 2026-06-16 | 15-Jan-26 A | 19-Jan-26 A
DatasheetForPAGA |  | 10-Jan-25 A | 23-Dec-25 A | 2026-06-16 | 2026-06-16 | 10-Jan-25 A | 23-Dec-25 A
A50910 | Datasheet For PAGA_IFR | 10-Jan-25 A | 20-Mar-25 A | 2026-06-16 | 2026-06-16 | 10-Jan-25 A | 20-Mar-25 A
A50920 | Datasheet For PAGA_RCC | 21-Mar-25 A | 20-Apr-25 A | 2026-06-16 | 2026-06-16 | 21-Mar-25 A | 20-Apr-25 A
A50930 | Datasheet For PAGA_IFA | 21-Apr-25 A | 30-May-25 A | 2026-06-16 | 2026-06-16 | 21-Apr-25 A | 30-May-25 A
A50940 | Datasheet For PAGA_RCA | 01-Jun-25 A | 21-Jun-25 A | 2026-06-16 | 2026-06-16 | 01-Jun-25 A | 21-Jun-25 A
A50950 | Datasheet For PAGA_IFD/IFC | 19-Dec-25 A | 23-Dec-25 A | 2026-06-16 | 2026-06-16 | 19-Dec-25 A | 23-Dec-25 A
DatasheetForAccessControlSystem |  | 15-Jan-25 A | 23-Dec-25 A | 2026-06-16 | 2026-06-16 | 15-Jan-25 A | 23-Dec-25 A
A50960 | Datasheet For Access Control System_IFR | 15-Jan-25 A | 27-Apr-25 A | 2026-06-16 | 2026-06-16 | 15-Jan-25 A | 27-Apr-25 A
A50970 | Datasheet For Access Control System_RCC | 28-Apr-25 A | 04-May-25 A | 2026-06-16 | 2026-06-16 | 28-Apr-25 A | 04-May-25 A
A50980 | Datasheet For Access Control System_IFA | 05-May-25 A | 09-Jun-25 A | 2026-06-16 | 2026-06-16 | 05-May-25 A | 09-Jun-25 A
A50990 | Datasheet For Access Control System_RCA | 10-Jun-25 A | 19-Sep-25 A | 2026-06-16 | 2026-06-16 | 10-Jun-25 A | 19-Sep-25 A
A51000 | Datasheet For Access Control System_IFD/IFC | 19-Dec-25 A | 23-Dec-25 A | 2026-06-16 | 2026-06-16 | 19-Dec-25 A | 23-Dec-25 A
DatasheetForDigitalNetworkAndTelephoneSystem |  | 15-Jan-25 A | 23-Dec-25 A | 2026-06-16 | 2026-06-16 | 15-Jan-25 A | 23-Dec-25 A
A51010 | Datasheet For Digital Network And Telephone System_IFR | 15-Jan-25 A | 27-Apr-25 A | 2026-06-16 | 2026-06-16 | 15-Jan-25 A | 27-Apr-25 A
A51020 | Datasheet For Digital Network And Telephone System_RCC | 28-Apr-25 A | 04-May-25 A | 2026-06-16 | 2026-06-16 | 28-Apr-25 A | 04-May-25 A
A51030 | Datasheet For Digital Network And Telephone System_IFA | 05-May-25 A | 10-Jun-25 A | 2026-06-16 | 2026-06-16 | 05-May-25 A | 10-Jun-25 A
A51040 | Datasheet For Digital Network And Telephone System_RCA | 11-Jun-25 A | 28-Aug-25 A | 2026-06-16 | 2026-06-16 | 11-Jun-25 A | 28-Aug-25 A
A51050 | Datasheet For Digital Network And Telephone System_IFD/IFC | 19-Dec-25 A | 23-Dec-25 A | 2026-06-16 | 2026-06-16 | 19-Dec-25 A | 23-Dec-25 A
WiringDiagramForProcessCctv |  | 08-Jan-25 A | 23-Dec-25 A | 2027-03-23 | 2027-03-23 | 08-Jan-25 A | 23-Dec-25 A
A51310 | Wiring Diagram For Process Cctv_IFR | 08-Jan-25 A | 12-Feb-25 A | 2027-03-23 | 2027-03-23 | 08-Jan-25 A | 12-Feb-25 A
A51320 | Wiring Diagram For Process Cctv_RCC | 13-Feb-25 A | 13-Mar-25 A | 2027-03-23 | 2027-03-23 | 13-Feb-25 A | 13-Mar-25 A
A51330 | Wiring Diagram For Process Cctv_IFA | 27-Oct-25 A | 03-Nov-25 A | 2027-03-23 | 2027-03-23 | 27-Oct-25 A | 03-Nov-25 A
A51340 | Wiring Diagram For Process Cctv_RCA | 04-Nov-25 A | 18-Nov-25 A | 2027-03-23 | 2027-03-23 | 04-Nov-25 A | 18-Nov-25 A
A51350 | Wiring Diagram For Process Cctv_IFD/IFC | 19-Dec-25 A | 23-Dec-25 A | 2027-03-23 | 2027-03-23 | 19-Dec-25 A | 23-Dec-25 A
WiringDiagramForPaga |  | 09-Jan-25 A | 19-Jan-26 A | 2027-03-23 | 2027-03-23 | 09-Jan-25 A | 19-Jan-26 A
A51360 | Wiring Diagram For Paga_IFR | 09-Jan-25 A | 12-Feb-25 A | 2027-03-23 | 2027-03-23 | 09-Jan-25 A | 12-Feb-25 A
A51370 | Wiring Diagram For Paga_RCC | 13-Feb-25 A | 13-Mar-25 A | 2027-03-23 | 2027-03-23 | 13-Feb-25 A | 13-Mar-25 A
A51380 | Wiring Diagram For Paga_IFA | 19-Dec-25 A | 24-Dec-25 A | 2027-03-23 | 2027-03-23 | 19-Dec-25 A | 24-Dec-25 A
A51390 | Wiring Diagram For Paga_RCA | 24-Dec-25 A | 15-Jan-26 A | 2027-03-23 | 2027-03-23 | 24-Dec-25 A | 15-Jan-26 A
A51400 | Wiring Diagram For Paga_IFD/IFC | 15-Jan-26 A | 19-Jan-26 A | 2027-03-23 | 2027-03-23 | 15-Jan-26 A | 19-Jan-26 A
WiringDiagramForDigitalNetworkAndTelephoneSystem |  | 22-Jan-25 A | 2026-06-16 | 2027-01-22 | 2027-03-23 | 22-Jan-25 A | 2026-04-21
A51410 | Wiring Diagram For Digital Network And Telephone System_IFR | 22-Jan-25 A | 2026-04-24 | 2027-01-22 | 2027-01-29 | 22-Jan-25 A | 2026-02-27
A51420 | Wiring Diagram For Digital Network And Telephone System_RCC | 2026-04-24 | 2026-05-18 | 2027-01-29 | 2027-02-22 | 2026-02-27 | 2026-03-23
A51430 | Wiring Diagram For Digital Network And Telephone System_IFA | 2026-05-18 | 2026-05-21 | 2027-02-22 | 2027-02-25 | 2026-03-23 | 2026-03-26
A51440 | Wiring Diagram For Digital Network And Telephone System_RCA | 2026-05-21 | 2026-06-12 | 2027-02-26 | 2027-03-19 | 2026-03-26 | 2026-04-17
A51450 | Wiring Diagram For Digital Network And Telephone System_IFD/IFC | 2026-06-12 | 2026-06-16 | 2027-03-19 | 2027-03-23 | 2026-04-17 | 2026-04-21
WiringDiagramForAccessControlSystem |  | 22-Jan-25 A | 2026-06-16 | 2027-01-22 | 2027-03-23 | 22-Jan-25 A | 2026-04-21
A51460 | Wiring Diagram For Access Control System_IFR | 22-Jan-25 A | 2026-04-24 | 2027-01-22 | 2027-01-29 | 22-Jan-25 A | 2026-02-27
A51470 | Wiring Diagram For Access Control System_RCC | 2026-04-24 | 2026-05-18 | 2027-01-29 | 2027-02-22 | 2026-02-27 | 2026-03-23
A51480 | Wiring Diagram For Access Control System_IFA | 2026-05-18 | 2026-05-21 | 2027-02-22 | 2027-02-25 | 2026-03-23 | 2026-03-26
A51490 | Wiring Diagram For Access Control System_RCA | 2026-05-21 | 2026-06-12 | 2027-02-26 | 2027-03-19 | 2026-03-26 | 2026-04-17
A51500 | Wiring Diagram For Access Control System_IFD/IFC | 2026-06-12 | 2026-06-16 | 2027-03-19 | 2027-03-23 | 2026-04-17 | 2026-04-21
MaterialRequisitionsForTelecomSystem(Paga,CCTV,ACS,Telephone&LANSystem) |  | 14-Mar-25 A | 22-Jan-26 A | 2026-06-16 | 2026-06-16 | 14-Mar-25 A | 22-Jan-26 A
A23780 | Material Requisitions For Telecom System (Paga, Cctv, Acs, Telephone & Lan System)_IFR | 14-Mar-25 A | 26-Apr-25 A | 2026-06-16 | 2026-06-16 | 14-Mar-25 A | 26-Apr-25 A
A23790 | Material Requisitions For Telecom System (Paga, Cctv, Acs, Telephone & Lan System)_RCC | 01-Jul-25 A | 29-Jul-25 A | 2026-06-16 | 2026-06-16 | 01-Jul-25 A | 29-Jul-25 A
A23800 | Material Requisitions For Telecom System (Paga, Cctv, Acs, Telephone & Lan System)_IFA | 24-Dec-25 A | 29-Dec-25 A | 2026-06-16 | 2026-06-16 | 24-Dec-25 A | 29-Dec-25 A
A23810 | Material Requisitions For Telecom System (Paga, Cctv, Acs, Telephone & Lan System)_RCA | 29-Dec-25 A | 20-Jan-26 A | 2026-06-16 | 2026-06-16 | 29-Dec-25 A | 20-Jan-26 A
A51910 | Material Requisitions For Telecom System (Paga, Cctv, Acs, Telephone & Lan System)_IFD/IFC | 20-Jan-26 A | 22-Jan-26 A | 2026-06-16 | 2026-06-16 | 20-Jan-26 A | 22-Jan-26 A
MaterialRequisitionsForTelecomCables |  | 01-May-25 A | 23-Dec-25 A | 2027-02-24 | 2027-03-23 | 01-May-25 A | 23-Dec-25 A
A23860 | Material Requisitions For Telecom Cables_RCA | 12-Nov-25 A | 21-Nov-25 A | 2027-03-23 | 2027-03-23 | 12-Nov-25 A | 21-Nov-25 A
A23870 | Material Requisitions For Telecom Cables_IFD/IFC | 19-Dec-25 A | 23-Dec-25 A | 2027-03-23 | 2027-03-23 | 19-Dec-25 A | 23-Dec-25 A
A51920 | Material Requisitions For Telecom Cables_IFR | 01-May-25 A | 22-May-25 A | 2027-02-24 | 2027-02-24 | 01-May-25 A | 22-May-25 A
A51930 | Material Requisitions For Telecom Cables_RCC | 01-Jul-25 A | 29-Jul-25 A | 2027-03-23 | 2027-03-23 | 01-Jul-25 A | 29-Jul-25 A
A51940 | Material Requisitions For Telecom Cables_IFA | 27-Oct-25 A | 11-Nov-25 A | 2027-03-23 | 2027-03-23 | 27-Oct-25 A | 11-Nov-25 A
TelecomEquipmentList |  | 10-Mar-25 A | 18-Dec-25 A | 2027-03-23 | 2027-03-23 | 10-Mar-25 A | 18-Dec-25 A
A23580 | Telecom Equipment List_IFR | 10-Mar-25 A | 27-Apr-25 A | 2027-03-23 | 2027-03-23 | 10-Mar-25 A | 27-Apr-25 A
A51760 | Telecom Equipment List_RCC | 28-Apr-25 A | 04-May-25 A | 2027-03-23 | 2027-03-23 | 28-Apr-25 A | 04-May-25 A
A51770 | Telecom Equipment List_IFA | 25-Aug-25 A | 15-Sep-25 A | 2027-03-23 | 2027-03-23 | 25-Aug-25 A | 15-Sep-25 A
A51780 | Telecom Equipment List_RCA | 10-Sep-25 A | 29-Sep-25 A | 2027-03-23 | 2027-03-23 | 10-Sep-25 A | 29-Sep-25 A
A51790 | Telecom Equipment List_IFD/IFC | 04-Dec-25 A | 18-Dec-25 A | 2027-03-23 | 2027-03-23 | 04-Dec-25 A | 18-Dec-25 A
TelecomCableSchedule |  | 14-Apr-25 A | 2026-05-18 | 2027-02-22 | 2027-03-23 | 14-Apr-25 A | 2026-03-23
A51640 | Telecom Cable Schedule_IFR | 14-Apr-25 A | 05-May-25 A | 2027-02-22 | 2027-02-22 | 14-Apr-25 A | 05-May-25 A
A51650 | Telecom Cable Schedule_RCC | 06-May-25 A | 29-Jul-25 A | 2027-02-22 | 2027-02-22 | 06-May-25 A | 29-Jul-25 A
A51660 | Telecom Cable Schedule_IFA | 2026-04-17 | 2026-04-22 | 2027-02-22 | 2027-02-25 | 2026-02-20 | 2026-02-25
A51670 | Telecom Cable Schedule_RCA | 2026-04-22 | 2026-05-14 | 2027-02-26 | 2027-03-19 | 2026-02-25 | 2026-03-19
A51680 | Telecom Cable Schedule_IFD/IFC | 2026-05-14 | 2026-05-18 | 2027-03-19 | 2027-03-23 | 2026-03-19 | 2026-03-23
TelecomJunctionBoxSchedule |  | 01-Aug-25 A | 23-Dec-25 A | 2027-03-23 | 2027-03-23 | 01-Aug-25 A | 23-Dec-25 A
A23520 | Telecom Junction Box Schedule_IFD/IFC | 19-Dec-25 A | 23-Dec-25 A | 2027-03-23 | 2027-03-23 | 19-Dec-25 A | 23-Dec-25 A
A51690 | Telecom Junction Box Schedule_IFR | 01-Aug-25 A | 15-Aug-25 A | 2027-03-23 | 2027-03-23 | 01-Aug-25 A | 15-Aug-25 A
A51700 | Telecom Junction Box Schedule_RCC | 04-Aug-25 A | 22-Aug-25 A | 2027-03-23 | 2027-03-23 | 04-Aug-25 A | 22-Aug-25 A
A51710 | Telecom Junction Box Schedule_IFA | 03-Nov-25 A | 11-Nov-25 A | 2027-03-23 | 2027-03-23 | 03-Nov-25 A | 11-Nov-25 A
A51720 | Telecom Junction Box Schedule_RCA | 12-Nov-25 A | 21-Nov-25 A | 2027-03-23 | 2027-03-23 | 12-Nov-25 A | 21-Nov-25 A
VoltageDropCalculationForPagaSystem |  | 2026-04-17 | 2026-06-16 | 2027-01-22 | 2027-03-23 | 2026-02-20 | 2026-04-21
A23550 | Voltage Drop Calculation For Paga System_IFA | 2026-05-18 | 2026-05-21 | 2027-02-22 | 2027-02-25 | 2026-03-23 | 2026-03-26
A23570 | Voltage Drop Calculation For Paga System_IFD/IFC | 2026-06-12 | 2026-06-16 | 2027-03-19 | 2027-03-23 | 2026-04-17 | 2026-04-21
A51730 | Voltage Drop Calculation For Paga System_IFR | 2026-04-17 | 2026-04-24 | 2027-01-22 | 2027-01-29 | 2026-02-20 | 2026-02-27
A51740 | Voltage Drop Calculation For Paga System_RCC | 2026-04-24 | 2026-05-18 | 2027-01-29 | 2027-02-22 | 2026-02-27 | 2026-03-23
A51750 | Voltage Drop Calculation For Paga System_RCA | 2026-05-21 | 2026-06-12 | 2027-02-26 | 2027-03-19 | 2026-03-26 | 2026-04-17
TechnicalBidEvaluationForTelecomCables |  | 01-Mar-26 A | 2026-05-14 | 2027-02-24 | 2027-03-23 | 2026-02-20 | 2026-04-21
A51980 | Technical Bid Evaluation For Telecom Cables_IFR | 11-Mar-26 A | 20-Mar-26 A | 2027-02-24 | 2027-02-24 | 2026-02-20 | 2026-02-27
A51990 | Technical Bid Evaluation For Telecom Cables_RCC | 01-Mar-26 A | 04-Mar-26 A | 2027-02-24 | 2027-02-24 | 2026-02-27 | 2026-03-23
A52000 | Technical Bid Evaluation For Telecom Cables_IFA | 05-Mar-26 A | 2026-05-11 | 2027-02-24 | 2027-03-19 | 2026-03-23 | 2026-03-26
A52010 | Technical Bid Evaluation For Telecom Cables_RCA | 19-Mar-26 A | 20-Mar-26 A | 2027-03-19 | 2027-03-19 | 2026-03-26 | 2026-04-17
A52020 | Technical Bid Evaluation For Telecom Cables_IFD/IFC | 2026-05-12 | 2026-05-14 | 2027-03-19 | 2027-03-23 | 2026-04-17 | 2026-04-21
CentralControlRoomEquipmentLayoutForTelecom |  | 01-Jul-25 A | 2026-05-12 | 2027-02-26 | 2027-03-23 | 01-Jul-25 A | 2026-03-17
A51840 | Central Control Room Equipment Layout For Telecom_IFR | 01-Jul-25 A | 13-Jul-25 A | 2027-02-26 | 2027-02-26 | 01-Jul-25 A | 13-Jul-25 A
A51850 | Central Control Room Equipment Layout For Telecom_RCC | 15-Aug-25 A | 15-Sep-25 A | 2027-02-26 | 2027-02-26 | 15-Aug-25 A | 15-Sep-25 A
A51860 | Central Control Room Equipment Layout For Telecom_IFA | 16-Sep-25 A | 29-Sep-25 A | 2027-02-26 | 2027-02-26 | 16-Sep-25 A | 29-Sep-25 A
A51870 | Central Control Room Equipment Layout For Telecom_RCA | 2026-04-17 | 2026-05-08 | 2027-02-26 | 2027-03-19 | 2026-02-20 | 2026-03-13
A51880 | Central Control Room Equipment Layout For Telecom_IFD/IFC | 2026-05-08 | 2026-05-12 | 2027-03-19 | 2027-03-23 | 2026-03-13 | 2026-03-17
TelecommunicationCoreAllocationDrawingForFiberOpticCable |  | 15-Apr-25 A | 23-Jan-26 A | 2027-03-23 | 2027-03-23 | 15-Apr-25 A | 23-Jan-26 A
A23750 | Telecommunication Core Allocation Drawing For Fiber Optic Cable_IFA | 03-Nov-25 A | 11-Nov-25 A | 2027-03-23 | 2027-03-23 | 03-Nov-25 A | 11-Nov-25 A
A23760 | Telecommunication Core Allocation Drawing For Fiber Optic Cable_RCA | 10-Nov-25 A | 21-Nov-25 A | 2027-03-23 | 2027-03-23 | 10-Nov-25 A | 21-Nov-25 A
A23770 | Telecommunication Core Allocation Drawing For Fiber Optic Cable_IFD/IFC | 23-Dec-25 A | 23-Jan-26 A | 2027-03-23 | 2027-03-23 | 23-Dec-25 A | 23-Jan-26 A
A51890 | Telecommunication Core Allocation Drawing For Fiber Optic Cable_IFR | 15-Apr-25 A | 28-Apr-25 A | 2027-03-23 | 2027-03-23 | 15-Apr-25 A | 28-Apr-25 A
A51900 | Telecommunication Core Allocation Drawing For Fiber Optic Cable_RCC | 29-Apr-25 A | 21-Jul-25 A | 2027-03-23 | 2027-03-23 | 29-Apr-25 A | 21-Jul-25 A
OverallTelecomCableRoutingLayoutDrawingForH2ExtractionUnit |  | 01-May-25 A | 23-Jan-26 A | 2027-01-22 | 2027-03-23 | 01-May-25 A | 23-Jan-26 A
A51560 | Overall Telecom Cable Routing Layout Drawing For H2 Extraction Unit_IFR | 01-May-25 A | 08-May-25 A | 2027-01-22 | 2027-01-22 | 01-May-25 A | 08-May-25 A
A51570 | Overall Telecom Cable Routing Layout Drawing For H2 Extraction Unit_RCC | 19-Dec-25 A | 25-Dec-25 A | 2027-03-23 | 2027-03-23 | 19-Dec-25 A | 25-Dec-25 A
A51580 | Overall Telecom Cable Routing Layout Drawing For H2 Extraction Unit_IFA | 25-Dec-25 A | 06-Jan-26 A | 2027-03-23 | 2027-03-23 | 25-Dec-25 A | 06-Jan-26 A
A51590 | Overall Telecom Cable Routing Layout Drawing For H2 Extraction Unit_RCA | 06-Jan-26 A | 14-Jan-26 A | 2027-03-23 | 2027-03-23 | 06-Jan-26 A | 14-Jan-26 A
A51600 | Overall Telecom Cable Routing Layout Drawing For H2 Extraction Unit_IFD/IFC | 10-Jan-26 A | 23-Jan-26 A | 2027-03-23 | 2027-03-23 | 10-Jan-26 A | 23-Jan-26 A
OverallTelecomEquipmentLayoutDrawingForH2ExtractionUnit |  | 01-May-25 A | 16-Jan-26 A | 2027-01-22 | 2027-03-23 | 01-May-25 A | 16-Jan-26 A
A51510 | Overall Telecom Equipment Layout Drawing For H2 Extraction Unit_IFR | 01-May-25 A | 20-May-25 A | 2027-01-22 | 2027-01-22 | 01-May-25 A | 20-May-25 A
A51520 | Overall Telecom Equipment Layout Drawing For H2 Extraction Unit_RCC | 21-May-25 A | 04-Jun-25 A | 2027-02-22 | 2027-02-22 | 21-May-25 A | 04-Jun-25 A
A51530 | Overall Telecom Equipment Layout Drawing For H2 Extraction Unit_IFA | 10-Oct-25 A | 16-Oct-25 A | 2027-02-22 | 2027-02-22 | 10-Oct-25 A | 16-Oct-25 A
A51540 | Overall Telecom Equipment Layout Drawing For H2 Extraction Unit_RCA | 17-Oct-25 A | 01-Nov-25 A | 2027-03-23 | 2027-03-23 | 17-Oct-25 A | 01-Nov-25 A
A51550 | Overall Telecom Equipment Layout Drawing For H2 Extraction Unit_IFD/IFC | 31-Dec-25 A | 16-Jan-26 A | 2027-03-23 | 2027-03-23 | 31-Dec-25 A | 16-Jan-26 A
TelecomSystemMaterialTakeOff |  | 02-Jul-25 A | 23-Dec-25 A | 2027-03-23 | 2027-03-23 | 02-Jul-25 A | 23-Dec-25 A
A51610 | Telecom System Material Take Off_IFR | 02-Jul-25 A | 18-Jul-25 A | 2027-03-23 | 2027-03-23 | 02-Jul-25 A | 18-Jul-25 A
A51620 | Telecom System Material Take Off_RCC | 07-Jul-25 A | 29-Jul-25 A | 2027-03-23 | 2027-03-23 | 07-Jul-25 A | 29-Jul-25 A
A51630 | Telecom System Material Take Off_IFD/IFC | 19-Dec-25 A | 23-Dec-25 A | 2027-03-23 | 2027-03-23 | 19-Dec-25 A | 23-Dec-25 A
Material/Corrosion |  | 15-Apr-25 A | 2026-05-18 | 2027-02-22 | 2027-03-23 | 15-Apr-25 A | 2026-03-23
MaterialSelection&CorrosionControlReport |  | 15-Apr-25 A | 2026-05-18 | 2027-02-22 | 2027-03-23 | 15-Apr-25 A | 2026-03-23
A24040 | Material Selection & Corrosion Control Report_RCC | 08-May-25 A | 03-Jun-25 A | 2027-02-22 | 2027-02-22 | 08-May-25 A | 03-Jun-25 A
A24050 | Material Selection & Corrosion Control Report_IFA | 2026-04-17 | 2026-04-22 | 2027-02-22 | 2027-02-25 | 2026-02-20 | 2026-02-25
A52070 | Material Selection & Corrosion Control Report_IFR | 15-Apr-25 A | 07-May-25 A | 2027-02-22 | 2027-02-22 | 15-Apr-25 A | 07-May-25 A
A52080 | Material Selection & Corrosion Control Report_RCA | 2026-04-22 | 2026-05-14 | 2027-02-26 | 2027-03-19 | 2026-02-25 | 2026-03-19
A52090 | Material Selection & Corrosion Control Report_IFD/IFC | 2026-05-14 | 2026-05-18 | 2027-03-19 | 2027-03-23 | 2026-03-19 | 2026-03-23
MaterialSelectionDiagrams(MSD) |  | 16-Apr-25 A | 2026-05-12 | 2027-02-26 | 2027-03-23 | 16-Apr-25 A | 2026-03-17
A24020 | Material Selection Diagrams (MSD)_IFD/IFC | 2026-05-08 | 2026-05-12 | 2027-03-19 | 2027-03-23 | 2026-03-13 | 2026-03-17
A52030 | Material Selection Diagrams (MSD)_IFR | 16-Apr-25 A | 25-Jul-25 A | 2027-02-26 | 2027-02-26 | 16-Apr-25 A | 25-Jul-25 A
A52040 | Material Selection Diagrams (MSD)_RCC | 25-Jul-25 A | 01-Aug-25 A | 2027-02-26 | 2027-02-26 | 25-Jul-25 A | 01-Aug-25 A
A52050 | Material Selection Diagrams (MSD)_IFA | 29-Nov-25 A | 18-Dec-25 A | 2027-02-26 | 2027-02-26 | 29-Nov-25 A | 18-Dec-25 A
A52060 | Material Selection Diagrams (MSD)_RCA | 2026-04-17 | 2026-05-08 | 2027-02-26 | 2027-03-19 | 2026-02-20 | 2026-03-13
HVAC |  | 13-Mar-25 A | 2026-06-09 | 2026-06-15 | 2027-03-23 | 03-Jun-25 A | 03-Jun-25 A
HVACDesignBasis |  | 13-Mar-25 A | 24-May-25 A | 2027-03-23 | 2027-03-23 | 13-Mar-25 A | 24-May-25 A
A52100 | HVAC Design Basis_IFR | 13-Mar-25 A | 26-Apr-25 A | 2027-03-23 | 2027-03-23 | 13-Mar-25 A | 26-Apr-25 A
A52110 | HVAC Design Basis_RCC | 27-Apr-25 A | 03-May-25 A | 2027-03-23 | 2027-03-23 | 27-Apr-25 A | 03-May-25 A
A52120 | HVAC Design Basis_IFA | 04-May-25 A | 10-May-25 A | 2027-03-23 | 2027-03-23 | 04-May-25 A | 10-May-25 A
A52130 | HVAC Design Basis_RCA | 11-May-25 A | 18-May-25 A | 2027-03-23 | 2027-03-23 | 11-May-25 A | 18-May-25 A
A52140 | HVAC Design Basis_IFD/IFC | 19-May-25 A | 24-May-25 A | 2027-03-23 | 2027-03-23 | 19-May-25 A | 24-May-25 A
HVACEquipmentAndAccessoriesSpecifications |  | 23-Mar-25 A | 19-May-25 A | 2027-03-23 | 2027-03-23 | 23-Mar-25 A | 19-May-25 A
A52150 | HVAC Equipment And Accessories Specifications_IFR | 23-Mar-25 A | 13-Apr-25 A | 2027-03-23 | 2027-03-23 | 23-Mar-25 A | 13-Apr-25 A
A52160 | HVAC Equipment And Accessories Specifications_RCC | 14-Apr-25 A | 22-Apr-25 A | 2027-03-23 | 2027-03-23 | 14-Apr-25 A | 22-Apr-25 A
A52170 | HVAC Equipment And Accessories Specifications_IFA | 23-Apr-25 A | 05-May-25 A | 2027-03-23 | 2027-03-23 | 23-Apr-25 A | 05-May-25 A
A52180 | HVAC Equipment And Accessories Specifications_RCA | 06-May-25 A | 12-May-25 A | 2027-03-23 | 2027-03-23 | 06-May-25 A | 12-May-25 A
A52190 | HVAC Equipment And Accessories Specifications_IFD/IFC | 13-May-25 A | 19-May-25 A | 2027-03-23 | 2027-03-23 | 13-May-25 A | 19-May-25 A
HVACCoolingLoadCalculationAndEquipmentSizing |  | 20-Apr-25 A | 03-Jun-25 A | 2026-06-15 | 2026-06-16 | 20-Apr-25 A | 03-Jun-25 A
A24210 | HVAC Cooling Load Calculation And Equipment Sizing_RCA | 26-May-25 A | 31-May-25 A | 2026-06-16 | 2026-06-16 | 26-May-25 A | 31-May-25 A
A24220 | HVAC Cooling Load Calculation And Equipment Sizing_IFD/IFC | 01-Jun-25 A | 03-Jun-25 A | 2026-06-16 | 2026-06-16 | 01-Jun-25 A | 03-Jun-25 A
A52200 | HVAC Cooling Load Calculation And Equipment Sizing_IFR | 20-Apr-25 A | 11-May-25 A | 2026-06-15 | 2026-06-15 | 20-Apr-25 A | 11-May-25 A
A52210 | HVAC Cooling Load Calculation And Equipment Sizing_RCC | 12-May-25 A | 18-May-25 A | 2026-06-16 | 2026-06-16 | 12-May-25 A | 18-May-25 A
A52220 | HVAC Cooling Load Calculation And Equipment Sizing_IFA | 23-May-25 A | 25-May-25 A | 2026-06-16 | 2026-06-16 | 23-May-25 A | 25-May-25 A
HVACAirflowSchematicDiagrams |  | 25-Apr-25 A | 25-Oct-25 A | 2027-01-03 | 2027-03-23 | 25-Apr-25 A | 25-Oct-25 A
A52540 | HVAC Airflow Schematic Diagrams_IFR | 25-Apr-25 A | 16-May-25 A | 2027-01-03 | 2027-01-03 | 25-Apr-25 A | 16-May-25 A
A52550 | HVAC Airflow Schematic Diagrams_RCC | 15-Jul-25 A | 01-Aug-25 A | 2027-03-23 | 2027-03-23 | 15-Jul-25 A | 01-Aug-25 A
A52560 | HVAC Airflow Schematic Diagrams_IFA | 29-Sep-25 A | 07-Oct-25 A | 2027-03-23 | 2027-03-23 | 29-Sep-25 A | 07-Oct-25 A
A52570 | HVAC Airflow Schematic Diagrams_RCA | 30-Sep-25 A | 20-Oct-25 A | 2027-03-23 | 2027-03-23 | 30-Sep-25 A | 20-Oct-25 A
A52580 | HVAC Airflow Schematic Diagrams_IFD/IFC | 21-Oct-25 A | 25-Oct-25 A | 2027-03-23 | 2027-03-23 | 21-Oct-25 A | 25-Oct-25 A
HVACChilledWaterPipingSchematicDiagrams |  | 20-Jun-25 A | 2026-06-09 | 2027-01-03 | 2027-03-23 | 20-Jun-25 A | 2026-04-14
A52590 | HVAC Chilled Water Piping Schematic Diagrams_IFR | 20-Jun-25 A | 05-Jul-25 A | 2027-01-03 | 2027-01-03 | 20-Jun-25 A | 05-Jul-25 A
A52600 | HVAC Chilled Water Piping Schematic Diagrams_RCC | 2026-04-17 | 2026-05-08 | 2027-01-29 | 2027-02-22 | 2026-02-20 | 2026-03-13
A52610 | HVAC Chilled Water Piping Schematic Diagrams_IFA | 2026-05-08 | 2026-05-14 | 2027-02-22 | 2027-02-25 | 2026-03-13 | 2026-03-19
A52620 | HVAC Chilled Water Piping Schematic Diagrams_RCA | 2026-05-14 | 2026-06-04 | 2027-02-26 | 2027-03-19 | 2026-03-19 | 2026-04-09
A52630 | HVAC Chilled Water Piping Schematic Diagrams_IFD/IFC | 2026-06-04 | 2026-06-09 | 2027-03-19 | 2027-03-23 | 2026-04-09 | 2026-04-14
HVACChilledWaterPipingAndInstrumentationDiagrams |  | 02-Jun-25 A | 2026-04-21 | 2027-01-03 | 2027-03-23 | 02-Jun-25 A | 2026-02-24
A52840 | HVAC Chilled Water Piping And Instrumentation Diagrams_IFR | 02-Jun-25 A | 05-Jul-25 A | 2027-01-03 | 2027-01-03 | 02-Jun-25 A | 05-Jul-25 A
A52850 | HVAC Chilled Water Piping And Instrumentation Diagrams_RCC | 11-Jul-25 A | 15-Aug-25 A | 2027-03-19 | 2027-03-19 | 11-Jul-25 A | 15-Aug-25 A
A52860 | HVAC Chilled Water Piping And Instrumentation Diagrams_IFH | 15-Aug-25 A | 22-Aug-25 A | 2027-03-19 | 2027-03-19 | 15-Aug-25 A | 22-Aug-25 A
A52870 | HVAC Chilled Water Piping And Instrumentation Diagrams_RCA | 25-Aug-25 A | 07-Oct-25 A | 2027-03-19 | 2027-03-19 | 25-Aug-25 A | 07-Oct-25 A
A52880 | HVAC Chilled Water Piping And Instrumentation Diagrams_IFD/IFC | 2026-04-17 | 2026-04-21 | 2027-03-19 | 2027-03-23 | 2026-02-20 | 2026-02-24
HVACDuctingandInstrumentationDiagrams |  | 17-Jun-25 A | 14-Oct-25 A | 2027-01-03 | 2027-03-23 | 17-Jun-25 A | 14-Oct-25 A
A52790 | HVAC Ducting and Instrumentation Diagrams_IFR | 17-Jun-25 A | 08-Jul-25 A | 2027-01-03 | 2027-01-03 | 17-Jun-25 A | 08-Jul-25 A
A52800 | HVAC Ducting and Instrumentation Diagrams_RCC | 09-Jul-25 A | 15-Aug-25 A | 2027-03-23 | 2027-03-23 | 09-Jul-25 A | 15-Aug-25 A
A52810 | HVAC Ducting and Instrumentation Diagrams_IFH | 18-Aug-25 A | 22-Aug-25 A | 2027-03-23 | 2027-03-23 | 18-Aug-25 A | 22-Aug-25 A
A52820 | HVAC Ducting and Instrumentation Diagrams_RCA | 29-Aug-25 A | 07-Oct-25 A | 2027-03-23 | 2027-03-23 | 29-Aug-25 A | 07-Oct-25 A
A52830 | HVAC Ducting and Instrumentation Diagrams_IFD/IFC | 08-Oct-25 A | 14-Oct-25 A | 2027-03-23 | 2027-03-23 | 08-Oct-25 A | 14-Oct-25 A
HVACEquipmentSchedules |  | 09-Jun-25 A | 2026-05-18 | 2027-02-22 | 2027-03-23 | 09-Jun-25 A | 2026-03-23
A52890 | HVAC Equipment Schedules_IFR | 09-Jun-25 A | 12-Jul-25 A | 2027-02-22 | 2027-02-22 | 09-Jun-25 A | 12-Jul-25 A
A52900 | HVAC Equipment Schedules_RCC | 17-Jun-25 A | 19-Jul-25 A | 2027-02-22 | 2027-02-22 | 17-Jun-25 A | 19-Jul-25 A
A52910 | HVAC Equipment Schedules_IFA | 2026-04-17 | 2026-04-22 | 2027-02-22 | 2027-02-25 | 2026-02-20 | 2026-02-25
A52920 | HVAC Equipment Schedules_RCA | 2026-04-22 | 2026-05-14 | 2027-02-26 | 2027-03-19 | 2026-02-25 | 2026-03-19
A52930 | HVAC Equipment Schedules_IFD/IFC | 2026-05-14 | 2026-05-18 | 2027-03-19 | 2027-03-23 | 2026-03-19 | 2026-03-23
HVACSystemCause&Effect |  | 21-Nov-25 A | 13-Jan-26 A | 2027-03-23 | 2027-03-23 | 21-Nov-25 A | 13-Jan-26 A
A52990 | HVAC System Cause & Effect_IFR | 21-Nov-25 A | 28-Nov-25 A | 2027-03-23 | 2027-03-23 | 21-Nov-25 A | 28-Nov-25 A
A53000 | HVAC System Cause & Effect_RCC | 27-Nov-25 A | 18-Dec-25 A | 2027-03-23 | 2027-03-23 | 27-Nov-25 A | 18-Dec-25 A
A53010 | HVAC System Cause & Effect_IFA | 18-Dec-25 A | 19-Dec-25 A | 2027-03-23 | 2027-03-23 | 18-Dec-25 A | 19-Dec-25 A
A53020 | HVAC System Cause & Effect_RCA | 19-Dec-25 A | 09-Jan-26 A | 2027-03-23 | 2027-03-23 | 19-Dec-25 A | 09-Jan-26 A
A53030 | HVAC System Cause & Effect_IFD/IFC | 09-Jan-26 A | 13-Jan-26 A | 2027-03-23 | 2027-03-23 | 09-Jan-26 A | 13-Jan-26 A
HVACChilledWaterPumpHeadCalculation |  | 01-Oct-25 A | 10-Nov-25 A | 2027-03-23 | 2027-03-23 | 01-Oct-25 A | 10-Nov-25 A
A53090 | HVAC Chilled Water Pump Head Calculation_IFR | 01-Oct-25 A | 13-Oct-25 A | 2027-03-23 | 2027-03-23 | 01-Oct-25 A | 13-Oct-25 A
A53100 | HVAC Chilled Water Pump Head Calculation_RCC | 14-Oct-25 A | 25-Oct-25 A | 2027-03-23 | 2027-03-23 | 14-Oct-25 A | 25-Oct-25 A
A53110 | HVAC Chilled Water Pump Head Calculation_IFA | 24-Oct-25 A | 28-Oct-25 A | 2027-03-23 | 2027-03-23 | 24-Oct-25 A | 28-Oct-25 A
A53120 | HVAC Chilled Water Pump Head Calculation_RCA | 28-Oct-25 A | 31-Oct-25 A | 2027-03-23 | 2027-03-23 | 28-Oct-25 A | 31-Oct-25 A
A53130 | HVAC Chilled Water Pump Head Calculation_IFD/IFC | 01-Nov-25 A | 10-Nov-25 A | 2027-03-23 | 2027-03-23 | 01-Nov-25 A | 10-Nov-25 A
HVACTechnicalDataSheetForAirHandlingUnit |  | 01-May-25 A | 10-Oct-25 A | 2026-06-15 | 2026-06-16 | 01-May-25 A | 10-Oct-25 A
A52240 | HVAC Technical Data Sheet For Air Handling Unit_IFR | 01-May-25 A | 22-May-25 A | 2026-06-15 | 2026-06-15 | 01-May-25 A | 22-May-25 A
A52250 | HVAC Technical Data Sheet For Air Handling Unit_RCC | 23-May-25 A | 10-Jun-25 A | 2026-06-16 | 2026-06-16 | 23-May-25 A | 10-Jun-25 A
A52260 | HVAC Technical Data Sheet For Air Handling Unit_IFA | 11-Jun-25 A | 26-Jun-25 A | 2026-06-16 | 2026-06-16 | 11-Jun-25 A | 26-Jun-25 A
A52270 | HVAC Technical Data Sheet For Air Handling Unit_RCA | 27-Jun-25 A | 10-Sep-25 A | 2026-06-16 | 2026-06-16 | 27-Jun-25 A | 10-Sep-25 A
A52280 | HVAC Technical Data Sheet For Air Handling Unit_IFD/IFC | 15-Sep-25 A | 10-Oct-25 A | 2026-06-16 | 2026-06-16 | 15-Sep-25 A | 10-Oct-25 A
HVACTechnicalDataSheetForAirCooledChiller |  | 26-May-25 A | 10-Jun-25 A | 2026-06-15 | 2026-06-16 | 26-May-25 A | 10-Jun-25 A
A24230 | HVAC Technical Data Sheet For Air Cooled Chiller_IFR | 26-May-25 A | 28-May-25 A | 2026-06-15 | 2026-06-15 | 26-May-25 A | 28-May-25 A
A24240 | HVAC Technical Data Sheet For Air Cooled Chiller_RCC | 29-May-25 A | 31-May-25 A | 2026-06-16 | 2026-06-16 | 29-May-25 A | 31-May-25 A
A24250 | HVAC Technical Data Sheet For Air Cooled Chiller_IFA | 01-Jun-25 A | 04-Jun-25 A | 2026-06-16 | 2026-06-16 | 01-Jun-25 A | 04-Jun-25 A
A24260 | HVAC Technical Data Sheet For Air Cooled Chiller_RCA | 05-Jun-25 A | 07-Jun-25 A | 2026-06-16 | 2026-06-16 | 05-Jun-25 A | 07-Jun-25 A
A52230 | HVAC Technical Data Sheet For Air Cooled Chiller_IFD/IFC | 08-Jun-25 A | 10-Jun-25 A | 2026-06-16 | 2026-06-16 | 08-Jun-25 A | 10-Jun-25 A
HVACTechnicalDataSheetForChilledWaterPump |  | 26-May-25 A | 10-Oct-25 A | 2026-06-15 | 2026-06-16 | 26-May-25 A | 10-Oct-25 A
A52290 | HVAC Technical Data Sheet For Chilled Water Pump_IFR | 26-May-25 A | 05-Jul-25 A | 2026-06-15 | 2026-06-15 | 26-May-25 A | 05-Jul-25 A
A52300 | HVAC Technical Data Sheet For Chilled Water Pump_RCC | 06-Jul-25 A | 01-Aug-25 A | 2026-06-16 | 2026-06-16 | 06-Jul-25 A | 01-Aug-25 A
A52310 | HVAC Technical Data Sheet For Chilled Water Pump_IFA | 02-Aug-25 A | 27-Aug-25 A | 2026-06-16 | 2026-06-16 | 02-Aug-25 A | 27-Aug-25 A
A52320 | HVAC Technical Data Sheet For Chilled Water Pump_RCA | 28-Aug-25 A | 10-Sep-25 A | 2026-06-16 | 2026-06-16 | 28-Aug-25 A | 10-Sep-25 A
A52330 | HVAC Technical Data Sheet For Chilled Water Pump_IFD/IFC | 15-Sep-25 A | 10-Oct-25 A | 2026-06-16 | 2026-06-16 | 15-Sep-25 A | 10-Oct-25 A
HVACTechnicalDataSheetForChemicalFilterUnit |  | 26-May-25 A | 10-Oct-25 A | 2026-06-15 | 2026-06-16 | 26-May-25 A | 10-Oct-25 A
A52340 | HVAC Technical Data Sheet For Chemical Filter Unit_IFR | 26-May-25 A | 05-Jul-25 A | 2026-06-15 | 2026-06-15 | 26-May-25 A | 05-Jul-25 A
A52350 | HVAC Technical Data Sheet For Chemical Filter Unit_RCC | 06-Jul-25 A | 01-Aug-25 A | 2026-06-16 | 2026-06-16 | 06-Jul-25 A | 01-Aug-25 A
A52360 | HVAC Technical Data Sheet For Chemical Filter Unit_IFA | 02-Aug-25 A | 29-Aug-25 A | 2026-06-16 | 2026-06-16 | 02-Aug-25 A | 29-Aug-25 A
A52370 | HVAC Technical Data Sheet For Chemical Filter Unit_RCA | 30-Aug-25 A | 12-Sep-25 A | 2026-06-16 | 2026-06-16 | 30-Aug-25 A | 12-Sep-25 A
A52380 | HVAC Technical Data Sheet For Chemical Filter Unit_IFD/IFC | 15-Sep-25 A | 10-Oct-25 A | 2026-06-16 | 2026-06-16 | 15-Sep-25 A | 10-Oct-25 A
HVACTechnicalDataSheetForInertiaFilterWithBleedFan |  | 26-May-25 A | 21-Nov-25 A | 2026-06-15 | 2026-06-16 | 26-May-25 A | 21-Nov-25 A
A52390 | HVAC Technical Data Sheet For Inertia Filter With Bleed Fan_IFR | 26-May-25 A | 05-Jul-25 A | 2026-06-15 | 2026-06-15 | 26-May-25 A | 05-Jul-25 A
A52400 | HVAC Technical Data Sheet For Inertia Filter With Bleed Fan_RCC | 06-Jul-25 A | 30-Jul-25 A | 2026-06-16 | 2026-06-16 | 06-Jul-25 A | 30-Jul-25 A
A52410 | HVAC Technical Data Sheet For Inertia Filter With Bleed Fan_IFA | 31-Jul-25 A | 22-Aug-25 A | 2026-06-16 | 2026-06-16 | 31-Jul-25 A | 22-Aug-25 A
A52420 | HVAC Technical Data Sheet For Inertia Filter With Bleed Fan_RCA | 23-Aug-25 A | 10-Sep-25 A | 2026-06-16 | 2026-06-16 | 23-Aug-25 A | 10-Sep-25 A
A52430 | HVAC Technical Data Sheet For Inertia Filter With Bleed Fan_IFD/IFC | 17-Nov-25 A | 21-Nov-25 A | 2026-06-16 | 2026-06-16 | 17-Nov-25 A | 21-Nov-25 A
HVACTechnicalDataSheetForExhaustAirFans |  | 26-May-25 A | 15-Sep-25 A | 2026-06-15 | 2026-06-16 | 26-May-25 A | 15-Sep-25 A
A52440 | HVAC Technical Data Sheet For Exhaust Air Fans_IFR | 26-May-25 A | 05-Jul-25 A | 2026-06-15 | 2026-06-15 | 26-May-25 A | 05-Jul-25 A
A52450 | HVAC Technical Data Sheet For Exhaust Air Fans_RCC | 06-Jul-25 A | 01-Aug-25 A | 2026-06-16 | 2026-06-16 | 06-Jul-25 A | 01-Aug-25 A
A52460 | HVAC Technical Data Sheet For Exhaust Air Fans_IFA | 02-Aug-25 A | 01-Sep-25 A | 2026-06-16 | 2026-06-16 | 02-Aug-25 A | 01-Sep-25 A
A52470 | HVAC Technical Data Sheet For Exhaust Air Fans_RCA | 02-Sep-25 A | 08-Sep-25 A | 2026-06-16 | 2026-06-16 | 02-Sep-25 A | 08-Sep-25 A
A52480 | HVAC Technical Data Sheet For Exhaust Air Fans_IFD/IFC | 09-Sep-25 A | 15-Sep-25 A | 2026-06-16 | 2026-06-16 | 09-Sep-25 A | 15-Sep-25 A
HVACTechnicalDataSheetForElectricDuctHeater |  | 26-May-25 A | 15-Sep-25 A | 2026-06-15 | 2026-06-16 | 26-May-25 A | 15-Sep-25 A
A52490 | HVAC Technical Data Sheet For Electric Duct Heater_IFR | 26-May-25 A | 01-Jun-25 A | 2026-06-15 | 2026-06-15 | 26-May-25 A | 01-Jun-25 A
A52500 | HVAC Technical Data Sheet For Electric Duct Heater_RCC | 02-Jun-25 A | 15-Jun-25 A | 2026-06-16 | 2026-06-16 | 02-Jun-25 A | 15-Jun-25 A
A52510 | HVAC Technical Data Sheet For Electric Duct Heater_IFA | 16-Jun-25 A | 20-Jun-25 A | 2026-06-16 | 2026-06-16 | 16-Jun-25 A | 20-Jun-25 A
A52520 | HVAC Technical Data Sheet For Electric Duct Heater_RCA | 21-Jun-25 A | 08-Sep-25 A | 2026-06-16 | 2026-06-16 | 21-Jun-25 A | 08-Sep-25 A
A52530 | HVAC Technical Data Sheet For Electric Duct Heater_IFD/IFC | 09-Sep-25 A | 15-Sep-25 A | 2026-06-16 | 2026-06-16 | 09-Sep-25 A | 15-Sep-25 A
HVACChilledWaterPipingLayouts&Sections |  | 10-Jul-25 A | 13-Jan-26 A | 2027-03-23 | 2027-03-23 | 10-Jul-25 A | 13-Jan-26 A
A52740 | HVAC Chilled Water Piping Layouts & Sections_IFR | 10-Jul-25 A | 07-Oct-25 A | 2027-03-23 | 2027-03-23 | 10-Jul-25 A | 07-Oct-25 A
A52750 | HVAC Chilled Water Piping Layouts & Sections_RCC | 08-Oct-25 A | 31-Oct-25 A | 2027-03-23 | 2027-03-23 | 08-Oct-25 A | 31-Oct-25 A
A52760 | HVAC Chilled Water Piping Layouts & Sections_IFA | 28-Nov-25 A | 10-Dec-25 A | 2027-03-23 | 2027-03-23 | 28-Nov-25 A | 10-Dec-25 A
A52770 | HVAC Chilled Water Piping Layouts & Sections_RCA | 19-Dec-25 A | 09-Jan-26 A | 2027-03-23 | 2027-03-23 | 19-Dec-25 A | 09-Jan-26 A
A52780 | HVAC Chilled Water Piping Layouts & Sections_IFD/IFC | 09-Jan-26 A | 13-Jan-26 A | 2027-03-23 | 2027-03-23 | 09-Jan-26 A | 13-Jan-26 A
HVACSystemSequenceOfOperationAndControlPhilosophy |  | 01-Jul-25 A | 04-Dec-25 A | 2027-03-23 | 2027-03-23 | 01-Jul-25 A | 04-Dec-25 A
A52940 | HVAC System Sequence Of Operation And Control Philosophy_IFR | 01-Jul-25 A | 16-Jul-25 A | 2027-03-23 | 2027-03-23 | 01-Jul-25 A | 16-Jul-25 A
A52950 | HVAC System Sequence Of Operation And Control Philosophy_RCC | 17-Jul-25 A | 22-Aug-25 A | 2027-03-23 | 2027-03-23 | 17-Jul-25 A | 22-Aug-25 A
A52960 | HVAC System Sequence Of Operation And Control Philosophy_IFA | 01-Oct-25 A | 28-Oct-25 A | 2027-03-23 | 2027-03-23 | 01-Oct-25 A | 28-Oct-25 A
A52970 | HVAC System Sequence Of Operation And Control Philosophy_RCA | 29-Oct-25 A | 17-Nov-25 A | 2027-03-23 | 2027-03-23 | 29-Oct-25 A | 17-Nov-25 A
A52980 | HVAC System Sequence Of Operation And Control Philosophy_IFD/IFC | 24-Nov-25 A | 04-Dec-25 A | 2027-03-23 | 2027-03-23 | 24-Nov-25 A | 04-Dec-25 A
MaterialRequisitionForHVACEquipments |  | 02-Jun-25 A | 19-Nov-25 A | 2026-06-15 | 2026-06-16 | 02-Jun-25 A | 19-Nov-25 A
A53190 | Material Requisition For HVAC Equipments_IFR | 02-Jun-25 A | 05-Jul-25 A | 2026-06-15 | 2026-06-15 | 02-Jun-25 A | 05-Jul-25 A
A53200 | Material Requisition For HVAC Equipments_RCC | 04-Jul-25 A | 30-Jul-25 A | 2026-06-16 | 2026-06-16 | 04-Jul-25 A | 30-Jul-25 A
A53210 | Material Requisition For HVAC Equipments_IFA | 29-Aug-25 A | 01-Oct-25 A | 2026-06-16 | 2026-06-16 | 29-Aug-25 A | 01-Oct-25 A
A53220 | Material Requisition For HVAC Equipments_RCA | 01-Oct-25 A | 24-Oct-25 A | 2026-06-16 | 2026-06-16 | 01-Oct-25 A | 24-Oct-25 A
A53230 | Material Requisition For HVAC Equipments_IFD/IFC | 27-Oct-25 A | 19-Nov-25 A | 2026-06-16 | 2026-06-16 | 27-Oct-25 A | 19-Nov-25 A
MaterialRequisitionforFireDetectionSystem&LFCP |  | 09-Jun-25 A | 25-Dec-25 A | 2026-06-15 | 2026-06-16 | 09-Jun-25 A | 25-Dec-25 A
A15420 | Material Requisition for Fire Detection System & LFCP_IFD/IFC | 23-Dec-25 A | 25-Dec-25 A | 2026-06-16 | 2026-06-16 | 23-Dec-25 A | 25-Dec-25 A
A47780 | Material Requisition for Fire Detection System & LFCP_IFR | 09-Jun-25 A | 05-Jul-25 A | 2026-06-15 | 2026-06-15 | 09-Jun-25 A | 05-Jul-25 A
A47790 | Material Requisition for Fire Detection System & LFCP_RCC | 07-Jul-25 A | 30-Jul-25 A | 2026-06-16 | 2026-06-16 | 07-Jul-25 A | 30-Jul-25 A
A47800 | Material Requisition for Fire Detection System & LFCP_IFA | 31-Jul-25 A | 26-Aug-25 A | 2026-06-16 | 2026-06-16 | 31-Jul-25 A | 26-Aug-25 A
A47810 | Material Requisition for Fire Detection System & LFCP_RCA | 15-Aug-25 A | 10-Sep-25 A | 2026-06-16 | 2026-06-16 | 15-Aug-25 A | 10-Sep-25 A
HVACEquipmentAndDuctingLayouts |  | 29-Jun-25 A | 18-Dec-25 A | 2027-01-03 | 2027-01-03 | 29-Jun-25 A | 18-Dec-25 A
A52640 | HVAC Equipment And Ducting Layouts_IFR | 29-Jun-25 A | 18-Jul-25 A | 2027-01-03 | 2027-01-03 | 29-Jun-25 A | 18-Jul-25 A
A52650 | HVAC Equipment And Ducting Layouts_RCC | 01-Aug-25 A | 14-Oct-25 A | 2027-01-03 | 2027-01-03 | 01-Aug-25 A | 14-Oct-25 A
A52660 | HVAC Equipment And Ducting Layouts_IFA | 01-Oct-25 A | 24-Oct-25 A | 2027-01-03 | 2027-01-03 | 01-Oct-25 A | 24-Oct-25 A
A52670 | HVAC Equipment And Ducting Layouts_RCA | 27-Oct-25 A | 21-Nov-25 A | 2027-01-03 | 2027-01-03 | 27-Oct-25 A | 21-Nov-25 A
A52680 | HVAC Equipment And Ducting Layouts_IFD/IFC | 02-Dec-25 A | 18-Dec-25 A | 2027-01-03 | 2027-01-03 | 02-Dec-25 A | 18-Dec-25 A
HVACDuctingSectionLayout |  | 03-Aug-25 A | 23-Dec-25 A | 2027-03-23 | 2027-03-23 | 03-Aug-25 A | 23-Dec-25 A
A52690 | HVAC Ducting Section Layout_IFR | 03-Aug-25 A | 18-Aug-25 A | 2027-03-23 | 2027-03-23 | 03-Aug-25 A | 18-Aug-25 A
A52700 | HVAC Ducting Section Layout_RCC | 19-Aug-25 A | 22-Aug-25 A | 2027-03-23 | 2027-03-23 | 19-Aug-25 A | 22-Aug-25 A
A52710 | HVAC Ducting Section Layout_IFA | 25-Aug-25 A | 26-Sep-25 A | 2027-03-23 | 2027-03-23 | 25-Aug-25 A | 26-Sep-25 A
A52720 | HVAC Ducting Section Layout_RCA | 15-Sep-25 A | 14-Oct-25 A | 2027-03-23 | 2027-03-23 | 15-Sep-25 A | 14-Oct-25 A
A52730 | HVAC Ducting Section Layout_IFD/IFC | 19-Dec-25 A | 23-Dec-25 A | 2027-03-23 | 2027-03-23 | 19-Dec-25 A | 23-Dec-25 A
HVACExternalStaticPressureCalculation |  | 31-Jan-26 A | 2026-04-21 | 2027-03-19 | 2027-03-23 | 2026-02-20 | 2026-04-21
A53040 | HVAC External Static Pressure Calculation_IFR | 31-Jan-26 A | 05-Feb-26 A | 2027-03-19 | 2027-03-19 | 2026-02-20 | 2026-02-27
A53050 | HVAC External Static Pressure Calculation_RCC | 01-Feb-26 A | 12-Feb-26 A | 2027-03-19 | 2027-03-19 | 2026-02-27 | 2026-03-23
A53060 | HVAC External Static Pressure Calculation_IFA | 01-Feb-26 A | 27-Feb-26 A | 2027-03-19 | 2027-03-19 | 2026-03-23 | 2026-03-26
A53070 | HVAC External Static Pressure Calculation_RCA | 01-Mar-26 A | 20-Mar-26 A | 2027-03-19 | 2027-03-19 | 2026-03-26 | 2026-04-17
A53080 | HVAC External Static Pressure Calculation_IFD/IFC | 2026-04-17 | 2026-04-21 | 2027-03-19 | 2027-03-23 | 2026-04-17 | 2026-04-21
HVACStandardInstallationDetails |  | 25-Apr-25 A | 07-Oct-25 A | 2027-03-23 | 2027-03-23 | 25-Apr-25 A | 07-Oct-25 A
A53140 | HVAC Standard Installation Details_IFR | 25-Apr-25 A | 16-May-25 A | 2027-03-23 | 2027-03-23 | 25-Apr-25 A | 16-May-25 A
A53150 | HVAC Standard Installation Details_RCC | 17-May-25 A | 10-Jun-25 A | 2027-03-23 | 2027-03-23 | 17-May-25 A | 10-Jun-25 A
A53160 | HVAC Standard Installation Details_IFA | 11-Jun-25 A | 20-Jun-25 A | 2027-03-23 | 2027-03-23 | 11-Jun-25 A | 20-Jun-25 A
A53170 | HVAC Standard Installation Details_RCA | 13-Jun-25 A | 30-Jun-25 A | 2027-03-23 | 2027-03-23 | 13-Jun-25 A | 30-Jun-25 A
A53180 | HVAC Standard Installation Details_IFD/IFC | 30-Jul-25 A | 07-Oct-25 A | 2027-03-23 | 2027-03-23 | 30-Jul-25 A | 07-Oct-25 A
TechnicalBidEvaluationforFireDetectionSystem&LFCP |  | 01-Oct-25 A | 19-Jan-26 A | 2026-06-15 | 2027-03-23 | 01-Oct-25 A | 19-Jan-26 A
A16940 | Technical Bid Evaluation for Fire Detection System & LFCP_RCC | 20-Oct-25 A | 06-Nov-25 A | 2026-06-15 | 2026-06-15 | 20-Oct-25 A | 06-Nov-25 A
A16950 | Technical Bid Evaluation for Fire Detection System & LFCP_IFA | 19-Dec-25 A | 24-Dec-25 A | 2026-06-15 | 2026-06-15 | 19-Dec-25 A | 24-Dec-25 A
A16960 | Technical Bid Evaluation for Fire Detection System & LFCP_RCA | 24-Dec-25 A | 15-Jan-26 A | 2027-03-23 | 2027-03-23 | 24-Dec-25 A | 15-Jan-26 A
A16970 | Technical Bid Evaluation for Fire Detection System & LFCP_IFD/IFC | 15-Jan-26 A | 19-Jan-26 A | 2027-03-23 | 2027-03-23 | 15-Jan-26 A | 19-Jan-26 A
A48260 | Technical Bid Evaluation for Fire Detection System & LFCP_IFR | 01-Oct-25 A | 09-Oct-25 A | 2026-06-15 | 2026-06-15 | 01-Oct-25 A | 09-Oct-25 A
Procurement-HOServices |  | 01-Jan-25 A | 2026-06-25 | 2026-06-09 | 2027-05-07 | 01-Jan-25 A | 2026-07-24
EquipmentPackages |  | 01-Jan-25 A | 2026-05-18 | 2026-06-15 | 2027-05-07 | 01-Jan-25 A | 15-Oct-25 A
Vessels |  | 01-Jan-25 A | 2026-05-18 | 2026-06-16 | 2027-05-07 | 01-Jan-25 A | 20-Jun-25 A
HydrogenProductFilter |  | 08-Oct-25 A | 30-Mar-26 A | 2027-04-07 | 2027-04-07
A63960 | Issue RFQ to Bidders | 08-Oct-25 A | 13-Oct-25 A | 2027-04-07 | 2027-04-07
A63970 | Issue Purchase Order to Vendor | 26-Mar-26 A | 30-Mar-26 A | 2027-04-07 | 2027-04-07
A63980 | Bid Evaluation(Completion) | 20-Nov-25 A | 24-Dec-25 A | 2027-04-07 | 2027-04-07
A63990 | Commercial Bid Evaluation(Completion) | 26-Dec-25 A | 16-Jan-26 A | 2027-04-07 | 2027-04-07
ActiveCarbonFilter |  | 06-Feb-26 A | 30-Mar-26 A | 2027-04-07 | 2027-04-07
A64000 | Issue RFQ to Bidders | 06-Feb-26 A | 10-Feb-26 A | 2027-04-07 | 2027-04-07
A64010 | Issue Purchase Order to Vendor | 24-Mar-26 A | 30-Mar-26 A | 2027-04-07 | 2027-04-07
A64020 | Bid Evaluation(Completion) | 27-Feb-26 A | 18-Mar-26 A | 2027-04-07 | 2027-04-07
A64030 | Commercial Bid Evaluation(Completion) | 17-Mar-26 A | 27-Mar-26 A | 2027-04-07 | 2027-04-07
InstrumentAirVessels |  | 06-Oct-25 A | 2026-05-18 | 2027-04-08 | 2027-05-07
A64040 | Issue RFQ to Bidders | 06-Oct-25 A | 10-Oct-25 A | 2027-04-08 | 2027-04-08
A64050 | Issue Purchase Order to Vendor | 2026-05-08 | 2026-05-18 | 2027-04-29 | 2027-05-07
A64060 | Bid Evaluation(Completion) | 2026-04-17 | 2026-04-27 | 2027-04-08 | 2027-04-16
A64070 | Commercial Bid Evaluation(Completion) | 2026-04-28 | 2026-05-07 | 2027-04-19 | 2027-04-28
C4GuardAdsorberCooler-(BF) |  | 01-Jan-25 A | 20-Jun-25 A | 2026-06-16 | 2026-11-12 | 01-Jan-25 A | 20-Jun-25 A
A57190 | Technical Bid Evaluation for Pressure Vessels & Internals_IFR | 28-Apr-25 A | 03-May-25 A | 2026-06-16 | 2026-06-16 | 28-Apr-25 A | 03-May-25 A
A57200 | Technical Bid Evaluation for Pressure Vessels & Internals_RCC | 04-May-25 A | 03-Jun-25 A | 2026-06-16 | 2026-06-16 | 04-May-25 A | 03-Jun-25 A
A57210 | Technical Bid Evaluation for Pressure Vessels & Internals_IFA | 04-Jun-25 A | 08-Jun-25 A | 2026-06-16 | 2026-06-16 | 04-Jun-25 A | 08-Jun-25 A
A57220 | Technical Bid Evaluation for Pressure Vessels & Internals_RCA | 09-Jun-25 A | 14-Jun-25 A | 2026-11-12 | 2026-11-12 | 09-Jun-25 A | 14-Jun-25 A
A57230 | Technical Bid Evaluation for Pressure Vessels & Internals_IFD/IFC | 15-Jun-25 A | 20-Jun-25 A | 2026-11-12 | 2026-11-12 | 15-Jun-25 A | 20-Jun-25 A
A8310 | Issue RFQ to Bidders | 01-Jan-25 A | 14-Jan-25 A | 2026-06-16 | 2026-06-16 | 01-Jan-25 A | 14-Jan-25 A
A8340 | Issue Purchase Order to Vendor | 20-Jun-25 A | 20-Jun-25 A | 2026-11-12 | 2026-11-12 | 20-Jun-25 A | 20-Jun-25 A
Vessel'sInternals(05Dimisterpads) |  | 01-Jan-25 A | 20-Jun-25 A | 2026-06-16 | 2026-09-16 | 01-Jan-25 A | 20-Jun-25 A
A15970 | Issue RFQ to Bidders | 01-Jan-25 A | 14-Jan-25 A | 2026-06-16 | 2026-06-16 | 01-Jan-25 A | 14-Jan-25 A
A18020 | Issue Purchase Order to Vendor | 20-Jun-25 A | 20-Jun-25 A | 2026-09-16 | 2026-09-16 | 20-Jun-25 A | 20-Jun-25 A
A18040 | Commercial Bid Evaluation(Completion) | 15-Jun-25 A | 20-Jun-25 A | 2026-09-16 | 2026-09-16 | 15-Jun-25 A | 20-Jun-25 A
A56540 | Technical Bid Evaluation for Pressure Vessels & Internals_IFR | 28-Apr-25 A | 03-May-25 A | 2026-06-16 | 2026-06-16 | 28-Apr-25 A | 03-May-25 A
A56550 | Technical Bid Evaluation for Pressure Vessels & Internals_RCC | 04-May-25 A | 03-Jun-25 A | 2026-06-16 | 2026-06-16 | 04-May-25 A | 03-Jun-25 A
A56560 | Technical Bid Evaluation for Pressure Vessels & Internals_IFA | 04-Jun-25 A | 08-Jun-25 A | 2026-06-16 | 2026-06-16 | 04-Jun-25 A | 08-Jun-25 A
A56570 | Technical Bid Evaluation for Pressure Vessels & Internals_RCA | 09-Jun-25 A | 14-Jun-25 A | 2026-09-16 | 2026-09-16 | 09-Jun-25 A | 14-Jun-25 A
A56580 | Technical Bid Evaluation for Pressure Vessels & Internals_IFD/IFC | 09-Jun-25 A | 14-Jun-25 A | 2026-09-16 | 2026-09-16 | 09-Jun-25 A | 14-Jun-25 A
Vessels/Drums |  | 01-Jan-25 A | 20-Jun-25 A | 2026-06-16 | 2026-09-26 | 01-Jan-25 A | 20-Jun-25 A
FGComp.2ndStageSuc.Drum(13-VV-706) |  | 01-Jan-25 A | 20-Jun-25 A | 2026-06-16 | 2026-09-08 | 01-Jan-25 A | 20-Jun-25 A
A35900 | Issue RFQ to Bidders | 01-Jan-25 A | 14-Jan-25 A | 2026-06-16 | 2026-06-16 | 01-Jan-25 A | 14-Jan-25 A
A35920 | Commercial Bid Evaluation(Completion) | 15-Jun-25 A | 20-Jun-25 A | 2026-09-08 | 2026-09-08 | 15-Jun-25 A | 20-Jun-25 A
A35930 | Issue Purchase Order to Vendor | 20-Jun-25 A | 20-Jun-25 A | 2026-09-08 | 2026-09-08 | 20-Jun-25 A | 20-Jun-25 A
A45960 | Technical Bid Evaluation for Pressure Vessels & Internals_IFR | 28-Apr-25 A | 03-May-25 A | 2026-06-16 | 2026-06-16 | 28-Apr-25 A | 03-May-25 A
A45970 | Technical Bid Evaluation for Pressure Vessels & Internals_RCC | 25-Mar-25 A | 27-Mar-25 A | 2026-06-16 | 2026-06-16 | 25-Mar-25 A | 27-Mar-25 A
A45980 | Technical Bid Evaluation for Pressure Vessels & Internals_IFA | 28-Mar-25 A | 29-Mar-25 A | 2026-06-16 | 2026-06-16 | 28-Mar-25 A | 29-Mar-25 A
A45990 | Technical Bid Evaluation for Pressure Vessels & Internals_RCA | 30-Mar-25 A | 31-Mar-25 A | 2026-09-08 | 2026-09-08 | 30-Mar-25 A | 31-Mar-25 A
A46000 | Technical Bid Evaluation for Pressure Vessels & Internals_IFD/IFC | 31-Mar-25 A | 01-Apr-25 A | 2026-09-08 | 2026-09-08 | 31-Mar-25 A | 01-Apr-25 A
FGComp.1stStageSuc.Drum(13-VV-705) |  | 01-Jan-25 A | 07-Apr-25 A | 2026-06-16 | 2026-09-08 | 01-Jan-25 A | 07-Apr-25 A
A17540 | Issue RFQ to Bidders | 01-Jan-25 A | 14-Jan-25 A | 2026-06-16 | 2026-06-16 | 01-Jan-25 A | 14-Jan-25 A
A56290 | Technical Bid Evaluation for Pressure Vessels & Internals_IFR | 23-Mar-25 A | 24-Mar-25 A | 2026-06-16 | 2026-06-16 | 23-Mar-25 A | 24-Mar-25 A
A56300 | Technical Bid Evaluation for Pressure Vessels & Internals_RCC | 25-Mar-25 A | 27-Mar-25 A | 2026-06-16 | 2026-06-16 | 25-Mar-25 A | 27-Mar-25 A
A56310 | Technical Bid Evaluation for Pressure Vessels & Internals_IFA | 28-Mar-25 A | 29-Mar-25 A | 2026-06-16 | 2026-06-16 | 28-Mar-25 A | 29-Mar-25 A
A56320 | Technical Bid Evaluation for Pressure Vessels & Internals_RCA | 30-Mar-25 A | 31-Mar-25 A | 2026-09-08 | 2026-09-08 | 30-Mar-25 A | 31-Mar-25 A
A56330 | Technical Bid Evaluation for Pressure Vessels & Internals_IFD/IFC | 01-Apr-25 A | 02-Apr-25 A | 2026-09-08 | 2026-09-08 | 01-Apr-25 A | 02-Apr-25 A
A9200 | Issue Purchase Order to Vendor | 04-Apr-25 A | 07-Apr-25 A | 2026-09-08 | 2026-09-08 | 04-Apr-25 A | 07-Apr-25 A
A9220 | Commercial Bid Evaluation(Completion) | 03-Apr-25 A | 04-Apr-25 A | 2026-09-08 | 2026-09-08 | 03-Apr-25 A | 04-Apr-25 A
PSA2SlopDrum(70-VV-1415) |  | 01-Jan-25 A | 12-Apr-25 A | 2026-06-16 | 2026-09-26 | 01-Jan-25 A | 12-Apr-25 A
A35940 | Issue RFQ to Bidders | 01-Jan-25 A | 14-Jan-25 A | 2026-06-16 | 2026-06-16 | 01-Jan-25 A | 14-Jan-25 A
A35960 | Commercial Bid Evaluation(Completion) | 02-Apr-25 A | 03-Apr-25 A | 2026-09-26 | 2026-09-26 | 02-Apr-25 A | 03-Apr-25 A
A35970 | Issue Purchase Order to Vendor | 04-Apr-25 A | 12-Apr-25 A | 2026-09-26 | 2026-09-26 | 04-Apr-25 A | 12-Apr-25 A
A56340 | Technical Bid Evaluation for Pressure Vessels & Internals_IFR | 23-Mar-25 A | 24-Mar-25 A | 2026-06-16 | 2026-06-16 | 23-Mar-25 A | 24-Mar-25 A
A56350 | Technical Bid Evaluation for Pressure Vessels & Internals_RCC | 25-Mar-25 A | 27-Mar-25 A | 2026-06-16 | 2026-06-16 | 25-Mar-25 A | 27-Mar-25 A
A56360 | Technical Bid Evaluation for Pressure Vessels & Internals_IFA | 28-Mar-25 A | 29-Mar-25 A | 2026-06-16 | 2026-06-16 | 28-Mar-25 A | 29-Mar-25 A
A56370 | Technical Bid Evaluation for Pressure Vessels & Internals_RCA | 30-Mar-25 A | 31-Mar-25 A | 2026-09-26 | 2026-09-26 | 30-Mar-25 A | 31-Mar-25 A
A56380 | Technical Bid Evaluation for Pressure Vessels & Internals_IFD/IFC | 31-Mar-25 A | 01-Apr-25 A | 2026-09-26 | 2026-09-26 | 31-Mar-25 A | 01-Apr-25 A
OGComp.2ndStageSuc.Drum(13-VV-713) |  | 01-Jan-25 A | 12-Apr-25 A | 2026-06-16 | 2026-09-15 | 01-Jan-25 A | 12-Apr-25 A
A35980 | Issue RFQ to Bidders | 01-Jan-25 A | 14-Jan-25 A | 2026-06-16 | 2026-06-16 | 01-Jan-25 A | 14-Jan-25 A
A36000 | Commercial Bid Evaluation(Completion) | 02-Apr-25 A | 03-Apr-25 A | 2026-09-15 | 2026-09-15 | 02-Apr-25 A | 03-Apr-25 A
A36010 | Issue Purchase Order to Vendor | 04-Apr-25 A | 12-Apr-25 A | 2026-09-15 | 2026-09-15 | 04-Apr-25 A | 12-Apr-25 A
A56390 | Technical Bid Evaluation for Pressure Vessels & Internals_IFR | 23-Mar-25 A | 24-Mar-25 A | 2026-06-16 | 2026-06-16 | 23-Mar-25 A | 24-Mar-25 A
A56400 | Technical Bid Evaluation for Pressure Vessels & Internals_RCC | 25-Mar-25 A | 27-Mar-25 A | 2026-06-16 | 2026-06-16 | 25-Mar-25 A | 27-Mar-25 A
A56410 | Technical Bid Evaluation for Pressure Vessels & Internals_IFA | 28-Mar-25 A | 29-Mar-25 A | 2026-06-16 | 2026-06-16 | 28-Mar-25 A | 29-Mar-25 A
A56420 | Technical Bid Evaluation for Pressure Vessels & Internals_RCA | 30-Mar-25 A | 31-Mar-25 A | 2026-09-15 | 2026-09-15 | 30-Mar-25 A | 31-Mar-25 A
A56430 | Technical Bid Evaluation for Pressure Vessels & Internals_IFD/IFC | 31-Mar-25 A | 01-Apr-25 A | 2026-09-15 | 2026-09-15 | 31-Mar-25 A | 01-Apr-25 A
FGComp.2ndStageDis.Drum(13-VV-707) |  | 01-Jan-25 A | 12-Apr-25 A | 2026-06-16 | 2026-08-28 | 01-Jan-25 A | 12-Apr-25 A
A36020 | Issue RFQ to Bidders | 01-Jan-25 A | 14-Jan-25 A | 2026-06-16 | 2026-06-16 | 01-Jan-25 A | 14-Jan-25 A
A36040 | Commercial Bid Evaluation(Completion) | 02-Apr-25 A | 03-Apr-25 A | 2026-08-28 | 2026-08-28 | 02-Apr-25 A | 03-Apr-25 A
A36050 | Issue Purchase Order to Vendor | 04-Apr-25 A | 12-Apr-25 A | 2026-08-28 | 2026-08-28 | 04-Apr-25 A | 12-Apr-25 A
A56440 | Technical Bid Evaluation for Pressure Vessels & Internals_IFR | 23-Mar-25 A | 24-Mar-25 A | 2026-06-16 | 2026-06-16 | 23-Mar-25 A | 24-Mar-25 A
A56450 | Technical Bid Evaluation for Pressure Vessels & Internals_RCC | 25-Mar-25 A | 27-Mar-25 A | 2026-06-16 | 2026-06-16 | 25-Mar-25 A | 27-Mar-25 A
A56460 | Technical Bid Evaluation for Pressure Vessels & Internals_IFA | 28-Mar-25 A | 29-Mar-25 A | 2026-06-16 | 2026-06-16 | 28-Mar-25 A | 29-Mar-25 A
A56470 | Technical Bid Evaluation for Pressure Vessels & Internals_RCA | 30-Mar-25 A | 31-Mar-25 A | 2026-08-28 | 2026-08-28 | 30-Mar-25 A | 31-Mar-25 A
A56480 | Technical Bid Evaluation for Pressure Vessels & Internals_IFD/IFC | 31-Mar-25 A | 01-Apr-25 A | 2026-08-28 | 2026-08-28 | 31-Mar-25 A | 01-Apr-25 A
OGBufferDrum(13-VV-712) |  | 01-Jan-25 A | 12-Apr-25 A | 2026-06-16 | 2026-09-26 | 01-Jan-25 A | 12-Apr-25 A
A36060 | Issue RFQ to Bidders | 01-Jan-25 A | 22-Mar-25 A | 2026-06-16 | 2026-06-16 | 01-Jan-25 A | 22-Mar-25 A
A36080 | Commercial Bid Evaluation(Completion) | 02-Apr-25 A | 03-Apr-25 A | 2026-09-26 | 2026-09-26 | 02-Apr-25 A | 03-Apr-25 A
A36090 | Issue Purchase Order to Vendor | 04-Apr-25 A | 12-Apr-25 A | 2026-09-26 | 2026-09-26 | 04-Apr-25 A | 12-Apr-25 A
A56490 | Technical Bid Evaluation for Pressure Vessels & Internals_IFR | 23-Mar-25 A | 24-Mar-25 A | 2026-06-16 | 2026-06-16 | 23-Mar-25 A | 24-Mar-25 A
A56500 | Technical Bid Evaluation for Pressure Vessels & Internals_RCC | 25-Mar-25 A | 27-Mar-25 A | 2026-06-16 | 2026-06-16 | 25-Mar-25 A | 27-Mar-25 A
A56510 | Technical Bid Evaluation for Pressure Vessels & Internals_IFA | 28-Mar-25 A | 29-Mar-25 A | 2026-06-16 | 2026-06-16 | 28-Mar-25 A | 29-Mar-25 A
A56520 | Technical Bid Evaluation for Pressure Vessels & Internals_RCA | 30-Mar-25 A | 31-Mar-25 A | 2026-09-26 | 2026-09-26 | 30-Mar-25 A | 31-Mar-25 A
A56530 | Technical Bid Evaluation for Pressure Vessels & Internals_IFD/IFC | 31-Mar-25 A | 01-Apr-25 A | 2026-09-26 | 2026-09-26 | 31-Mar-25 A | 01-Apr-25 A
WaterCollection&SanitaryWastewaterPumps |  | 01-Apr-25 A | 15-Oct-25 A | 2026-09-26 | 2026-09-26 | 01-Apr-25 A | 15-Oct-25 A
SanitaryWasteWaterSumpPump |  | 01-Apr-25 A | 15-Oct-25 A | 2026-09-26 | 2026-09-26 | 01-Apr-25 A | 15-Oct-25 A
A19470 | Issue Purchase Order to Vendor | 15-Sep-25 A | 17-Sep-25 A | 2026-09-26 | 2026-09-26 | 15-Sep-25 A | 17-Sep-25 A
A19490 | Commercial Bid Evaluation(Completion) | 08-Sep-25 A | 12-Sep-25 A | 2026-09-26 | 2026-09-26 | 08-Sep-25 A | 12-Sep-25 A
A45810 | Technical Bid Evaluation for Centrifugal Pump_IFR | 10-Jun-25 A | 12-Jun-25 A | 2026-09-26 | 2026-09-26 | 10-Jun-25 A | 12-Jun-25 A
A45820 | Technical Bid Evaluation for Centrifugal Pump_RCC | 13-Jun-25 A | 18-Jun-25 A | 2026-09-26 | 2026-09-26 | 13-Jun-25 A | 18-Jun-25 A
A45830 | Technical Bid Evaluation for Centrifugal Pump_IFA | 04-Jul-25 A | 23-Aug-25 A | 2026-09-26 | 2026-09-26 | 04-Jul-25 A | 23-Aug-25 A
A45840 | Technical Bid Evaluation for Centrifugal Pump_RCA | 24-Aug-25 A | 30-Aug-25 A | 2026-09-26 | 2026-09-26 | 24-Aug-25 A | 30-Aug-25 A
A45850 | Technical Bid Evaluation for Centrifugal Pump_IFD/IFC | 01-Sep-25 A | 15-Oct-25 A | 2026-09-26 | 2026-09-26 | 01-Sep-25 A | 15-Oct-25 A
A8430 | RFQs to Bid Receipt | 01-Apr-25 A | 10-Apr-25 A | 2026-09-26 | 2026-09-26 | 01-Apr-25 A | 10-Apr-25 A
WaterCollectionSumpPumpll |  | 01-Apr-25 A | 05-Aug-25 A | 2026-09-26 | 2026-09-26 | 01-Apr-25 A | 05-Aug-25 A
A19410 | Issue Purchase Order to Vendor | 30-Jul-25 A | 05-Aug-25 A | 2026-09-26 | 2026-09-26 | 30-Jul-25 A | 05-Aug-25 A
A19430 | Commercial Bid Evaluation(Completion) | 18-Jul-25 A | 29-Jul-25 A | 2026-09-26 | 2026-09-26 | 18-Jul-25 A | 29-Jul-25 A
A56890 | Technical Bid Evaluation for Centrifugal Pump_IFR | 10-Jun-25 A | 12-Jun-25 A | 2026-09-26 | 2026-09-26 | 10-Jun-25 A | 12-Jun-25 A
A56900 | Technical Bid Evaluation for Centrifugal Pump_RCC | 13-Jun-25 A | 18-Jun-25 A | 2026-09-26 | 2026-09-26 | 13-Jun-25 A | 18-Jun-25 A
A56910 | Technical Bid Evaluation for Centrifugal Pump_IFA | 19-Jun-25 A | 23-Jun-25 A | 2026-09-26 | 2026-09-26 | 19-Jun-25 A | 23-Jun-25 A
A56920 | Technical Bid Evaluation for Centrifugal Pump_RCA | 24-Jun-25 A | 29-Jun-25 A | 2026-09-26 | 2026-09-26 | 24-Jun-25 A | 29-Jun-25 A
A56930 | Technical Bid Evaluation for Centrifugal Pump_IFD/IFC | 30-Jun-25 A | 03-Jul-25 A | 2026-09-26 | 2026-09-26 | 30-Jun-25 A | 03-Jul-25 A
A8490 | RFQs to Bid Receipt | 01-Apr-25 A | 10-Apr-25 A | 2026-09-26 | 2026-09-26 | 01-Apr-25 A | 10-Apr-25 A
EOTCranes |  | 01-May-25 A | 18-Sep-25 A | 2026-06-15 | 2026-08-11 | 01-May-25 A | 18-Sep-25 A
EOTCraneforFGCompressor(1=60Ton) |  | 01-May-25 A | 13-Aug-25 A | 2026-06-15 | 2026-08-11 | 01-May-25 A | 13-Aug-25 A
A20470 | Issue Purchase Order to Vendor | 07-Aug-25 A | 13-Aug-25 A | 2026-08-11 | 2026-08-11 | 07-Aug-25 A | 13-Aug-25 A
A20490 | Commercial Bid Evaluation(Completion) | 23-Jul-25 A | 06-Aug-25 A | 2026-08-11 | 2026-08-11 | 23-Jul-25 A | 06-Aug-25 A
A45860 | Technical Bid Evaluation for EOT Crane_IFR | 20-Jun-25 A | 24-Jun-25 A | 2026-06-15 | 2026-06-15 | 20-Jun-25 A | 24-Jun-25 A
A45870 | Technical Bid Evaluation for EOT Crane_RCC | 25-Jun-25 A | 30-Jun-25 A | 2026-06-15 | 2026-06-15 | 25-Jun-25 A | 30-Jun-25 A
A45880 | Technical Bid Evaluation for EOT Crane_IFA | 30-Jun-25 A | 06-Jul-25 A | 2026-06-15 | 2026-06-15 | 30-Jun-25 A | 06-Jul-25 A
A45890 | Technical Bid Evaluation for EOT Crane_RCA | 06-Jul-25 A | 12-Jul-25 A | 2026-08-11 | 2026-08-11 | 06-Jul-25 A | 12-Jul-25 A
A45900 | Technical Bid Evaluation for EOT Crane_IFD/IFC | 13-Jul-25 A | 22-Jul-25 A | 2026-08-11 | 2026-08-11 | 13-Jul-25 A | 22-Jul-25 A
A8370 | Issue RFQ to Bidders | 01-May-25 A | 15-May-25 A | 2026-06-15 | 2026-06-15 | 01-May-25 A | 15-May-25 A
EOTCraneforOGCompressor(1=25Ton) |  | 01-May-25 A | 18-Sep-25 A | 2026-06-15 | 2026-08-11 | 01-May-25 A | 18-Sep-25 A
A20530 | Issue Purchase Order to Vendor | 17-Sep-25 A | 18-Sep-25 A | 2026-08-11 | 2026-08-11 | 17-Sep-25 A | 18-Sep-25 A
A20550 | Commercial Bid Evaluation(Completion) | 15-Sep-25 A | 17-Sep-25 A | 2026-08-11 | 2026-08-11 | 15-Sep-25 A | 17-Sep-25 A
A56940 | Technical Bid Evaluation for EOT Crane_IFR | 20-Jun-25 A | 15-Aug-25 A | 2026-06-15 | 2026-06-15 | 20-Jun-25 A | 15-Aug-25 A
A56950 | Technical Bid Evaluation for EOT Crane_RCC | 16-Aug-25 A | 22-Aug-25 A | 2026-06-15 | 2026-06-15 | 16-Aug-25 A | 22-Aug-25 A
A56960 | Technical Bid Evaluation for EOT Crane_IFA | 23-Aug-25 A | 30-Aug-25 A | 2026-06-15 | 2026-06-15 | 23-Aug-25 A | 30-Aug-25 A
A56970 | Technical Bid Evaluation for EOT Crane_RCA | 01-Sep-25 A | 05-Sep-25 A | 2026-08-11 | 2026-08-11 | 01-Sep-25 A | 05-Sep-25 A
A56980 | Technical Bid Evaluation for EOT Crane_IFD/IFC | 01-Sep-25 A | 12-Sep-25 A | 2026-08-11 | 2026-08-11 | 01-Sep-25 A | 12-Sep-25 A
A8250 | Issue RFQ to Bidders | 01-May-25 A | 20-Jun-25 A | 2026-06-15 | 2026-06-15 | 01-May-25 A | 20-Jun-25 A
HeatExchangers |  | 01-Jun-25 A | 02-Jul-25 A | 2026-08-05 | 2026-09-26 | 01-Jun-25 A | 02-Jul-25 A
HeatExchanger(TypeS&T=06Nos) |  | 01-Jun-25 A | 02-Jul-25 A | 2026-08-05 | 2026-09-26 | 01-Jun-25 A | 02-Jul-25 A
FGComp.InterstageCooler(BEM)-Tag#13-HE-703 |  | 01-Jun-25 A | 27-Jun-25 A | 2026-08-05 | 2026-08-05 | 01-Jun-25 A | 27-Jun-25 A
A36100 | Issue RFQ to Bidders | 01-Jun-25 A | 03-Jun-25 A | 2026-08-05 | 2026-08-05 | 01-Jun-25 A | 03-Jun-25 A
A36120 | Commercial Bid Evaluation(Completion) | 20-Jun-25 A | 24-Jun-25 A | 2026-08-05 | 2026-08-05 | 20-Jun-25 A | 24-Jun-25 A
A36130 | Issue Purchase Order to Vendor | 25-Jun-25 A | 27-Jun-25 A | 2026-08-05 | 2026-08-05 | 25-Jun-25 A | 27-Jun-25 A
A45460 | Technical Bid Evaluation for Heat Exchangers_IFR | 04-Jun-25 A | 07-Jun-25 A | 2026-08-05 | 2026-08-05 | 04-Jun-25 A | 07-Jun-25 A
A45470 | Technical Bid Evaluation for Heat Exchangers_RCC | 08-Jun-25 A | 11-Jun-25 A | 2026-08-05 | 2026-08-05 | 08-Jun-25 A | 11-Jun-25 A
A45480 | Technical Bid Evaluation for Heat Exchangers_IFA | 12-Jun-25 A | 14-Jun-25 A | 2026-08-05 | 2026-08-05 | 12-Jun-25 A | 14-Jun-25 A
A45490 | Technical Bid Evaluation for Heat Exchangers_RCA | 15-Jun-25 A | 17-Jun-25 A | 2026-08-05 | 2026-08-05 | 15-Jun-25 A | 17-Jun-25 A
A45500 | Technical Bid Evaluation for Heat Exchangers_IFD/IFC | 18-Jun-25 A | 20-Jun-25 A | 2026-08-05 | 2026-08-05 | 18-Jun-25 A | 20-Jun-25 A
OGComp.AfterCooler(BEU)-Tag#13-HE-709 |  | 01-Jun-25 A | 27-Jun-25 A | 2026-09-07 | 2026-09-07 | 01-Jun-25 A | 27-Jun-25 A
A36140 | Issue RFQ to Bidders | 01-Jun-25 A | 03-Jun-25 A | 2026-09-07 | 2026-09-07 | 01-Jun-25 A | 03-Jun-25 A
A36160 | Commercial Bid Evaluation(Completion) | 20-Jun-25 A | 24-Jun-25 A | 2026-09-07 | 2026-09-07 | 20-Jun-25 A | 24-Jun-25 A
A36170 | Issue Purchase Order to Vendor | 25-Jun-25 A | 27-Jun-25 A | 2026-09-07 | 2026-09-07 | 25-Jun-25 A | 27-Jun-25 A
A56640 | Technical Bid Evaluation for Heat Exchangers_IFR | 04-Jun-25 A | 07-Jun-25 A | 2026-09-07 | 2026-09-07 | 04-Jun-25 A | 07-Jun-25 A
A56650 | Technical Bid Evaluation for Heat Exchangers_RCC | 08-Jun-25 A | 11-Jun-25 A | 2026-09-07 | 2026-09-07 | 08-Jun-25 A | 11-Jun-25 A
A56660 | Technical Bid Evaluation for Heat Exchangers_IFA | 12-Jun-25 A | 14-Jun-25 A | 2026-09-07 | 2026-09-07 | 12-Jun-25 A | 14-Jun-25 A
A56670 | Technical Bid Evaluation for Heat Exchangers_RCA | 15-Jun-25 A | 17-Jun-25 A | 2026-09-07 | 2026-09-07 | 15-Jun-25 A | 17-Jun-25 A
A56680 | Technical Bid Evaluation for Heat Exchangers_IFD/IFC | 18-Jun-25 A | 20-Jun-25 A | 2026-09-07 | 2026-09-07 | 18-Jun-25 A | 20-Jun-25 A
FGComp.AfterCooler(BEM)-Tag#13-HE-704 |  | 01-Jun-25 A | 27-Jun-25 A | 2026-08-05 | 2026-08-05 | 01-Jun-25 A | 27-Jun-25 A
A36950 | Issue RFQ to Bidders | 01-Jun-25 A | 03-Jun-25 A | 2026-08-05 | 2026-08-05 | 01-Jun-25 A | 03-Jun-25 A
A36970 | Commercial Bid Evaluation(Completion) | 20-Jun-25 A | 24-Jun-25 A | 2026-08-05 | 2026-08-05 | 20-Jun-25 A | 24-Jun-25 A
A36980 | Issue Purchase Order to Vendor | 25-Jun-25 A | 27-Jun-25 A | 2026-08-05 | 2026-08-05 | 25-Jun-25 A | 27-Jun-25 A
A56690 | Technical Bid Evaluation for Heat Exchangers_IFR | 04-Jun-25 A | 07-Jun-25 A | 2026-08-05 | 2026-08-05 | 04-Jun-25 A | 07-Jun-25 A
A56700 | Technical Bid Evaluation for Heat Exchangers_RCC | 08-Jun-25 A | 11-Jun-25 A | 2026-08-05 | 2026-08-05 | 08-Jun-25 A | 11-Jun-25 A
A56710 | Technical Bid Evaluation for Heat Exchangers_IFA | 12-Jun-25 A | 14-Jun-25 A | 2026-08-05 | 2026-08-05 | 12-Jun-25 A | 14-Jun-25 A
A56720 | Technical Bid Evaluation for Heat Exchangers_RCA | 15-Jun-25 A | 17-Jun-25 A | 2026-08-05 | 2026-08-05 | 15-Jun-25 A | 17-Jun-25 A
A56730 | Technical Bid Evaluation for Heat Exchangers_IFD/IFC | 18-Jun-25 A | 20-Jun-25 A | 2026-08-05 | 2026-08-05 | 18-Jun-25 A | 20-Jun-25 A
OGComp.InterstageCooler(BEU)(13-HE-708) |  | 01-Jun-25 A | 27-Jun-25 A | 2026-09-07 | 2026-09-07 | 01-Jun-25 A | 27-Jun-25 A
A36990 | Issue RFQ to Bidders | 01-Jun-25 A | 03-Jun-25 A | 2026-09-07 | 2026-09-07 | 01-Jun-25 A | 03-Jun-25 A
A37010 | Commercial Bid Evaluation(Completion) | 20-Jun-25 A | 24-Jun-25 A | 2026-09-07 | 2026-09-07 | 20-Jun-25 A | 24-Jun-25 A
A37020 | Issue Purchase Order to Vendor | 25-Jun-25 A | 27-Jun-25 A | 2026-09-07 | 2026-09-07 | 25-Jun-25 A | 27-Jun-25 A
A56740 | Technical Bid Evaluation for Heat Exchangers_IFR | 04-Jun-25 A | 07-Jun-25 A | 2026-09-07 | 2026-09-07 | 04-Jun-25 A | 07-Jun-25 A
A56750 | Technical Bid Evaluation for Heat Exchangers_RCC | 08-Jun-25 A | 11-Jun-25 A | 2026-09-07 | 2026-09-07 | 08-Jun-25 A | 11-Jun-25 A
A56760 | Technical Bid Evaluation for Heat Exchangers_IFA | 12-Jun-25 A | 14-Jun-25 A | 2026-09-07 | 2026-09-07 | 12-Jun-25 A | 14-Jun-25 A
A56770 | Technical Bid Evaluation for Heat Exchangers_RCA | 15-Jun-25 A | 17-Jun-25 A | 2026-09-07 | 2026-09-07 | 15-Jun-25 A | 17-Jun-25 A
A56780 | Technical Bid Evaluation for Heat Exchangers_IFD/IFC | 18-Jun-25 A | 20-Jun-25 A | 2026-09-07 | 2026-09-07 | 18-Jun-25 A | 20-Jun-25 A
C4GuardRegen.GasCooler(BEU)(Tag#50-HE-1410) |  | 01-Jun-25 A | 02-Jul-25 A | 2026-09-26 | 2026-09-26 | 01-Jun-25 A | 02-Jul-25 A
A37030 | Issue RFQ to Bidders | 01-Jun-25 A | 03-Jun-25 A | 2026-09-26 | 2026-09-26 | 01-Jun-25 A | 03-Jun-25 A
A37050 | Commercial Bid Evaluation(Completion) | 20-Jun-25 A | 27-Jun-25 A | 2026-09-26 | 2026-09-26 | 20-Jun-25 A | 27-Jun-25 A
A37060 | Issue Purchase Order to Vendor | 30-Jun-25 A | 02-Jul-25 A | 2026-09-26 | 2026-09-26 | 30-Jun-25 A | 02-Jul-25 A
A56790 | Technical Bid Evaluation for Heat Exchangers_IFR | 04-Jun-25 A | 07-Jun-25 A | 2026-09-26 | 2026-09-26 | 04-Jun-25 A | 07-Jun-25 A
A56800 | Technical Bid Evaluation for Heat Exchangers_RCC | 08-Jun-25 A | 11-Jun-25 A | 2026-09-26 | 2026-09-26 | 08-Jun-25 A | 11-Jun-25 A
A56810 | Technical Bid Evaluation for Heat Exchangers_IFA | 12-Jun-25 A | 14-Jun-25 A | 2026-09-26 | 2026-09-26 | 12-Jun-25 A | 14-Jun-25 A
A56820 | Technical Bid Evaluation for Heat Exchangers_RCA | 15-Jun-25 A | 17-Jun-25 A | 2026-09-26 | 2026-09-26 | 15-Jun-25 A | 17-Jun-25 A
A56830 | Technical Bid Evaluation for Heat Exchangers_IFD/IFC | 18-Jun-25 A | 20-Jun-25 A | 2026-09-26 | 2026-09-26 | 18-Jun-25 A | 20-Jun-25 A
HVAC |  | 25-May-25 A | 29-Aug-25 A | 2026-10-15 | 2026-10-15 | 03-Jun-25 A | 03-Jun-25 A
HVAC |  | 25-May-25 A | 29-Aug-25 A | 2026-10-15 | 2026-10-15 | 03-Jun-25 A | 03-Jun-25 A
A16510 | Issue RFQ to Bidders | 25-May-25 A | 03-Jun-25 A | 2026-10-15 | 2026-10-15 | 25-May-25 A | 03-Jun-25 A
A19870 | Issue Purchase Order to Vendor | 20-Aug-25 A | 29-Aug-25 A | 2026-10-15 | 2026-10-15 | 20-Aug-25 A | 29-Aug-25 A
A19890 | Commercial Bid Evaluation(Completion) | 15-Jul-25 A | 31-Jul-25 A | 2026-10-15 | 2026-10-15 | 15-Jul-25 A | 31-Jul-25 A
A25290 | Technical Bid Evaluation For HVAC Equipments_RCC | 20-Jun-25 A | 25-Jun-25 A | 2026-10-15 | 2026-10-15 | 20-Jun-25 A | 25-Jun-25 A
A25300 | Technical Bid Evaluation For HVAC Equipments_IFA | 26-Jun-25 A | 02-Jul-25 A | 2026-10-15 | 2026-10-15 | 26-Jun-25 A | 02-Jul-25 A
A25310 | Technical Bid Evaluation For HVAC Equipments_RCA | 03-Jul-25 A | 08-Jul-25 A | 2026-10-15 | 2026-10-15 | 03-Jul-25 A | 08-Jul-25 A
A25320 | Technical Bid Evaluation For HVAC Equipments_IFD/IFC | 09-Jul-25 A | 14-Jul-25 A | 2026-10-15 | 2026-10-15 | 09-Jul-25 A | 14-Jul-25 A
A53240 | Technical Bid Evaluation For HVAC Equipments_IFR | 04-Jun-25 A | 19-Jun-25 A | 2026-10-15 | 2026-10-15 | 04-Jun-25 A | 19-Jun-25 A
BulkMaterials |  | 15-Jan-25 A | 2026-06-25 | 2026-06-09 | 2027-03-23 | 15-Jan-25 A | 2026-07-24
DripLeg |  | 01-Aug-25 A | 09-Sep-25 A | 2026-06-16 | 2026-06-29 | 01-Aug-25 A | 09-Sep-25 A
OGComp.Dis.Dripleg(02Nos) |  | 01-Aug-25 A | 09-Sep-25 A | 2026-06-16 | 2026-06-29 | 01-Aug-25 A | 09-Sep-25 A
A19350 | Issue Purchase Order to Vendor | 04-Sep-25 A | 09-Sep-25 A | 2026-06-29 | 2026-06-29 | 04-Sep-25 A | 09-Sep-25 A
A19370 | Commercial Bid Evaluation(Completion) | 30-Aug-25 A | 03-Sep-25 A | 2026-06-29 | 2026-06-29 | 30-Aug-25 A | 03-Sep-25 A
A56840 | Technical Bid Evaluation for Pressure Vessels & Internals_IFR | 06-Aug-25 A | 07-Aug-25 A | 2026-06-16 | 2026-06-16 | 06-Aug-25 A | 07-Aug-25 A
A56850 | Technical Bid Evaluation for Pressure Vessels & Internals_RCC | 08-Aug-25 A | 13-Aug-25 A | 2026-06-16 | 2026-06-16 | 08-Aug-25 A | 13-Aug-25 A
A56860 | Technical Bid Evaluation for Pressure Vessels & Internals_IFA | 14-Aug-25 A | 19-Aug-25 A | 2026-06-16 | 2026-06-16 | 14-Aug-25 A | 19-Aug-25 A
A56870 | Technical Bid Evaluation for Pressure Vessels & Internals_RCA | 20-Aug-25 A | 25-Aug-25 A | 2026-06-29 | 2026-06-29 | 20-Aug-25 A | 25-Aug-25 A
A56880 | Technical Bid Evaluation for Pressure Vessels & Internals_IFD/IFC | 26-Aug-25 A | 29-Aug-25 A | 2026-06-29 | 2026-06-29 | 26-Aug-25 A | 29-Aug-25 A
A8790 | Issue RFQ to Bidders | 01-Aug-25 A | 05-Aug-25 A | 2026-06-16 | 2026-06-16 | 01-Aug-25 A | 05-Aug-25 A
FireFightingEquipment |  | 11-Feb-25 A | 31-Mar-26 A | 2026-06-16 | 2026-09-12 | 11-Feb-25 A | 2026-03-19
TA_FireAlarmSystemModification-SAFCO |  | 11-Feb-25 A | 31-Mar-25 A | 2026-06-16 | 2026-06-16 | 11-Feb-25 A | 31-Mar-25 A
A37120 | Issue RFQ to Bidders | 11-Feb-25 A | 28-Feb-25 A | 2026-06-16 | 2026-06-16 | 11-Feb-25 A | 28-Feb-25 A
A37150 | Issue Purchase Order to Vendor | 03-Mar-25 A | 21-Mar-25 A | 2026-06-16 | 2026-06-16 | 03-Mar-25 A | 21-Mar-25 A
A57240 | TBE for ICT System Modification_Free Issue Material | 24-Mar-25 A | 31-Mar-25 A | 2026-06-16 | 2026-06-16 | 24-Mar-25 A | 31-Mar-25 A
VESDA(VeryEarlySmokeDetectionApparatus) |  | 01-May-25 A | 01-Oct-25 A | 2026-09-12 | 2026-09-12 | 01-May-25 A | 01-Oct-25 A
A20710 | Issue RFQ to Bidders | 01-May-25 A | 20-Jun-25 A | 2026-09-12 | 2026-09-12 | 01-May-25 A | 20-Jun-25 A
A20720 | Issue Purchase Order to Vendor for VESDA | 15-Sep-25 A | 01-Oct-25 A | 2026-09-12 | 2026-09-12 | 15-Sep-25 A | 01-Oct-25 A
A20730 | Bid Evaluation(Completion) | 25-Aug-25 A | 29-Aug-25 A | 2026-09-12 | 2026-09-12 | 25-Aug-25 A | 29-Aug-25 A
A20740 | Commercial Bid Evaluation(Completion) | 01-Sep-25 A | 12-Sep-25 A | 2026-09-12 | 2026-09-12 | 01-Sep-25 A | 12-Sep-25 A
FireFightingEquipment |  | 20-Oct-25 A | 31-Mar-26 A | 2026-07-06 | 2026-07-06 | 11-Feb-25 A | 2026-03-19
A17470 | Issue RFQ to Bidders | 20-Oct-25 A | 27-Oct-25 A | 2026-07-06 | 2026-07-06 | 20-Oct-25 A | 27-Oct-25 A
A18080 | Issue Purchase Order to Vendor for Fire Fighting Equipment | 20-Mar-26 A | 31-Mar-26 A | 2026-07-06 | 2026-07-06 | 2026-03-13 | 2026-03-19
A18090 | Bid Evaluation(Completion) | 01-Feb-26 A | 11-Mar-26 A | 2026-07-06 | 2026-07-06 | 01-Feb-26 A | 11-Mar-26 A
A18100 | Commercial Bid Evaluation(Completion) | 12-Feb-26 A | 20-Mar-26 A | 2026-07-06 | 2026-07-06 | 12-Feb-26 A | 2026-03-12
TailGasFilter/Silencer/Colesor |  | 01-Apr-25 A | 04-Feb-26 A | 2027-01-19 | 2027-01-19 | 01-Apr-25 A | 2026-03-02
Coalescer-(BF) |  | 01-Apr-25 A | 04-Feb-26 A | 2027-01-19 | 2027-01-19 | 01-Apr-25 A | 2026-03-02
A45510 | Technical Bid Evaluation for Coalscer_IFR | 24-Jan-26 A | 25-Jan-26 A | 2027-01-19 | 2027-01-19 | 24-Jan-26 A | 25-Jan-26 A
A45520 | Technical Bid Evaluation for Coalscer_RCC | 25-Jan-26 A | 26-Jan-26 A | 2027-01-19 | 2027-01-19 | 25-Jan-26 A | 26-Jan-26 A
A45530 | Technical Bid Evaluation for Coalscer_IFA | 27-Jan-26 A | 28-Jan-26 A | 2027-01-19 | 2027-01-19 | 27-Jan-26 A | 28-Jan-26 A
A45540 | Technical Bid Evaluation for Coalscer_RCA | 30-Jan-26 A | 02-Feb-26 A | 2027-01-19 | 2027-01-19 | 2026-02-20 | 2026-02-25
A45550 | Technical Bid Evaluation for Coalscer_IFD/IFC | 03-Feb-26 A | 04-Feb-26 A | 2027-01-19 | 2027-01-19 | 2026-02-25 | 2026-03-02
A8130 | Issue RFQ to Bidders | 01-Apr-25 A | 10-Apr-25 A | 2027-01-19 | 2027-01-19 | 01-Apr-25 A | 10-Apr-25 A
A8160 | Issue Purchase Order to Vendor | 29-Jan-26 A | 29-Jan-26 A | 2027-01-19 | 2027-01-19 | 29-Jan-26 A | 29-Jan-26 A
SteelStructure(material+sandwitchPanel) |  | 01-Mar-25 A | 09-Mar-26 A | 2026-06-16 | 2027-01-24 | 01-Mar-25 A | 2026-03-09
CivilBulkMaterial |  | 16-May-25 A | 10-Jul-25 A | 2027-01-24 | 2027-01-24 | 16-May-25 A | 10-Jul-25 A
A9550 | Issue RFQ to Bidders | 16-May-25 A | 01-Jun-25 A | 2027-01-24 | 2027-01-24 | 16-May-25 A | 01-Jun-25 A
A9560 | Vendor Quote Received | 02-Jun-25 A | 01-Jul-25 A | 2027-01-24 | 2027-01-24 | 02-Jun-25 A | 01-Jul-25 A
A9570 | Technical Bid Evaluation | 02-Jul-25 A | 10-Jul-25 A | 2027-01-24 | 2027-01-24 | 02-Jul-25 A | 10-Jul-25 A
A9580 | Issue Purchase Order to Vendor | 09-Jun-25 A | 20-Jun-25 A | 2027-01-24 | 2027-01-24 | 09-Jun-25 A | 20-Jun-25 A
TA_SteelStructure(AdditionalSteelStructurerequiredforBFW) |  | 01-Mar-25 A | 20-Mar-25 A | 2026-06-16 | 2026-06-16 | 01-Mar-25 A | 20-Mar-25 A
A21910 | Issue RFQs to Bidders (Remaining Steel Structure for TA) | 01-Mar-25 A | 05-Mar-25 A | 2026-06-16 | 2026-06-16 | 01-Mar-25 A | 05-Mar-25 A
A21920 | Vendor Quote Received | 05-Mar-25 A | 10-Mar-25 A | 2026-06-16 | 2026-06-16 | 05-Mar-25 A | 10-Mar-25 A
A21930 | Issue Purchase Order to Vendor | 16-Mar-25 A | 20-Mar-25 A | 2026-06-16 | 2026-06-16 | 16-Mar-25 A | 20-Mar-25 A
A21940 | TBE for Steel Structure (TA) | 11-Mar-25 A | 15-Mar-25 A | 2026-06-16 | 2026-06-16 | 11-Mar-25 A | 15-Mar-25 A
SteelStructure-PostTA |  | 01-Jun-25 A | 03-Oct-25 A | 2026-06-21 | 2026-11-01 | 01-Jun-25 A | 03-Oct-25 A
122 | Issue RFQ to Bidders | 01-Jun-25 A | 25-Jul-25 A | 2026-06-21 | 2026-06-21 | 01-Jun-25 A | 25-Jul-25 A
A34530 | Bid Evaluation(Completion) | 25-Aug-25 A | 05-Sep-25 A | 2026-06-21 | 2026-06-21 | 25-Aug-25 A | 05-Sep-25 A
A34540 | Commercial Bid Evaluation(Completion) | 08-Sep-25 A | 22-Sep-25 A | 2026-06-21 | 2026-06-21 | 08-Sep-25 A | 22-Sep-25 A
A34550 | Issue Purchase Order to Vendor | 23-Sep-25 A | 03-Oct-25 A | 2026-11-01 | 2026-11-01 | 23-Sep-25 A | 03-Oct-25 A
StructuralSteel |  | 01-Jun-25 A | 09-Mar-26 A | 2026-06-25 | 2026-06-25 | 01-Jun-25 A | 2026-03-09
A23620 | Issue RFQ to Bidders | 01-Jun-25 A | 25-Jun-25 A | 2026-06-25 | 2026-06-25 | 01-Jun-25 A | 25-Jun-25 A
A23630 | Vendor Quote Received | 25-Aug-25 A | 05-Sep-25 A | 2026-06-25 | 2026-06-25 | 25-Aug-25 A | 05-Sep-25 A
A23640 | Issue Purchase Order to Vendor | 15-Sep-25 A | 03-Oct-25 A | 2026-06-25 | 2026-06-25 | 15-Sep-25 A | 03-Oct-25 A
A57960 | Technical Bid Evaluation for Structural Steel_IFR | 08-Sep-25 A | 12-Sep-25 A | 2026-06-25 | 2026-06-25 | 08-Sep-25 A | 12-Sep-25 A
A57970 | Technical Bid Evaluation for Structural Steel_RCC | 15-Sep-25 A | 19-Sep-25 A | 2026-06-25 | 2026-06-25 | 15-Sep-25 A | 19-Sep-25 A
A57980 | Technical Bid Evaluation for Structural Steel_IFA | 19-Sep-25 A | 01-Oct-25 A | 2026-06-25 | 2026-06-25 | 19-Sep-25 A | 01-Oct-25 A
A57990 | Technical Bid Evaluation for Structural Steel_RCA | 20-Feb-26 A | 27-Feb-26 A | 2026-06-25 | 2026-06-25 | 2026-02-20 | 2026-02-27
A58000 | Technical Bid Evaluation for Structural Steel_IFD/IFC | 27-Feb-26 A | 09-Mar-26 A | 2026-06-25 | 2026-06-25 | 2026-02-27 | 2026-03-09
TurbingMaterial[SStubes,Connectors,unions,plugsetc.] |  | 2026-04-17 | 2026-06-11 | 2026-07-17 | 2026-09-10 | 2026-02-20 | 2026-04-16
TurbingMaterial[SStubes,Connectors,unions,plugsetc] |  | 2026-04-17 | 2026-06-11 | 2026-07-17 | 2026-09-10 | 2026-02-20 | 2026-04-16
A17410 | Issue RFQ to Bidders | 2026-04-17 | 2026-04-30 | 2026-07-17 | 2026-07-30 | 2026-02-20 | 2026-03-05
A18200 | Issue Purchase Order to Vendor | 2026-05-29 | 2026-06-11 | 2026-08-28 | 2026-09-10 | 2026-04-03 | 2026-04-16
A18210 | Bid Evaluation(Completion) | 2026-05-01 | 2026-05-14 | 2026-07-31 | 2026-08-13 | 2026-03-06 | 2026-03-19
A18220 | Commercial Bid Evaluation(Completion) | 2026-05-15 | 2026-05-28 | 2026-08-14 | 2026-08-27 | 2026-03-20 | 2026-04-02
Telecom(ACS+LAN+CCTV+PAGA) |  | 11-Mar-25 A | 2026-04-24 | 2026-06-16 | 2027-03-23 | 11-Mar-25 A | 2026-02-27
AcessControlSystem |  | 01-Aug-25 A | 2026-04-24 | 2026-07-09 | 2027-03-23 | 01-Aug-25 A | 2026-02-27
A18720 | RFQs to Bid Receipt | 01-Aug-25 A | 06-Aug-25 A | 2026-07-09 | 2026-07-09 | 01-Aug-25 A | 06-Aug-25 A
A22340 | Commercial Bid Evaluation(Completion) | 01-Dec-25 A | 03-Dec-25 A | 2026-07-09 | 2026-07-09 | 01-Dec-25 A | 03-Dec-25 A
A22350 | Issue Purchase Order to Vendor for ACS | 13-Dec-25 A | 19-Dec-25 A | 2026-07-09 | 2026-07-09 | 13-Dec-25 A | 19-Dec-25 A
A23880 | Technical Bid Evaluation For Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_IFR | 31-Oct-25 A | 14-Nov-25 A | 2026-07-09 | 2026-07-09 | 31-Oct-25 A | 14-Nov-25 A
A23890 | Technical Bid Evaluation For Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_RCC | 26-Nov-25 A | 28-Nov-25 A | 2026-07-09 | 2026-07-09 | 26-Nov-25 A | 28-Nov-25 A
A51950 | Technical Bid Evaluation For Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_IFA | 01-Dec-25 A | 03-Dec-25 A | 2026-07-09 | 2026-07-09 | 01-Dec-25 A | 03-Dec-25 A
A51960 | Technical Bid Evaluation For Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_RCA | 2026-04-17 | 2026-04-21 | 2027-03-16 | 2027-03-18 | 2026-02-20 | 2026-02-24
A51970 | Technical Bid Evaluation For Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_IFD/IFC | 2026-04-22 | 2026-04-24 | 2027-03-19 | 2027-03-23 | 2026-02-25 | 2026-02-27
TA_LANSystemModification-CISCO |  | 11-Mar-25 A | 10-Apr-25 A | 2026-06-16 | 2026-06-16 | 11-Mar-25 A | 10-Apr-25 A
A37200 | Issue RFQ to Bidders | 11-Mar-25 A | 27-Mar-25 A | 2026-06-16 | 2026-06-16 | 11-Mar-25 A | 27-Mar-25 A
A37230 | Issue Purchase Order to Vendor | 03-Apr-25 A | 10-Apr-25 A | 2026-06-16 | 2026-06-16 | 03-Apr-25 A | 10-Apr-25 A
A57480 | TBE for Electrical System Modification_Free Issue Material | 28-Mar-25 A | 03-Apr-25 A | 2026-06-16 | 2026-06-16 | 28-Mar-25 A | 03-Apr-25 A
PAGA+Telephone |  | 01-Aug-25 A | 2026-04-24 | 2026-08-04 | 2027-03-23 | 01-Aug-25 A | 2026-02-27
A18810 | RFQs to Bid Receipt | 01-Aug-25 A | 06-Aug-25 A | 2026-08-04 | 2026-08-04 | 01-Aug-25 A | 06-Aug-25 A
A19110 | Issue Purchase Order to Vendor for PAGA + Telephone | 11-Dec-25 A | 19-Dec-25 A | 2026-08-04 | 2026-08-04 | 11-Dec-25 A | 19-Dec-25 A
A19130 | Commercial Bid Evaluation(Completion) | 11-Dec-25 A | 15-Dec-25 A | 2026-08-04 | 2026-08-04 | 11-Dec-25 A | 15-Dec-25 A
A56990 | Technical Bid Evaluation For Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_IFR | 24-Nov-25 A | 26-Nov-25 A | 2026-08-04 | 2026-08-04 | 24-Nov-25 A | 26-Nov-25 A
A57000 | Technical Bid Evaluation For Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_RCC | 27-Nov-25 A | 01-Dec-25 A | 2026-08-04 | 2026-08-04 | 27-Nov-25 A | 01-Dec-25 A
A57010 | Technical Bid Evaluation For Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_IFA | 03-Dec-25 A | 05-Dec-25 A | 2026-08-04 | 2026-08-04 | 03-Dec-25 A | 05-Dec-25 A
A57020 | Technical Bid Evaluation For Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_RCA | 2026-04-17 | 2026-04-21 | 2027-03-16 | 2027-03-18 | 2026-02-20 | 2026-02-24
A57030 | Technical Bid Evaluation For Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_IFD/IFC | 2026-04-22 | 2026-04-24 | 2027-03-19 | 2027-03-23 | 2026-02-25 | 2026-02-27
CCTV |  | 01-Aug-25 A | 2026-04-24 | 2026-07-28 | 2027-03-23 | 01-Aug-25 A | 2026-02-27
A18900 | RFQs to Bid Receipt | 01-Aug-25 A | 06-Aug-25 A | 2026-07-28 | 2026-07-28 | 01-Aug-25 A | 06-Aug-25 A
A19170 | Issue Purchase Order to Vendor for CCTV | 11-Dec-25 A | 19-Dec-25 A | 2026-07-28 | 2026-07-28 | 11-Dec-25 A | 19-Dec-25 A
A19190 | Commercial Bid Evaluation(Completion) | 11-Dec-25 A | 15-Dec-25 A | 2026-07-28 | 2026-07-28 | 11-Dec-25 A | 15-Dec-25 A
A57040 | Technical Bid Evaluation For Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_IFR | 21-Nov-25 A | 25-Nov-25 A | 2026-07-28 | 2026-07-28 | 21-Nov-25 A | 25-Nov-25 A
A57050 | Technical Bid Evaluation For Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_RCC | 26-Nov-25 A | 28-Nov-25 A | 2026-07-28 | 2026-07-28 | 26-Nov-25 A | 28-Nov-25 A
A57060 | Technical Bid Evaluation For Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_IFA | 01-Dec-25 A | 03-Dec-25 A | 2026-07-28 | 2026-07-28 | 01-Dec-25 A | 03-Dec-25 A
A57070 | Technical Bid Evaluation For Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_RCA | 2026-04-17 | 2026-04-21 | 2027-03-16 | 2027-03-18 | 2026-02-20 | 2026-02-24
A57080 | Technical Bid Evaluation For Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_IFD/IFC | 2026-04-22 | 2026-04-24 | 2027-03-19 | 2027-03-23 | 2026-02-25 | 2026-02-27
Telecom(ACS+CCTV+PAGA)Integration |  | 01-Aug-25 A | 19-Dec-25 A | 2026-08-24 | 2026-08-24 | 01-Aug-25 A | 19-Dec-25 A
A16990 | Issue RFQ to Bidders | 01-Aug-25 A | 06-Aug-25 A | 2026-08-24 | 2026-08-24 | 01-Aug-25 A | 06-Aug-25 A
A22270 | Bid Evaluation(Completion) | 01-Dec-25 A | 03-Dec-25 A | 2026-08-24 | 2026-08-24 | 01-Dec-25 A | 03-Dec-25 A
A22280 | Commercial Bid Evaluation(Completion) | 02-Dec-25 A | 04-Dec-25 A | 2026-08-24 | 2026-08-24 | 02-Dec-25 A | 04-Dec-25 A
A22290 | Issue Purchase Order to Vendor for Telecom (ACS+CCTV+PAGA) Integration | 12-Dec-25 A | 19-Dec-25 A | 2026-08-24 | 2026-08-24 | 12-Dec-25 A | 19-Dec-25 A
LightingFixtures |  | 01-Mar-26 A | 2026-05-07 | 2026-10-07 | 2026-10-27 | 2026-02-20 | 2026-05-22
LightingFixtures(Almost50%Exd=354Nos) |  | 01-Mar-26 A | 2026-05-07 | 2026-10-07 | 2026-10-27 | 2026-02-20 | 2026-05-22
A16390 | Issue RFQ to Bidders | 01-Mar-26 A | 07-Mar-26 A | 2026-10-07 | 2026-10-07 | 2026-02-20 | 2026-03-20
A19590 | Issue Purchase Order to Vendor for Lighting Fixtures | 2026-04-17 | 2026-05-07 | 2026-10-07 | 2026-10-27 | 2026-05-04 | 2026-05-22
A19600 | Bid Evaluation(Completion) | 05-Mar-26 A | 17-Mar-26 A | 2026-10-07 | 2026-10-07 | 2026-03-23 | 2026-04-10
A19610 | Commercial Bid Evaluation(Completion) | 17-Mar-26 A | 20-Mar-26 A | 2026-10-07 | 2026-10-07 | 2026-04-13 | 2026-05-01
ManualValve |  | 20-May-25 A | 21-Nov-25 A | 2026-07-20 | 2026-08-04 | 20-May-25 A | 21-Nov-25 A
ManualValves(Gate9Nos,Check6Nos,GlobeValves64Nos) |  | 20-May-25 A | 21-Nov-25 A | 2026-07-20 | 2026-08-04 | 20-May-25 A | 21-Nov-25 A
A18140 | Issue Purchase Order to Vendor for Manual Valves | 27-Oct-25 A | 21-Nov-25 A | 2026-08-04 | 2026-08-04 | 27-Oct-25 A | 21-Nov-25 A
A18160 | Commercial Bid Evaluation(Completion) | 15-Oct-25 A | 24-Oct-25 A | 2026-08-04 | 2026-08-04 | 15-Oct-25 A | 24-Oct-25 A
A45020 | Technical Bid Evaluation (TBE) for Manual Valves_IFR | 19-Sep-25 A | 25-Sep-25 A | 2026-07-20 | 2026-07-20 | 19-Sep-25 A | 25-Sep-25 A
A45030 | Technical Bid Evaluation (TBE) for Manual Valves_RCC | 26-Sep-25 A | 02-Oct-25 A | 2026-07-20 | 2026-07-20 | 26-Sep-25 A | 02-Oct-25 A
A45040 | Technical Bid Evaluation (TBE) for Manual Valves_IFA | 03-Oct-25 A | 07-Nov-25 A | 2026-07-20 | 2026-07-20 | 03-Oct-25 A | 07-Nov-25 A
A45050 | Technical Bid Evaluation (TBE) for Manual Valves_RCA | 08-Oct-25 A | 10-Oct-25 A | 2026-08-04 | 2026-08-04 | 08-Oct-25 A | 10-Oct-25 A
A45060 | Technical Bid Evaluation (TBE) for Manual Valves_IFD/IFC | 10-Oct-25 A | 14-Oct-25 A | 2026-08-04 | 2026-08-04 | 10-Oct-25 A | 14-Oct-25 A
A9270 | Issue RFQ to Bidders | 20-May-25 A | 24-Jul-25 A | 2026-07-20 | 2026-07-20 | 20-May-25 A | 24-Jul-25 A
SpecialGGCandButterflyValves |  | 09-Oct-25 A | 2026-06-08 | 2026-06-23 | 2026-08-12
SpecialGGCandButterflyValves |  | 09-Oct-25 A | 2026-06-08 | 2026-06-23 | 2026-08-12
A63760 | Issue RFQ to Bidders | 09-Oct-25 A | 13-Oct-25 A | 2026-06-23 | 2026-06-23
A63770 | Issue Purchase Order to Vendor | 2026-05-20 | 2026-06-08 | 2026-07-24 | 2026-08-12
A63780 | Bid Evaluation(Completion) | 2026-04-17 | 2026-05-07 | 2026-06-23 | 2026-07-13
A63790 | Commercial Bid Evaluation(Completion) | 2026-05-08 | 2026-05-19 | 2026-07-14 | 2026-07-23
HoseCoupling |  | 23-Oct-25 A | 30-Mar-26 A | 2026-07-06 | 2026-07-06
HoseCoupling |  | 23-Oct-25 A | 30-Mar-26 A | 2026-07-06 | 2026-07-06
A64240 | Issue RFQ to Bidders | 23-Oct-25 A | 27-Oct-25 A | 2026-07-06 | 2026-07-06
A64250 | Issue Purchase Order to Vendor | 24-Mar-26 A | 30-Mar-26 A | 2026-07-06 | 2026-07-06
A64260 | Bid Evaluation(Completion) | 27-Feb-26 A | 10-Mar-26 A | 2026-07-06 | 2026-07-06
A64270 | Commercial Bid Evaluation(Completion) | 11-Mar-26 A | 19-Mar-26 A | 2026-07-06 | 2026-07-06
FlameArrestors |  | 23-Oct-25 A | 17-Apr-26 A | 2026-08-10 | 2026-08-10
FlameArrestors |  | 23-Oct-25 A | 17-Apr-26 A | 2026-08-10 | 2026-08-10
A64160 | Issue RFQ to Bidders | 23-Oct-25 A | 27-Oct-25 A | 2026-08-10 | 2026-08-10
A64170 | Issue Purchase Order to Vendor | 10-Apr-26 A | 17-Apr-26 A | 2026-08-10 | 2026-08-10
A64180 | Bid Evaluation(Completion) | 20-Feb-26 A | 11-Mar-26 A | 2026-08-10 | 2026-08-10
A64190 | Commercial Bid Evaluation(Completion) | 01-Apr-26 A | 09-Apr-26 A | 2026-08-10 | 2026-08-10
SteamTraps |  | 24-Oct-25 A | 17-Apr-26 A | 2026-08-20 | 2026-08-20
SteamTraps |  | 24-Oct-25 A | 17-Apr-26 A | 2026-08-20 | 2026-08-20
A64200 | Issue RFQ to Bidders | 24-Oct-25 A | 27-Oct-25 A | 2026-08-20 | 2026-08-20
A64210 | Issue Purchase Order to Vendor | 09-Apr-26 A | 17-Apr-26 A | 2026-08-20 | 2026-08-20
A64220 | Bid Evaluation(Completion) | 25-Jan-26 A | 10-Feb-26 A | 2026-08-20 | 2026-08-20
A64230 | Commercial Bid Evaluation(Completion) | 01-Apr-26 A | 04-Apr-26 A | 2026-08-20 | 2026-08-20
MechanicalInterlocks |  | 07-Nov-25 A | 30-Mar-26 A | 2026-07-08 | 2026-07-08
MechanicalInterlocks |  | 07-Nov-25 A | 30-Mar-26 A | 2026-07-08 | 2026-07-08
A64370 | Issue RFQ to Bidders | 07-Nov-25 A | 12-Nov-25 A | 2026-07-08 | 2026-07-08
A64380 | Issue Purchase Order to Vendor | 24-Mar-26 A | 30-Mar-26 A | 2026-07-08 | 2026-07-08
A64390 | Bid Evaluation(Completion) | 23-Feb-26 A | 11-Mar-26 A | 2026-07-08 | 2026-07-08
A64400 | Commercial Bid Evaluation(Completion) | 12-Mar-26 A | 23-Mar-26 A | 2026-07-08 | 2026-07-08
InsulatingGaskets |  | 19-Mar-26 A | 2026-06-08 | 2026-06-23 | 2026-08-12
InsulatingGaskets |  | 19-Mar-26 A | 2026-06-08 | 2026-06-23 | 2026-08-12
A63840 | Issue RFQ to Bidders | 19-Mar-26 A | 23-Mar-26 A | 2026-06-23 | 2026-06-23
A63850 | Issue Purchase Order to Vendor | 2026-05-20 | 2026-06-08 | 2026-07-24 | 2026-08-12
A63860 | Bid Evaluation(Completion) | 2026-04-17 | 2026-05-07 | 2026-06-23 | 2026-07-13
A63870 | Commercial Bid Evaluation(Completion) | 2026-05-08 | 2026-05-19 | 2026-07-14 | 2026-07-23
PipingBulk |  | 01-Jul-25 A | 2026-06-17 | 2026-06-09 | 2027-03-23 | 01-Jul-25 A | 2026-07-24
PipingLotforPostTA |  | 01-Jul-25 A | 17-Nov-25 A | 2026-06-09 | 2026-06-09 | 01-Jul-25 A | 17-Nov-25 A
112 | Issue RFQ to Bidders | 01-Jul-25 A | 21-Jul-25 A | 2026-06-09 | 2026-06-09 | 01-Jul-25 A | 21-Jul-25 A
A23680 | Issue Purchase Order to Vendor | 01-Sep-25 A | 06-Sep-25 A | 2026-06-09 | 2026-06-09 | 01-Sep-25 A | 06-Sep-25 A
A23700 | Commercial Bid Evaluation(Completion) | 15-Oct-25 A | 24-Oct-25 A | 2026-06-09 | 2026-06-09 | 15-Oct-25 A | 24-Oct-25 A
A57090 | Technical Bid Evaluation (TBE) for Piping Bulk_IFR | 22-Jul-25 A | 15-Sep-25 A | 2026-06-09 | 2026-06-09 | 22-Jul-25 A | 15-Sep-25 A
A57100 | Technical Bid Evaluation (TBE) for Piping Bulk_RCC | 15-Sep-25 A | 15-Oct-25 A | 2026-06-09 | 2026-06-09 | 15-Sep-25 A | 15-Oct-25 A
A57110 | Technical Bid Evaluation (TBE) for Piping Bulk_IFA | 25-Oct-25 A | 29-Oct-25 A | 2026-06-09 | 2026-06-09 | 25-Oct-25 A | 29-Oct-25 A
A57120 | Technical Bid Evaluation (TBE) for Piping Bulk_RCA | 30-Oct-25 A | 14-Nov-25 A | 2026-06-09 | 2026-06-09 | 30-Oct-25 A | 14-Nov-25 A
A57130 | Technical Bid Evaluation (TBE) for Piping Bulk_IFD/IFC | 14-Nov-25 A | 17-Nov-25 A | 2026-06-09 | 2026-06-09 | 14-Nov-25 A | 17-Nov-25 A
PipingSupports(SwingHangers)forPostTA |  | 04-Aug-25 A | 08-Sep-25 A | 2026-06-12 | 2026-08-11 | 04-Aug-25 A | 08-Sep-25 A
A23710 | Issue RFQ to Bidders | 04-Aug-25 A | 08-Aug-25 A | 2026-06-12 | 2026-06-12 | 04-Aug-25 A | 08-Aug-25 A
A23720 | Issue Purchase Order to Vendor | 01-Sep-25 A | 08-Sep-25 A | 2026-06-12 | 2026-06-12 | 01-Sep-25 A | 08-Sep-25 A
A23740 | Commercial Bid Evaluation(Completion) | 06-Aug-25 A | 30-Aug-25 A | 2026-06-12 | 2026-06-12 | 06-Aug-25 A | 30-Aug-25 A
A57140 | Technical Bid Evaluation (TBE) for Spring Hangers_IFR | 09-Aug-25 A | 14-Aug-25 A | 2026-06-12 | 2026-06-12 | 09-Aug-25 A | 14-Aug-25 A
A57150 | Technical Bid Evaluation (TBE) for Spring Hangers_RCC | 15-Aug-25 A | 16-Aug-25 A | 2026-06-12 | 2026-06-12 | 15-Aug-25 A | 16-Aug-25 A
A57160 | Technical Bid Evaluation (TBE) for Spring Hangers_IFA | 18-Aug-25 A | 19-Aug-25 A | 2026-06-12 | 2026-06-12 | 18-Aug-25 A | 19-Aug-25 A
A57170 | Technical Bid Evaluation (TBE) for Spring Hangers_RCA | 20-Aug-25 A | 22-Aug-25 A | 2026-08-11 | 2026-08-11 | 20-Aug-25 A | 22-Aug-25 A
A57180 | Technical Bid Evaluation (TBE) for Spring Hangers_IFD/IFC | 25-Aug-25 A | 26-Aug-25 A | 2026-08-11 | 2026-08-11 | 25-Aug-25 A | 26-Aug-25 A
Piping1stLotforGF |  | 01-Jul-25 A | 2026-05-08 | 2026-06-09 | 2027-03-23 | 01-Jul-25 A | 2026-03-13
100 | Issue RFQ to Bidders | 01-Jul-25 A | 21-Jul-25 A | 2026-06-09 | 2026-06-09 | 01-Jul-25 A | 21-Jul-25 A
A21350 | Issue Purchase Order to Vendor | 08-Sep-25 A | 19-Sep-25 A | 2026-06-21 | 2026-06-21 | 08-Sep-25 A | 19-Sep-25 A
A21370 | Commercial Bid Evaluation(Completion) | 25-Aug-25 A | 05-Sep-25 A | 2026-06-21 | 2026-06-21 | 25-Aug-25 A | 05-Sep-25 A
A44970 | Technical Bid Evaluation (TBE) for Piping Bulk_IFR | 19-Aug-25 A | 29-Aug-25 A | 2026-06-09 | 2026-06-09 | 19-Aug-25 A | 29-Aug-25 A
A44980 | Technical Bid Evaluation (TBE) for Piping Bulk_RCC | 30-Aug-25 A | 08-Sep-25 A | 2026-06-09 | 2026-06-09 | 30-Aug-25 A | 08-Sep-25 A
A44990 | Technical Bid Evaluation (TBE) for Piping Bulk_IFA | 09-Sep-25 A | 16-Sep-25 A | 2026-06-09 | 2026-06-09 | 09-Sep-25 A | 16-Sep-25 A
A45000 | Technical Bid Evaluation (TBE) for Piping Bulk_RCA | 2026-04-17 | 2026-04-28 | 2027-03-02 | 2027-03-12 | 2026-02-20 | 2026-03-03
A45010 | Technical Bid Evaluation (TBE) for Piping Bulk_IFD/IFC | 2026-04-28 | 2026-05-08 | 2027-03-12 | 2027-03-23 | 2026-03-03 | 2026-03-13
Piping2ndLotforGF(CSMaterial) |  | 01-Jan-26 A | 27-Feb-26 A | 2026-08-24 | 2026-08-24 | 2026-02-20 | 2026-03-19
101 | Issue RFQ to Bidders | 01-Jan-26 A | 22-Jan-26 A | 2026-08-24 | 2026-08-24 | 2026-02-20 | 2026-02-26
A21410 | Issue Purchase Order to Vendor | 17-Feb-26 A | 27-Feb-26 A | 2026-08-24 | 2026-08-24 | 2026-03-13 | 2026-03-19
A21420 | Bid Evaluation(Completion) | 22-Jan-26 A | 11-Feb-26 A | 2026-08-24 | 2026-08-24 | 2026-02-27 | 2026-03-05
A21430 | Commercial Bid Evaluation(Completion) | 01-Feb-26 A | 20-Feb-26 A | 2026-08-24 | 2026-08-24 | 2026-03-06 | 2026-03-12
Piping3rdLotGF(CSMaterial) |  | 2026-05-11 | 2026-06-17 | 2026-07-01 | 2026-08-07 | 2026-03-13 | 2026-04-22
102 | Issue RFQ to Bidders | 2026-05-11 | 2026-05-19 | 2026-07-01 | 2026-07-09 | 2026-03-13 | 2026-03-24
A21470 | Issue Purchase Order to Vendor | 2026-06-09 | 2026-06-17 | 2026-07-30 | 2026-08-07 | 2026-04-13 | 2026-04-22
A21480 | Bid Evaluation(Completion) | 2026-05-20 | 2026-05-28 | 2026-07-10 | 2026-07-20 | 2026-03-24 | 2026-04-02
A21490 | Commercial Bid Evaluation(Completion) | 2026-05-29 | 2026-06-08 | 2026-07-21 | 2026-07-29 | 2026-04-02 | 2026-04-13
PipingSupports(SwingHangers)forGF |  | 20-Feb-26 A | 2026-06-17 | 2026-07-08 | 2026-09-07 | 2026-02-20 | 2026-07-24
A21610 | Issue RFQ to Bidders | 20-Feb-26 A | 27-Feb-26 A | 2026-07-08 | 2026-07-08 | 2026-02-20 | 2026-02-26
A21620 | Issue Purchase Order to Vendor | 2026-05-29 | 2026-06-17 | 2026-08-19 | 2026-09-07 | 2026-07-06 | 2026-07-24
A21640 | Commercial Bid Evaluation(Completion) | 2026-04-17 | 2026-05-28 | 2026-07-08 | 2026-08-18 | 2026-05-25 | 2026-07-06
A45120 | Technical Bid Evaluation (TBE) for Spring Hangers_IFR | 01-Mar-26 A | 13-Mar-26 A | 2026-07-08 | 2026-07-08 | 2026-02-27 | 2026-03-16
A45130 | Technical Bid Evaluation (TBE) for Spring Hangers_RCC | 02-Mar-26 A | 16-Mar-26 A | 2026-07-08 | 2026-07-08 | 2026-03-16 | 2026-04-06
A45140 | Technical Bid Evaluation (TBE) for Spring Hangers_IFA | 05-Mar-26 A | 20-Mar-26 A | 2026-07-08 | 2026-07-08 | 2026-04-07 | 2026-04-22
A45150 | Technical Bid Evaluation (TBE) for Spring Hangers_RCA | 01-Mar-26 A | 03-Mar-26 A | 2026-07-08 | 2026-07-08 | 2026-04-22 | 2026-05-13
A45160 | Technical Bid Evaluation (TBE) for Spring Hangers_IFD/IFC | 04-Mar-26 A | 20-Mar-26 A | 2026-07-08 | 2026-07-08 | 2026-05-14 | 2026-05-25
RigidStruts |  | 24-Oct-25 A | 2026-05-18 | 2026-09-23 | 2026-10-22
A64120 | Issue RFQ to Bidders | 24-Oct-25 A | 27-Oct-25 A | 2026-09-23 | 2026-09-23
A64130 | Issue Purchase Order to Vendor | 2026-04-29 | 2026-05-18 | 2026-10-05 | 2026-10-22
A64140 | Bid Evaluation(Completion) | 27-Mar-26 A | 09-Apr-26 A | 2026-09-23 | 2026-09-23
A64150 | Commercial Bid Evaluation(Completion) | 2026-04-17 | 2026-04-28 | 2026-09-23 | 2026-10-02
HDPEPiping |  | 01-Aug-25 A | 19-Dec-25 A | 2026-09-03 | 2026-09-21 | 01-Aug-25 A | 19-Dec-25 A
HDPEPipingGF(FireWaterLines) |  | 01-Aug-25 A | 19-Dec-25 A | 2026-09-03 | 2026-09-21 | 01-Aug-25 A | 19-Dec-25 A
A21530 | Issue RFQ to Bidders | 01-Aug-25 A | 08-Aug-25 A | 2026-09-03 | 2026-09-03 | 01-Aug-25 A | 08-Aug-25 A
A21540 | Issue Purchase Order to Vendor | 18-Dec-25 A | 19-Dec-25 A | 2026-09-03 | 2026-09-03 | 18-Dec-25 A | 19-Dec-25 A
A21560 | Commercial Bid Evaluation(Completion) | 22-Aug-25 A | 30-Aug-25 A | 2026-09-03 | 2026-09-03 | 22-Aug-25 A | 30-Aug-25 A
A60270 | Technical Bid Evaluation (TBE) for Piping Bulk_IFR | 09-Aug-25 A | 12-Aug-25 A | 2026-09-03 | 2026-09-03 | 09-Aug-25 A | 12-Aug-25 A
A60280 | Technical Bid Evaluation (TBE) for Piping Bulk_RCC | 13-Aug-25 A | 15-Aug-25 A | 2026-09-03 | 2026-09-03 | 13-Aug-25 A | 15-Aug-25 A
A60290 | Technical Bid Evaluation (TBE) for Piping Bulk_IFA | 16-Aug-25 A | 18-Aug-25 A | 2026-09-03 | 2026-09-03 | 16-Aug-25 A | 18-Aug-25 A
A60300 | Technical Bid Evaluation (TBE) for Piping Bulk_RCA | 18-Aug-25 A | 19-Aug-25 A | 2026-09-21 | 2026-09-21 | 18-Aug-25 A | 19-Aug-25 A
A60310 | Technical Bid Evaluation (TBE) for Piping Bulk_IFD/IFC | 19-Aug-25 A | 21-Aug-25 A | 2026-09-21 | 2026-09-21 | 19-Aug-25 A | 21-Aug-25 A
GREPiping |  | 07-Nov-25 A | 30-Mar-26 A | 2026-09-03 | 2026-09-03
GREPiping |  | 07-Nov-25 A | 30-Mar-26 A | 2026-09-03 | 2026-09-03
A64410 | Issue RFQ to Bidders | 07-Nov-25 A | 12-Nov-25 A | 2026-09-03 | 2026-09-03
A64420 | Issue Purchase Order to Vendor | 24-Mar-26 A | 30-Mar-26 A | 2026-09-03 | 2026-09-03
A64430 | Bid Evaluation(Completion) | 23-Feb-26 A | 11-Mar-26 A | 2026-09-03 | 2026-09-03
A64440 | Commercial Bid Evaluation(Completion) | 12-Mar-26 A | 23-Mar-26 A | 2026-09-03 | 2026-09-03
PipingSPItems(strainer,filters) |  | 23-Jan-26 A | 26-Mar-26 A | 2026-07-20 | 2026-09-05 | 23-Jan-26 A | 2026-04-09
SpecializedItems(OrificeFlanges)CS300#1"-6"=08Nos |  | 01-Feb-26 A | 26-Mar-26 A | 2026-07-20 | 2026-09-05 | 2026-02-20 | 2026-04-01
A18340 | Issue RFQ to Bidders | 20-Mar-26 A | 26-Mar-26 A | 2026-07-20 | 2026-07-20 | 2026-02-20 | 2026-02-26
A18360 | Issue Purchase Order to Vendor | 19-Mar-26 A | 20-Mar-26 A | 2026-07-20 | 2026-07-20 | 2026-03-25 | 2026-04-01
A18380 | Commercial Bid Evaluation(Completion) | 03-Mar-26 A | 11-Mar-26 A | 2026-07-20 | 2026-07-20 | 2026-03-18 | 2026-03-25
A45070 | Technical Bid Evaluation (TBE) for Piping Speciality Items_IFR | 01-Feb-26 A | 28-Feb-26 A | 2026-07-20 | 2026-07-20 | 2026-02-27 | 2026-03-05
A45080 | Technical Bid Evaluation (TBE) for Piping Speciality Items_RCC | 10-Feb-26 A | 28-Feb-26 A | 2026-07-20 | 2026-07-20 | 2026-03-05 | 2026-03-11
A45090 | Technical Bid Evaluation (TBE) for Piping Speciality Items_IFA | 25-Feb-26 A | 02-Mar-26 A | 2026-07-20 | 2026-07-20 | 2026-03-12 | 2026-03-18
A45100 | Technical Bid Evaluation (TBE) for Piping Speciality Items_RCA | 27-Feb-26 A | 06-Mar-26 A | 2026-09-05 | 2026-09-05 | 2026-03-18 | 2026-03-24
A45110 | Technical Bid Evaluation (TBE) for Piping Speciality Items_IFD/IFC | 28-Feb-26 A | 12-Mar-26 A | 2026-09-05 | 2026-09-05 | 2026-03-25 | 2026-03-31
SpecializedItems(Strainer/Filter)CS&SS150#-300#2"-26"=08Nos |  | 23-Jan-26 A | 20-Mar-26 A | 2026-07-22 | 2026-07-22 | 23-Jan-26 A | 2026-04-09
A15910 | Issue RFQ to Bidders | 23-Jan-26 A | 04-Feb-26 A | 2026-07-22 | 2026-07-22 | 23-Jan-26 A | 04-Feb-26 A
A18260 | Issue Purchase Order to Vendor | 20-Mar-26 A | 20-Mar-26 A | 2026-07-22 | 2026-07-22 | 2026-02-27 | 2026-03-27
A18280 | Commercial Bid Evaluation(Completion) | 17-Feb-26 A | 20-Mar-26 A | 2026-07-22 | 2026-07-22 | 17-Feb-26 A | 2026-02-26
A56590 | Technical Bid Evaluation (TBE) for Piping Speciality Items_IFR | 05-Feb-26 A | 10-Feb-26 A | 2026-07-22 | 2026-07-22 | 05-Feb-26 A | 10-Feb-26 A
A56600 | Technical Bid Evaluation (TBE) for Piping Speciality Items_RCC | 11-Feb-26 A | 17-Feb-26 A | 2026-07-22 | 2026-07-22 | 11-Feb-26 A | 17-Feb-26 A
A56610 | Technical Bid Evaluation (TBE) for Piping Speciality Items_IFA | 02-Mar-26 A | 20-Mar-26 A | 2026-07-22 | 2026-07-22 | 2026-02-20 | 2026-03-09
A56620 | Technical Bid Evaluation (TBE) for Piping Speciality Items_RCA | 18-Mar-26 A | 20-Mar-26 A | 2026-07-22 | 2026-07-22 | 2026-03-09 | 2026-03-30
A56630 | Technical Bid Evaluation (TBE) for Piping Speciality Items_IFD/IFC | 03-Mar-26 A | 20-Mar-26 A | 2026-07-22 | 2026-07-22 | 2026-03-31 | 2026-04-09
Pressure/Temperature/LevelInstruments,Flowmeters |  | 18-Apr-25 A | 20-Mar-26 A | 2026-07-17 | 2026-08-15 | 18-Apr-25 A | 2026-03-25
Gauges(PG,TG,PDG)PG-10bar&40bar=19Nos,DP=05Nos,TG=09Nos |  | 15-Aug-25 A | 20-Mar-26 A | 2026-08-15 | 2026-08-15 | 15-Aug-25 A | 2026-03-25
A16340 | Technical Bid Evaluation for Temperature Gauges / Pressure Gauges_RCC | 26-Dec-25 A | 23-Jan-26 A | 2026-08-15 | 2026-08-15 | 26-Dec-25 A | 23-Jan-26 A
A16350 | Technical Bid Evaluation for Temperature Gauges / Pressure Gauges_IFA | 20-Feb-26 A | 09-Mar-26 A | 2026-08-15 | 2026-08-15 | 2026-02-20 | 2026-02-27
A16360 | Technical Bid Evaluation for Temperature Gauges / Pressure Gauges_RCA | 28-Feb-26 A | 03-Mar-26 A | 2026-08-15 | 2026-08-15 | 2026-02-27 | 2026-03-09
A16370 | Technical Bid Evaluation for Temperature Gauges / Pressure Gauges_IFD/IFC | 01-Feb-26 A | 13-Mar-26 A | 2026-08-15 | 2026-08-15 | 2026-03-09 | 2026-03-16
A17290 | RFQs to Bid Receipt | 15-Aug-25 A | 27-Aug-25 A | 2026-08-15 | 2026-08-15 | 15-Aug-25 A | 27-Aug-25 A
A19230 | Issue Purchase Order to Vendor Guages (PG, TG, PDG) | 06-Mar-26 A | 20-Mar-26 A | 2026-08-15 | 2026-08-15 | 2026-03-09 | 2026-03-25
A19250 | Commercial Bid Evaluation(Completion) | 01-Mar-26 A | 13-Mar-26 A | 2026-08-15 | 2026-08-15 | 2026-02-27 | 2026-03-09
A48180 | Technical Bid Evaluation for Temperature Gauges / Pressure Gauges_IFR | 19-Dec-25 A | 26-Dec-25 A | 2026-08-15 | 2026-08-15 | 19-Dec-25 A | 26-Dec-25 A
FlowElementsVenturi |  | 01-Jun-25 A | 11-Dec-25 A | 2026-07-23 | 2026-07-23 | 01-Jun-25 A | 11-Dec-25 A
A16230 | Technical Bid Evaluation for Flow Element (Venturi Tube)_IFR | 01-Sep-25 A | 10-Sep-25 A | 2026-07-23 | 2026-07-23 | 01-Sep-25 A | 10-Sep-25 A
A16240 | Technical Bid Evaluation for Flow Element (Venturi Tube)_RCC | 11-Sep-25 A | 15-Sep-25 A | 2026-07-23 | 2026-07-23 | 11-Sep-25 A | 15-Sep-25 A
A16250 | Technical Bid Evaluation for Flow Element (Venturi Tube)_IFA | 16-Sep-25 A | 25-Sep-25 A | 2026-07-23 | 2026-07-23 | 16-Sep-25 A | 25-Sep-25 A
A16260 | Technical Bid Evaluation for Flow Element (Venturi Tube)_RCA | 01-Oct-25 A | 15-Oct-25 A | 2026-07-23 | 2026-07-23 | 01-Oct-25 A | 15-Oct-25 A
A48170 | Technical Bid Evaluation for Flow Element (Venturi Tube)_IFD/IFC | 16-Oct-25 A | 31-Oct-25 A | 2026-07-23 | 2026-07-23 | 16-Oct-25 A | 31-Oct-25 A
A57610 | Issue RFQ to Bidders | 01-Jun-25 A | 22-Jun-25 A | 2026-07-23 | 2026-07-23 | 01-Jun-25 A | 22-Jun-25 A
A57630 | Commercial Bid Evaluation | 01-Nov-25 A | 17-Nov-25 A | 2026-07-23 | 2026-07-23 | 01-Nov-25 A | 17-Nov-25 A
A57640 | Issue Purchase Order to Vendor | 27-Nov-25 A | 11-Dec-25 A | 2026-07-23 | 2026-07-23 | 27-Nov-25 A | 11-Dec-25 A
FlowElementsOrifice |  | 01-May-25 A | 20-Mar-26 A | 2026-07-23 | 2026-07-23 | 01-May-25 A | 2026-03-25
A16180 | Technical Bid Evaluation for Flow Element (Orifice Plate)_IFR | 01-Sep-25 A | 23-Sep-25 A | 2026-07-23 | 2026-07-23 | 01-Sep-25 A | 23-Sep-25 A
A16190 | Technical Bid Evaluation for Flow Element (Orifice Plate)_RCC | 19-Sep-25 A | 30-Sep-25 A | 2026-07-23 | 2026-07-23 | 19-Sep-25 A | 30-Sep-25 A
A16200 | Technical Bid Evaluation for Flow Element (Orifice Plate)_IFA | 27-Nov-25 A | 02-Dec-25 A | 2026-07-23 | 2026-07-23 | 27-Nov-25 A | 02-Dec-25 A
A16220 | Technical Bid Evaluation for Flow Element (Orifice Plate)_IFD/IFC | 10-Mar-26 A | 20-Mar-26 A | 2026-07-23 | 2026-07-23 | 2026-03-13 | 2026-03-25
A48160 | Technical Bid Evaluation for Flow Element (Orifice Plate)_RCA | 28-Feb-26 A | 20-Mar-26 A | 2026-07-23 | 2026-07-23 | 2026-02-20 | 2026-03-13
A57920 | Issue RFQ to Bidders | 01-May-25 A | 15-May-25 A | 2026-07-23 | 2026-07-23 | 01-May-25 A | 15-May-25 A
A57930 | Issue Purchase Order to Vendor | 16-Dec-25 A | 18-Dec-25 A | 2026-07-23 | 2026-07-23 | 16-Dec-25 A | 18-Dec-25 A
A57950 | Commercial Bid Evaluation | 01-Dec-25 A | 12-Dec-25 A | 2026-07-23 | 2026-07-23 | 01-Dec-25 A | 12-Dec-25 A
PT,TT&DPT[PT50Nos,TT33Nos,DPT20Nos] |  | 18-Apr-25 A | 20-Mar-26 A | 2026-07-17 | 2026-07-17 | 18-Apr-25 A | 2026-03-23
A16130 | Technical Bid Evaluation for Electronic Transmitters_IFR | 19-Dec-25 A | 24-Dec-25 A | 2026-07-17 | 2026-07-17 | 19-Dec-25 A | 24-Dec-25 A
A16140 | Technical Bid Evaluation for Electronic Transmitters_RCC | 24-Dec-25 A | 17-Jan-26 A | 2026-07-17 | 2026-07-17 | 24-Dec-25 A | 17-Jan-26 A
A16160 | Technical Bid Evaluation for Electronic Transmitters_RCA | 01-Mar-26 A | 20-Mar-26 A | 2026-07-17 | 2026-07-17 | 2026-02-25 | 2026-03-02
A16170 | Technical Bid Evaluation for Electronic Transmitters_IFD/IFC | 01-Mar-26 A | 20-Mar-26 A | 2026-07-17 | 2026-07-17 | 2026-03-02 | 2026-03-06
A21030 | Issue RFQ to Bidders | 18-Apr-25 A | 09-May-25 A | 2026-07-17 | 2026-07-17 | 18-Apr-25 A | 09-May-25 A
A21040 | Issue Purchase Order to Vendor | 12-Mar-26 A | 20-Mar-26 A | 2026-07-17 | 2026-07-17 | 2026-03-11 | 2026-03-23
A21060 | Commercial Bid Evaluation(Completion) | 05-Mar-26 A | 20-Mar-26 A | 2026-07-17 | 2026-07-17 | 2026-03-06 | 2026-03-11
A48150 | Technical Bid Evaluation for Electronic Transmitters_IFA | 14-Mar-26 A | 20-Mar-26 A | 2026-07-17 | 2026-07-17 | 2026-02-20 | 2026-02-25
Rotameter |  | 29-Apr-25 A | 30-Jan-26 A | 2026-09-28 | 2026-09-28
Rotameter |  | 29-Apr-25 A | 30-Jan-26 A | 2026-09-28 | 2026-09-28
A64080 | Issue RFQ to Bidders | 29-Apr-25 A | 02-May-25 A | 2026-09-28 | 2026-09-28
A64090 | Issue Purchase Order to Vendor | 23-Jan-26 A | 30-Jan-26 A | 2026-09-28 | 2026-09-28
A64100 | Bid Evaluation(Completion) | 21-Nov-25 A | 29-Jan-26 A | 2026-09-28 | 2026-09-28
A64110 | Commercial Bid Evaluation(Completion) | 07-Jan-26 A | 20-Jan-26 A | 2026-09-28 | 2026-09-28
InstrumentBulkMaterial |  | 01-Feb-25 A | 20-Mar-26 A | 2026-06-15 | 2027-03-23 | 01-Feb-25 A | 2026-03-12
TA_InstrumentBulkMaterial(Single&Multicore=Approx.78,130Mtr,FOCablesJB&CableTrays)) |  | 01-Feb-25 A | 19-Mar-25 A | 2026-06-16 | 2026-06-16 | 01-Feb-25 A | 19-Mar-25 A
A22030 | Issue RFQs to Bidders | 01-Feb-25 A | 11-Feb-25 A | 2026-06-16 | 2026-06-16 | 01-Feb-25 A | 11-Feb-25 A
A22040 | Vendor Quote Received | 24-Feb-25 A | 04-Mar-25 A | 2026-06-16 | 2026-06-16 | 24-Feb-25 A | 04-Mar-25 A
A22050 | TBE for Instrument Bulk Material (TA) | 12-Feb-25 A | 21-Feb-25 A | 2026-06-16 | 2026-06-16 | 12-Feb-25 A | 21-Feb-25 A
A22070 | Issue Purchase Order to Vendor | 05-Mar-25 A | 19-Mar-25 A | 2026-06-16 | 2026-06-16 | 05-Mar-25 A | 19-Mar-25 A
Analyzer |  | 01-May-25 A | 08-Jun-25 A | 2027-01-28 | 2027-01-28 | 01-May-25 A | 08-Jun-25 A
A16380 | Technical Bid Evaluation for Analyzers_IFR | 01-May-25 A | 25-May-25 A | 2027-01-28 | 2027-01-28 | 01-May-25 A | 25-May-25 A
A16400 | Technical Bid Evaluation for Analyzers_IFA | 01-May-25 A | 23-May-25 A | 2027-01-28 | 2027-01-28 | 01-May-25 A | 23-May-25 A
A16410 | Technical Bid Evaluation for Analyzers_RCA | 01-May-25 A | 23-May-25 A | 2027-01-28 | 2027-01-28 | 01-May-25 A | 23-May-25 A
A16420 | Technical Bid Evaluation for Analyzers_IFD/IFC | 01-May-25 A | 23-May-25 A | 2027-01-28 | 2027-01-28 | 01-May-25 A | 23-May-25 A
A48190 | Technical Bid Evaluation for Analyzers_RCC | 01-May-25 A | 23-May-25 A | 2027-01-28 | 2027-01-28 | 01-May-25 A | 23-May-25 A
A57570 | Issue RFQ to Bidders | 01-May-25 A | 25-May-25 A | 2027-01-28 | 2027-01-28 | 01-May-25 A | 25-May-25 A
A57590 | Commercial Bid Evaluation | 25-May-25 A | 01-Jun-25 A | 2027-01-28 | 2027-01-28 | 25-May-25 A | 01-Jun-25 A
A57600 | Issue Purchase Order to Vendor | 02-Jun-25 A | 08-Jun-25 A | 2027-01-28 | 2027-01-28 | 02-Jun-25 A | 08-Jun-25 A
CableTrayandInstrumentJunctionBox(PerforatedCabletrayHeavyduty=5982Mtrs,JBs=73Nos) |  | 20-Jul-25 A | 20-Mar-26 A | 2026-08-31 | 2027-03-23 | 20-Jul-25 A | 2026-03-12
A16830 | Technical Bid Evaluation for Junction Boxes_IFR | 28-Nov-25 A | 12-Dec-25 A | 2026-08-31 | 2026-08-31 | 28-Nov-25 A | 12-Dec-25 A
A16840 | Technical Bid Evaluation for Junction Boxes_RCC | 19-Dec-25 A | 10-Jan-26 A | 2026-08-31 | 2026-08-31 | 19-Dec-25 A | 10-Jan-26 A
A16850 | Technical Bid Evaluation for Junction Boxes_IFA | 09-Mar-26 A | 11-Mar-26 A | 2026-08-31 | 2026-08-31 | 2026-02-20 | 2026-02-26
A16860 | Technical Bid Evaluation for Junction Boxes_RCA | 10-Mar-26 A | 12-Mar-26 A | 2027-03-23 | 2027-03-23 | 2026-02-27 | 2026-03-05
A16870 | Technical Bid Evaluation for Junction Boxes_IFD/IFC | 16-Mar-26 A | 20-Mar-26 A | 2027-03-23 | 2027-03-23 | 2026-03-06 | 2026-03-12
A17230 | Issue RFQ to Bidders | 20-Jul-25 A | 25-Oct-25 A | 2026-08-31 | 2026-08-31 | 20-Jul-25 A | 25-Oct-25 A
A20050 | Issue Purchase Order to Vendor | 15-Jan-26 A | 21-Jan-26 A | 2026-08-31 | 2026-08-31 | 15-Jan-26 A | 21-Jan-26 A
A20070 | Commercial Bid Evaluation(Completion) | 05-Jan-26 A | 14-Jan-26 A | 2026-08-31 | 2026-08-31 | 05-Jan-26 A | 14-Jan-26 A
MagneticLevelGauge(09Nos) |  | 18-Jul-25 A | 20-Mar-26 A | 2026-07-17 | 2026-07-17 | 18-Jul-25 A | 2026-02-26
A16430 | Technical Bid Evaluation for Level Gauges (Magnetic Type)_IFR | 07-Aug-25 A | 20-Aug-25 A | 2026-07-17 | 2026-07-17 | 07-Aug-25 A | 20-Aug-25 A
A16440 | Technical Bid Evaluation for Level Gauges (Magnetic Type)_RCC | 21-Aug-25 A | 29-Aug-25 A | 2026-07-17 | 2026-07-17 | 21-Aug-25 A | 29-Aug-25 A
A16460 | Technical Bid Evaluation for Level Gauges (Magnetic Type)_RCA | 16-Sep-25 A | 30-Sep-25 A | 2026-07-17 | 2026-07-17 | 16-Sep-25 A | 30-Sep-25 A
A16470 | Technical Bid Evaluation for Level Gauges (Magnetic Type)_IFD/IFC | 01-Oct-25 A | 30-Oct-25 A | 2026-07-17 | 2026-07-17 | 01-Oct-25 A | 30-Oct-25 A
A21270 | Issue RFQ to Bidders | 18-Jul-25 A | 06-Aug-25 A | 2026-07-17 | 2026-07-17 | 18-Jul-25 A | 06-Aug-25 A
A21280 | Issue Purchase Order to Vendor | 06-Mar-26 A | 20-Mar-26 A | 2026-07-17 | 2026-07-17 | 2026-02-20 | 2026-02-26
A21300 | Commercial Bid Evaluation(Completion) | 10-Nov-25 A | 21-Nov-25 A | 2026-07-17 | 2026-07-17 | 10-Nov-25 A | 21-Nov-25 A
A48200 | Technical Bid Evaluation for Level Gauges (Magnetic Type)_IFA | 30-Aug-25 A | 15-Sep-25 A | 2026-07-17 | 2026-07-17 | 30-Aug-25 A | 15-Sep-25 A
FibreOpticCable(Armoured,Telecom/IT/MAS) |  | 01-Jun-25 A | 18-Aug-25 A | 2026-06-15 | 2026-06-15 | 01-Jun-25 A | 18-Aug-25 A
A17170 | RFQs to Bid receipt | 01-Jun-25 A | 21-Jun-25 A | 2026-06-15 | 2026-06-15 | 01-Jun-25 A | 21-Jun-25 A
A18660 | Issue Purchase Order to Vendor | 09-Aug-25 A | 18-Aug-25 A | 2026-06-15 | 2026-06-15 | 09-Aug-25 A | 18-Aug-25 A
A18680 | Commercial Bid Evaluation(Completion) | 01-Aug-25 A | 08-Aug-25 A | 2026-06-15 | 2026-06-15 | 01-Aug-25 A | 08-Aug-25 A
A57510 | Technical Bid Evaluation for Instrument Cables_IFR | 30-Jul-25 A | 31-Jul-25 A | 2026-06-15 | 2026-06-15 | 30-Jul-25 A | 31-Jul-25 A
A57520 | Technical Bid Evaluation for Instrument Cables_RCC | 30-Jul-25 A | 31-Jul-25 A | 2026-06-15 | 2026-06-15 | 30-Jul-25 A | 31-Jul-25 A
A57530 | Technical Bid Evaluation for Instrument Cables_IFA | 30-Jul-25 A | 31-Jul-25 A | 2026-06-15 | 2026-06-15 | 30-Jul-25 A | 31-Jul-25 A
A57540 | Technical Bid Evaluation for Instrument Cables_RCA | 30-Jul-25 A | 31-Jul-25 A | 2026-06-15 | 2026-06-15 | 30-Jul-25 A | 31-Jul-25 A
A57550 | Technical Bid Evaluation for Instrument Cables_IFD/IFC | 30-Jul-25 A | 31-Jul-25 A | 2026-06-15 | 2026-06-15 | 30-Jul-25 A | 31-Jul-25 A
Earthing&PowerCables |  | 18-Jul-25 A | 24-Oct-25 A | 2026-07-30 | 2026-09-05 | 18-Jul-25 A | 24-Oct-25 A
PowerCables(11kV&33kV) |  | 01-Aug-25 A | 03-Sep-25 A | 2026-07-30 | 2026-07-30 | 01-Aug-25 A | 03-Sep-25 A
A58690 | Issue RFQ to Bidders | 01-Aug-25 A | 20-Aug-25 A | 2026-07-30 | 2026-07-30 | 01-Aug-25 A | 20-Aug-25 A
A58700 | Bid Evaluation(Completion) | 04-Aug-25 A | 25-Aug-25 A | 2026-07-30 | 2026-07-30 | 04-Aug-25 A | 25-Aug-25 A
A58710 | Commercial Bid Evaluation(Completion) | 06-Aug-25 A | 27-Aug-25 A | 2026-07-30 | 2026-07-30 | 06-Aug-25 A | 27-Aug-25 A
A58720 | Issue Purchase Order to Vendor | 25-Aug-25 A | 03-Sep-25 A | 2026-07-30 | 2026-07-30 | 25-Aug-25 A | 03-Sep-25 A
EarthingandPowerCables |  | 18-Jul-25 A | 24-Oct-25 A | 2026-08-23 | 2026-09-05 | 18-Jul-25 A | 24-Oct-25 A
A13230 | Technical Bid Evaluation For Power, Control And Earthing Cables_IFR | 21-Aug-25 A | 29-Aug-25 A | 2026-08-23 | 2026-08-23 | 21-Aug-25 A | 29-Aug-25 A
A13240 | Technical Bid Evaluation For Power, Control And Earthing Cables_RCC | 30-Aug-25 A | 10-Sep-25 A | 2026-08-23 | 2026-08-23 | 30-Aug-25 A | 10-Sep-25 A
A13250 | Technical Bid Evaluation For Power, Control And Earthing Cables_IFA | 11-Sep-25 A | 17-Sep-25 A | 2026-08-23 | 2026-08-23 | 11-Sep-25 A | 17-Sep-25 A
A13260 | Technical Bid Evaluation For Power, Control And Earthing Cables_RCA | 19-Sep-25 A | 30-Sep-25 A | 2026-09-05 | 2026-09-05 | 19-Sep-25 A | 30-Sep-25 A
A13270 | Technical Bid Evaluation For Power, Control And Earthing Cables_IFD/IFC | 01-Oct-25 A | 07-Oct-25 A | 2026-09-05 | 2026-09-05 | 01-Oct-25 A | 07-Oct-25 A
A16450 | Issue RFQ to Bidders | 18-Jul-25 A | 20-Aug-25 A | 2026-08-23 | 2026-08-23 | 18-Jul-25 A | 20-Aug-25 A
A20590 | Issue Purchase Order to Vendor | 15-Oct-25 A | 24-Oct-25 A | 2026-09-05 | 2026-09-05 | 15-Oct-25 A | 24-Oct-25 A
A20610 | Commercial Bid Evaluation(Completion) | 07-Oct-25 A | 14-Oct-25 A | 2026-09-05 | 2026-09-05 | 07-Oct-25 A | 14-Oct-25 A
TelecomCables |  | 05-Jan-26 A | 27-Feb-26 A | 2026-08-17 | 2026-08-17
TelecomCables |  | 05-Jan-26 A | 27-Feb-26 A | 2026-08-17 | 2026-08-17
A63800 | Issue RFQ to Bidders | 05-Jan-26 A | 12-Jan-26 A | 2026-08-17 | 2026-08-17
A63810 | Issue Purchase Order to Vendor | 24-Feb-26 A | 27-Feb-26 A | 2026-08-17 | 2026-08-17
A63820 | Bid Evaluation(Completion) | 10-Feb-26 A | 20-Feb-26 A | 2026-08-17 | 2026-08-17
A63830 | Commercial Bid Evaluation(Completion) | 18-Feb-26 A | 23-Feb-26 A | 2026-08-17 | 2026-08-17
ElectricalBulk |  | 15-Jan-25 A | 2026-06-25 | 2026-07-23 | 2026-09-30 | 15-Jan-25 A | 2026-05-29
TA_ElectricalBulkMaterial(Earthing,FO,PowerCables) |  | 15-Jan-25 A | 09-Mar-25 A | 2026-08-23 | 2026-08-23 | 15-Jan-25 A | 09-Mar-25 A
A17890 | Issue RFQ to Bidders | 15-Jan-25 A | 08-Feb-25 A | 2026-08-23 | 2026-08-23 | 15-Jan-25 A | 08-Feb-25 A
A17900 | Vendor Quote Received | 10-Feb-25 A | 19-Feb-25 A | 2026-08-23 | 2026-08-23 | 10-Feb-25 A | 19-Feb-25 A
A17910 | Negotiations and PO Placement (33 KVA) | 03-Mar-25 A | 09-Mar-25 A | 2026-08-23 | 2026-08-23 | 03-Mar-25 A | 09-Mar-25 A
A17920 | TBE | 20-Feb-25 A | 28-Feb-25 A | 2026-08-23 | 2026-08-23 | 20-Feb-25 A | 28-Feb-25 A
CableTrays,JBs,ConduitPipe,CableLugs,etc |  | 18-Mar-26 A | 2026-06-17 | 2026-07-27 | 2026-09-25 | 2026-02-20 | 2026-05-13
A20650 | Issue Purchase Order to Vendor | 2026-05-29 | 2026-06-17 | 2026-09-07 | 2026-09-25 | 2026-04-24 | 2026-05-13
A20660 | Bid Evaluation(Completion) | 2026-04-17 | 2026-05-07 | 2026-07-27 | 2026-08-17 | 2026-03-13 | 2026-04-02
A20670 | Commercial Bid Evaluation(Completion) | 2026-05-08 | 2026-05-28 | 2026-08-17 | 2026-09-07 | 2026-04-03 | 2026-04-23
A9450 | Issue RFQ to Bidders | 18-Mar-26 A | 20-Mar-26 A | 2026-07-27 | 2026-07-27 | 2026-02-20 | 2026-03-12
LCS&SnapSwitches |  | 01-Mar-26 A | 2026-06-25 | 2026-07-23 | 2026-09-30 | 2026-02-20 | 2026-05-29
A21690 | Issue RFQ to Bidders | 01-Mar-26 A | 20-Mar-26 A | 2026-07-23 | 2026-07-23 | 2026-02-20 | 2026-03-20
A21700 | Issue Purchase Order to Vendor | 2026-06-08 | 2026-06-25 | 2026-09-11 | 2026-09-30 | 2026-05-12 | 2026-05-29
A21710 | Bid Evaluation(Completion) | 2026-04-17 | 2026-05-15 | 2026-07-23 | 2026-08-20 | 2026-03-23 | 2026-04-20
A21720 | Commercial Bid Evaluation(Completion) | 2026-05-18 | 2026-06-05 | 2026-08-21 | 2026-09-10 | 2026-04-21 | 2026-05-11
MainAutomationEquipment |  | 01-Feb-25 A | 15-Apr-26 A | 2026-06-16 | 2026-11-24 | 01-Feb-25 A | 2026-04-02
OnOffValve/ControlValves |  | 10-Apr-25 A | 20-Oct-25 A | 2026-07-13 | 2026-08-04 | 10-Apr-25 A | 20-Oct-25 A
ESDValve |  | 10-Apr-25 A | 16-May-25 A | 2026-07-13 | 2026-07-14 | 10-Apr-25 A | 16-May-25 A
A59730 | Issue RFQ to Bidders | 10-Apr-25 A | 02-May-25 A | 2026-07-13 | 2026-07-13 | 10-Apr-25 A | 02-May-25 A
A59740 | Issue Purchase Order to Vendor for ESD | 15-May-25 A | 16-May-25 A | 2026-07-13 | 2026-07-13 | 15-May-25 A | 16-May-25 A
A59750 | Commercial Bid Evaluation(Completion) | 14-May-25 A | 15-May-25 A | 2026-07-13 | 2026-07-13 | 14-May-25 A | 15-May-25 A
A59760 | Technical Bid Evaluation for ESD_IFR | 02-May-25 A | 05-May-25 A | 2026-07-13 | 2026-07-13 | 02-May-25 A | 05-May-25 A
A59770 | Technical Bid Evaluation for ESD_RCC | 05-May-25 A | 07-May-25 A | 2026-07-13 | 2026-07-13 | 05-May-25 A | 07-May-25 A
A59780 | Technical Bid Evaluation for ESD_IFA | 08-May-25 A | 09-May-25 A | 2026-07-13 | 2026-07-13 | 08-May-25 A | 09-May-25 A
A59790 | Technical Bid Evaluation for ESD_RCA | 10-May-25 A | 12-May-25 A | 2026-07-14 | 2026-07-14 | 10-May-25 A | 12-May-25 A
A59800 | Technical Bid Evaluation for ESD_IFD/IFC | 13-May-25 A | 14-May-25 A | 2026-07-14 | 2026-07-14 | 13-May-25 A | 14-May-25 A
ControlValves(1"-24"Rating150,300&2500=32Nos)+SDV |  | 21-Apr-25 A | 20-Oct-25 A | 2026-07-13 | 2026-08-04 | 21-Apr-25 A | 20-Oct-25 A
A16480 | Technical Bid Evaluation for Control Valves_IFR | 23-Aug-25 A | 18-Sep-25 A | 2026-07-13 | 2026-07-13 | 23-Aug-25 A | 18-Sep-25 A
A16490 | Technical Bid Evaluation for Control Valves_RCC | 23-Aug-25 A | 18-Sep-25 A | 2026-07-13 | 2026-07-13 | 23-Aug-25 A | 18-Sep-25 A
A16500 | Technical Bid Evaluation for Control Valves_IFA | 23-Aug-25 A | 18-Sep-25 A | 2026-07-13 | 2026-07-13 | 23-Aug-25 A | 18-Sep-25 A
A16520 | Technical Bid Evaluation for Control Valves_IFD/IFC | 23-Aug-25 A | 18-Sep-25 A | 2026-07-13 | 2026-07-13 | 23-Aug-25 A | 18-Sep-25 A
A16750 | Issue RFQ to Bidders | 21-Apr-25 A | 15-May-25 A | 2026-07-13 | 2026-07-13 | 21-Apr-25 A | 15-May-25 A
A22100 | Commercial Bid Evaluation(Completion) | 17-Sep-25 A | 18-Sep-25 A | 2026-07-13 | 2026-07-13 | 17-Sep-25 A | 18-Sep-25 A
A22110 | Issue Purchase Order to Vendor for Control Valves | 01-Oct-25 A | 20-Oct-25 A | 2026-08-04 | 2026-08-04 | 01-Oct-25 A | 20-Oct-25 A
A48210 | Technical Bid Evaluation for Control Valves_RCA | 23-Aug-25 A | 18-Sep-25 A | 2026-07-13 | 2026-07-13 | 23-Aug-25 A | 18-Sep-25 A
MOVs |  | 21-Apr-25 A | 10-Sep-25 A | 2026-10-28 | 2026-10-28 | 21-Apr-25 A | 10-Sep-25 A
MOVs[BallType24"150#=01No] |  | 21-Apr-25 A | 10-Sep-25 A | 2026-10-28 | 2026-10-28 | 21-Apr-25 A | 10-Sep-25 A
A16640 | Technical Bid Evaluation for Motor Operated Valves_RCC | 22-Aug-25 A | 02-Sep-25 A | 2026-10-28 | 2026-10-28 | 22-Aug-25 A | 02-Sep-25 A
A16650 | Technical Bid Evaluation for Motor Operated Valves_IFA | 19-Aug-25 A | 29-Aug-25 A | 2026-10-28 | 2026-10-28 | 19-Aug-25 A | 29-Aug-25 A
A16660 | Technical Bid Evaluation for Motor Operated Valves_RCA | 30-Aug-25 A | 06-Sep-25 A | 2026-10-28 | 2026-10-28 | 30-Aug-25 A | 06-Sep-25 A
A16670 | Technical Bid Evaluation for Motor Operated Valves_IFD/IFC | 07-Sep-25 A | 10-Sep-25 A | 2026-10-28 | 2026-10-28 | 07-Sep-25 A | 10-Sep-25 A
A17050 | RFQs to Bid Receipt | 21-Apr-25 A | 15-May-25 A | 2026-10-28 | 2026-10-28 | 21-Apr-25 A | 15-May-25 A
A18600 | Issue Purchase Order to Vendor for MOVs | 26-Aug-25 A | 02-Sep-25 A | 2026-10-28 | 2026-10-28 | 26-Aug-25 A | 02-Sep-25 A
A18620 | Commercial Bid Evaluation(Completion) | 19-Aug-25 A | 01-Sep-25 A | 2026-10-28 | 2026-10-28 | 19-Aug-25 A | 01-Sep-25 A
A48230 | Technical Bid Evaluation for Motor Operated Valves_IFR | 16-May-25 A | 22-Aug-25 A | 2026-10-28 | 2026-10-28 | 16-May-25 A | 22-Aug-25 A
MachineConditionMonitoringSystem(MCMS) |  | 01-Feb-25 A | 01-Jun-25 A | 2026-06-16 | 2026-11-24 | 01-Feb-25 A | 01-Jun-25 A
TA_MCMSSystemModification-BentlyNevada |  | 01-Feb-25 A | 15-Mar-25 A | 2026-06-16 | 2026-06-16 | 01-Feb-25 A | 15-Mar-25 A
A37160 | Issue RFQ to Bidders | 01-Feb-25 A | 22-Feb-25 A | 2026-06-16 | 2026-06-16 | 01-Feb-25 A | 22-Feb-25 A
A37190 | Issue Purchase Order to Vendor | 10-Mar-25 A | 15-Mar-25 A | 2026-06-16 | 2026-06-16 | 10-Mar-25 A | 15-Mar-25 A
A57450 | TBE for ICT System Modification_Free Issue Material | 23-Feb-25 A | 09-Mar-25 A | 2026-06-16 | 2026-06-16 | 23-Feb-25 A | 09-Mar-25 A
MachineConditionMonitoringSystem |  | 01-Apr-25 A | 01-Jun-25 A | 2026-11-24 | 2026-11-24 | 01-Apr-25 A | 01-Jun-25 A
A17110 | Issue RFQ to Bidders | 01-Apr-25 A | 20-Apr-25 A | 2026-11-24 | 2026-11-24 | 01-Apr-25 A | 20-Apr-25 A
A19930 | Issue Purchase Order to Vendor for MCMS | 08-May-25 A | 15-May-25 A | 2026-11-24 | 2026-11-24 | 08-May-25 A | 15-May-25 A
A19950 | Commercial Bid Evaluation(Completion) | 26-May-25 A | 01-Jun-25 A | 2026-11-24 | 2026-11-24 | 26-May-25 A | 01-Jun-25 A
A58590 | Technical Bid Evaluation for MCMS System_IFR | 01-May-25 A | 15-May-25 A | 2026-11-24 | 2026-11-24 | 01-May-25 A | 15-May-25 A
A58600 | Technical Bid Evaluation for MCMS System_RCC | 16-May-25 A | 19-May-25 A | 2026-11-24 | 2026-11-24 | 16-May-25 A | 19-May-25 A
A58610 | Technical Bid Evaluation for MCMSSystem_IFA | 16-May-25 A | 19-May-25 A | 2026-11-24 | 2026-11-24 | 16-May-25 A | 19-May-25 A
A58620 | Technical Bid Evaluation for MCMS System_RCA | 16-May-25 A | 19-May-25 A | 2026-11-24 | 2026-11-24 | 16-May-25 A | 19-May-25 A
A58630 | Technical Bid Evaluation for MCMS System_IFD/IFC | 20-May-25 A | 25-May-25 A | 2026-11-24 | 2026-11-24 | 20-May-25 A | 25-May-25 A
IPCSModification(ABB) |  | 01-Feb-25 A | 25-Jul-25 A | 2026-06-16 | 2026-09-01 | 01-Feb-25 A | 25-Jul-25 A
TA_IntegratedProtectionandControlSystem-ABB/Hitachi |  | 01-Feb-25 A | 18-Mar-25 A | 2026-06-16 | 2026-06-16 | 01-Feb-25 A | 18-Mar-25 A
A20950 | Issue RFQ to Bidders | 01-Feb-25 A | 25-Feb-25 A | 2026-06-16 | 2026-06-16 | 01-Feb-25 A | 25-Feb-25 A
A20960 | Issue Purchase Order to Vendor | 10-Mar-25 A | 18-Mar-25 A | 2026-06-16 | 2026-06-16 | 10-Mar-25 A | 18-Mar-25 A
A57390 | TBE for Electrical System Modification_ Free Issue Material | 26-Feb-25 A | 09-Mar-25 A | 2026-06-16 | 2026-06-16 | 26-Feb-25 A | 09-Mar-25 A
IntegratedProtectionandControlSystem |  | 10-Apr-25 A | 25-Jul-25 A | 2026-09-01 | 2026-09-01 | 10-Apr-25 A | 25-Jul-25 A
A23820 | Issue RFQ to Bidders | 10-Apr-25 A | 01-May-25 A | 2026-09-01 | 2026-09-01 | 10-Apr-25 A | 01-May-25 A
A23830 | Issue Purchase Order to Vendor for IPCS | 17-Jul-25 A | 25-Jul-25 A | 2026-09-01 | 2026-09-01 | 17-Jul-25 A | 25-Jul-25 A
A23850 | Commercial Bid Evaluation(Completion) | 07-Jul-25 A | 16-Jul-25 A | 2026-09-01 | 2026-09-01 | 07-Jul-25 A | 16-Jul-25 A
A58540 | Technical Bid Evaluation for IPCS_IFR | 02-May-25 A | 10-May-25 A | 2026-09-01 | 2026-09-01 | 02-May-25 A | 10-May-25 A
A58550 | Technical Bid Evaluation for IPCS_RCC | 11-May-25 A | 20-May-25 A | 2026-09-01 | 2026-09-01 | 11-May-25 A | 20-May-25 A
A58560 | Technical Bid Evaluation for IPCS_IFA | 21-May-25 A | 26-May-25 A | 2026-09-01 | 2026-09-01 | 21-May-25 A | 26-May-25 A
A58570 | Technical Bid Evaluation for IPCS_RCA | 27-May-25 A | 31-May-25 A | 2026-09-01 | 2026-09-01 | 27-May-25 A | 31-May-25 A
A58580 | Technical Bid Evaluation for IPCS_IFD/IFC | 01-Jun-25 A | 04-Jun-25 A | 2026-09-01 | 2026-09-01 | 01-Jun-25 A | 04-Jun-25 A
OTS |  | 01-Feb-25 A | 20-Aug-25 A | 2026-06-16 | 2026-09-01 | 01-Feb-25 A | 20-Aug-25 A
TA_SCMSModification-Siemens |  | 01-Feb-25 A | 03-Mar-25 A | 2026-06-16 | 2026-06-16 | 01-Feb-25 A | 03-Mar-25 A
A24190 | Issue RFQ to Bidders | 01-Feb-25 A | 10-Feb-25 A | 2026-06-16 | 2026-06-16 | 01-Feb-25 A | 10-Feb-25 A
A24200 | Issue Purchase Order to Vendor | 25-Feb-25 A | 03-Mar-25 A | 2026-06-16 | 2026-06-16 | 25-Feb-25 A | 03-Mar-25 A
A57360 | TBE for Electrical System Modification_ Free Issue Material | 11-Feb-25 A | 24-Feb-25 A | 2026-06-16 | 2026-06-16 | 11-Feb-25 A | 24-Feb-25 A
SCMS |  | 19-Mar-25 A | 20-Aug-25 A | 2026-09-01 | 2026-09-01 | 19-Mar-25 A | 20-Aug-25 A
A60190 | Issue RFQ to Bidders | 19-Mar-25 A | 20-May-25 A | 2026-09-01 | 2026-09-01 | 19-Mar-25 A | 20-May-25 A
A60200 | Issue Purchase Order to Vendor for SCMS | 16-Jul-25 A | 20-Aug-25 A | 2026-09-01 | 2026-09-01 | 16-Jul-25 A | 20-Aug-25 A
A60210 | Commercial Bid Evaluation(Completion) | 04-Jul-25 A | 15-Jul-25 A | 2026-09-01 | 2026-09-01 | 04-Jul-25 A | 15-Jul-25 A
A60220 | Technical Bid Evaluation for SCMS_IFR | 21-May-25 A | 01-Jun-25 A | 2026-09-01 | 2026-09-01 | 21-May-25 A | 01-Jun-25 A
A60230 | Technical Bid Evaluation for SCMS_RCC | 02-Jun-25 A | 12-Jun-25 A | 2026-09-01 | 2026-09-01 | 02-Jun-25 A | 12-Jun-25 A
A60240 | Technical Bid Evaluation for SCMS_IFA | 13-Jun-25 A | 19-Jun-25 A | 2026-09-01 | 2026-09-01 | 13-Jun-25 A | 19-Jun-25 A
A60250 | Technical Bid Evaluation for SCMS_RCA | 20-Jun-25 A | 26-Jun-25 A | 2026-09-01 | 2026-09-01 | 20-Jun-25 A | 26-Jun-25 A
A60260 | Technical Bid Evaluation for SCMS_IFD/IFC | 27-Jun-25 A | 03-Jul-25 A | 2026-09-01 | 2026-09-01 | 27-Jun-25 A | 03-Jul-25 A
ICSS(IntegratedControlandSafetySystem)includingsys.Modifications |  | 07-Feb-25 A | 20-Jun-25 A | 2026-06-16 | 2026-07-30 | 07-Feb-25 A | 20-Jun-25 A
IntegratedControlandSafetySystemGF |  | 15-May-25 A | 20-Jun-25 A | 2026-07-30 | 2026-07-30 | 15-May-25 A | 20-Jun-25 A
A16880 | Technical Bid Evaluation for ICSS System_IFR | 26-May-25 A | 28-May-25 A | 2026-07-30 | 2026-07-30 | 26-May-25 A | 28-May-25 A
A16890 | Technical Bid Evaluation for ICSS System_RCC | 29-May-25 A | 30-May-25 A | 2026-07-30 | 2026-07-30 | 29-May-25 A | 30-May-25 A
A16900 | Technical Bid Evaluation for ICSS System_IFA | 30-May-25 A | 31-May-25 A | 2026-07-30 | 2026-07-30 | 30-May-25 A | 31-May-25 A
A16910 | Technical Bid Evaluation for ICSS System_RCA | 31-May-25 A | 01-Jun-25 A | 2026-07-30 | 2026-07-30 | 31-May-25 A | 01-Jun-25 A
A16920 | Technical Bid Evaluation for ICSS System_IFD/IFC | 01-Jun-25 A | 06-Jun-25 A | 2026-07-30 | 2026-07-30 | 01-Jun-25 A | 06-Jun-25 A
A23940 | Issue RFQ to Bidders | 15-May-25 A | 30-May-25 A | 2026-07-30 | 2026-07-30 | 15-May-25 A | 30-May-25 A
A23950 | Issue Purchase Order to Vendor for ICSS | 14-Jun-25 A | 20-Jun-25 A | 2026-07-30 | 2026-07-30 | 14-Jun-25 A | 20-Jun-25 A
A23970 | Commercial Bid Evaluation(Completion) | 07-Jun-25 A | 13-Jun-25 A | 2026-07-30 | 2026-07-30 | 07-Jun-25 A | 13-Jun-25 A
TA_IntegratedControl&SafetySystemBF-Honeywell |  | 07-Feb-25 A | 10-Mar-25 A | 2026-06-16 | 2026-06-16 | 07-Feb-25 A | 10-Mar-25 A
A19770 | Issue RFQ to Bidders | 07-Feb-25 A | 17-Feb-25 A | 2026-06-16 | 2026-06-16 | 07-Feb-25 A | 17-Feb-25 A
A19780 | Issue Purchase Order to Vendor | 01-Mar-25 A | 10-Mar-25 A | 2026-06-16 | 2026-06-16 | 01-Mar-25 A | 10-Mar-25 A
A56210 | TBE for ICT System Modification_Free Issue Material | 18-Feb-25 A | 28-Feb-25 A | 2026-06-16 | 2026-06-16 | 18-Feb-25 A | 28-Feb-25 A
InstrumentCables |  | 01-Nov-25 A | 20-Mar-26 A | 2026-09-15 | 2026-09-15 | 01-Nov-25 A | 2026-03-12
InstrumentCable(Single&Multicore=Approx.78,130Mtr) |  | 01-Nov-25 A | 20-Mar-26 A | 2026-09-15 | 2026-09-15 | 01-Nov-25 A | 2026-03-12
A16780 | Technical Bid Evaluation for Instrument Cables_IFR | 26-Jan-26 A | 31-Jan-26 A | 2026-09-15 | 2026-09-15 | 26-Jan-26 A | 31-Jan-26 A
A16790 | Technical Bid Evaluation for Instrument Cables_RCC | 02-Feb-26 A | 06-Feb-26 A | 2026-09-15 | 2026-09-15 | 02-Feb-26 A | 06-Feb-26 A
A16800 | Technical Bid Evaluation for Instrument Cables_IFA | 06-Feb-26 A | 10-Mar-26 A | 2026-09-15 | 2026-09-15 | 06-Feb-26 A | 2026-02-26
A16810 | Technical Bid Evaluation for Instrument Cables_RCA | 05-Mar-26 A | 16-Mar-26 A | 2026-09-15 | 2026-09-15 | 2026-02-27 | 2026-03-05
A16820 | Technical Bid Evaluation for Instrument Cables_IFD/IFC | 06-Mar-26 A | 18-Mar-26 A | 2026-09-15 | 2026-09-15 | 2026-03-06 | 2026-03-12
A21190 | Issue RFQ to Bidders | 01-Nov-25 A | 11-Nov-25 A | 2026-09-15 | 2026-09-15 | 01-Nov-25 A | 11-Nov-25 A
A21200 | Issue Purchase Order to Vendor | 12-Mar-26 A | 20-Mar-26 A | 2026-09-15 | 2026-09-15 | 2026-03-06 | 2026-03-12
A21220 | Commercial Bid Evaluation(Completion) | 05-Mar-26 A | 20-Mar-26 A | 2026-09-15 | 2026-09-15 | 2026-02-27 | 2026-03-05
LocalFireControlPanelincludingF&GDetectors |  | 20-Jun-25 A | 12-Dec-25 A | 2026-06-30 | 2026-06-30 | 20-Jun-25 A | 12-Dec-25 A
FireDetectionAlarmSystemandLocalFireControlPanel(CleanAgentUnit) |  | 20-Jun-25 A | 12-Dec-25 A | 2026-06-30 | 2026-06-30 | 20-Jun-25 A | 12-Dec-25 A
A16930 | Issue RFQ to Bidders | 20-Jun-25 A | 14-Aug-25 A | 2026-06-30 | 2026-06-30 | 20-Jun-25 A | 14-Aug-25 A
A19650 | Issue Purchase Order to Vendor for Fire Detection, Local Fire Control and Clean Agent | 01-Dec-25 A | 12-Dec-25 A | 2026-06-30 | 2026-06-30 | 01-Dec-25 A | 12-Dec-25 A
A19660 | Bid Evaluation(Completion) | 01-Nov-25 A | 14-Nov-25 A | 2026-06-30 | 2026-06-30 | 01-Nov-25 A | 14-Nov-25 A
A19670 | Commercial Bid Evaluation(Completion) | 28-Nov-25 A | 10-Dec-25 A | 2026-06-30 | 2026-06-30 | 28-Nov-25 A | 10-Dec-25 A
PSVs |  | 15-Oct-25 A | 30-Mar-26 A | 2026-06-19 | 2026-06-19 | 15-Oct-25 A | 2026-03-25
PSVs(1"x2"upto8"x10"-CSRating150/150,300/150=22Nos) |  | 15-Oct-25 A | 30-Mar-26 A | 2026-06-19 | 2026-06-19 | 15-Oct-25 A | 2026-03-25
A21110 | Issue RFQ to Bidders | 15-Oct-25 A | 27-Oct-25 A | 2026-06-19 | 2026-06-19 | 15-Oct-25 A | 27-Oct-25 A
A21120 | Issue Purchase Order to Vendor | 20-Mar-26 A | 30-Mar-26 A | 2026-06-19 | 2026-06-19 | 2026-03-17 | 2026-03-25
A21130 | Bid Evaluation(Completion) | 15-Feb-26 A | 04-Mar-26 A | 2026-06-19 | 2026-06-19 | 15-Feb-26 A | 2026-03-05
A21140 | Commercial Bid Evaluation(Completion) | 09-Mar-26 A | 20-Mar-26 A | 2026-06-19 | 2026-06-19 | 2026-03-06 | 2026-03-16
SamplingSystem |  | 12-Feb-25 A | 18-Mar-25 A | 2026-06-16 | 2026-06-16 | 12-Feb-25 A | 18-Mar-25 A
TA_CGCTurbineSoftwareUpgrade-HMI |  | 15-Feb-25 A | 18-Mar-25 A | 2026-06-16 | 2026-06-16 | 15-Feb-25 A | 18-Mar-25 A
A37240 | Issue RFQ to Bidders | 15-Feb-25 A | 25-Feb-25 A | 2026-06-16 | 2026-06-16 | 15-Feb-25 A | 25-Feb-25 A
A37270 | Issue Purchase Order to Vendor | 08-Mar-25 A | 18-Mar-25 A | 2026-06-16 | 2026-06-16 | 08-Mar-25 A | 18-Mar-25 A
A57300 | TBE for ICT System Modification_Free Issue Material | 26-Feb-25 A | 07-Mar-25 A | 2026-06-16 | 2026-06-16 | 26-Feb-25 A | 07-Mar-25 A
TA_SGMReplacement(AdditionalItem) |  | 12-Feb-25 A | 15-Mar-25 A | 2026-06-16 | 2026-06-16 | 12-Feb-25 A | 15-Mar-25 A
A37400 | Issue RFQ to Bidders | 12-Feb-25 A | 22-Feb-25 A | 2026-06-16 | 2026-06-16 | 12-Feb-25 A | 22-Feb-25 A
A37410 | Issue Purchase Order to Vendor | 05-Mar-25 A | 15-Mar-25 A | 2026-06-16 | 2026-06-16 | 05-Mar-25 A | 15-Mar-25 A
A57330 | TBE for ICT System Modification_Free Issue Material | 23-Feb-25 A | 04-Mar-25 A | 2026-06-16 | 2026-06-16 | 23-Feb-25 A | 04-Mar-25 A
F&G[324Nos]FlameDetectors,MCP,Beacon,etc. |  | 18-Jul-25 A | 15-Apr-26 A | 2026-07-10 | 2026-07-10 | 18-Jul-25 A | 2026-04-02
F&GFlameDetectors,MCP,Beacon(Nos324) |  | 18-Jul-25 A | 15-Apr-26 A | 2026-07-10 | 2026-07-10 | 18-Jul-25 A | 2026-04-02
A16530 | Technical Bid Evaluation for Fire & Gas Detectors_IFR | 01-Dec-25 A | 13-Feb-26 A | 2026-07-10 | 2026-07-10 | 01-Dec-25 A | 13-Feb-26 A
A16540 | Technical Bid Evaluation for Fire & Gas Detectors_RCC | 14-Feb-26 A | 10-Mar-26 A | 2026-07-10 | 2026-07-10 | 14-Feb-26 A | 2026-03-03
A16550 | Technical Bid Evaluation for Fire & Gas Detectors_IFA | 09-Mar-26 A | 15-Apr-26 A | 2026-07-10 | 2026-07-10 | 2026-03-03 | 2026-03-11
A16560 | Technical Bid Evaluation for Fire & Gas Detectors_RCA | 11-Mar-26 A | 18-Mar-26 A | 2026-07-10 | 2026-07-10 | 2026-03-11 | 2026-03-19
A17350 | Issue RFQ to Bidders | 18-Jul-25 A | 14-Aug-25 A | 2026-07-10 | 2026-07-10 | 18-Jul-25 A | 14-Aug-25 A
A20110 | Issue Purchase Order to Vendor F&G Flames Detectors, MCP, Beacon (nos 324) | 16-Mar-26 A | 20-Mar-26 A | 2026-07-10 | 2026-07-10 | 2026-03-17 | 2026-04-02
A20130 | Commercial Bid Evaluation(Completion) | 18-Mar-26 A | 20-Mar-26 A | 2026-07-10 | 2026-07-10 | 2026-03-03 | 2026-03-17
A48220 | Technical Bid Evaluation for Fire & Gas Detectors_IFD/IFC | 12-Mar-26 A | 20-Mar-26 A | 2026-07-10 | 2026-07-10 | 2026-03-19 | 2026-03-30
MainElectricalEquipment |  | 01-Feb-25 A | 2026-05-18 | 2026-06-16 | 2026-12-21 | 01-Feb-25 A | 2026-05-13
LVBusDuct |  | 11-Aug-25 A | 20-Mar-26 A | 2026-09-10 | 2026-09-10
LVBusDuct |  | 11-Aug-25 A | 20-Mar-26 A | 2026-09-10 | 2026-09-10
A63680 | Issue RFQ to Bidders | 11-Aug-25 A | 14-Aug-25 A | 2026-09-10 | 2026-09-10
A63690 | Issue Purchase Order to Vendor | 19-Mar-26 A | 20-Mar-26 A | 2026-09-10 | 2026-09-10
A63700 | Bid Evaluation(Completion) | 08-Dec-25 A | 26-Dec-25 A | 2026-09-10 | 2026-09-10
A63710 | Commercial Bid Evaluation(Completion) | 26-Dec-25 A | 16-Jan-26 A | 2026-09-10 | 2026-09-10
DGSet(750KVA) |  | 01-Feb-25 A | 25-Sep-25 A | 2026-07-11 | 2026-07-11 | 01-Feb-25 A | 25-Sep-25 A
DGSet |  | 01-Feb-25 A | 25-Sep-25 A | 2026-07-11 | 2026-07-11 | 01-Feb-25 A | 25-Sep-25 A
A13330 | Technical Bid Evaluation For Emergency Diesel Generator Set_IFR | 03-May-25 A | 21-May-25 A | 2026-07-11 | 2026-07-11 | 03-May-25 A | 21-May-25 A
A13340 | Technical Bid Evaluation For Emergency Diesel Generator Set_RCC | 14-Jul-25 A | 22-Aug-25 A | 2026-07-11 | 2026-07-11 | 14-Jul-25 A | 22-Aug-25 A
A13350 | Technical Bid Evaluation For Emergency Diesel Generator Set_IFA | 23-Aug-25 A | 08-Sep-25 A | 2026-07-11 | 2026-07-11 | 23-Aug-25 A | 08-Sep-25 A
A13360 | Technical Bid Evaluation For Emergency Diesel Generator Set_RCA | 20-Aug-25 A | 15-Sep-25 A | 2026-07-11 | 2026-07-11 | 20-Aug-25 A | 15-Sep-25 A
A13370 | Technical Bid Evaluation For Emergency Diesel Generator Set_IFD/IFC | 10-Sep-25 A | 25-Sep-25 A | 2026-07-11 | 2026-07-11 | 10-Sep-25 A | 25-Sep-25 A
A16030 | Issue RFQ to Bidders | 01-Feb-25 A | 07-Feb-25 A | 2026-07-11 | 2026-07-11 | 01-Feb-25 A | 07-Feb-25 A
A20410 | Issue Purchase Order to Vendor for DG Set | 09-Aug-25 A | 22-Aug-25 A | 2026-07-11 | 2026-07-11 | 09-Aug-25 A | 22-Aug-25 A
A20430 | Commercial Bid Evaluation(Completion) | 18-Jul-25 A | 08-Aug-25 A | 2026-07-11 | 2026-07-11 | 18-Jul-25 A | 08-Aug-25 A
UPS(AC-60KVA,20KVA,DC-UPS6.5KVA) |  | 12-Feb-25 A | 20-Mar-26 A | 2026-06-16 | 2026-09-23 | 12-Feb-25 A | 2026-03-09
TA_UPSModification(AdditionalItem)-ChlorideTechnology |  | 12-Feb-25 A | 15-Mar-25 A | 2026-06-16 | 2026-06-16 | 12-Feb-25 A | 15-Mar-25 A
A37080 | Issue RFQs to Bidders | 12-Feb-25 A | 22-Feb-25 A | 2026-06-16 | 2026-06-16 | 12-Feb-25 A | 22-Feb-25 A
A37090 | Issue Purchase Order to Vendor | 05-Mar-25 A | 15-Mar-25 A | 2026-06-16 | 2026-06-16 | 05-Mar-25 A | 15-Mar-25 A
A57420 | TBE for Electrical System Modification_ Free Issue Material | 23-Feb-25 A | 04-Mar-25 A | 2026-06-16 | 2026-06-16 | 23-Feb-25 A | 04-Mar-25 A
UPS(AC-60KVA,20KVA,DC-UPS6.5KVA)Qty1+1+1=03Nos |  | 07-Jul-25 A | 20-Mar-26 A | 2026-09-23 | 2026-09-23 | 07-Jul-25 A | 2026-03-09
A13080 | Technical Bid Evaluation For AC UPS_IFR | 06-Sep-25 A | 13-Sep-25 A | 2026-09-23 | 2026-09-23 | 06-Sep-25 A | 13-Sep-25 A
A13090 | Technical Bid Evaluation For AC UPS_RCC | 14-Sep-25 A | 20-Sep-25 A | 2026-09-23 | 2026-09-23 | 14-Sep-25 A | 20-Sep-25 A
A13100 | Technical Bid Evaluation For AC UPS_IFA | 20-Oct-25 A | 03-Nov-25 A | 2026-09-23 | 2026-09-23 | 20-Oct-25 A | 03-Nov-25 A
A13110 | Technical Bid Evaluation For AC UPS_RCA | 04-Nov-25 A | 12-Nov-25 A | 2026-09-23 | 2026-09-23 | 04-Nov-25 A | 12-Nov-25 A
A13120 | Technical Bid Evaluation For AC UPS_IFD/IFC | 18-Mar-26 A | 20-Mar-26 A | 2026-09-23 | 2026-09-23 | 2026-02-20 | 2026-03-09
A16090 | Issue RFQ to Bidders | 07-Jul-25 A | 04-Aug-25 A | 2026-09-23 | 2026-09-23 | 07-Jul-25 A | 04-Aug-25 A
A19530 | Issue Purchase Order to Vendor for UPS (GF) | 29-Sep-25 A | 16-Oct-25 A | 2026-09-23 | 2026-09-23 | 29-Sep-25 A | 16-Oct-25 A
A19550 | Commercial Bid Evaluation(Completion) | 01-Sep-25 A | 26-Sep-25 A | 2026-09-23 | 2026-09-23 | 01-Sep-25 A | 26-Sep-25 A
PowerTransformer |  | 10-May-25 A | 17-Sep-25 A | 2026-09-07 | 2026-09-07 | 10-May-25 A | 17-Sep-25 A
PowerTransformers(Qty05) |  | 10-May-25 A | 17-Sep-25 A | 2026-09-07 | 2026-09-07 | 10-May-25 A | 17-Sep-25 A
A12930 | Technical Bid Evaluation For Transformer (Power And Distribution)_IFR | 10-May-25 A | 22-May-25 A | 2026-09-07 | 2026-09-07 | 10-May-25 A | 22-May-25 A
A12940 | Technical Bid Evaluation For Transformer (Power And Distribution)_RCC | 15-May-25 A | 03-Jun-25 A | 2026-09-07 | 2026-09-07 | 15-May-25 A | 03-Jun-25 A
A12950 | Technical Bid Evaluation For Transformer (Power And Distribution)_IFA | 01-Aug-25 A | 10-Sep-25 A | 2026-09-07 | 2026-09-07 | 01-Aug-25 A | 10-Sep-25 A
A12960 | Technical Bid Evaluation For Transformer (Power And Distribution)_RCA | 30-Aug-25 A | 17-Sep-25 A | 2026-09-07 | 2026-09-07 | 30-Aug-25 A | 17-Sep-25 A
A12970 | Technical Bid Evaluation For Transformer (Power And Distribution)_IFD/IFC | 25-May-25 A | 01-Jun-25 A | 2026-09-07 | 2026-09-07 | 25-May-25 A | 01-Jun-25 A
A16150 | Issue RFQ to Bidders | 15-May-25 A | 25-May-25 A | 2026-09-07 | 2026-09-07 | 15-May-25 A | 25-May-25 A
A20170 | Issue Purchase Order to Vendor for Power Transformers | 09-Jun-25 A | 29-Jul-25 A | 2026-09-07 | 2026-09-07 | 09-Jun-25 A | 29-Jul-25 A
A20190 | Commercial Bid Evaluation(Completion) | 02-Jun-25 A | 08-Jun-25 A | 2026-09-07 | 2026-09-07 | 02-Jun-25 A | 08-Jun-25 A
ElectricalHeatTracing |  | 23-Feb-26 A | 20-Mar-26 A | 2026-07-30 | 2026-07-30 | 2026-02-20 | 2026-05-13
ElectricalHeatTracing(53Meterforpiping+340Meterforinstrumentation) |  | 23-Feb-26 A | 20-Mar-26 A | 2026-07-30 | 2026-07-30 | 2026-02-20 | 2026-05-13
A16270 | Issue RFQ to Bidders | 23-Feb-26 A | 26-Feb-26 A | 2026-07-30 | 2026-07-30 | 2026-02-20 | 2026-03-12
A22210 | Bid Evaluation(Completion) | 11-Mar-26 A | 20-Mar-26 A | 2026-07-30 | 2026-07-30 | 2026-03-13 | 2026-04-02
A22220 | Commercial Bid Evaluation(Completion) | 11-Mar-26 A | 20-Mar-26 A | 2026-07-30 | 2026-07-30 | 2026-04-03 | 2026-04-23
A22230 | Issue Purchase Order to Vendor | 19-Mar-26 A | 20-Mar-26 A | 2026-07-30 | 2026-07-30 | 2026-04-24 | 2026-05-13
CP |  | 21-Nov-25 A | 20-Mar-26 A | 2026-08-14 | 2026-08-14 | 21-Nov-25 A | 2026-02-27
CathodicProtection(CP)TotalCSPipingLength-499Meters |  | 21-Nov-25 A | 20-Mar-26 A | 2026-08-14 | 2026-08-14 | 21-Nov-25 A | 2026-02-27
A16210 | Issue RFQ to Bidders | 21-Nov-25 A | 18-Dec-25 A | 2026-08-14 | 2026-08-14 | 21-Nov-25 A | 18-Dec-25 A
A22150 | Bid Evaluation(Completion) | 24-Jan-26 A | 31-Jan-26 A | 2026-08-14 | 2026-08-14 | 24-Jan-26 A | 31-Jan-26 A
A22160 | Commercial Bid Evaluation(Completion) | 01-Feb-26 A | 20-Feb-26 A | 2026-08-14 | 2026-08-14 | 01-Feb-26 A | 20-Feb-26 A
A22170 | Issue Purchase Order to Vendor | 20-Feb-26 A | 20-Mar-26 A | 2026-08-14 | 2026-08-14 | 20-Feb-26 A | 2026-02-27
LV&MVSwitchgears |  | 18-Mar-25 A | 01-Nov-25 A | 2026-07-28 | 2026-07-28 | 18-Mar-25 A | 01-Nov-25 A
Switchgear(LV,MV) |  | 18-Mar-25 A | 01-Nov-25 A | 2026-07-28 | 2026-07-28 | 18-Mar-25 A | 01-Nov-25 A
A13030 | Technical Bid Evaluation For LV Switchgear_IFR | 15-Apr-25 A | 20-Apr-25 A | 2026-07-28 | 2026-07-28 | 15-Apr-25 A | 20-Apr-25 A
A13040 | Technical Bid Evaluation For LV Switchgear_RCC | 21-Apr-25 A | 25-Apr-25 A | 2026-07-28 | 2026-07-28 | 21-Apr-25 A | 25-Apr-25 A
A13050 | Technical Bid Evaluation For LV Switchgear_IFA | 28-Apr-25 A | 01-May-25 A | 2026-07-28 | 2026-07-28 | 28-Apr-25 A | 01-May-25 A
A13060 | Technical Bid Evaluation For LV Switchgear_RCA | 02-May-25 A | 10-May-25 A | 2026-07-28 | 2026-07-28 | 02-May-25 A | 10-May-25 A
A13070 | Technical Bid Evaluation For LV Switchgear_IFD/IFC | 30-May-25 A | 18-Jul-25 A | 2026-07-28 | 2026-07-28 | 30-May-25 A | 18-Jul-25 A
A16330 | Issue RFQ to Bidders | 18-Mar-25 A | 14-Apr-25 A | 2026-07-28 | 2026-07-28 | 18-Mar-25 A | 14-Apr-25 A
A20230 | Issue Purchase Order to Vendor for switchgear (LV, MV) | 24-Sep-25 A | 01-Nov-25 A | 2026-07-28 | 2026-07-28 | 24-Sep-25 A | 01-Nov-25 A
A20250 | Commercial Bid Evaluation(Completion) | 19-Jul-25 A | 29-Jul-25 A | 2026-07-28 | 2026-07-28 | 19-Jul-25 A | 29-Jul-25 A
SwitchGearModification(Siemens) |  | 20-Feb-25 A | 18-Mar-25 A | 2026-06-16 | 2026-06-16 | 20-Feb-25 A | 18-Mar-25 A
TA_Switchgear(MVSwitchgearModifications)-Siemens |  | 20-Feb-25 A | 18-Mar-25 A | 2026-06-16 | 2026-06-16 | 20-Feb-25 A | 18-Mar-25 A
A22400 | Issue RFQ to Bidders | 20-Feb-25 A | 25-Feb-25 A | 2026-06-16 | 2026-06-16 | 20-Feb-25 A | 25-Feb-25 A
A22420 | Issue Purchase Order to Vendor | 10-Mar-25 A | 18-Mar-25 A | 2026-06-16 | 2026-06-16 | 10-Mar-25 A | 18-Mar-25 A
A56240 | TBE for Electrical System Modification_Free Issue Material | 26-Feb-25 A | 09-Mar-25 A | 2026-06-16 | 2026-06-16 | 26-Feb-25 A | 09-Mar-25 A
MV&LVVFD's |  | 18-Jul-25 A | 12-Aug-25 A | 2026-12-21 | 2026-12-21 | 18-Jul-25 A | 12-Aug-25 A
VariableFequencyDrives(VFDs)LVQty=03 |  | 18-Jul-25 A | 12-Aug-25 A | 2026-12-21 | 2026-12-21 | 18-Jul-25 A | 12-Aug-25 A
A13380 | Technical Bid Evaluation For LV Variable Frequency Drive_IFR | 21-Jul-25 A | 23-Jul-25 A | 2026-12-21 | 2026-12-21 | 21-Jul-25 A | 23-Jul-25 A
A13390 | Technical Bid Evaluation For LV Variable Frequency Drive_RCC | 24-Jul-25 A | 25-Jul-25 A | 2026-12-21 | 2026-12-21 | 24-Jul-25 A | 25-Jul-25 A
A13400 | Technical Bid Evaluation For LV Variable Frequency Drive_IFA | 28-Jul-25 A | 30-Jul-25 A | 2026-12-21 | 2026-12-21 | 28-Jul-25 A | 30-Jul-25 A
A13410 | Technical Bid Evaluation For LV Variable Frequency Drive_RCA | 31-Jul-25 A | 01-Aug-25 A | 2026-12-21 | 2026-12-21 | 31-Jul-25 A | 01-Aug-25 A
A13420 | Technical Bid Evaluation For LV Variable Frequency Drive_IFD/IFC | 04-Aug-25 A | 06-Aug-25 A | 2026-12-21 | 2026-12-21 | 04-Aug-25 A | 06-Aug-25 A
A20790 | Issue RFQ to Bidders | 18-Jul-25 A | 20-Jul-25 A | 2026-12-21 | 2026-12-21 | 18-Jul-25 A | 20-Jul-25 A
A20800 | Issue Purchase Order to Vendor for VFDs | 11-Aug-25 A | 12-Aug-25 A | 2026-12-21 | 2026-12-21 | 11-Aug-25 A | 12-Aug-25 A
A20820 | Commercial Bid Evaluation(Completion) | 07-Aug-25 A | 08-Aug-25 A | 2026-12-21 | 2026-12-21 | 07-Aug-25 A | 08-Aug-25 A
HVCapacitorBay |  | 15-Apr-25 A | 15-Oct-25 A | 2026-11-03 | 2026-11-03 | 15-Apr-25 A | 15-Oct-25 A
HVCapacitorBay |  | 15-Apr-25 A | 15-Oct-25 A | 2026-11-03 | 2026-11-03 | 15-Apr-25 A | 15-Oct-25 A
A13180 | Technical Bid Evaluation For Capacitor Bank_IFR | 01-Sep-25 A | 05-Sep-25 A | 2026-11-03 | 2026-11-03 | 01-Sep-25 A | 05-Sep-25 A
A13190 | Technical Bid Evaluation For Capacitor Bank_RCC | 06-Sep-25 A | 10-Sep-25 A | 2026-11-03 | 2026-11-03 | 06-Sep-25 A | 10-Sep-25 A
A13200 | Technical Bid Evaluation For Capacitor Bank_IFA | 11-Sep-25 A | 15-Sep-25 A | 2026-11-03 | 2026-11-03 | 11-Sep-25 A | 15-Sep-25 A
A13210 | Technical Bid Evaluation For Capacitor Bank_RCA | 16-Sep-25 A | 20-Sep-25 A | 2026-11-03 | 2026-11-03 | 16-Sep-25 A | 20-Sep-25 A
A13220 | Technical Bid Evaluation For Capacitor Bank_IFD/IFC | 22-Sep-25 A | 25-Sep-25 A | 2026-11-03 | 2026-11-03 | 22-Sep-25 A | 25-Sep-25 A
A16570 | Issue RFQ to Bidders | 15-Apr-25 A | 06-May-25 A | 2026-11-03 | 2026-11-03 | 15-Apr-25 A | 06-May-25 A
A19990 | Issue Purchase Order to Vendor for HV Capacitor Bay | 30-Sep-25 A | 15-Oct-25 A | 2026-11-03 | 2026-11-03 | 30-Sep-25 A | 15-Oct-25 A
A20010 | Commercial Bid Evaluation(Completion) | 01-Sep-25 A | 29-Sep-25 A | 2026-11-03 | 2026-11-03 | 01-Sep-25 A | 29-Sep-25 A
PowerDistributionPanelandLCS,Battery&SafetySwitch,ResisterBank |  | 10-Apr-25 A | 20-Jun-25 A | 2026-12-01 | 2026-12-01 | 10-Apr-25 A | 20-Jun-25 A
NGRPanelQty02 |  | 10-Apr-25 A | 20-Jun-25 A | 2026-12-01 | 2026-12-01 | 10-Apr-25 A | 20-Jun-25 A
A13280 | Technical Bid Evaluation For Neutral Grounding Resistor_IFR | 02-May-25 A | 13-May-25 A | 2026-12-01 | 2026-12-01 | 02-May-25 A | 13-May-25 A
A13290 | Technical Bid Evaluation For Neutral Grounding Resistor_RCC | 14-May-25 A | 15-May-25 A | 2026-12-01 | 2026-12-01 | 14-May-25 A | 15-May-25 A
A13300 | Technical Bid Evaluation For Neutral Grounding Resistor_IFA | 14-May-25 A | 15-May-25 A | 2026-12-01 | 2026-12-01 | 14-May-25 A | 15-May-25 A
A13310 | Technical Bid Evaluation For Neutral Grounding Resistor_RCA | 14-May-25 A | 15-May-25 A | 2026-12-01 | 2026-12-01 | 14-May-25 A | 15-May-25 A
A13320 | Technical Bid Evaluation For Neutral Grounding Resistor_IFD/IFC | 15-May-25 A | 20-May-25 A | 2026-12-01 | 2026-12-01 | 15-May-25 A | 20-May-25 A
A16630 | Issue RFQ to Bidders | 10-Apr-25 A | 01-May-25 A | 2026-12-01 | 2026-12-01 | 10-Apr-25 A | 01-May-25 A
A20290 | Issue Purchase Order to Vendor for NGR Panel | 14-Jun-25 A | 20-Jun-25 A | 2026-12-01 | 2026-12-01 | 14-Jun-25 A | 20-Jun-25 A
A20310 | Commercial Bid Evaluation(Completion) | 21-May-25 A | 13-Jun-25 A | 2026-12-01 | 2026-12-01 | 21-May-25 A | 13-Jun-25 A
LightFitting,Switchesandsmallpowersockets |  | 03-Feb-26 A | 2026-05-18 | 2026-07-16 | 2026-08-14
LightFitting,Switchesandsmallpowersockets |  | 03-Feb-26 A | 2026-05-18 | 2026-07-16 | 2026-08-14
A63720 | Issue RFQ to Bidders | 03-Feb-26 A | 09-Feb-26 A | 2026-07-16 | 2026-07-16
A63730 | Issue Purchase Order to Vendor | 2026-04-29 | 2026-05-18 | 2026-07-28 | 2026-08-14
A63740 | Bid Evaluation(Completion) | 09-Mar-26 A | 16-Mar-26 A | 2026-07-16 | 2026-07-16
A63750 | Commercial Bid Evaluation(Completion) | 2026-04-17 | 2026-04-28 | 2026-07-16 | 2026-07-27
InterposingRelayPanel(IRP) |  | 20-Mar-26 A | 2026-05-08 | 2026-07-20 | 2026-10-05 | 2026-02-20 | 2026-03-18
InterposingRelayPanel |  | 20-Mar-26 A | 2026-05-08 | 2026-07-20 | 2026-10-05 | 2026-02-20 | 2026-03-18
A16690 | Issue RFQ to Bidders | 20-Mar-26 A | 24-Mar-26 A | 2026-07-20 | 2026-07-20 | 2026-02-20 | 2026-02-24
A20350 | Issue Purchase Order to Vendor for Interposing Relay Panel | 2026-05-05 | 2026-05-08 | 2026-08-05 | 2026-08-10 | 2026-03-13 | 2026-03-18
A20370 | Commercial Bid Evaluation(Completion) | 2026-04-30 | 2026-05-04 | 2026-07-31 | 2026-08-04 | 2026-03-10 | 2026-03-12
A58640 | Technical Bid Evaluation for Interposting Relay Panel_IFR | 2026-04-17 | 2026-04-21 | 2026-07-20 | 2026-07-22 | 2026-02-25 | 2026-02-27
A58650 | Technical Bid Evaluation for Interposting Relay Panel_RCC | 2026-04-22 | 2026-04-24 | 2026-07-23 | 2026-07-27 | 2026-03-02 | 2026-03-04
A58660 | Technical Bid Evaluation for Interposting Relay Panel_IFA | 2026-04-27 | 2026-04-29 | 2026-07-28 | 2026-07-30 | 2026-03-05 | 2026-03-09
A58670 | Technical Bid Evaluation for Interposting Relay Panel_RCA | 2026-04-30 | 2026-05-04 | 2026-09-28 | 2026-09-30 | 2026-03-10 | 2026-03-12
A58680 | Technical Bid Evaluation for Interposting Relay Panel_IFD/IFC | 2026-05-05 | 2026-05-07 | 2026-10-01 | 2026-10-05 | 2026-03-13 | 2026-03-17
SubcontractServices |  | 14-Nov-24 A | 11-Jun-25 A | 2026-06-09 | 2026-06-16 | 14-Nov-24 A | 11-Jun-25 A
DetailEngineeringSubcontract |  | 14-Nov-24 A | 06-Dec-24 A | 2026-06-09 | 2026-06-09 | 14-Nov-24 A | 06-Dec-24 A
A61090 | Issue RFQ to CONTRACTORs | 14-Nov-24 A | 15-Nov-24 A | 2026-06-09 | 2026-06-09 | 14-Nov-24 A | 15-Nov-24 A
A61100 | Technical Bid analysis and clarifications | 19-Nov-24 A | 22-Nov-24 A | 2026-06-09 | 2026-06-09 | 19-Nov-24 A | 22-Nov-24 A
A61110 | Bid analysis and clarifications | 23-Nov-24 A | 29-Nov-24 A | 2026-06-09 | 2026-06-09 | 23-Nov-24 A | 29-Nov-24 A
A61120 | Subcontract Awarded/Signed | 29-Nov-24 A | 06-Dec-24 A | 2026-06-09 | 2026-06-09 | 29-Nov-24 A | 06-Dec-24 A
TAConstruction |  | 09-Dec-24 A | 07-Mar-25 A | 2026-06-16 | 2026-06-16 | 09-Dec-24 A | 07-Mar-25 A
A61130 | Issue RFQ to CONTRACTORs | 09-Dec-24 A | 09-Dec-24 A | 2026-06-16 | 2026-06-16 | 09-Dec-24 A | 09-Dec-24 A
A61140 | Technical Bid analysis and clarifications | 08-Jan-25 A | 08-Jan-25 A | 2026-06-16 | 2026-06-16 | 08-Jan-25 A | 08-Jan-25 A
A61150 | Bid analysis and clarifications | 06-Feb-25 A | 06-Feb-25 A | 2026-06-16 | 2026-06-16 | 06-Feb-25 A | 06-Feb-25 A
A61160 | Subcontract Awarded/Signed | 07-Mar-25 A | 07-Mar-25 A | 2026-06-16 | 2026-06-16 | 07-Mar-25 A | 07-Mar-25 A
MainConstruction |  | 09-Dec-24 A | 10-Mar-25 A | 2026-06-15 | 2026-06-15 | 09-Dec-24 A | 10-Mar-25 A
A61170 | Issue RFQ to CONTRACTORs | 09-Dec-24 A | 01-Feb-25 A | 2026-06-15 | 2026-06-15 | 09-Dec-24 A | 01-Feb-25 A
A61180 | Technical Bid analysis and clarifications | 02-Feb-25 A | 15-Feb-25 A | 2026-06-15 | 2026-06-15 | 02-Feb-25 A | 15-Feb-25 A
A61190 | Bid analysis and clarifications | 16-Feb-25 A | 25-Feb-25 A | 2026-06-15 | 2026-06-15 | 16-Feb-25 A | 25-Feb-25 A
A61200 | Subcontract Awarded/Signed | 07-Mar-25 A | 10-Mar-25 A | 2026-06-15 | 2026-06-15 | 07-Mar-25 A | 10-Mar-25 A
Topgraphic |  | 01-Jan-25 A | 20-Mar-25 A | 2026-06-15 | 2026-06-15 | 01-Jan-25 A | 20-Mar-25 A
A61210 | Issue RFQ to CONTRACTORs | 01-Jan-25 A | 03-Jan-25 A | 2026-06-15 | 2026-06-15 | 01-Jan-25 A | 03-Jan-25 A
A61220 | Technical Bid analysis and clarifications | 04-Jan-25 A | 03-Feb-25 A | 2026-06-15 | 2026-06-15 | 04-Jan-25 A | 03-Feb-25 A
A61230 | Bid analysis and clarifications | 04-Feb-25 A | 01-Mar-25 A | 2026-06-15 | 2026-06-15 | 04-Feb-25 A | 01-Mar-25 A
A61240 | Subcontract Awarded/Signed | 02-Mar-25 A | 20-Mar-25 A | 2026-06-15 | 2026-06-15 | 02-Mar-25 A | 20-Mar-25 A
Piling |  | 01-Apr-25 A | 11-May-25 A | 2026-06-15 | 2026-06-15 | 01-Apr-25 A | 11-May-25 A
A61250 | Issue RFQ to CONTRACTORs | 01-Apr-25 A | 20-Apr-25 A | 2026-06-15 | 2026-06-15 | 01-Apr-25 A | 20-Apr-25 A
A61260 | Technical Bid analysis and clarifications | 21-Apr-25 A | 27-Apr-25 A | 2026-06-15 | 2026-06-15 | 21-Apr-25 A | 27-Apr-25 A
A61270 | Bid analysis and clarifications | 28-Apr-25 A | 04-May-25 A | 2026-06-15 | 2026-06-15 | 28-Apr-25 A | 04-May-25 A
A61280 | Subcontract Awarded/Signed | 05-May-25 A | 11-May-25 A | 2026-06-15 | 2026-06-15 | 05-May-25 A | 11-May-25 A
HSEStudies |  | 10-Feb-25 A | 11-Jun-25 A | 2026-06-11 | 2026-06-11 | 01-May-25 A | 2026-09-25
A61290 | Issue RFQ to CONTRACTORs | 10-Feb-25 A | 01-Mar-25 A | 2026-06-11 | 2026-06-11 | 10-Feb-25 A | 01-Mar-25 A
A61300 | Technical Bid analysis and clarifications | 02-Mar-25 A | 15-Mar-25 A | 2026-06-11 | 2026-06-11 | 02-Mar-25 A | 15-Mar-25 A
A61310 | Bid analysis and clarifications | 16-Mar-25 A | 18-Apr-25 A | 2026-06-11 | 2026-06-11 | 16-Mar-25 A | 18-Apr-25 A
A61320 | Subcontract Awarded/Signed | 19-Apr-25 A | 11-Jun-25 A | 2026-06-11 | 2026-06-11 | 19-Apr-25 A | 11-Jun-25 A
VSMServicesAgreements |  | 01-Feb-25 A | 08-Mar-25 A | 2026-06-16 | 2026-06-16 | 01-Feb-25 A | 08-Mar-25 A
A61330 | Issue RFQ to CONTRACTORs | 01-Feb-25 A | 15-Feb-25 A | 2026-06-16 | 2026-06-16 | 01-Feb-25 A | 15-Feb-25 A
A61340 | Technical Bid analysis and clarifications | 16-Feb-25 A | 22-Feb-25 A | 2026-06-16 | 2026-06-16 | 16-Feb-25 A | 22-Feb-25 A
A61350 | Bid analysis and clarifications | 23-Feb-25 A | 01-Mar-25 A | 2026-06-16 | 2026-06-16 | 23-Feb-25 A | 01-Mar-25 A
A61360 | Subcontract Awarded/Signed | 02-Mar-25 A | 08-Mar-25 A | 2026-06-16 | 2026-06-16 | 02-Mar-25 A | 08-Mar-25 A
As-Built&Packagehandover |  | 01-Jun-25 A | 2027-09-14 | 2026-06-16 | 2027-09-20 | 01-Jun-25 A | 2027-07-14
TA |  | 01-Jun-25 A | 15-Jul-25 A | 2026-06-16 | 2026-06-16 | 01-Jun-25 A | 15-Jul-25 A
A61430 | TA As-Built | 01-Jun-25 A | 15-Jul-25 A | 2026-06-16 | 2026-06-16 | 01-Jun-25 A | 15-Jul-25 A
MainScope |  | 2027-06-23 | 2027-09-14 | 2027-06-29 | 2027-09-20 | 2027-04-22 | 2027-07-14
A61440 | Main Scope As-Built | 2027-06-23 | 2027-09-14 | 2027-06-29 | 2027-09-20 | 2027-04-22 | 2027-07-14 |  |  | CP | CP
ManufacturingandDelivery |  | 25-Feb-25 A | 2026-11-09 | 2026-06-09 | 2027-09-20 | 25-Feb-25 A | 2026-09-29
51.C | Issue purchase orders for all remaining Mechanical / Rotating EQT/EQTPkgs |  | 31-Dec-25 A |  | 2026-09-26 |  | 31-Dec-25 A
52.C | Issue purchase orders for all major Electrical Equipments |  | 14-Jan-26 A |  | 2027-03-06 |  | 14-Jan-26 A
54.C | Issue purchase order for all major Instruments Control System |  | 07-Jan-26 A |  | 2027-03-06 |  | 07-Jan-26 A
79.D | All major electrical Equipment delivered to Site |  | 2026-09-09 |  | 2027-03-06 |  | 2026-08-20
EquipmentPackages |  | 20-Jun-25 A | 2026-09-30 | 2026-08-05 | 2027-09-20 | 01-Jan-25 A | 15-Oct-25 A
Vessels |  | 20-Jun-25 A | 2026-09-30 | 2026-08-28 | 2027-09-20 | 01-Jan-25 A | 20-Jun-25 A
Vessels/Drums |  | 20-Jun-25 A | 2026-05-31 | 2026-08-28 | 2026-12-11
FGComp.2ndStageDis.Drum(13-VV-707) |  | 20-Jun-25 A | 2026-05-21 | 2026-08-28 | 2026-10-01 | 01-Jan-25 A | 12-Apr-25 A
A35200 | Start Production (13-VV-707) | 19-Sep-25 A |  | 2026-08-28 |  | 19-Sep-25 A
A35210 | Key Vendor Drawings / Data Approved | 20-Jun-25 A | 23-Aug-25 A | 2026-08-28 | 2026-08-28 | 20-Jun-25 A | 23-Aug-25 A
A35220 | Purchase Order for Major Sub-ordered Materials | 25-Aug-25 A | 02-Sep-25 A | 2026-08-28 | 2026-08-28 | 25-Aug-25 A | 02-Sep-25 A
A35230 | Major Sub-ordered Materials Received by Vendor and Verified | 11-Aug-25 A | 12-Sep-25 A | 2026-08-28 | 2026-08-28 | 11-Aug-25 A | 12-Sep-25 A
A35240 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 15-Sep-25 A | 26-Sep-25 A | 2026-08-28 | 2026-08-28 | 15-Sep-25 A | 26-Sep-25 A
A35250 | Manufacturing / Ex Works (India/UAE) | 02-Dec-25 A | 20-Mar-26 A | 2026-08-28 | 2026-08-28 | 02-Dec-25 A | 2026-04-10
A35260 | Complete Manufacturing & ready for Final Inspection | 01-Mar-26 A | 20-Mar-26 A | 2026-08-28 | 2026-08-28 | 2026-04-13 | 2026-04-22
A35270 | Materials Successfully Inspected, Tested / Ex Work | 10-Mar-26 A | 20-Mar-26 A | 2026-08-28 | 2026-08-28 | 2026-04-22 | 2026-05-01
A35320 | Delivery of FG Comp. 2nd Stage Dis. Drum Tag# 13-VV-707 | 2026-04-17 | 2026-05-21 | 2026-08-28 | 2026-10-01 | 2026-05-11 | 2026-06-08
OGComp.2ndStageSuc.Drum(13-VV-713) |  | 20-Jun-25 A | 2026-05-08 | 2026-09-15 | 2026-10-07 | 01-Jan-25 A | 12-Apr-25 A
A35060 | Start Production (13-VV-713) | 20-Jun-25 A |  | 2026-09-15 |  | 20-Jun-25 A
A35070 | Key Vendor Drawings / Data Approved | 20-Jun-25 A | 23-Aug-25 A | 2026-09-15 | 2026-09-15 | 20-Jun-25 A | 23-Aug-25 A
A35080 | Purchase Order for Major Sub-ordered Materials | 25-Aug-25 A | 02-Sep-25 A | 2026-09-15 | 2026-09-15 | 25-Aug-25 A | 02-Sep-25 A
A35090 | Major Sub-ordered Materials Received by Vendor and Verified | 11-Aug-25 A | 12-Sep-25 A | 2026-09-15 | 2026-09-15 | 11-Aug-25 A | 12-Sep-25 A
A35100 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 15-Sep-25 A | 26-Oct-25 A | 2026-09-15 | 2026-09-15 | 15-Sep-25 A | 26-Oct-25 A
A35110 | Manufacturing / Ex Works (India/UAE) | 21-Nov-25 A | 20-Mar-26 A | 2026-09-15 | 2026-09-15 | 21-Nov-25 A | 2026-04-15
A35120 | Complete Manufacturing & ready for Final Inspection | 01-Mar-26 A | 20-Mar-26 A | 2026-09-15 | 2026-09-15 | 2026-04-16 | 2026-04-22
A35130 | Materials Successfully Inspected, Tested / Ex Work | 15-Mar-26 A | 17-Apr-26 A | 2026-09-15 | 2026-09-15 | 2026-04-23 | 2026-05-01
A35170 | Delivery of OG Comp. 2nd Stage Suc. Drum Tag# 13-VV-713 | 17-Apr-26 A | 2026-05-08 | 2026-09-22 | 2026-10-07 | 2026-05-09 | 2026-06-05
OGBufferDrum(13-VV-712) |  | 20-Jun-25 A | 2026-05-31 | 2026-10-12 | 2026-11-23 | 01-Jan-25 A | 12-Apr-25 A
A35340 | Start Production (13-VV-712) | 20-Jun-25 A |  | 2026-10-12 |  | 20-Jun-25 A
A35350 | Key Vendor Drawings / Data Approved | 20-Jun-25 A | 23-Aug-25 A | 2026-10-12 | 2026-10-12 | 20-Jun-25 A | 23-Aug-25 A
A35360 | Purchase Order for Major Sub-ordered Materials | 25-Aug-25 A | 02-Sep-25 A | 2026-10-12 | 2026-10-12 | 25-Aug-25 A | 02-Sep-25 A
A35370 | Major Sub-ordered Materials Received by Vendor and Verified | 11-Aug-25 A | 12-Sep-25 A | 2026-10-12 | 2026-10-12 | 11-Aug-25 A | 12-Sep-25 A
A35380 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 15-Sep-25 A | 26-Oct-25 A | 2026-10-12 | 2026-10-12 | 15-Sep-25 A | 26-Oct-25 A
A35390 | Manufacturing / Ex Works (India/UAE) | 21-Nov-25 A | 20-Mar-26 A | 2026-10-12 | 2026-10-12 | 21-Nov-25 A | 2026-04-15
A35400 | Complete Manufacturing & ready for Final Inspection | 01-Mar-26 A | 20-Mar-26 A | 2026-10-12 | 2026-10-12 | 2026-04-16 | 2026-04-22
A35410 | Materials Successfully Inspected, Tested / Ex Work | 18-Mar-26 A | 2026-05-04 | 2026-10-12 | 2026-10-27 | 2026-04-23 | 2026-05-01
A35470 | Delivery of OG Buffer Drum - Tag# 13-VV-712 | 2026-05-19 | 2026-05-31 | 2026-11-11 | 2026-11-23 | 2026-05-16 | 2026-06-12
PSA2SlopDrum(70-VV-1415) |  | 20-Jun-25 A | 2026-05-07 | 2026-11-21 | 2026-12-11 | 01-Jan-25 A | 12-Apr-25 A
A35480 | Start Production (70-VV-1415) | 20-Jun-25 A |  | 2026-11-21 |  | 20-Jun-25 A
A35490 | Key Vendor Drawings / Data Approved | 20-Jun-25 A | 23-Aug-25 A | 2026-11-21 | 2026-11-21 | 20-Jun-25 A | 23-Aug-25 A
A35500 | Purchase Order for Major Sub-ordered Materials | 25-Aug-25 A | 02-Sep-25 A | 2026-11-21 | 2026-11-21 | 25-Aug-25 A | 02-Sep-25 A
A35510 | Major Sub-ordered Materials Received by Vendor and Verified | 11-Aug-25 A | 12-Sep-25 A | 2026-11-21 | 2026-11-21 | 11-Aug-25 A | 12-Sep-25 A
A35520 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 15-Sep-25 A | 26-Oct-25 A | 2026-11-21 | 2026-11-21 | 15-Sep-25 A | 26-Oct-25 A
A35530 | Manufacturing / Ex Works (India/UAE) | 21-Nov-25 A | 20-Mar-26 A | 2026-11-21 | 2026-11-21 | 21-Nov-25 A | 2026-04-15
A35540 | Complete Manufacturing & ready for Final Inspection | 01-Mar-26 A | 20-Mar-26 A | 2026-11-21 | 2026-11-21 | 2026-04-16 | 2026-04-22
A35550 | Materials Successfully Inspected, Tested / Ex Work | 12-Mar-26 A | 20-Mar-26 A | 2026-11-21 | 2026-11-21 | 2026-04-23 | 2026-05-01
A35580 | Delivery of PSA2 Slop Drum Tag# 70-VV-1415 | 2026-04-17 | 2026-05-07 | 2026-11-21 | 2026-12-11 | 2026-05-08 | 2026-06-04
FGComp.2ndStageSuc.Drum(13-VV-706) |  | 20-Jun-25 A | 2026-05-07 | 2026-09-08 | 2026-09-28 | 01-Jan-25 A | 20-Jun-25 A
A35620 | Start Production (13-VV-706) | 20-Jun-25 A |  | 2026-09-08 |  | 20-Jun-25 A
A35630 | Key Vendor Drawings / Data Approved | 20-Jun-25 A | 23-Aug-25 A | 2026-09-08 | 2026-09-08 | 20-Jun-25 A | 23-Aug-25 A
A35640 | Purchase Order for Major Sub-ordered Materials | 25-Aug-25 A | 02-Sep-25 A | 2026-09-08 | 2026-09-08 | 25-Aug-25 A | 02-Sep-25 A
A35650 | Major Sub-ordered Materials Received by Vendor and Verified | 11-Aug-25 A | 12-Sep-25 A | 2026-09-08 | 2026-09-08 | 11-Aug-25 A | 12-Sep-25 A
A35660 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 15-Sep-25 A | 26-Oct-25 A | 2026-09-08 | 2026-09-08 | 15-Sep-25 A | 26-Oct-25 A
A35670 | Manufacturing / Ex Works (India/UAE) | 21-Nov-25 A | 20-Mar-26 A | 2026-09-08 | 2026-09-08 | 21-Nov-25 A | 2026-04-15
A35680 | Complete Manufacturing & ready for Final Inspection | 01-Mar-26 A | 20-Mar-26 A | 2026-09-08 | 2026-09-08 | 2026-04-16 | 2026-04-24
A35690 | Materials Successfully Inspected, Tested / Ex Work | 05-Mar-26 A | 20-Mar-26 A | 2026-09-08 | 2026-09-08 | 2026-04-27 | 2026-05-05
A35710 | Delivery of FG Comp. 2nd Stage Suc. Drum Tag# 13-VV-706 | 2026-04-17 | 2026-05-07 | 2026-09-08 | 2026-09-28 | 2026-05-06 | 2026-06-02
FGComp.1stStageSuc.Drum(13-VV-705) |  | 20-Jun-25 A | 2026-05-07 | 2026-09-26 | 2026-10-16 | 01-Jan-25 A | 07-Apr-25 A
A35760 | Start Production (13-VV-705) | 20-Jun-25 A |  | 2026-09-26 |  | 20-Jun-25 A
A35770 | Key Vendor Drawings / Data Approved | 20-Jun-25 A | 23-Aug-25 A | 2026-09-26 | 2026-09-26 | 20-Jun-25 A | 23-Aug-25 A
A35780 | Purchase Order for Major Sub-ordered Materials | 25-Aug-25 A | 02-Sep-25 A | 2026-09-26 | 2026-09-26 | 25-Aug-25 A | 02-Sep-25 A
A35790 | Major Sub-ordered Materials Received by Vendor and Verified | 11-Aug-25 A | 12-Sep-25 A | 2026-09-26 | 2026-09-26 | 11-Aug-25 A | 12-Sep-25 A
A35800 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 15-Sep-25 A | 26-Oct-25 A | 2026-09-26 | 2026-09-26 | 15-Sep-25 A | 26-Oct-25 A
A35810 | Manufacturing / Ex Works (India/UAE) | 21-Nov-25 A | 20-Mar-26 A | 2026-09-26 | 2026-09-26 | 21-Nov-25 A | 2026-04-15
A35820 | Complete Manufacturing & ready for Final Inspection | 03-Mar-26 A | 20-Mar-26 A | 2026-09-26 | 2026-09-26 | 2026-04-16 | 2026-04-23
A35830 | Materials Successfully Inspected, Tested / Ex Work | 12-Mar-26 A | 20-Mar-26 A | 2026-09-26 | 2026-09-26 | 2026-04-24 | 2026-05-04
A35840 | Delivery of FG Comp.1st Stage Suc. Drum (13-VV-705) | 2026-04-17 | 2026-05-07 | 2026-09-26 | 2026-10-16 | 2026-05-05 | 2026-06-01
Vessel'sInternals(05Dimisterpads) |  | 20-Jun-25 A | 2026-05-31 | 2026-09-16 | 2026-10-25 | 01-Jan-25 A | 20-Jun-25 A
A29960 | Key Vendor Drawings / Data Approved | 20-Jun-25 A | 23-Aug-25 A | 2026-09-16 | 2026-09-16 | 20-Jun-25 A | 23-Aug-25 A
A29970 | Purchase Order for Major Sub-ordered Materials | 25-Aug-25 A | 02-Sep-25 A | 2026-09-16 | 2026-09-16 | 25-Aug-25 A | 02-Sep-25 A
A29980 | Major Sub-ordered Materials Received by Vendor and Verified | 11-Aug-25 A | 12-Sep-25 A | 2026-09-16 | 2026-09-16 | 11-Aug-25 A | 12-Sep-25 A
A29990 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 15-Sep-25 A | 26-Oct-25 A | 2026-09-16 | 2026-09-16 | 15-Sep-25 A | 26-Oct-25 A
A30000 | Manufacturing / Ex Works (India/UAE) | 21-Nov-25 A | 20-Mar-26 A | 2026-09-16 | 2026-09-16 | 21-Nov-25 A | 2026-04-15
A30010 | Complete Manufacturing & ready for Final Inspection | 01-Mar-26 A | 20-Mar-26 A | 2026-09-16 | 2026-09-16 | 2026-04-16 | 2026-04-24
A30020 | Materials Successfully Inspected, Tested / Ex Work | 11-Mar-26 A | 20-Mar-26 A | 2026-09-16 | 2026-09-16 | 2026-04-27 | 2026-05-05
A33660 | Start Production | 20-Jun-25 A |  | 2026-09-16 |  | 20-Jun-25 A
A33670 | Delivery of Vessel's Internals (05 Dimister Pads) in Warehouse | 2026-04-21 | 2026-05-31 | 2026-09-16 | 2026-10-25 | 2026-05-06 | 2026-06-02
C4GuardAdsorberCoolerDripleg-(BF) |  | 20-Jun-25 A | 2026-05-31 | 2026-11-12 | 2026-12-26 | 20-Jun-25 A | 2026-06-02
A28160 | Key Vendor Drawings / Data Approved | 20-Jun-25 A | 23-Aug-25 A | 2026-11-12 | 2026-11-12 | 20-Jun-25 A | 23-Aug-25 A
A28170 | Purchase Order for Major Sub-ordered Materials | 25-Aug-25 A | 02-Sep-25 A | 2026-11-12 | 2026-11-12 | 25-Aug-25 A | 02-Sep-25 A
A28180 | Major Sub-ordered Materials Received by Vendor and Verified | 11-Aug-25 A | 12-Sep-25 A | 2026-11-12 | 2026-11-12 | 11-Aug-25 A | 12-Sep-25 A
A28190 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 15-Sep-25 A | 26-Oct-25 A | 2026-11-12 | 2026-11-12 | 15-Sep-25 A | 26-Oct-25 A
A28200 | Manufacturing / Ex Works (India/UAE) | 21-Nov-25 A | 20-Mar-26 A | 2026-11-12 | 2026-11-12 | 21-Nov-25 A | 2026-04-15
A28210 | Complete Manufacturing & ready for Final Inspection | 02-Mar-26 A | 20-Mar-26 A | 2026-11-12 | 2026-11-12 | 2026-04-16 | 2026-04-24
A28220 | Materials Successfully Inspected, Tested / Ex Work | 12-Mar-26 A | 20-Mar-26 A | 2026-11-12 | 2026-11-12 | 2026-04-27 | 2026-05-05
A34660 | Start Production | 20-Jun-25 A |  | 2026-11-12 |  | 20-Jun-25 A
A34670 | Delivery of C4 Guard Absorber Cooler Dripleg (Post - TA) | 2026-04-17 | 2026-05-31 | 2026-11-12 | 2026-12-26 | 2026-05-06 | 2026-06-02
HydrogenProductFilter |  | 17-Apr-26 A | 2026-09-30 | 2027-04-07 | 2027-09-20
A62960 | Key Vendor Drawings / Data Approved | 2026-04-17 | 2026-04-30 | 2027-04-07 | 2027-04-20
A62970 | Manufacturing / Ex Works (India/UAE) | 2026-05-29 | 2026-09-03 | 2027-05-20 | 2027-08-25
A62980 | Purchase Order for Major Sub-ordered Materials | 2026-04-30 | 2026-05-14 | 2027-04-21 | 2027-05-04
A62990 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-05-14 | 2026-05-28 | 2027-05-05 | 2027-05-18
A63000 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-05-28 | 2026-05-29 | 2027-05-19 | 2027-05-20
A63010 | Complete Manufacturing & ready for Final Inspection | 2026-09-03 | 2026-09-14 | 2027-08-25 | 2027-09-02
A63020 | Materials Successfully Inspected, Tested / Ex Work | 2026-09-14 | 2026-09-23 | 2027-09-03 | 2027-09-13
A63030 | Start Production | 17-Apr-26 A |  | 2027-04-07
A63040 | Delivery of Hydrogen Product Filter | 2026-09-23 | 2026-09-30 | 2027-09-14 | 2027-09-20
ActiveCarbonFilter |  | 17-Apr-26 A | 2026-09-30 | 2027-04-07 | 2027-09-20
A63050 | Key Vendor Drawings / Data Approved | 2026-04-17 | 2026-04-30 | 2027-04-07 | 2027-04-20
A63060 | Manufacturing / Ex Works (India/UAE) | 2026-05-29 | 2026-09-03 | 2027-05-20 | 2027-08-25
A63070 | Purchase Order for Major Sub-ordered Materials | 2026-04-30 | 2026-05-14 | 2027-04-21 | 2027-05-04
A63080 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-05-14 | 2026-05-28 | 2027-05-05 | 2027-05-18
A63090 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-05-28 | 2026-05-29 | 2027-05-19 | 2027-05-20
A63100 | Complete Manufacturing & ready for Final Inspection | 2026-09-03 | 2026-09-14 | 2027-08-25 | 2027-09-02
A63110 | Materials Successfully Inspected, Tested / Ex Work | 2026-09-14 | 2026-09-23 | 2027-09-03 | 2027-09-13
A63120 | Start Production | 17-Apr-26 A |  | 2027-04-07
A63130 | Delivery of Active Carbon Filter | 2026-09-23 | 2026-09-30 | 2027-09-14 | 2027-09-20
InstrumentAirVessel |  | 2026-05-18 | 2026-09-30 | 2027-05-10 | 2027-09-20
A63140 | Key Vendor Drawings / Data Approved | 2026-05-19 | 2026-06-01 | 2027-05-10 | 2027-05-21
A63150 | Manufacturing / Ex Works (India/UAE) | 2026-06-30 | 2026-09-18 | 2027-06-22 | 2027-09-10
A63160 | Purchase Order for Major Sub-ordered Materials | 2026-06-01 | 2026-06-15 | 2027-05-24 | 2027-06-04
A63170 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-06-15 | 2026-06-29 | 2027-06-07 | 2027-06-18
A63180 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-06-29 | 2026-06-30 | 2027-06-21 | 2027-06-22
A63190 | Complete Manufacturing & ready for Final Inspection | 2026-09-18 | 2026-09-23 | 2027-09-10 | 2027-09-14
A63200 | Materials Successfully Inspected, Tested / Ex Work | 2026-09-23 | 2026-09-28 | 2027-09-15 | 2027-09-17
A63210 | Start Production | 2026-05-18 |  | 2027-05-10
A63220 | Delivery of Instrument Air Vessel | 2026-09-28 | 2026-09-30 | 2027-09-19 | 2027-09-20
WaterCollection&SanitaryWasteWaterPumps |  | 10-Sep-25 A | 2026-06-25 | 2026-10-03 | 2026-12-11 | 10-Sep-25 A | 2026-06-05
SanitaryWasteWaterSumpPump |  | 10-Sep-25 A | 2026-06-25 | 2026-10-03 | 2026-12-07 | 01-Apr-25 A | 15-Oct-25 A
A30680 | Key Vendor Drawings / Data Approved | 21-Nov-25 A | 04-Dec-25 A | 2026-10-03 | 2026-10-03 | 21-Nov-25 A | 04-Dec-25 A
A30690 | Purchase Order for Major Sub-ordered Materials | 08-Dec-25 A | 19-Dec-25 A | 2026-10-03 | 2026-10-03 | 08-Dec-25 A | 19-Dec-25 A
A30700 | Major Sub-ordered Materials Received by Vendor and Verified | 19-Dec-25 A | 02-Jan-26 A | 2026-10-03 | 2026-10-03 | 19-Dec-25 A | 02-Jan-26 A
A30710 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 01-Jan-26 A | 15-Jan-26 A | 2026-10-03 | 2026-10-03 | 01-Jan-26 A | 15-Jan-26 A
A30720 | Manufacturing / Ex Works (India/UAE) | 01-Jan-26 A | 20-Mar-26 A | 2026-10-03 | 2026-10-03 | 01-Jan-26 A | 2026-04-20
A30730 | Complete Manufacturing & ready for Final Inspection | 01-Mar-26 A | 20-Mar-26 A | 2026-10-03 | 2026-10-03 | 2026-04-21 | 2026-04-29
A30740 | Materials Successfully Inspected, Tested / Ex Work | 10-Mar-26 A | 20-Mar-26 A | 2026-10-03 | 2026-10-03 | 2026-04-30 | 2026-05-08
A33850 | Start Production | 10-Sep-25 A |  | 2026-10-03 |  | 10-Sep-25 A
A33860 | Delivery of Sanitary Waste Water Sump Pump (01) | 2026-04-21 | 2026-06-25 | 2026-10-03 | 2026-12-07 | 2026-05-09 | 2026-06-05
WaterCollectionSumpPumpll |  | 10-Sep-25 A | 2026-06-25 | 2026-10-05 | 2026-12-11 | 01-Apr-25 A | 05-Aug-25 A
A30770 | Key Vendor Drawings / Data Approved | 21-Nov-25 A | 10-Dec-25 A | 2026-10-05 | 2026-10-05 | 21-Nov-25 A | 10-Dec-25 A
A30780 | Purchase Order for Major Sub-ordered Materials | 11-Dec-25 A | 19-Dec-25 A | 2026-10-05 | 2026-10-05 | 11-Dec-25 A | 19-Dec-25 A
A30790 | Major Sub-ordered Materials Received by Vendor and Verified | 19-Dec-25 A | 02-Jan-26 A | 2026-10-05 | 2026-10-05 | 19-Dec-25 A | 02-Jan-26 A
A30800 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 01-Jan-26 A | 15-Jan-26 A | 2026-10-05 | 2026-10-05 | 01-Jan-26 A | 15-Jan-26 A
A30810 | Manufacturing / Ex Works (India/UAE) | 26-Feb-26 A | 20-Mar-26 A | 2026-10-05 | 2026-10-05 | 01-Jan-26 A | 2026-04-20
A30820 | Complete Manufacturing & ready for Final Inspection | 03-Mar-26 A | 18-Mar-26 A | 2026-10-05 | 2026-10-05 | 2026-04-21 | 2026-04-29
A30830 | Materials Successfully Inspected, Tested / Ex Work | 20-Mar-26 A | 2026-05-28 | 2026-10-05 | 2026-11-13 | 2026-04-30 | 2026-05-08
A33870 | Start Production | 10-Sep-25 A |  | 2026-10-05 |  | 10-Sep-25 A
A33880 | Delivery of Water Sump Pump (02) | 2026-05-29 | 2026-06-25 | 2026-11-14 | 2026-12-11 | 2026-05-09 | 2026-06-05
EOTCranes |  | 15-Aug-25 A | 2026-08-18 | 2026-08-11 | 2026-12-11 | 01-May-25 A | 18-Sep-25 A
EOTCraneforFGCompressor(1=60Ton) |  | 15-Aug-25 A | 2026-08-18 | 2026-08-11 | 2026-12-11 | 01-May-25 A | 13-Aug-25 A
A30950 | Key Vendor Drawings / Data Approved | 23-Jan-26 A | 2026-05-21 | 2026-08-11 | 2026-09-15 | 23-Jan-26 A | 2026-03-26
A30960 | Purchase Order for Major Sub-ordered Materials | 01-Feb-26 A | 12-Feb-26 A | 2026-09-15 | 2026-09-15 | 01-Feb-26 A | 12-Feb-26 A
A30970 | Major Sub-ordered Materials Received by Vendor and Verified | 23-Feb-26 A | 06-Mar-26 A | 2026-09-15 | 2026-09-15 | 2026-03-26 | 2026-05-07
A30980 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 23-Feb-26 A | 12-Mar-26 A | 2026-09-15 | 2026-09-15 | 2026-03-26 | 2026-03-27
A30990 | Manufacturing / Ex Works (India/UAE) | 28-Feb-26 A | 2026-06-20 | 2026-09-15 | 2026-10-15 | 2026-03-27 | 2026-07-05
A31000 | Complete Manufacturing & ready for Final Inspection | 01-Apr-26 A | 2026-06-26 | 2026-10-15 | 2026-10-21 | 2026-07-06 | 2026-07-14
A31010 | Materials Successfully Inspected, Tested / Ex Work | 2026-06-26 | 2026-07-07 | 2026-10-22 | 2026-10-30 | 2026-07-15 | 2026-07-23
A33910 | Start Production | 15-Aug-25 A |  | 2026-08-11 |  | 15-Aug-25 A
A33920 | Delivery of Material in Warehouse (FG) Crane | 2026-07-07 | 2026-08-18 | 2026-10-31 | 2026-12-11 | 2026-07-24 | 2026-08-13
EOTCraneforOGCompressor(1=25Ton) |  | 10-Sep-25 A | 2026-08-18 | 2026-08-11 | 2026-12-11 | 01-May-25 A | 18-Sep-25 A
A31040 | Key Vendor Drawings / Data Approved | 23-Jan-26 A | 2026-05-21 | 2026-08-11 | 2026-09-15 | 23-Jan-26 A | 2026-03-26
A31050 | Purchase Order for Major Sub-ordered Materials | 01-Feb-26 A | 12-Feb-26 A | 2026-09-15 | 2026-09-15 | 01-Feb-26 A | 12-Feb-26 A
A31060 | Major Sub-ordered Materials Received by Vendor and Verified | 22-Feb-26 A | 17-Mar-26 A | 2026-09-15 | 2026-09-15 | 2026-03-26 | 2026-05-07
A31070 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 28-Feb-26 A | 05-Mar-26 A | 2026-09-15 | 2026-09-15 | 2026-03-26 | 2026-03-27
A31080 | Manufacturing / Ex Works (India/UAE) | 23-Feb-26 A | 2026-06-20 | 2026-09-15 | 2026-10-15 | 2026-03-27 | 2026-07-05
A31090 | Complete Manufacturing & ready for Final Inspection | 01-Apr-26 A | 2026-06-26 | 2026-10-15 | 2026-10-21 | 2026-07-06 | 2026-07-14
A31100 | Materials Successfully Inspected, Tested / Ex Work | 2026-06-26 | 2026-07-07 | 2026-10-22 | 2026-10-30 | 2026-07-15 | 2026-07-23
A33930 | Start Production | 10-Sep-25 A |  | 2026-08-11 |  | 10-Sep-25 A
A33940 | Delivery of (OG) Crane | 2026-07-07 | 2026-08-18 | 2026-10-31 | 2026-12-11 | 2026-07-24 | 2026-08-13
HeatExchangers |  | 11-Jul-25 A | 2026-05-31 | 2026-08-05 | 2026-12-11 | 01-Jun-25 A | 02-Jul-25 A
HeatExchanger(TypeS&T=06Nos) |  | 11-Jul-25 A | 2026-05-31 | 2026-08-05 | 2026-12-11 | 01-Jun-25 A | 02-Jul-25 A
FGComp.InterstageCooler(BEM)-Tag#13-HE-703 |  | 11-Jul-25 A | 2026-05-31 | 2026-08-05 | 2026-09-18 | 01-Jun-25 A | 27-Jun-25 A
A36300 | Start Production (13-HE-703) | 11-Jul-25 A |  | 2026-08-05 |  | 11-Jul-25 A
A36310 | Key Vendor Drawings / Data Approved | 18-Jul-25 A | 28-Aug-25 A | 2026-08-05 | 2026-08-05 | 18-Jul-25 A | 28-Aug-25 A
A36320 | Purchase Order for Major Sub-ordered Materials | 29-Aug-25 A | 02-Sep-25 A | 2026-08-05 | 2026-08-05 | 29-Aug-25 A | 02-Sep-25 A
A36330 | Major Sub-ordered Materials Received by Vendor and Verified | 11-Aug-25 A | 12-Sep-25 A | 2026-08-05 | 2026-08-05 | 11-Aug-25 A | 12-Sep-25 A
A36340 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 15-Sep-25 A | 26-Oct-25 A | 2026-08-05 | 2026-08-05 | 15-Sep-25 A | 26-Oct-25 A
A36350 | Manufacturing / Ex Works (India/UAE) | 21-Nov-25 A | 20-Feb-26 A | 2026-08-05 | 2026-08-05 | 21-Nov-25 A | 2026-02-27
A36360 | Complete Manufacturing & ready for Final Inspection | 10-Feb-26 A | 20-Feb-26 A | 2026-08-05 | 2026-08-05 | 2026-02-27 | 2026-03-13
A36370 | Materials Successfully Inspected, Tested / Ex Work | 10-Feb-26 A | 20-Feb-26 A | 2026-08-05 | 2026-08-05 | 2026-03-13 | 2026-03-30
A36380 | Delivery of FG Comp. Interstage Cooler (BEM) - Tag# 13-HE-703 | 2026-04-17 | 2026-05-31 | 2026-08-05 | 2026-09-18 | 2026-03-30 | 2026-04-27
OGComp.AfterCooler(BEU)-Tag#13-HE-709 |  | 11-Jul-25 A | 2026-05-31 | 2026-09-07 | 2026-10-22 | 01-Jun-25 A | 27-Jun-25 A
A36430 | Start Production (13-HE-709) | 11-Jul-25 A |  | 2026-09-07 |  | 11-Jul-25 A
A36440 | Key Vendor Drawings / Data Approved | 18-Jul-25 A | 28-Aug-25 A | 2026-09-07 | 2026-09-07 | 18-Jul-25 A | 28-Aug-25 A
A36450 | Purchase Order for Major Sub-ordered Materials | 29-Aug-25 A | 02-Sep-25 A | 2026-09-07 | 2026-09-07 | 29-Aug-25 A | 02-Sep-25 A
A36460 | Major Sub-ordered Materials Received by Vendor and Verified | 11-Aug-25 A | 12-Sep-25 A | 2026-09-07 | 2026-09-07 | 11-Aug-25 A | 12-Sep-25 A
A36470 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 15-Sep-25 A | 26-Oct-25 A | 2026-09-07 | 2026-09-07 | 15-Sep-25 A | 26-Oct-25 A
A36480 | Manufacturing / Ex Works (India/UAE) | 21-Nov-25 A | 20-Feb-26 A | 2026-09-07 | 2026-09-07 | 21-Nov-25 A | 2026-02-24
A36490 | Complete Manufacturing & ready for Final Inspection | 03-Feb-26 A | 20-Feb-26 A | 2026-09-07 | 2026-09-07 | 2026-02-24 | 2026-03-10
A36500 | Materials Successfully Inspected, Tested / Ex Work | 16-Feb-26 A | 20-Feb-26 A | 2026-09-07 | 2026-09-07 | 2026-03-10 | 2026-03-25
A36520 | Delivery of OG Comp. After Cooler (BEU) - Tag# 13-HE-709 | 2026-04-17 | 2026-05-31 | 2026-09-07 | 2026-10-22 | 2026-03-25 | 2026-04-22
FGComp.AfterCooler(BEM)-Tag#13-HE-704 |  | 11-Jul-25 A | 2026-05-31 | 2026-08-05 | 2026-09-18 | 01-Jun-25 A | 27-Jun-25 A
A36560 | Start Production (13-HE-704) | 11-Jul-25 A |  | 2026-08-05 |  | 11-Jul-25 A
A36570 | Key Vendor Drawings / Data Approved | 18-Jul-25 A | 28-Aug-25 A | 2026-08-05 | 2026-08-05 | 18-Jul-25 A | 28-Aug-25 A
A36580 | Purchase Order for Major Sub-ordered Materials | 29-Aug-25 A | 02-Sep-25 A | 2026-08-05 | 2026-08-05 | 29-Aug-25 A | 02-Sep-25 A
A36590 | Major Sub-ordered Materials Received by Vendor and Verified | 11-Aug-25 A | 12-Sep-25 A | 2026-08-05 | 2026-08-05 | 11-Aug-25 A | 12-Sep-25 A
A36600 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 15-Sep-25 A | 26-Oct-25 A | 2026-08-05 | 2026-08-05 | 15-Sep-25 A | 26-Oct-25 A
A36610 | Manufacturing / Ex Works (India/UAE) | 21-Nov-25 A | 20-Feb-26 A | 2026-08-05 | 2026-08-05 | 21-Nov-25 A | 2026-02-24
A36620 | Complete Manufacturing & ready for Final Inspection | 01-Feb-26 A | 20-Feb-26 A | 2026-08-05 | 2026-08-05 | 2026-02-24 | 2026-03-10
A36630 | Materials Successfully Inspected, Tested / Ex Work | 01-Feb-26 A | 20-Feb-26 A | 2026-08-05 | 2026-08-05 | 2026-03-10 | 2026-03-25
A36660 | Delivery of FG Comp. After Cooler (BEM) - Tag# 13-HE-704 | 2026-04-17 | 2026-05-31 | 2026-08-05 | 2026-09-18 | 2026-03-25 | 2026-04-22
OGComp.InterstageCooler(BEU)(13-HE-708) |  | 11-Jul-25 A | 2026-05-31 | 2026-09-07 | 2026-10-22 | 01-Jun-25 A | 27-Jun-25 A
A36690 | Start Production (13-HE-708) | 11-Jul-25 A |  | 2026-09-07 |  | 11-Jul-25 A
A36700 | Key Vendor Drawings / Data Approved | 18-Jul-25 A | 28-Aug-25 A | 2026-09-07 | 2026-09-07 | 18-Jul-25 A | 28-Aug-25 A
A36710 | Purchase Order for Major Sub-ordered Materials | 29-Aug-25 A | 02-Sep-25 A | 2026-09-07 | 2026-09-07 | 29-Aug-25 A | 02-Sep-25 A
A36720 | Major Sub-ordered Materials Received by Vendor and Verified | 11-Aug-25 A | 12-Sep-25 A | 2026-09-07 | 2026-09-07 | 11-Aug-25 A | 12-Sep-25 A
A36730 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 15-Sep-25 A | 26-Oct-25 A | 2026-09-07 | 2026-09-07 | 15-Sep-25 A | 26-Oct-25 A
A36740 | Manufacturing / Ex Works (India/UAE) | 21-Nov-25 A | 20-Feb-26 A | 2026-09-07 | 2026-09-07 | 21-Nov-25 A | 2026-02-24
A36750 | Complete Manufacturing & ready for Final Inspection | 02-Feb-26 A | 20-Feb-26 A | 2026-09-07 | 2026-09-07 | 2026-02-24 | 2026-03-10
A36760 | Materials Successfully Inspected, Tested / Ex Work | 05-Feb-26 A | 20-Feb-26 A | 2026-09-07 | 2026-09-07 | 2026-03-10 | 2026-03-25
A36800 | Delivery of GG Comp. Interstage Cooler (BEU) (13-HE-708) | 2026-04-17 | 2026-05-31 | 2026-09-07 | 2026-10-22 | 2026-03-25 | 2026-04-22
C4GuardRegen.GasCooler(BEU)(Tag#50-HE-1410) |  | 11-Jul-25 A | 2026-05-31 | 2026-10-28 | 2026-12-11 | 01-Jun-25 A | 02-Jul-25 A
A36820 | Start Production (50-HE-1410) | 11-Jul-25 A |  | 2026-10-28 |  | 11-Jul-25 A
A36830 | Key Vendor Drawings / Data Approved | 18-Jul-25 A | 28-Aug-25 A | 2026-10-28 | 2026-10-28 | 18-Jul-25 A | 28-Aug-25 A
A36840 | Purchase Order for Major Sub-ordered Materials | 29-Aug-25 A | 02-Sep-25 A | 2026-10-28 | 2026-10-28 | 29-Aug-25 A | 02-Sep-25 A
A36850 | Major Sub-ordered Materials Received by Vendor and Verified | 11-Aug-25 A | 12-Sep-25 A | 2026-10-28 | 2026-10-28 | 11-Aug-25 A | 12-Sep-25 A
A36860 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 15-Sep-25 A | 26-Oct-25 A | 2026-10-28 | 2026-10-28 | 15-Sep-25 A | 26-Oct-25 A
A36870 | Manufacturing / Ex Works (India/UAE) | 21-Nov-25 A | 13-Feb-26 A | 2026-10-28 | 2026-10-28 | 21-Nov-25 A | 2026-02-23
A36880 | Complete Manufacturing & ready for Final Inspection | 04-Feb-26 A | 20-Feb-26 A | 2026-10-28 | 2026-10-28 | 2026-02-24 | 2026-03-09
A36890 | Materials Successfully Inspected, Tested / Ex Work | 12-Feb-26 A | 20-Feb-26 A | 2026-10-28 | 2026-10-28 | 2026-03-10 | 2026-03-24
A36940 | Delivery of C4 Guard Regen. Gas Cooler (BEU) (Tag#50-HE-1410) | 2026-04-17 | 2026-05-31 | 2026-10-28 | 2026-12-11 | 2026-04-03 | 2026-04-26
HVAC |  | 29-Aug-25 A | 2026-08-13 | 2026-10-15 | 2027-02-17 | 03-Jun-25 A | 03-Jun-25 A
HVAC |  | 29-Aug-25 A | 2026-08-13 | 2026-10-15 | 2027-02-17 | 03-Jun-25 A | 03-Jun-25 A
A30860 | Key Vendor Drawings / Data Approved | 03-Sep-25 A | 01-Dec-25 A | 2026-10-15 | 2026-10-15 | 03-Sep-25 A | 01-Dec-25 A
A30870 | Purchase Order for Major Sub-ordered Materials | 02-Dec-25 A | 19-Dec-25 A | 2026-10-15 | 2026-10-15 | 02-Dec-25 A | 19-Dec-25 A
A30880 | Major Sub-ordered Materials Received by Vendor and Verified | 19-Dec-25 A | 01-Jan-26 A | 2026-10-15 | 2026-10-15 | 19-Dec-25 A | 01-Jan-26 A
A30890 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 01-Jan-26 A | 15-Jan-26 A | 2026-10-15 | 2026-10-15 | 01-Jan-26 A | 15-Jan-26 A
A30900 | Manufacturing / Ex Works (India/UAE) | 21-Feb-26 A | 2026-07-06 | 2026-10-15 | 2027-01-04 | 2026-02-20 | 2026-07-09
A30910 | Complete Manufacturing & ready for Final Inspection | 21-Mar-26 A | 2026-07-14 | 2027-01-04 | 2027-01-11 | 2026-07-10 | 2026-07-20
A30920 | Materials Successfully Inspected, Tested / Ex Work | 2026-07-14 | 2026-07-23 | 2027-01-12 | 2027-01-20 | 2026-07-21 | 2026-07-29
A33890 | Start Production | 29-Aug-25 A |  | 2026-10-15 |  | 29-Aug-25 A
A33900 | Delivery of Material HVAC (Main Equipments) | 2026-07-23 | 2026-08-13 | 2027-01-28 | 2027-02-17 | 2026-07-30 | 2026-08-26
A34770 | Delivery of HVAC Ducts, E&I Material , Clading, Piping, Insulation, Supports & Accessories | 2026-07-23 | 2026-08-04 | 2027-01-21 | 2027-02-01 | 2026-07-30 | 2026-08-10
BulkMaterials |  | 15-Mar-25 A | 2026-10-29 | 2026-06-09 | 2027-03-20 | 15-Jan-25 A | 2026-07-24
DripLeg |  | 03-Sep-25 A | 2026-09-30 | 2026-06-29 | 2026-12-11 | 01-Aug-25 A | 09-Sep-25 A
OGComp.Dis.Dripleg(02Nos) |  | 03-Sep-25 A | 2026-09-30 | 2026-06-29 | 2026-12-11 | 01-Aug-25 A | 09-Sep-25 A
A30590 | Key Vendor Drawings / Data Approved | 01-Oct-25 A | 03-Nov-25 A | 2026-06-29 | 2026-06-29 | 01-Oct-25 A | 03-Nov-25 A
A30600 | Purchase Order for Major Sub-ordered Materials | 03-Nov-25 A | 09-Nov-25 A | 2026-06-29 | 2026-06-29 | 03-Nov-25 A | 09-Nov-25 A
A30610 | Major Sub-ordered Materials Received by Vendor and Verified | 10-Nov-25 A | 17-Nov-25 A | 2026-06-29 | 2026-06-29 | 10-Nov-25 A | 17-Nov-25 A
A30620 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 18-Mar-26 A | 19-Mar-26 A | 2026-06-29 | 2026-06-29 | 2026-02-20 | 2026-02-20
A30630 | Manufacturing / Ex Works (India/UAE) | 2026-04-17 | 2026-07-25 | 2026-06-29 | 2026-10-07 | 2026-02-21 | 2026-05-21
A30640 | Complete Manufacturing & ready for Final Inspection | 2026-07-27 | 2026-08-05 | 2026-10-07 | 2026-10-16 | 2026-05-22 | 2026-06-01
A30650 | Materials Successfully Inspected, Tested / Ex Work | 2026-08-06 | 2026-08-19 | 2026-10-19 | 2026-10-30 | 2026-06-02 | 2026-06-10
A33830 | Start Production | 03-Sep-25 A |  | 2026-06-29 |  | 03-Sep-25 A
A33840 | Delivery of OG Compressor Discharge Drip Leg (02) | 2026-08-20 | 2026-09-30 | 2026-10-31 | 2026-12-11 | 2026-06-11 | 2026-07-22
FireFightingEquipment |  | 27-Oct-25 A | 2026-10-12 | 2026-07-06 | 2027-01-03 | 11-Feb-25 A | 2026-03-19
VESDA(VeryEarlySmokeDetectionApparatus) |  | 27-Oct-25 A | 2026-08-07 | 2026-09-12 | 2027-01-03 | 01-May-25 A | 01-Oct-25 A
A32210 | Key Vendor Drawings / Data Approved | 19-Dec-25 A | 26-Dec-25 A | 2026-09-12 | 2026-09-12 | 19-Dec-25 A | 26-Dec-25 A
A32220 | Purchase Order for Major Sub-ordered Materials | 23-Dec-25 A | 04-Jan-26 A | 2026-09-12 | 2026-09-12 | 23-Dec-25 A | 04-Jan-26 A
A32230 | Major Sub-ordered Materials Received by Vendor and Verified | 29-Dec-25 A | 02-Jan-26 A | 2026-09-12 | 2026-09-12 | 29-Dec-25 A | 02-Jan-26 A
A32240 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 06-Jan-26 A | 09-Jan-26 A | 2026-09-12 | 2026-09-12 | 06-Jan-26 A | 09-Jan-26 A
A32250 | Manufacturing / Ex Works (India/UAE) | 21-Feb-26 A | 2026-06-20 | 2026-09-12 | 2026-11-16 | 2026-02-20 | 2026-06-04
A32260 | Complete Manufacturing & ready for Final Inspection | 2026-06-22 | 2026-07-01 | 2026-11-16 | 2026-11-25 | 2026-06-05 | 2026-06-16
A32270 | Materials Successfully Inspected, Tested / Ex Work | 2026-07-01 | 2026-07-10 | 2026-11-25 | 2026-12-04 | 2026-06-16 | 2026-06-25
A34190 | Start Production | 27-Oct-25 A |  | 2026-09-12 |  | 27-Oct-25 A
A34200 | Delivery and Manufacturing VESDA | 2026-07-11 | 2026-08-07 | 2026-12-07 | 2027-01-03 | 2026-06-26 | 2026-07-23
FireFightingEquipment |  | 01-Mar-26 A | 2026-10-12 | 2026-07-06 | 2026-12-30 | 11-Feb-25 A | 2026-03-19
A31310 | Key Vendor Drawings / Data Approved | 2026-04-17 | 2026-05-28 | 2026-07-06 | 2026-08-14 | 2026-03-20 | 2026-04-09
A31320 | Purchase Order for Major Sub-ordered Materials | 01-Mar-26 A | 20-Mar-26 A | 2026-08-17 | 2026-08-17 | 2026-04-09 | 2026-04-20
A31330 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-05-28 | 2026-07-09 | 2026-08-17 | 2026-09-25 | 2026-04-20 | 2026-05-11
A31340 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-07-09 | 2026-07-10 | 2026-09-27 | 2026-09-28 | 2026-05-11 | 2026-05-12
A31350 | Manufacturing / Ex Works (India/UAE) | 2026-07-10 | 2026-09-08 | 2026-09-28 | 2026-11-27 | 2026-05-12 | 2026-06-16
A31360 | Complete Manufacturing & ready for Final Inspection | 2026-09-08 | 2026-09-17 | 2026-11-27 | 2026-12-07 | 2026-06-16 | 2026-06-25
A31370 | Materials Successfully Inspected, Tested / Ex Work | 2026-09-17 | 2026-09-28 | 2026-12-08 | 2026-12-16 | 2026-06-25 | 2026-07-06
A33990 | Start Production | 2026-04-17 |  | 2026-07-06 |  | 2026-03-19
A34000 | Delivery of Fire Fighting Equipments | 2026-09-28 | 2026-10-12 | 2026-12-17 | 2026-12-30 | 2026-07-06 | 2026-07-27
TailGasFilter/Silencer/Colesor |  | 30-Jan-26 A | 14-Feb-26 A | 2027-01-19 | 2027-01-19 | 01-Apr-25 A | 2026-03-02
Coalescer-(BF) |  | 30-Jan-26 A | 14-Feb-26 A | 2027-01-19 | 2027-01-19 | 01-Apr-25 A | 2026-03-02
A28250 | Key Vendor Drawings / Data Approved | 30-Jan-26 A | 31-Jan-26 A | 2027-01-19 | 2027-01-19 | 30-Jan-26 A | 31-Jan-26 A
A28260 | Purchase Order for Major Sub-ordered Materials | 01-Feb-26 A | 02-Feb-26 A | 2027-01-19 | 2027-01-19 | 01-Feb-26 A | 02-Feb-26 A
A28270 | Major Sub-ordered Materials Received by Vendor and Verified | 03-Feb-26 A | 04-Feb-26 A | 2027-01-19 | 2027-01-19 | 03-Feb-26 A | 04-Feb-26 A
A28280 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 05-Feb-26 A | 06-Feb-26 A | 2027-01-19 | 2027-01-19 | 05-Feb-26 A | 06-Feb-26 A
A28290 | Manufacturing / Ex Works (India/UAE) | 07-Feb-26 A | 08-Feb-26 A | 2027-01-19 | 2027-01-19 | 07-Feb-26 A | 08-Feb-26 A
A28300 | Complete Manufacturing & ready for Final Inspection | 09-Feb-26 A | 10-Feb-26 A | 2027-01-19 | 2027-01-19 | 09-Feb-26 A | 10-Feb-26 A
A28310 | Materials Successfully Inspected, Tested / Ex Work | 11-Feb-26 A | 12-Feb-26 A | 2027-01-19 | 2027-01-19 | 11-Feb-26 A | 12-Feb-26 A
A34680 | Start Production | 30-Jan-26 A |  | 2027-01-19 |  | 30-Jan-26 A
A34690 | Delivery of Coalescer (Post TA) | 13-Feb-26 A | 14-Feb-26 A | 2027-01-19 | 2027-01-19 | 13-Feb-26 A | 14-Feb-26 A
SteelStructureGreenfield(material+sandwitchPanel) |  | 21-Jun-25 A | 2026-07-02 | 2026-06-16 | 2027-01-24 | 21-Jun-25 A | 2026-05-17
CivilBulkMaterial |  | 21-Jun-25 A | 06-Oct-25 A | 2027-01-24 | 2027-01-24 | 16-May-25 A | 10-Jul-25 A
A28430 | Key Vendor Drawings / Data Approved | 23-Jun-25 A | 28-Jul-25 A | 2027-01-24 | 2027-01-24 | 23-Jun-25 A | 28-Jul-25 A
A28440 | Purchase Order for Major Sub-ordered Materials | 29-Jul-25 A | 23-Aug-25 A | 2027-01-24 | 2027-01-24 | 29-Jul-25 A | 23-Aug-25 A
A28450 | Major Sub-ordered Materials Received by Vendor and Verified | 25-Aug-25 A | 30-Aug-25 A | 2027-01-24 | 2027-01-24 | 25-Aug-25 A | 30-Aug-25 A
A28460 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 01-Sep-25 A | 06-Sep-25 A | 2027-01-24 | 2027-01-24 | 01-Sep-25 A | 06-Sep-25 A
A28470 | Manufacturing / Ex Works (India/UAE) | 18-Aug-25 A | 15-Sep-25 A | 2027-01-24 | 2027-01-24 | 18-Aug-25 A | 15-Sep-25 A
A28480 | Complete Manufacturing & ready for Final Inspection | 08-Sep-25 A | 20-Sep-25 A | 2027-01-24 | 2027-01-24 | 08-Sep-25 A | 20-Sep-25 A
A28490 | Materials Successfully Inspected, Tested / Ex Work | 22-Sep-25 A | 29-Sep-25 A | 2027-01-24 | 2027-01-24 | 22-Sep-25 A | 29-Sep-25 A
A28500 | Delivery of Civil Bulk Material | 30-Sep-25 A | 06-Oct-25 A | 2027-01-24 | 2027-01-24 | 30-Sep-25 A | 06-Oct-25 A
A33330 | Start Production | 21-Jun-25 A |  | 2027-01-24 |  | 21-Jun-25 A |  | Start of Procurement
StructuralSteel |  | 18-Sep-25 A | 2026-07-02 | 2026-06-16 | 2026-08-31 | 01-Jun-25 A | 2026-03-09
A28520 | Key Vendor Drawings / Data Approved | 19-Dec-25 A | 24-Jan-26 A | 2026-06-25 | 2026-06-25 | 19-Dec-25 A | 24-Jan-26 A
A28530 | Purchase Order for Major Sub-ordered Materials | 25-Jan-26 A | 16-Feb-26 A | 2026-06-25 | 2026-06-25 | 25-Jan-26 A | 16-Feb-26 A
A28540 | Major Sub-ordered Materials Received by Vendor and Verified | 17-Feb-26 A | 20-Mar-26 A | 2026-06-25 | 2026-06-25 | 17-Feb-26 A | 2026-03-12
A28550 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 17-Feb-26 A | 17-Feb-26 A | 2026-06-25 | 2026-06-25 | 17-Feb-26 A | 17-Feb-26 A
A28560 | Manufacturing / Ex Works | 13-Mar-26 A | 2026-05-15 | 2026-06-25 | 2026-07-23 | 2026-03-13 | 2026-04-28
A28570 | Complete Manufacturing & ready for Final Inspection | 18-Mar-26 A | 2026-05-22 | 2026-07-10 | 2026-07-30 | 2026-04-29 | 2026-05-05
A28580 | Materials Successfully Inspected, Tested / Ex Work | 2026-04-17 | 2026-06-11 | 2026-06-16 | 2026-08-10 | 2026-05-06 | 2026-05-12
A28590 | COMPANY Final decision on Compressor Shelter Height |  | 15-Dec-25 A |  | 2026-06-25 |  | 15-Dec-25 A
A33340 | Delivery of Structural Steel GF | 2026-05-21 | 2026-07-02 | 2026-07-20 | 2026-08-31 | 2026-05-13 | 2026-05-17
A33350 | Start Production | 18-Sep-25 A |  | 2026-06-25 |  | 18-Sep-25 A
TubingMaterial[SStubes,Connectors,unions,plugsetc.] |  | 2026-06-11 | 2026-09-30 | 2026-09-11 | 2026-12-30 | 2026-04-16 | 2026-09-13
TubingMaterial[SStubes,Connectors,unions,plugsetc] |  | 2026-06-11 | 2026-09-30 | 2026-09-11 | 2026-12-30 | 2026-04-16 | 2026-09-13
A30140 | Key Vendor Drawings / Data Approved | 2026-06-12 | 2026-06-25 | 2026-09-11 | 2026-09-24 | 2026-04-17 | 2026-05-14
A30150 | Purchase Order for Major Sub-ordered Materials | 2026-06-25 | 2026-07-09 | 2026-09-25 | 2026-10-08 | 2026-05-14 | 2026-06-04
A30160 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-07-09 | 2026-07-23 | 2026-10-09 | 2026-10-22 | 2026-06-04 | 2026-06-25
A30170 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-07-23 | 2026-07-24 | 2026-10-23 | 2026-10-24 | 2026-06-25 | 2026-06-26
A30180 | Manufacturing / Ex Works (India/UAE) | 2026-07-24 | 2026-09-07 | 2026-10-24 | 2026-12-08 | 2026-06-26 | 2026-08-15
A30190 | Complete Manufacturing & ready for Final Inspection | 2026-09-07 | 2026-09-14 | 2026-12-08 | 2026-12-14 | 2026-08-17 | 2026-08-25
A30200 | Materials Successfully Inspected, Tested / Ex Work | 2026-09-14 | 2026-09-23 | 2026-12-15 | 2026-12-23 | 2026-08-26 | 2026-09-03
A33700 | Start Production | 2026-06-11 |  | 2026-09-11 |  | 2026-04-16
A33710 | Delivery at site - (Tubing Material) | 2026-09-23 | 2026-09-30 | 2026-12-24 | 2026-12-30 | 2026-09-04 | 2026-09-13
SteelStructureBrownfield |  | 15-Mar-25 A | 2026-05-07 | 2026-06-16 | 2026-11-21 | 15-Mar-25 A | 2026-04-19
SteelStructure-PostTA-BF |  | 18-Sep-25 A | 2026-05-07 | 2026-11-01 | 2026-11-21 | 18-Sep-25 A | 2026-04-19
A34560 | Start Production | 18-Sep-25 A |  | 2026-11-01 |  | 18-Sep-25 A
A34570 | Key Vendor Drawings / Data Approved | 01-Feb-26 A | 06-Feb-26 A | 2026-11-01 | 2026-11-01 | 01-Feb-26 A | 06-Feb-26 A
A34580 | Purchase Order for Major Sub-ordered Materials | 09-Feb-26 A | 13-Feb-26 A | 2026-11-01 | 2026-11-01 | 09-Feb-26 A | 13-Feb-26 A
A34590 | Major Sub-ordered Materials Received by Vendor and Verified | 16-Feb-26 A | 16-Feb-26 A | 2026-11-01 | 2026-11-01 | 16-Feb-26 A | 16-Feb-26 A
A34600 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 17-Feb-26 A | 17-Feb-26 A | 2026-11-01 | 2026-11-01 | 17-Feb-26 A | 17-Feb-26 A
A34610 | Manufacturing / Ex Works | 18-Feb-26 A | 2026-04-26 | 2026-11-01 | 2026-11-11 | 18-Feb-26 A | 2026-03-31
A34620 | Complete Manufacturing & ready for Final Inspection | 10-Mar-26 A | 2026-04-29 | 2026-11-11 | 2026-11-13 | 2026-04-01 | 2026-04-07
A34630 | Materials Successfully Inspected, Tested / Ex Work | 2026-04-30 | 2026-05-04 | 2026-11-16 | 2026-11-18 | 2026-04-08 | 2026-04-14
A34650 | Delivery of (Steel Structure - PostTA) | 2026-05-05 | 2026-05-07 | 2026-11-19 | 2026-11-21 | 2026-04-15 | 2026-04-19
TA_SteelStructure(AdditionalSteelStructurerequiredforBFW) |  | 15-Mar-25 A | 09-May-25 A | 2026-06-16 | 2026-06-16 | 15-Mar-25 A | 09-May-25 A
A27800 | Key Vendor Drawings / Data Approved | 15-Mar-25 A | 20-Mar-25 A | 2026-06-16 | 2026-06-16 | 15-Mar-25 A | 20-Mar-25 A
A27810 | Purchase Order for Major Sub-ordered Materials | 17-Mar-25 A | 21-Mar-25 A | 2026-06-16 | 2026-06-16 | 17-Mar-25 A | 21-Mar-25 A
A27820 | Major Sub-ordered Materials Received by Vendor and Verified | 22-Mar-25 A | 28-Mar-25 A | 2026-06-16 | 2026-06-16 | 22-Mar-25 A | 28-Mar-25 A
A27830 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 29-Mar-25 A | 04-Apr-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 04-Apr-25 A
A27840 | Manufacturing / Ex Works (India/UAE) | 05-Apr-25 A | 11-Apr-25 A | 2026-06-16 | 2026-06-16 | 05-Apr-25 A | 11-Apr-25 A
A27850 | Complete Manufacturing & ready for Final Inspection | 12-Apr-25 A | 18-Apr-25 A | 2026-06-16 | 2026-06-16 | 12-Apr-25 A | 18-Apr-25 A
A27860 | Materials Successfully Inspected, Tested / Ex Work | 19-Apr-25 A | 25-Apr-25 A | 2026-06-16 | 2026-06-16 | 19-Apr-25 A | 25-Apr-25 A
A34450 | Delivery at Site by EPC ( Fabricated, Painted & Galvanized TA Steel Structure ) | 26-Apr-25 A | 09-May-25 A | 2026-06-16 | 2026-06-16 | 26-Apr-25 A | 09-May-25 A
A34490 | Start Production | 15-Mar-25 A |  | 2026-06-16 |  | 15-Mar-25 A
Telecom(ACS+LAN+CCTV+PAGA) |  | 11-Dec-25 A | 2026-10-05 | 2026-07-09 | 2027-02-10 | 11-Mar-25 A | 2026-02-27
Telecom(ACS+CCTV+PAGA)Integration |  | 11-Dec-25 A | 2026-10-05 | 2026-08-24 | 2027-02-10 | 01-Aug-25 A | 19-Dec-25 A
A31400 | Key Vendor Drawings / Data Approved | 20-Feb-26 A | 2026-05-07 | 2026-08-24 | 2026-09-11 | 20-Feb-26 A | 2026-03-20
A31410 | Purchase Order for Major Sub-ordered Materials | 11-Dec-25 A | 20-Feb-26 A | 2026-09-14 | 2026-09-14 | 11-Dec-25 A | 2026-03-20
A31420 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-05-07 | 2026-05-28 | 2026-09-14 | 2026-10-02 | 2026-03-20 | 2026-04-20
A31430 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-05-28 | 2026-05-29 | 2026-10-04 | 2026-10-05 | 2026-04-20 | 2026-04-21
A31440 | Manufacturing / Ex Works (India/UAE) | 2026-05-29 | 2026-09-01 | 2026-10-05 | 2027-01-08 | 2026-04-21 | 2026-07-20
A31450 | Complete Manufacturing & ready for Final Inspection | 2026-09-01 | 2026-09-10 | 2027-01-08 | 2027-01-18 | 2026-07-20 | 2026-07-29
A31460 | Materials Successfully Inspected, Tested / Ex Work | 2026-09-10 | 2026-09-21 | 2027-01-19 | 2027-01-27 | 2026-07-29 | 2026-08-07
A34010 | Start Production | 19-Dec-25 A |  | 2026-08-24 |  | 19-Dec-25 A
A34020 | Delivery of Telecom (ACS + CCTV + PAGA) Integration | 2026-09-21 | 2026-10-05 | 2027-01-28 | 2027-02-10 | 2026-08-07 | 2026-08-21
AcessControlSystem |  | 12-Dec-25 A | 2026-10-05 | 2026-07-09 | 2026-12-27 | 01-Aug-25 A | 2026-02-27
A31490 | Key Vendor Drawings / Data Approved | 20-Feb-26 A | 2026-05-07 | 2026-07-09 | 2026-07-29 | 20-Feb-26 A | 2026-04-09
A31500 | Purchase Order for Major Sub-ordered Materials | 12-Dec-25 A | 25-Dec-25 A | 2026-07-30 | 2026-07-30 | 12-Dec-25 A | 25-Dec-25 A
A31510 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-05-07 | 2026-05-28 | 2026-07-30 | 2026-08-19 | 2026-04-09 | 2026-05-07
A31520 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-05-28 | 2026-05-29 | 2026-08-20 | 2026-08-21 | 2026-05-07 | 2026-05-08
A31530 | Manufacturing / Ex Works (India/UAE) | 2026-05-29 | 2026-09-01 | 2026-08-21 | 2026-11-24 | 2026-05-08 | 2026-08-06
A31540 | Complete Manufacturing & ready for Final Inspection | 2026-09-01 | 2026-09-10 | 2026-11-24 | 2026-12-02 | 2026-08-06 | 2026-08-17
A31550 | Materials Successfully Inspected, Tested / Ex Work | 2026-09-10 | 2026-09-21 | 2026-12-03 | 2026-12-11 | 2026-08-17 | 2026-08-26
A34030 | Start Production | 12-Dec-25 A |  | 2026-07-09 |  | 12-Dec-25 A
A34040 | Delivery of ACS | 2026-09-21 | 2026-10-05 | 2026-12-14 | 2026-12-27 | 2026-08-26 | 2026-09-09
CCTV |  | 19-Dec-25 A | 2026-10-05 | 2026-07-28 | 2027-01-16 | 01-Aug-25 A | 2026-02-27
A32310 | Purchase Order for Major Sub-ordered Materials | 01-Mar-26 A | 11-Mar-26 A | 2026-08-18 | 2026-08-18 | 2026-03-19 | 2026-04-02
A32320 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-05-07 | 2026-05-28 | 2026-08-18 | 2026-09-07 | 2026-04-02 | 2026-05-14
A32330 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-05-28 | 2026-05-29 | 2026-09-08 | 2026-09-09 | 2026-05-14 | 2026-05-15
A32340 | Manufacturing / Ex Works (India/UAE) | 2026-05-29 | 2026-09-06 | 2026-09-09 | 2026-12-18 | 2026-05-15 | 2026-07-29
A32350 | Complete Manufacturing & ready for Final Inspection | 2026-09-07 | 2026-09-10 | 2026-12-18 | 2026-12-23 | 2026-07-29 | 2026-08-07
A32360 | Materials Successfully Inspected, Tested / Ex Work | 2026-09-11 | 2026-09-21 | 2026-12-24 | 2027-01-01 | 2026-08-07 | 2026-08-18
A34210 | Start Production | 19-Dec-25 A |  | 2026-07-28 |  | 19-Dec-25 A
A34220 | Key Vendor Drawings / Data Approved | 28-Feb-26 A | 2026-05-07 | 2026-07-28 | 2026-08-17 | 2026-02-20 | 2026-04-02
A34250 | Delivery of CCTV | 2026-09-22 | 2026-10-05 | 2027-01-03 | 2027-01-16 | 2026-08-18 | 2026-08-25
PAGA+Telephone |  | 11-Dec-25 A | 2026-10-05 | 2026-08-04 | 2027-01-23 | 01-Aug-25 A | 2026-02-27
A31580 | Key Vendor Drawings / Data Approved | 19-Dec-25 A | 2026-05-07 | 2026-08-04 | 2026-08-24 | 19-Dec-25 A | 2026-03-20
A31590 | Purchase Order for Major Sub-ordered Materials | 11-Dec-25 A | 20-Mar-26 A | 2026-08-25 | 2026-08-25 | 11-Dec-25 A | 2026-03-20
A31600 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-05-07 | 2026-05-28 | 2026-08-25 | 2026-09-14 | 2026-03-20 | 2026-04-20
A31610 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-05-28 | 2026-05-29 | 2026-09-15 | 2026-09-16 | 2026-04-20 | 2026-04-21
A31620 | Manufacturing / Ex Works (India/UAE) | 2026-05-29 | 2026-09-06 | 2026-09-16 | 2026-12-25 | 2026-04-21 | 2026-07-20
A31630 | Complete Manufacturing & ready for Final Inspection | 2026-09-07 | 2026-09-10 | 2026-12-25 | 2026-12-30 | 2026-07-20 | 2026-07-29
A31640 | Materials Successfully Inspected, Tested / Ex Work | 2026-09-11 | 2026-09-21 | 2026-12-31 | 2027-01-08 | 2026-07-29 | 2026-08-07
A34050 | Start Production | 19-Dec-25 A |  | 2026-08-04 |  | 19-Dec-25 A
A34060 | Delivery of PAGA + Telephone | 2026-09-22 | 2026-10-05 | 2027-01-10 | 2027-01-23 | 2026-08-07 | 2026-08-21
LightingFixtures |  | 2026-05-07 | 2026-09-30 | 2026-10-28 | 2027-03-20 | 2026-02-20 | 2026-05-22
LightingFixtures(Almost50%Exd=354Nos) |  | 2026-05-07 | 2026-09-30 | 2026-10-28 | 2027-03-20 | 2026-02-20 | 2026-05-22
A32390 | Key Vendor Drawings / Data Approved | 2026-05-08 | 2026-06-18 | 2026-10-28 | 2026-12-08 | 2026-05-25 | 2026-06-22
A32400 | Purchase Order for Major Sub-ordered Materials | 2026-06-18 | 2026-07-02 | 2026-12-09 | 2026-12-22 | 2026-06-22 | 2026-07-06
A32410 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-07-02 | 2026-07-21 | 2026-12-23 | 2027-01-08 | 2026-07-06 | 2026-07-27
A32420 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-07-21 | 2026-07-22 | 2027-01-10 | 2027-01-11 | 2026-07-27 | 2026-07-28
A32430 | Manufacturing / Ex Works (India/UAE) | 2026-07-22 | 2026-09-02 | 2027-01-11 | 2027-02-22 | 2026-07-28 | 2026-09-01
A32440 | Complete Manufacturing & ready for Final Inspection | 2026-09-02 | 2026-09-09 | 2027-02-22 | 2027-02-26 | 2026-09-01 | 2026-09-08
A32450 | Materials Successfully Inspected, Tested / Ex Work | 2026-09-09 | 2026-09-16 | 2027-03-01 | 2027-03-05 | 2026-09-08 | 2026-09-15
A34230 | Start Production | 2026-05-07 |  | 2026-10-28 |  | 2026-05-22
A34240 | Delivery of Material in Warehouse Lighting Fixtures | 2026-09-16 | 2026-09-30 | 2027-03-07 | 2027-03-20 | 2026-09-15 | 2026-09-22
ManualValve |  | 20-Nov-25 A | 2026-09-24 | 2026-08-04 | 2026-12-30 | 20-May-25 A | 21-Nov-25 A
ManualValves(Gate9Nos,Check6Nos,GlobeValves64Nos) |  | 20-Nov-25 A | 2026-09-24 | 2026-08-04 | 2026-12-30 | 20-May-25 A | 21-Nov-25 A
A30050 | Key Vendor Drawings / Data Approved | 20-Feb-26 A | 28-Feb-26 A | 2026-08-04 | 2026-08-04 | 20-Feb-26 A | 2026-03-05
A30060 | Purchase Order for Major Sub-ordered Materials | 01-Mar-26 A | 10-Mar-26 A | 2026-08-04 | 2026-08-04 | 2026-03-05 | 2026-03-12
A30070 | Major Sub-ordered Materials Received by Vendor and Verified | 12-Mar-26 A | 17-Mar-26 A | 2026-08-04 | 2026-08-04 | 2026-03-12 | 2026-04-23
A30080 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 13-Mar-26 A | 13-Mar-26 A | 2026-08-04 | 2026-08-04 | 2026-03-12 | 2026-03-13
A30090 | Manufacturing / Ex Works (India/UAE) | 18-Mar-26 A | 2026-07-19 | 2026-08-04 | 2026-10-23 | 2026-03-13 | 2026-06-21
A30100 | Complete Manufacturing & ready for Final Inspection | 2026-07-20 | 2026-07-30 | 2026-10-23 | 2026-11-04 | 2026-06-22 | 2026-06-30
A30110 | Materials Successfully Inspected, Tested / Ex Work | 2026-07-31 | 2026-08-13 | 2026-11-05 | 2026-11-18 | 2026-07-01 | 2026-07-09
A33680 | Start Production | 20-Nov-25 A |  | 2026-08-04 |  | 20-Nov-25 A
A33690 | Delivery at site warehouse for Manual Valves (Gate 9 Nos, Check 6 Nos, Globe Valves 64 Nos) | 2026-08-14 | 2026-09-24 | 2026-11-19 | 2026-12-30 | 2026-07-10 | 2026-07-30
SteamTraps |  | 17-Apr-26 A | 2026-08-31 | 2026-08-20 | 2027-01-01
SteamTraps |  | 17-Apr-26 A | 2026-08-31 | 2026-08-20 | 2027-01-01
A63320 | Key Vendor Drawings / Data Approved | 2026-04-17 | 2026-04-30 | 2026-08-20 | 2026-09-02
A63330 | Manufacturing / Ex Works (UAE) | 2026-05-26 | 2026-08-04 | 2026-09-29 | 2026-12-08
A63340 | Purchase Order for Major Sub-ordered Materials | 2026-04-30 | 2026-05-14 | 2026-09-03 | 2026-09-16
A63350 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-05-14 | 2026-05-25 | 2026-09-17 | 2026-09-25
A63360 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-05-25 | 2026-05-26 | 2026-09-28 | 2026-09-29
A63370 | Complete Manufacturing & ready for Final Inspection | 2026-08-04 | 2026-08-13 | 2026-12-08 | 2026-12-16
A63380 | Materials Successfully Inspected, Tested / Ex Work | 2026-08-13 | 2026-08-24 | 2026-12-17 | 2026-12-25
A63390 | Start Production | 17-Apr-26 A |  | 2026-08-20
A63400 | Delivery of Steam Traps | 2026-08-24 | 2026-08-31 | 2026-12-26 | 2027-01-01
HoseCoupling |  | 17-Apr-26 A | 2026-10-15 | 2026-07-06 | 2027-01-01
HoseCoupling |  | 17-Apr-26 A | 2026-10-15 | 2026-07-06 | 2027-01-01
A63590 | Key Vendor Drawings / Data Approved | 2026-04-17 | 2026-05-06 | 2026-07-06 | 2026-07-23
A63600 | Manufacturing / Ex Works | 2026-06-11 | 2026-09-09 | 2026-08-29 | 2026-11-27
A63610 | Purchase Order for Major Sub-ordered Materials | 2026-05-06 | 2026-05-20 | 2026-07-24 | 2026-08-06
A63620 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-05-20 | 2026-06-10 | 2026-08-07 | 2026-08-27
A63630 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-06-10 | 2026-06-11 | 2026-08-28 | 2026-08-29
A63640 | Complete Manufacturing & ready for Final Inspection | 2026-09-09 | 2026-09-18 | 2026-11-27 | 2026-12-07
A63650 | Materials Successfully Inspected, Tested / Ex Work | 2026-09-18 | 2026-09-29 | 2026-12-08 | 2026-12-16
A63660 | Start Production | 17-Apr-26 A |  | 2026-07-06
A63670 | Delivery of Hose Coupling | 2026-09-29 | 2026-10-15 | 2026-12-17 | 2027-01-01
SpecialGGCandButterflyVlaves |  | 2026-06-08 | 2026-10-29 | 2026-08-13 | 2027-01-01
SpecialGGCandButterflyVlaves |  | 2026-06-08 | 2026-10-29 | 2026-08-13 | 2027-01-01
A62600 | Key Vendor Drawings / Data Approved | 2026-06-09 | 2026-06-29 | 2026-08-13 | 2026-09-02
A62610 | Manufacturing / Ex Works | 2026-08-04 | 2026-10-03 | 2026-10-09 | 2026-12-08
A62620 | Purchase Order for Major Sub-ordered Materials | 2026-06-29 | 2026-07-13 | 2026-09-03 | 2026-09-16
A62630 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-07-13 | 2026-08-03 | 2026-09-17 | 2026-10-07
A62640 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-08-03 | 2026-08-04 | 2026-10-08 | 2026-10-09
A62650 | Complete Manufacturing & ready for Final Inspection | 2026-10-05 | 2026-10-13 | 2026-12-08 | 2026-12-16
A62660 | Materials Successfully Inspected, Tested / Ex Work | 2026-10-14 | 2026-10-22 | 2026-12-17 | 2026-12-25
A62670 | Start Production | 2026-06-08 |  | 2026-08-13
A62680 | Delivery of Special GGC and Butterfly Valves | 2026-10-23 | 2026-10-29 | 2026-12-26 | 2027-01-01
MechanicalInterlocks |  | 01-Apr-26 A | 2026-10-10 | 2026-07-08 | 2027-01-01
MechanicalInterlocks |  | 01-Apr-26 A | 2026-10-10 | 2026-07-08 | 2027-01-01
A64280 | Key Vendor Drawings / Data Approved | 2026-04-17 | 2026-05-07 | 2026-07-08 | 2026-07-28
A64290 | Manufacturing / Ex Works (UAE) | 2026-06-12 | 2026-09-05 | 2026-09-03 | 2026-11-27
A64300 | Purchase Order for Major Sub-ordered Materials | 2026-05-07 | 2026-05-21 | 2026-07-29 | 2026-08-11
A64310 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-05-21 | 2026-06-11 | 2026-08-12 | 2026-09-01
A64320 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-06-11 | 2026-06-12 | 2026-09-02 | 2026-09-03
A64330 | Complete Manufacturing & ready for Final Inspection | 2026-09-07 | 2026-09-15 | 2026-11-27 | 2026-12-07
A64340 | Materials Successfully Inspected, Tested / Ex Work | 2026-09-16 | 2026-09-24 | 2026-12-08 | 2026-12-16
A64350 | Start Production | 01-Apr-26 A |  | 2026-07-08
A64360 | Delivery of Mechanical Interlocks | 2026-09-25 | 2026-10-10 | 2026-12-17 | 2027-01-01
PipingBulk |  | 01-Sep-25 A | 2026-09-26 | 2026-06-09 | 2027-01-01 | 01-Jul-25 A | 2026-07-24
PipingLotforPostTA |  | 01-Sep-25 A | 2026-04-30 | 2026-06-09 | 2026-06-22 | 01-Jul-25 A | 17-Nov-25 A
84.D50 | Delivery of Piping Material in Warehouse (1st Lot, GF) | 10-Feb-26 A | 2026-04-30 | 2026-06-09 | 2026-06-22 | 10-Feb-26 A | 2026-03-06
A27990 | Purchase Order for Major Sub-ordered Materials | 02-Sep-25 A | 08-Sep-25 A | 2026-06-09 | 2026-06-09 | 02-Sep-25 A | 08-Sep-25 A
A28000 | Major Sub-ordered Materials Received by Vendor and Verified | 22-Oct-25 A | 31-Oct-25 A | 2026-06-09 | 2026-06-09 | 22-Oct-25 A | 31-Oct-25 A
A28010 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 03-Nov-25 A | 25-Dec-25 A | 2026-06-09 | 2026-06-09 | 03-Nov-25 A | 25-Dec-25 A
A28020 | Manufacturing / Ex Works (India/UAE) | 26-Dec-25 A | 18-Jan-26 A | 2026-06-09 | 2026-06-09 | 26-Dec-25 A | 18-Jan-26 A
A28030 | Complete Manufacturing & ready for Final Inspection | 26-Jan-26 A | 30-Jan-26 A | 2026-06-09 | 2026-06-09 | 26-Jan-26 A | 30-Jan-26 A
A28040 | Materials Successfully Inspected, Tested / Ex Work | 02-Feb-26 A | 06-Feb-26 A | 2026-06-09 | 2026-06-09 | 02-Feb-26 A | 06-Feb-26 A
A34500 | Start Production | 01-Sep-25 A |  | 2026-06-09 |  | 01-Sep-25 A
PipingSupports(SwingHangers)forPostTA |  | 09-Sep-25 A | 2026-09-07 | 2026-06-12 | 2026-11-09 | 04-Aug-25 A | 08-Sep-25 A
A28070 | Key Vendor Drawings / Data Approved | 2026-04-17 | 2026-05-14 | 2026-06-12 | 2026-07-09 | 2026-02-20 | 2026-03-19
A28080 | Purchase Order for Major Sub-ordered Materials | 2026-05-14 | 2026-05-21 | 2026-07-10 | 2026-07-16 | 2026-03-19 | 2026-03-26
A28090 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-05-21 | 2026-06-15 | 2026-07-17 | 2026-08-10 | 2026-03-26 | 2026-04-16
A28100 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-06-15 | 2026-06-16 | 2026-08-11 | 2026-08-12 | 2026-04-16 | 2026-04-23
A28110 | Manufacturing / Ex Works | 2026-06-16 | 2026-08-11 | 2026-08-12 | 2026-10-07 | 2026-04-23 | 2026-06-18
A28120 | Complete Manufacturing & ready for Final Inspection | 2026-08-11 | 2026-08-20 | 2026-10-07 | 2026-10-15 | 2026-06-18 | 2026-07-02
A28130 | Materials Successfully Inspected, Tested / Ex Work | 2026-08-20 | 2026-08-31 | 2026-10-16 | 2026-10-26 | 2026-07-02 | 2026-07-09
A34510 | Start Production | 09-Sep-25 A |  | 2026-06-12 |  | 2026-02-20
A34520 | Delivery of Material in Warehouse ( Piping Swing Hangers - PostTA) | 2026-08-31 | 2026-09-07 | 2026-11-03 | 2026-11-09 | 2026-07-09 | 2026-07-16
Piping1stLotforGF |  | 01-Sep-25 A | 31-Jan-26 A | 2026-06-21 | 2026-06-21 | 01-Jul-25 A | 2026-03-13
84.D40 | Delivery of Piping Material in Warehouse (1st Lot, GF) | 26-Jan-26 A | 31-Jan-26 A | 2026-06-21 | 2026-06-21 | 26-Jan-26 A | 31-Jan-26 A
A28620 | Purchase Order for Major Sub-ordered Materials | 02-Sep-25 A | 08-Sep-25 A | 2026-06-21 | 2026-06-21 | 02-Sep-25 A | 08-Sep-25 A
A28630 | Major Sub-ordered Materials Received by Vendor and Verified | 03-Sep-25 A | 15-Sep-25 A | 2026-06-21 | 2026-06-21 | 03-Sep-25 A | 15-Sep-25 A
A28640 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 19-Dec-25 A | 25-Dec-25 A | 2026-06-21 | 2026-06-21 | 19-Dec-25 A | 25-Dec-25 A
A28650 | Manufacturing / Ex Works (India/UAE) | 26-Dec-25 A | 18-Jan-26 A | 2026-06-21 | 2026-06-21 | 26-Dec-25 A | 18-Jan-26 A
A28660 | Complete Manufacturing & ready for Final Inspection | 19-Jan-26 A | 23-Jan-26 A | 2026-06-21 | 2026-06-21 | 19-Jan-26 A | 23-Jan-26 A
A28670 | Materials Successfully Inspected, Tested / Ex Work | 19-Jan-26 A | 23-Jan-26 A | 2026-06-21 | 2026-06-21 | 19-Jan-26 A | 23-Jan-26 A
A33360 | Start Production | 01-Sep-25 A |  | 2026-06-21 |  | 01-Sep-25 A
Piping2ndLotforGF(CSMaterial) |  | 26-Dec-25 A | 2026-05-31 | 2026-08-02 | 2026-09-15 | 2026-02-20 | 2026-03-19
85.D10 | Delivery of Piping Material in Warehouse (2nd Lot) | 2026-04-17 | 2026-05-31 | 2026-08-02 | 2026-09-15 | 2026-04-04 | 2026-04-17
A28710 | Purchase Order for Major Sub-ordered Materials | 28-Dec-25 A | 02-Jan-26 A | 2026-08-02 | 2026-08-02 | 28-Dec-25 A | 02-Jan-26 A
A28720 | Major Sub-ordered Materials Received by Vendor and Verified | 26-Dec-25 A | 09-Jan-26 A | 2026-08-02 | 2026-08-02 | 26-Dec-25 A | 09-Jan-26 A
A28730 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 09-Jan-26 A | 16-Jan-26 A | 2026-08-02 | 2026-08-02 | 09-Jan-26 A | 16-Jan-26 A
A28740 | Manufacturing / Ex Works (India/UAE) | 15-Jan-26 A | 20-Mar-26 A | 2026-08-02 | 2026-08-02 | 15-Jan-26 A | 2026-03-21
A28750 | Complete Manufacturing & ready for Final Inspection | 01-Mar-26 A | 20-Mar-26 A | 2026-08-02 | 2026-08-02 | 2026-03-23 | 2026-03-27
A28760 | Materials Successfully Inspected, Tested / Ex Work | 02-Mar-26 A | 20-Mar-26 A | 2026-08-02 | 2026-08-02 | 2026-03-30 | 2026-04-03
A33370 | Start Production | 26-Dec-25 A |  | 2026-08-02 |  | 26-Dec-25 A
Piping3rdLotGF(CSMaterial) |  | 2026-06-17 | 2026-09-17 | 2026-08-10 | 2026-11-09 | 2026-03-13 | 2026-04-22
A28800 | Purchase Order for Major Sub-ordered Materials | 2026-06-17 | 2026-06-24 | 2026-08-10 | 2026-08-14 | 2026-04-22 | 2026-04-29
A28810 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-06-24 | 2026-07-01 | 2026-08-17 | 2026-08-21 | 2026-04-29 | 2026-05-20
A28820 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-07-01 | 2026-07-04 | 2026-08-22 | 2026-08-25 | 2026-05-20 | 2026-05-23
A28830 | Manufacturing / Ex Works (India/UAE) | 2026-07-04 | 2026-08-18 | 2026-08-25 | 2026-10-09 | 2026-05-23 | 2026-07-22
A28840 | Complete Manufacturing & ready for Final Inspection | 2026-08-18 | 2026-08-25 | 2026-10-09 | 2026-10-15 | 2026-07-22 | 2026-07-29
A28850 | Materials Successfully Inspected, Tested / Ex Work | 2026-08-25 | 2026-09-03 | 2026-10-16 | 2026-10-26 | 2026-07-29 | 2026-08-07
A28860 | Delivery of Piping Material in Warehouse (Final Lot) | 2026-09-03 | 2026-09-17 | 2026-10-27 | 2026-11-09 | 2026-08-07 | 2026-08-21
A33380 | Start Production | 2026-06-17 |  | 2026-08-10 |  | 2026-04-22
PipingSupports(SwingHangers)forGF |  | 2026-06-17 | 2026-09-26 | 2026-09-08 | 2026-12-17 | 2026-02-20 | 2026-07-24
A28970 | Key Vendor Drawings / Data Approved | 2026-06-18 | 2026-06-24 | 2026-09-08 | 2026-09-14 | 2026-07-24 | 2026-07-31
A28980 | Purchase Order for Major Sub-ordered Materials | 2026-06-24 | 2026-07-01 | 2026-09-15 | 2026-09-21 | 2026-07-31 | 2026-08-07
A28990 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-07-01 | 2026-07-08 | 2026-09-22 | 2026-09-28 | 2026-08-07 | 2026-08-14
A29000 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-07-08 | 2026-07-13 | 2026-09-29 | 2026-10-04 | 2026-08-14 | 2026-08-19
A29010 | Manufacturing / Ex Works (India/UAE) | 2026-07-13 | 2026-08-12 | 2026-10-04 | 2026-11-03 | 2026-08-19 | 2026-08-29
A29020 | Complete Manufacturing & ready for Final Inspection | 2026-08-12 | 2026-08-19 | 2026-11-03 | 2026-11-09 | 2026-08-31 | 2026-09-04
A29030 | Materials Successfully Inspected, Tested / Ex Work | 2026-08-19 | 2026-08-27 | 2026-11-10 | 2026-11-17 | 2026-09-07 | 2026-09-14
A29040 | Delivery of Pipng Supports | 2026-08-27 | 2026-09-26 | 2026-11-18 | 2026-12-17 | 2026-09-15 | 2026-09-29
A33400 | Start Production | 2026-06-17 |  | 2026-09-08 |  | 2026-07-24
RigidStruts |  | 2026-05-18 | 2026-07-30 | 2026-10-23 | 2027-01-01
A63230 | Key Vendor Drawings / Data Approved | 2026-05-19 | 2026-05-25 | 2026-10-23 | 2026-10-29
A63240 | Manufacturing / Ex Works | 2026-06-09 | 2026-07-09 | 2026-11-14 | 2026-12-14
A63250 | Purchase Order for Major Sub-ordered Materials | 2026-05-25 | 2026-06-01 | 2026-10-30 | 2026-11-05
A63260 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-06-01 | 2026-06-08 | 2026-11-06 | 2026-11-12
A63270 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-06-08 | 2026-06-09 | 2026-11-13 | 2026-11-14
A63280 | Complete Manufacturing & ready for Final Inspection | 2026-07-09 | 2026-07-16 | 2026-12-14 | 2026-12-18
A63290 | Materials Successfully Inspected, Tested / Ex Work | 2026-07-16 | 2026-07-23 | 2026-12-21 | 2026-12-25
A63300 | Start Production | 2026-05-18 |  | 2026-10-23
A63310 | Delivery of Rigid Struts | 2026-07-23 | 2026-07-30 | 2026-12-26 | 2027-01-01
InsulatingGaskets |  | 2026-06-08 | 2026-10-29 | 2026-08-13 | 2027-01-01
InsulatingGaskets |  | 2026-06-08 | 2026-10-29 | 2026-08-13 | 2027-01-01
A62780 | Key Vendor Drawings / Data Approved | 2026-06-09 | 2026-06-29 | 2026-08-13 | 2026-09-02
A62790 | Manufacturing / Ex Works | 2026-08-04 | 2026-10-03 | 2026-10-09 | 2026-12-08
A62800 | Purchase Order for Major Sub-ordered Materials | 2026-06-29 | 2026-07-13 | 2026-09-03 | 2026-09-16
A62810 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-07-13 | 2026-08-03 | 2026-09-17 | 2026-10-07
A62820 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-08-03 | 2026-08-04 | 2026-10-08 | 2026-10-09
A62830 | Complete Manufacturing & ready for Final Inspection | 2026-10-05 | 2026-10-13 | 2026-12-08 | 2026-12-16
A62840 | Materials Successfully Inspected, Tested / Ex Work | 2026-10-14 | 2026-10-22 | 2026-12-17 | 2026-12-25
A62850 | Start Production | 2026-06-08 |  | 2026-08-13
A62860 | Delivery of Inuslating Gaskets | 2026-10-23 | 2026-10-29 | 2026-12-26 | 2027-01-01
HDPEPiping |  | 19-Mar-26 A | 2026-06-17 | 2026-09-03 | 2026-11-03 | 01-Aug-25 A | 19-Dec-25 A
HDPEPipingGF(FireWaterLines) |  | 19-Mar-26 A | 2026-06-17 | 2026-09-03 | 2026-11-03 | 01-Aug-25 A | 19-Dec-25 A
A28880 | Key Vendor Drawings / Data Approved | 20-Mar-26 A | 2026-04-22 | 2026-09-03 | 2026-09-08 | 2026-02-20 | 2026-03-19
A28890 | Purchase Order for Major Sub-ordered Materials | 23-Mar-26 A | 2026-04-28 | 2026-09-09 | 2026-09-14 | 2026-03-19 | 2026-03-26
A28900 | Major Sub-ordered Materials Received by Vendor and Verified | 25-Mar-26 A | 2026-05-04 | 2026-09-15 | 2026-09-18 | 2026-03-26 | 2026-04-16
A28910 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 01-Apr-26 A | 2026-05-05 | 2026-09-20 | 2026-09-21 | 2026-04-16 | 2026-04-17
A28920 | Manufacturing / Ex Works | 2026-05-05 | 2026-05-30 | 2026-09-21 | 2026-10-16 | 2026-04-17 | 2026-06-16
A28930 | Complete Manufacturing & ready for Final Inspection | 2026-06-01 | 2026-06-05 | 2026-10-16 | 2026-10-22 | 2026-06-16 | 2026-06-23
A28940 | Materials Successfully Inspected, Tested / Ex Work | 2026-06-08 | 2026-06-12 | 2026-10-23 | 2026-10-29 | 2026-06-23 | 2026-07-02
A28950 | Delivery of HDPE Piping GF (Fire Water Lines) | 2026-06-13 | 2026-06-17 | 2026-10-30 | 2026-11-03 | 2026-07-02 | 2026-07-16
A33390 | Start Production | 19-Mar-26 A |  | 2026-09-03 |  | 2026-02-20
GREPiping |  | 2026-04-17 | 2026-08-10 | 2026-09-03 | 2026-12-26
GREPiping |  | 2026-04-17 | 2026-08-10 | 2026-09-03 | 2026-12-26
A64450 | Key Vendor Drawings / Data Approved | 2026-04-17 | 2026-04-27 | 2026-09-03 | 2026-09-11
A64460 | Manufacturing / Ex Works (UAE) | 2026-05-16 | 2026-07-07 | 2026-10-03 | 2026-11-24
A64470 | Purchase Order for Major Sub-ordered Materials | 2026-04-27 | 2026-05-06 | 2026-09-14 | 2026-09-22
A64480 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-05-06 | 2026-05-15 | 2026-09-23 | 2026-10-01
A64490 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-05-15 | 2026-05-16 | 2026-10-02 | 2026-10-03
A64500 | Complete Manufacturing & ready for Final Inspection | 2026-07-07 | 2026-07-16 | 2026-11-24 | 2026-12-02
A64510 | Materials Successfully Inspected, Tested / Ex Work | 2026-07-16 | 2026-07-27 | 2026-12-03 | 2026-12-11
A64520 | Start Production | 2026-04-17 |  | 2026-09-03
A64530 | Delivery of GRE Piping | 2026-07-27 | 2026-08-10 | 2026-12-13 | 2026-12-26
PipingSPItems(strainer,filters) |  | 20-Mar-26 A | 2026-09-29 | 2026-07-20 | 2027-01-01 | 23-Jan-26 A | 2026-04-09
SpecializedItems(OrificeFlanges)CS300#1"-6"=08Nos |  | 20-Mar-26 A | 2026-09-29 | 2026-07-20 | 2027-01-01 | 2026-02-20 | 2026-04-01
A30230 | Key Vendor Drawings / Data Approved | 2026-04-17 | 2026-05-07 | 2026-07-20 | 2026-08-07 | 2026-04-01 | 2026-04-22
A30240 | Purchase Order for Major Sub-ordered Materials | 2026-05-07 | 2026-05-14 | 2026-08-10 | 2026-08-14 | 2026-04-22 | 2026-04-29
A30250 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-05-14 | 2026-06-04 | 2026-08-17 | 2026-09-04 | 2026-04-29 | 2026-05-20
A30260 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-06-04 | 2026-06-05 | 2026-09-05 | 2026-09-06 | 2026-05-20 | 2026-05-21
A30270 | Manufacturing / Ex Works (India/UAE) | 2026-06-05 | 2026-08-19 | 2026-09-06 | 2026-11-20 | 2026-05-21 | 2026-08-04
A30280 | Complete Manufacturing & ready for Final Inspection | 2026-08-19 | 2026-08-27 | 2026-11-20 | 2026-11-27 | 2026-08-04 | 2026-08-11
A30290 | Materials Successfully Inspected, Tested / Ex Work | 2026-08-27 | 2026-09-04 | 2026-11-30 | 2026-12-07 | 2026-08-11 | 2026-08-18
A30300 | Delivery of Orifice Flanges | 2026-09-04 | 2026-09-29 | 2026-12-08 | 2027-01-01 | 2026-08-18 | 2026-09-01
A33720 | Start Production | 20-Mar-26 A |  | 2026-07-20 |  | 2026-04-01
SpecializedItems(Strainer/Filter)CS&SS150#-300#2"-26"=08Nos |  | 20-Mar-26 A | 2026-09-28 | 2026-07-22 | 2027-01-01 | 23-Jan-26 A | 2026-04-09
A30320 | Key Vendor Drawings / Data Approved | 20-Mar-26 A | 31-Mar-26 A | 2026-07-22 | 2026-07-22 | 2026-03-30 | 2026-04-24
A30330 | Purchase Order for Major Sub-ordered Materials | 25-Mar-26 A | 10-Apr-26 A | 2026-07-22 | 2026-07-22 | 2026-04-24 | 2026-05-01
A30340 | Major Sub-ordered Materials Received by Vendor and Verified | 01-Apr-26 A | 17-Apr-26 A | 2026-07-22 | 2026-07-22 | 2026-05-01 | 2026-05-29
A30350 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-04-17 | 2026-04-17 | 2026-07-22 | 2026-07-23 | 2026-05-29 | 2026-05-30
A30360 | Manufacturing / Ex Works (India/UAE) | 2026-04-18 | 2026-08-15 | 2026-07-23 | 2026-11-20 | 2026-05-30 | 2026-07-25
A30370 | Complete Manufacturing & ready for Final Inspection | 2026-08-17 | 2026-08-24 | 2026-11-20 | 2026-11-27 | 2026-07-27 | 2026-07-31
A30380 | Materials Successfully Inspected, Tested / Ex Work | 2026-08-25 | 2026-08-31 | 2026-11-30 | 2026-12-04 | 2026-08-03 | 2026-08-07
A30390 | Delivery of Strainer/Filters Flanges | 2026-09-01 | 2026-09-28 | 2026-12-05 | 2027-01-01 | 2026-08-08 | 2026-09-04
A33730 | Start Production | 20-Mar-26 A |  | 2026-07-22 |  | 2026-03-27
FlameArrestor |  | 17-Apr-26 A | 2026-09-15 | 2026-08-10 | 2027-01-06
FlameArrestor |  | 17-Apr-26 A | 2026-09-15 | 2026-08-10 | 2027-01-06
A63500 | Key Vendor Drawings / Data Approved | 2026-04-17 | 2026-04-30 | 2026-08-10 | 2026-08-21
A63510 | Manufacturing / Ex Works | 2026-05-29 | 2026-08-12 | 2026-09-20 | 2026-12-04
A63520 | Purchase Order for Major Sub-ordered Materials | 2026-04-30 | 2026-05-14 | 2026-08-24 | 2026-09-04
A63530 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-05-14 | 2026-05-28 | 2026-09-07 | 2026-09-18
A63540 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-05-28 | 2026-05-29 | 2026-09-19 | 2026-09-20
A63550 | Complete Manufacturing & ready for Final Inspection | 2026-08-12 | 2026-08-21 | 2026-12-04 | 2026-12-14
A63560 | Materials Successfully Inspected, Tested / Ex Work | 2026-08-21 | 2026-09-01 | 2026-12-15 | 2026-12-23
A63570 | Start Production | 17-Apr-26 A |  | 2026-08-10
A63580 | Delivery of Flame Arrestors | 2026-09-01 | 2026-09-15 | 2026-12-24 | 2027-01-06
Pressure/Temperature/LevelInstruments,Flowmeters |  | 20-Dec-25 A | 2026-09-29 | 2026-07-17 | 2026-12-30 | 18-Apr-25 A | 2026-03-25
PT,TT&DPT[PT50Nos,TT33Nos,DPT20Nos] |  | 20-Dec-25 A | 2026-09-29 | 2026-07-17 | 2026-12-30 | 18-Apr-25 A | 2026-03-23
A29510 | Key Vendor Drawings / Data Approved | 2026-04-17 | 2026-05-07 | 2026-07-17 | 2026-08-06 | 2026-02-20 | 2026-03-19
A29520 | Purchase Order for Major Sub-ordered Materials | 2026-05-07 | 2026-06-04 | 2026-08-07 | 2026-09-03 | 2026-03-19 | 2026-04-16
A29530 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-06-04 | 2026-06-26 | 2026-09-04 | 2026-09-25 | 2026-04-16 | 2026-05-14
A29540 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-06-26 | 2026-06-27 | 2026-09-27 | 2026-09-28 | 2026-05-14 | 2026-05-15
A29550 | Manufacturing / Ex Works (India/UAE) | 2026-06-27 | 2026-08-26 | 2026-09-28 | 2026-11-27 | 2026-05-15 | 2026-07-14
A29560 | Complete Manufacturing & ready for Final Inspection | 2026-08-26 | 2026-09-04 | 2026-11-27 | 2026-12-07 | 2026-07-14 | 2026-08-04
A29570 | Materials Successfully Inspected, Tested / Ex Work | 2026-09-04 | 2026-09-15 | 2026-12-08 | 2026-12-16 | 2026-08-04 | 2026-08-25
A33510 | Start Production | 20-Dec-25 A |  | 2026-07-17 |  | 20-Dec-25 A
A33520 | Delivery of Material in Warehouse for PT,TT & DPT | 2026-09-15 | 2026-09-29 | 2026-12-17 | 2026-12-30 | 2026-08-25 | 2026-09-02
Rotameter |  | 17-Apr-26 A | 2026-07-30 | 2026-09-28 | 2027-01-11
Rotameter |  | 17-Apr-26 A | 2026-07-30 | 2026-09-28 | 2027-01-11
A63410 | Key Vendor Drawings / Data Approved | 2026-04-17 | 2026-04-23 | 2026-09-28 | 2026-10-02
A63420 | Manufacturing / Ex Works | 2026-05-08 | 2026-07-07 | 2026-10-19 | 2026-12-18
A63430 | Purchase Order for Major Sub-ordered Materials | 2026-04-23 | 2026-04-30 | 2026-10-05 | 2026-10-09
A63440 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-04-30 | 2026-05-07 | 2026-10-12 | 2026-10-16
A63450 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-05-07 | 2026-05-08 | 2026-10-18 | 2026-10-19
A63460 | Complete Manufacturing & ready for Final Inspection | 2026-07-07 | 2026-07-15 | 2026-12-18 | 2026-12-25
A63470 | Materials Successfully Inspected, Tested / Ex Work | 2026-07-15 | 2026-07-23 | 2026-12-28 | 2027-01-04
A63480 | Start Production | 17-Apr-26 A |  | 2026-09-28
A63490 | Delivery of Rotameter | 2026-07-23 | 2026-07-30 | 2027-01-05 | 2027-01-11
InstrumentBulkMaterial |  | 24-May-25 A | 2026-09-30 | 2026-06-15 | 2027-01-28 | 01-Feb-25 A | 2026-03-12
Gauges(PG,TG,PDG)PG-10bar&40bar=19Nos,DP=05Nos,TG=09Nos |  | 20-Mar-26 A | 2026-08-30 | 2026-08-15 | 2026-12-30 | 15-Aug-25 A | 2026-03-25
A32840 | Key Vendor Drawings / Data Approved | 20-Mar-26 A | 31-Mar-26 A | 2026-08-15 | 2026-08-15 | 2026-03-25 | 2026-04-23
A32850 | Purchase Order for Major Sub-ordered Materials | 25-Mar-26 A | 08-Apr-26 A | 2026-08-15 | 2026-08-15 | 2026-04-23 | 2026-05-14
A32860 | Major Sub-ordered Materials Received by Vendor and Verified | 01-Apr-26 A | 17-Apr-26 A | 2026-08-15 | 2026-08-15 | 2026-05-14 | 2026-06-04
A32870 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-04-17 | 2026-04-23 | 2026-08-15 | 2026-08-22 | 2026-06-04 | 2026-06-11
A32880 | Manufacturing / Ex Works (India/UAE) | 2026-04-24 | 2026-07-27 | 2026-08-22 | 2026-11-25 | 2026-06-11 | 2026-07-21
A32890 | Complete Manufacturing & ready for Final Inspection | 2026-07-28 | 2026-08-05 | 2026-11-25 | 2026-12-03 | 2026-07-21 | 2026-07-30
A32900 | Materials Successfully Inspected, Tested / Ex Work | 2026-08-06 | 2026-08-14 | 2026-12-04 | 2026-12-14 | 2026-07-30 | 2026-08-10
A34340 | Start Production | 20-Mar-26 A |  | 2026-08-15 |  | 2026-03-25
A34350 | Delivery of Magnetic Level Gauges, PG, TG, PDG | 2026-08-15 | 2026-08-30 | 2026-12-15 | 2026-12-30 | 2026-08-10 | 2026-08-24
Analyzers |  | 24-May-25 A | 12-Jul-25 A | 2027-01-28 | 2027-01-28 | 24-May-25 A | 12-Jul-25 A
A57650 | Start Production | 24-May-25 A |  | 2027-01-28 |  | 24-May-25 A
A57660 | Key Vendor Drawings / Data Approved | 25-May-25 A | 31-May-25 A | 2027-01-28 | 2027-01-28 | 25-May-25 A | 31-May-25 A
A57670 | Purchase Order for Major Sub-ordered Materials | 01-Jun-25 A | 07-Jun-25 A | 2027-01-28 | 2027-01-28 | 01-Jun-25 A | 07-Jun-25 A
A57680 | Major Sub-ordered Materials Received by Vendor and Verified | 07-Jun-25 A | 14-Jun-25 A | 2027-01-28 | 2027-01-28 | 07-Jun-25 A | 14-Jun-25 A
A57690 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 15-Jun-25 A | 21-Jun-25 A | 2027-01-28 | 2027-01-28 | 15-Jun-25 A | 21-Jun-25 A
A57700 | Manufacturing / Ex Works (India/UAE) | 22-Jun-25 A | 28-Jun-25 A | 2027-01-28 | 2027-01-28 | 22-Jun-25 A | 28-Jun-25 A
A57710 | Complete Manufacturing & ready for Final Inspection | 29-Jun-25 A | 05-Jul-25 A | 2027-01-28 | 2027-01-28 | 29-Jun-25 A | 05-Jul-25 A
A57720 | Materials Successfully Inspected, Tested / Ex Work | 29-Jun-25 A | 05-Jul-25 A | 2027-01-28 | 2027-01-28 | 29-Jun-25 A | 05-Jul-25 A
A57730 | Delivery of Material in Warehouse for Analyzer | 06-Jul-25 A | 12-Jul-25 A | 2027-01-28 | 2027-01-28 | 06-Jul-25 A | 12-Jul-25 A
FlowElementsVenturi |  | 20-Mar-26 A | 2026-09-30 | 2026-07-23 | 2027-01-05 | 01-Jun-25 A | 11-Dec-25 A
A57830 | Key Vendor Drawings / Data Approved | 20-Mar-26 A | 31-Mar-26 A | 2026-07-23 | 2026-07-23 | 2026-02-20 | 2026-03-20
A57840 | Manufacturing / Ex Works (India/UAE) | 2026-04-17 | 2026-08-04 | 2026-07-23 | 2026-11-10 | 2026-04-27 | 2026-07-26
A57850 | Purchase Order for Major Sub-ordered Materials | 01-Apr-26 A | 07-Apr-26 A | 2026-07-23 | 2026-07-23 | 11-Dec-25 A | 2026-03-20
A57860 | Major Sub-ordered Materials Received by Vendor and Verified | 05-Apr-26 A | 10-Apr-26 A | 2026-07-23 | 2026-07-23 | 2026-03-20 | 2026-04-20
A57870 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 08-Apr-26 A | 17-Apr-26 A | 2026-07-23 | 2026-07-23 | 2026-04-20 | 2026-04-27
A57880 | Complete Manufacturing & ready for Final Inspection | 2026-08-05 | 2026-08-18 | 2026-11-10 | 2026-11-23 | 2026-07-27 | 2026-08-04
A57890 | Materials Successfully Inspected, Tested / Ex Work | 2026-08-19 | 2026-08-31 | 2026-11-24 | 2026-12-04 | 2026-08-05 | 2026-08-13
A57900 | Start Production | 20-Mar-26 A |  | 2026-07-23 |  | 2026-02-20
A57910 | Delivery of Material in Warehouse for Flow Elements Venturi | 2026-09-01 | 2026-09-30 | 2026-12-07 | 2027-01-05 | 2026-08-14 | 2026-08-27
FlowElementsOrifice |  | 18-Dec-25 A | 2026-09-30 | 2026-07-23 | 2027-01-05 | 01-May-25 A | 2026-03-25
A57740 | Start Production | 18-Dec-25 A |  | 2026-07-23 |  | 18-Dec-25 A
A57750 | Key Vendor Drawings / Data Approved | 18-Dec-25 A | 08-Jan-26 A | 2026-07-23 | 2026-07-23 | 18-Dec-25 A | 08-Jan-26 A
A57760 | Purchase Order for Major Sub-ordered Materials | 09-Jan-26 A | 22-Jan-26 A | 2026-07-23 | 2026-07-23 | 09-Jan-26 A | 22-Jan-26 A
A57770 | Major Sub-ordered Materials Received by Vendor and Verified | 23-Jan-26 A | 31-Jan-26 A | 2026-07-23 | 2026-07-23 | 23-Jan-26 A | 31-Jan-26 A
A57780 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 01-Feb-26 A | 31-Mar-26 A | 2026-07-23 | 2026-07-23 | 01-Feb-26 A | 2026-02-24
A57790 | Manufacturing / Ex Works (India/UAE) | 2026-04-17 | 2026-08-04 | 2026-07-23 | 2026-11-10 | 2026-03-25 | 2026-06-23
A57800 | Complete Manufacturing & ready for Final Inspection | 2026-08-05 | 2026-08-18 | 2026-11-10 | 2026-11-23 | 2026-06-23 | 2026-07-02
A57810 | Materials Successfully Inspected, Tested / Ex Work | 2026-08-19 | 2026-08-31 | 2026-11-24 | 2026-12-04 | 2026-07-02 | 2026-07-13
A57820 | Delivery of Material in Warehouse for Flow Elements Orifice | 2026-09-01 | 2026-09-30 | 2026-12-07 | 2027-01-05 | 2026-07-13 | 2026-07-25
CableTrayandInstrumentJunctionBox(PerforatedCabletrayHeavyduty=5982Mtrs,JBs=73Nos) |  | 2026-04-17 | 2026-08-31 | 2026-08-31 | 2027-01-11 | 20-Jul-25 A | 2026-03-12
A29420 | Key Vendor Drawings / Data Approved | 2026-04-17 | 2026-05-07 | 2026-08-31 | 2026-09-18 | 2026-02-27 | 2026-04-23
A29430 | Purchase Order for Major Sub-ordered Materials | 2026-05-07 | 2026-05-18 | 2026-09-21 | 2026-09-29 | 2026-04-23 | 2026-05-04
A29440 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-05-18 | 2026-06-08 | 2026-09-30 | 2026-10-20 | 2026-05-04 | 2026-06-15
A29450 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-06-08 | 2026-06-09 | 2026-10-21 | 2026-10-22 | 2026-06-15 | 2026-06-16
A29460 | Manufacturing / Ex Works (India/UAE) | 2026-06-09 | 2026-08-08 | 2026-10-22 | 2026-12-21 | 2026-06-16 | 2026-08-15
A29470 | Complete Manufacturing & ready for Final Inspection | 2026-08-10 | 2026-08-13 | 2026-12-21 | 2026-12-24 | 2026-08-17 | 2026-08-25
A29480 | Materials Successfully Inspected, Tested / Ex Work | 2026-08-14 | 2026-08-24 | 2026-12-25 | 2027-01-04 | 2026-08-26 | 2026-09-03
A33490 | Start Production | 2026-04-17 |  | 2026-08-31 |  | 2026-02-26
A33500 | Delivery of Material in Warehouse for Cable Tray and Instrument Junction Box | 2026-08-25 | 2026-08-31 | 2027-01-05 | 2027-01-11 | 2026-09-04 | 2026-09-24
FibreOpticCable(Armoured,Telecom/IT/MAS) |  | 18-Aug-25 A | 20-Mar-26 A | 2026-06-15 | 2026-11-18 | 01-Jun-25 A | 18-Aug-25 A
A32750 | Key Vendor Drawings / Data Approved | 21-Nov-25 A | 10-Dec-25 A | 2026-06-15 | 2026-06-15 | 21-Nov-25 A | 10-Dec-25 A
A32760 | Purchase Order for Major Sub-ordered Materials | 11-Dec-25 A | 19-Dec-25 A | 2026-11-18 | 2026-11-18 | 11-Dec-25 A | 19-Dec-25 A
A32770 | Major Sub-ordered Materials Received by Vendor and Verified | 19-Dec-25 A | 26-Dec-25 A | 2026-11-18 | 2026-11-18 | 19-Dec-25 A | 26-Dec-25 A
A32780 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 25-Dec-25 A | 16-Jan-26 A | 2026-11-18 | 2026-11-18 | 25-Dec-25 A | 16-Jan-26 A
A32790 | Manufacturing / Ex Works (India/UAE) | 25-Dec-25 A | 23-Jan-26 A | 2026-11-18 | 2026-11-18 | 25-Dec-25 A | 23-Jan-26 A
A32800 | Complete Manufacturing & ready for Final Inspection | 10-Mar-26 A | 20-Mar-26 A | 2026-11-18 | 2026-11-18 | 2026-02-20 | 2026-03-02
A32810 | Materials Successfully Inspected, Tested / Ex Work | 09-Mar-26 A | 20-Mar-26 A | 2026-11-18 | 2026-11-18 | 2026-03-03 | 2026-03-11
A34320 | Start Production | 18-Aug-25 A |  | 2026-06-15 |  | 18-Aug-25 A
A34330 | Delivery of Fibre Optic Cable | 01-Mar-26 A | 20-Mar-26 A | 2026-11-18 | 2026-11-18 | 2026-03-12 | 2026-03-25
MagneticLevelGauge(09Nos) |  | 20-Mar-26 A | 2026-09-30 | 2026-07-17 | 2026-12-30 | 18-Jul-25 A | 2026-02-26
A29780 | Key Vendor Drawings / Data Approved | 20-Mar-26 A | 01-Apr-26 A | 2026-07-17 | 2026-07-17 | 2026-02-27 | 2026-03-27
A29790 | Purchase Order for Major Sub-ordered Materials | 01-Apr-26 A | 10-Apr-26 A | 2026-07-17 | 2026-07-17 | 2026-03-27 | 2026-04-10
A29800 | Major Sub-ordered Materials Received by Vendor and Verified | 11-Apr-26 A | 17-Apr-26 A | 2026-07-17 | 2026-07-17 | 2026-04-10 | 2026-05-11
A29810 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-04-17 | 2026-04-17 | 2026-07-17 | 2026-07-18 | 2026-05-11 | 2026-05-18
A29820 | Manufacturing / Ex Works (India/UAE) | 2026-04-18 | 2026-08-20 | 2026-07-18 | 2026-11-20 | 2026-05-18 | 2026-07-27
A29830 | Complete Manufacturing & ready for Final Inspection | 2026-08-21 | 2026-08-31 | 2026-11-20 | 2026-11-30 | 2026-07-27 | 2026-08-05
A29840 | Materials Successfully Inspected, Tested / Ex Work | 2026-09-01 | 2026-09-09 | 2026-12-01 | 2026-12-09 | 2026-08-05 | 2026-08-14
A33570 | Start Production | 20-Mar-26 A |  | 2026-07-17 |  | 2026-02-26
A33580 | Delivery of Material in Warehouse for Magnetic Level Gauge | 2026-09-10 | 2026-09-30 | 2026-12-10 | 2026-12-30 | 2026-08-14 | 2026-09-04
InstrumentBulkMaterial(Single&Multicore=Approx.78,130Mtr,FOCablesJB&CableTrays)) |  | 20-Mar-26 A | 2026-08-31 | 2026-07-26 | 2026-12-09 | 11-Dec-25 A | 2026-05-22
A27890 | Key Vendor Drawings / Data Approved | 20-Mar-26 A | 01-Apr-26 A | 2026-07-26 | 2026-07-26 | 2026-02-20 | 2026-03-19
A27900 | Purchase Order for Major Sub-ordered Materials | 01-Apr-26 A | 16-Apr-26 A | 2026-07-26 | 2026-07-26 | 11-Dec-25 A | 2026-03-19
A27910 | Major Sub-ordered Materials Received by Vendor and Verified | 10-Apr-26 A | 17-Apr-26 A | 2026-07-26 | 2026-07-26 | 2026-03-19 | 2026-03-26
A27920 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-04-17 | 2026-04-17 | 2026-07-26 | 2026-07-27 | 2026-03-26 | 2026-03-27
A27930 | Manufacturing / Ex Works (India/UAE) | 2026-04-18 | 2026-07-26 | 2026-07-27 | 2026-11-04 | 2026-03-27 | 2026-04-17
A27940 | Complete Manufacturing & ready for Final Inspection | 2026-07-27 | 2026-07-31 | 2026-11-04 | 2026-11-10 | 2026-04-17 | 2026-04-24
A27950 | Materials Successfully Inspected, Tested / Ex Work | 2026-08-03 | 2026-08-10 | 2026-11-11 | 2026-11-18 | 2026-04-24 | 2026-05-01
A34460 | Delivery of Material in Warehouse Instrument Bulk (Post TA) | 2026-08-11 | 2026-08-31 | 2026-11-19 | 2026-12-09 | 2026-05-01 | 2026-05-22
A34470 | Start Production | 20-Mar-26 A |  | 2026-07-26 |  | 2026-02-20
Earthing&PowerCables |  | 05-Nov-25 A | 2026-07-30 | 2026-09-05 | 2026-12-19 | 18-Jul-25 A | 24-Oct-25 A
EarthingandPowerCables |  | 05-Nov-25 A | 2026-07-30 | 2026-09-05 | 2026-12-19 | 18-Jul-25 A | 24-Oct-25 A
A28340 | Key Vendor Drawings / Data Approved | 24-Jan-26 A | 30-Jan-26 A | 2026-09-05 | 2026-09-05 | 24-Jan-26 A | 30-Jan-26 A
A28350 | Purchase Order for Major Sub-ordered Materials | 31-Jan-26 A | 12-Feb-26 A | 2026-09-05 | 2026-09-05 | 31-Jan-26 A | 12-Feb-26 A
A28360 | Major Sub-ordered Materials Received by Vendor and Verified | 13-Feb-26 A | 27-Feb-26 A | 2026-09-05 | 2026-09-05 | 13-Feb-26 A | 2026-03-10
A28370 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 04-Mar-26 A | 13-Mar-26 A | 2026-09-05 | 2026-09-05 | 2026-03-11 | 2026-03-17
A28380 | Manufacturing / Ex Works (India/UAE) | 17-Mar-26 A | 2026-06-23 | 2026-09-05 | 2026-11-12 | 2026-03-18 | 2026-06-15
A28390 | Complete Manufacturing & ready for Final Inspection | 01-Apr-26 A | 2026-06-30 | 2026-11-12 | 2026-11-19 | 2026-06-16 | 2026-06-24
A28400 | Materials Successfully Inspected, Tested / Ex Work | 10-Apr-26 A | 2026-07-09 | 2026-11-19 | 2026-11-27 | 2026-06-25 | 2026-07-03
A33310 | Start Production | 05-Nov-25 A |  | 2026-09-05 |  | 05-Nov-25 A
A33320 | Delivery of Earthing and Power Cables | 2026-07-09 | 2026-07-30 | 2026-11-29 | 2026-12-19 | 2026-07-04 | 2026-07-17
TelecomCables |  | 02-Mar-26 A | 2026-10-10 | 2026-08-17 | 2027-02-07
TelecomCables |  | 02-Mar-26 A | 2026-10-10 | 2026-08-17 | 2027-02-07
A62690 | Key Vendor Drawings / Data Approved | 2026-04-17 | 2026-05-07 | 2026-08-17 | 2026-09-04
A62700 | Manufacturing / Ex Works (India/UAE) | 2026-06-12 | 2026-09-05 | 2026-10-12 | 2027-01-05
A62710 | Purchase Order for Major Sub-ordered Materials | 2026-05-07 | 2026-05-21 | 2026-09-07 | 2026-09-18
A62720 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-05-21 | 2026-06-11 | 2026-09-21 | 2026-10-09
A62730 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-06-11 | 2026-06-12 | 2026-10-11 | 2026-10-12
A62740 | Complete Manufacturing & ready for Final Inspection | 2026-09-07 | 2026-09-15 | 2027-01-05 | 2027-01-13
A62750 | Materials Successfully Inspected, Tested / Ex Work | 2026-09-16 | 2026-09-24 | 2027-01-14 | 2027-01-22
A62760 | Start Production | 02-Mar-26 A |  | 2026-08-17
A62770 | Delivery of Telecom Cables | 2026-09-25 | 2026-10-10 | 2027-01-23 | 2027-02-07
ElectricalBulk |  | 03-Oct-25 A | 2026-09-24 | 2026-08-23 | 2026-12-30 | 15-Jan-25 A | 2026-05-29
CableTrays,JBs,ConduitPipe,CableLugs,etc |  | 2026-06-17 | 2026-08-31 | 2026-09-25 | 2026-12-08 | 2026-02-20 | 2026-05-13
A29150 | Key Vendor Drawings / Data Approved | 2026-06-18 | 2026-07-01 | 2026-09-25 | 2026-10-09 | 2026-05-14 | 2026-06-10
A29160 | Purchase Order for Major Sub-ordered Materials | 2026-07-01 | 2026-07-08 | 2026-10-09 | 2026-10-16 | 2026-06-10 | 2026-06-17
A29170 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-07-08 | 2026-07-15 | 2026-10-16 | 2026-10-23 | 2026-06-17 | 2026-06-24
A29180 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-07-15 | 2026-07-16 | 2026-10-23 | 2026-10-24 | 2026-06-24 | 2026-06-25
A29190 | Manufacturing / Ex Works (India/UAE) | 2026-07-16 | 2026-08-10 | 2026-10-24 | 2026-11-18 | 2026-06-25 | 2026-07-20
A29200 | Complete Manufacturing & ready for Final Inspection | 2026-08-10 | 2026-08-17 | 2026-11-18 | 2026-11-24 | 2026-07-20 | 2026-07-27
A29210 | Materials Successfully Inspected, Tested / Ex Work | 2026-08-17 | 2026-08-24 | 2026-11-25 | 2026-12-01 | 2026-07-27 | 2026-08-03
A33430 | Start Production | 2026-06-17 |  | 2026-09-25 |  | 2026-05-13
A33440 | Delivery of Material in Warehouse for Cable Trays, JBs, Conduit Pipe, Cable Lugs, etc | 2026-08-24 | 2026-08-31 | 2026-12-02 | 2026-12-08 | 2026-08-03 | 2026-08-17
PowerCables(11kV&33kV) |  | 03-Oct-25 A | 2026-07-30 | 2026-08-26 | 2026-12-08 | 01-Aug-25 A | 03-Sep-25 A
A61450 | Power Cables | 10-Oct-25 A | 17-Oct-25 A | 2026-08-26 | 2026-08-26 | 10-Oct-25 A | 17-Oct-25 A
A61460 | Key Vendor Drawings / Data Approved | 03-Oct-25 A | 23-Oct-25 A | 2026-08-26 | 2026-08-26 | 03-Oct-25 A | 23-Oct-25 A
A61470 | Start Production | 24-Oct-25 A |  | 2026-08-26 |  | 24-Oct-25 A
A61480 | Purchase Order for Major Sub-ordered Materials | 17-Mar-26 A | 20-Mar-26 A | 2026-08-26 | 2026-08-26 | 2026-02-20 | 2026-02-26
A61490 | Major Sub-ordered Materials Received by Vendor and Verified | 19-Mar-26 A | 19-Mar-26 A | 2026-08-26 | 2026-08-26 | 2026-02-27 | 2026-03-05
A61500 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 20-Mar-26 A | 2026-04-28 | 2026-08-26 | 2026-09-07 | 2026-03-06 | 2026-03-06
A61510 | Manufacturing / Ex Works (India/UAE) | 01-Apr-26 A | 2026-06-12 | 2026-09-07 | 2026-10-22 | 2026-03-07 | 2026-03-31
A61520 | Complete Manufacturing & ready for Final Inspection | 05-Apr-26 A | 2026-06-23 | 2026-10-22 | 2026-10-30 | 2026-03-31 | 2026-04-07
A61530 | Materials Successfully Inspected, Tested / Ex Work | 2026-06-24 | 2026-06-30 | 2026-11-02 | 2026-11-06 | 2026-04-07 | 2026-04-14
A61540 | Delivery of Material in Warehouse for Cable Trays, JBs, Conduit Pipe, Cable Lugs, etc | 2026-07-01 | 2026-07-30 | 2026-11-09 | 2026-12-08 | 2026-04-14 | 2026-05-05
LCS&SnapSwitches |  | 2026-06-25 | 2026-09-24 | 2026-10-01 | 2026-12-30 | 2026-02-20 | 2026-05-29
A29330 | Key Vendor Drawings / Data Approved | 2026-06-26 | 2026-07-16 | 2026-10-01 | 2026-10-21 | 2026-06-01 | 2026-06-19
A29340 | Purchase Order for Major Sub-ordered Materials | 2026-07-16 | 2026-07-23 | 2026-10-21 | 2026-10-28 | 2026-06-19 | 2026-06-26
A29350 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-07-23 | 2026-08-06 | 2026-10-28 | 2026-11-11 | 2026-06-26 | 2026-07-10
A29360 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-08-06 | 2026-08-07 | 2026-11-11 | 2026-11-12 | 2026-07-10 | 2026-07-11
A29370 | Manufacturing / Ex Works (India/UAE) | 2026-08-07 | 2026-09-04 | 2026-11-12 | 2026-12-10 | 2026-07-11 | 2026-08-08
A29380 | Complete Manufacturing & ready for Final Inspection | 2026-09-04 | 2026-09-10 | 2026-12-10 | 2026-12-16 | 2026-08-10 | 2026-08-14
A29390 | Materials Successfully Inspected, Tested / Ex Work | 2026-09-11 | 2026-09-17 | 2026-12-17 | 2026-12-23 | 2026-08-14 | 2026-08-21
A33470 | Start Production | 2026-06-25 |  | 2026-10-01 |  | 2026-05-29
A33480 | Delivery of Material in Warehouse for LCS & snap Switches | 2026-09-18 | 2026-09-24 | 2026-12-24 | 2026-12-30 | 2026-08-21 | 2026-08-28
ElectricalBulkMaterial(Earthing,FO,PowerCables) |  | 21-Nov-25 A | 2026-07-30 | 2026-08-23 | 2026-12-06 | 21-Nov-25 A | 2026-07-28
A17930 | Start Production | 21-Nov-25 A |  | 2026-08-23 |  | 21-Nov-25 A
A27440 | Key Vendor Drawings / Data Approved | 21-Nov-25 A | 28-Nov-25 A | 2026-08-23 | 2026-08-23 | 21-Nov-25 A | 28-Nov-25 A
A27450 | Purchase Order for Major Sub-ordered Materials | 11-Dec-25 A | 19-Dec-25 A | 2026-08-23 | 2026-08-23 | 11-Dec-25 A | 19-Dec-25 A
A27460 | Major Sub-ordered Materials Received by Vendor and Verified | 11-Mar-26 A | 20-Mar-26 A | 2026-08-23 | 2026-08-23 | 2026-02-20 | 2026-04-02
A27470 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 20-Mar-26 A | 31-Mar-26 A | 2026-08-23 | 2026-08-23 | 2026-04-03 | 2026-04-03
A27480 | Manufacturing / Ex Works (India/UAE) | 01-Apr-26 A | 2026-06-20 | 2026-08-23 | 2026-10-27 | 2026-04-04 | 2026-06-17
A27490 | Complete Manufacturing & ready for Final Inspection | 01-Apr-26 A | 2026-06-30 | 2026-10-27 | 2026-11-04 | 2026-06-18 | 2026-06-26
A27500 | Materials Successfully Inspected, Tested / Ex Work | 2026-07-01 | 2026-07-09 | 2026-11-05 | 2026-11-13 | 2026-06-29 | 2026-07-07
A33300 | Delivery of Electrical Bulk Material (Earthing, FO, 11 KVA Cable) (Post TA) | 2026-07-10 | 2026-07-30 | 2026-11-16 | 2026-12-06 | 2026-07-08 | 2026-07-28
MainAutomationEquipment |  | 26-Feb-25 A | 2026-11-09 | 2026-06-16 | 2027-09-20 | 01-Feb-25 A | 2026-04-02
OnOffValve/ControlValves |  | 27-Oct-25 A | 2026-11-06 | 2026-07-13 | 2027-02-01 | 10-Apr-25 A | 20-Oct-25 A
ESDValves |  | 30-Oct-25 A | 2026-11-06 | 2026-07-13 | 2027-02-01 | 30-Oct-25 A | 2026-09-27
A59810 | Key Vendor Drawings / Data Approved | 20-Feb-26 A | 27-Feb-26 A | 2026-07-13 | 2026-07-13 | 2026-02-20 | 2026-04-23
A59820 | Manufacturing / Ex Works (India/UAE) | 2026-04-18 | 2026-10-04 | 2026-07-14 | 2026-12-31 | 2026-03-16 | 2026-09-02
A59830 | Purchase Order for Major Sub-ordered Materials | 11-Mar-26 A | 20-Mar-26 A | 2026-07-13 | 2026-07-13 | 2026-02-20 | 2026-02-28
A59840 | Major Sub-ordered Materials Received by Vendor and Verified | 28-Feb-26 A | 20-Mar-26 A | 2026-07-13 | 2026-07-13 | 2026-02-28 | 2026-03-25
A59850 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-04-17 | 2026-04-17 | 2026-07-13 | 2026-07-14 | 2026-03-15 | 2026-03-16
A59860 | Complete Manufacturing & ready for Final Inspection | 2026-10-05 | 2026-10-10 | 2026-12-31 | 2027-01-06 | 2026-09-02 | 2026-09-07
A59870 | Materials Successfully Inspected, Tested / Ex Work | 2026-10-10 | 2026-10-16 | 2027-01-06 | 2027-01-11 | 2026-09-07 | 2026-09-13
A59880 | Start Production | 30-Oct-25 A |  | 2026-07-13 |  | 30-Oct-25 A
A59890 | Delivery of Control Valves | 2026-10-16 | 2026-11-06 | 2027-01-12 | 2027-02-01 | 2026-09-13 | 2026-09-27
ControlValves(1"-24"Rating150,300&2500=32Nos)+SDV |  | 27-Oct-25 A | 2026-09-12 | 2026-08-04 | 2026-12-30 | 21-Apr-25 A | 20-Oct-25 A
A30410 | Key Vendor Drawings / Data Approved | 18-Dec-25 A | 20-Feb-26 A | 2026-08-04 | 2026-08-04 | 18-Dec-25 A | 20-Feb-26 A
A30420 | Purchase Order for Major Sub-ordered Materials | 15-Feb-26 A | 05-Mar-26 A | 2026-08-04 | 2026-08-04 | 15-Feb-26 A | 2026-03-05
A30430 | Major Sub-ordered Materials Received by Vendor and Verified | 20-Feb-26 A | 10-Mar-26 A | 2026-08-04 | 2026-08-04 | 2026-03-06 | 2026-04-16
A30440 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 20-Feb-26 A | 27-Feb-26 A | 2026-08-04 | 2026-08-04 | 2026-02-20 | 2026-02-26
A30450 | Manufacturing / Ex Works (India/UAE) | 19-Mar-26 A | 2026-08-08 | 2026-08-04 | 2026-11-25 | 2026-02-27 | 2026-07-08
A30460 | Complete Manufacturing & ready for Final Inspection | 2026-08-09 | 2026-08-15 | 2026-11-26 | 2026-12-02 | 2026-07-09 | 2026-07-14
A30470 | Materials Successfully Inspected, Tested / Ex Work | 2026-08-16 | 2026-08-22 | 2026-12-03 | 2026-12-09 | 2026-07-14 | 2026-07-20
A33740 | Start Production | 27-Oct-25 A |  | 2026-08-04 |  | 27-Oct-25 A
A33750 | Delivery of Control Valves | 2026-08-23 | 2026-09-12 | 2026-12-10 | 2026-12-30 | 2026-07-20 | 2026-08-10
MOVs |  | 02-Sep-25 A | 2026-07-30 | 2026-10-28 | 2027-02-10 | 21-Apr-25 A | 10-Sep-25 A
MOVs[BallType24"150#=01No] |  | 02-Sep-25 A | 2026-07-30 | 2026-10-28 | 2027-02-10 | 21-Apr-25 A | 10-Sep-25 A
A32660 | Key Vendor Drawings / Data Approved | 21-Nov-25 A | 10-Dec-25 A | 2026-10-28 | 2026-10-28 | 21-Nov-25 A | 10-Dec-25 A
A32670 | Purchase Order for Major Sub-ordered Materials | 10-Dec-25 A | 18-Dec-25 A | 2026-10-28 | 2026-10-28 | 10-Dec-25 A | 18-Dec-25 A
A32680 | Major Sub-ordered Materials Received by Vendor and Verified | 02-Mar-26 A | 20-Mar-26 A | 2026-10-28 | 2026-10-28 | 2026-02-20 | 2026-04-02
A32690 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 01-Mar-26 A | 20-Mar-26 A | 2026-10-28 | 2026-10-28 | 2026-04-03 | 2026-04-03
A32700 | Manufacturing / Ex Works (India/UAE) | 01-Apr-26 A | 2026-06-20 | 2026-10-28 | 2027-01-01 | 2026-04-04 | 2026-08-21
A32710 | Complete Manufacturing & ready for Final Inspection | 2026-06-22 | 2026-06-30 | 2027-01-01 | 2027-01-11 | 2026-08-24 | 2026-09-01
A32720 | Materials Successfully Inspected, Tested / Ex Work | 2026-07-01 | 2026-07-09 | 2027-01-12 | 2027-01-20 | 2026-09-02 | 2026-09-10
A34300 | Start Production | 02-Sep-25 A |  | 2026-10-28 |  | 02-Sep-25 A
A34310 | Delivery of MOVs | 2026-07-10 | 2026-07-30 | 2027-01-21 | 2027-02-10 | 2026-09-11 | 2026-09-24
MachineConditionMonitoringSystem(MCMS) |  | 25-May-25 A | 2026-05-22 | 2026-11-24 | 2026-12-27 | 01-Feb-25 A | 01-Jun-25 A
MachineConditionMonitoringSystem |  | 25-May-25 A | 2026-05-22 | 2026-11-24 | 2026-12-27 | 01-Apr-25 A | 01-Jun-25 A
A31940 | Key Vendor Drawings / Data Approved | 19-Dec-25 A | 19-Dec-25 A | 2026-11-24 | 2026-11-24 | 19-Dec-25 A | 19-Dec-25 A
A31950 | Purchase Order for Major Sub-ordered Materials | 20-Dec-25 A | 26-Dec-25 A | 2026-11-24 | 2026-11-24 | 20-Dec-25 A | 26-Dec-25 A
A31960 | Major Sub-ordered Materials Received by Vendor and Verified | 27-Dec-25 A | 02-Jan-26 A | 2026-11-24 | 2026-11-24 | 27-Dec-25 A | 02-Jan-26 A
A31970 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 01-Jan-26 A | 09-Jan-26 A | 2026-11-24 | 2026-11-24 | 01-Jan-26 A | 09-Jan-26 A
A31980 | Manufacturing / Ex Works (India/UAE) | 01-Mar-26 A | 2026-04-23 | 2026-11-24 | 2026-12-01 | 2026-02-20 | 2026-05-05
A31990 | Complete Manufacturing & ready for Final Inspection | 01-Apr-26 A | 2026-04-28 | 2026-12-01 | 2026-12-03 | 2026-05-06 | 2026-05-12
A32000 | Materials Successfully Inspected, Tested / Ex Work | 2026-04-28 | 2026-05-05 | 2026-12-04 | 2026-12-10 | 2026-05-13 | 2026-05-19
A34130 | Start Production | 25-May-25 A |  | 2026-11-24 |  | 25-May-25 A
A34140 | Delivery of MCMS | 2026-05-05 | 2026-05-22 | 2026-12-11 | 2026-12-27 | 2026-05-20 | 2026-06-05
IPCSModification(ABB) |  | 21-Mar-25 A | 2026-07-30 | 2026-06-16 | 2026-12-15 | 01-Feb-25 A | 25-Jul-25 A
TA_IntegratedProtectionandControlSystemBF-ABB/Hitachi |  | 21-Mar-25 A | 16-May-25 A | 2026-06-16 | 2026-06-16 | 21-Mar-25 A | 16-May-25 A
A27710 | Key Vendor Drawings / Data Approved | 21-Mar-25 A | 28-Mar-25 A | 2026-06-16 | 2026-06-16 | 21-Mar-25 A | 28-Mar-25 A
A27720 | Purchase Order for Major Sub-ordered Materials | 01-Apr-25 A | 04-Apr-25 A | 2026-06-16 | 2026-06-16 | 01-Apr-25 A | 04-Apr-25 A
A27730 | Major Sub-ordered Materials Received by Vendor and Verified | 05-Apr-25 A | 11-Apr-25 A | 2026-06-16 | 2026-06-16 | 05-Apr-25 A | 11-Apr-25 A
A27740 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 12-Apr-25 A | 18-Apr-25 A | 2026-06-16 | 2026-06-16 | 12-Apr-25 A | 18-Apr-25 A
A27750 | Manufacturing / Ex Works (India/UAE) | 19-Apr-25 A | 25-Apr-25 A | 2026-06-16 | 2026-06-16 | 19-Apr-25 A | 25-Apr-25 A
A27760 | Complete Manufacturing & ready for Final Inspection | 26-Apr-25 A | 02-May-25 A | 2026-06-16 | 2026-06-16 | 26-Apr-25 A | 02-May-25 A
A27770 | Materials Successfully Inspected, Tested / Ex Work | 03-May-25 A | 09-May-25 A | 2026-06-16 | 2026-06-16 | 03-May-25 A | 09-May-25 A
A27780 | Delivery of FOPP (02 Nos) | 10-May-25 A | 16-May-25 A | 2026-06-16 | 2026-06-16 | 10-May-25 A | 16-May-25 A
A34480 | Start Production | 21-Mar-25 A |  | 2026-06-16 |  | 21-Mar-25 A
IntegratedProtectionControlSystem |  | 25-Jul-25 A | 2026-07-30 | 2026-09-01 | 2026-12-15 | 25-Jul-25 A | 2026-07-31
A24030 | Start Production | 25-Jul-25 A |  | 2026-09-01 |  | 25-Jul-25 A
A31220 | Key Vendor Drawings / Data Approved | 10-Sep-25 A | 20-Dec-25 A | 2026-09-01 | 2026-09-01 | 10-Sep-25 A | 20-Dec-25 A
A31230 | Purchase Order for Major Sub-ordered Materials | 21-Dec-25 A | 27-Dec-25 A | 2026-09-01 | 2026-09-01 | 21-Dec-25 A | 27-Dec-25 A
A31240 | Major Sub-ordered Materials Received by Vendor and Verified | 28-Dec-25 A | 03-Jan-26 A | 2026-09-01 | 2026-09-01 | 28-Dec-25 A | 03-Jan-26 A
A31250 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 10-Jan-26 A | 13-Mar-26 A | 2026-09-01 | 2026-09-01 | 10-Jan-26 A | 2026-02-22
A31260 | Manufacturing / Ex Works (India/UAE) | 10-Mar-26 A | 2026-06-20 | 2026-09-01 | 2026-11-05 | 2026-02-22 | 2026-06-22
A31270 | Complete Manufacturing & ready for Final Inspection | 01-Apr-26 A | 2026-06-30 | 2026-11-05 | 2026-11-13 | 2026-06-22 | 2026-07-01
A31280 | Materials Successfully Inspected, Tested / Ex Work | 09-Apr-26 A | 2026-07-09 | 2026-11-16 | 2026-11-24 | 2026-07-01 | 2026-07-10
A33970 | Delivery of IPCS | 2026-07-10 | 2026-07-30 | 2026-11-25 | 2026-12-15 | 2026-07-10 | 2026-07-31
OTS |  | 13-Mar-25 A | 2026-10-10 | 2026-06-16 | 2027-09-20 | 01-Feb-25 A | 20-Aug-25 A
A64540 | Start Production | 17-Apr-26 A |  | 2027-03-29
A64550 | Key Vendor Drawings / Data Approved | 2026-04-17 | 2026-05-07 | 2027-03-29 | 2027-04-16
A64560 | Purchase Order for Major Sub-ordered Materials | 2026-05-07 | 2026-05-21 | 2027-04-19 | 2027-04-30
A64570 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-05-21 | 2026-06-11 | 2027-05-03 | 2027-05-21
A64580 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-06-11 | 2026-06-12 | 2027-05-23 | 2027-05-24
A64590 | Manufacturing / Ex Works (India/UAE) | 2026-06-12 | 2026-09-05 | 2027-05-24 | 2027-08-17
A64600 | Complete Manufacturing & ready for Final Inspection | 2026-09-07 | 2026-09-15 | 2027-08-17 | 2027-08-25
A64610 | Materials Successfully Inspected, Tested / Ex Work | 2026-09-16 | 2026-09-24 | 2027-08-26 | 2027-09-03
A64620 | Delivery of LV Bus Duct | 2026-09-25 | 2026-10-10 | 2027-09-05 | 2027-09-20
TA_SCMSSystem-Siemens |  | 13-Mar-25 A | 11-May-25 A | 2026-06-16 | 2026-06-16 | 13-Mar-25 A | 11-May-25 A
A27620 | Key Vendor Drawings / Data Approved | 13-Mar-25 A | 16-Mar-25 A | 2026-06-16 | 2026-06-16 | 13-Mar-25 A | 16-Mar-25 A
A27630 | Purchase Order for Major Sub-ordered Materials | 24-Mar-25 A | 30-Mar-25 A | 2026-06-16 | 2026-06-16 | 24-Mar-25 A | 30-Mar-25 A
A27640 | Major Sub-ordered Materials Received by Vendor and Verified | 31-Mar-25 A | 06-Apr-25 A | 2026-06-16 | 2026-06-16 | 31-Mar-25 A | 06-Apr-25 A
A27650 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 07-Apr-25 A | 13-Apr-25 A | 2026-06-16 | 2026-06-16 | 07-Apr-25 A | 13-Apr-25 A
A27660 | Manufacturing / Ex Works (India/UAE) | 14-Apr-25 A | 20-Apr-25 A | 2026-06-16 | 2026-06-16 | 14-Apr-25 A | 20-Apr-25 A
A27670 | Complete Manufacturing & ready for Final Inspection | 21-Apr-25 A | 27-Apr-25 A | 2026-06-16 | 2026-06-16 | 21-Apr-25 A | 27-Apr-25 A
A27680 | Materials Successfully Inspected, Tested / Ex Work | 28-Apr-25 A | 04-May-25 A | 2026-06-16 | 2026-06-16 | 28-Apr-25 A | 04-May-25 A
A27690 | Delivery of SCMS | 05-May-25 A | 11-May-25 A | 2026-06-16 | 2026-06-16 | 05-May-25 A | 11-May-25 A
A33290 | Start Production | 23-Mar-25 A |  | 2026-06-16 |  | 23-Mar-25 A
SCMSSystem |  | 23-May-25 A | 2026-07-30 | 2026-09-01 | 2026-12-15 | 23-May-25 A | 2026-09-16
A60100 | Start Production | 23-May-25 A |  | 2026-09-01 |  | 23-May-25 A
A60110 | Key Vendor Drawings / Data Approved | 06-Jan-26 A | 14-Jan-26 A | 2026-09-01 | 2026-09-01 | 06-Jan-26 A | 2026-03-20
A60120 | Manufacturing / Ex Works (India/UAE) | 18-Apr-26 A | 2026-06-20 | 2026-09-01 | 2026-11-05 | 2026-05-05 | 2026-08-13
A60130 | Purchase Order for Major Sub-ordered Materials | 01-Jan-26 A | 03-Jan-26 A | 2026-09-01 | 2026-09-01 | 2026-03-20 | 2026-04-03
A60140 | Major Sub-ordered Materials Received by Vendor and Verified | 15-Jan-26 A | 16-Jan-26 A | 2026-09-01 | 2026-09-01 | 2026-04-03 | 2026-05-04
A60150 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 17-Apr-26 A | 17-Apr-26 A | 2026-09-01 | 2026-09-01 | 2026-05-04 | 2026-05-05
A60160 | Complete Manufacturing & ready for Final Inspection | 2026-06-22 | 2026-06-30 | 2026-11-05 | 2026-11-13 | 2026-08-13 | 2026-08-24
A60170 | Materials Successfully Inspected, Tested / Ex Work | 2026-07-01 | 2026-07-09 | 2026-11-16 | 2026-11-24 | 2026-08-24 | 2026-09-02
A60180 | Delivery of SCMS | 2026-07-10 | 2026-07-30 | 2026-11-25 | 2026-12-15 | 2026-09-02 | 2026-09-16
ICSS(IntegratedControlandSafetySystem)includingsys.Modifications |  | 20-Mar-25 A | 2026-09-10 | 2026-06-16 | 2026-12-23 | 07-Feb-25 A | 20-Jun-25 A
TA_IntegratedControlandSafetySystemBF-Honeywell |  | 20-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 20-Mar-25 A | 17-May-25 A
A27530 | Key Vendor Drawings / Data Approved | 20-Mar-25 A | 29-Mar-25 A | 2026-06-16 | 2026-06-16 | 20-Mar-25 A | 29-Mar-25 A
A27540 | Purchase Order for Major Sub-ordered Materials | 29-Mar-25 A | 05-Apr-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 05-Apr-25 A
A27550 | Major Sub-ordered Materials Received by Vendor and Verified | 06-Apr-25 A | 12-Apr-25 A | 2026-06-16 | 2026-06-16 | 06-Apr-25 A | 12-Apr-25 A
A27560 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 13-Apr-25 A | 19-Apr-25 A | 2026-06-16 | 2026-06-16 | 13-Apr-25 A | 19-Apr-25 A
A27570 | Manufacturing / Ex Works (India/UAE) | 20-Apr-25 A | 26-Apr-25 A | 2026-06-16 | 2026-06-16 | 20-Apr-25 A | 26-Apr-25 A
A27580 | Complete Manufacturing & ready for Final Inspection | 27-Apr-25 A | 03-May-25 A | 2026-06-16 | 2026-06-16 | 27-Apr-25 A | 03-May-25 A
A27590 | Materials Successfully Inspected, Tested / Ex Work | 04-May-25 A | 10-May-25 A | 2026-06-16 | 2026-06-16 | 04-May-25 A | 10-May-25 A
A27600 | Delivery of loose Material for ICSS Modification | 11-May-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 11-May-25 A | 17-May-25 A
A33280 | Start Production | 22-Mar-25 A |  | 2026-06-16 |  | 22-Mar-25 A
IntegratedControlandSafetySystemGF |  | 20-Jun-25 A | 2026-09-10 | 2026-07-30 | 2026-12-23 | 15-May-25 A | 20-Jun-25 A
A31130 | Key Vendor Drawings / Data Approved | 05-Aug-25 A | 20-Dec-25 A | 2026-07-30 | 2026-07-30 | 05-Aug-25 A | 20-Dec-25 A
A31140 | Purchase Order for Major Sub-ordered Materials | 21-Dec-25 A | 27-Dec-25 A | 2026-07-30 | 2026-07-30 | 21-Dec-25 A | 27-Dec-25 A
A31150 | Major Sub-ordered Materials Received by Vendor and Verified | 27-Dec-25 A | 03-Jan-26 A | 2026-07-30 | 2026-07-30 | 27-Dec-25 A | 03-Jan-26 A
A31160 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 10-Jan-26 A | 13-Mar-26 A | 2026-07-30 | 2026-07-30 | 10-Jan-26 A | 2026-02-20
A31170 | Manufacturing / Ex Works (India/UAE) | 16-Mar-26 A | 2026-07-31 | 2026-07-30 | 2026-11-13 | 2026-02-20 | 2026-08-19
A31180 | Complete Manufacturing & ready for Final Inspection | 01-Apr-26 A | 2026-08-11 | 2026-11-13 | 2026-11-23 | 2026-08-19 | 2026-08-28
A31190 | Materials Successfully Inspected, Tested / Ex Work | 08-Apr-26 A | 2026-08-20 | 2026-11-24 | 2026-12-02 | 2026-08-28 | 2026-09-08
A33950 | Start Production | 20-Jun-25 A |  | 2026-07-30 |  | 20-Jun-25 A
A33960 | Delivery of Material in Warehouse ICSS | 2026-08-21 | 2026-09-10 | 2026-12-03 | 2026-12-23 | 2026-09-08 | 2026-09-29
InstrumentCables |  | 13-Mar-26 A | 2026-07-30 | 2026-09-15 | 2026-12-30 | 01-Nov-25 A | 2026-03-12
InstrumentCable(Single&Multicore=Approx.78,130Mtr) |  | 13-Mar-26 A | 2026-07-30 | 2026-09-15 | 2026-12-30 | 01-Nov-25 A | 2026-03-12
A29690 | Key Vendor Drawings / Data Approved | 2026-04-17 | 2026-04-27 | 2026-09-15 | 2026-09-23 | 2026-03-13 | 2026-04-23
A29700 | Purchase Order for Major Sub-ordered Materials | 2026-04-27 | 2026-05-06 | 2026-09-24 | 2026-10-02 | 2026-04-23 | 2026-05-07
A29710 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-05-06 | 2026-05-15 | 2026-10-05 | 2026-10-13 | 2026-05-07 | 2026-05-28
A29720 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-05-15 | 2026-05-16 | 2026-10-14 | 2026-10-15 | 2026-05-28 | 2026-05-29
A29730 | Manufacturing / Ex Works (India/UAE) | 2026-05-16 | 2026-07-05 | 2026-10-15 | 2026-12-04 | 2026-05-29 | 2026-08-12
A29740 | Complete Manufacturing & ready for Final Inspection | 2026-07-06 | 2026-07-14 | 2026-12-04 | 2026-12-14 | 2026-08-12 | 2026-08-21
A29750 | Materials Successfully Inspected, Tested / Ex Work | 2026-07-15 | 2026-07-23 | 2026-12-15 | 2026-12-23 | 2026-08-21 | 2026-09-01
A33550 | Start Production | 13-Mar-26 A |  | 2026-09-15 |  | 2026-03-12
A33560 | Delivery of Material in Warehouse for Instrument Cable | 2026-07-24 | 2026-07-30 | 2026-12-24 | 2026-12-30 | 2026-09-01 | 2026-09-08
LocalFireControlPanelincludingF&GDetectors |  | 12-Dec-25 A | 2026-10-30 | 2026-06-30 | 2027-01-12 | 12-Dec-25 A | 2026-07-27
FireDetectionAlarmSystemandLocalFireControlPanel(CleanAgentUnit) |  | 12-Dec-25 A | 2026-10-30 | 2026-06-30 | 2027-01-12 | 20-Jun-25 A | 12-Dec-25 A
A31760 | Key Vendor Drawings / Data Approved | 24-Jan-26 A | 16-Feb-26 A | 2026-06-30 | 2026-06-30 | 24-Jan-26 A | 2026-03-19
A31770 | Purchase Order for Major Sub-ordered Materials | 01-Feb-26 A | 14-Feb-26 A | 2026-06-30 | 2026-06-30 | 2026-03-19 | 2026-03-30
A31780 | Major Sub-ordered Materials Received by Vendor and Verified | 11-Feb-26 A | 28-Feb-26 A | 2026-06-30 | 2026-06-30 | 2026-03-30 | 2026-04-08
A31790 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 12-Feb-26 A | 18-Feb-26 A | 2026-06-30 | 2026-06-30 | 2026-04-08 | 2026-04-09
A31800 | Manufacturing / Ex Works | 01-Mar-26 A | 2026-09-10 | 2026-06-30 | 2026-11-24 | 2026-04-09 | 2026-06-23
A31810 | Complete Manufacturing & ready for Final Inspection | 26-Mar-26 A | 2026-09-21 | 2026-11-24 | 2026-12-02 | 2026-06-23 | 2026-07-02
A31820 | Materials Successfully Inspected, Tested / Ex Work | 2026-09-22 | 2026-09-30 | 2026-12-03 | 2026-12-11 | 2026-07-02 | 2026-07-13
A34090 | Start Production | 12-Dec-25 A |  | 2026-06-30 |  | 12-Dec-25 A
A34100 | Delivery of FDAS, LFCP, Clean Agent Unit | 2026-10-01 | 2026-10-30 | 2026-12-14 | 2027-01-12 | 2026-07-13 | 2026-07-27
PSVs |  | 01-Apr-26 A | 2026-11-09 | 2026-06-19 | 2027-01-11 | 15-Oct-25 A | 2026-03-25
PSVs(1"x2"upto8"x10"-CSRating150/150,300/150=22Nos) |  | 01-Apr-26 A | 2026-11-09 | 2026-06-19 | 2027-01-11 | 15-Oct-25 A | 2026-03-25
A29600 | Key Vendor Drawings / Data Approved | 2026-04-17 | 2026-05-28 | 2026-06-19 | 2026-07-30 | 2026-03-26 | 2026-05-06
A29610 | Purchase Order for Major Sub-ordered Materials | 2026-05-28 | 2026-06-11 | 2026-07-31 | 2026-08-13 | 2026-05-06 | 2026-05-15
A29620 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-06-11 | 2026-07-16 | 2026-08-14 | 2026-09-17 | 2026-05-15 | 2026-06-05
A29630 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-07-16 | 2026-07-16 | 2026-09-18 | 2026-09-18 | 2026-06-05 | 2026-06-05
A29640 | Manufacturing / Ex Works (India/UAE) | 2026-07-16 | 2026-09-29 | 2026-09-18 | 2026-12-02 | 2026-06-05 | 2026-08-19
A29650 | Complete Manufacturing & ready for Final Inspection | 2026-09-29 | 2026-10-08 | 2026-12-02 | 2026-12-10 | 2026-08-19 | 2026-08-28
A29660 | Materials Successfully Inspected, Tested / Ex Work | 2026-10-08 | 2026-10-19 | 2026-12-11 | 2026-12-21 | 2026-08-28 | 2026-09-08
A33530 | Start Production | 01-Apr-26 A |  | 2026-06-19 |  | 2026-03-25
A33540 | Delivery of Material in Warehouse for PSVs | 2026-10-19 | 2026-11-09 | 2026-12-22 | 2027-01-11 | 2026-09-08 | 2026-09-22
SamplingSystem |  | 26-Feb-25 A | 12-May-25 A | 2027-02-01 | 2027-02-01 | 12-Feb-25 A | 18-Mar-25 A
TA_SGMReplacement(AdditionalItem) |  | 26-Feb-25 A | 12-May-25 A | 2027-02-01 | 2027-02-01 | 12-Feb-25 A | 15-Mar-25 A
A37420 | Start Production | 17-Mar-25 A |  | 2027-02-01 |  | 17-Mar-25 A
A37430 | Key Vendor Drawings / Data Approved | 26-Feb-25 A | 24-Mar-25 A | 2027-02-01 | 2027-02-01 | 26-Feb-25 A | 24-Mar-25 A
A37440 | Purchase Order for Major Sub-ordered Materials | 25-Mar-25 A | 31-Mar-25 A | 2027-02-01 | 2027-02-01 | 25-Mar-25 A | 31-Mar-25 A
A37450 | Major Sub-ordered Materials Received by Vendor and Verified | 01-Apr-25 A | 07-Apr-25 A | 2027-02-01 | 2027-02-01 | 01-Apr-25 A | 07-Apr-25 A
A37460 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 08-Apr-25 A | 14-Apr-25 A | 2027-02-01 | 2027-02-01 | 08-Apr-25 A | 14-Apr-25 A
A37470 | Manufacturing / Ex Works (India/UAE) | 15-Apr-25 A | 21-Apr-25 A | 2027-02-01 | 2027-02-01 | 15-Apr-25 A | 21-Apr-25 A
A37480 | Complete Manufacturing & ready for Final Inspection | 22-Apr-25 A | 28-Apr-25 A | 2027-02-01 | 2027-02-01 | 22-Apr-25 A | 28-Apr-25 A
A37490 | Materials Successfully Inspected, Tested / Ex Work | 29-Apr-25 A | 05-May-25 A | 2027-02-01 | 2027-02-01 | 29-Apr-25 A | 05-May-25 A
A37500 | Delivery of Additional Material to be Procured | 06-May-25 A | 12-May-25 A | 2027-02-01 | 2027-02-01 | 06-May-25 A | 12-May-25 A
F&GFlameDetectors,MCP,Beacon,etc. |  | 13-Mar-26 A | 2026-10-09 | 2026-07-10 | 2027-01-01 | 2026-04-02 | 2026-09-02
F&GFlameDetectors,MCP,Beacon(Nos324) |  | 13-Mar-26 A | 2026-10-09 | 2026-07-10 | 2027-01-01 | 18-Jul-25 A | 2026-04-02
A32120 | Key Vendor Drawings / Data Approved | 2026-04-17 | 2026-05-07 | 2026-07-10 | 2026-07-30 | 2026-04-02 | 2026-04-23
A32130 | Purchase Order for Major Sub-ordered Materials | 2026-05-07 | 2026-05-21 | 2026-07-31 | 2026-08-13 | 2026-04-23 | 2026-05-07
A32140 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-05-21 | 2026-06-15 | 2026-08-14 | 2026-09-07 | 2026-05-07 | 2026-05-28
A32150 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-06-15 | 2026-06-16 | 2026-09-08 | 2026-09-09 | 2026-05-28 | 2026-05-29
A32160 | Manufacturing / Ex Works | 2026-06-16 | 2026-09-09 | 2026-09-09 | 2026-12-03 | 2026-05-29 | 2026-07-28
A32170 | Complete Manufacturing & ready for Final Inspection | 2026-09-09 | 2026-09-18 | 2026-12-03 | 2026-12-11 | 2026-07-28 | 2026-08-06
A32180 | Materials Successfully Inspected, Tested / Ex Work | 2026-09-18 | 2026-09-25 | 2026-12-14 | 2026-12-18 | 2026-08-06 | 2026-08-13
A34170 | Start Production | 13-Mar-26 A |  | 2026-07-10 |  | 2026-04-02
A34180 | Delivery of F&G Detectors | 2026-09-25 | 2026-10-09 | 2026-12-19 | 2027-01-01 | 2026-08-13 | 2026-09-02
MainElectricalEquipment |  | 25-Feb-25 A | 2026-10-23 | 2026-06-16 | 2027-03-06 | 01-Feb-25 A | 2026-05-13
LVBusDuct |  | 17-Apr-26 A | 2026-09-16 | 2026-09-10 | 2027-02-07
LVBusDuct |  | 17-Apr-26 A | 2026-09-16 | 2026-09-10 | 2027-02-07
A62510 | Start Production | 17-Apr-26 A |  | 2026-09-10 |  | 2026-02-20 | 2026-02-26
A62520 | Key Vendor Drawings / Data Approved | 2026-04-17 | 2026-05-07 | 2026-09-10 | 2026-09-30
A62530 | Purchase Order for Major Sub-ordered Materials | 2026-05-07 | 2026-05-21 | 2026-10-01 | 2026-10-14
A62540 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-05-21 | 2026-06-11 | 2026-10-15 | 2026-11-04
A62550 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-06-11 | 2026-06-12 | 2026-11-05 | 2026-11-06
A62560 | Manufacturing / Ex Works (India/UAE) | 2026-06-12 | 2026-08-11 | 2026-11-06 | 2027-01-05
A62570 | Complete Manufacturing & ready for Final Inspection | 2026-08-11 | 2026-08-20 | 2027-01-05 | 2027-01-13
A62580 | Materials Successfully Inspected, Tested / Ex Work | 2026-08-20 | 2026-08-31 | 2027-01-14 | 2027-01-22
A62590 | Delivery of LV Bus Duct | 2026-08-31 | 2026-09-16 | 2027-01-23 | 2027-02-07
DGSet(750KVA)01Nos |  | 22-Aug-25 A | 2026-10-09 | 2026-07-11 | 2027-01-04 | 22-Aug-25 A | 2026-08-06
DGSet |  | 22-Aug-25 A | 2026-10-09 | 2026-07-11 | 2027-01-04 | 01-Feb-25 A | 25-Sep-25 A
A33200 | Key Vendor Drawings / Data Approved | 01-Sep-25 A | 27-Nov-25 A | 2026-07-11 | 2026-07-11 | 01-Sep-25 A | 27-Nov-25 A
A33210 | Purchase Order for Major Sub-ordered Materials | 30-Nov-25 A | 19-Dec-25 A | 2026-07-11 | 2026-07-11 | 30-Nov-25 A | 19-Dec-25 A
A33220 | Major Sub-ordered Materials Received by Vendor and Verified | 26-Nov-25 A | 01-Dec-25 A | 2026-07-11 | 2026-07-11 | 26-Nov-25 A | 01-Dec-25 A
A33230 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 02-Dec-25 A | 09-Dec-25 A | 2026-07-11 | 2026-07-11 | 02-Dec-25 A | 09-Dec-25 A
A33240 | Manufacturing / Ex Works (India/UAE) | 10-Dec-25 A | 2026-08-31 | 2026-07-11 | 2026-11-25 | 10-Dec-25 A | 2026-06-29
A33250 | Complete Manufacturing & ready for Final Inspection | 01-Apr-26 A | 2026-09-09 | 2026-11-25 | 2026-12-03 | 2026-06-30 | 2026-07-08
A33260 | Materials Successfully Inspected, Tested / Ex Work | 2026-09-10 | 2026-09-18 | 2026-12-04 | 2026-12-14 | 2026-07-09 | 2026-07-17
A34420 | Start Production | 22-Aug-25 A |  | 2026-07-11 |  | 22-Aug-25 A
A34430 | Delivery of Material in Warehouse DG Set | 2026-09-19 | 2026-10-09 | 2026-12-15 | 2027-01-04 | 2026-07-18 | 2026-08-06
UPS(AC-60KVA,20KVA,DC-UPS6.5KVA)03Nos. |  | 25-Feb-25 A | 2026-09-29 | 2026-06-16 | 2027-03-06 | 25-Feb-25 A | 2026-09-28
TA_UPSModification-ChlorideTechnology |  | 25-Feb-25 A | 03-May-25 A | 2026-06-16 | 2026-06-16 | 25-Feb-25 A | 03-May-25 A
A37280 | Start Production | 25-Feb-25 A |  | 2026-06-16 |  | 25-Feb-25 A
A37290 | Key Vendor Drawings / Data Approved | 27-Feb-25 A | 04-Mar-25 A | 2026-06-16 | 2026-06-16 | 27-Feb-25 A | 04-Mar-25 A
A37300 | Purchase Order for Major Sub-ordered Materials | 06-Mar-25 A | 22-Mar-25 A | 2026-06-16 | 2026-06-16 | 06-Mar-25 A | 22-Mar-25 A
A37310 | Major Sub-ordered Materials Received by Vendor and Verified | 23-Mar-25 A | 29-Mar-25 A | 2026-06-16 | 2026-06-16 | 23-Mar-25 A | 29-Mar-25 A
A37320 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 30-Mar-25 A | 05-Apr-25 A | 2026-06-16 | 2026-06-16 | 30-Mar-25 A | 05-Apr-25 A
A37330 | Manufacturing / Ex Works (India/UAE) | 06-Apr-25 A | 12-Apr-25 A | 2026-06-16 | 2026-06-16 | 06-Apr-25 A | 12-Apr-25 A
A37340 | Complete Manufacturing & ready for Final Inspection | 13-Apr-25 A | 19-Apr-25 A | 2026-06-16 | 2026-06-16 | 13-Apr-25 A | 19-Apr-25 A
A37350 | Materials Successfully Inspected, Tested / Ex Work | 20-Apr-25 A | 26-Apr-25 A | 2026-06-16 | 2026-06-16 | 20-Apr-25 A | 26-Apr-25 A
A37360 | Delivery of Material for UPS Modification | 27-Apr-25 A | 03-May-25 A | 2026-06-16 | 2026-06-16 | 27-Apr-25 A | 03-May-25 A
UPS(AC-60KVA,20KVA,DC-UPS6.5KVA)Qty1+1+1=03Nos |  | 16-Oct-25 A | 2026-09-29 | 2026-09-23 | 2027-03-06 | 07-Jul-25 A | 2026-03-09
A31670 | Key Vendor Drawings / Data Approved | 04-Feb-26 A | 20-Feb-26 A | 2026-09-23 | 2026-09-23 | 2026-02-20 | 2026-03-13
A31680 | Purchase Order for Major Sub-ordered Materials | 12-Feb-26 A | 20-Feb-26 A | 2026-09-23 | 2026-09-23 | 2026-03-13 | 2026-03-27
A31690 | Major Sub-ordered Materials Received by Vendor and Verified | 03-Feb-26 A | 20-Feb-26 A | 2026-09-23 | 2026-09-23 | 2026-03-27 | 2026-05-08
A31700 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 23-Feb-26 A | 28-Feb-26 A | 2026-09-23 | 2026-09-23 | 2026-05-08 | 2026-05-10
A31710 | Manufacturing / Ex Works (India/UAE) | 26-Feb-26 A | 2026-08-14 | 2026-09-23 | 2027-01-21 | 2026-05-10 | 2026-08-18
A31720 | Complete Manufacturing & ready for Final Inspection | 01-Apr-26 A | 2026-08-28 | 2027-01-21 | 2027-02-03 | 2026-08-18 | 2026-08-27
A31730 | Materials Successfully Inspected, Tested / Ex Work | 2026-08-31 | 2026-09-08 | 2027-02-04 | 2027-02-12 | 2026-08-27 | 2026-09-07
A34070 | Start Production | 16-Oct-25 A |  | 2026-09-23 |  | 16-Oct-25 A
A34080 | Delivery of Material in Warehouse UPS | 2026-09-09 | 2026-09-29 | 2027-02-14 | 2027-03-06 | 2026-09-07 | 2026-09-28
PowerTransformer(05Nos) |  | 10-Sep-25 A | 2026-07-31 | 2026-09-07 | 2026-12-23 | 10-Sep-25 A | 2026-08-14
PowerTransformers(Qty05) |  | 10-Sep-25 A | 2026-07-31 | 2026-09-07 | 2026-12-23 | 10-May-25 A | 17-Sep-25 A
A31850 | Key Vendor Drawings / Data Approved | 21-Nov-25 A | 02-Dec-25 A | 2026-09-07 | 2026-09-07 | 21-Nov-25 A | 02-Dec-25 A
A31860 | Purchase Order for Major Sub-ordered Materials | 02-Dec-25 A | 19-Dec-25 A | 2026-09-07 | 2026-09-07 | 02-Dec-25 A | 19-Dec-25 A
A31870 | Major Sub-ordered Materials Received by Vendor and Verified | 19-Dec-25 A | 03-Jan-26 A | 2026-09-07 | 2026-09-07 | 19-Dec-25 A | 03-Jan-26 A
A31880 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 01-Jan-26 A | 11-Jan-26 A | 2026-09-07 | 2026-09-07 | 01-Jan-26 A | 11-Jan-26 A
A31890 | Manufacturing / Ex Works (India/UAE) | 21-Feb-26 A | 2026-06-15 | 2026-09-07 | 2026-11-06 | 2026-02-20 | 2026-06-29
A31900 | Complete Manufacturing & ready for Final Inspection | 21-Mar-26 A | 2026-06-24 | 2026-11-06 | 2026-11-16 | 2026-06-30 | 2026-07-08
A31910 | Materials Successfully Inspected, Tested / Ex Work | 2026-06-25 | 2026-07-03 | 2026-11-17 | 2026-11-25 | 2026-07-09 | 2026-07-17
A34110 | Start Production | 10-Sep-25 A |  | 2026-09-07 |  | 10-Sep-25 A
A34120 | Delivery of Material in Warehouse Power Transformers | 2026-07-04 | 2026-07-31 | 2026-11-26 | 2026-12-23 | 2026-07-18 | 2026-08-14
ElectricalHeatTracing |  | 13-Mar-26 A | 2026-09-28 | 2026-07-30 | 2027-01-10 | 2026-02-20 | 2026-05-13
ElectricalHeatTracing(53Meterforpiping+340Meterforinstrumentation) |  | 13-Mar-26 A | 2026-09-28 | 2026-07-30 | 2027-01-10 | 2026-02-20 | 2026-05-13
A29060 | Key Vendor Drawings / Data Approved | 2026-04-17 | 2026-05-28 | 2026-07-30 | 2026-09-09 | 2026-05-14 | 2026-06-24
A29070 | Purchase Order for Major Sub-ordered Materials | 2026-05-28 | 2026-06-11 | 2026-09-10 | 2026-09-23 | 2026-06-24 | 2026-06-29
A29080 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-06-11 | 2026-06-25 | 2026-09-24 | 2026-10-07 | 2026-06-29 | 2026-07-06
A29090 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-06-25 | 2026-06-26 | 2026-10-08 | 2026-10-09 | 2026-07-06 | 2026-07-07
A29100 | Manufacturing / Ex Works (India/UAE) | 2026-06-26 | 2026-08-25 | 2026-10-09 | 2026-12-08 | 2026-07-07 | 2026-08-01
A29110 | Complete Manufacturing & ready for Final Inspection | 2026-08-25 | 2026-09-03 | 2026-12-08 | 2026-12-16 | 2026-08-03 | 2026-08-06
A29120 | Materials Successfully Inspected, Tested / Ex Work | 2026-09-03 | 2026-09-14 | 2026-12-17 | 2026-12-25 | 2026-08-06 | 2026-08-17
A33410 | Start Production | 13-Mar-26 A |  | 2026-07-30 |  | 2026-05-13
A33420 | Delivery of Material in Warehouse for Electrical Heat Tracing | 2026-09-14 | 2026-09-28 | 2026-12-28 | 2027-01-10 | 2026-08-17 | 2026-08-31
CP |  | 16-Feb-26 A | 2026-08-28 | 2026-08-14 | 2026-12-27 | 21-Nov-25 A | 2026-02-27
CathodicProtection(CP)TotalCSPipingLength-499Meters |  | 16-Feb-26 A | 2026-08-28 | 2026-08-14 | 2026-12-27 | 21-Nov-25 A | 2026-02-27
A29240 | Key Vendor Drawings / Data Approved | 2026-04-17 | 2026-05-07 | 2026-08-14 | 2026-09-03 | 2026-03-02 | 2026-04-10
A29250 | Purchase Order for Major Sub-ordered Materials | 2026-05-07 | 2026-05-14 | 2026-09-04 | 2026-09-10 | 2026-04-10 | 2026-04-17
A29260 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-05-14 | 2026-06-11 | 2026-09-11 | 2026-10-08 | 2026-04-17 | 2026-05-15
A29270 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-06-11 | 2026-06-12 | 2026-10-09 | 2026-10-10 | 2026-05-15 | 2026-05-16
A29280 | Manufacturing / Ex Works | 2026-06-12 | 2026-07-27 | 2026-10-10 | 2026-11-24 | 2026-05-16 | 2026-06-30
A29290 | Complete Manufacturing & ready for Final Inspection | 2026-07-27 | 2026-08-05 | 2026-11-24 | 2026-12-02 | 2026-06-30 | 2026-07-09
A29300 | Materials Successfully Inspected, Tested / Ex Work | 2026-08-05 | 2026-08-14 | 2026-12-03 | 2026-12-11 | 2026-07-09 | 2026-07-20
A33450 | Start Production | 16-Feb-26 A |  | 2026-08-14 |  | 2026-02-27
A33460 | Delivery of Material in Warehouse for Cathodic Protection | 2026-08-14 | 2026-08-28 | 2026-12-14 | 2026-12-27 | 2026-07-20 | 2026-08-03
LV&MVSwitchgears |  | 12-Sep-25 A | 2026-09-09 | 2026-07-28 | 2026-12-19 | 18-Mar-25 A | 01-Nov-25 A
Switchgear(MV&LV) |  | 12-Sep-25 A | 2026-09-09 | 2026-07-28 | 2026-12-19 | 12-Sep-25 A | 2026-08-20
A32480 | Key Vendor Drawings / Data Approved | 21-Nov-25 A | 02-Dec-25 A | 2026-07-28 | 2026-07-28 | 21-Nov-25 A | 02-Dec-25 A
A32490 | Purchase Order for Major Sub-ordered Materials | 11-Dec-25 A | 19-Dec-25 A | 2026-07-28 | 2026-07-28 | 11-Dec-25 A | 19-Dec-25 A
A32500 | Major Sub-ordered Materials Received by Vendor and Verified | 20-Jan-26 A | 31-Mar-26 A | 2026-07-28 | 2026-07-28 | 20-Jan-26 A | 2026-02-24
A32510 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 20-Feb-26 A | 01-Apr-26 A | 2026-07-28 | 2026-07-28 | 2026-02-25 | 2026-02-25
A32520 | Manufacturing / Ex Works (India/UAE) | 10-Mar-26 A | 2026-07-30 | 2026-07-28 | 2026-11-10 | 2026-02-26 | 2026-07-10
A32530 | Complete Manufacturing & ready for Final Inspection | 21-Mar-26 A | 2026-08-10 | 2026-11-10 | 2026-11-18 | 2026-07-13 | 2026-07-21
A32540 | Materials Successfully Inspected, Tested / Ex Work | 01-Apr-26 A | 2026-08-19 | 2026-11-19 | 2026-11-27 | 2026-07-22 | 2026-07-30
A34260 | Start Production | 12-Sep-25 A |  | 2026-07-28 |  | 12-Sep-25 A
A34270 | Delivery of Switchgear (MV & LV) | 2026-08-20 | 2026-09-09 | 2026-11-29 | 2026-12-19 | 2026-07-31 | 2026-08-20
SwitchGearModification(Siemens) |  | 17-Mar-25 A | 12-May-25 A | 2026-06-16 | 2026-06-16 | 20-Feb-25 A | 18-Mar-25 A
TA_Switchgear(MVSwitchgearModifications)-Siemens |  | 17-Mar-25 A | 12-May-25 A | 2026-06-16 | 2026-06-16 | 20-Feb-25 A | 18-Mar-25 A
A22410 | Delivery of Material For Switchgear Modification | 06-May-25 A | 12-May-25 A | 2026-06-16 | 2026-06-16 | 06-May-25 A | 12-May-25 A
A22450 | Start Production | 17-Mar-25 A |  | 2026-06-16 |  | 17-Mar-25 A
A22460 | Key Vendor Drawings / Data Approved | 18-Mar-25 A | 24-Mar-25 A | 2026-06-16 | 2026-06-16 | 18-Mar-25 A | 24-Mar-25 A
A22470 | Manufacturing / Ex Works (India/UAE) | 15-Apr-25 A | 21-Apr-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 21-Apr-25 A
A22740 | Purchase Order for Major Sub-ordered Materials | 25-Mar-25 A | 31-Mar-25 A | 2026-06-16 | 2026-06-16 | 25-Mar-25 A | 31-Mar-25 A
A22760 | Major Sub-ordered Materials Received by Vendor and Verified | 01-Apr-25 A | 07-Apr-25 A | 2026-06-16 | 2026-06-16 | 01-Apr-25 A | 07-Apr-25 A
A22770 | Complete Manufacturing & ready for Final Inspection | 22-Apr-25 A | 28-Apr-25 A | 2026-06-16 | 2026-06-16 | 22-Apr-25 A | 28-Apr-25 A
A22780 | Materials Successfully Inspected, Tested / Ex Work | 29-Apr-25 A | 05-May-25 A | 2026-06-16 | 2026-06-16 | 29-Apr-25 A | 05-May-25 A
A24280 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 08-Apr-25 A | 14-Apr-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 14-Apr-25 A
MV&LVVFD's |  | 13-Aug-25 A | 20-Feb-26 A | 2026-12-21 | 2026-12-21 | 18-Jul-25 A | 12-Aug-25 A
VariableFequencyDrives(VFDs)LVQty=03 |  | 13-Aug-25 A | 20-Feb-26 A | 2026-12-21 | 2026-12-21 | 18-Jul-25 A | 12-Aug-25 A
A32570 | Key Vendor Drawings / Data Approved | 13-Aug-25 A | 14-Aug-25 A | 2026-12-21 | 2026-12-21 | 13-Aug-25 A | 14-Aug-25 A
A32580 | Purchase Order for Major Sub-ordered Materials | 15-Aug-25 A | 16-Aug-25 A | 2026-12-21 | 2026-12-21 | 15-Aug-25 A | 16-Aug-25 A
A32590 | Major Sub-ordered Materials Received by Vendor and Verified | 17-Aug-25 A | 18-Aug-25 A | 2026-12-21 | 2026-12-21 | 17-Aug-25 A | 18-Aug-25 A
A32600 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 19-Aug-25 A | 19-Aug-25 A | 2026-12-21 | 2026-12-21 | 19-Aug-25 A | 19-Aug-25 A
A32610 | Manufacturing / Ex Works (India/UAE) | 20-Aug-25 A | 20-Aug-25 A | 2026-12-21 | 2026-12-21 | 20-Aug-25 A | 20-Aug-25 A
A32620 | Complete Manufacturing & ready for Final Inspection | 20-Aug-25 A | 21-Aug-25 A | 2026-12-21 | 2026-12-21 | 20-Aug-25 A | 21-Aug-25 A
A32630 | Materials Successfully Inspected, Tested / Ex Work | 22-Aug-25 A | 22-Aug-25 A | 2026-12-21 | 2026-12-21 | 22-Aug-25 A | 22-Aug-25 A
A34280 | Start Production | 13-Aug-25 A |  | 2026-12-21 |  | 13-Aug-25 A
A34290 | Delivery of VFDs | 13-Feb-26 A | 20-Feb-26 A | 2026-12-21 | 2026-12-21 | 2026-02-20 | 2026-03-19
HVCapacitorBay |  | 27-Oct-25 A | 2026-06-29 | 2026-11-03 | 2027-01-17 | 15-Apr-25 A | 15-Oct-25 A
HVCapacitorBay |  | 27-Oct-25 A | 2026-06-29 | 2026-11-03 | 2027-01-17 | 15-Apr-25 A | 15-Oct-25 A
A32030 | Key Vendor Drawings / Data Approved | 19-Dec-25 A | 26-Feb-26 A | 2026-11-03 | 2026-11-03 | 19-Dec-25 A | 26-Feb-26 A
A32040 | Purchase Order for Major Sub-ordered Materials | 19-Feb-26 A | 27-Feb-26 A | 2026-11-03 | 2026-11-03 | 2026-02-20 | 2026-03-05
A32050 | Major Sub-ordered Materials Received by Vendor and Verified | 18-Feb-26 A | 01-Mar-26 A | 2026-11-03 | 2026-11-03 | 2026-03-06 | 2026-04-16
A32060 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 01-Mar-26 A | 03-Mar-26 A | 2026-11-03 | 2026-11-03 | 2026-04-17 | 2026-04-17
A32070 | Manufacturing / Ex Works (India/UAE) | 09-Mar-26 A | 2026-06-08 | 2026-11-03 | 2026-12-25 | 2026-04-18 | 2026-07-01
A32080 | Complete Manufacturing & ready for Final Inspection | 21-Mar-26 A | 2026-06-15 | 2026-12-25 | 2027-01-01 | 2026-07-02 | 2026-07-10
A32090 | Materials Successfully Inspected, Tested / Ex Work | 01-Apr-26 A | 2026-06-22 | 2027-01-01 | 2027-01-08 | 2026-07-13 | 2026-07-21
A34150 | Start Production | 27-Oct-25 A |  | 2026-11-03 |  | 27-Oct-25 A
A34160 | Delivery of Material in Warehouse HV Capacitor Bay | 2026-06-23 | 2026-06-29 | 2027-01-11 | 2027-01-17 | 2026-07-22 | 2026-07-28
PowerDistributionPanelandLCS,Battery&SafetySwitch,ResisterBank |  | 06-Jun-25 A | 2026-05-31 | 2026-12-01 | 2027-01-14 | 10-Apr-25 A | 20-Jun-25 A
NGRPanelQty02 |  | 06-Jun-25 A | 2026-05-31 | 2026-12-01 | 2027-01-14 | 10-Apr-25 A | 20-Jun-25 A
A33020 | Key Vendor Drawings / Data Approved | 19-Dec-25 A | 20-Dec-25 A | 2026-12-01 | 2026-12-01 | 19-Dec-25 A | 20-Dec-25 A
A33030 | Purchase Order for Major Sub-ordered Materials | 22-Dec-25 A | 27-Dec-25 A | 2026-12-01 | 2026-12-01 | 22-Dec-25 A | 27-Dec-25 A
A33040 | Major Sub-ordered Materials Received by Vendor and Verified | 28-Dec-25 A | 03-Jan-26 A | 2026-12-01 | 2026-12-01 | 28-Dec-25 A | 03-Jan-26 A
A33050 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 02-Jan-26 A | 10-Jan-26 A | 2026-12-01 | 2026-12-01 | 02-Jan-26 A | 10-Jan-26 A
A33060 | Manufacturing / Ex Works (India/UAE) | 01-Jan-26 A | 17-Jan-26 A | 2026-12-01 | 2026-12-01 | 01-Jan-26 A | 17-Jan-26 A
A33070 | Complete Manufacturing & ready for Final Inspection | 28-Feb-26 A | 20-Mar-26 A | 2026-12-01 | 2026-12-01 | 2026-02-20 | 2026-03-02
A33080 | Materials Successfully Inspected, Tested / Ex Work | 10-Mar-26 A | 17-Apr-26 A | 2026-12-01 | 2026-12-01 | 2026-03-03 | 2026-03-11
A34380 | Start Production | 06-Jun-25 A |  | 2026-12-01 |  | 06-Jun-25 A
A34390 | Delivery of NGR Panel | 2026-04-17 | 2026-05-31 | 2026-12-01 | 2027-01-14 | 2026-03-12 | 2026-04-08
LightFitting,Switchesandsmallpowersockets |  | 2026-05-18 | 2026-10-17 | 2026-08-17 | 2027-01-15
LightFitting,Switchesandsmallpowersockets |  | 2026-05-18 | 2026-10-17 | 2026-08-17 | 2027-01-15
A62870 | Key Vendor Drawings / Data Approved | 2026-05-19 | 2026-06-08 | 2026-08-17 | 2026-09-04
A62880 | Manufacturing / Ex Works (India/UAE) | 2026-07-14 | 2026-09-12 | 2026-10-12 | 2026-12-11
A62890 | Purchase Order for Major Sub-ordered Materials | 2026-06-08 | 2026-06-22 | 2026-09-07 | 2026-09-18
A62900 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-06-22 | 2026-07-13 | 2026-09-21 | 2026-10-09
A62910 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-07-13 | 2026-07-14 | 2026-10-11 | 2026-10-12
A62920 | Complete Manufacturing & ready for Final Inspection | 2026-09-14 | 2026-09-22 | 2026-12-11 | 2026-12-21
A62930 | Materials Successfully Inspected, Tested / Ex Work | 2026-09-23 | 2026-10-01 | 2026-12-22 | 2026-12-30
A62940 | Start Production | 2026-05-18 |  | 2026-08-17
A62950 | Delivery of Light Fitting, Switches and Small Sockets | 2026-10-02 | 2026-10-17 | 2026-12-31 | 2027-01-15
InterposingRelayPanel(IRP) |  | 2026-05-08 | 2026-10-23 | 2026-08-11 | 2027-01-23 | 2026-02-20 | 2026-03-18
InterposingRelayPanel |  | 2026-05-08 | 2026-10-23 | 2026-08-11 | 2027-01-23 | 2026-02-20 | 2026-03-18
A33110 | Key Vendor Drawings / Data Approved | 2026-05-11 | 2026-05-29 | 2026-08-11 | 2026-08-31 | 2026-03-19 | 2026-04-08
A33120 | Purchase Order for Major Sub-ordered Materials | 2026-05-29 | 2026-06-12 | 2026-09-01 | 2026-09-14 | 2026-04-08 | 2026-04-22
A33130 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-06-12 | 2026-07-03 | 2026-09-15 | 2026-10-05 | 2026-04-22 | 2026-05-13
A33140 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-07-03 | 2026-07-04 | 2026-10-06 | 2026-10-07 | 2026-05-13 | 2026-05-14
A33150 | Manufacturing / Ex Works (India/UAE) | 2026-07-04 | 2026-09-17 | 2026-10-07 | 2026-12-21 | 2026-05-14 | 2026-08-22
A33160 | Complete Manufacturing & ready for Final Inspection | 2026-09-17 | 2026-09-28 | 2026-12-21 | 2026-12-29 | 2026-08-24 | 2026-09-01
A33170 | Materials Successfully Inspected, Tested / Ex Work | 2026-09-28 | 2026-10-07 | 2026-12-30 | 2027-01-07 | 2026-09-02 | 2026-09-10
A34400 | Start Production | 2026-05-08 |  | 2026-08-11 |  | 2026-03-18
A34410 | Delivery of Interposing relay Panel | 2026-10-07 | 2026-10-23 | 2027-01-08 | 2027-01-23 | 2026-09-11 | 2026-09-17
ConstructionandPre-Commissioning |  | 09-Jan-25 A | 2027-06-10 | 2026-06-15 | 2027-09-20 | 09-Jan-25 A | 2027-07-01
Construction/Pre-Commissioning |  | 10-Jun-25 A | 2026-12-28 | 2026-10-22 | 2027-03-06 | 10-Jun-25 A | 2026-12-21
GreenFieldWorks |  | 10-Jun-25 A | 2026-12-28 | 2026-10-22 | 2027-03-06 | 10-Jun-25 A | 2026-12-21
General/Common |  | 10-Jun-25 A | 15-Oct-25 A | 2026-10-22 | 2026-10-22 | 27-Nov-24 A | 21-Jan-25 A
A3250 | Complete Site Preparation and Grading works |  | 16-Jun-25 A |  | 2026-10-22 |  | 16-Jun-25 A
CONS | TSF Construction / Commence on SITE | 01-Jul-25 A | 15-Oct-25 A | 2026-10-22 | 2026-10-22 | 01-Jul-25 A | 15-Oct-25 A
CONS10 | Installation of Isolation Fence Plant Site | 10-Jun-25 A | 13-Aug-25 A | 2026-10-22 | 2026-10-22 | 10-Jun-25 A | 13-Aug-25 A
Electrical&InstrumentationWorks |  | 2026-06-13 | 2026-12-28 | 2026-11-29 | 2027-03-06 | 2026-05-09 | 2026-12-21
A18510 | Cable Laying - Trenches | 2026-06-13 | 2026-08-25 | 2026-12-08 | 2027-02-20 | 2026-05-09 | 2026-07-21
A3709 | E&I Bulk & Equipment Deliveries - Plant Site |  | 2026-11-09 |  | 2027-01-11 |  | 2026-09-24
A3719 | E&I Works (CCB & SIS) For cable trays and cable laying | 2026-09-15 | 2026-12-12 | 2026-12-09 | 2027-03-06 | 2026-09-26 | 2026-12-21
A3739 | Complete E&I Equipment / Panels Installation CCB &SIS |  | 2026-12-10 |  | 2027-03-06 |  | 2026-10-18
A3749 | Complete Cable termination and loop test - Overall |  | 2026-12-28 |  | 2027-03-06 |  | 2026-12-21
A3759 | Complete E&I Work at plant site |  | 2026-12-09 |  | 2027-02-20 |  | 2026-11-17
A3889 | Electrical Works Plant Site (Cable trays, cable laying, termination, DBs, Jbs etc) | 2026-09-26 | 2026-12-09 | 2026-11-29 | 2027-02-10 | 2026-08-26 | 2026-11-08
A3909 | Instrumentation Works Plant Site (Control/Manual Valves, Gauges, TT, PT, DPT, PSVs, Switches etc) | 2026-10-19 | 2026-12-09 | 2026-12-31 | 2027-02-20 | 2026-09-27 | 2026-11-17
AccommodationandMessing |  | 15-Apr-25 A | 24-Jul-25 A | 2026-07-07 | 2026-07-07 | 15-Apr-25 A | 24-Jul-25 A
MobilisationofCamp(AccommodationandMessing) |  | 15-Apr-25 A | 24-Jul-25 A | 2026-07-07 | 2026-07-07 | 15-Apr-25 A | 24-Jul-25 A
A61550 | TA - Mobilisation of Camp (Accommodation and messing) | 15-Apr-25 A | 20-Apr-25 A | 2026-07-07 | 2026-07-07 | 15-Apr-25 A | 20-Apr-25 A
A62210 | Main Scope - Mobilisation of Camp (Accommodation and messing) | 22-Apr-25 A | 24-Jul-25 A | 2026-07-07 | 2026-07-07 | 22-Apr-25 A | 24-Jul-25 A
Fabrication,Storage,Workshops(TemporaryFacilities) |  | 01-Apr-25 A | 2027-06-10 | 2026-07-07 | 2027-09-20 | 01-Apr-25 A | 2027-07-01
MobilisationofTemporaryFacilities |  | 01-Apr-25 A | 24-Oct-25 A | 2026-07-07 | 2026-07-07 | 01-Apr-25 A | 24-Oct-25 A
A61560 | Mobilisation of Temporary Facilities - TA | 01-Apr-25 A | 31-May-25 A | 2026-07-07 | 2026-07-07 | 01-Apr-25 A | 31-May-25 A
A62230 | Mobilisation of Temporary Facilities - Main Scope | 01-Aug-25 A | 24-Oct-25 A | 2026-07-07 | 2026-07-07 | 01-Aug-25 A | 24-Oct-25 A
MaintenanceofTemporaryFacilities |  | 01-Nov-25 A | 2027-02-25 | 2026-07-07 | 2027-06-07 | 01-Nov-25 A | 2027-03-18
A61570 | Maintenance of Temporary Facilities - Q2 | 01-Jan-26 A | 24-Jan-26 A | 2026-07-07 | 2026-07-07 | 01-Jan-26 A | 24-Jan-26 A
A62240 | Maintenance of Temporary Facilities - Q1 | 01-Nov-25 A | 18-Nov-25 A | 2026-07-07 | 2026-07-07 | 01-Nov-25 A | 18-Nov-25 A
A62250 | Maintenance of Temporary Facilities - Q3 | 20-Feb-26 A | 17-Apr-26 A | 2026-07-28 | 2026-07-28 | 2026-04-11 | 2026-05-07
A62260 | Maintenance of Temporary Facilities - Q4 | 2026-07-04 | 2026-07-30 | 2026-10-13 | 2026-11-09 | 2026-07-25 | 2026-08-20
A62270 | Maintenance of Temporary Facilities - Q5 | 2026-10-17 | 2026-11-12 | 2027-01-26 | 2027-02-22 | 2026-11-07 | 2026-12-03
A62280 | Maintenance of Temporary Facilities - Q6 | 2027-01-30 | 2027-02-25 | 2027-05-11 | 2027-06-07 | 2027-02-20 | 2027-03-18
DemobilisationofTemporaryFacilities |  | 25-Jun-25 A | 2027-06-10 | 2027-08-24 | 2027-09-20 | 25-Jun-25 A | 2027-07-01
A61580 | Demobiisation of Temporary Facilities - TA | 25-Jun-25 A | 11-Jul-25 A | 2027-08-24 | 2027-08-24 | 25-Jun-25 A | 11-Jul-25 A
A62290 | Demobiisation of Temporary Facilities - Main Scope | 2027-05-15 | 2027-06-10 | 2027-08-24 | 2027-09-20 | 2027-06-05 | 2027-07-01
CivilConstruction |  | 09-Jan-25 A | 2027-01-26 | 2026-06-15 | 2027-03-23 | 09-Jan-25 A | 2027-01-11
SitePreparation |  | 01-Apr-25 A | 15-Sep-25 A | 2026-07-07 | 2026-07-07 | 01-Apr-25 A | 15-Sep-25 A
A61590 | Site Preparation - TA | 01-Apr-25 A | 21-Jun-25 A | 2026-07-07 | 2026-07-07 | 01-Apr-25 A | 21-Jun-25 A
A62220 | Site Preparation - Main Scope | 22-Aug-25 A | 15-Sep-25 A | 2026-07-07 | 2026-07-07 | 22-Aug-25 A | 15-Sep-25 A
Fencing |  | 17-Apr-25 A | 22-Aug-25 A | 2026-07-07 | 2026-07-07 | 17-Apr-25 A | 22-Aug-25 A
A61600 | Fencing | 17-Apr-25 A | 22-Aug-25 A | 2026-07-07 | 2026-07-07 | 17-Apr-25 A | 22-Aug-25 A
Excavationandtrenching |  | 01-Apr-26 A | 2026-09-07 | 2026-07-07 | 2026-12-05 | 2026-03-02 | 2026-08-15
GFSumpsandPits |  | 01-Apr-26 A | 2026-09-07 | 2026-07-07 | 2026-11-02 | 2026-03-07 | 2026-08-11
AccidentallyOilyWaterSump70-TD-1407 |  | 01-Apr-26 A | 2026-07-08 | 2026-07-08 | 2026-09-28 | 2026-03-07 | 2026-05-28
A26600 | Excavation | 01-Apr-26 A | 2026-04-27 | 2026-07-08 | 2026-07-19 | 2026-03-07 | 2026-03-17
A26610 | Surface leveling and compaction | 02-Apr-26 A | 2026-04-29 | 2026-07-19 | 2026-07-21 | 2026-03-18 | 2026-03-19
A26620 | Lean concrete | 03-Apr-26 A | 2026-05-02 | 2026-07-21 | 2026-07-22 | 2026-03-21 | 2026-03-22
A26630 | Water proofing and bitumen coating/sheet | 2026-05-09 | 2026-05-13 | 2026-07-30 | 2026-08-03 | 2026-03-30 | 2026-04-02
A26640 | Formworks | 2026-05-13 | 2026-05-25 | 2026-08-04 | 2026-08-15 | 2026-04-04 | 2026-04-14
A26650 | Rebar works | 2026-05-13 | 2026-05-25 | 2026-08-04 | 2026-08-15 | 2026-04-04 | 2026-04-14
A26660 | Concrete pouring | 2026-05-27 | 2026-06-08 | 2026-08-18 | 2026-08-29 | 2026-04-18 | 2026-04-28
A26670 | Concrete Curing | 2026-05-28 | 2026-06-14 | 2026-08-19 | 2026-09-03 | 2026-04-19 | 2026-05-04
A26680 | Formwork removal | 2026-05-31 | 2026-06-16 | 2026-08-22 | 2026-09-06 | 2026-04-21 | 2026-05-06
A26690 | Protective Coating | 2026-06-16 | 2026-06-30 | 2026-09-07 | 2026-09-20 | 2026-05-07 | 2026-05-20
A26700 | Back filling and compaction in layers | 2026-06-30 | 2026-07-08 | 2026-09-21 | 2026-09-28 | 2026-05-21 | 2026-05-28
OilContaminatedWaterSump70-TD-1408 |  | 2026-05-10 | 2026-08-01 | 2026-07-07 | 2026-09-28 | 2026-03-25 | 2026-06-16
A26710 | Excavation | 2026-05-10 | 2026-05-20 | 2026-07-07 | 2026-07-18 | 2026-03-25 | 2026-04-05
A26720 | Surface leveling and compaction | 2026-05-21 | 2026-05-23 | 2026-07-19 | 2026-07-20 | 2026-04-06 | 2026-04-07
A26730 | Lean concrete | 2026-05-24 | 2026-05-25 | 2026-07-21 | 2026-07-22 | 2026-04-08 | 2026-04-09
A26740 | Water proofing and bitumen coating/sheet | 2026-06-02 | 2026-06-06 | 2026-07-30 | 2026-08-03 | 2026-04-18 | 2026-04-21
A26750 | Formworks | 2026-06-07 | 2026-06-17 | 2026-08-04 | 2026-08-15 | 2026-04-22 | 2026-05-03
A26760 | Rebar works | 2026-06-07 | 2026-06-17 | 2026-08-04 | 2026-08-15 | 2026-04-22 | 2026-05-03
A26770 | Concrete pouring | 2026-06-21 | 2026-07-01 | 2026-08-18 | 2026-08-29 | 2026-05-06 | 2026-05-17
A26780 | Concrete Curing | 2026-06-22 | 2026-07-07 | 2026-08-19 | 2026-09-03 | 2026-05-07 | 2026-05-23
A26790 | Formwork removal | 2026-06-24 | 2026-07-09 | 2026-08-22 | 2026-09-06 | 2026-05-10 | 2026-05-25
A26800 | Protective Coating | 2026-07-11 | 2026-07-23 | 2026-09-07 | 2026-09-20 | 2026-05-26 | 2026-06-08
A26810 | Back filling and compaction in layers | 2026-07-25 | 2026-08-01 | 2026-09-21 | 2026-09-28 | 2026-06-09 | 2026-06-16
SanitaryWasteWaterSump70-TD-1409 |  | 2026-04-26 | 2026-06-20 | 2026-08-05 | 2026-09-28 | 2026-05-10 | 2026-07-02
A26820 | Excavation | 2026-04-26 | 2026-05-04 | 2026-08-05 | 2026-08-12 | 2026-05-10 | 2026-05-17
A26830 | Surface leveling and compaction | 2026-05-04 | 2026-05-05 | 2026-08-13 | 2026-08-13 | 2026-05-18 | 2026-05-18
A26840 | Lean concrete | 2026-05-05 | 2026-05-06 | 2026-08-15 | 2026-08-15 | 2026-05-19 | 2026-05-19
A26850 | Water proofing and bitumen coating/sheet | 2026-05-13 | 2026-05-16 | 2026-08-23 | 2026-08-24 | 2026-05-27 | 2026-05-28
A26860 | Formworks | 2026-05-16 | 2026-05-27 | 2026-08-25 | 2026-09-05 | 2026-05-30 | 2026-06-09
A26870 | Rebar works | 2026-05-16 | 2026-05-27 | 2026-08-25 | 2026-09-05 | 2026-05-30 | 2026-06-09
A26880 | Concrete pouring | 2026-05-23 | 2026-05-31 | 2026-09-01 | 2026-09-08 | 2026-06-06 | 2026-06-13
A26890 | Concrete Curing | 2026-05-24 | 2026-06-09 | 2026-09-02 | 2026-09-17 | 2026-06-07 | 2026-06-22
A26900 | Formwork removal | 2026-05-26 | 2026-06-03 | 2026-09-05 | 2026-09-12 | 2026-06-09 | 2026-06-16
A26910 | Protective Coating | 2026-06-03 | 2026-06-11 | 2026-09-13 | 2026-09-20 | 2026-06-17 | 2026-06-24
A26920 | Back filling and compaction in layers | 2026-06-11 | 2026-06-20 | 2026-09-21 | 2026-09-28 | 2026-06-25 | 2026-07-02
PSA2SlopeDrumPit |  | 2026-04-18 | 2026-06-25 | 2026-07-21 | 2026-09-28 | 2026-03-15 | 2026-05-23
A26930 | Excavation | 2026-04-18 | 2026-04-25 | 2026-07-21 | 2026-07-28 | 2026-03-15 | 2026-03-22
A26940 | Surface leveling and compaction | 2026-04-26 | 2026-04-27 | 2026-07-29 | 2026-07-30 | 2026-03-23 | 2026-03-24
A26950 | Lean concrete | 2026-04-28 | 2026-04-29 | 2026-08-01 | 2026-08-02 | 2026-03-25 | 2026-03-26
A26960 | Water proofing and bitumen coating/sheet | 2026-05-07 | 2026-05-11 | 2026-08-10 | 2026-08-13 | 2026-04-04 | 2026-04-07
A26970 | Formworks | 2026-05-12 | 2026-05-19 | 2026-08-15 | 2026-08-22 | 2026-04-08 | 2026-04-15
A26980 | Rebar works | 2026-05-12 | 2026-05-19 | 2026-08-15 | 2026-08-22 | 2026-04-08 | 2026-04-15
A26990 | Concrete pouring | 2026-05-26 | 2026-06-02 | 2026-08-29 | 2026-09-05 | 2026-04-22 | 2026-04-29
A27000 | Concrete Curing | 2026-05-27 | 2026-06-11 | 2026-08-30 | 2026-09-14 | 2026-04-23 | 2026-05-09
A27010 | Formwork removal | 2026-05-30 | 2026-06-09 | 2026-09-01 | 2026-09-12 | 2026-04-26 | 2026-05-06
A27020 | Protective Coating | 2026-06-10 | 2026-06-17 | 2026-09-13 | 2026-09-20 | 2026-05-07 | 2026-05-14
A27030 | Back filling and compaction in layers | 2026-06-18 | 2026-06-25 | 2026-09-21 | 2026-09-28 | 2026-05-16 | 2026-05-23
CoolingWaterValvePit |  | 2026-07-04 | 2026-09-07 | 2026-08-29 | 2026-11-02 | 2026-06-07 | 2026-08-11
A27040 | Excavation | 2026-07-04 | 2026-07-11 | 2026-08-29 | 2026-09-05 | 2026-06-07 | 2026-06-14
A27050 | Surface leveling and compaction | 2026-07-12 | 2026-07-13 | 2026-09-06 | 2026-09-07 | 2026-06-15 | 2026-06-16
A27060 | Lean concrete | 2026-07-14 | 2026-07-15 | 2026-09-08 | 2026-09-09 | 2026-06-17 | 2026-06-18
A27070 | Water proofing and bitumen coating/sheet | 2026-07-23 | 2026-07-27 | 2026-09-17 | 2026-09-21 | 2026-06-27 | 2026-06-30
A27080 | Formworks | 2026-07-28 | 2026-08-08 | 2026-09-22 | 2026-10-03 | 2026-07-01 | 2026-07-12
A27090 | Rebar works | 2026-07-28 | 2026-08-08 | 2026-09-22 | 2026-10-03 | 2026-07-01 | 2026-07-12
A27100 | Concrete pouring | 2026-08-11 | 2026-08-18 | 2026-10-06 | 2026-10-13 | 2026-07-15 | 2026-07-22
A27110 | Concrete Curing | 2026-08-12 | 2026-08-27 | 2026-10-07 | 2026-10-22 | 2026-07-16 | 2026-08-01
A27120 | Formwork removal | 2026-08-15 | 2026-08-22 | 2026-10-10 | 2026-10-17 | 2026-07-19 | 2026-07-26
A27130 | Protective Coating | 2026-08-23 | 2026-08-30 | 2026-10-18 | 2026-10-25 | 2026-07-27 | 2026-08-03
A27140 | Back filling and compaction in layers | 2026-08-31 | 2026-09-07 | 2026-10-26 | 2026-11-02 | 2026-08-04 | 2026-08-11
GFUGPipingandTrenches |  | 2026-04-21 | 2026-08-19 | 2026-07-29 | 2026-11-09 | 2026-03-17 | 2026-08-15
Piping |  | 2026-05-26 | 2026-08-19 | 2026-07-29 | 2026-10-22 | 03-Feb-25 A | 24-Feb-25 A
A18530 | Excavation and Valve Pits for Fire Water Line | 2026-05-26 | 2026-08-02 | 2026-07-29 | 2026-10-05 | 2026-04-11 | 2026-06-17
A3440 | Trenching for UG Piping | 2026-05-26 | 2026-06-25 | 2026-07-29 | 2026-08-29 | 2026-04-11 | 2026-05-11
A3450 | Complete UG Piping & Backfilling | 2026-06-13 | 2026-08-19 | 2026-08-16 | 2026-10-22 | 2026-05-12 | 2026-07-19
Cables |  | 2026-04-21 | 2026-07-13 | 2026-08-25 | 2026-11-09 | 2026-03-17 | 2026-08-15
A18460 | Direct Buried Trenches for Power and Instrumentation cables | 2026-05-26 | 2026-06-18 | 2026-09-22 | 2026-10-15 | 2026-04-11 | 2026-05-04
A18480 | Backfilling of E&I trenches | 2026-06-20 | 2026-07-13 | 2026-10-17 | 2026-11-09 | 2026-07-22 | 2026-08-15
A3460 | Concrete Trenches for Electrical and Instrumentation Cable | 2026-04-21 | 2026-06-11 | 2026-08-25 | 2026-10-15 | 2026-03-17 | 2026-05-07
BFTrenches |  | 2026-04-18 | 2026-07-07 | 2026-09-08 | 2026-12-05 | 2026-03-02 | 2026-05-23
A21770 | Direct buried trenches - BF | 2026-05-28 | 2026-07-07 | 2026-10-26 | 2026-12-05 | 2026-04-12 | 2026-05-23
A21800 | Duct Banks/Road Crossing | 2026-04-18 | 2026-05-27 | 2026-09-08 | 2026-10-19 | 2026-03-02 | 2026-04-12
Foundations |  | 03-Jul-25 A | 2027-01-26 | 2026-06-15 | 2027-03-23 | 03-Jul-25 A | 2027-01-11
GFSISBuildingStructureWorks |  | 02-Sep-25 A | 2026-05-04 | 2026-06-21 | 2026-08-10 | 02-Sep-25 A | 2026-05-02
Sub-Structure |  | 02-Sep-25 A | 2026-04-25 | 2026-06-21 | 2026-08-02 | 02-Sep-25 A | 2026-03-09
A1590 | Foundation Works (Excavation, PCC & RCC) | 02-Sep-25 A | 01-Jan-26 A | 2026-06-21 | 2026-06-21 | 02-Sep-25 A | 01-Jan-26 A
A1600 | RCC Columns and Walls Upto FFL | 16-Dec-25 A | 16-Jan-26 A | 2026-07-25 | 2026-07-25 | 16-Dec-25 A | 16-Jan-26 A
A1610 | Waterproofing & Backfilling | 16-Dec-25 A | 2026-04-25 | 2026-07-25 | 2026-08-02 | 16-Dec-25 A | 2026-02-28
A1620 | Plinth Beams | 16-Dec-25 A | 2026-04-20 | 2026-07-25 | 2026-07-27 | 16-Dec-25 A | 2026-03-09
Super-Structure |  | 21-Feb-26 A | 2026-05-04 | 2026-07-28 | 2026-08-10 | 2026-03-10 | 2026-05-02
A1500 | RCC Columns and Walls Upto First Slab | 21-Feb-26 A | 2026-05-04 | 2026-07-28 | 2026-08-10 | 2026-03-10 | 2026-04-13
A1510 | First Slab and Beams | 01-Mar-26 A | 2026-05-04 | 2026-07-28 | 2026-08-10 | 2026-03-29 | 2026-05-02
GFSub-StationSub-Structure |  | 25-Aug-25 A | 2027-01-11 | 2026-06-21 | 2027-03-23 | 25-Aug-25 A | 2027-01-04
A1030 | Plinth Beams (Casting Suti) | 15-Dec-25 A | 2026-04-23 | 2026-07-30 | 2026-08-04 | 15-Dec-25 A | 2026-03-26
A26360 | Foundation Works (Excavation, PCC & RCC) | 25-Aug-25 A | 16-Sep-25 A | 2026-06-21 | 2026-06-21 | 25-Aug-25 A | 16-Sep-25 A
A26370 | RCC Base & Columns Upto FFL | 21-Nov-25 A | 10-Feb-26 A | 2026-07-27 | 2026-07-27 | 21-Nov-25 A | 10-Feb-26 A
A26380 | Waterproofing & Backfilling (handingover to Precast) | 15-Sep-25 A | 22-Sep-25 A | 2026-07-27 | 2026-07-27 | 15-Sep-25 A | 22-Sep-25 A
GFSub-StationSuper-Structure |  | 24-Jan-26 A | 2027-01-11 | 2026-07-27 | 2027-03-23 | 24-Jan-26 A | 2027-01-04
GroundFloor-CellarArea |  | 24-Jan-26 A | 2026-04-23 | 2026-07-27 | 2026-08-03 | 24-Jan-26 A | 2026-03-26
A26390 | RCC Columns and Walls Upto First Slab | 24-Jan-26 A | 2026-04-23 | 2026-07-27 | 2026-08-03 | 24-Jan-26 A | 2026-03-26
A26400 | First Slab and Beams | 21-Feb-26 A | 2026-04-23 | 2026-07-27 | 2026-08-03 | 2026-02-21 | 2026-03-26
FirstFloor |  | 21-Feb-26 A | 2027-01-11 | 2026-07-27 | 2027-03-23 | 2026-03-11 | 2027-01-04
A26410 | RCC Columns Upto 2nd Slab | 22-Feb-26 A | 2026-04-23 | 2026-07-27 | 2026-08-02 | 2026-03-11 | 2026-04-11
A26420 | 2nd Slab and Beams | 21-Feb-26 A | 2026-04-26 | 2026-07-27 | 2026-08-04 | 2026-03-26 | 2026-05-09
C1059 | Punch List Close Out (Construction / Mechanical) | 31-Mar-26 A | 2027-01-11 | 2027-03-10 | 2027-03-23 | 2026-12-22 | 2027-01-04
GFTransformersStructureWorks |  | 01-Apr-26 A | 2026-07-20 | 2026-06-21 | 2026-09-14 | 2026-02-21 | 2026-06-06
Sub-Structure |  | 01-Apr-26 A | 2026-06-29 | 2026-06-21 | 2026-09-14 | 02-Sep-25 A | 2026-03-09
A1150 | RCC Walls Upto FFL | 2026-05-12 | 2026-06-15 | 2026-07-07 | 2026-08-10 | 2026-03-25 | 2026-04-28
A26460 | Foundation Works (Excavation, PCC & RCC) | 01-Apr-26 A | 2026-05-04 | 2026-06-21 | 2026-07-07 | 2026-02-21 | 2026-03-26
A26470 | Waterproofing & Backfilling | 2026-05-26 | 2026-06-29 | 2026-08-11 | 2026-09-14 | 2026-04-08 | 2026-05-12
Super-Structure |  | 2026-06-16 | 2026-07-20 | 2026-08-11 | 2026-09-14 | 2026-03-10 | 2026-05-02
A1190 | RCC Walls above Ground | 2026-06-16 | 2026-07-20 | 2026-08-11 | 2026-09-14 | 2026-05-03 | 2026-06-06
RoadsandPavementConstruction |  | 2026-08-04 | 2027-01-26 | 2026-09-29 | 2027-03-23 | 2026-07-20 | 2027-01-11
A6860 | Subgarde and Sub-Base for Road | 2026-08-04 | 2026-10-01 | 2026-09-29 | 2026-11-26 | 2026-07-20 | 2026-09-16
A6870 | Base Course and Asphalt working | 2026-11-29 | 2027-01-26 | 2027-01-24 | 2027-03-23 | 2026-11-14 | 2027-01-11
A6880 | Concrete Flooring on Plant Side | 2026-10-03 | 2026-11-28 | 2026-11-28 | 2027-01-23 | 2026-09-17 | 2026-11-12
BFFoundation |  | 01-Apr-26 A | 2026-07-30 | 2026-09-23 | 2027-01-05 | 2026-02-21 | 2026-06-04
BFW3000 | General Civil Work - Equipment Foundations & Pipe Support (TBC) | 01-Apr-26 A | 2026-07-30 | 2026-09-23 | 2027-01-05 | 2026-02-21 | 2026-06-04
GFFoundations |  | 03-Jul-25 A | 2026-07-19 | 2026-06-15 | 2026-10-22 | 03-Jul-25 A | 2026-06-25
FG/OGCompressorandShleterFoundationincludingshelterconcretetrench |  | 31-Jul-25 A | 2026-04-29 | 2026-06-15 | 2026-06-27 | 31-Jul-25 A | 2026-03-23
A15660 | Excavation | 31-Jul-25 A | 23-Aug-25 A | 2026-06-15 | 2026-06-15 | 31-Jul-25 A | 23-Aug-25 A
A15670 | Surface leveling and compaction | 11-Aug-25 A | 25-Aug-25 A | 2026-06-15 | 2026-06-15 | 11-Aug-25 A | 25-Aug-25 A
A15740 | Lean concrete | 25-Aug-25 A | 30-Aug-25 A | 2026-06-15 | 2026-06-15 | 25-Aug-25 A | 30-Aug-25 A
A15750 | Water proofing and bitumen coating/sheet | 15-Oct-25 A | 16-Mar-26 A | 2026-06-15 | 2026-06-15 | 15-Oct-25 A | 2026-02-28
A15790 | Formworks | 19-Dec-25 A | 17-Mar-26 A | 2026-06-15 | 2026-06-15 | 19-Dec-25 A | 2026-02-28
A15840 | Rebar works | 15-Dec-25 A | 18-Mar-26 A | 2026-06-15 | 2026-06-15 | 15-Dec-25 A | 2026-02-28
A15850 | Concrete pouring | 19-Dec-25 A | 20-Mar-26 A | 2026-06-15 | 2026-06-15 | 19-Dec-25 A | 2026-03-09
A15860 | Concrete Curing | 27-Dec-25 A | 2026-04-29 | 2026-06-15 | 2026-06-27 | 27-Dec-25 A | 2026-03-04
A15870 | Formwork removal | 15-Mar-26 A | 2026-04-21 | 2026-06-15 | 2026-06-18 | 2026-02-21 | 2026-03-09
A15880 | Protective Coating | 15-Mar-26 A | 2026-04-21 | 2026-06-15 | 2026-06-18 | 2026-02-28 | 2026-03-16
A15890 | Back filling and compaction in layers | 15-Mar-26 A | 2026-04-21 | 2026-06-15 | 2026-06-18 | 2026-03-07 | 2026-03-23
PipeRack(PrimarySR81&SecondarySR80)Foundation |  | 23-Dec-25 A | 2026-05-25 | 2026-06-15 | 2026-07-22 | 23-Dec-25 A | 2026-04-09
A26240 | Excavation - Pipe Rack (SR81 & SR80) | 23-Dec-25 A | 20-Jan-26 A | 2026-06-15 | 2026-06-15 | 23-Dec-25 A | 20-Jan-26 A
A26250 | Surface leveling and compaction | 30-Dec-25 A | 2026-04-23 | 2026-06-15 | 2026-06-21 | 30-Dec-25 A | 2026-02-26
A26260 | Lean concrete | 06-Jan-26 A | 2026-04-23 | 2026-06-15 | 2026-06-21 | 06-Jan-26 A | 2026-02-26
A26270 | Water proofing and bitumen coating/sheet | 13-Jan-26 A | 2026-04-30 | 2026-06-15 | 2026-06-28 | 13-Jan-26 A | 2026-03-05
A26280 | Formworks | 21-Feb-26 A | 2026-05-02 | 2026-06-15 | 2026-06-29 | 2026-02-21 | 2026-03-16
A26290 | Rebar works | 22-Mar-26 A | 2026-05-02 | 2026-06-15 | 2026-06-29 | 2026-02-21 | 2026-03-16
A26300 | Concrete Pouring | 01-Mar-26 A | 2026-05-02 | 2026-06-15 | 2026-06-29 | 2026-02-28 | 2026-03-23
A26310 | Concrete Curing | 05-Mar-26 A | 2026-05-10 | 2026-06-15 | 2026-07-07 | 2026-03-01 | 2026-03-24
A26320 | Formwork removal | 2026-04-18 | 2026-05-11 | 2026-06-15 | 2026-07-08 | 2026-03-03 | 2026-03-26
A26330 | Protective Coating | 2026-04-25 | 2026-05-18 | 2026-06-22 | 2026-07-15 | 2026-03-10 | 2026-04-02
A26340 | Back filling and compaction in layers | 2026-05-02 | 2026-05-25 | 2026-06-29 | 2026-07-22 | 2026-03-17 | 2026-04-09
OGCompressorDischargeDripLeg(13-SP-7004) |  | 03-Mar-26 A | 2026-06-13 | 2026-07-16 | 2026-10-22 | 2026-03-28 | 2026-05-23
A24810 | Excavation | 2026-05-09 | 2026-05-13 | 2026-07-16 | 2026-07-21 | 2026-03-28 | 2026-03-31
A24820 | Surface leveling and compaction | 03-Mar-26 A | 2026-05-14 | 2026-09-21 | 2026-09-22 | 2026-04-01 | 2026-04-05
A24830 | Lean concrete | 04-Mar-26 A | 2026-05-16 | 2026-09-22 | 2026-09-23 | 2026-04-06 | 2026-04-09
A24840 | Water proofing and bitumen coating/sheet | 09-Mar-26 A | 2026-05-18 | 2026-09-23 | 2026-09-27 | 2026-04-11 | 2026-04-19
A24850 | Formworks | 10-Mar-26 A | 2026-05-20 | 2026-09-27 | 2026-09-29 | 2026-04-20 | 2026-04-27
A24860 | Rebar works | 10-Mar-26 A | 2026-05-20 | 2026-09-27 | 2026-09-29 | 2026-04-20 | 2026-04-27
A24870 | Concrete pouring | 10-Mar-26 A | 2026-05-23 | 2026-09-29 | 2026-09-30 | 2026-04-28 | 2026-05-02
A24880 | Concrete Curing | 21-Mar-26 A | 2026-05-26 | 2026-09-29 | 2026-10-04 | 2026-04-28 | 2026-05-13
A24890 | Formwork removal | 2026-05-20 | 2026-05-25 | 2026-09-29 | 2026-10-04 | 2026-04-30 | 2026-05-04
A24900 | Protective Coating | 2026-05-25 | 2026-06-03 | 2026-10-04 | 2026-10-13 | 2026-05-05 | 2026-05-13
A24910 | Back filling and compaction in layers | 2026-06-03 | 2026-06-13 | 2026-10-13 | 2026-10-22 | 2026-05-14 | 2026-05-23
PSA2PackagebyLinde(10Vessels) |  | 03-Jul-25 A | 20-Feb-26 A | 2026-10-22 | 2026-10-22 | 03-Jul-25 A | 20-Feb-26 A
A24920 | Excavation | 03-Jul-25 A | 15-Jul-25 A | 2026-10-22 | 2026-10-22 | 03-Jul-25 A | 15-Jul-25 A | Start of Construction
A24930 | Surface leveling and compaction | 11-Jul-25 A | 25-Jul-25 A | 2026-10-22 | 2026-10-22 | 11-Jul-25 A | 25-Jul-25 A
A24940 | Lean concrete | 01-Sep-25 A | 18-Sep-25 A | 2026-10-22 | 2026-10-22 | 01-Sep-25 A | 18-Sep-25 A
A24950 | Water proofing and bitumen coating/sheet | 19-Sep-25 A | 26-Sep-25 A | 2026-10-22 | 2026-10-22 | 19-Sep-25 A | 26-Sep-25 A
A24960 | Formworks | 27-Sep-25 A | 01-Feb-26 A | 2026-10-22 | 2026-10-22 | 27-Sep-25 A | 01-Feb-26 A
A24970 | Rebar works | 22-Oct-25 A | 05-Feb-26 A | 2026-10-22 | 2026-10-22 | 22-Oct-25 A | 05-Feb-26 A
A24980 | Concrete pouring | 04-Nov-25 A | 03-Feb-26 A | 2026-10-22 | 2026-10-22 | 04-Nov-25 A | 03-Feb-26 A
A24990 | Concrete Curing | 19-Dec-25 A | 16-Feb-26 A | 2026-10-22 | 2026-10-22 | 19-Dec-25 A | 16-Feb-26 A
A25000 | Formwork removal | 05-Feb-26 A | 05-Feb-26 A | 2026-10-22 | 2026-10-22 | 05-Feb-26 A | 05-Feb-26 A
A25010 | Protective Coating | 01-Jan-26 A | 15-Feb-26 A | 2026-10-22 | 2026-10-22 | 01-Jan-26 A | 15-Feb-26 A
A25020 | Back filling and compaction in layers | 01-Feb-26 A | 20-Feb-26 A | 2026-10-22 | 2026-10-22 | 01-Feb-26 A | 20-Feb-26 A
OGCompAfterCooler(13-HE-709) |  | 01-Mar-26 A | 2026-06-13 | 2026-07-21 | 2026-10-08 | 2026-04-01 | 2026-05-16
A25030 | Excavation | 01-Mar-26 A | 2026-05-16 | 2026-07-21 | 2026-07-25 | 2026-04-01 | 2026-04-04
A25040 | Surface leveling and compaction | 01-Mar-26 A | 2026-05-18 | 2026-09-10 | 2026-09-12 | 2026-04-05 | 2026-04-06
A25050 | Lean concrete | 01-Mar-26 A | 2026-05-19 | 2026-09-12 | 2026-09-14 | 2026-04-07 | 2026-04-08
A25060 | Water proofing and bitumen coating/sheet | 01-Mar-26 A | 2026-05-27 | 2026-09-21 | 2026-09-22 | 2026-04-16 | 2026-04-18
A25070 | Formworks | 01-Mar-26 A | 2026-06-02 | 2026-09-22 | 2026-09-27 | 2026-04-19 | 2026-04-26
A25080 | Rebar works | 01-Mar-26 A | 2026-06-02 | 2026-09-22 | 2026-09-27 | 2026-04-19 | 2026-04-26
A25090 | Concrete pouring | 01-Mar-26 A | 2026-06-02 | 2026-09-22 | 2026-09-27 | 2026-04-27 | 2026-05-04
A25100 | Concrete Curing | 01-Mar-26 A | 2026-06-07 | 2026-09-22 | 2026-10-03 | 2026-04-28 | 2026-05-13
A25110 | Formwork removal | 2026-05-27 | 2026-06-04 | 2026-09-22 | 2026-09-30 | 2026-04-30 | 2026-05-07
A25120 | Protective Coating | 2026-06-01 | 2026-06-06 | 2026-09-27 | 2026-10-01 | 2026-05-05 | 2026-05-09
A25130 | Back filling and compaction in layers | 2026-06-06 | 2026-06-13 | 2026-10-01 | 2026-10-08 | 2026-05-10 | 2026-05-16
FGComp2ndStageDischargeDrum(13-VV-707) |  | 01-Mar-26 A | 2026-06-22 | 2026-07-25 | 2026-09-23 | 2026-04-05 | 2026-06-02
A25140 | Excavation | 2026-05-16 | 2026-05-19 | 2026-07-25 | 2026-07-28 | 2026-04-05 | 2026-04-07
A25150 | Surface leveling and compaction | 01-Mar-26 A | 2026-05-20 | 2026-08-22 | 2026-08-23 | 2026-04-08 | 2026-04-09
A25160 | Lean concrete | 01-Mar-26 A | 2026-05-20 | 2026-08-23 | 2026-08-23 | 2026-04-11 | 2026-04-11
A25170 | Water proofing and bitumen coating/sheet | 01-Mar-26 A | 2026-05-30 | 2026-08-30 | 2026-08-31 | 2026-04-19 | 2026-04-22
A25180 | Formworks | 01-Mar-26 A | 2026-06-01 | 2026-09-01 | 2026-09-03 | 2026-04-23 | 2026-04-30
A25190 | Rebar works | 01-Mar-26 A | 2026-06-01 | 2026-09-01 | 2026-09-03 | 2026-04-23 | 2026-04-30
A25200 | Concrete pouring | 01-Mar-26 A | 2026-06-01 | 2026-09-01 | 2026-09-03 | 2026-05-07 | 2026-05-14
A25210 | Concrete Curing | 01-Mar-26 A | 2026-06-03 | 2026-09-01 | 2026-09-06 | 2026-05-09 | 2026-05-24
A25220 | Formwork removal | 2026-05-30 | 2026-06-07 | 2026-09-01 | 2026-09-08 | 2026-05-11 | 2026-05-18
A25230 | Protective Coating | 2026-06-07 | 2026-06-14 | 2026-09-09 | 2026-09-15 | 2026-05-19 | 2026-05-25
A25240 | Back filling and compaction in layers | 2026-06-14 | 2026-06-22 | 2026-09-16 | 2026-09-23 | 2026-05-26 | 2026-06-02
FGComp1stStageSuctionDrum(13-VV-705) |  | 09-Feb-26 A | 2026-06-27 | 2026-07-28 | 2026-10-01 | 2026-04-08 | 2026-06-07
A25360 | Excavation | 2026-05-19 | 2026-05-23 | 2026-07-28 | 2026-08-01 | 2026-04-08 | 2026-04-11
A25370 | Surface leveling and compaction | 26-Feb-26 A | 2026-05-24 | 2026-08-29 | 2026-08-29 | 2026-04-12 | 2026-04-13
A25380 | Lean concrete | 26-Feb-26 A | 2026-05-25 | 2026-08-30 | 2026-08-30 | 2026-04-14 | 2026-04-15
A25390 | Water proofing and bitumen coating/sheet | 26-Feb-26 A | 2026-06-03 | 2026-09-07 | 2026-09-08 | 2026-04-23 | 2026-04-27
A25400 | Formworks | 26-Feb-26 A | 2026-06-08 | 2026-09-09 | 2026-09-13 | 2026-04-28 | 2026-05-05
A25410 | Rebar works | 26-Feb-26 A | 2026-06-08 | 2026-09-09 | 2026-09-13 | 2026-04-28 | 2026-05-05
A25420 | Concrete pouring | 09-Feb-26 A | 2026-06-08 | 2026-09-09 | 2026-09-13 | 2026-05-12 | 2026-05-19
A25430 | Concrete Curing | 01-Mar-26 A | 2026-06-11 | 2026-09-09 | 2026-09-16 | 2026-05-13 | 2026-05-28
A25440 | Formwork removal | 2026-06-03 | 2026-06-11 | 2026-09-09 | 2026-09-16 | 2026-05-16 | 2026-05-23
A25450 | Protective Coating | 2026-06-11 | 2026-06-18 | 2026-09-17 | 2026-09-23 | 2026-05-24 | 2026-05-30
A25460 | Back filling and compaction in layers | 2026-06-18 | 2026-06-27 | 2026-09-24 | 2026-10-01 | 2026-05-31 | 2026-06-07
FGComp2ndStageSuctionDrum(13-VV-706) |  | 25-Feb-26 A | 2026-06-29 | 2026-08-01 | 2026-09-19 | 2026-04-12 | 2026-06-10
A25470 | Excavation | 2026-05-23 | 2026-05-26 | 2026-08-01 | 2026-08-04 | 2026-04-12 | 2026-04-14
A25480 | Surface leveling and compaction | 25-Feb-26 A | 2026-05-27 | 2026-08-17 | 2026-08-18 | 2026-04-15 | 2026-04-16
A25490 | Lean concrete | 25-Feb-26 A | 2026-05-28 | 2026-08-18 | 2026-08-18 | 2026-04-18 | 2026-04-19
A25500 | Water proofing and bitumen coating/sheet | 25-Feb-26 A | 2026-06-06 | 2026-08-25 | 2026-08-26 | 2026-04-27 | 2026-04-30
A25510 | Formworks | 25-Feb-26 A | 2026-06-08 | 2026-08-27 | 2026-08-30 | 2026-05-02 | 2026-05-09
A25520 | Rebar works | 25-Feb-26 A | 2026-06-08 | 2026-08-27 | 2026-08-30 | 2026-05-02 | 2026-05-09
A25530 | Concrete pouring | 22-Mar-26 A | 2026-06-08 | 2026-08-27 | 2026-08-30 | 2026-05-16 | 2026-05-23
A25540 | Concrete Curing | 25-Mar-26 A | 2026-06-10 | 2026-08-27 | 2026-09-01 | 2026-05-17 | 2026-06-01
A25550 | Formwork removal | 2026-06-06 | 2026-06-14 | 2026-08-27 | 2026-09-03 | 2026-05-19 | 2026-05-26
A25560 | Protective Coating | 2026-06-14 | 2026-06-21 | 2026-09-05 | 2026-09-10 | 2026-05-27 | 2026-06-02
A25570 | Back filling and compaction in layers | 2026-06-21 | 2026-06-29 | 2026-09-12 | 2026-09-19 | 2026-06-03 | 2026-06-10
PSA2SlopeDrum(70-VV-1415) |  | 2026-05-26 | 2026-07-19 | 2026-08-04 | 2026-10-22 | 2026-04-15 | 2026-06-07
A25580 | Excavation | 2026-05-26 | 2026-05-31 | 2026-08-04 | 2026-08-09 | 2026-04-15 | 2026-04-19
A25590 | Surface leveling and compaction | 2026-05-31 | 2026-06-04 | 2026-09-03 | 2026-09-08 | 2026-04-20 | 2026-04-23
A25600 | Lean concrete | 2026-06-04 | 2026-06-09 | 2026-09-08 | 2026-09-13 | 2026-04-25 | 2026-04-28
A25610 | Water proofing and bitumen coating/sheet | 2026-06-09 | 2026-06-17 | 2026-09-13 | 2026-09-21 | 2026-04-29 | 2026-05-06
A25620 | Formworks | 2026-06-17 | 2026-06-25 | 2026-09-21 | 2026-09-29 | 2026-05-07 | 2026-05-14
A25630 | Rebar works | 2026-06-17 | 2026-06-25 | 2026-09-21 | 2026-09-29 | 2026-05-07 | 2026-05-14
A25640 | Concrete pouring | 2026-06-25 | 2026-06-30 | 2026-09-29 | 2026-10-04 | 2026-05-16 | 2026-05-19
A25650 | Concrete Curing | 2026-06-25 | 2026-07-12 | 2026-09-29 | 2026-10-15 | 2026-05-16 | 2026-05-31
A25660 | Formwork removal | 2026-06-28 | 2026-07-02 | 2026-10-01 | 2026-10-06 | 2026-05-18 | 2026-05-21
A25670 | Protective Coating | 2026-07-02 | 2026-07-11 | 2026-10-06 | 2026-10-14 | 2026-05-23 | 2026-05-30
A25680 | Back filling and compaction in layers | 2026-07-11 | 2026-07-19 | 2026-10-14 | 2026-10-22 | 2026-05-31 | 2026-06-07
FGCompAfterCooler(13-HE-704) |  | 21-Feb-26 A | 2026-07-04 | 2026-08-09 | 2026-09-10 | 2026-04-20 | 2026-06-04
A25690 | Excavation | 2026-05-31 | 2026-06-03 | 2026-08-09 | 2026-08-12 | 2026-04-20 | 2026-04-22
A25700 | Surface leveling and compaction | 21-Feb-26 A | 2026-06-06 | 2026-08-12 | 2026-08-13 | 2026-04-23 | 2026-04-25
A25710 | Lean concrete | 21-Feb-26 A | 2026-06-07 | 2026-08-13 | 2026-08-15 | 2026-04-26 | 2026-04-27
A25720 | Water proofing and bitumen coating/sheet | 21-Feb-26 A | 2026-06-15 | 2026-08-22 | 2026-08-23 | 2026-05-05 | 2026-05-06
A25730 | Formworks | 21-Feb-26 A | 2026-06-20 | 2026-08-24 | 2026-08-29 | 2026-05-07 | 2026-05-14
A25740 | Rebar works | 21-Feb-26 A | 2026-06-20 | 2026-08-24 | 2026-08-29 | 2026-05-07 | 2026-05-14
A25750 | Concrete pouring | 21-Feb-26 A | 2026-06-20 | 2026-08-24 | 2026-08-29 | 2026-05-14 | 2026-05-21
A25760 | Concrete Curing | 21-Feb-26 A | 2026-06-24 | 2026-08-24 | 2026-09-02 | 2026-05-16 | 2026-05-31
A25770 | Formwork removal | 2026-06-15 | 2026-06-23 | 2026-08-24 | 2026-08-31 | 2026-05-18 | 2026-05-25
A25780 | Protective Coating | 2026-06-18 | 2026-06-28 | 2026-08-27 | 2026-09-05 | 2026-05-21 | 2026-05-30
A25790 | Back filling and compaction in layers | 2026-06-28 | 2026-07-04 | 2026-09-06 | 2026-09-10 | 2026-05-31 | 2026-06-04
FGCompInterstageCooler(13-HE-703) |  | 01-Mar-26 A | 2026-07-06 | 2026-08-24 | 2026-09-24 | 2026-04-23 | 2026-06-08
A26490 | Excavation | 2026-06-03 | 2026-06-07 | 2026-08-24 | 2026-08-27 | 2026-04-23 | 2026-04-26
A26500 | Surface leveling and compaction | 01-Mar-26 A | 2026-06-09 | 2026-08-27 | 2026-08-29 | 2026-04-27 | 2026-04-28
A26510 | Lean concrete | 01-Mar-26 A | 2026-06-10 | 2026-08-29 | 2026-08-30 | 2026-04-29 | 2026-04-30
A26520 | Water proofing and bitumen coating/sheet | 01-Mar-26 A | 2026-06-18 | 2026-09-06 | 2026-09-07 | 2026-05-09 | 2026-05-10
A26530 | Formworks | 01-Mar-26 A | 2026-06-23 | 2026-09-08 | 2026-09-12 | 2026-05-11 | 2026-05-18
A26540 | Rebar works | 01-Mar-26 A | 2026-06-23 | 2026-09-08 | 2026-09-12 | 2026-05-11 | 2026-05-18
A26550 | Concrete pouring | 01-Mar-26 A | 2026-06-23 | 2026-09-08 | 2026-09-12 | 2026-05-18 | 2026-05-25
A26560 | Concrete Curing | 01-Mar-26 A | 2026-06-27 | 2026-09-08 | 2026-09-16 | 2026-05-19 | 2026-06-03
A26570 | Formwork removal | 2026-06-18 | 2026-06-27 | 2026-09-08 | 2026-09-15 | 2026-05-21 | 2026-05-28
A26580 | Protective Coating | 2026-06-22 | 2026-06-30 | 2026-09-12 | 2026-09-19 | 2026-05-26 | 2026-06-02
A26590 | Back filling and compaction in layers | 2026-06-30 | 2026-07-06 | 2026-09-20 | 2026-09-24 | 2026-06-03 | 2026-06-08
OGComp2ndStageSuctionDrum(13-VV-713) |  | 10-Mar-26 A | 2026-07-14 | 2026-09-16 | 2026-10-22 | 2026-04-27 | 2026-06-25
A25800 | Excavation | 2026-06-07 | 2026-06-10 | 2026-09-16 | 2026-09-19 | 2026-04-27 | 2026-04-29
A25810 | Surface leveling and compaction | 10-Mar-26 A | 2026-06-11 | 2026-09-20 | 2026-09-20 | 2026-04-30 | 2026-05-02
A25820 | Lean concrete | 10-Mar-26 A | 2026-06-13 | 2026-09-20 | 2026-09-21 | 2026-05-03 | 2026-05-04
A25830 | Water proofing and bitumen coating/sheet | 10-Mar-26 A | 2026-06-21 | 2026-09-28 | 2026-09-29 | 2026-05-12 | 2026-05-16
A25840 | Formworks | 10-Mar-26 A | 2026-06-23 | 2026-09-29 | 2026-10-01 | 2026-05-17 | 2026-05-24
A25850 | Rebar works | 10-Mar-26 A | 2026-06-23 | 2026-09-29 | 2026-10-01 | 2026-05-17 | 2026-05-24
A25860 | Concrete pouring | 10-Mar-26 A | 2026-06-23 | 2026-09-29 | 2026-10-01 | 2026-05-31 | 2026-06-07
A25870 | Concrete Curing | 10-Mar-26 A | 2026-06-25 | 2026-09-29 | 2026-10-04 | 2026-06-01 | 2026-06-16
A25880 | Formwork removal | 2026-06-21 | 2026-06-29 | 2026-09-29 | 2026-10-07 | 2026-06-03 | 2026-06-10
A25890 | Protective Coating | 2026-06-29 | 2026-07-06 | 2026-10-07 | 2026-10-14 | 2026-06-11 | 2026-06-17
A25900 | Back filling and compaction in layers | 2026-07-06 | 2026-07-14 | 2026-10-14 | 2026-10-22 | 2026-06-18 | 2026-06-25
OGBufferDrum(13-VV-712) |  | 31-Dec-25 A | 2026-05-18 | 2026-07-28 | 2026-10-22 | 01-Jan-25 A | 12-Apr-25 A
A26020 | Excavation | 31-Dec-25 A | 15-Jan-26 A | 2026-07-28 | 2026-07-28 | 31-Dec-25 A | 15-Jan-26 A
A26030 | Surface leveling and compaction | 10-Jan-26 A | 17-Jan-26 A | 2026-09-21 | 2026-09-21 | 10-Jan-26 A | 17-Jan-26 A
A26040 | Lean concrete | 19-Jan-26 A | 21-Jan-26 A | 2026-09-21 | 2026-09-21 | 19-Jan-26 A | 21-Jan-26 A
A26050 | Water proofing and bitumen coating/sheet | 22-Jan-26 A | 20-Mar-26 A | 2026-09-21 | 2026-09-21 | 22-Jan-26 A | 2026-02-24
A26060 | Formworks | 01-Mar-26 A | 20-Mar-26 A | 2026-09-21 | 2026-09-21 | 2026-02-24 | 2026-03-14
A26070 | Rebar works | 01-Mar-26 A | 20-Mar-26 A | 2026-09-21 | 2026-09-21 | 2026-02-24 | 2026-03-14
A26080 | Concrete pouring | 04-Mar-26 A | 2026-04-19 | 2026-09-21 | 2026-09-22 | 2026-03-14 | 2026-03-22
A26090 | Concrete Curing | 10-Mar-26 A | 2026-04-27 | 2026-09-21 | 2026-09-30 | 2026-03-14 | 2026-03-30
A26100 | Formwork removal | 2026-04-18 | 2026-05-03 | 2026-09-21 | 2026-10-07 | 2026-03-16 | 2026-04-01
A26110 | Protective Coating | 2026-05-04 | 2026-05-10 | 2026-10-07 | 2026-10-14 | 2026-04-01 | 2026-04-08
A26120 | Back filling and compaction in layers | 2026-05-11 | 2026-05-18 | 2026-10-14 | 2026-10-22 | 2026-04-08 | 2026-04-16
OGCompressorInterstageCooler(13-HE-708) |  | 01-Jan-26 A | 2026-05-14 | 2026-06-25 | 2026-10-08 | 01-Jan-26 A | 2026-04-02
A26130 | Excavation | 01-Jan-26 A | 23-Jan-26 A | 2026-06-25 | 2026-06-25 | 01-Jan-26 A | 23-Jan-26 A
A26140 | Surface leveling and compaction | 25-Feb-26 A | 2026-04-19 | 2026-06-25 | 2026-06-27 | 2026-02-21 | 2026-02-22
A26150 | Lean concrete | 25-Feb-26 A | 2026-04-20 | 2026-06-27 | 2026-06-29 | 2026-02-23 | 2026-02-24
A26160 | Water proofing and bitumen coating/sheet | 25-Feb-26 A | 2026-04-29 | 2026-07-06 | 2026-07-07 | 2026-03-04 | 2026-03-05
A26170 | Formworks | 25-Feb-26 A | 2026-05-11 | 2026-07-07 | 2026-07-19 | 2026-03-07 | 2026-03-23
A26180 | Rebar works | 25-Feb-26 A | 2026-05-11 | 2026-07-07 | 2026-07-19 | 2026-03-07 | 2026-03-23
A26190 | Concrete pouring | 25-Feb-26 A | 2026-05-09 | 2026-07-07 | 2026-07-16 | 2026-03-14 | 2026-03-26
A26200 | Concrete Curing | 04-Mar-26 A | 2026-05-12 | 2026-09-23 | 2026-10-06 | 2026-03-15 | 2026-04-02
A26210 | Formwork removal | 2026-04-29 | 2026-05-13 | 2026-09-23 | 2026-10-07 | 2026-03-17 | 2026-03-30
A26220 | Protective Coating | 2026-05-03 | 2026-05-10 | 2026-09-27 | 2026-10-04 | 2026-03-22 | 2026-03-28
A26230 | Back filling and compaction in layers | 2026-05-10 | 2026-05-14 | 2026-10-04 | 2026-10-08 | 2026-03-29 | 2026-04-01
StructuralSteelandShades |  | 09-Mar-25 A | 2026-11-11 | 2026-06-16 | 2027-03-09 | 09-Mar-25 A | 2026-09-26
TAPrefabricationofSteelStructureforBFW |  | 09-Mar-25 A | 18-May-25 A | 2026-06-16 | 2026-06-16 | 09-Mar-25 A | 18-May-25 A
A61610 | TA prefabrication of steel structure for BFW | 09-Mar-25 A | 18-May-25 A | 2026-06-16 | 2026-06-16 | 09-Mar-25 A | 18-May-25 A
TAErectionofSteelStructureforBFW |  | 19-Apr-25 A | 24-May-25 A | 2026-06-16 | 2026-06-16 | 19-Apr-25 A | 24-May-25 A
A23330 | Erection of Steel Structure of BFW Preheater - Pre TA ( By external Subcontractor) | 19-Apr-25 A | 24-May-25 A | 2026-06-16 | 2026-06-16 | 19-Apr-25 A | 24-May-25 A
BFStructureSteel |  | 2026-06-16 | 2026-08-01 | 2026-11-22 | 2027-01-05 | 2026-04-29 | 2026-06-14
BFW4020 | Structure Installation (Platform on the existing Piperack + strengthen) | 2026-06-16 | 2026-08-01 | 2026-11-22 | 2027-01-05 | 2026-04-29 | 2026-06-14
GFSteelWorks |  | 2026-07-20 | 2026-11-11 | 2026-07-20 | 2027-03-09 | 2026-05-19 | 2026-09-26
A17810 | Compressors Area- Steel Structure Erection | 2026-07-20 | 2026-11-11 | 2026-07-20 | 2026-11-11 | 2026-05-19 | 2026-09-10 |  |  | CP | CP
A17820 | Pipe Rack SR81 - Structure Installation | 2026-08-29 | 2026-11-11 | 2026-08-29 | 2026-11-11 | 2026-06-28 | 2026-09-10 |  |  | CP | CP
A18420 | Secondary Pipe Rack (SR80) Structure installation | 2026-10-15 | 2026-11-11 | 2027-01-05 | 2027-02-01 | 2026-08-15 | 2026-09-10
A23500 | Piping Platforms | 2026-10-13 | 2026-11-11 | 2026-10-13 | 2026-11-11 | 2026-08-12 | 2026-09-10 |  |  | CP | CP
A23510 | Transformer Shed - Sub Station Building | 2026-10-03 | 2026-10-27 | 2027-02-13 | 2027-03-09 | 2026-09-01 | 2026-09-26
ExternalFinishes |  | 2026-07-19 | 2026-10-11 | 2026-12-30 | 2027-03-23 | 2026-07-18 | 2026-10-08
A61620 | External Finishing | 2026-07-19 | 2026-10-11 | 2026-12-30 | 2027-03-23 | 2026-07-18 | 2026-10-08
InternalFinishes |  | 2026-04-18 | 2026-11-03 | 2026-09-02 | 2027-03-23 | 2026-02-21 | 2026-10-21
GFSISBuildingArchitecturalWorks |  | 2026-04-18 | 2026-08-05 | 2026-09-14 | 2026-12-15 | 2026-02-21 | 2026-08-03
A1540 | Block Works and E&I Conduiting Works | 2026-05-04 | 2026-06-14 | 2026-09-14 | 2026-10-24 | 2026-05-03 | 2026-06-11
A1550 | Plaster Works | 2026-05-25 | 2026-07-19 | 2026-10-05 | 2026-11-28 | 2026-05-24 | 2026-07-16
A1560 | Painting Works | 2026-06-17 | 2026-08-05 | 2026-10-28 | 2026-12-15 | 2026-06-16 | 2026-08-03
A1570 | Roof Treatments | 2026-05-18 | 2026-06-21 | 2026-11-12 | 2026-12-15 | 2026-05-17 | 2026-06-18
A1580 | PCC Flooring Works | 2026-04-18 | 2026-05-17 | 2026-09-21 | 2026-10-20 | 2026-02-21 | 2026-03-22
A1660 | Floor Finshes (Tiling, Skirting & Dado etc.) | 2026-05-18 | 2026-07-12 | 2026-10-21 | 2026-12-15 | 2026-03-23 | 2026-05-17
GFTransformersArchitecturalWorks |  | 2026-07-04 | 2026-11-03 | 2026-10-26 | 2027-03-23 | 2026-05-20 | 2026-10-21
A1240 | Painting External Works | 2026-07-04 | 2026-08-23 | 2026-10-26 | 2026-12-15 | 2026-05-20 | 2026-07-09
A1250 | Foundation for E&I Support Structure | 2026-07-21 | 2026-08-26 | 2026-11-09 | 2026-12-15 | 2026-06-07 | 2026-07-13
A1260 | Installation of Fence and Doors | 2026-07-21 | 2026-08-15 | 2026-11-21 | 2026-12-15 | 2026-06-07 | 2026-07-01
A1270 | Steel Structure / Corrugated Sheet Installation | 2026-10-07 | 2026-11-03 | 2027-02-24 | 2027-03-23 | 2026-09-24 | 2026-10-21
GFSub-StationArchitecturalWorks |  | 2026-04-25 | 2026-08-20 | 2026-09-02 | 2027-03-23 | 2026-03-28 | 2026-07-23
GroundFloor-CellarArea |  | 2026-04-25 | 2026-07-15 | 2026-12-31 | 2027-03-23 | 24-Jan-26 A | 2026-03-26
A1630 | E&I Support Structure | 2026-04-25 | 2026-05-20 | 2026-12-31 | 2027-01-26 | 2026-03-28 | 2026-04-22
A1640 | Flooring works | 2026-05-21 | 2026-06-24 | 2027-01-27 | 2027-03-02 | 2026-04-23 | 2026-05-27
A1650 | Installation of Fence and Doors | 2026-06-25 | 2026-07-15 | 2027-03-03 | 2027-03-23 | 2026-05-28 | 2026-06-17
FirstFloor |  | 2026-05-09 | 2026-08-20 | 2026-09-02 | 2026-12-15 | 2026-03-11 | 2027-01-04
A1090 | Plaster Works | 2026-05-24 | 2026-07-18 | 2026-09-17 | 2026-11-11 | 2026-04-26 | 2026-06-20
A1180 | PCC Flooring Works | 2026-06-13 | 2026-07-13 | 2026-10-17 | 2026-11-16 | 2026-05-16 | 2026-06-15
A1200 | Floor Finshes (Tiling, Skirting & Dado etc.) | 2026-07-14 | 2026-08-11 | 2026-11-17 | 2026-12-15 | 2026-06-16 | 2026-07-14
A26430 | Block Works and E&I Conduiting Works | 2026-05-09 | 2026-07-02 | 2026-09-02 | 2026-10-27 | 2026-04-11 | 2026-06-04
A26440 | Roof Treatments | 2026-05-09 | 2026-06-17 | 2026-11-07 | 2026-12-15 | 2026-05-23 | 2026-06-30
A26450 | Painting Works (Release for Electrical Equipments) | 2026-07-02 | 2026-08-20 | 2026-10-27 | 2026-12-15 | 2026-06-04 | 2026-07-23
Others |  | 09-Jan-25 A | 20-Jun-25 A | 2026-06-15 | 2026-06-15 | 20-Dec-24 A | 2027-07-20
Topographic |  | 09-Jan-25 A | 23-May-25 A | 2026-06-15 | 2026-06-15 | 09-Jan-25 A | 23-May-25 A
Topographic/UGSurvey |  | 09-Jan-25 A | 22-May-25 A | 2026-06-15 | 2026-06-15 | 09-Jan-25 A | 22-May-25 A
A28960 | TBE for Topo,UG & Getechnical Survey_IFD/IFC | 11-Feb-25 A | 01-Mar-25 A | 2026-06-15 | 2026-06-15 | 11-Feb-25 A | 01-Mar-25 A
A56190 | TBE for Topo,UG & Getechnical Survey_IFR | 09-Jan-25 A | 15-Jan-25 A | 2026-06-15 | 2026-06-15 | 09-Jan-25 A | 15-Jan-25 A
A56200 | TBE for Topo,UG & Getechnical Survey_RCC | 16-Jan-25 A | 10-Feb-25 A | 2026-06-15 | 2026-06-15 | 16-Jan-25 A | 10-Feb-25 A
E1060 | Geotech / Survery of Site | 09-May-25 A | 15-May-25 A | 2026-06-15 | 2026-06-15 | 09-May-25 A | 15-May-25 A
E1070 | Topo/ UG Scanning Survey | 18-Apr-25 A | 30-Apr-25 A | 2026-06-15 | 2026-06-15 | 18-Apr-25 A | 30-Apr-25 A
E1080 | TBE & PO issuance of Geotech / UG Scanning | 02-Mar-25 A | 20-Mar-25 A | 2026-06-15 | 2026-06-15 | 02-Mar-25 A | 20-Mar-25 A
E1090 | Mobilization of Geotech / UG Scanning | 01-May-25 A | 08-May-25 A | 2026-06-15 | 2026-06-15 | 01-May-25 A | 08-May-25 A
E1100 | Reports of Getech Investigation / UG Scanning | 16-May-25 A | 22-May-25 A | 2026-06-15 | 2026-06-15 | 16-May-25 A | 22-May-25 A
E1110 | CICPA Passes for Geotech Sub Contractor | 21-Mar-25 A | 17-Apr-25 A | 2026-06-15 | 2026-06-15 | 21-Mar-25 A | 17-Apr-25 A
Geotech/Topographic/UGSurvey |  | 11-Feb-25 A | 23-May-25 A | 2026-06-15 | 2026-06-15 | 11-Feb-25 A | 23-May-25 A
E1000 | RFQ of Geotech / UG Scanning | 11-Feb-25 A | 01-Mar-25 A | 2026-06-15 | 2026-06-15 | 11-Feb-25 A | 01-Mar-25 A
E1010 | TBE & PO issuance of Geotech / UG Scanning | 02-Mar-25 A | 20-Mar-25 A | 2026-06-15 | 2026-06-15 | 02-Mar-25 A | 20-Mar-25 A
E1020 | Mobilization of Geotech / UG Scanning | 01-May-25 A | 08-May-25 A | 2026-06-15 | 2026-06-15 | 01-May-25 A | 08-May-25 A
E1030 | Geotech / Survery of Site | 10-May-25 A | 16-May-25 A | 2026-06-15 | 2026-06-15 | 10-May-25 A | 16-May-25 A
E1040 | Reports of Getech Investigation / UG Scanning | 17-May-25 A | 23-May-25 A | 2026-06-15 | 2026-06-15 | 17-May-25 A | 23-May-25 A
E1050 | CICPA Passes for Geotech Sub Contractor | 21-Mar-25 A | 17-Apr-25 A | 2026-06-15 | 2026-06-15 | 21-Mar-25 A | 17-Apr-25 A
Piling(Norequired) |  | 20-Jun-25 A | 20-Jun-25 A | 2026-06-15 | 2026-06-15 | 20-Jun-25 A | 20-Jun-25 A
PilingWorks |  | 20-Jun-25 A | 20-Jun-25 A | 2026-06-15 | 2026-06-15 | 20-Jun-25 A | 20-Jun-25 A
A15550 | Piling Work (Compressors, Sheds & Equipment) | 20-Jun-25 A | 20-Jun-25 A | 2026-06-15 | 2026-06-15 | 20-Jun-25 A | 20-Jun-25 A
A15570 | Piling Works - Pipe Racks and OG Buffer Drum | 20-Jun-25 A | 20-Jun-25 A | 2026-06-15 | 2026-06-15 | 20-Jun-25 A | 20-Jun-25 A
A15610 | Piling work PSA2 Unit (10 Vessels) | 20-Jun-25 A | 20-Jun-25 A | 2026-06-15 | 2026-06-15 | 20-Jun-25 A | 20-Jun-25 A
A15650 | Test Piles (including curing time) | 20-Jun-25 A | 20-Jun-25 A | 2026-06-15 | 2026-06-15 | 20-Jun-25 A | 20-Jun-25 A
A15690 | Data for Test pile |  | 20-Jun-25 A |  | 2026-06-15 |  | 20-Jun-25 A
A15720 | PO for Piling Contractor | 20-Jun-25 A | 20-Jun-25 A | 2026-06-15 | 2026-06-15 | 20-Jun-25 A | 20-Jun-25 A
A15730 | Mobilization of piling contractor | 20-Jun-25 A | 20-Jun-25 A | 2026-06-15 | 2026-06-15 | 20-Jun-25 A | 20-Jun-25 A
A23610 | Mobilization for Production Piles | 20-Jun-25 A | 20-Jun-25 A | 2026-06-15 | 2026-06-15 | 20-Jun-25 A | 20-Jun-25 A
MechanicalConstruction |  | 05-Mar-25 A | 2027-02-07 | 2026-06-16 | 2027-09-20 | 05-Mar-25 A | 2027-01-17
Equipmenterectionandinstallation |  | 19-Apr-25 A | 2027-02-01 | 2026-06-16 | 2027-03-23 | 19-Apr-25 A | 2026-12-01
HVACWorks |  | 2026-07-26 | 2026-11-28 | 2027-01-03 | 2027-03-23 | 2026-07-12 | 2026-09-29
A18570 | Fabrication and installation of ductwork inside the building | 2026-07-26 | 2026-08-24 | 2027-01-03 | 2027-02-01 | 2026-07-12 | 2026-08-10
A18580 | Fabrication and installation of ductwork outside the building | 2026-07-30 | 2026-08-29 | 2027-01-18 | 2027-02-16 | 2026-07-16 | 2026-08-15
A18590 | Insulation of ductwork outside the building | 2026-08-13 | 2026-09-16 | 2027-02-01 | 2027-03-07 | 2026-07-30 | 2026-09-02
A18760 | Installation of electrical works inside the building (excluding installation of HVAC power control panel) | 2026-08-02 | 2026-08-31 | 2027-01-19 | 2027-02-17 | 2026-07-19 | 2026-08-17
A18770 | Installation of piping inside and outside the building | 2026-07-26 | 2026-08-24 | 2027-01-03 | 2027-02-01 | 2026-07-12 | 2026-08-10
A18780 | Pressure testing of pipes | 2026-08-25 | 2026-09-07 | 2027-02-02 | 2027-02-15 | 2026-08-11 | 2026-08-24
A18790 | Flushing, cleaning, air blowing of Piping | 2026-09-01 | 2026-09-14 | 2027-02-09 | 2027-02-22 | 2026-08-18 | 2026-08-31
A18820 | Assembly of Air Handling Unit (AHU) | 2026-10-31 | 2026-11-04 | 2027-02-23 | 2027-02-28 | 2026-09-01 | 2026-09-06
A18830 | Installation and alignment of air handling units (AHU) | 2026-11-05 | 2026-11-11 | 2027-03-01 | 2027-03-07 | 2026-09-07 | 2026-09-13
A18840 | Installation of Exhaust Fan | 2026-11-05 | 2026-11-11 | 2027-03-08 | 2027-03-14 | 2026-09-07 | 2026-09-13
A18850 | Complete Duct Connection to AHU & Fan | 2026-11-07 | 2026-11-17 | 2027-03-08 | 2027-03-18 | 2026-09-08 | 2026-09-19
A18860 | Installation and alignment of refrigerant cycle and chiller | 2026-11-05 | 2026-11-11 | 2027-03-01 | 2027-03-07 | 2026-09-07 | 2026-09-13
A18870 | Installation of buffer tank | 2026-11-05 | 2026-11-11 | 2027-03-01 | 2027-03-07 | 2026-09-07 | 2026-09-13
A18890 | Insulation of refrigerant pipework outside the building | 2026-09-03 | 2026-09-20 | 2027-02-18 | 2027-03-07 | 2026-08-20 | 2026-09-06
A18910 | Installation of electrical / power system and HVAC control system | 2026-09-01 | 2026-09-17 | 2027-02-18 | 2027-03-07 | 2026-08-27 | 2026-09-13
A18920 | HVAC Testing and Commissioning works | 2026-11-12 | 2026-11-28 | 2027-03-08 | 2027-03-23 | 2026-09-14 | 2026-09-29
GFSanitaryWaterSumpPump(01No)(70-PC-1409) |  | 2026-07-15 | 2026-08-31 | 2026-12-27 | 2027-02-10 | 2026-07-04 | 2026-08-18
A22600 | Installation of Sanitary Water Sump Pump (70-PC-1409) | 2026-07-15 | 2026-07-29 | 2026-12-27 | 2027-01-10 | 2026-07-04 | 2026-07-16
A22830 | Alignment of Sanitary Water Sump Pump (70-PC-1409) | 2026-07-29 | 2026-08-19 | 2027-01-10 | 2027-01-31 | 2026-07-18 | 2026-08-06
A22840 | Grouting of Sanitary Water Sump Pump (70-PC-1409) | 2026-08-19 | 2026-08-31 | 2027-01-31 | 2027-02-10 | 2026-08-08 | 2026-08-18
GFFeedGasCompressorandAuxilaryEquipmentErrection |  | 2026-06-15 | 2027-02-01 | 2026-06-20 | 2027-02-01 | 2026-03-24 | 2026-12-01
FGComp1stStageSuctionDrum(13-VV-705) |  | 2026-07-11 | 2026-09-05 | 2026-10-17 | 2026-12-10 | 2026-04-08 | 2026-06-07
A22480 | Delivery inspection, Unpacked and Installation of FG Comp 1st Stage Suction Drum(13-VV-705) | 2026-07-11 | 2026-07-19 | 2026-10-17 | 2026-10-24 | 2026-06-22 | 2026-06-29
A23020 | Alignment of FG Comp 1st Stage Suction Drum(13-VV-705) | 2026-07-19 | 2026-07-27 | 2026-10-25 | 2026-11-01 | 2026-06-30 | 2026-07-07
A23030 | Grouting of FG Comp 1st Stage Suction Drum(13-VV-705) | 2026-07-27 | 2026-08-02 | 2026-11-02 | 2026-11-07 | 2026-07-08 | 2026-07-13
A23080 | Internals (Demister) of FG Comp 1st Stage Suction Drum(13-VV-705) | 2026-08-02 | 2026-08-19 | 2026-11-08 | 2026-11-24 | 2026-07-14 | 2026-07-30
A23230 | Insulation of FG Comp 1st Stage Suction Drum(13-VV-705) | 2026-08-19 | 2026-09-05 | 2026-11-25 | 2026-12-10 | 2026-08-01 | 2026-08-16
FGCompressorInterstageCooler(13-HE-703) |  | 2026-07-06 | 2026-09-03 | 2026-09-26 | 2026-11-23 | 2026-06-09 | 2026-08-06
A23600 | Intallation of FG Compressor Interstage Cooler (13-HE-703) | 2026-07-06 | 2026-07-18 | 2026-09-26 | 2026-10-06 | 2026-06-09 | 2026-06-20
A23910 | Alignment of FG Compressor Interstage Cooler (13-HE-703) | 2026-07-18 | 2026-07-29 | 2026-10-07 | 2026-10-18 | 2026-06-21 | 2026-07-01
A23920 | Grouting of FG Compressor Interstage Cooler (13-HE-703) | 2026-07-29 | 2026-08-10 | 2026-10-19 | 2026-10-29 | 2026-07-02 | 2026-07-13
A23980 | Insulation of FG Compressor Interstage Cooler (13-HE-703) | 2026-08-10 | 2026-09-03 | 2026-10-31 | 2026-11-23 | 2026-07-14 | 2026-08-06
FGCompAfterCooler(13-HE-704) |  | 2026-07-18 | 2026-09-15 | 2026-09-26 | 2026-11-23 | 2026-04-20 | 2026-06-04
A22540 | Installation of FG Comp After Cooler ( 13-HE-704) | 2026-07-18 | 2026-07-29 | 2026-09-26 | 2026-10-06 | 2026-06-20 | 2026-06-30
A23240 | Alignment of FG Comp After Cooler ( 13-HE-704) | 2026-07-29 | 2026-08-10 | 2026-10-07 | 2026-10-18 | 2026-07-01 | 2026-07-12
A23250 | Grouting of FG Comp After Cooler ( 13-HE-704) | 2026-08-10 | 2026-08-22 | 2026-10-19 | 2026-10-29 | 2026-07-13 | 2026-07-23
A23370 | Insulation of FG Comp After Cooler ( 13-HE-704) | 2026-08-22 | 2026-09-15 | 2026-10-31 | 2026-11-23 | 2026-07-25 | 2026-08-17
FGComp2ndStageDischargeDrum(13-VV-707) |  | 2026-07-18 | 2026-09-01 | 2026-10-08 | 2026-11-23 | 2026-04-05 | 2026-06-02
A22530 | Installation of FG Comp 2nd Stage Discharge Drum (13-VV-707) | 2026-07-18 | 2026-07-22 | 2026-10-08 | 2026-10-13 | 2026-07-14 | 2026-07-19
A23380 | Alignment of FG Comp 2nd Stage Discharge Drum (13-VV-707) | 2026-07-23 | 2026-07-28 | 2026-10-14 | 2026-10-19 | 2026-07-20 | 2026-07-25
A23390 | Grouting of FG Comp 2nd Stage Discharge Drum (13-VV-707) | 2026-07-29 | 2026-08-03 | 2026-10-20 | 2026-10-25 | 2026-07-26 | 2026-07-30
A23400 | Internals (Demister Pad) of FG Comp 2nd Stage Discharge Drum (13-VV-707) | 2026-08-04 | 2026-08-15 | 2026-10-26 | 2026-11-05 | 2026-08-01 | 2026-08-11
A23410 | Insulation of FG Comp 2nd Stage Discharge Drum (13-VV-707) | 2026-08-16 | 2026-09-01 | 2026-11-07 | 2026-11-23 | 2026-08-12 | 2026-08-29
FGComp2ndStageSuctionDrum(13-VV-706) |  | 2026-07-13 | 2026-09-02 | 2026-10-04 | 2026-11-23 | 2026-04-12 | 2026-06-10
A22490 | Delivery inspection, Unpacked and Installation of FG Comp 2nd Stage Suction Drum (13-VV-706) | 2026-07-13 | 2026-07-25 | 2026-10-04 | 2026-10-14 | 2026-06-25 | 2026-07-06
A23420 | Alignment of FG Comp 2nd Stage Suction Drum (13-VV-706) | 2026-07-25 | 2026-07-30 | 2026-10-15 | 2026-10-20 | 2026-07-07 | 2026-07-12
A23430 | Grouting of FG Comp 2nd Stage Suction Drum (13-VV-706) | 2026-07-30 | 2026-08-05 | 2026-10-21 | 2026-10-26 | 2026-07-13 | 2026-07-18
A23440 | Internals (Demister Pad) of FG Comp 2nd Stage Suction Drum (13-VV-706) | 2026-08-05 | 2026-08-17 | 2026-10-27 | 2026-11-07 | 2026-07-19 | 2026-07-29
A23450 | Insulation of FG Comp 2nd Stage Suction Drum (13-VV-706) | 2026-08-17 | 2026-09-02 | 2026-11-08 | 2026-11-23 | 2026-07-30 | 2026-08-15
FeedGas(FG)CompressorInstallation |  | 2026-06-15 | 2027-02-01 | 2026-06-20 | 2027-02-01 | 2026-03-24 | 2026-12-01
C1000 | FG Foundation Plan - Foundation Check & Dimensional Examination - FG Compressor | 2026-06-15 | 2026-06-22 | 2026-06-20 | 2026-06-27 | 2026-03-24 | 2026-04-09 |  |  | CP | CP
C1001 | Installation of FG Compressor (Setting of Pad, Preparation, Position and Leveling) | 2026-07-06 | 2026-07-19 | 2026-07-06 | 2026-07-19 | 2026-05-05 | 2026-05-18 |  |  | CP | CP
C1002 | Setting of FG Compressor Base Plate (Temporary settng, Elevation, Level, Tolerance, Position) | 2026-06-28 | 2026-07-05 | 2026-06-28 | 2026-07-05 | 2026-04-11 | 2026-05-04 |  |  | CP | CP
C1003 | Grouting - FG Compressor | 2026-08-17 | 2026-08-29 | 2026-10-01 | 2026-10-12 | 2026-06-16 | 2026-06-28
C1004 | Pre-alignment of FG Compressor | 2026-07-30 | 2026-08-17 | 2026-09-14 | 2026-09-30 | 2026-05-30 | 2026-06-16
C1005 | Coupling Alignment - FG Compressor | 2026-08-29 | 2026-09-21 | 2026-10-20 | 2026-11-11 | 2026-06-28 | 2026-07-21
C1006 | Installation of Auxiliary Equipment - FG Compressor |  | 2026-11-02 |  | 2026-12-10 |  | 2026-09-15
C1007 | Installation of Piping - FG Compressor | 2026-11-12 | 2027-01-03 | 2026-11-12 | 2027-01-03 | 2026-09-12 | 2026-11-02 |  |  | CP | CP
C1008 | E&I Installation - FG Compressor | 2026-12-06 | 2027-01-20 | 2026-12-06 | 2027-01-20 | 2026-10-05 | 2026-11-19 |  |  | CP | CP
C1009 | Punch List Close Out FG Compressor | 2027-01-21 | 2027-02-01 | 2027-01-21 | 2027-02-01 | 2026-11-21 | 2026-12-01 |  |  | CP | CP
C1031 | Installation of FG Compressor Main Driver Motor | 2026-07-20 | 2026-07-30 | 2026-09-02 | 2026-09-13 | 2026-05-19 | 2026-05-30
GFOffGasCompressorandAuxilaryEquipmentErrection |  | 2026-04-21 | 2027-01-24 | 2026-08-05 | 2027-02-10 | 2026-03-24 | 2026-11-23
OffGas(OG)CompressorInstallation |  | 2026-04-21 | 2027-01-24 | 2026-08-05 | 2027-02-01 | 2026-03-24 | 2026-11-23
C1069 | OG Foundation Plan - Foundation Check & Dimensional Examination | 2026-04-21 | 2026-05-09 | 2026-08-05 | 2026-08-23 | 2026-03-24 | 2026-04-09
C1079 | Installation of OG Compressor (Setting of Pad, Preparation, Position and Leveling) | 2026-06-02 | 2026-06-16 | 2026-09-16 | 2026-09-30 | 2026-05-05 | 2026-05-18
C1089 | Setting of OG Compressor Base Plate (Temporary setting, Elevation, Level, Tolerance, Position) | 2026-05-09 | 2026-06-02 | 2026-08-23 | 2026-09-16 | 2026-04-11 | 2026-05-04
C1099 | Grouting - OG Compressor | 2026-07-20 | 2026-07-30 | 2026-10-27 | 2026-11-08 | 2026-06-15 | 2026-06-25
C1109 | Pre-alignment of OG Compressor | 2026-06-25 | 2026-07-13 | 2026-10-10 | 2026-10-27 | 2026-05-28 | 2026-06-14
C1119 | Coupling and Alignment - OG Compressor | 2026-08-01 | 2026-08-23 | 2026-11-08 | 2026-12-01 | 2026-06-27 | 2026-07-19
C1129 | Installation of Auxiliary Equipment - OG Compressor |  | 2026-09-02 |  | 2026-12-07 |  | 2026-08-29
C1139 | Installation of Piping - OG Compressor | 2026-11-23 | 2027-01-02 | 2026-12-01 | 2027-01-11 | 2026-09-22 | 2026-11-01 |  |  | CP | CP
C1149 | E&I Installation - OG Compressor | 2026-11-29 | 2027-01-09 | 2026-12-08 | 2027-01-17 | 2026-09-28 | 2026-11-08 |  |  | CP | CP
C1159 | Punch List Close Out (Mechanical) - OG Compressor | 2027-01-09 | 2027-01-24 | 2027-01-18 | 2027-02-01 | 2026-11-08 | 2026-11-23 |  |  | CP | CP
C1169 | Installation of OG Compressor Main Driver Motor | 2026-06-16 | 2026-06-25 | 2026-09-30 | 2026-10-10 | 2026-05-19 | 2026-05-27
OGBufferDrum(13-VV-712) |  | 2026-06-01 | 2026-08-18 | 2026-12-01 | 2027-02-10 | 01-Jan-25 A | 12-Apr-25 A
A22500 | Installation of OG Buffer Drum (13-VV-712) | 2026-06-22 | 2026-06-28 | 2026-12-15 | 2026-12-21 | 2026-07-04 | 2026-07-09
A22790 | Alignment of OG Buffer Drum (13-VV-712) | 2026-06-29 | 2026-07-05 | 2026-12-29 | 2027-01-04 | 2026-07-11 | 2026-07-16
A22800 | Grouting of OG Buffer Drum (13-VV-712) | 2026-07-06 | 2026-07-12 | 2027-01-05 | 2027-01-11 | 2026-07-18 | 2026-07-23
A22810 | Internals (Demister) of OG Buffer Drum (13-VV-712) | 2026-07-20 | 2026-08-02 | 2027-01-12 | 2027-01-25 | 2026-08-01 | 2026-08-13
A22820 | Insulation of OG Buffer Drum (13-VV-712) | 2026-08-03 | 2026-08-18 | 2027-01-26 | 2027-02-10 | 2026-08-15 | 2026-08-30
A25270 | Ground Preparatory Works for Crane | 2026-06-01 | 2026-06-14 | 2026-12-01 | 2026-12-14 | 2026-06-13 | 2026-06-25
A25280 | Scafolding Works | 2026-06-29 | 2026-07-19 | 2026-12-22 | 2027-01-11 | 2026-07-11 | 2026-07-30
OGCompressorInterstageCooler(13-HE-708) |  | 2026-06-01 | 2026-07-15 | 2026-10-22 | 2026-12-07 | 01-Jan-26 A | 2026-04-02
A22570 | Intallation of OG Compressor Interstage Cooler (13-HE-708) | 2026-06-01 | 2026-06-04 | 2026-10-22 | 2026-10-27 | 2026-04-22 | 2026-04-27
A23460 | Alignment of OG Compressor Interstage Cooler (13-HE-708) | 2026-06-06 | 2026-06-10 | 2026-10-27 | 2026-11-02 | 2026-04-27 | 2026-05-03
A23470 | Grouting of OG Compressor Interstage Cooler (13-HE-708) | 2026-06-11 | 2026-06-22 | 2026-11-02 | 2026-11-14 | 2026-05-03 | 2026-05-14
A23480 | Insulation of OG Compressor Interstage Cooler (13-HE-708) | 2026-06-23 | 2026-07-15 | 2026-11-14 | 2026-12-07 | 2026-05-14 | 2026-06-07
OGCompAfterCooler(13-HE-709) |  | 2026-07-19 | 2026-09-02 | 2026-10-22 | 2026-12-07 | 2026-04-01 | 2026-05-16
A22550 | Installation of OG Comp After Cooler ( 13-HE-709) | 2026-07-19 | 2026-07-25 | 2026-10-22 | 2026-10-28 | 2026-06-27 | 2026-07-01
A23490 | Alignment of OG Comp After Cooler ( 13-HE-709) | 2026-07-25 | 2026-07-29 | 2026-10-28 | 2026-11-02 | 2026-07-02 | 2026-07-06
A23930 | Grouting of OG Comp After Cooler ( 13-HE-709) | 2026-07-29 | 2026-08-10 | 2026-11-02 | 2026-11-14 | 2026-07-07 | 2026-07-18
A23990 | Insulation of OG Comp After Cooler ( 13-HE-709) | 2026-08-10 | 2026-09-02 | 2026-11-14 | 2026-12-07 | 2026-07-19 | 2026-08-10
OGCompressorDischargeDripLeg(13-SP-7004) |  | 2026-10-01 | 2026-11-07 | 2026-12-12 | 2027-01-17 | 2026-03-28 | 2026-05-23
A3490 | Installation of OG Compressor Discharge Drip Leg | 2026-10-01 | 2026-10-05 | 2026-12-12 | 2026-12-15 | 2026-07-23 | 2026-07-27
A3500 | Alignment of OG Compressor Discharge Drip Leg | 2026-10-06 | 2026-10-10 | 2026-12-16 | 2026-12-20 | 2026-07-28 | 2026-08-01
A3510 | Grouting of OG Compressor Discharge Drip Leg | 2026-10-11 | 2026-10-14 | 2026-12-21 | 2026-12-24 | 2026-08-02 | 2026-08-05
A3520 | Internals of OG Compressor Discharge Drip Leg | 2026-10-15 | 2026-10-26 | 2026-12-26 | 2027-01-05 | 2026-08-06 | 2026-08-17
A3530 | Insulation of OG Compressor Discharge Drip Leg | 2026-10-27 | 2026-11-07 | 2027-01-06 | 2027-01-17 | 2026-08-18 | 2026-08-29
OGComp2ndStageSuctionDrum(13-VV-713) |  | 2026-07-08 | 2026-08-24 | 2026-10-21 | 2026-12-07 | 2026-04-27 | 2026-06-25
A22510 | Installation of OG Comp 2nd Stage Suction Drum (13-VV-713) | 2026-07-08 | 2026-07-14 | 2026-10-21 | 2026-10-27 | 2026-06-21 | 2026-06-25
A24000 | Alignment of OG Comp 2nd Stage Suction Drum (13-VV-713) | 2026-07-14 | 2026-07-20 | 2026-10-27 | 2026-11-02 | 2026-06-27 | 2026-07-01
A24010 | Grouting of OG Comp 2nd Stage Suction Drum (13-VV-713) | 2026-07-20 | 2026-07-26 | 2026-11-02 | 2026-11-08 | 2026-07-02 | 2026-07-07
A25250 | Internals (Demster Pad) of OG Comp 2nd Stage Suction Drum (13-VV-713) | 2026-07-26 | 2026-08-06 | 2026-11-08 | 2026-11-19 | 2026-07-08 | 2026-07-19
A25260 | Insulation of OG Comp 2nd Stage Suction Drum (13-VV-713) | 2026-08-06 | 2026-08-24 | 2026-11-19 | 2026-12-07 | 2026-07-20 | 2026-08-05
TABoilerFeedWaterInstallation |  | 19-Apr-25 A | 24-May-25 A | 2026-06-16 | 2026-06-16 | 19-Apr-25 A | 24-May-25 A
A3787 | Installation of BFW Preheater | 19-Apr-25 A | 24-May-25 A | 2026-06-16 | 2026-06-16 | 19-Apr-25 A | 24-May-25 A
BFMechanicalEquipments |  | 2026-08-01 | 2026-09-16 | 2027-01-06 | 2027-03-06 | 2026-06-14 | 2026-07-30
A22560 | Installation of C4 Guard Regeneration Cooler (50-HE-1410) | 2026-08-01 | 2026-09-16 | 2027-01-06 | 2027-02-21 | 2026-06-14 | 2026-07-30
A9650 | Installation of Dripleg (1 No) | 2026-08-01 | 2026-09-16 | 2027-01-06 | 2027-02-21 | 2026-06-14 | 2026-07-30
A9660 | Installation of Coalescer (1 No) | 2026-08-01 | 2026-09-16 | 2027-01-19 | 2027-03-06 | 2026-06-14 | 2026-07-30
GFPSA2PackagebyLinde(10Vessels) |  | 16-Mar-26 A | 2026-11-23 | 2026-11-09 | 2027-02-10 | 2026-03-22 | 2026-10-20
A22610 | Installation of PSA2 Package by Linde ( 10 Vessels) | 16-Mar-26 A | 03-Apr-26 A | 2026-11-16 | 2026-11-16 | 2026-03-22 | 2026-05-30
A22850 | Alignment of PSA2 Package by Linde ( 10 Vessels) | 01-Apr-26 A | 2026-05-26 | 2026-11-16 | 2026-11-25 | 2026-05-31 | 2026-07-21
A22860 | Grouting of PSA2 Package by Linde ( 10 Vessels) | 01-Apr-26 A | 2026-06-20 | 2026-11-09 | 2026-12-20 | 2026-06-24 | 2026-08-15
A22870 | Internals of PSA2 Package by Linde ( 10 Vessels) | 2026-10-03 | 2026-11-23 | 2026-12-21 | 2027-02-10 | 2026-08-30 | 2026-10-20
GFWaterSumpPump(02Nos)(70-PC-1407) |  | 2026-08-02 | 2026-09-16 | 2026-12-27 | 2027-02-10 | 2026-06-17 | 2026-08-02
A22590 | Installation of Water Sump Pump (70-PC-1407) | 2026-08-02 | 2026-08-15 | 2026-12-27 | 2027-01-09 | 2026-06-17 | 2026-06-30
A22880 | Alignment of Water Sump Pump (70-PC-1407) | 2026-08-16 | 2026-09-05 | 2027-01-10 | 2027-01-30 | 2026-07-01 | 2026-07-21
A22890 | Grouting of Water Sump Pump (70-PC-1407) | 2026-09-06 | 2026-09-16 | 2027-01-31 | 2027-02-10 | 2026-07-22 | 2026-08-02
GFPSA2SlopeDrum(70-VV-1415) |  | 2026-08-02 | 2026-09-13 | 2026-12-31 | 2027-02-10 | 2026-07-20 | 2026-08-30
A22520 | Installation of PSA2 Slope Drum ( 70-VV-1415) | 2026-08-02 | 2026-08-08 | 2026-12-31 | 2027-01-05 | 2026-07-20 | 2026-07-25
A22930 | Alignment of PSA2 Slope Drum ( 70-VV-1415) | 2026-08-08 | 2026-08-13 | 2027-01-06 | 2027-01-11 | 2026-07-26 | 2026-07-30
A22960 | Grouting of PSA2 Slope Drum ( 70-VV-1415) | 2026-08-13 | 2026-08-19 | 2027-01-12 | 2027-01-17 | 2026-08-01 | 2026-08-05
A22990 | Internals of PSA2 Slope Drum ( 70-VV-1415) | 2026-08-19 | 2026-08-31 | 2027-01-18 | 2027-01-28 | 2026-08-06 | 2026-08-17
A23010 | Insulation of PSA2 Slope Drum ( 70-VV-1415) | 2026-08-31 | 2026-09-13 | 2027-01-30 | 2027-02-10 | 2026-08-18 | 2026-08-30
GFEOTCraneforFGCompressor |  | 2026-11-12 | 2026-12-13 | 2026-12-16 | 2027-01-20 | 2026-09-12 | 2026-10-12
C1319 | LT rail line installation | 2026-11-12 | 2026-11-23 | 2026-12-16 | 2026-12-27 | 2026-09-12 | 2026-09-22
C1329 | Assembly of main girders at ground level | 2026-11-12 | 2026-11-23 | 2026-12-21 | 2026-12-31 | 2026-09-12 | 2026-09-22
C1339 | Installation of electrical equipment | 2026-11-12 | 2026-11-16 | 2026-12-28 | 2026-12-31 | 2026-09-12 | 2026-09-15
C1349 | Installation of end carriage & main girder | 2026-11-24 | 2026-11-28 | 2027-01-02 | 2027-01-05 | 2026-09-23 | 2026-09-27
C1359 | Crab erection | 2026-11-29 | 2026-12-01 | 2027-01-06 | 2027-01-09 | 2026-09-28 | 2026-09-30
C1369 | Installation of the platform, hand railing, cabin, ladder, DSL cage and DSL guard | 2026-12-02 | 2026-12-13 | 2027-01-10 | 2027-01-20 | 2026-10-01 | 2026-10-12
GFEOTCraneforOGCompressor |  | 2026-11-19 | 2026-12-14 | 2026-12-23 | 2027-01-17 | 2026-09-19 | 2026-10-13
C1259 | LT rail line installation | 2026-11-19 | 2026-11-30 | 2026-12-23 | 2027-01-03 | 2026-09-19 | 2026-09-29
C1269 | Assembly of main girders at ground level | 2026-11-19 | 2026-11-30 | 2026-12-23 | 2027-01-03 | 2026-09-19 | 2026-09-29
C1279 | Installation of end carriage & main girder | 2026-12-01 | 2026-12-05 | 2027-01-04 | 2027-01-07 | 2026-09-30 | 2026-10-04
C1289 | Cran erection | 2026-12-06 | 2026-12-07 | 2027-01-09 | 2027-01-10 | 2026-10-05 | 2026-10-06
C1299 | Installation of the platform, hand railing, cabin, ladder, DSL cage and DSL guard | 2026-12-06 | 2026-12-14 | 2027-01-09 | 2027-01-17 | 2026-10-05 | 2026-10-13
C1309 | Installation of electrical equipment | 2026-11-19 | 2026-11-23 | 2026-12-30 | 2027-01-03 | 2026-09-19 | 2026-09-22
PipingFabrication |  | 05-Mar-25 A | 18-Apr-25 A | 2026-06-16 | 2026-06-16 | 05-Mar-25 A | 18-Apr-25 A
TAPipingWork |  | 05-Mar-25 A | 18-Apr-25 A | 2026-06-16 | 2026-06-16 | 05-Mar-25 A | 18-Apr-25 A
A17730 | Installation of Scaffolding | 05-Mar-25 A | 08-Apr-25 A | 2026-06-16 | 2026-06-16 | 05-Mar-25 A | 08-Apr-25 A
BFW4000 | Prefabrication of Tie-ins Spools | 28-Mar-25 A | 04-Apr-25 A | 2026-06-16 | 2026-06-16 | 28-Mar-25 A | 04-Apr-25 A
BFW4010 | Prefabrication of Piping Spools for the BFW | 11-Apr-25 A | 18-Apr-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 18-Apr-25 A
BFW4050 | Sand blastinfg and painting | 01-Apr-25 A | 15-Apr-25 A | 2026-06-16 | 2026-06-16 | 01-Apr-25 A | 15-Apr-25 A
PipingandValvesInstallation |  | 29-Mar-25 A | 2027-02-07 | 2026-06-16 | 2027-05-12 | 29-Mar-25 A | 2027-01-17
BFPipingWorks |  | 21-Mar-26 A | 2026-12-10 | 2026-07-08 | 2027-02-02 | 2026-02-21 | 2026-10-27
A18520 | Scaffolding for Piping errection on Piperack | 21-Mar-26 A | 2026-05-31 | 2026-07-08 | 2026-08-20 | 2026-02-21 | 2026-03-31
A9670 | Piping Erection / Installation in Brown Field | 2026-05-16 | 2026-10-03 | 2026-07-08 | 2026-11-24 | 2026-04-01 | 2026-08-18
BFW4030 | Piping Hydrotesting - BF | 2026-09-21 | 2026-11-05 | 2026-11-14 | 2026-12-29 | 2026-08-08 | 2026-09-22
BFW4040 | Piping connections with tie-ins | 2026-10-25 | 2026-12-10 | 2026-12-17 | 2027-02-02 | 2026-09-10 | 2026-10-27
TATie-InExecution-A/GTie-Ins |  | 29-Mar-25 A | 24-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 24-May-25 A
Package1 |  | 11-Apr-25 A | 24-May-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 24-May-25 A
TailgasfromTieInpointEU3toEU3H2Tag#IP-B-B3-H3-L-2010 |  | 11-Apr-25 A | 24-May-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 24-May-25 A
A38390 | Start of Work | 11-Apr-25 A | 24-May-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 24-May-25 A
A38400 | Removal of insulation & Wallthickness measurement | 11-Apr-25 A | 24-May-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 24-May-25 A
A38410 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 11-Apr-25 A | 24-May-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 24-May-25 A
A38420 | Install pipe supports (if any) | 25-Apr-25 A | 26-Apr-25 A | 2026-06-16 | 2026-06-16 | 25-Apr-25 A | 26-Apr-25 A
A38430 | Prepare and hydrotest up to XX BarG (if required) | 25-Apr-25 A | 26-Apr-25 A | 2026-06-16 | 2026-06-16 | 25-Apr-25 A | 26-Apr-25 A
A38440 | Hydrotest witness inspection (if required) | 25-Apr-25 A | 26-Apr-25 A | 2026-06-16 | 2026-06-16 | 25-Apr-25 A | 26-Apr-25 A
A9680 | Obtain Work Permit | 11-Apr-25 A | 24-May-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 24-May-25 A
A9710 | Cut old piping (existing line 45024), haul to ground level | 11-Apr-25 A | 24-May-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 24-May-25 A
A9720 | Grinding, bevelling of old piping & fit-up with new spool | 11-Apr-25 A | 24-May-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 24-May-25 A
A9730 | Full welding of joints & installation of Tie-In spool 45076 | 25-Apr-25 A | 26-Apr-25 A | 2026-06-16 | 2026-06-16 | 25-Apr-25 A | 26-Apr-25 A
A9740 | Inspection NDT / RT of selected joints | 25-Apr-25 A | 26-Apr-25 A | 2026-06-16 | 2026-06-16 | 25-Apr-25 A | 26-Apr-25 A
A9780 | Reinstall back piping components (TW/TE, TG, PT, PG if any) | 25-Apr-25 A | 26-Apr-25 A | 2026-06-16 | 2026-06-16 | 25-Apr-25 A | 26-Apr-25 A
A9790 | Touch-up painting works | 25-Apr-25 A | 15-May-25 A | 2026-06-16 | 2026-06-16 | 25-Apr-25 A | 15-May-25 A
A9800 | Deblinding, remove temporary support / scaffolds | 25-Apr-25 A | 15-May-25 A | 2026-06-16 | 2026-06-16 | 25-Apr-25 A | 15-May-25 A
A9810 | Reinstall insulation (if any) | 25-Apr-25 A | 15-May-25 A | 2026-06-16 | 2026-06-16 | 25-Apr-25 A | 15-May-25 A
A9820 | Torquing / flange management & hand-over to Ops | 25-Apr-25 A | 15-May-25 A | 2026-06-16 | 2026-06-16 | 25-Apr-25 A | 15-May-25 A
A9830 | End of Work | 16-May-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 16-May-25 A | 17-May-25 A
TailgasTag#IP-B-B3-M3-L-3010 |  | 11-Apr-25 A | 24-May-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 24-May-25 A
A38280 | Start of Work | 11-Apr-25 A | 24-May-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 24-May-25 A
A38290 | Obtain Work Permit | 11-Apr-25 A | 24-May-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 24-May-25 A
A38300 | Removal of insulation & Wallthickness measurement | 11-Apr-25 A | 24-May-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 24-May-25 A
A38310 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 11-Apr-25 A | 24-May-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 24-May-25 A
A38320 | Cut old piping (existing line 45024), haul to ground level | 11-Apr-25 A | 24-May-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 24-May-25 A
A38330 | Grinding, bevelling of old piping & fit-up with new spool | 11-Apr-25 A | 24-May-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 24-May-25 A
A38340 | Full welding of joints & installation of Tie-In spool 45024 | 25-Apr-25 A | 26-Apr-25 A | 2026-06-16 | 2026-06-16 | 25-Apr-25 A | 26-Apr-25 A
A38350 | Inspection NDT / RT of selected joints | 25-Apr-25 A | 26-Apr-25 A | 2026-06-16 | 2026-06-16 | 25-Apr-25 A | 26-Apr-25 A
A38360 | Install pipe supports (if any) | 25-Apr-25 A | 26-Apr-25 A | 2026-06-16 | 2026-06-16 | 25-Apr-25 A | 26-Apr-25 A
A38370 | Torquing / flange management & hand-over to Ops | 25-Apr-25 A | 15-May-25 A | 2026-06-16 | 2026-06-16 | 25-Apr-25 A | 15-May-25 A
A38380 | End of Work | 16-May-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 16-May-25 A | 17-May-25 A
A9590 | Prepare and hydrotest up to XX BarG (if required) | 25-Apr-25 A | 26-Apr-25 A | 2026-06-16 | 2026-06-16 | 25-Apr-25 A | 26-Apr-25 A
A9600 | Hydrotest witness inspection (if required) | 25-Apr-25 A | 26-Apr-25 A | 2026-06-16 | 2026-06-16 | 25-Apr-25 A | 26-Apr-25 A
A9610 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 25-Apr-25 A | 26-Apr-25 A | 2026-06-16 | 2026-06-16 | 25-Apr-25 A | 26-Apr-25 A
A9620 | Touch-up painting works | 25-Apr-25 A | 15-May-25 A | 2026-06-16 | 2026-06-16 | 25-Apr-25 A | 15-May-25 A
A9630 | Deblinding, remove temporary support / scaffolds | 25-Apr-25 A | 15-May-25 A | 2026-06-16 | 2026-06-16 | 25-Apr-25 A | 15-May-25 A
A9640 | Reinstall insulation (if any) | 25-Apr-25 A | 15-May-25 A | 2026-06-16 | 2026-06-16 | 25-Apr-25 A | 15-May-25 A
TailgasTag#IP-B-M3-B3-L-3020 |  | 11-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 17-May-25 A
A38270 | Touch-up painting works | 16-May-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 16-May-25 A | 17-May-25 A
A9330 | Start of Work | 11-Apr-25 A | 11-Apr-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 11-Apr-25 A
A9340 | Obtain Work Permit | 11-Apr-25 A | 11-Apr-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 11-Apr-25 A
A9350 | Removal of insulation & Wallthickness measurement | 11-Apr-25 A | 11-Apr-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 11-Apr-25 A
A9360 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 11-Apr-25 A | 11-Apr-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 11-Apr-25 A
A9370 | Cut old piping (existing line 45024), haul to ground level | 11-Apr-25 A | 11-Apr-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 11-Apr-25 A
A9380 | Grinding, bevelling of old piping & fit-up with new spool | 11-Apr-25 A | 11-Apr-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 11-Apr-25 A
A9390 | Full welding of joints & installation of Tie-In spool 45024 | 11-Apr-25 A | 11-Apr-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 11-Apr-25 A
A9400 | Inspection NDT / RT of selected joints | 11-Apr-25 A | 11-Apr-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 11-Apr-25 A
A9410 | Install pipe supports (if any) | 11-Apr-25 A | 11-Apr-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 11-Apr-25 A
A9420 | Prepare and hydrotest up to XX BarG (if required) | 16-May-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 16-May-25 A | 17-May-25 A
A9430 | Hydrotest witness inspection (if required) | 16-May-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 16-May-25 A | 17-May-25 A
A9440 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 16-May-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 16-May-25 A | 17-May-25 A
A9460 | Deblinding, remove temporary support / scaffolds | 16-May-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 16-May-25 A | 17-May-25 A
A9470 | Reinstall insulation (if any) | 16-May-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 16-May-25 A | 17-May-25 A
A9480 | Torquing / flange management & hand-over to Ops | 16-May-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 16-May-25 A | 17-May-25 A
A9490 | End of Work | 16-May-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 16-May-25 A | 17-May-25 A
TailgasTag#IP-B-B3-M3-L-3030 |  | 11-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 17-May-25 A
A38230 | Cut old piping (existing line 45024), haul to ground level | 11-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 17-May-25 A
A38240 | Grinding, bevelling of old piping & fit-up with new spool | 11-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 17-May-25 A
A38250 | Full welding of joints & installation of Tie-In spool 45075 | 11-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 17-May-25 A
A38260 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 11-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 17-May-25 A
A9160 | Start of Work | 11-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 17-May-25 A
A9170 | Obtain Work Permit | 11-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 17-May-25 A
A9180 | Removal of insulation & Wall thickness measurement | 11-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 17-May-25 A
A9190 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 11-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 17-May-25 A
A9230 | Inspection NDT / RT of selected joints | 11-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 17-May-25 A
A9240 | Install pipe supports (if any) | 11-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 17-May-25 A
A9250 | Prepare and hydrotest up to XX BarG | 11-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 17-May-25 A
A9260 | Hydrotest witness inspection | 11-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 17-May-25 A
A9280 | Touch-up painting works | 11-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 17-May-25 A
A9290 | Deblinding, remove temporary support / scaffolds | 11-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 17-May-25 A
A9300 | Reinstall insulation (if any) | 11-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 17-May-25 A
A9310 | Torquing / flange management & hand-over to Ops | 11-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 17-May-25 A
A9320 | End of Work | 11-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 17-May-25 A
TailgasTag#IP-B-B3-M3-L-3050 |  | 11-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 17-May-25 A
A8990 | Start of Work | 11-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 17-May-25 A
A9000 | Obtain Work Permit | 11-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 17-May-25 A
A9010 | Removal of existing valve | 11-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 17-May-25 A
A9020 | Installation of new valve | 11-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 17-May-25 A
A9030 | Gas measurement | 11-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 17-May-25 A
A9120 | Deblinding, remove temporary support / scaffolds | 11-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 17-May-25 A
A9130 | Reinstall insulation (if any) | 11-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 17-May-25 A
A9140 | Torquing / flange management & hand-over to Ops | 11-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 17-May-25 A
A9150 | End of Work | 11-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 17-May-25 A
Regenerationgasfrom50-HE-1402Tag#IP-B-B3-M3-L-3090 |  | 11-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 17-May-25 A
A8820 | Start of Work | 11-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 17-May-25 A
A8830 | Obtain Work Permit | 11-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 17-May-25 A
A8840 | Wallthickness measurement | 11-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 17-May-25 A
A8850 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 11-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 17-May-25 A
A8860 | Cut old piping (existing line 140025), haul to ground level | 11-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 17-May-25 A
A8870 | Grinding, bevelling of old piping & fit-up with new spool | 11-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 17-May-25 A
A8880 | Full welding of joints & installation of Tie-In spool 140068 | 11-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 17-May-25 A
A8890 | Inspection NDT / RT of selected joints | 11-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 17-May-25 A
A8900 | Install pipe supports (if any) | 11-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 17-May-25 A
A8910 | Prepare and hydrotest up to XX BarG | 11-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 17-May-25 A
A8920 | Hydrotest witness inspection | 11-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 17-May-25 A
A8930 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 11-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 17-May-25 A
A8940 | Touch-up painting works | 11-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 17-May-25 A
A8950 | Deblinding, remove temporary support / scaffolds | 11-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 17-May-25 A
A8960 | Reinstall insulation (if any) | 11-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 17-May-25 A
A8970 | Torquing / flange management & hand-over to Ops | 11-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 17-May-25 A
A8980 | End of Work | 11-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 17-May-25 A
Tailgasfrom13-KX-402Tag#IP-B-B3-M3-L-3100 |  | 11-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 17-May-25 A
A38220 | Reinstall insulation (if any) | 11-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 17-May-25 A
A8650 | Start of Work | 11-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 17-May-25 A
A8660 | Obtain Work Permit | 11-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 17-May-25 A
A8670 | Removal of insulation & Wallthickness measurement | 11-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 17-May-25 A
A8680 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 11-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 17-May-25 A
A8690 | Cut old piping (existing line 45024), haul to ground level | 11-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 17-May-25 A
A8700 | Grinding, bevelling of old piping & fit-up with new spool | 11-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 17-May-25 A
A8710 | Full welding of joints & installation of Tie-In spool 45024 | 11-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 17-May-25 A
A8720 | Inspection NDT / RT of selected joints | 11-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 17-May-25 A
A8730 | Install pipe supports (if any) | 11-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 17-May-25 A
A8740 | Prepare and hydrotest up to XX BarG (if required) | 11-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 17-May-25 A
A8750 | Hydrotest witness inspection (if required) | 11-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 17-May-25 A
A8760 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 11-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 17-May-25 A
A8770 | Touch-up painting works | 11-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 17-May-25 A
A8780 | Deblinding, remove temporary support / scaffolds | 11-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 17-May-25 A
A8800 | Torquing / flange management & hand-over to Ops | 11-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 17-May-25 A
A8810 | End of Work | 11-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 11-Apr-25 A | 17-May-25 A
CoolingWaterfromEU3TieInPointto50-HE-1410Tag#IP-B-B3-M3-L-3120 |  | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A38210 | Obtain Work Permit | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A8480 | Start of Work | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A8500 | Wallthickness measurement | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A8510 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A8520 | Cut old piping (existing line 140036) , haul to ground level | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A8530 | Grinding, bevelling of old piping & fit-up with new spool | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A8540 | Full welding of joints & installation of Tie-In spool 140033 | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A8550 | Inspection NDT / RT of selected joints | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A8560 | Install pipe supports (if any) | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A8570 | Prepare and hydrotest up to XX BarG (if required) | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A8580 | Hydrotest witness inspection (if required) | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A8590 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A8600 | Touch-up painting works | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A8610 | Deblinding, remove temporary support / scaffolds | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A8620 | Reinstall insulation (if any) | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A8630 | Torquing / flange management & hand-over to Ops | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A8640 | End of Work | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
RegenerationGasC4Hydrogenationfrom13-VA-804A/BTag#IP-B-B3-M3-L-3170 |  | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A38150 | Start of Work | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A38160 | Obtain Work Permit | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A38170 | Removal of insulation & Wallthickness measurement | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A38180 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A38190 | Full welding of joints & installation of Tie-In spool 81142 | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A38200 | Touch-up painting works | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A8350 | Cut old piping (existing line 41022), haul to ground level | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A8360 | Grinding, bevelling of old piping & fit-up with new spool | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A8380 | Inspection NDT / RT of selected joints | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A8390 | Install pipe supports (if any) | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A8400 | Prepare and hydrotest up to XX BarG (if required) | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A8410 | Hydrotest witness inspection (if required) | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A8420 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A8440 | Deblinding, remove temporary support / scaffolds | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A8450 | Reinstall insulation (if any) | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A8460 | Torquing / flange management & hand-over to Ops | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A8470 | End of Work | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
TailgaslinebleedTag#IP-B-B3-M3-L-3180 |  | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A38110 | Start of Work | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A38120 | Obtain Work Permit | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A38130 | Removal of insulation & Wallthickness measurement | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A38140 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A8170 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A8180 | Cut old piping (existing line 45024), haul to ground level | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A8190 | Grinding, bevelling of old piping & fit-up with new spool | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A8200 | Full welding of joints & installation of Tie-In spool 45024 | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A8210 | Inspection NDT / RT of selected joints | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A8220 | Install pipe supports (if any) | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A8230 | Prepare and hydrotest up to XX BarG (if required) | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A8240 | Hydrotest witness inspection (if required) | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A8260 | Touch-up painting works | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A8270 | Deblinding, remove temporary support / scaffolds | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A8280 | Reinstall insulation (if any) | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A8290 | Torquing / flange management & hand-over to Ops | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A8300 | End of Work | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
TreatedVHPBFWPreheater52-HE-1402bypassvalveTag#IP-B-B3-M3-L-3190 |  | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A38100 | End of Work | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7970 | Start of Work | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7980 | Obtain Work Permit | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7990 | Removal of insulation & Wallthickness measurement | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A8000 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A8010 | Cut old piping (existing line 140025), haul to ground level | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A8020 | Grinding, bevelling & fit-up of valve with new spool | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A8030 | Welding of gate valve & installation of Tie-In spool 140025 | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A8040 | Inspection NDT / RT of selected joints | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A8050 | Install pipe supports (if any) | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A8060 | Prepare and hydrotest up to XX BarG (if required) | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A8070 | Hydrotest witness inspection (if required) | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A8080 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A8090 | Touch-up painting works | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A8100 | Deblinding, remove temporary support / scaffolds | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A8110 | Reinstall insulation (if any) | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A8120 | Torquing / flange management & hand-over to Ops | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
TreatedVHPBFWfromEU3to52-HE-1402Tag#IP-B-B3-M3-L-3210 |  | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7800 | Start of Work | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7810 | Obtain Work Permit | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7820 | Removal of insulation & Wallthickness measurement | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7830 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7840 | Cut old piping (existing line 140025), haul to ground level | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7850 | Grinding, bevelling of old piping & fit-up with new spool | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7860 | Full welding of joints & installation of Tie-In spool 140219 | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7870 | Inspection NDT / RT of selected joints | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7880 | Install pipe supports (if any) | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7890 | Prepare and hydrotest up to XX BarG | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7900 | Hydrotest witness inspection | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7910 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7920 | Touch-up painting works | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7930 | Deblinding, remove temporary support / scaffolds | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7940 | Reinstall insulation (if any) | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7950 | Torquing / flange management & hand-over to Ops | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7960 | End of Work | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
LP-SteamfromEU3TieInPointto52-HE-1402Tag#IP-B-B3-M3-L-3230 |  | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7630 | Start of Work | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7640 | Obtain Work Permit | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7650 | Removal of insulation & Wallthickness measurement | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7660 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7670 | Cut old piping (existing line 140472), haul to ground level | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7680 | Grinding, bevelling of old piping & fit-up with new spool | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7690 | Welding of weldolet and installation of Tie-In spool 140489 | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7700 | Inspection NDT / RT of selected joints | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7710 | Install pipe supports (if any) | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7720 | Prepare and hydrotest up to XX BarG Iif required) | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7730 | Hydrotest witness inspection Iif required) | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7740 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7750 | Touch-up painting works | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7760 | Deblinding, remove temporary support / scaffolds | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7770 | Reinstall insulation (if any) | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7780 | Torquing / flange management & hand-over to Ops | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7790 | End of Work | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
Package2 |  | 29-Mar-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 20-May-25 A
RegenerationGasfrom50-HE-1402Tag#IP-B-B3-M3-L-3260 |  | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7460 | Start of Work | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7470 | Obtain Work Permit | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7480 | Wallthickness measurement | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7490 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7500 | Cut old piping (existing line 140025), haul to ground level | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7510 | Grinding, bevelling of old piping & fit-up with new spool | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7520 | Full welding of joints & installation of Tie-In spool 140025 | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7530 | Inspection NDT / RT of selected joints | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7540 | Install pipe supports (if any) | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7550 | Prepare and hydrotest up to XX BarG (if required) | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7560 | Hydrotest witness inspection (if required) | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7570 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7580 | Touch-up painting works | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7590 | Deblinding, remove temporary support / scaffolds | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7600 | Reinstall insulation (if any) | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7610 | Torquing / flange management & hand-over to Ops | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7620 | End of Work | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
NitrogenfromEU3to64PSV14001Tag#IP-B-B3-M3-L-3380 |  | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7290 | Start of Work | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7300 | Obtain Work Permit | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7310 | Wallthickness measurement | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7320 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7330 | Cut old piping (existing line 140148) , haul to ground level | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7340 | Grinding, bevelling of old piping & fit-up with new spool | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7350 | Full welding of joints & installation of Tie-In spool 140038 | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7360 | Inspection NDT / RT of selected joints | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7370 | Install pipe supports (if any) | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7380 | Prepare and hydrotest up to XX BarG | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7390 | Hydrotest witness inspection | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7400 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7410 | Touch-up painting works | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7420 | Deblinding, remove temporary support / scaffolds | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7430 | Reinstall insulation (if any) | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7440 | Torquing / flange management & hand-over to Ops | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7450 | End of Work | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
RegenerationGasC4HydrogenationTag#IP-B-B3-M3-L-3390 |  | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7120 | Start of Work | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7130 | Obtain Work Permit | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7140 | Removal of insulation & Wallthickness measurement | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7150 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7160 | Cut old piping (existing line 81142), haul to ground level | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7170 | Grinding, bevelling of old piping & fit-up with new spool | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7180 | Full welding of joints & installation of Tie-In spool 81184 | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7190 | Inspection NDT / RT of selected joints & Additional Testing of Tie-in Valve | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7200 | Install pipe supports (if any) | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7210 | Prepare and hydrotest up to XX BarG (if required) | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7220 | Hydrotest witness inspection (if required) | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7230 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7240 | Touch-up painting works | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7250 | Deblinding, remove temporary support / scaffolds | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7260 | Reinstall insulation (if any) | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7270 | Torquing / flange management & hand-over to Ops | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7280 | End of Work | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
50AT-14101AsampletapTag#IP-B-B3-M3-L-3430 |  | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A6950 | Start of Work | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A6960 | Obtain Work Permit | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A6970 | Removal of insulation & Wallthickness measurement | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A6980 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A6990 | Cut old piping & support, haul to ground level | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7000 | Grinding, bevelling of old piping & fit-up with new spool | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7010 | Full welding of joints including weldolet & installation of Tie-In spool | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7020 | Inspection NDT / RT of selected joints | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7030 | Install pipe supports (if any) | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7040 | Prepare and hydrotest up to XX BarG (if required) | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7050 | Hydrotest witness inspection (if required) | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7060 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7070 | Touch-up painting works | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7080 | Deblinding, remove temporary support / scaffolds | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7090 | Reinstall insulation (if any) | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7100 | Torquing / flange management & hand-over to Ops | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
A7110 | End of Work | 15-Apr-25 A | 20-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 20-May-25 A
RegenerationGasC4HydrogenationventpointTag#P-B-B3-M3-L-3500 |  | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A38070 | Install pipe supports (if any) | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A38080 | Prepare and hydrotest up to XX BarG (if required) | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A38090 | Hydrotest witness inspection (if required) | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6780 | Start of Work | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6790 | Obtain Work Permit | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6800 | Removal of Insulation & Wallthickness measurement | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6810 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6820 | Cut old piping (existing line 81142), haul to ground level | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6830 | Grinding, bevelling of old piping & fit-up with new spool | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6840 | Welding of 8x1" weldolet and flange with valve and instrument | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6850 | Inspection NDT / RT of selected joints | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6890 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6900 | Touch-up painting works | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6910 | Deblinding, remove temporary support / scaffolds | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6920 | Reinstall insulation (if any) | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6930 | Torquing / flange management & hand-over to Ops | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6940 | End of Work | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
SamplepointinRegenerationgascooleroutletTag#IP-B-B3-M3-L-3510 |  | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6610 | Start of Work | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6620 | Obtain Work Permit | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6630 | Wallthickness measurement | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6640 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6650 | Cut old piping (existing line 140024), haul to ground level | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6660 | Grinding, bevelling of old piping & fit-up with new spool | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6670 | Welding of 20x1" weldolet and flange with valve and instrument 50S-14161L | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6680 | Inspection NDT / RT of selected joints | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6690 | Install pipe supports (if any) | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6700 | Prepare and hydrotest up to XX BarG (if required) | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6710 | Hydrotest witness inspection (if required) | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6720 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6730 | Touch-up painting works | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6740 | Deblinding, remove temporary support / scaffolds | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6750 | Reinstall insulation (if any) | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6760 | Torquing / flange management & hand-over to Ops | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6770 | End of Work | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
ReinforcedBranchconnectionforWGflare(Installationof5TieIns)Tag#IP-B-B3-M3-L-3520 |  | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6440 | Start of Work | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6450 | Obtain Work Permit | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6460 | Wallthickness measurement | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6470 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6480 | Cut old piping (existing line 140301), haul to ground level | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6490 | Grinding, bevelling of old piping & fit-up with new spool | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6500 | Full welding of joints (tie in Tee piece, than the tie in spools) | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6510 | Inspection NDT / RT of selected joints | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6520 | Install pipe supports (if any) | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6530 | Prepare and hydrotest up to XX BarG (if required) | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6540 | Hydrotest witness inspection (if required) | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6550 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6560 | Touch-up painting works | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6570 | Deblinding, remove temporary support / scaffolds | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6580 | Reinstall insulation (if any) | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6590 | Torquing / flange management & hand-over to Ops | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6600 | End of Work | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
ReinforcedBranchconnectionpipespecificationbreakforWGflareTag#P-B-B3-M3-L-3530 |  | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6270 | Start of Work | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6280 | Obtain Work Permit | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6290 | Wallthickness measurement | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6300 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6310 | Cut old piping (existing line 140301), haul to ground level | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6320 | Grinding, bevelling of old piping & fit-up with new spool | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6330 | Full welding of joints | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6340 | Inspection NDT / RT of selected joints | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6350 | Install pipe supports (if any) | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6360 | Prepare and hydrotest up to XX BarG (if required) | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6370 | Hydrotest witness inspection (if required) | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6380 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6390 | Touch-up painting works | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6400 | Deblinding, remove temporary support / scaffolds | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6410 | Reinstall insulation (if any) | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6420 | Torquing / flange management & hand-over to Ops | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6430 | End of Work | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
PSA2OffGasfromEU3toEU3TieInpointTag#IP-B-H3-B3-L-2022 |  | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6100 | Start of Work | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6110 | Obtain Work Permit | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6120 | Removal of insulation & Wallthickness measurement | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6130 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6140 | Cut old piping (existing line 45024) , haul to ground level | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6150 | Grinding, bevelling of old piping & fit-up with new spool | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6160 | Full welding of joints, Tee & installation of Tie-In spool 72069 | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6170 | Inspection NDT / RT of selected joints | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6180 | Install pipe supports (if any) | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6190 | Prepare and hydrotest up to XX BarG (if required) | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6200 | Hydrotest witness inspection (if required) | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6210 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6220 | Touch-up painting works | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6230 | Deblinding, remove temporary support / scaffolds | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6240 | Reinstall insulation (if any) | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6250 | Torquing / flange management & hand-over to Ops | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6260 | End of Work | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
ProcessWaterfromEU3H2toEU3TieInPointTag#IP-B-H3-B3-L-2042 |  | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A5930 | Start of Work | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A5940 | Obtain Work Permit | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A5950 | Wallthickness measurement | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A5960 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A5970 | Cut old piping (existing line 20002), haul to ground level | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A5980 | Grinding, bevelling of old piping & fit-up with new spool | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A5990 | Welding of Tie-in spool weldolet | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6000 | Inspection NDT / RT of selected joints | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6010 | Install pipe supports (if any) | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6020 | Prepare and hydrotest up to XX BarG (if required) | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6030 | Hydrotest witness inspection (if required) | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6040 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6050 | Touch-up painting works | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6060 | Deblinding, remove temporary support / scaffolds | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6070 | Reinstall insulation (if any) | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6080 | Torquing / flange management & hand-over to Ops | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
A6090 | End of Work | 29-Mar-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 29-Mar-25 A | 17-May-25 A
WarmLiquidFlarefromEU3toEU3TieInpointTag#IP-B-H3-B3-L-2052 |  | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5760 | Start of Work | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5770 | Obtain Work Permit | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5780 | Wallthickness measurement | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5790 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5800 | Cut old piping (existing line 140301), haul to ground level | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5810 | Grinding, bevelling of old piping & fit-up with new spool | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5820 | Full welding of joints & installation of Tie-In spool 140382 | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5830 | Inspection NDT / RT of selected joints | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5840 | Install pipe supports (if any) | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5850 | Prepare and hydrotest up to XX BarG | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5860 | Hydrotest witness inspection | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5870 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5880 | Touch-up painting works | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5890 | Deblinding, remove temporary support / scaffolds | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5900 | Reinstall insulation (if any) | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5910 | Torquing / flange management & hand-over to Ops | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5920 | End of Work | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
WarmGasFlarefromEU3toEU3TieInpointTag#IP-B-H3-B3-L-2062 |  | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5590 | Start of Work | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5600 | Obtain Work Permit | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5610 | Wallthickness measurement | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5620 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5630 | Cut old piping (existing line 140301), haul to ground level | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5640 | Grinding, bevelling of old piping & fit-up with new spool | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5650 | Full welding of joints & installation of Tie-In spool 140381 | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5660 | Inspection NDT / RT of selected joints | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5670 | Install pipe supports (if any) | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5680 | Prepare and hydrotest up to XX BarG | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5690 | Hydrotest witness inspection | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5700 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5710 | Touch-up painting works | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5720 | Deblinding, remove temporary support / scaffolds | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5730 | Reinstall insulation (if any) | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5740 | Torquing / flange management & hand-over to Ops | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5750 | End of Work | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
LPCondensatefromEU3H2toEU3TieInpointTag#IP-B-H3-B3-L-2072 |  | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5420 | Start of Work | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5430 | Obtain Work Permit | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5440 | Removal of insulation & Wallthickness measurement | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5450 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5460 | Cut old piping (existing line 140101), haul to ground level | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5470 | Grinding, bevelling of old piping & fit-up with new spool | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5480 | Full welding of joints including weldolet & installation of Tie-In spool 140434 | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5490 | Inspection NDT / RT of selected joints | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5500 | Install pipe supports (if any) | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5510 | Prepare and hydrotest up to XX BarG (if required) | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5520 | Hydrotest witness inspection (if required) | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5530 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5540 | Touch-up painting works | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5550 | Deblinding, remove temporary support / scaffolds | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5560 | Reinstall insulation (if any) | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5570 | Torquing / flange management & hand-over to Ops | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5580 | End of Work | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
Package3 |  | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 27-Nov-24 A | 2026-09-25
CoolingWaterReturnfromEU3H2toU&O3TieInpointTag#IP-B-H3-U3-L-1101 |  | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5250 | Start of Work | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5260 | Obtain Work Permit | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5270 | Wall thickness measurement | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5280 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5290 | Cut old piping (existing line '00018), haul to ground level | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5300 | Grinding, bevelling of old piping & fit-up with new spool | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5310 | Full welding of joints including weldolet & installation of Tie-In spool 00215 | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5320 | Inspection NDT / RT of selected joints | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5330 | Install pipe supports (if any) | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5340 | Prepare and hydrotest up to XX BarG (if required) | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5350 | Hydrotest witness inspection (if required) | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5360 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5370 | Touch-up painting works | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5380 | Deblinding, remove temporary support / scaffolds | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5390 | Reinstall insulation (if any) | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5400 | Torquing / flange management & hand-over to Ops | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5410 | End of Work | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
PSA2OffGasRecycletoCGCTag#IP-B-M3-B3-L-3040 |  | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A38010 | Install pipe supports (if any) | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A38020 | Prepare and hydrotest up to XX BarG (if required) | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A38030 | Hydrotest witness inspection (if required) | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A38040 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A38050 | Touch-up painting works | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A38060 | Deblinding, remove temporary support / scaffolds | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5080 | Start of Work | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5090 | Obtain Work Permit | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5100 | Removal of insulation & Wall thickness measurement | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5110 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5120 | Cut old piping & support, haul to ground level | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5130 | Grinding, bevelling of old piping & fit-up with new spool | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5140 | Full welding of weldolet & installation of Tie-In spool 72068 | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5150 | Inspection NDT / RT of selected joints | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5220 | Reinstall insulation (if any) | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5230 | Torquing / flange management & hand-over to Ops | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5240 | End of Work | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
RegenerationGasfrom50-HE-1410to50-VV-1401Tag#IP-B-M3-B3-L-3070 |  | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A4910 | Start of Work | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A4920 | Obtain Work Permit | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A4930 | Removal of insulation & Wall thickness measurement | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A4940 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A4950 | Cut old piping (existing line 45024), haul to ground level | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A4960 | Grinding, bevelling of old piping & fit-up with new spool | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A4970 | Full welding of joints & installation of Tie-In spool 140489 | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A4980 | Inspection NDT / RT of selected joints | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A4990 | Install pipe supports (if any) | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5000 | Prepare and hydrotest up to XX BarG (if required) | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5010 | Hydrotest witness inspection (if required) | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5020 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5030 | Touch-up painting works | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5040 | Deblinding, remove temporary support / scaffolds | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5050 | Reinstall insulation (if any) | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5060 | Torquing / flange management & hand-over to Ops | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A5070 | End of Work | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
RegenerationGasto50-VV-1401Tag#IP-B-M3-B3-L-3110 |  | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A4740 | Start of Work | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A4750 | Obtain Work Permit | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A4760 | Wall thickness measurement | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A4770 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A4780 | Cut old piping (existing line 140025) , haul to ground level | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A4790 | Grinding, bevelling of old piping & fit-up with new spool | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A4800 | Full welding of joints | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A4810 | Inspection NDT / RT of selected joints | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A4820 | Install pipe supports (if any) | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A4830 | Prepare and hydrotest up to XX BarG (if required) | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A4840 | Hydrotest witness inspection (if required) | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A4850 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A4860 | Touch-up painting works | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A4870 | Deblinding, remove temporary support / scaffolds | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A4880 | Reinstall insulation (if any) | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A4890 | Torquing / flange management & hand-over to Ops | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
A4900 | End of Work | 02-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 02-Apr-25 A | 17-May-25 A
CoolingWaterfrom50-HE-1410toEU3Tie-InPointTag#IP-B-M3-B3-L-3130 |  | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A4570 | Start of Work | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A4580 | Obtain Work Permit | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A4590 | Wall thickness measurement | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A4600 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A4610 | Cut old piping (existing line 140034) & support, haul to ground level | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A4620 | Grinding, bevelling of old piping & fit-up with new spool | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A4630 | Full welding of joints & installation of Tie-In spool 140065 | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A4640 | Inspection NDT / RT of selected joints | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A4650 | Install pipe supports (if any) | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A4660 | Prepare and hydrotest up to XX BarG (if required) | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A4670 | Hydrotest witness inspection (if required) | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A4680 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A4690 | Touch-up painting works | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A4700 | Deblinding, remove temporary support / scaffolds | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A4710 | Reinstall insulation (if any) | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A4720 | Torquing / flange management & hand-over to Ops | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A4730 | End of Work | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
WarmGasFlarefrom50-HE-1410toEU3TieInPointTag#IP-B-M3-B3-L-3140 |  | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A4400 | Start of Work | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A4410 | Obtain Work Permit | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A4420 | Wall thickness measurement | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A4430 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A4440 | Cut old piping (existing line 140301), haul to ground level | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A4450 | Grinding, bevelling of old piping & fit-up with new spool | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A4460 | Full welding of joints & installation of Tie-In spool 140379 | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A4470 | Inspection NDT / RT of selected joints | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A4480 | Install pipe supports (if any) | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A4490 | Prepare and hydrotest up to XX BarG (if required) | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A4500 | Hydrotest witness inspection (if required) | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A4510 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A4520 | Touch-up painting works | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A4530 | Deblinding, remove temporary support / scaffolds | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A4540 | Reinstall insulation (if any) | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A4550 | Torquing / flange management & hand-over to Ops | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A4560 | End of Work | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
TreatedVHPBFWfrom52-HE-1402toEU3Tag#IP-B-M3-B3-L-3220 |  | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A4230 | Start of Work | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A4240 | Obtain Work Permit | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A4250 | Removal of insulation and wall thickness measurement | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A4260 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A4270 | Cut old piping (existing line 140025) & support, haul to ground level | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A4280 | Grinding, bevelling of old piping & fit-up with new spool | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A4290 | Full welding of joints (Tee-piece) & installation of Tie-In spool 140218 | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A4300 | Inspection NDT / RT of selected joints | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A4310 | Install pipe supports (if any) | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A4320 | Prepare and hydrotest up to XX BarG (if required) | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A4330 | Hydrotest witness inspection (if required) | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A4340 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A4350 | Touch-up painting works | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A4360 | Deblinding, remove temporary support / scaffolds | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A4370 | Reinstall insulation (if any) | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A4380 | Torquing / flange management & hand-over to Ops | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A4390 | End of Work | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
LP-Condensatefrom52-HE-1402to54-VV-1402Tag#IP-B-M3-B3-L-3240 |  | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A4060 | Start of Work | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A4070 | Obtain Work Permit | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A4080 | Removal of insulation | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A4090 | Removal of blind flange 54-VV-1402, N02 & Gas measurement | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A4100 | Check of cleanliness of vessel and new pipe | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A4110 | Connection of tie in spool | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A4190 | Deblinding, remove temporary support / scaffolds | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A4200 | Reinstall insulation (if any) | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A4210 | Torquing / flange management & hand-over to Ops | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A4220 | End of Work | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
Tailgasto50-VV-1401Tag#IP-B-M3-B3-L-3250 |  | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A38000 | End of Work | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A3890 | Start of Work | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A3900 | Obtain Work Permit | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A3910 | Removal of insulation and wall thickness measurement | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A3920 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A3930 | Cut old piping (existing line 45024), haul to ground level | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A3940 | Grinding, bevelling of old piping & fit-up with new spool | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A3950 | Full welding of joints & installation of Tie-In spool 45024 | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A3960 | Inspection NDT / RT of selected joints | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A3970 | Install pipe supports (if any) | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A3980 | Prepare and hydrotest up to XX BarG (if required) | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A3990 | Hydrotest witness inspection (if required) | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A4000 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A4010 | Touch-up painting works | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A4020 | Deblinding, remove temporary support / scaffolds | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A4030 | Reinstall insulation (if any) | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A4040 | Torquing / flange management & hand-over to Ops | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
RegenerationGasC4Hydrogenationto50-HE-1402Tag#IP-B-M3-B3-L-3280 |  | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A3720 | Start of Work | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A3730 | Obtain Work Permit | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A3740 | Removal of insulation and wall thickness measurement | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A3750 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A3760 | Cut old piping (existing line 41022), haul to ground level | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A3770 | Grinding, bevelling of old piping & fit-up with new spool | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A3780 | Full welding of joints & installation of Tie-In spool 81142 | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A3790 | Inspection NDT / RT of selected joints | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A3800 | Install pipe supports (if any) | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A3810 | Prepare and hydrotest up to XX BarG (if required) | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A3820 | Hydrotest witness inspection (if required) | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A3830 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A3840 | Touch-up painting works | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A3850 | Deblinding, remove temporary support / scaffolds | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A3860 | Reinstall insulation (if any) | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A3870 | Torquing / flange management & hand-over to Ops | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A3880 | End of Work | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
RegenerationGasC4HydrogenationCondensateTag#IP-B-M3-B3-L-3290 |  | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A3550 | Start of Work | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A3570 | Wall thickness measurement | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A3600 | Grinding, bevelling of old piping & fit-up with new spool | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A3610 | Full welding of joints & installation of Tie-In spool 140066 | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A3620 | Inspection NDT / RT of selected joints | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A3630 | Install pipe supports (if any) | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A3640 | Prepare and hydrotest up to XX BarG (if any) | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A3650 | Hydrotest witness inspection (if any) | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A3660 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A3670 | Touch-up painting works | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A3680 | Deblinding, remove temporary support / scaffolds | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A3690 | Reinstall insulation (if any) | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A3700 | Torquing / flange management & hand-over to Ops | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A3710 | End of Work | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A37970 | Obtain Work Permit | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A37980 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A37990 | Cut old piping (existing line 140028) , haul to ground level | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
WarmGasFlarefrom13-KX-402/50-HE-1402toEU3TieInPointTag#P-B-M3-B3-L-3300 |  | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A3390 | Obtain Work Permit | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A3540 | End of Work | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A37820 | Start of Work | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A37830 | Wall thickness measurement | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A37840 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A37850 | Cut old piping (existing line 140301) , haul to ground level | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A37860 | Grinding, bevelling of old piping & fit-up with new spool | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A37870 | Full welding of joints & installation of Tie-In spool 140301 | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A37880 | Inspection NDT / RT of selected joints | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A37890 | Install pipe supports (if any) | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A37900 | Prepare and hydrotest up to XX BarG | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A37910 | Hydrotest witness inspection | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A37920 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A37930 | Touch-up painting works | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A37940 | Deblinding, remove temporary support / scaffolds | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A37950 | Reinstall insulation (if any) | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A37960 | Torquing / flange management & hand-over to Ops | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
ColdGasfrom13-PSV-4508toEU3TieInTag#P-B-M3-B3-L-3410 |  | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A3210 | Start of Work | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A3220 | Obtain Work Permit | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A3230 | Wall thickness measurement | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A3240 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A3260 | Grinding, bevelling of old piping & fit-up with new spool | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A3270 | Purge with 24" balloons & welding of Tie-In spool 144564 | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A3280 | Inspection NDT / RT of selected joints | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A3290 | Install pipe supports (if any) | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A3300 | Prepare and hydrotest up to XX BarG (if required) | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A3310 | Hydrotest witness inspection (if required) | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A3320 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A3330 | Touch-up painting works | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A3340 | Deblinding, remove temporary support / scaffolds | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A3360 | Torquing / flange management & hand-over to Ops | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A3370 | End of Work | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A37800 | Cut old piping (existing line 140321) & support, haul to ground level | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A37810 | Reinstall insulation (if any) | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
Package4 |  | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
50AT-14101AsampletapventreturntoprocessTag#IP-B-M3-B3-L-3420 |  | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A3040 | Start of Work | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A3050 | Obtain Work Permit | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A3060 | Gas measurement | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A3070 | Making tubing connection | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A3170 | Deblinding, remove temporary support / scaffolds | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
A3200 | End of Work | 10-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 10-Apr-25 A | 17-May-25 A
InstrumentAirfromU&O3TieInpointtoEU3H2Tag#IP-B-U3-H3-L-1020 |  | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A2870 | Start of Work | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A2880 | Obtain Work Permit | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A3030 | End of Work | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
PlantAirfromU&O3TieInpointtoEU3H2Tag#IP-B-U3-H3-L-1030 |  | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A2700 | Start of Work | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A2710 | Obtain Work Permit | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A2860 | End of Work | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
NitrogenfromU&O3TieInpointtoEU3H2Tag#IP-B-U3-H3-L-1040 |  | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A2530 | Start of Work | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A2540 | Obtain Work Permit | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A2690 | End of Work | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
LPSteamfromU&O3TieInpointtoEU3H2Tag#IP-B-U3-H3-L-1050 |  | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A2360 | Start of Work | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A2370 | Obtain Work Permit | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A2380 | Wall thickness measurement | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A2390 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A2400 | Cut old piping (existing line 00271) & support, haul to ground level | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A2410 | Grinding, bevelling of old piping & fit-up with new spool | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A2420 | Full welding of joints & Installation of Tie-In spool '0005 | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A2430 | Inspection NDT / RT of selected joints | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A2440 | Install pipe supports (if any) | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A2450 | Prepare and hydrotest up to XX BarG | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A2460 | Hydrotest witness inspection | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A2470 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A2480 | Touch-up painting works | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A2490 | Deblinding, remove temporary support / scaffolds | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A2500 | Reinstall insulation (if any) | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A2510 | Torquing / flange management & hand-over to Ops | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A2520 | End of Work | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
ServicewaterfromU&O3TieInpointtotoEU3H2Tag#IP-B-U3-H3-L-1060 |  | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A2190 | Start of Work | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A2200 | Obtain Work Permit | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A2210 | Removal of insulation and wall thickness measurement | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A2220 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A2230 | Cut old piping (existing line '00061) & support, haul to ground level | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A2240 | Grinding, bevelling of old piping & fit-up with new spool | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A2250 | Full welding of joints | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A2260 | Inspection NDT / RT of selected joints | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A2270 | Install pipe supports (if any) | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A2280 | Prepare and hydrotest up to XX BarG | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A2290 | Hydrotest witness inspection | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A2300 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A2310 | Touch-up painting works | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A2320 | Deblinding, remove temporary support / scaffolds | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A2330 | Reinstall insulation (if any) | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A2340 | Torquing / flange management & hand-over to Ops | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A2350 | End of Work | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
PotablewaterfromU&O3TieInpointtoEU3H2Tag#IP-B-U3-H3-L-1070 |  | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A2020 | Start of Work | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A2030 | Obtain Work Permit | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A2040 | Wall thickness measurement | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A2050 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A2060 | Cut old piping & support, haul to ground level | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A2070 | Grinding, bevelling of old piping & fit-up with new spool | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A2080 | Full welding of joints | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A2090 | Inspection NDT / RT of selected joints | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A2100 | Install pipe supports (if any) | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A2110 | Prepare and hydrotest up to XX BarG | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A2120 | Hydrotest witness inspection | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A2130 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A2140 | Touch-up painting works | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A2150 | Deblinding, remove temporary support / scaffolds | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A2160 | Reinstall insulation (if any) | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A2170 | Torquing / flange management & hand-over to Ops | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A2180 | End of Work | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
CoolingWaterSupplyfromU&O3TieInPointtoEU3H2Tag#P-B-U3-H3-L-1090 |  | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A1340 | Start of Work | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A1350 | Obtain Work Permit | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A1360 | Removal of insulation (if any) & measurement of wall thickness | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A1370 | Pull-out piping components (Valves, TW/TE, TG, PT, PG if any) | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A1380 | Cut old piping (existing line '00234) & support, haul to ground level | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A1390 | Grinding, bevelling of old piping & fit-up with new spool | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A1400 | Welding of weldolet | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A1410 | Inspection NDT / RT of selected joints | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A1420 | Install pipe supports (if any) | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A1430 | Prepare and hydrotest up to XX BarG (if required) | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A1440 | Hydrotest witness inspection (if required) | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A1450 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A1460 | Touch-up painting works (if any) | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A1470 | Deblinding, remove temporary support / scaffolds | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A1480 | Reinstall insulation (if any) | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A1490 | Torquing / flange management & hand-over to Ops | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A37650 | End of Work | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
OilywaterfromEU3H2toU&O3TieInpointTag#IP-B-U3-H3-L-1121 |  | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A1210 | Cut old piping (existing line '00018), haul to ground level | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A1220 | Grinding, bevelling of old piping & fit-up with new spool | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A1230 | Full welding of joints | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A1280 | Reinstall back piping components (TW/TE, TG, PT, PG if any) | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A1290 | Touch-up painting works | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A1300 | Deblinding, remove temporary support / scaffolds | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A1310 | Reinstall insulation (if any) | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A1320 | Torquing / flange management & hand-over to Ops | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A1330 | End of Work | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A37570 | Start of Work | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A37580 | Obtain Work Permit | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A37590 | Removal of insulation & measurement of wall thickness | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A37600 | Drilling one hole (cold drilling, air-driven) & Gas measurement | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A37610 | Inspection NDT / RT of selected joints | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A37620 | Install pipe supports (if any) | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A37630 | Prepare and hydrotest up to XX BarG (if required) | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A37640 | Hydrotest witness inspection (if required) | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
TATie-InExecution-U/GTie-Ins |  | 03-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 03-Apr-25 A | 17-May-25 A
Package4 |  | 03-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
FireWaterfromU&O3TiepointtoEU3H2(Southwest)Tag#IP-B-U3-H3-L-1080 |  | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A1850 | Start of Work | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A1860 | Obtain Work Permit | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A1870 | Install temporary support / scaffolds as site | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A1880 | Install isolation balloon | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A1980 | Deblinding, remove temporary support / scaffolds | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A1990 | Reinstall insulation (if any) | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A2000 | Torquing / flange management & hand-over to Ops | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
A2010 | End of Work | 08-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 08-Apr-25 A | 17-May-25 A
FireWaterfromU&O3TiepointtoEU3H2(southeast)Tag#IP-B-U3-H3-L-1082 |  | 03-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 03-Apr-25 A | 17-May-25 A
A1680 | Start of Work | 03-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 03-Apr-25 A | 17-May-25 A
A1690 | Obtain Work Permit | 03-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 03-Apr-25 A | 17-May-25 A
A1700 | Removal of insulation & wall thickness measurement | 03-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 03-Apr-25 A | 17-May-25 A
A1710 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 03-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 03-Apr-25 A | 17-May-25 A
A1720 | Cut old piping & support, haul to ground level | 03-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 03-Apr-25 A | 17-May-25 A
A1730 | Grinding, bevelling of old piping & fit-up with new spool | 03-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 03-Apr-25 A | 17-May-25 A
A1740 | Full welding of joints | 03-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 03-Apr-25 A | 17-May-25 A
A1750 | Inspection NDT / RT of selected joints | 03-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 03-Apr-25 A | 17-May-25 A
A1760 | Install pipe supports (if any) | 03-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 03-Apr-25 A | 17-May-25 A
A1770 | Prepare and hydrotest up to XX BarG | 03-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 03-Apr-25 A | 17-May-25 A
A1780 | Hydrotest witness inspection | 03-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 03-Apr-25 A | 17-May-25 A
A1790 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 03-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 03-Apr-25 A | 17-May-25 A
A1800 | Touch-up painting works | 03-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 03-Apr-25 A | 17-May-25 A
A1810 | Deblinding, remove temporary support / scaffolds | 03-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 03-Apr-25 A | 17-May-25 A
A1820 | Reinstall insulation (if any) | 03-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 03-Apr-25 A | 17-May-25 A
A1830 | Torquing / flange management & hand-over to Ops | 03-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 03-Apr-25 A | 17-May-25 A
A1840 | End of Work | 03-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 03-Apr-25 A | 17-May-25 A
FireWaterfromU&O3TiepointtoEU3H2(Northeast)Tag#IP-B-U3-H3-L-1086 |  | 03-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 03-Apr-25 A | 17-May-25 A
A1520 | Obtain Work Permit | 03-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 03-Apr-25 A | 17-May-25 A
A1530 | Install temporary support / scaffolds as site | 03-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 03-Apr-25 A | 17-May-25 A
A1670 | End of Work | 03-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 03-Apr-25 A | 17-May-25 A
A37660 | Start of Work | 03-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 03-Apr-25 A | 17-May-25 A
A37670 | Pull-out piping components (Valves, TW/TE, TG, PT, PG if any) | 03-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 03-Apr-25 A | 17-May-25 A
A37680 | Cut old piping (20" HDPE Line), haul to ground level | 03-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 03-Apr-25 A | 17-May-25 A
A37690 | Grinding, bevelling of old piping & fit-up with new spool (new HDPE TEE) | 03-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 03-Apr-25 A | 17-May-25 A
A37700 | Installation, alignment and welding of HDPE Tee to existing header 18011 & install. of tie-in spools 18481 & welding | 03-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 03-Apr-25 A | 17-May-25 A
A37710 | Inspection (all required HDPE welding examinations) of selected joints | 03-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 03-Apr-25 A | 17-May-25 A
A37720 | Install pipe supports (if any) | 03-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 03-Apr-25 A | 17-May-25 A
A37730 | Prepare and hydrotest up to XX BarG (if any) | 03-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 03-Apr-25 A | 17-May-25 A
A37740 | Hydrotest witness inspection (if any) | 03-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 03-Apr-25 A | 17-May-25 A
A37750 | Reinstall back piping components (TW/TE, TG, PT, PG if any) | 03-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 03-Apr-25 A | 17-May-25 A
A37760 | Touch-up painting works | 03-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 03-Apr-25 A | 17-May-25 A
A37770 | Deblinding, remove temporary support / scaffolds | 03-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 03-Apr-25 A | 17-May-25 A
A37780 | Reinstall insulation (if any) | 03-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 03-Apr-25 A | 17-May-25 A
A37790 | Torquing / flange management & hand-over to Ops | 03-Apr-25 A | 17-May-25 A | 2026-06-16 | 2026-06-16 | 03-Apr-25 A | 17-May-25 A
GFPipingWorks |  | 2026-04-18 | 2027-02-07 | 2026-06-21 | 2027-05-12 | 2026-03-28 | 2027-01-17
AG |  | 2026-04-18 | 2027-02-07 | 2026-06-21 | 2027-05-12 | 2026-03-28 | 2027-01-17
A3380 | Piping Eection at Site | 2026-05-23 | 2026-11-14 | 2026-07-26 | 2027-01-16 | 2026-05-02 | 2026-10-22
A3400 | Painting Piping - Fabrication Shop | 2026-05-05 | 2026-10-26 | 2026-07-08 | 2026-12-29 | 2026-04-14 | 2026-10-05
A3410 | Piping Insulation | 2026-10-31 | 2027-02-07 | 2027-02-02 | 2027-05-12 | 2026-10-10 | 2027-01-17
A3420 | Final Touch up and painting of joints | 2026-10-22 | 2026-12-19 | 2027-01-25 | 2027-03-23 | 2026-10-01 | 2026-11-28
A3430 | Hydro testing and reinstatment | 2026-10-11 | 2026-12-07 | 2027-01-13 | 2027-03-11 | 2026-09-20 | 2026-11-16
A60800 | Piping - Pre-Fabrication Shop | 2026-04-18 | 2026-10-08 | 2026-06-21 | 2026-12-12 | 2026-03-28 | 2026-09-17
UG |  | 2026-06-20 | 2026-11-05 | 2026-10-17 | 2027-03-23 | 2026-06-06 | 2026-12-03
A23540 | Piping Erection of Fire water piping (HDPE) UG including hydrotesting | 2026-06-20 | 2026-11-05 | 2026-11-04 | 2027-03-23 | 2026-07-16 | 2026-12-03
A3470 | U/G Piping Erection & Hydrotesting Cooling Water Lines (CS) | 2026-06-27 | 2026-10-20 | 2026-10-17 | 2027-02-09 | 2026-06-06 | 2026-09-29
A3480 | U/G Piping Erection Oily Water (CS) | 2026-08-31 | 2026-09-24 | 2027-02-28 | 2027-03-23 | 2026-08-16 | 2026-09-08
Insulation |  | 2026-07-26 | 2026-11-07 | 2026-12-09 | 2027-03-23 | 2026-06-23 | 2026-10-05
A3580 | Complete Insulation, Fire-Proofing and Painting works | 2026-07-26 | 2026-11-07 | 2026-12-09 | 2027-03-23 | 2026-06-23 | 2026-10-05
Painting |  | 2026-08-30 | 2026-12-19 | 2027-05-27 | 2027-09-15 | 2026-08-09 | 2026-11-28
A61630 | Painting | 2026-08-30 | 2026-12-19 | 2027-05-27 | 2027-09-15 | 2026-08-09 | 2026-11-28
Others |  | 2026-12-20 | 2026-12-23 | 2027-09-16 | 2027-09-20 | 20-Dec-24 A | 2027-07-20
A61640 | Painting punch clearing | 2026-12-20 | 2026-12-23 | 2027-09-16 | 2027-09-20 | 2026-11-29 | 2026-12-02
ElectricalConstruction |  | 01-Mar-25 A | 2027-01-18 | 2026-06-16 | 2027-03-23 | 01-Mar-25 A | 2026-12-28
EquipmentInstallation |  | 03-Apr-25 A | 2027-01-18 | 2026-06-16 | 2027-03-23 | 03-Apr-25 A | 2026-12-28
SystemandPanelsInstallation |  | 2026-06-08 | 2026-08-02 | 2027-01-27 | 2027-03-23 | 2026-04-16 | 2026-06-10
A61650 | System and Panels Installations | 2026-06-08 | 2026-08-02 | 2027-01-27 | 2027-03-23 | 2026-04-16 | 2026-06-10
GFInterposingRelayPanel |  | 2026-10-24 | 2026-12-21 | 2027-01-24 | 2027-03-23 | 2026-09-19 | 2026-11-16
A24070 | Installation of Interposting Relay Panel | 2026-10-24 | 2026-11-05 | 2027-01-24 | 2027-02-06 | 2026-09-19 | 2026-10-01
A24580 | Cable terminations and loop testing - IRP | 2026-11-07 | 2026-11-30 | 2027-02-07 | 2027-03-02 | 2026-10-03 | 2026-10-26
A24790 | IRP - Pre Comm | 2026-12-01 | 2026-12-21 | 2027-03-03 | 2027-03-23 | 2026-10-27 | 2026-11-16
GFDGSet |  | 2026-10-10 | 2026-12-26 | 2027-01-05 | 2027-03-23 | 2026-08-08 | 2026-10-24
A24590 | Cable terminations and loop testing - DG Set | 2026-11-10 | 2026-12-05 | 2027-02-06 | 2027-03-02 | 2026-09-08 | 2026-10-03
A24800 | DG Set - Pre Comm | 2026-12-06 | 2026-12-26 | 2027-03-03 | 2027-03-23 | 2026-10-04 | 2026-10-24
A3829 | Installation of DG Set | 2026-10-10 | 2026-11-09 | 2027-01-05 | 2027-02-04 | 2026-08-08 | 2026-09-07
GFElectricalHeatTracing(53Meterforpiping+340Meterforinstrumentation) |  | 2026-09-28 | 2026-12-09 | 2027-01-11 | 2027-03-23 | 2026-08-31 | 2026-11-11
A24090 | Electrical Heat Tracing works | 2026-09-28 | 2026-10-21 | 2027-01-11 | 2027-02-02 | 2026-08-31 | 2026-09-23
A24410 | Cable terminations and loop testing - Electric Heat Tracing | 2026-10-21 | 2026-11-18 | 2027-02-03 | 2027-03-02 | 2026-09-23 | 2026-10-21
A24660 | Electric Heat Tracing - Pre Comm | 2026-11-18 | 2026-12-09 | 2027-03-03 | 2027-03-23 | 2026-10-21 | 2026-11-11
GFPowerTransformers(Qty05) |  | 2026-08-27 | 2026-11-24 | 2026-12-24 | 2027-03-23 | 2026-08-15 | 2026-11-11
A24120 | Installation of Power Transformers | 2026-08-27 | 2026-10-06 | 2026-12-24 | 2027-02-02 | 2026-08-15 | 2026-09-23
A24470 | Cable terminations and loop testing - Power Transformers | 2026-10-07 | 2026-11-03 | 2027-02-03 | 2027-03-02 | 2026-09-24 | 2026-10-21
A24680 | Power Transformers - Pre Comm | 2026-11-04 | 2026-11-24 | 2027-03-03 | 2027-03-23 | 2026-10-22 | 2026-11-11
GFHVCapacitorBay |  | 2026-08-27 | 2026-10-31 | 2027-01-18 | 2027-03-23 | 2026-08-04 | 2026-10-07
A24080 | Installation of Capacitor Bay | 2026-08-27 | 2026-09-16 | 2027-01-18 | 2027-02-07 | 2026-08-04 | 2026-08-24
A24490 | Cable terminations and HV Capacitor Bay | 2026-09-17 | 2026-10-11 | 2027-02-08 | 2027-03-03 | 2026-08-25 | 2026-09-17
A24700 | HV Capacitor Bay - Pre Comm | 2026-10-12 | 2026-10-31 | 2027-03-04 | 2027-03-23 | 2026-09-19 | 2026-10-07
GFSwitchgear(LV,MV) |  | 2026-09-10 | 2026-12-13 | 2026-12-20 | 2027-03-23 | 2026-08-22 | 2026-11-23
A24530 | Cable terminations and loop testing - Switchgear (LV, MV) | 2026-10-15 | 2026-11-18 | 2027-01-24 | 2027-02-27 | 2026-09-26 | 2026-10-29
A24740 | Switchgear (LV, MV) - Pre Comm | 2026-11-19 | 2026-12-13 | 2027-02-28 | 2027-03-23 | 2026-10-31 | 2026-11-23
A3839 | Installation of Switchgear | 2026-09-10 | 2026-10-14 | 2026-12-20 | 2027-01-23 | 2026-08-22 | 2026-09-24
GFVariableFequencyDrives(VFDs)LVQty=03 |  | 2026-08-27 | 2026-11-28 | 2026-12-21 | 2027-03-23 | 2026-08-04 | 2026-11-04
A24140 | Installation of VFD | 2026-08-27 | 2026-09-23 | 2026-12-21 | 2027-01-17 | 2026-08-04 | 2026-08-31
A24540 | Cable terminations and loop testing - VFD | 2026-09-24 | 2026-10-31 | 2027-01-18 | 2027-02-23 | 2026-09-01 | 2026-10-07
A24750 | VFDs - Pre Comm | 2026-11-01 | 2026-11-28 | 2027-02-24 | 2027-03-23 | 2026-10-08 | 2026-11-04
GFNGRPanelQty02 |  | 2026-08-27 | 2026-10-24 | 2027-01-25 | 2027-03-23 | 2026-08-04 | 2026-09-30
A24570 | Cable terminations and loop testing NGR Panel | 2026-09-10 | 2026-10-04 | 2027-02-08 | 2027-03-03 | 2026-08-18 | 2026-09-10
A24780 | NGR Panel - Pre Comm | 2026-10-05 | 2026-10-24 | 2027-03-04 | 2027-03-23 | 2026-09-12 | 2026-09-30
A3869 | Installation of NGR Panel | 2026-08-27 | 2026-09-09 | 2027-01-25 | 2027-02-07 | 2026-08-04 | 2026-08-17
GFCathodicProtection(CP)TotalCSPipingLength-499Meters |  | 2026-10-25 | 2027-01-18 | 2026-12-28 | 2027-03-23 | 2026-10-04 | 2026-12-28
A24100 | Cathodic Protection for complete CS Piping | 2026-10-25 | 2026-11-30 | 2026-12-28 | 2027-02-02 | 2026-10-04 | 2026-11-09
A24420 | Cable terminations and loop testing - Cathodic Protection | 2026-12-01 | 2026-12-28 | 2027-02-03 | 2027-03-02 | 2026-11-10 | 2026-12-07
A24670 | Cathodic Protection - Pre Comm | 2026-12-29 | 2027-01-18 | 2027-03-03 | 2027-03-23 | 2026-12-08 | 2026-12-28
GFUPS(AC-60KVA,20KVA,DC-UPS6.5KVA)Qty1+1+1=03Nos |  | 2026-08-27 | 2026-11-07 | 2027-01-11 | 2027-03-23 | 2026-08-15 | 2026-10-25
A24060 | Installation of UPS | 2026-08-27 | 2026-09-23 | 2027-01-11 | 2027-02-07 | 2026-08-15 | 2026-09-10
A24450 | Cable terminations and loop testing - UPS | 2026-09-24 | 2026-10-17 | 2027-02-08 | 2027-03-02 | 2026-09-12 | 2026-10-04
A24640 | UPS - Pre Comm | 2026-10-18 | 2026-11-07 | 2027-03-03 | 2027-03-23 | 2026-10-05 | 2026-10-25
TAIPCSModificationbyABB |  | 03-Apr-25 A | 10-May-25 A | 2026-06-16 | 2026-06-16 | 03-Apr-25 A | 10-May-25 A
A34830 | Installation of FOPP (02 )in existing CCB | 03-Apr-25 A | 10-May-25 A | 2026-06-16 | 2026-06-16 | 03-Apr-25 A | 10-May-25 A
TASwitchgearModificationbySIEMENS |  | 03-Apr-25 A | 10-May-25 A | 2026-06-16 | 2026-06-16 | 03-Apr-25 A | 10-May-25 A
A17970 | Bus-bar differential testing Bus-A - feeder H01 (TA) | 03-Apr-25 A | 10-May-25 A | 2026-06-16 | 2026-06-16 | 03-Apr-25 A | 10-May-25 A
A17980 | Bus-bar differential testing Bus-B - feeder H16 (TA) | 03-Apr-25 A | 10-May-25 A | 2026-06-16 | 2026-06-16 | 03-Apr-25 A | 10-May-25 A
A34440 | Switchgear Modifications - Siemens | 03-Apr-25 A | 10-May-25 A | 2026-06-16 | 2026-06-16 | 03-Apr-25 A | 10-May-25 A
A34800 | Installation of Surge Arersstor | 03-Apr-25 A | 10-May-25 A | 2026-06-16 | 2026-06-16 | 03-Apr-25 A | 10-May-25 A
A34810 | Installation of Dummy Plugs | 03-Apr-25 A | 10-May-25 A | 2026-06-16 | 2026-06-16 | 03-Apr-25 A | 10-May-25 A
A34820 | Installation of Castle key interlock and key exchange box | 03-Apr-25 A | 10-May-25 A | 2026-06-16 | 2026-06-16 | 03-Apr-25 A | 10-May-25 A
TASCMSModificationbySIEMENS |  | 14-Apr-25 A | 14-May-25 A | 2026-06-16 | 2026-06-16 | 14-Apr-25 A | 14-May-25 A
A17990 | SCMS FOPP Modifications - Siemens (By Client) | 14-Apr-25 A | 25-Apr-25 A | 2026-06-16 | 2026-06-16 | 14-Apr-25 A | 25-Apr-25 A
A34780 | Mapping of SCMS in IPCS | 26-Apr-25 A | 30-Apr-25 A | 2026-06-16 | 2026-06-16 | 26-Apr-25 A | 30-Apr-25 A
A34840 | Annuciator Panel Modification | 01-May-25 A | 09-May-25 A | 2026-06-16 | 2026-06-16 | 01-May-25 A | 09-May-25 A
A34850 | HMI Graphics Update | 10-May-25 A | 14-May-25 A | 2026-06-16 | 2026-06-16 | 10-May-25 A | 14-May-25 A
TAUPSModification |  | 15-Apr-25 A | 13-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 13-May-25 A
A17960 | Modification in DC power supply arrangmeent- UPS | 15-Apr-25 A | 13-May-25 A | 2026-06-16 | 2026-06-16 | 15-Apr-25 A | 13-May-25 A
CablingWork |  | 2026-08-01 | 2026-11-15 | 2026-12-07 | 2027-03-23 | 2026-07-29 | 2026-11-12
BFElectricalWorks |  | 2026-08-01 | 2026-11-15 | 2026-12-07 | 2027-03-23 | 2026-07-29 | 2026-11-12
A17740 | Power Cables Laying | 2026-08-01 | 2026-09-10 | 2026-12-07 | 2027-01-17 | 2026-07-29 | 2026-09-08
A18740 | Termination of Power cables and Loop Testing | 2026-09-12 | 2026-10-11 | 2027-01-18 | 2027-02-16 | 2026-09-09 | 2026-10-08
A18750 | FO Cable laying for IPCSS and SCMS | 2026-08-01 | 2026-09-10 | 2026-12-15 | 2027-01-26 | 2026-07-29 | 2026-09-08
A21980 | FO Cable termination for IPCSS and SCMS | 2026-09-23 | 2026-10-22 | 2027-01-30 | 2027-02-28 | 2026-09-21 | 2026-10-20
BFW4080 | Other Electrical Works | 2026-10-24 | 2026-11-15 | 2027-03-01 | 2027-03-23 | 2026-10-21 | 2026-11-12
EarthingSystemInstallation |  | 2026-08-09 | 2026-11-01 | 2026-12-30 | 2027-03-23 | 2026-07-28 | 2026-10-19
A61660 | Earthing System Installation | 2026-08-09 | 2026-10-18 | 2026-12-30 | 2027-03-09 | 2026-07-28 | 2026-10-05
A61670 | Earthing System Testing | 2026-10-18 | 2026-11-01 | 2027-03-10 | 2027-03-23 | 2026-10-06 | 2026-10-19
LightningSystemInstallation |  | 2026-09-16 | 2026-10-04 | 2027-03-07 | 2027-03-23 | 2026-09-15 | 2026-10-03
GFLightingFixtures(Almost50%Exd=354Nos) |  | 2026-09-16 | 2026-10-04 | 2027-03-07 | 2027-03-23 | 2026-09-15 | 2026-10-03
A3590 | Complete Street lighting | 2026-09-16 | 2026-10-04 | 2027-03-07 | 2027-03-23 | 2026-09-15 | 2026-10-03
Others |  | 01-Mar-25 A | 15-Mar-25 A | 2026-06-16 | 2026-06-16 | 20-Dec-24 A | 2027-07-20
TASiteSurveyAC&DCUPS(ChlorideTerchnology) |  | 01-Mar-25 A | 15-Mar-25 A | 2026-06-16 | 2026-06-16 | 01-Mar-25 A | 15-Mar-25 A
A35010 | Site Survey for UPS Modification | 01-Mar-25 A | 07-Mar-25 A | 2026-06-16 | 2026-06-16 | 01-Mar-25 A | 07-Mar-25 A
A37540 | Site Survey Report for UPS Modification | 08-Mar-25 A | 15-Mar-25 A | 2026-06-16 | 2026-06-16 | 08-Mar-25 A | 15-Mar-25 A
TASiteSurveyMCMSSystem(BentlyNevada) |  | 01-Mar-25 A | 15-Mar-25 A | 2026-06-16 | 2026-06-16 | 01-Mar-25 A | 15-Mar-25 A
A35020 | Site Survey for MCMS Modification | 01-Mar-25 A | 07-Mar-25 A | 2026-06-16 | 2026-06-16 | 01-Mar-25 A | 07-Mar-25 A
A37550 | Site Survey Report for MCMS Modification | 08-Mar-25 A | 15-Mar-25 A | 2026-06-16 | 2026-06-16 | 08-Mar-25 A | 15-Mar-25 A
ForSwitchgear&SCMS(Siemens) |  | 01-Mar-25 A | 15-Mar-25 A | 2026-06-16 | 2026-06-16 | 01-Mar-25 A | 15-Mar-25 A
A34980 | Site Survey for SG & SCMS Modification | 01-Mar-25 A | 07-Mar-25 A | 2026-06-16 | 2026-06-16 | 01-Mar-25 A | 07-Mar-25 A
A35140 | Health Check / Site Survey Report | 08-Mar-25 A | 15-Mar-25 A | 2026-06-16 | 2026-06-16 | 08-Mar-25 A | 15-Mar-25 A
Instrumentation/TelecomConstruction |  | 11-Feb-25 A | 2027-01-07 | 2026-06-16 | 2027-03-23 | 11-Feb-25 A | 2026-12-28
MCMS/DCS/ESD/F&GModification/Installation(asapplicable) |  | 01-May-25 A | 2027-01-07 | 2026-06-16 | 2027-03-23 | 01-May-25 A | 2026-11-23
GFFireFightingEquipment |  | 2026-10-12 | 2027-01-03 | 2026-12-31 | 2027-03-23 | 2026-08-04 | 2026-10-25
A24400 | Cable terminations and loop testing - Fire Fighting Equipment | 2026-11-23 | 2026-12-13 | 2027-02-11 | 2027-03-02 | 2026-09-15 | 2026-10-04
A24610 | Fire Fighting Equip - Pre Comm | 2026-12-13 | 2027-01-03 | 2027-03-03 | 2027-03-23 | 2026-10-05 | 2026-10-25
A3849 | Installation of Fire Fighting Equipment | 2026-10-12 | 2026-11-23 | 2026-12-31 | 2027-02-10 | 2026-08-04 | 2026-09-14
BFDCS/ESDModificationbyHoneywell |  | 2026-07-08 | 2026-08-17 | 2026-12-22 | 2027-01-31 | 2026-05-23 | 2026-07-02
A17750 | DCS modification for integration between brownfield and greenfield | 2026-07-08 | 2026-08-17 | 2026-12-22 | 2027-01-31 | 2026-05-23 | 2026-07-02
GFFireDetectionAlarmSystem,LocalFireControlPanel&CleanAgentUnit |  | 2026-10-31 | 2027-01-07 | 2027-01-13 | 2027-03-23 | 2026-08-04 | 2026-11-16
A24110 | Installation of Fire Detection Alarm System, LFCP and Clean Agent Unit | 2026-10-31 | 2026-12-10 | 2027-01-13 | 2027-02-23 | 2026-08-04 | 2026-09-14
A24460 | Cable terminations and loop testing - FDAS, LFCP and Clean Agent Unit | 2026-11-17 | 2026-12-21 | 2027-01-31 | 2027-03-06 | 2026-09-15 | 2026-10-19
A24650 | FDAS, LFCP & CAU - Pre Comm | 2026-12-12 | 2027-01-07 | 2027-02-24 | 2027-03-23 | 2026-10-20 | 2026-11-16
TAEU3ICSS(DCS/ESD/GDS)ModificationsbyHONEYWELL |  | 01-May-25 A | 15-May-25 A | 2026-06-16 | 2026-06-16 | 01-May-25 A | 15-May-25 A
A21970 | Cross wiring between existing marshalling racks ( Instrument Tie-in No 6,7) | 01-May-25 A | 15-May-25 A | 2026-06-16 | 2026-06-16 | 01-May-25 A | 15-May-25 A
A34910 | Installation of New Non-IS ESD Cabinet (83-JM3021-D) (Intrument Tie-In-8) | 01-May-25 A | 15-May-25 A | 2026-06-16 | 2026-06-16 | 01-May-25 A | 15-May-25 A
A34920 | Non-UPS Power &earthing for New Non-IS ESD Cabinet (Intrument Tie-In- 9) | 01-May-25 A | 15-May-25 A | 2026-06-16 | 2026-06-16 | 01-May-25 A | 15-May-25 A
A34930 | (OEM) Vendor (Honeywell) loose supplied (Intrument Tie-In- 9.1) | 01-May-25 A | 15-May-25 A | 2026-06-16 | 2026-06-16 | 01-May-25 A | 15-May-25 A
A34940 | COLD Section ESD shutdown console switches (Intrument Tie-In- 11) | 01-May-25 A | 15-May-25 A | 2026-06-16 | 2026-06-16 | 01-May-25 A | 15-May-25 A
A34950 | OEM) Vendor loose supplied material installation Including Honeywell, Safetec (Instrument Tie-12) | 01-May-25 A | 15-May-25 A | 2026-06-16 | 2026-06-16 | 01-May-25 A | 15-May-25 A
A34960 | Change in the Existing DCS configuration for BF added/ Modified Field Tag (Instrument TieIn-14) | 01-May-25 A | 15-May-25 A | 2026-06-16 | 2026-06-16 | 01-May-25 A | 15-May-25 A
A34970 | Change in the Existing ESD configuration for BF added/ Modified Field Tag(Instrument TieIn-14.1) | 01-May-25 A | 15-May-25 A | 2026-06-16 | 2026-06-16 | 01-May-25 A | 15-May-25 A
GFF&GFlameDetectors,MCP,Beacon(Nos324) |  | 2026-10-10 | 2026-12-29 | 2027-01-02 | 2027-03-23 | 2026-09-02 | 2026-11-23
A24130 | Installation of F&G Detectors, MCP,Beacon | 2026-10-10 | 2026-11-11 | 2027-01-02 | 2027-02-03 | 2026-09-02 | 2026-10-06
A24500 | Cable terminations and loop testing - F&G Detectors, MCP, Beacon | 2026-11-12 | 2026-12-08 | 2027-02-04 | 2027-03-02 | 2026-10-06 | 2026-11-02
A24710 | F&G, MCP, Beacon - Pre Comm | 2026-12-09 | 2026-12-29 | 2027-03-03 | 2027-03-23 | 2026-11-02 | 2026-11-23
TAFireAlarmSystemModificationbySAFCO+HONEYWELL |  | 15-May-25 A | 25-May-25 A | 2026-06-16 | 2026-06-16 | 15-May-25 A | 25-May-25 A
A34740 | Existing Deluge Console switches shall be relocated including retesting of existing loops on new dual tier Console | 15-May-25 A | 25-May-25 A | 2026-06-16 | 2026-06-16 | 15-May-25 A | 25-May-25 A
TAModificationinMCMSSystembyBENTLYNAVEDA |  | 01-May-25 A | 15-May-25 A | 2027-02-01 | 2027-02-01 | 01-May-25 A | 15-May-25 A
A34710 | Existing MCMS system 1 will be upgraded with new EVO series servers for EU3 existing network | 01-May-25 A | 15-May-25 A | 2027-02-01 | 2027-02-01 | 01-May-25 A | 15-May-25 A
FieldInstrumentInstallation |  | 01-May-25 A | 2026-12-30 | 2026-06-16 | 2027-03-23 | 01-May-25 A | 2026-12-28
GFMachineConditionMonitoringSystem |  | 2026-08-27 | 2026-11-21 | 2026-12-28 | 2027-03-23 | 2026-08-04 | 2026-10-28
A24480 | Cable terminations and loop testing - MCMS | 2026-10-08 | 2026-11-01 | 2027-02-08 | 2027-03-03 | 2026-09-15 | 2026-10-08
A24690 | MCMS - Pre Comm | 2026-11-02 | 2026-11-21 | 2027-03-04 | 2027-03-23 | 2026-10-10 | 2026-10-28
A3789 | Installation of MCMS | 2026-08-27 | 2026-10-07 | 2026-12-28 | 2027-02-07 | 2026-08-04 | 2026-09-14
TAReplacementofExistingAirDistributionPot |  | 01-May-25 A | 15-May-25 A | 2026-06-16 | 2026-06-16 | 01-May-25 A | 15-May-25 A
A34860 | Replacoment of existing ADP (E3-SP-0146) from 6-ways to 10-ways (Intrument Tie-In- 1.1) | 01-May-25 A | 15-May-25 A | 2026-06-16 | 2026-06-16 | 01-May-25 A | 15-May-25 A
A34870 | Replacoment of existing ADP (E3-SP-0322) from 6-ways to 10-ways (Intrument Tie-In- 1) | 01-May-25 A | 15-May-25 A | 2026-06-16 | 2026-06-16 | 01-May-25 A | 15-May-25 A
A34880 | Replacoment of existing ADP (E3-SP-0149) from 6-ways to 10-ways (Intrument Tie-In- 2) | 01-May-25 A | 15-May-25 A | 2026-06-16 | 2026-06-16 | 01-May-25 A | 15-May-25 A
GFAcessControlSystem |  | 2026-10-05 | 2026-12-30 | 2026-12-28 | 2027-03-23 | 2026-09-09 | 2026-12-05
A24430 | Cable terminations and loop testing - ACS | 2026-11-02 | 2026-12-09 | 2027-01-25 | 2027-03-02 | 2026-10-07 | 2026-11-14
A24620 | ACS - Pre Comm | 2026-12-09 | 2026-12-30 | 2027-03-03 | 2027-03-23 | 2026-11-14 | 2026-12-05
A3859 | Installation of Access Control System | 2026-10-05 | 2026-11-02 | 2026-12-28 | 2027-01-24 | 2026-09-09 | 2026-10-07
GFVESDA(VeryEarlySmokeDetectionApparatus) |  | 2026-08-27 | 2026-11-14 | 2027-01-04 | 2027-03-23 | 2026-08-04 | 2026-10-21
A24510 | Cable terminations and loop testing VESDA | 2026-09-28 | 2026-10-24 | 2027-02-04 | 2027-03-02 | 2026-09-05 | 2026-09-30
A24720 | VESDA - Pre Comm | 2026-10-25 | 2026-11-14 | 2027-03-03 | 2027-03-23 | 2026-10-01 | 2026-10-21
A3799 | Installation of VESDA | 2026-08-27 | 2026-09-27 | 2027-01-04 | 2027-02-03 | 2026-08-04 | 2026-09-03
GFMOVs[BallType24"150#=01No] |  | 2026-08-01 | 2026-09-02 | 2027-02-15 | 2027-03-23 | 2026-09-26 | 2026-10-28
A24160 | Installatrion of MOV | 2026-08-01 | 2026-08-05 | 2027-02-15 | 2027-02-20 | 2026-09-26 | 2026-09-30
A24550 | Cable terminations and lop termination - MOVs | 2026-08-05 | 2026-08-19 | 2027-02-21 | 2027-03-06 | 2026-09-30 | 2026-10-14
A24760 | MOVS - Pre Comm | 2026-08-19 | 2026-09-02 | 2027-03-10 | 2027-03-23 | 2026-10-14 | 2026-10-28
TACompresoorCGCTurbinebyMHI |  | 01-Sep-25 A | 10-Sep-25 A | 2026-06-16 | 2026-06-16 | 01-Sep-25 A | 10-Sep-25 A
A21840 | Turbine Governor Software modification by MHI (Intrument Tie-In- 15) | 01-Sep-25 A | 10-Sep-25 A | 2026-06-16 | 2026-06-16 | 01-Sep-25 A | 10-Sep-25 A
TASGMReplacement(EMERSON) |  | 01-May-25 A | 15-May-25 A | 2027-02-01 | 2027-02-01 | 01-May-25 A | 15-May-25 A
A34720 | Existing Gas density Meter to replaced by SGM (EMERSON) (Intrument Tie-In- 3) | 01-May-25 A | 15-May-25 A | 2027-02-01 | 2027-02-01 | 01-May-25 A | 15-May-25 A
A34890 | SGM meter connection to nearest Power Distruribution Board (Intrument Tie-In- 3.1) | 01-May-25 A | 15-May-25 A | 2027-02-01 | 2027-02-01 | 01-May-25 A | 15-May-25 A
A34900 | New Tubing for Votex cooling of sgm Cabinet SGM (EMERSON) ((Intrument Tie-In- 2) | 01-May-25 A | 15-May-25 A | 2027-02-01 | 2027-02-01 | 01-May-25 A | 15-May-25 A
GFIntegratedControlandSafetySystemGF |  | 2026-09-12 | 2026-12-09 | 2026-12-24 | 2027-03-23 | 2026-09-29 | 2026-12-28
A3729 | Installation of ICSS System | 2026-09-12 | 2026-10-21 | 2026-12-24 | 2027-02-02 | 2026-09-29 | 2026-11-09
A3879 | Cable terminations and loop testing ICSS - GF | 2026-10-22 | 2026-11-15 | 2027-02-03 | 2027-02-27 | 2026-11-09 | 2026-12-03
A3899 | ICSS - Pre Comm | 2026-11-16 | 2026-12-09 | 2027-02-28 | 2027-03-23 | 2026-12-03 | 2026-12-28
GFGauges(PG,TG,PDG,Analzer,FE)PG-10bar&40bar=19Nos,DP=05Nos,TG=09Nos |  | 2026-10-01 | 2026-12-16 | 2027-01-06 | 2027-03-23 | 2026-08-29 | 2026-11-12
A24150 | Installation of Field Instruments | 2026-10-01 | 2026-10-28 | 2027-01-06 | 2027-02-02 | 2026-08-29 | 2026-09-24
A24560 | Cable terminations and loop testing - Gauges (PG, TG, PDG) | 2026-10-29 | 2026-11-25 | 2027-02-03 | 2027-03-02 | 2026-09-26 | 2026-10-22
A24770 | Guages (PG, TG, PDG) - Pre Comm (Calibration/Testing) | 2026-11-26 | 2026-12-16 | 2027-03-03 | 2027-03-23 | 2026-10-24 | 2026-11-12
TAFieldInstrumentModification |  | 01-May-25 A | 15-May-25 A | 2027-02-01 | 2027-02-01 | 01-May-25 A | 15-May-25 A
A21850 | Dp Flow Transmitters to be re-calibrated ( approx qty- 20 nos.) in existing EU3 plant area | 01-May-25 A | 15-May-25 A | 2027-02-01 | 2027-02-01 | 01-May-25 A | 15-May-25 A
A21860 | Replacement of 13-PV-4515 and stroke calibration, loop Testing (Intrument Tie-In- 4) | 01-May-25 A | 15-May-25 A | 2027-02-01 | 2027-02-01 | 01-May-25 A | 15-May-25 A
A34700 | Flow Element to be re-calibrated ( approx qty- 19 nos.) in existing EU3 plant area | 01-May-25 A | 15-May-25 A | 2027-02-01 | 2027-02-01 | 01-May-25 A | 15-May-25 A
GFIntegratedProtectionControlSystem |  | 2026-08-27 | 2026-12-02 | 2026-12-16 | 2027-03-23 | 2026-09-16 | 2026-12-23
A24390 | Cable terminations and loop testing - IPCS | 2026-10-01 | 2026-11-04 | 2027-01-20 | 2027-02-23 | 2026-10-21 | 2026-11-25
A24600 | IPCS - Pre Comm | 2026-11-05 | 2026-12-02 | 2027-02-24 | 2027-03-23 | 2026-11-25 | 2026-12-23
A3769 | Installation of IPCS | 2026-08-27 | 2026-09-30 | 2026-12-16 | 2027-01-19 | 2026-09-16 | 2026-10-21
TAInstrumentationWork |  | 01-May-25 A | 15-May-25 A | 2027-01-03 | 2027-02-01 | 01-May-25 A | 15-May-25 A
A18330 | Instrument Air Tubing from existing Spare ADP connections to new valves in Brown Field area- @ 7 nos. | 01-May-25 A | 15-May-25 A | 2027-02-01 | 2027-02-01 | 01-May-25 A | 15-May-25 A
A23560 | Heath Check for ICSS Report | 01-May-25 A | 15-May-25 A | 2027-01-03 | 2027-01-03 | 01-May-25 A | 15-May-25 A
Cablingwork |  | 2026-07-08 | 2026-11-18 | 2026-11-18 | 2027-03-23 | 2026-07-29 | 2026-11-12
GFCableTrayandInstrumentJunctionBox(PerforatedCabletrayHeavyduty=5982Mtrs,JBs=73Nos) |  | 2026-07-29 | 2026-11-18 | 2026-12-02 | 2027-03-23 | 2026-07-29 | 2026-11-18
A61680 | GF Cable Tray and Junction Box | 2026-07-29 | 2026-11-18 | 2026-12-02 | 2027-03-23 | 2026-07-29 | 2026-11-18
GFFibreOpticCable(Armoured,Telecom/IT/MAS) |  | 2026-07-21 | 2026-11-09 | 2026-11-18 | 2027-03-09 | 2026-03-26 | 2026-07-15
A61690 | GF Fiber Optic cable | 2026-07-21 | 2026-11-09 | 2026-11-18 | 2027-03-09 | 2026-03-26 | 2026-07-15
BFInstrumentationWorks |  | 2026-07-08 | 2026-10-22 | 2026-11-29 | 2027-03-23 | 2026-05-23 | 2026-09-14
A18730 | Laying UTP/CAT5 cable from B3-CCB Network cabinet (82-JS- 4844) located Ethernet swtich to B3-CCB located SOE PC | 2026-08-01 | 2026-08-23 | 2026-12-15 | 2027-01-06 | 2026-07-29 | 2026-08-20
A21790 | Cable tray in EU3 SIS and H2 Extraction Plant SIS | 2026-09-01 | 2026-09-14 | 2027-01-13 | 2027-01-26 | 2026-05-23 | 2026-06-04
FOCableLaying |  | 2026-09-01 | 2026-09-28 | 2026-12-15 | 2027-02-09 | 2026-05-23 | 2026-06-22
A17760 | Laying FO cables inside existing trenches/pipe/conduit between EU3 SIS &new H2 Plant SIS | 2026-09-01 | 2026-09-28 | 2027-01-13 | 2027-02-09 | 2026-05-23 | 2026-06-20
A21780 | Laying FO cables inside existing trenches/pipe/conduit between B3 CCB to new H2 Plant SIS | 2026-09-01 | 2026-09-21 | 2026-12-15 | 2027-01-04 | 2026-06-01 | 2026-06-22
A21880 | Laying PU ASC PLC (TRICONEX) FO cable between new SIS at H2 Green Field area and B3-CCB for TRICONEX PLC | 2026-09-06 | 2026-09-19 | 2026-12-20 | 2027-01-02 | 2026-06-06 | 2026-06-20
HardwiredCableLaying |  | 2026-07-08 | 2026-08-17 | 2026-11-29 | 2027-03-23 | 2026-05-23 | 2026-07-02
A17770 | Trench & cable laying | 2026-07-08 | 2026-08-17 | 2027-02-11 | 2027-03-23 | 2026-05-23 | 2026-07-02
A18320 | Hardwired multicore/pair cable laying between EU3 SIS to H2 Extraction Plant SIS | 2026-07-08 | 2026-08-05 | 2026-11-29 | 2026-12-27 | 2026-05-23 | 2026-06-20
Termination |  | 2026-08-05 | 2026-10-22 | 2026-12-10 | 2027-01-31 | 2026-05-23 | 2026-09-14
A17780 | FO Patch cord laying | 2026-09-01 | 2026-09-28 | 2026-12-10 | 2027-01-06 | 2026-05-23 | 2026-06-18
A21810 | Termination & Testing of various FO cables laid between EU3 SIS to new H2 Plant SIS | 2026-09-29 | 2026-10-22 | 2027-01-07 | 2027-01-31 | 2026-08-20 | 2026-09-14
A21820 | Termination & Testing of FO cables laid between B3-CCB to new H2 Plant SIS | 2026-08-23 | 2026-09-16 | 2027-01-07 | 2027-01-31 | 2026-08-20 | 2026-09-14
A21830 | Termination of Hardwiring multicore/pair cable inside existing/new marshalling cabinets | 2026-08-05 | 2026-08-25 | 2026-12-27 | 2027-01-16 | 2026-06-20 | 2026-07-11
A21890 | Termination at Green Field H2 SIS of' PU ASC PLC (TRICONEX) FO cable between new SIS at H2 Green Field area and B3-CCB | 2026-09-20 | 2026-10-18 | 2027-01-03 | 2027-01-31 | 2026-06-27 | 2026-07-26
TelecommunicationSystemInstallation |  | 01-May-25 A | 2026-12-10 | 2026-06-16 | 2027-03-23 | 01-May-25 A | 2026-10-31
GFPAGA+Telephone |  | 2026-10-06 | 2026-12-03 | 2027-01-24 | 2027-03-23 | 2026-08-22 | 2026-10-19
A24440 | Cable terminations and loop testing - PAGA + Telephone | 2026-10-31 | 2026-11-16 | 2027-02-17 | 2027-03-06 | 2026-09-15 | 2026-10-01
A24630 | PAGA + Telephone - Pre Comm | 2026-11-17 | 2026-12-03 | 2027-03-07 | 2027-03-23 | 2026-10-03 | 2026-10-19
A3809 | Installation of PAGA+Telephone | 2026-10-06 | 2026-10-29 | 2027-01-24 | 2027-02-16 | 2026-08-22 | 2026-09-14
GFCCTV |  | 2026-10-06 | 2026-12-10 | 2027-01-17 | 2027-03-23 | 2026-08-25 | 2026-10-31
A24520 | Cable terminations and loop testing - CCTV | 2026-10-31 | 2026-11-23 | 2027-02-10 | 2027-03-06 | 2026-09-19 | 2026-10-13
A24730 | CCTV - Pre Comm | 2026-11-24 | 2026-12-10 | 2027-03-07 | 2027-03-23 | 2026-10-13 | 2026-10-31
A3819 | Installation of CCTV | 2026-10-06 | 2026-10-29 | 2027-01-17 | 2027-02-09 | 2026-08-25 | 2026-09-19
TATelecomRelated |  | 01-May-25 A | 15-May-25 A | 2026-06-16 | 2026-06-16 | 01-May-25 A | 15-May-25 A
A18010 | Installation of 08 Nos of Cards in existing system | 01-May-25 A | 15-May-25 A | 2026-06-16 | 2026-06-16 | 01-May-25 A | 15-May-25 A
A37380 | Installation of SFP in existing distribution switch (Hemal / Rommel). | 01-May-25 A | 15-May-25 A | 2026-06-16 | 2026-06-16 | 01-May-25 A | 15-May-25 A
Testing |  | 2026-10-13 | 2026-11-23 | 2027-02-10 | 2027-03-23 | 2026-06-20 | 2026-08-01
A61700 | Fiber Optical Testing | 2026-10-13 | 2026-11-23 | 2027-02-10 | 2027-03-23 | 2026-06-20 | 2026-08-01
Others |  | 11-Feb-25 A | 26-Apr-25 A | 2026-06-16 | 2026-06-16 | 20-Dec-24 A | 2027-07-20
TASiteSurveyForIPCS(ABB) |  | 20-Feb-25 A | 18-Mar-25 A | 2026-06-16 | 2026-06-16 | 20-Feb-25 A | 18-Mar-25 A
A34990 | Site Survey for IPCS Modification | 20-Feb-25 A | 25-Feb-25 A | 2026-06-16 | 2026-06-16 | 20-Feb-25 A | 25-Feb-25 A
A35150 | Health Check / Site Survey Report | 26-Feb-25 A | 18-Mar-25 A | 2026-06-16 | 2026-06-16 | 26-Feb-25 A | 18-Mar-25 A
TASiteSurveyForICSS(Honeywell) |  | 20-Feb-25 A | 18-Mar-25 A | 2026-06-16 | 2026-06-16 | 20-Feb-25 A | 18-Mar-25 A
A35000 | Site Survey for ICSS Modification | 20-Feb-25 A | 25-Feb-25 A | 2026-06-16 | 2026-06-16 | 20-Feb-25 A | 25-Feb-25 A
A37510 | Health Check / Site Survey Report | 26-Feb-25 A | 18-Mar-25 A | 2026-06-16 | 2026-06-16 | 26-Feb-25 A | 18-Mar-25 A
TASiteSurveyForLANSystem(CISCO) |  | 19-Apr-25 A | 26-Apr-25 A | 2026-06-16 | 2026-06-16 | 19-Apr-25 A | 26-Apr-25 A
A37370 | Site Survey for LAN System Modification | 19-Apr-25 A | 22-Apr-25 A | 2026-06-16 | 2026-06-16 | 19-Apr-25 A | 22-Apr-25 A
A37520 | Health Check / Site Survey Report | 23-Apr-25 A | 26-Apr-25 A | 2026-06-16 | 2026-06-16 | 23-Apr-25 A | 26-Apr-25 A
TASiteSurveyForCGCTurbineSoftwareUpgarde |  | 11-Feb-25 A | 21-Feb-25 A | 2026-06-16 | 2026-06-16 | 11-Feb-25 A | 21-Feb-25 A
A37390 | Site Survey for CGC Turbine Software Upgrade | 11-Feb-25 A | 14-Feb-25 A | 2026-06-16 | 2026-06-16 | 11-Feb-25 A | 14-Feb-25 A
A37530 | Site Survey Report for CGC Turbine Software Upgrade | 17-Feb-25 A | 21-Feb-25 A | 2026-06-16 | 2026-06-16 | 17-Feb-25 A | 21-Feb-25 A
TASiteSurveyFireAlarmSystem(SAFCO) |  | 19-Apr-25 A | 26-Apr-25 A | 2026-06-16 | 2026-06-16 | 19-Apr-25 A | 26-Apr-25 A
A35030 | Site Survey for Fire Alaram System Modification | 19-Apr-25 A | 22-Apr-25 A | 2026-06-16 | 2026-06-16 | 19-Apr-25 A | 22-Apr-25 A
A37560 | Site Survey Report for Fire Alaram System Modification | 23-Apr-25 A | 26-Apr-25 A | 2026-06-16 | 2026-06-16 | 23-Apr-25 A | 26-Apr-25 A
Pre-commissioning |  | 2026-09-16 | 2027-03-23 | 2027-02-01 | 2027-03-23 | 2026-07-30 | 2027-01-20
GFPreCommissioningFG/OGCompressor |  | 2027-02-02 | 2027-03-23 | 2027-02-02 | 2027-03-23 | 2026-12-02 | 2027-01-20
C1010 | Flushing/Airblowing and inspection of piping | 2027-02-02 | 2027-02-18 | 2027-02-02 | 2027-02-18 | 2026-12-02 | 2026-12-19 |  |  | CP | CP
C1011 | Lube Oil Flushing | 2027-02-02 | 2027-02-13 | 2027-02-02 | 2027-02-13 | 2026-12-02 | 2026-12-13 |  |  | CP | CP
C1013 | Final compressor/driver alignment | 2027-02-14 | 2027-03-06 | 2027-02-14 | 2027-03-06 | 2026-12-14 | 2027-01-03 |  |  | CP | CP
C1014 | Pre-commissioning punchlist clearing | 2027-03-07 | 2027-03-23 | 2027-03-07 | 2027-03-23 | 2027-01-04 | 2027-01-20 |  |  | CP | CP
GFPre-Comm |  | 2026-10-27 | 2027-03-02 | 2027-02-10 | 2027-03-23 | 2026-10-06 | 2027-01-07
A17800 | Overall Plant & CCB/SIS Building Pre-Commissioning |  | 2027-03-02 |  | 2027-03-23 |  | 2027-01-07
A23590 | Plant Equipments Pre Commissionning | 2027-01-21 | 2027-03-02 | 2027-02-11 | 2027-03-23 | 2026-11-29 | 2027-01-07
A23900 | CCB/SIS systems overall Pre-commissioning |  | 2027-01-07 |  | 2027-03-23 |  | 2026-12-28
A3560 | Piping Cleaning, Flushing & Blowing (Pre Comm) | 2026-10-27 | 2026-12-07 | 2027-02-10 | 2027-03-23 | 2026-10-06 | 2026-11-16
BFPreCommissioning |  | 2026-09-16 | 2027-01-28 | 2027-02-01 | 2027-03-23 | 2026-07-30 | 2026-12-28
BFW4070 | Pre Commissioning works - Instrumentation & Control | 2026-10-24 | 2026-11-25 | 2027-02-01 | 2027-03-06 | 2026-09-14 | 2026-10-18
BFW4090 | Piping Cleaning, Flushing & Blowing (Pre Comm) | 2026-12-12 | 2027-01-28 | 2027-02-03 | 2027-03-23 | 2026-11-10 | 2026-12-28
BFW4100 | Equipment pre commissioning | 2026-09-16 | 2026-10-17 | 2027-02-22 | 2027-03-23 | 2026-07-30 | 2026-08-30
Commissioning,RFSU,Start-Up |  | 2026-07-08 | 2027-06-29 | 2027-04-11 | 2027-09-20 | 2026-05-23 | 2027-04-28
CommissioningandStart-up |  | 2026-07-08 | 2027-06-16 | 2027-04-11 | 2027-09-20 | 2026-05-23 | 2027-04-15
A26480 | Telecom (PAGA / PABX / LAN / CCTV) | 2027-04-29 | 2027-05-10 | 2027-05-17 | 2027-05-29 | 2027-02-27 | 2027-03-09
A27150 | Emergency Diesel Storage & Power Generation System | 2027-04-11 | 2027-04-21 | 2027-04-28 | 2027-05-10 | 2027-02-08 | 2027-02-18
A27160 | Potable & Service Water System | 2027-04-01 | 2027-04-08 | 2027-04-19 | 2027-04-27 | 2027-01-30 | 2027-02-06
A27170 | Sanitary Waste Water System | 2027-04-08 | 2027-04-13 | 2027-04-26 | 2027-05-02 | 2027-02-06 | 2027-02-10
A27180 | Industrial Buildings (MCC / Control Room including HVAC System / Building Fire Alarm System / Clean Agent etc) | 2027-03-24 | 2027-04-06 | 2027-04-11 | 2027-04-25 | 2027-01-21 | 2027-02-03
A27190 | Plant Lighting System | 2027-04-20 | 2027-05-01 | 2027-05-08 | 2027-05-19 | 2027-02-17 | 2027-02-28
A27200 | Power Supply System (Existing 33 KVA) | 2027-04-13 | 2027-04-24 | 2027-05-01 | 2027-05-12 | 2027-02-10 | 2027-02-21
A27240 | MCC | 2027-04-15 | 2027-04-28 | 2027-05-03 | 2027-05-17 | 2027-02-13 | 2027-02-25
A27250 | UPS System | 2027-04-18 | 2027-04-28 | 2027-05-05 | 2027-05-17 | 2027-02-15 | 2027-02-25
A27260 | DCS / ESD / Compressor Control Systems / Machine Monitoring Systems (MMS) | 2027-04-22 | 2027-05-12 | 2027-05-10 | 2027-05-31 | 2027-02-20 | 2027-03-11
A27270 | Anti-Surge Protection System/ PSA2 PLC Control System / Plant F&G System / Deluge Fire Suppression System / Analyzers | 2027-04-25 | 2027-05-08 | 2027-05-12 | 2027-05-26 | 2027-02-22 | 2027-03-07
A27280 | CP System / Heat Tracing System | 2027-04-27 | 2027-05-08 | 2027-05-15 | 2027-05-26 | 2027-02-24 | 2027-03-07
A27290 | Instrument & Plant Air System | 2027-03-29 | 2027-04-08 | 2027-04-15 | 2027-04-27 | 2027-01-26 | 2027-02-06
A27300 | Inert Gas / Nitrogen System | 2027-03-30 | 2027-04-12 | 2027-04-17 | 2027-05-01 | 2027-01-27 | 2027-02-09
A27310 | Fire Water & Fire Suppression System | 2027-03-27 | 2027-04-06 | 2027-04-13 | 2027-04-25 | 2027-01-24 | 2027-02-03
A27320 | LP Steam System | 2027-04-04 | 2027-04-14 | 2027-04-21 | 2027-05-03 | 2027-02-01 | 2027-02-11
A27330 | Oily Water System | 2027-05-04 | 2027-05-09 | 2027-05-22 | 2027-05-27 | 2027-03-03 | 2027-03-08
A27340 | Slop / Drainage System | 2027-05-02 | 2027-05-06 | 2027-05-19 | 2027-05-25 | 2027-03-01 | 2027-03-06
A27350 | Warm & Cold Flare Blowdown System | 2027-05-09 | 2027-05-22 | 2027-05-26 | 2027-06-09 | 2027-03-08 | 2027-03-21
A27360 | LP Condensate Collection System | 2027-04-06 | 2027-04-17 | 2027-04-24 | 2027-05-05 | 2027-02-03 | 2027-02-14
A27370 | Cooling Water Distribution System | 2027-05-06 | 2027-05-13 | 2027-05-24 | 2027-06-01 | 2027-03-06 | 2027-03-13
A27380 | C4 Guard Bed Adsorber Regeneration Gas Cooler & Drip Leg to Existing Fuel Gas System | 2027-05-11 | 2027-05-24 | 2027-05-29 | 2027-06-12 | 2027-03-10 | 2027-03-23
A27390 | Feed Gas from Existing Fuel Gas, C1/C2 Separation Tail Gas Expander Booster Interface Battery Limits | 2027-05-13 | 2027-05-26 | 2027-05-31 | 2027-06-14 | 2027-03-13 | 2027-03-25
A27400 | PSA2 Feed Gas Compressor | 2027-05-17 | 2027-05-30 | 2027-06-03 | 2027-06-17 | 2027-03-16 | 2027-03-29
A27410 | PSA2 H2 Extraction Unit, Closed Sampling & Onwards to Interface Battery Limits | 2027-05-20 | 2027-06-02 | 2027-06-07 | 2027-06-21 | 2027-03-20 | 2027-04-01
A27420 | PSA2 Off Gas Compression (including all drums & coolers), Drip Leg & Onwards to Interface Battery Limits | 2027-05-24 | 2027-06-05 | 2027-06-10 | 2027-06-22 | 2027-03-23 | 2027-04-04
Commissioning&Handover |  | 2026-07-08 | 2027-04-20 | 2027-04-26 | 2027-09-20 | 2026-05-23 | 2027-02-17
A9915 | As BuiltUpdation of UG Composite Layouts in B3/U3 areas, Substation Layouts (B3/ U3) under revamp / modification scope | 2026-07-08 | 2026-10-27 | 2027-05-31 | 2027-09-20 | 2026-05-23 | 2026-09-12
C1039 | PSSR | 2027-03-24 | 2027-04-20 | 2027-04-26 | 2027-05-23 | 2027-01-21 | 2027-02-17
FG&OGCompressor-Commissioing |  | 2027-03-24 | 2027-05-11 | 2027-04-20 | 2027-06-07 | 2027-01-21 | 2027-03-10
C1015 | Compressor UCP Pre-Check / Power | 2027-03-24 | 2027-04-13 | 2027-04-20 | 2027-05-10 | 2027-01-21 | 2027-02-10
C1016 | Hot Loop Testing | 2027-03-30 | 2027-04-19 | 2027-04-26 | 2027-05-16 | 2027-01-27 | 2027-02-16
C1017 | Energization and Motor Solo Run | 2027-04-04 | 2027-04-24 | 2027-05-01 | 2027-05-20 | 2027-02-01 | 2027-02-21
C1018 | Interlock and Emergency Shutdown Tests - Part of Dry Commissioning (C&E Check) | 2027-04-12 | 2027-05-02 | 2027-05-09 | 2027-05-29 | 2027-02-09 | 2027-03-01
C1019 | Control system sequence checks - Part of Dry Commissioning | 2027-04-21 | 2027-05-11 | 2027-05-18 | 2027-06-07 | 2027-02-18 | 2027-03-10
C1020 | Compressor Oil Lubrication System Check | 2027-04-21 | 2027-04-26 | 2027-05-18 | 2027-05-23 | 2027-02-18 | 2027-02-23
C1021 | PSSR | 2027-04-27 | 2027-05-03 | 2027-05-24 | 2027-05-30 | 2027-02-24 | 2027-03-02
RFSU&Handover |  | 2027-04-21 | 2027-06-16 | 2027-05-31 | 2027-09-20 | 2027-02-18 | 2027-04-15
PC1010 | Ready for Start-Up |  | 2027-06-05 |  | 2027-06-22 |  | 2027-04-04 | Start of Start up
PC1030 | Issue "AS BUILT STATUS" Maintenance & Safety Manual | 2027-04-21 | 2027-06-16 | 2027-07-27 | 2027-09-20 | 2027-02-18 | 2027-04-15
PC1050 | Project Close Out ( Handover of Care, Custody & Control of Plant ) |  | 2027-06-15 |  | 2027-09-20 |  | 2027-04-14
FG&OGCompressor-RFSU |  | 2027-05-04 | 2027-05-26 | 2027-05-31 | 2027-06-22 | 2027-03-03 | 2027-03-25
C1022 | Surge Testing | 2027-05-04 | 2027-05-24 | 2027-05-31 | 2027-06-20 | 2027-03-03 | 2027-03-23
C1023 | For motor drives, motor current readings shall be obtained. | 2027-05-04 | 2027-05-24 | 2027-05-31 | 2027-06-20 | 2027-03-03 | 2027-03-23
C1024 | Vibration signatures shall be obtained for all bearings | 2027-05-04 | 2027-05-24 | 2027-05-31 | 2027-06-20 | 2027-03-03 | 2027-03-23
C1025 | Equipment performance data - Mapping | 2027-05-06 | 2027-05-26 | 2027-06-02 | 2027-06-22 | 2027-03-06 | 2027-03-25
Commissioning |  | 2027-03-24 | 2027-05-18 | 2027-06-15 | 2027-08-09 | 01-Aug-25 A | 2027-07-20
A61710 | Commissioning | 2027-03-24 | 2027-05-18 | 2027-06-15 | 2027-08-09 | 2027-01-21 | 2027-03-17
Start-up |  | 2027-05-19 | 2027-06-01 | 2027-08-24 | 2027-09-07 | 2027-03-18 | 2027-03-31
A61720 | Start-Up | 2027-05-19 | 2027-06-01 | 2027-08-24 | 2027-09-07 | 2027-03-18 | 2027-03-31
InitialOperations |  | 2027-06-02 | 2027-06-08 | 2027-09-07 | 2027-09-14 | 2027-04-01 | 2027-04-07
A61730 | Intial Operations | 2027-06-02 | 2027-06-08 | 2027-09-07 | 2027-09-14 | 2027-04-01 | 2027-04-07
PerformanceTestRun |  | 2027-06-08 | 2027-06-15 | 2027-09-14 | 2027-09-20 | 2027-04-07 | 2027-04-14
A61740 | Performance test Run | 2027-06-08 | 2027-06-15 | 2027-09-14 | 2027-09-20 | 2027-04-07 | 2027-04-14
Training |  | 2027-05-19 | 2027-06-29 | 2027-08-10 | 2027-09-20 | 2027-03-18 | 2027-04-28
A61750 | Training | 2027-05-19 | 2027-06-29 | 2027-08-10 | 2027-09-20 | 2027-03-18 | 2027-04-28
OptionalItem’sPrices |  | 10-Sep-25 A | 10-Sep-25 A | 2026-06-16 | 2026-06-16 | 10-Sep-25 A | 10-Sep-25 A
FurnaceModification–OptionalScope |  | 10-Sep-25 A | 10-Sep-25 A | 2026-06-16 | 2026-06-16 | 10-Sep-25 A | 10-Sep-25 A
A61080 | COMPANY Activation for Optional Scope |  | 10-Sep-25 A |  | 2026-06-16 |  | 10-Sep-25 A
ReimbursableItems(ProvisionalSums) |  | 2027-03-24 | 2027-05-10 | 2027-08-04 | 2027-09-20 | 2027-01-21 | 2027-03-09
ProvisionalSumforTwoYearOperatingSpares |  | 2027-03-24 | 2027-05-10 | 2027-08-04 | 2027-09-20 | 2027-01-21 | 2027-03-09
A61760 | Provisional Sum for Two Year Operating Spares | 2027-03-24 | 2027-05-10 | 2027-08-04 | 2027-09-20 | 2027-01-21 | 2027-03-09
ProvisionalSumforAdditionalAssistancetoCompanyIPMT’s |  | 2027-03-24 | 2027-05-10 | 2027-08-04 | 2027-09-20 | 2027-01-21 | 2027-03-09
A61770 | Provisional Sum for Additional Assistance to Company IPMT’s | 2027-03-24 | 2027-05-10 | 2027-08-04 | 2027-09-20 | 2027-01-21 | 2027-03-09
ProvisionalSumforAdditionalStartUpAssistancetoCOMPANY |  | 2027-03-24 | 2027-05-10 | 2027-08-04 | 2027-09-20 | 2027-01-21 | 2027-03-09
A61780 | Provisional Sum for Additional Start Up Assistance to COMPANY | 2027-03-24 | 2027-05-10 | 2027-08-04 | 2027-09-20 | 2027-01-21 | 2027-03-09
TrainingofCOMPANYpersonnel |  | 2027-03-24 | 2027-05-10 | 2027-08-04 | 2027-09-20 | 2027-01-21 | 2027-03-09
A61790 | Training of COMPANY personnel | 2027-03-24 | 2027-05-10 | 2027-08-04 | 2027-09-20 | 2027-01-21 | 2027-03-09
InitialFillsand/orOne(1)fullSpareCharge(refertoAddendumtoScope |  | 2027-03-24 | 2027-05-10 | 2027-08-04 | 2027-09-20 | 2027-01-21 | 2027-03-09
A61800 | Initial Fills and / or One (1) full Spare Charge (refer to Addendum to Scope | 2027-03-24 | 2027-05-10 | 2027-08-04 | 2027-09-20 | 2027-01-21 | 2027-03-09
Feed-gasCompressorFinaldesignconfiguration(3Casingdesign) |  | 2027-03-24 | 2027-05-10 | 2027-08-04 | 2027-09-20 | 2027-01-21 | 2027-03-09
A61810 | Feed-gas Compressor Final design configuration (3 Casing design) | 2027-03-24 | 2027-05-10 | 2027-08-04 | 2027-09-20 | 2027-01-21 | 2027-03-09
AccommodationforIPMT(Site) |  | 2027-03-24 | 2027-05-10 | 2027-08-04 | 2027-09-20 | 2027-01-21 | 2027-03-09
A61820 | Accommodation for IPMT (Site) | 2027-03-24 | 2027-05-10 | 2027-08-04 | 2027-09-20 | 2027-01-21 | 2027-03-09
UnforeseendevelopmentduringExecutionforadditionalservicesoverandabove |  | 2027-03-24 | 2027-05-10 | 2027-08-04 | 2027-09-20 | 2027-01-21 | 2027-03-09
A61830 | Unforeseen development during Execution for additional services over and above | 2027-03-24 | 2027-05-10 | 2027-08-04 | 2027-09-20 | 2027-01-21 | 2027-03-09