## Sheet1
Activity ID | Activity Name | Original Duration | Early Start | Early Finish | Late Start | Late Finish | Total Float
Borouge EU3 H2 Extraction EPC Project - MPR - Feb-2026 |  | 675 | 07-Nov-24 A | 2027-07-20 | 2026-02-21 | 2027-07-20 | 0
COMPANY / PKG 1&2 Interfaces |  | 541 | 20-Nov-24 A | 2027-01-20 | 2026-02-27 | 2027-07-20 | 129
Engineering |  | 365 | 20-Nov-24 A | 2026-05-06 | 2026-05-11 | 2027-07-20 | 305
Required Inputs from COMPANY / Pkg 1&2 |  | 314 | 20-Nov-24 A | 2026-02-20 | 2026-05-11 | 2027-07-20 | 356
A60790 | Receipt of Design parameters within received line list - Pkg 1&2 | 0 |  | 15-Jun-25 A
A60710 | Receipt of Native files of 3D model building & structural design (FEED stage) - Pkg 1&2 | 0 |  | 20-May-25 A
A60740 | Receipt of System architecture & cable block diagram for MCMS, compressor control | 0 |  | 13-Feb-25 A
A60780 | Receipt of Approved vendor data for FG & OG compressor | 0 |  | 24-Apr-25 A
A60770 | Receipt of Approved Vendor data - GAD for PSA-2 unit | 0 |  | 17-Mar-25 A
A60760 | Receipt of Piping TA MTO | 0 |  | 20-Feb-25 A
A60750 | Receipt of FEED datasheets for all telecom systems - Pkg 1&2 | 0 |  | 15-Jan-25 A
A60730 | Receipt of PSCAD native files for electrical studies - Pkg 1&2 | 0 |  | 15-Jan-25 A
A60720 | Receipt of Native files of 3D model, STAAD model, calculations for brown field - Pkg 1&2 | 0 |  | 15-Jan-25 A
A60660 | Receipt of SPI database login | 0 |  | 11-Feb-25 A
A60690 | Receipt of Unit Plot Plan Native File - Pkg 1&2 | 0 |  | 25-Mar-25 A
A5200 | TA Construction Dossier (IFC) - Pkg 1&2 | 0 |  | 04-Apr-25 A
A60700 | Receipt of Drawings for all UG systems | 0 |  | 20-Nov-24 A
P&IDs Status |  | 212 | 19-Jun-25 A | 2026-02-20 | 2026-05-11 | 2027-07-20 | 356
A62490 | Receipt of Final Process Data for Piping Line list - Pkg 1&2 - IFC | 0 |  | 2026-02-20 |  |  | 356
A61020 | Receipt of Final P&ID's - Pkg 1&2 - IFC | 0 |  | 2026-02-20 |  |  | 54
A61030 | Latest Path of Mark-up P&ID by Pkg 3 | 0 |  | 12-Dec-25 A
A60680 | Receipt of Updated P&ID's Updated Line List (Tie-in list, PDS etc) - Pkg 1&2 - Pre-60% Model Review | 0 |  | 05-Sep-25 A |  | 46153
A60670 | Receipt of Updated P&ID's - Pkg 1&2 - Pre-HAZOP | 0 |  | 19-Jun-25 A |  | 46588
SP3D Database Status |  | 229 | 25-Apr-25 A | 19-Nov-25 A
A61010 | Receipt of corrected SP3D database from COMPANY | 0 |  | 19-Nov-25 A
A60650 | Receipt of SP3D database from COMPANY (Not correct) | 0 |  | 25-Apr-25 A
Required Inputs from Pkg 3 to Pkg 1&2 |  | 318 | 04-Mar-25 A | 2026-05-06 | 2026-09-25 | 2026-09-25 | 102
A60950 | Vendor manuals package to be provided by EPC Contractor for Linde's review | 0 |  | 2026-05-06 |  |  | 102
A60850 | Data sheet of control valve, shut down, PSV, check valve and flow element (vendor data sheet) | 0 |  | 2026-05-06 |  |  | 102
A60870 | Instrument data sheet for level, pressure and temperature | 0 |  | 2026-03-19 |  |  | 136
A60830 | Piping isos for main process piping and 3D model | 0 |  | 31-Jul-25 A
A60910 | By-pass line sizing and routing and hot gas bypass valve details | 0 |  | 23-Apr-25 A
A60900 | List of inputs required in compressor process loop | 0 |  | 23-Apr-25 A
A60840 | Mechanical data sheet (vendor data sheet) of vessels and exchangers | 0 |  | 20-Jun-25 A
A60970 | HSE Action Tracking Register - Pkg 3 Actions | 0 |  | 20-May-25 A
A60890 | Review and Confirmation by Pkg -3 contractor as per issue 02 for EICT Cables | 0 |  | 15-May-25 A
A60820 | All EPC Contractor H status input (detail refer Main Activities for P&ID) | 0 |  | 18-Jun-25 A
A60980 | Safty Follow up HAZOP/LOPA Recommendations Package 1c - Pkg 3 related | 0 |  | 23-Apr-25 A
A60960 | Follow up HAZOP/LOPA Recommendations report - 13-KC-701 - PSA2 Feed Gas Compressor - Pkg 3 related | 0 |  | 23-Apr-25 A
A60930 | H2-SIS layout required + power cable details. | 0 |  | 16-Apr-25 A
A60860 | Cause and effect update | 0 |  | 13-Mar-25 A
A60810 | All EPC Contractor G status input (detail refer Main Activities for P&ID) | 0 |  | 13-Mar-25 A
A60920 | GF Balance of Plant maturity w.r.t. Compressor & PSA2 model integration | 0 |  | 27-Mar-25 A
A60990 | Selection for Option of MV motor (650% or 500% of rated current) or Starting VFD for Off Comp. | 0 |  | 04-Mar-25 A
A61000 | Compressor Motor VDDR Motor datasheet - Electrical Cable list | 0 |  | 20-Mar-25 A |  | 46290
A60940 | Homerun cable length with its datasheet required for UCP signal IS calculation | 0 |  | 04-Apr-25 A |  | 46290
A60880 | Review & Confirmation on compressor GAD, Foundation plan & Anchor bolt locations | 0 |  | 20-Mar-25 A |  | 46290
Procurement |  | 503 | 15-Apr-25 A | 2026-10-07 | 2026-02-27 | 2027-01-20 | 105
76.D | FG Compressor - Delivery | 0 |  | 2026-03-03 |  |  | 8
78.D | OG Compressor - Delivery | 0 |  | 2026-03-01 |  |  | 95
A61070 | Approved Key Vendor Data (LLI, Package Details and Design Data) | 0 |  | 2026-02-20 |  | 2026-03-11 | 20
A9950 | PSA Unit Delivery - Delivery | 0 |  | 2026-02-20 |  | 2026-04-25 | 65
A5170 | Key Vendor Data (LLI, Package Details and Design Data) | 0 |  | 2026-02-20 |  | 2026-03-11 | 20
A5210 | BFW Preheater - Delivery | 0 |  | 15-Apr-25 A |  | 46177
A5190 | Free Issue TA Material latest delivery | 0 |  | 15-Apr-25 A |  | 46092
Feed Gas Compressor - Delivery |  | 95 | 13-Feb-26 A | 2026-05-25 | 2026-02-27 | 2027-01-20 | 240
A62320 | Anti-surge valve | 0 |  | 2026-05-25 |  |  | 125
A62370 | Transformer | 0 |  | 2026-04-27 |  | 2026-02-27 | 119
A62310 | LO Console | 0 |  | 2026-03-16 |  | 2026-03-11 | 160
A62360 | VSD | 0 |  | 13-Feb-26 A |  | 46407
A62340 | Main Driver (Motor) for FGC | 0 |  | 2026-03-09 |  | 2026-06-24 | 107
A62330 | Capital Spares | 0 |  | 2026-03-09 |  | 2026-08-23 | 317
A62300 | Feed Gas Compressor (incl. Baseplate, Gear, Gas seal module & Booster) | 0 |  | 2026-03-03 |  | 2026-08-23 | 8
A62350 | UCP | 0 |  | 2026-02-20 |  | 2026-09-27 | 8
Off Gas Compressor: Vendor - Delivery |  | 15 | 2026-02-20 | 2026-03-07 | 2026-05-25 | 2026-08-31 | 177
A62430 | Seal Gas Unit | 0 |  | 2026-03-07 |  | 2026-05-25 | 177
A62400 | Main Driver (Motor) for OGC | 0 |  | 2026-03-04 |  | 2026-05-28 | 122
A62420 | Lube Oil Unit | 0 |  | 2026-03-01 |  | 2026-06-04 | 122
A62380 | Off Gas Compressor | 0 |  | 2026-03-01 |  | 2026-07-01 | 95
A62390 | Capital Spares | 0 |  | 2026-02-22 |  | 2026-07-04 | 95
A62410 | UCP | 0 |  | 2026-02-20 |  | 2026-08-31 | 95
PSA Unit: Vendor - Delivery |  | 384 | 03-Sep-25 A | 2026-10-07 | 2026-07-10 | 2026-12-21 | 75
A62480 | Analyzer (PO pending) | 0 |  | 2026-10-07 |  |  | 75
A62470 | Adsorbent Material (PO pending) | 0 |  | 2026-08-21 |  |  | 51
A62450 | PSA Valve Skid | 0 |  | 2026-02-20 |  | 2026-07-10 | 141
A62460 | PLC Cabinet | 0 |  | 03-Sep-25 A |  | 46306
A62440 | PSA Pressure vessels | 0 |  | 03-Sep-25 A |  | 46377
Construction & Commissioning |  | 0 | 2027-01-20 | 2027-01-20 | 2027-04-27 | 2027-04-27 | 83
A40290 | Nitrogen (Needs) | 0 |  | 2027-01-20 |  | 2027-04-27 | 83
A40280 | Demin water (Needs) | 0 |  | 2027-01-20 |  | 2027-04-27 | 83
A40270 | ETP (Effluent Treatment Package) System (Needs) | 0 |  | 2027-01-20 |  | 2027-04-27 | 83
A40260 | Fire Water (Needs) | 0 |  | 2027-01-20 |  | 2027-04-27 | 83
A40250 | Instrument Air (Needs) for Boiler RFSU | 0 |  | 2027-01-20 |  | 2027-04-27 | 83
A40240 | Chilled Water for Safety Shower | 0 |  | 2027-01-20 |  | 2027-04-27 | 83
A40230 | SANITARY Water system (Needs) | 0 |  | 2027-01-20 |  | 2027-04-27 | 83
A40220 | Potable Water and Service water (Needs) | 0 |  | 2027-01-20 |  | 2027-04-27 | 83
Project Management |  | 650 | 07-Nov-24 A | 2027-07-20 | 2026-03-02 | 2027-07-20 | 0
Project Management |  | 521 | 07-Nov-24 A | 2027-04-05 | 2026-03-27 | 2027-07-20 | 77
Project Management Deliverables |  | 210 | 22-Mar-25 A | 2026-03-17 | 2026-03-27 | 2027-07-20 | 339
A1-PM-PMD-0033 | PM-050-Acceptance Certificate | 4 | 2026-03-13 | 2026-03-17 |  |  | 491
A1-PM-PMD-0048 | PM-078-Guidelines for Acceptance of Work | 5 | 2026-03-06 | 2026-03-13 | 2026-06-11 | 2026-06-11 | 351
A1-PM-PMD-0047 | PM-077-Operating Procedure/Guidelines | 5 | 2026-02-27 | 2026-03-06 | 2026-06-11 | 2026-06-11 | 351
A1-PM-PMD-0028 | PM-045-Project Close out Report | 5 | 2026-02-27 | 2026-03-05 | 2026-06-11 | 2026-06-11 | 358
A1-PM-PMD-0046 | PM-076-Project Training Requirements and Training Plan | 5 | 2026-02-20 | 2026-02-27 | 2026-06-11 | 2026-06-11 | 351
A1-PM-PMD-0058 | PM-088-Process and Utilities Overall Block Flow Diagram Borouge-4 Facilities | 5 | 21-Jul-25 A | 19-Dec-25 A | 46184 | 46184
A1-PM-PMD-0060 | PM-090-Piping External/Internal Connections Layout drawings | 5 | 08-Aug-25 A | 19-Dec-25 A | 46184 | 46184
A1-PM-PMD-0064 | PM-094-Package 1 Deliverables IFC | 5 | 15-May-25 A | 12-Jul-25 A | 46199 | 46199
A1-PM-PMD-0056 | PM-086-Interface Dependency Table | 5 | 14-Jul-25 A | 19-Dec-25 A | 46184 | 46184
A1-PM-PMD-0059 | PM-089-Process and Utilities Block Flow Diagram Interconnecting | 5 | 08-Aug-25 A | 2026-02-20 | 2026-06-11 | 2026-06-11 | 79
A1-PM-PMD-0063 | PM-093-QA/QC Dossiers | 5 | 01-Aug-25 A | 2026-03-16 | 2026-03-27 | 2026-03-27 | 77
A1-PM-PMD-0057 | PM-087-Master Boundary Interface Layout Drawing | 5 | 20-Jun-25 A | 19-Dec-25 A | 46184 | 46184
A1-PM-PMD-0062 | PM-092-Material Record Book (MRB) | 5 | 01-Aug-25 A | 2026-03-05 | 2026-06-11 | 2026-06-11 | 77
A1-PM-PMD-0053 | PM-083-EPC Responsibility Matrix for Control Systems | 5 | 25-Jul-25 A | 19-Dec-25 A | 46184 | 46184
A1-PM-PMD-0052 | PM-082-Interface Responsibility Philosophy | 5 | 21-Jun-25 A | 12-Jul-25 A | 46184 | 46184
A1-PM-PMD-0055 | PM-085-Interface Point Registers | 5 | 08-Aug-25 A | 19-Dec-25 A | 46184 | 46184
A1-PM-PMD-0049 | PM-079-Synergies Study Report | 5 | 08-Sep-25 A | 2026-02-24 | 2026-06-11 | 2026-06-11 | 80
A1-PM-PMD-0061 | PM-091-MRB Index | 5 | 01-Aug-25 A | 2026-02-24 | 2026-06-11 | 2026-06-11 | 77
A1-PM-PMD-0051 | PM-081-Interface Management Plan - EPC | 5 | 25-May-25 A | 10-Sep-25 A | 46184 | 46184
A1-PM-PMD-0054 | PM-084-EPC Responsibility Matrix for ICT & IT/OT | 5 | 08-Aug-25 A | 18-Dec-25 A | 46184 | 46184
A1-PM-PMD-0050 | PM-080-Project IT/EDMS Requirements | 5 | 25-May-25 A | 16-Sep-25 A | 46184 | 46184
A1-PM-PMD-0045 | PM-075-Constructability Action Closeout Report | 5 | 28-Oct-25 A | 2026-02-20 | 2026-06-11 | 2026-06-11 | 351
A1-PM-PMD-0027 | PM-041-List of startup spares | 5 | 25-Aug-25 A | 2026-02-26 | 2026-06-11 | 2026-06-11 | 358
A1-PM-PMD-0044 | PM-074-Asset Integrated Management System (AIMS) / Project Integrity Management Plan | 5 | 08-Aug-25 A | 18-Dec-25 A | 46184 | 46184
A1-PM-PMD-0043 | PM-073-Feed Documents | 5 | 25-May-25 A | 08-Sep-25 A | 46184 | 46184
A1-PM-PMD-0030 | PM-047-Project Execution Plan | 0 |  | 12-Nov-25 A | 46184 | 46184
A1-PM-PMD-0038 | PM-061-Insurance Policies | 5 | 25-May-25 A | 01-Sep-25 A | 46184 | 46184
A1-PM-PMD-0037 | PM-057-Project Specification | 5 | 25-May-25 A | 25-Aug-25 A | 46184 | 46184
A1-PM-PMD-0036 | PM-054-Master Document schedule and Status Report | 5 | 25-May-25 A | 25-Jul-25 A | 46184 | 46184
A1-PM-PMD-0032 | PM-049-Risk Analysis | 5 | 25-May-25 A | 17-Sep-25 A | 46184 | 46184
A1-PM-PMD-0031 | PM-048-HSE Audit Procedure | 5 | 21-Jun-25 A | 12-Jul-25 A | 46184 | 46184
A1-PM-PMD-0042 | PM-065-Requests for Variation | 5 | 01-Sep-25 A | 04-Sep-25 A | 46184 | 46184
A1-PM-PMD-0029 | PM-046-Procurement Status Report | 5 | 25-May-25 A | 25-Jul-25 A | 46184 | 46184
A1-PM-PMD-0041 | PM-064-Claims | 5 | 27-Aug-25 A | 30-Aug-25 A | 46184 | 46184
A1-PM-PMD-0040 | PM-063-Insurance claim status report | 5 | 23-Aug-25 A | 26-Aug-25 A | 46184 | 46184
A1-PM-PMD-0039 | PM-062-Insurance Claims | 5 | 25-Aug-25 A | 05-Sep-25 A | 46184 | 46184
A1-PM-PMD-0034 | PM-052-Contract Trending procedure | 5 | 25-May-25 A | 26-Aug-25 A | 46184 | 46184
A1-PM-PMD-0026 | PM-040-List of Commissioning Spares | 5 | 30-Jul-25 A | 2026-02-24 | 2026-06-11 | 2026-06-11 | 358
A1-PM-PMD-0025 | PM-039-List of Claims for Damage | 5 | 25-May-25 A | 12-Jul-25 A | 46184 | 46184
A1-PM-PMD-0002 | PM-002-Project Coordination Procedure | 0 |  | 18-Apr-25 A | 46184 | 46184
A1-PM-PMD-0024 | PM-038-Documentation List | 5 | 25-May-25 A | 04-Sep-25 A | 46184 | 46184
A1-PM-PMD-0022 | PM-032-Tie-in & Interface Matrix | 5 | 25-May-25 A | 26-Aug-25 A | 46184 | 46184
A1-PM-PMD-0021 | PM-031-Temporary Site Establishment plan | 5 | 25-May-25 A | 25-Aug-25 A
A1-PM-PMD-0019 | PM-029-Recovery Plan | 5 | 25-May-25 A | 12-Jul-25 A | 46563 | 46563
A1-PM-PMD-0018 | PM-028-Project Organization Charts | 5 | 25-May-25 A | 27-Aug-25 A | 46184 | 46184
A1-PM-PMD-0017 | PM-017-HSE Training plan & procedure | 5 | 21-Jun-25 A | 12-Jul-25 A | 46184 | 46184
A1-PM-PMD-0035 | PM-053-Contract Trend notice / Log | 6 | 22-Mar-25 A | 27-Aug-25 A | 46184 | 46184
A1-PM-PMD-0015 | PM-015-CADD Systems As-built Database and System integrated Deliverables (PDS/IN Tools/SP PID/SPEL/ETAP/ Caesar-II / STA | 5 | 25-May-25 A | 05-Sep-25 A | 46184 | 46184
A1-PM-PMD-0023 | PM-037-Document/Drawing Index | 5 | 25-May-25 A | 30-Aug-25 A | 46184 | 46184
A1-PM-PMD-0014 | PM-014-Documentation and CADD Systems / Database Handover Schedule | 5 | 25-May-25 A | 01-Sep-25 A | 46184 | 46184
A1-PM-PMD-0013 | PM-013-PDS / Smart3D Generated List of Drawings / Documents | 5 | 25-May-25 A | 27-Aug-25 A | 46183 | 46183
A1-PM-PMD-0012 | PM-012-PDS / Smart3D Raceways Guideline | 5 | 25-May-25 A | 23-Aug-25 A | 46563 | 46563
A1-PM-PMD-0011 | PM-011-Project Engineering CADD Applications & Deliverables Guideline | 5 | 25-May-25 A | 21-Aug-25 A | 46183 | 46184
A1-PM-PMD-0010 | PM-010-PDS / Smart3D Physical Support Modeling Guideline for End Users | 5 | 25-May-25 A | 16-Sep-25 A | 46181 | 46183
A1-PM-PMD-0009 | PM-009-CADD Project Hierarchy & Setup Guideline (PDS /Intools/ SP PID/ SPEL) | 5 | 25-May-25 A | 12-Sep-25 A | 46575 | 46577
A1-PM-PMD-0008 | PM-008-PDS / Smart3D CADD Area/Model Index/ Plan | 5 | 25-May-25 A | 08-Sep-25 A | 46184 | 46189
A1-PM-PMD-0007 | PM-007-SPEL (Smart Plant Electrical) Guideline for End Users | 5 | 25-May-25 A | 02-Sep-25 A | 46575 | 46581
A1-PM-PMD-0006 | PM-006-SP PID (Smart Plant P&ID ) Guideline for End User | 5 | 25-May-25 A | 30-Aug-25 A | 46566 | 46570
A1-PM-PMD-0005 | PM-005-SPI (Smart Plant Instrumentation) INtoos Guideline for End User | 5 | 25-May-25 A | 26-Aug-25 A | 46191 | 46192
A1-PM-PMD-0004 | PM-004-PDS / Smart3D 3D Modeling Guideline for End User | 5 | 25-May-25 A | 25-Aug-25 A | 46582 | 46588
A1-PM-PMD-0020 | PM-030-Worksite HSE Plan | 5 | 25-May-25 A | 28-May-25 A | 46573 | 46577
A1-PM-PMD-0003 | PM-003-Code of accounts | 5 | 25-May-25 A | 15-Aug-25 A | 46580 | 46584
A1-PM-PMD-0001 | PM-001-Job Bulletins | 5 | 25-May-25 A | 15-Aug-25 A | 46199 | 46203
A1-PM-PMD-0016 | PM-016-Site Mobilization Plan | 6 | 25-May-25 A | 07-Sep-25 A | 46585 | 46588
Project Control Deliverables |  | 256 | 15-Feb-25 A | 2026-02-27 | 2026-03-27 | 2026-11-13 | 185
A1-PM-PCD-0023 | PC-023-SAT Reports | 2 | 2026-02-26 | 2026-02-27 | 2026-03-27 | 2026-03-27 | 185
A1-PM-PCD-0022 | PC-022-SAT Procedures | 2 | 2026-02-24 | 2026-02-25 | 2026-03-27 | 2026-03-27 | 185
A1-PM-PCD-0021 | PC-021-FAT Reports | 2 | 2026-02-20 | 2026-02-23 | 2026-03-27 | 2026-03-27 | 185
A1-PM-PCD-0020 | PC-020-FAT Procedures | 2 | 15-Feb-25 A | 17-Nov-25 A | 46108 | 46108
A1-PM-PCD-0019 | PC-019-Project Execution Plan | 0 |  | 17-Nov-25 A | 46108 | 46108
A1-PM-PCD-0024 | PC-024-P&ID change notes | 2 | 06-Sep-25 A | 07-Sep-25 A | 46108 | 46108
A1-PM-PCD-0029 | PC-029-Site Queries | 2 | 27-Aug-25 A | 29-Aug-25 A | 46108 | 46108
A1-PM-PCD-0015 | PC-015-Annual Reports | 2 | 15-May-25 A | 23-May-25 A | 46108 | 46108
A1-PM-PCD-0002 | PC-002-Distribution Matrix | 2 | 04-Mar-25 A | 03-Nov-25 A | 46108 | 46108
A1-PM-PCD-0028 | PC-028-Field Queries | 2 | 01-Sep-25 A | 08-Sep-25 A | 46108 | 46108
A1-PM-PCD-0014 | PC-014-Suppliers Lists | 2 | 19-Aug-25 A | 20-Aug-25 A | 46108 | 46108
A1-PM-PCD-0027 | PC-027-Change Orders | 2 | 25-Aug-25 A | 29-Aug-25 A | 46108 | 46108
A1-PM-PCD-0035 | PC-035-Back charges Status Report | 2 | 21-Jun-25 A | 12-Jul-25 A | 46108 | 46108
A1-PM-PCD-0034 | PC-034-Cash Flow Forecast | 2 | 25-May-25 A | 14-Oct-25 A | 46108 | 46108
A1-PM-PCD-0032 | PC-032-Invoices Status Report | 2 | 25-May-25 A | 20-Nov-25 A | 46108 | 46108
A1-PM-PCD-0030 | PC-030-Technical Queries | 2 | 25-May-25 A | 27-Aug-25 A | 46108 | 46108
A1-PM-PCD-0026 | PC-026-Query Form | 2 | 25-May-25 A | 09-Sep-25 A | 46108 | 46108
A1-PM-PCD-0025 | PC-025-Engineering Document Change Note | 2 | 25-May-25 A | 02-Sep-25 A | 46108 | 46108
A1-PM-PCD-0018 | PC-018-Forecasts for Completion | 2 | 25-May-25 A | 21-Aug-25 A | 46108 | 46108
A1-PM-PCD-0033 | PC-033-Bank Bonds and Guarantees | 2 | 25-May-25 A | 26-Aug-25 A | 46108 | 46108
A1-PM-PCD-0013 | PC-013-Spares Lists | 2 | 21-Jun-25 A | 12-Jul-25 A | 46108 | 46108
A1-PM-PCD-0031 | PC-031-Invoices | 2 | 25-May-25 A | 20-Nov-25 A | 46108 | 46108
A1-PM-PCD-0012 | PC-012-Specialty Item List | 2 | 21-Jun-25 A | 21-Aug-25 A | 46108 | 46108
A1-PM-PCD-0011 | PC-011-Document/Drawing Index | 2 | 21-Jun-25 A | 12-Jul-25 A | 46108 | 46108
A1-PM-PCD-0010 | PC-010-Variations | 2 | 21-Jun-25 A | 12-Jul-25 A | 46108 | 46108
A1-PM-PCD-0017 | PC-017-Weekly Reports | 2 | 25-May-25 A | 19-Aug-25 A | 46108 | 46108
A1-PM-PCD-0016 | PC-016-Monthly Reports | 2 | 26-May-25 A | 20-Jul-25 A | 46108 | 46108
A1-PM-PCD-0040 | PC-040-Planning Package | 2 | 15-Feb-25 A | 15-Nov-25 A | 46108 | 46108
A1-PM-PCD-0039 | PC-039-Equipment Deployment Plan | 2 | 15-Feb-25 A | 15-Nov-25 A | 46108 | 46108
A1-PM-PCD-0038 | PC-038-Manpower Mobilization Plan | 2 | 15-Feb-25 A | 19-Nov-25 A | 46108 | 46108
A1-PM-PCD-0037 | PC-037-Schedule Risk Analysis Reports | 2 | 15-Feb-25 A | 28-Jun-25 A | 46108 | 46108
A1-PM-PCD-0036 | PC-036-Progress Review and Certification Procedure | 2 | 15-Feb-25 A | 10-Sep-25 A | 46108 | 46108
A1-PM-PCD-0009 | PC-009-Detailed Commissioning and Pre Commissioning Schedule | 2 | 15-Feb-25 A | 17-Jun-25 A
A1-PM-PCD-0008 | PC-008-Detailed Control Log / Schedule | 2 | 15-Feb-25 A | 08-Nov-25 A | 46332 | 46332
A1-PM-PCD-0007 | PC-007-Detailed Construction Schedule | 2 | 15-Feb-25 A | 17-Nov-25 A | 46108 | 46108
A1-PM-PCD-0006 | PC-006-Detailed Engineering Schedule | 2 | 15-Feb-25 A | 17-Nov-25 A | 46108 | 46108
A1-PM-PCD-0005 | PC-005-Detailed Procurement schedule | 2 | 15-Feb-25 A | 14-Nov-25 A | 46108 | 46108
A1-PM-PCD-0004 | PC-004-Overall Project Schedule | 2 | 15-Feb-25 A | 17-Nov-25 A | 46332 | 46335
A1-PM-PCD-0003 | PC-003-Time Schedule / Program | 2 | 15-Feb-25 A | 17-Nov-25 A | 46336 | 46337
A1-PM-PCD-0001 | PC-001-Procedures | 2 | 15-Feb-25 A | 17-Nov-25 A | 46338 | 46339
Project Risk Analysis Workshops |  | 460 | 25-May-25 A | 2027-03-25 | 2026-06-26 | 2027-07-09 | 77
A1-PM-PRA-0008 | PRA08-Project Risk Analysis Workshop - Update - Q07 | 0 |  | 2027-03-25 |  |  | 77
A1-PM-PRA-0007 | PRA07-Project Risk Analysis Workshop - Update - Q06 | 0 |  | 2026-11-19 |  |  | 77
A1-PM-PRA-0006 | PRA06-Project Risk Analysis Workshop - Update - Q05 | 0 |  | 2026-07-16 |  |  | 77
A1-PM-PRA-0005 | PRA05-Project Risk Analysis Workshop - Update - Q04 | 0 |  | 2026-03-12 |  |  | 77
A1-PM-PRA-0004 | PRA04-Project Risk Analysis Workshop - Update - Q03 | 0 |  | 24-Oct-25 A |  | 46199
A1-PM-PRA-0003 | PRA03-Project Risk Analysis Workshop - Update - Q02 | 0 |  | 20-Aug-25 A |  | 46325
A1-PM-PRA-0002 | PRA02-Project Risk Analysis Workshop - Update - Q01 | 0 |  | 21-Jun-25 A |  | 46451
A1-PM-PRA-0001 | PRA01-Project Risk Analysis - Risk Identifications Workshop | 0 |  | 25-May-25 A |  | 46577
Schedule Risk Analysis Workshops |  | 402 | 15-May-25 A | 2027-04-05 | 2026-06-19 | 2027-07-20 | 77
A1-PM-SRA-0008 | SRA08-Schedule Risk Analysis Workshop - Updated Schedule - Q07 | 0 |  | 2027-04-05 |  |  | 77
A1-PM-SRA-0007 | SRA07-Schedule Risk Analysis Workshop - Updated Schedule - Q06 | 0 |  | 2027-03-04 |  |  | 86
A1-PM-SRA-0006 | SRA06-Schedule Risk Analysis Workshop - Updated Schedule - Q05 | 0 |  | 2026-10-29 |  |  | 86
A1-PM-SRA-0005 | SRA05-Schedule Risk Analysis Workshop - Updated Schedule - Q04 | 0 |  | 2026-06-25 |  | 2026-06-19 | 86
A1-PM-SRA-0004 | SRA04-Schedule Risk Analysis Workshop - Updated Schedule - Q03 | 0 |  | 2026-02-20 |  | 2026-10-23 | 86
A1-PM-SRA-0002 | SRA02-Schedule Risk Analysis Workshop - UpdatedSchedule - Q01 | 0 |  | 10-Jul-25 A |  | 46444
A1-PM-SRA-0003 | SRA03-Schedule Risk Analysis Workshop - Updated Schedule - Q02 | 0 |  | 17-Sep-25 A |  | 46570
A1-PM-SRA-0001 | SRA01-Schedule Risk Analysis Workshop - Baseline Schedule | 0 |  | 15-May-25 A |  | 46588
Project Lesson Learn Workshops |  | 462 | 25-May-25 A | 2027-03-30 | 2026-07-07 | 2027-07-20 | 81
A1-PM-LLW-0008 | PRA08-Project Lesson Learn Workshop - Update - Q07 | 0 |  | 2027-03-30 |  |  | 81
A1-PM-LLW-0007 | PRA07-Project Lesson Learn Workshop - Update - Q06 | 0 |  | 2026-11-24 |  |  | 81
A1-PM-LLW-0006 | PRA06-Project Lesson Learn Workshop - Update - Q05 | 0 |  | 2026-07-21 |  |  | 81
A1-PM-LLW-0005 | PRA05-Project Lesson Learn Workshop - Update - Q04 | 0 |  | 2026-03-17 |  |  | 81
A1-PM-LLW-0004 | PRA04-Project Lesson Learn Workshop - Update - Q03 | 0 |  | 01-Oct-25 A |  | 46210
A1-PM-LLW-0003 | PRA03-Project Lesson Learn Workshop - Update - Q02 | 0 |  | 15-Sep-25 A |  | 46336
A1-PM-LLW-0002 | PRA02-Project Lesson Learn Workshop - Update - Q01 | 0 |  | 21-Jun-25 A |  | 46462
A1-PM-LLW-0001 | PRA01-Project Lesson Learn Workshop - Lesson Learn Identifications | 0 |  | 25-May-25 A |  | 46588
Project Management Interim Milestones |  | 160 | 07-Nov-24 A | 30-Oct-25 A
A1-PM-PMM-0003 | 1.A*-Issue Overall Project Execution Plan | 0 |  | 30-Oct-25 A
A1-PM-PMM-0004 | 1.A*-Issue Coordination Procedure | 0 |  | 30-Apr-25 A
A1-PM-PMM-0002 | 10.A-Kick-off Meeting Completed | 0 |  | 06-Dec-24 A
A1-PM-PMM-0001 | Letter of Award (LOA) Recieved - Project Commencement Date | 0 |  | 07-Nov-24 A
QAQC Interim Milestones |  | 0 | 26-May-25 A | 26-May-25 A
General Project Management |  | 0 | 26-May-25 A | 26-May-25 A
A1-PM-QCM-0001 | 1.A*-Issue Project Quality Procedures (Final Issue). | 0 |  | 26-May-25 A
HSE Interim Milestones |  | 0 | 30-Apr-25 A | 30-Apr-25 A
General Project Management |  | 0 | 30-Apr-25 A | 30-Apr-25 A
A1-PM-HSM-0001 | 1.A*-Issue Project HSE Procedure. | 0 |  | 30-Apr-25 A
Project Control Interim Milestones |  | 0 | 24-Mar-25 A | 24-Mar-25 A
A1-PM-PCM-0001 | 2.A-Issue Project Control Propcedures | 0 |  | 24-Mar-25 A
A1-PM-PCM-0004 | 2.A-Issue Planning Docs | 0 |  | 24-Mar-25 A
A1-PM-PCM-0003 | 2.A-Issue Cost Control Procedure | 0 |  | 24-Mar-25 A
A1-PM-PCM-0002 | 2.A-Issue Progress Measurement & Reporting System | 0 |  | 24-Mar-25 A
Moblization of Key Personnel |  | 155 | 15-Nov-24 A | 13-Nov-25 A
A1-PM-KPM-0020 | Moblization of Project Training Manager* | 0 |  | 13-Nov-25 A
A1-PM-KPM-0019 | Moblization of Project Commissioning Manager* | 0 |  | 13-Nov-25 A
A1-PM-KPM-0022 | Moblization of Field Engineering Manager | 0 |  | 22-Aug-25 A
A1-PM-KPM-0021 | Moblization of Project IT Manager | 0 |  | 15-May-25 A
A1-PM-KPM-0018 | Moblization of Lead Cost Engineer / Estimator | 0 |  | 01-Apr-25 A
A1-PM-KPM-0017 | Moblization of Project HSE Manager(s) (Home Office/Construction) | 0 |  | 20-Dec-24 A
A1-PM-KPM-0016 | Moblization of Project Construction Field Superintendent | 0 |  | 15-Apr-25 A
A1-PM-KPM-0015 | Moblization of Project Construction Chief Field Engineer | 0 |  | 01-Mar-25 A
A1-PM-KPM-0014 | Moblization of Project Construction Director/Manager(s)* | 0 |  | 14-Apr-25 A
A1-PM-KPM-0013 | Moblization of Project Contracts/Subcontracts Manager* | 0 |  | 01-Jun-25 A
A1-PM-KPM-0012 | Moblization of Construction Planner | 0 |  | 27-Mar-25 A
A1-PM-KPM-0011 | Moblization of Lead Planner | 0 |  | 21-Jun-25 A
A1-PM-KPM-0010 | Moblization of Project Control Manager* | 0 |  | 15-Nov-24 A
A1-PM-KPM-0009 | Moblization of Project Traffic and Logistics Manager | 0 |  | 01-Dec-24 A
A1-PM-KPM-0008 | Moblization of Project Commercial/Prime Contracts Manager | 0 |  | 01-Jan-25 A
A1-PM-KPM-0007 | Moblization of Procurement Manager (s) * | 0 |  | 15-Nov-24 A
A1-PM-KPM-0006 | Moblization of Process Manager (s) * | 0 |  | 01-Feb-25 A
A1-PM-KPM-0005 | Moblization of Lead Discipline and Supervisory Engineers * - RAD | 0 |  | 01-Dec-24 A
A1-PM-KPM-0004 | Moblization of Quality Assurance and Quality Control Manager (Home Office/SITE) | 0 |  | 20-Feb-25 A
A1-PM-KPM-0003 | Moblization of Engineering Manager * | 0 |  | 15-Feb-25 A
A1-PM-KPM-0002 | Moblization of Project Turnaround Manager * | 0 |  | 21-Nov-24 A
A1-PM-KPM-0001 | Moblization of Project Director or Project Manager * | 0 |  | 18-Dec-24 A
Detailed Design and Engineering |  | 412 | 02-Apr-25 A | 2027-01-21 | 2026-03-27 | 2027-07-20 | 129
Engineering Workshops |  | 183 | 25-May-25 A | 2026-03-06 | 2026-03-27 | 2026-03-27 | 15
A1-PM-EWS-0003 | Engineering Workshops - 90% Model Review | 0 |  | 2026-03-06 |  |  | 15
A1-PM-EWS-0002 | Engineering Workshops - 60% Model Review | 0 |  | 19-Sep-25 A
A1-PM-EWS-0001 | Engineering Workshops - 30% Model Review | 0 |  | 25-May-25 A |  | 46108
Engineering Interim Milestones |  | 412 | 02-Apr-25 A | 2027-01-21 | 2026-03-27 | 2027-07-20 | 129
General Project Management |  | 403 | 30-Apr-25 A | 2027-01-21 | 2027-07-20 | 2027-07-20 | 129
A1-PM-EIM-0002 | 8.A*-As Built drawings handover to COMPANY | 0 |  | 2027-01-21 |  |  | 129
A1-PM-EIM-0001 | 1.A*-Issue Engineering Procedure. | 0 |  | 30-Apr-25 A |  | 46588
Detail Engineering |  | 247 | 02-Apr-25 A | 2026-06-04 | 2026-03-27 | 2027-07-20 | 294
A1-PM-EIM-0023 | 29.B-Issue 50% Piping Isometrics IFC | 0 |  | 2026-06-04 |  |  | 162
A1-PM-EIM-0031 | 38.B*-Issue IFC Instrument cable schedules, cable layouts, equipment layouts, JB details, trench details etc. complete | 0 |  | 2026-06-03 |  |  | 164
A1-PM-EIM-0017 | 23.B-Issue IFC 95% of Civil / Structural drawings for pipe supports, pipe trestles, sleepers etc. complete. | 0 |  | 2026-05-14 |  |  | 31
A1-PM-EIM-0034 | 42.B-Finalize and issue IFC all instrumentation loop diagrams. | 0 |  | 2026-05-06 |  |  | 172
A1-PM-EIM-0029 | 35.B*-Issue IFC Electrical cable schedules, cable layouts, equipment layouts earthing layouts, lighting layouts, JB deta | 0 |  | 2026-05-06 |  |  | 108
A1-PM-EIM-0024 | 30.B-Complete Piping Isometrics IFC | 0 |  | 2026-05-01 |  |  | 15
A1-PM-EIM-0014 | 20.B*-Receipt of key VENDOR data (by major equipment) | 0 |  | 2026-04-23 |  |  | 81
A1-PM-EIM-0035 | 44.B-Issue Operating, Maintenance and Safety Manual. | 0 |  | 2026-04-21 |  |  | 196
A1-PM-EIM-0033 | 41.B*-Issue IFC Electrical/Instrument layouts, interconnection diagrams etc. including all building control SYSTEMS, HVA | 0 |  | 2026-04-21 |  |  | 183
A1-PM-EIM-0028 | 34.B-Establish piping interface details and finalize procedures with COMPANY | 0 |  | 2026-04-21 |  |  | 128
A1-PM-EIM-0012 | 18.B-Issue IFC all Single Line Diagrams, Hazardous Area classification details for all facilities (complete). | 0 |  | 2026-04-14 |  |  | 189
A1-PM-EIM-0007 | 13.B*-Issue IFC PFDs, P&IDs, Data Sheets, Equipment Lists, Line Lists complete incorporating HAZOP comments | 0 |  | 2026-04-14 |  |  | 200
A1-PM-EIM-0027 | 33.B-Issue final MTO and MRs for piping bulk materials | 0 |  | 2026-04-08 |  |  | 47
A1-PM-EIM-0016 | 22.B*-Issue IFC all foundation & superstructure drawings for all Equipment & Packages | 0 |  | 2026-03-23 |  |  | 347
A1-PM-EIM-0021 | 27.B-Complete 90% 3D-CAD model review | 0 |  | 2026-03-06 |  | 2026-03-27 | 44
A1-PM-EIM-0026 | 32.B-Issue Intermediate MTO and MR’s for piping bulk materials | 0 |  | 2026-02-24 |  | 2026-03-27 | 23
A1-PM-EIM-0011 | 17.B-Steam Balance Frozen for U&O | 0 |  | 2026-02-24 |  | 2026-03-27 | 23
A1-PM-EIM-0010 | 16.B-Effluent Summary & Flare Loads Frozen for U&O | 0 |  | 2026-02-24 |  | 2026-03-27 | 23
A1-PM-EIM-0022 | 28.B*-Start issue piping isometrics IFC | 0 |  | 2026-02-20 |  | 2026-03-27 | 25
A1-PM-EIM-0003 | 9.B*-Issue Utility demands, associated line sizes and electrical load data and equipment ratings final. | 0 |  | 2026-02-20 |  | 2026-05-06 | 25
A1-PM-EIM-0030 | 36.B-Issue first MTO and MRs for electrical bulk materials | 0 |  | 21-Jun-25 A |  | 46588
A1-PM-EIM-0008 | 14.B*-Issue IFC Plot Plans, Equipment Layouts etc. complete | 0 |  | 06-May-25 A |  | 46185
A1-PM-EIM-0006 | 12.B-Process design frozen | 0 |  | 18-Aug-25 A |  | 46405
A1-PM-EIM-0005 | 11.B-Complete HAZOP/ SIL Review and submit Close Out Report with all actions closed. | 0 |  | 05-Sep-25 A |  | 46388
A1-PM-EIM-0015 | 21.B*-Issue IFC all underground services drawings | 0 |  | 15-Nov-25 A |  | 46311
A1-PM-EIM-0018 | 24.B-Issue IFC 95% of Civil / Structural drawings etc. for all Buildings. | 0 |  | 01-Sep-25 A |  | 46388
A1-PM-EIM-0009 | 15.B-Utility Consumption Issued for U&O | 0 |  | 20-Jun-25 A |  | 46407
A1-PM-EIM-0020 | 26.B*-Complete 60% 3D-CAD model review | 0 |  | 18-Sep-25 A |  | 46248
A1-PM-EIM-0013 | 19.B*-Issue MRs for all Major Equipment & Packages for purchase. | 0 |  | 16-Sep-25 A |  | 46164
A1-PM-EIM-0004 | 10.B-Issue for COMPANY approval all documents for HAZOP / SIL review | 0 |  | 21-Jun-25 A |  | 46300
A1-PM-EIM-0025 | 31.B*-Issue 1st MTO and MRs for piping bulk materials | 0 |  | 21-Jun-25 A |  | 46388
A1-PM-EIM-0032 | 39.B-Issue first MTO and MRs for instrument bulk materials | 0 |  | 21-Jun-25 A |  | 46199
A1-PM-EIM-0036 | 45.B-Design for Turnaround Works | 0 |  | 02-Apr-25 A |  | 46405
A1-PM-EIM-0019 | 25.B-Complete 30% 3D-CAD model review | 0 |  | 25-May-25 A |  | 46405
Procurement |  | 441 | 21-Feb-25 A | 2027-01-20 | 2026-05-04 | 2027-07-20 | 129
Procurement Deliverables |  | 154 | 03-Mar-25 A | 2026-02-24 | 2026-07-23 | 2026-07-27 | 109
A1-PM-PRD-0029 | PM-071-Purchasing Status Report | 5 | 21-Jun-25 A | 12-Jul-25 A | 46226 | 46226
A1-PM-PRD-0028 | PM-070-Material Status Report | 5 | 21-Jun-25 A | 12-Jul-25 A | 46226 | 46226
A1-PM-PRD-0027 | PM-069-Sub contractor performance feed back report | 5 | 21-Jun-25 A | 12-Jul-25 A | 46226 | 46226
A1-PM-PRD-0026 | PM-068-Subcontract status report | 5 | 21-Jun-25 A | 12-Jul-25 A | 46226 | 46226
A1-PM-PRD-0025 | PM-067-Delivery Certificate on Site | 5 | 21-Jun-25 A | 12-Jul-25 A | 46226 | 46226
A1-PM-PRD-0024 | PM-066-Copy of Bill of Loading | 5 | 21-Jun-25 A | 12-Jul-25 A | 46226 | 46226
A1-PM-PRD-0030 | PM-072-Vendor Performance feed back report | 5 | 25-Oct-25 A | 2026-02-24 | 2026-07-23 | 2026-07-23 | 109
A1-PM-PRD-0023 | PM-060-Award Recommendation | 5 | 21-Jun-25 A | 12-Jul-25 A | 46226 | 46226
A1-PM-PRD-0022 | PM-059-Subcontract control log | 5 | 21-Jun-25 A | 12-Jul-25 A | 46226 | 46226
A1-PM-PRD-0020 | PM-056-Vendor Manufacturing Quality Plan | 5 | 21-Jun-25 A | 23-Jul-25 A | 46226 | 46226
A1-PM-PRD-0019 | PM-055-Subcontract Pre Qualification | 5 | 19-Jun-25 A | 25-Aug-25 A | 46226 | 46226
A1-PM-PRD-0018 | PM-051-Copy of unpriced sub contract agreement | 5 | 19-Jun-25 A | 02-Sep-25 A | 46226 | 46226
A1-PM-PRD-0017 | PM-044-Vendor List | 5 | 12-Jun-25 A | 25-Aug-25 A | 46226 | 46226
A1-PM-PRD-0016 | PM-043-Vendors List / Bidders Lists | 5 | 21-Jun-25 A | 12-Jul-25 A | 46226 | 46226
A1-PM-PRD-0015 | PM-042-Subcontract Bidders List | 5 | 21-Jun-25 A | 12-Jul-25 A | 46226 | 46226
A1-PM-PRD-0021 | PM-058-Subcontract technical & commercial bid evaluation | 5 | 03-Mar-25 A | 28-May-25 A | 46226 | 46226
A1-PM-PRD-0014 | PM-036-Vendor Technical Queries /Answers | 5 | 21-Jun-25 A | 12-Jul-25 A | 46226 | 46226
A1-PM-PRD-0013 | PM-035-Vendor Prequalification's | 5 | 21-Jun-25 A | 12-Jul-25 A | 46226 | 46226
A1-PM-PRD-0012 | PM-034-Subcontract Award Recommendation | 5 | 21-Jun-25 A | 12-Jul-25 A | 46226 | 46226
A1-PM-PRD-0011 | PM-033-Commercial Bid Analysis | 5 | 21-Jun-25 A | 12-Jul-25 A | 46226 | 46226
A1-PM-PRD-0010 | PM-027-Shipping Progress Report | 5 | 21-Jun-25 A | 12-Jul-25 A | 46226 | 46226
A1-PM-PRD-0009 | PM-026-Vendor Schedules | 5 | 21-Jun-25 A | 12-Jul-25 A | 46226 | 46226
A1-PM-PRD-0008 | PM-025-Copy of priced and unpriced Purchase Order | 5 | 21-Jun-25 A | 12-Jul-25 A | 46226 | 46226
A1-PM-PRD-0007 | PM-024-Shipping Forecast | 5 | 21-Jun-25 A | 12-Jul-25 A | 46226 | 46226
A1-PM-PRD-0005 | PM-022-Procurement Control Log | 5 | 21-Jun-25 A | 12-Jul-25 A | 46226 | 46226
A1-PM-PRD-0006 | PM-023-Transportation Plan & Procedure | 5 | 24-May-25 A | 25-Aug-25 A | 46226 | 46226
A1-PM-PRD-0002 | PM-019-Subcontracting Procedure | 5 | 25-May-25 A | 02-Sep-25 A | 46226 | 46226
A1-PM-PRD-0001 | PM-018-Equipment Delivery and storage Plan | 5 | 25-May-25 A | 25-Aug-25 A | 46226 | 46226
A1-PM-PRD-0004 | PM-021-Procurement Plan | 5 | 25-May-25 A | 15-Jun-25 A | 46226 | 46226
A1-PM-PRD-0003 | PM-020-Procurement Procedures | 5 | 01-Jun-25 A | 25-Aug-25 A | 46226 | 46230
Procurement Interim Milestones |  | 441 | 21-Feb-25 A | 2027-01-20 | 2026-05-04 | 2027-07-20 | 129
General Project Management |  | 306 | 28-Mar-25 A | 2026-10-18 | 2027-01-03 | 2027-01-03 | 52
A1-PM-PRM-0002 | 7.A-VENDOR training and visits planned | 0 |  | 2026-10-18 |  |  | 67
A1-PM-PRM-0001 | 1.A*-Issue Procurement Procedures. | 0 |  | 28-Mar-25 A |  | 46390
Procurement Equipment & Materials |  | 221 | 21-Feb-25 A | 2026-05-13 | 2026-06-12 | 2027-01-20 | 309
A1-PM-PRM-0006 | 52.C*-Issue purchase orders for all major electrical Equipment | 0 |  | 2026-05-13 |  |  | 180
A1-PM-PRM-0010 | 57.C-Issue final purchase order for piping bulk materials | 0 |  | 2026-04-22 |  |  | 37
A1-PM-PRM-0011 | 58.C-Issue purchase orders for all field instrument tagged items | 0 |  | 2026-03-25 |  |  | 216
A1-PM-PRM-0009 | 56.C-Issue intermediate purchase order for piping bulk materials | 0 |  | 2026-03-19 |  |  | 61
A1-PM-PRM-0012 | 59.C*-Issue first purchase orders for bulk electrical materials | 0 |  | 21-Jun-25 A
A1-PM-PRM-0007 | 54.C*-Issue purchase order for all major instrument control SYSTEMS | 0 |  | 21-Nov-25 A
A1-PM-PRM-0005 | 51.C*-Issue purchase orders for all remaining Mechanical / Rotating Equipment & Equipment Packages | 0 |  | 01-Sep-25 A
A1-PM-PRM-0004 | 50.C*-Issue purchase orders for Furnaces | 0 |  | 21-Jun-25 A
A1-PM-PRM-0008 | 55.C*-Issue first purchase order for piping bulk materials | 0 |  | 19-Sep-25 A
A1-PM-PRM-0014 | 61.C*-Issue first purchase orders for bulk instrument materials | 0 |  | 21-Jun-25 A |  | 46185
A1-PM-PRM-0003 | 49.C*-Issue purchase order for Compressors Centrifugal / Reciprocating | 0 |  | 30-May-25 A |  | 46407
A1-PM-PRM-0015 | 62.C-Issue purchase order Piping MTO for Shut Down Works | 0 |  | 21-Feb-25 A |  | 46185
A1-PM-PRM-0013 | 60.C-Issue purchase orders for all Shut Down Materials (Piping, Electrical and Instrumentation | 0 |  | 28-Mar-25 A |  | 46407
Subcontracts |  | 257 | 30-May-25 A | 01-Sep-25 A
A1-PM-PRM-0023 | 70.C*-Instrument subcontract award | 0 |  | 15-Jun-25 A
A1-PM-PRM-0022 | 69.C*-Electrical subcontract award | 0 |  | 15-Jun-25 A
A1-PM-PRM-0021 | 68.C-Painting subcontract award | 0 |  | 15-Jun-25 A
A1-PM-PRM-0020 | 67.C-Insulation subcontract award | 0 |  | 15-Jun-25 A
A1-PM-PRM-0018 | 65.C-Steel fabrication/erection subcontract award | 0 |  | 01-Sep-25 A
A1-PM-PRM-0019 | 66.C*-Mechanical subcontract award | 0 |  | 15-Jun-25 A
A1-PM-PRM-0016 | 63.C-Piling subcontract award | 0 |  | 01-Jun-25 A
A1-PM-PRM-0024 | 71.C*-Buildings subcontract award | 0 |  | 30-May-25 A
A1-PM-PRM-0017 | 64.C*-Civil subcontract award | 0 |  | 15-Jun-25 A
Manufacturing & Delivery |  | 423 | 20-Mar-25 A | 2027-01-20 | 2026-05-04 | 2027-07-20 | 129
A1-PM-PRM-0026 | 77.D*-Furnaces delivered to SITE | 0 |  | 10-Sep-25 A
A1-PM-PRM-0040 | 93.D*-All VENDOR Documentation Handed over to COMPANY | 0 |  | 2027-01-20 |  |  | 155
A1-PM-PRM-0039 | 92.D*-Operating Spares for all item’s arrival at SITE and handover to COMPANY. | 0 |  | 2027-01-20 |  | 2026-05-06 | 155
A1-PM-PRM-0038 | 91.D-Insurance spares for all equipment & packages arrival at SITE and handover to COMPANY | 0 |  | 2027-01-20 |  | 2026-05-04 | 155
A1-PM-PRM-0031 | 82.D-Instrument Control SYSTEMS for CCB delivered to SITE | 0 |  | 2026-09-29 |  | 2026-07-15 | 72
A1-PM-PRM-0030 | 81.D*-Major instrument control SYSTEMS delivered to SITE | 0 |  | 2026-09-29 |  | 2026-10-07 | 72
A1-PM-PRM-0028 | 79.D*-All major electrical Equipment delivered to SITE | 0 |  | 2026-09-29 |  | 2026-12-28 | 96
A1-PM-PRM-0032 | 83.D-Field instrument tagged items delivered to SITE | 0 |  | 2026-09-27 |  | 2026-12-10 | 75
A1-PM-PRM-0037 | 90.D-Bulk instrument materials final MTO delivered to SITE | 0 |  | 2026-09-24 |  | 2027-07-20 | 13
A1-PM-PRM-0027 | 78.D*-Remaining Mechanical / Rotating Equipment & Equipment Packages delivered to SITE | 0 |  | 2026-09-13 |  | 2026-10-07 | 310
A1-PM-PRM-0036 | 88.D-Bulk electrical materials final MTO delivered to SITE | 0 |  | 2026-08-31 |  | 2026-12-10 | 102
A1-PM-PRM-0029 | 80.D*-HVAC, Fire Detection and Fire Fighting SYSTEMS for all buildings delivered to SITE | 0 |  | 2026-08-26 |  | 2027-01-03 | 106
A1-PM-PRM-0035 | 86.D*-Bulk piping materials final MTO delivered to SITE | 0 |  | 2026-08-22 |  | 2026-12-10 | 41
A1-PM-PRM-0034 | 85.D*-Bulk piping materials intermediate MTO delivered to SITE | 0 |  | 2026-04-18 |  | 2026-12-10 | 77
A1-PM-PRM-0025 | 76.D*-Compressors Centrifugal / Reciprocating delivered to SITE | 0 |  | 2026-03-03 |  | 2027-07-20 | 53
A1-PM-PRM-0033 | 84.D*-Bulk piping materials initial MTO delivered to SITE | 0 |  | 2026-02-20 |  | 2027-07-20 | 76
A1-PM-PRM-0041 | 94.D-Piping MTO for Shut Down Works Delivered to SITE | 0 |  | 20-Mar-25 A |  | 46588
Construction |  | 469 | 10-Mar-25 A | 2027-03-10 | 2026-07-30 | 2027-07-20 | 94
Construction Deliverables |  | 469 | 10-Mar-25 A | 2027-03-10 | 2026-08-14 | 2027-04-21 | 30
A1-PM-COD-0002 | CS-002-Construction Handover Dossier ( ALL Discipline wise) | 5 | 22-Jun-25 A | 2027-03-10 | 2026-08-14 | 2026-08-14 | 30
A1-PM-COD-0001 | CS-001-QC Dossier | 5 | 2027-01-21 | 2027-01-27 | 2026-08-22 | 2026-08-22 | 30
A1-PM-COD-0032 | CS-032-Camp and Accommodation Plan | 5 | 21-Jun-25 A | 12-Jul-25 A | 46248 | 46248
A1-PM-COD-0030 | CS-030-mobilisation/demobilisation plan | 5 | 01-Jul-25 A | 19-Dec-25 A | 46248 | 46248
A1-PM-COD-0029 | CS-029-Logistics plan | 5 | 21-Jun-25 A | 30-Jun-25 A | 46248 | 46248
A1-PM-COD-0027 | CS-027-Temporary facilities plan | 5 | 21-Jun-25 A | 30-Jun-25 A | 46248 | 46248
A1-PM-COD-0026 | CS-026-Civil Specifications | 5 | 21-Jun-25 A | 31-Jul-25 A | 46248 | 46248
A1-PM-COD-0025 | CS-025-Electrical Specifications | 5 | 21-Jun-25 A | 20-Aug-25 A | 46248 | 46248
A1-PM-COD-0021 | CS-021-Quality Control Procedure | 5 | 01-Oct-25 A | 19-Dec-25 A | 46248 | 46248
A1-PM-COD-0033 | CS-033-Construction logistic plan | 5 | 01-Aug-25 A | 2026-02-23 | 2026-08-14 | 2026-08-14 | 126
A1-PM-COD-0024 | CS-024-Non-Conformance Requests | 5 | 01-Sep-25 A | 19-Dec-25 A | 46248 | 46248
A1-PM-COD-0019 | CS-019-HSE | 5 | 01-Oct-25 A | 18-Dec-25 A | 46248 | 46248
A1-PM-COD-0023 | CS-023-Concession Requests | 5 | 01-Sep-25 A | 19-Dec-25 A | 46248 | 46248
A1-PM-COD-0022 | CS-022-Construction Strategies | 5 | 21-Jun-25 A | 19-Dec-25 A | 46248 | 46248
A1-PM-COD-0020 | CS-020-Test Certificate | 5 | 10-Mar-25 A | 26-Mar-25 A | 46248 | 46248
A1-PM-COD-0031 | CS-031-Construction Cleanliness Plant | 5 | 01-Aug-25 A | 2026-02-24 | 2026-08-14 | 2026-08-14 | 126
A1-PM-COD-0017 | CS-017-Check List | 5 | 15-Oct-25 A | 19-Dec-25 A | 46248 | 46248
A1-PM-COD-0016 | CS-016-Punch List | 5 | 21-Jun-25 A | 2026-02-20 | 2026-08-14 | 2026-08-14 | 126
A1-PM-COD-0015 | CS-015-Insulation / Painting / Fire Proofing | 5 | 01-Apr-25 A | 2026-02-26 | 2026-08-14 | 2026-08-14 | 126
A1-PM-COD-0014 | CS-014-Technical Bid Analysis | 5 | 21-Jun-25 A | 12-Jul-25 A | 46248 | 46248
A1-PM-COD-0013 | CS-013-Locking List | 5 | 02-Jun-25 A | 20-Jun-25 A | 46248 | 46248
A1-PM-COD-0012 | CS-012-label | 5 | 21-Jun-25 A | 12-Jul-25 A | 46248 | 46248
A1-PM-COD-0011 | CS-011-Temporary Works | 5 | 21-Jun-25 A | 12-Jul-25 A | 46248 | 46248
A1-PM-COD-0010 | CS-010-Demolition plan | 5 | 21-Jun-25 A | 12-Jul-25 A | 46248 | 46248
A1-PM-COD-0009 | CS-009-Site plans | 5 | 21-Jun-25 A | 12-Jul-25 A | 46248 | 46248
A1-PM-COD-0018 | CS-018-Quality Assurance Docs | 5 | 02-Jun-25 A | 19-Jun-25 A | 46248 | 46248
A1-PM-COD-0008 | CS-008-Lifting | 5 | 21-Jun-25 A | 12-Jul-25 A | 46426 | 46426
A1-PM-COD-0007 | CS-007-Time Schedule / Programme | 5 | 19-Mar-25 A | 19-Jun-25 A | 46248 | 46251
A1-PM-COD-0006 | CS-006-Method Statements | 5 | 21-Jun-25 A | 12-Jul-25 A | 46248 | 46251
A1-PM-COD-0004 | CS-004-Procedures | 5 | 21-Jun-25 A | 12-Jul-25 A | 46248 | 46251
A1-PM-COD-0003 | CS-003-Execution Plan | 5 | 25-May-25 A | 15-Nov-25 A | 46248 | 46253
A1-PM-COD-0005 | CS-005-Field instructions | 5 | 01-Sep-25 A | 2026-02-20 | 2026-08-14 | 2026-08-21 | 126
A1-PM-COD-0034 | CS-034-Field Construction Execution plan | 21 | 08-Apr-25 A | 19-Dec-25 A | 46450 | 46456
A1-PM-COD-0028 | CS-028-Construction execution methodologies (work methods) | 15 | 01-Apr-25 A | 07-Apr-25 A | 46496 | 46498
Construction Interim Milestones |  | 436 | 25-Mar-25 A | 2027-02-21 | 2026-07-30 | 2027-07-20 | 107
General Project Management |  | 212 | 31-May-25 A | 2026-04-14 | 2026-12-09 | 2027-02-08 | 215
A1-PM-CIM-0010 | 4.A-Issue Handover Procedures and plan (Final). | 0 |  | 2026-04-14 |  |  | 172
A1-PM-CIM-0009 | 4.A-Issue COMMISSIONING Procedures and plan (Final). | 0 |  | 2026-04-14 |  |  | 215
A1-PM-CIM-0008 | 4.A-Issue PRECOMMISSIONING Procedures and plan (Final). | 0 |  | 2026-04-14 |  |  | 215
A1-PM-CIM-0007 | 4.A-Issue Purging Procedures and plan (Final). | 0 |  | 2026-04-14 |  |  | 215
A1-PM-CIM-0006 | 4.A-Issue Drying Procedures and plan (Final). | 0 |  | 2026-04-14 |  | 2027-02-08 | 215
A1-PM-CIM-0005 | 4.A-Issue Hydrotesting Procedures and plan (Final). | 0 |  | 2026-04-14 |  | 2027-02-08 | 215
A1-PM-CIM-0002 | 3.A-Issue Construction Execution Procedures (Excluding Hydrotesting, Drying, Purging, PRE-COMMISSIONING and COMMISSIONIN | 0 |  | 21-Jun-25 A |  | 46426
A1-PM-CIM-0001 | 3.A-Issue Construction Execution Plan (Excluding Hydrotesting, Drying, Purging, PRE-COMMISSIONING and COMMISSIONING Proc | 0 |  | 21-Jun-25 A |  | 46426
A1-PM-CIM-0004 | 3.A-Tie-in/Shutdown philosophy etc. (Excluding Hydrotesting, Drying, Purging, PRE-COMMISSIONING and COMMISSIONING Proced | 0 |  | 31-May-25 A |  | 46426
A1-PM-CIM-0003 | 3.A-Issue Construction Execution Method Statements (Excluding Hydrotesting, Drying, Purging, PRE-COMMISSIONING and COMMI | 0 |  | 21-Jun-25 A |  | 46365
Construction & Commissioning |  | 392 | 25-Mar-25 A | 2026-12-21 | 2026-07-30 | 2027-01-20 | 22
A1-PM-CIM-0040 | 129.E-Complete electrical cabling and termination works (field works) for all plant facilities including continuity chec | 0 |  | 2026-12-21 |  |  | 26
A1-PM-CIM-0035 | 124.E-Complete Fire Water System including tanks, pumps and piping works up to Mechanical Completion. | 0 |  | 2026-12-03 |  |  | 41
A1-PM-CIM-0033 | 122.E-Piping Hydrotesting 100% complete | 0 |  | 2026-12-03 |  |  | 41
A1-PM-CIM-0032 | 121.E-Piping Hydrotesting 50% complete | 0 |  | 2026-11-16 |  |  | 56
A1-PM-CIM-0031 | 120.E-Commence hydrotesting of Pipework | 0 |  | 2026-11-16 |  |  | 56
A1-PM-CIM-0022 | 111.E-Complete installation of all remaining mechanical, rotating & packaged equipment | 0 |  | 2026-11-02 |  |  | 68
A1-PM-CIM-0030 | 119.E-Piping Erection 100% complete | 0 |  | 2026-10-22 |  | 2027-01-20 | 77
A1-PM-CIM-0029 | 118.E-Piping erection 50% Complete | 0 |  | 2026-10-22 |  | 2026-12-09 | 77
A1-PM-CIM-0027 | 116.E-Complete installation of pipe supports, sleepers, trestles etc. | 0 |  | 2026-10-22 |  | 2027-01-20 | 77
A1-PM-CIM-0038 | 127.E-Complete installation of all Substation electrical equipment | 0 |  | 2026-10-18 |  | 2026-08-15 | 82
A1-PM-CIM-0036 | 125.E-Complete Heat Tracing, Insulation, Fire Proofing and Painting works | 0 |  | 2026-10-05 |  | 2027-01-20 | 92
A1-PM-CIM-0026 | 115.E-Complete prefabrication 98% piping | 0 |  | 2026-10-05 |  | 2026-07-30 | 92
A1-PM-CIM-0041 | 130.E-Complete Street lighting | 0 |  | 2026-10-03 |  | 2026-12-09 | 94
A1-PM-CIM-0025 | 114.E-Complete prefabrication 50% piping. | 0 |  | 2026-09-17 |  | 2026-08-22 | 107
A1-PM-CIM-0037 | 126.E-Complete installation of platforms, walkways, crossovers etc. | 0 |  | 2026-09-10 |  | 2027-01-20 | 113
A1-PM-CIM-0020 | 106.E-Complete installation of steel structural works for shelters, and Package Units etc. | 0 |  | 2026-09-10 |  | 2027-01-20 | 113
A1-PM-CIM-0024 | 113.E-Start Piping Prefabrication | 0 |  | 25-Mar-25 A |  | 46407
A1-PM-CIM-0016 | 102.E-Complete all underground piping | 0 |  | 2026-07-19 |  | 2027-01-20 | 159
A1-PM-CIM-0014 | 100.E-Complete construction of foundations for all remaining mechanical, rotating & packaged equipment | 0 |  | 2026-06-25 |  | 2027-01-20 | 48
A1-PM-CIM-0018 | 104.E-Complete installation of all underground instrument cabling | 0 |  | 2026-06-20 |  | 2027-01-20 | 149
A1-PM-CIM-0028 | 117.E-Start Piping erection | 0 |  | 15-Apr-25 A |  | 46407
A1-PM-CIM-0023 | 112.E-Completion of Heavy Lifts | 0 |  | 2026-05-18 |  | 2027-01-20 | 63
A1-PM-CIM-0021 | 110.E-Complete installation of Turbines/Compressors | 0 |  | 2026-05-18 |  | 2027-01-20 | 212
A1-PM-CIM-0039 | 128.E-Trench for Main Electrical Feeder cables Main to Unit Substations available | 0 |  | 2026-05-07 |  | 2027-01-20 | 85
A1-PM-CIM-0019 | 105.E-Trench for data highway cables SIS to Control Building available | 0 |  | 2026-05-07 |  | 2027-01-20 | 221
A1-PM-CIM-0017 | 103.E-Complete installation of all underground electrical cabling | 0 |  | 2026-05-07 |  | 2027-01-20 | 185
A1-PM-CIM-0015 | 101.E-Complete all Piperack foundations | 0 |  | 2026-04-09 |  | 2027-01-20 | 245
A1-PM-CIM-0012 | 95.E-Complete Construction of Temporary Facilities at SITE. | 0 |  | 15-Nov-25 A |  | 46407
A1-PM-CIM-0034 | 123.E-Complete all piping tie-ins (Including Interface Tie-Ins) | 0 |  | 20-May-25 A |  | 46407
A1-PM-CIM-0013 | 96.E-Complete SITE preparation and grading works | 0 |  | 21-Jun-25 A |  | 46407
A1-PM-CIM-0011 | 94.E*-Commence on SITE | 0 |  | 31-May-25 A |  | 46407
Eelectrical |  | 22 | 2027-01-20 | 2027-02-21 | 2027-04-21 | 2027-07-20 | 107
A1-PM-CIM-0043 | 134.E-Complete motor run | 0 |  | 2027-02-21 |  | 2027-07-20 | 51
A1-PM-CIM-0042 | 131.E-Power from TRANSCO (Needs) | 0 |  | 2027-01-20 |  | 2027-04-21 | 181
Instrumentation |  | 37 | 2026-11-08 | 2026-12-21 | 2027-04-21 | 2027-04-21 | 104
A1-PM-CIM-0045 | 136.E-Complete instrumentation system loop checks and other PRE-COMMISSIONING checks | 0 |  | 2026-12-21 |  | 2027-04-21 | 104
A1-PM-CIM-0044 | 135.E-Control System Cables including Fiber opticinstalled and tested | 0 |  | 2026-11-08 |  | 2027-04-21 | 141
Mechanical Completion & Ready for START UP |  | 0 | 2027-01-20 | 2027-01-20 | 2027-07-20 | 2027-07-20 | 181
A1-PM-CIM-0046 | 138.F-Mechanical Completion | 0 |  | 2027-01-20 |  | 2027-07-20 | 181
Construction Workshops |  | 25 | 27-Aug-25 A | 29-Aug-25 A | 46378 | 46378
A1-PM-CWS-0002 | SIMOPS Workshop | 5 | 28-Aug-25 A | 29-Aug-25 A | 46378 | 46378
A1-PM-CWS-0001 | Constructabilty Workshop | 5 | 27-Aug-25 A | 27-Aug-25 A | 46378 | 46378
Commissioning |  | 417 | 01-Aug-25 A | 2027-07-20 | 2026-08-12 | 2027-07-20 | 0
Commissioning Deliverables |  | 166 | 01-Aug-25 A | 2026-07-10 | 2026-08-12 | 2026-12-30 | 124
A1-PM-CMD-0007 | CM-007-Pre-Commisioning & Commissioning Method of Statements | 15 | 2026-06-19 | 2026-07-10 | 2026-08-12 | 2026-08-26 | 124
A1-PM-CMD-0006 | CM-006-Pre- Commissioning Procedure | 15 | 2026-05-29 | 2026-06-19 | 2026-08-27 | 2026-09-16 | 124
A1-PM-CMD-0005 | CM-005-Pre-Commisioning & Commissioning systems identification drawings (P&IDs, single line diagram, etc) | 15 | 2026-05-08 | 2026-05-29 | 2026-09-17 | 2026-10-07 | 124
A1-PM-CMD-0004 | CM-004-Pre-Commisioning & Commissioning Schedule | 15 | 2026-04-17 | 2026-05-08 | 2026-10-08 | 2026-10-28 | 124
A1-PM-CMD-0003 | CM-003-Commissioning Procedures | 15 | 2026-03-27 | 2026-04-17 | 2026-10-29 | 2026-11-18 | 124
A1-PM-CMD-0002 | CM-002-Performance Test Run Report | 15 | 2026-03-06 | 2026-03-27 | 2026-11-19 | 2026-12-09 | 124
A1-PM-CMD-0001 | CM-001-Performance Test Run Procedure | 15 | 01-Aug-25 A | 2026-03-06 | 2026-12-10 | 2026-12-30 | 124
Commissioning Interim Milestones |  | 219 | 2026-09-14 | 2027-07-20 | 2027-04-21 | 2027-07-20 | 0
General Project Management |  | 0 | 2027-01-20 | 2027-01-21 | 2027-04-21 | 2027-04-21 | 65
A1-PM-CMM-0006 | 5.A-Issue SYSTEMS definition IFC & SYSTEMS completion Schedule | 0 |  | 2027-01-21 |  | 2027-04-21 | 65
A1-PM-CMM-0001 | 6.A-Training program for COMPANY staff issued to COMPANY for APPROVAL | 0 |  | 2027-01-20 |  | 2027-04-21 | 91
Mechanical Completion & Ready for START UP |  | 219 | 2026-09-14 | 2027-07-20 | 2027-07-20 | 2027-07-20 | 0
A1-PM-CMM-0005 | 144.F-PROVISIONAL ACCEPTANCE CERTIFICATE | 0 |  | 2027-07-20 |  |  | 0
A1-PM-CMM-0002 | 145.F-Ready for Start-Up | 0 |  | 2027-04-22 | 2026-09-14 | 1900-08-09 | 64
A1-PM-CMM-0003 | 142.F-Commercial Production | 0 |  | 2027-04-14 |  | 2027-07-20 | 83
A1-PM-CMM-0004 | 143.F-Issue "AS BUILT STATUS” |  |  |  |  | 46588
operating/Maintenance & Safety Manual | 0 |  | 2026-09-14 | 222 |  | 46588
HSE Management |  | 401 | 17-Feb-25 A | 2026-09-25 | 2026-03-02 | 2027-01-20 | 81
HSE Deliverables |  | 306 | 17-Feb-25 A | 2026-04-21 | 2026-04-02 | 2026-12-09 | 167
A1-PM-HSD-0040 | S-040-HSEIA Screening/ HSEIA Report/ HSEIA Dossier | 5 | 2026-04-14 | 2026-04-21 | 2026-04-02 | 2026-04-02 | 100
A1-PM-HSD-0029 | S-029-COSHH Assessments | 5 | 01-Aug-25 A | 25-Sep-25 A | 46255 | 46255
A1-PM-HSD-0041 | S-041-HSE deliverables as per HSE-RM-ST02 EPC deliverable requirements; not limited to : Building Fire and Safety revie | 5 | 01-Aug-25 A | 2026-04-21 | 2026-09-04 | 2026-09-04 | 100
A1-PM-HSD-0038 | S-038-List of Applicable Regulatory Requirements | 5 | 2026-03-03 | 2026-03-09 | 2026-12-09 | 2026-12-09 | 130
A1-PM-HSD-0039 | S-039-Waste Management Plan | 5 | 25-May-25 A | 06-Jan-26 A | 46269 | 46269
A1-PM-HSD-0037 | S-037-PHSER and Close Out Report | 5 | 2026-02-24 | 2026-03-02 | 2026-09-04 | 2026-09-04 | 130
A1-PM-HSD-0034 | S-034-Specifications | 5 | 21-Jun-25 A | 12-Jul-25 A | 46269 | 46269
A1-PM-HSD-0028 | S-028-QRA Reports | 5 | 05-Aug-25 A | 2026-02-23 | 2026-09-04 | 2026-09-04 | 140
A1-PM-HSD-0027 | S-027-HSE Report / Close out Report/Atmospheric Relief System Report/ HSE- Safety Reviews | 5 | 05-Aug-25 A | 2026-02-24 | 2026-08-21 | 2026-08-21 | 140
A1-PM-HSD-0026 | S-026-Environmental / Effluent Disposal System/ Gas Dispersion /Environmental Pollution Reports / Fugitive Emissions Rep | 5 | 04-Aug-25 A | 2026-02-23 | 2026-08-21 | 2026-08-21 | 140
A1-PM-HSD-0030 | S-030-Risk Assessment | 5 | 21-Jun-25 A | 12-Jul-25 A
A1-PM-HSD-0025 | S-025-Installation, Operation and Maintenance | 5 | 01-Aug-25 A | 2026-02-24 | 2026-09-04 | 2026-09-04 | 140
A1-PM-HSD-0020 | S-020-Hydraulic Calculations Report | 5 | 04-Aug-25 A | 2026-02-23 | 2026-12-09 | 2026-12-09 | 140
A1-PM-HSD-0019 | S-019-Fire and Safety Calculations / Explosion Over Pressure Calculations / Hydraulic Calculation | 5 | 01-Aug-25 A | 2026-02-23 | 2026-08-21 | 2026-08-21 | 140
A1-PM-HSD-0013 | S-013-Fire Alarm Drawings (Building) | 5 | 01-Aug-25 A | 2026-02-20 | 2026-08-21 | 2026-08-21 | 140
A1-PM-HSD-0036 | S-036-Safety Equipment and safety Routes Layout | 5 | 04-Aug-25 A | 2026-02-23 | 2026-09-04 | 2026-09-04 | 130
A1-PM-HSD-0031 | S-031-Process Philosophies & HSE Plan | 30 | 14-Jul-25 A | 13-Aug-25 A | 46269 | 46269
A1-PM-HSD-0012 | S-012-Fire Alarm Drawings (Plant) | 5 | 01-Aug-25 A | 2026-02-20 | 2026-09-04 | 2026-09-04 | 140
A1-PM-HSD-0035 | S-035-Ergonomic Study/ Human Factor Engineering / Assessment | 5 | 02-Aug-25 A | 2026-02-24 | 2026-04-02 | 2026-04-02 | 130
A1-PM-HSD-0024 | S-024-Manufacturing Data Report | 5 | 04-Aug-25 A | 2026-02-24 | 2026-08-21 | 2026-08-21 | 140
A1-PM-HSD-0017 | S-017-Hazard and Effect Register / HSECES Register/ HSE Critical Activities | 5 | 01-Aug-25 A | 2026-02-20 | 2026-09-04 | 2026-09-04 | 140
A1-PM-HSD-0011 | S-011-Fire Exposure Envelop Drawings / Heat Flux Boundary Drawings | 5 | 01-Aug-25 A | 2026-02-20 | 2026-09-04 | 2026-09-04 | 140
A1-PM-HSD-0023 | S-023-Quality Assurance Docs | 5 | 05-Aug-25 A | 2026-02-20 | 2026-09-04 | 2026-09-04 | 140
A1-PM-HSD-0008 | S-008-Fire Proofing Zone layout (Plant / Area Wise) | 5 | 01-Aug-25 A | 2026-02-20 | 2026-09-04 | 2026-09-04 | 140
A1-PM-HSD-0004 | S-004-Fire Fighting Diagram / Fire Protection Diagram | 5 | 01-Aug-25 A | 2026-02-20 | 2026-09-04 | 2026-09-04 | 140
A1-PM-HSD-0002 | S-002-Requisition / Supply Specifications/ Technical Specifications | 5 | 01-Aug-25 A | 2026-02-20 | 2026-09-04 | 2026-09-04 | 130
A1-PM-HSD-0021 | S-021-HAZOP / SIL (LOPA) Reports | 0 |  | 18-Jul-25 A | 46269 | 46269
A1-PM-HSD-0015 | S-015-Safety Schedule / Sheets | 5 | 09-Jun-25 A | 20-Jun-25 A | 46269 | 46269
A1-PM-HSD-0007 | S-007-Project Construction HSE Plan / House Keeping Plan | 30 | 10-Jun-25 A | 11-Jul-25 A | 46269 | 46272
A1-PM-HSD-0014 | S-014-Bill of material | 5 | 02-Jun-25 A | 09-Jun-25 A | 46269 | 46272
A1-PM-HSD-0018 | S-018-Equipment List | 5 | 21-Jun-25 A | 21-Jul-25 A | 46269 | 46272
A1-PM-HSD-0016 | S-016-Technical Bid Analysis | 5 | 21-Jun-25 A | 12-Jul-25 A | 46269 | 46272
A1-PM-HSD-0033 | S-033-Data sheets (ALL Type of Safety Data sheets) | 5 | 20-Aug-25 A | 26-Aug-25 A | 46255 | 46258
A1-PM-HSD-0032 | S-032-Philosophies | 5 | 14-Aug-25 A | 19-Aug-25 A | 46269 | 46273
A1-PM-HSD-0022 | S-022-Hazard Study / Fire Protection Design Study / Noise Vibration Study/ SIMOPS Study | 5 | 11-Aug-25 A | 29-Aug-25 A | 46269 | 46273
A1-PM-HSD-0010 | S-010-Hazardous area Layouts | 5 | 22-Jul-25 A | 2026-02-20 | 2026-09-04 | 2026-09-08 | 140
A1-PM-HSD-0009 | S-009-HSE Layouts | 5 | 21-Jun-25 A | 12-Jul-25 A | 46255 | 46259
A1-PM-HSD-0006 | S-006-Overall Fire Water & Ringman Header Layout | 5 | 21-Jun-25 A | 12-Jul-25 A | 46259 | 46265
A1-PM-HSD-0005 | S-005-Site Plans / Plot Plans / Key Plans | 5 | 21-Jun-25 A | 12-Jul-25 A | 46266 | 46272
A1-PM-HSD-0003 | S-003-HSE Requirements | 5 | 03-Mar-25 A | 06-Sep-25 A | 46266 | 46272
A1-PM-HSD-0001 | S-001-Procedures & Management of Change | 5 | 17-Feb-25 A | 03-Mar-25 A | 46269 | 46272
HSE Studies |  | 305 | 01-May-25 A | 2026-09-25 | 2026-03-02 | 2027-01-20 | 81
HAZID/ENVID/OHID |  | 181 | 01-May-25 A | 2026-03-16 | 2026-03-02 | 2026-08-31 | 120
A58820 | HAZID / ENVID / OHID /_IFD/IFC | 17 | 2026-02-20 | 2026-03-16 | 2026-03-02 | 2026-03-02 | 120
A58810 | HAZID / ENVID / OHID /_RCA | 17 | 15-Dec-25 A | 22-Dec-25 A | 46241 | 46241
A58800 | HAZID / ENVID / OHID /_IFA | 17 | 02-Sep-25 A | 08-Sep-25 A | 46241 | 46241
A58790 | HAZID / ENVID / OHID /_RCC | 17 | 26-May-25 A | 01-Sep-25 A | 46241 | 46241
A60330 | HAZID / ENVID / OHID /_IFR | 11 | 11-May-25 A | 20-May-25 A | 46241 | 46241
A58780 | HAZID / ENVID / OHID Workshop | 11 | 01-May-25 A | 10-May-25 A | 46241 | 46265
Inherent Safer Design Review |  | 164 | 23-Jul-25 A | 2026-04-08 | 2026-12-04 | 2027-01-20 | 205
A59470 | Inherent Safer Design Review_IFD/IFC | 17 | 2026-03-16 | 2026-04-08 | 2026-12-04 | 2026-12-04 | 205
A59460 | Inherent Safer Design Review_RCA | 17 | 2026-02-20 | 2026-03-16 | 2026-12-04 | 2026-12-04 | 205
A59450 | Inherent Safer Design Review_IFA | 17 | 05-Sep-25 A | 11-Sep-25 A | 46360 | 46360
A59430 | Inherent Safer Design Review Preparation | 11 | 23-Jul-25 A | 31-Jul-25 A | 46360 | 46360
A59440 | Inherent Safer Design Review_RCC | 17 | 28-Aug-25 A | 04-Sep-25 A | 46360 | 46385
A60460 | Inherent Safer Design Review_IFR | 11 | 01-Aug-25 A | 28-Aug-25 A | 46385 | 46407
Bow-tie Development & HSE Critical Equipment & Systems and Performance Standards |  | 164 | 25-Jul-25 A | 2026-04-08 | 2026-03-02 | 2026-08-31 | 103
A59320 | Bow-tie Development & HSE Critical Equipment & Systems and Performance Standards_IFD/IFC | 17 | 2026-03-16 | 2026-04-08 | 2026-03-02 | 2026-03-02 | 103
A59310 | Bow-tie Development & HSE Critical Equipment & Systems and Performance Standards_RCA | 17 | 2026-02-20 | 2026-03-16 | 2026-07-15 | 2026-07-15 | 103
A59300 | Bow-tie Development & HSE Critical Equipment & Systems and Performance Standards_IFA | 17 | 05-Sep-25 A | 11-Sep-25 A | 46218 | 46218
A59290 | Bow-tie Development & HSE Critical Equipment & Systems and Performance Standards_RCC | 17 | 26-Aug-25 A | 04-Sep-25 A | 46218 | 46218
A60430 | Bow-tie Development & HSE Critical Equipment & Systems and Performance Standards_IFR | 11 | 01-Aug-25 A | 25-Aug-25 A | 46218 | 46241
A59280 | Bow-tie Development & HSE Critical Equipment & Systems and Performance Standards_Workshop | 11 | 25-Jul-25 A | 31-Jul-25 A | 46241 | 46265
HSECES and Performance Standards |  | 178 | 23-Jul-25 A | 2026-05-26 | 2026-10-19 | 2027-01-20 | 172
A62020 | HSE Critical Equipment & Systems and Performance Standards_IFD/IFC | 17 | 2026-05-01 | 2026-05-26 | 2026-10-19 | 2026-10-19 | 172
A62010 | HSE Critical Equipment & Systems and Performance Standards_RCA | 17 | 2026-04-08 | 2026-05-01 | 2026-10-19 | 2026-10-19 | 172
A62000 | HSE Critical Equipment & Systems and Performance Standards_IFA | 17 | 2026-03-16 | 2026-04-08 | 2026-10-19 | 2026-11-11 | 172
A61990 | HSE Critical Equipment & Systems and Performance Standards_RCC | 17 | 2026-02-20 | 2026-03-16 | 2026-11-11 | 2026-12-04 | 172
A61980 | HSE Critical Equipment & Systems and Performance Standards_IFR | 11 | 01-Aug-25 A | 28-Aug-25 A | 46360 | 46385
A61970 | HSE Critical Equipment & Systems and Performance Standards_Preparation | 7 | 23-Jul-25 A | 31-Jul-25 A | 46385 | 46407
HAZOP |  | 102 | 01-Jul-25 A | 22-Sep-25 A | 46106 | 46114
A62080 | HAZOP_IFD/IFC | 17 | 16-Sep-25 A | 22-Sep-25 A | 46106 | 46106
A62070 | HAZOP_RCA | 17 | 09-Sep-25 A | 15-Sep-25 A | 46114 | 46114
A62060 | HAZOP_IFA | 17 | 02-Sep-25 A | 08-Sep-25 A | 46114 | 46114
A62050 | HAZOP_RCC | 17 | 26-Aug-25 A | 01-Sep-25 A | 46114 | 46114
A62040 | HAZOP_IFR | 11 | 12-Jul-25 A | 25-Aug-25 A | 46114 | 46114
A62030 | HAZOP_Workshop | 11 | 01-Jul-25 A | 11-Jul-25 A | 46114 | 46114
SIL |  | 30 | 15-Aug-25 A | 25-Sep-25 A | 46106 | 46114
A23220 | Issue for Construction | 5 | 12-Sep-25 A | 25-Sep-25 A | 46106 | 46106
A23210 | Issue for Company Approval | 11 | 05-Sep-25 A | 11-Sep-25 A | 46114 | 46114
A23200 | SIL Review Workshop | 14 | 15-Aug-25 A | 17-Aug-25 A | 46114 | 46114
A60510 | Issue for Company Review | 14 | 18-Aug-25 A | 28-Aug-25 A | 46114 | 46114
Fire and Explosion Risk Assessment (FERA) |  | 167 | 01-Aug-25 A | 2026-04-14 | 2026-07-09 | 2026-08-31 | 100
A59520 | Fire and Explosion Risk Assessment (FERA)_IFD/IFC | 2 | 2026-04-09 | 2026-04-14 | 2026-07-09 | 2026-07-09 | 100
A59510 | Fire and Explosion Risk Assessment (FERA)_RCA | 16 | 2026-03-19 | 2026-04-09 | 2026-07-09 | 2026-07-09 | 100
A59500 | Fire and Explosion Risk Assessment (FERA)_IFA | 3 | 2026-03-13 | 2026-03-19 | 2026-07-09 | 2026-07-31 | 100
A59490 | Fire and Explosion Risk Assessment (FERA)_RCC | 16 | 2026-02-20 | 2026-03-13 | 2026-07-31 | 2026-08-05 | 100
A59480 | Fire and Explosion Risk Assessment (FERA)_Preparation | 6 | 01-Aug-25 A | 20-Aug-25 A | 46240 | 46261
A60470 | Fire and Explosion Risk Assessment (FERA)_IFR | 28 | 22-Aug-25 A | 31-Oct-25 A | 46261 | 46265
QRA |  | 109 | 07-Jul-25 A | 2026-04-14 | 2026-03-17 | 2026-08-31 | 100
A60640 | QRA Report_IFD/IFC | 2 | 2026-04-09 | 2026-04-14 | 2026-03-17 | 2026-03-17 | 100
A60630 | QRA Report_RCA | 16 | 2026-03-19 | 2026-04-09 | 2026-07-09 | 2026-07-09 | 100
A60620 | QRA Report_IFA | 3 | 2026-03-13 | 2026-03-19 | 2026-07-09 | 2026-07-31 | 100
A60610 | QRA Report_RCC | 16 | 2026-02-20 | 2026-03-13 | 2026-07-31 | 2026-08-05 | 100
A60600 | QRA Report_IFR | 28 | 16-Jul-25 A | 28-Aug-25 A | 46240 | 46261
A60590 | Workshop - QRA | 15 | 07-Jul-25 A | 15-Jul-25 A | 46261 | 46265
BRA |  | 113 | 07-Jul-25 A | 2026-04-14 | 2026-11-30 | 2027-01-20 | 202
A60580 | BRA Report_IFD/IFC | 2 | 2026-04-09 | 2026-04-14 | 2026-11-30 | 2026-11-30 | 202
A60570 | BRA Report_RCA | 16 | 2026-03-19 | 2026-04-09 | 2026-11-30 | 2026-11-30 | 202
A60560 | BRA Report_IFA | 3 | 2026-03-13 | 2026-03-19 | 2026-11-30 | 2026-12-22 | 202
A60550 | BRA Report_RCC | 16 | 2026-02-20 | 2026-03-13 | 2026-12-22 | 2026-12-25 | 202
A60540 | BRA Report_IFR | 28 | 16-Jul-25 A | 28-Aug-25 A | 46384 | 46405
A23290 | Workshop - BRA | 15 | 07-Jul-25 A | 15-Jul-25 A | 46405 | 46407
Escape Evacuation and Rescue Assessment (EERA) |  | 113 | 01-Aug-25 A | 2026-04-14 | 2026-07-09 | 2026-08-31 | 100
A59570 | Escape Evacuation and Rescue Assessment (EERA)_IFD/IFC | 2 | 2026-04-09 | 2026-04-14 | 2026-07-09 | 2026-07-09 | 100
A59560 | Escape Evacuation and Rescue Assessment (EERA)_RCA | 16 | 2026-03-19 | 2026-04-09 | 2026-07-09 | 2026-07-09 | 100
A59550 | Escape Evacuation and Rescue Assessment (EERA)_IFA | 3 | 2026-03-13 | 2026-03-19 | 2026-07-09 | 2026-07-31 | 100
A59540 | Escape Evacuation and Rescue Assessment (EERA)_RCC | 16 | 2026-02-20 | 2026-03-13 | 2026-07-31 | 2026-08-05 | 100
A60480 | Escape Evacuation and Rescue Assessment (EERA)_IFR | 6 | 16-Aug-25 A | 31-Oct-25 A | 46240 | 46261
A59530 | Escape Evacuation and Rescue Assessment (EERA)_Preparation | 6 | 01-Aug-25 A | 15-Aug-25 A | 46261 | 46265
Emergency Systems Survivability Analysis (ESSA) |  | 113 | 01-Aug-25 A | 2026-04-14 | 2026-07-09 | 2026-08-31 | 100
A58870 | Emergency Systems Survivability Analysis (ESSA)_IFD/IFC | 2 | 2026-04-09 | 2026-04-14 | 2026-07-09 | 2026-07-09 | 100
A58860 | Emergency Systems Survivability Analysis (ESSA)_RCA | 16 | 2026-03-19 | 2026-04-09 | 2026-07-09 | 2026-07-09 | 100
A58850 | Emergency Systems Survivability Analysis (ESSA)_IFA | 3 | 2026-03-13 | 2026-03-19 | 2026-07-09 | 2026-07-31 | 100
A58840 | Emergency Systems Survivability Analysis (ESSA)_RCC | 16 | 2026-02-20 | 2026-03-13 | 2026-07-31 | 2026-08-05 | 100
A58830 | Emergency Systems Survivability Analysis (ESSA)_IFR | 28 | 18-Aug-25 A | 31-Oct-25 A | 46240 | 46261
A60340 | Emergency Systems Survivability Analysis (ESSA)_Preparation | 6 | 01-Aug-25 A | 15-Aug-25 A | 46261 | 46265
Risk Reduction ALARP Workshop |  | 38 | 28-Jul-25 A | 2026-04-15 | 2026-11-27 | 2027-01-20 | 201
A59170 | Risk Reduction ALARP Workshop Report_IFD/IFC | 2 | 2026-04-13 | 2026-04-15 | 2026-11-27 | 2026-11-27 | 201
A59160 | Risk Reduction ALARP Workshop Report_RCA | 16 | 2026-03-20 | 2026-04-10 | 2026-11-27 | 2026-12-07 | 201
A59150 | Risk Reduction ALARP Workshop Report_IFA | 3 | 2026-03-16 | 2026-03-20 | 2026-12-07 | 2026-12-22 | 201
A59140 | Risk Reduction ALARP Workshop_Report RCC | 11 | 2026-02-27 | 2026-03-16 | 2026-12-22 | 2026-12-25 | 201
A59130 | Risk Reduction ALARP Workshop | 6 | 28-Jul-25 A | 07-Aug-25 A | 46384 | 46405
A60400 | Risk Reduction ALARP Workshop Report_IFR | 6 | 2026-02-20 | 2026-02-27 | 2027-01-18 | 2027-01-20 | 201
Air Emission Dispersion Assessment |  | 167 | 01-Aug-25 A | 2026-04-14 | 2026-07-09 | 2026-08-31 | 100
A59120 | Air Emission Dispersion Assessment_IFD/IFC | 2 | 2026-04-09 | 2026-04-14 | 2026-07-09 | 2026-07-09 | 100
A59110 | Air Emission Dispersion Assessment_RCA | 16 | 2026-03-19 | 2026-04-09 | 2026-07-09 | 2026-07-09 | 100
A59100 | Air Emission Dispersion Assessment_IFA | 3 | 2026-03-13 | 2026-03-19 | 2026-07-09 | 2026-07-31 | 100
A59090 | Air Emission Dispersion Assessment_RCC | 16 | 2026-02-20 | 2026-03-13 | 2026-07-31 | 2026-08-05 | 100
A59080 | Air Emission Dispersion Assessment_IFR | 6 | 16-Aug-25 A | 25-Sep-25 A | 46240 | 46261
A60390 | Air Emission Dispersion Assessment_Preparation | 6 | 01-Aug-25 A | 15-Aug-25 A | 46261 | 46265
Noise Study & Contours Report |  | 164 | 01-Aug-25 A | 2026-04-08 | 2026-03-17 | 2026-08-31 | 103
A62140 | Noise study & control report_IFD/IFC | 2 | 2026-04-06 | 2026-04-08 | 2026-03-17 | 2026-03-17 | 103
A62130 | Noise study & control report_RCA | 14 | 2026-03-17 | 2026-04-06 | 2026-07-15 | 2026-07-15 | 103
A62120 | Noise study & control report_IFA | 3 | 2026-03-12 | 2026-03-17 | 2026-07-15 | 2026-08-04 | 103
A62110 | Noise study & control report_RCC | 14 | 2026-02-20 | 2026-03-11 | 2026-08-04 | 2026-08-07 | 103
A62100 | Noise study & control report_IFR | 6 | 16-Aug-25 A | 25-Sep-25 A | 46241 | 46261
A62090 | Noise study & control report_Preparation | 6 | 01-Aug-25 A | 15-Aug-25 A | 46261 | 46265
Best Available Techniques Study (BAT) |  | 86 | 01-Aug-25 A | 2026-03-23 | 2026-03-17 | 2026-08-31 | 116
A58970 | Best Available Techniques Study_IFD/IFC | 2 | 2026-03-19 | 2026-03-23 | 2026-03-17 | 2026-03-17 | 116
A58960 | Best Available Techniques Study_RCA | 16 | 2026-02-25 | 2026-03-19 | 2026-03-27 | 2026-03-27 | 116
A58950 | Best Available Techniques Study_IFA | 3 | 2026-02-20 | 2026-02-25 | 2026-03-17 | 2026-03-17 | 116
A58940 | Best Available Techniques Study_RCC | 16 | 21-Aug-25 A | 29-Aug-25 A | 46234 | 46239
A58930 | Best Available Techniques Study_IFR | 6 | 21-Aug-25 A | 18-Sep-25 A | 46240 | 46261
A60360 | Best Available Techniques Study_Workshop | 6 | 01-Aug-25 A | 20-Aug-25 A | 46261 | 46265
Energy Review Workshop & Report |  | 97 | 01-Sep-25 A | 2026-04-21 | 2026-03-27 | 2027-01-20 | 196
A59420 | Energy Review Workshop & Report_IFD/IFC | 2 | 2026-04-17 | 2026-04-21 | 2026-03-27 | 2026-03-27 | 196
A59410 | Energy Review Workshop & Report_RCA | 16 | 2026-03-26 | 2026-04-17 | 2026-11-23 | 2026-11-30 | 196
A59400 | Energy Review Workshop & Report_IFA | 3 | 2026-03-23 | 2026-03-26 | 2026-11-30 | 2026-12-22 | 196
A59390 | Energy Review Workshop & Report_RCC | 16 | 2026-02-27 | 2026-03-23 | 2026-12-22 | 2026-12-25 | 196
A60450 | Energy Review Workshop & Report_IFR | 6 | 2026-02-20 | 2026-02-27 | 2026-12-28 | 2027-01-18 | 196
A59380 | Energy Review Workshop | 6 | 01-Sep-25 A | 19-Sep-25 A | 46405 | 46407
Vent & Flare Dispersion and Radiation Study |  | 102 | 01-Oct-25 A | 2026-04-14 | 2026-03-27 | 2027-01-20 | 202
A59670 | Vent & Flare Dispersion and Radiation Study_IFD/IFC | 2 | 2026-04-09 | 2026-04-14 | 2026-03-27 | 2026-03-27 | 202
A59660 | Vent & Flare Dispersion and Radiation Study_RCA | 16 | 2026-03-19 | 2026-04-09 | 2026-03-27 | 2026-03-27 | 202
A59650 | Vent & Flare Dispersion and Radiation Study_IFA | 3 | 2026-03-13 | 2026-03-19 | 2026-11-30 | 2026-12-22 | 202
A59640 | Vent & Flare Dispersion and Radiation Study_RCC | 16 | 2026-02-20 | 2026-03-13 | 2026-12-22 | 2026-12-25 | 202
A60500 | Vent & Flare Dispersion and Radiation Study_IFR | 6 | 16-Oct-25 A | 31-Oct-25 A | 46384 | 46405
A59630 | Vent & Flare Dispersion and Radiation Study Preparation ---- | 6 | 01-Oct-25 A | 15-Oct-25 A | 46405 | 46407
Environment Impact Assessment |  | 75 | 28-Aug-25 A | 2026-04-08 | 2026-07-15 | 2026-08-31 | 103
A59070 | Environment Impact Assessment_IFD/IFC | 2 | 2026-04-06 | 2026-04-08 | 2026-07-15 | 2026-07-15 | 103
A59060 | Environment Impact Assessment_RCA | 14 | 2026-03-17 | 2026-04-06 | 2026-07-15 | 2026-07-15 | 103
A59050 | Environment Impact Assessment_IFA | 3 | 2026-03-12 | 2026-03-17 | 2026-07-15 | 2026-08-04 | 103
A59040 | Environment Impact Assessment_RCC | 14 | 2026-02-20 | 2026-03-11 | 2026-08-04 | 2026-08-07 | 103
A59030 | Environment Impact Assessment_IFR | 6 | 06-Sep-25 A | 18-Sep-25 A | 46241 | 46261
A60380 | Environment Impact Assessment_Workshop ---- | 6 | 28-Aug-25 A | 05-Sep-25 A | 46261 | 46265
Ergonomics and Human Factor Engineering Study |  | 112 | 25-Aug-25 A | 2026-07-01 | 2026-09-11 | 2027-01-20 | 146
A58770 | Ergonomics and Human Factor Engineering Study_IFD/IFC | 17 | 2026-06-08 | 2026-07-01 | 2026-09-11 | 2026-09-11 | 146
A58760 | Ergonomics and Human Factor Engineering Study_RCA | 24 | 2026-05-05 | 2026-06-08 | 2026-09-11 | 2026-09-21 | 146
A58750 | Ergonomics and Human Factor Engineering Study_IFA | 24 | 2026-04-02 | 2026-05-05 | 2026-09-21 | 2026-10-22 | 146
A58740 | Ergonomics and Human Factor Engineering Study_RCC | 24 | 2026-02-27 | 2026-04-02 | 2026-10-22 | 2026-11-25 | 146
A58730 | Ergonomics and Human Factor Engineering Study_IFR | 6 | 2026-02-20 | 2026-02-27 | 2026-11-25 | 2026-12-29 | 146
A60320 | Ergonomics and Human Factor Engineering Study Workshop | 5 | 25-Aug-25 A | 01-Sep-25 A | 46385 | 46407
Dropped Objects Study (DOS) |  | 63 | 2026-02-20 | 2026-05-19 | 2026-10-26 | 2027-01-20 | 176
A58920 | Dropped Objects Study (DOS)_IFD/IFC | 2 | 2026-05-15 | 2026-05-19 | 2026-10-26 | 2026-11-02 | 176
A58910 | Dropped Objects Study (DOS)_RCA | 16 | 2026-04-24 | 2026-05-15 | 2026-11-02 | 2026-11-30 | 176
A58900 | Dropped Objects Study (DOS)_IFA | 3 | 2026-04-20 | 2026-04-23 | 2026-11-30 | 2026-12-22 | 176
A58890 | Dropped Objects Study (DOS)_RCC | 16 | 2026-03-27 | 2026-04-20 | 2026-12-22 | 2026-12-25 | 176
A58880 | Dropped Objects Study (DOS)_IFR | 20 | 2026-02-27 | 2026-03-27 | 2026-12-28 | 2027-01-18 | 176
A60350 | Dropped Objects Study (DOS)_Workshop | 6 | 2026-02-20 | 2026-02-27 | 2027-01-18 | 2027-01-20 | 176
3D F&G mapping study |  | 48 | 2026-02-20 | 2026-04-29 | 2026-11-13 | 2027-01-20 | 191
A59020 | 3D F&G mapping study_IFD/IFC | 2 | 2026-04-27 | 2026-04-29 | 2026-11-13 | 2026-11-23 | 191
A59010 | 3D F&G mapping study_RCA | 16 | 2026-04-03 | 2026-04-27 | 2026-11-23 | 2026-11-30 | 191
A59000 | 3D F&G mapping study_IFA | 3 | 2026-03-31 | 2026-04-03 | 2026-11-30 | 2026-12-22 | 191
A58990 | 3D F&G mapping study_RCC | 16 | 2026-03-09 | 2026-03-30 | 2026-12-22 | 2026-12-25 | 191
A58980 | 3D F&G mapping study_IFR | 6 | 2026-02-27 | 2026-03-09 | 2026-12-28 | 2027-01-18 | 191
A60370 | 3D F&G mapping study_Preparation | 6 | 2026-02-20 | 2026-02-27 | 2027-01-18 | 2027-01-20 | 191
E-HAZOP |  | 102 | 25-Aug-25 A | 2026-04-21 | 2026-03-17 | 2027-01-20 | 196
A62200 | E-HAZOP_IFD/IFC | 2 | 2026-04-17 | 2026-04-21 | 2026-03-17 | 2026-03-17 | 196
A62190 | E-HAZOP_RCA | 16 | 2026-03-26 | 2026-04-17 | 2026-11-23 | 2026-11-30 | 196
A62180 | E-HAZOP_IFA | 3 | 2026-03-23 | 2026-03-26 | 2026-11-30 | 2026-12-22 | 196
A62170 | E-HAZOP_RCC | 16 | 2026-02-27 | 2026-03-23 | 2026-12-22 | 2026-12-25 | 196
A62160 | E-HAZOP_IFR | 6 | 2026-02-20 | 2026-02-27 | 2026-12-28 | 2027-01-18 | 196
A62150 | E-HAZOP_Workshop | 3 | 25-Aug-25 A | 01-Sep-25 A | 46405 | 46407
Constructability Review |  | 146 | 27-Aug-25 A | 2026-03-23 | 2026-12-22 | 2027-01-20 | 218
A59220 | Constructability Review_IFD/IFC | 2 | 2026-03-19 | 2026-03-23 | 2026-12-22 | 2026-12-22 | 218
A59210 | Constructability Review_RCA | 16 | 2026-02-25 | 2026-03-19 | 2026-12-22 | 2026-12-22 | 218
A59200 | Constructability Review_IFA | 3 | 2026-02-20 | 2026-02-25 | 2026-12-22 | 2026-12-22 | 218
A59190 | Constructability Review_RCC | 16 | 01-Dec-25 A | 10-Dec-25 A | 46378 | 46381
A60410 | Constructability Review_IFR | 6 | 17-Nov-25 A | 30-Nov-25 A | 46384 | 46405
A59180 | Constructability Review Workshop | 6 | 27-Aug-25 A | 27-Aug-25 A | 46405 | 46407
SIMPOS |  | 170 | 25-Aug-25 A | 2026-03-23 | 2026-12-22 | 2027-01-20 | 218
A59720 | SIMOPS Report_IFD/IFC | 2 | 2026-03-19 | 2026-03-23 | 2026-12-22 | 2026-12-22 | 218
A59710 | SIMOPS Report_RCA | 16 | 2026-02-25 | 2026-03-19 | 2026-12-22 | 2026-12-22 | 218
A59700 | SIMOPS Report_IFA | 3 | 2026-02-20 | 2026-02-25 | 2026-12-22 | 2026-12-22 | 218
A59690 | SIMOPS Report_RCC | 16 | 08-Dec-25 A | 16-Dec-25 A | 46378 | 46381
A60520 | SIMOPS Report_IFR | 6 | 11-Nov-25 A | 30-Nov-25 A | 46384 | 46405
A59680 | SIMOPS Workshop | 6 | 25-Aug-25 A | 28-Aug-25 A | 46405 | 46407
HSEIA |  | 41 | 24-Dec-25 A | 2026-03-26 | 2026-04-02 | 2027-01-20 | 205
A61390 | HSEIA Report_RCC | 16 | 07-Jan-26 A | 23-Jan-26 A | 46114 | 46114
A61380 | HSEIA Report_IFR | 6 | 01-Jan-26 A | 06-Jan-26 A | 46114 | 46114
A61840 | HSEIA Report ADNOC Approval | 25 | 2026-02-20 | 2026-03-26 | 2026-12-29 | 2026-12-29 | 29
A62500 | Assesemnt on new requirements by COMPANY | 21 | 13-Feb-26 A | 2026-02-27 | 2026-12-29 | 2027-01-06 | 210
A61370 | HSEIA Report Preparation | 6 | 24-Dec-25 A | 31-Dec-25 A | 46393 | 46398
A61420 | HSEIA Report_IFD/IFC | 2 | 2026-03-12 | 2026-03-16 | 2027-01-11 | 2027-01-18 | 222
A61410 | HSEIA Report_RCA | 5 | 2026-03-05 | 2026-03-12 | 2027-01-18 | 2027-01-20 | 222
A61400 | HSEIA Report_IFA | 3 | 2026-03-02 | 2026-03-05 | 2026-04-02 | 2026-05-06 | 222
PHSER III |  | 48 | 2026-03-06 | 2026-05-13 | 2026-07-01 | 2026-09-08 | 84
A59370 | PHSER III_IFD/IFC | 2 | 2026-05-11 | 2026-05-13 | 2026-07-01 | 2026-07-09 | 84
A59360 | PHSER III_RCA | 16 | 2026-04-17 | 2026-05-11 | 2026-07-09 | 2026-07-17 | 84
A59350 | PHSER III_IFA | 3 | 2026-04-14 | 2026-04-17 | 2026-07-17 | 2026-08-07 | 84
A59340 | PHSER III_RCC | 16 | 2026-03-23 | 2026-04-14 | 2026-08-07 | 2026-08-13 | 84
A60440 | PHSER III_IFR | 6 | 2026-03-13 | 2026-03-23 | 2026-08-13 | 2026-09-03 | 84
A59330 | PHSER III_Workshop | 6 | 2026-03-06 | 2026-03-13 | 2026-09-04 | 2026-09-08 | 84
PHSER IV |  | 48 | 2026-05-13 | 2026-07-20 | 2026-09-08 | 2026-11-13 | 84
A61890 | PHSER IV_IFD/IFC | 2 | 2026-07-16 | 2026-07-20 | 2026-09-08 | 2026-09-15 | 84
A61880 | PHSER IV_RCA | 16 | 2026-06-24 | 2026-07-16 | 2026-09-15 | 2026-09-23 | 84
A61870 | PHSER IV_IFA | 3 | 2026-06-19 | 2026-06-24 | 2026-09-23 | 2026-10-15 | 84
A61860 | PHSER IV_RCC | 16 | 2026-05-28 | 2026-06-19 | 2026-10-15 | 2026-10-20 | 84
A61900 | PHSER IV_IFR | 6 | 2026-05-21 | 2026-05-28 | 2026-10-20 | 2026-11-11 | 84
A61850 | PHSER IV_Workshop | 6 | 2026-05-13 | 2026-05-21 | 2026-11-11 | 2026-11-13 | 84
PHSER V |  | 48 | 2026-07-20 | 2026-09-25 | 2026-11-13 | 2027-01-20 | 84
A61950 | PHSER V_IFD/IFC | 2 | 2026-09-23 | 2026-09-25 | 2026-11-13 | 2026-11-23 | 84
A61940 | PHSER V_RCA | 16 | 2026-09-01 | 2026-09-22 | 2026-11-23 | 2026-11-30 | 84
A61930 | PHSER V_FA | 3 | 2026-08-26 | 2026-09-01 | 2026-11-30 | 2026-12-22 | 84
A61920 | PHSER V_RCC | 16 | 2026-08-05 | 2026-08-26 | 2026-12-22 | 2026-12-25 | 84
A61960 | PHSER V_IFR | 6 | 2026-07-28 | 2026-08-05 | 2026-12-28 | 2027-01-18 | 84
A61910 | PHSER V_Workshop | 6 | 2026-07-20 | 2026-07-28 | 2027-01-18 | 2027-01-20 | 84
QA/QC Management |  | 400 | 12-May-25 A | 2026-06-11 | 2026-03-20 | 2027-07-20 | 288
QAQC Deliverables |  | 275 | 25-May-25 A | 2026-06-11 | 2026-03-20 | 2027-04-21 | 224
A1-PM-QCD-0014 | PCQ-014-Inspection Release Report | 5 | 2026-06-05 | 2026-06-11 | 2026-03-27 | 2026-03-27 | 224
A1-PM-QCD-0013 | PCQ-013-Inspection Plan and Schedule | 5 | 15-Aug-25 A | 2026-06-04 | 2026-11-06 | 2026-11-06 | 224
A1-PM-QCD-0010 | PCQ-010-Vendor Shop Inspection & Quality Control Plans | 5 | 18-Aug-25 A | 2026-05-26 | 2026-03-20 | 2026-03-27 | 224
A1-PM-QCD-0009 | PCQ-009-Inspection / Expediting / Reports | 5 | 15-Aug-25 A | 2026-05-15 | 2027-01-11 | 2027-01-15 | 224
A1-PM-QCD-0008 | PCQ-008-Inspection Guidelines (Source and Field) | 5 | 15-Aug-25 A | 2026-05-06 | 2027-01-20 | 2027-01-26 | 224
A1-PM-QCD-0007 | PCQ-007-Quality Assurance Docs | 5 | 15-Aug-25 A | 2026-04-27 | 2027-01-29 | 2027-02-04 | 224
A1-PM-QCD-0006 | PCQ-006-Inspection and Test Plan | 5 | 16-Jun-25 A | 2026-04-16 | 2027-02-15 | 2027-02-15 | 224
A1-PM-QCD-0005 | PCQ-005-Inspection and Test Plan Site | 5 | 16-Jun-25 A | 2026-04-07 | 2027-02-24 | 2027-02-24 | 224
A1-PM-QCD-0004 | PCQ-004-Inspection and Test Plan Vendor | 5 | 14-Aug-25 A | 2026-03-27 | 2027-03-05 | 2027-03-05 | 224
A1-PM-QCD-0003 | PCQ-003-Test Certificate | 5 | 14-Aug-25 A | 2026-03-18 | 2027-03-16 | 2027-03-16 | 224
A1-PM-QCD-0002 | PCQ-002-Inspection Check List | 5 | 08-Aug-25 A | 2026-03-09 | 2027-03-25 | 2027-03-25 | 224
A1-PM-QCD-0001 | PCQ-001-Inspection Record | 5 | 08-Aug-25 A | 2026-02-26 | 2027-04-05 | 2027-04-05 | 20
A1-PM-QCD-0012 | PCQ-012-Worksite Quality Plan | 5 | 03-Sep-25 A | 15-Sep-25 A | 46491 | 46491
A1-PM-QCD-0011 | PCQ-011-Site Contractors Quality Plans | 5 | 25-May-25 A | 03-Sep-25 A | 46492 | 46498
QAQC Audit Plan |  | 380 | 12-May-25 A | 25-May-25 A | 46588 | 46588
A1-PM-QAP-0001 | QAQC Audit Plan | 380 | 12-May-25 A | 25-May-25 A | 46588 | 46588
Contractor's Temporary Facilities |  | 0 | 20-Jan-25 A | 20-Jan-25 A
Home Office |  | 0 | 20-Jan-25 A | 20-Jan-25 A
A1-PM-CTF-0001 | Home Office Ready for IPMT Moblization | 0 |  | 20-Jan-25 A
Others |  | 650 | 20-Dec-24 A | 2027-07-20 | 2026-03-27 | 2027-07-20 | 0
Project Key Milestones |  | 739 | 12-Apr-25 A | 2027-07-20 | 2026-03-27 | 2027-07-20 | 0
A1-PM-PKM-0004 | Provisional Acceptance Certificate (PAC) | 0 |  | 2027-07-20 | 2026-03-27 | 2026-03-27 | 0
A1-PM-PKM-0003 | Ready for Start-up (RFSU) | 0 |  | 2027-04-21 |  | 2027-01-20 | 0
A1-PM-PKM-0002 | Mechanical Completion (MC) | 0 |  | 2027-01-20 |  | 2027-04-21 | 0
A1-PM-PKM-0001 | Turnaround Scope Completion (TA) | 38 | 12-Apr-25 A | 17-May-25 A |  | 46588
Weekly Progress Report |  | 537 | 03-Jan-25 A | 2027-02-24 | 2026-07-16 | 2027-07-20 | 105
A1-PM-WPR-0113 | Weekly Progress Report Issuance - WPR0113 | 0 |  | 2027-02-24 |  |  | 146
A1-PM-WPR-0112 | Weekly Progress Report Issuance - WPR0112 | 0 |  | 2027-02-18 |  |  | 146
A1-PM-WPR-0111 | Weekly Progress Report Issuance - WPR0111 | 0 |  | 2027-02-13 |  |  | 146
A1-PM-WPR-0110 | Weekly Progress Report Issuance - WPR0110 | 0 |  | 2027-02-07 |  |  | 146
A1-PM-WPR-0109 | Weekly Progress Report Issuance - WPR0109 | 0 |  | 2027-02-02 |  |  | 146
A1-PM-WPR-0108 | Weekly Progress Report Issuance - WPR0108 | 0 |  | 2027-01-27 |  |  | 146
A1-PM-WPR-0107 | Weekly Progress Report Issuance - WPR0107 | 0 |  | 2027-01-21 |  |  | 146
A1-PM-WPR-0106 | Weekly Progress Report Issuance - WPR0106 | 0 |  | 2027-01-16 |  |  | 146
A1-PM-WPR-0105 | Weekly Progress Report Issuance - WPR0105 | 0 |  | 2027-01-10 |  |  | 146
A1-PM-WPR-0104 | Weekly Progress Report Issuance - WPR0104 | 0 |  | 2027-01-05 |  |  | 146
A1-PM-WPR-0103 | Weekly Progress Report Issuance - WPR0103 | 0 |  | 2026-12-30 |  |  | 146
A1-PM-WPR-0102 | Weekly Progress Report Issuance - WPR0102 | 0 |  | 2026-12-24 |  |  | 146
A1-PM-WPR-0101 | Weekly Progress Report Issuance - WPR0101 | 0 |  | 2026-12-19 |  |  | 146
A1-PM-WPR-0100 | Weekly Progress Report Issuance - WPR0100 | 0 |  | 2026-12-13 |  |  | 146
A1-PM-WPR-0099 | Weekly Progress Report Issuance - WPR0099 | 0 |  | 2026-12-08 |  |  | 146
A1-PM-WPR-0098 | Weekly Progress Report Issuance - WPR0098 | 0 |  | 2026-12-02 |  |  | 146
A1-PM-WPR-0097 | Weekly Progress Report Issuance - WPR0097 | 0 |  | 2026-11-26 |  |  | 146
A1-PM-WPR-0096 | Weekly Progress Report Issuance - WPR0096 | 0 |  | 2026-11-21 |  |  | 146
A1-PM-WPR-0095 | Weekly Progress Report Issuance - WPR0095 | 0 |  | 2026-11-15 |  |  | 146
A1-PM-WPR-0094 | Weekly Progress Report Issuance - WPR0094 | 0 |  | 2026-11-10 |  |  | 146
A1-PM-WPR-0093 | Weekly Progress Report Issuance - WPR0093 | 0 |  | 2026-11-04 |  |  | 146
A1-PM-WPR-0092 | Weekly Progress Report Issuance - WPR0092 | 0 |  | 2026-10-29 |  |  | 146
A1-PM-WPR-0091 | Weekly Progress Report Issuance - WPR0091 | 0 |  | 2026-10-24 |  |  | 146
A1-PM-WPR-0090 | Weekly Progress Report Issuance - WPR0090 | 0 |  | 2026-10-18 |  |  | 146
A1-PM-WPR-0089 | Weekly Progress Report Issuance - WPR0089 | 0 |  | 2026-10-13 |  |  | 146
A1-PM-WPR-0088 | Weekly Progress Report Issuance - WPR0088 | 0 |  | 2026-10-07 |  |  | 146
A1-PM-WPR-0087 | Weekly Progress Report Issuance - WPR0087 | 0 |  | 2026-10-01 |  |  | 146
A1-PM-WPR-0086 | Weekly Progress Report Issuance - WPR0086 | 0 |  | 2026-09-26 |  |  | 146
A1-PM-WPR-0085 | Weekly Progress Report Issuance - WPR0085 | 0 |  | 2026-09-20 |  |  | 146
A1-PM-WPR-0084 | Weekly Progress Report Issuance - WPR0084 | 0 |  | 2026-09-15 |  |  | 146
A1-PM-WPR-0083 | Weekly Progress Report Issuance - WPR0083 | 0 |  | 2026-09-09 |  |  | 146
A1-PM-WPR-0082 | Weekly Progress Report Issuance - WPR0082 | 0 |  | 2026-09-03 |  |  | 146
A1-PM-WPR-0081 | Weekly Progress Report Issuance - WPR0081 | 0 |  | 2026-08-29 |  |  | 146
A1-PM-WPR-0080 | Weekly Progress Report Issuance - WPR0080 | 0 |  | 2026-08-23 |  |  | 146
A1-PM-WPR-0079 | Weekly Progress Report Issuance - WPR0079 | 0 |  | 2026-08-18 |  |  | 146
A1-PM-WPR-0078 | Weekly Progress Report Issuance - WPR0078 | 0 |  | 2026-08-12 |  |  | 146
A1-PM-WPR-0077 | Weekly Progress Report Issuance - WPR0077 | 0 |  | 2026-08-06 |  |  | 146
A1-PM-WPR-0076 | Weekly Progress Report Issuance - WPR0076 | 0 |  | 2026-08-01 |  |  | 146
A1-PM-WPR-0075 | Weekly Progress Report Issuance - WPR0075 | 0 |  | 2026-07-26 |  |  | 146
A1-PM-WPR-0074 | Weekly Progress Report Issuance - WPR0074 | 0 |  | 2026-07-21 |  |  | 146
A1-PM-WPR-0073 | Weekly Progress Report Issuance - WPR0073 | 0 |  | 2026-07-15 |  |  | 146
A1-PM-WPR-0072 | Weekly Progress Report Issuance - WPR0072 | 0 |  | 2026-07-09 |  |  | 146
A1-PM-WPR-0071 | Weekly Progress Report Issuance - WPR0071 | 0 |  | 2026-07-04 |  |  | 146
A1-PM-WPR-0070 | Weekly Progress Report Issuance - WPR0070 | 0 |  | 2026-06-28 |  |  | 146
A1-PM-WPR-0069 | Weekly Progress Report Issuance - WPR0069 | 0 |  | 2026-06-23 |  |  | 146
A1-PM-WPR-0068 | Weekly Progress Report Issuance - WPR0068 | 0 |  | 2026-06-17 |  |  | 146
A1-PM-WPR-0067 | Weekly Progress Report Issuance - WPR0067 | 0 |  | 2026-06-11 |  | 2026-07-16 | 146
A1-PM-WPR-0066 | Weekly Progress Report Issuance - WPR0066 | 0 |  | 2026-06-06 |  | 2026-07-21 | 146
A1-PM-WPR-0065 | Weekly Progress Report Issuance - WPR0065 | 0 |  | 2026-05-31 |  | 2026-07-27 | 146
A1-PM-WPR-0064 | Weekly Progress Report Issuance - WPR0064 | 0 |  | 2026-05-26 |  | 2026-08-02 | 146
A1-PM-WPR-0063 | Weekly Progress Report Issuance - WPR0063 | 0 |  | 2026-05-20 |  | 2026-08-07 | 146
A1-PM-WPR-0062 | Weekly Progress Report Issuance - WPR0062 | 0 |  | 2026-05-14 |  | 2026-08-13 | 146
A1-PM-WPR-0061 | Weekly Progress Report Issuance - WPR0061 | 0 |  | 2026-05-09 |  | 2026-08-18 | 146
A1-PM-WPR-0060 | Weekly Progress Report Issuance - WPR0060 | 0 |  | 2026-05-03 |  | 2026-08-24 | 146
A1-PM-WPR-0059 | Weekly Progress Report Issuance - WPR0059 | 0 |  | 2026-04-28 |  | 2026-08-30 | 146
A1-PM-WPR-0058 | Weekly Progress Report Issuance - WPR0058 | 0 |  | 2026-04-22 |  | 2026-09-04 | 146
A1-PM-WPR-0057 | Weekly Progress Report Issuance - WPR0057 | 0 |  | 2026-04-16 |  | 2026-09-10 | 146
A1-PM-WPR-0056 | Weekly Progress Report Issuance - WPR0056 | 0 |  | 2026-04-11 |  | 2026-09-15 | 146
A1-PM-WPR-0055 | Weekly Progress Report Issuance - WPR0055 | 0 |  | 2026-04-05 |  | 2026-09-21 | 146
A1-PM-WPR-0054 | Weekly Progress Report Issuance - WPR0054 | 0 |  | 2026-03-31 |  | 2026-09-27 | 146
A1-PM-WPR-0053 | Weekly Progress Report Issuance - WPR0053 | 0 |  | 2026-03-25 |  | 2026-10-02 | 146
A1-PM-WPR-0052 | Weekly Progress Report Issuance - WPR0052 | 0 |  | 2026-03-19 |  | 2026-10-08 | 146
A1-PM-WPR-0051 | Weekly Progress Report Issuance - WPR0051 | 0 |  | 2026-03-14 |  | 2026-10-13 | 146
A1-PM-WPR-0050 | Weekly Progress Report Issuance - WPR0050 | 0 |  | 2026-03-08 |  | 2026-10-19 | 146
A1-PM-WPR-0049 | Weekly Progress Report Issuance - WPR0049 | 0 |  | 2026-03-03 |  | 2026-10-25 | 146
A1-PM-WPR-0048 | Weekly Progress Report Issuance - WPR0048 | 0 |  | 2026-02-25 |  | 2026-10-30 | 146
A1-PM-WPR-0047 | Weekly Progress Report Issuance - WPR0047 | 0 |  | 2026-02-20 |  | 2026-11-05 | 146
A1-PM-WPR-0046 | Weekly Progress Report Issuance - WPR0046 | 0 |  | 18-Nov-25 A |  | 46336
A1-PM-WPR-0045 | Weekly Progress Report Issuance - WPR0045 | 0 |  | 12-Nov-25 A |  | 46342
A1-PM-WPR-0044 | Weekly Progress Report Issuance - WPR0044 | 0 |  | 04-Nov-25 A |  | 46348
A1-PM-WPR-0043 | Weekly Progress Report Issuance - WPR0043 | 0 |  | 30-Oct-25 A |  | 46353
A1-PM-WPR-0042 | Weekly Progress Report Issuance - WPR0042 | 0 |  | 24-Oct-25 A |  | 46359
A1-PM-WPR-0041 | Weekly Progress Report Issuance - WPR0041 | 0 |  | 17-Oct-25 A |  | 46364
A1-PM-WPR-0040 | Weekly Progress Report Issuance - WPR0040 | 0 |  | 10-Oct-25 A |  | 46370
A1-PM-WPR-0039 | Weekly Progress Report Issuance - WPR0039 | 0 |  | 03-Oct-25 A |  | 46376
A1-PM-WPR-0038 | Weekly Progress Report Issuance - WPR0038 | 0 |  | 19-Sep-25 A |  | 46381
A1-PM-WPR-0036 | Weekly Progress Report Issuance - WPR0036 | 0 |  | 15-Sep-25 A |  | 46387
A1-PM-WPR-0035 | Weekly Progress Report Issuance - WPR0035 | 0 |  | 15-Sep-25 A |  | 46392
A1-PM-WPR-0037 | Weekly Progress Report Issuance - WPR0037 | 0 |  | 12-Sep-25 A |  | 46398
A1-PM-WPR-0034 | Weekly Progress Report Issuance - WPR0034 | 0 |  | 27-Aug-25 A |  | 46404
A1-PM-WPR-0033 | Weekly Progress Report Issuance - WPR0033 | 0 |  | 13-Sep-25 A |  | 46409
A1-PM-WPR-0032 | Weekly Progress Report Issuance - WPR0032 | 0 |  | 07-Sep-25 A |  | 46415
A1-PM-WPR-0031 | Weekly Progress Report Issuance - WPR0031 | 0 |  | 02-Sep-25 A |  | 46420
A1-PM-WPR-0030 | Weekly Progress Report Issuance - WPR0030 | 0 |  | 27-Aug-25 A |  | 46426
A1-PM-WPR-0029 | Weekly Progress Report Issuance - WPR0029 | 0 |  | 22-Aug-25 A |  | 46432
A1-PM-WPR-0028 | Weekly Progress Report Issuance - WPR0028 | 0 |  | 18-Jul-25 A |  | 46437
A1-PM-WPR-0027 | Weekly Progress Report Issuance - WPR0027 | 0 |  | 10-Jul-25 A |  | 46443
A1-PM-WPR-0020 | Weekly Progress Report Issuance - WPR0020 | 0 |  | 21-May-25 A |  | 46448
A1-PM-WPR-0026 | Weekly Progress Report Issuance - WPR0026 | 0 |  | 30-Jun-25 A |  | 46454
A1-PM-WPR-0025 | Weekly Progress Report Issuance - WPR0025 | 0 |  | 21-Jun-25 A |  | 46460
A1-PM-WPR-0019 | Weekly Progress Report Issuance - WPR0019 | 0 |  | 13-May-25 A |  | 46465
A1-PM-WPR-0018 | Weekly Progress Report Issuance - WPR0018 | 0 |  | 09-May-25 A |  | 46471
A1-PM-WPR-0024 | Weekly Progress Report Issuance - WPR0024 | 0 |  | 13-Jun-25 A |  | 46476
A1-PM-WPR-0023 | Weekly Progress Report Issuance - WPR0023 | 0 |  | 06-Jun-25 A |  | 46482
A1-PM-WPR-0017 | Weekly Progress Report Issuance - WPR0017 | 0 |  | 09-May-25 A |  | 46488
A1-PM-WPR-0022 | Weekly Progress Report Issuance - WPR0022 | 0 |  | 08-Jun-25 A |  | 46493
A1-PM-WPR-0021 | Weekly Progress Report Issuance - WPR0021 | 0 |  | 28-May-25 A |  | 46499
A1-PM-WPR-0015 | Weekly Progress Report Issuance - WPR0015 | 0 |  | 06-May-25 A |  | 46504
A1-PM-WPR-0014 | Weekly Progress Report Issuance - WPR0014 | 0 |  | 06-May-25 A |  | 46510
A1-PM-WPR-0013 | Weekly Progress Report Issuance - WPR0013 | 0 |  | 06-May-25 A |  | 46516
A1-PM-WPR-0012 | Weekly Progress Report Issuance - WPR0012 | 0 |  | 06-May-25 A |  | 46521
A1-PM-WPR-0011 | Weekly Progress Report Issuance - WPR0011 | 0 |  | 06-May-25 A |  | 46527
A1-PM-WPR-0016 | Weekly Progress Report Issuance - WPR0016 | 0 |  | 18-Apr-25 A |  | 46532
A1-PM-WPR-0010 | Weekly Progress Report Issuance - WPR0010 | 0 |  | 06-May-25 A |  | 46538
A1-PM-WPR-0009 | Weekly Progress Report Issuance - WPR0009 | 0 |  | 28-Feb-25 A |  | 46544
A1-PM-WPR-0008 | Weekly Progress Report Issuance - WPR0008 | 0 |  | 21-Feb-25 A |  | 46549
A1-PM-WPR-0007 | Weekly Progress Report Issuance - WPR0007 | 0 |  | 14-Feb-25 A |  | 46555
A1-PM-WPR-0006 | Weekly Progress Report Issuance - WPR0006 | 0 |  | 07-Feb-25 A |  | 46560
A1-PM-WPR-0005 | Weekly Progress Report Issuance - WPR0005 | 0 |  | 31-Jan-25 A |  | 46566
A1-PM-WPR-0004 | Weekly Progress Report Issuance - WPR0004 | 0 |  | 24-Jan-25 A |  | 46572
A1-PM-WPR-0003 | Weekly Progress Report Issuance - WPR0003 | 0 |  | 17-Jan-25 A |  | 46577
A1-PM-WPR-0002 | Weekly Progress Report Issuance - WPR0002 | 0 |  | 10-Jan-25 A |  | 46583
A1-PM-WPR-0001 | Weekly Progress Report Issuance - WPR0001 | 0 |  | 03-Jan-25 A |  | 46588
Monthly Progress Report |  | 790 | 20-Dec-24 A | 2027-02-18 | 2026-07-21 | 2027-07-20 | 152
A1-PM-MPR-0027 | Monthly Progress Report Issuance - MPR027 | 0 |  | 2027-02-18 |  |  | 152
A1-PM-MPR-0026 | Monthly Progress Report Issuance - MPR026 | 0 |  | 2027-01-27 |  |  | 152
A1-PM-MPR-0025 | Monthly Progress Report Issuance - MPR025 | 0 |  | 2026-12-30 |  |  | 152
A1-PM-MPR-0024 | Monthly Progress Report Issuance - MPR024 | 0 |  | 2026-12-08 |  |  | 152
A1-PM-MPR-0023 | Monthly Progress Report Issuance - MPR023 | 0 |  | 2026-11-15 |  |  | 152
A1-PM-MPR-0022 | Monthly Progress Report Issuance - MPR022 | 0 |  | 2026-10-18 |  |  | 152
A1-PM-MPR-0021 | Monthly Progress Report Issuance - MPR021 | 0 |  | 2026-09-26 |  |  | 152
A1-PM-MPR-0020 | Monthly Progress Report Issuance - MPR020 | 0 |  | 2026-09-03 |  |  | 152
A1-PM-MPR-0019 | Monthly Progress Report Issuance - MPR019 | 0 |  | 2026-08-06 |  |  | 152
A1-PM-MPR-0018 | Monthly Progress Report Issuance - MPR018 | 0 |  | 2026-07-15 |  |  | 152
A1-PM-MPR-0017 | Monthly Progress Report Issuance - MPR017 | 0 |  | 2026-06-17 |  |  | 152
A1-PM-MPR-0016 | Monthly Progress Report Issuance - MPR016 | 0 |  | 2026-05-26 |  | 2026-07-21 | 152
A1-PM-MPR-0015 | Monthly Progress Report Issuance - MPR015 | 0 |  | 2026-05-03 |  | 2026-08-13 | 152
A1-PM-MPR-0014 | Monthly Progress Report Issuance - MPR014 | 0 |  | 2026-04-11 |  | 2026-09-10 | 152
A1-PM-MPR-0013 | Monthly Progress Report Issuance - MPR013 | 0 |  | 2026-03-14 |  | 2026-10-02 | 152
A1-PM-MPR-0012 | Monthly Progress Report Issuance - MPR012 | 0 |  | 2026-02-20 |  | 2026-10-25 | 152
A1-PM-MPR-0011 | Monthly Progress Report Issuance - MPR011 | 0 |  | 21-Nov-25 A |  | 46342
A1-PM-MPR-0010 | Monthly Progress Report Issuance - MPR010 | 0 |  | 30-Oct-25 A |  | 46370
A1-PM-MPR-0009 | Monthly Progress Report Issuance - MPR009 | 0 |  | 10-Sep-25 A |  | 46392
A1-PM-MPR-0008 | Monthly Progress Report Issuance - MPR008 | 0 |  | 22-Aug-25 A |  | 46420
A1-PM-MPR-0007 | Monthly Progress Report Issuance - MPR007 | 0 |  | 01-Jul-25 A |  | 46443
A1-PM-MPR-0006 | Monthly Progress Report Issuance - MPR006 | 0 |  | 17-Jun-25 A |  | 46465
A1-PM-MPR-0005 | Monthly Progress Report Issuance - MPR005 | 0 |  | 13-May-25 A |  | 46493
A1-PM-MPR-0003 | Monthly Progress Report Issuance - MPR003 | 0 |  | 17-Jun-25 A |  | 46516
A1-PM-MPR-0004 | Monthly Progress Report Issuance - MPR004 | 0 |  | 14-Apr-25 A |  | 46538
A1-PM-MPR-0002 | Monthly Progress Report Issuance - MPR002 | 0 |  | 24-Jan-25 A |  | 46566
A1-PM-MPR-0001 | Monthly Progress Report Issuance - MPR001 | 0 |  | 20-Dec-24 A |  | 46588
Team Building Workshops |  | 561 | 06-Mar-25 A | 2026-12-04 | 2026-10-05 | 2027-07-20 | 228
A1-PM-TBW-0007 | TBW01-Team Building Event-007 | 0 |  | 2026-12-04 |  |  | 228
A1-PM-TBW-0006 | TBW01-Team Building Event-006 | 0 |  | 2026-08-30 |  |  | 228
A1-PM-TBW-0005 | TBW01-Team Building Event-005 | 0 |  | 2026-05-26 |  |  | 228
A1-PM-TBW-0004 | TBW01-Team Building Event-004 | 0 |  | 2026-02-20 |  | 2026-10-05 | 228
A1-PM-TBW-0003 | TBW01-Team Building Event-003 | 0 |  | 12-Aug-25 A |  | 46396
A1-PM-TBW-0002 | TBW01-Team Building Event-002 | 0 |  | 21-Jun-25 A |  | 46492
A1-PM-TBW-0001 | TBW01-Team Building Event-001 | 0 |  | 06-Mar-25 A |  | 46588
Invoicing Plan |  | 655 | 07-Feb-25 A | 2027-04-05 | 2026-06-06 | 2027-07-20 | 106
A1-PM-MIP-0027 | Monthly Invoicing Plan - MIP027 | 0 |  | 2027-04-05 |  |  | 106
A1-PM-MIP-0026 | Monthly Invoicing Plan - MIP026 | 0 |  | 2027-03-08 |  |  | 106
A1-PM-MIP-0025 | Monthly Invoicing Plan - MIP025 | 0 |  | 2027-02-05 |  |  | 106
A1-PM-MIP-0024 | Monthly Invoicing Plan - MIP024 | 0 |  | 2027-01-05 |  |  | 106
A1-PM-MIP-0023 | Monthly Invoicing Plan - MIP023 | 0 |  | 2026-12-06 |  |  | 106
A1-PM-MIP-0022 | Monthly Invoicing Plan - MIP022 | 0 |  | 2026-11-05 |  |  | 106
A1-PM-MIP-0021 | Monthly Invoicing Plan - MIP021 | 0 |  | 2026-10-06 |  |  | 106
A1-PM-MIP-0020 | Monthly Invoicing Plan - MIP020 | 0 |  | 2026-09-05 |  |  | 106
A1-PM-MIP-0019 | Monthly Invoicing Plan - MIP019 | 0 |  | 2026-08-05 |  |  | 106
A1-PM-MIP-0018 | Monthly Invoicing Plan - MIP018 | 0 |  | 2026-08-05 |  |  | 106
A1-PM-MIP-0017 | Monthly Invoicing Plan - MIP017 | 0 |  | 2026-07-06 |  |  | 106
A1-PM-MIP-0016 | Monthly Invoicing Plan - MIP016 | 0 |  | 2026-06-05 |  | 2026-06-06 | 106
A1-PM-MIP-0015 | Monthly Invoicing Plan - MIP015 | 0 |  | 2026-05-06 |  | 2026-06-22 | 106
A1-PM-MIP-0014 | Monthly Invoicing Plan - MIP014 | 0 |  | 2026-04-05 |  | 2026-07-20 | 106
A1-PM-MIP-0013 | Monthly Invoicing Plan - MIP013 | 0 |  | 2026-03-08 |  | 2026-08-20 | 106
A1-PM-MIP-0012 | Monthly Invoicing Plan - MIP012 | 0 |  | 2026-02-20 |  | 2026-09-19 | 106
A1-PM-MIP-0011 | Monthly Invoicing Plan - MIP011 | 0 |  | 11-Nov-25 A |  | 46315
A1-PM-MIP-0010 | Monthly Invoicing Plan - MIP010 | 0 |  | 24-Oct-25 A |  | 46345
A1-PM-MIP-0009 | Monthly Invoicing Plan - MIP009 | 0 |  | 19-Sep-25 A |  | 46345
A1-PM-MIP-0007 | Monthly Invoicing Plan - MIP007 | 0 |  | 21-Jun-25 A |  | 46376
A1-PM-MIP-0006 | Monthly Invoicing Plan - MIP006 | 0 |  | 21-Jun-25 A |  | 46407
A1-PM-MIP-0005 | Monthly Invoicing Plan - MIP005 | 0 |  | 21-Jun-25 A |  | 46437
A1-PM-MIP-0008 | Monthly Invoicing Plan - MIP008 | 0 |  | 29-Aug-25 A |  | 46468
A1-PM-MIP-0004 | Monthly Invoicing Plan - MIP004 | 0 |  | 10-May-25 A |  | 46498
A1-PM-MIP-0003 | Monthly Invoicing Plan - MIP003 | 0 |  | 10-Apr-25 A |  | 46529
A1-PM-MIP-0002 | Monthly Invoicing Plan - MIP002 | 0 |  | 07-Mar-25 A |  | 46560
A1-PM-MIP-0001 | Monthly Invoicing Plan - MIP001 (Advanced Payment) | 0 |  | 07-Feb-25 A |  | 46588
Home Office Services |  | 695 | 14-Nov-24 A | 2027-07-14 | 2026-02-21 | 2027-07-20 | 4
Detailed Design - EDDR |  | 511 | 27-Nov-24 A | 2026-09-25 | 2026-02-21 | 2027-07-20 | 213
Package 1&2 |  | 0 | 01-Aug-25 A | 22-Aug-25 A
Deliverables to be Recieved from Pkg 1&2 |  | 0 | 01-Aug-25 A | 22-Aug-25 A
1B-DE-P12-0151 | Safety - 11 Deleverables | 0 |  | 22-Aug-25 A
1B-DE-P12-0141 | Project Management - 86 Deleverables | 0 |  | 21-Aug-25 A
1B-DE-P12-0131 | Project Control Quality - 14 Deleverables | 0 |  | 20-Aug-25 A
1B-DE-P12-0121 | Project Control - 29 Deleverables | 0 |  | 19-Aug-25 A
1B-DE-P12-0111 | Process and Safety Engineering - 38 Deleverables | 0 |  | 18-Aug-25 A
1B-DE-P12-0101 | Piping Engineering - 43 Deleverables | 0 |  | 15-Aug-25 A
1B-DE-P12-0091 | MS-Mechanical Static - 9 Deleverables | 0 |  | 14-Aug-25 A
1B-DE-P12-0081 | Mechanical Rotating/Package - 9 Deleverables | 0 |  | 13-Aug-25 A
1B-DE-P12-0071 | Mechanical Rotating - 19 Deleverables | 0 |  | 12-Aug-25 A
1B-DE-P12-0061 | Material and Corrosion - 24 Deleverables | 0 |  | 11-Aug-25 A
1B-DE-P12-0051 | IT/TELECOM - 69 Deleverables | 0 |  | 08-Aug-25 A
1B-DE-P12-0041 | Instrument and Control System - 90 Deleverables | 0 |  | 07-Aug-25 A
1B-DE-P12-0031 | HVAC - 26 Deleverables | 0 |  | 06-Aug-25 A
1B-DE-P12-0021 | Electrical Engineering - 73 Deleverables | 0 |  | 05-Aug-25 A
1B-DE-P12-0011 | Construction - 30 Deleverables | 0 |  | 04-Aug-25 A
1B-DE-P12-0001 | Civil / Architecture / Structure - 63 Deleverables | 0 |  | 01-Aug-25 A
Package 3 |  | 511 | 27-Nov-24 A | 2026-09-25 | 2026-02-21 | 2027-07-20 | 213
Milestone |  | 467 | 11-Dec-24 A | 2026-09-25 | 2027-01-20 | 2027-01-20 | 84
General |  | 467 | 11-Dec-24 A | 2026-09-25 | 2027-01-20 | 2027-01-20 | 84
Turnaround |  | 0 | 11-Dec-24 A | 11-Dec-24 A
A40690 | Commencement of TA Engginering Works | 0 | 11-Dec-24 A
Balance of Plant |  | 467 | 11-Dec-24 A | 2026-09-25 | 2027-01-20 | 2027-01-20 | 84
A40320 | Completion of Engineering | 0 | 2026-09-25 |  |  |  | 84
A120 | Commencement of BOP Engineering Works | 0 | 11-Dec-24 A |  | 46407
General / Common |  | 40 | 27-Nov-24 A | 21-Jan-25 A | 46108 | 46108
MSE1300 | Site Survey & Data Collection / FEED Verification | 40 | 27-Nov-24 A | 21-Jan-25 A | 46108 | 46108
Project Management |  | 498 | 04-Dec-24 A | 2026-06-16 | 2026-02-21 | 2027-07-20 | 285
Preliminaries |  | 32 | 04-Dec-24 A | 23-May-25 A | 46074 | 46108
A40360 | Site Visit Report Before TA | 6 | 09-Jan-25 A | 16-Jan-25 A | 46074 | 46074
A40350 | Site Visit for TA Activities (CSA, Piping) | 6 | 09-Jan-25 A | 16-Jan-25 A | 46083 | 46083
A53340 | Site Visit for BOP | 6 | 25-Dec-24 A | 31-Dec-24 A | 46083 | 46083
A53330 | Medicals and CICPA Passes | 16 | 05-Dec-24 A | 24-Dec-24 A | 46083 | 46083
A53320 | Receipt of Source Data | 8 | 05-Dec-24 A | 23-May-25 A | 46108 | 46108
A53290 | LOA Request | 8 | 05-Dec-24 A | 13-Dec-24 A | 46108 | 46108
A53280 | Engineering Subcontractor KOM | 1 | 04-Dec-24 A | 04-Dec-24 A | 46074 | 46074
TA related Inputs |  | 492 | 12-Dec-24 A | 2026-06-16 | 2026-02-21 | 2027-07-20 | 285
TA Phase |  | 202 | 12-Dec-24 A | 22-Apr-25 A | 46074 | 46108
A28140 | Receipt of Approved Topo, UG & geotechnical investigation report | 1 | 08-Apr-25 A | 22-Apr-25 A | 46083 | 46083
A40340 | Receipt of Approved Electrical Site Adequacy Report | 1 | 12-Feb-25 A | 13-Feb-25 A | 46108 | 46108
A40330 | Receipt of Approved ICT Site Adequacy Report | 1 | 12-Feb-25 A | 13-Feb-25 A | 46108 | 46108
A55740 | Receipt of HSE third party offers by RAD (Descon) | 1 | 12-Dec-24 A | 12-Dec-24 A | 46074 | 46074
Vendor Offer Receipt (to enable Eng Subcon to perform TBE) |  | 23 | 09-Jan-25 A | 15-Jul-25 A
Piping |  | 8 | 03-Feb-25 A | 24-Feb-25 A
A53570 | Piping Speciality Items_All Technical Vendor Offers Receipt | 0 |  | 24-Feb-25 A
A53590 | Rigid Struts_All Technical Vendor Offers Receipt | 0 |  | 17-Feb-25 A
A53580 | Spring Hangers_All Technical Vendor Offers Receipt | 0 |  | 21-Feb-25 A
A53560 | Manual Valves_All Technical Vendor Offers Receipt | 0 |  | 11-Feb-25 A
A53550 | Piping Bulk_All Technical Vendor Offers Receipt | 0 |  | 03-Feb-25 A
Mechanical |  | 0 | 07-Feb-25 A | 07-May-25 A
A53440 | Pressure Vessels & Internals_All Technical Vendor Offers Receipt | 0 |  | 07-Feb-25 A
A53430 | Coalscer_All Technical Vendor Offers Receipt | 0 |  | 21-Mar-25 A
A53420 | EOT Crane_All Technical Vendor Offers Receipt | 0 |  | 07-May-25 A
A53410 | Centrifugal Pump_All Technical Vendor Offers Receipt | 0 |  | 21-Mar-25 A
A53400 | Heat Exchangers_All Technical Vendor Offers Receipt | 0 |  | 14-Mar-25 A
Electrical |  | 0 | 09-Jan-25 A | 13-May-25 A
A53650 | Capacitor Bank_All Technical Vendor Offers Receipt | 0 |  | 21-Apr-25 A
A53640 | DC UPS_All Technical Vendor Offers Receipt | 0 |  | 21-Feb-25 A
A53630 | AC UPS_All Technical Vendor Offers Receipt | 0 |  | 22-Jan-25 A
A53690 | LV Variable Frequency Drive_All Technical Vendor Offers Receipt | 0 |  | 21-Feb-25 A
A53680 | Emergency Diesel Generator Set_All Technical Vendor Offers Receipt | 0 |  | 22-Jan-25 A
A53670 | Neutral Grounding Resistor_All Technical Vendor Offers Receipt | 0 |  | 17-Jan-25 A
A53660 | Power, Control And Earthing Cables_All Technical Vendor Offers Receipt | 0 |  | 13-May-25 A
A53620 | LV Switchgear_All Technical Vendor Offers Receipt | 0 |  | 28-Feb-25 A
A53610 | 11KV Switchgear_All Technical Vendor Offers Receipt | 0 |  | 06-Mar-25 A
A53600 | Transformer (Power And Distribution)_All Technical Vendor Offers Receipt | 0 |  | 09-Jan-25 A
Instrumentation & Controls |  | 0 | 23-Apr-25 A | 15-Jul-25 A
A53750 | Fire Detection System & LFCP_All Technical Vendor Offers Receipt | 0 |  | 12-Jun-25 A
A53730 | Junction Boxes_All Technical Vendor Offers Receipt | 0 |  | 05-Jul-25 A
A53720 | Instrument Cables_All Technical Vendor Offers Receipt | 0 |  | 05-Jul-25 A
A26010 | Rotameter_All Technical Vendor Offers Receipt | 0 |  | 01-May-25 A
A26000 | ESD Valves_All Technical Vendor Offers Receipt | 0 |  | 30-Apr-25 A
A25990 | Motor Operated Valves_All Technical Vendor Offers Receipt | 0 |  | 27-Apr-25 A
A25970 | Fire & Gas Detectors_All Technical Vendor Offers Receipt | 0 |  | 05-Jul-25 A
A25950 | Level Gauges (Magnetic Type)_All Technical Vendor Offers Receipt | 0 |  | 23-Apr-25 A
A25930 | Temperature Gauges / Pressure Gauges_All Technical Vendor Offers Receipt | 0 |  | 30-Apr-25 A
A25920 | Temperature Element / Thermowell_All Technical Vendor Offers Receipt | 0 |  | 07-May-25 A
A25910 | Flow Element (Venturi Tube)_All Technical Vendor Offers Receipt | 0 |  | 30-Apr-25 A
A53700 | Electronic Transmitters_All Technical Vendor Offers Receipt | 0 |  | 28-Apr-25 A
A53740 | ICSS System_All Technical Vendor Offers Receipt | 0 |  | 24-Apr-25 A
A25980 | Level Transmitters (GWR type)_All Technical Vendor Offers Receipt | 0 |  | 28-Apr-25 A
A25960 | Control Valves_All Technical Vendor Offers Receipt | 0 |  | 27-Apr-25 A
A25940 | Analyzers_All Technical Vendor Offers Receipt | 0 |  | 15-Jul-25 A
A53710 | Flow Element (Orifice Plate)_All Technical Vendor Offers Receipt | 0 |  | 29-Apr-25 A
Telecom |  | 0 | 26-Apr-25 A | 22-May-25 A
A53770 | Telecom Cables_All Technical Vendor Offers Receipt | 0 |  | 22-May-25 A
A53760 | Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_All Technical Vendor Offers Receipt | 0 |  | 26-Apr-25 A
HVAC |  | 0 | 03-Jun-25 A | 03-Jun-25 A
A53780 | HVAC Equipments_All Technical Vendor Offers Receipt | 0 |  | 03-Jun-25 A
Ist Issuance of Vendor Data Receipt-1 |  | 354 | 03-Feb-25 A | 2026-05-22 | 2026-03-19 | 2027-07-06 | 292
Piping |  | 73 | 24-Mar-25 A | 2026-05-22 | 2026-05-15 | 2027-06-28 | 285
A53820 | Spring Hangers_1st issuance of Vendor Data Receipt | 0 |  | 2026-05-22 |  |  | 238
A53830 | Rigid Struts_1st issuance of Vendor Data Receipt | 0 |  | 24-Mar-25 A
A53800 | Manual Valves_1st issuance of Vendor Data Receipt | 0 |  | 2026-02-20 |  | 2027-06-28 | 61
A53790 | Piping Bulk_1st issuance of Vendor Data Receipt | 0 |  | 2026-02-20 |  | 2026-05-15 | 351
A53810 | Piping Speciality Items_1st issuance of Vendor Data Receipt | 0 |  | 05-Aug-25 A |  | 46499
Mechanical |  | 116 | 27-Aug-25 A | 2026-02-27 | 2027-06-28 | 2027-06-28 | 346
A53530 | Coalscer_1st issuance of Vendor Data Receipt | 0 |  | 2026-02-27 |  |  | 346
A53520 | EOT Crane_1st issuance of Vendor Data Receipt | 0 |  | 04-Nov-25 A
A53510 | Centrifugal Pump_1st issuance of Vendor Data Receipt | 0 |  | 30-Oct-25 A
A28780 | PSA Unit_1st issuance of Vendor Data Receipt | 0 |  | 09-Sep-25 A
A28770 | Compressors (FG & OG)_1st issuance of Vendor Data Receipt | 0 |  | 27-Aug-25 A
A53540 | Pressure Vessels & Internals_1st issuance of Vendor Data Receipt | 0 |  | 02-Sep-25 A
A53500 | Heat Exchangers_1st issuance of Vendor Data Receipt | 0 |  | 02-Sep-25 A |  | 46566
Electrical |  | 0 | 2026-02-20 | 2026-02-20 | 2026-03-19 | 2027-06-28 | 351
A53930 | LV Variable Frequency Drive_1st issuance of Vendor Data Receipt | 0 |  | 2026-02-20 |  | 2026-11-23 | 351
A53920 | Emergency Diesel Generator Set_1st issuance of Vendor Data Receipt | 0 |  | 2026-02-20 |  | 2027-06-28 | 239
A53910 | Neutral Grounding Resistor_1st issuance of Vendor Data Receipt | 0 |  | 2026-02-20 |  | 2027-06-28 | 351
A53900 | Power, Control And Earthing Cables_1st issuance of Vendor Data Receipt | 0 |  | 2026-02-20 |  | 2027-06-28 | 351
A53890 | Capacitor Bank_1st issuance of Vendor Data Receipt | 0 |  | 2026-02-20 |  | 2026-03-19 | 351
A53880 | DC UPS_1st issuance of Vendor Data Receipt | 0 |  | 2026-02-20 |  | 2027-06-28 | 20
A53870 | AC UPS_1st issuance of Vendor Data Receipt | 0 |  | 2026-02-20 |  | 2027-06-28 | 351
A53860 | LV Switchgear_1st issuance of Vendor Data Receipt | 0 |  | 2026-02-20 |  | 2027-06-28 | 351
A53850 | 11KV Switchgear_1st issuance of Vendor Data Receipt | 0 |  | 2026-02-20 |  | 2027-01-20 | 351
A53840 | Transformer (Power And Distribution)_1st issuance of Vendor Data Receipt | 0 |  | 2026-02-20 |  | 2027-06-28 | 196
Instrumentation & Controls |  | 354 | 03-Feb-25 A | 2026-03-27 | 2026-03-19 | 2027-07-06 | 332
A53990 | Analyzers_1st issuance of Vendor Data Receipt | 0 |  | 03-Feb-25 A
A53940 | Electronic Transmitters_1st issuance of Vendor Data Receipt | 0 |  | 2026-03-27 |  |  | 325
A54020 | Fire & Gas Detectors_1st issuance of Vendor Data Receipt | 0 |  | 17-Mar-25 A
A54080 | Junction Boxes_1st issuance of Vendor Data Receipt | 0 |  | 2026-03-12 |  |  | 343
A53970 | Temperature Element / Thermowell_1st issuance of Vendor Data Receipt | 0 |  | 18-Mar-25 A
A54100 | Fire Detection System & LFCP_1st issuance of Vendor Data Receipt | 0 |  | 2026-02-20 |  |  | 20
A54090 | ICSS System_1st issuance of Vendor Data Receipt | 0 |  | 2026-02-20 |  | 2027-06-28 | 351
A54050 | ESD Valves_1st issuance of Vendor Data Receipt | 0 |  | 2026-02-20 |  | 2027-06-28 | 351
A54040 | Motor Operated Valves_1st issuance of Vendor Data Receipt | 0 |  | 2026-02-20 |  | 2027-06-28 | 351
A54030 | Level Transmitters (GWR type)_1st issuance of Vendor Data Receipt | 0 |  | 2026-02-20 |  | 2027-06-28 | 351
A54010 | Control Valves_1st issuance of Vendor Data Receipt | 0 |  | 2026-02-20 |  | 2027-06-28 | 351
A54000 | Level Gauges (Magnetic Type)_1st issuance of Vendor Data Receipt | 0 |  | 2026-02-20 |  | 2027-06-28 | 351
A53960 | Flow Element (Venturi Tube)_1st issuance of Vendor Data Receipt | 0 |  | 2026-02-20 |  | 2027-06-28 | 351
A53950 | Flow Element (Orifice Plate)_1st issuance of Vendor Data Receipt | 0 |  | 2026-02-20 |  | 2027-06-28 | 351
A53980 | Temperature Gauges / Pressure Gauges_1st issuance of Vendor Data Receipt | 0 |  | 29-May-25 A |  | 46100
A54070 | Instrument Cables_1st issuance of Vendor Data Receipt | 0 |  | 30-Nov-25 A |  | 46574
A54060 | Rotameter_1st issuance of Vendor Data Receipt | 0 |  | 29-May-25 A |  | 46566
Telecom |  | 2 | 18-Mar-25 A | 2026-02-20 | 2027-06-28 | 2027-06-28 | 351
A54120 | Telecom Cables_1st issuance of Vendor Data Receipt | 0 |  | 18-Mar-25 A
A54110 | Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_1st issuance of Vendor Data Receipt | 0 |  | 2026-02-20 |  | 2027-06-28 | 351
HVAC |  | 0 | 2026-02-20 | 2026-02-20 | 2027-06-28 | 2027-06-28 | 351
A54130 | HVAC Equipments_1st issuance of Vendor Data Receipt | 0 |  | 2026-02-20 |  | 2027-06-28 | 351
Approved Vender Data Receipt |  | 291 | 04-Mar-25 A | 2026-06-16 | 2026-03-19 | 2027-07-20 | 285
Piping |  | 83 | 26-Aug-25 A | 2026-06-16 | 2026-03-19 | 2027-07-20 | 285
A54170 | Spring Hangers_Approved Vendor Data Receipt | 0 |  | 2026-06-16 |  |  | 238
A54140 | Piping Bulk_Approved Vendor Data Receipt | 0 |  | 2026-03-16 |  | 2026-03-19 | 351
A54150 | Manual Valves_Approved Vendor Data Receipt | 0 |  | 2026-03-05 |  | 2026-05-29 | 61
A54160 | Piping Speciality Items_Approved Vendor Data Receipt | 0 |  | 26-Aug-25 A |  | 46588
A54180 | Rigid Struts_Approved Vendor Data Receipt | 0 |  | 2026-02-20 |  | 2027-05-14 | 20
Mechanical |  | 130 | 10-Jun-25 A | 2026-03-24 | 2026-03-19 | 2027-07-20 | 346
A53480 | Coalscer_Approved Vendor Data Receipt | 0 |  | 2026-03-24 |  |  | 346
A53470 | EOT Crane_Approved Vendor Data Receipt | 0 |  | 2026-02-20 |  |  | 20
A53460 | Centrifugal Pump_Approved Vendor Data Receipt | 0 |  | 2026-02-20 |  |  | 20
A28150 | Compressors (FG & OG)_Approved Vendor Data Receipt | 0 |  | 19-Sep-25 A
A55640 | PSA Unit_Approved Vendor Data Receipt | 0 |  | 10-Jun-25 A |  | 46100
A53490 | Pressure Vessels & Internals_Approved Vendor Data Receipt | 0 |  | 02-Sep-25 A |  | 46100
A53450 | Heat Exchangers_Approved Vendor Data Receipt | 0 |  | 02-Sep-25 A |  | 46588
Electrical |  | 17 | 2026-02-20 | 2026-03-16 | 2026-03-19 | 2027-07-20 | 351
A54280 | LV Variable Frequency Drive_Approved Vendor Data Receipt | 0 |  | 2026-03-16 |  | 2026-03-19 | 351
A54260 | Neutral Grounding Resistor_Approved Vendor Data Receipt | 0 |  | 2026-03-16 |  | 2027-01-20 | 351
A54250 | Power, Control And Earthing Cables_Approved Vendor Data Receipt | 0 |  | 2026-03-16 |  | 2027-07-20 | 351
A54240 | Capacitor Bank_Approved Vendor Data Receipt | 0 |  | 2026-03-16 |  | 2026-12-22 | 351
A54220 | AC UPS_Approved Vendor Data Receipt | 0 |  | 2026-03-16 |  | 2027-07-20 | 351
A54210 | LV Switchgear_Approved Vendor Data Receipt | 0 |  | 2026-03-16 |  | 2027-07-20 | 351
A54200 | 11KV Switchgear_Approved Vendor Data Receipt | 0 |  | 2026-03-16 |  | 2027-07-20 | 351
A54190 | Transformer (Power And Distribution)_Approved Vendor Data Receipt | 0 |  | 2026-03-16 |  | 2027-07-20 | 201
A55650 | Notice to proceed - All Electrical equipment footprint & load data to freeze Electrical building Equipment layout | 0 |  | 2026-02-20 |  | 2027-07-20 | 368
A54270 | Emergency Diesel Generator Set_Approved Vendor Data Receipt | 0 |  | 2026-02-20 |  | 2027-07-20 | 239
A54230 | DC UPS_Approved Vendor Data Receipt | 0 |  | 2026-02-20 |  | 2027-07-20 | 20
Instrumentation & Controls |  | 291 | 04-Mar-25 A | 2026-04-21 | 2026-03-19 | 2027-07-20 | 325
A54340 | Analyzers_Approved Vendor Data Receipt | 0 |  | 04-Mar-25 A
A54290 | Electronic Transmitters_Approved Vendor Data Receipt | 0 |  | 2026-04-21 |  |  | 325
A54370 | Fire & Gas Detectors_Approved Vendor Data Receipt | 0 |  | 09-Apr-25 A
A54430 | Junction Boxes_Approved Vendor Data Receipt | 0 |  | 2026-03-26 |  |  | 343
A54440 | ICSS System_Approved Vendor Data Receipt | 0 |  | 2026-03-16 |  |  | 351
A54400 | ESD Valves_Approved Vendor Data Receipt | 0 |  | 2026-03-16 |  | 2026-03-19 | 351
A54390 | Motor Operated Valves_Approved Vendor Data Receipt | 0 |  | 2026-03-16 |  | 2026-03-19 | 351
A54380 | Level Transmitters (GWR type)_Approved Vendor Data Receipt | 0 |  | 2026-03-16 |  | 2026-03-19 | 351
A54360 | Control Valves_Approved Vendor Data Receipt | 0 |  | 2026-03-16 |  | 2027-07-20 | 351
A54350 | Level Gauges (Magnetic Type)_Approved Vendor Data Receipt | 0 |  | 2026-03-16 |  | 2027-07-20 | 351
A54310 | Flow Element (Venturi Tube)_Approved Vendor Data Receipt | 0 |  | 2026-03-16 |  | 2027-07-20 | 351
A54300 | Flow Element (Orifice Plate)_Approved Vendor Data Receipt | 0 |  | 2026-03-16 |  | 2027-07-20 | 351
A54330 | Temperature Gauges / Pressure Gauges_Approved Vendor Data Receipt | 0 |  | 29-May-25 A |  | 46588
A54410 | Rotameter_Approved Vendor Data Receipt | 0 |  | 23-May-25 A |  | 46588
A54450 | Fire Detection System & LFCP_Approved Vendor Data Receipt | 0 |  | 2026-02-20 |  | 2027-07-20 | 20
A54420 | Instrument Cables_Approved Vendor Data Receipt | 0 |  | 2026-02-20 |  | 2027-07-20 | 20
A54320 | Temperature Element / Thermowell_Approved Vendor Data Receipt | 0 |  | 2026-02-20 |  | 2027-07-20 | 20
A55660 | Notice to proceed - All ICT equipment footprint & load data to freeze SIS Equipment layout | 0 |  | 23-Jun-25 A |  | 46588
Telecom |  | 17 | 2026-02-20 | 2026-03-16 | 2026-03-19 | 2027-07-20 | 351
A54460 | Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_Approved Vendor Data Receipt | 0 |  | 2026-03-16 |  | 2026-03-19 | 351
A54470 | Telecom Cables_Approved Vendor Data Receipt | 0 |  | 2026-02-20 |  | 2027-07-20 | 20
HVAC |  | 0 | 2026-03-16 | 2026-03-16 | 2027-07-20 | 2027-07-20 | 351
A54480 | HVAC Equipments_Approved Vendor Data Receipt | 0 |  | 2026-03-16 |  | 2027-07-20 | 351
Workshops / Studies / Model Reviews |  | 182 | 05-May-25 A | 2026-03-16 | 2026-03-02 | 2026-11-23 | 179
A53250 | PHSER-3 | 1 | 2026-03-13 | 2026-03-16 | 2026-03-02 | 2026-03-02 | 179
A53390 | 90% Model Review | 6 | 2026-02-26 | 2026-03-06 | 2026-03-02 | 2026-03-02 | 15
A53270 | Energy Review | 1 | 2026-02-23 | 2026-02-24 | 2026-03-02 | 2026-03-02 | 18
A55730 | Constructability Review | 1 | 27-Aug-25 A | 27-Aug-25 A | 46083 | 46083
A55720 | SIMOPS | 1 | 28-Aug-25 A | 28-Aug-25 A | 46114 | 46114
A55710 | ALARP Demonstration | 1 | 2026-02-20 | 2026-02-23 | 2026-03-02 | 2026-03-02 | 24
A55700 | E-HAZOP | 1 | 2026-02-20 | 2026-02-23 | 2026-03-02 | 2026-03-02 | 18
A55680 | HSEIA Screening | 1 | 01-Jan-26 A | 06-Jan-26 A | 46083 | 46083
A53380 | 60% Model Review | 17 | 08-Sep-25 A | 18-Sep-25 A | 46100 | 46100
A53260 | SIL/LOPA | 2 | 17-Aug-25 A | 20-Aug-25 A | 46100 | 46100
A55690 | Bow-Tie | 1 | 12-Aug-25 A | 12-Aug-25 A | 46083 | 46083
A53360 | Plot Plan Review | 1 | 13-May-25 A | 21-May-25 A | 46114 | 46114
A25340 | ISD Workshop | 1 | 04-Jul-25 A | 04-Jul-25 A | 46098 | 46099
A53350 | Design Review | 3 | 05-May-25 A | 09-May-25 A | 46107 | 46108
A25330 | PHA (HAZID/ENVID/OHID) | 5 | 03-Jul-25 A | 03-Jul-25 A | 46099 | 46100
A25350 | HAZOP | 7 | 08-Jul-25 A | 20-Jul-25 A | 46100 | 46108
A53370 | 30% Model Review | 1 | 13-May-25 A | 16-May-25 A | 46346 | 46349
Turnaround (TA) |  | 208 | 27-Nov-24 A | 21-Jun-25 A | 46074 | 46108
TA - Engineering Workpack |  | 202 | 27-Nov-24 A | 12-Apr-25 A | 46108 | 46108
B1-DE-TA-TAD-0001 | Verify TA Dossier & Provid List of Missing Materials to EPC Contractor | 17 | 07-Jan-25 A | 27-Mar-25 A | 46108 | 46108
B1-DE-TA-TAD-0002 | Engineering Support During Pre-TA & TA Phase | 53 | 17-Jan-25 A | 12-Apr-25 A
Piping Driven - Workpack |  | 28 | 27-Nov-24 A | 10-Feb-25 A | 46108 | 46108
Preliminary Workpack |  | 5 | 27-Nov-24 A | 13-Jan-25 A | 46108 | 46108
B1-DE-TA-PIP-0052 | Workpack Nos. 41 to 52 - Preliminary Issuance | 1 | 23-Dec-24 A | 13-Jan-25 A | 46108 | 46108
B1-DE-TA-PIP-0051 | Workpack Nos. 41 to 52 - Preliminary Issuance | 1 | 23-Dec-24 A | 13-Jan-25 A | 46108 | 46108
B1-DE-TA-PIP-0050 | Workpack Nos. 41 to 52 - Preliminary Issuance | 1 | 23-Dec-24 A | 13-Jan-25 A | 46108 | 46108
B1-DE-TA-PIP-0049 | Workpack Nos. 41 to 52 - Preliminary Issuance | 1 | 23-Dec-24 A | 13-Jan-25 A | 46108 | 46108
B1-DE-TA-PIP-0048 | Workpack Nos. 41 to 52 - Preliminary Issuance | 1 | 23-Dec-24 A | 13-Jan-25 A | 46108 | 46108
B1-DE-TA-PIP-0047 | Workpack Nos. 41 to 52 - Preliminary Issuance | 1 | 23-Dec-24 A | 13-Jan-25 A | 46108 | 46108
B1-DE-TA-PIP-0046 | Workpack Nos. 41 to 52 - Preliminary Issuance | 1 | 23-Dec-24 A | 13-Jan-25 A | 46108 | 46108
B1-DE-TA-PIP-0045 | Workpack Piping Nos. 0003 Preliminary Issuance | 1 | 23-Dec-24 A | 13-Jan-25 A | 46108 | 46108
B1-DE-TA-PIP-0044 | Workpack Piping Nos. 0042 Preliminary Issuance | 1 | 23-Dec-24 A | 13-Jan-25 A | 46108 | 46108
B1-DE-TA-PIP-0043 | Workpack Piping Nos. 0041 Preliminary Issuance | 1 | 23-Dec-24 A | 13-Jan-25 A | 46108 | 46108
B1-DE-TA-PIP-0042 | Workpack Piping Nos. 0040 Preliminary Issuance | 1 | 17-Dec-24 A | 07-Jan-25 A | 46108 | 46108
B1-DE-TA-PIP-0041 | Workpack Piping Nos. 0039 Preliminary Issuance | 1 | 17-Dec-24 A | 07-Jan-25 A | 46108 | 46108
B1-DE-TA-PIP-0040 | Workpack Piping Nos. 0038 Preliminary Issuance | 1 | 17-Dec-24 A | 07-Jan-25 A | 46108 | 46108
B1-DE-TA-PIP-0039 | Workpack Piping Nos. 0037 Preliminary Issuance | 1 | 17-Dec-24 A | 07-Jan-25 A | 46108 | 46108
B1-DE-TA-PIP-0038 | Workpack Piping Nos. 0036 Preliminary Issuance | 1 | 17-Dec-24 A | 07-Jan-25 A | 46108 | 46108
B1-DE-TA-PIP-0037 | Workpack Piping Nos. 0035 Preliminary Issuance | 1 | 17-Dec-24 A | 07-Jan-25 A | 46108 | 46108
B1-DE-TA-PIP-0036 | Workpack Piping Nos. 0034 Preliminary Issuance | 1 | 17-Dec-24 A | 07-Jan-25 A | 46108 | 46108
B1-DE-TA-PIP-0035 | Workpack Piping Nos. 0033 Preliminary Issuance | 1 | 17-Dec-24 A | 07-Jan-25 A | 46108 | 46108
B1-DE-TA-PIP-0034 | Workpack Piping Nos. 0032 Preliminary Issuance | 1 | 17-Dec-24 A | 07-Jan-25 A | 46108 | 46108
B1-DE-TA-PIP-0033 | Workpack Piping Nos. 0031 Preliminary Issuance | 1 | 17-Dec-24 A | 07-Jan-25 A | 46108 | 46108
B1-DE-TA-PIP-0032 | Workpack Piping Nos. 0030 Preliminary Issuance | 1 | 17-Dec-24 A | 07-Jan-25 A | 46108 | 46108
B1-DE-TA-PIP-0031 | Workpack Piping Nos. 0029 Preliminary Issuance | 1 | 27-Nov-24 A | 18-Dec-24 A | 46108 | 46108
B1-DE-TA-PIP-0030 | Workpack Piping Nos. 0028 Preliminary Issuance | 1 | 27-Nov-24 A | 18-Dec-24 A | 46108 | 46108
B1-DE-TA-PIP-0029 | Workpack Piping Nos. 0027 Preliminary Issuance | 1 | 27-Nov-24 A | 18-Dec-24 A | 46108 | 46108
B1-DE-TA-PIP-0028 | Workpack Piping Nos. 0026 Preliminary Issuance | 1 | 27-Nov-24 A | 18-Dec-24 A | 46108 | 46108
B1-DE-TA-PIP-0027 | Workpack Piping Nos. 0025 Preliminary Issuance | 1 | 27-Nov-24 A | 18-Dec-24 A | 46108 | 46108
B1-DE-TA-PIP-0026 | Workpack Piping Nos. 0026 Preliminary Issuance | 1 | 27-Nov-24 A | 18-Dec-24 A | 46108 | 46108
B1-DE-TA-PIP-0025 | Workpack Piping Nos. 0025 Preliminary Issuance | 1 | 27-Nov-24 A | 18-Dec-24 A | 46108 | 46108
B1-DE-TA-PIP-0024 | Workpack Piping Nos. 0024 Preliminary Issuance | 1 | 27-Nov-24 A | 18-Dec-24 A | 46108 | 46108
B1-DE-TA-PIP-0023 | Workpack Piping Nos. 0023 Preliminary Issuance | 1 | 27-Nov-24 A | 18-Dec-24 A | 46108 | 46108
B1-DE-TA-PIP-0022 | Workpack Piping Nos. 0022 Preliminary Issuance | 1 | 27-Nov-24 A | 18-Dec-24 A | 46108 | 46108
B1-DE-TA-PIP-0021 | Workpack Piping Nos. 0021 Preliminary Issuance | 1 | 27-Nov-24 A | 18-Dec-24 A | 46108 | 46108
B1-DE-TA-PIP-0020 | Workpack Piping Nos. 0020 Preliminary Issuance | 1 | 27-Nov-24 A | 18-Dec-24 A | 46108 | 46108
B1-DE-TA-PIP-0019 | Workpack Piping Nos. 0019 Preliminary Issuance | 1 | 27-Nov-24 A | 18-Dec-24 A | 46108 | 46108
B1-DE-TA-PIP-0018 | Workpack Piping Nos. 0018 Preliminary Issuance | 1 | 27-Nov-24 A | 18-Dec-24 A | 46108 | 46108
B1-DE-TA-PIP-0017 | Workpack Piping Nos. 0017 Preliminary Issuance | 1 | 27-Nov-24 A | 18-Dec-24 A | 46108 | 46108
B1-DE-TA-PIP-0016 | Workpack Piping Nos. 0016 Preliminary Issuance | 1 | 27-Nov-24 A | 18-Dec-24 A | 46108 | 46108
B1-DE-TA-PIP-0015 | Workpack Piping Nos. 0015 Preliminary Issuance | 1 | 27-Nov-24 A | 18-Dec-24 A | 46108 | 46108
B1-DE-TA-PIP-0014 | Workpack Piping Nos. 0014 Preliminary Issuance | 1 | 27-Nov-24 A | 18-Dec-24 A | 46108 | 46108
B1-DE-TA-PIP-0013 | Workpack Piping Nos. 0013 Preliminary Issuance | 1 | 27-Nov-24 A | 18-Dec-24 A | 46108 | 46108
B1-DE-TA-PIP-0012 | Workpack Piping Nos. 0012 Preliminary Issuance | 1 | 27-Nov-24 A | 18-Dec-24 A | 46108 | 46108
B1-DE-TA-PIP-0011 | Workpack Piping Nos. 0011 Preliminary Issuance | 1 | 27-Nov-24 A | 18-Dec-24 A | 46108 | 46108
B1-DE-TA-PIP-0010 | Workpack Piping Nos. 0010 Preliminary Issuance | 1 | 27-Nov-24 A | 18-Dec-24 A | 46108 | 46108
B1-DE-TA-PIP-0009 | Workpack Piping Nos. 0009 Preliminary Issuance | 1 | 27-Nov-24 A | 18-Dec-24 A | 46108 | 46108
B1-DE-TA-PIP-0008 | Workpack Piping Nos. 0008 Preliminary Issuance | 1 | 27-Nov-24 A | 18-Dec-24 A | 46108 | 46108
B1-DE-TA-PIP-0007 | Workpack Piping Nos. 0007 Preliminary Issuance | 1 | 27-Nov-24 A | 18-Dec-24 A | 46108 | 46108
B1-DE-TA-PIP-0006 | Workpack Piping Nos. 0006 Preliminary Issuance | 1 | 27-Nov-24 A | 18-Dec-24 A | 46108 | 46108
B1-DE-TA-PIP-0005 | Workpack Piping Nos. 0005 Preliminary Issuance | 1 | 27-Nov-24 A | 18-Dec-24 A | 46108 | 46108
B1-DE-TA-PIP-0004 | Workpack Piping Nos. 0004 Preliminary Issuance | 1 | 27-Nov-24 A | 18-Dec-24 A | 46108 | 46108
B1-DE-TA-PIP-0003 | Workpack Piping Nos. 0003 Preliminary Issuance | 1 | 27-Nov-24 A | 18-Dec-24 A | 46108 | 46108
B1-DE-TA-PIP-0002 | Workpack Piping Nos. 0002 Preliminary Issuance | 1 | 27-Nov-24 A | 18-Dec-24 A | 46108 | 46108
B1-DE-TA-PIP-0001 | Workpack Piping Nos. 0001 Preliminary Issuance | 1 | 27-Nov-24 A | 18-Dec-24 A | 46108 | 46108
Final Workpack |  | 10 | 19-Dec-24 A | 10-Feb-25 A | 46108 | 46108
A40470 | Workpack Nos. 41 to 52 - Final Issuance | 2 | 24-Dec-24 A | 10-Feb-25 A | 46108 | 46108
A40460 | Workpack Nos. 31 to 40 - Final Issuance | 2 | 08-Jan-25 A | 06-Feb-25 A | 46108 | 46108
A40450 | Workpack Nos. 21 to 30 - Final Issuance | 2 | 08-Jan-25 A | 06-Feb-25 A | 46108 | 46108
A40440 | Workpack Nos. 11 to 20 - Final Issuance | 2 | 19-Dec-24 A | 15-Jan-25 A | 46108 | 46108
A40430 | Workpack Nos. 1 to 10 - Final Issuance | 2 | 19-Dec-24 A | 15-Jan-25 A | 46108 | 46108
ICT Driven - Workpack |  | 40 | 02-Jan-25 A | 20-Jan-25 A | 46108 | 46108
Preliminary Workpack |  | 5 | 02-Jan-25 A | 16-Jan-25 A | 46108 | 46108
A40520 | Workpack Nos. 68 to 70 - Preliminary Issuance | 1 | 06-Jan-25 A | 16-Jan-25 A | 46108 | 46108
A40510 | Workpack Nos. 64 to 67 - Preliminary Issuance | 1 | 06-Jan-25 A | 16-Jan-25 A | 46108 | 46108
A40500 | Workpack Nos. 60 to 63 - Preliminary Issuance | 1 | 02-Jan-25 A | 07-Jan-25 A | 46108 | 46108
A40490 | Workpack Nos. 57 to 59 - Preliminary Issuance | 1 | 02-Jan-25 A | 07-Jan-25 A | 46108 | 46108
A40480 | Workpack Nos. 53 to 56 - Preliminary Issuance | 1 | 02-Jan-25 A | 07-Jan-25 A | 46108 | 46108
Final Workpack |  | 10 | 08-Jan-25 A | 20-Jan-25 A | 46108 | 46108
A40570 | Workpack Nos. 68 to 70 - Final Issuance | 2 | 17-Jan-25 A | 20-Jan-25 A | 46108 | 46108
A40560 | Workpack Nos. 64 to 67 - Final Issuance | 2 | 17-Jan-25 A | 20-Jan-25 A | 46108 | 46108
A40550 | Workpack Nos. 60 to 63 - Final Issuance | 2 | 08-Jan-25 A | 16-Jan-25 A | 46108 | 46108
A40540 | Workpack Nos. 57 to 59 - Final Issuance | 2 | 08-Jan-25 A | 16-Jan-25 A | 46108 | 46108
A40530 | Workpack Nos. 53 to 56 - Final Issuance | 2 | 08-Jan-25 A | 16-Jan-25 A | 46108 | 46108
Civil/Structural/Architectural Driven - Workpack |  | 21 | 31-Dec-24 A | 29-Jan-25 A | 46108 | 46108
Preliminary Workpack |  | 5 | 31-Dec-24 A | 06-Jan-25 A | 46108 | 46108
A40590 | Workpack Nos. 72 - Preliminary Issuance | 2 | 01-Jan-25 A | 06-Jan-25 A | 46108 | 46108
A40580 | Workpack No. 71 - Preliminary Issuance | 3 | 31-Dec-24 A | 03-Jan-25 A | 46108 | 46108
Final Workpack |  | 5 | 04-Jan-25 A | 29-Jan-25 A | 46108 | 46108
A40610 | Workpack No. 72 - Final Issuance | 2 | 29-Jan-25 A | 29-Jan-25 A | 46108 | 46108
A40600 | Workpack No. 71 - Final Issuance | 3 | 04-Jan-25 A | 16-Jan-25 A | 46108 | 46108
Electrical Driven - Workpack |  | 41 | 27-Dec-24 A | 17-Jan-25 A | 46108 | 46108
Preliminary Workpack |  | 5 | 27-Dec-24 A | 02-Jan-25 A | 46108 | 46108
A40670 | Workpack Nos. 75 - Preliminary Issuance | 1 | 27-Dec-24 A | 02-Jan-25 A | 46108 | 46108
A40660 | Workpack Nos. 74 - Preliminary Issuance | 2 | 27-Dec-24 A | 02-Jan-25 A | 46108 | 46108
A40650 | Workpack Nos. 73 - Preliminary Issuance | 2 | 27-Dec-24 A | 02-Jan-25 A | 46108 | 46108
Final Workpack |  | 11 | 03-Jan-25 A | 17-Jan-25 A | 46108 | 46108
A40640 | Workpack No. 75 - Final Issuance | 3 | 03-Jan-25 A | 17-Jan-25 A | 46108 | 46108
A40630 | Workpack No. 74 - Final Issuance | 5 | 03-Jan-25 A | 17-Jan-25 A | 46108 | 46108
A40620 | Workpack No. 73 - Final Issuance | 3 | 03-Jan-25 A | 17-Jan-25 A | 46108 | 46108
Subcontracting Support |  | 108 | 01-Jan-25 A | 21-Jun-25 A | 46074 | 46108
SOW & Requisition for ICT System Modification |  | 23 | 15-Jan-25 A | 28-Feb-25 A | 46108 | 46108
A56070 | SOW & Requisition for ICT System Modification_IFD/IFC | 6 | 13-Feb-25 A | 28-Feb-25 A | 46108 | 46108
A56060 | SOW & Requisition for ICT System Modification_RCC | 16 | 31-Jan-25 A | 12-Feb-25 A | 46108 | 46108
A56050 | SOW & Requisition for ICT System Modification_IFR | 6 | 15-Jan-25 A | 30-Jan-25 A | 46108 | 46108
SOW & Requisition for Electrical System Modification |  | 23 | 07-Jan-25 A | 14-Feb-25 A | 46108 | 46108
A56100 | SOW & Requisition for Electrical System Modification_IFD/IFC | 6 | 03-Feb-25 A | 14-Feb-25 A | 46108 | 46108
A56090 | SOW & Requisition for Electrical System Modification_RCC | 16 | 23-Jan-25 A | 31-Jan-25 A | 46108 | 46108
A56080 | SOW & Requisition for Electrical System Modification_IFR | 6 | 07-Jan-25 A | 22-Jan-25 A | 46108 | 46108
SOW & Requisition for Topo & UG survey |  | 23 | 01-Jan-25 A | 05-Feb-25 A | 46074 | 46074
A28870 | SOW & Requisition for Topo & UG survey_IFD/IFC | 6 | 27-Jan-25 A | 05-Feb-25 A | 46074 | 46074
A56120 | SOW & Requisition for Topo & UG survey_RCC | 16 | 13-Jan-25 A | 24-Jan-25 A | 46074 | 46074
A56110 | SOW & Requisition for Topo & UG survey_IFR | 6 | 01-Jan-25 A | 09-Jan-25 A | 46074 | 46074
SOW & Requisition for Geotechnical investigation |  | 23 | 01-Jan-25 A | 05-Feb-25 A | 46074 | 46074
A56150 | SOW & Requisition for Geotechnical investigation_IFD/IFC | 6 | 27-Jan-25 A | 05-Feb-25 A | 46074 | 46074
A56140 | SOW & Requisition for Geotechnical investigation_RCC | 16 | 13-Jan-25 A | 24-Jan-25 A | 46074 | 46074
A56130 | SOW & Requisition for Geotechnical investigation_IFR | 6 | 01-Jan-25 A | 09-Jan-25 A | 46074 | 46074
SOW & Requisition for Third party HSE studies |  | 39 | 30-Jan-25 A | 01-Jun-25 A | 46083 | 46083
A56180 | SOW & Requisition for HSE third party studies_IFD/IFC | 17 | 28-Feb-25 A | 01-Jun-25 A | 46083 | 46083
A56170 | SOW & Requisition for HSE third party studies_RCC | 16 | 21-Feb-25 A | 27-Feb-25 A | 46083 | 46083
A56160 | SOW & Requisition for HSE third party studies_IFR | 6 | 30-Jan-25 A | 20-Feb-25 A | 46083 | 46083
Technical Bid Evaluation for Third Party HSE Studies |  | 31 | 25-Feb-25 A | 21-Jun-25 A | 46083 | 46083
A55970 | Technical Bid Evaluation for Third Party HSE Studies_IFD/IFC | 11 | 05-Jun-25 A | 21-Jun-25 A | 46083 | 46083
A55960 | Technical Bid Evaluation for Third Party HSE Studies_RCA | 16 | 19-Mar-25 A | 04-Jun-25 A | 46083 | 46083
A55950 | Technical Bid Evaluation for Third Party HSE Studies_IFR | 6 | 25-Feb-25 A | 18-Mar-25 A | 46083 | 46083
MTO Support |  | 122 | 01-Feb-25 A | 07-Mar-25 A | 46100 | 46108
A40760 | Issue Final MTO for Structural Steel Bulks | 7 | 24-Feb-25 A | 28-Feb-25 A | 46108 | 46108
A40780 | Issue Final MTO for Electrical Bulks | 6 | 17-Feb-25 A | 27-Feb-25 A | 46108 | 46108
A40750 | Issue Final MTO for Piping Bulks | 6 | 10-Feb-25 A | 19-Feb-25 A | 46108 | 46108
A40740 | Issue Preliminary MTO for Electrical Bulks | 6 | 13-Feb-25 A | 26-Feb-25 A | 46108 | 46108
A40720 | Issue Preliminary MTO for Structural Steel Bulks | 6 | 17-Feb-25 A | 28-Feb-25 A | 46108 | 46108
A40710 | Issue Preliminary MTO for Piping Bulks | 6 | 18-Feb-25 A | 28-Feb-25 A | 46100 | 46100
A40770 | Issue Final MTO for ICT Bulks | 6 | 14-Feb-25 A | 07-Mar-25 A | 46108 | 46108
A40730 | Issue Preliminary MTO for ICT Bulks | 6 | 01-Feb-25 A | 07-Feb-25 A | 46108 | 46108
Balance of Plant |  | 500 | 28-Nov-24 A | 2026-06-08 | 2026-02-21 | 2027-01-20 | 162
General |  | 371 | 28-Nov-24 A | 2026-05-14 | 2026-03-02 | 2027-01-20 | 179
Master Deliverable Register (MDR) |  | 39 | 28-Nov-24 A | 16-Jan-25 A | 46083 | 46407
A40830 | Master Deliverable Register (MDR)_IFD/IFC | 2 | 10-Jan-25 A | 16-Jan-25 A | 46083 | 46083
A40820 | Master Deliverable Register (MDR)_RCA | 16 | 03-Jan-25 A | 09-Jan-25 A | 46407 | 46407
A40810 | Master Deliverable Register (MDR)_IFA | 3 | 27-Dec-24 A | 02-Jan-25 A | 46407 | 46407
A40800 | Master Deliverable Register (MDR)_RCC | 16 | 19-Dec-24 A | 26-Dec-24 A | 46407 | 46407
A40790 | Master Deliverable Register (MDR)_IFR | 6 | 28-Nov-24 A | 19-Dec-24 A | 46407 | 46407
Planning Package / EDDR |  | 81 | 01-Jan-25 A | 13-Apr-25 A | 46407 | 46407
A40870 | Planning Package / EDDR_RCA | 58 | 30-Mar-25 A | 04-Apr-25 A | 46407 | 46407
A40880 | Planning Package / EDDR_IFD/IFC | 2 | 07-Apr-25 A | 13-Apr-25 A | 46407 | 46407
A40860 | Planning Package / EDDR_IFA | 3 | 22-Mar-25 A | 29-Mar-25 A | 46407 | 46407
A40850 | Planning Package / EDDR_RCC | 16 | 23-Jan-25 A | 21-Mar-25 A | 46407 | 46407
A40840 | Planning Package / EDDR_IFR | 6 | 01-Jan-25 A | 22-Jan-25 A | 46407 | 46407
Project Execution Plan |  | 193 | 03-Mar-25 A | 01-Sep-25 A | 46199 | 46199
A40930 | Project Execution Plan_IFD/IFC | 2 | 31-Aug-25 A | 01-Sep-25 A | 46199 | 46199
A40920 | Project Execution Plan_RCA | 6 | 31-Mar-25 A | 06-Apr-25 A | 46199 | 46199
A40900 | Project Execution Plan_RCC | 16 | 23-Mar-25 A | 29-Mar-25 A | 46199 | 46199
A40910 | Project Execution Plan_IFA | 3 | 30-Mar-25 A | 05-Apr-25 A | 46199 | 46199
A40890 | Project Execution Plan_IFR | 6 | 03-Mar-25 A | 22-Mar-25 A | 46199 | 46199
FEED Verification Report |  | 117 | 27-Mar-25 A | 15-May-25 A | 46083 | 46407
A40970 | FEED Verification Report_RCA | 16 | 01-May-25 A | 08-May-25 A | 46083 | 46083
A40980 | FEED Verification Report_IFD/IFC | 2 | 02-May-25 A | 15-May-25 A | 46083 | 46083
A40960 | FEED Verification Report_IFA | 3 | 21-Apr-25 A | 30-Apr-25 A | 46407 | 46407
A40950 | FEED Verification Report_RCC | 11 | 07-Apr-25 A | 18-Apr-25 A | 46407 | 46407
A40940 | FEED Verification Report_IFR | 6 | 27-Mar-25 A | 04-Apr-25 A | 46407 | 46407
Site Visit Report for BOP |  | 42 | 15-Mar-25 A | 20-Jun-25 A | 46083 | 46083
A41030 | Site Visit Report for BOP_IFD/IFC | 2 | 14-Jun-25 A | 20-Jun-25 A | 46083 | 46083
A41020 | Site Visit Report for BOP_RCA | 16 | 06-Apr-25 A | 13-Jun-25 A | 46083 | 46083
A41010 | Site Visit Report for BOP_IFA | 3 | 30-Mar-25 A | 05-Apr-25 A | 46083 | 46083
A41000 | Site Visit Report for BOP_RCC | 16 | 23-Mar-25 A | 29-Mar-25 A | 46083 | 46083
A40990 | Site Visit Report for BOP_IFR | 6 | 15-Mar-25 A | 22-Mar-25 A | 46083 | 46083
Project Risk Register |  | 173 | 21-Feb-25 A | 13-Sep-25 A | 46407 | 46407
A41080 | Project Risk Register_IFD/IFC | 17 | 26-Aug-25 A | 13-Sep-25 A | 46407 | 46407
A41070 | Project Risk Register_RCA | 16 | 20-Aug-25 A | 06-Sep-25 A | 46407 | 46407
A41060 | Project Risk Register_IFA | 17 | 13-Aug-25 A | 31-Aug-25 A | 46407 | 46407
A41050 | Project Risk Register_RCC | 24 | 30-Jul-25 A | 24-Aug-25 A | 46407 | 46407
A41040 | Project Risk Register_IFR | 17 | 21-Feb-25 A | 10-Jun-25 A | 46407 | 46407
Project Lesson Learnt Register |  | 137 | 09-Jan-25 A | 14-Sep-25 A | 46407 | 46407
A1920 | Project Lesson Learnt Register_IFD/IFC | 2 | 10-Sep-25 A | 14-Sep-25 A | 46407 | 46407
A1910 | Project Lesson Learnt Register_RCA | 16 | 28-Aug-25 A | 06-Sep-25 A | 46407 | 46407
A1900 | Project Lesson Learnt Register_IFA | 3 | 08-Aug-25 A | 30-Aug-25 A | 46407 | 46407
A1890 | Project Lesson Learnt Register_RCC | 16 | 01-Aug-25 A | 24-Aug-25 A | 46407 | 46407
A41090 | Project Lesson Learnt Register_IFR | 6 | 09-Jan-25 A | 10-Jun-25 A | 46407 | 46407
Criticality Rating Report |  | 127 | 21-Jun-25 A | 13-Sep-25 A | 46407 | 46407
A1970 | Criticality Rating Report_IFD/IFC | 2 | 10-Sep-25 A | 13-Sep-25 A | 46407 | 46407
A1960 | Criticality Rating Report_RCA | 16 | 20-Aug-25 A | 06-Sep-25 A | 46407 | 46407
A1950 | Criticality Rating Report_IFA | 3 | 21-Aug-25 A | 30-Aug-25 A | 46407 | 46407
A1940 | Criticality Rating Report_RCC | 16 | 08-Aug-25 A | 24-Aug-25 A | 46407 | 46407
A1930 | Criticality Rating Report_IFR | 6 | 21-Jun-25 A | 12-Jul-25 A | 46407 | 46407
Project Close Out Report |  | 38 | 2026-03-23 | 2026-05-14 | 2026-11-27 | 2027-01-20 | 179
A41140 | Project Close Out Report_IFD/IFC | 1 | 2026-05-13 | 2026-05-14 | 2026-11-27 | 2026-12-01 | 179
A41130 | Project Close Out Report_RCA | 16 | 2026-04-21 | 2026-05-13 | 2026-12-02 | 2026-12-23 | 179
A41120 | Project Close Out Report_IFA | 3 | 2026-04-16 | 2026-04-21 | 2026-12-23 | 2026-12-29 | 179
A41110 | Project Close Out Report_RCC | 16 | 2026-03-25 | 2026-04-16 | 2026-12-29 | 2027-01-19 | 179
A41100 | Project Close Out Report_IFR | 2 | 2026-03-23 | 2026-03-25 | 2027-01-19 | 2027-01-20 | 179
Energy Review Closeout Report |  | 48 | 2026-02-24 | 2026-05-01 | 2026-11-13 | 2027-01-20 | 188
A41190 | Energy Review Closeout Report_IFD/IFC | 2 | 2026-04-29 | 2026-05-01 | 2026-11-13 | 2026-11-30 | 188
A41180 | Energy Review Closeout Report_RCA | 16 | 2026-04-07 | 2026-04-29 | 2026-11-30 | 2026-12-22 | 188
A41170 | Energy Review Closeout Report_IFA | 3 | 2026-04-02 | 2026-04-07 | 2026-12-22 | 2026-12-25 | 188
A41160 | Energy Review Closeout Report_RCC | 16 | 2026-03-11 | 2026-04-02 | 2026-12-28 | 2027-01-18 | 188
A41150 | Energy Review Closeout Report_IFR | 11 | 2026-02-24 | 2026-03-11 | 2027-01-18 | 2027-01-20 | 188
Process |  | 354 | 27-Dec-24 A | 2026-04-23 | 2026-03-02 | 2027-01-20 | 194
Utility Design Basis |  | 260 | 27-Dec-24 A | 18-Aug-25 A | 46100 | 46407
A41240 | Utility Design Basis_IFD/IFC | 2 | 13-Aug-25 A | 18-Aug-25 A | 46100 | 46100
A41230 | Utility Design Basis_RCA | 16 | 05-Aug-25 A | 12-Aug-25 A | 46407 | 46407
A41220 | Utility Design Basis_IFA | 3 | 01-Aug-25 A | 04-Aug-25 A | 46407 | 46407
A41210 | Utility Design Basis_RCC | 16 | 18-Jan-25 A | 31-Jan-25 A | 46407 | 46407
A41200 | Utility Design Basis_IFR | 6 | 27-Dec-24 A | 17-Jan-25 A | 46407 | 46407
Criticality Rating of System |  | 341 | 10-Jan-25 A | 2026-04-14 | 2026-11-30 | 2027-01-20 | 202
A41290 | Criticality Rating of System_IFD/IFC | 2 | 2026-04-09 | 2026-04-14 | 2026-11-30 | 2026-11-30 | 202
A41280 | Criticality Rating of System_RCA | 16 | 2026-03-19 | 2026-04-09 | 2026-11-30 | 2026-12-22 | 202
A41270 | Criticality Rating of System_IFA | 3 | 2026-03-13 | 2026-03-19 | 2026-12-22 | 2026-12-25 | 202
A41260 | Criticality Rating of System_RCC | 16 | 2026-02-20 | 2026-03-13 | 2026-12-28 | 2027-01-18 | 202
A41250 | Criticality Rating of System_IFR | 6 | 10-Jan-25 A | 06-Jun-25 A | 46405 | 46407
List Of Process Simulation Cases |  | 256 | 27-Dec-24 A | 12-Jul-25 A | 46407 | 46407
A41340 | List Of Process Simulation Cases_IFD/IFC | 2 | 09-Jul-25 A | 12-Jul-25 A | 46407 | 46407
A41330 | List Of Process Simulation Cases_RCA | 16 | 20-Jun-25 A | 05-Jul-25 A | 46407 | 46407
A41320 | List Of Process Simulation Cases_IFA | 3 | 23-Jun-25 A | 28-Jun-25 A | 46407 | 46407
A41310 | List Of Process Simulation Cases_RCC | 16 | 03-Jun-25 A | 21-Jun-25 A | 46407 | 46407
A41300 | List Of Process Simulation Cases_IFR | 6 | 27-Dec-24 A | 17-Jan-25 A | 46407 | 46407
Isolation Philosophy |  | 263 | 03-Jan-25 A | 23-Dec-25 A | 46345 | 46407
A41810 | Isolation Philosophy_IFD/IFC | 2 | 19-Dec-25 A | 23-Dec-25 A | 46345 | 46345
A41800 | Isolation Philosophy_RCA | 16 | 14-Jun-25 A | 21-Jun-25 A | 46407 | 46407
A41790 | Isolation Philosophy_IFA | 3 | 20-Apr-25 A | 13-Jun-25 A | 46407 | 46407
A3190 | Isolation Philosophy_RCC | 16 | 18-Apr-25 A | 19-Apr-25 A | 46407 | 46407
A3180 | Isolation Philosophy_IFR | 6 | 03-Jan-25 A | 24-Jan-25 A | 46407 | 46407
Relief and Blowdown Philosophy |  | 319 | 09-Jan-25 A | 2026-03-17 | 2026-11-19 | 2027-01-20 | 221
A41860 | Relief and Blowdown Philosophy_IFD/IFC | 2 | 2026-03-13 | 2026-03-17 | 2026-11-19 | 2026-11-19 | 221
A41850 | Relief and Blowdown Philosophy_RCA | 16 | 2026-02-20 | 2026-03-13 | 2026-12-28 | 2026-12-28 | 221
A41840 | Relief and Blowdown Philosophy_IFA | 3 | 10-Dec-25 A | 19-Dec-25 A | 46384 | 46384
A41830 | Relief and Blowdown Philosophy_RCC | 16 | 31-Jan-25 A | 20-Apr-25 A | 46384 | 46405
A41820 | Relief and Blowdown Philosophy_IFR | 6 | 09-Jan-25 A | 30-Jan-25 A | 46405 | 46407
Vent and Drain Philosophy |  | 340 | 03-Jan-25 A | 2026-04-23 | 2026-11-19 | 2027-01-20 | 194
A41910 | Vent and Drain Philosophy_IFD/IFC | 2 | 2026-04-21 | 2026-04-23 | 2026-11-19 | 2026-11-19 | 194
A41900 | Vent and Drain Philosophy_RCA | 16 | 31-Jul-25 A | 15-Aug-25 A | 46405 | 46405
A41890 | Vent and Drain Philosophy_IFA | 3 | 21-Apr-25 A | 17-Jun-25 A | 46405 | 46405
A41880 | Vent and Drain Philosophy_RCC | 16 | 25-Jan-25 A | 20-Apr-25 A | 46405 | 46405
A41870 | Vent and Drain Philosophy_IFR | 6 | 03-Jan-25 A | 24-Jan-25 A | 46405 | 46407
Operating manual including operating procedure/guidelines including startup and shutdown procedure |  | 43 | 2026-02-20 | 2026-04-21 | 2026-11-19 | 2027-01-18 | 194
A56020 | Operating manual including operating procedure/guidelines including startup and shutdown procedure_IFD/IFC | 2 | 2026-04-17 | 2026-04-21 | 2026-11-19 | 2026-11-26 | 194
A56010 | Operating manual including operating procedure/guidelines including startup and shutdown procedure_RCA | 16 | 2026-03-26 | 2026-04-17 | 2026-11-26 | 2026-12-18 | 194
A56000 | Operating manual including operating procedure/guidelines including startup and shutdown procedure_IFA | 3 | 2026-03-23 | 2026-03-26 | 2026-12-18 | 2026-12-23 | 194
A55990 | Operating manual including operating procedure/guidelines including startup and shutdown procedure_RCC | 16 | 2026-02-27 | 2026-03-23 | 2026-12-23 | 2027-01-14 | 194
A55980 | Operating manual including operating procedure/guidelines including startup and shutdown procedure_IFR | 6 | 2026-02-20 | 2026-02-27 | 2027-01-14 | 2027-01-18 | 194
Process Safeguarding Diagram: List |  | 217 | 04-Jan-25 A | 28-Jun-25 A | 46083 | 46345
A41960 | Process Safeguarding Diagram: List_IFD/IFC | 2 | 22-Jun-25 A | 28-Jun-25 A | 46083 | 46083
A41950 | Process Safeguarding Diagram: List_RCA | 16 | 28-May-25 A | 21-Jun-25 A | 46083 | 46083
A41940 | Process Safeguarding Diagram: List_IFH | 11 | 21-Feb-25 A | 27-May-25 A | 46083 | 46083
A41930 | Process Safeguarding Diagram: List_RCC | 16 | 26-Jan-25 A | 20-Feb-25 A | 46345 | 46345
A41920 | Process Safeguarding Diagram: List_IFR | 11 | 04-Jan-25 A | 25-Jan-25 A | 46345 | 46345
Process Safeguarding Diagram: Feed Pretreatment |  | 217 | 04-Jan-25 A | 28-Jun-25 A | 46083 | 46407
A42010 | Process Safeguarding Diagram: Feed Pretreatment_IFD/IFC | 2 | 22-Jun-25 A | 28-Jun-25 A | 46083 | 46083
A42000 | Process Safeguarding Diagram: Feed Pretreatment_RCA | 16 | 28-May-25 A | 21-Jun-25 A | 46083 | 46083
A41990 | Process Safeguarding Diagram: Feed Pretreatment_IFH | 11 | 21-Feb-25 A | 27-May-25 A | 46083 | 46083
A41980 | Process Safeguarding Diagram: Feed Pretreatment_RCC | 16 | 26-Jan-25 A | 20-Feb-25 A | 46407 | 46407
A41970 | Process Safeguarding Diagram: Feed Pretreatment_IFR | 11 | 04-Jan-25 A | 25-Jan-25 A | 46407 | 46407
Process Safeguarding Diagram: Wash Water System |  | 217 | 04-Jan-25 A | 28-Jun-25 A | 46083 | 46407
A42060 | Process Safeguarding Diagram: Wash Water System_IFD/IFC | 2 | 22-Jun-25 A | 28-Jun-25 A | 46083 | 46083
A42050 | Process Safeguarding Diagram: Wash Water System_RCA | 16 | 28-May-25 A | 21-Jun-25 A | 46083 | 46083
A42040 | Process Safeguarding Diagram: Wash Water System_IFH | 11 | 21-Feb-25 A | 27-May-25 A | 46083 | 46083
A42030 | Process Safeguarding Diagram: Wash Water System_RCC | 16 | 26-Jan-25 A | 20-Feb-25 A | 46407 | 46407
A42020 | Process Safeguarding Diagram: Wash Water System_IFR | 11 | 04-Jan-25 A | 25-Jan-25 A | 46407 | 46407
Process Safeguarding Diagram: Cracked Gas Compression |  | 217 | 04-Jan-25 A | 28-Jun-25 A | 46083 | 46407
A42110 | Process Safeguarding Diagram: Cracked Gas Compression_IFD/IFC | 2 | 22-Jun-25 A | 28-Jun-25 A | 46083 | 46083
A42100 | Process Safeguarding Diagram: Cracked Gas Compression_RCA | 16 | 28-May-25 A | 21-Jun-25 A | 46083 | 46083
A42090 | Process Safeguarding Diagram: Cracked Gas Compression_IFH | 11 | 21-Feb-25 A | 27-May-25 A | 46083 | 46083
A42080 | Process Safeguarding Diagram: Cracked Gas Compression_RCC | 16 | 26-Jan-25 A | 20-Feb-25 A | 46407 | 46407
A42070 | Process Safeguarding Diagram: Cracked Gas Compression_IFR | 11 | 04-Jan-25 A | 25-Jan-25 A | 46407 | 46407
Process Safeguarding Diagram: C1/C2 Separation |  | 217 | 04-Jan-25 A | 28-Jun-25 A | 46083 | 46407
A42160 | Process Safeguarding Diagram: C1/C2 Separation_IFD/IFC | 2 | 22-Jun-25 A | 28-Jun-25 A | 46083 | 46083
A42150 | Process Safeguarding Diagram: C1/C2 Separation_RCA | 16 | 28-May-25 A | 21-Jun-25 A | 46083 | 46083
A42140 | Process Safeguarding Diagram: C1/C2 Separation_IFH | 11 | 21-Feb-25 A | 27-May-25 A | 46083 | 46083
A42130 | Process Safeguarding Diagram: C1/C2 Separation_RCC | 16 | 26-Jan-25 A | 20-Feb-25 A | 46407 | 46407
A42120 | Process Safeguarding Diagram: C1/C2 Separation_IFR | 11 | 04-Jan-25 A | 25-Jan-25 A | 46407 | 46407
Process Safeguarding Diagram: H2 Extraction Unit |  | 217 | 04-Jan-25 A | 28-Jun-25 A | 46083 | 46407
A42210 | Process Safeguarding Diagram: H2 Extraction Unit_IFD/IFC | 2 | 22-Jun-25 A | 28-Jun-25 A | 46083 | 46083
A42200 | Process Safeguarding Diagram: H2 Extraction Unit_RCA | 16 | 28-May-25 A | 21-Jun-25 A | 46083 | 46083
A42190 | Process Safeguarding Diagram: H2 Extraction Unit_IFH | 11 | 21-Feb-25 A | 27-May-25 A | 46083 | 46083
A42180 | Process Safeguarding Diagram: H2 Extraction Unit_RCC | 16 | 26-Jan-25 A | 20-Feb-25 A | 46407 | 46407
A42170 | Process Safeguarding Diagram: H2 Extraction Unit_IFR | 11 | 04-Jan-25 A | 25-Jan-25 A | 46407 | 46407
Process Safeguarding Diagram: H2 Extraction Unit II |  | 217 | 04-Jan-25 A | 28-Jun-25 A | 46083 | 46407
A42260 | Process Safeguarding Diagram: H2 Extraction Unit II_IFD/IFC | 2 | 22-Jun-25 A | 28-Jun-25 A | 46083 | 46083
A42250 | Process Safeguarding Diagram: H2 Extraction Unit II_RCA | 16 | 28-May-25 A | 21-Jun-25 A | 46083 | 46083
A42240 | Process Safeguarding Diagram: H2 Extraction Unit II_IFH | 11 | 21-Feb-25 A | 27-May-25 A | 46083 | 46083
A42230 | Process Safeguarding Diagram: H2 Extraction Unit II_RCC | 16 | 26-Jan-25 A | 20-Feb-25 A | 46407 | 46407
A42220 | Process Safeguarding Diagram: H2 Extraction Unit II_IFR | 11 | 04-Jan-25 A | 25-Jan-25 A | 46407 | 46407
Process Safeguarding Diagram: C4 Selective Hydrogenation IV |  | 217 | 04-Jan-25 A | 28-Jun-25 A | 46083 | 46407
A42310 | Process Safeguarding Diagram: C4 Selective Hydrogenation IV_IFD/IFC | 2 | 22-Jun-25 A | 28-Jun-25 A | 46083 | 46083
A42300 | Process Safeguarding Diagram: C4 Selective Hydrogenation IV_RCA | 16 | 28-May-25 A | 21-Jun-25 A | 46083 | 46083
A42290 | Process Safeguarding Diagram: C4 Selective Hydrogenation IV_IFH | 11 | 21-Feb-25 A | 27-May-25 A | 46083 | 46083
A42280 | Process Safeguarding Diagram: C4 Selective Hydrogenation IV_RCC | 16 | 26-Jan-25 A | 20-Feb-25 A | 46407 | 46407
A42270 | Process Safeguarding Diagram: C4 Selective Hydrogenation IV_IFR | 11 | 04-Jan-25 A | 25-Jan-25 A | 46407 | 46407
Process Safeguarding Diagram: Fuel Gas System |  | 217 | 04-Jan-25 A | 28-Jun-25 A | 46083 | 46407
A42360 | Process Safeguarding Diagram: Fuel Gas System_IFD/IFC | 2 | 22-Jun-25 A | 28-Jun-25 A | 46083 | 46083
A42350 | Process Safeguarding Diagram: Fuel Gas System_RCA | 16 | 28-May-25 A | 21-Jun-25 A | 46083 | 46083
A42340 | Process Safeguarding Diagram: Fuel Gas System_IFH | 11 | 21-Feb-25 A | 27-May-25 A | 46083 | 46083
A42330 | Process Safeguarding Diagram: Fuel Gas System_RCC | 16 | 26-Jan-25 A | 20-Feb-25 A | 46407 | 46407
A42320 | Process Safeguarding Diagram: Fuel Gas System_IFR | 11 | 04-Jan-25 A | 25-Jan-25 A | 46407 | 46407
Process Safeguarding Diagram: Regeneration System |  | 217 | 04-Jan-25 A | 28-Jun-25 A | 46083 | 46407
A42410 | Process Safeguarding Diagram: Regeneration System_IFD/IFC | 2 | 22-Jun-25 A | 28-Jun-25 A | 46083 | 46083
A42400 | Process Safeguarding Diagram: Regeneration System_RCA | 16 | 28-May-25 A | 21-Jun-25 A | 46083 | 46083
A42390 | Process Safeguarding Diagram: Regeneration System_IFH | 11 | 21-Feb-25 A | 27-May-25 A | 46083 | 46083
A42380 | Process Safeguarding Diagram: Regeneration System_RCC | 16 | 26-Jan-25 A | 20-Feb-25 A | 46407 | 46407
A42370 | Process Safeguarding Diagram: Regeneration System_IFR | 11 | 04-Jan-25 A | 25-Jan-25 A | 46407 | 46407
Process Safeguarding Diagram: Boiler Feed Water System |  | 217 | 04-Jan-25 A | 28-Jun-25 A | 46083 | 46407
A42460 | Process Safeguarding Diagram: Boiler Feed Water System_IFD/IFC | 2 | 22-Jun-25 A | 28-Jun-25 A | 46083 | 46083
A42450 | Process Safeguarding Diagram: Boiler Feed Water System_RCA | 16 | 28-May-25 A | 21-Jun-25 A | 46083 | 46083
A42440 | Process Safeguarding Diagram: Boiler Feed Water System_IFH | 11 | 21-Feb-25 A | 27-May-25 A | 46083 | 46083
A42430 | Process Safeguarding Diagram: Boiler Feed Water System_RCC | 16 | 26-Jan-25 A | 20-Feb-25 A | 46407 | 46407
A42420 | Process Safeguarding Diagram: Boiler Feed Water System_IFR | 11 | 04-Jan-25 A | 25-Jan-25 A | 46407 | 46407
Process Safeguarding Diagram: Condensate Collection System |  | 217 | 04-Jan-25 A | 28-Jun-25 A | 46083 | 46407
A42510 | Process Safeguarding Diagram: Condensate Collection System_IFD/IFC | 2 | 22-Jun-25 A | 28-Jun-25 A | 46083 | 46083
A42500 | Process Safeguarding Diagram: Condensate Collection System_RCA | 16 | 28-May-25 A | 21-Jun-25 A | 46083 | 46083
A42490 | Process Safeguarding Diagram: Condensate Collection System_IFH | 11 | 21-Feb-25 A | 27-May-25 A | 46083 | 46083
A42480 | Process Safeguarding Diagram: Condensate Collection System_RCC | 16 | 26-Jan-25 A | 20-Feb-25 A | 46407 | 46407
A42470 | Process Safeguarding Diagram: Condensate Collection System_IFR | 11 | 04-Jan-25 A | 25-Jan-25 A | 46407 | 46407
Process Safeguarding Diagram: Cooling Water System |  | 217 | 04-Jan-25 A | 28-Jun-25 A | 46083 | 46407
A42560 | Process Safeguarding Diagram: Cooling Water System_IFD/IFC | 2 | 22-Jun-25 A | 28-Jun-25 A | 46083 | 46083
A42550 | Process Safeguarding Diagram: Cooling Water System_RCA | 16 | 28-May-25 A | 21-Jun-25 A | 46083 | 46083
A42540 | Process Safeguarding Diagram: Cooling Water System_IFH | 11 | 21-Feb-25 A | 27-May-25 A | 46083 | 46083
A42530 | Process Safeguarding Diagram: Cooling Water System_RCC | 16 | 26-Jan-25 A | 20-Feb-25 A | 46407 | 46407
A42520 | Process Safeguarding Diagram: Cooling Water System_IFR | 11 | 04-Jan-25 A | 25-Jan-25 A | 46407 | 46407
Process Safeguarding Diagram: Utility System For H2 Extraction Unit |  | 217 | 04-Jan-25 A | 28-Jun-25 A | 46083 | 46407
A42610 | Process Safeguarding Diagram: Utility System For H2 Extraction Unit_IFD/IFC | 2 | 22-Jun-25 A | 28-Jun-25 A | 46083 | 46083
A42600 | Process Safeguarding Diagram: Utility System For H2 Extraction Unit_RCA | 16 | 28-May-25 A | 21-Jun-25 A | 46083 | 46083
A42590 | Process Safeguarding Diagram: Utility System For H2 Extraction Unit_IFH | 11 | 21-Feb-25 A | 27-May-25 A | 46083 | 46083
A42580 | Process Safeguarding Diagram: Utility System For H2 Extraction Unit_RCC | 16 | 26-Jan-25 A | 20-Feb-25 A | 46407 | 46407
A42570 | Process Safeguarding Diagram: Utility System For H2 Extraction Unit_IFR | 11 | 04-Jan-25 A | 25-Jan-25 A | 46407 | 46407
Process Safeguarding Diagram: Blowdown Vessels And Acid Gas Flare |  | 217 | 04-Jan-25 A | 28-Jun-25 A | 46083 | 46407
A42660 | Process Safeguarding Diagram: Blowdown Vessels And Acid Gas Flare_IFD/IFC | 2 | 22-Jun-25 A | 28-Jun-25 A | 46083 | 46083
A42650 | Process Safeguarding Diagram: Blowdown Vessels And Acid Gas Flare_RCA | 16 | 28-May-25 A | 21-Jun-25 A | 46083 | 46083
A42640 | Process Safeguarding Diagram: Blowdown Vessels And Acid Gas Flare_IFH | 11 | 21-Feb-25 A | 27-May-25 A | 46083 | 46083
A42630 | Process Safeguarding Diagram: Blowdown Vessels And Acid Gas Flare_RCC | 16 | 26-Jan-25 A | 20-Feb-25 A | 46407 | 46407
A42620 | Process Safeguarding Diagram: Blowdown Vessels And Acid Gas Flare_IFR | 11 | 04-Jan-25 A | 25-Jan-25 A | 46407 | 46407
Process Safeguarding Diagram: Slop,Sewer And Drainage System |  | 217 | 04-Jan-25 A | 28-Jun-25 A | 46083 | 46407
A42710 | Process Safeguarding Diagram: Slop,Sewer And Drainage System_IFD/IFC | 2 | 22-Jun-25 A | 28-Jun-25 A | 46083 | 46083
A42700 | Process Safeguarding Diagram: Slop,Sewer And Drainage System_RCA | 16 | 28-May-25 A | 21-Jun-25 A | 46083 | 46083
A42690 | Process Safeguarding Diagram: Slop,Sewer And Drainage System_IFH | 11 | 21-Feb-25 A | 27-May-25 A | 46083 | 46083
A42680 | Process Safeguarding Diagram: Slop,Sewer And Drainage System_RCC | 16 | 26-Jan-25 A | 20-Feb-25 A | 46407 | 46407
A42670 | Process Safeguarding Diagram: Slop,Sewer And Drainage System_IFR | 11 | 04-Jan-25 A | 25-Jan-25 A | 46407 | 46407
Process Safeguarding Diagram: Slop,Sewer And Drainage System II |  | 217 | 04-Jan-25 A | 28-Jun-25 A | 46083 | 46407
A4170 | Process Safeguarding Diagram: Slop,Sewer And Drainage System II_IFD/IFC | 2 | 22-Jun-25 A | 28-Jun-25 A | 46083 | 46083
A4160 | Process Safeguarding Diagram: Slop,Sewer And Drainage System II_RCA | 16 | 28-May-25 A | 21-Jun-25 A | 46083 | 46083
A4150 | Process Safeguarding Diagram: Slop,Sewer And Drainage System II_IFH | 11 | 21-Feb-25 A | 27-May-25 A | 46083 | 46083
A4140 | Process Safeguarding Diagram: Slop,Sewer And Drainage System II_RCC | 16 | 26-Jan-25 A | 20-Feb-25 A | 46083 | 46083
A4130 | Process Safeguarding Diagram: Slop,Sewer And Drainage System II_IFR | 11 | 04-Jan-25 A | 25-Jan-25 A | 46407 | 46407
Utility Consumption |  | 87 | 21-Jun-25 A | 2026-02-24 | 2026-03-25 | 2026-03-27 | 23
A42800 | Utility Consumption_IFD/IFC | 2 | 2026-02-20 | 2026-02-24 | 2026-03-25 | 2026-03-25 | 23
A42790 | Utility Consumption_RCA | 16 | 16-Dec-25 A | 26-Dec-25 A | 46106 | 46106
A42780 | Utility Consumption_IFA | 3 | 16-Dec-25 A | 26-Dec-25 A | 46106 | 46106
A42770 | Utility Consumption_RCC | 16 | 02-Oct-25 A | 22-Oct-25 A | 46106 | 46106
A42760 | Utility Consumption_IFR | 6 | 21-Jun-25 A | 12-Jul-25 A | 46106 | 46108
Safeguarding Memorendum |  | 72 | 02-Sep-25 A | 2026-02-24 | 2027-01-18 | 2027-01-20 | 237
A42750 | Safeguarding Memorandum_IFD/IFC | 2 | 2026-02-20 | 2026-02-24 | 2027-01-18 | 2027-01-18 | 237
A42740 | Safeguarding Memorandum_RCA | 16 | 25-Nov-25 A | 29-Dec-25 A | 46405 | 46405
A42730 | Safeguarding Memorandum_IFA | 3 | 06-Oct-25 A | 25-Nov-25 A | 46405 | 46405
A42720 | Safeguarding Memorandum_RCC | 16 | 17-Sep-25 A | 06-Oct-25 A | 46405 | 46405
A4180 | Safeguarding Memorandum_IFR | 6 | 02-Sep-25 A | 13-Sep-25 A | 46405 | 46407
Process Utility Adequacy Check Report |  | 61 | 10-Oct-25 A | 19-Jan-26 A | 46108 | 46108
A43250 | Process Utility Adequacy Check Report_IFD/IFC | 2 | 15-Jan-26 A | 19-Jan-26 A | 46108 | 46108
A43240 | Process Utility Adequacy Check Report_RCA | 16 | 24-Dec-25 A | 15-Jan-26 A | 46108 | 46108
A43230 | Process Utility Adequacy Check Report_IFA | 3 | 19-Dec-25 A | 24-Dec-25 A | 46108 | 46108
A43220 | Process Utility Adequacy Check Report_RCC | 16 | 11-Oct-25 A | 24-Oct-25 A | 46108 | 46108
A43210 | Process Utility Adequacy Check Report_IFR | 6 | 10-Oct-25 A | 17-Oct-25 A | 46108 | 46108
Process Datasheet for PSA2 Feed Gas Compressor 1st Stage Suction Drum |  | 124 | 31-Dec-24 A | 21-May-25 A | 46083 | 46407
A41390 | Process Datasheet for PSA2 Feed Gas Compressor 1st Stage Suction Drum_IFD/IFC | 2 | 15-May-25 A | 21-May-25 A | 46083 | 46083
A41380 | Process Datasheet for PSA2 Feed Gas Compressor 1st Stage Suction Drum_RCA | 16 | 20-Apr-25 A | 14-May-25 A | 46407 | 46407
A41370 | Process Datasheet for PSA2 Feed Gas Compressor 1st Stage Suction Drum_IFA | 2 | 19-Mar-25 A | 19-Apr-25 A | 46407 | 46407
A41360 | Process Datasheet for PSA2 Feed Gas Compressor 1st Stage Suction Drum_RCC | 16 | 25-Jan-25 A | 18-Mar-25 A | 46407 | 46407
A41350 | Process Datasheet for PSA2 Feed Gas Compressor 1st Stage Suction Drum_IFR | 2 | 31-Dec-24 A | 24-Jan-25 A | 46407 | 46407
Process Datasheet for PSA2 Feed Gas Compressor 1st Stage Cooler |  | 131 | 01-Jan-25 A | 21-Jun-25 A | 46083 | 46407
A41430 | Process Datasheet for PSA2 Feed Gas Compressor 1st Stage Cooler_RCA | 16 | 21-May-25 A | 02-Jun-25 A | 46083 | 46083
A41440 | Process Datasheet for PSA2 Feed Gas Compressor 1st Stage Cooler_IFD/IFC | 2 | 03-Jun-25 A | 21-Jun-25 A | 46407 | 46407
A41420 | Process Datasheet for PSA2 Feed Gas Compressor 1st Stage Cooler_IFA | 2 | 20-Mar-25 A | 20-May-25 A | 46407 | 46407
A41410 | Process Datasheet for PSA2 Feed Gas Compressor 1st Stage Cooler_RCC | 16 | 27-Jan-25 A | 19-Mar-25 A | 46407 | 46407
A41400 | Process Datasheet for PSA2 Feed Gas Compressor 1st Stage Cooler_IFR | 2 | 01-Jan-25 A | 26-Jan-25 A | 46407 | 46407
Process Datasheet for PSA2 Feed Gas Compressor 2nd Stage Suction Drum |  | 123 | 31-Dec-24 A | 21-May-25 A | 46083 | 46407
A41490 | Process Datasheet for PSA2 Feed Gas Compressor 2nd Stage Suction Drum_IFD/IFC | 2 | 15-May-25 A | 21-May-25 A | 46083 | 46083
A41480 | Process Datasheet for PSA2 Feed Gas Compressor 2nd Stage Suction Drum_RCA | 16 | 20-Apr-25 A | 14-May-25 A | 46407 | 46407
A41470 | Process Datasheet for PSA2 Feed Gas Compressor 2nd Stage Suction Drum_IFA | 2 | 19-Mar-25 A | 19-Apr-25 A | 46407 | 46407
A41460 | Process Datasheet for PSA2 Feed Gas Compressor 2nd Stage Suction Drum_RCC | 16 | 25-Jan-25 A | 18-Mar-25 A | 46407 | 46407
A41450 | Process Datasheet for PSA2 Feed Gas Compressor 2nd Stage Suction Drum_IFR | 2 | 31-Dec-24 A | 24-Jan-25 A | 46407 | 46407
Process Datasheet for PSA2 Feed Gas Compressor 2nd Stage Cooler |  | 131 | 01-Jan-25 A | 21-Jun-25 A | 46083 | 46407
A41530 | Process Datasheet for PSA2 Feed Gas Compressor 2nd Stage Cooler_RCA | 16 | 21-May-25 A | 02-Jun-25 A | 46083 | 46083
A41540 | Process Datasheet for PSA2 Feed Gas Compressor 2nd Stage Cooler_IFD/IFC | 2 | 03-Jun-25 A | 21-Jun-25 A | 46407 | 46407
A41520 | Process Datasheet for PSA2 Feed Gas Compressor 2nd Stage Cooler_IFA | 2 | 20-Mar-25 A | 20-May-25 A | 46407 | 46407
A41510 | Process Datasheet for PSA2 Feed Gas Compressor 2nd Stage Cooler_RCC | 16 | 27-Jan-25 A | 19-Mar-25 A | 46407 | 46407
A41500 | Process Datasheet for PSA2 Feed Gas Compressor 2nd Stage Cooler_IFR | 2 | 01-Jan-25 A | 26-Jan-25 A | 46407 | 46407
Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Suction Drum |  | 123 | 31-Dec-24 A | 20-May-25 A | 46083 | 46407
A41590 | Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Suction Drum_IFD/IFC | 2 | 14-May-25 A | 20-May-25 A | 46083 | 46083
A41580 | Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Suction Drum_RCA | 16 | 20-Apr-25 A | 13-May-25 A | 46407 | 46407
A41570 | Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Suction Drum_IFA | 2 | 19-Mar-25 A | 19-Apr-25 A | 46407 | 46407
A41560 | Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Suction Drum_RCC | 16 | 25-Jan-25 A | 18-Mar-25 A | 46407 | 46407
A41550 | Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Suction Drum_IFR | 2 | 31-Dec-24 A | 24-Jan-25 A | 46407 | 46407
Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Cooler |  | 232 | 01-Jan-25 A | 20-Jul-25 A | 46083 | 46407
A41640 | Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Cooler_IFD/IFC | 2 | 16-Jul-25 A | 20-Jul-25 A | 46083 | 46083
A41630 | Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Cooler_RCA | 16 | 28-Jun-25 A | 14-Jul-25 A | 46407 | 46407
A41620 | Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Cooler_IFA | 2 | 20-Mar-25 A | 21-Jun-25 A | 46407 | 46407
A41610 | Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Cooler_RCC | 16 | 27-Jan-25 A | 19-Mar-25 A | 46407 | 46407
A41600 | Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Cooler_IFR | 2 | 01-Jan-25 A | 26-Jan-25 A | 46407 | 46407
Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Discharge Drum |  | 37 | 31-Dec-24 A | 20-May-25 A | 46083 | 46407
A2570 | Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Discharge Drum_IFD/IFC | 2 | 14-May-25 A | 20-May-25 A | 46083 | 46083
A2560 | Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Discharge Drum_RCA | 16 | 20-Apr-25 A | 13-May-25 A | 46407 | 46407
A2550 | Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Discharge Drum_IFA | 2 | 19-Mar-25 A | 19-Apr-25 A | 46407 | 46407
A41660 | Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Discharge Drum_RCC | 16 | 25-Jan-25 A | 18-Mar-25 A | 46407 | 46407
A41650 | Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Discharge Drum_IFR | 2 | 31-Dec-24 A | 24-Jan-25 A | 46407 | 46407
Process Datasheet for PSA2 Off Gas Buffer Drum - 13-VV-712 |  | 132 | 31-Dec-24 A | 12-Jun-25 A | 46083 | 46407
A2620 | Process Datasheet for PSA2 Off Gas Buffer Drum - 13-VV-712_IFD/IFC | 2 | 03-Jun-25 A | 12-Jun-25 A | 46083 | 46083
A2610 | Process Datasheet for PSA2 Off Gas Buffer Drum - 13-VV-712_RCA | 16 | 22-May-25 A | 02-Jun-25 A | 46407 | 46407
A2600 | Process Datasheet for PSA2 Off Gas Buffer Drum - 13-VV-712_IFA | 2 | 15-May-25 A | 21-May-25 A | 46407 | 46407
A2590 | Process Datasheet for PSA2 Off Gas Buffer Drum - 13-VV-712_RCC | 16 | 25-Jan-25 A | 14-May-25 A | 46407 | 46407
A2580 | Process Datasheet for PSA2 Off Gas Buffer Drum - 13-VV-712_IFR | 2 | 31-Dec-24 A | 24-Jan-25 A | 46407 | 46407
Process Datasheet for PSA2 Off Gas Compressor Interstage Cooler - 13-HE-708 |  | 131 | 01-Jan-25 A | 21-Jun-25 A | 46083 | 46407
A2660 | Process Datasheet for PSA2 Off Gas Compressor Interstage Cooler - 13-HE-708_RCA | 16 | 21-May-25 A | 11-Jun-25 A | 46083 | 46083
A2670 | Process Datasheet for PSA2 Off Gas Compressor Interstage Cooler - 13-HE-708_IFD/IFC | 2 | 12-Jun-25 A | 21-Jun-25 A | 46407 | 46407
A2650 | Process Datasheet for PSA2 Off Gas Compressor Interstage Cooler - 13-HE-708_IFA | 2 | 20-Mar-25 A | 20-May-25 A | 46407 | 46407
A2640 | Process Datasheet for PSA2 Off Gas Compressor Interstage Cooler - 13-HE-708_RCC | 16 | 27-Jan-25 A | 19-Mar-25 A | 46407 | 46407
A2630 | Process Datasheet for PSA2 Off Gas Compressor Interstage Cooler - 13-HE-708_IFR | 2 | 01-Jan-25 A | 26-Jan-25 A | 46407 | 46407
Process Datasheet for PSA2 Off Gas Compressor 2Nd Stage Suction Drum 13-VV-713 |  | 132 | 31-Dec-24 A | 13-Jun-25 A | 46083 | 46407
A2720 | Process Datasheet for PSA2 Off Gas Compressor 2Nd Stage Suction Drum 13-VV-713_IFD/IFC | 2 | 03-Jun-25 A | 13-Jun-25 A | 46083 | 46083
A41690 | Process Datasheet for PSA2 Off Gas Compressor 2Nd Stage Suction Drum 13-VV-713_RCA | 16 | 22-May-25 A | 02-Jun-25 A | 46407 | 46407
A41680 | Process Datasheet for PSA2 Off Gas Compressor 2Nd Stage Suction Drum 13-VV-713_IFA | 2 | 15-May-25 A | 21-May-25 A | 46407 | 46407
A41670 | Process Datasheet for PSA2 Off Gas Compressor 2Nd Stage Suction Drum 13-VV-713_RCC | 16 | 25-Jan-25 A | 14-May-25 A | 46407 | 46407
A2680 | Process Datasheet for PSA2 Off Gas Compressor 2Nd Stage Suction Drum 13-VV-713_IFR | 2 | 31-Dec-24 A | 24-Jan-25 A | 46407 | 46407
Process Datasheet for PSA2 Off Gas Compressor Aftercooler - 13-HE-709 |  | 301 | 01-Jan-25 A | 2026-02-24 | 2026-03-02 | 2027-01-20 | 237
A2770 | Process Datasheet for PSA2 Off Gas Compressor Aftercooler - 13-HE-709_IFD/IFC | 2 | 2026-02-20 | 2026-02-24 | 2026-03-02 | 2026-03-02 | 237
A2760 | Process Datasheet for PSA2 Off Gas Compressor Aftercooler - 13-HE-709_RCA | 16 | 21-May-25 A | 11-Jun-25 A | 46405 | 46405
A2750 | Process Datasheet for PSA2 Off Gas Compressor Aftercooler - 13-HE-709_IFA | 2 | 20-Mar-25 A | 20-May-25 A | 46405 | 46405
A2740 | Process Datasheet for PSA2 Off Gas Compressor Aftercooler - 13-HE-709_RCC | 16 | 27-Jan-25 A | 19-Mar-25 A | 46405 | 46405
A2730 | Process Datasheet for PSA2 Off Gas Compressor Aftercooler - 13-HE-709_IFR | 2 | 01-Jan-25 A | 26-Jan-25 A | 46405 | 46407
Process Datasheet for PSA2 Off Gas Compressor Discharge Dripleg - 13-SP-7004* |  | 220 | 01-Jan-25 A | 25-Jun-25 A | 46083 | 46405
A55750 | Process Datasheet for PSA2 Off Gas Compressor Discharge Dripleg - 13-SP-7004_IFD/IFC | 6 | 23-Jun-25 A | 25-Jun-25 A | 46083 | 46083
A2810 | Process Datasheet for PSA2 Off Gas Compressor Discharge Dripleg - 13-SP-7004_RCA | 16 | 12-Jun-25 A | 21-Jun-25 A | 46405 | 46405
A2800 | Process Datasheet for PSA2 Off Gas Compressor Discharge Dripleg - 13-SP-7004_IFA | 2 | 06-May-25 A | 11-Jun-25 A | 46405 | 46405
A2790 | Process Datasheet for PSA2 Off Gas Compressor Discharge Dripleg - 13-SP-7004_RCC | 16 | 25-Jan-25 A | 05-May-25 A | 46405 | 46405
A2780 | Process Datasheet for PSA2 Off Gas Compressor Discharge Dripleg - 13-SP-7004_IFR | 2 | 01-Jan-25 A | 24-Jan-25 A | 46405 | 46405
Process Datasheet for 52-SP-14067 Vhp Boiler Feed Water Preheater Dripleg |  | 335 | 01-Jan-25 A | 2026-04-10 | 2026-03-02 | 2027-01-20 | 203
A41710 | Process Datasheet for 52-SP-14067 Vhp Boiler Feed Water Preheater Dripleg_IFD/IFC | 2 | 2026-04-08 | 2026-04-10 | 2026-03-02 | 2026-03-02 | 203
A41700 | Process Datasheet for 52-SP-14067 Vhp Boiler Feed Water Preheater Dripleg_RCA | 16 | 2026-03-18 | 2026-04-08 | 2026-12-02 | 2026-12-23 | 203
A2850 | Process Datasheet for 52-SP-14067 Vhp Boiler Feed Water Preheater Dripleg_IFA | 2 | 2026-03-13 | 2026-03-17 | 2026-12-23 | 2026-12-25 | 203
A2840 | Process Datasheet for 52-SP-14067 Vhp Boiler Feed Water Preheater Dripleg_RCC | 16 | 2026-02-20 | 2026-03-13 | 2026-12-28 | 2027-01-18 | 203
A2830 | Process Datasheet for 52-SP-14067 Vhp Boiler Feed Water Preheater Dripleg_IFR | 2 | 01-Jan-25 A | 06-Jun-25 A | 46405 | 46407
Process Datasheet for 50-HE-1410 C4 Guard Adsorber Regeneration Gas Cooler |  | 215 | 01-Jan-25 A | 2026-02-24 | 2026-03-02 | 2027-01-20 | 237
A2920 | Process Datasheet for 50-HE-1410 C4 Guard Adsorber Regeneration Gas Cooler_IFD/IFC | 2 | 2026-02-20 | 2026-02-24 | 2026-03-02 | 2026-03-02 | 237
A2910 | Process Datasheet for 50-HE-1410 C4 Guard Adsorber Regeneration Gas Cooler_RCA | 16 | 01-Jun-25 A | 21-Jun-25 A | 46405 | 46405
A2900 | Process Datasheet for 50-HE-1410 C4 Guard Adsorber Regeneration Gas Cooler_IFA | 2 | 05-May-25 A | 30-May-25 A | 46405 | 46405
A2890 | Process Datasheet for 50-HE-1410 C4 Guard Adsorber Regeneration Gas Cooler_RCC | 16 | 28-Apr-25 A | 04-May-25 A | 46405 | 46405
A41720 | Process Datasheet for 50-HE-1410 C4 Guard Adsorber Regeneration Gas Cooler_IFR | 2 | 01-Jan-25 A | 27-Apr-25 A | 46405 | 46407
Process Datasheet for 50-VV-1403 C4 Guard Adsorber Regeneration Gas Coalescer |  | 319 | 01-Jan-25 A | 2026-03-20 | 2026-03-02 | 2027-01-20 | 219
A3020 | Process Datasheet for 50-VV-1403 C4 Guard Adsorber Regeneration Gas Coalescer_IFD/IFC | 2 | 2026-03-18 | 2026-03-20 | 2026-03-02 | 2026-03-02 | 219
A3010 | Process Datasheet for 50-VV-1403 C4 Guard Adsorber Regeneration Gas Coalescer_RCA | 16 | 2026-02-24 | 2026-03-17 | 2026-12-23 | 2026-12-23 | 219
A3000 | Process Datasheet for 50-VV-1403 C4 Guard Adsorber Regeneration Gas Coalescer_IFA | 2 | 2026-02-20 | 2026-02-24 | 2026-12-23 | 2026-12-25 | 219
A2990 | Process Datasheet for 50-VV-1403 C4 Guard Adsorber Regeneration Gas Coalescer_RCC | 16 | 31-Jan-25 A | 20-Apr-25 A | 46384 | 46405
A2980 | Process Datasheet for 50-VV-1403 C4 Guard Adsorber Regeneration Gas Coalescer_IFR | 2 | 01-Jan-25 A | 30-Jan-25 A | 46405 | 46407
Process Datasheet for 70-PC-1407 Water Collection Sump Pump II |  | 272 | 01-Jan-25 A | 13-Jan-26 A | 46083 | 46407
A41770 | Process Datasheet for 70-PC-1407 Water Collection Sump Pump II_IFD/IFC | 2 | 09-Jan-26 A | 13-Jan-26 A | 46083 | 46083
A41760 | Process Datasheet for 70-PC-1407 Water Collection Sump Pump II_RCA | 16 | 19-Dec-25 A | 09-Jan-26 A | 46407 | 46407
A41750 | Process Datasheet for 70-PC-1407 Water Collection Sump Pump II_IFA | 2 | 03-May-25 A | 19-Sep-25 A | 46407 | 46407
A41740 | Process Datasheet for 70-PC-1407 Water Collection Sump Pump II_RCC | 16 | 25-Jan-25 A | 02-May-25 A | 46407 | 46407
A41730 | Process Datasheet for 70-PC-1407 Water Collection Sump Pump II_IFR | 2 | 01-Jan-25 A | 24-Jan-25 A | 46407 | 46407
Process Datasheet for 70-PC-1409 A/B Sanitary Waste Water Sump Pump |  | 297 | 01-Jan-25 A | 12-Nov-25 A | 46083 | 46407
A3120 | Process Datasheet for 70-PC-1409 A/B Sanitary Waste Water Sump Pump_IFD/IFC | 2 | 02-Sep-25 A | 12-Nov-25 A | 46083 | 46083
A3110 | Process Datasheet for 70-PC-1409 A/B Sanitary Waste Water Sump Pump_RCA | 16 | 05-Aug-25 A | 25-Aug-25 A | 46407 | 46407
A3100 | Process Datasheet for 70-PC-1409 A/B Sanitary Waste Water Sump Pump_IFA | 2 | 01-Aug-25 A | 05-Aug-25 A | 46407 | 46407
A3090 | Process Datasheet for 70-PC-1409 A/B Sanitary Waste Water Sump Pump_RCC | 16 | 25-Jan-25 A | 02-May-25 A | 46407 | 46407
A3080 | Process Datasheet for 70-PC-1409 A/B Sanitary Waste Water Sump Pump_IFR | 2 | 01-Jan-25 A | 24-Jan-25 A | 46407 | 46407
Process Datasheet for 70-VV-1415 PSA2 Slop Drum |  | 216 | 01-Jan-25 A | 03-Nov-25 A | 46083 | 46407
A41780 | Process Datasheet for 70-VV-1415 PSA2 Slop Drum_IFD/IFC | 2 | 24-Oct-25 A | 03-Nov-25 A | 46083 | 46083
A3160 | Process Datasheet for 70-VV-1415 PSA2 Slop Drum_RCA | 16 | 12-Jun-25 A | 21-Jun-25 A | 46407 | 46407
A3150 | Process Datasheet for 70-VV-1415 PSA2 Slop Drum_IFA | 2 | 06-May-25 A | 11-Jun-25 A | 46407 | 46407
A3140 | Process Datasheet for 70-VV-1415 PSA2 Slop Drum_RCC | 16 | 25-Jan-25 A | 05-May-25 A | 46407 | 46407
A3130 | Process Datasheet for 70-VV-1415 PSA2 Slop Drum_IFR | 2 | 01-Jan-25 A | 24-Jan-25 A | 46407 | 46407
Process Datasheet of Off-Gas Compressor Coalescer |  | 252 | 05-Jun-25 A | 12-Jul-25 A | 46407 | 46407
A55780 | Process Datasheet of Off-Gas Compressor Coalescer_IFD/IFC | 2 | 10-Jul-25 A | 12-Jul-25 A | 46407 | 46407
A55770 | Process Datasheet of Off-Gas Compressor Coalescer_RCA | 16 | 20-Jun-25 A | 05-Jul-25 A | 46407 | 46407
A55760 | Process Datasheet of Off-Gas Compressor Coalescer_IFA | 2 | 26-Jun-25 A | 28-Jun-25 A | 46407 | 46407
A28240 | Process Datasheet of Off-Gas Compressor Coalescer_RCC | 16 | 05-Jun-25 A | 25-Jun-25 A | 46407 | 46407
A28230 | Process Datasheet of Off-Gas Compressor Coalescer_IFR | 2 | 18-Jun-25 A | 21-Jun-25 A | 46407 | 46407
Sample Point /Connection Lists |  | 139 | 21-Jun-25 A | 2026-02-24 | 2027-01-18 | 2027-01-20 | 237
A43100 | Sample Point /Connection Lists_IFD/IFC | 2 | 2026-02-20 | 2026-02-24 | 2027-01-18 | 2027-01-18 | 237
A43090 | Sample Point /Connection Lists_RCA | 16 | 01-Nov-25 A | 05-Nov-25 A | 46405 | 46405
A43080 | Sample Point /Connection Lists_IFA | 3 | 28-Oct-25 A | 31-Oct-25 A | 46405 | 46405
A43070 | Sample Point /Connection Lists_RCC | 16 | 01-Oct-25 A | 27-Oct-25 A | 46405 | 46405
A43060 | Sample Point /Connection Lists_IFR | 6 | 21-Jun-25 A | 12-Jul-25 A | 46405 | 46407
Process Calculation Report |  | 282 | 20-Feb-25 A | 2026-03-23 | 2026-12-22 | 2027-01-20 | 218
A43000 | Process Calculation Report_IFD/IFC | 2 | 2026-03-19 | 2026-03-23 | 2026-12-22 | 2026-12-22 | 218
A42990 | Process Calculation Report_RCA | 16 | 2026-02-25 | 2026-03-19 | 2026-12-22 | 2026-12-22 | 218
A42980 | Process Calculation Report_IFA | 3 | 2026-02-20 | 2026-02-25 | 2026-12-22 | 2026-12-25 | 218
A42970 | Process Calculation Report_RCC | 16 | 26-Dec-25 A | 10-Jan-26 A | 46384 | 46405
A42960 | Process Calculation Report_IFR | 6 | 20-Feb-25 A | 26-Dec-25 A | 46405 | 46407
Process Datasheet for Control Valve |  | 158 | 20-Feb-25 A | 12-Jul-25 A | 46083 | 46407
A42850 | Process Datasheet for Control Valve_IFD/IFC | 2 | 06-Jul-25 A | 12-Jul-25 A | 46083 | 46083
A42840 | Process Datasheet for Control Valve_RCA | 16 | 29-Jun-25 A | 05-Jul-25 A | 46407 | 46407
A42830 | Process Datasheet for Control Valve_IFA | 3 | 22-Jun-25 A | 28-Jun-25 A | 46407 | 46407
A42820 | Process Datasheet for Control Valve_RCC | 16 | 28-Apr-25 A | 21-Jun-25 A | 46407 | 46407
A42810 | Process Datasheet for Control Valve_IFR | 6 | 20-Feb-25 A | 27-Apr-25 A | 46407 | 46407
Process Datasheet for Relief Valve |  | 275 | 25-Jan-25 A | 19-Jan-26 A | 46083 | 46407
A42900 | Process Datasheet for Relief Valve_IFD/IFC | 2 | 15-Jan-26 A | 19-Jan-26 A | 46083 | 46083
A42890 | Process Datasheet for Relief Valve_RCA | 16 | 24-Dec-25 A | 15-Jan-26 A | 46407 | 46407
A42880 | Process Datasheet for Relief Valve_IFA | 3 | 19-Dec-25 A | 24-Dec-25 A | 46407 | 46407
A42870 | Process Datasheet for Relief Valve_RCC | 16 | 16-Jul-25 A | 01-Aug-25 A | 46407 | 46407
A42860 | Process Datasheet for Relief Valve_IFR | 6 | 25-Jan-25 A | 20-Apr-25 A | 46407 | 46407
Process Datasheet for Flow Instrument |  | 320 | 20-Feb-25 A | 2026-03-23 | 2026-03-02 | 2027-01-20 | 218
A42950 | Process Datasheet for Flow Instrument_IFD/IFC | 2 | 2026-03-19 | 2026-03-23 | 2026-03-02 | 2026-03-02 | 218
A42940 | Process Datasheet for Flow Instrument_RCA | 16 | 2026-02-25 | 2026-03-19 | 2026-12-22 | 2026-12-22 | 218
A42930 | Process Datasheet for Flow Instrument_IFA | 3 | 2026-02-20 | 2026-02-25 | 2026-12-22 | 2026-12-25 | 218
A42920 | Process Datasheet for Flow Instrument_RCC | 16 | 26-Apr-25 A | 26-May-25 A | 46384 | 46405
A42910 | Process Datasheet for Flow Instrument_IFR | 6 | 20-Feb-25 A | 25-Apr-25 A | 46405 | 46407
Flare Relief Load Summary |  | 278 | 31-Jan-25 A | 2026-02-24 | 2026-03-25 | 2026-03-27 | 23
A43200 | Flare Relief Load Summary_IFD/IFC | 2 | 2026-02-20 | 2026-02-24 | 2026-03-25 | 2026-03-25 | 23
A43190 | Flare Relief Load Summary_RCA | 16 | 16-Dec-25 A | 13-Feb-26 A | 46106 | 46106
A43180 | Flare Relief Load Summary_IFA | 3 | 09-Dec-25 A | 19-Dec-25 A | 46106 | 46106
A43170 | Flare Relief Load Summary_RCC | 16 | 12-Mar-25 A | 20-Apr-25 A | 46106 | 46106
A43160 | Flare Relief Load Summary_IFR | 6 | 31-Jan-25 A | 11-Mar-25 A | 46106 | 46108
Flare Relief & Blowdown Report |  | 103 | 03-May-25 A | 2026-03-17 | 2026-11-23 | 2027-01-20 | 221
A43150 | Flare Relief & Blowdown Report_IFD/IFC | 2 | 2026-03-13 | 2026-03-17 | 2026-11-23 | 2026-11-23 | 221
A43140 | Flare Relief & Blowdown Report_RCA | 16 | 2026-02-20 | 2026-03-13 | 2026-12-28 | 2026-12-28 | 221
A43130 | Flare Relief & Blowdown Report_IFA | 3 | 05-Dec-25 A | 19-Dec-25 A | 46384 | 46384
A43120 | Flare Relief & Blowdown Report_RCC | 16 | 05-May-25 A | 18-May-25 A | 46384 | 46405
A43110 | Flare Relief & Blowdown Report_IFR | 6 | 03-May-25 A | 11-May-25 A | 46405 | 46407
Dynamic Flare Simulation Study |  | 43 | 2026-02-20 | 2026-04-21 | 2026-11-23 | 2027-01-20 | 196
A43050 | Dynamic Flare Simulation Study_IFD/IFC | 2 | 2026-04-17 | 2026-04-21 | 2026-11-23 | 2026-11-30 | 196
A43040 | Dynamic Flare Simulation Study_RCA | 16 | 2026-03-26 | 2026-04-17 | 2026-11-30 | 2026-12-22 | 196
A43030 | Dynamic Flare Simulation Study_IFA | 3 | 2026-03-23 | 2026-03-26 | 2026-12-22 | 2026-12-25 | 196
A43020 | Dynamic Flare Simulation Study_RCC | 16 | 2026-02-27 | 2026-03-23 | 2026-12-28 | 2027-01-18 | 196
A43010 | Dynamic Flare Simulation Study_IFR | 6 | 2026-02-20 | 2026-02-27 | 2027-01-18 | 2027-01-20 | 196
Piping |  | 376 | 16-Jan-25 A | 2026-06-08 | 2026-03-02 | 2027-01-20 | 162
3D Modelling Procedure |  | 224 | 01-Mar-25 A | 15-Oct-25 A | 46083 | 46407
A43300 | 3D Modelling Procedure_IFD/IFC | 2 | 12-Oct-25 A | 15-Oct-25 A | 46083 | 46083
A43290 | 3D Modelling Procedure_RCA | 16 | 01-Aug-25 A | 23-Aug-25 A | 46407 | 46407
A43280 | 3D Modelling Procedure_IFA | 3 | 29-Apr-25 A | 21-Jun-25 A | 46407 | 46407
A43270 | 3D Modelling Procedure_RCC | 16 | 21-Apr-25 A | 28-Apr-25 A | 46407 | 46407
A43260 | 3D Modelling Procedure_IFR | 6 | 01-Mar-25 A | 20-Apr-25 A | 46407 | 46407
3D Model Execution Philosophy |  | 224 | 25-Mar-25 A | 14-Oct-25 A | 46314 | 46407
A55440 | 3D Model Execution Philosophy_IFD/IFC | 2 | 11-Oct-25 A | 14-Oct-25 A | 46314 | 46314
A55430 | 3D Model Execution Philosophy_RCA | 16 | 20-Jul-25 A | 08-Aug-25 A | 46407 | 46407
A55420 | 3D Model Execution Philosophy_IFA | 3 | 29-Apr-25 A | 21-Jun-25 A | 46407 | 46407
A55410 | 3D Model Execution Philosophy_RCC | 16 | 16-Apr-25 A | 28-Apr-25 A | 46407 | 46407
A55400 | 3D Model Execution Philosophy_IFR | 6 | 25-Mar-25 A | 15-Apr-25 A | 46407 | 46407
3D Model Review Procedure |  | 248 | 25-Mar-25 A | 23-Dec-25 A | 46407 | 46407
A43350 | 3D Model Review Procedure_IFD/IFC | 2 | 19-Dec-25 A | 23-Dec-25 A | 46407 | 46407
A43340 | 3D Model Review Procedure_RCA | 16 | 22-Jun-25 A | 05-Sep-25 A | 46407 | 46407
A43330 | 3D Model Review Procedure_IFA | 3 | 29-Apr-25 A | 21-Jun-25 A | 46407 | 46407
A43320 | 3D Model Review Procedure_RCC | 16 | 16-Apr-25 A | 28-Apr-25 A | 46407 | 46407
A43310 | 3D Model Review Procedure_IFR | 6 | 25-Mar-25 A | 15-Apr-25 A | 46407 | 46407
Clash Check Procedure |  | 117 | 22-Mar-25 A | 11-May-25 A | 46314 | 46407
A55470 | Clash Check Procedure_IFD/IFC | 2 | 05-May-25 A | 11-May-25 A | 46314 | 46314
A55460 | Clash Check Procedure_RCA | 16 | 28-Apr-25 A | 04-May-25 A | 46407 | 46407
A27880 | Clash Check Procedure_IFA | 3 | 21-Apr-25 A | 27-Apr-25 A | 46407 | 46407
A27870 | Clash Check Procedure_RCC | 16 | 13-Apr-25 A | 20-Apr-25 A | 46407 | 46407
A55450 | Clash Check Procedure_IFR | 6 | 22-Mar-25 A | 12-Apr-25 A | 46407 | 46407
Deliverables Extraction Procedure |  | 38 | 23-Jan-25 A | 12-Mar-25 A | 46314 | 46407
A55520 | Deliverables Extraction Procedure_IFD/IFC | 2 | 06-Mar-25 A | 12-Mar-25 A | 46314 | 46314
A55510 | Deliverables Extraction Procedure_RCA | 16 | 27-Feb-25 A | 05-Mar-25 A | 46407 | 46407
A55500 | Deliverables Extraction Procedure_IFA | 3 | 20-Feb-25 A | 26-Feb-25 A | 46407 | 46407
A55490 | Deliverables Extraction Procedure_RCC | 16 | 13-Feb-25 A | 19-Feb-25 A | 46407 | 46407
A55480 | Deliverables Extraction Procedure_IFR | 6 | 23-Jan-25 A | 12-Feb-25 A | 46407 | 46407
Data Handover Procedure |  | 212 | 21-Jun-25 A | 2026-04-14 | 2026-10-19 | 2026-12-09 | 172
A55550 | Data Handover Procedure_IFD/IFC | 2 | 2026-04-09 | 2026-04-14 | 2026-10-19 | 2026-10-19 | 172
A55540 | Data Handover Procedure_RCA | 16 | 2026-03-19 | 2026-04-09 | 2026-10-19 | 2026-11-10 | 172
A55530 | Data Handover Procedure_IFA | 3 | 2026-03-13 | 2026-03-19 | 2026-11-10 | 2026-11-13 | 172
A27970 | Data Handover Procedure_RCC | 16 | 2026-02-20 | 2026-03-13 | 2026-11-16 | 2026-12-07 | 172
A27960 | Data Handover Procedure_IFR | 6 | 21-Jun-25 A | 12-Jul-25 A | 46363 | 46365
Stress Critical Line List |  | 287 | 15-Apr-25 A | 2026-03-17 | 2026-12-28 | 2027-01-20 | 221
A43500 | Stress Critical Line List_IFD/IFC | 2 | 2026-03-13 | 2026-03-17 | 2026-12-28 | 2026-12-28 | 221
A43490 | Stress Critical Line List_RCA | 16 | 2026-02-20 | 2026-03-13 | 2026-12-28 | 2026-12-28 | 221
A43480 | Stress Critical Line List_IFA | 3 | 04-Dec-25 A | 19-Dec-25 A | 46384 | 46384
A43470 | Stress Critical Line List_RCC | 16 | 07-May-25 A | 13-May-25 A | 46384 | 46405
A43460 | Stress Critical Line List_IFR | 11 | 15-Apr-25 A | 06-May-25 A | 46405 | 46407
Datasheets for Ball Valves |  | 255 | 16-Jan-25 A | 21-Nov-25 A | 46098 | 46098
A43700 | Datasheets for Ball Valves_IFD/IFC | 2 | 10-Nov-25 A | 21-Nov-25 A | 46098 | 46098
A43690 | Datasheets for Ball Valves_RCA | 16 | 31-Oct-25 A | 07-Nov-25 A | 46098 | 46098
A43680 | Datasheets for Ball Valves_IFA | 3 | 22-Oct-25 A | 30-Oct-25 A | 46098 | 46098
A43670 | Datasheets for Ball Valves_RCC | 16 | 01-Aug-25 A | 25-Aug-25 A | 46098 | 46098
A43660 | Datasheets for Ball Valves_IFR | 6 | 16-Jan-25 A | 14-May-25 A | 46098 | 46098
Datasheets for Double Block & Bleed Valves |  | 208 | 27-Jan-25 A | 22-Aug-25 A | 46098 | 46100
A43790 | Datasheets for Double Block & Bleed Valves_RCA | 16 | 16-Aug-25 A | 20-Aug-25 A | 46098 | 46098
A43800 | Datasheets for Double Block & Bleed Valves_IFD/IFC | 2 | 21-Aug-25 A | 22-Aug-25 A | 46100 | 46100
A43780 | Datasheets for Double Block & Bleed Valves_IFA | 3 | 11-Aug-25 A | 15-Aug-25 A | 46100 | 46100
A43770 | Datasheets for Double Block & Bleed Valves_RCC | 16 | 02-Aug-25 A | 10-Aug-25 A | 46100 | 46100
A43760 | Datasheets for Double Block & Bleed Valves_IFR | 6 | 27-Jan-25 A | 01-Aug-25 A | 46100 | 46100
Datasheets for Check Valves |  | 232 | 23-Jan-25 A | 17-Nov-25 A | 46098 | 46100
A43750 | Datasheets for Check Valves_IFD/IFC | 2 | 04-Nov-25 A | 17-Nov-25 A | 46098 | 46098
A43740 | Datasheets for Check Valves_RCA | 16 | 02-Sep-25 A | 03-Nov-25 A | 46100 | 46100
A43730 | Datasheets for Check Valves_IFA | 3 | 06-Aug-25 A | 12-Aug-25 A | 46100 | 46100
A43720 | Datasheets for Check Valves_RCC | 16 | 15-May-25 A | 21-Jun-25 A | 46100 | 46100
A43710 | Datasheets for Check Valves_IFR | 2 | 23-Jan-25 A | 14-May-25 A | 46100 | 46100
Datasheets for Butterfly Valves |  | 246 | 16-Jan-25 A | 20-Nov-25 A | 46098 | 46100
A43840 | Datasheets for Butterfly Valves_RCA | 16 | 20-Sep-25 A | 13-Oct-25 A | 46098 | 46098
A43850 | Datasheets for Butterfly Valves_IFD/IFC | 2 | 10-Nov-25 A | 20-Nov-25 A | 46100 | 46100
A43830 | Datasheets for Butterfly Valves_IFA | 3 | 31-Aug-25 A | 03-Sep-25 A | 46100 | 46100
A43820 | Datasheets for Butterfly Valves_RCC | 16 | 04-Aug-25 A | 27-Aug-25 A | 46100 | 46100
A43810 | Datasheets for Butterfly Valves_IFR | 2 | 16-Jan-25 A | 12-Jun-25 A | 46100 | 46100
Datasheets for Needle Valves |  | 200 | 01-Aug-25 A | 22-Aug-25 A | 46098 | 46100
A43900 | Datasheets for Needle Valves_IFD/IFC | 2 | 20-Aug-25 A | 22-Aug-25 A | 46098 | 46098
A43890 | Datasheets for Needle Valves_RCA | 16 | 16-Aug-25 A | 20-Aug-25 A | 46100 | 46100
A43880 | Datasheets for Needle Valves_IFA | 3 | 13-Aug-25 A | 15-Aug-25 A | 46100 | 46100
A43870 | Datasheets for Needle Valves_RCC | 16 | 06-Aug-25 A | 12-Aug-25 A | 46100 | 46100
A43860 | Datasheets for Needle Valves_IFR | 2 | 01-Aug-25 A | 05-Aug-25 A | 46100 | 46100
Datasheets for Insulating Gaskets |  | 58 | 22-Sep-25 A | 13-Jan-26 A | 46098 | 46098
A43950 | Datasheets for Insulating Gaskets_IFD/IFC | 2 | 09-Jan-26 A | 13-Jan-26 A | 46098 | 46098
A43940 | Datasheets for Insulating Gaskets_RCA | 16 | 19-Dec-25 A | 09-Jan-26 A | 46098 | 46098
A43930 | Datasheets for Insulating Gaskets_IFA | 3 | 03-Dec-25 A | 18-Dec-25 A | 46098 | 46098
A43920 | Datasheets for Insulating Gaskets_RCC | 16 | 23-Sep-25 A | 06-Oct-25 A | 46098 | 46098
A43910 | Datasheets for Insulating Gaskets_IFR | 2 | 22-Sep-25 A | 29-Sep-25 A | 46098 | 46098
Datasheets for Flame Arrestors |  | 125 | 20-Apr-25 A | 23-Dec-25 A | 46129 | 46407
A44000 | Datasheets for Flame Arrestors_IFD/IFC | 2 | 19-Dec-25 A | 23-Dec-25 A | 46129 | 46129
A43990 | Datasheets for Flame Arrestors_RCA | 16 | 26-May-25 A | 14-Oct-25 A | 46407 | 46407
A43980 | Datasheets for Flame Arrestors_IFA | 3 | 19-May-25 A | 25-May-25 A | 46407 | 46407
A43970 | Datasheets for Flame Arrestors_RCC | 16 | 12-May-25 A | 18-May-25 A | 46407 | 46407
A43960 | Datasheets for Flame Arrestors_IFR | 2 | 20-Apr-25 A | 11-May-25 A | 46407 | 46407
Datasheets for Flame Bird Screen |  | 193 | 15-Apr-25 A | 23-Dec-25 A | 46129 | 46407
A44050 | Datasheets for Flame Bird Screen_IFD/IFC | 2 | 19-Dec-25 A | 23-Dec-25 A | 46129 | 46129
A44040 | Datasheets for Flame Bird Screen_RCA | 16 | 01-Oct-25 A | 27-Oct-25 A | 46407 | 46407
A44030 | Datasheets for Flame Bird Screen_IFA | 3 | 20-Aug-25 A | 27-Aug-25 A | 46407 | 46407
A44020 | Datasheets for Flame Bird Screen_RCC | 16 | 07-May-25 A | 13-May-25 A | 46407 | 46407
A44010 | Datasheets for Flame Bird Screen_IFR | 2 | 15-Apr-25 A | 06-May-25 A | 46407 | 46407
Datasheets for Hose Coupling |  | 128 | 01-Jul-25 A | 23-Dec-25 A | 46098 | 46098
A44100 | Datasheets for Hose Coupling_IFD/IFC | 2 | 19-Dec-25 A | 23-Dec-25 A | 46098 | 46098
A44090 | Datasheets for Hose Coupling_RCA | 16 | 09-Aug-25 A | 27-Aug-25 A | 46098 | 46098
A44080 | Datasheets for Hose Coupling_IFA | 3 | 05-Aug-25 A | 12-Aug-25 A | 46098 | 46098
A44070 | Datasheets for Hose Coupling_RCC | 16 | 05-Jul-25 A | 25-Jul-25 A | 46098 | 46098
A44060 | Datasheets for Hose Coupling_IFR | 6 | 01-Jul-25 A | 12-Jul-25 A | 46098 | 46098
Datasheets for Strainers |  | 188 | 14-Apr-25 A | 23-Dec-25 A | 46129 | 46407
A44150 | Datasheets for Strainers_IFD/IFC | 2 | 19-Dec-25 A | 23-Dec-25 A | 46129 | 46129
A44140 | Datasheets for Strainers_RCA | 16 | 02-Sep-25 A | 08-Sep-25 A | 46407 | 46407
A44130 | Datasheets for Strainers_IFA | 3 | 13-May-25 A | 01-Sep-25 A | 46407 | 46407
A44120 | Datasheets for Strainers_RCC | 16 | 06-May-25 A | 12-May-25 A | 46407 | 46407
A44110 | Datasheets for Strainers_IFR | 6 | 14-Apr-25 A | 05-May-25 A | 46407 | 46407
Datasheets for Spring Hangers |  | 306 | 25-Apr-25 A | 2026-03-23 | 2026-03-19 | 2027-01-18 | 215
A44200 | Datasheets for Spring Hangers_IFD/IFC | 2 | 2026-03-19 | 2026-03-23 | 2026-03-19 | 2026-03-19 | 215
A44190 | Datasheets for Spring Hangers_RCA | 16 | 2026-02-25 | 2026-03-19 | 2026-12-18 | 2026-12-18 | 215
A44180 | Datasheets for Spring Hangers_IFA | 3 | 2026-02-20 | 2026-02-25 | 2026-12-18 | 2026-12-23 | 215
A44170 | Datasheets for Spring Hangers_RCC | 16 | 01-May-25 A | 15-May-25 A | 46379 | 46401
A44160 | Datasheets for Spring Hangers_IFR | 2 | 25-Apr-25 A | 30-Apr-25 A | 46401 | 46405
Datasheets for Rigid Struts |  | 301 | 15-Apr-25 A | 2026-03-17 | 2026-12-23 | 2027-01-18 | 219
A44250 | Datasheets for Rigid Struts_IFD/IFC | 2 | 2026-03-13 | 2026-03-17 | 2026-12-23 | 2026-12-23 | 219
A44240 | Datasheets for Rigid Struts_RCA | 16 | 2026-02-20 | 2026-03-13 | 2026-12-23 | 2026-12-23 | 219
A44230 | Datasheets for Rigid Struts_IFA | 3 | 10-Dec-25 A | 17-Dec-25 A | 46379 | 46379
A44220 | Datasheets for Rigid Struts_RCC | 16 | 07-May-25 A | 13-May-25 A | 46379 | 46401
A44210 | Datasheets for Rigid Struts_IFR | 2 | 15-Apr-25 A | 06-May-25 A | 46401 | 46405
Datasheet for Piping Speciality Items |  | 131 | 01-Sep-25 A | 2026-03-23 | 2026-04-17 | 2027-01-18 | 215
A54530 | Datasheet for Piping Speciality Items_IFD/IFC | 2 | 2026-03-19 | 2026-03-23 | 2026-04-17 | 2026-04-17 | 215
A54520 | Datasheet for Piping Speciality Items_RCA | 16 | 2026-02-25 | 2026-03-19 | 2026-12-17 | 2026-12-17 | 215
A54510 | Datasheet for Piping Speciality Items_IFA | 3 | 2026-02-20 | 2026-02-25 | 2026-12-17 | 2026-12-22 | 214
A54500 | Datasheet for Piping Speciality Items_RCC | 16 | 15-Sep-25 A | 19-Sep-25 A | 46379 | 46401
A54490 | Datasheet for Piping Speciality Items_IFR | 2 | 01-Sep-25 A | 12-Sep-25 A | 46401 | 46405
Material Requisition for Piping Bulk |  | 260 | 15-Apr-25 A | 16-Jan-26 A | 46100 | 46100
A44760 | Material Requisition for Piping Bulk_IFD/IFC | 2 | 14-Jan-26 A | 16-Jan-26 A | 46100 | 46100
A44750 | Material Requisition for Piping Bulk_RCA | 16 | 30-Oct-25 A | 10-Nov-25 A | 46100 | 46100
A44730 | Material Requisition for Piping Bulk_RCC | 16 | 20-Jul-25 A | 10-Aug-25 A | 46100 | 46100
A44740 | Material Requisition for Piping Bulk_IFA | 3 | 15-Oct-25 A | 29-Oct-25 A | 46100 | 46100
A44720 | Material Requisition for Piping Bulk_IFR | 6 | 15-Apr-25 A | 06-May-25 A | 46100 | 46100
Material Requisition for HDPE Piping Bulk |  | 100 | 15-Oct-25 A | 2026-02-24 | 2026-03-17 | 2026-03-19 | 18
A60080 | Material Requisition for HDPE Piping Bulk_RCA | 16 | 27-Nov-25 A | 16-Dec-25 A | 46098 | 46098
A60090 | Material Requisition for HDPE Piping Bulk_IFD/IFC | 2 | 2026-02-20 | 2026-02-24 | 2026-03-17 | 2026-03-17 | 18
A60070 | Material Requisition for HDPE Piping Bulk_IFA | 3 | 10-Nov-25 A | 27-Nov-25 A | 46098 | 46098
A60060 | Material Requisition for HDPE Piping Bulk_RCC | 16 | 26-Oct-25 A | 10-Nov-25 A | 46098 | 46098
A60050 | Material Requisition for HDPE Piping Bulk_IFR | 6 | 15-Oct-25 A | 26-Oct-25 A | 46098 | 46100
Material Requisition for Manual Valves |  | 129 | 01-Jul-25 A | 10-Oct-25 A | 46100 | 46100
A44810 | Material Requisition for Manual Valves_IFD/IFC | 2 | 22-Sep-25 A | 10-Oct-25 A | 46100 | 46100
A44800 | Material Requisition for Manual Valves_RCA | 16 | 11-Sep-25 A | 15-Sep-25 A | 46100 | 46100
A44790 | Material Requisition for Manual Valves_IFA | 1 | 01-Sep-25 A | 10-Sep-25 A | 46100 | 46100
A44780 | Material Requisition for Manual Valves_RCC | 6 | 21-Aug-25 A | 31-Aug-25 A | 46100 | 46100
A44770 | Material Requisition for Manual Valves_IFR | 1 | 01-Jul-25 A | 12-Jul-25 A | 46100 | 46100
Material Requisition for Piping Speciality Items |  | 147 | 15-Sep-25 A | 2026-04-14 | 2026-04-17 | 2027-01-20 | 202
A44860 | Material Requisition for Piping Speciality Items_IFD/IFC | 2 | 2026-04-09 | 2026-04-14 | 2026-04-17 | 2026-04-17 | 202
A44850 | Material Requisition for Piping Speciality Items_RCA | 16 | 2026-03-19 | 2026-04-09 | 2026-11-30 | 2026-12-22 | 202
A44840 | Material Requisition for Piping Speciality Items_IFA | 3 | 2026-03-13 | 2026-03-19 | 2026-12-22 | 2026-12-25 | 202
A44830 | Material Requisition for Piping Speciality Items_RCC | 16 | 2026-02-20 | 2026-03-13 | 2026-12-28 | 2027-01-18 | 202
A44820 | Material Requisition for Piping Speciality Items_IFR | 6 | 15-Sep-25 A | 16-Sep-25 A | 46405 | 46407
Material Requisition for Spring Hangers |  | 222 | 22-Apr-25 A | 2026-03-25 | 2026-03-19 | 2027-01-20 | 215
A44910 | Material Requisition for Spring Hangers_IFD/IFC | 2 | 2026-03-23 | 2026-03-25 | 2026-03-19 | 2026-03-19 | 215
A44900 | Material Requisition for Spring Hangers_RCA | 16 | 2026-02-20 | 2026-03-13 | 2026-03-30 | 2026-03-30 | 221
A44890 | Material Requisition for Spring Hangers_IFA | 3 | 04-Dec-25 A | 18-Dec-25 A | 46384 | 46384
A44880 | Material Requisition for Spring Hangers_RCC | 16 | 14-May-25 A | 20-May-25 A | 46384 | 46405
A44870 | Material Requisition for Spring Hangers_IFR | 2 | 22-Apr-25 A | 13-May-25 A | 46405 | 46407
Material Requisition for Rigid Struts |  | 216 | 22-Apr-25 A | 2026-03-20 | 2026-12-28 | 2027-01-20 | 219
A44960 | Material Requisition for Rigid Struts_IFD/IFC | 2 | 2026-03-18 | 2026-03-20 | 2026-12-28 | 2026-12-28 | 219
A44950 | Material Requisition for Rigid Struts_RCA | 16 | 2026-02-20 | 2026-03-13 | 2026-12-28 | 2026-12-28 | 221
A44940 | Material Requisition for Rigid Struts_IFA | 3 | 01-Dec-25 A | 12-Dec-25 A | 46384 | 46384
A44930 | Material Requisition for Rigid Struts_RCC | 16 | 14-May-25 A | 20-May-25 A | 46384 | 46405
A44920 | Material Requisition for Rigid Struts_IFR | 6 | 22-Apr-25 A | 13-May-25 A | 46405 | 46407
Utility Station Location Plan |  | 231 | 15-Apr-25 A | 19-Jan-26 A | 46407 | 46407
A43550 | Utility Station Location Plan_IFD/IFC | 2 | 15-Jan-26 A | 19-Jan-26 A | 46407 | 46407
A43540 | Utility Station Location Plan_RCA | 16 | 24-Dec-25 A | 15-Jan-26 A | 46407 | 46407
A43530 | Utility Station Location Plan_IFA | 3 | 19-Dec-25 A | 24-Dec-25 A | 46407 | 46407
A43520 | Utility Station Location Plan_RCC | 16 | 20-Jul-25 A | 08-Aug-25 A | 46407 | 46407
A43510 | Utility Station Location Plan_IFR | 6 | 15-Apr-25 A | 06-May-25 A | 46407 | 46407
30% 3D Model Review Report |  | 108 | 25-Apr-25 A | 21-Aug-25 A | 46083 | 46098
A43590 | 30% 3D Model Review Report_RCA | 16 | 11-Aug-25 A | 15-Aug-25 A | 46083 | 46083
A43600 | 30% 3D Model Review Report_IFD/IFC | 2 | 16-Aug-25 A | 21-Aug-25 A | 46098 | 46098
A43580 | 30% 3D Model Review Report_IFA | 3 | 24-May-25 A | 10-Aug-25 A | 46098 | 46098
A43570 | 30% 3D Model Review Report_RCC | 16 | 17-May-25 A | 23-May-25 A | 46098 | 46098
A43560 | 30% 3D Model Review Report_IFR | 6 | 25-Apr-25 A | 16-May-25 A | 46098 | 46098
30% 3D Model Review Closeout Report |  | 120 | 01-Jul-25 A | 19-Dec-25 A | 46083 | 46099
A43650 | 30% 3D Model Review Closeout Report_IFD/IFC | 2 | 10-Dec-25 A | 19-Dec-25 A | 46083 | 46083
A43640 | 30% 3D Model Review Closeout Report_RCA | 16 | 02-Dec-25 A | 15-Dec-25 A | 46099 | 46099
A43630 | 30% 3D Model Review Closeout Report_IFA | 3 | 27-Nov-25 A | 02-Dec-25 A | 46099 | 46099
A43620 | 30% 3D Model Review Closeout Report_RCC | 16 | 27-Aug-25 A | 27-Nov-25 A | 46099 | 46099
A43610 | 30% 3D Model Review Closeout Report_IFR | 6 | 01-Jul-25 A | 12-Jul-25 A | 46099 | 46099
Plot Plan |  | 228 | 09-Mar-25 A | 25-Oct-25 A | 46083 | 46311
A45260 | Plot Plan_IFD/IFC | 2 | 23-Oct-25 A | 25-Oct-25 A | 46083 | 46083
A45250 | Plot Plan_RCA | 16 | 02-Oct-25 A | 24-Oct-25 A | 46083 | 46083
A45240 | Plot Plan_IFA | 3 | 03-Oct-25 A | 10-Oct-25 A | 46100 | 46100
A45230 | Plot Plan_RCC | 16 | 28-Apr-25 A | 11-Jun-25 A | 46100 | 46100
A55670 | Plot Plan_Preliminary issuance for Plot plan workshop | 6 | 09-Mar-25 A | 12-Mar-25 A | 46311 | 46311
A45220 | Plot Plan_IFR | 6 | 14-Mar-25 A | 27-Apr-25 A | 46311 | 46311
Plot Plan Review Report |  | 121 | 19-Apr-25 A | 16-Oct-25 A | 46407 | 46407
A43400 | Plot Plan Review Report_IFD/IFC | 2 | 10-Oct-25 A | 16-Oct-25 A | 46407 | 46407
A43390 | Plot Plan Review Report_RCA | 16 | 22-Jun-25 A | 28-Jun-25 A | 46407 | 46407
A43380 | Plot Plan Review Report_IFA | 3 | 18-May-25 A | 21-Jun-25 A | 46407 | 46407
A43370 | Plot Plan Review Report_RCC | 16 | 11-May-25 A | 17-May-25 A | 46407 | 46407
A43360 | Plot Plan Review Report_IFR | 6 | 19-Apr-25 A | 10-May-25 A | 46407 | 46407
First Material Take Off |  | 21 | 02-Jun-25 A | 27-Jun-25 A | 46134 | 46134
A45280 | First Material Take Off_RCC | 16 | 09-Jun-25 A | 20-Jun-25 A | 46134 | 46134
A45290 | First Material Take Off_IFD/IFC | 2 | 23-Jun-25 A | 27-Jun-25 A | 46134 | 46134
A45270 | First Material Take Off_IFR | 6 | 02-Jun-25 A | 06-Jun-25 A | 46134 | 46134
Plot Plan Close Out Report |  | 136 | 19-Apr-25 A | 18-Dec-25 A | 46407 | 46407
A43450 | Plot Plan Close Out report_IFD/IFC | 2 | 15-Dec-25 A | 18-Dec-25 A | 46407 | 46407
A43440 | Plot Plan Close Out report_RCA | 16 | 10-Oct-25 A | 27-Oct-25 A | 46407 | 46407
A43430 | Plot Plan Close Out report_IFA | 3 | 10-Oct-25 A | 14-Oct-25 A | 46407 | 46407
A43420 | Plot Plan Close Out report_RCC | 16 | 11-May-25 A | 17-May-25 A | 46407 | 46407
A43410 | Plot Plan Close Out report_IFR | 6 | 19-Apr-25 A | 10-May-25 A | 46407 | 46407
Manual Valves List (Valves MTOs) |  | 231 | 25-Feb-25 A | 23-Dec-25 A | 46407 | 46407
A44710 | Manual Valves List (Valves MTOs)_IFD/IFC | 2 | 19-Dec-25 A | 23-Dec-25 A | 46407 | 46407
A44700 | Manual Valves List (Valves MTOs)_RCC | 16 | 02-Aug-25 A | 25-Aug-25 A | 46407 | 46407
A44690 | Manual Valves List (Valves MTOs)_IFR | 6 | 25-Feb-25 A | 10-Apr-25 A | 46407 | 46407
Technical Bid Evaluation (TBE) for Rigid Struts |  | 43 | 2026-02-20 | 2026-04-21 | 2026-11-23 | 2027-01-20 | 196
A45210 | Technical Bid Evaluation (TBE) for Rigid Struts_IFD/IFC | 2 | 2026-04-17 | 2026-04-21 | 2026-11-23 | 2026-11-30 | 196
A45200 | Technical Bid Evaluation (TBE) for Rigid Struts_RCA | 16 | 2026-03-26 | 2026-04-17 | 2026-11-30 | 2026-12-22 | 196
A45190 | Technical Bid Evaluation (TBE) for Rigid Struts_IFA | 3 | 2026-03-23 | 2026-03-26 | 2026-12-22 | 2026-12-25 | 196
A45180 | Technical Bid Evaluation (TBE) for Rigid Struts_RCC | 16 | 2026-02-27 | 2026-03-23 | 2026-12-28 | 2027-01-18 | 196
A45170 | Technical Bid Evaluation (TBE) for Rigid Struts_IFR | 6 | 2026-02-20 | 2026-02-27 | 2027-01-18 | 2027-01-20 | 196
60% 3D Model Review Report |  | 64 | 26-Sep-25 A | 21-Jan-26 A | 46100 | 46407
A44300 | 60% 3D Model Review Report_IFD/IFC | 2 | 19-Jan-26 A | 21-Jan-26 A | 46100 | 46100
A44290 | 60% 3D Model Review Report_RCA | 16 | 24-Dec-25 A | 15-Jan-26 A | 46407 | 46407
A44280 | 60% 3D Model Review Report_IFA | 3 | 19-Dec-25 A | 24-Dec-25 A | 46407 | 46407
A44270 | 60% 3D Model Review Report_RCC | 16 | 13-Oct-25 A | 04-Nov-25 A | 46407 | 46407
A44260 | 60% 3D Model Review Report_IFR | 6 | 26-Sep-25 A | 02-Oct-25 A | 46407 | 46407
60% 3D Model Review Closeout Report |  | 48 | 2026-02-20 | 2026-04-29 | 2026-07-22 | 2027-01-20 | 191
A44350 | 60% 3D Model Review Closeout Report_IFD/IFC | 2 | 2026-04-27 | 2026-04-29 | 2026-07-22 | 2026-08-06 | 191
A44340 | 60% 3D Model Review Closeout Report_RCA | 16 | 2026-04-03 | 2026-04-27 | 2026-10-22 | 2026-11-13 | 191
A44330 | 60% 3D Model Review Closeout Report_IFA | 3 | 2026-03-31 | 2026-04-03 | 2026-11-13 | 2026-11-18 | 164
A44320 | 60% 3D Model Review Closeout Report_RCC | 16 | 2026-03-09 | 2026-03-30 | 2026-12-28 | 2027-01-18 | 164
A44310 | 60% 3D Model Review Closeout Report_IFR | 11 | 2026-02-20 | 2026-03-09 | 2027-01-18 | 2027-01-20 | 108
Piping Stress Analysis Reports |  | 127 | 06-Jul-25 A | 23-Jan-26 A | 46162 | 46162
A44680 | Piping Stress Analysis Reports_IFD/IFC | 6 | 15-Jan-26 A | 23-Jan-26 A | 46162 | 46162
A44670 | Piping Stress Analysis Reports_RCA | 16 | 05-Jan-26 A | 14-Jan-26 A | 46162 | 46162
A44660 | Piping Stress Analysis Reports_IFA | 11 | 19-Dec-25 A | 05-Jan-26 A | 46162 | 46162
A44650 | Piping Stress Analysis Reports_RCC | 16 | 20-Jul-25 A | 07-Aug-25 A | 46162 | 46162
A44640 | Piping Stress Analysis Reports_IFR | 23 | 06-Jul-25 A | 31-Jul-25 A | 46162 | 46162
Piping GA Drawings & Key Plan for Piping GADs |  | 88 | 01-Dec-25 A | 2026-04-07 | 2026-03-19 | 2027-01-20 | 206
A44580 | Piping GA Drawings & Key Plan for Piping GADs_IFD/IFC | 6 | 2026-03-31 | 2026-04-07 | 2026-03-19 | 2026-03-19 | 206
A44570 | Piping GA Drawings & Key Plan for Piping GADs_RCA | 16 | 2026-03-09 | 2026-03-30 | 2026-03-19 | 2026-03-19 | 206
A44560 | Piping GA Drawings & Key Plan for Piping GADs_IFA | 11 | 2026-02-20 | 2026-03-09 | 2026-12-07 | 2026-12-22 | 206
A44550 | Piping GA Drawings & Key Plan for Piping GADs_RCC | 16 | 01-Dec-25 A | 02-Dec-25 A | 46378 | 46400
A44540 | Piping GA Drawings & Key Plan for Piping GADs_IFR | 37 | 05-Dec-25 A | 18-Dec-25 A | 46400 | 46407
Piping Isometrics (large bore) |  | 94 | 14-Jan-26 A | 2026-06-04 | 2026-03-13 | 2026-08-28 | 62
A44400 | Piping Isometrics (large bore)_IFD/IFC | 6 | 2026-05-27 | 2026-06-04 | 2026-03-13 | 2026-04-17 | 62
A44390 | Piping Isometrics (large bore)_RCA | 16 | 2026-05-06 | 2026-05-27 | 2026-06-23 | 2026-07-15 | 62
A44380 | Piping Isometrics (large bore)_IFA | 11 | 2026-04-20 | 2026-05-05 | 2026-07-15 | 2026-07-30 | 62
A44370 | Piping Isometrics (large bore)_RCC | 16 | 2026-03-30 | 2026-04-20 | 2026-07-30 | 2026-08-21 | 62
A44360 | Piping Isometrics (large bore)_IFR | 34 | 14-Jan-26 A | 2026-03-27 | 2026-08-21 | 2026-08-28 | 15
Second Material Take Off |  | 24 | 23-Dec-25 A | 2026-02-24 | 2026-03-25 | 2026-03-27 | 23
A45320 | Second Material Take Off_IFD/IFC | 2 | 23-Jan-26 A | 2026-02-24 | 2026-03-25 | 2026-03-25 | 23
A45310 | Second Material Take Off_RCC | 16 | 16-Jan-26 A | 23-Jan-26 A | 46106 | 46106
A45300 | Second Material Take Off_IFR | 6 | 23-Dec-25 A | 15-Jan-26 A | 46106 | 46108
90% 3D Model Review Report |  | 67 | 2026-03-06 | 2026-06-08 | 2026-11-12 | 2027-01-20 | 162
A44450 | 90% 3D Model Review Report_IFD/IFC | 2 | 2026-06-04 | 2026-06-08 | 2026-11-12 | 2026-11-20 | 162
A44440 | 90% 3D Model Review Report_RCA | 16 | 2026-04-09 | 2026-05-01 | 2026-11-30 | 2026-12-22 | 186
A44430 | 90% 3D Model Review Report_IFA | 3 | 2026-04-06 | 2026-04-09 | 2026-12-22 | 2026-12-25 | 186
A44420 | 90% 3D Model Review Report_RCC | 16 | 2026-03-13 | 2026-04-06 | 2026-12-28 | 2027-01-18 | 186
A44410 | 90% 3D Model Review Report_IFR | 6 | 2026-03-06 | 2026-03-13 | 2027-01-18 | 2027-01-20 | 179
Piping Isometrics(Small Bore) |  | 41 | 2026-03-06 | 2026-05-01 | 2026-03-27 | 2026-05-22 | 15
A44530 | Piping Isometrics(Small Bore)_IFD/IFC | 2 | 2026-04-29 | 2026-05-01 | 2026-03-27 | 2026-04-28 | 15
A44520 | Piping Isometrics(Small Bore)_RCC | 16 | 2026-04-07 | 2026-04-29 | 2026-04-29 | 2026-05-20 | 15
A44510 | Piping Isometrics(Small Bore)_IFR | 23 | 2026-03-06 | 2026-04-07 | 2026-05-20 | 2026-05-22 | 15
Piping Tie-Ins Schedule |  | 43 | 2026-02-20 | 2026-04-21 | 2026-08-19 | 2026-10-16 | 128
A44630 | Piping Tie-Ins Schedule_IFD/IFC | 2 | 2026-04-17 | 2026-04-21 | 2026-08-19 | 2026-08-26 | 128
A44620 | Piping Tie-Ins Schedule_RCA | 16 | 2026-03-26 | 2026-04-17 | 2026-08-26 | 2026-09-17 | 128
A44610 | Piping Tie-Ins Schedule_IFA | 3 | 2026-03-23 | 2026-03-26 | 2026-09-17 | 2026-09-22 | 128
A44600 | Piping Tie-Ins Schedule_RCC | 16 | 2026-02-27 | 2026-03-23 | 2026-09-23 | 2026-10-14 | 128
A44590 | Piping Tie-Ins Schedule_IFR | 6 | 2026-02-20 | 2026-02-27 | 2026-10-14 | 2026-10-16 | 128
90% 3D Model Review Closeout Report |  | 43 | 2026-03-13 | 2026-05-13 | 2026-11-20 | 2027-01-20 | 181
A44500 | 90% 3D Model Review Closeout Report_IFD/IFC | 2 | 2026-05-11 | 2026-05-13 | 2026-11-20 | 2026-11-27 | 181
A44490 | 90% 3D Model Review Closeout Report_RCA | 16 | 2026-04-17 | 2026-05-11 | 2026-11-30 | 2026-12-22 | 181
A44480 | 90% 3D Model Review Closeout Report_IFA | 3 | 2026-04-14 | 2026-04-17 | 2026-12-22 | 2026-12-25 | 181
A44470 | 90% 3D Model Review Closeout Report_RCC | 16 | 2026-03-23 | 2026-04-14 | 2026-12-28 | 2027-01-18 | 181
A44460 | 90% 3D Model Review Closeout Report_IFR | 6 | 2026-03-13 | 2026-03-23 | 2027-01-18 | 2027-01-20 | 179
Final Material Take Off |  | 24 | 2026-03-06 | 2026-04-08 | 2026-03-27 | 2026-05-04 | 18
A45350 | Final Material Take Off_IFD/IFC | 2 | 2026-04-06 | 2026-04-08 | 2026-03-27 | 2026-04-03 | 18
A45340 | Final Material Take Off_RCC | 16 | 2026-03-13 | 2026-04-06 | 2026-04-09 | 2026-04-30 | 18
A45330 | Final Material Take Off_IFR | 6 | 2026-03-06 | 2026-03-13 | 2026-04-30 | 2026-05-04 | 15
Mechanical |  | 346 | 31-Dec-24 A | 2026-04-14 | 2026-03-02 | 2027-01-20 | 202
Mechanical Static |  | 346 | 31-Dec-24 A | 2026-04-14 | 2026-03-02 | 2027-01-20 | 202
Mechanical Datasheet For Psa2 Feed Gas Compressor 1St Stage Suction Drum (Tag No. 13-Vv-705) |  | 132 | 31-Dec-24 A | 10-May-25 A | 46083 | 46407
A54630 | Mechanical Datasheet For Psa2 Feed Gas Compressor 1St Stage Suction Drum (Tag No. 13-Vv-705)_IFD/IFC | 2 | 04-May-25 A | 10-May-25 A | 46083 | 46083
A54620 | Mechanical Datasheet For Psa2 Feed Gas Compressor 1St Stage Suction Drum (Tag No. 13-Vv-705)_RCA | 16 | 27-Apr-25 A | 03-May-25 A | 46407 | 46407
A54610 | Mechanical Datasheet For Psa2 Feed Gas Compressor 1St Stage Suction Drum (Tag No. 13-Vv-705)_IFA | 3 | 20-Apr-25 A | 26-Apr-25 A | 46407 | 46407
A54600 | Mechanical Datasheet For Psa2 Feed Gas Compressor 1St Stage Suction Drum (Tag No. 13-Vv-705)_RCC | 16 | 07-Feb-25 A | 19-Apr-25 A | 46407 | 46407
A54590 | Mechanical Datasheet For Psa2 Feed Gas Compressor 1St Stage Suction Drum (Tag No. 13-Vv-705)_IFR | 1 | 31-Dec-24 A | 06-Feb-25 A | 46407 | 46407
Mechanical Datasheet For Psa2 Feed Gas Compressor 2Nd Stage Suction Drum (Tag No. 13-Vv-706) |  | 131 | 31-Dec-24 A | 10-May-25 A | 46083 | 46407
A54680 | Mechanical Datasheet For Psa2 Feed Gas Compressor 2Nd Stage Suction Drum (Tag No. 13-Vv-706)_IFD/IFC | 2 | 04-May-25 A | 10-May-25 A | 46083 | 46083
A54670 | Mechanical Datasheet For Psa2 Feed Gas Compressor 2Nd Stage Suction Drum (Tag No. 13-Vv-706)_RCA | 16 | 27-Apr-25 A | 03-May-25 A | 46407 | 46407
A54660 | Mechanical Datasheet For Psa2 Feed Gas Compressor 2Nd Stage Suction Drum (Tag No. 13-Vv-706)_IFA | 3 | 20-Apr-25 A | 26-Apr-25 A | 46407 | 46407
A54650 | Mechanical Datasheet For Psa2 Feed Gas Compressor 2Nd Stage Suction Drum (Tag No. 13-Vv-706)_RCC | 16 | 07-Feb-25 A | 19-Apr-25 A | 46407 | 46407
A54640 | Mechanical Datasheet For Psa2 Feed Gas Compressor 2Nd Stage Suction Drum (Tag No. 13-Vv-706)_IFR | 1 | 31-Dec-24 A | 06-Feb-25 A | 46407 | 46407
Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Suction Drum (Tag No. 13-Vv-707) |  | 130 | 31-Dec-24 A | 10-May-25 A | 46083 | 46407
A54730 | Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Suction Drum (Tag No. 13-Vv-707)_IFD/IFC | 2 | 04-May-25 A | 10-May-25 A | 46083 | 46083
A54720 | Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Suction Drum (Tag No. 13-Vv-707)_RCA | 16 | 27-Apr-25 A | 03-May-25 A | 46407 | 46407
A54710 | Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Suction Drum (Tag No. 13-Vv-707)_IFA | 3 | 20-Apr-25 A | 26-Apr-25 A | 46407 | 46407
A54700 | Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Suction Drum (Tag No. 13-Vv-707)_RCC | 16 | 07-Feb-25 A | 19-Apr-25 A | 46407 | 46407
A54690 | Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Suction Drum (Tag No. 13-Vv-707)_IFR | 1 | 31-Dec-24 A | 06-Feb-25 A | 46407 | 46407
Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Discharge Drum (Tag No. 13-Vv-Xxx) |  | 148 | 31-Dec-24 A | 05-Jul-25 A | 46083 | 46407
A54780 | Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Discharge Drum (Tag No. 13-Vv-Xxx)_IFD/IFC | 2 | 29-Jun-25 A | 05-Jul-25 A | 46083 | 46083
A54770 | Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Discharge Drum (Tag No. 13-Vv-Xxx)_RCA | 16 | 22-Jun-25 A | 28-Jun-25 A | 46407 | 46407
A54760 | Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Discharge Drum (Tag No. 13-Vv-Xxx)_IFA | 3 | 20-Apr-25 A | 21-Jun-25 A | 46407 | 46407
A54750 | Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Discharge Drum (Tag No. 13-Vv-Xxx)_RCC | 16 | 25-Jan-25 A | 19-Apr-25 A | 46407 | 46407
A54740 | Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Discharge Drum (Tag No. 13-Vv-Xxx)_IFR | 1 | 31-Dec-24 A | 24-Jan-25 A | 46407 | 46407
Mechanical Datasheet For Psa2 Off Gas Buffer Drum (Tag No. 13-Vv-712) |  | 128 | 31-Dec-24 A | 10-May-25 A | 46083 | 46407
A54830 | Mechanical Datasheet For Psa2 Off Gas Buffer Drum (Tag No. 13-Vv-712)_IFD/IFC | 2 | 04-May-25 A | 10-May-25 A | 46083 | 46083
A54820 | Mechanical Datasheet For Psa2 Off Gas Buffer Drum (Tag No. 13-Vv-712)_RCA | 16 | 27-Apr-25 A | 03-May-25 A | 46407 | 46407
A54810 | Mechanical Datasheet For Psa2 Off Gas Buffer Drum (Tag No. 13-Vv-712)_IFA | 3 | 20-Apr-25 A | 26-Apr-25 A | 46407 | 46407
A54800 | Mechanical Datasheet For Psa2 Off Gas Buffer Drum (Tag No. 13-Vv-712)_RCC | 16 | 07-Feb-25 A | 19-Apr-25 A | 46407 | 46407
A54790 | Mechanical Datasheet For Psa2 Off Gas Buffer Drum (Tag No. 13-Vv-712)_IFR | 1 | 31-Dec-24 A | 06-Feb-25 A | 46407 | 46407
Mechanical Datasheet For Psa2 Off Gas Compressor 2Nd Stage Suction Drum (Tag No. 13-Vv-713) |  | 127 | 31-Dec-24 A | 10-May-25 A | 46083 | 46407
A54880 | Mechanical Datasheet For Psa2 Off Gas Compressor 2Nd Stage Suction Drum (Tag No. 13-Vv-713)_IFD/IFC | 2 | 04-May-25 A | 10-May-25 A | 46083 | 46083
A54870 | Mechanical Datasheet For Psa2 Off Gas Compressor 2Nd Stage Suction Drum (Tag No. 13-Vv-713)_RCA | 16 | 27-Apr-25 A | 03-May-25 A | 46407 | 46407
A54860 | Mechanical Datasheet For Psa2 Off Gas Compressor 2Nd Stage Suction Drum (Tag No. 13-Vv-713)_IFA | 3 | 20-Apr-25 A | 26-Apr-25 A | 46407 | 46407
A54850 | Mechanical Datasheet For Psa2 Off Gas Compressor 2Nd Stage Suction Drum (Tag No. 13-Vv-713)_RCC | 16 | 07-Feb-25 A | 19-Apr-25 A | 46407 | 46407
A54840 | Mechanical Datasheet For Psa2 Off Gas Compressor 2Nd Stage Suction Drum (Tag No. 13-Vv-713)_IFR | 1 | 31-Dec-24 A | 06-Feb-25 A | 46407 | 46407
Mechanical Datasheet For Psa2 Slop Drum (Tag No. 70-Vv-1415) |  | 126 | 01-Jan-25 A | 10-May-25 A | 46083 | 46407
A54900 | Mechanical Datasheet For Psa2 Slop Drum (Tag No. 70-Vv-1415)_IFD/IFC | 2 | 04-May-25 A | 10-May-25 A | 46083 | 46083
A54890 | Mechanical Datasheet For Psa2 Slop Drum (Tag No. 70-Vv-1415)_RCA | 16 | 27-Apr-25 A | 03-May-25 A | 46407 | 46407
A27230 | Mechanical Datasheet For Psa2 Slop Drum (Tag No. 70-Vv-1415)_IFA | 3 | 20-Apr-25 A | 26-Apr-25 A | 46407 | 46407
A27220 | Mechanical Datasheet For Psa2 Slop Drum (Tag No. 70-Vv-1415)_RCC | 16 | 07-Feb-25 A | 19-Apr-25 A | 46407 | 46407
A27210 | Mechanical Datasheet For Psa2 Slop Drum (Tag No. 70-Vv-1415)_IFR | 1 | 01-Jan-25 A | 06-Feb-25 A | 46407 | 46407
Mechanical Datasheet For Psa2 Feed Gas Compressor 1St Stage Cooler (Tag No. 13-He-703) |  | 125 | 07-Jan-25 A | 10-May-25 A | 46083 | 46083
A54950 | Mechanical Datasheet For Psa2 Feed Gas Compressor 1St Stage Cooler (Tag No. 13-He-703)_IFD/IFC | 2 | 04-May-25 A | 10-May-25 A | 46083 | 46083
A54940 | Mechanical Datasheet For Psa2 Feed Gas Compressor 1St Stage Cooler (Tag No. 13-He-703)_RCA | 16 | 27-Apr-25 A | 03-May-25 A | 46083 | 46083
A54930 | Mechanical Datasheet For Psa2 Feed Gas Compressor 1St Stage Cooler (Tag No. 13-He-703)_IFA | 3 | 20-Apr-25 A | 26-Apr-25 A | 46083 | 46083
A54920 | Mechanical Datasheet For Psa2 Feed Gas Compressor 1St Stage Cooler (Tag No. 13-He-703)_RCC | 16 | 07-Feb-25 A | 19-Apr-25 A | 46083 | 46083
A54910 | Mechanical Datasheet For Psa2 Feed Gas Compressor 1St Stage Cooler (Tag No. 13-He-703)_IFR | 1 | 07-Jan-25 A | 06-Feb-25 A | 46083 | 46083
Mechanical Datasheet For Psa2 Feed Gas Compressor 2Nd Stage Cooler (Tag No. 13-He-704) |  | 104 | 14-Feb-25 A | 03-May-25 A | 46083 | 46083
A55000 | Mechanical Datasheet For Psa2 Feed Gas Compressor 2Nd Stage Cooler (Tag No. 13-He-704)_IFD/IFC | 2 | 01-May-25 A | 03-May-25 A | 46083 | 46083
A54990 | Mechanical Datasheet For Psa2 Feed Gas Compressor 2Nd Stage Cooler (Tag No. 13-He-704)_RCA | 16 | 22-Mar-25 A | 30-Apr-25 A | 46083 | 46083
A54980 | Mechanical Datasheet For Psa2 Feed Gas Compressor 2Nd Stage Cooler (Tag No. 13-He-704)_IFA | 3 | 15-Mar-25 A | 21-Mar-25 A | 46083 | 46083
A54970 | Mechanical Datasheet For Psa2 Feed Gas Compressor 2Nd Stage Cooler (Tag No. 13-He-704)_RCC | 16 | 08-Mar-25 A | 14-Mar-25 A | 46083 | 46083
A54960 | Mechanical Datasheet For Psa2 Feed Gas Compressor 2Nd Stage Cooler (Tag No. 13-He-704)_IFR | 1 | 14-Feb-25 A | 07-Mar-25 A | 46083 | 46083
Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Cooler (Tag No. 13-He-703) |  | 142 | 20-Jan-25 A | 14-Jun-25 A | 46083 | 46083
A55050 | Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Cooler (Tag No. 13-He-703)_IFD/IFC | 2 | 11-Jun-25 A | 14-Jun-25 A | 46083 | 46083
A55040 | Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Cooler (Tag No. 13-He-703)_RCA | 16 | 08-Jun-25 A | 10-Jun-25 A | 46083 | 46083
A55030 | Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Cooler (Tag No. 13-He-703)_IFA | 3 | 20-Apr-25 A | 26-Apr-25 A | 46083 | 46083
A55020 | Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Cooler (Tag No. 13-He-703)_RCC | 16 | 27-Feb-25 A | 19-Apr-25 A | 46083 | 46083
A55010 | Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Cooler (Tag No. 13-He-703)_IFR | 1 | 20-Jan-25 A | 26-Feb-25 A | 46083 | 46083
Mechanical Datasheet For Psa2 Off Gas Compressor Interstage Cooler(Tag No. 13-He-708) |  | 119 | 25-Feb-25 A | 09-May-25 A | 46083 | 46083
A55090 | Mechanical Datasheet For Psa2 Off Gas Compressor Interstage Cooler(Tag No. 13-He-708)_IFD/IFC | 2 | 03-May-25 A | 09-May-25 A | 46083 | 46083
A55080 | Mechanical Datasheet For Psa2 Off Gas Compressor Interstage Cooler(Tag No. 13-He-708)_RCA | 16 | 26-Apr-25 A | 02-May-25 A | 46083 | 46083
A55070 | Mechanical Datasheet For Psa2 Off Gas Compressor Interstage Cooler(Tag No. 13-He-708)_RCC | 16 | 27-Feb-25 A | 04-Mar-25 A | 46083 | 46083
A27430 | Mechanical Datasheet For Psa2 Off Gas Compressor Interstage Cooler(Tag No. 13-He-708)_IFA | 3 | 05-Mar-25 A | 25-Apr-25 A | 46083 | 46083
A55060 | Mechanical Datasheet For Psa2 Off Gas Compressor Interstage Cooler(Tag No. 13-He-708)_IFR | 1 | 25-Feb-25 A | 26-Feb-25 A | 46083 | 46083
Mechanical Datasheet For Psa2 Off Gas Compressor Aftercooler(Tag No. 13-He-709) |  | 104 | 25-Feb-25 A | 09-May-25 A | 46083 | 46083
A55140 | Mechanical Datasheet For Psa2 Off Gas Compressor Aftercooler(Tag No. 13-He-709)_IFD/IFC | 2 | 03-May-25 A | 09-May-25 A | 46083 | 46083
A55130 | Mechanical Datasheet For Psa2 Off Gas Compressor Aftercooler(Tag No. 13-He-709)_RCA | 16 | 26-Apr-25 A | 02-May-25 A | 46083 | 46083
A55120 | Mechanical Datasheet For Psa2 Off Gas Compressor Aftercooler(Tag No. 13-He-709)_IFA | 3 | 05-Mar-25 A | 25-Apr-25 A | 46083 | 46083
A55110 | Mechanical Datasheet For Psa2 Off Gas Compressor Aftercooler(Tag No. 13-He-709)_RCC | 16 | 27-Feb-25 A | 04-Mar-25 A | 46083 | 46083
A55100 | Mechanical Datasheet For Psa2 Off Gas Compressor Aftercooler(Tag No. 13-He-709)_IFR | 1 | 25-Feb-25 A | 26-Feb-25 A | 46083 | 46083
Mechanical Datasheet For Psa2 Off Gas Compressor Discharge Dripleg -13-Sp-7004 |  | 119 | 01-Jan-25 A | 10-May-25 A | 46083 | 46407
A55170 | Mechanical Datasheet For Psa2 Off Gas Compressor Discharge Dripleg -13-Sp-7004_IFD/IFC | 2 | 04-May-25 A | 10-May-25 A | 46083 | 46083
A55160 | Mechanical Datasheet For Psa2 Off Gas Compressor Discharge Dripleg -13-Sp-7004_RCA | 16 | 27-Apr-25 A | 03-May-25 A | 46407 | 46407
A55150 | Mechanical Datasheet For Psa2 Off Gas Compressor Discharge Dripleg -13-Sp-7004_IFA | 3 | 20-Apr-25 A | 26-Apr-25 A | 46407 | 46407
A27520 | Mechanical Datasheet For Psa2 Off Gas Compressor Discharge Dripleg -13-Sp-7004_RCC | 16 | 25-Jan-25 A | 19-Apr-25 A | 46407 | 46407
A27510 | Mechanical Datasheet For Psa2 Off Gas Compressor Discharge Dripleg -13-Sp-7004_IFR | 1 | 01-Jan-25 A | 24-Jan-25 A | 46407 | 46407
Mechanical Datasheet For C4 Guard Adsorber Regeneration Gas Cooler(Tag No. 50-He-1410) |  | 118 | 27-Feb-25 A | 10-May-25 A | 46083 | 46083
A55220 | Mechanical Datasheet For C4 Guard Adsorber Regeneration Gas Cooler(Tag No. 50-He-1410)_IFD/IFC | 2 | 04-May-25 A | 10-May-25 A | 46083 | 46083
A55210 | Mechanical Datasheet For C4 Guard Adsorber Regeneration Gas Cooler(Tag No. 50-He-1410)_RCA | 16 | 27-Apr-25 A | 03-May-25 A | 46083 | 46083
A55200 | Mechanical Datasheet For C4 Guard Adsorber Regeneration Gas Cooler(Tag No. 50-He-1410)_IFA | 3 | 20-Apr-25 A | 26-Apr-25 A | 46083 | 46083
A55190 | Mechanical Datasheet For C4 Guard Adsorber Regeneration Gas Cooler(Tag No. 50-He-1410)_RCC | 16 | 21-Mar-25 A | 19-Apr-25 A | 46083 | 46083
A55180 | Mechanical Datasheet For C4 Guard Adsorber Regeneration Gas Cooler(Tag No. 50-He-1410)_IFR | 1 | 27-Feb-25 A | 20-Mar-25 A | 46083 | 46083
Mechanical Datasheet For Vhp Boiler Feed Water Preheater Dripleg |  | 212 | 01-Jul-25 A | 2026-04-14 | 2026-03-02 | 2027-01-20 | 202
A55260 | Mechanical Datasheet For Vhp Boiler Feed Water Preheater Dripleg_IFD/IFC | 2 | 2026-04-09 | 2026-04-14 | 2026-03-02 | 2026-03-02 | 202
A55250 | Mechanical Datasheet For Vhp Boiler Feed Water Preheater Dripleg_RCA | 16 | 2026-03-19 | 2026-04-09 | 2026-11-30 | 2026-12-22 | 202
A55240 | Mechanical Datasheet For Vhp Boiler Feed Water Preheater Dripleg_IFA | 3 | 2026-03-13 | 2026-03-19 | 2026-12-22 | 2026-12-25 | 202
A55230 | Mechanical Datasheet For Vhp Boiler Feed Water Preheater Dripleg_RCC | 16 | 2026-02-20 | 2026-03-13 | 2026-12-28 | 2027-01-18 | 202
A27610 | Mechanical Datasheet For Vhp Boiler Feed Water Preheater Dripleg_IFR | 1 | 01-Jul-25 A | 12-Jul-25 A | 46405 | 46407
Mechanical Datasheet For Off-Gas Compressor Coalescer |  | 34 | 13-Jan-25 A | 03-Mar-25 A | 46083 | 46083
A27700 | Mechanical Datasheet For Off-Gas Compressor Coalescer_IFD/IFC | 2 | 25-Feb-25 A | 03-Mar-25 A | 46083 | 46083
A55300 | Mechanical Datasheet For Off-Gas Compressor Coalescer_RCA | 16 | 18-Feb-25 A | 24-Feb-25 A | 46083 | 46083
A55290 | Mechanical Datasheet For Off-Gas Compressor Coalescer_IFA | 3 | 11-Feb-25 A | 17-Feb-25 A | 46083 | 46083
A55280 | Mechanical Datasheet For Off-Gas Compressor Coalescer_RCC | 16 | 04-Feb-25 A | 10-Feb-25 A | 46083 | 46083
A55270 | Mechanical Datasheet For Off-Gas Compressor Coalescer_IFR | 1 | 13-Jan-25 A | 03-Feb-25 A | 46083 | 46083
Mechanical Datasheet For Guard Adsorber Regeneration Gas Coalescer |  | 116 | 06-Jan-25 A | 10-May-25 A | 46083 | 46083
A55350 | Mechanical Datasheet For Guard Adsorber Regeneration Gas Coalescer_IFD/IFC | 2 | 04-May-25 A | 10-May-25 A | 46083 | 46083
A55340 | Mechanical Datasheet For Guard Adsorber Regeneration Gas Coalescer_RCA | 16 | 27-Apr-25 A | 03-May-25 A | 46083 | 46083
A55330 | Mechanical Datasheet For Guard Adsorber Regeneration Gas Coalescer_IFA | 3 | 20-Apr-25 A | 26-Apr-25 A | 46083 | 46083
A55320 | Mechanical Datasheet For Guard Adsorber Regeneration Gas Coalescer_RCC | 16 | 15-Mar-25 A | 19-Apr-25 A | 46083 | 46083
A55310 | Mechanical Datasheet For Guard Adsorber Regeneration Gas Coalescer_IFR | 1 | 06-Jan-25 A | 14-Mar-25 A | 46083 | 46083
Mechanical Datasheet For Tail Gas Silencer |  | 211 | 01-Jul-25 A | 2026-04-14 | 2026-11-30 | 2027-01-20 | 202
A55390 | Mechanical Datasheet For Tail Gas Silencer_IFD/IFC | 2 | 2026-04-09 | 2026-04-14 | 2026-11-30 | 2026-11-30 | 202
A27790 | Mechanical Datasheet For Tail Gas Silencer_RCA | 16 | 2026-03-19 | 2026-04-09 | 2026-11-30 | 2026-12-22 | 202
A55380 | Mechanical Datasheet For Tail Gas Silencer_IFA | 3 | 2026-03-13 | 2026-03-19 | 2026-12-22 | 2026-12-25 | 202
A55370 | Mechanical Datasheet For Tail Gas Silencer_RCC | 16 | 2026-02-20 | 2026-03-13 | 2026-12-28 | 2027-01-18 | 202
A55360 | Mechanical Datasheet For Tail Gas Silencer_IFR | 1 | 01-Jul-25 A | 12-Jul-25 A | 46405 | 46407
Material Requisiton for Coalscer |  | 118 | 28-Feb-25 A | 14-May-25 A | 46083 | 46083
A45450 | Material Requisiton for Coalscer_IFD/IFC | 2 | 08-May-25 A | 14-May-25 A | 46083 | 46083
A45440 | Material Requisiton for Coalscer_RCA | 16 | 01-May-25 A | 07-May-25 A | 46083 | 46083
A45430 | Material Requisiton for Coalscer_IFA | 3 | 22-Apr-25 A | 30-Apr-25 A | 46083 | 46083
A45420 | Material Requisiton for Coalscer_RCC | 16 | 22-Mar-25 A | 21-Apr-25 A | 46083 | 46083
A45410 | Material Requisiton for Coalscer_IFR | 6 | 28-Feb-25 A | 21-Mar-25 A | 46083 | 46083
Material Requisiton for Shell and Tube Heat Exchangers |  | 153 | 21-Feb-25 A | 20-Jun-25 A | 46083 | 46083
A45390 | Material Requisiton for Heat Exchangers_RCA | 16 | 11-Jun-25 A | 15-Jun-25 A | 46083 | 46083
A45380 | Material Requisiton for Heat Exchangers_IFA | 3 | 06-Jun-25 A | 10-Jun-25 A | 46083 | 46083
A45370 | Material Requisiton for Heat Exchangers_RCC | 16 | 01-Jun-25 A | 05-Jun-25 A | 46083 | 46083
A45400 | Material Requisiton for Heat Exchangers_IFD/IFC | 2 | 16-Jun-25 A | 20-Jun-25 A | 46083 | 46083
A45360 | Material Requisiton for Heat Exchangers_IFR | 6 | 21-Feb-25 A | 14-Mar-25 A | 46083 | 46083
Material Requisiton for Pressure Vessels & Internals |  | 122 | 17-Jan-25 A | 09-May-25 A | 46083 | 46083
A45950 | Material Requisiton for Pressure Vessels & Internals_IFD/IFC | 2 | 03-May-25 A | 09-May-25 A | 46083 | 46083
A45940 | Material Requisiton for Pressure Vessels & Internals_RCA | 16 | 26-Apr-25 A | 02-May-25 A | 46083 | 46083
A45930 | Material Requisiton for Pressure Vessels & Internals_IFA | 3 | 15-Feb-25 A | 25-Apr-25 A | 46083 | 46083
A45920 | Material Requisiton for Pressure Vessels & Internals_RCC | 16 | 08-Feb-25 A | 14-Feb-25 A | 46083 | 46083
A45910 | Material Requisiton for Pressure Vessels & Internals_IFR | 6 | 17-Jan-25 A | 07-Feb-25 A | 46083 | 46083
Mechanical Rotating |  | 151 | 04-Jan-25 A | 28-Jun-25 A | 46083 | 46083
Mechanical Datasheet For Sanitary Water Collection Pump |  | 132 | 05-Feb-25 A | 10-May-25 A | 46083 | 46083
A54580 | Mechanical Datasheet For Sanitary Water Collection Pump_IFD/IFC | 2 | 04-May-25 A | 10-May-25 A | 46083 | 46083
A54570 | Mechanical Datasheet For Sanitary Water Collection Pump_RCA | 16 | 27-Apr-25 A | 03-May-25 A | 46083 | 46083
A54560 | Mechanical Datasheet For Sanitary Water Collection Pump_IFA | 3 | 20-Apr-25 A | 26-Apr-25 A | 46083 | 46083
A54550 | Mechanical Datasheet For Sanitary Water Collection Pump_RCC | 16 | 27-Feb-25 A | 19-Apr-25 A | 46083 | 46083
A54540 | Mechanical Datasheet For Sanitary Water Collection Pump_IFR | 2 | 05-Feb-25 A | 26-Feb-25 A | 46083 | 46083
Mechanical Data Sheet for EOT Crane for Feed Gas Compressor |  | 151 | 27-Jan-25 A | 28-Jun-25 A | 46083 | 46083
A45650 | Mechanical Data Sheet for EOT Crane for Feed Gas Compressor_IFD/IFC | 2 | 22-Jun-25 A | 28-Jun-25 A | 46083 | 46083
A45640 | Mechanical Data Sheet for EOT Crane for Feed Gas Compressor_RCA | 16 | 11-Jun-25 A | 21-Jun-25 A | 46083 | 46083
A45630 | Mechanical Data Sheet for EOT Crane for Feed Gas Compressor_IFA | 3 | 20-Apr-25 A | 10-Jun-25 A | 46083 | 46083
A45620 | Mechanical Data Sheet for EOT Crane for Feed Gas Compressor_RCC | 16 | 27-Feb-25 A | 19-Apr-25 A | 46083 | 46083
A45610 | Mechanical Data Sheet for EOT Crane for Feed Gas Compressor_IFR | 6 | 27-Jan-25 A | 26-Feb-25 A | 46083 | 46083
Mechanical Data Sheet EOT Crane for Off Gas Compressor |  | 151 | 27-Jan-25 A | 28-Jun-25 A | 46083 | 46083
A45700 | Mechanical Data Sheet EOT Crane for Off Gas Compressor_IFD/IFC | 2 | 22-Jun-25 A | 28-Jun-25 A | 46083 | 46083
A45690 | Mechanical Data Sheet EOT Crane for Off Gas Compressor_RCA | 16 | 11-Jun-25 A | 21-Jun-25 A | 46083 | 46083
A45680 | Mechanical Data Sheet EOT Crane for Off Gas Compressor_IFA | 3 | 19-Mar-25 A | 10-Jun-25 A | 46083 | 46083
A45670 | Mechanical Data Sheet EOT Crane for Off Gas Compressor_RCC | 16 | 27-Feb-25 A | 18-Mar-25 A | 46083 | 46083
A45660 | Mechanical Data Sheet EOT Crane for Off Gas Compressor_IFR | 6 | 27-Jan-25 A | 26-Feb-25 A | 46083 | 46083
Mechanical Datasheet for Water Collection Sump Pump |  | 130 | 04-Jan-25 A | 10-May-25 A | 46083 | 46083
A45600 | Mechanical Datasheet for Water Collection Sump Pump_IFD/IFC | 2 | 04-May-25 A | 10-May-25 A | 46083 | 46083
A45590 | Mechanical Datasheet for Water Collection Sump Pump_RCA | 16 | 27-Apr-25 A | 03-May-25 A | 46083 | 46083
A45580 | Mechanical Datasheet for Water Collection Sump Pump_IFA | 3 | 20-Apr-25 A | 26-Apr-25 A | 46083 | 46083
A45570 | Mechanical Datasheet for Water Collection Sump Pump_RCC | 16 | 26-Jan-25 A | 19-Apr-25 A | 46083 | 46083
A45560 | Mechanical Datasheet for Water Collection Sump Pump_IFR | 2 | 04-Jan-25 A | 25-Jan-25 A | 46083 | 46083
Material Requisiton for EOT Crane |  | 141 | 15-Apr-25 A | 13-Jun-25 A | 46083 | 46083
A45800 | Material Requisiton for EOT Crane_IFD/IFC | 2 | 03-Jun-25 A | 13-Jun-25 A | 46083 | 46083
A45790 | Material Requisiton for EOT Crane_RCA | 16 | 21-May-25 A | 02-Jun-25 A | 46083 | 46083
A45780 | Material Requisiton for EOT Crane_IFA | 3 | 14-May-25 A | 20-May-25 A | 46083 | 46083
A45770 | Material Requisiton for EOT Crane_RCC | 16 | 07-May-25 A | 13-May-25 A | 46083 | 46083
A45760 | Material Requisiton for EOT Crane_IFR | 3 | 15-Apr-25 A | 06-May-25 A | 46083 | 46083
Material Requisiton for Centrifugal Pump |  | 136 | 27-Jan-25 A | 21-Jun-25 A | 46083 | 46083
A45740 | Material Requisiton for Centrifugal Pump_RCA | 16 | 02-May-25 A | 26-May-25 A | 46083 | 46083
A45750 | Material Requisiton for Centrifugal Pump_IFD/IFC | 2 | 27-May-25 A | 21-Jun-25 A | 46083 | 46083
A45730 | Material Requisiton for Centrifugal Pump_IFA | 3 | 20-Apr-25 A | 01-May-25 A | 46083 | 46083
A45720 | Material Requisiton for Centrifugal Pump_RCC | 16 | 22-Mar-25 A | 19-Apr-25 A | 46083 | 46083
A45710 | Material Requisiton for Centrifugal Pump_IFR | 6 | 27-Jan-25 A | 21-Mar-25 A | 46083 | 46083
Safety |  | 369 | 31-Dec-24 A | 2026-05-14 | 2026-03-02 | 2027-01-20 | 179
Engineering HSE Plan |  | 103 | 30-Jan-25 A | 19-May-25 A | 46083 | 46407
A46050 | Engineering HSE Plan_IFD/IFC | 2 | 13-May-25 A | 19-May-25 A | 46083 | 46083
A46040 | Engineering HSE Plan_RCA | 16 | 07-Mar-25 A | 12-May-25 A | 46407 | 46407
A46030 | Engineering HSE Plan_IFA | 3 | 28-Feb-25 A | 06-Mar-25 A | 46407 | 46407
A46020 | Engineering HSE Plan_RCC | 16 | 21-Feb-25 A | 27-Feb-25 A | 46407 | 46407
A46010 | Engineering HSE Plan_IFR | 6 | 30-Jan-25 A | 20-Feb-25 A | 46407 | 46407
Project HSE Philosophy |  | 112 | 31-Dec-24 A | 20-May-25 A | 46083 | 46407
A46100 | Project HSE Philosophy_IFD/IFC | 2 | 14-Mar-25 A | 20-May-25 A | 46083 | 46083
A46090 | Project HSE Philosophy_RCA | 16 | 11-Mar-25 A | 13-Mar-25 A | 46114 | 46114
A46080 | Project HSE Philosophy_IFA | 3 | 04-Mar-25 A | 10-Mar-25 A | 46114 | 46114
A46070 | Project HSE Philosophy_RCC | 16 | 24-Jan-25 A | 03-Mar-25 A | 46407 | 46407
A46060 | Project HSE Philosophy_IFR | 6 | 31-Dec-24 A | 23-Jan-25 A | 46407 | 46407
Fire Protection and Detection Philosophy |  | 246 | 07-Feb-25 A | 19-Nov-25 A | 46083 | 46407
A46150 | Fire Protection and Detection Philosophy_IFD/IFC | 2 | 10-Nov-25 A | 19-Nov-25 A | 46083 | 46083
A46140 | Fire Protection and Detection Philosophy_RCA | 16 | 28-Aug-25 A | 16-Oct-25 A | 46407 | 46407
A46130 | Fire Protection and Detection Philosophy_IFA | 3 | 22-Jun-25 A | 28-Jun-25 A | 46407 | 46407
A46120 | Fire Protection and Detection Philosophy_RCC | 16 | 01-Mar-25 A | 21-Jun-25 A | 46407 | 46407
A46110 | Fire Protection and Detection Philosophy_IFR | 6 | 07-Feb-25 A | 28-Feb-25 A | 46407 | 46407
Hazardous Area Classification Schedule |  | 256 | 17-Jan-25 A | 23-Dec-25 A | 46100 | 46407
A46200 | Hazardous Area Classification Schedule_IFD/IFC | 2 | 19-Dec-25 A | 23-Dec-25 A | 46100 | 46100
A46190 | Hazardous Area Classification Schedule_RCA | 16 | 23-Jun-25 A | 22-Aug-25 A | 46100 | 46100
A46180 | Hazardous Area Classification Schedule_IFA | 3 | 07-May-25 A | 20-May-25 A | 46100 | 46100
A46170 | Hazardous Area Classification Schedule_RCC | 16 | 08-Feb-25 A | 06-May-25 A | 46407 | 46407
A46160 | Hazardous Area Classification Schedule_IFR | 6 | 17-Jan-25 A | 07-Feb-25 A | 46407 | 46407
Fire Protection and Safety Equipment Layouts (Building) |  | 241 | 27-Feb-25 A | 23-Dec-25 A | 46132 | 46407
A46400 | Fire Protection and Safety Equipment Layouts (Building)_IFD/IFC | 2 | 19-Dec-25 A | 23-Dec-25 A | 46132 | 46132
A46390 | Fire Protection and Safety Equipment Layouts (Building)_RCA | 16 | 29-Jul-25 A | 27-Aug-25 A | 46407 | 46407
A46380 | Fire Protection and Safety Equipment Layouts (Building)_IFA | 3 | 22-Jun-25 A | 28-Jul-25 A | 46407 | 46407
A46370 | Fire Protection and Safety Equipment Layouts (Building)_RCC | 16 | 21-Mar-25 A | 21-Jun-25 A | 46407 | 46407
A46360 | Fire Protection and Safety Equipment Layouts (Building)_IFR | 6 | 27-Feb-25 A | 20-Mar-25 A | 46407 | 46407
Escape Route and Safety Signs Layouts (Building) |  | 241 | 27-Feb-25 A | 23-Dec-25 A | 46132 | 46407
A46500 | Escape Route and Safety Signs Layouts (Building)_IFD/IFC | 2 | 19-Dec-25 A | 23-Dec-25 A | 46132 | 46132
A46490 | Escape Route and Safety Signs Layouts (Building)_RCA | 16 | 03-Oct-25 A | 14-Oct-25 A | 46407 | 46407
A46480 | Escape Route and Safety Signs Layouts (Building)_IFA | 3 | 01-Oct-25 A | 07-Oct-25 A | 46407 | 46407
A46470 | Escape Route and Safety Signs Layouts (Building)_RCC | 16 | 21-Mar-25 A | 21-Jun-25 A | 46407 | 46407
A46460 | Escape Route and Safety Signs Layouts (Building)_IFR | 6 | 27-Feb-25 A | 20-Mar-25 A | 46407 | 46407
Fire & Gas Detectors Layouts (Building) |  | 241 | 27-Feb-25 A | 23-Dec-25 A | 46132 | 46407
A46600 | Fire & Gas Detectors Layouts (Building)_IFD/IFC | 2 | 19-Dec-25 A | 23-Dec-25 A | 46132 | 46132
A46590 | Fire & Gas Detectors Layouts (Building)_RCA | 16 | 08-Sep-25 A | 07-Oct-25 A | 46407 | 46407
A46580 | Fire & Gas Detectors Layouts (Building)_IFA | 3 | 22-Jun-25 A | 16-Jul-25 A | 46407 | 46407
A46570 | Fire & Gas Detectors Layouts (Building)_RCC | 16 | 21-Mar-25 A | 21-Jun-25 A | 46407 | 46407
A46560 | Fire & Gas Detectors Layouts (Building)_IFR | 6 | 27-Feb-25 A | 20-Mar-25 A | 46407 | 46407
F&G Cause and Effects Matrix |  | 43 | 2026-02-20 | 2026-04-21 | 2026-11-23 | 2027-01-20 | 196
A46650 | F&G Cause and Effects Matrix_IFD/IFC | 2 | 2026-04-17 | 2026-04-21 | 2026-11-23 | 2026-11-30 | 196
A46640 | F&G Cause and Effects Matrix_RCA | 16 | 2026-03-26 | 2026-04-17 | 2026-11-30 | 2026-12-22 | 196
A46630 | F&G Cause and Effects Matrix_IFA | 3 | 2026-03-23 | 2026-03-26 | 2026-12-22 | 2026-12-25 | 196
A46620 | F&G Cause and Effects Matrix_RCC | 16 | 2026-02-27 | 2026-03-23 | 2026-12-28 | 2027-01-18 | 196
A46610 | F&G Cause and Effects Matrix_IFR | 6 | 2026-02-20 | 2026-02-27 | 2027-01-18 | 2027-01-20 | 196
Specification for Fire Protection and Safety Equipment |  | 259 | 07-Feb-25 A | 23-Dec-25 A | 46132 | 46407
A46800 | Specification for Fire Protection and Safety Equipment_IFD/IFC | 2 | 19-Dec-25 A | 23-Dec-25 A | 46132 | 46132
A46790 | Specification for Fire Protection and Safety Equipment_RCA | 16 | 03-Oct-25 A | 14-Oct-25 A | 46407 | 46407
A46780 | Specification for Fire Protection and Safety Equipment_IFA | 3 | 01-Oct-25 A | 07-Oct-25 A | 46407 | 46407
A46770 | Specification for Fire Protection and Safety Equipment_RCC | 16 | 01-Mar-25 A | 31-Jul-25 A | 46407 | 46407
A46760 | Specification for Fire Protection and Safety Equipment_IFR | 6 | 07-Feb-25 A | 28-Feb-25 A | 46407 | 46407
Specification for Clean Agent System |  | 189 | 11-Feb-25 A | 10-Oct-25 A | 46147 | 46407
A46850 | Specification for Clean Agent System_IFD/IFC | 2 | 01-Oct-25 A | 10-Oct-25 A | 46147 | 46147
A46840 | Specification for Clean Agent System_RCA | 16 | 12-Jul-25 A | 30-Jul-25 A | 46407 | 46407
A46830 | Specification for Clean Agent System_IFA | 3 | 22-Jun-25 A | 30-Jun-25 A | 46407 | 46407
A46820 | Specification for Clean Agent System_RCC | 16 | 05-Mar-25 A | 21-Jun-25 A | 46407 | 46407
A46810 | Specification for Clean Agent System_IFR | 6 | 11-Feb-25 A | 04-Mar-25 A | 46407 | 46407
MR for Clean Agent System |  | 213 | 28-Feb-25 A | 10-Oct-25 A | 46147 | 46147
A47270 | MR for Clean Agent System_IFD/IFC | 2 | 01-Oct-25 A | 10-Oct-25 A | 46147 | 46147
A47260 | MR for Clean Agent System_RCA | 16 | 24-Aug-25 A | 30-Aug-25 A | 46147 | 46147
A47250 | MR for Clean Agent System_IFA | 3 | 22-Jun-25 A | 23-Aug-25 A | 46147 | 46147
A47240 | MR for Clean Agent System_RCC | 16 | 22-Mar-25 A | 21-Jun-25 A | 46147 | 46147
A47230 | MR for Clean Agent System_IFR | 6 | 28-Feb-25 A | 21-Mar-25 A | 46147 | 46147
Firewater Line List |  | 286 | 28-Feb-25 A | 2026-04-17 | 2026-11-30 | 2027-01-20 | 199
A47170 | Firewater Line List_IFD/IFC | 2 | 2026-04-15 | 2026-04-17 | 2026-11-30 | 2026-11-30 | 199
A47160 | Firewater Line List_RCA | 16 | 2026-03-24 | 2026-04-15 | 2026-11-30 | 2026-12-22 | 199
A47150 | Firewater Line List_IFA | 3 | 2026-03-19 | 2026-03-24 | 2026-12-22 | 2026-12-25 | 199
A47140 | Firewater Line List_RCC | 16 | 2026-02-20 | 2026-03-13 | 2026-12-28 | 2027-01-18 | 202
A47130 | Firewater Line List_IFR | 6 | 28-Feb-25 A | 21-Mar-25 A | 46405 | 46407
Passive Fire Protection schedule |  | 250 | 28-Feb-25 A | 23-Dec-25 A | 46407 | 46407
A46700 | Passive Fire Protection schedule_IFD/IFC | 2 | 19-Dec-25 A | 23-Dec-25 A | 46407 | 46407
A46690 | Passive Fire Protection schedule_RCA | 16 | 08-Sep-25 A | 07-Oct-25 A | 46407 | 46407
A46680 | Passive Fire Protection schedule_IFA | 3 | 22-Jun-25 A | 18-Jul-25 A | 46407 | 46407
A46670 | Passive Fire Protection schedule_RCC | 16 | 22-Mar-25 A | 21-Jun-25 A | 46407 | 46407
A46660 | Passive Fire Protection schedule_IFR | 6 | 28-Feb-25 A | 21-Mar-25 A | 46407 | 46407
Firewater Demand Report |  | 230 | 17-Jan-25 A | 03-Nov-25 A | 46356 | 46407
A47070 | Firewater Demand Report_IFD/IFC | 2 | 30-Oct-25 A | 03-Nov-25 A | 46356 | 46356
A9110 | Firewater Demand Report_RCA | 16 | 07-Sep-25 A | 13-Sep-25 A | 46407 | 46407
A9100 | Firewater Demand Report_IFA | 3 | 22-Jul-25 A | 06-Sep-25 A | 46407 | 46407
A9090 | Firewater Demand Report_RCC | 16 | 12-Mar-25 A | 21-Jul-25 A | 46407 | 46407
A9080 | Firewater Demand Report_IFR | 6 | 17-Jan-25 A | 11-Mar-25 A | 46407 | 46407
HAZID ENVID OHID Closeout Report |  | 103 | 01-Sep-25 A | 2026-03-17 | 2026-04-02 | 2027-01-20 | 221
A47370 | HAZID ENVID OHID Closeout Report_IFD/IFC | 2 | 2026-03-13 | 2026-03-17 | 2026-04-02 | 2026-04-02 | 221
A47360 | HAZID ENVID OHID Closeout Report_RCA | 16 | 2026-02-20 | 2026-03-13 | 2026-11-20 | 2026-11-20 | 221
A47350 | HAZID ENVID OHID Closeout Report_IFA | 3 | 28-Nov-25 A | 19-Dec-25 A | 46346 | 46346
A47340 | HAZID ENVID OHID Closeout Report_RCC | 16 | 05-Sep-25 A | 20-Sep-25 A | 46384 | 46405
A47330 | HAZID ENVID OHID Closeout Report_IFR | 6 | 01-Sep-25 A | 12-Sep-25 A | 46405 | 46407
Escape Route and Safety Signs Layouts (Plant) |  | 222 | 16-Apr-25 A | 23-Dec-25 A | 46132 | 46407
A46450 | Escape Route and Safety Signs Layouts (Plant)_IFD/IFC | 2 | 19-Dec-25 A | 23-Dec-25 A | 46132 | 46132
A46440 | Escape Route and Safety Signs Layouts (Plant)_RCA | 16 | 29-Jul-25 A | 30-Aug-25 A | 46407 | 46407
A46430 | Escape Route and Safety Signs Layouts (Plant)_IFA | 3 | 22-Jun-25 A | 28-Jul-25 A | 46407 | 46407
A46420 | Escape Route and Safety Signs Layouts (Plant)_RCC | 16 | 08-May-25 A | 21-Jun-25 A | 46407 | 46407
A46410 | Escape Route and Safety Signs Layouts (Plant)_IFR | 6 | 16-Apr-25 A | 07-May-25 A | 46407 | 46407
Fire & Gas Detectors Layouts (Plant) |  | 222 | 06-Apr-25 A | 23-Dec-25 A | 46132 | 46407
A46550 | Fire & Gas Detectors Layouts (Plant)_IFD/IFC | 2 | 19-Dec-25 A | 23-Dec-25 A | 46132 | 46132
A46540 | Fire & Gas Detectors Layouts (Plant)_RCA | 16 | 01-Sep-25 A | 07-Oct-25 A | 46407 | 46407
A46530 | Fire & Gas Detectors Layouts (Plant)_IFA | 3 | 22-Jun-25 A | 28-Jun-25 A | 46407 | 46407
A46520 | Fire & Gas Detectors Layouts (Plant)_RCC | 16 | 28-Apr-25 A | 21-Jun-25 A | 46407 | 46407
A46510 | Fire & Gas Detectors Layouts (Plant)_IFR | 6 | 06-Apr-25 A | 27-Apr-25 A | 46407 | 46407
Passive Fire Protection Layouts |  | 245 | 08-Apr-25 A | 23-Dec-25 A | 46407 | 46407
A46750 | Passive Fire Protection Layouts_IFD/IFC | 2 | 19-Dec-25 A | 23-Dec-25 A | 46407 | 46407
A46740 | Passive Fire Protection Layouts_RCA | 16 | 08-Sep-25 A | 07-Oct-25 A | 46407 | 46407
A46730 | Passive Fire Protection Layouts_IFA | 3 | 22-Jun-25 A | 29-Jul-25 A | 46407 | 46407
A46720 | Passive Fire Protection Layouts_RCC | 16 | 30-Apr-25 A | 21-Jun-25 A | 46407 | 46407
A46710 | Passive Fire Protection Layouts_IFR | 6 | 08-Apr-25 A | 29-Apr-25 A | 46407 | 46407
HAZOP Closeout Report |  | 86 | 01-Aug-25 A | 04-Sep-25 A | 46100 | 46100
A47470 | HAZOP Closeout Report_IFD/IFC | 2 | 01-Sep-25 A | 04-Sep-25 A | 46100 | 46100
A47460 | HAZOP Closeout Report_RCA | 16 | 29-Aug-25 A | 31-Aug-25 A | 46100 | 46100
A47450 | HAZOP Closeout Report_IFA | 3 | 25-Aug-25 A | 28-Aug-25 A | 46100 | 46100
A47440 | HAZOP Closeout Report_RCC | 16 | 04-Aug-25 A | 25-Aug-25 A | 46100 | 46100
A47430 | HAZOP Closeout Report_IFR | 6 | 01-Aug-25 A | 16-Aug-25 A | 46100 | 46100
Fire Protection and Safety Equipment Layouts (Plant) |  | 267 | 28-Mar-25 A | 2026-02-24 | 2026-04-20 | 2027-01-20 | 237
A46350 | Fire Protection and Safety Equipment Layouts (Plant)_IFD/IFC | 2 | 2026-02-20 | 2026-02-24 | 2026-04-20 | 2026-04-20 | 237
A46340 | Fire Protection and Safety Equipment Layouts (Plant)_RCA | 16 | 29-Jul-25 A | 30-Aug-25 A | 46405 | 46405
A46330 | Fire Protection and Safety Equipment Layouts (Plant)_IFA | 3 | 22-Jun-25 A | 28-Jul-25 A | 46405 | 46405
A46320 | Fire Protection and Safety Equipment Layouts (Plant)_RCC | 16 | 22-Apr-25 A | 21-Jun-25 A | 46405 | 46405
A46310 | Fire Protection and Safety Equipment Layouts (Plant)_IFR | 6 | 28-Mar-25 A | 21-Apr-25 A | 46405 | 46407
Firewater Hydraulic Report |  | 212 | 02-Jul-25 A | 2026-04-14 | 2026-11-30 | 2027-01-20 | 202
A47120 | Firewater Hydraulic Report_IFD/IFC | 2 | 2026-04-09 | 2026-04-14 | 2026-11-30 | 2026-11-30 | 202
A47110 | Firewater Hydraulic Report_RCA | 16 | 2026-03-19 | 2026-04-09 | 2026-11-30 | 2026-12-22 | 202
A47100 | Firewater Hydraulic Report_IFA | 3 | 2026-03-13 | 2026-03-19 | 2026-12-22 | 2026-12-25 | 202
A47090 | Firewater Hydraulic Report_RCC | 16 | 2026-02-20 | 2026-03-13 | 2026-12-28 | 2027-01-18 | 202
A47080 | Firewater Hydraulic Report_IFR | 6 | 02-Jul-25 A | 11-Jul-25 A | 46405 | 46407
Datasheets for Fire Protection and Safety Equipment |  | 217 | 17-Apr-25 A | 23-Dec-25 A | 46132 | 46185
A46900 | Datasheets for Fire Protection and Safety Equipment_IFD/IFC | 2 | 19-Dec-25 A | 23-Dec-25 A | 46132 | 46132
A46890 | Datasheets for Fire Protection and Safety Equipment_RCA | 16 | 01-Sep-25 A | 07-Oct-25 A | 46185 | 46185
A46880 | Datasheets for Fire Protection and Safety Equipment_IFA | 3 | 18-Aug-25 A | 25-Aug-25 A | 46185 | 46185
A46870 | Datasheets for Fire Protection and Safety Equipment_RCC | 16 | 09-May-25 A | 21-Jun-25 A | 46185 | 46185
A46860 | Datasheets for Fire Protection and Safety Equipment_IFR | 6 | 17-Apr-25 A | 08-May-25 A | 46185 | 46185
Fire Zone Layout |  | 278 | 02-Apr-25 A | 10-Sep-25 A | 46407 | 46407
A46300 | Fire Zone Layout_IFD/IFC | 2 | 08-Sep-25 A | 10-Sep-25 A | 46407 | 46407
A46280 | Fire Zone Layout_IFA | 3 | 13-Aug-25 A | 15-Aug-25 A | 46407 | 46407
A46270 | Fire Zone Layout_RCC | 16 | 24-Apr-25 A | 12-Aug-25 A | 46407 | 46407
A46290 | Fire Zone Layout_RCA | 16 | 16-Aug-25 A | 07-Sep-25 A | 46407 | 46407
A46260 | Fire Zone Layout_IFR | 6 | 02-Apr-25 A | 23-Apr-25 A | 46407 | 46407
Hazardous Area Classification Layouts |  | 228 | 06-Apr-25 A | 13-Jan-26 A | 46407 | 46407
A46250 | Hazardous Area Classification Layouts_IFD/IFC | 2 | 09-Jan-26 A | 13-Jan-26 A | 46407 | 46407
A46240 | Hazardous Area Classification Layouts_RCA | 16 | 19-Dec-25 A | 09-Jan-26 A | 46407 | 46407
A46230 | Hazardous Area Classification Layouts_IFA | 3 | 22-Jun-25 A | 29-Aug-25 A | 46407 | 46407
A46220 | Hazardous Area Classification Layouts_RCC | 16 | 28-Apr-25 A | 21-Jun-25 A | 46407 | 46407
A46210 | Hazardous Area Classification Layouts_IFR | 6 | 06-Apr-25 A | 27-Apr-25 A | 46407 | 46407
MR for Fire Protection and Safety Equipment |  | 146 | 14-May-25 A | 25-Dec-25 A | 46164 | 46185
A47220 | MR for Fire Protection and Safety Equipment_IFD/IFC | 2 | 23-Dec-25 A | 25-Dec-25 A | 46164 | 46164
A47210 | MR for Fire Protection and Safety Equipment_RCA | 16 | 01-Jul-25 A | 28-Jul-25 A | 46185 | 46185
A47200 | MR for Fire Protection and Safety Equipment_IFA | 3 | 23-Jun-25 A | 21-Jul-25 A | 46185 | 46185
A47190 | MR for Fire Protection and Safety Equipment_RCC | 16 | 14-May-25 A | 21-Jun-25 A | 46185 | 46185
A47180 | MR for Fire Protection and Safety Equipment_IFR | 6 | 04-Jun-25 A | 13-Jun-25 A | 46185 | 46185
Fire Water Layout |  | 215 | 17-Apr-25 A | 23-Dec-25 A | 46407 | 46407
A46930 | Fire Water Layout_IFA | 3 | 27-Jun-25 A | 21-Jul-25 A | 46407 | 46407
A46950 | Fire Water Layout_IFD/IFC | 2 | 19-Dec-25 A | 23-Dec-25 A | 46407 | 46407
A46940 | Fire Water Layout_RCA | 16 | 01-Jul-25 A | 28-Jul-25 A | 46407 | 46407
A46920 | Fire Water Layout_RCC | 16 | 09-May-25 A | 21-Jun-25 A | 46407 | 46407
A46910 | Fire Water Layout_IFR | 6 | 17-Apr-25 A | 08-May-25 A | 46407 | 46407
P&ID - Firewater Network |  | 292 | 21-Feb-25 A | 2026-04-14 | 2026-11-25 | 2027-01-18 | 200
A47000 | P&ID - Firewater Network_IFD/IFC | 2 | 2026-04-09 | 2026-04-14 | 2026-11-25 | 2026-11-25 | 200
A46990 | P&ID - Firewater Network_RCA | 16 | 2026-03-19 | 2026-04-09 | 2026-11-25 | 2026-12-17 | 200
A46980 | P&ID - Firewater Network_IFA | 3 | 2026-03-13 | 2026-03-19 | 2026-12-17 | 2026-12-22 | 199
A46970 | P&ID - Firewater Network_RCC | 16 | 2026-02-20 | 2026-03-13 | 2026-12-23 | 2027-01-14 | 199
A46960 | P&ID - Firewater Network_IFR | 11 | 21-Feb-25 A | 14-Mar-25 A | 46401 | 46405
P&ID - Deluge Spray System |  | 223 | 19-Apr-25 A | 2026-04-14 | 2026-11-26 | 2027-01-18 | 200
A47050 | P&ID - Deluge Spray System_IFD/IFC | 2 | 2026-04-09 | 2026-04-14 | 2026-11-26 | 2026-11-26 | 200
A47040 | P&ID - Deluge Spray System_RCA | 16 | 2026-03-19 | 2026-04-09 | 2026-11-26 | 2026-12-18 | 200
A47030 | P&ID - Deluge Spray System_IFA | 3 | 2026-03-13 | 2026-03-19 | 2026-12-18 | 2026-12-23 | 200
A47020 | P&ID - Deluge Spray System_RCC | 16 | 2026-02-20 | 2026-03-13 | 2026-12-23 | 2027-01-14 | 200
A47010 | P&ID - Deluge Spray System_IFR | 11 | 19-Apr-25 A | 10-May-25 A | 46401 | 46405
P&ID - Clean Agent System |  | 292 | 21-Feb-25 A | 2026-04-14 | 2026-11-26 | 2027-01-18 | 200
A9070 | P&ID - Clean Agent System_IFD/IFC | 2 | 2026-04-09 | 2026-04-14 | 2026-11-26 | 2026-11-26 | 200
A9060 | P&ID - Clean Agent System_RCA | 16 | 2026-03-19 | 2026-04-09 | 2026-11-26 | 2026-12-18 | 200
A9050 | P&ID - Clean Agent System_IFA | 3 | 2026-03-13 | 2026-03-19 | 2026-12-18 | 2026-12-23 | 200
A9040 | P&ID - Clean Agent System_RCC | 16 | 2026-02-20 | 2026-03-13 | 2026-12-23 | 2027-01-14 | 200
A47060 | P&ID - Clean Agent System_IFR | 11 | 21-Feb-25 A | 14-Mar-25 A | 46401 | 46405
ISD Closeout Report |  | 106 | 01-Oct-25 A | 2026-03-23 | 2026-12-22 | 2027-01-20 | 218
A47420 | ISD Closeout Report_IFD/IFC | 2 | 2026-03-19 | 2026-03-23 | 2026-12-22 | 2026-12-22 | 218
A47410 | ISD Closeout Report_RCA | 16 | 2026-02-25 | 2026-03-19 | 2026-12-22 | 2026-12-22 | 218
A47400 | ISD Closeout Report_IFA | 3 | 2026-02-20 | 2026-02-25 | 2026-12-22 | 2026-12-25 | 218
A47390 | ISD Closeout Report_RCC | 16 | 20-Oct-25 A | 17-Nov-25 A | 46384 | 46405
A47380 | ISD Closeout Report_IFR | 6 | 01-Oct-25 A | 09-Oct-25 A | 46405 | 46407
PHSER 3 Closeout Report |  | 43 | 2026-03-16 | 2026-05-14 | 2026-11-23 | 2027-01-20 | 179
A47520 | PHSER 3 Closeout Report_IFD/IFC | 2 | 2026-05-12 | 2026-05-14 | 2026-11-23 | 2026-11-30 | 179
A47510 | PHSER 3 Closeout Report_RCA | 16 | 2026-04-20 | 2026-05-12 | 2026-11-30 | 2026-12-22 | 179
A47500 | PHSER 3 Closeout Report_IFA | 3 | 2026-04-15 | 2026-04-20 | 2026-12-22 | 2026-12-25 | 179
A47490 | PHSER 3 Closeout Report_RCC | 16 | 2026-03-24 | 2026-04-15 | 2026-12-28 | 2027-01-18 | 179
A47480 | PHSER 3 Closeout Report_IFR | 6 | 2026-03-16 | 2026-03-24 | 2027-01-18 | 2027-01-20 | 179
HSE Action Tracking Register |  | 71 | 03-Nov-25 A | 2026-03-23 | 2026-12-22 | 2027-01-20 | 218
A47280 | HSE Action Tracking Register_IFR | 6 | 03-Nov-25 A | 17-Nov-25 A | 46378 | 46378
A47320 | HSE Action Tracking Register_IFD/IFC | 2 | 2026-03-19 | 2026-03-23 | 2026-12-22 | 2026-12-22 | 218
A47310 | HSE Action Tracking Register_RCA | 16 | 2026-02-25 | 2026-03-19 | 2026-12-22 | 2026-12-25 | 218
A47300 | HSE Action Tracking Register_IFA | 3 | 2026-02-20 | 2026-02-25 | 2026-12-28 | 2027-01-18 | 218
A47290 | HSE Action Tracking Register_RCC | 16 | 19-Dec-25 A | 09-Jan-26 A | 46405 | 46407
Electrical |  | 365 | 13-Dec-24 A | 2026-05-06 | 2026-03-02 | 2027-01-20 | 185
Scope Of Work For Cathodic Protection |  | 97 | 08-Aug-25 A | 23-Dec-25 A | 46157 | 46407
A10670 | Scope Of Work For Cathodic Protection_IFD/IFC | 2 | 19-Dec-25 A | 23-Dec-25 A | 46157 | 46157
A10660 | Scope Of Work For Cathodic Protection_RCA | 16 | 11-Nov-25 A | 20-Nov-25 A | 46157 | 46157
A10650 | Scope Of Work For Cathodic Protection_IFA | 3 | 03-Nov-25 A | 10-Nov-25 A | 46157 | 46157
A10640 | Scope Of Work For Cathodic Protection_RCC | 16 | 15-Aug-25 A | 19-Sep-25 A | 46407 | 46407
A10630 | Scope Of Work For Cathodic Protection_IFR | 6 | 08-Aug-25 A | 14-Aug-25 A | 46407 | 46407
Electrical System Operating Philosophy |  | 43 | 2026-02-20 | 2026-04-21 | 2026-11-23 | 2027-01-20 | 196
A47570 | Electrical System Operating Philosophy_IFD/IFC | 2 | 2026-04-17 | 2026-04-21 | 2026-11-23 | 2026-11-30 | 196
A47560 | Electrical System Operating Philosophy_RCA | 16 | 2026-03-26 | 2026-04-17 | 2026-11-30 | 2026-12-22 | 196
A47550 | Electrical System Operating Philosophy_IFA | 3 | 2026-03-23 | 2026-03-26 | 2026-12-22 | 2026-12-25 | 196
A47540 | Electrical System Operating Philosophy_RCC | 16 | 2026-02-27 | 2026-03-23 | 2026-12-28 | 2027-01-18 | 196
A47530 | Electrical System Operating Philosophy_IFR | 6 | 2026-02-20 | 2026-02-27 | 2027-01-18 | 2027-01-20 | 196
Technical Data Sheet For Transformer (Power and Distribution) |  | 146 | 23-Dec-24 A | 03-Jul-25 A | 46083 | 46083
A47620 | Technical Data Sheet For Transformer (Power and Distribution)_IFD/IFC | 2 | 27-Jun-25 A | 03-Jul-25 A | 46083 | 46083
A47610 | Technical Data Sheet For Transformer (Power and Distribution)_RCA | 16 | 20-Jun-25 A | 26-Jun-25 A | 46083 | 46083
A47600 | Technical Data Sheet For Transformer (Power and Distribution)_IFA | 3 | 07-May-25 A | 19-Jun-25 A | 46083 | 46083
A47590 | Technical Data Sheet For Transformer (Power and Distribution)_RCC | 16 | 14-Jan-25 A | 06-May-25 A | 46083 | 46083
A47580 | Technical Data Sheet For Transformer (Power and Distribution)_IFR | 2 | 23-Dec-24 A | 13-Jan-25 A | 46083 | 46083
Technical Data Sheet For LV Motors |  | 106 | 01-Jan-25 A | 03-May-25 A | 46083 | 46407
A9870 | Technical Data Sheet For LV Motors_IFD/IFC | 2 | 27-Apr-25 A | 03-May-25 A | 46083 | 46083
A9860 | Technical Data Sheet For LV Motors_RCA | 16 | 20-Apr-25 A | 26-Apr-25 A | 46407 | 46407
A9850 | Technical Data Sheet For LV Motors_IFA | 3 | 01-Mar-25 A | 19-Apr-25 A | 46407 | 46407
A9840 | Technical Data Sheet For LV Motors_RCC | 16 | 23-Jan-25 A | 28-Feb-25 A | 46407 | 46407
A47630 | Technical Data Sheet For LV Motors_IFR | 2 | 01-Jan-25 A | 22-Jan-25 A | 46407 | 46407
Technical Data Sheet For Emergency Diesel Generator |  | 208 | 09-Jan-25 A | 10-Sep-25 A | 46083 | 46083
A9920 | Technical Data Sheet For Emergency Diesel Generator_IFD/IFC | 2 | 09-Sep-25 A | 10-Sep-25 A | 46083 | 46083
A9910 | Technical Data Sheet For Emergency Diesel Generator_RCA | 16 | 19-Aug-25 A | 08-Sep-25 A | 46083 | 46083
A9900 | Technical Data Sheet For Emergency Diesel Generator_IFA | 3 | 03-May-25 A | 16-May-25 A | 46083 | 46083
A9890 | Technical Data Sheet For Emergency Diesel Generator_RCC | 16 | 03-Mar-25 A | 02-May-25 A | 46083 | 46083
A9880 | Technical Data Sheet For Emergency Diesel Generator_IFR | 2 | 09-Jan-25 A | 02-Mar-25 A | 46083 | 46083
Technical Data Sheet For Intergrated Protection Control Panel |  | 97 | 01-May-25 A | 06-Jun-25 A | 46083 | 46083
A58420 | Technical Data Sheet For IPCS_RCA | 16 | 26-May-25 A | 30-May-25 A | 46083 | 46083
A58430 | Technical Data Sheet For IPCS_IFD/IFC | 2 | 02-Jun-25 A | 06-Jun-25 A | 46083 | 46083
A58410 | Technical Data Sheet For IPCS_IFA | 3 | 19-May-25 A | 23-May-25 A | 46083 | 46083
A58400 | Technical Data Sheet For IPCS_RCC | 16 | 06-May-25 A | 16-May-25 A | 46083 | 46083
A58390 | Technical Data Sheet For IPCS_IFR | 2 | 01-May-25 A | 05-May-25 A | 46083 | 46083
Technical Data Sheet For SCMS |  | 97 | 05-May-25 A | 13-Jun-25 A | 46083 | 46083
A59930 | Technical Data Sheet For SCMS_RCA | 16 | 02-Jun-25 A | 06-Jun-25 A | 46083 | 46083
A59940 | Technical Data Sheet For SCMS_IFD/IFC | 2 | 09-Jun-25 A | 13-Jun-25 A | 46083 | 46083
A59920 | Technical Data Sheet For SCMS_IFA | 3 | 26-May-25 A | 30-May-25 A | 46083 | 46083
A59910 | Technical Data Sheet For SCMS_RCC | 16 | 12-May-25 A | 23-May-25 A | 46083 | 46083
A59900 | Technical Data Sheet For SCMS_IFR | 2 | 05-May-25 A | 09-May-25 A | 46083 | 46083
Technical Data Sheet For 11KV Switchgear |  | 140 | 19-Dec-24 A | 21-Jun-25 A | 46083 | 46083
A9960 | Technical Data Sheet For 11KV Switchgear_RCA | 16 | 22-Mar-25 A | 02-Jun-25 A | 46083 | 46083
A9970 | Technical Data Sheet For 11KV Switchgear_IFD/IFC | 2 | 03-Jun-25 A | 21-Jun-25 A | 46083 | 46083
A47640 | Technical Data Sheet For 11KV Switchgear_IFA | 3 | 15-Feb-25 A | 21-Mar-25 A | 46083 | 46083
A9940 | Technical Data Sheet For 11KV Switchgear_RCC | 16 | 10-Jan-25 A | 14-Feb-25 A | 46083 | 46083
A9930 | Technical Data Sheet For 11KV Switchgear_IFR | 2 | 19-Dec-24 A | 09-Jan-25 A | 46083 | 46083
Technical Data Sheet For LV Switchgear |  | 127 | 27-Dec-24 A | 11-May-25 A | 46083 | 46083
A10020 | Technical Data Sheet For LV Switchgear_IFD/IFC | 2 | 06-May-25 A | 11-May-25 A | 46083 | 46083
A10010 | Technical Data Sheet For LV Switchgear_RCA | 16 | 28-Apr-25 A | 04-May-25 A | 46083 | 46083
A10000 | Technical Data Sheet For LV Switchgear_IFA | 3 | 21-Apr-25 A | 27-Apr-25 A | 46083 | 46083
A9990 | Technical Data Sheet For LV Switchgear_RCC | 16 | 18-Jan-25 A | 20-Apr-25 A | 46083 | 46083
A9980 | Technical Data Sheet For LV Switchgear_IFR | 2 | 27-Dec-24 A | 17-Jan-25 A | 46083 | 46083
Technical Data Sheet For LV Variable Frequency Drive |  | 145 | 31-Jan-25 A | 05-Jul-25 A | 46083 | 46083
A10070 | Technical Data Sheet For LV Variable Frequency Drive_IFD/IFC | 2 | 29-Jun-25 A | 05-Jul-25 A | 46083 | 46083
A10060 | Technical Data Sheet For LV Variable Frequency Drive_RCA | 16 | 22-Jun-25 A | 28-Jun-25 A | 46083 | 46083
A10050 | Technical Data Sheet For LV Variable Frequency Drive_IFA | 3 | 21-Apr-25 A | 21-Jun-25 A | 46083 | 46083
A10040 | Technical Data Sheet For LV Variable Frequency Drive_RCC | 16 | 22-Feb-25 A | 20-Apr-25 A | 46083 | 46083
A10030 | Technical Data Sheet For LV Variable Frequency Drive_IFR | 2 | 31-Jan-25 A | 21-Feb-25 A | 46083 | 46083
Technical Data Sheet For Neutral Earthing Resistor |  | 133 | 19-Dec-24 A | 21-Jun-25 A | 46083 | 46083
A10110 | Technical Data Sheet For Neutral Earthing Resistor_RCA | 16 | 07-Mar-25 A | 29-May-25 A | 46083 | 46083
A10120 | Technical Data Sheet For Neutral Earthing Resistor_IFD/IFC | 2 | 30-May-25 A | 21-Jun-25 A | 46083 | 46083
A10100 | Technical Data Sheet For Neutral Earthing Resistor_IFA | 3 | 22-Feb-25 A | 06-Mar-25 A | 46083 | 46083
A10090 | Technical Data Sheet For Neutral Earthing Resistor_RCC | 16 | 10-Jan-25 A | 21-Feb-25 A | 46083 | 46083
A10080 | Technical Data Sheet For Neutral Earthing Resistor_IFR | 2 | 19-Dec-24 A | 09-Jan-25 A | 46083 | 46083
Technical Data Sheet For Interposting Relay Panel |  | 39 | 01-Aug-25 A | 17-Sep-25 A | 46140 | 46407
A58280 | Technical Data Sheet For Interpopsting Relay Panel_IFD/IFC | 2 | 15-Sep-25 A | 17-Sep-25 A | 46140 | 46140
A58270 | Technical Data Sheet For Interpopsting Relay Panel_RCA | 16 | 01-Sep-25 A | 12-Sep-25 A | 46407 | 46407
A58260 | Technical Data Sheet For Interpopsting Relay Panel_IFA | 3 | 25-Aug-25 A | 29-Aug-25 A | 46407 | 46407
A58250 | Technical Data Sheet For Interpopsting Relay Panel_RCC | 16 | 11-Aug-25 A | 22-Aug-25 A | 46407 | 46407
A58240 | Technical Data Sheet For Interpopsting Relay Panel _IFR | 2 | 01-Aug-25 A | 08-Aug-25 A | 46407 | 46407
Technical Data Sheet For Power, Control And Earthing Cables |  | 201 | 10-Jan-25 A | 05-Sep-25 A | 46100 | 46100
A10170 | Technical Data Sheet For Power, Control And Earthing Cables_IFD/IFC | 2 | 01-Sep-25 A | 05-Sep-25 A | 46100 | 46100
A10160 | Technical Data Sheet For Power, Control And Earthing Cables_RCA | 16 | 25-Aug-25 A | 29-Aug-25 A | 46100 | 46100
A10150 | Technical Data Sheet For Power, Control And Earthing Cables_IFA | 3 | 20-May-25 A | 11-Jun-25 A | 46100 | 46100
A10140 | Technical Data Sheet For Power, Control And Earthing Cables_RCC | 16 | 21-Apr-25 A | 19-May-25 A | 46100 | 46100
A10130 | Technical Data Sheet For Power, Control And Earthing Cables_IFR | 2 | 10-Jan-25 A | 20-Apr-25 A | 46100 | 46100
Technical Data Sheet For Direct Current UPS System |  | 103 | 01-Jan-25 A | 21-Jun-25 A | 46083 | 46083
A10210 | Technical Data Sheet For Direct Current UPS System_RCA | 16 | 22-Mar-25 A | 02-Jun-25 A | 46083 | 46083
A10220 | Technical Data Sheet For Direct Current UPS System_IFD/IFC | 2 | 03-Jun-25 A | 21-Jun-25 A | 46083 | 46083
A10200 | Technical Data Sheet For Direct Current UPS System_IFA | 3 | 08-Mar-25 A | 21-Mar-25 A | 46083 | 46083
A10190 | Technical Data Sheet For Direct Current UPS System_RCC | 16 | 23-Jan-25 A | 07-Mar-25 A | 46083 | 46083
A10180 | Technical Data Sheet For Direct Current UPS System_IFR | 2 | 01-Jan-25 A | 22-Jan-25 A | 46083 | 46083
Technical Data Sheet For Static AC UPS System |  | 27 | 27-Dec-24 A | 28-Jun-25 A | 46083 | 46083
A10270 | Technical Data Sheet For Static AC UPS System_IFD/IFC | 2 | 22-Jun-25 A | 28-Jun-25 A | 46083 | 46083
A10260 | Technical Data Sheet For Static AC UPS System_RCA | 16 | 13-Jun-25 A | 21-Jun-25 A | 46083 | 46083
A10250 | Technical Data Sheet For Static AC UPS System_IFA | 3 | 19-Feb-25 A | 12-Jun-25 A | 46083 | 46083
A10240 | Technical Data Sheet For Static AC UPS System_RCC | 16 | 18-Jan-25 A | 18-Feb-25 A | 46083 | 46083
A10230 | Technical Data Sheet For Static AC UPS System_IFR | 2 | 27-Dec-24 A | 17-Jan-25 A | 46083 | 46083
Technical Data Sheet For Power Factor Correction Capacitor |  | 191 | 20-Jan-25 A | 28-Aug-25 A | 46083 | 46083
A10310 | Technical Data Sheet For Power Factor Correction Capacitor_RCA | 16 | 12-Aug-25 A | 26-Aug-25 A | 46083 | 46083
A10320 | Technical Data Sheet For Power Factor Correction Capacitor_IFD/IFC | 2 | 26-Aug-25 A | 28-Aug-25 A | 46083 | 46083
A10300 | Technical Data Sheet For Power Factor Correction Capacitor_IFA | 3 | 09-Aug-25 A | 12-Aug-25 A | 46083 | 46083
A10290 | Technical Data Sheet For Power Factor Correction Capacitor_RCC | 16 | 19-Jul-25 A | 08-Aug-25 A | 46083 | 46083
A10280 | Technical Data Sheet For Power Factor Correction Capacitor_IFR | 2 | 20-Jan-25 A | 21-Feb-25 A | 46083 | 46083
Neutral Earthing Resistor Sizing Calculation |  | 134 | 13-Dec-24 A | 13-May-25 A | 46114 | 46407
A10420 | Neutral Earthing Resistor Sizing Calculation_IFD/IFC | 2 | 07-May-25 A | 13-May-25 A | 46114 | 46114
A10410 | Neutral Earthing Resistor Sizing Calculation_RCA | 16 | 13-Mar-25 A | 06-May-25 A | 46407 | 46407
A10400 | Neutral Earthing Resistor Sizing Calculation_IFA | 3 | 22-Feb-25 A | 12-Mar-25 A | 46407 | 46407
A10390 | Neutral Earthing Resistor Sizing Calculation_RCC | 16 | 10-Jan-25 A | 21-Feb-25 A | 46407 | 46407
A10380 | Neutral Earthing Resistor Sizing Calculation_IFR | 6 | 13-Dec-24 A | 09-Jan-25 A | 46407 | 46407
Interposting Relay Panel Sizing Calculation |  | 43 | 2026-02-20 | 2026-04-21 | 2026-05-14 | 2027-01-20 | 196
A58330 | Interpopsting Relay Panel Sizing Calculation_IFD/IFC | 2 | 2026-04-17 | 2026-04-21 | 2026-05-14 | 2026-05-22 | 196
A58320 | Interpopsting Relay Panel Sizing Calculation_RCA | 16 | 2026-03-26 | 2026-04-17 | 2026-05-22 | 2026-06-15 | 196
A58310 | Interpopsting Relay Panel Sizing Calculation_IFA | 3 | 2026-03-23 | 2026-03-26 | 2026-06-15 | 2026-06-18 | 60
A58300 | Interpopsting Relay Panel Sizing Calculation_RCC | 16 | 2026-02-27 | 2026-03-23 | 2026-12-28 | 2027-01-18 | 60
A58290 | Interpopsting Relay Panel Sizing Calculation_IFR | 6 | 2026-02-20 | 2026-02-27 | 2027-01-18 | 2027-01-20 | 60
Transformer Sizing Calculation |  | 151 | 29-Mar-25 A | 28-Jun-25 A | 46083 | 46407
A10720 | Transformer Sizing Calculation_IFD/IFC | 2 | 22-Jun-25 A | 28-Jun-25 A | 46083 | 46083
A10710 | Transformer Sizing Calculation_RCA | 16 | 21-Apr-25 A | 21-Jun-25 A | 46407 | 46407
A10700 | Transformer Sizing Calculation_IFA | 3 | 14-Apr-25 A | 20-Apr-25 A | 46407 | 46407
A10690 | Transformer Sizing Calculation_RCC | 16 | 30-Mar-25 A | 13-Apr-25 A | 46407 | 46407
A10680 | Transformer Sizing Calculation_IFR | 6 | 29-Mar-25 A | 06-Apr-25 A | 46407 | 46407
Electrical Load List - EU3 H2 Extraction Unit |  | 227 | 19-Dec-24 A | 30-Apr-25 A | 46083 | 46108
A10370 | Electrical Load List - EU3 H2 Extraction Unit_IFD/IFC | 2 | 30-Apr-25 A | 30-Apr-25 A | 46083 | 46083
A10360 | Electrical Load List - EU3 H2 Extraction Unit_RCA | 16 | 14-Mar-25 A | 29-Apr-25 A | 46083 | 46083
A10350 | Electrical Load List - EU3 H2 Extraction Unit_IFA | 3 | 25-Feb-25 A | 13-Mar-25 A | 46108 | 46108
A10340 | Electrical Load List - EU3 H2 Extraction Unit_RCC | 16 | 10-Jan-25 A | 18-Feb-25 A | 46108 | 46108
A10330 | Electrical Load List - EU3 H2 Extraction Unit_IFR | 6 | 19-Dec-24 A | 09-Jan-25 A | 46108 | 46108
Electrical Load Summary for Utilities & Offsites Area |  | 280 | 14-Feb-25 A | 19-Jan-26 A | 46108 | 46108
A28320 | Electrical Load Summary for Utilities & Offsites Area_IFD/IFC | 2 | 15-Jan-26 A | 19-Jan-26 A | 46108 | 46108
A55820 | Electrical Load Summary for Utilities & Offsites Area_RCA | 16 | 24-Dec-25 A | 15-Jan-26 A | 46108 | 46108
A55810 | Electrical Load Summary for Utilities & Offsites Area_IFA | 3 | 19-Dec-25 A | 24-Dec-25 A | 46108 | 46108
A55800 | Electrical Load Summary for Utilities & Offsites Area_RCC | 16 | 30-Sep-25 A | 16-Oct-25 A | 46108 | 46108
A55790 | Electrical Load Summary for Utilities & Offsites Area_IFR | 6 | 14-Feb-25 A | 20-Mar-25 A | 46108 | 46108
AC UPS Sizing Calculation |  | 266 | 01-Aug-25 A | 23-Dec-25 A | 46114 | 46407
A10970 | AC UPS Sizing Calculation_IFD/IFC | 2 | 19-Dec-25 A | 23-Dec-25 A | 46114 | 46114
A10960 | AC UPS Sizing Calculation_RCA | 16 | 24-Sep-25 A | 16-Oct-25 A | 46407 | 46407
A10950 | AC UPS Sizing Calculation_IFA | 3 | 17-Sep-25 A | 09-Oct-25 A | 46407 | 46407
A10940 | AC UPS Sizing Calculation_RCC | 16 | 04-Aug-25 A | 22-Aug-25 A | 46407 | 46407
A10930 | AC UPS Sizing Calculation_IFR | 6 | 01-Aug-25 A | 15-Aug-25 A | 46407 | 46407
DC UPS Sizing Calculation |  | 261 | 30-Mar-25 A | 23-Dec-25 A | 46114 | 46407
A11020 | DC UPS Sizing Calculation_IFD/IFC | 2 | 19-Dec-25 A | 23-Dec-25 A | 46114 | 46114
A11010 | DC UPS Sizing Calculation_RCA | 16 | 15-May-25 A | 21-Jun-25 A | 46407 | 46407
A11000 | DC UPS Sizing Calculation_IFA | 3 | 21-Apr-25 A | 27-Apr-25 A | 46407 | 46407
A10990 | DC UPS Sizing Calculation_RCC | 16 | 01-Apr-25 A | 20-Apr-25 A | 46407 | 46407
A10980 | DC UPS Sizing Calculation_IFR | 6 | 30-Mar-25 A | 13-Apr-25 A | 46407 | 46407
EDG Sizing Calculation |  | 166 | 19-Dec-24 A | 28-Jun-25 A | 46083 | 46407
A11070 | EDG Sizing Calculation_IFD/IFC | 2 | 22-Jun-25 A | 28-Jun-25 A | 46083 | 46083
A11060 | EDG Sizing Calculation_RCA | 16 | 21-Apr-25 A | 21-Jun-25 A | 46407 | 46407
A11050 | EDG Sizing Calculation_IFA | 3 | 21-Feb-25 A | 20-Apr-25 A | 46407 | 46407
A11040 | EDG Sizing Calculation_RCC | 16 | 10-Jan-25 A | 20-Feb-25 A | 46407 | 46407
A11030 | EDG Sizing Calculation_IFR | 6 | 19-Dec-24 A | 09-Jan-25 A | 46407 | 46407
IO List For IPCS |  | 192 | 29-Mar-25 A | 18-Sep-25 A | 46407 | 46407
A11120 | IO List For IPCS_IFD/IFC | 2 | 22-Jun-25 A | 18-Sep-25 A | 46407 | 46407
A11110 | IO List For IPCS_RCA | 16 | 30-Apr-25 A | 21-Jun-25 A | 46407 | 46407
A11100 | IO List For IPCS_IFA | 3 | 14-Apr-25 A | 20-Apr-25 A | 46407 | 46407
A11090 | IO List For IPCS_RCC | 16 | 01-Apr-25 A | 13-Apr-25 A | 46407 | 46407
A11080 | IO List For IPCS_IFR | 6 | 29-Mar-25 A | 06-Apr-25 A | 46407 | 46407
IO List For SCMS |  | 192 | 24-Jan-25 A | 23-Dec-25 A | 46407 | 46407
A11170 | IO List For SCMS_IFD/IFC | 2 | 22-Jun-25 A | 23-Dec-25 A | 46407 | 46407
A11160 | IO List For SCMS_RCA | 16 | 21-Apr-25 A | 21-Jun-25 A | 46407 | 46407
A11150 | IO List For SCMS_IFA | 3 | 21-Apr-25 A | 27-Apr-25 A | 46407 | 46407
A11140 | IO List For SCMS_RCC | 16 | 25-Feb-25 A | 20-Apr-25 A | 46407 | 46407
A11130 | IO List For SCMS_IFR | 6 | 24-Jan-25 A | 24-Feb-25 A | 46407 | 46407
Power System Study Report - ARC Flash, Harmonics Resonance |  | 112 | 18-Jul-25 A | 23-Dec-25 A | 46083 | 46407
A11270 | Power System Study Report - ARC Flash, Harmonics Resonance_IFD/IFC | 2 | 19-Dec-25 A | 23-Dec-25 A | 46083 | 46083
A11260 | Power System Study Report - ARC Flash, Harmonics Resonance_RCA | 16 | 20-Sep-25 A | 17-Oct-25 A | 46407 | 46407
A11250 | Power System Study Report - ARC Flash, Harmonics Resonance_IFA | 3 | 04-Sep-25 A | 10-Oct-25 A | 46407 | 46407
A11240 | Power System Study Report - ARC Flash, Harmonics Resonance_RCC | 16 | 12-Aug-25 A | 28-Aug-25 A | 46407 | 46407
A11230 | Power System Study Report - ARC Flash, Harmonics Resonance_IFR | 6 | 18-Jul-25 A | 11-Aug-25 A | 46407 | 46407
Power System Study Report - Load Flow, Short Circuit and Motor Starting |  | 165 | 28-Apr-25 A | 23-Dec-25 A | 46083 | 46407
A11220 | Power System Study Report - Load Flow, Short Circuit and Motor Starting_IFD/IFC | 2 | 19-Dec-25 A | 23-Dec-25 A | 46083 | 46083
A11210 | Power System Study Report - Load Flow, Short Circuit and Motor Starting_RCA | 16 | 20-Aug-25 A | 04-Sep-25 A | 46407 | 46407
A11200 | Power System Study Report - Load Flow, Short Circuit and Motor Starting_IFA | 3 | 26-Jul-25 A | 28-Aug-25 A | 46407 | 46407
A11190 | Power System Study Report - Load Flow, Short Circuit and Motor Starting_RCC | 16 | 25-Jun-25 A | 25-Jul-25 A | 46407 | 46407
A11180 | Power System Study Report - Load Flow, Short Circuit and Motor Starting_IFR | 6 | 28-Apr-25 A | 19-May-25 A | 46407 | 46407
PSCAD Study Report - Transient Stability And Insulation Coordination |  | 160 | 01-May-25 A | 23-Dec-25 A | 46349 | 46407
A11320 | Pscad Study Report - Transient Stability And Insulation Coordination_IFD/IFC | 2 | 19-Dec-25 A | 23-Dec-25 A | 46349 | 46349
A11310 | Pscad Study Report - Transient Stability And Insulation Coordination_RCA | 16 | 10-Sep-25 A | 03-Oct-25 A | 46407 | 46407
A11300 | Pscad Study Report - Transient Stability And Insulation Coordination_IFA | 3 | 31-Jul-25 A | 26-Sep-25 A | 46407 | 46407
A11290 | Pscad Study Report - Transient Stability And Insulation Coordination_RCC | 16 | 11-Jun-25 A | 25-Jul-25 A | 46407 | 46407
A11280 | Pscad Study Report - Transient Stability And Insulation Coordination_IFR | 6 | 01-May-25 A | 22-May-25 A | 46407 | 46407
Power System Study Report - Protection Coordination and Relay Setting |  | 43 | 2026-02-20 | 2026-04-21 | 2026-11-23 | 2027-01-20 | 196
A11370 | Power System Study Report - Protection Coordination and Relay Setting_IFD/IFC | 2 | 2026-04-17 | 2026-04-21 | 2026-11-23 | 2026-11-30 | 196
A11360 | Power System Study Report - Protection Coordination and Relay Setting_RCA | 16 | 2026-03-26 | 2026-04-17 | 2026-11-30 | 2026-12-22 | 196
A11350 | Power System Study Report - Protection Coordination and Relay Setting_IFA | 3 | 2026-03-23 | 2026-03-26 | 2026-12-22 | 2026-12-25 | 196
A11340 | Power System Study Report - Protection Coordination and Relay Setting_RCC | 16 | 2026-02-27 | 2026-03-23 | 2026-12-28 | 2027-01-18 | 196
A11330 | Power System Study Report - Protection Coordination and Relay Setting_IFR | 6 | 2026-02-20 | 2026-02-27 | 2027-01-18 | 2027-01-20 | 196
Material Requisition For Transformer (Power And Distribution) |  | 146 | 19-Dec-24 A | 28-Jun-25 A | 46083 | 46083
A12470 | Material Requisition For Transformer (Power And Distribution)_IFD/IFC | 2 | 22-Jun-25 A | 28-Jun-25 A | 46083 | 46083
A12460 | Material Requisition For Transformer (Power And Distribution)_RCA | 16 | 22-Mar-25 A | 21-Jun-25 A | 46083 | 46083
A12450 | Material Requisition For Transformer (Power And Distribution)_IFA | 3 | 19-Feb-25 A | 21-Mar-25 A | 46083 | 46083
A12440 | Material Requisition For Transformer (Power And Distribution)_RCC | 16 | 10-Jan-25 A | 18-Feb-25 A | 46083 | 46083
A12430 | Material Requisition For Transformer (Power And Distribution)_IFR | 6 | 19-Dec-24 A | 09-Jan-25 A | 46083 | 46083
Material Requisition For 11KV Switchgear |  | 120 | 13-Feb-25 A | 12-May-25 A | 46083 | 46083
A12520 | Material Requisition For 11KV Switchgear_IFD/IFC | 2 | 06-May-25 A | 12-May-25 A | 46083 | 46083
A12510 | Material Requisition For 11KV Switchgear_RCA | 16 | 29-Apr-25 A | 05-May-25 A | 46083 | 46083
A12500 | Material Requisition For 11KV Switchgear_IFA | 3 | 22-Apr-25 A | 28-Apr-25 A | 46083 | 46083
A12490 | Material Requisition For 11KV Switchgear_RCC | 16 | 07-Mar-25 A | 21-Apr-25 A | 46083 | 46083
A12480 | Material Requisition For 11KV Switchgear_IFR | 6 | 13-Feb-25 A | 06-Mar-25 A | 46083 | 46083
Material Requisition For LV Switchgear |  | 195 | 20-Jan-25 A | 11-Jul-25 A | 46083 | 46083
A12570 | Material Requisition For LV Switchgear_IFD/IFC | 2 | 07-Jul-25 A | 11-Jul-25 A | 46083 | 46083
A12560 | Material Requisition For LV Switchgear_RCA | 16 | 23-Jun-25 A | 04-Jul-25 A | 46083 | 46083
A12550 | Material Requisition For LV Switchgear_IFA | 3 | 07-May-25 A | 21-Jun-25 A | 46083 | 46083
A12540 | Material Requisition For LV Switchgear_RCC | 16 | 01-Mar-25 A | 06-May-25 A | 46083 | 46083
A12530 | Material Requisition For LV Switchgear_IFR | 6 | 20-Jan-25 A | 28-Feb-25 A | 46083 | 46083
Material Requisition For Capacitor Bank |  | 173 | 03-Mar-25 A | 04-Sep-25 A | 46083 | 46083
A12620 | Material Requisition For Capacitor Bank_IFD/IFC | 2 | 29-Aug-25 A | 04-Sep-25 A | 46083 | 46083
A12610 | Material Requisition For Capacitor Bank_RCA | 16 | 22-Jun-25 A | 28-Aug-25 A | 46083 | 46083
A12600 | Material Requisition For Capacitor Bank_IFA | 3 | 05-May-25 A | 21-Jun-25 A | 46083 | 46083
A12590 | Material Requisition For Capacitor Bank_RCC | 16 | 28-Apr-25 A | 04-May-25 A | 46083 | 46083
A12580 | Material Requisition For Capacitor Bank_IFR | 6 | 03-Mar-25 A | 27-Apr-25 A | 46083 | 46083
Material Requisition For Power, Control And Earthing Cables |  | 118 | 22-Apr-25 A | 2026-02-20 | 2026-03-19 | 2026-03-19 | 20
A12660 | Material Requisition For Power, Control And Earthing Cables_RCA | 16 | 15-Sep-25 A | 15-Oct-25 A | 46100 | 46100
A12640 | Material Requisition For Power, Control And Earthing Cables_RCC | 16 | 26-May-25 A | 31-Jul-25 A | 46100 | 46100
A12650 | Material Requisition For Power, Control And Earthing Cables_IFA | 3 | 01-Aug-25 A | 20-Aug-25 A | 46100 | 46100
A12670 | Material Requisition For Power, Control And Earthing Cables_IFD/IFC | 2 | 20-Sep-25 A | 2026-02-20 | 2026-03-19 | 2026-03-19 | 20
A12630 | Material Requisition For Power, Control And Earthing Cables_IFR | 6 | 22-Apr-25 A | 13-May-25 A | 46100 | 46100
Material Requisition For Emergency Diesel Generator |  | 144 | 01-Jan-25 A | 28-Jun-25 A | 46083 | 46083
A12720 | Material Requisition For Emergency Diesel Generator_IFD/IFC | 2 | 22-Jun-25 A | 28-Jun-25 A | 46083 | 46083
A12710 | Material Requisition For Emergency Diesel Generator_RCA | 16 | 21-Apr-25 A | 21-Jun-25 A | 46083 | 46083
A12700 | Material Requisition For Emergency Diesel Generator_IFA | 3 | 08-Mar-25 A | 20-Apr-25 A | 46083 | 46083
A12690 | Material Requisition For Emergency Diesel Generator_RCC | 16 | 23-Jan-25 A | 07-Mar-25 A | 46083 | 46083
A12680 | Material Requisition For Emergency Diesel Generator_IFR | 6 | 01-Jan-25 A | 22-Jan-25 A | 46083 | 46083
Material Requisition For AC UPS |  | 172 | 01-Jan-25 A | 30-Apr-25 A | 46083 | 46083
A12760 | Material Requisition For AC UPS_RCA | 16 | 24-Mar-25 A | 04-Apr-25 A | 46083 | 46083
A12770 | Material Requisition For AC UPS_IFD/IFC | 2 | 07-Apr-25 A | 30-Apr-25 A | 46083 | 46083
A12750 | Material Requisition For AC UPS_IFA | 3 | 10-Mar-25 A | 21-Mar-25 A | 46083 | 46083
A12740 | Material Requisition For AC UPS_RCC | 16 | 25-Feb-25 A | 07-Mar-25 A | 46083 | 46083
A12730 | Material Requisition For AC UPS_IFR | 6 | 01-Jan-25 A | 22-Jan-25 A | 46083 | 46083
Material Requisition For DC UPS |  | 112 | 31-Jan-25 A | 28-Jun-25 A | 46083 | 46083
A12820 | Material Requisition For DC UPS_IFD/IFC | 2 | 22-Jun-25 A | 28-Jun-25 A | 46083 | 46083
A12810 | Material Requisition For DC UPS_RCA | 16 | 22-Mar-25 A | 21-Jun-25 A | 46083 | 46083
A12800 | Material Requisition For DC UPS_IFA | 3 | 13-Mar-25 A | 21-Mar-25 A | 46083 | 46083
A12790 | Material Requisition For DC UPS_RCC | 16 | 21-Feb-25 A | 14-Mar-25 A | 46083 | 46083
A12780 | Material Requisition For DC UPS_IFR | 6 | 31-Jan-25 A | 21-Feb-25 A | 46083 | 46083
Material Requisition For LV Variable Frequency Drive |  | 154 | 31-Jan-25 A | 12-Jul-25 A | 46083 | 46083
A12870 | Material Requisition For LV Variable Frequency Drive_IFD/IFC | 2 | 06-Jul-25 A | 12-Jul-25 A | 46083 | 46083
A12860 | Material Requisition For LV Variable Frequency Drive_RCA | 16 | 27-Jun-25 A | 05-Jul-25 A | 46083 | 46083
A12850 | Material Requisition For LV Variable Frequency Drive_IFA | 3 | 22-Jun-25 A | 28-Jun-25 A | 46083 | 46083
A12840 | Material Requisition For LV Variable Frequency Drive_RCC | 16 | 22-Feb-25 A | 21-Jun-25 A | 46083 | 46083
A12830 | Material Requisition For LV Variable Frequency Drive_IFR | 6 | 31-Jan-25 A | 21-Feb-25 A | 46083 | 46083
Material Requisition For Neutral Grounding Resistor |  | 105 | 13-Dec-24 A | 15-Oct-25 A | 46083 | 46083
A12920 | Material Requisition For Neutral Grounding Resistor_IFD/IFC | 2 | 01-Sep-25 A | 15-Oct-25 A | 46083 | 46083
A12910 | Material Requisition For Neutral Grounding Resistor_RCA | 16 | 15-Mar-25 A | 06-May-25 A | 46083 | 46083
A12900 | Material Requisition For Neutral Grounding Resistor_IFA | 3 | 11-Feb-25 A | 14-Mar-25 A | 46083 | 46083
A12890 | Material Requisition For Neutral Grounding Resistor_RCC | 16 | 08-Jan-25 A | 10-Feb-25 A | 46083 | 46083
A12880 | Material Requisition For Neutral Grounding Resistor_IFR | 6 | 13-Dec-24 A | 17-Jan-25 A | 46083 | 46083
Material Requisition For Interposting Relay Panel |  | 154 | 01-Sep-25 A | 2026-04-27 | 2026-04-28 | 2026-07-17 | 60
A58380 | Material Requisition For Interpopsting Relay Panel_IFD/IFC | 2 | 2026-04-22 | 2026-04-27 | 2026-04-28 | 2026-04-28 | 60
A58370 | Material Requisition For Interpopsting Relay Panel_RCA | 16 | 2026-04-01 | 2026-04-22 | 2026-05-27 | 2026-06-18 | 60
A58360 | Material Requisition For Interpopsting Relay Panel_IFA | 3 | 2026-03-26 | 2026-04-01 | 2026-06-18 | 2026-06-23 | 60
A58350 | Material Requisition For Interpopsting Relay Panel_RCC | 16 | 2026-02-20 | 2026-03-13 | 2026-06-24 | 2026-07-15 | 69
A58340 | Material Requisition For Interpopsting Relay Panel_IFR | 6 | 01-Sep-25 A | 05-Sep-25 A | 46218 | 46220
Material Requisition For Integrated Protection Control Panel |  | 36 | 19-Jul-25 A | 04-Sep-25 A | 46146 | 46407
A58170 | Material Requisition For IPCS_RCA | 16 | 17-Aug-25 A | 30-Aug-25 A | 46146 | 46146
A58180 | Material Requisition For IPCS_IFD/IFC | 2 | 30-Aug-25 A | 04-Sep-25 A | 46407 | 46407
A58150 | Material Requisition For IPCS_RCC | 16 | 26-Jul-25 A | 14-Aug-25 A | 46407 | 46407
A58160 | Material Requisition For IPCS_IFA | 3 | 14-Aug-25 A | 17-Aug-25 A | 46407 | 46407
A58140 | Material Requisition For IPCS_IFR | 6 | 19-Jul-25 A | 25-Jul-25 A | 46407 | 46407
Material Requisition For SCMS |  | 36 | 19-Jul-25 A | 04-Sep-25 A | 46101 | 46101
A59980 | Material Requisition For SCMS_RCA | 16 | 17-Aug-25 A | 30-Aug-25 A | 46101 | 46101
A59990 | Material Requisition For SCMS_IFD/IFC | 2 | 30-Aug-25 A | 04-Sep-25 A | 46101 | 46101
A59960 | Material Requisition For SCMS_RCC | 16 | 26-Jul-25 A | 14-Aug-25 A | 46101 | 46101
A59970 | Material Requisition For SCMS_IFA | 3 | 14-Aug-25 A | 17-Aug-25 A | 46101 | 46101
A59950 | Material Requisition For SCMS_IFR | 6 | 19-Jul-25 A | 25-Jul-25 A | 46101 | 46101
Key Single Line Diagram - Hydrogen Extraction Unit |  | 261 | 28-May-25 A | 23-Dec-25 A | 46083 | 46407
A11420 | Key Single Line Diagram - Hydrogen Extraction Unit_IFD/IFC | 2 | 19-Dec-25 A | 23-Dec-25 A | 46083 | 46083
A11410 | Key Single Line Diagram - Hydrogen Extraction Unit_RCA | 16 | 01-Jul-25 A | 10-Sep-25 A | 46407 | 46407
A11400 | Key Single Line Diagram - Hydrogen Extraction Unit_IFA | 3 | 15-Jun-25 A | 21-Jun-25 A | 46407 | 46407
A11390 | Key Single Line Diagram - Hydrogen Extraction Unit_RCC | 16 | 30-May-25 A | 14-Jun-25 A | 46407 | 46407
A11380 | Key Single Line Diagram - Hydrogen Extraction Unit_IFR | 6 | 28-May-25 A | 07-Jun-25 A | 46407 | 46407
Single Line Diagram For Integrated Protection Control Panel |  | 147 | 19-Aug-25 A | 2026-04-14 | 2026-03-20 | 2027-01-01 | 189
A58480 | Single Line Diagram For IPCS_IFD/IFC | 2 | 2026-04-09 | 2026-04-14 | 2026-03-20 | 2026-03-20 | 189
A58470 | Single Line Diagram For IPCS_RCA | 16 | 2026-03-19 | 2026-04-09 | 2026-11-11 | 2026-12-03 | 189
A58460 | Single Line Diagram For IPCS_IFA | 3 | 2026-03-13 | 2026-03-19 | 2026-12-03 | 2026-12-08 | 189
A58450 | Single Line Diagram For IPCS_RCC | 16 | 2026-02-20 | 2026-03-13 | 2026-12-09 | 2026-12-30 | 189
A58440 | Single Line Diagram For IPCS_IFR | 6 | 19-Aug-25 A | 25-Aug-25 A | 46386 | 46388
Single Line Diagram For SCMS |  | 147 | 19-Aug-25 A | 2026-04-14 | 2026-03-20 | 2027-01-01 | 189
A60040 | Single Line Diagram For SCMS_IFD/IFC | 2 | 2026-04-09 | 2026-04-14 | 2026-03-20 | 2026-03-20 | 189
A60030 | Single Line Diagram For SCMS_RCA | 16 | 2026-03-19 | 2026-04-09 | 2026-11-11 | 2026-12-03 | 189
A60020 | Single Line Diagram For SCMS_IFA | 3 | 2026-03-13 | 2026-03-19 | 2026-12-03 | 2026-12-08 | 189
A60010 | Single Line Diagram For SCMS_RCC | 16 | 2026-02-20 | 2026-03-13 | 2026-12-09 | 2026-12-30 | 189
A60000 | Single Line Diagram For SCMS_IFR | 6 | 19-Aug-25 A | 25-Aug-25 A | 46386 | 46388
Single Line Diagram For 11KV Switchgear |  | 224 | 31-Jan-25 A | 23-Aug-25 A | 46083 | 46388
A11570 | Single Line Diagram For 11KV Switchgear_IFD/IFC | 2 | 22-Jun-25 A | 23-Aug-25 A | 46083 | 46083
A11560 | Single Line Diagram For 11KV Switchgear_RCA | 16 | 28-Apr-25 A | 21-Jun-25 A | 46388 | 46388
A11550 | Single Line Diagram For 11KV Switchgear_IFA | 3 | 21-Apr-25 A | 27-Apr-25 A | 46388 | 46388
A11540 | Single Line Diagram For 11KV Switchgear_RCC | 16 | 22-Feb-25 A | 20-Apr-25 A | 46388 | 46388
A11530 | Single Line Diagram For 11KV Switchgear_IFR | 6 | 31-Jan-25 A | 21-Feb-25 A | 46388 | 46388
Single Line Diagram For AC UPS |  | 67 | 26-Aug-25 A | 23-Dec-25 A | 46364 | 46388
A11620 | Single Line Diagram For AC UPS_IFD/IFC | 2 | 19-Dec-25 A | 23-Dec-25 A | 46364 | 46364
A11610 | Single Line Diagram For AC UPS_RCA | 16 | 01-Nov-25 A | 21-Nov-25 A | 46388 | 46388
A11600 | Single Line Diagram For AC UPS_IFA | 3 | 08-Sep-25 A | 12-Sep-25 A | 46388 | 46388
A11590 | Single Line Diagram For AC UPS_RCC | 16 | 02-Sep-25 A | 05-Sep-25 A | 46388 | 46388
A11580 | Single Line Diagram For AC UPS_IFR | 6 | 26-Aug-25 A | 02-Sep-25 A | 46388 | 46388
Single Line Diagram For DC UPS |  | 248 | 03-Feb-25 A | 25-Dec-25 A | 46364 | 46388
A11670 | Single Line Diagram For DC UPS_IFD/IFC | 2 | 23-Dec-25 A | 25-Dec-25 A | 46364 | 46364
A11660 | Single Line Diagram For DC UPS_RCA | 16 | 30-Apr-25 A | 02-Jun-25 A | 46364 | 46364
A11650 | Single Line Diagram For DC UPS_IFA | 3 | 19-Mar-25 A | 29-Apr-25 A | 46388 | 46388
A11640 | Single Line Diagram For DC UPS_RCC | 16 | 25-Feb-25 A | 18-Mar-25 A | 46388 | 46388
A11630 | Single Line Diagram For DC UPS_IFR | 6 | 03-Feb-25 A | 24-Feb-25 A | 46388 | 46388
Single Line Diagram For LV Switchgear |  | 256 | 20-Jan-25 A | 23-Dec-25 A | 46388 | 46388
A11720 | Single Line Diagram For LV Switchgear_IFD/IFC | 2 | 19-Dec-25 A | 23-Dec-25 A | 46388 | 46388
A11710 | Single Line Diagram For LV Switchgear_RCA | 16 | 15-Jul-25 A | 10-Sep-25 A | 46388 | 46388
A11700 | Single Line Diagram For LV Switchgear_IFA | 3 | 07-May-25 A | 21-Jun-25 A | 46388 | 46388
A11690 | Single Line Diagram For LV Switchgear_RCC | 16 | 22-Feb-25 A | 06-May-25 A | 46388 | 46388
A11680 | Single Line Diagram For LV Switchgear_IFR | 6 | 20-Jan-25 A | 21-Feb-25 A | 46388 | 46388
Single Line Diagram For Lighting And Small Power |  | 38 | 28-Oct-25 A | 2026-03-17 | 2026-12-08 | 2027-01-01 | 208
A11770 | Single Line Diagram For Lighting And Small Power_IFD/IFC | 2 | 2026-03-13 | 2026-03-17 | 2026-12-08 | 2026-12-08 | 208
A11760 | Single Line Diagram For Lighting And Small Power_RCA | 16 | 2026-02-20 | 2026-03-13 | 2026-12-08 | 2026-12-08 | 208
A11750 | Single Line Diagram For Lighting And Small Power_IFA | 3 | 23-Jan-26 A | 2026-02-20 | 2026-12-08 | 2026-12-08 | 208
A11740 | Single Line Diagram For Lighting And Small Power_RCC | 16 | 05-Nov-25 A | 14-Nov-25 A | 46365 | 46386
A11730 | Single Line Diagram For Lighting And Small Power_IFR | 6 | 28-Oct-25 A | 05-Nov-25 A | 46386 | 46388
One Line Diagram 220/33 KV Main Substation (Unit No-80) - Update |  | 172 | 25-Mar-25 A | 28-Jun-25 A | 46407 | 46407
A55860 | One Line Diagram 220/33 KV Main Substation (Unit No-80) - Update_IFD/IFC | 2 | 22-Jun-25 A | 28-Jun-25 A | 46407 | 46407
A55850 | One Line Diagram 220/33 KV Main Substation (Unit No-80) - Update_RCA | 16 | 05-Jun-25 A | 21-Jun-25 A | 46407 | 46407
A55840 | One Line Diagram 220/33 KV Main Substation (Unit No-80) - Update_IFA | 3 | 16-May-25 A | 04-Jun-25 A | 46407 | 46407
A55830 | One Line Diagram 220/33 KV Main Substation (Unit No-80) - Update_RCC | 16 | 29-Apr-25 A | 15-May-25 A | 46407 | 46407
A28330 | One Line Diagram 220/33 KV Main Substation (Unit No-80) - Update_IFR | 6 | 25-Mar-25 A | 28-Apr-25 A | 46407 | 46407
Protection and Metering One Line Diagram 220/33 KV Main Substation 33 KV Switchgear 80-ES-1802 - Upd |  | 232 | 18-Feb-25 A | 13-Jan-26 A | 46407 | 46407
A28420 | Protection and Metering One Line Diagram 220/33 KV Main Substation 33 KV Switchgear 80-ES-1802 - Update_IFD/IFC | 2 | 09-Jan-26 A | 13-Jan-26 A | 46407 | 46407
A28410 | Protection and Metering One Line Diagram 220/33 KV Main Substation 33 KV Switchgear 80-ES-1802 - Update_RCA | 16 | 19-Dec-25 A | 09-Jan-26 A | 46407 | 46407
A55890 | Protection and Metering One Line Diagram 220/33 KV Main Substation 33 KV Switchgear 80-ES-1802 - Update_IFA | 3 | 16-May-25 A | 21-Jun-25 A | 46407 | 46407
A55880 | Protection and Metering One Line Diagram 220/33 KV Main Substation 33 KV Switchgear 80-ES-1802 - Update_RCC | 16 | 12-Mar-25 A | 18-Mar-25 A | 46407 | 46407
A55870 | Protection and Metering One Line Diagram 220/33 KV Main Substation 33 KV Switchgear 80-ES-1802 - Update_IFR | 6 | 18-Feb-25 A | 11-Mar-25 A | 46407 | 46407
Electrical Legend Sheet |  | 161 | 28-Mar-25 A | 28-Jun-25 A | 46356 | 46407
A12170 | Electrical Legend Sheet_IFD/IFC | 2 | 22-Jun-25 A | 28-Jun-25 A | 46356 | 46356
A12160 | Electrical Legend Sheet_RCA | 16 | 21-Apr-25 A | 21-Jun-25 A | 46407 | 46407
A12150 | Electrical Legend Sheet_IFA | 3 | 14-Apr-25 A | 20-Apr-25 A | 46407 | 46407
A12140 | Electrical Legend Sheet_RCC | 16 | 31-Mar-25 A | 13-Apr-25 A | 46407 | 46407
A12130 | Electrical Legend Sheet_IFR | 6 | 28-Mar-25 A | 06-Apr-25 A | 46407 | 46407
Electrical Equipment And Motor List |  | 217 | 28-Mar-25 A | 04-May-25 A | 46356 | 46407
A12270 | Electrical Equipment And Motor List_IFD/IFC | 2 | 28-Apr-25 A | 04-May-25 A | 46356 | 46356
A12260 | Electrical Equipment And Motor List_RCA | 16 | 18-Apr-25 A | 27-Apr-25 A | 46407 | 46407
A12250 | Electrical Equipment And Motor List_IFA | 3 | 14-Apr-25 A | 20-Apr-25 A | 46407 | 46407
A12240 | Electrical Equipment And Motor List_RCC | 16 | 31-Mar-25 A | 13-Apr-25 A | 46407 | 46407
A12230 | Electrical Equipment And Motor List_IFR | 6 | 28-Mar-25 A | 06-Apr-25 A | 46407 | 46407
System Architecture Diagram For IPCS |  | 236 | 12-Feb-25 A | 23-Dec-25 A | 46407 | 46407
A12320 | System Architecture Diagram For IPCS_IFD/IFC | 2 | 19-Dec-25 A | 23-Dec-25 A | 46407 | 46407
A12310 | System Architecture Diagram For IPCS_RCA | 16 | 15-Aug-25 A | 04-Sep-25 A | 46407 | 46407
A12300 | System Architecture Diagram For IPCS_IFA | 3 | 21-Apr-25 A | 27-Apr-25 A | 46407 | 46407
A12290 | System Architecture Diagram For IPCS_RCC | 16 | 06-Mar-25 A | 20-Apr-25 A | 46407 | 46407
A12280 | System Architecture Diagram For IPCS_IFR | 6 | 12-Feb-25 A | 05-Mar-25 A | 46407 | 46407
System Architecture Diagram For SCMS - Update |  | 39 | 01-Jul-25 A | 08-Sep-25 A | 46407 | 46407
A12360 | System Architecture Diagram For SCMS - Update_RCA | 16 | 21-Aug-25 A | 01-Sep-25 A | 46407 | 46407
A12370 | System Architecture Diagram For SCMS - Update_IFD/IFC | 2 | 02-Sep-25 A | 08-Sep-25 A | 46407 | 46407
A12350 | System Architecture Diagram For SCMS - Update_IFA | 3 | 31-Jul-25 A | 20-Aug-25 A | 46407 | 46407
A12340 | System Architecture Diagram For SCMS - Update_RCC | 16 | 09-Jul-25 A | 30-Jul-25 A | 46407 | 46407
A12330 | System Architecture Diagram For SCMS - Update_IFR | 6 | 01-Jul-25 A | 08-Jul-25 A | 46407 | 46407
Capacitor Bank Sizing Calculation |  | 207 | 22-Mar-25 A | 16-Oct-25 A | 46083 | 46407
A10820 | Capacitor Bank Sizing Calculation_IFD/IFC | 2 | 10-Oct-25 A | 16-Oct-25 A | 46083 | 46083
A10810 | Capacitor Bank Sizing Calculation_RCA | 16 | 20-Jul-25 A | 22-Aug-25 A | 46407 | 46407
A10790 | Capacitor Bank Sizing Calculation_RCC | 16 | 22-Mar-25 A | 26-May-25 A | 46407 | 46407
A10800 | Capacitor Bank Sizing Calculation_IFA | 3 | 27-May-25 A | 21-Jun-25 A | 46407 | 46407
A10780 | Capacitor Bank Sizing Calculation_IFR | 6 | 30-Apr-25 A | 19-May-25 A | 46407 | 46407
Technical Bid Evaluation For 11KV Switchgear |  | 132 | 01-Jul-25 A | 23-Dec-25 A | 46407 | 46407
A13020 | Technical Bid Evaluation For 11KV Switchgear_IFD/IFC | 2 | 19-Dec-25 A | 23-Dec-25 A | 46407 | 46407
A13010 | Technical Bid Evaluation For 11KV Switchgear_RCA | 16 | 06-Nov-25 A | 17-Nov-25 A | 46407 | 46407
A13000 | Technical Bid Evaluation For 11KV Switchgear_IFA | 3 | 27-Oct-25 A | 05-Nov-25 A | 46407 | 46407
A12990 | Technical Bid Evaluation For 11KV Switchgear_RCC | 16 | 21-Jul-25 A | 22-Aug-25 A | 46407 | 46407
A12980 | Technical Bid Evaluation For 11KV Switchgear_IFR | 6 | 01-Jul-25 A | 18-Jul-25 A | 46407 | 46407
Technical Bid Evaluation For DC UPS |  | 61 | 01-Oct-25 A | 19-Jan-26 A | 46100 | 46407
A13170 | Technical Bid Evaluation For DC UPS_IFD/IFC | 2 | 15-Jan-26 A | 19-Jan-26 A | 46100 | 46100
A13160 | Technical Bid Evaluation For DC UPS_RCA | 16 | 24-Dec-25 A | 15-Jan-26 A | 46100 | 46100
A13150 | Technical Bid Evaluation For DC UPS_IFA | 3 | 19-Dec-25 A | 24-Dec-25 A | 46100 | 46100
A13140 | Technical Bid Evaluation For DC UPS_RCC | 16 | 08-Oct-25 A | 24-Oct-25 A | 46407 | 46407
A13130 | Technical Bid Evaluation For DC UPS_IFR | 6 | 01-Oct-25 A | 10-Oct-25 A | 46407 | 46407
Cable (MV and LV) Sizing Calculation |  | 95 | 19-Feb-25 A | 16-Oct-25 A | 46300 | 46407
A10750 | Cable (MV and LV) Sizing Calculation_IFA | 3 | 07-May-25 A | 19-Jun-25 A | 46300 | 46300
A10740 | Cable (MV and LV) Sizing Calculation_RCC | 16 | 13-Mar-25 A | 06-May-25 A | 46407 | 46407
A10760 | Cable (MV and LV) Sizing Calculation_RCA | 16 | 20-Jun-25 A | 26-Jun-25 A | 46407 | 46407
A10770 | Cable (MV and LV) Sizing Calculation_IFD/IFC | 2 | 10-Oct-25 A | 16-Oct-25 A | 46407 | 46407
A10730 | Cable (MV and LV) Sizing Calculation_IFR | 6 | 19-Feb-25 A | 12-Mar-25 A | 46407 | 46407
Lighting Design Calculation |  | 143 | 31-Jul-25 A | 23-Dec-25 A | 46407 | 46407
A10870 | Lighting Design Calculation_IFD/IFC | 2 | 19-Dec-25 A | 23-Dec-25 A | 46407 | 46407
A10860 | Lighting Design Calculation_RCA | 16 | 01-Oct-25 A | 17-Oct-25 A | 46407 | 46407
A10850 | Lighting Design Calculation_IFA | 3 | 01-Oct-25 A | 09-Oct-25 A | 46407 | 46407
A10840 | Lighting Design Calculation_RCC | 16 | 02-Aug-25 A | 22-Aug-25 A | 46407 | 46407
A10830 | Lighting Design Calculation_IFR | 6 | 31-Jul-25 A | 15-Aug-25 A | 46407 | 46407
Earthing and Lightning Protection Calculation |  | 87 | 31-Jul-25 A | 2026-02-24 | 2027-01-18 | 2027-01-20 | 237
A10920 | Earthing and Lightning Protection Calculation_IFD/IFC | 2 | 2026-02-20 | 2026-02-24 | 2027-01-18 | 2027-01-18 | 237
A10910 | Earthing and Lightning Protection Calculation_RCA | 16 | 28-Sep-25 A | 16-Oct-25 A | 46405 | 46405
A10900 | Earthing and Lightning Protection Calculation_IFA | 3 | 24-Sep-25 A | 09-Oct-25 A | 46405 | 46405
A10890 | Earthing and Lightning Protection Calculation_RCC | 16 | 10-Aug-25 A | 30-Aug-25 A | 46405 | 46405
A10880 | Earthing and Lightning Protection Calculation_IFR | 6 | 31-Jul-25 A | 11-Aug-25 A | 46405 | 46407
Power And Control Cable Schedule |  | 61 | 01-Aug-25 A | 19-Jan-26 A | 46300 | 46300
A12220 | Power And Control Cable Schedule_IFD/IFC | 2 | 15-Jan-26 A | 19-Jan-26 A | 46300 | 46300
A12210 | Power And Control Cable Schedule_RCA | 16 | 24-Dec-25 A | 15-Jan-26 A | 46300 | 46300
A12200 | Power And Control Cable Schedule_IFA | 3 | 19-Dec-25 A | 24-Dec-25 A | 46300 | 46300
A12190 | Power And Control Cable Schedule_RCC | 16 | 08-Aug-25 A | 22-Aug-25 A | 46300 | 46300
A12180 | Power And Control Cable Schedule_IFR | 6 | 01-Aug-25 A | 15-Aug-25 A | 46300 | 46300
Interconnection Schedule |  | 43 | 2026-02-20 | 2026-04-21 | 2026-11-04 | 2027-01-01 | 183
A12420 | Interconnection Schedule_IFD/IFC | 2 | 2026-04-17 | 2026-04-21 | 2026-11-04 | 2026-11-11 | 183
A12410 | Interconnection Schedule_RCA | 16 | 2026-03-26 | 2026-04-17 | 2026-11-11 | 2026-12-03 | 183
A12400 | Interconnection Schedule_IFA | 3 | 2026-03-23 | 2026-03-26 | 2026-12-03 | 2026-12-08 | 183
A12390 | Interconnection Schedule_RCC | 16 | 2026-02-27 | 2026-03-23 | 2026-12-09 | 2026-12-30 | 183
A12380 | Interconnection Schedule_IFR | 6 | 2026-02-20 | 2026-02-27 | 2026-12-30 | 2027-01-01 | 183
Electrical Substation Building Layout |  | 274 | 03-Jan-25 A | 30-Dec-25 A | 46095 | 46407
A11970 | Electrical Substation Building Layout_IFD/IFC | 2 | 26-Dec-25 A | 30-Dec-25 A | 46095 | 46095
A11960 | Electrical Substation Building Layout_RCA | 16 | 24-Aug-25 A | 30-Aug-25 A | 46095 | 46095
A11950 | Electrical Substation Building Layout_IFA | 3 | 16-May-25 A | 23-Aug-25 A | 46095 | 46095
A11940 | Electrical Substation Building Layout_RCC | 16 | 25-Jan-25 A | 15-May-25 A | 46407 | 46407
A11930 | Electrical Substation Building Layout_IFR | 6 | 03-Jan-25 A | 24-Jan-25 A | 46407 | 46407
Cable and Tray Routing Layout - Outdoor |  | 92 | 01-Oct-25 A | 2026-04-15 | 2026-09-01 | 2026-10-05 | 124
A11870 | Cable and Tray Routing Layout - Outdoor_IFD/IFC | 6 | 2026-04-07 | 2026-04-15 | 2026-09-01 | 2026-09-01 | 124
A11860 | Cable and Tray Routing Layout - Outdoor_RCA | 16 | 2026-02-25 | 2026-03-19 | 2026-09-01 | 2026-09-01 | 137
A11850 | Cable and Tray Routing Layout - Outdoor_IFA | 3 | 2026-02-20 | 2026-02-25 | 2026-09-01 | 2026-09-04 | 137
A11840 | Cable and Tray Routing Layout - Outdoor_RCC | 16 | 19-Dec-25 A | 21-Jan-26 A | 46269 | 46293
A11830 | Cable and Tray Routing Layout - Outdoor_IFR | 6 | 01-Oct-25 A | 10-Oct-25 A | 46293 | 46300
Underground 33KV Cable Routing Layout Overall - Update |  | 122 | 17-Oct-25 A | 2026-04-15 | 2026-09-10 | 2026-10-05 | 124
A55940 | Underground 33KV Cable Routing Layout Overall - Update_IFD/IFC | 2 | 2026-04-13 | 2026-04-15 | 2026-09-10 | 2026-09-10 | 124
A55930 | Underground 33KV Cable Routing Layout Overall - Update_RCA | 16 | 2026-02-20 | 2026-03-13 | 2026-09-10 | 2026-09-10 | 144
A55920 | Underground 33KV Cable Routing Layout Overall - Update_IFA | 3 | 10-Dec-25 A | 19-Dec-25 A | 46275 | 46275
A55900 | Underground 33KV Cable Routing Layout Overall - Update_IFR | 6 | 17-Oct-25 A | 25-Oct-25 A | 46275 | 46296
A55910 | Underground 33KV Cable Routing Layout Overall - Update_RCC | 16 | 27-Oct-25 A | 06-Nov-25 A | 46296 | 46300
Cable and Tray Routing Layout - Indoor |  | 43 | 2026-03-09 | 2026-05-06 | 2026-08-06 | 2026-10-05 | 108
A11920 | Cable and Tray Routing Layout - Indoor_IFD/IFC | 2 | 2026-05-04 | 2026-05-06 | 2026-08-06 | 2026-08-13 | 108
A11910 | Cable and Tray Routing Layout - Indoor_RCA | 16 | 2026-04-13 | 2026-05-04 | 2026-08-13 | 2026-09-04 | 108
A11900 | Cable and Tray Routing Layout - Indoor_IFA | 3 | 2026-04-07 | 2026-04-10 | 2026-09-04 | 2026-09-09 | 108
A11890 | Cable and Tray Routing Layout - Indoor_RCC | 16 | 2026-03-16 | 2026-04-07 | 2026-09-10 | 2026-10-01 | 108
A11880 | Cable and Tray Routing Layout - Indoor_IFR | 6 | 2026-03-09 | 2026-03-16 | 2026-10-01 | 2026-10-05 | 108
Overall Lighting & Small Power Layout |  | 118 | 23-Aug-25 A | 23-Jan-26 A | 46300 | 46300
A12020 | Overall Lighting & Small Power Layout_IFD/IFC | 6 | 15-Jan-26 A | 23-Jan-26 A | 46300 | 46300
A12010 | Overall Lighting & Small Power Layout_RCA | 16 | 24-Dec-25 A | 15-Jan-26 A | 46300 | 46300
A12000 | Overall Lighting & Small Power Layout_IFA | 3 | 19-Dec-25 A | 24-Dec-25 A | 46300 | 46300
A11980 | Overall Lighting & Small Power Layout_IFR | 6 | 23-Aug-25 A | 13-Sep-25 A | 46300 | 46300
A11990 | Overall Lighting & Small Power Layout_RCC | 16 | 28-Aug-25 A | 20-Sep-25 A | 46300 | 46300
Earthing And Lightning Protection System Layout |  | 59 | 20-Dec-25 A | 2026-03-26 | 2026-09-01 | 2026-10-05 | 137
A12070 | Earthing And Lightning Protection System Layout_IFD/IFC | 6 | 2026-03-19 | 2026-03-26 | 2026-09-01 | 2026-09-01 | 137
A12060 | Earthing And Lightning Protection System Layout_RCA | 16 | 2026-02-25 | 2026-03-19 | 2026-09-01 | 2026-09-01 | 137
A12050 | Earthing And Lightning Protection System Layout_IFA | 3 | 2026-02-20 | 2026-02-25 | 2026-09-01 | 2026-09-04 | 137
A12040 | Earthing And Lightning Protection System Layout_RCC | 16 | 12-Jan-26 A | 17-Jan-26 A | 46269 | 46293
A12030 | Earthing And Lightning Protection System Layout_IFR | 6 | 20-Dec-25 A | 12-Jan-26 A | 46293 | 46300
Updation of Earthing Layout Butene 1, EU3, B3/EU3 |  | 136 | 10-Sep-25 A | 2026-04-17 | 2026-04-14 | 2027-01-20 | 199
A12120 | Updation of Earthing Layout Butene 1, EU3, B3/EU3_IFD/IFC | 6 | 2026-04-09 | 2026-04-17 | 2026-04-14 | 2026-04-14 | 199
A12110 | Updation of Earthing Layout Butene 1, EU3, B3/EU3_RCA | 16 | 2026-03-19 | 2026-04-09 | 2026-11-25 | 2026-12-17 | 199
A12100 | Updation of Earthing Layout Butene 1, EU3, B3/EU3_IFA | 3 | 2026-03-13 | 2026-03-19 | 2026-12-17 | 2026-12-22 | 199
A12090 | Updation of Earthing Layout Butene 1, EU3, B3/EU3_RCC | 16 | 2026-02-20 | 2026-03-13 | 2026-12-22 | 2027-01-13 | 199
A12080 | Updation of Earthing Layout Butene 1, EU3, B3/EU3_IFR | 6 | 10-Sep-25 A | 15-Sep-25 A | 46400 | 46407
Electrical Bulk MTO |  | 73 | 20-Apr-25 A | 25-May-25 A | 46126 | 46168
A13470 | Electrical Bulk MTO_IFD/IFC | 2 | 19-May-25 A | 25-May-25 A | 46126 | 46126
A13440 | Electrical Bulk MTO_RCC | 16 | 12-May-25 A | 18-May-25 A | 46126 | 46126
A13430 | Electrical Bulk MTO_IFR | 6 | 20-Apr-25 A | 11-May-25 A | 46168 | 46168
Instrumentation |  | 384 | 31-Dec-24 A | 2026-06-03 | 2026-03-02 | 2027-01-20 | 166
Scope of Work for the ICSS System |  | 212 | 01-Jul-25 A | 2026-04-14 | 2026-03-19 | 2027-01-20 | 202
A14570 | Scope of Work for the ICSS System_IFD/IFC | 2 | 2026-04-09 | 2026-04-14 | 2026-03-19 | 2026-03-19 | 202
A14560 | Scope of Work for the ICSS System_RCA | 16 | 2026-03-19 | 2026-04-09 | 2026-11-30 | 2026-12-22 | 202
A14550 | Scope of Work for the ICSS System_IFA | 3 | 2026-03-13 | 2026-03-19 | 2026-12-22 | 2026-12-25 | 202
A14540 | Scope of Work for the ICSS System_RCC | 16 | 2026-02-20 | 2026-03-13 | 2026-12-28 | 2027-01-18 | 202
A14530 | Scope of Work for the ICSS System_IFR | 6 | 01-Jul-25 A | 12-Jul-25 A | 46405 | 46407
Scope of Work for the MCMS System |  | 212 | 01-Mar-25 A | 2026-04-14 | 2026-03-19 | 2027-01-20 | 202
A58530 | Scope of Work for the MCMS System_IFD/IFC | 2 | 2026-04-09 | 2026-04-14 | 2026-03-19 | 2026-03-19 | 202
A58520 | Scope of Work for the MCMSSystem_RCA | 16 | 2026-03-19 | 2026-04-09 | 2026-11-30 | 2026-12-22 | 202
A58510 | Scope of Work for the MCMS System_IFA | 3 | 2026-03-13 | 2026-03-19 | 2026-12-22 | 2026-12-25 | 202
A58500 | Scope of Work for the MCMS System_RCC | 16 | 2026-02-20 | 2026-03-13 | 2026-12-28 | 2027-01-18 | 202
A58490 | Scope of Work for the MCMS System_IFR | 6 | 01-Mar-25 A | 10-Mar-25 A | 46405 | 46407
Instrument Datasheet for ESD Valves |  | 293 | 13-Mar-25 A | 2026-02-24 | 2026-03-02 | 2026-03-19 | 18
A14470 | Instrument Datasheet for ESD Valves_IFD/IFC | 2 | 2026-02-20 | 2026-02-24 | 2026-03-02 | 2026-03-02 | 18
A14460 | Instrument Datasheet for ESD Valves_RCA | 16 | 24-Nov-25 A | 22-Jan-26 A | 46098 | 46098
A14450 | Instrument Datasheet for ESD Valves_IFA | 3 | 14-Jun-25 A | 21-Jun-25 A | 46098 | 46098
A14440 | Instrument Datasheet for ESD Valves_RCC | 16 | 28-Apr-25 A | 13-Jun-25 A | 46098 | 46098
A14430 | Instrument Datasheet for ESD Valves_IFR | 1 | 13-Mar-25 A | 27-Apr-25 A | 46098 | 46100
Instrument Datasheet for Control Valves |  | 196 | 13-Mar-25 A | 10-Sep-25 A | 46100 | 46100
A14320 | Instrument Datasheet for Control Valves_IFD/IFC | 2 | 09-Sep-25 A | 10-Sep-25 A | 46100 | 46100
A14310 | Instrument Datasheet for Control Valves_RCA | 16 | 19-Aug-25 A | 08-Sep-25 A | 46100 | 46100
A14300 | Instrument Datasheet for Control Valves_IFA | 3 | 22-Jun-25 A | 28-Jun-25 A | 46100 | 46100
A14290 | Instrument Datasheet for Control Valves_RCC | 16 | 28-Apr-25 A | 21-Jun-25 A | 46100 | 46100
A14280 | Instrument Datasheet for Control Valves_IFR | 1 | 13-Mar-25 A | 27-Apr-25 A | 46100 | 46100
Instrument Datasheet for Motor Operated Valves |  | 195 | 13-Mar-25 A | 10-Sep-25 A | 46100 | 46100
A14370 | Instrument Datasheet for Motor Operated Valves_IFD/IFC | 2 | 09-Sep-25 A | 10-Sep-25 A | 46100 | 46100
A14360 | Instrument Datasheet for Motor Operated Valves_RCA | 16 | 19-Aug-25 A | 08-Sep-25 A | 46100 | 46100
A14350 | Instrument Datasheet for Motor Operated Valves_IFA | 3 | 14-Jun-25 A | 21-Jun-25 A | 46100 | 46100
A14340 | Instrument Datasheet for Motor Operated Valves_RCC | 16 | 28-Apr-25 A | 13-Jun-25 A | 46100 | 46100
A14330 | Instrument Datasheet for Motor Operated Valves_IFR | 1 | 13-Mar-25 A | 27-Apr-25 A | 46100 | 46100
Instrument Datasheet for Analyzers |  | 166 | 01-Jul-25 A | 2026-02-24 | 2026-03-02 | 2026-03-17 | 15
A14170 | Instrument Datasheet for Analyzers_IFD/IFC | 2 | 2026-02-20 | 2026-02-24 | 2026-03-02 | 2026-03-02 | 15
A14160 | Instrument Datasheet for Analyzers_RCA | 16 | 25-Aug-25 A | 06-Sep-25 A | 46094 | 46094
A14150 | Instrument Datasheet for Analyzers_IFA | 3 | 22-Aug-25 A | 30-Aug-25 A | 46094 | 46094
A14140 | Instrument Datasheet for Analyzers_RCC | 16 | 04-Aug-25 A | 25-Aug-25 A | 46094 | 46094
A14130 | Instrument Datasheet for Analyzers_IFR | 1 | 01-Jul-25 A | 12-Jul-25 A | 46094 | 46098
Instrument Datasheet for Flow Element (Orifice Plate) |  | 244 | 07-Apr-25 A | 23-Dec-25 A | 46083 | 46407
A13870 | Instrument Datasheet for Flow Element (Orifice Plate)_IFD/IFC | 2 | 19-Dec-25 A | 23-Dec-25 A | 46083 | 46083
A13860 | Instrument Datasheet for Flow Element (Orifice Plate)_RCA | 16 | 29-Jun-25 A | 05-Jul-25 A | 46407 | 46407
A13850 | Instrument Datasheet for Flow Element (Orifice Plate)_IFA | 3 | 22-Jun-25 A | 28-Jun-25 A | 46407 | 46407
A13840 | Instrument Datasheet for Flow Element (Orifice Plate)_RCC | 16 | 29-Apr-25 A | 21-Jun-25 A | 46407 | 46407
A13830 | Instrument Datasheet for Flow Element (Orifice Plate)_IFR | 1 | 07-Apr-25 A | 28-Apr-25 A | 46407 | 46407
Instrument Datasheet for Flow Element (Venturi Tube) |  | 178 | 13-Mar-25 A | 22-Aug-25 A | 46083 | 46083
A13920 | Instrument Datasheet for Flow Element (Venturi Tube)_IFD/IFC | 2 | 19-Aug-25 A | 22-Aug-25 A | 46083 | 46083
A13910 | Instrument Datasheet for Flow Element (Venturi Tube)_RCA | 16 | 22-Jun-25 A | 28-Jun-25 A | 46083 | 46083
A13900 | Instrument Datasheet for Flow Element (Venturi Tube)_IFA | 3 | 14-Jun-25 A | 21-Jun-25 A | 46083 | 46083
A13890 | Instrument Datasheet for Flow Element (Venturi Tube)_RCC | 16 | 28-Apr-25 A | 13-Jun-25 A | 46083 | 46083
A13880 | Instrument Datasheet for Flow Element (Venturi Tube)_IFR | 1 | 13-Mar-25 A | 27-Apr-25 A | 46083 | 46083
Instrument Datasheet for Rotameter |  | 222 | 13-Mar-25 A | 21-Nov-25 A | 46083 | 46100
A14520 | Instrument Datasheet for Rotameter_IFD/IFC | 2 | 14-Nov-25 A | 21-Nov-25 A | 46083 | 46083
A14510 | Instrument Datasheet for Rotameter_RCA | 16 | 22-Jun-25 A | 08-Sep-25 A | 46100 | 46100
A14500 | Instrument Datasheet for Rotameter_IFA | 3 | 14-Jun-25 A | 21-Jun-25 A | 46100 | 46100
A14490 | Instrument Datasheet for Rotameter_RCC | 16 | 28-Apr-25 A | 13-Jun-25 A | 46100 | 46100
A14480 | Instrument Datasheet for Rotameter_IFR | 1 | 13-Mar-25 A | 27-Apr-25 A | 46100 | 46100
Instrument Datasheet for Electronic Transmitters (Pressure / Level / DP) |  | 241 | 26-Mar-25 A | 23-Dec-25 A | 46083 | 46100
A13720 | Instrument Datasheet for Electronic Transmitters (Pressure / Level / DP)_IFD/IFC | 2 | 19-Dec-25 A | 23-Dec-25 A | 46083 | 46083
A13710 | Instrument Datasheet for Electronic Transmitters (Pressure / Level / DP)_RCA | 16 | 16-Aug-25 A | 30-Aug-25 A | 46100 | 46100
A13700 | Instrument Datasheet for Electronic Transmitters (Pressure / Level / DP)_IFA | 3 | 19-Aug-25 A | 23-Aug-25 A | 46100 | 46100
A13690 | Instrument Datasheet for Electronic Transmitters (Pressure / Level / DP)_RCC | 16 | 17-Apr-25 A | 02-May-25 A | 46100 | 46100
A13680 | Instrument Datasheet for Electronic Transmitters (Pressure / Level / DP)_IFR | 1 | 26-Mar-25 A | 16-Apr-25 A | 46100 | 46100
Instrument Datasheet for Electronic Transmitters (Flow) |  | 240 | 13-Mar-25 A | 23-Dec-25 A | 46083 | 46100
A13770 | Instrument Datasheet for Electronic Transmitters (Flow)_IFD/IFC | 2 | 19-Dec-25 A | 23-Dec-25 A | 46083 | 46083
A13760 | Instrument Datasheet for Electronic Transmitters (Flow)_RCA | 16 | 22-Jun-25 A | 10-Sep-25 A | 46100 | 46100
A13750 | Instrument Datasheet for Electronic Transmitters (Flow)_IFA | 3 | 05-May-25 A | 21-Jun-25 A | 46100 | 46100
A13740 | Instrument Datasheet for Electronic Transmitters (Flow)_RCC | 16 | 28-Apr-25 A | 04-May-25 A | 46100 | 46100
A13730 | Instrument Datasheet for Electronic Transmitters (Flow)_IFR | 1 | 13-Mar-25 A | 27-Apr-25 A | 46100 | 46100
Instrument Datasheet for Temperature Transmitters (Head mounted) |  | 284 | 25-Mar-25 A | 2026-02-24 | 2026-03-02 | 2027-01-20 | 237
A14420 | Instrument Datasheet for Temperature Transmitters (Head mounted)_IFD/IFC | 2 | 2026-02-20 | 2026-02-24 | 2026-03-02 | 2026-03-02 | 237
A14410 | Instrument Datasheet for Temperature Transmitters (Head mounted)_RCA | 16 | 06-Jul-25 A | 12-Jul-25 A | 46405 | 46405
A14400 | Instrument Datasheet for Temperature Transmitters (Head mounted)_IFA | 3 | 29-Jun-25 A | 05-Jul-25 A | 46405 | 46405
A14390 | Instrument Datasheet for Temperature Transmitters (Head mounted)_RCC | 16 | 22-Jun-25 A | 28-Jun-25 A | 46405 | 46405
A14380 | Instrument Datasheet for Temperature Transmitters (Head mounted)_IFR | 1 | 25-Mar-25 A | 21-Jun-25 A | 46405 | 46407
Instrument Datasheet for Level Transmitters (GWR type) |  | 232 | 13-Mar-25 A | 18-Dec-25 A | 46083 | 46407
A14110 | Instrument Datasheet for Level Transmitters (GWR type)_RCA | 16 | 03-Nov-25 A | 21-Nov-25 A | 46083 | 46083
A14120 | Instrument Datasheet for Level Transmitters (GWR type)_IFD/IFC | 2 | 08-Dec-25 A | 18-Dec-25 A | 46100 | 46100
A14100 | Instrument Datasheet for Level Transmitters (GWR type)_IFA | 3 | 19-Aug-25 A | 23-Aug-25 A | 46100 | 46100
A14090 | Instrument Datasheet for Level Transmitters (GWR type)_RCC | 16 | 28-Apr-25 A | 23-Jun-25 A | 46407 | 46407
A14080 | Instrument Datasheet for Level Transmitters (GWR type)_IFR | 1 | 13-Mar-25 A | 27-Apr-25 A | 46407 | 46407
Instrument Datasheet for Temperature Element / Thermowell |  | 237 | 29-May-25 A | 23-Dec-25 A | 46083 | 46100
A13970 | Instrument Datasheet for Temperature Element / Thermowell_IFD/IFC | 2 | 19-Dec-25 A | 23-Dec-25 A | 46083 | 46083
A13960 | Instrument Datasheet for Temperature Element / Thermowell_RCA | 16 | 02-Jul-25 A | 18-Jul-25 A | 46100 | 46100
A13950 | Instrument Datasheet for Temperature Element / Thermowell_IFA | 3 | 30-Jun-25 A | 07-Jul-25 A | 46100 | 46100
A13940 | Instrument Datasheet for Temperature Element / Thermowell_RCC | 16 | 30-May-25 A | 28-Jun-25 A | 46100 | 46100
A13930 | Instrument Datasheet for Temperature Element / Thermowell_IFR | 1 | 29-May-25 A | 20-Jun-25 A | 46100 | 46100
Instrument Datasheet for Temperature Gauges / Thermowell |  | 236 | 13-Mar-25 A | 23-Dec-25 A | 46083 | 46407
A14070 | Instrument Datasheet for Temperature Gauges / Thermowell_IFD/IFC | 2 | 19-Dec-25 A | 23-Dec-25 A | 46083 | 46083
A14060 | Instrument Datasheet for Temperature Gauges / Thermowell_RCA | 16 | 20-Oct-25 A | 12-Nov-25 A | 46407 | 46407
A14050 | Instrument Datasheet for Temperature Gauges / Thermowell_IFA | 3 | 11-Jul-25 A | 28-Jul-25 A | 46407 | 46407
A14040 | Instrument Datasheet for Temperature Gauges / Thermowell_RCC | 16 | 19-Apr-25 A | 13-Jun-25 A | 46407 | 46407
A14030 | Instrument Datasheet for Temperature Gauges / Thermowell_IFR | 1 | 13-Mar-25 A | 28-Apr-25 A | 46407 | 46407
Instrument Datasheet for Pressure Gauges |  | 235 | 21-Apr-25 A | 23-Dec-25 A | 46083 | 46405
A14020 | Instrument Datasheet for Pressure Gauges_IFD/IFC | 2 | 19-Dec-25 A | 23-Dec-25 A | 46083 | 46083
A14010 | Instrument Datasheet for Pressure Gauges_RCA | 16 | 01-Nov-25 A | 21-Nov-25 A | 46378 | 46378
A14000 | Instrument Datasheet for Pressure Gauges_IFA | 3 | 31-Jul-25 A | 13-Aug-25 A | 46378 | 46378
A13990 | Instrument Datasheet for Pressure Gauges_RCC | 16 | 26-Jun-25 A | 20-Jul-25 A | 46405 | 46405
A13980 | Instrument Datasheet for Pressure Gauges_IFR | 1 | 21-Apr-25 A | 27-Apr-25 A | 46405 | 46405
Instrument Datasheet for Level Gauges (Magnetic Type) |  | 169 | 13-Mar-25 A | 22-Aug-25 A | 46083 | 46083
A14220 | Instrument Datasheet for Level Gauges (Magnetic Type)_IFD/IFC | 2 | 19-Aug-25 A | 22-Aug-25 A | 46083 | 46083
A14210 | Instrument Datasheet for Level Gauges (Magnetic Type)_RCA | 16 | 22-Jun-25 A | 28-Jun-25 A | 46083 | 46083
A14190 | Instrument Datasheet for Level Gauges (Magnetic Type)_RCC | 16 | 24-Apr-25 A | 13-Jun-25 A | 46083 | 46083
A14200 | Instrument Datasheet for Level Gauges (Magnetic Type)_IFA | 3 | 14-Jun-25 A | 21-Jun-25 A | 46083 | 46083
A14180 | Instrument Datasheet for Level Gauges (Magnetic Type)_IFR | 1 | 13-Mar-25 A | 27-Apr-25 A | 46083 | 46083
Instrument Datasheet for Fire & Gas Detectors |  | 122 | 26-May-25 A | 23-Dec-25 A | 46100 | 46100
A14270 | Instrument Datasheet for Fire & Gas Detectors_IFD/IFC | 2 | 19-Dec-25 A | 23-Dec-25 A | 46100 | 46100
A14260 | Instrument Datasheet for Fire & Gas Detectors_RCA | 16 | 10-Oct-25 A | 25-Oct-25 A | 46100 | 46100
A14250 | Instrument Datasheet for Fire & Gas Detectors_IFA | 3 | 26-Sep-25 A | 13-Oct-25 A | 46100 | 46100
A14240 | Instrument Datasheet for Fire & Gas Detectors_RCC | 11 | 07-Aug-25 A | 01-Sep-25 A | 46100 | 46100
A14230 | Instrument Datasheet for Fire & Gas Detectors_IFR | 1 | 26-May-25 A | 05-Jul-25 A | 46100 | 46100
Instrument Datasheet for Loop Powered Indicator |  | 132 | 07-Apr-25 A | 05-Jul-25 A | 46407 | 46407
A13820 | Instrument Datasheet for Loop Powered Indicator_IFD/IFC | 2 | 29-Jun-25 A | 05-Jul-25 A | 46407 | 46407
A13810 | Instrument Datasheet for Loop Powered Indicator_RCA | 16 | 22-Jun-25 A | 28-Jun-25 A | 46407 | 46407
A13790 | Instrument Datasheet for Loop Powered Indicator_RCC | 16 | 29-Apr-25 A | 30-May-25 A | 46407 | 46407
A13800 | Instrument Datasheet for Loop Powered Indicator_IFA | 3 | 01-Jun-25 A | 21-Jun-25 A | 46407 | 46407
A13780 | Instrument Datasheet for Loop Powered Indicator_IFR | 1 | 07-Apr-25 A | 28-Apr-25 A | 46407 | 46407
Material Requisition for ESD Valves |  | 225 | 24-Mar-25 A | 03-Sep-25 A | 46083 | 46100
A15170 | Material Requisition for ESD Valves_IFD/IFC | 2 | 28-Aug-25 A | 03-Sep-25 A | 46083 | 46083
A15160 | Material Requisition for ESD Valves_RCA | 16 | 29-Jun-25 A | 27-Aug-25 A | 46100 | 46100
A15140 | Material Requisition for ESD Valves_RCC | 16 | 01-May-25 A | 21-Jun-25 A | 46100 | 46100
A15150 | Material Requisition for ESD Valves_IFA | 3 | 22-Jun-25 A | 28-Jun-25 A | 46100 | 46100
A15130 | Material Requisition for ESD Valves_IFR | 2 | 24-Mar-25 A | 30-Apr-25 A | 46100 | 46100
Material Requisition for Control Valves |  | 197 | 13-Mar-25 A | 19-Sep-25 A | 46100 | 46100
A15020 | Material Requisition for Control Valves_IFD/IFC | 2 | 10-Sep-25 A | 19-Sep-25 A | 46100 | 46100
A15010 | Material Requisition for Control Valves_RCA | 16 | 29-Jun-25 A | 02-Sep-25 A | 46100 | 46100
A15000 | Material Requisition for Control Valves_IFA | 3 | 22-Jun-25 A | 28-Jun-25 A | 46100 | 46100
A14990 | Material Requisition for Control Valves_RCC | 16 | 28-Apr-25 A | 21-Jun-25 A | 46100 | 46100
A14980 | Material Requisition for Control Valves_IFR | 2 | 13-Mar-25 A | 27-Apr-25 A | 46100 | 46100
Material Requisition for Motor Operated Valves |  | 196 | 24-Mar-25 A | 13-Sep-25 A | 46100 | 46100
A15120 | Material Requisition for Motor Operated Valves_IFD/IFC | 2 | 11-Sep-25 A | 13-Sep-25 A | 46100 | 46100
A15110 | Material Requisition for Motor Operated Valves_RCA | 16 | 22-Jun-25 A | 08-Sep-25 A | 46100 | 46100
A15100 | Material Requisition for Motor Operated Valves_IFA | 3 | 14-Jun-25 A | 21-Jun-25 A | 46100 | 46100
A15090 | Material Requisition for Motor Operated Valves_RCC | 16 | 28-Apr-25 A | 13-Jun-25 A | 46100 | 46100
A15080 | Material Requisition for Motor Operated Valves_IFR | 2 | 24-Mar-25 A | 27-Apr-25 A | 46100 | 46100
Material Requisition for Analyzers |  | 168 | 01-Jul-25 A | 2026-02-26 | 2026-03-17 | 2026-03-19 | 15
A14870 | Material Requisition for Analyzers_IFD/IFC | 2 | 2026-02-24 | 2026-02-26 | 2026-03-17 | 2026-03-17 | 15
A14860 | Material Requisition for Analyzers_RCA | 16 | 20-Aug-25 A | 11-Sep-25 A | 46098 | 46098
A14850 | Material Requisition for Analyzers_IFA | 3 | 26-Aug-25 A | 30-Aug-25 A | 46098 | 46098
A14840 | Material Requisition for Analyzers_RCC | 16 | 01-Aug-25 A | 25-Aug-25 A | 46098 | 46098
A14830 | Material Requisition for Analyzers_IFR | 2 | 01-Jul-25 A | 15-Jul-25 A | 46098 | 46100
Material Requisition for Flow Element (Orifice Plate) |  | 246 | 14-Mar-25 A | 25-Dec-25 A | 46177 | 46407
A14670 | Material Requisition for Flow Element (Orifice Plate)_IFD/IFC | 2 | 23-Dec-25 A | 25-Dec-25 A | 46177 | 46177
A14660 | Material Requisition for Flow Element (Orifice Plate)_RCA | 16 | 29-Jun-25 A | 05-Jul-25 A | 46407 | 46407
A14650 | Material Requisition for Flow Element (Orifice Plate)_IFA | 3 | 22-Jun-25 A | 28-Jun-25 A | 46407 | 46407
A14640 | Material Requisition for Flow Element (Orifice Plate)_RCC | 16 | 30-Apr-25 A | 21-Jun-25 A | 46407 | 46407
A14630 | Material Requisition for Flow Element (Orifice Plate)_IFR | 2 | 14-Mar-25 A | 29-Apr-25 A | 46407 | 46407
Material Requisition for Flow Element (Venturi Tube) |  | 172 | 13-Mar-25 A | 15-Sep-25 A | 46083 | 46083
A14720 | Material Requisition for Flow Element (Venturi Tube)_IFD/IFC | 2 | 12-Sep-25 A | 15-Sep-25 A | 46083 | 46083
A14710 | Material Requisition for Flow Element (Venturi Tube)_RCA | 16 | 22-Aug-25 A | 11-Sep-25 A | 46083 | 46083
A14700 | Material Requisition for Flow Element (Venturi Tube)_IFA | 3 | 22-Jun-25 A | 28-Jun-25 A | 46083 | 46083
A14690 | Material Requisition for Flow Element (Venturi Tube)_RCC | 16 | 01-May-25 A | 21-Jun-25 A | 46083 | 46083
A14680 | Material Requisition for Flow Element (Venturi Tube)_IFR | 2 | 13-Mar-25 A | 30-Apr-25 A | 46083 | 46083
Material Requisition for Rotameter |  | 204 | 25-Mar-25 A | 04-Oct-25 A | 46100 | 46100
A15220 | Material Requisition for Rotameter_IFD/IFC | 2 | 26-Sep-25 A | 04-Oct-25 A | 46100 | 46100
A15210 | Material Requisition for Rotameter_RCA | 16 | 22-Jun-25 A | 07-Jul-25 A | 46100 | 46100
A15200 | Material Requisition for Rotameter_IFA | 3 | 14-Jun-25 A | 28-Jun-25 A | 46100 | 46100
A15190 | Material Requisition for Rotameter_RCC | 16 | 02-May-25 A | 21-Jun-25 A | 46100 | 46100
A15180 | Material Requisition for Rotameter_IFR | 1 | 25-Mar-25 A | 01-May-25 A | 46100 | 46100
Material Requisition for Electronic Transmitters |  | 241 | 25-Mar-25 A | 25-Dec-25 A | 46100 | 46100
A14620 | Material Requisition for Electronic Transmitters_IFD/IFC | 2 | 23-Dec-25 A | 25-Dec-25 A | 46100 | 46100
A14610 | Material Requisition for Electronic Transmitters_RCA | 16 | 24-Aug-25 A | 06-Sep-25 A | 46100 | 46100
A14600 | Material Requisition for Electronic Transmitters_IFA | 3 | 31-Jul-25 A | 23-Aug-25 A | 46100 | 46100
A14590 | Material Requisition for Electronic Transmitters_RCC | 16 | 29-Apr-25 A | 30-Jul-25 A | 46100 | 46100
A14580 | Material Requisition for Electronic Transmitters_IFR | 2 | 25-Mar-25 A | 28-Apr-25 A | 46100 | 46100
Material Requisition for Level Transmitters (GWR type) |  | 215 | 26-Mar-25 A | 28-Aug-25 A | 46100 | 46100
A14920 | Material Requisition for Level Transmitters (GWR type)_IFD/IFC | 2 | 20-Aug-25 A | 28-Aug-25 A | 46100 | 46100
A14910 | Material Requisition for Level Transmitters (GWR type)_RCA | 16 | 01-Aug-25 A | 19-Aug-25 A | 46100 | 46100
A14900 | Material Requisition for Level Transmitters (GWR type)_IFA | 3 | 31-Jul-25 A | 11-Aug-25 A | 46100 | 46100
A14890 | Material Requisition for Level Transmitters (GWR type)_RCC | 16 | 04-Jul-25 A | 28-Jul-25 A | 46100 | 46100
A14880 | Material Requisition for Level Transmitters (GWR type)_IFR | 2 | 26-Mar-25 A | 28-Apr-25 A | 46100 | 46100
Material Requisition for Temperature Element / Thermowell |  | 176 | 13-Mar-25 A | 23-Jan-26 A | 46100 | 46100
A14770 | Material Requisition for Temperature Element / Thermowell_IFD/IFC | 2 | 20-Jan-26 A | 23-Jan-26 A | 46100 | 46100
A14760 | Material Requisition for Temperature Element / Thermowell_RCA | 16 | 15-Jan-26 A | 20-Jan-26 A | 46100 | 46100
A14750 | Material Requisition for Temperature Element / Thermowell_IFA | 3 | 09-Jan-26 A | 15-Jan-26 A | 46100 | 46100
A14740 | Material Requisition for Temperature Element / Thermowell_RCC | 16 | 19-Dec-25 A | 09-Jan-26 A | 46100 | 46100
A14730 | Material Requisition for Temperature Element / Thermowell_IFR | 2 | 13-Mar-25 A | 07-May-25 A | 46100 | 46100
Material Requisition for Temperature Gauges / Pressure Gauges |  | 298 | 25-Mar-25 A | 2026-03-23 | 2026-03-19 | 2027-01-20 | 218
A14820 | Material Requisition for Temperature Gauges / Pressure Gauges_IFD/IFC | 2 | 2026-03-19 | 2026-03-23 | 2026-03-19 | 2026-03-19 | 218
A14810 | Material Requisition for Temperature Gauges / Pressure Gauges_RCA | 16 | 2026-02-25 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 218
A14800 | Material Requisition for Temperature Gauges / Pressure Gauges_IFA | 3 | 2026-02-20 | 2026-02-25 | 2026-12-22 | 2026-12-25 | 218
A14790 | Material Requisition for Temperature Gauges / Pressure Gauges_RCC | 16 | 01-May-25 A | 21-Jun-25 A | 46384 | 46405
A14780 | Material Requisition for Temperature Gauges / Pressure Gauges_IFR | 2 | 25-Mar-25 A | 30-Apr-25 A | 46405 | 46407
Material Requisition for Level Gauges (Magnetic Type) |  | 180 | 25-Mar-25 A | 17-Sep-25 A | 46083 | 46083
A14970 | Material Requisition for Level Gauges (Magnetic Type)_IFD/IFC | 2 | 03-Sep-25 A | 17-Sep-25 A | 46083 | 46083
A14960 | Material Requisition for Level Gauges (Magnetic Type)_RCA | 16 | 27-Aug-25 A | 02-Sep-25 A | 46083 | 46083
A14950 | Material Requisition for Level Gauges (Magnetic Type)_IFA | 3 | 31-Jul-25 A | 26-Aug-25 A | 46083 | 46083
A14940 | Material Requisition for Level Gauges (Magnetic Type)_RCC | 16 | 24-Apr-25 A | 30-Jul-25 A | 46083 | 46083
A14930 | Material Requisition for Level Gauges (Magnetic Type)_IFR | 2 | 25-Mar-25 A | 23-Apr-25 A | 46083 | 46083
Material Requisition for Fire & Gas Detectors |  | 124 | 27-May-25 A | 25-Dec-25 A | 46100 | 46100
A15070 | Material Requisition for Fire & Gas Detectors_IFD/IFC | 2 | 23-Dec-25 A | 25-Dec-25 A | 46100 | 46100
A15060 | Material Requisition for Fire & Gas Detectors_RCA | 11 | 29-Sep-25 A | 20-Oct-25 A | 46100 | 46100
A15050 | Material Requisition for Fire & Gas Detectors_IFA | 3 | 26-Sep-25 A | 06-Oct-25 A | 46100 | 46100
A15040 | Material Requisition for Fire & Gas Detectors_RCC | 16 | 07-Jul-25 A | 30-Jul-25 A | 46100 | 46100
A15030 | Material Requisition for Fire & Gas Detectors_IFR | 2 | 27-May-25 A | 05-Jul-25 A | 46100 | 46100
Material Requisition for Instrument Cables |  | 81 | 27-May-25 A | 08-Aug-25 A | 46100 | 46100
A47680 | Material Requisition for Instrument Cables_IFD/IFC | 2 | 04-Aug-25 A | 08-Aug-25 A | 46100 | 46100
A47660 | Material Requisition for Instrument Cables_IFA | 3 | 02-Jun-25 A | 06-Jun-25 A | 46100 | 46100
A47670 | Material Requisition for Instrument Cables_RCA | 16 | 21-Jul-25 A | 01-Aug-25 A | 46100 | 46100
A47650 | Material Requisition for Instrument Cables_RCC | 16 | 07-Jul-25 A | 18-Jul-25 A | 46100 | 46100
A15230 | Material Requisition for Instrument Cables_IFR | 2 | 27-May-25 A | 05-Jul-25 A | 46100 | 46100
Material Requisition for Junction Boxes |  | 127 | 27-May-25 A | 19-Dec-25 A | 46086 | 46100
A47720 | Material Requisition for Junction Boxes_RCA | 16 | 03-Nov-25 A | 13-Nov-25 A | 46086 | 46086
A47710 | Material Requisition for Junction Boxes_IFA | 3 | 21-Oct-25 A | 03-Nov-25 A | 46100 | 46100
A47730 | Material Requisition for Junction Boxes_IFD/IFC | 2 | 30-Nov-25 A | 19-Dec-25 A | 46100 | 46100
A47700 | Material Requisition for Junction Boxes_RCC | 16 | 22-Sep-25 A | 09-Oct-25 A | 46100 | 46100
A47690 | Material Requisition for Junction Boxes_IFR | 2 | 27-May-25 A | 05-Jul-25 A | 46100 | 46100
Material Requisition for ICSS System |  | 157 | 31-Dec-24 A | 14-Aug-25 A | 46083 | 46083
A15370 | Material Requisition for ICSS System_IFD/IFC | 2 | 04-Aug-25 A | 14-Aug-25 A | 46083 | 46083
A47770 | Material Requisition for ICSS System_RCA | 16 | 22-Jun-25 A | 28-Jun-25 A | 46083 | 46083
A47760 | Material Requisition for ICSS System_IFA | 3 | 02-Jun-25 A | 21-Jun-25 A | 46083 | 46083
A47750 | Material Requisition for ICSS System_RCC | 16 | 01-May-25 A | 30-May-25 A | 46083 | 46083
A47740 | Material Requisition for ICSS System_IFR | 2 | 31-Dec-24 A | 23-Jan-25 A | 46083 | 46083
Material Requisition for MCMS System |  | 36 | 20-Apr-25 A | 07-May-25 A | 46083 | 46083
A58230 | Material Requisition for MCMS System_IFD/IFC | 2 | 05-May-25 A | 07-May-25 A | 46083 | 46083
A58220 | Material Requisition for MCMS System_RCA | 16 | 02-May-25 A | 05-May-25 A | 46083 | 46083
A58210 | Material Requisition for MCMS System_IFA | 3 | 28-Apr-25 A | 01-May-25 A | 46083 | 46083
A58200 | Material Requisition for MCMS System_RCC | 16 | 25-Apr-25 A | 27-Apr-25 A | 46083 | 46083
A58190 | Material Requisition for MCMS System_IFR | 2 | 20-Apr-25 A | 24-Apr-25 A | 46083 | 46083
Technical Bid Evaluation for ESD Valves |  | 103 | 01-Oct-25 A | 2026-03-17 | 2026-12-28 | 2027-01-20 | 221
A16720 | Technical Bid Evaluation for ESD Valves_IFD/IFC | 2 | 2026-03-13 | 2026-03-17 | 2026-12-28 | 2026-12-28 | 221
A16710 | Technical Bid Evaluation for ESD Valves_RCA | 16 | 2026-02-20 | 2026-03-13 | 2026-12-28 | 2026-12-28 | 221
A16700 | Technical Bid Evaluation for ESD Valves_IFA | 3 | 28-Nov-25 A | 11-Dec-25 A | 46384 | 46384
A48240 | Technical Bid Evaluation for ESD Valves_RCC | 16 | 03-Oct-25 A | 14-Oct-25 A | 46384 | 46405
A16680 | Technical Bid Evaluation for ESD Valves_IFR | 6 | 01-Oct-25 A | 07-Oct-25 A | 46405 | 46407
Technical Bid Evaluation for Rotameter |  | 86 | 30-Nov-25 A | 2026-03-23 | 2026-12-22 | 2027-01-20 | 218
A16770 | Technical Bid Evaluation for Rotameter_IFD/IFC | 2 | 2026-03-19 | 2026-03-23 | 2026-12-22 | 2026-12-22 | 218
A16760 | Technical Bid Evaluation for Rotameter_RCA | 16 | 2026-02-25 | 2026-03-19 | 2026-12-22 | 2026-12-22 | 218
A48250 | Technical Bid Evaluation for Rotameter_IFA | 3 | 2026-02-20 | 2026-02-25 | 2026-12-22 | 2026-12-25 | 218
A16740 | Technical Bid Evaluation for Rotameter_RCC | 16 | 19-Dec-25 A | 09-Jan-26 A | 46384 | 46405
A16730 | Technical Bid Evaluation for Rotameter_IFR | 6 | 30-Nov-25 A | 08-Dec-25 A | 46405 | 46407
Technical Bid Evaluation for Level Transmitters (GWR type) |  | 103 | 23-Aug-25 A | 13-Jan-26 A | 46407 | 46407
A16620 | Technical Bid Evaluation for Level Transmitters (GWR type)_IFD/IFC | 2 | 09-Jan-26 A | 13-Jan-26 A | 46407 | 46407
A16610 | Technical Bid Evaluation for Level Transmitters (GWR type)_RCA | 16 | 19-Dec-25 A | 09-Jan-26 A | 46407 | 46407
A16600 | Technical Bid Evaluation for Level Transmitters (GWR type)_IFA | 3 | 28-Nov-25 A | 18-Dec-25 A | 46407 | 46407
A16590 | Technical Bid Evaluation for Level Transmitters (GWR type)_RCC | 16 | 05-Sep-25 A | 29-Sep-25 A | 46407 | 46407
A16580 | Technical Bid Evaluation for Level Transmitters (GWR type)_IFR | 6 | 23-Aug-25 A | 18-Sep-25 A | 46407 | 46407
Technical Bid Evaluation for Temperature Element / Thermowell |  | 66 | 19-Dec-25 A | 2026-03-23 | 2026-12-22 | 2027-01-20 | 218
A16320 | Technical Bid Evaluation for Temperature Element / Thermowell_IFD/IFC | 2 | 2026-03-19 | 2026-03-23 | 2026-12-22 | 2026-12-22 | 218
A16310 | Technical Bid Evaluation for Temperature Element / Thermowell_RCA | 16 | 2026-02-25 | 2026-03-19 | 2026-12-22 | 2026-12-22 | 218
A16300 | Technical Bid Evaluation for Temperature Element / Thermowell_IFA | 3 | 2026-02-20 | 2026-02-25 | 2026-12-22 | 2026-12-25 | 218
A16290 | Technical Bid Evaluation for Temperature Element / Thermowell_RCC | 16 | 26-Dec-25 A | 19-Jan-26 A | 46384 | 46405
A16280 | Technical Bid Evaluation for Temperature Element / Thermowell_IFR | 6 | 19-Dec-25 A | 26-Dec-25 A | 46405 | 46407
SIL/LOPA CLoseout Report |  | 43 | 2026-02-20 | 2026-04-21 | 2026-11-12 | 2027-01-20 | 196
A13520 | SIL/LOPA Closeout Report_IFD/IFC | 2 | 2026-04-17 | 2026-04-21 | 2026-11-12 | 2026-11-20 | 196
A13510 | SIL/LOPA Closeout Report_RCA | 16 | 2026-03-26 | 2026-04-17 | 2026-11-30 | 2026-12-22 | 196
A13500 | SIL/LOPA Closeout Report_IFA | 3 | 2026-03-23 | 2026-03-26 | 2026-12-22 | 2026-12-25 | 196
A13490 | SIL/LOPA Closeout Report_RCC | 16 | 2026-02-27 | 2026-03-23 | 2026-12-28 | 2027-01-18 | 196
A13480 | SIL/LOPA Closeout Report_IFR | 6 | 2026-02-20 | 2026-02-27 | 2027-01-18 | 2027-01-20 | 190
Overall Control System Architecture Drawing |  | 130 | 09-Jun-25 A | 23-Dec-25 A | 46349 | 46407
A15470 | Overall Control System Architecture Drawing_IFD/IFC | 2 | 19-Dec-25 A | 23-Dec-25 A | 46349 | 46349
A15460 | Overall Control System Architecture Drawing_RCA | 16 | 10-Sep-25 A | 16-Sep-25 A | 46407 | 46407
A15450 | Overall Control System Architecture Drawing_IFA | 3 | 31-Jul-25 A | 09-Sep-25 A | 46407 | 46407
A15440 | Overall Control System Architecture Drawing_RCC | 16 | 06-Jul-25 A | 30-Jul-25 A | 46407 | 46407
A15430 | Overall Control System Architecture Drawing_IFR | 6 | 09-Jun-25 A | 05-Jul-25 A | 46407 | 46407
Instrument Index |  | 172 | 10-Jun-25 A | 2026-03-17 | 2026-11-23 | 2027-01-20 | 221
A15520 | Instrument Index_IFD/IFC | 2 | 2026-03-13 | 2026-03-17 | 2026-11-23 | 2026-11-23 | 221
A15510 | Instrument Index_RCA | 16 | 2026-02-20 | 2026-03-13 | 2026-12-28 | 2026-12-28 | 221
A15500 | Instrument Index_IFA | 3 | 22-Aug-25 A | 30-Aug-25 A | 46384 | 46384
A15490 | Instrument Index_RCC | 16 | 01-Aug-25 A | 25-Aug-25 A | 46384 | 46405
A15480 | Instrument Index_IFR | 6 | 10-Jun-25 A | 05-Jul-25 A | 46405 | 46407
Instrument & F&G I/O list |  | 119 | 26-May-25 A | 23-Dec-25 A | 46349 | 46407
A47840 | Instrument & F&G I/O list_IFD/IFC | 2 | 19-Dec-25 A | 23-Dec-25 A | 46349 | 46349
A47830 | Instrument & F&G I/O list_RCA | 16 | 21-Aug-25 A | 01-Sep-25 A | 46407 | 46407
A47820 | Instrument & F&G I/O list_IFA | 3 | 11-Aug-25 A | 20-Aug-25 A | 46407 | 46407
A15540 | Instrument & F&G I/O list_RCC | 16 | 06-Jul-25 A | 10-Aug-25 A | 46407 | 46407
A15530 | Instrument & F&G I/O list_IFR | 6 | 26-May-25 A | 05-Jul-25 A | 46407 | 46407
Cable Block Diagram |  | 183 | 08-May-25 A | 2026-02-24 | 2026-11-23 | 2027-01-20 | 237
A15620 | Cable Block Diagram_IFD/IFC | 2 | 2026-02-20 | 2026-02-24 | 2026-11-23 | 2026-11-23 | 237
A15600 | Cable Block Diagram_IFA | 3 | 14-Aug-25 A | 20-Aug-25 A | 46405 | 46405
A15590 | Cable Block Diagram_RCC | 16 | 07-Aug-25 A | 13-Sep-25 A | 46405 | 46405
A47850 | Cable Block Diagram_RCA | 16 | 21-Aug-25 A | 01-Sep-25 A | 46405 | 46405
A15580 | Cable Block Diagram_IFR | 17 | 08-May-25 A | 06-Aug-25 A | 46405 | 46407
Process & Pneumatic Hookup Drawings |  | 43 | 2026-02-20 | 2026-04-21 | 2026-11-23 | 2027-01-20 | 196
A47890 | Process & Pneumatic Hookup Drawings_IFD/IFC | 2 | 2026-04-17 | 2026-04-21 | 2026-11-23 | 2026-11-30 | 196
A47880 | Process & Pneumatic Hookup Drawings_RCA | 16 | 2026-03-26 | 2026-04-17 | 2026-11-30 | 2026-12-22 | 196
A47870 | Process & Pneumatic Hookup Drawings_IFA | 3 | 2026-03-23 | 2026-03-26 | 2026-12-22 | 2026-12-25 | 196
A47860 | Process & Pneumatic Hookup Drawings_RCC | 16 | 2026-02-27 | 2026-03-23 | 2026-12-28 | 2027-01-18 | 196
A15630 | Process & Pneumatic Hookup Drawings_IFR | 6 | 2026-02-20 | 2026-02-27 | 2027-01-18 | 2027-01-20 | 196
Junction Box Schedule |  | 174 | 26-May-25 A | 2026-04-14 | 2026-11-26 | 2027-01-20 | 202
A47930 | Junction Box Schedule_IFD/IFC | 2 | 2026-04-09 | 2026-04-14 | 2026-11-26 | 2026-11-26 | 202
A47920 | Junction Box Schedule_RCA | 16 | 2026-03-19 | 2026-04-09 | 2026-11-30 | 2026-12-22 | 202
A47910 | Junction Box Schedule_IFA | 3 | 2026-03-13 | 2026-03-19 | 2026-12-22 | 2026-12-25 | 202
A47900 | Junction Box Schedule_RCC | 16 | 2026-02-20 | 2026-03-13 | 2026-12-28 | 2027-01-18 | 202
A15680 | Junction Box Schedule_IFR | 6 | 26-May-25 A | 07-Jul-25 A | 46405 | 46407
Instrument Cable Schedule |  | 169 | 27-Jun-25 A | 2026-04-14 | 2026-11-26 | 2027-01-18 | 200
A47980 | Instrument Cable Schedule_IFD/IFC | 2 | 2026-04-09 | 2026-04-14 | 2026-11-26 | 2026-11-26 | 200
A47970 | Instrument Cable Schedule_RCA | 16 | 2026-03-19 | 2026-04-09 | 2026-11-26 | 2026-12-18 | 200
A47960 | Instrument Cable Schedule_IFA | 3 | 2026-03-13 | 2026-03-19 | 2026-12-18 | 2026-12-23 | 200
A47950 | Instrument Cable Schedule_RCC | 16 | 2026-02-20 | 2026-03-13 | 2026-12-23 | 2027-01-14 | 200
A47940 | Instrument Cable Schedule_IFR | 6 | 27-Jun-25 A | 05-Jul-25 A | 46401 | 46405
SIS Building Equipment Layout |  | 223 | 08-Apr-25 A | 27-Jun-25 A | 46095 | 46095
A48080 | SIS Building Equipment Layout_IFD/IFC | 2 | 23-Jun-25 A | 27-Jun-25 A | 46095 | 46095
A48070 | SIS Building Equipment Layout_RCA | 16 | 09-Jun-25 A | 20-Jun-25 A | 46095 | 46095
A48060 | SIS Building Equipment Layout_IFA | 3 | 02-Jun-25 A | 06-Jun-25 A | 46095 | 46095
A48050 | SIS Building Equipment Layout_RCC | 16 | 30-Apr-25 A | 30-May-25 A | 46095 | 46095
A48040 | SIS Building Equipment Layout_IFR | 6 | 08-Apr-25 A | 29-Apr-25 A | 46095 | 46095
Instrument & JB Wiring Diagram |  | 55 | 20-Dec-25 A | 2026-03-23 | 2026-12-18 | 2027-01-18 | 215
A48030 | Instrument & JB wiring Diagram_IFD/IFC | 2 | 2026-03-19 | 2026-03-23 | 2026-12-18 | 2026-12-18 | 215
A48020 | Instrument & JB wiring Diagram_RCA | 16 | 2026-02-25 | 2026-03-19 | 2026-12-18 | 2026-12-18 | 215
A48010 | Instrument & JB wiring Diagram_IFA | 3 | 2026-02-20 | 2026-02-25 | 2026-12-18 | 2026-12-23 | 215
A48000 | Instrument & JB wiring Diagram_RCC | 16 | 12-Jan-26 A | 17-Jan-26 A | 46379 | 46401
A47990 | Instrument & JB wiring Diagram_IFR | 6 | 20-Dec-25 A | 12-Jan-26 A | 46401 | 46405
Instrument Loop Diagram |  | 43 | 2026-03-09 | 2026-05-06 | 2026-11-04 | 2027-01-01 | 172
A16120 | Instrument Loop Diagram_IFD/IFC | 2 | 2026-05-04 | 2026-05-06 | 2026-11-04 | 2026-11-11 | 172
A16110 | Instrument Loop Diagram_RCA | 16 | 2026-04-13 | 2026-05-04 | 2026-11-11 | 2026-12-03 | 172
A16100 | Instrument Loop Diagram_IFA | 3 | 2026-04-07 | 2026-04-10 | 2026-12-03 | 2026-12-08 | 172
A48140 | Instrument Loop Diagram_RCC | 16 | 2026-03-16 | 2026-04-07 | 2026-12-09 | 2026-12-30 | 172
A16080 | Instrument Loop Diagram_IFR | 6 | 2026-03-09 | 2026-03-16 | 2026-12-30 | 2027-01-01 | 172
Instrument Location Layout |  | 43 | 2026-04-03 | 2026-06-03 | 2026-11-19 | 2027-01-18 | 164
A15920 | Instrument Location Layout_IFD/IFC | 2 | 2026-05-29 | 2026-06-03 | 2026-11-19 | 2026-11-26 | 164
A48110 | Instrument Location Layout_RCA | 16 | 2026-05-08 | 2026-05-29 | 2026-11-26 | 2026-12-18 | 164
A15900 | Instrument Location Layout_IFA | 3 | 2026-05-04 | 2026-05-08 | 2026-12-18 | 2026-12-23 | 164
A48100 | Instrument Location Layout_RCC | 16 | 2026-04-13 | 2026-05-04 | 2026-12-23 | 2027-01-14 | 164
A48090 | Instrument Location Layout_IFR | 6 | 2026-04-03 | 2026-04-10 | 2027-01-14 | 2027-01-18 | 164
Instrument Cable & trench routing layout |  | 36 | 20-Dec-25 A | 2026-03-23 | 2026-12-18 | 2027-01-18 | 215
A48120 | Instrument Cable & trench routing layout_IFD/IFC | 2 | 2026-03-19 | 2026-03-23 | 2026-12-18 | 2026-12-18 | 215
A15960 | Instrument Cable & trench routing layout_RCA | 16 | 2026-02-25 | 2026-03-19 | 2026-12-18 | 2026-12-18 | 215
A15940 | Instrument Cable & trench routing layout_RCC | 16 | 01-Jan-26 A | 17-Jan-26 A | 46374 | 46379
A15950 | Instrument Cable & trench routing layout_IFA | 3 | 2026-02-20 | 2026-02-25 | 2026-12-23 | 2027-01-14 | 215
A15930 | Instrument Cable & trench routing layout_IFR | 6 | 20-Dec-25 A | 01-Jan-26 A | 46401 | 46405
MCT Installation Drawing |  | 86 | 10-Nov-25 A | 2026-03-23 | 2026-12-22 | 2027-01-20 | 218
A16020 | MCT Installation Drawing_IFD/IFC | 2 | 2026-03-19 | 2026-03-23 | 2026-12-22 | 2026-12-22 | 218
A16010 | MCT Installation Drawing_RCA | 16 | 2026-02-25 | 2026-03-19 | 2026-12-22 | 2026-12-22 | 218
A16000 | MCT Installation Drawing_IFA | 3 | 2026-02-20 | 2026-02-25 | 2026-12-22 | 2026-12-25 | 218
A15990 | MCT Installation Drawing_RCC | 16 | 19-Dec-25 A | 09-Jan-26 A | 46384 | 46405
A15980 | MCT Installation Drawing_IFR | 6 | 10-Nov-25 A | 21-Nov-25 A | 46405 | 46407
Instrumentation & Control Material Take Off |  | 47 | 19-Dec-25 A | 2026-02-24 | 2026-04-07 | 2027-01-20 | 237
A16070 | Instrumentation & Control Material Take Off_IFD/IFC | 2 | 2026-02-20 | 2026-02-24 | 2026-04-07 | 2026-04-07 | 237
A16040 | Instrumentation & Control Material Take Off_RCC | 16 | 26-Dec-25 A | 19-Jan-26 A | 46405 | 46405
A48130 | Instrumentation & Control Material Take Off_IFR | 6 | 19-Dec-25 A | 26-Dec-25 A | 46405 | 46407
SPI |  | 242 | 25-Mar-25 A | 2026-04-14 | 2026-11-30 | 2027-01-20 | 202
SPI Execution Philoshpy |  | 242 | 25-Mar-25 A | 2026-04-14 | 2026-11-30 | 2027-01-20 | 202
A28050 | SPI Execution Philoshpy_IFD/IFC | 2 | 2026-04-09 | 2026-04-14 | 2026-11-30 | 2026-11-30 | 202
A55590 | SPI Execution Philoshpy_RCA | 16 | 2026-03-19 | 2026-04-09 | 2026-11-30 | 2026-12-22 | 202
A55580 | SPI Execution Philoshpy_IFA | 3 | 2026-03-13 | 2026-03-19 | 2026-12-22 | 2026-12-25 | 202
A55570 | SPI Execution Philoshpy_RCC | 16 | 2026-02-20 | 2026-03-13 | 2026-12-28 | 2027-01-18 | 202
A55560 | SPI Execution Philoshpy_IFR | 6 | 25-Mar-25 A | 28-Apr-25 A | 46405 | 46407
SPI Extraction Procedure |  | 212 | 01-Jul-25 A | 2026-04-14 | 2026-11-30 | 2027-01-20 | 202
A55630 | SPI Extraction Procedure_IFD/IFC | 2 | 2026-04-09 | 2026-04-14 | 2026-11-30 | 2026-11-30 | 202
A55620 | SPI Extraction Procedure_RCA | 16 | 2026-03-19 | 2026-04-09 | 2026-11-30 | 2026-12-22 | 202
A55610 | SPI Extraction Procedure_IFA | 3 | 2026-03-13 | 2026-03-19 | 2026-12-22 | 2026-12-25 | 202
A55600 | SPI Extraction Procedure_RCC | 16 | 2026-02-20 | 2026-03-13 | 2026-12-28 | 2027-01-18 | 202
A28060 | SPI Extraction Procedure_IFR | 6 | 01-Jul-25 A | 12-Jul-25 A | 46405 | 46407
Civil/Structural/Architectural |  | 485 | 16-Jan-25 A | 2026-05-14 | 2026-02-21 | 2027-01-20 | 179
Structure & Foundation design - Piperack & other pipe supports |  | 194 | 21-Apr-25 A | 2026-05-14 | 2026-03-02 | 2027-01-20 | 179
Structural GA, Section and Details - Pipe Rack SR8001 |  | 65 | 02-Jun-25 A | 08-Aug-25 A | 46083 | 46083
A48540 | Structural GA, Section and Details - Pipe Rack SR8001_IFD/IFC | 6 | 04-Aug-25 A | 08-Aug-25 A | 46083 | 46083
A48530 | Structural GA, Section and Details - Pipe Rack SR8001_RCA | 16 | 21-Jul-25 A | 01-Aug-25 A | 46083 | 46083
A18000 | Structural GA, Section and Details - Pipe Rack SR8001_IFA | 11 | 07-Jul-25 A | 18-Jul-25 A | 46083 | 46083
A48520 | Structural GA, Section and Details - Pipe Rack SR8001_RCC | 16 | 23-Jun-25 A | 04-Jul-25 A | 46083 | 46083
A48510 | Structural GA, Section and Details - Pipe Rack SR8001_IFR | 17 | 02-Jun-25 A | 20-Jun-25 A | 46083 | 46083
Design Calculation Report for Structural Steel - Pipe Rack SR8001 |  | 65 | 02-Jun-25 A | 01-Aug-25 A | 46083 | 46407
A18070 | Design Calculation Report for Structural Steel - Pipe Rack SR8001_IFD/IFC | 6 | 28-Jul-25 A | 01-Aug-25 A | 46083 | 46083
A18060 | Design Calculation Report for Structural Steel - Pipe Rack SR8001_RCA | 16 | 14-Jul-25 A | 25-Jul-25 A | 46407 | 46407
A18050 | Design Calculation Report for Structural Steel - Pipe Rack SR8001_IFA | 11 | 30-Jun-25 A | 11-Jul-25 A | 46407 | 46407
A48560 | Design Calculation Report for Structural Steel - Pipe Rack SR8001_RCC | 16 | 16-Jun-25 A | 27-Jun-25 A | 46407 | 46407
A48550 | Design Calculation Report for Structural Steel - Pipe Rack SR8001_IFR | 17 | 02-Jun-25 A | 13-Jun-25 A | 46407 | 46407
Foundation layout, Section and Details - Pipe Rack SR8001 |  | 91 | 25-Jun-25 A | 23-Dec-25 A | 46083 | 46083
A18120 | Foundation layout, Section and Details - Pipe Rack SR8001_IFD/IFC | 2 | 19-Dec-25 A | 23-Dec-25 A | 46083 | 46083
A18110 | Foundation layout, Section and Details - Pipe Rack SR8001_RCA | 16 | 13-Nov-25 A | 21-Nov-25 A | 46083 | 46083
A48590 | Foundation layout, Section and Details - Pipe Rack SR8001_IFA | 3 | 31-Oct-25 A | 11-Nov-25 A | 46083 | 46083
A48580 | Foundation layout, Section and Details - Pipe Rack SR8001_RCC | 16 | 14-Jul-25 A | 22-Aug-25 A | 46083 | 46083
A48570 | Foundation layout, Section and Details - Pipe Rack SR8001_IFR | 6 | 25-Jun-25 A | 12-Jul-25 A | 46083 | 46083
Design Calculation Report for Foundations - Pipe Rack SR8001 |  | 91 | 01-Jul-25 A | 23-Dec-25 A | 46407 | 46407
A18170 | Design Calculation Report for Foundations - Pipe Rack SR8001_IFD/IFC | 2 | 19-Dec-25 A | 23-Dec-25 A | 46407 | 46407
A48620 | Design Calculation Report for Foundations - Pipe Rack SR8001_RCA | 16 | 12-Nov-25 A | 21-Nov-25 A | 46407 | 46407
A48610 | Design Calculation Report for Foundations - Pipe Rack SR8001_IFA | 3 | 31-Oct-25 A | 11-Nov-25 A | 46407 | 46407
A48600 | Design Calculation Report for Foundations - Pipe Rack SR8001_RCC | 16 | 14-Jul-25 A | 22-Aug-25 A | 46407 | 46407
A18130 | Design Calculation Report for Foundations - Pipe Rack SR8001_IFR | 6 | 01-Jul-25 A | 12-Jul-25 A | 46407 | 46407
Structural GA, Section and Details - Pipe Rack 13-I-08001 |  | 68 | 01-Aug-25 A | 24-Dec-25 A | 46083 | 46201
A48650 | Structural GA, Section and Details - Pipe Rack 13-I-08001_IFD/IFC | 3 | 19-Dec-25 A | 24-Dec-25 A | 46083 | 46083
A48640 | Structural GA, Section and Details - Pipe Rack 13-I-08001_RCA | 16 | 01-Sep-25 A | 22-Oct-25 A | 46083 | 46083
A48630 | Structural GA, Section and Details - Pipe Rack 13-I-08001_IFA | 6 | 25-Aug-25 A | 29-Aug-25 A | 46083 | 46083
A18190 | Structural GA, Section and Details - Pipe Rack 13-I-08001_RCC | 16 | 04-Aug-25 A | 22-Aug-25 A | 46201 | 46201
A18180 | Structural GA, Section and Details - Pipe Rack 13-I-08001_IFR | 11 | 01-Aug-25 A | 15-Aug-25 A | 46201 | 46201
Design Calculation Report for Structural Steel - Pipe Rack 13-I-08001 |  | 52 | 07-Jul-25 A | 12-Sep-25 A | 46083 | 46083
A48670 | Design Calculation Report for Structural Steel - Pipe Rack 13-I-08001_IFD/IFC | 3 | 08-Sep-25 A | 12-Sep-25 A | 46083 | 46083
A48660 | Design Calculation Report for Structural Steel - Pipe Rack 13-I-08001_RCA | 16 | 20-Aug-25 A | 05-Sep-25 A | 46083 | 46083
A18250 | Design Calculation Report for Structural Steel - Pipe Rack 13-I-08001_IFA | 6 | 11-Aug-25 A | 19-Aug-25 A | 46083 | 46083
A18240 | Design Calculation Report for Structural Steel - Pipe Rack 13-I-08001_RCC | 16 | 21-Jul-25 A | 08-Aug-25 A | 46083 | 46083
A18230 | Design Calculation Report for Structural Steel - Pipe Rack 13-I-08001_IFR | 11 | 07-Jul-25 A | 18-Jul-25 A | 46083 | 46083
Foundation layout, Section and Details - Pipe Rack 13-I-08001 |  | 80 | 30-Jun-25 A | 23-Dec-25 A | 46083 | 46083
A48690 | Foundation layout, Section and Details - Pipe Rack 13-I-08001_IFD/IFC | 2 | 19-Dec-25 A | 23-Dec-25 A | 46083 | 46083
A18310 | Foundation layout, Section and Details - Pipe Rack 13-I-08001_RCA | 16 | 11-Aug-25 A | 05-Sep-25 A | 46083 | 46083
A18300 | Foundation layout, Section and Details - Pipe Rack 13-I-08001_IFA | 3 | 25-Aug-25 A | 29-Aug-25 A | 46083 | 46083
A18290 | Foundation layout, Section and Details - Pipe Rack 13-I-08001_RCC | 16 | 16-Jul-25 A | 22-Aug-25 A | 46083 | 46083
A48680 | Foundation layout, Section and Details - Pipe Rack 13-I-08001_IFR | 6 | 30-Jun-25 A | 15-Jul-25 A | 46083 | 46083
Design Calculation Report for Foundations - Pipe Rack 13-I-08001 |  | 80 | 02-Jul-25 A | 23-Dec-25 A | 46083 | 46083
A48730 | Design Calculation Report for Foundations - Pipe Rack 13-I-08001_IFD/IFC | 2 | 19-Dec-25 A | 23-Dec-25 A | 46083 | 46083
A48720 | Design Calculation Report for Foundations - Pipe Rack 13-I-08001_RCA | 16 | 18-Aug-25 A | 05-Sep-25 A | 46083 | 46083
A18350 | Design Calculation Report for Foundations - Pipe Rack 13-I-08001_IFA | 3 | 25-Aug-25 A | 29-Aug-25 A | 46083 | 46083
A48710 | Design Calculation Report for Foundations - Pipe Rack 13-I-08001_RCC | 16 | 14-Jul-25 A | 22-Aug-25 A | 46083 | 46083
A48700 | Design Calculation Report for Foundations - Pipe Rack 13-I-08001_IFR | 6 | 02-Jul-25 A | 12-Jul-25 A | 46083 | 46083
Structral steel GA and details Field Supports SF8200 |  | 115 | 03-Jul-25 A | 2026-03-23 | 2026-05-28 | 2026-06-26 | 70
A21020 | Structral steel GA and details Field Supports SF8200_IFD/IFC | 2 | 2026-03-19 | 2026-03-23 | 2026-05-28 | 2026-05-28 | 70
A21010 | Structral steel GA and details Field Supports SF8200_RCA | 16 | 2026-02-25 | 2026-03-19 | 2026-05-28 | 2026-05-28 | 70
A21000 | Structral steel GA and details Field Supports SF8200_IFA | 3 | 2026-02-20 | 2026-02-25 | 2026-05-28 | 2026-06-02 | 70
A20990 | Structral steel GA and details Field Supports SF8200_RCC | 16 | 19-Dec-25 A | 09-Jan-26 A | 46176 | 46197
A20980 | Structral steel GA and details Field Supports SF8200_IFR | 6 | 03-Jul-25 A | 20-Jul-25 A | 46197 | 46199
Design Calculation Report for structural steel Field Supports SF8200 |  | 131 | 19-Aug-25 A | 2026-03-23 | 2026-04-16 | 2026-06-18 | 63
A21070 | Design Calculation Report for structural steel Field Supports SF8200_IFD/IFC | 2 | 2026-03-19 | 2026-03-23 | 2026-04-16 | 2026-04-16 | 63
A49990 | Design Calculation Report for structural steel Field Supports SF8200_RCA | 16 | 2026-02-25 | 2026-03-19 | 2026-05-14 | 2026-05-14 | 63
A49980 | Design Calculation Report for structural steel Field Supports SF8200_IFA | 3 | 2026-02-20 | 2026-02-25 | 2026-05-14 | 2026-05-19 | 60
A49970 | Design Calculation Report for structural steel Field Supports SF8200_RCC | 16 | 19-Dec-25 A | 09-Jan-26 A | 46167 | 46188
A49960 | Design Calculation Report for structural steel Field Supports SF8200_IFR | 6 | 19-Aug-25 A | 25-Aug-25 A | 46189 | 46191
Foundation Layout, Section and details Field Supports SF8200 |  | 70 | 19-Dec-25 A | 2026-03-26 | 2026-12-22 | 2027-01-20 | 214
A50010 | Foundation Layout, Section and details Field Supports SF8200_IFD/IFC | 2 | 2026-03-24 | 2026-03-26 | 2026-12-22 | 2026-12-22 | 214
A50000 | Foundation Layout, Section and details Field Supports SF8200_RCA | 16 | 2026-03-02 | 2026-03-24 | 2026-12-22 | 2026-12-22 | 214
A21100 | Foundation Layout, Section and details Field Supports SF8200_IFA | 3 | 2026-02-25 | 2026-03-02 | 2026-12-22 | 2026-12-25 | 214
A21090 | Foundation Layout, Section and details Field Supports SF8200_RCC | 16 | 26-Dec-25 A | 19-Jan-26 A | 46384 | 46405
A21080 | Foundation Layout, Section and details Field Supports SF8200_IFR | 6 | 19-Dec-25 A | 26-Dec-25 A | 46405 | 46407
Design Calculation Report for Foundations Field Supports SF8200 |  | 70 | 19-Dec-25 A | 2026-03-26 | 2026-12-22 | 2027-01-20 | 214
A21170 | Design Calculation Report for Foundations Field Supports SF8200_IFD/IFC | 2 | 2026-03-24 | 2026-03-26 | 2026-12-22 | 2026-12-22 | 214
A21160 | Design Calculation Report for Foundations Field Supports SF8200_RCA | 16 | 2026-03-02 | 2026-03-24 | 2026-12-22 | 2026-12-22 | 214
A21150 | Design Calculation Report for Foundations Field Supports SF8200_IFA | 3 | 2026-02-25 | 2026-03-02 | 2026-12-22 | 2026-12-25 | 214
A50030 | Design Calculation Report for Foundations Field Supports SF8200_RCC | 16 | 26-Dec-25 A | 19-Jan-26 A | 46384 | 46405
A50020 | Design Calculation Report for Foundations Field Supports SF8200_IFR | 6 | 19-Dec-25 A | 26-Dec-25 A | 46405 | 46407
Structural GA and Details, Field supports in CA37 |  | 43 | 2026-02-20 | 2026-04-21 | 2026-04-16 | 2026-06-22 | 44
A50460 | Structural GA and Details, Field supports in CA37_IFD/IFC | 2 | 2026-04-17 | 2026-04-21 | 2026-04-16 | 2026-04-23 | 44
A50450 | Structural GA and Details, Field supports in CA37_RCA | 16 | 2026-03-26 | 2026-04-17 | 2026-04-28 | 2026-05-19 | 44
A21900 | Structural GA and Details, Field supports in CA37_IFA | 3 | 2026-03-23 | 2026-03-26 | 2026-05-19 | 2026-05-25 | 42
A50440 | Structural GA and Details, Field supports in CA37_RCC | 16 | 2026-02-27 | 2026-03-23 | 2026-05-27 | 2026-06-18 | 42
A50430 | Structural GA and Details, Field supports in CA37_IFR | 6 | 2026-02-20 | 2026-02-27 | 2026-06-18 | 2026-06-22 | 39
Design Calculation report of structural steel Field supports CA37 |  | 43 | 2026-02-20 | 2026-04-21 | 2026-04-16 | 2026-06-22 | 44
A22020 | Design Calculation report of structural steel Field supports CA37_IFD/IFC | 2 | 2026-04-17 | 2026-04-21 | 2026-04-16 | 2026-04-23 | 44
A50520 | Design Calculation report of structural steel Field supports CA37_RCA | 16 | 2026-03-26 | 2026-04-17 | 2026-04-28 | 2026-05-19 | 44
A50510 | Design Calculation report of structural steel Field supports CA37_IFA | 3 | 2026-03-23 | 2026-03-26 | 2026-05-19 | 2026-05-25 | 42
A21990 | Design Calculation report of structural steel Field supports CA37_RCC | 16 | 2026-02-27 | 2026-03-23 | 2026-05-27 | 2026-06-18 | 42
A50500 | Design Calculation report of structural steel Field supports CA37_IFR | 6 | 2026-02-20 | 2026-02-27 | 2026-06-18 | 2026-06-22 | 39
Design Calculation report of Foundations Field supports CA37 |  | 43 | 2026-02-27 | 2026-04-29 | 2026-11-23 | 2027-01-20 | 191
A50560 | Design Calculation report of Foundations Field supports CA37_IFD/IFC | 2 | 2026-04-27 | 2026-04-29 | 2026-11-23 | 2026-11-30 | 191
A22060 | Design Calculation report of Foundations Field supports CA37_RCA | 16 | 2026-04-03 | 2026-04-27 | 2026-11-30 | 2026-12-22 | 191
A50550 | Design Calculation report of Foundations Field supports CA37_IFA | 3 | 2026-03-31 | 2026-04-03 | 2026-12-22 | 2026-12-25 | 191
A50540 | Design Calculation report of Foundations Field supports CA37_RCC | 16 | 2026-03-09 | 2026-03-30 | 2026-12-28 | 2027-01-18 | 191
A50530 | Design Calculation report of Foundations Field supports CA37_IFR | 6 | 2026-02-27 | 2026-03-09 | 2027-01-18 | 2027-01-20 | 191
Foundation layout and details, Field supports in CA37 |  | 43 | 2026-02-27 | 2026-04-29 | 2026-11-23 | 2027-01-20 | 191
A50490 | Foundation layout and details, Field supports in CA37_IFD/IFC | 2 | 2026-04-27 | 2026-04-29 | 2026-11-23 | 2026-11-30 | 191
A21960 | Foundation layout and details, Field supports in CA37_RCA | 16 | 2026-04-03 | 2026-04-27 | 2026-11-30 | 2026-12-22 | 191
A21950 | Foundation layout and details, Field supports in CA37_IFA | 3 | 2026-03-31 | 2026-04-03 | 2026-12-22 | 2026-12-25 | 191
A50480 | Foundation layout and details, Field supports in CA37_RCC | 16 | 2026-03-09 | 2026-03-30 | 2026-12-28 | 2027-01-18 | 191
A50470 | Foundation layout and details, Field supports in CA37_IFR | 6 | 2026-02-27 | 2026-03-09 | 2027-01-18 | 2027-01-20 | 191
Structural GA, Section and Details - Pipe Bridge SR81 |  | 43 | 23-Jun-25 A | 14-Aug-25 A | 46083 | 46083
A48750 | Structural GA, Section and Details - Pipe Bridge SR81_IFD/IFC | 2 | 11-Aug-25 A | 14-Aug-25 A | 46083 | 46083
A18410 | Structural GA, Section and Details - Pipe Bridge SR81_RCA | 16 | 28-Jul-25 A | 08-Aug-25 A | 46083 | 46083
A18400 | Structural GA, Section and Details - Pipe Bridge SR81_IFA | 3 | 21-Jul-25 A | 25-Jul-25 A | 46083 | 46083
A18390 | Structural GA, Section and Details - Pipe Bridge SR81_RCC | 16 | 03-Jul-25 A | 18-Jul-25 A | 46083 | 46083
A48740 | Structural GA, Section and Details - Pipe Bridge SR81_IFR | 6 | 23-Jun-25 A | 02-Jul-25 A | 46083 | 46083
Design Calculation Report for Structural Steel - Pipe Bridge SR81 |  | 50 | 03-Jul-25 A | 12-Sep-25 A | 46083 | 46083
A18470 | Design Calculation Report for Structural Steel - Pipe Bridge SR81_IFD/IFC | 2 | 08-Sep-25 A | 12-Sep-25 A | 46083 | 46083
A48770 | Design Calculation Report for Structural Steel - Pipe Bridge SR81_RCA | 16 | 18-Aug-25 A | 05-Sep-25 A | 46083 | 46083
A18450 | Design Calculation Report for Structural Steel - Pipe Bridge SR81_IFA | 3 | 11-Aug-25 A | 15-Aug-25 A | 46083 | 46083
A18440 | Design Calculation Report for Structural Steel - Pipe Bridge SR81_RCC | 16 | 21-Jul-25 A | 08-Aug-25 A | 46083 | 46083
A48760 | Design Calculation Report for Structural Steel - Pipe Bridge SR81_IFR | 6 | 03-Jul-25 A | 20-Jul-25 A | 46083 | 46083
Design Calculation Report for Foundations - Pipe Bridge SR81 |  | 47 | 21-Apr-25 A | 17-Jul-25 A | 46083 | 46083
A48870 | Design Calculation Report for Foundations - Pipe Bridge SR81_IFD/IFC | 2 | 14-Jul-25 A | 17-Jul-25 A | 46083 | 46083
A48860 | Design Calculation Report for Foundations - Pipe Bridge SR81_RCA | 16 | 23-Jun-25 A | 11-Jul-25 A | 46083 | 46083
A48840 | Design Calculation Report for Foundations - Pipe Bridge SR81_RCC | 16 | 13-May-25 A | 19-May-25 A | 46083 | 46083
A48830 | Design Calculation Report for Foundations - Pipe Bridge SR81_IFR | 6 | 21-Apr-25 A | 12-May-25 A | 46083 | 46083
A48850 | Design Calculation Report for Foundations - Pipe Bridge SR81_IFA | 3 | 20-May-25 A | 20-Jun-25 A | 46083 | 46083
Foundation layout, Section and Details - Pipe Bridge SR81 |  | 47 | 21-Apr-25 A | 13-Sep-25 A | 46083 | 46083
A48820 | Foundation layout, Section and Details - Pipe Bridge SR81_IFD/IFC | 2 | 08-Sep-25 A | 13-Sep-25 A | 46083 | 46083
A48790 | Foundation layout, Section and Details - Pipe Bridge SR81_RCC | 16 | 13-May-25 A | 19-May-25 A | 46083 | 46083
A48780 | Foundation layout, Section and Details - Pipe Bridge SR81_IFR | 6 | 21-Apr-25 A | 12-May-25 A | 46083 | 46083
A48810 | Foundation layout, Section and Details - Pipe Bridge SR81_RCA | 16 | 21-Jun-25 A | 06-Sep-25 A | 46083 | 46083
A48800 | Foundation layout, Section and Details - Pipe Bridge SR81_IFA | 3 | 20-May-25 A | 20-Jun-25 A | 46083 | 46083
Structral steel GA and details Field Supports SF8300 |  | 43 | 2026-02-27 | 2026-04-29 | 2026-04-23 | 2026-06-24 | 40
A50070 | Structral steel GA and details Field Supports SF8300_IFD/IFC | 2 | 2026-04-27 | 2026-04-29 | 2026-04-23 | 2026-05-01 | 40
A50060 | Structral steel GA and details Field Supports SF8300_RCA | 16 | 2026-04-03 | 2026-04-27 | 2026-05-01 | 2026-05-25 | 40
A50050 | Structral steel GA and details Field Supports SF8300_IFA | 3 | 2026-03-31 | 2026-04-03 | 2026-05-25 | 2026-05-28 | 39
A50040 | Structral steel GA and details Field Supports SF8300_RCC | 16 | 2026-03-09 | 2026-03-30 | 2026-05-29 | 2026-06-22 | 39
A21180 | Structral steel GA and details Field Supports SF8300_IFR | 6 | 2026-02-27 | 2026-03-09 | 2026-06-22 | 2026-06-24 | 39
Design Calculation Report for structural steel Field Supports SF8300 |  | 43 | 2026-02-27 | 2026-04-29 | 2026-11-23 | 2027-01-20 | 191
A50080 | Design Calculation Report for structural steel Field Supports SF8300_IFD/IFC | 2 | 2026-04-27 | 2026-04-29 | 2026-11-23 | 2026-11-30 | 191
A21260 | Design Calculation Report for structural steel Field Supports SF8300_RCA | 16 | 2026-04-03 | 2026-04-27 | 2026-11-30 | 2026-12-22 | 191
A21250 | Design Calculation Report for structural steel Field Supports SF8300_IFA | 3 | 2026-03-31 | 2026-04-03 | 2026-12-22 | 2026-12-25 | 191
A21240 | Design Calculation Report for structural steel Field Supports SF8300_RCC | 16 | 2026-03-09 | 2026-03-30 | 2026-12-28 | 2027-01-18 | 191
A21230 | Design Calculation Report for structural steel Field Supports SF8300_IFR | 6 | 2026-02-27 | 2026-03-09 | 2027-01-18 | 2027-01-20 | 191
Design Calculation Report for Foundations Field Supports SF8300 |  | 88 | 20-Dec-25 A | 2026-05-04 | 2026-12-22 | 2027-01-20 | 187
A50140 | Design Calculation Report for Foundations Field Supports SF8300_IFD/IFC | 2 | 2026-04-30 | 2026-05-04 | 2026-12-22 | 2026-12-22 | 187
A50130 | Design Calculation Report for Foundations Field Supports SF8300_RCA | 16 | 2026-04-08 | 2026-04-30 | 2026-12-22 | 2026-12-22 | 187
A50120 | Design Calculation Report for Foundations Field Supports SF8300_IFA | 3 | 2026-04-03 | 2026-04-08 | 2026-12-22 | 2026-12-25 | 187
A21340 | Design Calculation Report for Foundations Field Supports SF8300_RCC | 16 | 01-Jan-26 A | 16-Jan-26 A | 46384 | 46405
A21330 | Design Calculation Report for Foundations Field Supports SF8300_IFR | 6 | 20-Dec-25 A | 01-Jan-26 A | 46405 | 46407
Foundation Layout, Section and details Field Supports SF8300 |  | 86 | 20-Dec-25 A | 2026-05-04 | 2026-12-22 | 2027-01-20 | 187
A21320 | Foundation Layout, Section and details Field Supports SF8300_IFD/IFC | 2 | 2026-04-30 | 2026-05-04 | 2026-12-22 | 2026-12-22 | 187
A21310 | Foundation Layout, Section and details Field Supports SF8300_RCA | 16 | 2026-04-08 | 2026-04-30 | 2026-12-22 | 2026-12-22 | 187
A50110 | Foundation Layout, Section and details Field Supports SF8300_IFA | 3 | 2026-04-03 | 2026-04-08 | 2026-12-22 | 2026-12-25 | 187
A50100 | Foundation Layout, Section and details Field Supports SF8300_RCC | 16 | 01-Jan-26 A | 15-Jan-26 A | 46384 | 46405
A50090 | Foundation Layout, Section and details Field Supports SF8300_IFR | 6 | 20-Dec-25 A | 01-Jan-26 A | 46405 | 46407
Structral steel GA and details Field Supports SF8100 |  | 86 | 20-Dec-25 A | 2026-05-04 | 2026-05-28 | 2026-06-26 | 39
A49930 | Structral steel GA and details Field Supports SF8100_IFD/IFC | 2 | 2026-04-30 | 2026-05-04 | 2026-05-28 | 2026-05-28 | 39
A49920 | Structral steel GA and details Field Supports SF8100_RCA | 16 | 2026-04-08 | 2026-04-30 | 2026-05-28 | 2026-05-28 | 39
A49910 | Structral steel GA and details Field Supports SF8100_IFA | 3 | 2026-04-03 | 2026-04-08 | 2026-05-28 | 2026-06-02 | 39
A49900 | Structral steel GA and details Field Supports SF8100_RCC | 16 | 12-Jan-26 A | 15-Jan-26 A | 46176 | 46197
A20780 | Structral steel GA and details Field Supports SF8100_IFR | 6 | 20-Dec-25 A | 12-Jan-26 A | 46197 | 46199
Design Calculation Report for structural steel Field Supports SF8100 |  | 86 | 20-Dec-25 A | 2026-05-04 | 2026-12-17 | 2027-01-18 | 185
A20870 | Design Calculation Report for structural steel Field Supports SF8100_IFD/IFC | 2 | 2026-04-30 | 2026-05-04 | 2026-12-17 | 2026-12-17 | 185
A20860 | Design Calculation Report for structural steel Field Supports SF8100_RCA | 16 | 2026-04-08 | 2026-04-30 | 2026-12-17 | 2026-12-17 | 185
A20850 | Design Calculation Report for structural steel Field Supports SF8100_IFA | 3 | 2026-04-03 | 2026-04-08 | 2026-12-17 | 2026-12-22 | 184
A20840 | Design Calculation Report for structural steel Field Supports SF8100_RCC | 16 | 12-Jan-26 A | 15-Jan-26 A | 46379 | 46401
A20830 | Design Calculation Report for structural steel Field Supports SF8100_IFR | 6 | 20-Dec-25 A | 12-Jan-26 A | 46401 | 46405
Design Calculation Report for Foundations Field Supports SF8100 |  | 83 | 20-Dec-25 A | 2026-05-08 | 2026-12-22 | 2027-01-20 | 184
A20970 | Design Calculation Report for Foundations Field Supports SF8100_IFD/IFC | 2 | 2026-05-05 | 2026-05-08 | 2026-12-22 | 2026-12-22 | 184
A49950 | Design Calculation Report for Foundations Field Supports SF8100_RCA | 16 | 2026-04-14 | 2026-05-05 | 2026-12-22 | 2026-12-22 | 184
A49940 | Design Calculation Report for Foundations Field Supports SF8100_IFA | 3 | 2026-04-08 | 2026-04-14 | 2026-12-22 | 2026-12-25 | 184
A20940 | Design Calculation Report for Foundations Field Supports SF8100_RCC | 16 | 01-Jan-26 A | 15-Jan-26 A | 46384 | 46405
A20930 | Design Calculation Report for Foundations Field Supports SF8100_IFR | 6 | 20-Dec-25 A | 01-Jan-26 A | 46405 | 46407
Foundation Layout, Section and details Field Supports SF8100 |  | 83 | 20-Dec-25 A | 2026-05-08 | 2026-12-22 | 2027-01-20 | 184
A20920 | Foundation Layout, Section and details Field Supports SF8100_IFD/IFC | 2 | 2026-05-05 | 2026-05-08 | 2026-12-22 | 2026-12-22 | 184
A20910 | Foundation Layout, Section and details Field Supports SF8100_RCA | 16 | 2026-04-14 | 2026-05-05 | 2026-12-22 | 2026-12-22 | 184
A20900 | Foundation Layout, Section and details Field Supports SF8100_IFA | 3 | 2026-04-08 | 2026-04-14 | 2026-12-22 | 2026-12-25 | 184
A20890 | Foundation Layout, Section and details Field Supports SF8100_RCC | 16 | 01-Jan-26 A | 15-Jan-26 A | 46384 | 46405
A20880 | Foundation Layout, Section and details Field Supports SF8100_IFR | 6 | 20-Dec-25 A | 01-Jan-26 A | 46405 | 46407
Adequacy check of Pipe rack SR70 |  | 43 | 2026-02-20 | 2026-04-21 | 2026-04-06 | 2026-06-18 | 42
A50630 | Adequacy check of Pipe rack SR70_IFD/IFC | 2 | 2026-04-17 | 2026-04-21 | 2026-04-06 | 2026-04-13 | 42
A50620 | Adequacy check of Pipe rack SR70_RCA | 16 | 2026-03-26 | 2026-04-17 | 2026-04-22 | 2026-05-14 | 42
A50610 | Adequacy check of Pipe rack SR70_IFA | 3 | 2026-03-23 | 2026-03-26 | 2026-05-14 | 2026-05-19 | 38
A22140 | Adequacy check of Pipe rack SR70_RCC | 16 | 2026-02-27 | 2026-03-23 | 2026-05-25 | 2026-06-15 | 38
A22130 | Adequacy check of Pipe rack SR70_IFR | 6 | 2026-02-20 | 2026-02-27 | 2026-06-16 | 2026-06-18 | 31
Structural GA and Details, Pipe Rack SR70 |  | 43 | 2026-02-27 | 2026-04-29 | 2026-04-29 | 2026-06-26 | 43
A22120 | Structural GA and Details, Pipe Rack SR70_IFD/IFC | 2 | 2026-04-27 | 2026-04-29 | 2026-04-29 | 2026-05-06 | 43
A50600 | Structural GA and Details, Pipe Rack SR70_RCA | 16 | 2026-04-03 | 2026-04-27 | 2026-05-06 | 2026-05-28 | 43
A50590 | Structural GA and Details, Pipe Rack SR70_IFA | 3 | 2026-03-31 | 2026-04-03 | 2026-05-28 | 2026-06-02 | 43
A50580 | Structural GA and Details, Pipe Rack SR70_RCC | 16 | 2026-03-09 | 2026-03-30 | 2026-06-03 | 2026-06-24 | 43
A50570 | Structural GA and Details, Pipe Rack SR70_IFR | 6 | 2026-02-27 | 2026-03-09 | 2026-06-24 | 2026-06-26 | 43
Adequacy check of Pipe rack SR73 |  | 43 | 2026-02-27 | 2026-04-29 | 2026-04-14 | 2026-06-22 | 38
A50670 | Adequacy check of Pipe rack SR73_IFD/IFC | 2 | 2026-04-27 | 2026-04-29 | 2026-04-14 | 2026-04-21 | 38
A22260 | Adequacy check of Pipe rack SR73_RCA | 16 | 2026-04-03 | 2026-04-27 | 2026-04-28 | 2026-05-19 | 38
A22250 | Adequacy check of Pipe rack SR73_IFA | 3 | 2026-03-31 | 2026-04-03 | 2026-05-19 | 2026-05-25 | 36
A22240 | Adequacy check of Pipe rack SR73_RCC | 16 | 2026-03-09 | 2026-03-30 | 2026-05-27 | 2026-06-18 | 36
A50660 | Adequacy check of Pipe rack SR73_IFR | 6 | 2026-02-27 | 2026-03-09 | 2026-06-18 | 2026-06-22 | 31
Structural GA and Details, Pipe Rack SR73 |  | 43 | 2026-03-16 | 2026-05-14 | 2026-04-29 | 2026-06-26 | 31
A50650 | Structural GA and Details, Pipe Rack SR73_IFD/IFC | 2 | 2026-05-12 | 2026-05-14 | 2026-04-29 | 2026-05-06 | 31
A50640 | Structural GA and Details, Pipe Rack SR73_RCA | 16 | 2026-04-20 | 2026-05-12 | 2026-05-06 | 2026-05-28 | 31
A22200 | Structural GA and Details, Pipe Rack SR73_IFA | 3 | 2026-04-15 | 2026-04-20 | 2026-05-28 | 2026-06-02 | 31
A22190 | Structural GA and Details, Pipe Rack SR73_RCC | 16 | 2026-03-24 | 2026-04-15 | 2026-06-03 | 2026-06-24 | 31
A22180 | Structural GA and Details, Pipe Rack SR73_IFR | 6 | 2026-03-16 | 2026-03-24 | 2026-06-24 | 2026-06-26 | 31
Adequacy check of U&O Rack SR37 |  | 43 | 2026-03-09 | 2026-05-06 | 2026-04-21 | 2026-06-24 | 35
A22370 | Adequacy check of U&O Rack SR37_IFD/IFC | 2 | 2026-05-04 | 2026-05-06 | 2026-04-21 | 2026-04-29 | 35
A22360 | Adequacy check of U&O Rack SR37_RCA | 16 | 2026-04-13 | 2026-05-04 | 2026-05-01 | 2026-05-25 | 35
A50720 | Adequacy check of U&O Rack SR37_IFA | 3 | 2026-04-07 | 2026-04-10 | 2026-05-25 | 2026-05-28 | 34
A50710 | Adequacy check of U&O Rack SR37_RCC | 16 | 2026-03-16 | 2026-04-07 | 2026-05-29 | 2026-06-22 | 34
A50700 | Adequacy check of U&O Rack SR37_IFR | 6 | 2026-03-09 | 2026-03-16 | 2026-06-22 | 2026-06-24 | 31
Structural GA and Details, U&O Rack SR37 |  | 43 | 2026-03-16 | 2026-05-14 | 2026-04-29 | 2026-06-26 | 31
A22320 | Structural GA and Details, U&O Rack SR37_IFD/IFC | 2 | 2026-05-12 | 2026-05-14 | 2026-04-29 | 2026-05-06 | 31
A22310 | Structural GA and Details, U&O Rack SR37_RCA | 16 | 2026-04-20 | 2026-05-12 | 2026-05-06 | 2026-05-28 | 31
A22300 | Structural GA and Details, U&O Rack SR37_IFA | 3 | 2026-04-15 | 2026-04-20 | 2026-05-28 | 2026-06-02 | 31
A50690 | Structural GA and Details, U&O Rack SR37_RCC | 16 | 2026-03-24 | 2026-04-15 | 2026-06-03 | 2026-06-24 | 31
A50680 | Structural GA and Details, U&O Rack SR37_IFR | 6 | 2026-03-16 | 2026-03-24 | 2026-06-24 | 2026-06-26 | 31
Structure & Foundation design - Mechanical |  | 268 | 10-Apr-25 A | 2026-03-23 | 2026-02-21 | 2027-01-20 | 218
Foundation Drawing- Lube Oil unit for PSA-2 FeedGas Compressor |  | 204 | 12-Apr-25 A | 23-Dec-25 A | 46407 | 46407
A19020 | Foundation Drawing- Lube Oil unit for PSA-2 FeedGas Compressor_IFD/IFC | 2 | 19-Dec-25 A | 23-Dec-25 A | 46407 | 46407
A19010 | Foundation Drawing- Lube Oil unit for PSA-2 FeedGas Compressor_RCA | 16 | 27-Jun-25 A | 15-Aug-25 A | 46407 | 46407
A18990 | Foundation Drawing- Lube Oil unit for PSA-2 FeedGas Compressor_RCC | 16 | 04-May-25 A | 10-May-25 A | 46407 | 46407
A19000 | Foundation Drawing- Lube Oil unit for PSA-2 FeedGas Compressor_IFA | 3 | 11-May-25 A | 21-Jun-25 A | 46407 | 46407
A18980 | Foundation Drawing- Lube Oil unit for PSA-2 FeedGas Compressor_IFR | 6 | 12-Apr-25 A | 03-May-25 A | 46407 | 46407
Design Calculation report for foundation of Lube Oil unit for PSA-2 FeedGas Compressor |  | 204 | 13-Apr-25 A | 23-Dec-25 A | 46407 | 46407
A19070 | Design Calculation report for foundation of Lube Oil unit for PSA-2 FeedGas Compressor_IFD/IFC | 2 | 19-Dec-25 A | 23-Dec-25 A | 46407 | 46407
A19060 | Design Calculation report for foundation of Lube Oil unit for PSA-2 FeedGas Compressor_RCA | 16 | 27-Jun-25 A | 15-Aug-25 A | 46407 | 46407
A19040 | Design Calculation report for foundation of Lube Oil unit for PSA-2 FeedGas Compressor_RCC | 16 | 04-May-25 A | 10-May-25 A | 46407 | 46407
A19050 | Design Calculation report for foundation of Lube Oil unit for PSA-2 FeedGas Compressor_IFA | 3 | 11-May-25 A | 21-Jun-25 A | 46407 | 46407
A19030 | Design Calculation report for foundation of Lube Oil unit for PSA-2 FeedGas Compressor_IFR | 6 | 13-Apr-25 A | 03-May-25 A | 46407 | 46407
Foundation Drawing- Lube Oil unit for PSA-2 OffGas Compressor |  | 101 | 26-May-25 A | 23-Dec-25 A | 46407 | 46407
A49160 | Foundation Drawing- Lube Oil unit for PSA-2 OffGas Compressor_IFD/IFC | 2 | 19-Dec-25 A | 23-Dec-25 A | 46407 | 46407
A49150 | Foundation Drawing- Lube Oil unit for PSA-2 OffGas Compressor_RCA | 16 | 07-Aug-25 A | 15-Aug-25 A | 46407 | 46407
A19100 | Foundation Drawing- Lube Oil unit for PSA-2 OffGas Compressor_IFA | 3 | 04-Aug-25 A | 08-Aug-25 A | 46407 | 46407
A19090 | Foundation Drawing- Lube Oil unit for PSA-2 OffGas Compressor_RCC | 16 | 07-Jul-25 A | 01-Aug-25 A | 46407 | 46407
A19080 | Foundation Drawing- Lube Oil unit for PSA-2 OffGas Compressor_IFR | 6 | 26-May-25 A | 05-Jul-25 A | 46407 | 46407
Design Calculation report for foundation of Lube Oil unit for PSA-2 OffGas Compressor |  | 101 | 26-May-25 A | 23-Dec-25 A | 46407 | 46407
A49180 | Design Calculation report for foundation of Lube Oil unit for PSA-2 OffGas Compressor_IFD/IFC | 2 | 19-Dec-25 A | 23-Dec-25 A | 46407 | 46407
A19160 | Design Calculation report for foundation of Lube Oil unit for PSA-2 OffGas Compressor_RCA | 16 | 07-Aug-25 A | 15-Aug-25 A | 46407 | 46407
A19150 | Design Calculation report for foundation of Lube Oil unit for PSA-2 OffGas Compressor_IFA | 3 | 04-Aug-25 A | 08-Aug-25 A | 46407 | 46407
A19140 | Design Calculation report for foundation of Lube Oil unit for PSA-2 OffGas Compressor_RCC | 16 | 07-Jul-25 A | 01-Aug-25 A | 46407 | 46407
A49170 | Design Calculation report for foundation of Lube Oil unit for PSA-2 OffGas Compressor_IFR | 6 | 26-May-25 A | 05-Jul-25 A | 46407 | 46407
Foundation drawing PSA-2 FeedGas Compressor 13-KC-701 |  | 156 | 19-Jul-25 A | 2026-03-17 | 2026-02-21 | 2027-01-20 | 221
A49050 | Foundation drawing PSA-2 FeedGas Compressor 13-KC-701_IFD/IFC | 2 | 2026-03-13 | 2026-03-17 | 2026-02-21 | 2026-02-21 | 221
A49040 | Foundation drawing PSA-2 FeedGas Compressor 13-KC-701_RCA | 16 | 2026-02-20 | 2026-03-13 | 2026-12-28 | 2026-12-28 | 221
A18800 | Foundation drawing PSA-2 FeedGas Compressor 13-KC-701_IFA | 3 | 01-Sep-25 A | 05-Sep-25 A | 46384 | 46384
A49030 | Foundation drawing PSA-2 FeedGas Compressor 13-KC-701_RCC | 16 | 01-Aug-25 A | 29-Aug-25 A | 46384 | 46405
A49020 | Foundation drawing PSA-2 FeedGas Compressor 13-KC-701_IFR | 11 | 19-Jul-25 A | 22-Aug-25 A | 46405 | 46407
Design Calculation Report PSA-2 FeedGas Compressor 13-KC-701 |  | 210 | 12-Apr-25 A | 13-Jan-26 A | 46407 | 46407
A49100 | Design Calculation Report PSA-2 FeedGas Compressor 13-KC-701_IFD/IFC | 2 | 09-Jan-26 A | 13-Jan-26 A | 46407 | 46407
A49090 | Design Calculation Report PSA-2 FeedGas Compressor 13-KC-701_RCA | 16 | 19-Aug-25 A | 29-Aug-25 A | 46407 | 46407
A49080 | Design Calculation Report PSA-2 FeedGas Compressor 13-KC-701_IFA | 3 | 18-Aug-25 A | 22-Aug-25 A | 46407 | 46407
A49070 | Design Calculation Report PSA-2 FeedGas Compressor 13-KC-701_RCC | 16 | 28-Jul-25 A | 15-Aug-25 A | 46407 | 46407
A49060 | Design Calculation Report PSA-2 FeedGas Compressor 13-KC-701_IFR | 11 | 12-Apr-25 A | 27-Jul-25 A | 46407 | 46407
Foundation drawing PSA-2 OffGas Compressor 13-KC-702 |  | 57 | 30-Jun-25 A | 05-Sep-25 A | 46074 | 46074
A49130 | Foundation drawing PSA-2 OffGas Compressor 13-KC-702_RCA | 16 | 23-Aug-25 A | 29-Aug-25 A | 46074 | 46074
A49140 | Foundation drawing PSA-2 OffGas Compressor 13-KC-702_IFD/IFC | 2 | 30-Aug-25 A | 05-Sep-25 A | 46074 | 46074
A49120 | Foundation drawing PSA-2 OffGas Compressor 13-KC-702_IFA | 3 | 16-Aug-25 A | 22-Aug-25 A | 46074 | 46074
A18880 | Foundation drawing PSA-2 OffGas Compressor 13-KC-702_IFR | 11 | 30-Jun-25 A | 10-Jul-25 A | 46074 | 46074
A49110 | Foundation drawing PSA-2 OffGas Compressor 13-KC-702_RCC | 16 | 11-Jul-25 A | 15-Aug-25 A | 46074 | 46074
Design Calculation Report PSA-2 OffGas Compressor 13-KC-702 |  | 87 | 01-Sep-25 A | 2026-02-24 | 2027-01-18 | 2027-01-20 | 237
A18970 | Design Calculation Report PSA-2 OffGas Compressor 13-KC-702_IFD/IFC | 2 | 2026-02-20 | 2026-02-24 | 2027-01-18 | 2027-01-18 | 237
A18960 | Design Calculation Report PSA-2 OffGas Compressor 13-KC-702_RCA | 16 | 24-Sep-25 A | 04-Oct-25 A | 46405 | 46405
A18950 | Design Calculation Report PSA-2 OffGas Compressor 13-KC-702_IFA | 3 | 22-Sep-25 A | 26-Sep-25 A | 46405 | 46405
A18940 | Design Calculation Report PSA-2 OffGas Compressor 13-KC-702_RCC | 16 | 05-Sep-25 A | 20-Sep-25 A | 46405 | 46405
A18930 | Design Calculation Report PSA-2 OffGas Compressor 13-KC-702_IFR | 11 | 01-Sep-25 A | 13-Sep-25 A | 46405 | 46407
Foundation Drawing PSA-2 Unit - Hydrogen Purification 13-XA-710 |  | 87 | 05-May-25 A | 10-Jul-25 A | 46407 | 46407
A20220 | Foundation Drawing PSA-2 Unit - Hydrogen Purification 13-XA-710_IFD/IFC | 2 | 09-Jun-25 A | 10-Jul-25 A | 46407 | 46407
A20210 | Foundation Drawing PSA-2 Unit - Hydrogen Purification 13-XA-710_RCA | 16 | 21-May-25 A | 04-Jun-25 A | 46407 | 46407
A20200 | Foundation Drawing PSA-2 Unit - Hydrogen Purification 13-XA-710_IFA | 3 | 22-May-25 A | 28-May-25 A | 46407 | 46407
A49610 | Foundation Drawing PSA-2 Unit - Hydrogen Purification 13-XA-710_RCC | 16 | 08-May-25 A | 21-May-25 A | 46407 | 46407
A49600 | Foundation Drawing PSA-2 Unit - Hydrogen Purification 13-XA-710_IFR | 6 | 05-May-25 A | 14-May-25 A | 46407 | 46407
Design Calculation Report for foundation of PSA-2 Unit - Hydrogen Purification 13-XA-710 |  | 87 | 26-May-25 A | 05-Sep-25 A | 46407 | 46407
A20270 | Design Calculation Report for foundation of PSA-2 Unit - Hydrogen Purification 13-XA-710_IFD/IFC | 2 | 01-Sep-25 A | 05-Sep-25 A | 46407 | 46407
A20260 | Design Calculation Report for foundation of PSA-2 Unit - Hydrogen Purification 13-XA-710_RCA | 16 | 11-Aug-25 A | 29-Aug-25 A | 46407 | 46407
A49640 | Design Calculation Report for foundation of PSA-2 Unit - Hydrogen Purification 13-XA-710_IFA | 3 | 18-Aug-25 A | 22-Aug-25 A | 46407 | 46407
A49630 | Design Calculation Report for foundation of PSA-2 Unit - Hydrogen Purification 13-XA-710_RCC | 16 | 08-Jul-25 A | 15-Aug-25 A | 46407 | 46407
A49620 | Design Calculation Report for foundation of PSA-2 Unit - Hydrogen Purification 13-XA-710_IFR | 6 | 26-May-25 A | 07-Jul-25 A | 46407 | 46407
Foundation drawing for Equipment 50-HE-1410 |  | 215 | 02-May-25 A | 2026-02-24 | 2026-03-29 | 2027-01-20 | 237
A50380 | Foundation drawing for Equipment 50-HE-1410_IFD/IFC | 2 | 2026-02-20 | 2026-02-24 | 2026-03-29 | 2026-03-29 | 237
A50370 | Foundation drawing for Equipment 50-HE-1410_RCA | 16 | 11-Aug-25 A | 29-Aug-25 A | 46405 | 46405
A50360 | Foundation drawing for Equipment 50-HE-1410_IFA | 3 | 01-Aug-25 A | 22-Aug-25 A | 46405 | 46405
A50350 | Foundation drawing for Equipment 50-HE-1410_RCC | 16 | 24-May-25 A | 29-May-25 A | 46405 | 46405
A50340 | Foundation drawing for Equipment 50-HE-1410_IFR | 6 | 02-May-25 A | 23-May-25 A | 46405 | 46407
Design calculation for foundation of Equipment 50-HE-1410 |  | 123 | 02-May-25 A | 23-Dec-25 A | 46407 | 46407
A21870 | Design calculation for foundation of Equipment 50-HE-1410_IFD/IFC | 2 | 19-Dec-25 A | 23-Dec-25 A | 46407 | 46407
A50420 | Design calculation for foundation of Equipment 50-HE-1410_RCA | 16 | 29-Sep-25 A | 24-Oct-25 A | 46407 | 46407
A50410 | Design calculation for foundation of Equipment 50-HE-1410_IFA | 3 | 15-Jul-25 A | 22-Aug-25 A | 46407 | 46407
A50390 | Design calculation for foundation of Equipment 50-HE-1410_IFR | 6 | 02-May-25 A | 23-May-25 A | 46407 | 46407
A50400 | Design calculation for foundation of Equipment 50-HE-1410_RCC | 16 | 24-May-25 A | 21-Jun-25 A | 46407 | 46407
Foundation Drawing PSA-2 OffGas Compressor Interstage Cooler 13-HE-708 |  | 108 | 01-May-25 A | 10-Oct-25 A | 46110 | 46110
A49570 | Foundation Drawing PSA-2 OffGas Compressor Interstage Cooler 13-HE-708_IFD/IFC | 2 | 26-Sep-25 A | 10-Oct-25 A | 46110 | 46110
A49560 | Foundation Drawing PSA-2 OffGas Compressor Interstage Cooler 13-HE-708_RCA | 16 | 01-Aug-25 A | 21-Aug-25 A | 46110 | 46110
A20100 | Foundation Drawing PSA-2 OffGas Compressor Interstage Cooler 13-HE-708_IFA | 3 | 23-May-25 A | 21-Jun-25 A | 46110 | 46110
A20090 | Foundation Drawing PSA-2 OffGas Compressor Interstage Cooler 13-HE-708_RCC | 16 | 16-May-25 A | 22-May-25 A | 46110 | 46110
A20080 | Foundation Drawing PSA-2 OffGas Compressor Interstage Cooler 13-HE-708_IFR | 6 | 01-May-25 A | 15-May-25 A | 46110 | 46110
Design Calculation Report for foundation of PSA-2 OffGas Compressor Interstage Cooler 13-HE-708 |  | 82 | 28-Apr-25 A | 10-Oct-25 A | 46407 | 46407
A49590 | Design Calculation Report for foundation of PSA-2 OffGas Compressor Interstage Cooler 13-HE-708_IFD/IFC | 2 | 22-Sep-25 A | 10-Oct-25 A | 46407 | 46407
A20160 | Design Calculation Report for foundation of PSA-2 OffGas Compressor Interstage Cooler 13-HE-708_RCA | 16 | 21-Jul-25 A | 21-Aug-25 A | 46407 | 46407
A20150 | Design Calculation Report for foundation of PSA-2 OffGas Compressor Interstage Cooler 13-HE-708_IFA | 3 | 22-Jun-25 A | 28-Jun-25 A | 46407 | 46407
A20140 | Design Calculation Report for foundation of PSA-2 OffGas Compressor Interstage Cooler 13-HE-708_RCC | 16 | 20-May-25 A | 21-Jun-25 A | 46407 | 46407
A49580 | Design Calculation Report for foundation of PSA-2 OffGas Compressor Interstage Cooler 13-HE-708_IFR | 6 | 28-Apr-25 A | 19-May-25 A | 46407 | 46407
Foundation Drawing PSA-2 Feed Gas Compressor AfterCooler 13-HE-704 |  | 111 | 28-Apr-25 A | 25-Jul-25 A | 46145 | 46168
A19320 | Foundation Drawing PSA-2 Feed Gas Compressor AfterCooler 13-HE-704_IFD/IFC | 2 | 21-Jul-25 A | 25-Jul-25 A | 46145 | 46145
A19310 | Foundation Drawing PSA-2 Feed Gas Compressor AfterCooler 13-HE-704_RCA | 16 | 30-Jun-25 A | 18-Jul-25 A | 46168 | 46168
A19300 | Foundation Drawing PSA-2 Feed Gas Compressor AfterCooler 13-HE-704_IFA | 3 | 22-Jun-25 A | 28-Jun-25 A | 46168 | 46168
A19290 | Foundation Drawing PSA-2 Feed Gas Compressor AfterCooler 13-HE-704_RCC | 16 | 20-May-25 A | 21-Jun-25 A | 46168 | 46168
A19280 | Foundation Drawing PSA-2 Feed Gas Compressor AfterCooler 13-HE-704_IFR | 6 | 28-Apr-25 A | 19-May-25 A | 46168 | 46168
Design Calculation Report for foundation of PSA-2 Feed Gas Compressor AfterCooler 13-HE-704 |  | 36 | 28-Apr-25 A | 08-Sep-25 A | 46407 | 46407
A49260 | Design Calculation Report for foundation of PSA-2 Feed Gas Compressor AfterCooler 13-HE-704_IFD/IFC | 2 | 29-Jun-25 A | 08-Sep-25 A | 46407 | 46407
A19340 | Design Calculation Report for foundation of PSA-2 Feed Gas Compressor AfterCooler 13-HE-704_RCC | 16 | 04-May-25 A | 19-May-25 A | 46407 | 46407
A49250 | Design Calculation Report for foundation of PSA-2 Feed Gas Compressor AfterCooler 13-HE-704_RCA | 16 | 22-Jun-25 A | 28-Jun-25 A | 46407 | 46407
A19330 | Design Calculation Report for foundation of PSA-2 Feed Gas Compressor AfterCooler 13-HE-704_IFR | 6 | 28-Apr-25 A | 03-May-25 A | 46407 | 46407
A49240 | Design Calculation Report for foundation of PSA-2 Feed Gas Compressor AfterCooler 13-HE-704_IFA | 3 | 20-May-25 A | 21-Jun-25 A | 46407 | 46407
Foundation Drawing PSA-2 Feed Gas Compressor Interstage Cooler 13-HE-703 |  | 103 | 24-Apr-25 A | 15-Sep-25 A | 46145 | 46166
A19520 | Foundation Drawing PSA-2 Feed Gas Compressor Interstage Cooler 13-HE-703_IFD/IFC | 2 | 09-Sep-25 A | 15-Sep-25 A | 46145 | 46145
A19510 | Foundation Drawing PSA-2 Feed Gas Compressor Interstage Cooler 13-HE-703_RCA | 16 | 02-Sep-25 A | 08-Sep-25 A | 46166 | 46166
A19500 | Foundation Drawing PSA-2 Feed Gas Compressor Interstage Cooler 13-HE-703_IFA | 3 | 23-May-25 A | 01-Sep-25 A | 46166 | 46166
A49320 | Foundation Drawing PSA-2 Feed Gas Compressor Interstage Cooler 13-HE-703_RCC | 16 | 16-May-25 A | 22-May-25 A | 46166 | 46166
A49310 | Foundation Drawing PSA-2 Feed Gas Compressor Interstage Cooler 13-HE-703_IFR | 6 | 24-Apr-25 A | 15-May-25 A | 46166 | 46166
Design Calculation Report for foundation of PSA-2 Feed Gas Compressor Interstage Cooler 13-HE-703 |  | 53 | 24-Apr-25 A | 15-Sep-25 A | 46407 | 46407
A19570 | Design Calculation Report for foundation of PSA-2 Feed Gas Compressor Interstage Cooler 13-HE-703_IFD/IFC | 2 | 10-Sep-25 A | 15-Sep-25 A | 46407 | 46407
A19560 | Design Calculation Report for foundation of PSA-2 Feed Gas Compressor Interstage Cooler 13-HE-703_RCA | 16 | 02-Sep-25 A | 09-Sep-25 A | 46407 | 46407
A49350 | Design Calculation Report for foundation of PSA-2 Feed Gas Compressor Interstage Cooler 13-HE-703_IFA | 3 | 23-May-25 A | 01-Sep-25 A | 46407 | 46407
A49340 | Design Calculation Report for foundation of PSA-2 Feed Gas Compressor Interstage Cooler 13-HE-703_RCC | 16 | 16-May-25 A | 22-May-25 A | 46407 | 46407
A49330 | Design Calculation Report for foundation of PSA-2 Feed Gas Compressor Interstage Cooler 13-HE-703_IFR | 6 | 24-Apr-25 A | 15-May-25 A | 46407 | 46407
Foundation Drawing PSA-2 OffGas Compressor AfterCooler 13-HE-709 |  | 101 | 20-May-25 A | 10-Oct-25 A | 46145 | 46149
A19820 | Foundation Drawing PSA-2 OffGas Compressor AfterCooler 13-HE-709_IFD/IFC | 2 | 16-Sep-25 A | 10-Oct-25 A | 46145 | 46145
A19810 | Foundation Drawing PSA-2 OffGas Compressor AfterCooler 13-HE-709_RCA | 16 | 30-Jun-25 A | 15-Sep-25 A | 46149 | 46149
A19800 | Foundation Drawing PSA-2 OffGas Compressor AfterCooler 13-HE-709_IFA | 3 | 22-Jun-25 A | 28-Jun-25 A | 46149 | 46149
A19790 | Foundation Drawing PSA-2 OffGas Compressor AfterCooler 13-HE-709_RCC | 16 | 20-May-25 A | 21-Jun-25 A | 46149 | 46149
A49430 | Foundation Drawing PSA-2 OffGas Compressor AfterCooler 13-HE-709_IFR | 6 | 30-May-25 A | 13-Jun-25 A | 46149 | 46149
Design Calculation Report for foundation of PSA-2 OffGas Compressor AfterCooler 13-HE-709 |  | 36 | 28-Apr-25 A | 08-Oct-25 A | 46407 | 46407
A49440 | Design Calculation Report for foundation of PSA-2 OffGas Compressor AfterCooler 13-HE-709_IFD/IFC | 2 | 09-Sep-25 A | 08-Oct-25 A | 46407 | 46407
A19860 | Design Calculation Report for foundation of PSA-2 OffGas Compressor AfterCooler 13-HE-709_RCA | 16 | 29-Jun-25 A | 08-Sep-25 A | 46407 | 46407
A19850 | Design Calculation Report for foundation of PSA-2 OffGas Compressor AfterCooler 13-HE-709_IFA | 3 | 22-Jun-25 A | 28-Jun-25 A | 46407 | 46407
A19840 | Design Calculation Report for foundation of PSA-2 OffGas Compressor AfterCooler 13-HE-709_RCC | 16 | 20-May-25 A | 21-Jun-25 A | 46407 | 46407
A19830 | Design Calculation Report for foundation of PSA-2 OffGas Compressor AfterCooler 13-HE-709_IFR | 6 | 28-Apr-25 A | 19-May-25 A | 46407 | 46407
Foundation Drawing PSA-2 OffGas Compressor Discharge Dripleg 13-SP-7004 |  | 44 | 16-Apr-25 A | 04-Sep-25 A | 46145 | 46145
A49520 | Foundation Drawing PSA-2 OffGas Compressor Discharge Dripleg 13-SP-7004_RCA | 16 | 04-Jun-25 A | 21-Jun-25 A | 46145 | 46145
A49510 | Foundation Drawing PSA-2 OffGas Compressor Discharge Dripleg 13-SP-7004_IFA | 3 | 15-May-25 A | 03-Jun-25 A | 46145 | 46145
A49500 | Foundation Drawing PSA-2 OffGas Compressor Discharge Dripleg 13-SP-7004_RCC | 16 | 08-May-25 A | 14-May-25 A | 46145 | 46145
A19980 | Foundation Drawing PSA-2 OffGas Compressor Discharge Dripleg 13-SP-7004_IFR | 6 | 16-Apr-25 A | 07-May-25 A | 46145 | 46145
A20020 | Foundation Drawing PSA-2 OffGas Compressor Discharge Dripleg 13-SP-7004_IFD/IFC | 2 | 22-Jun-25 A | 04-Sep-25 A | 46145 | 46145
Design Calculation Report for foundation of PSA-2 OffGas Compressor Discharge Dripleg 13-SP-7004 |  | 47 | 16-Apr-25 A | 10-Oct-25 A | 46407 | 46407
A49550 | Design Calculation Report for foundation of PSA-2 OffGas Compressor Discharge Dripleg 13-SP-7004_IFD/IFC | 2 | 29-Sep-25 A | 10-Oct-25 A | 46407 | 46407
A49540 | Design Calculation Report for foundation of PSA-2 OffGas Compressor Discharge Dripleg 13-SP-7004_RCA | 16 | 04-Jun-25 A | 21-Jun-25 A | 46407 | 46407
A49530 | Design Calculation Report for foundation of PSA-2 OffGas Compressor Discharge Dripleg 13-SP-7004_IFA | 3 | 15-May-25 A | 03-Jun-25 A | 46407 | 46407
A20040 | Design Calculation Report for foundation of PSA-2 OffGas Compressor Discharge Dripleg 13-SP-7004_RCC | 16 | 08-May-25 A | 14-May-25 A | 46407 | 46407
A20030 | Design Calculation Report for foundation of PSA-2 OffGas Compressor Discharge Dripleg 13-SP-7004_IFR | 6 | 16-Apr-25 A | 07-May-25 A | 46407 | 46407
Foundation Drawing PSA-2 Slop Drum 70-VV-1415 |  | 146 | 24-Apr-25 A | 2026-03-23 | 2026-05-11 | 2027-01-20 | 218
A20320 | Foundation Drawing PSA-2 Slop Drum 70-VV-1415_IFD/IFC | 2 | 2026-03-19 | 2026-03-23 | 2026-05-11 | 2026-05-11 | 218
A49670 | Foundation Drawing PSA-2 Slop Drum 70-VV-1415_RCA | 16 | 2026-02-25 | 2026-03-19 | 2026-05-21 | 2026-05-21 | 218
A49660 | Foundation Drawing PSA-2 Slop Drum 70-VV-1415_IFA | 3 | 2026-02-20 | 2026-02-25 | 2026-12-22 | 2026-12-25 | 218
A49650 | Foundation Drawing PSA-2 Slop Drum 70-VV-1415_RCC | 16 | 16-May-25 A | 22-May-25 A | 46384 | 46405
A20280 | Foundation Drawing PSA-2 Slop Drum 70-VV-1415_IFR | 6 | 24-Apr-25 A | 15-May-25 A | 46405 | 46407
Design Calculation Report for foundation of PSA-2 Slop Drum 70-VV-1415 |  | 74 | 01-Aug-25 A | 19-Jan-26 A | 46407 | 46407
A49700 | Design Calculation Report for foundation of PSA-2 Slop Drum 70-VV-1415_IFD/IFC | 2 | 15-Jan-26 A | 19-Jan-26 A | 46407 | 46407
A49690 | Design Calculation Report for foundation of PSA-2 Slop Drum 70-VV-1415_RCA | 16 | 25-Aug-25 A | 09-Sep-25 A | 46407 | 46407
A49680 | Design Calculation Report for foundation of PSA-2 Slop Drum 70-VV-1415_IFA | 3 | 27-Aug-25 A | 02-Sep-25 A | 46407 | 46407
A20340 | Design Calculation Report for foundation of PSA-2 Slop Drum 70-VV-1415_RCC | 16 | 08-Aug-25 A | 26-Aug-25 A | 46407 | 46407
A20330 | Design Calculation Report for foundation of PSA-2 Slop Drum 70-VV-1415_IFR | 6 | 01-Aug-25 A | 22-Aug-25 A | 46407 | 46407
Foundation Drawing PSA-2 Feed Gas Compressor 2nd Stage Discharge Drum 13-VV-707 |  | 76 | 20-Apr-25 A | 23-Dec-25 A | 46153 | 46153
A19220 | Foundation Drawing PSA-2 Feed Gas Compressor 2nd Stage Discharge Drum 13-VV-707_IFD/IFC | 2 | 19-Dec-25 A | 23-Dec-25 A | 46153 | 46153
A19210 | Foundation Drawing PSA-2 Feed Gas Compressor 2nd Stage Discharge Drum 13-VV-707_RCA | 16 | 22-Sep-25 A | 10-Oct-25 A | 46153 | 46153
A19200 | Foundation Drawing PSA-2 Feed Gas Compressor 2nd Stage Discharge Drum 13-VV-707_IFA | 3 | 19-May-25 A | 11-Jun-25 A | 46153 | 46153
A49200 | Foundation Drawing PSA-2 Feed Gas Compressor 2nd Stage Discharge Drum 13-VV-707_RCC | 16 | 12-May-25 A | 18-May-25 A | 46153 | 46153
A49190 | Foundation Drawing PSA-2 Feed Gas Compressor 2nd Stage Discharge Drum 13-VV-707_IFR | 6 | 20-Apr-25 A | 11-May-25 A | 46153 | 46153
Design Calculation Report-Foundation of PSA-2 FeedGas Compressor 2ndStage DischargeDrum 13-VV-707 |  | 76 | 20-Apr-25 A | 23-Dec-25 A | 46407 | 46407
A19270 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 FEED GAS COMPRESSOR 2ND STAGE DISCHARGE DRUM 13-VV-707_IFD/IFC | 2 | 19-Dec-25 A | 23-Dec-25 A | 46407 | 46407
A19260 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 FEED GAS COMPRESSOR 2ND STAGE DISCHARGE DRUM 13-VV-707_RCA | 16 | 22-Sep-25 A | 10-Oct-25 A | 46407 | 46407
A49230 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 FEED GAS COMPRESSOR 2ND STAGE DISCHARGE DRUM 13-VV-707_IFA | 3 | 19-May-25 A | 11-Jun-25 A | 46407 | 46407
A49220 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 FEED GAS COMPRESSOR 2ND STAGE DISCHARGE DRUM 13-VV-707_RCC | 16 | 12-May-25 A | 18-May-25 A | 46407 | 46407
A49210 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 FEED GAS COMPRESSOR 2ND STAGE DISCHARGE DRUM 13-VV-707_IFR | 6 | 20-Apr-25 A | 11-May-25 A | 46407 | 46407
Foundation Drawing PSA-2 Feed Gas Compressor 2nd Stage Suction Drum 13-VV-706 |  | 43 | 16-Apr-25 A | 16-Sep-25 A | 46156 | 46160
A19400 | Foundation Drawing PSA-2 Feed Gas Compressor 2nd Stage Suction Drum 13-VV-706_IFA | 3 | 11-May-25 A | 11-Jun-25 A | 46156 | 46156
A19390 | Foundation Drawing PSA-2 Feed Gas Compressor 2nd Stage Suction Drum 13-VV-706_RCC | 16 | 04-May-25 A | 10-May-25 A | 46160 | 46160
A19380 | Foundation Drawing PSA-2 Feed Gas Compressor 2nd Stage Suction Drum 13-VV-706_IFR | 6 | 16-Apr-25 A | 03-May-25 A | 46160 | 46160
A49280 | Foundation Drawing PSA-2 Feed Gas Compressor 2nd Stage Suction Drum 13-VV-706_IFD/IFC | 2 | 02-Sep-25 A | 16-Sep-25 A | 46160 | 46160
A49270 | Foundation Drawing PSA-2 Feed Gas Compressor 2nd Stage Suction Drum 13-VV-706_RCA | 16 | 12-Jun-25 A | 01-Sep-25 A | 46160 | 46160
Design Calculation Report Foundation of PSA-2 FeedGas Compressor 2ndStage Suction Drum 13-VV-706 |  | 29 | 16-Apr-25 A | 08-Sep-25 A | 46407 | 46407
A19460 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 FEED GAS COMPRESSOR 2ND STAGE SUCTION DRUM 13-VV-706_RCA | 16 | 12-Jun-25 A | 21-Jun-25 A | 46407 | 46407
A19450 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 FEED GAS COMPRESSOR 2ND STAGE SUCTION DRUM 13-VV-706_IFA | 3 | 11-May-25 A | 11-Jun-25 A | 46407 | 46407
A19440 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 FEED GAS COMPRESSOR 2ND STAGE SUCTION DRUM 13-VV-706_RCC | 16 | 04-May-25 A | 10-May-25 A | 46407 | 46407
A49290 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 FEED GAS COMPRESSOR 2ND STAGE SUCTION DRUM 13-VV-706_IFR | 6 | 16-Apr-25 A | 03-May-25 A | 46407 | 46407
A49300 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 FEED GAS COMPRESSOR 2ND STAGE SUCTION DRUM 13-VV-706_IFD/IFC | 2 | 22-Jun-25 A | 08-Sep-25 A | 46407 | 46407
Foundation Drawing PSA-2 Feed Gas Compressor 1st Stage Suction Drum 13-VV-705 |  | 66 | 24-Apr-25 A | 23-Dec-25 A | 46156 | 46156
A19620 | Foundation Drawing PSA-2 Feed Gas Compressor 1st Stage Suction Drum 13-VV-705_IFD/IFC | 2 | 19-Dec-25 A | 23-Dec-25 A | 46156 | 46156
A49380 | Foundation Drawing PSA-2 Feed Gas Compressor 1st Stage Suction Drum 13-VV-705_RCA | 16 | 05-Jun-25 A | 21-Jun-25 A | 46156 | 46156
A49370 | Foundation Drawing PSA-2 Feed Gas Compressor 1st Stage Suction Drum 13-VV-705_IFA | 3 | 23-May-25 A | 04-Jun-25 A | 46156 | 46156
A49360 | Foundation Drawing PSA-2 Feed Gas Compressor 1st Stage Suction Drum 13-VV-705_RCC | 16 | 16-May-25 A | 22-May-25 A | 46156 | 46156
A19580 | Foundation Drawing PSA-2 Feed Gas Compressor 1st Stage Suction Drum 13-VV-705_IFR | 6 | 24-Apr-25 A | 15-May-25 A | 46156 | 46156
Design Calculation Report Foundation of PSA-2 FeedGas Compressor 1stStage Suction Drum 13-VV-705 |  | 66 | 24-Apr-25 A | 23-Dec-25 A | 46407 | 46407
A49410 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 FEED GAS COMPRESSOR 1ST STAGE SUCTION DRUM 13-VV-705_IFD/IFC | 2 | 19-Dec-25 A | 23-Dec-25 A | 46407 | 46407
A49400 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 FEED GAS COMPRESSOR 1ST STAGE SUCTION DRUM 13-VV-705_RCA | 16 | 04-Jun-25 A | 21-Jun-25 A | 46407 | 46407
A49390 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 FEED GAS COMPRESSOR 1ST STAGE SUCTION DRUM 13-VV-705_IFA | 3 | 23-May-25 A | 03-Jun-25 A | 46407 | 46407
A19640 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 FEED GAS COMPRESSOR 1ST STAGE SUCTION DRUM 13-VV-705_RCC | 16 | 16-May-25 A | 22-May-25 A | 46407 | 46407
A19630 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 FEED GAS COMPRESSOR 1ST STAGE SUCTION DRUM 13-VV-705_IFR | 6 | 24-Apr-25 A | 15-May-25 A | 46407 | 46407
Foundation Drawing PSA-2 OffGas Compressor 2nd Stage Suction Drum 13-VV-713 |  | 47 | 15-Apr-25 A | 29-Jul-25 A | 46156 | 46195
A19690 | Foundation Drawing PSA-2 OffGas Compressor 2nd Stage Suction Drum 13-VV-713_RCC | 16 | 07-May-25 A | 13-Jun-25 A | 46156 | 46156
A19680 | Foundation Drawing PSA-2 OffGas Compressor 2nd Stage Suction Drum 13-VV-713_IFR | 6 | 15-Apr-25 A | 06-May-25 A | 46195 | 46195
A19700 | Foundation Drawing PSA-2 OffGas Compressor 2nd Stage Suction Drum 13-VV-713_IFA | 3 | 16-Jun-25 A | 30-Jun-25 A | 46195 | 46195
A19720 | Foundation Drawing PSA-2 OffGas Compressor 2nd Stage Suction Drum 13-VV-713_IFD/IFC | 2 | 15-Jul-25 A | 29-Jul-25 A | 46195 | 46195
A19710 | Foundation Drawing PSA-2 OffGas Compressor 2nd Stage Suction Drum 13-VV-713_RCA | 16 | 16-Jun-25 A | 14-Jul-25 A | 46195 | 46195
Design Calculation Report Foundation of PSA-2 OffGas Compressor 2ndStage Suction Drum 13-VV-713 |  | 50 | 20-Apr-25 A | 10-Oct-25 A | 46407 | 46407
A49420 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 OFFGAS COMPRESSOR 2ND STAGE SUCTION DRUM 13-VV-713_IFD/IFC | 2 | 08-Sep-25 A | 10-Oct-25 A | 46407 | 46407
A19760 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 OFFGAS COMPRESSOR 2ND STAGE SUCTION DRUM 13-VV-713_RCA | 16 | 01-Jul-25 A | 04-Sep-25 A | 46407 | 46407
A19730 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 OFFGAS COMPRESSOR 2ND STAGE SUCTION DRUM 13-VV-713_IFR | 6 | 20-Apr-25 A | 11-May-25 A | 46407 | 46407
A19750 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 OFFGAS COMPRESSOR 2ND STAGE SUCTION DRUM 13-VV-713_IFA | 3 | 22-Jun-25 A | 28-Jun-25 A | 46407 | 46407
A19740 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 OFFGAS COMPRESSOR 2ND STAGE SUCTION DRUM 13-VV-713_RCC | 16 | 12-May-25 A | 21-Jun-25 A | 46407 | 46407
Foundation Drawing PSA-2 OffGas Buffer Drum 13-VV-712 |  | 21 | 22-Apr-25 A | 10-Oct-25 A | 46156 | 46156
A19920 | Foundation Drawing PSA-2 OffGas Buffer Drum 13-VV-712_IFD/IFC | 2 | 26-Sep-25 A | 10-Oct-25 A | 46156 | 46156
A19910 | Foundation Drawing PSA-2 OffGas Buffer Drum 13-VV-712_RCA | 16 | 22-Jun-25 A | 28-Jun-25 A | 46156 | 46156
A49460 | Foundation Drawing PSA-2 OffGas Buffer Drum 13-VV-712_RCC | 16 | 14-May-25 A | 29-May-25 A | 46156 | 46156
A49450 | Foundation Drawing PSA-2 OffGas Buffer Drum 13-VV-712_IFR | 6 | 22-Apr-25 A | 13-May-25 A | 46156 | 46156
A19900 | Foundation Drawing PSA-2 OffGas Buffer Drum 13-VV-712_IFA | 3 | 30-May-25 A | 21-Jun-25 A | 46156 | 46156
Design Calculation Report for foundation of PSA-2 OffGas Buffer Drum 13-VV-712 |  | 47 | 22-Apr-25 A | 10-Oct-25 A | 46407 | 46407
A19970 | Design Calculation Report for foundation of PSA-2 OffGas Buffer Drum 13-VV-712_IFD/IFC | 2 | 26-Sep-25 A | 10-Oct-25 A | 46407 | 46407
A49480 | Design Calculation Report for foundation of PSA-2 OffGas Buffer Drum 13-VV-712_RCC | 16 | 14-May-25 A | 03-Jun-25 A | 46407 | 46407
A49470 | Design Calculation Report for foundation of PSA-2 OffGas Buffer Drum 13-VV-712_IFR | 6 | 22-Apr-25 A | 13-May-25 A | 46407 | 46407
A49490 | Design Calculation Report for foundation of PSA-2 OffGas Buffer Drum 13-VV-712_IFA | 3 | 04-Jun-25 A | 21-Jun-25 A | 46407 | 46407
A19960 | Design Calculation Report for foundation of PSA-2 OffGas Buffer Drum 13-VV-712_RCA | 16 | 22-Jun-25 A | 06-Sep-25 A | 46407 | 46407
Pile Layout Compressor Shelter & SR8001 |  | 39 | 01-Jul-25 A | 13-Sep-25 A | 46074 | 46074
A17660 | Pile Layout Compressor Shelter & SR8001_RCA | 16 | 25-Aug-25 A | 06-Sep-25 A | 46074 | 46074
A17670 | Pile Layout Compressor Shelter & SR8001_IFD/IFC | 2 | 08-Sep-25 A | 13-Sep-25 A | 46074 | 46074
A17650 | Pile Layout Compressor Shelter & SR8001_IFA | 3 | 25-Aug-25 A | 30-Aug-25 A | 46074 | 46074
A17640 | Pile Layout Compressor Shelter & SR8001_RCC | 16 | 14-Jul-25 A | 22-Aug-25 A | 46074 | 46074
A17630 | Pile Layout Compressor Shelter & SR8001_IFR | 6 | 01-Jul-25 A | 12-Jul-25 A | 46074 | 46074
Pile Reinforcement Drawing |  | 39 | 01-Jul-25 A | 18-Jul-25 A | 46074 | 46407
A17520 | Pile Reinforcement Drawing_IFD/IFC | 2 | 01-Jul-25 A | 18-Jul-25 A | 46074 | 46074
A17510 | Pile Reinforcement Drawing_RCA | 16 | 01-Jul-25 A | 18-Jul-25 A | 46407 | 46407
A17500 | Pile Reinforcement Drawing_IFA | 3 | 01-Jul-25 A | 18-Jul-25 A | 46407 | 46407
A17490 | Pile Reinforcement Drawing_RCC | 16 | 01-Jul-25 A | 18-Jul-25 A | 46407 | 46407
A17480 | Pile Reinforcement Drawing_IFR | 6 | 01-Jul-25 A | 18-Jul-25 A | 46407 | 46407
Pile Layout PSA-2 FeedGas Compressor 13-KC-701 |  | 149 | 10-Apr-25 A | 15-Sep-25 A | 46074 | 46074
A48320 | Pile Layout PSA-2 FeedGas Compressor 13-KC-701_RCC | 16 | 16-Aug-25 A | 22-Aug-25 A | 46074 | 46074
A17570 | Pile Layout PSA-2 FeedGas Compressor 13-KC-701_IFD/IFC | 2 | 08-Sep-25 A | 15-Sep-25 A | 46074 | 46074
A17560 | Pile Layout PSA-2 FeedGas Compressor 13-KC-701_RCA | 16 | 18-Aug-25 A | 05-Sep-25 A | 46074 | 46074
A17550 | Pile Layout PSA-2 FeedGas Compressor 13-KC-701_IFA | 3 | 22-Aug-25 A | 29-Aug-25 A | 46074 | 46074
A17530 | Pile Layout PSA-2 FeedGas Compressor 13-KC-701_IFR | 6 | 10-Apr-25 A | 15-Aug-25 A | 46074 | 46074
Pile Layout PSA-2 OffGas Compressor 13-KC-702 |  | 39 | 01-Jul-25 A | 15-Sep-25 A | 46074 | 46074
A17610 | Pile Layout PSA-2 OffGas Compressor 13-KC-702_RCA | 16 | 01-Aug-25 A | 06-Sep-25 A | 46074 | 46074
A17620 | Pile Layout PSA-2 OffGas Compressor 13-KC-702_IFD/IFC | 2 | 08-Sep-25 A | 15-Sep-25 A | 46074 | 46074
A17600 | Pile Layout PSA-2 OffGas Compressor 13-KC-702_IFA | 3 | 25-Aug-25 A | 30-Aug-25 A | 46074 | 46074
A17590 | Pile Layout PSA-2 OffGas Compressor 13-KC-702_RCC | 16 | 14-Jul-25 A | 22-Aug-25 A | 46074 | 46074
A17580 | Pile Layout PSA-2 OffGas Compressor 13-KC-702_IFR | 6 | 01-Jul-25 A | 11-Jul-25 A | 46074 | 46074
Pile Layout PSA-2 Unit - Hydrogen Purification 13-XA-710 |  | 38 | 30-Jun-25 A | 13-Sep-25 A | 46083 | 46083
A48360 | Pile Layout PSA-2 Unit - Hydrogen Purification 13-XA-710_RCA | 16 | 19-Aug-25 A | 06-Sep-25 A | 46083 | 46083
A48370 | Pile Layout PSA-2 Unit - Hydrogen Purification 13-XA-710_IFD/IFC | 2 | 08-Sep-25 A | 13-Sep-25 A | 46083 | 46083
A48350 | Pile Layout PSA-2 Unit - Hydrogen Purification 13-XA-710_IFA | 3 | 25-Aug-25 A | 30-Aug-25 A | 46083 | 46083
A48340 | Pile Layout PSA-2 Unit - Hydrogen Purification 13-XA-710_RCC | 16 | 14-Jul-25 A | 22-Aug-25 A | 46083 | 46083
A48330 | Pile Layout PSA-2 Unit - Hydrogen Purification 13-XA-710_IFR | 6 | 30-Jun-25 A | 11-Jul-25 A | 46083 | 46083
Pile Layout PSA-2 OffGas Buffer Drum 13-VV-712 |  | 39 | 02-Jun-25 A | 05-Jul-25 A | 46083 | 46083
A17710 | Pile Layout PSA-2 OffGas Buffer Drum 13-VV-712_RCA | 16 | 17-Jun-25 A | 28-Jun-25 A | 46083 | 46083
A17720 | Pile Layout PSA-2 OffGas Buffer Drum 13-VV-712_IFD/IFC | 2 | 30-Jun-25 A | 05-Jul-25 A | 46083 | 46083
A17700 | Pile Layout PSA-2 OffGas Buffer Drum 13-VV-712_IFA | 3 | 17-Jun-25 A | 23-Jun-25 A | 46083 | 46083
A17690 | Pile Layout PSA-2 OffGas Buffer Drum 13-VV-712_RCC | 16 | 06-Jun-25 A | 16-Jun-25 A | 46083 | 46083
A17680 | Pile Layout PSA-2 OffGas Buffer Drum 13-VV-712_IFR | 6 | 02-Jun-25 A | 07-Jun-25 A | 46083 | 46083
Structure & Foundation design - Buildings/Shelters/Electrical |  | 321 | 05-Feb-25 A | 2026-04-07 | 2026-03-14 | 2027-01-20 | 206
Structural GA, Section and Details - Compressor Shelter |  | 61 | 01-Oct-25 A | 19-Jan-26 A | 46161 | 46161
A48920 | Structural GA, Section and Details - Compressor Shelter_IFD/IFC | 6 | 09-Jan-26 A | 19-Jan-26 A | 46161 | 46161
A48910 | Structural GA, Section and Details - Compressor Shelter_RCA | 16 | 19-Dec-25 A | 09-Jan-26 A | 46161 | 46161
A48900 | Structural GA, Section and Details - Compressor Shelter_IFA | 11 | 23-Oct-25 A | 24-Oct-25 A | 46161 | 46161
A48890 | Structural GA, Section and Details - Compressor Shelter_RCC | 16 | 08-Oct-25 A | 23-Oct-25 A | 46161 | 46161
A48880 | Structural GA, Section and Details - Compressor Shelter_IFR | 17 | 01-Oct-25 A | 07-Oct-25 A | 46161 | 46161
Design Calculation Report for structural steel- Compressor Shelter |  | 118 | 01-Sep-25 A | 2026-04-07 | 2026-12-07 | 2027-01-20 | 206
A48960 | Design Calculation Report for structural steel- Compressor Shelter_IFD/IFC | 6 | 2026-03-31 | 2026-04-07 | 2026-12-07 | 2026-12-07 | 206
A18710 | Design Calculation Report for structural steel- Compressor Shelter_RCA | 16 | 2026-03-09 | 2026-03-30 | 2026-12-07 | 2026-12-07 | 206
A18700 | Design Calculation Report for structural steel- Compressor Shelter_IFA | 11 | 2026-02-20 | 2026-03-09 | 2026-12-07 | 2026-12-22 | 206
A18690 | Design Calculation Report for structural steel- Compressor Shelter_RCC | 16 | 10-Sep-25 A | 01-Oct-25 A | 46378 | 46400
A48950 | Design Calculation Report for structural steel- Compressor Shelter_IFR | 17 | 01-Sep-25 A | 13-Sep-25 A | 46400 | 46407
Foundation Drawing- Compressor Shelter |  | 107 | 01-Jul-25 A | 21-Jan-26 A | 46407 | 46407
A48930 | Foundation Drawing- Compressor Shelter_RCA | 16 | 31-Oct-25 A | 14-Nov-25 A | 46407 | 46407
A48940 | Foundation Drawing- Compressor Shelter_IFD/IFC | 2 | 19-Jan-26 A | 21-Jan-26 A | 46407 | 46407
A18650 | Foundation Drawing- Compressor Shelter_IFA | 3 | 20-Oct-25 A | 30-Oct-25 A | 46407 | 46407
A18640 | Foundation Drawing- Compressor Shelter_RCC | 16 | 15-Jul-25 A | 22-Aug-25 A | 46407 | 46407
A18630 | Foundation Drawing- Compressor Shelter_IFR | 6 | 01-Jul-25 A | 12-Jul-25 A | 46407 | 46407
Design Calculation Report for Foundations- Compressor Shelter |  | 104 | 28-Jun-25 A | 21-Jan-26 A | 46407 | 46407
A49010 | Design Calculation Report for Foundations- Compressor Shelter_IFD/IFC | 2 | 19-Jan-26 A | 21-Jan-26 A | 46407 | 46407
A49000 | Design Calculation Report for Foundations- Compressor Shelter_RCA | 16 | 20-Aug-25 A | 05-Sep-25 A | 46407 | 46407
A48990 | Design Calculation Report for Foundations- Compressor Shelter_IFA | 3 | 25-Aug-25 A | 29-Aug-25 A | 46407 | 46407
A48980 | Design Calculation Report for Foundations- Compressor Shelter_RCC | 16 | 16-Jul-25 A | 22-Aug-25 A | 46407 | 46407
A48970 | Design Calculation Report for Foundations- Compressor Shelter_IFR | 6 | 28-Jun-25 A | 15-Jul-25 A | 46407 | 46407
Architectural Drawing- Substation, SIS Building |  | 218 | 05-Feb-25 A | 18-Sep-25 A | 46095 | 46095
A48410 | Architectural Drawing- Substation, SIS Building_IFD/IFC | 2 | 08-Sep-25 A | 18-Sep-25 A | 46095 | 46095
A48400 | Architectural Drawing- Substation, SIS Building_RCA | 16 | 20-Jun-25 A | 04-Sep-25 A | 46095 | 46095
A48390 | Architectural Drawing- Substation, SIS Building_IFA | 6 | 21-Apr-25 A | 19-Jun-25 A | 46095 | 46095
A17790 | Architectural Drawing- Substation, SIS Building_RCC | 16 | 12-Mar-25 A | 20-Apr-25 A | 46095 | 46095
A48380 | Architectural Drawing- Substation, SIS Building_IFR | 6 | 05-Feb-25 A | 11-Mar-25 A | 46095 | 46095
Structural Concrete GA, Section and Details- Substation, SIS Building |  | 80 | 21-Apr-25 A | 29-Aug-25 A | 46095 | 46095
A48460 | Structural Concrete GA, Section and Details- Substation, SIS Building_IFD/IFC | 2 | 22-Aug-25 A | 29-Aug-25 A | 46095 | 46095
A48450 | Structural Concrete GA, Section and Details- Substation, SIS Building_RCA | 16 | 07-Aug-25 A | 22-Aug-25 A | 46095 | 46095
A48440 | Structural Concrete GA, Section and Details- Substation, SIS Building_IFA | 6 | 04-Jun-25 A | 15-Aug-25 A | 46095 | 46095
A17880 | Structural Concrete GA, Section and Details- Substation, SIS Building_IFR | 17 | 21-Apr-25 A | 12-May-25 A | 46095 | 46095
A48430 | Structural Concrete GA, Section and Details- Substation, SIS Building_RCC | 16 | 13-May-25 A | 03-Jun-25 A | 46095 | 46095
Design Calculation report for Substation, SIS Building |  | 105 | 20-Apr-25 A | 29-Aug-25 A | 46095 | 46095
A48500 | Design Calculation report for Substation, SIS Building_IFD/IFC | 2 | 25-Aug-25 A | 29-Aug-25 A | 46095 | 46095
A48490 | Design Calculation report for Substation, SIS Building_RCA | 16 | 16-Jun-25 A | 22-Aug-25 A | 46095 | 46095
A48480 | Design Calculation report for Substation, SIS Building_IFA | 6 | 06-Jun-25 A | 15-Aug-25 A | 46095 | 46095
A48470 | Design Calculation report for Substation, SIS Building_IFR | 17 | 20-Apr-25 A | 11-May-25 A | 46095 | 46095
A17940 | Design Calculation report for Substation, SIS Building_RCC | 16 | 12-May-25 A | 05-Jun-25 A | 46095 | 46095
Foundation Layout, Section and Details- Substation, SIS Building |  | 107 | 21-Apr-25 A | 29-Aug-25 A | 46095 | 46095
A17870 | Foundation Layout, Section and Details- Substation, SIS Building_IFD/IFC | 2 | 25-Aug-25 A | 29-Aug-25 A | 46095 | 46095
A17860 | Foundation Layout, Section and Details- Substation, SIS Building_RCA | 16 | 23-Jun-25 A | 22-Aug-25 A | 46095 | 46095
A48420 | Foundation Layout, Section and Details- Substation, SIS Building_IFR | 17 | 21-Apr-25 A | 12-May-25 A | 46095 | 46095
A17850 | Foundation Layout, Section and Details- Substation, SIS Building_IFA | 6 | 30-May-25 A | 21-Jun-25 A | 46095 | 46095
A17840 | Foundation Layout, Section and Details- Substation, SIS Building_RCC | 16 | 13-May-25 A | 29-May-25 A | 46095 | 46095
Structure design - U/G facilities |  | 190 | 10-Jun-25 A | 2026-04-21 | 2026-03-19 | 2027-01-20 | 196
Sump Pit plan and details Accidentally Oil contaminated water collection 70-TD-1407 |  | 87 | 18-Aug-25 A | 23-Dec-25 A | 46148 | 46148
A49720 | Sump Pit plan and details Accidentally Oil contaminated water collection 70-TD-1407_IFD/IFC | 2 | 19-Dec-25 A | 23-Dec-25 A | 46148 | 46148
A49710 | Sump Pit plan and details Accidentally Oil contaminated water collection 70-TD-1407_RCA | 16 | 27-Aug-25 A | 09-Sep-25 A | 46148 | 46148
A20400 | Sump Pit plan and details Accidentally Oil contaminated water collection 70-TD-1407_IFA | 3 | 28-Aug-25 A | 02-Sep-25 A | 46148 | 46148
A20390 | Sump Pit plan and details Accidentally Oil contaminated water collection 70-TD-1407_RCC | 16 | 20-Aug-25 A | 27-Aug-25 A | 46148 | 46148
A20380 | Sump Pit plan and details Accidentally Oil contaminated water collection 70-TD-1407_IFR | 6 | 18-Aug-25 A | 22-Aug-25 A | 46148 | 46148
Design Calculation Report for Accidentally Oil contaminated water collection Sump Pit 70-TD-1407 |  | 86 | 23-Aug-25 A | 23-Dec-25 A | 46148 | 46148
A49740 | Design Calculation Report for Accidentally Oil contaminated water collection Sump Pit 70-TD-1407_IFD/IFC | 2 | 19-Dec-25 A | 23-Dec-25 A | 46148 | 46148
A20460 | Design Calculation Report for Accidentally Oil contaminated water collection Sump Pit 70-TD-1407_RCA | 16 | 25-Sep-25 A | 04-Oct-25 A | 46148 | 46148
A20450 | Design Calculation Report for Accidentally Oil contaminated water collection Sump Pit 70-TD-1407_IFA | 3 | 23-Sep-25 A | 29-Sep-25 A | 46148 | 46148
A20440 | Design Calculation Report for Accidentally Oil contaminated water collection Sump Pit 70-TD-1407_RCC | 16 | 29-Aug-25 A | 22-Sep-25 A | 46148 | 46148
A49730 | Design Calculation Report for Accidentally Oil contaminated water collection Sump Pit 70-TD-1407_IFR | 6 | 23-Aug-25 A | 13-Sep-25 A | 46148 | 46148
Sump Pit plan and details Oily Water 70-TD-1408 |  | 98 | 01-Aug-25 A | 13-Jan-26 A | 46148 | 46148
A20520 | Sump Pit plan and details Oily Water 70-TD-1408_IFD/IFC | 2 | 09-Jan-26 A | 13-Jan-26 A | 46148 | 46148
A20510 | Sump Pit plan and details Oily Water 70-TD-1408_RCA | 16 | 01-Sep-25 A | 09-Sep-25 A | 46148 | 46148
A20500 | Sump Pit plan and details Oily Water 70-TD-1408_IFA | 3 | 29-Aug-25 A | 02-Sep-25 A | 46148 | 46148
A49760 | Sump Pit plan and details Oily Water 70-TD-1408_RCC | 16 | 15-Aug-25 A | 26-Aug-25 A | 46148 | 46148
A49750 | Sump Pit plan and details Oily Water 70-TD-1408_IFR | 6 | 01-Aug-25 A | 22-Aug-25 A | 46148 | 46148
Design Calculation Report for Oily Water Sump Pit 70-TD-1408 |  | 102 | 23-Aug-25 A | 13-Jan-26 A | 46148 | 46148
A20570 | Design Calculation Report for Oily Water Sump Pit 70-TD-1408_IFD/IFC | 2 | 09-Jan-26 A | 13-Jan-26 A | 46148 | 46148
A20560 | Design Calculation Report for Oily Water Sump Pit 70-TD-1408_RCA | 16 | 19-Dec-25 A | 09-Jan-26 A | 46148 | 46148
A49790 | Design Calculation Report for Oily Water Sump Pit 70-TD-1408_IFA | 3 | 17-Oct-25 A | 23-Oct-25 A | 46148 | 46148
A49780 | Design Calculation Report for Oily Water Sump Pit 70-TD-1408_RCC | 16 | 15-Sep-25 A | 16-Oct-25 A | 46148 | 46148
A49770 | Design Calculation Report for Oily Water Sump Pit 70-TD-1408_IFR | 6 | 23-Aug-25 A | 13-Sep-25 A | 46148 | 46148
Sump Pit plan and details Sanitary Waste Water 70-TD-1409 |  | 82 | 23-Aug-25 A | 23-Dec-25 A | 46321 | 46321
A20620 | Sump Pit plan and details Sanitary Waste Water 70-TD-1409_IFD/IFC | 2 | 19-Dec-25 A | 23-Dec-25 A | 46321 | 46321
A49820 | Sump Pit plan and details Sanitary Waste Water 70-TD-1409_RCA | 16 | 29-Sep-25 A | 08-Oct-25 A | 46321 | 46321
A49810 | Sump Pit plan and details Sanitary Waste Water 70-TD-1409_IFA | 3 | 25-Sep-25 A | 01-Oct-25 A | 46321 | 46321
A49800 | Sump Pit plan and details Sanitary Waste Water 70-TD-1409_RCC | 16 | 01-Sep-25 A | 24-Sep-25 A | 46321 | 46321
A20580 | Sump Pit plan and details Sanitary Waste Water 70-TD-1409_IFR | 6 | 23-Aug-25 A | 13-Sep-25 A | 46321 | 46321
Design Calculation Report for Sanitary Waste Water Sump Pit 70-TD-1409 |  | 82 | 23-Aug-25 A | 23-Dec-25 A | 46321 | 46321
A49850 | Design Calculation Report for Sanitary Waste Water Sump Pit 70-TD-1409_IFD/IFC | 2 | 19-Dec-25 A | 23-Dec-25 A | 46321 | 46321
A49840 | Design Calculation Report for Sanitary Waste Water Sump Pit 70-TD-1409_RCA | 16 | 15-Oct-25 A | 24-Oct-25 A | 46321 | 46321
A49830 | Design Calculation Report for Sanitary Waste Water Sump Pit 70-TD-1409_IFA | 3 | 14-Oct-25 A | 20-Oct-25 A | 46321 | 46321
A20640 | Design Calculation Report for Sanitary Waste Water Sump Pit 70-TD-1409_RCC | 16 | 15-Sep-25 A | 13-Oct-25 A | 46321 | 46321
A20630 | Design Calculation Report for Sanitary Waste Water Sump Pit 70-TD-1409_IFR | 6 | 23-Aug-25 A | 13-Sep-25 A | 46321 | 46321
Transformer Foundation Drawing for Bay-A to Bay-E |  | 43 | 2026-02-20 | 2026-04-21 | 2026-11-23 | 2027-01-20 | 196
A49870 | Transformer Foundation Drawing for Bay-A to Bay-E_IFD/IFC | 2 | 2026-04-17 | 2026-04-21 | 2026-11-23 | 2026-11-30 | 196
A49860 | Transformer Foundation Drawing for Bay-A to Bay-E_RCA | 16 | 2026-03-26 | 2026-04-17 | 2026-11-30 | 2026-12-22 | 196
A20700 | Transformer Foundation Drawing for Bay-A to Bay-E_IFA | 3 | 2026-03-23 | 2026-03-26 | 2026-12-22 | 2026-12-25 | 196
A20690 | Transformer Foundation Drawing for Bay-A to Bay-E_RCC | 16 | 2026-02-27 | 2026-03-23 | 2026-12-28 | 2027-01-18 | 196
A20680 | Transformer Foundation Drawing for Bay-A to Bay-E_IFR | 6 | 2026-02-20 | 2026-02-27 | 2027-01-18 | 2027-01-20 | 196
Design Calculation Report for Foundation- Transformer for Bay-A to Bay-E |  | 43 | 2026-02-20 | 2026-04-21 | 2026-11-23 | 2027-01-20 | 196
A20770 | Design Calculation Report for Foundation- Transformer for Bay-A to Bay-E_IFD/IFC | 2 | 2026-04-17 | 2026-04-21 | 2026-11-23 | 2026-11-30 | 196
A20760 | Design Calculation Report for Foundation- Transformer for Bay-A to Bay-E_RCA | 16 | 2026-03-26 | 2026-04-17 | 2026-11-30 | 2026-12-22 | 196
A20750 | Design Calculation Report for Foundation- Transformer for Bay-A to Bay-E_IFA | 3 | 2026-03-23 | 2026-03-26 | 2026-12-22 | 2026-12-25 | 196
A49890 | Design Calculation Report for Foundation- Transformer for Bay-A to Bay-E_RCC | 16 | 2026-02-27 | 2026-03-23 | 2026-12-28 | 2027-01-18 | 196
A49880 | Design Calculation Report for Foundation- Transformer for Bay-A to Bay-E_IFR | 6 | 2026-02-20 | 2026-02-27 | 2027-01-18 | 2027-01-20 | 196
Firewater Valve Pit Plan, Section and Details |  | 42 | 01-Oct-25 A | 23-Dec-25 A | 46132 | 46132
A50160 | Firewater Valve Pit Plan, Section and Details_IFD/IFC | 2 | 19-Dec-25 A | 23-Dec-25 A | 46132 | 46132
A50150 | Firewater Valve Pit Plan, Section and Details_RCA | 16 | 28-Oct-25 A | 21-Nov-25 A | 46132 | 46132
A21400 | Firewater Valve Pit Plan, Section and Details_IFA | 3 | 20-Oct-25 A | 27-Oct-25 A | 46132 | 46132
A21390 | Firewater Valve Pit Plan, Section and Details_RCC | 16 | 06-Oct-25 A | 17-Oct-25 A | 46132 | 46132
A21380 | Firewater Valve Pit Plan, Section and Details_IFR | 6 | 01-Oct-25 A | 10-Oct-25 A | 46132 | 46132
Cooling water Valve Pit Plan, Section and Details |  | 55 | 01-Oct-25 A | 23-Dec-25 A | 46201 | 46201
A21460 | Cooling water Valve Pit Plan, Section and Details_RCA | 16 | 31-Oct-25 A | 21-Nov-25 A | 46201 | 46201
A50180 | Cooling water Valve Pit Plan, Section and Details_IFD/IFC | 2 | 19-Dec-25 A | 23-Dec-25 A | 46201 | 46201
A21450 | Cooling water Valve Pit Plan, Section and Details_IFA | 3 | 25-Oct-25 A | 20-Nov-25 A | 46201 | 46201
A21440 | Cooling water Valve Pit Plan, Section and Details_RCC | 16 | 11-Oct-25 A | 24-Oct-25 A | 46201 | 46201
A50170 | Cooling water Valve Pit Plan, Section and Details_IFR | 6 | 01-Oct-25 A | 10-Oct-25 A | 46201 | 46201
Underground Layout |  | 116 | 10-Jun-25 A | 22-Oct-25 A | 46100 | 46108
A21570 | Underground Layout_IFD/IFC | 2 | 14-Oct-25 A | 22-Oct-25 A | 46100 | 46100
A50240 | Underground Layout_RCA | 16 | 15-Sep-25 A | 10-Oct-25 A | 46100 | 46100
A50220 | Underground Layout_RCC | 16 | 18-Aug-25 A | 12-Sep-25 A | 46100 | 46100
A50230 | Underground Layout_IFA | 3 | 11-Aug-25 A | 15-Aug-25 A | 46108 | 46108
A50210 | Underground Layout_IFR | 6 | 10-Jun-25 A | 08-Jul-25 A | 46108 | 46108
Composite Underground drawing |  | 101 | 22-Sep-25 A | 2026-03-23 | 2026-03-19 | 2026-04-17 | 20
A50260 | Composite Underground drawing_IFD/IFC | 2 | 2026-03-19 | 2026-03-23 | 2026-03-19 | 2026-03-19 | 20
A50250 | Composite Underground drawing_RCA | 16 | 2026-02-25 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 20
A21600 | Composite Underground drawing_IFA | 3 | 2026-02-20 | 2026-02-25 | 2026-03-19 | 2026-03-24 | 20
A21590 | Composite Underground drawing_RCC | 16 | 24-Sep-25 A | 07-Oct-25 A | 46106 | 46127
A21580 | Composite Underground drawing_IFR | 6 | 22-Sep-25 A | 30-Sep-25 A | 46127 | 46129
Underground Trench Layout drawing and details |  | 61 | 01-Oct-25 A | 19-Jan-26 A | 46100 | 46123
A21670 | Underground Trench Layout drawing and details_IFD/IFC | 2 | 15-Jan-26 A | 19-Jan-26 A | 46100 | 46100
A21660 | Underground Trench Layout drawing and details_RCA | 16 | 24-Dec-25 A | 15-Jan-26 A | 46100 | 46100
A21650 | Underground Trench Layout drawing and details_IFA | 3 | 19-Dec-25 A | 24-Dec-25 A | 46100 | 46100
A50280 | Underground Trench Layout drawing and details_RCC | 16 | 10-Oct-25 A | 10-Nov-25 A | 46123 | 46123
A50270 | Underground Trench Layout drawing and details_IFR | 6 | 01-Oct-25 A | 09-Oct-25 A | 46123 | 46123
Design Calculation for Concrete Trenches and Duct Banks (If Required) |  | 66 | 19-Dec-25 A | 2026-03-23 | 2026-12-22 | 2027-01-20 | 218
A50320 | Design Calculation for Concrete Trenches and Duct Banks (If Required)_IFD/IFC | 2 | 2026-03-19 | 2026-03-23 | 2026-12-22 | 2026-12-22 | 218
A50310 | Design Calculation for Concrete Trenches and Duct Banks (If Required)_RCA | 16 | 2026-02-25 | 2026-03-19 | 2026-12-22 | 2026-12-22 | 218
A50300 | Design Calculation for Concrete Trenches and Duct Banks (If Required)_IFA | 3 | 2026-02-20 | 2026-02-25 | 2026-12-22 | 2026-12-25 | 218
A50290 | Design Calculation for Concrete Trenches and Duct Banks (If Required)_RCC | 16 | 26-Dec-25 A | 19-Jan-26 A | 46384 | 46405
A21680 | Design Calculation for Concrete Trenches and Duct Banks (If Required)_IFR | 6 | 19-Dec-25 A | 26-Dec-25 A | 46405 | 46407
Calculation for UG Hydraulics |  | 99 | 10-Jun-25 A | 23-Dec-25 A | 46407 | 46407
A50330 | Calculation for UG Hydraulics_IFD/IFC | 2 | 19-Dec-25 A | 23-Dec-25 A | 46407 | 46407
A21760 | Calculation for UG Hydraulics_RCA | 16 | 20-Aug-25 A | 29-Aug-25 A | 46407 | 46407
A21750 | Calculation for UG Hydraulics_IFA | 3 | 18-Aug-25 A | 22-Aug-25 A | 46407 | 46407
A21740 | Calculation for UG Hydraulics_RCC | 16 | 07-Jul-25 A | 15-Aug-25 A | 46407 | 46407
A21730 | Calculation for UG Hydraulics_IFR | 6 | 10-Jun-25 A | 04-Jul-25 A | 46407 | 46407
Other Civil deliverables |  | 485 | 16-Jan-25 A | 2026-04-21 | 2026-02-23 | 2027-01-20 | 196
General notes for Civil and Concrete Works |  | 112 | 30-Jan-25 A | 10-May-25 A | 46407 | 46407
A17220 | General notes for Civil and Concrete Works_IFD/IFC | 2 | 04-May-25 A | 10-May-25 A | 46407 | 46407
A17210 | General notes for Civil and Concrete Works_RCA | 16 | 27-Apr-25 A | 03-May-25 A | 46407 | 46407
A17200 | General notes for Civil and Concrete Works_IFA | 3 | 20-Apr-25 A | 26-Apr-25 A | 46407 | 46407
A17190 | General notes for Civil and Concrete Works_RCC | 16 | 21-Feb-25 A | 19-Apr-25 A | 46407 | 46407
A17180 | General notes for Civil and Concrete Works_IFR | 6 | 30-Jan-25 A | 20-Feb-25 A | 46407 | 46407
Standard details for stair and ladder foundation |  | 127 | 01-Jul-25 A | 08-Oct-25 A | 46356 | 46407
A17320 | Standard details for stair and ladder foundation_IFD/IFC | 2 | 02-Oct-25 A | 08-Oct-25 A | 46356 | 46356
A17310 | Standard details for stair and ladder foundation_RCA | 16 | 15-Sep-25 A | 01-Oct-25 A | 46407 | 46407
A17300 | Standard details for stair and ladder foundation_IFA | 3 | 18-Sep-25 A | 24-Sep-25 A | 46407 | 46407
A48280 | Standard details for stair and ladder foundation_RCC | 16 | 31-Jul-25 A | 17-Sep-25 A | 46407 | 46407
A17280 | Standard details for stair and ladder foundation_IFR | 6 | 01-Jul-25 A | 11-Jul-25 A | 46407 | 46407
Site Grading Layout |  | 42 | 03-Sep-25 A | 23-Dec-25 A | 46407 | 46407
A48310 | Site Grading Layout_IFD/IFC | 2 | 19-Dec-25 A | 23-Dec-25 A | 46407 | 46407
A17460 | Site Grading Layout_RCA | 16 | 07-Nov-25 A | 20-Nov-25 A | 46407 | 46407
A17450 | Site Grading Layout_IFA | 3 | 31-Oct-25 A | 06-Nov-25 A | 46407 | 46407
A17440 | Site Grading Layout_RCC | 16 | 06-Sep-25 A | 22-Sep-25 A | 46407 | 46407
A17430 | Site Grading Layout_IFR | 6 | 03-Sep-25 A | 15-Sep-25 A | 46407 | 46407
General notes for Structural steel Works |  | 95 | 16-Jan-25 A | 03-May-25 A | 46356 | 46407
A17270 | General notes for Structural steel Works_IFD/IFC | 2 | 27-Apr-25 A | 03-May-25 A | 46356 | 46356
A17260 | General notes for Structural steel Works_RCA | 16 | 20-Apr-25 A | 26-Apr-25 A | 46407 | 46407
A17250 | General notes for Structural steel Works_IFA | 3 | 14-Mar-25 A | 19-Apr-25 A | 46407 | 46407
A17240 | General notes for Structural steel Works_RCC | 16 | 21-Feb-25 A | 13-Mar-25 A | 46407 | 46407
A48270 | General notes for Structural steel Works_IFR | 6 | 16-Jan-25 A | 20-Feb-25 A | 46407 | 46407
Typical Road Details |  | 206 | 02-Jul-25 A | 2026-04-14 | 2026-11-30 | 2027-01-20 | 202
A17370 | Typical Road Details_IFD/IFC | 2 | 2026-04-09 | 2026-04-14 | 2026-11-30 | 2026-11-30 | 202
A17360 | Typical Road Details_RCA | 16 | 2026-03-19 | 2026-04-09 | 2026-11-30 | 2026-12-22 | 202
A48290 | Typical Road Details_IFA | 3 | 2026-03-13 | 2026-03-19 | 2026-12-22 | 2026-12-25 | 202
A17340 | Typical Road Details_RCC | 16 | 2026-02-20 | 2026-03-13 | 2026-12-28 | 2027-01-18 | 202
A17330 | Typical Road Details_IFR | 6 | 02-Jul-25 A | 09-Jul-25 A | 46405 | 46407
MTO for Civil Works |  | 299 | 05-May-25 A | 10-Jun-25 A | 46349 | 46407
A50770 | MTO for Civil Works_IFD/IFC | 2 | 08-Jun-25 A | 10-Jun-25 A | 46349 | 46349
A22440 | MTO for Civil Works_RCC | 16 | 19-May-25 A | 05-Jun-25 A | 46407 | 46407
A22430 | MTO for Civil Works_IFR | 11 | 05-May-25 A | 16-May-25 A | 46407 | 46407
MTO for Structural Steel |  | 21 | 25-Aug-25 A | 12-Sep-25 A | 46076 | 46227
A50790 | MTO for Structural Steel_RCC | 16 | 01-Sep-25 A | 05-Sep-25 A | 46076 | 46076
A50800 | MTO for Structural Steel_IFD/IFC | 2 | 08-Sep-25 A | 12-Sep-25 A | 46227 | 46227
A50780 | MTO for Structural Steel_IFR | 6 | 25-Aug-25 A | 29-Aug-25 A | 46227 | 46227
Tie-in Manhole modification drawing |  | 43 | 2026-02-20 | 2026-04-21 | 2026-11-23 | 2027-01-20 | 196
A50760 | Tie-in Manhole modification drawing_IFD/IFC | 2 | 2026-04-17 | 2026-04-21 | 2026-11-23 | 2026-11-30 | 196
A50750 | Tie-in Manhole modification drawing_RCA | 16 | 2026-03-26 | 2026-04-17 | 2026-11-30 | 2026-12-22 | 196
A50740 | Tie-in Manhole modification drawing_IFA | 3 | 2026-03-23 | 2026-03-26 | 2026-12-22 | 2026-12-25 | 196
A50730 | Tie-in Manhole modification drawing_RCC | 16 | 2026-02-27 | 2026-03-23 | 2026-12-28 | 2027-01-18 | 196
A22380 | Tie-in Manhole modification drawing_IFR | 6 | 2026-02-20 | 2026-02-27 | 2027-01-18 | 2027-01-20 | 196
Fence and Gate Layout |  | 199 | 01-May-25 A | 23-Jan-26 A | 46407 | 46407
A17420 | Fence and Gate Layout_IFD/IFC | 2 | 30-Dec-25 A | 23-Jan-26 A | 46407 | 46407
A17400 | Fence and Gate Layout_IFA | 3 | 18-Jun-25 A | 24-Jun-25 A | 46407 | 46407
A48300 | Fence and Gate Layout_RCA | 16 | 25-Jun-25 A | 16-Sep-25 A | 46407 | 46407
A17390 | Fence and Gate Layout_RCC | 16 | 23-May-25 A | 17-Jun-25 A | 46407 | 46407
A17380 | Fence and Gate Layout_IFR | 6 | 01-May-25 A | 22-May-25 A | 46407 | 46407
Road and Paving Layout |  | 45 | 02-Jun-25 A | 23-Jan-26 A | 46232 | 46232
A50190 | Road and Paving Layout_IFR | 6 | 02-Jun-25 A | 07-Jul-25 A | 46232 | 46232
A21520 | Road and Paving Layout_IFD/IFC | 2 | 19-Jan-26 A | 23-Jan-26 A | 46232 | 46232
A56280 | Road and Paving Layout_RCA | 16 | 15-Jan-26 A | 19-Jan-26 A | 46232 | 46232
A56270 | Road and Paving Layout_IFA | 3 | 09-Jan-26 A | 15-Jan-26 A | 46232 | 46232
A50200 | Road and Paving Layout_RCC | 16 | 19-Dec-25 A | 09-Jan-26 A | 46232 | 46232
Telecom |  | 352 | 30-Dec-24 A | 2026-04-21 | 2026-03-19 | 2027-01-20 | 196
Block Diagram For Process CCTV |  | 196 | 30-Dec-24 A | 19-Sep-25 A | 46100 | 46407
A51100 | Block Diagram For Process CCTV_IFD/IFC | 2 | 13-Sep-25 A | 19-Sep-25 A | 46100 | 46100
A51090 | Block Diagram For Process CCTV_RCA | 16 | 23-Apr-25 A | 12-Sep-25 A | 46407 | 46407
A51080 | Block Diagram For Process CCTV_IFA | 3 | 15-Feb-25 A | 22-Apr-25 A | 46407 | 46407
A51070 | Block Diagram For Process CCTV_RCC | 16 | 21-Jan-25 A | 14-Feb-25 A | 46407 | 46407
A51060 | Block Diagram For Process CCTV_IFR | 6 | 30-Dec-24 A | 20-Jan-25 A | 46407 | 46407
Block Diagram For PAGA |  | 221 | 30-Dec-24 A | 15-Oct-25 A | 46100 | 46407
A51150 | Block Diagram For PAGA_IFD/IFC | 2 | 15-Sep-25 A | 15-Oct-25 A | 46100 | 46100
A51140 | Block Diagram For PAGA_RCA | 16 | 23-Apr-25 A | 10-Sep-25 A | 46407 | 46407
A51130 | Block Diagram For PAGA_IFA | 3 | 15-Feb-25 A | 22-Apr-25 A | 46407 | 46407
A51120 | Block Diagram For PAGA_RCC | 16 | 21-Jan-25 A | 14-Feb-25 A | 46407 | 46407
A51110 | Block Diagram For PAGA_IFR | 6 | 30-Dec-24 A | 20-Jan-25 A | 46407 | 46407
Block Diagram For Digital Network And Telephone System |  | 216 | 01-Aug-25 A | 22-Oct-25 A | 46100 | 46407
A51200 | Block Diagram For Digital Network And Telephone System_IFD/IFC | 2 | 01-Oct-25 A | 22-Oct-25 A | 46100 | 46100
A51190 | Block Diagram For Digital Network And Telephone System_RCA | 16 | 25-Aug-25 A | 11-Sep-25 A | 46407 | 46407
A51180 | Block Diagram For Digital Network And Telephone System_IFA | 3 | 25-Aug-25 A | 29-Aug-25 A | 46407 | 46407
A51170 | Block Diagram For Digital Network And Telephone System_RCC | 16 | 04-Aug-25 A | 22-Aug-25 A | 46407 | 46407
A51160 | Block Diagram For Digital Network And Telephone System_IFR | 6 | 01-Aug-25 A | 15-Aug-25 A | 46407 | 46407
Block Diagram For Access Control System |  | 165 | 30-Dec-24 A | 19-Sep-25 A | 46100 | 46407
A51250 | Block Diagram For Access Control System_IFD/IFC | 2 | 22-Jun-25 A | 19-Sep-25 A | 46100 | 46100
A51240 | Block Diagram For Access Control System_RCA | 16 | 23-Apr-25 A | 21-Jun-25 A | 46407 | 46407
A51230 | Block Diagram For Access Control System_IFA | 3 | 15-Feb-25 A | 22-Apr-25 A | 46407 | 46407
A51220 | Block Diagram For Access Control System_RCC | 16 | 21-Jan-25 A | 14-Feb-25 A | 46407 | 46407
A51210 | Block Diagram For Access Control System_IFR | 6 | 30-Dec-24 A | 20-Jan-25 A | 46407 | 46407
Overall Telecom System Block Diagram |  | 290 | 25-Jan-25 A | 2026-02-24 | 2027-01-18 | 2027-01-20 | 237
A51300 | Overall Telecom System Block Diagram_IFD/IFC | 2 | 2026-02-20 | 2026-02-24 | 2027-01-18 | 2027-01-18 | 237
A51290 | Overall Telecom System Block Diagram_RCA | 16 | 22-Sep-25 A | 07-Oct-25 A | 46405 | 46405
A51280 | Overall Telecom System Block Diagram_IFA | 3 | 31-Jul-25 A | 23-Sep-25 A | 46405 | 46405
A51270 | Overall Telecom System Block Diagram_RCC | 16 | 01-Jul-25 A | 29-Jul-25 A | 46405 | 46405
A51260 | Overall Telecom System Block Diagram_IFR | 6 | 25-Jan-25 A | 27-Apr-25 A | 46405 | 46407
Telecom Tie-In Schedule |  | 206 | 13-Mar-25 A | 01-Sep-25 A | 46407 | 46407
A51830 | Telecom Tie-In Schedule_IFD/IFC | 2 | 26-Aug-25 A | 01-Sep-25 A | 46407 | 46407
A23660 | Telecom Tie-In Schedule_RCA | 16 | 12-May-25 A | 25-Aug-25 A | 46407 | 46407
A51820 | Telecom Tie-In Schedule_IFA | 3 | 05-May-25 A | 11-May-25 A | 46407 | 46407
A51810 | Telecom Tie-In Schedule_RCC | 16 | 28-Apr-25 A | 04-May-25 A | 46407 | 46407
A51800 | Telecom Tie-In Schedule_IFR | 11 | 13-Mar-25 A | 27-Apr-25 A | 46407 | 46407
Datasheet For Fiber Optic Cable |  | 116 | 30-Jan-25 A | 11-May-25 A | 46100 | 46407
A50850 | Datasheet For Fiber Optic Cable_IFD/IFC | 2 | 05-May-25 A | 11-May-25 A | 46100 | 46100
A50840 | Datasheet For Fiber Optic Cable_RCA | 16 | 28-Apr-25 A | 04-May-25 A | 46407 | 46407
A50830 | Datasheet For Fiber Optic Cable_IFA | 3 | 21-Apr-25 A | 27-Apr-25 A | 46407 | 46407
A50820 | Datasheet For Fiber Optic Cable_RCC | 16 | 21-Feb-25 A | 20-Apr-25 A | 46407 | 46407
A50810 | Datasheet For Fiber Optic Cable_IFR | 6 | 30-Jan-25 A | 20-Feb-25 A | 46407 | 46407
Datasheet For Process CCTV |  | 269 | 01-Aug-25 A | 19-Jan-26 A | 46100 | 46100
A50900 | Datasheet For Process CCTV_IFD/IFC | 2 | 15-Jan-26 A | 19-Jan-26 A | 46100 | 46100
A50890 | Datasheet For Process CCTV_RCA | 16 | 24-Dec-25 A | 15-Jan-26 A | 46100 | 46100
A50880 | Datasheet For Process CCTV_IFA | 3 | 19-Dec-25 A | 24-Dec-25 A | 46100 | 46100
A50870 | Datasheet For Process CCTV_RCC | 16 | 15-Sep-25 A | 15-Oct-25 A | 46100 | 46100
A50860 | Datasheet For Process CCTV_IFR | 6 | 01-Aug-25 A | 15-Aug-25 A | 46100 | 46100
Datasheet For PAGA |  | 250 | 10-Jan-25 A | 23-Dec-25 A | 46100 | 46100
A50950 | Datasheet For PAGA_IFD/IFC | 2 | 19-Dec-25 A | 23-Dec-25 A | 46100 | 46100
A50940 | Datasheet For PAGA_RCA | 16 | 01-Jun-25 A | 21-Jun-25 A | 46100 | 46100
A50930 | Datasheet For PAGA_IFA | 3 | 21-Apr-25 A | 30-May-25 A | 46100 | 46100
A50920 | Datasheet For PAGA_RCC | 16 | 21-Mar-25 A | 20-Apr-25 A | 46100 | 46100
A50910 | Datasheet For PAGA_IFR | 6 | 10-Jan-25 A | 20-Mar-25 A | 46100 | 46100
Datasheet For Access Control System |  | 245 | 15-Jan-25 A | 23-Dec-25 A | 46100 | 46100
A51000 | Datasheet For Access Control System_IFD/IFC | 2 | 19-Dec-25 A | 23-Dec-25 A | 46100 | 46100
A50990 | Datasheet For Access Control System_RCA | 16 | 10-Jun-25 A | 19-Sep-25 A | 46100 | 46100
A50980 | Datasheet For Access Control System_IFA | 3 | 05-May-25 A | 09-Jun-25 A | 46100 | 46100
A50970 | Datasheet For Access Control System_RCC | 16 | 28-Apr-25 A | 04-May-25 A | 46100 | 46100
A50960 | Datasheet For Access Control System_IFR | 6 | 15-Jan-25 A | 27-Apr-25 A | 46100 | 46100
Datasheet For Digital Network And Telephone System |  | 245 | 15-Jan-25 A | 23-Dec-25 A | 46100 | 46100
A51050 | Datasheet For Digital Network And Telephone System_IFD/IFC | 2 | 19-Dec-25 A | 23-Dec-25 A | 46100 | 46100
A51040 | Datasheet For Digital Network And Telephone System_RCA | 16 | 11-Jun-25 A | 28-Aug-25 A | 46100 | 46100
A51030 | Datasheet For Digital Network And Telephone System_IFA | 3 | 05-May-25 A | 10-Jun-25 A | 46100 | 46100
A51020 | Datasheet For Digital Network And Telephone System_RCC | 16 | 28-Apr-25 A | 04-May-25 A | 46100 | 46100
A51010 | Datasheet For Digital Network And Telephone System_IFR | 6 | 15-Jan-25 A | 27-Apr-25 A | 46100 | 46100
Wiring Diagram For Process Cctv |  | 261 | 08-Jan-25 A | 23-Dec-25 A | 46407 | 46407
A51350 | Wiring Diagram For Process Cctv_IFD/IFC | 2 | 19-Dec-25 A | 23-Dec-25 A | 46407 | 46407
A51340 | Wiring Diagram For Process Cctv_RCA | 16 | 04-Nov-25 A | 18-Nov-25 A | 46407 | 46407
A51330 | Wiring Diagram For Process Cctv_IFA | 3 | 27-Oct-25 A | 03-Nov-25 A | 46407 | 46407
A51320 | Wiring Diagram For Process Cctv_RCC | 16 | 13-Feb-25 A | 13-Mar-25 A | 46407 | 46407
A51310 | Wiring Diagram For Process Cctv_IFR | 6 | 08-Jan-25 A | 12-Feb-25 A | 46407 | 46407
Wiring Diagram For Paga |  | 275 | 09-Jan-25 A | 19-Jan-26 A | 46407 | 46407
A51400 | Wiring Diagram For Paga_IFD/IFC | 2 | 15-Jan-26 A | 19-Jan-26 A | 46407 | 46407
A51390 | Wiring Diagram For Paga_RCA | 16 | 24-Dec-25 A | 15-Jan-26 A | 46407 | 46407
A51380 | Wiring Diagram For Paga_IFA | 3 | 19-Dec-25 A | 24-Dec-25 A | 46407 | 46407
A51370 | Wiring Diagram For Paga_RCC | 16 | 13-Feb-25 A | 13-Mar-25 A | 46407 | 46407
A51360 | Wiring Diagram For Paga_IFR | 6 | 09-Jan-25 A | 12-Feb-25 A | 46407 | 46407
Wiring Diagram For Digital Network And Telephone System |  | 336 | 22-Jan-25 A | 2026-04-21 | 2026-11-23 | 2027-01-20 | 196
A51450 | Wiring Diagram For Digital Network And Telephone System_IFD/IFC | 2 | 2026-04-17 | 2026-04-21 | 2026-11-23 | 2026-11-30 | 196
A51440 | Wiring Diagram For Digital Network And Telephone System_RCA | 16 | 2026-03-26 | 2026-04-17 | 2026-11-30 | 2026-12-22 | 196
A51430 | Wiring Diagram For Digital Network And Telephone System_IFA | 3 | 2026-03-23 | 2026-03-26 | 2026-12-22 | 2026-12-25 | 196
A51420 | Wiring Diagram For Digital Network And Telephone System_RCC | 16 | 2026-02-27 | 2026-03-23 | 2026-12-28 | 2027-01-18 | 196
A51410 | Wiring Diagram For Digital Network And Telephone System_IFR | 6 | 22-Jan-25 A | 2026-02-27 | 2027-01-18 | 2027-01-20 | 196
Wiring Diagram For Access Control System |  | 331 | 22-Jan-25 A | 2026-04-21 | 2026-11-23 | 2027-01-20 | 196
A51500 | Wiring Diagram For Access Control System_IFD/IFC | 2 | 2026-04-17 | 2026-04-21 | 2026-11-23 | 2026-11-30 | 196
A51490 | Wiring Diagram For Access Control System_RCA | 16 | 2026-03-26 | 2026-04-17 | 2026-11-30 | 2026-12-22 | 196
A51480 | Wiring Diagram For Access Control System_IFA | 3 | 2026-03-23 | 2026-03-26 | 2026-12-22 | 2026-12-25 | 196
A51470 | Wiring Diagram For Access Control System_RCC | 16 | 2026-02-27 | 2026-03-23 | 2026-12-28 | 2027-01-18 | 196
A51460 | Wiring Diagram For Access Control System_IFR | 6 | 22-Jan-25 A | 2026-02-27 | 2027-01-18 | 2027-01-20 | 196
Material Requisitions For Telecom System (Paga, CCTV, ACS, Telephone & LAN System) |  | 263 | 14-Mar-25 A | 22-Jan-26 A | 46100 | 46100
A51910 | Material Requisitions For Telecom System (Paga, Cctv, Acs, Telephone & Lan System)_IFD/IFC | 2 | 20-Jan-26 A | 22-Jan-26 A | 46100 | 46100
A23810 | Material Requisitions For Telecom System (Paga, Cctv, Acs, Telephone & Lan System)_RCA | 16 | 29-Dec-25 A | 20-Jan-26 A | 46100 | 46100
A23800 | Material Requisitions For Telecom System (Paga, Cctv, Acs, Telephone & Lan System)_IFA | 3 | 24-Dec-25 A | 29-Dec-25 A | 46100 | 46100
A23790 | Material Requisitions For Telecom System (Paga, Cctv, Acs, Telephone & Lan System)_RCC | 16 | 01-Jul-25 A | 29-Jul-25 A | 46100 | 46100
A23780 | Material Requisitions For Telecom System (Paga, Cctv, Acs, Telephone & Lan System)_IFR | 6 | 14-Mar-25 A | 26-Apr-25 A | 46100 | 46100
Material Requisitions For Telecom Cables |  | 161 | 01-May-25 A | 23-Dec-25 A | 46349 | 46407
A23870 | Material Requisitions For Telecom Cables_IFD/IFC | 2 | 19-Dec-25 A | 23-Dec-25 A | 46349 | 46349
A23860 | Material Requisitions For Telecom Cables_RCA | 16 | 12-Nov-25 A | 21-Nov-25 A | 46407 | 46407
A51940 | Material Requisitions For Telecom Cables_IFA | 3 | 27-Oct-25 A | 11-Nov-25 A | 46407 | 46407
A51930 | Material Requisitions For Telecom Cables_RCC | 16 | 01-Jul-25 A | 29-Jul-25 A | 46407 | 46407
A51920 | Material Requisitions For Telecom Cables_IFR | 6 | 01-May-25 A | 22-May-25 A | 46407 | 46407
Telecom Equipment List |  | 220 | 10-Mar-25 A | 18-Dec-25 A | 46407 | 46407
A51790 | Telecom Equipment List_IFD/IFC | 2 | 04-Dec-25 A | 18-Dec-25 A | 46407 | 46407
A51780 | Telecom Equipment List_RCA | 16 | 10-Sep-25 A | 29-Sep-25 A | 46407 | 46407
A51770 | Telecom Equipment List_IFA | 3 | 25-Aug-25 A | 15-Sep-25 A | 46407 | 46407
A51760 | Telecom Equipment List_RCC | 16 | 28-Apr-25 A | 04-May-25 A | 46407 | 46407
A23580 | Telecom Equipment List_IFR | 6 | 10-Mar-25 A | 27-Apr-25 A | 46407 | 46407
Telecom Cable Schedule |  | 276 | 14-Apr-25 A | 2026-03-23 | 2026-12-22 | 2027-01-20 | 218
A51680 | Telecom Cable Schedule_IFD/IFC | 2 | 2026-03-19 | 2026-03-23 | 2026-12-22 | 2026-12-22 | 218
A51670 | Telecom Cable Schedule_RCA | 16 | 2026-02-25 | 2026-03-19 | 2026-12-22 | 2026-12-22 | 218
A51660 | Telecom Cable Schedule_IFA | 3 | 2026-02-20 | 2026-02-25 | 2026-12-22 | 2026-12-25 | 218
A51650 | Telecom Cable Schedule_RCC | 16 | 06-May-25 A | 29-Jul-25 A | 46384 | 46405
A51640 | Telecom Cable Schedule_IFR | 6 | 14-Apr-25 A | 05-May-25 A | 46405 | 46407
Telecom Junction Box Schedule |  | 143 | 01-Aug-25 A | 23-Dec-25 A | 46407 | 46407
A23520 | Telecom Junction Box Schedule_IFD/IFC | 2 | 19-Dec-25 A | 23-Dec-25 A | 46407 | 46407
A51720 | Telecom Junction Box Schedule_RCA | 16 | 12-Nov-25 A | 21-Nov-25 A | 46407 | 46407
A51710 | Telecom Junction Box Schedule_IFA | 3 | 03-Nov-25 A | 11-Nov-25 A | 46407 | 46407
A51700 | Telecom Junction Box Schedule_RCC | 16 | 04-Aug-25 A | 22-Aug-25 A | 46407 | 46407
A51690 | Telecom Junction Box Schedule_IFR | 6 | 01-Aug-25 A | 15-Aug-25 A | 46407 | 46407
Voltage Drop Calculation For Paga System |  | 43 | 2026-02-20 | 2026-04-21 | 2026-11-23 | 2027-01-20 | 196
A23570 | Voltage Drop Calculation For Paga System_IFD/IFC | 2 | 2026-04-17 | 2026-04-21 | 2026-11-23 | 2026-11-30 | 196
A51750 | Voltage Drop Calculation For Paga System_RCA | 16 | 2026-03-26 | 2026-04-17 | 2026-11-30 | 2026-12-22 | 196
A23550 | Voltage Drop Calculation For Paga System_IFA | 3 | 2026-03-23 | 2026-03-26 | 2026-12-22 | 2026-12-25 | 196
A51740 | Voltage Drop Calculation For Paga System_RCC | 16 | 2026-02-27 | 2026-03-23 | 2026-12-28 | 2027-01-18 | 196
A51730 | Voltage Drop Calculation For Paga System_IFR | 6 | 2026-02-20 | 2026-02-27 | 2027-01-18 | 2027-01-20 | 196
Technical Bid Evaluation For Telecom Cables |  | 43 | 2026-02-20 | 2026-04-21 | 2026-11-23 | 2027-01-20 | 196
A52020 | Technical Bid Evaluation For Telecom Cables_IFD/IFC | 2 | 2026-04-17 | 2026-04-21 | 2026-11-23 | 2026-11-30 | 196
A52010 | Technical Bid Evaluation For Telecom Cables_RCA | 16 | 2026-03-26 | 2026-04-17 | 2026-11-30 | 2026-12-22 | 196
A52000 | Technical Bid Evaluation For Telecom Cables_IFA | 3 | 2026-03-23 | 2026-03-26 | 2026-12-22 | 2026-12-25 | 196
A51990 | Technical Bid Evaluation For Telecom Cables_RCC | 16 | 2026-02-27 | 2026-03-23 | 2026-12-28 | 2027-01-18 | 196
A51980 | Technical Bid Evaluation For Telecom Cables_IFR | 6 | 2026-02-20 | 2026-02-27 | 2027-01-18 | 2027-01-20 | 196
Central Control Room Equipment Layout For Telecom |  | 193 | 01-Jul-25 A | 2026-03-17 | 2026-12-28 | 2027-01-20 | 221
A51880 | Central Control Room Equipment Layout For Telecom_IFD/IFC | 2 | 2026-03-13 | 2026-03-17 | 2026-12-28 | 2026-12-28 | 221
A51870 | Central Control Room Equipment Layout For Telecom_RCA | 16 | 2026-02-20 | 2026-03-13 | 2026-12-28 | 2026-12-28 | 221
A51860 | Central Control Room Equipment Layout For Telecom_IFA | 3 | 16-Sep-25 A | 29-Sep-25 A | 46384 | 46384
A51850 | Central Control Room Equipment Layout For Telecom_RCC | 16 | 15-Aug-25 A | 15-Sep-25 A | 46384 | 46405
A51840 | Central Control Room Equipment Layout For Telecom_IFR | 6 | 01-Jul-25 A | 13-Jul-25 A | 46405 | 46407
Telecommunication Core Allocation Drawing For Fiber Optic Cable |  | 78 | 15-Apr-25 A | 23-Jan-26 A | 46407 | 46407
A23770 | Telecommunication Core Allocation Drawing For Fiber Optic Cable_IFD/IFC | 2 | 23-Dec-25 A | 23-Jan-26 A | 46407 | 46407
A23760 | Telecommunication Core Allocation Drawing For Fiber Optic Cable_RCA | 16 | 10-Nov-25 A | 21-Nov-25 A | 46407 | 46407
A23750 | Telecommunication Core Allocation Drawing For Fiber Optic Cable_IFA | 3 | 03-Nov-25 A | 11-Nov-25 A | 46407 | 46407
A51900 | Telecommunication Core Allocation Drawing For Fiber Optic Cable_RCC | 16 | 29-Apr-25 A | 21-Jul-25 A | 46407 | 46407
A51890 | Telecommunication Core Allocation Drawing For Fiber Optic Cable_IFR | 6 | 15-Apr-25 A | 28-Apr-25 A | 46407 | 46407
Overall Telecom Cable Routing Layout Drawing For H2 Extraction Unit |  | 78 | 01-May-25 A | 23-Jan-26 A | 46349 | 46407
A51600 | Overall Telecom Cable Routing Layout Drawing For H2 Extraction Unit_IFD/IFC | 2 | 10-Jan-26 A | 23-Jan-26 A | 46349 | 46349
A51590 | Overall Telecom Cable Routing Layout Drawing For H2 Extraction Unit_RCA | 16 | 06-Jan-26 A | 14-Jan-26 A | 46407 | 46407
A51580 | Overall Telecom Cable Routing Layout Drawing For H2 Extraction Unit_IFA | 3 | 25-Dec-25 A | 06-Jan-26 A | 46407 | 46407
A51570 | Overall Telecom Cable Routing Layout Drawing For H2 Extraction Unit_RCC | 16 | 19-Dec-25 A | 25-Dec-25 A | 46407 | 46407
A51560 | Overall Telecom Cable Routing Layout Drawing For H2 Extraction Unit_IFR | 11 | 01-May-25 A | 08-May-25 A | 46407 | 46407
Overall Telecom Equipment Layout Drawing For H2 Extraction Unit |  | 98 | 01-May-25 A | 16-Jan-26 A | 46349 | 46407
A51550 | Overall Telecom Equipment Layout Drawing For H2 Extraction Unit_IFD/IFC | 2 | 31-Dec-25 A | 16-Jan-26 A | 46349 | 46349
A51540 | Overall Telecom Equipment Layout Drawing For H2 Extraction Unit_RCA | 16 | 17-Oct-25 A | 01-Nov-25 A | 46378 | 46378
A51530 | Overall Telecom Equipment Layout Drawing For H2 Extraction Unit_IFA | 3 | 10-Oct-25 A | 16-Oct-25 A | 46378 | 46378
A51520 | Overall Telecom Equipment Layout Drawing For H2 Extraction Unit_RCC | 16 | 21-May-25 A | 04-Jun-25 A | 46407 | 46407
A51510 | Overall Telecom Equipment Layout Drawing For H2 Extraction Unit_IFR | 11 | 01-May-25 A | 20-May-25 A | 46407 | 46407
Telecom System Material Take Off |  | 116 | 02-Jul-25 A | 23-Dec-25 A | 46407 | 46407
A51630 | Telecom System Material Take Off_IFD/IFC | 2 | 19-Dec-25 A | 23-Dec-25 A | 46407 | 46407
A51620 | Telecom System Material Take Off_RCC | 16 | 07-Jul-25 A | 29-Jul-25 A | 46407 | 46407
A51610 | Telecom System Material Take Off_IFR | 6 | 02-Jul-25 A | 18-Jul-25 A | 46407 | 46407
Material/Corrosion |  | 320 | 15-Apr-25 A | 2026-03-23 | 2026-12-22 | 2027-01-20 | 218
Material Selection & Corrosion Control Report |  | 320 | 15-Apr-25 A | 2026-03-23 | 2026-12-22 | 2027-01-20 | 218
A52090 | Material Selection & Corrosion Control Report_IFD/IFC | 2 | 2026-03-19 | 2026-03-23 | 2026-12-22 | 2026-12-22 | 218
A52080 | Material Selection & Corrosion Control Report_RCA | 16 | 2026-02-25 | 2026-03-19 | 2026-12-22 | 2026-12-22 | 218
A24050 | Material Selection & Corrosion Control Report_IFA | 3 | 2026-02-20 | 2026-02-25 | 2026-12-22 | 2026-12-25 | 218
A24040 | Material Selection & Corrosion Control Report_RCC | 16 | 08-May-25 A | 03-Jun-25 A | 46384 | 46405
A52070 | Material Selection & Corrosion Control Report_IFR | 6 | 15-Apr-25 A | 07-May-25 A | 46405 | 46407
Material Selection Diagrams (MSD) |  | 311 | 16-Apr-25 A | 2026-03-17 | 2026-12-28 | 2027-01-20 | 221
A24020 | Material Selection Diagrams (MSD)_IFD/IFC | 2 | 2026-03-13 | 2026-03-17 | 2026-12-28 | 2026-12-28 | 221
A52060 | Material Selection Diagrams (MSD)_RCA | 16 | 2026-02-20 | 2026-03-13 | 2026-12-28 | 2026-12-28 | 221
A52050 | Material Selection Diagrams (MSD)_IFA | 3 | 29-Nov-25 A | 18-Dec-25 A | 46384 | 46384
A52040 | Material Selection Diagrams (MSD)_RCC | 16 | 25-Jul-25 A | 01-Aug-25 A | 46384 | 46405
A52030 | Material Selection Diagrams (MSD)_IFR | 6 | 16-Apr-25 A | 25-Jul-25 A | 46405 | 46407
HVAC |  | 342 | 13-Mar-25 A | 2026-04-21 | 2026-03-19 | 2027-01-20 | 196
HVAC Design Basis |  | 137 | 13-Mar-25 A | 24-May-25 A | 46407 | 46407
A52130 | HVAC Design Basis_RCA | 16 | 11-May-25 A | 18-May-25 A | 46407 | 46407
A52140 | HVAC Design Basis_IFD/IFC | 2 | 19-May-25 A | 24-May-25 A | 46407 | 46407
A52120 | HVAC Design Basis_IFA | 3 | 04-May-25 A | 10-May-25 A | 46407 | 46407
A52110 | HVAC Design Basis_RCC | 16 | 27-Apr-25 A | 03-May-25 A | 46407 | 46407
A52100 | HVAC Design Basis_IFR | 6 | 13-Mar-25 A | 26-Apr-25 A | 46407 | 46407
HVAC Equipment And Accessories Specifications |  | 133 | 23-Mar-25 A | 19-May-25 A | 46407 | 46407
A52190 | HVAC Equipment And Accessories Specifications_IFD/IFC | 2 | 13-May-25 A | 19-May-25 A | 46407 | 46407
A52180 | HVAC Equipment And Accessories Specifications_RCA | 16 | 06-May-25 A | 12-May-25 A | 46407 | 46407
A52170 | HVAC Equipment And Accessories Specifications_IFA | 3 | 23-Apr-25 A | 05-May-25 A | 46407 | 46407
A52160 | HVAC Equipment And Accessories Specifications_RCC | 16 | 14-Apr-25 A | 22-Apr-25 A | 46407 | 46407
A52150 | HVAC Equipment And Accessories Specifications_IFR | 6 | 23-Mar-25 A | 13-Apr-25 A | 46407 | 46407
HVAC Cooling Load Calculation And Equipment Sizing |  | 66 | 20-Apr-25 A | 03-Jun-25 A | 46100 | 46100
A24220 | HVAC Cooling Load Calculation And Equipment Sizing_IFD/IFC | 2 | 01-Jun-25 A | 03-Jun-25 A | 46100 | 46100
A24210 | HVAC Cooling Load Calculation And Equipment Sizing_RCA | 16 | 26-May-25 A | 31-May-25 A | 46100 | 46100
A52220 | HVAC Cooling Load Calculation And Equipment Sizing_IFA | 3 | 23-May-25 A | 25-May-25 A | 46100 | 46100
A52210 | HVAC Cooling Load Calculation And Equipment Sizing_RCC | 16 | 12-May-25 A | 18-May-25 A | 46100 | 46100
A52200 | HVAC Cooling Load Calculation And Equipment Sizing_IFR | 11 | 20-Apr-25 A | 11-May-25 A | 46100 | 46100
HVAC Airflow Schematic Diagrams |  | 67 | 25-Apr-25 A | 25-Oct-25 A | 46328 | 46407
A52580 | HVAC Airflow Schematic Diagrams_IFD/IFC | 2 | 21-Oct-25 A | 25-Oct-25 A | 46328 | 46328
A52570 | HVAC Airflow Schematic Diagrams_RCA | 16 | 30-Sep-25 A | 20-Oct-25 A | 46407 | 46407
A52560 | HVAC Airflow Schematic Diagrams_IFA | 3 | 29-Sep-25 A | 07-Oct-25 A | 46407 | 46407
A52550 | HVAC Airflow Schematic Diagrams_RCC | 16 | 15-Jul-25 A | 01-Aug-25 A | 46407 | 46407
A52540 | HVAC Airflow Schematic Diagrams_IFR | 6 | 25-Apr-25 A | 16-May-25 A | 46407 | 46407
HVAC Chilled Water Piping Schematic Diagrams |  | 189 | 20-Jun-25 A | 2026-04-14 | 2026-11-02 | 2027-01-20 | 202
A52630 | HVAC Chilled Water Piping Schematic Diagrams_IFD/IFC | 2 | 2026-04-09 | 2026-04-14 | 2026-11-02 | 2026-11-02 | 202
A52620 | HVAC Chilled Water Piping Schematic Diagrams_RCA | 16 | 2026-03-19 | 2026-04-09 | 2026-11-30 | 2026-12-22 | 202
A52610 | HVAC Chilled Water Piping Schematic Diagrams_IFA | 3 | 2026-03-13 | 2026-03-19 | 2026-12-22 | 2026-12-25 | 202
A52600 | HVAC Chilled Water Piping Schematic Diagrams_RCC | 16 | 2026-02-20 | 2026-03-13 | 2026-12-28 | 2027-01-18 | 202
A52590 | HVAC Chilled Water Piping Schematic Diagrams_IFR | 2 | 20-Jun-25 A | 05-Jul-25 A | 46405 | 46407
HVAC Chilled Water Piping And Instrumentation Diagrams |  | 169 | 02-Jun-25 A | 2026-02-24 | 2026-11-02 | 2027-01-20 | 237
A52880 | HVAC Chilled Water Piping And Instrumentation Diagrams_IFD/IFC | 2 | 2026-02-20 | 2026-02-24 | 2026-11-02 | 2026-11-02 | 237
A52870 | HVAC Chilled Water Piping And Instrumentation Diagrams_RCA | 16 | 25-Aug-25 A | 07-Oct-25 A | 46405 | 46405
A52860 | HVAC Chilled Water Piping And Instrumentation Diagrams_IFH | 3 | 15-Aug-25 A | 22-Aug-25 A | 46405 | 46405
A52850 | HVAC Chilled Water Piping And Instrumentation Diagrams_RCC | 16 | 11-Jul-25 A | 15-Aug-25 A | 46405 | 46405
A52840 | HVAC Chilled Water Piping And Instrumentation Diagrams_IFR | 6 | 02-Jun-25 A | 05-Jul-25 A | 46405 | 46407
HVAC Ducting and Instrumentation Diagrams |  | 114 | 17-Jun-25 A | 14-Oct-25 A | 46328 | 46407
A52830 | HVAC Ducting and Instrumentation Diagrams_IFD/IFC | 2 | 08-Oct-25 A | 14-Oct-25 A | 46328 | 46328
A52820 | HVAC Ducting and Instrumentation Diagrams_RCA | 16 | 29-Aug-25 A | 07-Oct-25 A | 46407 | 46407
A52810 | HVAC Ducting and Instrumentation Diagrams_IFH | 3 | 18-Aug-25 A | 22-Aug-25 A | 46407 | 46407
A52800 | HVAC Ducting and Instrumentation Diagrams_RCC | 16 | 09-Jul-25 A | 15-Aug-25 A | 46407 | 46407
A52790 | HVAC Ducting and Instrumentation Diagrams_IFR | 6 | 17-Jun-25 A | 08-Jul-25 A | 46407 | 46407
HVAC Equipment Schedules |  | 131 | 09-Jun-25 A | 2026-03-23 | 2026-12-22 | 2027-01-20 | 218
A52930 | HVAC Equipment Schedules_IFD/IFC | 2 | 2026-03-19 | 2026-03-23 | 2026-12-22 | 2026-12-22 | 218
A52920 | HVAC Equipment Schedules_RCA | 16 | 2026-02-25 | 2026-03-19 | 2026-12-22 | 2026-12-22 | 218
A52910 | HVAC Equipment Schedules_IFA | 3 | 2026-02-20 | 2026-02-25 | 2026-12-22 | 2026-12-25 | 218
A52900 | HVAC Equipment Schedules_RCC | 16 | 17-Jun-25 A | 19-Jul-25 A | 46384 | 46405
A52890 | HVAC Equipment Schedules_IFR | 6 | 09-Jun-25 A | 12-Jul-25 A | 46405 | 46407
HVAC System Cause & Effect |  | 38 | 21-Nov-25 A | 13-Jan-26 A | 46407 | 46407
A53030 | HVAC System Cause & Effect_IFD/IFC | 2 | 09-Jan-26 A | 13-Jan-26 A | 46407 | 46407
A53020 | HVAC System Cause & Effect_RCA | 16 | 19-Dec-25 A | 09-Jan-26 A | 46407 | 46407
A53010 | HVAC System Cause & Effect_IFA | 3 | 18-Dec-25 A | 19-Dec-25 A | 46407 | 46407
A53000 | HVAC System Cause & Effect_RCC | 16 | 27-Nov-25 A | 18-Dec-25 A | 46407 | 46407
A52990 | HVAC System Cause & Effect_IFR | 6 | 21-Nov-25 A | 28-Nov-25 A | 46407 | 46407
HVAC Chilled Water Pump Head Calculation |  | 61 | 01-Oct-25 A | 10-Nov-25 A | 46407 | 46407
A53130 | HVAC Chilled Water Pump Head Calculation_IFD/IFC | 2 | 01-Nov-25 A | 10-Nov-25 A | 46407 | 46407
A53120 | HVAC Chilled Water Pump Head Calculation_RCA | 16 | 28-Oct-25 A | 31-Oct-25 A | 46407 | 46407
A53110 | HVAC Chilled Water Pump Head Calculation_IFA | 3 | 24-Oct-25 A | 28-Oct-25 A | 46407 | 46407
A53100 | HVAC Chilled Water Pump Head Calculation_RCC | 16 | 14-Oct-25 A | 25-Oct-25 A | 46407 | 46407
A53090 | HVAC Chilled Water Pump Head Calculation_IFR | 6 | 01-Oct-25 A | 13-Oct-25 A | 46407 | 46407
HVAC Technical Data Sheet For Air Handling Unit |  | 102 | 01-May-25 A | 10-Oct-25 A | 46100 | 46100
A52280 | HVAC Technical Data Sheet For Air Handling Unit_IFD/IFC | 2 | 15-Sep-25 A | 10-Oct-25 A | 46100 | 46100
A52270 | HVAC Technical Data Sheet For Air Handling Unit_RCA | 16 | 27-Jun-25 A | 10-Sep-25 A | 46100 | 46100
A52260 | HVAC Technical Data Sheet For Air Handling Unit_IFA | 3 | 11-Jun-25 A | 26-Jun-25 A | 46100 | 46100
A52250 | HVAC Technical Data Sheet For Air Handling Unit_RCC | 16 | 23-May-25 A | 10-Jun-25 A | 46100 | 46100
A52240 | HVAC Technical Data Sheet For Air Handling Unit_IFR | 2 | 01-May-25 A | 22-May-25 A | 46100 | 46100
HVAC Technical Data Sheet For Air Cooled Chiller |  | 53 | 26-May-25 A | 10-Jun-25 A | 46100 | 46100
A52230 | HVAC Technical Data Sheet For Air Cooled Chiller_IFD/IFC | 2 | 08-Jun-25 A | 10-Jun-25 A | 46100 | 46100
A24260 | HVAC Technical Data Sheet For Air Cooled Chiller_RCA | 16 | 05-Jun-25 A | 07-Jun-25 A | 46100 | 46100
A24250 | HVAC Technical Data Sheet For Air Cooled Chiller_IFA | 3 | 01-Jun-25 A | 04-Jun-25 A | 46100 | 46100
A24240 | HVAC Technical Data Sheet For Air Cooled Chiller_RCC | 16 | 29-May-25 A | 31-May-25 A | 46100 | 46100
A24230 | HVAC Technical Data Sheet For Air Cooled Chiller_IFR | 2 | 26-May-25 A | 28-May-25 A | 46100 | 46100
HVAC Technical Data Sheet For Chilled Water Pump |  | 84 | 26-May-25 A | 10-Oct-25 A | 46100 | 46100
A52330 | HVAC Technical Data Sheet For Chilled Water Pump_IFD/IFC | 2 | 15-Sep-25 A | 10-Oct-25 A | 46100 | 46100
A52320 | HVAC Technical Data Sheet For Chilled Water Pump_RCA | 16 | 28-Aug-25 A | 10-Sep-25 A | 46100 | 46100
A52310 | HVAC Technical Data Sheet For Chilled Water Pump_IFA | 3 | 02-Aug-25 A | 27-Aug-25 A | 46100 | 46100
A52300 | HVAC Technical Data Sheet For Chilled Water Pump_RCC | 16 | 06-Jul-25 A | 01-Aug-25 A | 46100 | 46100
A52290 | HVAC Technical Data Sheet For Chilled Water Pump_IFR | 2 | 26-May-25 A | 05-Jul-25 A | 46100 | 46100
HVAC Technical Data Sheet For Chemical Filter Unit |  | 82 | 26-May-25 A | 10-Oct-25 A | 46100 | 46100
A52380 | HVAC Technical Data Sheet For Chemical Filter Unit_IFD/IFC | 2 | 15-Sep-25 A | 10-Oct-25 A | 46100 | 46100
A52370 | HVAC Technical Data Sheet For Chemical Filter Unit_RCA | 16 | 30-Aug-25 A | 12-Sep-25 A | 46100 | 46100
A52360 | HVAC Technical Data Sheet For Chemical Filter Unit_IFA | 3 | 02-Aug-25 A | 29-Aug-25 A | 46100 | 46100
A52350 | HVAC Technical Data Sheet For Chemical Filter Unit_RCC | 16 | 06-Jul-25 A | 01-Aug-25 A | 46100 | 46100
A52340 | HVAC Technical Data Sheet For Chemical Filter Unit_IFR | 2 | 26-May-25 A | 05-Jul-25 A | 46100 | 46100
HVAC Technical Data Sheet For Inertia Filter With Bleed Fan |  | 100 | 26-May-25 A | 21-Nov-25 A | 46100 | 46100
A52430 | HVAC Technical Data Sheet For Inertia Filter With Bleed Fan_IFD/IFC | 2 | 17-Nov-25 A | 21-Nov-25 A | 46100 | 46100
A52420 | HVAC Technical Data Sheet For Inertia Filter With Bleed Fan_RCA | 16 | 23-Aug-25 A | 10-Sep-25 A | 46100 | 46100
A52410 | HVAC Technical Data Sheet For Inertia Filter With Bleed Fan_IFA | 3 | 31-Jul-25 A | 22-Aug-25 A | 46100 | 46100
A52400 | HVAC Technical Data Sheet For Inertia Filter With Bleed Fan_RCC | 16 | 06-Jul-25 A | 30-Jul-25 A | 46100 | 46100
A52390 | HVAC Technical Data Sheet For Inertia Filter With Bleed Fan_IFR | 2 | 26-May-25 A | 05-Jul-25 A | 46100 | 46100
HVAC Technical Data Sheet For Exhaust Air Fans |  | 65 | 26-May-25 A | 15-Sep-25 A | 46100 | 46100
A52480 | HVAC Technical Data Sheet For Exhaust Air Fans_IFD/IFC | 2 | 09-Sep-25 A | 15-Sep-25 A | 46100 | 46100
A52470 | HVAC Technical Data Sheet For Exhaust Air Fans_RCA | 16 | 02-Sep-25 A | 08-Sep-25 A | 46100 | 46100
A52460 | HVAC Technical Data Sheet For Exhaust Air Fans_IFA | 3 | 02-Aug-25 A | 01-Sep-25 A | 46100 | 46100
A52450 | HVAC Technical Data Sheet For Exhaust Air Fans_RCC | 16 | 06-Jul-25 A | 01-Aug-25 A | 46100 | 46100
A52440 | HVAC Technical Data Sheet For Exhaust Air Fans_IFR | 2 | 26-May-25 A | 05-Jul-25 A | 46100 | 46100
HVAC Technical Data Sheet For Electric Duct Heater |  | 46 | 26-May-25 A | 15-Sep-25 A | 46100 | 46100
A52530 | HVAC Technical Data Sheet For Electric Duct Heater_IFD/IFC | 2 | 09-Sep-25 A | 15-Sep-25 A | 46100 | 46100
A52520 | HVAC Technical Data Sheet For Electric Duct Heater_RCA | 16 | 21-Jun-25 A | 08-Sep-25 A | 46100 | 46100
A52500 | HVAC Technical Data Sheet For Electric Duct Heater_RCC | 16 | 02-Jun-25 A | 15-Jun-25 A | 46100 | 46100
A52510 | HVAC Technical Data Sheet For Electric Duct Heater_IFA | 3 | 16-Jun-25 A | 20-Jun-25 A | 46100 | 46100
A52490 | HVAC Technical Data Sheet For Electric Duct Heater_IFR | 2 | 26-May-25 A | 01-Jun-25 A | 46100 | 46100
HVAC Chilled Water Piping Layouts & Sections |  | 101 | 10-Jul-25 A | 13-Jan-26 A | 46407 | 46407
A52780 | HVAC Chilled Water Piping Layouts & Sections_IFD/IFC | 2 | 09-Jan-26 A | 13-Jan-26 A | 46407 | 46407
A52770 | HVAC Chilled Water Piping Layouts & Sections_RCA | 16 | 19-Dec-25 A | 09-Jan-26 A | 46407 | 46407
A52750 | HVAC Chilled Water Piping Layouts & Sections_RCC | 16 | 08-Oct-25 A | 31-Oct-25 A | 46407 | 46407
A52760 | HVAC Chilled Water Piping Layouts & Sections_IFA | 3 | 28-Nov-25 A | 10-Dec-25 A | 46407 | 46407
A52740 | HVAC Chilled Water Piping Layouts & Sections_IFR | 6 | 10-Jul-25 A | 07-Oct-25 A | 46407 | 46407
HVAC System Sequence Of Operation And Control Philosophy |  | 110 | 01-Jul-25 A | 04-Dec-25 A | 46407 | 46407
A52970 | HVAC System Sequence Of Operation And Control Philosophy_RCA | 16 | 29-Oct-25 A | 17-Nov-25 A | 46407 | 46407
A52960 | HVAC System Sequence Of Operation And Control Philosophy_IFA | 3 | 01-Oct-25 A | 28-Oct-25 A | 46407 | 46407
A52950 | HVAC System Sequence Of Operation And Control Philosophy_RCC | 16 | 17-Jul-25 A | 22-Aug-25 A | 46407 | 46407
A52980 | HVAC System Sequence Of Operation And Control Philosophy_IFD/IFC | 2 | 24-Nov-25 A | 04-Dec-25 A | 46407 | 46407
A52940 | HVAC System Sequence Of Operation And Control Philosophy_IFR | 6 | 01-Jul-25 A | 16-Jul-25 A | 46407 | 46407
Material Requisition For HVAC Equipments |  | 97 | 02-Jun-25 A | 19-Nov-25 A | 46100 | 46100
A53230 | Material Requisition For HVAC Equipments_IFD/IFC | 2 | 27-Oct-25 A | 19-Nov-25 A | 46100 | 46100
A53220 | Material Requisition For HVAC Equipments_RCA | 16 | 01-Oct-25 A | 24-Oct-25 A | 46100 | 46100
A53200 | Material Requisition For HVAC Equipments_RCC | 16 | 04-Jul-25 A | 30-Jul-25 A | 46100 | 46100
A53210 | Material Requisition For HVAC Equipments_IFA | 3 | 29-Aug-25 A | 01-Oct-25 A | 46100 | 46100
A53190 | Material Requisition For HVAC Equipments_IFR | 6 | 02-Jun-25 A | 05-Jul-25 A | 46100 | 46100
Material Requisition for Fire Detection System & LFCP |  | 137 | 09-Jun-25 A | 25-Dec-25 A | 46100 | 46100
A15420 | Material Requisition for Fire Detection System & LFCP_IFD/IFC | 2 | 23-Dec-25 A | 25-Dec-25 A | 46100 | 46100
A47810 | Material Requisition for Fire Detection System & LFCP_RCA | 16 | 15-Aug-25 A | 10-Sep-25 A | 46100 | 46100
A47790 | Material Requisition for Fire Detection System & LFCP_RCC | 16 | 07-Jul-25 A | 30-Jul-25 A | 46100 | 46100
A47780 | Material Requisition for Fire Detection System & LFCP_IFR | 2 | 09-Jun-25 A | 05-Jul-25 A | 46100 | 46100
A47800 | Material Requisition for Fire Detection System & LFCP_IFA | 3 | 31-Jul-25 A | 26-Aug-25 A | 46100 | 46100
HVAC Equipment And Ducting Layouts |  | 94 | 29-Jun-25 A | 18-Dec-25 A | 46328 | 46328
A52670 | HVAC Equipment And Ducting Layouts_RCA | 16 | 27-Oct-25 A | 21-Nov-25 A | 46328 | 46328
A52660 | HVAC Equipment And Ducting Layouts_IFA | 3 | 01-Oct-25 A | 24-Oct-25 A | 46328 | 46328
A52680 | HVAC Equipment And Ducting Layouts_IFD/IFC | 2 | 02-Dec-25 A | 18-Dec-25 A | 46328 | 46328
A52650 | HVAC Equipment And Ducting Layouts_RCC | 16 | 01-Aug-25 A | 14-Oct-25 A | 46328 | 46328
A52640 | HVAC Equipment And Ducting Layouts_IFR | 6 | 29-Jun-25 A | 18-Jul-25 A | 46328 | 46328
HVAC Ducting Section Layout |  | 95 | 03-Aug-25 A | 23-Dec-25 A | 46407 | 46407
A52730 | HVAC Ducting Section Layout_IFD/IFC | 2 | 19-Dec-25 A | 23-Dec-25 A | 46407 | 46407
A52720 | HVAC Ducting Section Layout_RCA | 16 | 15-Sep-25 A | 14-Oct-25 A | 46407 | 46407
A52710 | HVAC Ducting Section Layout_IFA | 3 | 25-Aug-25 A | 26-Sep-25 A | 46407 | 46407
A52700 | HVAC Ducting Section Layout_RCC | 16 | 19-Aug-25 A | 22-Aug-25 A | 46407 | 46407
A52690 | HVAC Ducting Section Layout_IFR | 6 | 03-Aug-25 A | 18-Aug-25 A | 46407 | 46407
HVAC External Static Pressure Calculation |  | 43 | 2026-02-20 | 2026-04-21 | 2026-11-23 | 2027-01-20 | 196
A53080 | HVAC External Static Pressure Calculation_IFD/IFC | 2 | 2026-04-17 | 2026-04-21 | 2026-11-23 | 2026-11-30 | 196
A53070 | HVAC External Static Pressure Calculation_RCA | 16 | 2026-03-26 | 2026-04-17 | 2026-11-30 | 2026-12-22 | 196
A53060 | HVAC External Static Pressure Calculation_IFA | 3 | 2026-03-23 | 2026-03-26 | 2026-12-22 | 2026-12-25 | 196
A53050 | HVAC External Static Pressure Calculation_RCC | 16 | 2026-02-27 | 2026-03-23 | 2026-12-28 | 2027-01-18 | 196
A53040 | HVAC External Static Pressure Calculation_IFR | 6 | 2026-02-20 | 2026-02-27 | 2027-01-18 | 2027-01-20 | 196
HVAC Standard Installation Details |  | 121 | 25-Apr-25 A | 07-Oct-25 A | 46407 | 46407
A53180 | HVAC Standard Installation Details_IFD/IFC | 2 | 30-Jul-25 A | 07-Oct-25 A | 46407 | 46407
A53170 | HVAC Standard Installation Details_RCA | 16 | 13-Jun-25 A | 30-Jun-25 A | 46407 | 46407
A53160 | HVAC Standard Installation Details_IFA | 3 | 11-Jun-25 A | 20-Jun-25 A | 46407 | 46407
A53150 | HVAC Standard Installation Details_RCC | 16 | 17-May-25 A | 10-Jun-25 A | 46407 | 46407
A53140 | HVAC Standard Installation Details_IFR | 6 | 25-Apr-25 A | 16-May-25 A | 46407 | 46407
Technical Bid Evaluation for Fire Detection System & LFCP |  | 61 | 01-Oct-25 A | 19-Jan-26 A | 46100 | 46407
A16970 | Technical Bid Evaluation for Fire Detection System & LFCP_IFD/IFC | 2 | 15-Jan-26 A | 19-Jan-26 A | 46100 | 46100
A16960 | Technical Bid Evaluation for Fire Detection System & LFCP_RCA | 16 | 24-Dec-25 A | 15-Jan-26 A | 46100 | 46100
A16950 | Technical Bid Evaluation for Fire Detection System & LFCP_IFA | 3 | 19-Dec-25 A | 24-Dec-25 A | 46100 | 46100
A16940 | Technical Bid Evaluation for Fire Detection System & LFCP_RCC | 11 | 20-Oct-25 A | 06-Nov-25 A | 46407 | 46407
A48260 | Technical Bid Evaluation for Fire Detection System & LFCP_IFR | 6 | 01-Oct-25 A | 09-Oct-25 A | 46407 | 46407
Procurement - HO Services |  | 399 | 01-Jan-25 A | 2026-07-24 | 2026-02-23 | 2027-07-20 | 257
Equipment Packages |  | 210 | 01-Jan-25 A | 15-Oct-25 A | 46100 | 46218
Vessels |  | 210 | 01-Jan-25 A | 20-Jun-25 A | 46100 | 46218
C4 Guard Adsorber Cooler - (BF) |  | 68 | 01-Jan-25 A | 20-Jun-25 A | 46100 | 46218
A57230 | Technical Bid Evaluation for Pressure Vessels & Internals_IFD/IFC | 11 | 15-Jun-25 A | 20-Jun-25 A | 46100 | 46100
A57220 | Technical Bid Evaluation for Pressure Vessels & Internals_RCA | 16 | 09-Jun-25 A | 14-Jun-25 A | 46100 | 46100
A57210 | Technical Bid Evaluation for Pressure Vessels & Internals_IFA | 3 | 04-Jun-25 A | 08-Jun-25 A | 46100 | 46100
A57200 | Technical Bid Evaluation for Pressure Vessels & Internals_RCC | 16 | 04-May-25 A | 03-Jun-25 A | 46100 | 46100
A8340 | Issue Purchase Order to Vendor | 30 | 20-Jun-25 A | 20-Jun-25 A | 46218 | 46218
A57190 | Technical Bid Evaluation for Pressure Vessels & Internals_IFR | 6 | 28-Apr-25 A | 03-May-25 A | 46218 | 46218
A8310 | Issue RFQ to Bidders | 20 | 01-Jan-25 A | 14-Jan-25 A | 46218 | 46218
Vessel's Internals (05 Dimister pads) |  | 106 | 01-Jan-25 A | 20-Jun-25 A | 46100 | 46156
A18040 | Commercial Bid Evaluation(Completion) | 30 | 15-Jun-25 A | 20-Jun-25 A | 46100 | 46100
A56580 | Technical Bid Evaluation for Pressure Vessels & Internals_IFD/IFC | 8 | 09-Jun-25 A | 14-Jun-25 A | 46100 | 46100
A56570 | Technical Bid Evaluation for Pressure Vessels & Internals_RCA | 16 | 09-Jun-25 A | 14-Jun-25 A | 46100 | 46100
A18020 | Issue Purchase Order to Vendor | 21 | 20-Jun-25 A | 20-Jun-25 A | 46100 | 46100
A56560 | Technical Bid Evaluation for Pressure Vessels & Internals_IFA | 11 | 04-Jun-25 A | 08-Jun-25 A | 46156 | 46156
A56550 | Technical Bid Evaluation for Pressure Vessels & Internals_RCC | 16 | 04-May-25 A | 03-Jun-25 A | 46156 | 46156
A56540 | Technical Bid Evaluation for Pressure Vessels & Internals_IFR | 11 | 28-Apr-25 A | 03-May-25 A | 46156 | 46156
A15970 | Issue RFQ to Bidders | 20 | 01-Jan-25 A | 14-Jan-25 A | 46156 | 46156
Vessels/Drums |  | 124 | 01-Jan-25 A | 20-Jun-25 A | 46100 | 46168
FG Comp. 2nd Stage Suc. Drum (13-VV-706) |  | 104 | 01-Jan-25 A | 20-Jun-25 A | 46100 | 46129
A35930 | Issue Purchase Order to Vendor | 10 | 20-Jun-25 A | 20-Jun-25 A | 46100 | 46100
A35920 | Commercial Bid Evaluation(Completion) | 21 | 15-Jun-25 A | 20-Jun-25 A | 46100 | 46100
A46000 | Technical Bid Evaluation for Pressure Vessels & Internals_IFD/IFC | 8 | 31-Mar-25 A | 01-Apr-25 A | 46100 | 46100
A45990 | Technical Bid Evaluation for Pressure Vessels & Internals_RCA | 16 | 30-Mar-25 A | 31-Mar-25 A | 46129 | 46129
A45980 | Technical Bid Evaluation for Pressure Vessels & Internals_IFA | 11 | 28-Mar-25 A | 29-Mar-25 A | 46129 | 46129
A45970 | Technical Bid Evaluation for Pressure Vessels & Internals_RCC | 16 | 25-Mar-25 A | 27-Mar-25 A | 46100 | 46100
A45960 | Technical Bid Evaluation for Pressure Vessels & Internals_IFR | 11 | 28-Apr-25 A | 03-May-25 A | 46129 | 46129
A35900 | Issue RFQ to Bidders | 15 | 01-Jan-25 A | 14-Jan-25 A | 46129 | 46129
FG Comp.1st Stage Suc. Drum (13-VV-705) |  | 104 | 01-Jan-25 A | 07-Apr-25 A | 46100 | 46129
A9200 | Issue Purchase Order to Vendor | 10 | 04-Apr-25 A | 07-Apr-25 A | 46100 | 46100
A9220 | Commercial Bid Evaluation(Completion) | 21 | 03-Apr-25 A | 04-Apr-25 A | 46100 | 46100
A56330 | Technical Bid Evaluation for Pressure Vessels & Internals_IFD/IFC | 8 | 01-Apr-25 A | 02-Apr-25 A | 46100 | 46100
A56320 | Technical Bid Evaluation for Pressure Vessels & Internals_RCA | 16 | 30-Mar-25 A | 31-Mar-25 A | 46100 | 46100
A56310 | Technical Bid Evaluation for Pressure Vessels & Internals_IFA | 11 | 28-Mar-25 A | 29-Mar-25 A | 46129 | 46129
A56300 | Technical Bid Evaluation for Pressure Vessels & Internals_RCC | 16 | 25-Mar-25 A | 27-Mar-25 A | 46129 | 46129
A56290 | Technical Bid Evaluation for Pressure Vessels & Internals_IFR | 11 | 23-Mar-25 A | 24-Mar-25 A | 46129 | 46129
A17540 | Issue RFQ to Bidders | 15 | 01-Jan-25 A | 14-Jan-25 A | 46129 | 46129
PSA2 Slop Drum (70-VV-1415) |  | 124 | 01-Jan-25 A | 12-Apr-25 A | 46100 | 46168
A35970 | Issue Purchase Order to Vendor | 21 | 04-Apr-25 A | 12-Apr-25 A | 46100 | 46100
A35960 | Commercial Bid Evaluation(Completion) | 30 | 02-Apr-25 A | 03-Apr-25 A | 46100 | 46100
A56380 | Technical Bid Evaluation for Pressure Vessels & Internals_IFD/IFC | 8 | 31-Mar-25 A | 01-Apr-25 A | 46100 | 46100
A56370 | Technical Bid Evaluation for Pressure Vessels & Internals_RCA | 16 | 30-Mar-25 A | 31-Mar-25 A | 46100 | 46100
A56360 | Technical Bid Evaluation for Pressure Vessels & Internals_IFA | 11 | 28-Mar-25 A | 29-Mar-25 A | 46168 | 46168
A56350 | Technical Bid Evaluation for Pressure Vessels & Internals_RCC | 16 | 25-Mar-25 A | 27-Mar-25 A | 46168 | 46168
A56340 | Technical Bid Evaluation for Pressure Vessels & Internals_IFR | 11 | 23-Mar-25 A | 24-Mar-25 A | 46168 | 46168
A35940 | Issue RFQ to Bidders | 15 | 01-Jan-25 A | 14-Jan-25 A | 46168 | 46168
OG Comp. 2nd Stage Suc. Drum (13-VV-713) |  | 97 | 01-Jan-25 A | 12-Apr-25 A | 46100 | 46134
A36010 | Issue Purchase Order to Vendor | 10 | 04-Apr-25 A | 12-Apr-25 A | 46100 | 46100
A36000 | Commercial Bid Evaluation(Completion) | 14 | 02-Apr-25 A | 03-Apr-25 A | 46100 | 46100
A56430 | Technical Bid Evaluation for Pressure Vessels & Internals_IFD/IFC | 8 | 31-Mar-25 A | 01-Apr-25 A | 46100 | 46100
A56420 | Technical Bid Evaluation for Pressure Vessels & Internals_RCA | 16 | 30-Mar-25 A | 31-Mar-25 A | 46100 | 46100
A56410 | Technical Bid Evaluation for Pressure Vessels & Internals_IFA | 11 | 28-Mar-25 A | 29-Mar-25 A | 46134 | 46134
A56400 | Technical Bid Evaluation for Pressure Vessels & Internals_RCC | 16 | 25-Mar-25 A | 27-Mar-25 A | 46134 | 46134
A56390 | Technical Bid Evaluation for Pressure Vessels & Internals_IFR | 11 | 23-Mar-25 A | 24-Mar-25 A | 46134 | 46134
A35980 | Issue RFQ to Bidders | 15 | 01-Jan-25 A | 14-Jan-25 A | 46134 | 46134
FG Comp. 2nd Stage Dis. Drum (13-VV-707) |  | 100 | 01-Jan-25 A | 12-Apr-25 A | 46100 | 46128
A36050 | Issue Purchase Order to Vendor | 14 | 04-Apr-25 A | 12-Apr-25 A | 46100 | 46100
A36040 | Commercial Bid Evaluation(Completion) | 14 | 02-Apr-25 A | 03-Apr-25 A | 46100 | 46100
A56480 | Technical Bid Evaluation for Pressure Vessels & Internals_IFD/IFC | 8 | 31-Mar-25 A | 01-Apr-25 A | 46100 | 46100
A56470 | Technical Bid Evaluation for Pressure Vessels & Internals_RCA | 16 | 30-Mar-25 A | 31-Mar-25 A | 46100 | 46100
A56460 | Technical Bid Evaluation for Pressure Vessels & Internals_IFA | 11 | 28-Mar-25 A | 29-Mar-25 A | 46128 | 46128
A56450 | Technical Bid Evaluation for Pressure Vessels & Internals_RCC | 16 | 25-Mar-25 A | 27-Mar-25 A | 46128 | 46128
A56440 | Technical Bid Evaluation for Pressure Vessels & Internals_IFR | 11 | 23-Mar-25 A | 24-Mar-25 A | 46128 | 46128
A36020 | Issue RFQ to Bidders | 14 | 01-Jan-25 A | 14-Jan-25 A | 46128 | 46128
OG Buffer Drum (13-VV-712) |  | 108 | 01-Jan-25 A | 12-Apr-25 A | 46100 | 46168
A36090 | Issue Purchase Order to Vendor | 14 | 04-Apr-25 A | 12-Apr-25 A | 46100 | 46100
A36080 | Commercial Bid Evaluation(Completion) | 21 | 02-Apr-25 A | 03-Apr-25 A | 46100 | 46100
A56530 | Technical Bid Evaluation for Pressure Vessels & Internals_IFD/IFC | 8 | 31-Mar-25 A | 01-Apr-25 A | 46100 | 46100
A56520 | Technical Bid Evaluation for Pressure Vessels & Internals_RCA | 16 | 30-Mar-25 A | 31-Mar-25 A | 46100 | 46100
A56510 | Technical Bid Evaluation for Pressure Vessels & Internals_IFA | 11 | 28-Mar-25 A | 29-Mar-25 A | 46168 | 46168
A56500 | Technical Bid Evaluation for Pressure Vessels & Internals_RCC | 16 | 25-Mar-25 A | 27-Mar-25 A | 46168 | 46168
A56490 | Technical Bid Evaluation for Pressure Vessels & Internals_IFR | 11 | 23-Mar-25 A | 24-Mar-25 A | 46168 | 46168
A36060 | Issue RFQ to Bidders | 15 | 01-Jan-25 A | 22-Mar-25 A | 46168 | 46168
Water Collection & Sanitary Wastewater Pumps |  | 85 | 01-Apr-25 A | 15-Oct-25 A | 46168 | 46168
Sanitary Waste Water Sump Pump |  | 83 | 01-Apr-25 A | 15-Oct-25 A | 46168 | 46168
A19470 | Issue Purchase Order to Vendor | 3 | 15-Sep-25 A | 17-Sep-25 A | 46168 | 46168
A19490 | Commercial Bid Evaluation(Completion) | 3 | 08-Sep-25 A | 12-Sep-25 A | 46168 | 46168
A45850 | Technical Bid Evaluation for Centrifugal Pump_IFD/IFC | 3 | 01-Sep-25 A | 15-Oct-25 A | 46168 | 46168
A45830 | Technical Bid Evaluation for Centrifugal Pump_IFA | 7 | 04-Jul-25 A | 23-Aug-25 A | 46168 | 46168
A45840 | Technical Bid Evaluation for Centrifugal Pump_RCA | 3 | 24-Aug-25 A | 30-Aug-25 A | 46168 | 46168
A8430 | RFQs to Bid Receipt | 21 | 01-Apr-25 A | 10-Apr-25 A | 46168 | 46168
A45820 | Technical Bid Evaluation for Centrifugal Pump_RCC | 3 | 13-Jun-25 A | 18-Jun-25 A | 46168 | 46168
A45810 | Technical Bid Evaluation for Centrifugal Pump_IFR | 3 | 10-Jun-25 A | 12-Jun-25 A | 46168 | 46168
Water Collection Sump Pump ll |  | 37 | 01-Apr-25 A | 05-Aug-25 A | 46168 | 46168
A19410 | Issue Purchase Order to Vendor | 3 | 30-Jul-25 A | 05-Aug-25 A | 46168 | 46168
A19430 | Commercial Bid Evaluation(Completion) | 3 | 18-Jul-25 A | 29-Jul-25 A | 46168 | 46168
A56930 | Technical Bid Evaluation for Centrifugal Pump_IFD/IFC | 3 | 30-Jun-25 A | 03-Jul-25 A | 46168 | 46168
A8490 | RFQs to Bid Receipt | 21 | 01-Apr-25 A | 10-Apr-25 A | 46168 | 46168
A56920 | Technical Bid Evaluation for Centrifugal Pump_RCA | 3 | 24-Jun-25 A | 29-Jun-25 A | 46168 | 46168
A56910 | Technical Bid Evaluation for Centrifugal Pump_IFA | 3 | 19-Jun-25 A | 23-Jun-25 A | 46168 | 46168
A56900 | Technical Bid Evaluation for Centrifugal Pump_RCC | 5 | 13-Jun-25 A | 18-Jun-25 A | 46168 | 46168
A56890 | Technical Bid Evaluation for Centrifugal Pump_IFR | 3 | 10-Jun-25 A | 12-Jun-25 A | 46168 | 46168
EOT Cranes |  | 124 | 01-May-25 A | 18-Sep-25 A | 46100 | 46140
EOT Crane for FG Compressor (1 = 60 Ton) |  | 92 | 01-May-25 A | 13-Aug-25 A | 46100 | 46133
A20470 | Issue Purchase Order to Vendor | 10 | 07-Aug-25 A | 13-Aug-25 A | 46100 | 46100
A20490 | Commercial Bid Evaluation(Completion) | 3 | 23-Jul-25 A | 06-Aug-25 A | 46100 | 46100
A45900 | Technical Bid Evaluation for EOT Crane_IFD/IFC | 6 | 13-Jul-25 A | 22-Jul-25 A | 46100 | 46100
A45890 | Technical Bid Evaluation for EOT Crane_RCA | 6 | 06-Jul-25 A | 12-Jul-25 A | 46100 | 46100
A45880 | Technical Bid Evaluation for EOT Crane_IFA | 6 | 30-Jun-25 A | 06-Jul-25 A | 46133 | 46133
A45870 | Technical Bid Evaluation for EOT Crane_RCC | 5 | 25-Jun-25 A | 30-Jun-25 A | 46133 | 46133
A45860 | Technical Bid Evaluation for EOT Crane_IFR | 11 | 20-Jun-25 A | 24-Jun-25 A | 46133 | 46133
A8370 | Issue RFQ to Bidders | 21 | 01-May-25 A | 15-May-25 A | 46133 | 46133
EOT Crane for OG Compressor (1 = 25 Ton) |  | 98 | 01-May-25 A | 18-Sep-25 A | 46100 | 46140
A20530 | Issue Purchase Order to Vendor | 10 | 17-Sep-25 A | 18-Sep-25 A | 46100 | 46100
A20550 | Commercial Bid Evaluation(Completion) | 3 | 15-Sep-25 A | 17-Sep-25 A | 46100 | 46100
A56980 | Technical Bid Evaluation for EOT Crane_IFD/IFC | 6 | 01-Sep-25 A | 12-Sep-25 A | 46100 | 46100
A56970 | Technical Bid Evaluation for EOT Crane_RCA | 6 | 01-Sep-25 A | 05-Sep-25 A | 46100 | 46100
A56960 | Technical Bid Evaluation for EOT Crane_IFA | 6 | 23-Aug-25 A | 30-Aug-25 A | 46140 | 46140
A56950 | Technical Bid Evaluation for EOT Crane_RCC | 5 | 16-Aug-25 A | 22-Aug-25 A | 46140 | 46140
A56940 | Technical Bid Evaluation for EOT Crane_IFR | 11 | 20-Jun-25 A | 15-Aug-25 A | 46140 | 46140
A8250 | Issue RFQ to Bidders | 21 | 01-May-25 A | 20-Jun-25 A | 46140 | 46140
Heat Exchangers |  | 36 | 01-Jun-25 A | 02-Jul-25 A | 46156 | 46168
Heat Exchanger (Type S & T = 06 Nos) |  | 36 | 01-Jun-25 A | 02-Jul-25 A | 46156 | 46168
FG Comp. Interstage Cooler (BEM) - Tag# 13-HE-703 |  | 26 | 01-Jun-25 A | 27-Jun-25 A | 46156 | 46156
A36120 | Commercial Bid Evaluation(Completion) | 6 | 20-Jun-25 A | 24-Jun-25 A | 46156 | 46156
A45500 | Technical Bid Evaluation for Heat Exchangers_IFD/IFC | 3 | 18-Jun-25 A | 20-Jun-25 A | 46156 | 46156
A45490 | Technical Bid Evaluation for Heat Exchangers_RCA | 6 | 15-Jun-25 A | 17-Jun-25 A | 46156 | 46156
A45470 | Technical Bid Evaluation for Heat Exchangers_RCC | 5 | 08-Jun-25 A | 11-Jun-25 A | 46156 | 46156
A45460 | Technical Bid Evaluation for Heat Exchangers_IFR | 6 | 04-Jun-25 A | 07-Jun-25 A | 46156 | 46156
A36130 | Issue Purchase Order to Vendor | 3 | 25-Jun-25 A | 27-Jun-25 A | 46156 | 46156
A36100 | Issue RFQ to Bidders | 6 | 01-Jun-25 A | 03-Jun-25 A | 46156 | 46156
A45480 | Technical Bid Evaluation for Heat Exchangers_IFA | 6 | 12-Jun-25 A | 14-Jun-25 A | 46156 | 46156
OG Comp. After Cooler (BEU) - Tag# 13-HE-709 |  | 36 | 01-Jun-25 A | 27-Jun-25 A | 46168 | 46168
A56660 | Technical Bid Evaluation for Heat Exchangers_IFA | 6 | 12-Jun-25 A | 14-Jun-25 A | 46168 | 46168
A56650 | Technical Bid Evaluation for Heat Exchangers_RCC | 5 | 08-Jun-25 A | 11-Jun-25 A | 46168 | 46168
A56640 | Technical Bid Evaluation for Heat Exchangers_IFR | 6 | 04-Jun-25 A | 07-Jun-25 A | 46168 | 46168
A36160 | Commercial Bid Evaluation(Completion) | 6 | 20-Jun-25 A | 24-Jun-25 A | 46168 | 46168
A36140 | Issue RFQ to Bidders | 21 | 01-Jun-25 A | 03-Jun-25 A | 46168 | 46168
A56680 | Technical Bid Evaluation for Heat Exchangers_IFD/IFC | 3 | 18-Jun-25 A | 20-Jun-25 A | 46168 | 46168
A56670 | Technical Bid Evaluation for Heat Exchangers_RCA | 6 | 15-Jun-25 A | 17-Jun-25 A | 46168 | 46168
A36170 | Issue Purchase Order to Vendor | 3 | 25-Jun-25 A | 27-Jun-25 A | 46168 | 46168
FG Comp. After Cooler (BEM) - Tag# 13-HE-704 |  | 35 | 01-Jun-25 A | 27-Jun-25 A | 46159 | 46159
A56710 | Technical Bid Evaluation for Heat Exchangers_IFA | 6 | 12-Jun-25 A | 14-Jun-25 A | 46159 | 46159
A56700 | Technical Bid Evaluation for Heat Exchangers_RCC | 5 | 08-Jun-25 A | 11-Jun-25 A | 46159 | 46159
A36970 | Commercial Bid Evaluation(Completion) | 6 | 20-Jun-25 A | 24-Jun-25 A | 46159 | 46159
A56690 | Technical Bid Evaluation for Heat Exchangers_IFR | 6 | 04-Jun-25 A | 07-Jun-25 A | 46159 | 46159
A56730 | Technical Bid Evaluation for Heat Exchangers_IFD/IFC | 3 | 18-Jun-25 A | 20-Jun-25 A | 46159 | 46159
A36950 | Issue RFQ to Bidders | 20 | 01-Jun-25 A | 03-Jun-25 A | 46159 | 46159
A56720 | Technical Bid Evaluation for Heat Exchangers_RCA | 6 | 15-Jun-25 A | 17-Jun-25 A | 46159 | 46159
A36980 | Issue Purchase Order to Vendor | 3 | 25-Jun-25 A | 27-Jun-25 A | 46159 | 46159
OG Comp. Interstage Cooler (BEU) (13-HE-708) |  | 36 | 01-Jun-25 A | 27-Jun-25 A | 46168 | 46168
A56760 | Technical Bid Evaluation for Heat Exchangers_IFA | 6 | 12-Jun-25 A | 14-Jun-25 A | 46168 | 46168
A56750 | Technical Bid Evaluation for Heat Exchangers_RCC | 5 | 08-Jun-25 A | 11-Jun-25 A | 46168 | 46168
A56740 | Technical Bid Evaluation for Heat Exchangers_IFR | 6 | 04-Jun-25 A | 07-Jun-25 A | 46168 | 46168
A37010 | Commercial Bid Evaluation(Completion) | 6 | 20-Jun-25 A | 24-Jun-25 A | 46168 | 46168
A36990 | Issue RFQ to Bidders | 21 | 01-Jun-25 A | 03-Jun-25 A | 46168 | 46168
A56780 | Technical Bid Evaluation for Heat Exchangers_IFD/IFC | 3 | 18-Jun-25 A | 20-Jun-25 A | 46168 | 46168
A56770 | Technical Bid Evaluation for Heat Exchangers_RCA | 6 | 15-Jun-25 A | 17-Jun-25 A | 46168 | 46168
A37020 | Issue Purchase Order to Vendor | 3 | 25-Jun-25 A | 27-Jun-25 A | 46168 | 46168
C4 Guard Regen. Gas Cooler (BEU) (Tag#50-HE-1410) |  | 36 | 01-Jun-25 A | 02-Jul-25 A | 46168 | 46168
A56810 | Technical Bid Evaluation for Heat Exchangers_IFA | 6 | 12-Jun-25 A | 14-Jun-25 A | 46168 | 46168
A56800 | Technical Bid Evaluation for Heat Exchangers_RCC | 5 | 08-Jun-25 A | 11-Jun-25 A | 46168 | 46168
A56790 | Technical Bid Evaluation for Heat Exchangers_IFR | 6 | 04-Jun-25 A | 07-Jun-25 A | 46168 | 46168
A37030 | Issue RFQ to Bidders | 21 | 01-Jun-25 A | 03-Jun-25 A | 46168 | 46168
A56830 | Technical Bid Evaluation for Heat Exchangers_IFD/IFC | 3 | 18-Jun-25 A | 20-Jun-25 A | 46168 | 46168
A56820 | Technical Bid Evaluation for Heat Exchangers_RCA | 6 | 15-Jun-25 A | 17-Jun-25 A | 46168 | 46168
A37060 | Issue Purchase Order to Vendor | 3 | 30-Jun-25 A | 02-Jul-25 A | 46168 | 46168
A37050 | Commercial Bid Evaluation(Completion) | 3 | 20-Jun-25 A | 27-Jun-25 A | 46168 | 46168
HVAC |  | 66 | 25-May-25 A | 29-Aug-25 A | 46188 | 46188
HVAC |  | 66 | 25-May-25 A | 29-Aug-25 A | 46188 | 46188
A19870 | Issue Purchase Order to Vendor | 1 | 20-Aug-25 A | 29-Aug-25 A | 46188 | 46188
A16510 | Issue RFQ to Bidders | 20 | 25-May-25 A | 03-Jun-25 A | 46188 | 46188
A19890 | Commercial Bid Evaluation(Completion) | 1 | 15-Jul-25 A | 31-Jul-25 A | 46188 | 46188
A25290 | Technical Bid Evaluation For HVAC Equipments_RCC | 1 | 20-Jun-25 A | 25-Jun-25 A | 46188 | 46188
A53240 | Technical Bid Evaluation For HVAC Equipments_IFR | 11 | 04-Jun-25 A | 19-Jun-25 A | 46188 | 46188
A25320 | Technical Bid Evaluation For HVAC Equipments_IFD/IFC | 5 | 09-Jul-25 A | 14-Jul-25 A | 46188 | 46188
A25310 | Technical Bid Evaluation For HVAC Equipments_RCA | 5 | 03-Jul-25 A | 08-Jul-25 A | 46188 | 46188
A25300 | Technical Bid Evaluation For HVAC Equipments_IFA | 5 | 26-Jun-25 A | 02-Jul-25 A | 46188 | 46188
Bulk Materials |  | 326 | 15-Jan-25 A | 2026-07-24 | 2026-02-23 | 2027-07-20 | 257
Drip Leg |  | 71 | 01-Aug-25 A | 09-Sep-25 A | 46100 | 46112
OG Comp. Dis. Drip leg (02 Nos) |  | 71 | 01-Aug-25 A | 09-Sep-25 A | 46100 | 46112
A19350 | Issue Purchase Order to Vendor | 11 | 04-Sep-25 A | 09-Sep-25 A | 46100 | 46100
A19370 | Commercial Bid Evaluation(Completion) | 15 | 30-Aug-25 A | 03-Sep-25 A | 46100 | 46100
A56880 | Technical Bid Evaluation for Pressure Vessels & Internals_IFD/IFC | 8 | 26-Aug-25 A | 29-Aug-25 A | 46100 | 46100
A56870 | Technical Bid Evaluation for Pressure Vessels & Internals_RCA | 8 | 20-Aug-25 A | 25-Aug-25 A | 46100 | 46100
A56860 | Technical Bid Evaluation for Pressure Vessels & Internals_IFA | 8 | 14-Aug-25 A | 19-Aug-25 A | 46112 | 46112
A56850 | Technical Bid Evaluation for Pressure Vessels & Internals_RCC | 8 | 08-Aug-25 A | 13-Aug-25 A | 46112 | 46112
A56840 | Technical Bid Evaluation for Pressure Vessels & Internals_IFR | 8 | 06-Aug-25 A | 07-Aug-25 A | 46112 | 46112
A8790 | Issue RFQ to Bidders | 15 | 01-Aug-25 A | 05-Aug-25 A | 46112 | 46112
Fire Fighting Equipment |  | 197 | 11-Feb-25 A | 2026-03-19 | 2026-03-27 | 2026-06-18 | 65
TA_Fire Alarm System Modification - SAFCO |  | 48 | 11-Feb-25 A | 31-Mar-25 A | 46108 | 46108
A37150 | Issue Purchase Order to Vendor | 10 | 03-Mar-25 A | 21-Mar-25 A | 46108 | 46108
A57240 | TBE for ICT System Modification_Free Issue Material | 23 | 24-Mar-25 A | 31-Mar-25 A | 46108 | 46108
A37120 | Issue RFQ to Bidders | 20 | 11-Feb-25 A | 28-Feb-25 A | 46108 | 46108
VESDA (Very Early Smoke Detection Apparatus) |  | 127 | 01-May-25 A | 01-Oct-25 A | 46175 | 46175
A20720 | Issue Purchase Order to Vendor for VESDA | 10 | 15-Sep-25 A | 01-Oct-25 A | 46175 | 46175
A20740 | Commercial Bid Evaluation(Completion) | 20 | 01-Sep-25 A | 12-Sep-25 A | 46175 | 46175
A20730 | Bid Evaluation(Completion) | 40 | 25-Aug-25 A | 29-Aug-25 A | 46175 | 46175
A20710 | Issue RFQ to Bidders | 21 | 01-May-25 A | 20-Jun-25 A | 46175 | 46175
Fire Fighting Equipment |  | 95 | 20-Oct-25 A | 2026-03-19 | 2026-05-22 | 2026-06-18 | 65
A18100 | Commercial Bid Evaluation(Completion) | 15 | 12-Feb-26 A | 2026-03-12 | 2026-05-22 | 2026-05-22 | 65
A18080 | Issue Purchase Order to Vendor for Fire Fighting Equipment | 5 | 2026-03-13 | 2026-03-19 | 2026-05-22 | 2026-05-22 | 65
A18090 | Bid Evaluation(Completion) | 15 | 01-Feb-26 A | 11-Mar-26 A | 46164 | 46184
A17470 | Issue RFQ to Bidders | 5 | 20-Oct-25 A | 27-Oct-25 A | 46185 | 46191
Tail Gas Filter/Silencer/Colesor |  | 187 | 01-Apr-25 A | 2026-03-02 | 2026-11-09 | 2026-11-18 | 186
Coalescer - (BF) |  | 187 | 01-Apr-25 A | 2026-03-02 | 2026-11-09 | 2026-11-18 | 186
A8160 | Issue Purchase Order to Vendor | 3 | 29-Jan-26 A | 29-Jan-26 A | 46335 | 46335
A45530 | Technical Bid Evaluation for Coalscer_IFA | 3 | 27-Jan-26 A | 28-Jan-26 A | 46335 | 46335
A45550 | Technical Bid Evaluation for Coalscer_IFD/IFC | 3 | 2026-02-25 | 2026-03-02 | 2026-11-09 | 2026-11-09 | 186
A45520 | Technical Bid Evaluation for Coalscer_RCC | 3 | 25-Jan-26 A | 26-Jan-26 A | 46335 | 46335
A45540 | Technical Bid Evaluation for Coalscer_RCA | 3 | 2026-02-20 | 2026-02-25 | 2026-11-18 | 2026-11-18 | 186
A45510 | Technical Bid Evaluation for Coalscer_IFR | 3 | 24-Jan-26 A | 25-Jan-26 A | 46335 | 46338
A8130 | Issue RFQ to Bidders | 20 | 01-Apr-25 A | 10-Apr-25 A | 46338 | 46343
Steel Structure (material +sandwitch Panel) |  | 181 | 01-Mar-25 A | 2026-03-09 | 2026-02-23 | 2026-11-23 | 185
Civil Bulk Material |  | 54 | 16-May-25 A | 10-Jul-25 A | 46349 | 46349
A9570 | Technical Bid Evaluation | 21 | 02-Jul-25 A | 10-Jul-25 A | 46349 | 46349
A9580 | Issue Purchase Order to Vendor | 21 | 09-Jun-25 A | 20-Jun-25 A | 46349 | 46349
A9560 | Vendor Quote Received | 30 | 02-Jun-25 A | 01-Jul-25 A | 46349 | 46349
A9550 | Issue RFQ to Bidders | 21 | 16-May-25 A | 01-Jun-25 A | 46349 | 46349
TA_Steel Structure (Additional Steel Structure required for BFW) |  | 30 | 01-Mar-25 A | 20-Mar-25 A | 46108 | 46108
A21930 | Issue Purchase Order to Vendor | 5 | 16-Mar-25 A | 20-Mar-25 A | 46108 | 46108
A21940 | TBE for Steel Structure (TA) | 10 | 11-Mar-25 A | 15-Mar-25 A | 46108 | 46108
A21920 | Vendor Quote Received | 10 | 05-Mar-25 A | 10-Mar-25 A | 46108 | 46108
A21910 | Issue RFQs to Bidders (Remaining Steel Structure for TA) | 5 | 01-Mar-25 A | 05-Mar-25 A | 46108 | 46108
Steel Structure - Post TA |  | 95 | 01-Jun-25 A | 03-Oct-25 A | 46076 | 46227
A34550 | Issue Purchase Order to Vendor | 10 | 23-Sep-25 A | 03-Oct-25 A | 46076 | 46076
A34540 | Commercial Bid Evaluation(Completion) | 10 | 08-Sep-25 A | 22-Sep-25 A | 46132 | 46132
A34530 | Bid Evaluation(Completion) | 10 | 25-Aug-25 A | 05-Sep-25 A | 46132 | 46132
122 | Issue RFQ to Bidders | 10 | 01-Jun-25 A | 25-Jul-25 A | 46227 | 46227
Structural Steel |  | 181 | 01-Jun-25 A | 2026-03-09 | 2026-02-23 | 2026-03-13 | 5
A58000 | Technical Bid Evaluation for Structural Steel_IFD/IFC | 6 | 2026-02-27 | 2026-03-09 | 2026-02-23 | 2026-02-23 | 5
A57990 | Technical Bid Evaluation for Structural Steel_RCA | 6 | 2026-02-20 | 2026-02-27 | 2026-02-23 | 2026-02-23 | 5
A23640 | Issue Purchase Order to Vendor | 10 | 15-Sep-25 A | 03-Oct-25 A | 46076 | 46076
A57960 | Technical Bid Evaluation for Structural Steel_IFR | 6 | 08-Sep-25 A | 12-Sep-25 A | 46076 | 46076
A57980 | Technical Bid Evaluation for Structural Steel_IFA | 6 | 19-Sep-25 A | 01-Oct-25 A | 46076 | 46076
A23630 | Vendor Quote Received | 10 | 25-Aug-25 A | 05-Sep-25 A | 46076 | 46076
A57970 | Technical Bid Evaluation for Structural Steel_RCC | 6 | 15-Sep-25 A | 19-Sep-25 A | 46079 | 46087
A23620 | Issue RFQ to Bidders | 10 | 01-Jun-25 A | 25-Jun-25 A | 46087 | 46094
Turbing Material [SS tubes, Connectors, unions, plugs etc.] |  | 40 | 2026-02-20 | 2026-04-16 | 2026-04-07 | 2026-06-01 | 32
Turbing Material [SS tubes, Connectors, unions, plugs etc] |  | 40 | 2026-02-20 | 2026-04-16 | 2026-04-07 | 2026-06-01 | 32
A18200 | Issue Purchase Order to Vendor | 10 | 2026-04-03 | 2026-04-16 | 2026-04-07 | 2026-04-20 | 32
A18220 | Commercial Bid Evaluation(Completion) | 10 | 2026-03-20 | 2026-04-02 | 2026-04-21 | 2026-05-04 | 32
A18210 | Bid Evaluation(Completion) | 10 | 2026-03-06 | 2026-03-19 | 2026-05-05 | 2026-05-18 | 32
A17410 | Issue RFQ to Bidders | 10 | 2026-02-20 | 2026-03-05 | 2026-05-19 | 2026-06-01 | 32
Telecom (ACS+LAN +CCTV+PAGA) |  | 111 | 11-Mar-25 A | 2026-02-27 | 2026-03-27 | 2027-01-20 | 233
Acess Control System |  | 91 | 01-Aug-25 A | 2026-02-27 | 2026-04-08 | 2027-01-20 | 233
A51970 | Technical Bid Evaluation For Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_IFD/IFC | 3 | 2026-02-25 | 2026-02-27 | 2026-04-08 | 2026-04-08 | 233
A51960 | Technical Bid Evaluation For Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_RCA | 3 | 2026-02-20 | 2026-02-24 | 2026-04-08 | 2026-04-08 | 233
A22350 | Issue Purchase Order to Vendor for ACS | 3 | 13-Dec-25 A | 19-Dec-25 A | 46120 | 46120
A51950 | Technical Bid Evaluation For Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_IFA | 3 | 01-Dec-25 A | 03-Dec-25 A | 46120 | 46120
A22340 | Commercial Bid Evaluation(Completion) | 3 | 01-Dec-25 A | 03-Dec-25 A | 46120 | 46120
A23890 | Technical Bid Evaluation For Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_RCC | 3 | 26-Nov-25 A | 28-Nov-25 A | 46120 | 46120
A23880 | Technical Bid Evaluation For Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_IFR | 3 | 31-Oct-25 A | 14-Nov-25 A | 46400 | 46402
A18720 | RFQs to Bid Receipt | 3 | 01-Aug-25 A | 06-Aug-25 A | 46405 | 46407
TA_LAN System Modification - CISCO |  | 48 | 11-Mar-25 A | 10-Apr-25 A | 46108 | 46108
A37230 | Issue Purchase Order to Vendor | 10 | 03-Apr-25 A | 10-Apr-25 A | 46108 | 46108
A57480 | TBE for Electrical System Modification_Free Issue Material | 23 | 28-Mar-25 A | 03-Apr-25 A | 46108 | 46108
A37200 | Issue RFQ to Bidders | 20 | 11-Mar-25 A | 27-Mar-25 A | 46108 | 46108
PAGA + Telephone |  | 91 | 01-Aug-25 A | 2026-02-27 | 2026-05-22 | 2027-01-20 | 233
A57030 | Technical Bid Evaluation For Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_IFD/IFC | 3 | 2026-02-25 | 2026-02-27 | 2026-05-22 | 2026-05-22 | 233
A57020 | Technical Bid Evaluation For Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_RCA | 3 | 2026-02-20 | 2026-02-24 | 2026-05-22 | 2026-05-22 | 233
A19110 | Issue Purchase Order to Vendor for PAGA + Telephone | 3 | 11-Dec-25 A | 19-Dec-25 A | 46164 | 46164
A19130 | Commercial Bid Evaluation(Completion) | 3 | 11-Dec-25 A | 15-Dec-25 A | 46164 | 46164
A57010 | Technical Bid Evaluation For Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_IFA | 3 | 03-Dec-25 A | 05-Dec-25 A | 46164 | 46164
A57000 | Technical Bid Evaluation For Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_RCC | 3 | 27-Nov-25 A | 01-Dec-25 A | 46164 | 46164
A56990 | Technical Bid Evaluation For Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_IFR | 3 | 24-Nov-25 A | 26-Nov-25 A | 46400 | 46402
A18810 | RFQs to Bid Receipt | 3 | 01-Aug-25 A | 06-Aug-25 A | 46405 | 46407
CCTV |  | 91 | 01-Aug-25 A | 2026-02-27 | 2026-05-13 | 2027-01-20 | 233
A57080 | Technical Bid Evaluation For Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_IFD/IFC | 3 | 2026-02-25 | 2026-02-27 | 2026-05-13 | 2026-05-13 | 233
A57070 | Technical Bid Evaluation For Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_RCA | 3 | 2026-02-20 | 2026-02-24 | 2026-05-13 | 2026-05-13 | 233
A19170 | Issue Purchase Order to Vendor for CCTV | 3 | 11-Dec-25 A | 19-Dec-25 A | 46155 | 46155
A19190 | Commercial Bid Evaluation(Completion) | 3 | 11-Dec-25 A | 15-Dec-25 A | 46155 | 46155
A57060 | Technical Bid Evaluation For Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_IFA | 3 | 01-Dec-25 A | 03-Dec-25 A | 46155 | 46155
A57050 | Technical Bid Evaluation For Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_RCC | 3 | 26-Nov-25 A | 28-Nov-25 A | 46155 | 46155
A57040 | Technical Bid Evaluation For Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_IFR | 3 | 21-Nov-25 A | 25-Nov-25 A | 46400 | 46402
A18900 | RFQs to Bid Receipt | 3 | 01-Aug-25 A | 06-Aug-25 A | 46405 | 46407
Telecom (ACS + CCTV + PAGA) Integration |  | 48 | 01-Aug-25 A | 19-Dec-25 A | 46184 | 46184
A22290 | Issue Purchase Order to Vendor for Telecom (ACS+CCTV+PAGA) Integration | 3 | 12-Dec-25 A | 19-Dec-25 A | 46184 | 46184
A22280 | Commercial Bid Evaluation(Completion) | 3 | 02-Dec-25 A | 04-Dec-25 A | 46184 | 46184
A22270 | Bid Evaluation(Completion) | 3 | 01-Dec-25 A | 03-Dec-25 A | 46184 | 46184
A16990 | Issue RFQ to Bidders | 3 | 01-Aug-25 A | 06-Aug-25 A | 46184 | 46184
Lighting Fixtures |  | 66 | 2026-02-20 | 2026-05-22 | 2026-06-11 | 2026-09-10 | 79
Lighting Fixtures (Almost 50% Exd = 354 Nos) |  | 66 | 2026-02-20 | 2026-05-22 | 2026-06-11 | 2026-09-10 | 79
A19590 | Issue Purchase Order to Vendor for Lighting Fixtures | 15 | 2026-05-04 | 2026-05-22 | 2026-06-11 | 2026-07-09 | 79
A19610 | Commercial Bid Evaluation(Completion) | 15 | 2026-04-13 | 2026-05-01 | 2026-07-10 | 2026-07-30 | 79
A19600 | Bid Evaluation(Completion) | 15 | 2026-03-23 | 2026-04-10 | 2026-07-31 | 2026-08-20 | 79
A16390 | Issue RFQ to Bidders | 21 | 2026-02-20 | 2026-03-20 | 2026-08-21 | 2026-09-10 | 79
Manual Valve |  | 152 | 20-May-25 A | 21-Nov-25 A | 46157 | 46160
Manual Valves (Gate 9 Nos, Check 6 Nos, Globe Valves 64 Nos) |  | 152 | 20-May-25 A | 21-Nov-25 A | 46157 | 46160
A18140 | Issue Purchase Order to Vendor for Manual Valves | 21 | 27-Oct-25 A | 21-Nov-25 A | 46157 | 46157
A18160 | Commercial Bid Evaluation(Completion) | 6 | 15-Oct-25 A | 24-Oct-25 A | 46157 | 46157
A45060 | Technical Bid Evaluation (TBE) for Manual Valves_IFD/IFC | 6 | 10-Oct-25 A | 14-Oct-25 A | 46157 | 46157
A45050 | Technical Bid Evaluation (TBE) for Manual Valves_RCA | 6 | 08-Oct-25 A | 10-Oct-25 A | 46160 | 46160
A45040 | Technical Bid Evaluation (TBE) for Manual Valves_IFA | 6 | 03-Oct-25 A | 07-Nov-25 A | 46160 | 46160
A45030 | Technical Bid Evaluation (TBE) for Manual Valves_RCC | 6 | 26-Sep-25 A | 02-Oct-25 A | 46160 | 46160
A45020 | Technical Bid Evaluation (TBE) for Manual Valves_IFR | 6 | 19-Sep-25 A | 25-Sep-25 A | 46157 | 46157
A9270 | Issue RFQ to Bidders | 21 | 20-May-25 A | 24-Jul-25 A | 46160 | 46160
Piping Bulk |  | 241 | 01-Jul-25 A | 2026-07-24 | 2026-03-30 | 2027-05-14 | 210
Piping Lot for Post TA |  | 80 | 01-Jul-25 A | 17-Nov-25 A | 46134 | 46134
A57130 | Technical Bid Evaluation (TBE) for Piping Bulk_IFD/IFC | 6 | 14-Nov-25 A | 17-Nov-25 A | 46134 | 46134
A57120 | Technical Bid Evaluation (TBE) for Piping Bulk_RCA | 8 | 30-Oct-25 A | 14-Nov-25 A | 46134 | 46134
A57110 | Technical Bid Evaluation (TBE) for Piping Bulk_IFA | 7 | 25-Oct-25 A | 29-Oct-25 A | 46134 | 46134
A23680 | Issue Purchase Order to Vendor | 6 | 01-Sep-25 A | 06-Sep-25 A | 46134 | 46134
A23700 | Commercial Bid Evaluation(Completion) | 6 | 15-Oct-25 A | 24-Oct-25 A | 46134 | 46134
A57100 | Technical Bid Evaluation (TBE) for Piping Bulk_RCC | 8 | 15-Sep-25 A | 15-Oct-25 A | 46134 | 46134
A57090 | Technical Bid Evaluation (TBE) for Piping Bulk_IFR | 6 | 22-Jul-25 A | 15-Sep-25 A | 46134 | 46134
112 | Issue RFQ to Bidders | 15 | 01-Jul-25 A | 21-Jul-25 A | 46134 | 46134
Piping Supports (Swing Hangers) for Post TA |  | 83 | 04-Aug-25 A | 08-Sep-25 A | 46111 | 46167
A23720 | Issue Purchase Order to Vendor | 7 | 01-Sep-25 A | 08-Sep-25 A | 46111 | 46111
A57180 | Technical Bid Evaluation (TBE) for Spring Hangers_IFD/IFC | 8 | 25-Aug-25 A | 26-Aug-25 A | 46111 | 46111
A23740 | Commercial Bid Evaluation(Completion) | 21 | 06-Aug-25 A | 30-Aug-25 A | 46111 | 46111
A57170 | Technical Bid Evaluation (TBE) for Spring Hangers_RCA | 16 | 20-Aug-25 A | 22-Aug-25 A | 46111 | 46111
A57160 | Technical Bid Evaluation (TBE) for Spring Hangers_IFA | 8 | 18-Aug-25 A | 19-Aug-25 A | 46167 | 46167
A57150 | Technical Bid Evaluation (TBE) for Spring Hangers_RCC | 16 | 15-Aug-25 A | 16-Aug-25 A | 46167 | 46167
A57140 | Technical Bid Evaluation (TBE) for Spring Hangers_IFR | 11 | 09-Aug-25 A | 14-Aug-25 A | 46111 | 46111
A23710 | Issue RFQ to Bidders | 20 | 04-Aug-25 A | 08-Aug-25 A | 46111 | 46111
Piping 1st Lot for GF |  | 146 | 01-Jul-25 A | 2026-03-13 | 2026-04-20 | 2027-01-20 | 223
A45010 | Technical Bid Evaluation (TBE) for Piping Bulk_IFD/IFC | 8 | 2026-03-03 | 2026-03-13 | 2026-04-20 | 2026-04-20 | 223
A45000 | Technical Bid Evaluation (TBE) for Piping Bulk_RCA | 8 | 2026-02-20 | 2026-03-03 | 2026-04-20 | 2026-04-20 | 223
A21350 | Issue Purchase Order to Vendor | 14 | 08-Sep-25 A | 19-Sep-25 A | 46132 | 46132
A21370 | Commercial Bid Evaluation(Completion) | 15 | 25-Aug-25 A | 05-Sep-25 A | 46132 | 46132
A44990 | Technical Bid Evaluation (TBE) for Piping Bulk_IFA | 8 | 09-Sep-25 A | 16-Sep-25 A | 46132 | 46132
A44980 | Technical Bid Evaluation (TBE) for Piping Bulk_RCC | 8 | 30-Aug-25 A | 08-Sep-25 A | 46132 | 46132
A44970 | Technical Bid Evaluation (TBE) for Piping Bulk_IFR | 8 | 19-Aug-25 A | 29-Aug-25 A | 46386 | 46398
100 | Issue RFQ to Bidders | 21 | 01-Jul-25 A | 21-Jul-25 A | 46398 | 46407
Piping 2nd Lot for GF (CS Material) |  | 20 | 2026-02-20 | 2026-03-19 | 2026-05-18 | 2026-06-12 | 61
A21410 | Issue Purchase Order to Vendor | 5 | 2026-03-13 | 2026-03-19 | 2026-05-18 | 2026-05-22 | 61
A21430 | Commercial Bid Evaluation(Completion) | 5 | 2026-03-06 | 2026-03-12 | 2026-05-25 | 2026-05-29 | 61
A21420 | Bid Evaluation(Completion) | 5 | 2026-02-27 | 2026-03-05 | 2026-06-01 | 2026-06-05 | 61
101 | Issue RFQ to Bidders | 5 | 2026-02-20 | 2026-02-26 | 2026-06-08 | 2026-06-12 | 61
Piping 3rd Lot GF (CS Material) |  | 28 | 2026-03-13 | 2026-04-22 | 2026-04-06 | 2026-05-13 | 15
A21470 | Issue Purchase Order to Vendor | 7 | 2026-04-13 | 2026-04-22 | 2026-04-06 | 2026-04-14 | 15
A21490 | Commercial Bid Evaluation(Completion) | 7 | 2026-04-02 | 2026-04-13 | 2026-04-15 | 2026-04-23 | 15
A21480 | Bid Evaluation(Completion) | 7 | 2026-03-24 | 2026-04-02 | 2026-04-24 | 2026-05-04 | 15
102 | Issue RFQ to Bidders | 7 | 2026-03-13 | 2026-03-24 | 2026-05-05 | 2026-05-13 | 15
Piping Supports (Swing Hangers) for GF |  | 111 | 2026-02-20 | 2026-07-24 | 2026-10-20 | 2027-05-14 | 210
A21620 | Issue Purchase Order to Vendor | 14 | 2026-07-06 | 2026-07-24 | 2026-10-20 | 2026-10-27 | 210
A21640 | Commercial Bid Evaluation(Completion) | 30 | 2026-05-25 | 2026-07-06 | 2026-10-27 | 2026-11-11 | 210
A45160 | Technical Bid Evaluation (TBE) for Spring Hangers_IFD/IFC | 8 | 2026-05-14 | 2026-05-25 | 2026-11-11 | 2026-12-03 | 172
A45150 | Technical Bid Evaluation (TBE) for Spring Hangers_RCA | 16 | 2026-04-22 | 2026-05-13 | 2026-12-03 | 2026-12-18 | 172
A45140 | Technical Bid Evaluation (TBE) for Spring Hangers_IFA | 11 | 2026-04-07 | 2026-04-22 | 2026-12-18 | 2027-01-11 | 172
A45130 | Technical Bid Evaluation (TBE) for Spring Hangers_RCC | 16 | 2026-03-16 | 2026-04-06 | 2027-01-11 | 2027-01-20 | 172
A45120 | Technical Bid Evaluation (TBE) for Spring Hangers_IFR | 11 | 2026-02-27 | 2026-03-16 | 2027-03-16 | 2027-04-26 | 172
A21610 | Issue RFQ to Bidders | 5 | 2026-02-20 | 2026-02-26 | 2027-04-27 | 2027-05-14 | 172
HDPE Piping |  | 59 | 01-Aug-25 A | 19-Dec-25 A | 46121 | 46178
HDPE Piping GF (Fire Water Lines) |  | 59 | 01-Aug-25 A | 19-Dec-25 A | 46121 | 46178
A21560 | Commercial Bid Evaluation(Completion) | 21 | 22-Aug-25 A | 30-Aug-25 A | 46121 | 46121
A60310 | Technical Bid Evaluation (TBE) for Piping Bulk_IFD/IFC | 8 | 19-Aug-25 A | 21-Aug-25 A | 46121 | 46121
A60300 | Technical Bid Evaluation (TBE) for Piping Bulk_RCA | 8 | 18-Aug-25 A | 19-Aug-25 A | 46121 | 46121
A21540 | Issue Purchase Order to Vendor | 10 | 18-Dec-25 A | 19-Dec-25 A | 46121 | 46121
A60290 | Technical Bid Evaluation (TBE) for Piping Bulk_IFA | 8 | 16-Aug-25 A | 18-Aug-25 A | 46178 | 46178
A60280 | Technical Bid Evaluation (TBE) for Piping Bulk_RCC | 16 | 13-Aug-25 A | 15-Aug-25 A | 46178 | 46178
A60270 | Technical Bid Evaluation (TBE) for Piping Bulk_IFR | 8 | 09-Aug-25 A | 12-Aug-25 A | 46121 | 46121
A21530 | Issue RFQ to Bidders | 10 | 01-Aug-25 A | 08-Aug-25 A | 46121 | 46121
Piping SP Items (strainer, filters) |  | 78 | 23-Jan-26 A | 2026-04-09 | 2026-04-17 | 2026-07-24 | 76
Specialized Items (Orifice Flanges) CS 300# 1" - 6" = 08 Nos |  | 29 | 2026-02-20 | 2026-04-01 | 2026-04-22 | 2026-07-20 | 79
A18360 | Issue Purchase Order to Vendor | 5 | 2026-03-25 | 2026-04-01 | 2026-04-22 | 2026-04-29 | 44
A45110 | Technical Bid Evaluation (TBE) for Piping Speciality Items_IFD/IFC | 5 | 2026-03-25 | 2026-03-31 | 2026-04-29 | 2026-05-05 | 80
A18380 | Commercial Bid Evaluation(Completion) | 5 | 2026-03-18 | 2026-03-25 | 2026-05-06 | 2026-05-12 | 44
A45100 | Technical Bid Evaluation (TBE) for Piping Speciality Items_RCA | 5 | 2026-03-18 | 2026-03-24 | 2026-05-12 | 2026-05-18 | 80
A45090 | Technical Bid Evaluation (TBE) for Piping Speciality Items_IFA | 5 | 2026-03-12 | 2026-03-18 | 2026-07-08 | 2026-07-14 | 44
A45080 | Technical Bid Evaluation (TBE) for Piping Speciality Items_RCC | 5 | 2026-03-05 | 2026-03-11 | 2026-05-19 | 2026-05-25 | 44
A45070 | Technical Bid Evaluation (TBE) for Piping Speciality Items_IFR | 5 | 2026-02-27 | 2026-03-05 | 2026-07-14 | 2026-07-20 | 44
A18340 | Issue RFQ to Bidders | 5 | 2026-02-20 | 2026-02-26 | 2026-05-26 | 2026-06-01 | 44
Specialized Items (Strainer/Filter) CS & SS 150 # -300# 2" - 26" = 08 Nos |  | 78 | 23-Jan-26 A | 2026-04-09 | 2026-04-17 | 2026-07-24 | 76
A18280 | Commercial Bid Evaluation(Completion) | 30 | 17-Feb-26 A | 2026-02-26 | 2026-04-17 | 2026-04-17 | 40
A56630 | Technical Bid Evaluation (TBE) for Piping Speciality Items_IFD/IFC | 8 | 2026-03-31 | 2026-04-09 | 2026-04-17 | 2026-04-17 | 76
A56600 | Technical Bid Evaluation (TBE) for Piping Speciality Items_RCC | 16 | 11-Feb-26 A | 17-Feb-26 A | 46129 | 46129
A56620 | Technical Bid Evaluation (TBE) for Piping Speciality Items_RCA | 16 | 2026-03-09 | 2026-03-30 | 2026-04-17 | 2026-04-23 | 76
A18260 | Issue Purchase Order to Vendor | 21 | 2026-02-27 | 2026-03-27 | 2026-06-08 | 2026-06-23 | 40
A56590 | Technical Bid Evaluation (TBE) for Piping Speciality Items_IFR | 11 | 05-Feb-26 A | 10-Feb-26 A | 46136 | 46164
A56610 | Technical Bid Evaluation (TBE) for Piping Speciality Items_IFA | 11 | 2026-02-20 | 2026-03-09 | 2026-06-23 | 2026-07-15 | 76
A15910 | Issue RFQ to Bidders | 21 | 23-Jan-26 A | 04-Feb-26 A | 46218 | 46227
Pressure / Temperature / Level Instruments, Flowmeters |  | 235 | 18-Apr-25 A | 2026-03-25 | 2026-04-30 | 2027-07-20 | 344
Gauges (PG, TG, PDG) PG - 10bar & 40bar = 19 Nos, DP = 05 Nos, TG = 09 Nos |  | 88 | 15-Aug-25 A | 2026-03-25 | 2026-04-30 | 2026-06-02 | 50
A19230 | Issue Purchase Order to Vendor Guages (PG, TG, PDG) | 12 | 2026-03-09 | 2026-03-25 | 2026-04-30 | 2026-04-30 | 50
A16370 | Technical Bid Evaluation for Temperature Gauges / Pressure Gauges_IFD/IFC | 6 | 2026-03-09 | 2026-03-16 | 2026-04-30 | 2026-04-30 | 56
A16360 | Technical Bid Evaluation for Temperature Gauges / Pressure Gauges_RCA | 6 | 2026-02-27 | 2026-03-09 | 2026-04-30 | 2026-04-30 | 56
A19250 | Commercial Bid Evaluation(Completion) | 6 | 2026-02-27 | 2026-03-09 | 2026-04-30 | 2026-05-08 | 50
A16350 | Technical Bid Evaluation for Temperature Gauges / Pressure Gauges_IFA | 6 | 2026-02-20 | 2026-02-27 | 2026-05-08 | 2026-05-15 | 50
A16340 | Technical Bid Evaluation for Temperature Gauges / Pressure Gauges_RCC | 6 | 26-Dec-25 A | 23-Jan-26 A | 46160 | 46168
A48180 | Technical Bid Evaluation for Temperature Gauges / Pressure Gauges_IFR | 6 | 19-Dec-25 A | 26-Dec-25 A | 46168 | 46175
A17290 | RFQs to Bid Receipt | 2 | 15-Aug-25 A | 27-Aug-25 A | 46160 | 46175
Flow Elements Venturi |  | 139 | 01-Jun-25 A | 11-Dec-25 A | 46142 | 46142
A48170 | Technical Bid Evaluation for Flow Element (Venturi Tube)_IFD/IFC | 8 | 16-Oct-25 A | 31-Oct-25 A | 46142 | 46142
A16260 | Technical Bid Evaluation for Flow Element (Venturi Tube)_RCA | 16 | 01-Oct-25 A | 15-Oct-25 A | 46142 | 46142
A57630 | Commercial Bid Evaluation | 10 | 01-Nov-25 A | 17-Nov-25 A | 46142 | 46142
A57640 | Issue Purchase Order to Vendor | 10 | 27-Nov-25 A | 11-Dec-25 A | 46142 | 46142
A16250 | Technical Bid Evaluation for Flow Element (Venturi Tube)_IFA | 8 | 16-Sep-25 A | 25-Sep-25 A | 46142 | 46142
A16240 | Technical Bid Evaluation for Flow Element (Venturi Tube)_RCC | 8 | 11-Sep-25 A | 15-Sep-25 A | 46142 | 46142
A16230 | Technical Bid Evaluation for Flow Element (Venturi Tube)_IFR | 8 | 01-Sep-25 A | 10-Sep-25 A | 46142 | 46142
A57610 | Issue RFQ to Bidders | 20 | 01-Jun-25 A | 22-Jun-25 A | 46142 | 46142
Flow Elements Orifice |  | 235 | 01-May-25 A | 2026-03-25 | 2026-06-04 | 2026-07-07 | 74
A16220 | Technical Bid Evaluation for Flow Element (Orifice Plate)_IFD/IFC | 8 | 2026-03-13 | 2026-03-25 | 2026-06-04 | 2026-06-04 | 74
A48160 | Technical Bid Evaluation for Flow Element (Orifice Plate)_RCA | 16 | 2026-02-20 | 2026-03-13 | 2026-06-04 | 2026-06-04 | 74
A57930 | Issue Purchase Order to Vendor | 10 | 16-Dec-25 A | 18-Dec-25 A | 46177 | 46177
A57950 | Commercial Bid Evaluation | 10 | 01-Dec-25 A | 12-Dec-25 A | 46177 | 46177
A16200 | Technical Bid Evaluation for Flow Element (Orifice Plate)_IFA | 8 | 27-Nov-25 A | 02-Dec-25 A | 46206 | 46206
A16190 | Technical Bid Evaluation for Flow Element (Orifice Plate)_RCC | 8 | 19-Sep-25 A | 30-Sep-25 A | 46206 | 46206
A16180 | Technical Bid Evaluation for Flow Element (Orifice Plate)_IFR | 8 | 01-Sep-25 A | 23-Sep-25 A | 46177 | 46199
A57920 | Issue RFQ to Bidders | 20 | 01-May-25 A | 15-May-25 A | 46199 | 46210
PT, TT & DPT [PT 50 Nos, TT 33 Nos, DPT 20 Nos] |  | 186 | 18-Apr-25 A | 2026-03-23 | 2027-01-06 | 2027-07-20 | 347
A21040 | Issue Purchase Order to Vendor | 8 | 2026-03-11 | 2026-03-23 | 2027-01-06 | 2027-01-06 | 347
A21060 | Commercial Bid Evaluation(Completion) | 3 | 2026-03-06 | 2026-03-11 | 2027-01-06 | 2027-01-06 | 347
A16170 | Technical Bid Evaluation for Electronic Transmitters_IFD/IFC | 3 | 2026-03-02 | 2026-03-06 | 2027-01-06 | 2027-01-06 | 229
A16160 | Technical Bid Evaluation for Electronic Transmitters_RCA | 3 | 2026-02-25 | 2026-03-02 | 2027-01-06 | 2027-01-12 | 229
A48150 | Technical Bid Evaluation for Electronic Transmitters_IFA | 3 | 2026-02-20 | 2026-02-25 | 2027-01-12 | 2027-01-15 | 229
A16140 | Technical Bid Evaluation for Electronic Transmitters_RCC | 3 | 24-Dec-25 A | 17-Jan-26 A | 46402 | 46407
A16130 | Technical Bid Evaluation for Electronic Transmitters_IFR | 3 | 19-Dec-25 A | 24-Dec-25 A | 46573 | 46576
A21030 | Issue RFQ to Bidders | 21 | 18-Apr-25 A | 09-May-25 A | 46577 | 46588
Instrument Bulk Material |  | 230 | 01-Feb-25 A | 2026-03-12 | 2026-03-05 | 2027-01-20 | 224
TA_Instrument Bulk Materia l(Single & Multicore = Approx. 78,130 Mtr, FO Cables JB & Cable Trays)) |  | 53 | 01-Feb-25 A | 19-Mar-25 A | 46108 | 46108
A22070 | Issue Purchase Order to Vendor | 7 | 05-Mar-25 A | 19-Mar-25 A | 46108 | 46108
A22050 | TBE for Instrument Bulk Material (TA) | 15 | 12-Feb-25 A | 21-Feb-25 A | 46108 | 46108
A22040 | Vendor Quote Received | 10 | 24-Feb-25 A | 04-Mar-25 A | 46108 | 46108
A22030 | Issue RFQs to Bidders | 21 | 01-Feb-25 A | 11-Feb-25 A | 46108 | 46108
Analyzer |  | 116 | 01-May-25 A | 08-Jun-25 A | 46354 | 46354
A57600 | Issue Purchase Order to Vendor | 14 | 02-Jun-25 A | 08-Jun-25 A | 46354 | 46354
A57590 | Commercial Bid Evaluation | 15 | 25-May-25 A | 01-Jun-25 A | 46354 | 46354
A16380 | Technical Bid Evaluation for Analyzers_IFR | 8 | 01-May-25 A | 25-May-25 A | 46354 | 46354
A57570 | Issue RFQ to Bidders | 20 | 01-May-25 A | 25-May-25 A | 46354 | 46354
A16420 | Technical Bid Evaluation for Analyzers_IFD/IFC | 19 | 01-May-25 A | 23-May-25 A | 46354 | 46354
A16410 | Technical Bid Evaluation for Analyzers_RCA | 19 | 01-May-25 A | 23-May-25 A | 46354 | 46354
A16400 | Technical Bid Evaluation for Analyzers_IFA | 19 | 01-May-25 A | 23-May-25 A | 46354 | 46354
A48190 | Technical Bid Evaluation for Analyzers_RCC | 19 | 01-May-25 A | 23-May-25 A | 46354 | 46354
Cable Tray and Instrument Junction Box (Perforated Cable tray Heavy duty = 5982 Mtrs, JBs = 73 Nos) |  | 168 | 20-Jul-25 A | 2026-03-12 | 2026-03-05 | 2027-01-20 | 224
A16870 | Technical Bid Evaluation for Junction Boxes_IFD/IFC | 5 | 2026-03-06 | 2026-03-12 | 2026-03-05 | 2026-03-05 | 224
A16860 | Technical Bid Evaluation for Junction Boxes_RCA | 5 | 2026-02-27 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 224
A16850 | Technical Bid Evaluation for Junction Boxes_IFA | 5 | 2026-02-20 | 2026-02-26 | 2026-03-05 | 2026-03-05 | 9
A20050 | Issue Purchase Order to Vendor | 5 | 15-Jan-26 A | 21-Jan-26 A | 46093 | 46093
A20070 | Commercial Bid Evaluation(Completion) | 5 | 05-Jan-26 A | 14-Jan-26 A | 46093 | 46093
A16840 | Technical Bid Evaluation for Junction Boxes_RCC | 5 | 19-Dec-25 A | 10-Jan-26 A | 46086 | 46092
A16830 | Technical Bid Evaluation for Junction Boxes_IFR | 5 | 28-Nov-25 A | 12-Dec-25 A | 46394 | 46400
A17230 | Issue RFQ to Bidders | 21 | 20-Jul-25 A | 25-Oct-25 A | 46401 | 46407
Magnetic Level Gauge ( 09 Nos) |  | 160 | 18-Jul-25 A | 2026-02-26 | 2026-03-25 | 2026-03-31 | 23
A21280 | Issue Purchase Order to Vendor | 5 | 2026-02-20 | 2026-02-26 | 2026-03-25 | 2026-03-25 | 23
A21300 | Commercial Bid Evaluation(Completion) | 3 | 10-Nov-25 A | 21-Nov-25 A | 46106 | 46106
A16470 | Technical Bid Evaluation for Level Gauges (Magnetic Type)_IFD/IFC | 3 | 01-Oct-25 A | 30-Oct-25 A | 46106 | 46106
A16460 | Technical Bid Evaluation for Level Gauges (Magnetic Type)_RCA | 3 | 16-Sep-25 A | 30-Sep-25 A | 46106 | 46106
A48200 | Technical Bid Evaluation for Level Gauges (Magnetic Type)_IFA | 3 | 30-Aug-25 A | 15-Sep-25 A | 46106 | 46106
A16440 | Technical Bid Evaluation for Level Gauges (Magnetic Type)_RCC | 3 | 21-Aug-25 A | 29-Aug-25 A | 46106 | 46106
A16430 | Technical Bid Evaluation for Level Gauges (Magnetic Type)_IFR | 3 | 07-Aug-25 A | 20-Aug-25 A | 46106 | 46106
A21270 | Issue RFQ to Bidders | 3 | 18-Jul-25 A | 06-Aug-25 A | 46106 | 46112
Fibre Optic Cable (Armoured, Telecom/IT/MAS) |  | 56 | 01-Jun-25 A | 18-Aug-25 A | 46100 | 46100
A18680 | Commercial Bid Evaluation(Completion) | 6 | 01-Aug-25 A | 08-Aug-25 A | 46100 | 46100
A17170 | RFQs to Bid receipt | 21 | 01-Jun-25 A | 21-Jun-25 A | 46100 | 46100
A18660 | Issue Purchase Order to Vendor | 6 | 09-Aug-25 A | 18-Aug-25 A | 46100 | 46100
A57550 | Technical Bid Evaluation for Instrument Cables_IFD/IFC | 6 | 30-Jul-25 A | 31-Jul-25 A | 46100 | 46100
A57540 | Technical Bid Evaluation for Instrument Cables_RCA | 6 | 30-Jul-25 A | 31-Jul-25 A | 46100 | 46100
A57530 | Technical Bid Evaluation for Instrument Cables_IFA | 6 | 30-Jul-25 A | 31-Jul-25 A | 46100 | 46100
A57520 | Technical Bid Evaluation for Instrument Cables_RCC | 6 | 30-Jul-25 A | 31-Jul-25 A | 46100 | 46100
A57510 | Technical Bid Evaluation for Instrument Cables_IFR | 6 | 30-Jul-25 A | 31-Jul-25 A | 46100 | 46100
Earthing & Power Cables |  | 139 | 18-Jul-25 A | 24-Oct-25 A | 46164 | 46216
Power Cables ( 11kV & 33kV) |  | 129 | 01-Aug-25 A | 03-Sep-25 A | 46216 | 46216
A58720 | Issue Purchase Order to Vendor | 14 | 25-Aug-25 A | 03-Sep-25 A | 46216 | 46216
A58710 | Commercial Bid Evaluation(Completion) | 25 | 06-Aug-25 A | 27-Aug-25 A | 46216 | 46216
A58700 | Bid Evaluation(Completion) | 30 | 04-Aug-25 A | 25-Aug-25 A | 46216 | 46216
A58690 | Issue RFQ to Bidders | 21 | 01-Aug-25 A | 20-Aug-25 A | 46216 | 46216
Earthing and Power Cables |  | 100 | 18-Jul-25 A | 24-Oct-25 A | 46164 | 46183
A13270 | Technical Bid Evaluation For Power, Control And Earthing Cables_IFD/IFC | 3 | 01-Oct-25 A | 07-Oct-25 A | 46164 | 46164
A13260 | Technical Bid Evaluation For Power, Control And Earthing Cables_RCA | 3 | 19-Sep-25 A | 30-Sep-25 A | 46164 | 46164
A13250 | Technical Bid Evaluation For Power, Control And Earthing Cables_IFA | 3 | 11-Sep-25 A | 17-Sep-25 A | 46164 | 46164
A20590 | Issue Purchase Order to Vendor | 3 | 15-Oct-25 A | 24-Oct-25 A | 46183 | 46183
A20610 | Commercial Bid Evaluation(Completion) | 3 | 07-Oct-25 A | 14-Oct-25 A | 46183 | 46183
A13240 | Technical Bid Evaluation For Power, Control And Earthing Cables_RCC | 3 | 30-Aug-25 A | 10-Sep-25 A | 46183 | 46183
A13230 | Technical Bid Evaluation For Power, Control And Earthing Cables_IFR | 3 | 21-Aug-25 A | 29-Aug-25 A | 46164 | 46164
A16450 | Issue RFQ to Bidders | 21 | 18-Jul-25 A | 20-Aug-25 A | 46164 | 46164
Electrical Bulk |  | 196 | 15-Jan-25 A | 2026-05-29 | 2026-04-14 | 2026-07-27 | 41
TA_Electrical Bulk Material (Earthing ,FO, Power Cables) |  | 91 | 15-Jan-25 A | 09-Mar-25 A | 46142 | 46142
A17910 | Negotiations and PO Placement (33 KVA) | 15 | 03-Mar-25 A | 09-Mar-25 A | 46142 | 46142
A17920 | TBE | 30 | 20-Feb-25 A | 28-Feb-25 A | 46142 | 46142
A17900 | Vendor Quote Received | 30 | 10-Feb-25 A | 19-Feb-25 A | 46142 | 46142
A17890 | Issue RFQ to Bidders | 20 | 15-Jan-25 A | 08-Feb-25 A | 46142 | 46142
Cable Trays, JBs, Conduit Pipe, Cable Lugs, etc |  | 59 | 2026-02-20 | 2026-05-13 | 2026-04-14 | 2026-07-03 | 37
A20650 | Issue Purchase Order to Vendor | 14 | 2026-04-24 | 2026-05-13 | 2026-04-14 | 2026-05-04 | 37
A20670 | Commercial Bid Evaluation(Completion) | 15 | 2026-04-03 | 2026-04-23 | 2026-05-05 | 2026-05-25 | 37
A20660 | Bid Evaluation(Completion) | 15 | 2026-03-13 | 2026-04-02 | 2026-05-26 | 2026-06-15 | 37
A9450 | Issue RFQ to Bidders | 15 | 2026-02-20 | 2026-03-12 | 2026-06-16 | 2026-07-03 | 37
LCS & Snap Switches |  | 71 | 2026-02-20 | 2026-05-29 | 2026-04-20 | 2026-07-27 | 41
A21700 | Issue Purchase Order to Vendor | 14 | 2026-05-12 | 2026-05-29 | 2026-04-20 | 2026-05-18 | 41
A21720 | Commercial Bid Evaluation(Completion) | 15 | 2026-04-21 | 2026-05-11 | 2026-05-19 | 2026-06-16 | 41
A21710 | Bid Evaluation(Completion) | 21 | 2026-03-23 | 2026-04-20 | 2026-06-17 | 2026-07-07 | 41
A21690 | Issue RFQ to Bidders | 21 | 2026-02-20 | 2026-03-20 | 2026-07-08 | 2026-07-27 | 41
Main Automation Equipment |  | 245 | 01-Feb-25 A | 2026-04-02 | 2026-03-18 | 2026-07-15 | 73
On Off Valve / Control Valves |  | 181 | 10-Apr-25 A | 20-Oct-25 A | 46106 | 46154
ESD Valve |  | 181 | 10-Apr-25 A | 16-May-25 A | 46106 | 46130
A59800 | Technical Bid Evaluation for ESD_IFD/IFC | 8 | 13-May-25 A | 14-May-25 A | 46106 | 46106
A59790 | Technical Bid Evaluation for ESD_RCA | 16 | 10-May-25 A | 12-May-25 A | 46106 | 46106
A59780 | Technical Bid Evaluation for ESD_IFA | 11 | 08-May-25 A | 09-May-25 A | 46106 | 46106
A59740 | Issue Purchase Order to Vendor for ESD | 21 | 15-May-25 A | 16-May-25 A | 46106 | 46106
A59770 | Technical Bid Evaluation for ESD_RCC | 16 | 05-May-25 A | 07-May-25 A | 46130 | 46130
A59750 | Commercial Bid Evaluation(Completion) | 21 | 14-May-25 A | 15-May-25 A | 46130 | 46130
A59760 | Technical Bid Evaluation for ESD_IFR | 11 | 02-May-25 A | 05-May-25 A | 46106 | 46106
A59730 | Issue RFQ to Bidders | 21 | 10-Apr-25 A | 02-May-25 A | 46106 | 46106
Control Valves (1" - 24" Rating 150, 300 & 2500 = 32 Nos) + SDV |  | 171 | 21-Apr-25 A | 20-Oct-25 A | 46106 | 46154
A22110 | Issue Purchase Order to Vendor for Control Valves | 21 | 01-Oct-25 A | 20-Oct-25 A | 46106 | 46106
A22100 | Commercial Bid Evaluation(Completion) | 21 | 17-Sep-25 A | 18-Sep-25 A | 46106 | 46106
A16520 | Technical Bid Evaluation for Control Valves_IFD/IFC | 8 | 23-Aug-25 A | 18-Sep-25 A | 46106 | 46106
A48210 | Technical Bid Evaluation for Control Valves_RCA | 8 | 23-Aug-25 A | 18-Sep-25 A | 46106 | 46106
A16500 | Technical Bid Evaluation for Control Valves_IFA | 8 | 23-Aug-25 A | 18-Sep-25 A | 46106 | 46106
A16490 | Technical Bid Evaluation for Control Valves_RCC | 8 | 23-Aug-25 A | 18-Sep-25 A | 46106 | 46106
A16480 | Technical Bid Evaluation for Control Valves_IFR | 8 | 23-Aug-25 A | 18-Sep-25 A | 46106 | 46106
A16750 | Issue RFQ to Bidders | 21 | 21-Apr-25 A | 15-May-25 A | 46154 | 46154
MOVs |  | 121 | 21-Apr-25 A | 10-Sep-25 A | 46153 | 46153
MOVs [Ball Type 24" 150# = 01 No] |  | 121 | 21-Apr-25 A | 10-Sep-25 A | 46153 | 46153
A18600 | Issue Purchase Order to Vendor for MOVs | 14 | 26-Aug-25 A | 02-Sep-25 A | 46153 | 46153
A18620 | Commercial Bid Evaluation(Completion) | 5 | 19-Aug-25 A | 01-Sep-25 A | 46153 | 46153
A16670 | Technical Bid Evaluation for Motor Operated Valves_IFD/IFC | 5 | 07-Sep-25 A | 10-Sep-25 A | 46153 | 46153
A16660 | Technical Bid Evaluation for Motor Operated Valves_RCA | 6 | 30-Aug-25 A | 06-Sep-25 A | 46153 | 46153
A16650 | Technical Bid Evaluation for Motor Operated Valves_IFA | 8 | 19-Aug-25 A | 29-Aug-25 A | 46153 | 46153
A16640 | Technical Bid Evaluation for Motor Operated Valves_RCC | 6 | 22-Aug-25 A | 02-Sep-25 A | 46153 | 46153
A48230 | Technical Bid Evaluation for Motor Operated Valves_IFR | 11 | 16-May-25 A | 22-Aug-25 A | 46153 | 46153
A17050 | RFQs to Bid Receipt | 21 | 21-Apr-25 A | 15-May-25 A | 46153 | 46153
Machine Condition Monitoring System (MCMS) |  | 117 | 01-Feb-25 A | 01-Jun-25 A | 46108 | 46218
TA_MCMS System Modification - Bently Nevada |  | 48 | 01-Feb-25 A | 15-Mar-25 A | 46108 | 46108
A37190 | Issue Purchase Order to Vendor | 5 | 10-Mar-25 A | 15-Mar-25 A | 46108 | 46108
A57450 | TBE for ICT System Modification_Free Issue Material | 23 | 23-Feb-25 A | 09-Mar-25 A | 46108 | 46108
A37160 | Issue RFQ to Bidders | 20 | 01-Feb-25 A | 22-Feb-25 A | 46108 | 46108
Machine Condition Monitoring System |  | 99 | 01-Apr-25 A | 01-Jun-25 A | 46218 | 46218
A19930 | Issue Purchase Order to Vendor for MCMS | 21 | 08-May-25 A | 15-May-25 A | 46218 | 46218
A19950 | Commercial Bid Evaluation(Completion) | 21 | 26-May-25 A | 01-Jun-25 A | 46218 | 46218
A58630 | Technical Bid Evaluation for MCMS System_IFD/IFC | 8 | 20-May-25 A | 25-May-25 A | 46218 | 46218
A58620 | Technical Bid Evaluation for MCMS System_RCA | 16 | 16-May-25 A | 19-May-25 A | 46218 | 46218
A58610 | Technical Bid Evaluation for MCMSSystem_IFA | 11 | 16-May-25 A | 19-May-25 A | 46218 | 46218
A58600 | Technical Bid Evaluation for MCMS System_RCC | 16 | 16-May-25 A | 19-May-25 A | 46218 | 46218
A58590 | Technical Bid Evaluation for MCMS System_IFR | 11 | 01-May-25 A | 15-May-25 A | 46218 | 46218
A17110 | Issue RFQ to Bidders | 20 | 01-Apr-25 A | 20-Apr-25 A | 46218 | 46218
IPCS Modification (ABB) |  | 94 | 01-Feb-25 A | 25-Jul-25 A | 46108 | 46146
TA_Integrated Protection and Control System - ABB/Hitachi |  | 37 | 01-Feb-25 A | 18-Mar-25 A | 46108 | 46108
A20960 | Issue Purchase Order to Vendor | 7 | 10-Mar-25 A | 18-Mar-25 A | 46108 | 46108
A57390 | TBE for Electrical System Modification_ Free Issue Material | 8 | 26-Feb-25 A | 09-Mar-25 A | 46108 | 46108
A20950 | Issue RFQ to Bidders | 20 | 01-Feb-25 A | 25-Feb-25 A | 46108 | 46108
Integrated Protection and Control System |  | 82 | 10-Apr-25 A | 25-Jul-25 A | 46146 | 46146
A58580 | Technical Bid Evaluation for IPCS_IFD/IFC | 8 | 01-Jun-25 A | 04-Jun-25 A | 46146 | 46146
A58570 | Technical Bid Evaluation for IPCS_RCA | 16 | 27-May-25 A | 31-May-25 A | 46146 | 46146
A23830 | Issue Purchase Order to Vendor for IPCS | 5 | 17-Jul-25 A | 25-Jul-25 A | 46146 | 46146
A58560 | Technical Bid Evaluation for IPCS_IFA | 11 | 21-May-25 A | 26-May-25 A | 46146 | 46146
A58550 | Technical Bid Evaluation for IPCS_RCC | 16 | 11-May-25 A | 20-May-25 A | 46146 | 46146
A23850 | Commercial Bid Evaluation(Completion) | 10 | 07-Jul-25 A | 16-Jul-25 A | 46146 | 46146
A58540 | Technical Bid Evaluation for IPCS_IFR | 8 | 02-May-25 A | 10-May-25 A | 46146 | 46146
A23820 | Issue RFQ to Bidders | 20 | 10-Apr-25 A | 01-May-25 A | 46146 | 46146
OTS |  | 98 | 01-Feb-25 A | 20-Aug-25 A | 46101 | 46108
TA_SCMS Modification - Siemens |  | 27 | 01-Feb-25 A | 03-Mar-25 A | 46108 | 46108
A24200 | Issue Purchase Order to Vendor | 7 | 25-Feb-25 A | 03-Mar-25 A | 46108 | 46108
A57360 | TBE for Electrical System Modification_ Free Issue Material | 11 | 11-Feb-25 A | 24-Feb-25 A | 46108 | 46108
A24190 | Issue RFQ to Bidders | 10 | 01-Feb-25 A | 10-Feb-25 A | 46108 | 46108
SCMS |  | 98 | 19-Mar-25 A | 20-Aug-25 A | 46101 | 46101
A60200 | Issue Purchase Order to Vendor for SCMS | 6 | 16-Jul-25 A | 20-Aug-25 A | 46101 | 46101
A60210 | Commercial Bid Evaluation(Completion) | 6 | 04-Jul-25 A | 15-Jul-25 A | 46101 | 46101
A60260 | Technical Bid Evaluation for SCMS_IFD/IFC | 6 | 27-Jun-25 A | 03-Jul-25 A | 46101 | 46101
A60250 | Technical Bid Evaluation for SCMS_RCA | 6 | 20-Jun-25 A | 26-Jun-25 A | 46101 | 46101
A60240 | Technical Bid Evaluation for SCMS_IFA | 6 | 13-Jun-25 A | 19-Jun-25 A | 46101 | 46101
A60220 | Technical Bid Evaluation for SCMS_IFR | 11 | 21-May-25 A | 01-Jun-25 A | 46101 | 46101
A60230 | Technical Bid Evaluation for SCMS_RCC | 6 | 02-Jun-25 A | 12-Jun-25 A | 46101 | 46101
A60190 | Issue RFQ to Bidders | 21 | 19-Mar-25 A | 20-May-25 A | 46101 | 46101
ICSS (Integrated Control and Safety System) including sys. Modifications |  | 128 | 07-Feb-25 A | 20-Jun-25 A | 46099 | 46108
Integrated Control and Safety System GF |  | 105 | 15-May-25 A | 20-Jun-25 A | 46099 | 46099
A23950 | Issue Purchase Order to Vendor for ICSS | 14 | 14-Jun-25 A | 20-Jun-25 A | 46099 | 46099
A23970 | Commercial Bid Evaluation(Completion) | 21 | 07-Jun-25 A | 13-Jun-25 A | 46099 | 46099
A16920 | Technical Bid Evaluation for ICSS System_IFD/IFC | 8 | 01-Jun-25 A | 06-Jun-25 A | 46099 | 46099
A16910 | Technical Bid Evaluation for ICSS System_RCA | 16 | 31-May-25 A | 01-Jun-25 A | 46099 | 46099
A16900 | Technical Bid Evaluation for ICSS System_IFA | 11 | 30-May-25 A | 31-May-25 A | 46099 | 46099
A16890 | Technical Bid Evaluation for ICSS System_RCC | 16 | 29-May-25 A | 30-May-25 A | 46099 | 46099
A16880 | Technical Bid Evaluation for ICSS System_IFR | 11 | 26-May-25 A | 28-May-25 A | 46099 | 46099
A23940 | Issue RFQ to Bidders | 14 | 15-May-25 A | 30-May-25 A | 46099 | 46099
TA_Integrated Control & Safety System BF - Honeywell |  | 27 | 07-Feb-25 A | 10-Mar-25 A | 46108 | 46108
A19780 | Issue Purchase Order to Vendor | 7 | 01-Mar-25 A | 10-Mar-25 A | 46108 | 46108
A56210 | TBE for ICT System Modification_Free Issue Material | 11 | 18-Feb-25 A | 28-Feb-25 A | 46108 | 46108
A19770 | Issue RFQ to Bidders | 10 | 07-Feb-25 A | 17-Feb-25 A | 46108 | 46108
Instrument Cables |  | 80 | 01-Nov-25 A | 2026-03-12 | 2026-03-23 | 2026-04-10 | 21
Instrument Cable (Single & Multicore = Approx. 78,130 Mtr) |  | 80 | 01-Nov-25 A | 2026-03-12 | 2026-03-23 | 2026-04-10 | 21
A16820 | Technical Bid Evaluation for Instrument Cables_IFD/IFC | 5 | 2026-03-06 | 2026-03-12 | 2026-03-23 | 2026-03-23 | 21
A16800 | Technical Bid Evaluation for Instrument Cables_IFA | 5 | 06-Feb-26 A | 2026-02-26 | 2026-03-23 | 2026-03-23 | 21
A21200 | Issue Purchase Order to Vendor | 5 | 2026-03-06 | 2026-03-12 | 2026-03-23 | 2026-03-23 | 21
A16810 | Technical Bid Evaluation for Instrument Cables_RCA | 5 | 2026-02-27 | 2026-03-05 | 2026-03-23 | 2026-03-27 | 21
A16790 | Technical Bid Evaluation for Instrument Cables_RCC | 5 | 02-Feb-26 A | 06-Feb-26 A | 46111 | 46115
A21220 | Commercial Bid Evaluation(Completion) | 5 | 2026-02-27 | 2026-03-05 | 2026-03-30 | 2026-04-03 | 21
A16780 | Technical Bid Evaluation for Instrument Cables_IFR | 5 | 26-Jan-26 A | 31-Jan-26 A | 46118 | 46122
A21190 | Issue RFQ to Bidders | 5 | 01-Nov-25 A | 11-Nov-25 A | 46118 | 46122
Local Fire Control Panel including F & G Detectors |  | 173 | 20-Jun-25 A | 12-Dec-25 A | 46147 | 46147
Fire Detection Alarm System and Local Fire Control Panel (Clean Agent Unit) |  | 173 | 20-Jun-25 A | 12-Dec-25 A | 46147 | 46147
A19650 | Issue Purchase Order to Vendor for Fire Detection, Local Fire Control and Clean Agent | 6 | 01-Dec-25 A | 12-Dec-25 A | 46147 | 46147
A19670 | Commercial Bid Evaluation(Completion) | 18 | 28-Nov-25 A | 10-Dec-25 A | 46147 | 46147
A19660 | Bid Evaluation(Completion) | 15 | 01-Nov-25 A | 14-Nov-25 A | 46147 | 46147
A16930 | Issue RFQ to Bidders | 20 | 20-Jun-25 A | 14-Aug-25 A | 46147 | 46147
PSVs |  | 89 | 15-Oct-25 A | 2026-03-25 | 2026-03-20 | 2026-04-22 | 20
PSVs (1"x2" upto 8"x10" - CS Rating 150/150, 300/150 = 22 Nos) |  | 89 | 15-Oct-25 A | 2026-03-25 | 2026-03-20 | 2026-04-22 | 20
A21120 | Issue Purchase Order to Vendor | 7 | 2026-03-17 | 2026-03-25 | 2026-03-20 | 2026-03-20 | 20
A21140 | Commercial Bid Evaluation(Completion) | 7 | 2026-03-06 | 2026-03-16 | 2026-03-20 | 2026-04-02 | 20
A21130 | Bid Evaluation(Completion) | 10 | 15-Feb-26 A | 2026-03-05 | 2026-04-03 | 2026-04-13 | 20
A21110 | Issue RFQ to Bidders | 5 | 15-Oct-25 A | 27-Oct-25 A | 46126 | 46134
Sampling System |  | 53 | 12-Feb-25 A | 18-Mar-25 A | 46108 | 46108
TA_CGC Turbine Software Upgrade - HMI |  | 31 | 15-Feb-25 A | 18-Mar-25 A | 46108 | 46108
A37270 | Issue Purchase Order to Vendor | 10 | 08-Mar-25 A | 18-Mar-25 A | 46108 | 46108
A57300 | TBE for ICT System Modification_Free Issue Material | 11 | 26-Feb-25 A | 07-Mar-25 A | 46108 | 46108
A37240 | Issue RFQ to Bidders | 10 | 15-Feb-25 A | 25-Feb-25 A | 46108 | 46108
TA_SGM Replacement (Additional Item) |  | 53 | 12-Feb-25 A | 15-Mar-25 A | 46108 | 46108
A37410 | Issue Purchase Order to Vendor | 10 | 05-Mar-25 A | 15-Mar-25 A | 46108 | 46108
A57330 | TBE for ICT System Modification_Free Issue Material | 23 | 23-Feb-25 A | 04-Mar-25 A | 46108 | 46108
A37400 | Issue RFQ to Bidders | 20 | 12-Feb-25 A | 22-Feb-25 A | 46108 | 46108
F&G [324 Nos] Flame Detectors, MCP, Beacon, etc. |  | 185 | 18-Jul-25 A | 2026-04-02 | 2026-04-20 | 2026-05-29 | 41
F&G Flame Detectors, MCP, Beacon (Nos 324) |  | 185 | 18-Jul-25 A | 2026-04-02 | 2026-04-20 | 2026-05-29 | 41
A20110 | Issue Purchase Order to Vendor F&G Flames Detectors, MCP, Beacon (nos 324) | 12 | 2026-03-17 | 2026-04-02 | 2026-04-20 | 2026-04-20 | 41
A48220 | Technical Bid Evaluation for Fire & Gas Detectors_IFD/IFC | 8 | 2026-03-19 | 2026-03-30 | 2026-04-20 | 2026-04-20 | 44
A16560 | Technical Bid Evaluation for Fire & Gas Detectors_RCA | 6 | 2026-03-11 | 2026-03-19 | 2026-04-20 | 2026-04-29 | 44
A20130 | Commercial Bid Evaluation(Completion) | 10 | 2026-03-03 | 2026-03-17 | 2026-05-04 | 2026-05-12 | 41
A16550 | Technical Bid Evaluation for Fire & Gas Detectors_IFA | 6 | 2026-03-03 | 2026-03-11 | 2026-04-30 | 2026-05-13 | 44
A16540 | Technical Bid Evaluation for Fire & Gas Detectors_RCC | 8 | 14-Feb-26 A | 2026-03-03 | 2026-05-12 | 2026-05-20 | 41
A16530 | Technical Bid Evaluation for Fire & Gas Detectors_IFR | 14 | 01-Dec-25 A | 13-Feb-26 A | 46162 | 46171
A17350 | Issue RFQ to Bidders | 4 | 18-Jul-25 A | 14-Aug-25 A | 46156 | 46171
Main Electrical Equipment |  | 309 | 01-Feb-25 A | 2026-05-13 | 2026-03-27 | 2026-09-29 | 98
DG Set (750 KVA) |  | 78 | 01-Feb-25 A | 25-Sep-25 A | 46160 | 46160
DG Set |  | 78 | 01-Feb-25 A | 25-Sep-25 A | 46160 | 46160
A13370 | Technical Bid Evaluation For Emergency Diesel Generator Set_IFD/IFC | 8 | 10-Sep-25 A | 25-Sep-25 A | 46160 | 46160
A13360 | Technical Bid Evaluation For Emergency Diesel Generator Set_RCA | 16 | 20-Aug-25 A | 15-Sep-25 A | 46160 | 46160
A13350 | Technical Bid Evaluation For Emergency Diesel Generator Set_IFA | 11 | 23-Aug-25 A | 08-Sep-25 A | 46160 | 46160
A20410 | Issue Purchase Order to Vendor for DG Set | 5 | 09-Aug-25 A | 22-Aug-25 A | 46160 | 46160
A13340 | Technical Bid Evaluation For Emergency Diesel Generator Set_RCC | 16 | 14-Jul-25 A | 22-Aug-25 A | 46160 | 46160
A20430 | Commercial Bid Evaluation(Completion) | 5 | 18-Jul-25 A | 08-Aug-25 A | 46160 | 46160
A13330 | Technical Bid Evaluation For Emergency Diesel Generator Set_IFR | 11 | 03-May-25 A | 21-May-25 A | 46160 | 46160
A16030 | Issue RFQ to Bidders | 21 | 01-Feb-25 A | 07-Feb-25 A | 46160 | 46160
UPS (AC - 60 KVA, 20 KVA, DC-UPS 6.5 KVA) |  | 226 | 12-Feb-25 A | 2026-03-09 | 2026-03-27 | 2026-08-13 | 114
TA_UPS Modification (Additional Item) - Chloride Technology |  | 50 | 12-Feb-25 A | 15-Mar-25 A | 46108 | 46108
A37090 | Issue Purchase Order to Vendor | 7 | 05-Mar-25 A | 15-Mar-25 A | 46108 | 46108
A57420 | TBE for Electrical System Modification_ Free Issue Material | 23 | 23-Feb-25 A | 04-Mar-25 A | 46108 | 46108
A37080 | Issue RFQs to Bidders | 20 | 12-Feb-25 A | 22-Feb-25 A | 46108 | 46108
UPS (AC - 60 KVA, 20 KVA, DC-UPS 6.5 KVA) Qty 1+1+1 = 03 Nos |  | 177 | 07-Jul-25 A | 2026-03-09 | 2026-05-28 | 2026-08-13 | 114
A13120 | Technical Bid Evaluation For AC UPS_IFD/IFC | 11 | 2026-02-20 | 2026-03-09 | 2026-05-28 | 2026-05-28 | 114
A19530 | Issue Purchase Order to Vendor for UPS (GF) | 6 | 29-Sep-25 A | 16-Oct-25 A | 46170 | 46170
A13110 | Technical Bid Evaluation For AC UPS_RCA | 6 | 04-Nov-25 A | 12-Nov-25 A | 46170 | 46170
A19550 | Commercial Bid Evaluation(Completion) | 6 | 01-Sep-25 A | 26-Sep-25 A | 46170 | 46170
A13100 | Technical Bid Evaluation For AC UPS_IFA | 6 | 20-Oct-25 A | 03-Nov-25 A | 46170 | 46170
A13090 | Technical Bid Evaluation For AC UPS_RCC | 6 | 14-Sep-25 A | 20-Sep-25 A | 46232 | 46232
A13080 | Technical Bid Evaluation For AC UPS_IFR | 11 | 06-Sep-25 A | 13-Sep-25 A | 46232 | 46232
A16090 | Issue RFQ to Bidders | 21 | 07-Jul-25 A | 04-Aug-25 A | 46232 | 46247
Power Transformer |  | 97 | 10-May-25 A | 17-Sep-25 A | 46143 | 46143
Power Transformers (Qty 05) |  | 97 | 10-May-25 A | 17-Sep-25 A | 46143 | 46143
A20190 | Commercial Bid Evaluation(Completion) | 21 | 02-Jun-25 A | 08-Jun-25 A | 46143 | 46143
A12970 | Technical Bid Evaluation For Transformer (Power And Distribution)_IFD/IFC | 8 | 25-May-25 A | 01-Jun-25 A | 46143 | 46143
A12960 | Technical Bid Evaluation For Transformer (Power And Distribution)_RCA | 16 | 30-Aug-25 A | 17-Sep-25 A | 46143 | 46143
A12950 | Technical Bid Evaluation For Transformer (Power And Distribution)_IFA | 11 | 01-Aug-25 A | 10-Sep-25 A | 46143 | 46143
A12940 | Technical Bid Evaluation For Transformer (Power And Distribution)_RCC | 16 | 15-May-25 A | 03-Jun-25 A | 46143 | 46143
A20170 | Issue Purchase Order to Vendor for Power Transformers | 5 | 09-Jun-25 A | 29-Jul-25 A | 46143 | 46143
A12930 | Technical Bid Evaluation For Transformer (Power And Distribution)_IFR | 11 | 10-May-25 A | 22-May-25 A | 46143 | 46143
A16150 | Issue RFQ to Bidders | 20 | 15-May-25 A | 25-May-25 A | 46143 | 46143
Electrical Heat Tracing |  | 59 | 2026-02-20 | 2026-05-13 | 2026-04-21 | 2026-07-13 | 42
Electrical Heat Tracing (53 Meter for piping + 340 Meter for instrumentation) |  | 59 | 2026-02-20 | 2026-05-13 | 2026-04-21 | 2026-07-13 | 42
A22230 | Issue Purchase Order to Vendor | 14 | 2026-04-24 | 2026-05-13 | 2026-04-21 | 2026-05-12 | 42
A22220 | Commercial Bid Evaluation(Completion) | 15 | 2026-04-03 | 2026-04-23 | 2026-05-12 | 2026-06-02 | 42
A22210 | Bid Evaluation(Completion) | 15 | 2026-03-13 | 2026-04-02 | 2026-06-02 | 2026-06-23 | 42
A16270 | Issue RFQ to Bidders | 15 | 2026-02-20 | 2026-03-12 | 2026-06-23 | 2026-07-13 | 42
CP |  | 155 | 21-Nov-25 A | 2026-02-27 | 2026-05-15 | 2026-05-22 | 60
Cathodic Protection (CP) Total CS Piping Length - 499 Meters |  | 155 | 21-Nov-25 A | 2026-02-27 | 2026-05-15 | 2026-05-22 | 60
A22170 | Issue Purchase Order to Vendor | 30 | 20-Feb-26 A | 2026-02-27 | 2026-05-15 | 2026-05-15 | 60
A22160 | Commercial Bid Evaluation(Completion) | 15 | 01-Feb-26 A | 20-Feb-26 A | 46157 | 46157
A22150 | Bid Evaluation(Completion) | 45 | 24-Jan-26 A | 31-Jan-26 A | 46157 | 46157
A16210 | Issue RFQ to Bidders | 20 | 21-Nov-25 A | 18-Dec-25 A | 46157 | 46164
LV & MV Switchgears |  | 125 | 18-Mar-25 A | 01-Nov-25 A | 46134 | 46134
Switchgear (LV, MV) |  | 125 | 18-Mar-25 A | 01-Nov-25 A | 46134 | 46134
A20230 | Issue Purchase Order to Vendor for switchgear (LV, MV) | 16 | 24-Sep-25 A | 01-Nov-25 A | 46134 | 46134
A13070 | Technical Bid Evaluation For LV Switchgear_IFD/IFC | 8 | 30-May-25 A | 18-Jul-25 A | 46134 | 46134
A13060 | Technical Bid Evaluation For LV Switchgear_RCA | 16 | 02-May-25 A | 10-May-25 A | 46134 | 46134
A20250 | Commercial Bid Evaluation(Completion) | 2 | 19-Jul-25 A | 29-Jul-25 A | 46134 | 46134
A13030 | Technical Bid Evaluation For LV Switchgear_IFR | 11 | 15-Apr-25 A | 20-Apr-25 A | 46134 | 46134
A16330 | Issue RFQ to Bidders | 21 | 18-Mar-25 A | 14-Apr-25 A | 46134 | 46134
A13040 | Technical Bid Evaluation For LV Switchgear_RCC | 16 | 21-Apr-25 A | 25-Apr-25 A | 46134 | 46134
A13050 | Technical Bid Evaluation For LV Switchgear_IFA | 5 | 28-Apr-25 A | 01-May-25 A | 46134 | 46134
Switch Gear Modification (Siemens) |  | 25 | 20-Feb-25 A | 18-Mar-25 A | 46108 | 46108
TA_Switchgear (MV Switchgear Modifications) - Siemens |  | 25 | 20-Feb-25 A | 18-Mar-25 A | 46108 | 46108
A22420 | Issue Purchase Order to Vendor | 7 | 10-Mar-25 A | 18-Mar-25 A | 46108 | 46108
A56240 | TBE for Electrical System Modification_Free Issue Material | 11 | 26-Feb-25 A | 09-Mar-25 A | 46108 | 46108
A22400 | Issue RFQ to Bidders | 5 | 20-Feb-25 A | 25-Feb-25 A | 46108 | 46108
MV & LV VFD's |  | 105 | 18-Jul-25 A | 12-Aug-25 A | 46287 | 46287
Variable Fequency Drives (VFDs) LV Qty = 03 |  | 105 | 18-Jul-25 A | 12-Aug-25 A | 46287 | 46287
A20800 | Issue Purchase Order to Vendor for VFDs | 14 | 11-Aug-25 A | 12-Aug-25 A | 46287 | 46287
A20820 | Commercial Bid Evaluation(Completion) | 21 | 07-Aug-25 A | 08-Aug-25 A | 46287 | 46287
A13420 | Technical Bid Evaluation For LV Variable Frequency Drive_IFD/IFC | 8 | 04-Aug-25 A | 06-Aug-25 A | 46287 | 46287
A13410 | Technical Bid Evaluation For LV Variable Frequency Drive_RCA | 16 | 31-Jul-25 A | 01-Aug-25 A | 46287 | 46287
A13400 | Technical Bid Evaluation For LV Variable Frequency Drive_IFA | 11 | 28-Jul-25 A | 30-Jul-25 A | 46287 | 46287
A13390 | Technical Bid Evaluation For LV Variable Frequency Drive_RCC | 16 | 24-Jul-25 A | 25-Jul-25 A | 46287 | 46287
A13380 | Technical Bid Evaluation For LV Variable Frequency Drive_IFR | 11 | 21-Jul-25 A | 23-Jul-25 A | 46287 | 46287
A20790 | Issue RFQ to Bidders | 20 | 18-Jul-25 A | 20-Jul-25 A | 46287 | 46287
HV Capacitor Bay |  | 140 | 15-Apr-25 A | 15-Oct-25 A | 46184 | 46240
HV Capacitor Bay |  | 140 | 15-Apr-25 A | 15-Oct-25 A | 46184 | 46240
A13210 | Technical Bid Evaluation For Capacitor Bank_RCA | 3 | 16-Sep-25 A | 20-Sep-25 A | 46184 | 46184
A13220 | Technical Bid Evaluation For Capacitor Bank_IFD/IFC | 3 | 22-Sep-25 A | 25-Sep-25 A | 46184 | 46184
A13200 | Technical Bid Evaluation For Capacitor Bank_IFA | 3 | 11-Sep-25 A | 15-Sep-25 A | 46184 | 46184
A19990 | Issue Purchase Order to Vendor for HV Capacitor Bay | 3 | 30-Sep-25 A | 15-Oct-25 A | 46240 | 46240
A20010 | Commercial Bid Evaluation(Completion) | 3 | 01-Sep-25 A | 29-Sep-25 A | 46240 | 46240
A13190 | Technical Bid Evaluation For Capacitor Bank_RCC | 3 | 06-Sep-25 A | 10-Sep-25 A | 46240 | 46240
A13180 | Technical Bid Evaluation For Capacitor Bank_IFR | 3 | 01-Sep-25 A | 05-Sep-25 A | 46184 | 46184
A16570 | Issue RFQ to Bidders | 21 | 15-Apr-25 A | 06-May-25 A | 46184 | 46184
Power Distribution Panel and LCS, Battery & Safety Switch, Resister Bank |  | 109 | 10-Apr-25 A | 20-Jun-25 A | 46294 | 46294
NGR Panel Qty 02 |  | 109 | 10-Apr-25 A | 20-Jun-25 A | 46294 | 46294
A20290 | Issue Purchase Order to Vendor for NGR Panel | 14 | 14-Jun-25 A | 20-Jun-25 A | 46294 | 46294
A20310 | Commercial Bid Evaluation(Completion) | 21 | 21-May-25 A | 13-Jun-25 A | 46294 | 46294
A13320 | Technical Bid Evaluation For Neutral Grounding Resistor_IFD/IFC | 8 | 15-May-25 A | 20-May-25 A | 46294 | 46294
A13310 | Technical Bid Evaluation For Neutral Grounding Resistor_RCA | 16 | 14-May-25 A | 15-May-25 A | 46294 | 46294
A13300 | Technical Bid Evaluation For Neutral Grounding Resistor_IFA | 11 | 14-May-25 A | 15-May-25 A | 46294 | 46294
A13290 | Technical Bid Evaluation For Neutral Grounding Resistor_RCC | 16 | 14-May-25 A | 15-May-25 A | 46294 | 46294
A13280 | Technical Bid Evaluation For Neutral Grounding Resistor_IFR | 11 | 02-May-25 A | 13-May-25 A | 46294 | 46294
A16630 | Issue RFQ to Bidders | 21 | 10-Apr-25 A | 01-May-25 A | 46294 | 46294
Interposing Relay Panel (IRP) |  | 19 | 2026-02-20 | 2026-03-18 | 2026-04-28 | 2026-07-17 | 87
Interposing Relay Panel |  | 19 | 2026-02-20 | 2026-03-18 | 2026-04-28 | 2026-07-17 | 87
A20350 | Issue Purchase Order to Vendor for Interposing Relay Panel | 4 | 2026-03-13 | 2026-03-18 | 2026-04-28 | 2026-04-30 | 47
A58680 | Technical Bid Evaluation for Interposting Relay Panel_IFD/IFC | 3 | 2026-03-13 | 2026-03-17 | 2026-05-01 | 2026-05-05 | 88
A58670 | Technical Bid Evaluation for Interposting Relay Panel_RCA | 3 | 2026-03-10 | 2026-03-12 | 2026-05-06 | 2026-05-08 | 88
A20370 | Commercial Bid Evaluation(Completion) | 3 | 2026-03-10 | 2026-03-12 | 2026-05-11 | 2026-05-13 | 47
A58660 | Technical Bid Evaluation for Interposting Relay Panel_IFA | 3 | 2026-03-05 | 2026-03-09 | 2026-05-14 | 2026-05-18 | 47
A58650 | Technical Bid Evaluation for Interposting Relay Panel_RCC | 3 | 2026-03-02 | 2026-03-04 | 2026-07-10 | 2026-07-14 | 47
A58640 | Technical Bid Evaluation for Interposting Relay Panel_IFR | 3 | 2026-02-25 | 2026-02-27 | 2026-07-15 | 2026-07-17 | 47
A16690 | Issue RFQ to Bidders | 3 | 2026-02-20 | 2026-02-24 | 2026-05-19 | 2026-05-22 | 47
Subcontract Services |  | 198 | 14-Nov-24 A | 11-Jun-25 A | 46074 | 46108
Detail Engineering Subcontract |  | 12 | 14-Nov-24 A | 06-Dec-24 A | 46074 | 46074
A61120 | Subcontract Awarded/Signed | 3 | 29-Nov-24 A | 06-Dec-24 A | 46074 | 46074
A61110 | Bid analysis and clarifications | 3 | 23-Nov-24 A | 29-Nov-24 A | 46074 | 46074
A61100 | Technical Bid analysis and clarifications | 3 | 19-Nov-24 A | 22-Nov-24 A | 46074 | 46074
A61090 | Issue RFQ to CONTRACTORs | 3 | 14-Nov-24 A | 15-Nov-24 A | 46074 | 46074
TA Construction |  | 85 | 09-Dec-24 A | 07-Mar-25 A | 46092 | 46092
A61160 | Subcontract Awarded/Signed | 21 | 07-Mar-25 A | 07-Mar-25 A | 46092 | 46092
A61150 | Bid analysis and clarifications | 21 | 06-Feb-25 A | 06-Feb-25 A | 46092 | 46092
A61140 | Technical Bid analysis and clarifications | 21 | 08-Jan-25 A | 08-Jan-25 A | 46092 | 46092
A61130 | Issue RFQ to CONTRACTORs | 21 | 09-Dec-24 A | 09-Dec-24 A | 46092 | 46092
Main Construction |  | 85 | 09-Dec-24 A | 10-Mar-25 A | 46074 | 46074
A61200 | Subcontract Awarded/Signed | 21 | 07-Mar-25 A | 10-Mar-25 A | 46074 | 46074
A61190 | Bid analysis and clarifications | 21 | 16-Feb-25 A | 25-Feb-25 A | 46074 | 46074
A61180 | Technical Bid analysis and clarifications | 21 | 02-Feb-25 A | 15-Feb-25 A | 46074 | 46074
A61170 | Issue RFQ to CONTRACTORs | 21 | 09-Dec-24 A | 01-Feb-25 A | 46074 | 46074
Topgraphic |  | 85 | 01-Jan-25 A | 20-Mar-25 A | 46074 | 46074
A61240 | Subcontract Awarded/Signed | 21 | 02-Mar-25 A | 20-Mar-25 A | 46074 | 46074
A61230 | Bid analysis and clarifications | 21 | 04-Feb-25 A | 01-Mar-25 A | 46074 | 46074
A61220 | Technical Bid analysis and clarifications | 21 | 04-Jan-25 A | 03-Feb-25 A | 46074 | 46074
A61210 | Issue RFQ to CONTRACTORs | 21 | 01-Jan-25 A | 03-Jan-25 A | 46074 | 46074
Piling |  | 87 | 01-Apr-25 A | 11-May-25 A | 46074 | 46074
A61280 | Subcontract Awarded/Signed | 21 | 05-May-25 A | 11-May-25 A | 46074 | 46074
A61270 | Bid analysis and clarifications | 21 | 28-Apr-25 A | 04-May-25 A | 46074 | 46074
A61260 | Technical Bid analysis and clarifications | 21 | 21-Apr-25 A | 27-Apr-25 A | 46074 | 46074
A61250 | Issue RFQ to CONTRACTORs | 21 | 01-Apr-25 A | 20-Apr-25 A | 46074 | 46074
HSE Studies |  | 175 | 10-Feb-25 A | 11-Jun-25 A | 46083 | 46083
A61320 | Subcontract Awarded/Signed | 21 | 19-Apr-25 A | 11-Jun-25 A | 46083 | 46083
A61310 | Bid analysis and clarifications | 21 | 16-Mar-25 A | 18-Apr-25 A | 46083 | 46083
A61300 | Technical Bid analysis and clarifications | 21 | 02-Mar-25 A | 15-Mar-25 A | 46083 | 46083
A61290 | Issue RFQ to CONTRACTORs | 21 | 10-Feb-25 A | 01-Mar-25 A | 46083 | 46083
VSM Services Agreements |  | 85 | 01-Feb-25 A | 08-Mar-25 A | 46108 | 46108
A61360 | Subcontract Awarded/Signed | 21 | 02-Mar-25 A | 08-Mar-25 A | 46108 | 46108
A61350 | Bid analysis and clarifications | 21 | 23-Feb-25 A | 01-Mar-25 A | 46108 | 46108
A61340 | Technical Bid analysis and clarifications | 21 | 16-Feb-25 A | 22-Feb-25 A | 46108 | 46108
A61330 | Issue RFQ to CONTRACTORs | 21 | 01-Feb-25 A | 15-Feb-25 A | 46108 | 46108
As-Built & Package handover |  | 463 | 01-Jun-25 A | 2027-07-14 | 2026-03-27 | 2027-07-20 | 4
TA |  | 30 | 01-Jun-25 A | 15-Jul-25 A | 46108 | 46108
A61430 | TA As-Built | 30 | 01-Jun-25 A | 15-Jul-25 A | 46108 | 46108
Main Scope |  | 60 | 2027-04-22 | 2027-07-14 | 2027-04-28 | 2027-07-20 | 4
A61440 | Main Scope As-Built | 60 | 2027-04-22 | 2027-07-14 | 2027-04-28 | 2027-07-20 | 4
Manufacturing and Delivery |  | 489 | 25-Feb-25 A | 2026-09-29 | 2026-02-23 | 2027-07-20 | 207
79.D | All major electrical Equipment delivered to Site | 0 |  | 2026-08-20 |  |  | 136
52.C | Issue purchase orders for all major Electrical Equipments | 0 |  | 14-Jan-26 A
54.C | Issue purchase order for all major Instruments Control System | 0 |  | 07-Jan-26 A
51.C | Issue purchase orders for all remaining Mechanical / Rotating EQT. & EQT. Pkgs | 0 |  | 31-Dec-25 A |  | 46390
Equipment Packages |  | 289 | 20-Jun-25 A | 2026-08-26 | 2026-04-16 | 2027-07-20 | 231
Vessels |  | 219 | 20-Jun-25 A | 2026-06-12 | 2026-04-16 | 2026-10-30 | 98
Vessels / Drums (by Linde) |  | 219 | 20-Jun-25 A | 2026-06-12 | 2026-04-16 | 2026-10-30 | 98
FG Comp. 2nd Stage Dis. Drum (13-VV-707) |  | 175 | 20-Jun-25 A | 2026-06-08 | 2026-04-16 | 2026-08-01 | 39
A35320 | Delivery of FG Comp. 2nd Stage Dis. Drum Tag# 13-VV-707 | 28 | 2026-05-11 | 2026-06-08 | 2026-04-16 | 2026-04-16 | 55
A35270 | Materials Successfully Inspected, Tested / Ex Work | 7 | 2026-04-22 | 2026-05-01 | 2026-04-16 | 2026-04-16 | 40
A35260 | Complete Manufacturing & ready for Final Inspection | 7 | 2026-04-13 | 2026-04-22 | 2026-04-16 | 2026-04-16 | 40
A35250 | Manufacturing / Ex Works (India/UAE) | 110 | 02-Dec-25 A | 2026-04-10 |  |  | 56
A35240 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 1 | 15-Sep-25 A | 26-Sep-25 A | 46128 | 46128
A35230 | Major Sub-ordered Materials Received by Vendor and Verified | 30 | 11-Aug-25 A | 12-Sep-25 A | 46128 | 46178
A35220 | Purchase Order for Major Sub-ordered Materials | 5 | 25-Aug-25 A | 02-Sep-25 A | 46178 | 46189
A35210 | Key Vendor Drawings / Data Approved | 30 | 20-Jun-25 A | 23-Aug-25 A | 46190 | 46198
A35200 | Start Production (13-VV-707) | 0 | 19-Sep-25 A |  | 46208 | 46235
OG Comp. 2nd Stage Suc. Drum (13-VV-713) |  | 175 | 20-Jun-25 A | 2026-06-05 | 2026-04-22 | 2026-08-06 | 42
A35170 | Delivery of OG Comp. 2nd Stage Suc. Drum Tag# 13-VV-713 | 28 | 2026-05-09 | 2026-06-05 |  |  | 61
A35130 | Materials Successfully Inspected, Tested / Ex Work | 7 | 2026-04-23 | 2026-05-01 | 2026-04-22 | 2026-04-22 | 43
A35120 | Complete Manufacturing & ready for Final Inspection | 5 | 2026-04-16 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 43
A35110 | Manufacturing / Ex Works (India/UAE) | 110 | 21-Nov-25 A | 2026-04-15 | 2026-04-22 | 2026-04-22 | 61
A35100 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 1 | 15-Sep-25 A | 26-Oct-25 A | 46134 | 46134
A35090 | Major Sub-ordered Materials Received by Vendor and Verified | 30 | 11-Aug-25 A | 12-Sep-25 A | 46134 | 46189
A35080 | Purchase Order for Major Sub-ordered Materials | 5 | 25-Aug-25 A | 02-Sep-25 A | 46189 | 46196
A35070 | Key Vendor Drawings / Data Approved | 30 | 20-Jun-25 A | 23-Aug-25 A | 46196 | 46205
A35060 | Start Production (13-VV-713) | 0 | 20-Jun-25 A |  | 46212 | 46240
OG Buffer Drum (13-VV-712) |  | 180 | 20-Jun-25 A | 2026-06-12 | 2026-06-02 | 2026-09-22 | 70
A35470 | Delivery of OG Buffer Drum - Tag# 13-VV-712 | 28 | 2026-05-16 | 2026-06-12 |  |  | 102
A35410 | Materials Successfully Inspected, Tested / Ex Work | 7 | 2026-04-23 | 2026-05-01 | 2026-06-02 | 2026-06-02 | 72
A35400 | Complete Manufacturing & ready for Final Inspection | 5 | 2026-04-16 | 2026-04-22 | 2026-06-02 | 2026-06-02 | 72
A35390 | Manufacturing / Ex Works (India/UAE) | 110 | 21-Nov-25 A | 2026-04-15 | 2026-06-02 | 2026-06-02 | 102
A35380 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 1 | 15-Sep-25 A | 26-Oct-25 A | 46175 | 46175
A35370 | Major Sub-ordered Materials Received by Vendor and Verified | 30 | 11-Aug-25 A | 12-Sep-25 A | 46175 | 46230
A35360 | Purchase Order for Major Sub-ordered Materials | 5 | 25-Aug-25 A | 02-Sep-25 A | 46230 | 46234
A35350 | Key Vendor Drawings / Data Approved | 30 | 20-Jun-25 A | 23-Aug-25 A | 46237 | 46245
A35340 | Start Production (13-VV-712) | 0 | 20-Jun-25 A |  | 46260 | 46287
PSA2 Slop Drum (70-VV-1415) |  | 174 | 20-Jun-25 A | 2026-06-04 | 2026-07-18 | 2026-10-30 | 104
A35580 | Delivery of PSA2 Slop Drum Tag# 70-VV-1415 | 28 | 2026-05-08 | 2026-06-04 |  |  | 148
A35550 | Materials Successfully Inspected, Tested / Ex Work | 7 | 2026-04-23 | 2026-05-01 | 2026-07-18 | 2026-07-18 | 106
A35540 | Complete Manufacturing & ready for Final Inspection | 5 | 2026-04-16 | 2026-04-22 | 2026-07-18 | 2026-07-18 | 106
A35530 | Manufacturing / Ex Works (India/UAE) | 110 | 21-Nov-25 A | 2026-04-15 | 2026-07-18 | 2026-07-18 | 148
A35520 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 1 | 15-Sep-25 A | 26-Oct-25 A | 46221 | 46221
A35510 | Major Sub-ordered Materials Received by Vendor and Verified | 30 | 11-Aug-25 A | 12-Sep-25 A | 46221 | 46276
A35500 | Purchase Order for Major Sub-ordered Materials | 5 | 25-Aug-25 A | 02-Sep-25 A | 46276 | 46282
A35490 | Key Vendor Drawings / Data Approved | 30 | 20-Jun-25 A | 23-Aug-25 A | 46283 | 46293
A35480 | Start Production (70-VV-1415) | 0 | 20-Jun-25 A |  | 46298 | 46325
FG Comp. 2nd Stage Suc. Drum (13-VV-706) |  | 172 | 20-Jun-25 A | 2026-06-02 | 2026-04-17 | 2026-07-28 | 39
A35710 | Delivery of FG Comp. 2nd Stage Suc. Drum Tag# 13-VV-706 | 28 | 2026-05-06 | 2026-06-02 |  |  | 56
A35690 | Materials Successfully Inspected, Tested / Ex Work | 7 | 2026-04-27 | 2026-05-05 | 2026-04-17 | 2026-04-17 | 40
A35680 | Complete Manufacturing & ready for Final Inspection | 7 | 2026-04-16 | 2026-04-24 | 2026-04-17 | 2026-04-17 | 40
A35670 | Manufacturing / Ex Works (India/UAE) | 110 | 21-Nov-25 A | 2026-04-15 | 2026-04-17 | 2026-04-17 | 56
A35660 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 1 | 15-Sep-25 A | 26-Oct-25 A | 46129 | 46129
A35650 | Major Sub-ordered Materials Received by Vendor and Verified | 30 | 11-Aug-25 A | 12-Sep-25 A | 46129 | 46184
A35640 | Purchase Order for Major Sub-ordered Materials | 5 | 25-Aug-25 A | 02-Sep-25 A | 46184 | 46192
A35630 | Key Vendor Drawings / Data Approved | 30 | 20-Jun-25 A | 23-Aug-25 A | 46195 | 46203
A35620 | Start Production (13-VV-706) | 0 | 20-Jun-25 A |  | 46204 | 46231
FG Comp.1st Stage Suc. Drum (13-VV-705) |  | 210 | 20-Jun-25 A | 2026-06-01 | 2026-05-07 | 2026-08-15 | 53
A35840 | Delivery of FG Comp.1st Stage Suc. Drum (13-VV-705) | 28 | 2026-05-05 | 2026-06-01 |  |  | 75
A35830 | Materials Successfully Inspected, Tested / Ex Work | 7 | 2026-04-24 | 2026-05-04 | 2026-05-07 | 2026-05-07 | 54
A35820 | Complete Manufacturing & ready for Final Inspection | 6 | 2026-04-16 | 2026-04-23 | 2026-05-07 | 2026-05-07 | 54
A35810 | Manufacturing / Ex Works (India/UAE) | 110 | 21-Nov-25 A | 2026-04-15 | 2026-05-07 | 2026-05-07 | 76
A35800 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 21 | 15-Sep-25 A | 26-Oct-25 A | 46149 | 46149
A35790 | Major Sub-ordered Materials Received by Vendor and Verified | 30 | 11-Aug-25 A | 12-Sep-25 A | 46149 | 46204
A35780 | Purchase Order for Major Sub-ordered Materials | 5 | 25-Aug-25 A | 02-Sep-25 A | 46204 | 46211
A35770 | Key Vendor Drawings / Data Approved | 30 | 20-Jun-25 A | 23-Aug-25 A | 46212 | 46220
A35760 | Start Production (13-VV-705) | 0 | 20-Jun-25 A |  | 46222 | 46249
Vessel's Internals (05 Dimister pads) |  | 201 | 20-Jun-25 A | 2026-06-02 | 2026-05-14 | 2026-08-24 | 58
A33670 | Delivery of Vessel's Internals (05 Dimister Pads) in Warehouse | 28 | 2026-05-06 | 2026-06-02 |  |  | 83
A30020 | Materials Successfully Inspected, Tested / Ex Work | 7 | 2026-04-27 | 2026-05-05 | 2026-05-14 | 2026-05-14 | 59
A30010 | Complete Manufacturing & ready for Final Inspection | 7 | 2026-04-16 | 2026-04-24 | 2026-05-14 | 2026-05-14 | 59
A30000 | Manufacturing / Ex Works (India/UAE) | 110 | 21-Nov-25 A | 2026-04-15 | 2026-05-14 | 2026-05-14 | 83
A29990 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 1 | 15-Sep-25 A | 26-Oct-25 A | 46156 | 46156
A29980 | Major Sub-ordered Materials Received by Vendor and Verified | 20 | 11-Aug-25 A | 12-Sep-25 A | 46156 | 46211
A29970 | Purchase Order for Major Sub-ordered Materials | 5 | 25-Aug-25 A | 02-Sep-25 A | 46211 | 46219
A29960 | Key Vendor Drawings / Data Approved | 30 | 20-Jun-25 A | 23-Aug-25 A | 46220 | 46230
A33660 | Start Production | 0 | 20-Jun-25 A |  | 46231 | 46258
C4 Guard Adsorber Cooler Dripleg - (BF) |  | 188 | 20-Jun-25 A | 2026-06-02 | 2026-07-15 | 2026-10-25 | 101
A34670 | Delivery of C4 Guard Absorber Cooler Dripleg (Post - TA) | 28 | 2026-05-06 | 2026-06-02 |  |  | 145
A28220 | Materials Successfully Inspected, Tested / Ex Work | 7 | 2026-04-27 | 2026-05-05 | 2026-07-15 | 2026-07-15 | 103
A28210 | Complete Manufacturing & ready for Final Inspection | 7 | 2026-04-16 | 2026-04-24 | 2026-07-15 | 2026-07-15 | 103
A28200 | Manufacturing / Ex Works (India/UAE) | 120 | 21-Nov-25 A | 2026-04-15 | 2026-07-15 | 2026-07-15 | 145
A28190 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 7 | 15-Sep-25 A | 26-Oct-25 A | 46218 | 46218
A28180 | Major Sub-ordered Materials Received by Vendor and Verified | 21 | 11-Aug-25 A | 12-Sep-25 A | 46218 | 46273
A28170 | Purchase Order for Major Sub-ordered Materials | 30 | 25-Aug-25 A | 02-Sep-25 A | 46273 | 46281
A28160 | Key Vendor Drawings / Data Approved | 60 | 20-Jun-25 A | 23-Aug-25 A | 46282 | 46290
A34660 | Start Production | 0 | 20-Jun-25 A |  | 46293 | 46320
Water Collection & Sanitary Waste Water Pumps |  | 235 | 10-Sep-25 A | 2026-06-05 | 2026-06-20 | 2026-10-18 | 93
Sanitary Waste Water Sump Pump |  | 205 | 10-Sep-25 A | 2026-06-05 | 2026-06-20 | 2026-10-06 | 85
A30720 | Manufacturing / Ex Works (India/UAE) | 140 | 01-Jan-26 A | 2026-04-20 |  |  | 121
A33860 | Delivery of Sanitary Waste Water Sump Pump (01) | 28 | 2026-05-09 | 2026-06-05 | 2026-06-20 | 2026-06-20 | 123
A30740 | Materials Successfully Inspected, Tested / Ex Work | 7 | 2026-04-30 | 2026-05-08 | 2026-06-20 | 2026-06-20 | 87
A30730 | Complete Manufacturing & ready for Final Inspection | 7 | 2026-04-21 | 2026-04-29 | 2026-06-20 | 2026-06-20 | 87
A30710 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 1 | 01-Jan-26 A | 15-Jan-26 A | 46193 | 46193
A30700 | Major Sub-ordered Materials Received by Vendor and Verified | 40 | 19-Dec-25 A | 02-Jan-26 A | 46193 | 46253
A30690 | Purchase Order for Major Sub-ordered Materials | 5 | 08-Dec-25 A | 19-Dec-25 A | 46253 | 46262
A30680 | Key Vendor Drawings / Data Approved | 30 | 21-Nov-25 A | 04-Dec-25 A | 46262 | 46273
A33850 | Start Production | 0 | 10-Sep-25 A |  | 46273 | 46301
Water Collection Sump Pump ll |  | 212 | 10-Sep-25 A | 2026-06-05 | 2026-07-03 | 2026-10-18 | 93
A33880 | Delivery of Water Sump Pump (02) | 28 | 2026-05-09 | 2026-06-05 |  |  | 135
A30830 | Materials Successfully Inspected, Tested / Ex Work | 7 | 2026-04-30 | 2026-05-08 | 2026-07-03 | 2026-07-03 | 95
A30820 | Complete Manufacturing & ready for Final Inspection | 7 | 2026-04-21 | 2026-04-29 | 2026-07-03 | 2026-07-03 | 95
A30810 | Manufacturing / Ex Works (India/UAE) | 60 | 01-Jan-26 A | 2026-04-20 | 2026-07-03 | 2026-07-03 | 133
A30800 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 1 | 01-Jan-26 A | 15-Jan-26 A | 46206 | 46206
A30790 | Major Sub-ordered Materials Received by Vendor and Verified | 40 | 19-Dec-25 A | 02-Jan-26 A | 46206 | 46266
A30780 | Purchase Order for Major Sub-ordered Materials | 5 | 11-Dec-25 A | 19-Dec-25 A | 46266 | 46274
A30770 | Key Vendor Drawings / Data Approved | 30 | 21-Nov-25 A | 10-Dec-25 A | 46275 | 46283
A33870 | Start Production | 0 | 10-Sep-25 A |  | 46286 | 46313
EOT Cranes |  | 227 | 15-Aug-25 A | 2026-08-13 | 2026-04-21 | 2027-07-20 | 239
EOT Crane for FG Compressor (1 = 60 Ton) |  | 227 | 15-Aug-25 A | 2026-08-13 | 2026-04-21 | 2027-07-20 | 239
A33920 | Delivery of Material in Warehouse (FG) Crane | 21 | 2026-07-24 | 2026-08-13 |  |  | 62
A31010 | Materials Successfully Inspected, Tested / Ex Work | 7 | 2026-07-15 | 2026-07-23 | 2027-06-09 | 2027-06-09 | 44
A31000 | Complete Manufacturing & ready for Final Inspection | 7 | 2026-07-06 | 2026-07-14 | 2026-04-21 | 2026-05-25 | 44
A30990 | Manufacturing / Ex Works (India/UAE) | 100 | 2026-03-27 | 2026-07-05 | 2026-05-26 | 2026-05-27 | 60
A30970 | Major Sub-ordered Materials Received by Vendor and Verified | 30 | 2026-03-26 | 2026-05-07 | 2027-06-09 | 2027-07-20 | 313
A30950 | Key Vendor Drawings / Data Approved | 50 | 23-Jan-26 A | 2026-03-26 | 2026-05-27 | 2026-09-04 | 42
A30980 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 1 | 2026-03-26 | 2026-03-27 | 2026-09-04 | 2026-09-14 | 60
A30960 | Purchase Order for Major Sub-ordered Materials | 5 | 01-Feb-26 A | 12-Feb-26 A | 46280 | 46288
A33910 | Start Production | 0 | 15-Aug-25 A |  | 46289 | 46309
EOT Crane for OG Compressor (1 = 25 Ton) |  | 205 | 10-Sep-25 A | 2026-08-13 | 2026-04-28 | 2027-07-20 | 239
A33940 | Delivery of (OG) Crane | 21 | 2026-07-24 | 2026-08-13 |  |  | 69
A31100 | Materials Successfully Inspected, Tested / Ex Work | 7 | 2026-07-15 | 2026-07-23 | 2027-06-09 | 2027-06-09 | 49
A31090 | Complete Manufacturing & ready for Final Inspection | 7 | 2026-07-06 | 2026-07-14 | 2026-04-28 | 2026-06-01 | 49
A31080 | Manufacturing / Ex Works (India/UAE) | 100 | 2026-03-27 | 2026-07-05 | 2026-06-02 | 2026-06-03 | 67
A31060 | Major Sub-ordered Materials Received by Vendor and Verified | 30 | 2026-03-26 | 2026-05-07 | 2027-06-09 | 2027-07-20 | 313
A31070 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 1 | 2026-03-26 | 2026-03-27 | 2026-06-03 | 2026-09-11 | 67
A31050 | Purchase Order for Major Sub-ordered Materials | 5 | 01-Feb-26 A | 12-Feb-26 A | 46276 | 46286
A31040 | Key Vendor Drawings / Data Approved | 35 | 23-Jan-26 A | 2026-03-26 | 2026-09-22 | 2026-09-30 | 47
A33930 | Start Production | 0 | 10-Sep-25 A |  | 46296 | 46316
Heat Exchangers |  | 208 | 11-Jul-25 A | 2026-04-27 | 2026-05-14 | 2026-11-04 | 132
Heat Exchanger (Type S & T = 06 Nos) |  | 208 | 11-Jul-25 A | 2026-04-27 | 2026-05-14 | 2026-11-04 | 132
FG Comp. Interstage Cooler (BEM) - Tag# 13-HE-703 |  | 208 | 11-Jul-25 A | 2026-04-27 | 2026-05-14 | 2026-07-18 | 55
A36380 | Delivery of FG Comp. Interstage Cooler (BEM) - Tag# 13-HE-703 | 28 | 2026-03-30 | 2026-04-27 |  |  | 83
A36350 | Manufacturing / Ex Works (India/UAE) | 150 | 21-Nov-25 A | 2026-02-27 | 2026-05-14 | 2026-05-14 | 84
A36370 | Materials Successfully Inspected, Tested / Ex Work | 11 | 2026-03-13 | 2026-03-30 | 2026-05-14 | 2026-05-14 | 60
A36360 | Complete Manufacturing & ready for Final Inspection | 10 | 2026-02-27 | 2026-03-13 | 2026-05-14 | 2026-05-14 | 60
A36340 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 10 | 15-Sep-25 A | 26-Oct-25 A | 46156 | 46156
A36330 | Major Sub-ordered Materials Received by Vendor and Verified | 35 | 11-Aug-25 A | 12-Sep-25 A | 46156 | 46164
A36320 | Purchase Order for Major Sub-ordered Materials | 35 | 29-Aug-25 A | 02-Sep-25 A | 46164 | 46177
A36310 | Key Vendor Drawings / Data Approved | 30 | 18-Jul-25 A | 28-Aug-25 A | 46178 | 46192
A36300 | Start Production (13-HE-703) | 0 | 11-Jul-25 A |  | 46194 | 46221
OG Comp. After Cooler (BEU) - Tag# 13-HE-709 |  | 205 | 11-Jul-25 A | 2026-04-22 | 2026-06-21 | 2026-08-22 | 82
A36520 | Delivery of OG Comp. After Cooler (BEU) - Tag# 13-HE-709 | 28 | 2026-03-25 | 2026-04-22 |  |  | 122
A36500 | Materials Successfully Inspected, Tested / Ex Work | 11 | 2026-03-10 | 2026-03-25 | 2026-06-21 | 2026-06-21 | 87
A36490 | Complete Manufacturing & ready for Final Inspection | 10 | 2026-02-24 | 2026-03-10 | 2026-06-21 | 2026-06-21 | 87
A36480 | Manufacturing / Ex Works (India/UAE) | 95 | 21-Nov-25 A | 2026-02-24 | 2026-06-21 | 2026-06-21 | 121
A36470 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 10 | 15-Sep-25 A | 26-Oct-25 A | 46194 | 46194
A36460 | Major Sub-ordered Materials Received by Vendor and Verified | 35 | 11-Aug-25 A | 12-Sep-25 A | 46194 | 46199
A36450 | Purchase Order for Major Sub-ordered Materials | 35 | 29-Aug-25 A | 02-Sep-25 A | 46199 | 46212
A36440 | Key Vendor Drawings / Data Approved | 30 | 18-Jul-25 A | 28-Aug-25 A | 46213 | 46227
A36430 | Start Production (13-HE-709) | 0 | 11-Jul-25 A |  | 46228 | 46256
FG Comp. After Cooler (BEM) - Tag# 13-HE-704 |  | 205 | 11-Jul-25 A | 2026-04-22 | 2026-05-17 | 2026-07-18 | 57
A36660 | Delivery of FG Comp. After Cooler (BEM) - Tag# 13-HE-704 | 28 | 2026-03-25 | 2026-04-22 |  |  | 87
A36630 | Materials Successfully Inspected, Tested / Ex Work | 11 | 2026-03-10 | 2026-03-25 | 2026-05-17 | 2026-05-17 | 62
A36620 | Complete Manufacturing & ready for Final Inspection | 10 | 2026-02-24 | 2026-03-10 | 2026-05-17 | 2026-05-17 | 62
A36610 | Manufacturing / Ex Works (India/UAE) | 95 | 21-Nov-25 A | 2026-02-24 | 2026-05-17 | 2026-05-17 | 86
A36600 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 10 | 15-Sep-25 A | 26-Oct-25 A | 46159 | 46159
A36590 | Major Sub-ordered Materials Received by Vendor and Verified | 35 | 11-Aug-25 A | 12-Sep-25 A | 46159 | 46164
A36580 | Purchase Order for Major Sub-ordered Materials | 35 | 29-Aug-25 A | 02-Sep-25 A | 46164 | 46177
A36570 | Key Vendor Drawings / Data Approved | 30 | 18-Jul-25 A | 28-Aug-25 A | 46178 | 46192
A36560 | Start Production (13-HE-704) | 0 | 11-Jul-25 A |  | 46194 | 46221
OG Comp. Interstage Cooler (BEU) (13-HE-708) |  | 205 | 11-Jul-25 A | 2026-04-22 | 2026-06-21 | 2026-08-22 | 82
A36800 | Delivery of GG Comp. Interstage Cooler (BEU) (13-HE-708) | 28 | 2026-03-25 | 2026-04-22 |  |  | 122
A36760 | Materials Successfully Inspected, Tested / Ex Work | 11 | 2026-03-10 | 2026-03-25 | 2026-06-21 | 2026-06-21 | 87
A36750 | Complete Manufacturing & ready for Final Inspection | 10 | 2026-02-24 | 2026-03-10 | 2026-06-21 | 2026-06-21 | 87
A36740 | Manufacturing / Ex Works (India/UAE) | 95 | 21-Nov-25 A | 2026-02-24 | 2026-06-21 | 2026-06-21 | 121
A36730 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 10 | 15-Sep-25 A | 26-Oct-25 A | 46194 | 46194
A36720 | Major Sub-ordered Materials Received by Vendor and Verified | 35 | 11-Aug-25 A | 12-Sep-25 A | 46194 | 46199
A36710 | Purchase Order for Major Sub-ordered Materials | 35 | 29-Aug-25 A | 02-Sep-25 A | 46199 | 46212
A36700 | Key Vendor Drawings / Data Approved | 30 | 18-Jul-25 A | 28-Aug-25 A | 46213 | 46227
A36690 | Start Production (13-HE-708) | 0 | 11-Jul-25 A |  | 46228 | 46256
C4 Guard Regen. Gas Cooler (BEU) (Tag#50-HE-1410) |  | 204 | 11-Jul-25 A | 2026-04-26 | 2026-08-29 | 2026-11-04 | 132
A36940 | Delivery of C4 Guard Regen. Gas Cooler (BEU) (Tag#50-HE-1410) | 24 | 2026-04-03 | 2026-04-26 |  |  | 192
A36890 | Materials Successfully Inspected, Tested / Ex Work | 11 | 2026-03-10 | 2026-03-24 | 2026-08-29 | 2026-08-29 | 136
A36880 | Complete Manufacturing & ready for Final Inspection | 10 | 2026-02-24 | 2026-03-09 | 2026-08-29 | 2026-08-29 | 136
A36860 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 10 | 15-Sep-25 A | 26-Oct-25 A | 46263 | 46263
A36870 | Manufacturing / Ex Works (India/UAE) | 80 | 21-Nov-25 A | 2026-02-23 | 2026-08-29 | 2026-08-29 | 190
A36850 | Major Sub-ordered Materials Received by Vendor and Verified | 35 | 11-Aug-25 A | 12-Sep-25 A | 46263 | 46267
A36840 | Purchase Order for Major Sub-ordered Materials | 35 | 29-Aug-25 A | 02-Sep-25 A | 46267 | 46280
A36830 | Key Vendor Drawings / Data Approved | 30 | 18-Jul-25 A | 28-Aug-25 A | 46281 | 46295
A36820 | Start Production (50-HE-1410) | 0 | 11-Jul-25 A |  | 46307 | 46330
HVAC |  | 231 | 29-Aug-25 A | 2026-08-26 | 2026-06-15 | 2026-12-18 | 79
HVAC |  | 231 | 29-Aug-25 A | 2026-08-26 | 2026-06-15 | 2026-12-18 | 79
A33900 | Delivery of Material HVAC (Main Equipments) | 28 | 2026-07-30 | 2026-08-26 |  |  | 114
A34770 | Delivery of HVAC Ducts, E&I Material , Clading, Piping, Insulation, Supports & Accessories | 12 | 2026-07-30 | 2026-08-10 | 2026-06-15 | 2026-06-15 | 113
A30920 | Materials Successfully Inspected, Tested / Ex Work | 7 | 2026-07-21 | 2026-07-29 | 2026-06-15 | 2026-06-15 | 81
A30910 | Complete Manufacturing & ready for Final Inspection | 7 | 2026-07-10 | 2026-07-20 | 2026-06-15 | 2026-06-15 | 81
A30900 | Manufacturing / Ex Works (India/UAE) | 140 | 2026-02-20 | 2026-07-09 | 2026-06-15 | 2026-06-15 | 115
A30870 | Purchase Order for Major Sub-ordered Materials | 10 | 02-Dec-25 A | 19-Dec-25 A | 46188 | 46328
A30890 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 1 | 01-Jan-26 A | 15-Jan-26 A | 46328 | 46336
A30880 | Major Sub-ordered Materials Received by Vendor and Verified | 45 | 19-Dec-25 A | 01-Jan-26 A | 46337 | 46345
A30860 | Key Vendor Drawings / Data Approved | 60 | 03-Sep-25 A | 01-Dec-25 A | 46346 | 46357
A33890 | Start Production | 0 | 29-Aug-25 A |  | 46347 | 46374
Bulk Materials |  | 489 | 15-Mar-25 A | 2026-09-29 | 2026-02-23 | 2027-07-20 | 207
Drip Leg |  | 207 | 03-Sep-25 A | 2026-07-22 | 2026-03-31 | 2026-08-30 | 26
OG Comp. Dis. Drip leg (02 Nos) |  | 207 | 03-Sep-25 A | 2026-07-22 | 2026-03-31 | 2026-08-30 | 26
A33840 | Delivery of OG Compressor Discharge Drip Leg (02) | 42 | 2026-06-11 | 2026-07-22 |  |  | 38
A30650 | Materials Successfully Inspected, Tested / Ex Work | 7 | 2026-06-02 | 2026-06-10 | 2026-03-31 | 2026-03-31 | 27
A30640 | Complete Manufacturing & ready for Final Inspection | 7 | 2026-05-22 | 2026-06-01 | 2026-03-31 | 2026-03-31 | 27
A30630 | Manufacturing / Ex Works (India/UAE) | 90 | 2026-02-21 | 2026-05-21 | 2026-03-31 | 2026-03-31 | 39
A30610 | Major Sub-ordered Materials Received by Vendor and Verified | 25 | 10-Nov-25 A | 17-Nov-25 A | 46112 | 46113
A30600 | Purchase Order for Major Sub-ordered Materials | 8 | 03-Nov-25 A | 09-Nov-25 A | 46113 | 46203
A30620 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 1 | 2026-02-20 | 2026-02-20 | 2026-06-30 | 2026-07-08 | 39
A30590 | Key Vendor Drawings / Data Approved | 60 | 01-Oct-25 A | 03-Nov-25 A | 46212 | 46220
A33830 | Start Production | 0 | 03-Sep-25 A |  | 46222 | 46264
Fire Fighting Equipment |  | 165 | 27-Oct-25 A | 2026-07-27 | 2026-06-02 | 2026-11-02 | 69
VESDA (Very Early Smoke Detection Apparatus) |  | 163 | 27-Oct-25 A | 2026-07-23 | 2026-06-02 | 2026-11-02 | 71
A34200 | Delivery and Manufacturing VESDA | 28 | 2026-06-26 | 2026-07-23 |  |  | 102
A32270 | Materials Successfully Inspected, Tested / Ex Work | 8 | 2026-06-16 | 2026-06-25 | 2026-06-02 | 2026-06-02 | 72
A32260 | Complete Manufacturing & ready for Final Inspection | 8 | 2026-06-05 | 2026-06-16 | 2026-06-02 | 2026-06-02 | 72
A32250 | Manufacturing / Ex Works (India/UAE) | 105 | 2026-02-20 | 2026-06-04 | 2026-06-02 | 2026-06-02 | 102
A32240 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 1 | 06-Jan-26 A | 09-Jan-26 A | 46175 | 46175
A32230 | Major Sub-ordered Materials Received by Vendor and Verified | 40 | 29-Dec-25 A | 02-Jan-26 A | 46175 | 46280
A32210 | Key Vendor Drawings / Data Approved | 50 | 19-Dec-25 A | 26-Dec-25 A | 46280 | 46289
A32220 | Purchase Order for Major Sub-ordered Materials | 10 | 23-Dec-25 A | 04-Jan-26 A | 46289 | 46300
A34190 | Start Production | 0 | 27-Oct-25 A |  | 46301 | 46328
Fire Fighting Equipment |  | 86 | 2026-03-19 | 2026-07-27 | 2026-06-19 | 2026-10-26 | 64
A34000 | Delivery of Fire Fighting Equipments | 21 | 2026-07-06 | 2026-07-27 | 2026-06-19 |  | 91
A31370 | Materials Successfully Inspected, Tested / Ex Work | 7 | 2026-06-25 | 2026-07-06 | 2026-06-19 | 2026-07-09 | 65
A31360 | Complete Manufacturing & ready for Final Inspection | 7 | 2026-06-16 | 2026-06-25 | 2026-07-10 | 2026-07-20 | 65
A31350 | Manufacturing / Ex Works (India/UAE) | 35 | 2026-05-12 | 2026-06-16 | 2026-07-21 | 2026-08-10 | 91
A31340 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 1 | 2026-05-11 | 2026-05-12 | 2026-08-11 | 2026-08-12 | 91
A31330 | Major Sub-ordered Materials Received by Vendor and Verified | 15 | 2026-04-20 | 2026-05-11 | 2026-08-12 | 2026-09-16 | 65
A31320 | Purchase Order for Major Sub-ordered Materials | 7 | 2026-04-09 | 2026-04-20 | 2026-09-16 | 2026-09-24 | 65
A31310 | Key Vendor Drawings / Data Approved | 15 | 2026-03-20 | 2026-04-09 | 2026-09-25 | 2026-10-05 | 65
A33990 | Start Production | 0 | 2026-03-19 |  | 46301 | 46321 | 91
Tail Gas Filter/Silencer/Colesor |  | 211 | 30-Jan-26 A | 14-Feb-26 A | 46344 | 46344
Coalescer - (BF) |  | 211 | 30-Jan-26 A | 14-Feb-26 A | 46344 | 46344
A34690 | Delivery of Coalescer (Post TA) | 30 | 13-Feb-26 A | 14-Feb-26 A
A28310 | Materials Successfully Inspected, Tested / Ex Work | 7 | 11-Feb-26 A | 12-Feb-26 A | 46344 | 46344
A28300 | Complete Manufacturing & ready for Final Inspection | 7 | 09-Feb-26 A | 10-Feb-26 A | 46344 | 46344
A28290 | Manufacturing / Ex Works (India/UAE) | 100 | 07-Feb-26 A | 08-Feb-26 A | 46344 | 46344
A28280 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 7 | 05-Feb-26 A | 06-Feb-26 A | 46344 | 46344
A28270 | Major Sub-ordered Materials Received by Vendor and Verified | 45 | 03-Feb-26 A | 04-Feb-26 A | 46344 | 46344
A28260 | Purchase Order for Major Sub-ordered Materials | 15 | 01-Feb-26 A | 02-Feb-26 A | 46344 | 46344
A28250 | Key Vendor Drawings / Data Approved | 50 | 30-Jan-26 A | 31-Jan-26 A | 46344 | 46344
A34680 | Start Production | 0 | 30-Jan-26 A |  | 46344 | 46344
Steel Structure Greenfield (material +sandwitch Panel) |  | 139 | 21-Jun-25 A | 2026-05-17 | 2026-02-23 | 2026-11-23 | 129
Civil Bulk Material |  | 122 | 21-Jun-25 A | 06-Oct-25 A | 46349 | 46349
A28500 | Delivery of Civil Bulk Material | 15 | 30-Sep-25 A | 06-Oct-25 A
A28490 | Materials Successfully Inspected, Tested / Ex Work | 7 | 22-Sep-25 A | 29-Sep-25 A | 46349 | 46349
A28480 | Complete Manufacturing & ready for Final Inspection | 15 | 08-Sep-25 A | 20-Sep-25 A | 46349 | 46349
A28470 | Manufacturing / Ex Works (India/UAE) | 30 | 18-Aug-25 A | 15-Sep-25 A | 46349 | 46349
A28460 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 7 | 01-Sep-25 A | 06-Sep-25 A | 46349 | 46349
A28450 | Major Sub-ordered Materials Received by Vendor and Verified | 15 | 25-Aug-25 A | 30-Aug-25 A | 46349 | 46349
A28440 | Purchase Order for Major Sub-ordered Materials | 30 | 29-Jul-25 A | 23-Aug-25 A | 46349 | 46349
A28430 | Key Vendor Drawings / Data Approved | 25 | 23-Jun-25 A | 28-Jul-25 A | 46349 | 46349
A33330 | Start Production | 0 | 21-Jun-25 A |  | 46349 | 46349
Structural Steel |  | 124 | 18-Sep-25 A | 2026-05-17 | 2026-02-23 | 2026-05-18 | 1
A33340 | Delivery of Structural Steel GF | 5 | 2026-05-13 | 2026-05-17 |  |  | 1
A28580 | Materials Successfully Inspected, Tested / Ex Work | 5 | 2026-05-06 | 2026-05-12 |  |  | 1
A28570 | Complete Manufacturing & ready for Final Inspection | 5 | 2026-04-29 | 2026-05-05 | 2026-02-23 | 2026-02-23 | 1
A28560 | Manufacturing / Ex Works | 47 | 2026-03-13 | 2026-04-28 | 2026-02-23 | 2026-02-23 | 1
A28550 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 7 | 17-Feb-26 A | 17-Feb-26 A | 46095 | 46095
A28540 | Major Sub-ordered Materials Received by Vendor and Verified | 14 | 17-Feb-26 A | 2026-03-12 | 2026-02-23 | 2026-03-13 | 1
A28530 | Purchase Order for Major Sub-ordered Materials | 5 | 25-Jan-26 A | 16-Feb-26 A | 46095 | 46142
A28520 | Key Vendor Drawings / Data Approved | 20 | 19-Dec-25 A | 24-Jan-26 A | 46142 | 46148
A28590 | COMPANY Final decision on Compressor Shelter Height | 0 |  | 15-Dec-25 A | 46149 | 46155
A33350 | Start Production | 0 | 18-Sep-25 A |  | 46156 | 46160
Tubing Material [SS tubes, Connectors, unions, plugs etc.] |  | 100 | 2026-04-16 | 2026-09-13 | 2026-06-02 | 2026-10-30 | 35
Tubing Material [SS tubes, Connectors, unions, plugs etc] |  | 100 | 2026-04-16 | 2026-09-13 | 2026-06-02 | 2026-10-30 | 35
A33710 | Delivery at site - (Tubing Material) | 10 | 2026-09-04 | 2026-09-13 | 2026-06-02 |  | 47
A30200 | Materials Successfully Inspected, Tested / Ex Work | 7 | 2026-08-26 | 2026-09-03 | 2026-06-02 | 2026-06-29 | 33
A30190 | Complete Manufacturing & ready for Final Inspection | 7 | 2026-08-17 | 2026-08-25 | 2026-06-30 | 2026-07-20 | 33
A30180 | Manufacturing / Ex Works (India/UAE) | 50 | 2026-06-26 | 2026-08-15 | 2026-07-21 | 2026-08-10 | 46
A30170 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 1 | 2026-06-25 | 2026-06-26 | 2026-08-11 | 2026-08-12 | 46
A30160 | Major Sub-ordered Materials Received by Vendor and Verified | 15 | 2026-06-04 | 2026-06-25 | 2026-08-12 | 2026-10-01 | 32
A30150 | Purchase Order for Major Sub-ordered Materials | 15 | 2026-05-14 | 2026-06-04 | 2026-10-01 | 2026-10-09 | 32
A30140 | Key Vendor Drawings / Data Approved | 20 | 2026-04-17 | 2026-05-14 | 2026-10-12 | 2026-10-20 | 32
A33700 | Start Production | 0 | 2026-04-16 |  | 46316 | 46325 | 46
Steel Structure Brownfield |  | 345 | 15-Mar-25 A | 2026-04-19 | 2026-03-27 | 2026-09-20 | 104
Steel Structure - Post TA - BF |  | 151 | 18-Sep-25 A | 2026-04-19 | 2026-07-24 | 2026-09-20 | 104
A34610 | Manufacturing / Ex Works | 40 | 18-Feb-26 A | 2026-03-31 |  |  | 154
A34600 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 7 | 17-Feb-26 A | 17-Feb-26 A | 46227 | 46227
A34590 | Major Sub-ordered Materials Received by Vendor and Verified | 21 | 16-Feb-26 A | 16-Feb-26 A | 46227 | 46227
A34650 | Delivery of (Steel Structure - PostTA) | 5 | 2026-04-15 | 2026-04-19 | 2026-07-24 | 2026-07-24 | 154
A34630 | Materials Successfully Inspected, Tested / Ex Work | 5 | 2026-04-08 | 2026-04-14 | 2026-07-24 | 2026-07-24 | 110
A34580 | Purchase Order for Major Sub-ordered Materials | 14 | 09-Feb-26 A | 13-Feb-26 A | 46227 | 46267
A34620 | Complete Manufacturing & ready for Final Inspection | 5 | 2026-04-01 | 2026-04-07 | 2026-09-02 | 2026-09-08 | 110
A34570 | Key Vendor Drawings / Data Approved | 20 | 01-Feb-26 A | 06-Feb-26 A | 46274 | 46280
A34560 | Start Production | 0 | 18-Sep-25 A |  | 46281 | 46285
TA_Steel Structure ( Additional Steel Structure required for BFW) |  | 99 | 15-Mar-25 A | 09-May-25 A | 46108 | 46108
A34450 | Delivery at Site by EPC ( Fabricated, Painted & Galvanized TA Steel Structure ) | 4 | 26-Apr-25 A | 09-May-25 A
A27860 | Materials Successfully Inspected, Tested / Ex Work | 5 | 19-Apr-25 A | 25-Apr-25 A | 46108 | 46108
A27800 | Key Vendor Drawings / Data Approved | 5 | 15-Mar-25 A | 20-Mar-25 A | 46108 | 46108
A27850 | Complete Manufacturing & ready for Final Inspection | 2 | 12-Apr-25 A | 18-Apr-25 A | 46108 | 46108
A27840 | Manufacturing / Ex Works (India/UAE) | 45 | 05-Apr-25 A | 11-Apr-25 A | 46108 | 46108
A27830 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 1 | 29-Mar-25 A | 04-Apr-25 A | 46108 | 46108
A27820 | Major Sub-ordered Materials Received by Vendor and Verified | 5 | 22-Mar-25 A | 28-Mar-25 A | 46108 | 46108
A27810 | Purchase Order for Major Sub-ordered Materials | 5 | 17-Mar-25 A | 21-Mar-25 A | 46108 | 46108
A34490 | Start Production | 0 | 15-Mar-25 A |  | 46108 | 46108
Telecom (ACS+LAN +CCTV+PAGA) |  | 185 | 11-Dec-25 A | 2026-09-09 | 2026-04-08 | 2026-12-10 | 63
Telecom (ACS + CCTV + PAGA) Integration |  | 123 | 11-Dec-25 A | 2026-08-21 | 2026-06-11 | 2026-12-10 | 75
A34020 | Delivery of Telecom (ACS + CCTV + PAGA) Integration | 14 | 2026-08-07 | 2026-08-21 |  |  | 111
A31460 | Materials Successfully Inspected, Tested / Ex Work | 7 | 2026-07-29 | 2026-08-07 | 2026-06-11 | 2026-07-09 | 79
A31450 | Complete Manufacturing & ready for Final Inspection | 7 | 2026-07-20 | 2026-07-29 | 2026-06-29 | 2026-07-09 | 79
A31440 | Manufacturing / Ex Works (India/UAE) | 90 | 2026-04-21 | 2026-07-20 | 2026-07-10 | 2026-08-07 | 111
A31430 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 1 | 2026-04-20 | 2026-04-21 | 2026-08-10 | 2026-08-11 | 111
A31420 | Major Sub-ordered Materials Received by Vendor and Verified | 21 | 2026-03-20 | 2026-04-20 | 2026-08-11 | 2026-11-09 | 79
A31400 | Key Vendor Drawings / Data Approved | 40 | 20-Feb-26 A | 2026-03-20 | 2026-11-09 | 2026-11-17 | 79
A31410 | Purchase Order for Major Sub-ordered Materials | 10 | 11-Dec-25 A | 2026-03-20 | 2026-11-18 | 2026-11-26 | 79
A34010 | Start Production | 0 | 19-Dec-25 A |  | 46353 | 46366
Acess Control System |  | 184 | 12-Dec-25 A | 2026-09-09 | 2026-04-08 | 2026-10-26 | 33
A34040 | Delivery of ACS | 14 | 2026-08-26 | 2026-09-09 |  |  | 47
A31550 | Materials Successfully Inspected, Tested / Ex Work | 7 | 2026-08-17 | 2026-08-26 | 2026-05-27 | 2026-05-27 | 33
A31540 | Complete Manufacturing & ready for Final Inspection | 7 | 2026-08-06 | 2026-08-17 | 2026-04-08 | 2026-05-26 | 33
A31530 | Manufacturing / Ex Works (India/UAE) | 90 | 2026-05-08 | 2026-08-06 | 2026-05-27 | 2026-06-23 | 47
A31520 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 1 | 2026-05-07 | 2026-05-08 | 2026-06-24 | 2026-06-25 | 47
A31510 | Major Sub-ordered Materials Received by Vendor and Verified | 20 | 2026-04-09 | 2026-05-07 | 2026-06-25 | 2026-09-23 | 33
A31490 | Key Vendor Drawings / Data Approved | 50 | 20-Feb-26 A | 2026-04-09 | 2026-09-23 | 2026-10-01 | 33
A31500 | Purchase Order for Major Sub-ordered Materials | 10 | 12-Dec-25 A | 25-Dec-25 A | 46297 | 46307
A34030 | Start Production | 0 | 12-Dec-25 A |  | 46308 | 46321
CCTV |  | 124 | 19-Dec-25 A | 2026-08-25 | 2026-05-13 | 2026-11-15 | 58
A34250 | Delivery of CCTV | 7 | 2026-08-18 | 2026-08-25 |  |  | 82
A32360 | Materials Successfully Inspected, Tested / Ex Work | 7 | 2026-08-07 | 2026-08-18 | 2026-06-10 | 2026-06-23 | 58
A32350 | Complete Manufacturing & ready for Final Inspection | 7 | 2026-07-29 | 2026-08-07 | 2026-05-13 | 2026-06-23 | 58
A32340 | Manufacturing / Ex Works (India/UAE) | 75 | 2026-05-15 | 2026-07-29 | 2026-06-24 | 2026-08-04 | 82
A32330 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 1 | 2026-05-14 | 2026-05-15 | 2026-08-05 | 2026-08-06 | 82
A32320 | Major Sub-ordered Materials Received by Vendor and Verified | 30 | 2026-04-02 | 2026-05-14 | 2026-08-06 | 2026-10-20 | 58
A34220 | Key Vendor Drawings / Data Approved | 30 | 2026-02-20 | 2026-04-02 | 2026-10-20 | 2026-10-28 | 58
A32310 | Purchase Order for Major Sub-ordered Materials | 10 | 2026-03-19 | 2026-04-02 | 2026-10-29 | 2026-11-06 | 58
A34210 | Start Production | 0 | 19-Dec-25 A |  | 46335 | 46341
PAGA + Telephone |  | 173 | 11-Dec-25 A | 2026-08-21 | 2026-05-22 | 2026-11-22 | 64
A34060 | Delivery of PAGA + Telephone | 14 | 2026-08-07 | 2026-08-21 |  |  | 93
A31640 | Materials Successfully Inspected, Tested / Ex Work | 7 | 2026-07-29 | 2026-08-07 | 2026-05-22 | 2026-06-19 | 65
A31630 | Complete Manufacturing & ready for Final Inspection | 7 | 2026-07-20 | 2026-07-29 | 2026-06-09 | 2026-06-19 | 65
A31620 | Manufacturing / Ex Works (India/UAE) | 90 | 2026-04-21 | 2026-07-20 | 2026-06-22 | 2026-07-20 | 91
A31580 | Key Vendor Drawings / Data Approved | 50 | 19-Dec-25 A | 2026-03-20 | 2026-07-21 | 2026-07-22 | 65
A31610 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 1 | 2026-04-20 | 2026-04-21 | 2026-07-22 | 2026-10-20 | 91
A31600 | Major Sub-ordered Materials Received by Vendor and Verified | 21 | 2026-03-20 | 2026-04-20 | 2026-10-20 | 2026-10-28 | 65
A34050 | Start Production | 0 | 19-Dec-25 A |  | 46324 | 46332
A31590 | Purchase Order for Major Sub-ordered Materials | 10 | 11-Dec-25 A | 2026-03-20 | 2026-11-09 | 2026-11-22 | 65
Lighting Fixtures |  | 81 | 2026-05-22 | 2026-09-22 | 2026-09-11 | 2027-01-10 | 75
Lighting Fixtures (Almost 50% Exd = 354 Nos) |  | 81 | 2026-05-22 | 2026-09-22 | 2026-09-11 | 2027-01-10 | 75
A34240 | Delivery of Material in Warehouse Lighting Fixtures | 7 | 2026-09-15 | 2026-09-22 | 2026-09-11 |  | 110
A32450 | Materials Successfully Inspected, Tested / Ex Work | 5 | 2026-09-08 | 2026-09-15 | 2026-09-11 | 2026-10-09 | 78
A32440 | Complete Manufacturing & ready for Final Inspection | 5 | 2026-09-01 | 2026-09-08 | 2026-10-12 | 2026-10-23 | 78
A32430 | Manufacturing / Ex Works (India/UAE) | 35 | 2026-07-28 | 2026-09-01 | 2026-10-26 | 2026-11-13 | 110
A32420 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 1 | 2026-07-27 | 2026-07-28 | 2026-11-15 | 2026-11-16 | 110
A32410 | Major Sub-ordered Materials Received by Vendor and Verified | 15 | 2026-07-06 | 2026-07-27 | 2026-11-16 | 2026-12-21 | 79
A32400 | Purchase Order for Major Sub-ordered Materials | 10 | 2026-06-22 | 2026-07-06 | 2026-12-21 | 2026-12-25 | 79
A32390 | Key Vendor Drawings / Data Approved | 21 | 2026-05-25 | 2026-06-22 | 2026-12-28 | 2027-01-01 | 79
A34230 | Start Production | 0 | 2026-05-22 |  | 46391 | 46397 | 111
Manual Valve |  | 168 | 20-Nov-25 A | 2026-07-30 | 2026-05-18 | 2026-10-26 | 61
Manual Valves (Gate 9 Nos, Check 6 Nos, Globe Valves 64 Nos) |  | 168 | 20-Nov-25 A | 2026-07-30 | 2026-05-18 | 2026-10-26 | 61
A33690 | Delivery at site warehouse for Manual Valves (Gate 9 Nos, Check 6 Nos, Globe Valves 64 Nos) | 21 | 2026-07-10 | 2026-07-30 |  |  | 88
A30110 | Materials Successfully Inspected, Tested / Ex Work | 7 | 2026-07-01 | 2026-07-09 | 2026-05-18 | 2026-05-29 | 62
A30100 | Complete Manufacturing & ready for Final Inspection | 7 | 2026-06-22 | 2026-06-30 | 2026-06-01 | 2026-06-05 | 62
A30090 | Manufacturing / Ex Works (India/UAE) | 100 | 2026-03-13 | 2026-06-21 | 2026-06-07 | 2026-06-08 | 86
A30070 | Major Sub-ordered Materials Received by Vendor and Verified | 30 | 2026-03-12 | 2026-04-23 | 2026-06-05 | 2026-07-17 | 61
A30050 | Key Vendor Drawings / Data Approved | 30 | 20-Feb-26 A | 2026-03-05 | 2026-06-08 | 2026-09-16 | 61
A30080 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 1 | 2026-03-12 | 2026-03-13 | 2026-09-16 | 2026-09-24 | 86
A30060 | Purchase Order for Major Sub-ordered Materials | 5 | 2026-03-05 | 2026-03-12 | 2026-09-25 | 2026-10-05 | 61
A33680 | Start Production | 0 | 20-Nov-25 A |  | 46301 | 46321
Piping Bulk |  | 230 | 01-Sep-25 A | 2026-09-29 | 2026-03-30 | 2027-07-20 | 207
Piping Lot for Post TA |  | 135 | 01-Sep-25 A | 2026-03-06 | 2026-04-22 | 2026-05-06 | 40
84.D50 | Delivery of Piping Material in Warehouse (1st Lot, GF) | 10 | 10-Feb-26 A | 2026-03-06 |  |  | 61
A28040 | Materials Successfully Inspected, Tested / Ex Work | 10 | 02-Feb-26 A | 06-Feb-26 A | 46134 | 46134
A28030 | Complete Manufacturing & ready for Final Inspection | 7 | 26-Jan-26 A | 30-Jan-26 A | 46134 | 46134
A28020 | Manufacturing / Ex Works (India/UAE) | 80 | 26-Dec-25 A | 18-Jan-26 A | 46134 | 46134
A28010 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 7 | 03-Nov-25 A | 25-Dec-25 A | 46134 | 46134
A28000 | Major Sub-ordered Materials Received by Vendor and Verified | 15 | 22-Oct-25 A | 31-Oct-25 A | 46134 | 46134
A27990 | Purchase Order for Major Sub-ordered Materials | 5 | 02-Sep-25 A | 08-Sep-25 A | 46134 | 46134
A34500 | Start Production | 0 | 01-Sep-25 A |  | 46134 | 46148
Piping Supports (Swing Hangers) for Post TA |  | 97 | 2026-02-20 | 2026-07-16 | 2026-03-30 | 2026-09-08 | 37
A34520 | Delivery of Material in Warehouse ( Piping Swing Hangers - PostTA) | 7 | 2026-07-09 | 2026-07-16 | 2026-03-30 |  | 54
A28130 | Materials Successfully Inspected, Tested / Ex Work | 5 | 2026-07-02 | 2026-07-09 | 2026-03-30 | 2026-04-24 | 26
A28120 | Complete Manufacturing & ready for Final Inspection | 10 | 2026-06-18 | 2026-07-02 | 2026-04-27 | 2026-05-01 | 26
A28110 | Manufacturing / Ex Works | 56 | 2026-04-23 | 2026-06-18 | 2026-05-04 | 2026-05-22 | 38
A28100 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 7 | 2026-04-16 | 2026-04-23 | 2026-05-25 | 2026-06-01 | 38
A28090 | Major Sub-ordered Materials Received by Vendor and Verified | 15 | 2026-03-26 | 2026-04-16 | 2026-06-01 | 2026-07-27 | 26
A28080 | Purchase Order for Major Sub-ordered Materials | 5 | 2026-03-19 | 2026-03-26 | 2026-07-27 | 2026-08-07 | 26
A28070 | Key Vendor Drawings / Data Approved | 20 | 2026-02-20 | 2026-03-19 | 2026-08-10 | 2026-08-14 | 26
A34510 | Start Production | 0 | 2026-02-20 |  | 46267 | 46273 | 38
Piping 1st Lot for GF |  | 92 | 01-Sep-25 A | 31-Jan-26 A | 46132 | 46132
84.D40 | Delivery of Piping Material in Warehouse (1st Lot, GF) | 7 | 26-Jan-26 A | 31-Jan-26 A
A28670 | Materials Successfully Inspected, Tested / Ex Work | 5 | 19-Jan-26 A | 23-Jan-26 A | 46132 | 46132
A28660 | Complete Manufacturing & ready for Final Inspection | 2 | 19-Jan-26 A | 23-Jan-26 A | 46132 | 46132
A28650 | Manufacturing / Ex Works (India/UAE) | 60 | 26-Dec-25 A | 18-Jan-26 A | 46132 | 46132
A28640 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 7 | 19-Dec-25 A | 25-Dec-25 A | 46132 | 46132
A28630 | Major Sub-ordered Materials Received by Vendor and Verified | 10 | 03-Sep-25 A | 15-Sep-25 A | 46132 | 46132
A28620 | Purchase Order for Major Sub-ordered Materials | 5 | 02-Sep-25 A | 08-Sep-25 A | 46132 | 46132
A33360 | Start Production | 0 | 01-Sep-25 A |  | 46132 | 46132
Piping 2nd Lot for GF (CS Material) |  | 69 | 26-Dec-25 A | 2026-04-17 | 2026-05-19 | 2026-07-15 | 58
A28740 | Manufacturing / Ex Works (India/UAE) | 60 | 15-Jan-26 A | 2026-03-21 |  |  | 88
85.D10 | Delivery of Piping Material in Warehouse (2nd Lot) | 14 | 2026-04-04 | 2026-04-17 | 2026-05-19 | 2026-05-19 | 89
A28760 | Materials Successfully Inspected, Tested / Ex Work | 5 | 2026-03-30 | 2026-04-03 | 2026-05-19 | 2026-05-19 | 63
A28750 | Complete Manufacturing & ready for Final Inspection | 5 | 2026-03-23 | 2026-03-27 | 2026-05-19 | 2026-05-19 | 63
A28730 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 7 | 09-Jan-26 A | 16-Jan-26 A | 46161 | 46191
A28720 | Major Sub-ordered Materials Received by Vendor and Verified | 15 | 26-Dec-25 A | 09-Jan-26 A | 46191 | 46197
A28710 | Purchase Order for Major Sub-ordered Materials | 10 | 28-Dec-25 A | 02-Jan-26 A | 46198 | 46204
A33370 | Start Production | 0 | 26-Dec-25 A |  | 46205 | 46218
Piping 3rd Lot GF (CS Material) |  | 82 | 2026-04-22 | 2026-08-21 | 2026-05-14 | 2026-09-11 | 14
A28860 | Delivery of Piping Material in Warehouse (Final Lot) | 14 | 2026-08-07 | 2026-08-21 | 2026-05-14 |  | 21
A28850 | Materials Successfully Inspected, Tested / Ex Work | 7 | 2026-07-29 | 2026-08-07 | 2026-05-14 | 2026-05-20 | 15
A28840 | Complete Manufacturing & ready for Final Inspection | 5 | 2026-07-22 | 2026-07-29 | 2026-05-21 | 2026-06-10 | 15
A28830 | Manufacturing / Ex Works (India/UAE) | 60 | 2026-05-23 | 2026-07-22 | 2026-06-11 | 2026-06-14 | 21
A28820 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 3 | 2026-05-20 | 2026-05-23 | 2026-06-14 | 2026-08-13 | 21
A28810 | Major Sub-ordered Materials Received by Vendor and Verified | 15 | 2026-04-29 | 2026-05-20 | 2026-08-13 | 2026-08-19 | 15
A28800 | Purchase Order for Major Sub-ordered Materials | 5 | 2026-04-22 | 2026-04-29 | 2026-08-20 | 2026-08-28 | 15
A33380 | Start Production | 0 | 2026-04-22 |  | 46263 | 46276 | 21
Piping Supports (Swing Hangers) for GF |  | 46 | 2026-07-24 | 2026-09-29 | 2027-05-17 | 2027-07-20 | 207
A29040 | Delivery of Pipng Supports | 15 | 2026-09-15 | 2026-09-29 | 2027-05-17 |  | 294
A29030 | Materials Successfully Inspected, Tested / Ex Work | 6 | 2026-09-07 | 2026-09-14 | 2027-05-17 | 2027-05-21 | 210
A29020 | Complete Manufacturing & ready for Final Inspection | 5 | 2026-08-31 | 2026-09-04 | 2027-05-24 | 2027-05-28 | 210
A29010 | Manufacturing / Ex Works (India/UAE) | 10 | 2026-08-19 | 2026-08-29 | 2027-05-31 | 2027-06-04 | 295
A29000 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 5 | 2026-08-14 | 2026-08-19 | 2027-06-06 | 2027-06-11 | 295
A28990 | Major Sub-ordered Materials Received by Vendor and Verified | 5 | 2026-08-07 | 2026-08-14 | 2027-06-11 | 2027-06-21 | 210
A28980 | Purchase Order for Major Sub-ordered Materials | 5 | 2026-07-31 | 2026-08-07 | 2027-06-21 | 2027-06-25 | 210
A28970 | Key Vendor Drawings / Data Approved | 5 | 2026-07-24 | 2026-07-31 | 2027-06-28 | 2027-07-05 | 210
A33400 | Start Production | 0 | 2026-07-24 |  | 46574 | 46588 | 296
HDPE Piping |  | 97 | 2026-02-20 | 2026-07-16 | 2026-04-09 | 2026-09-02 | 33
HDPE Piping GF (Fire Water Lines) |  | 97 | 2026-02-20 | 2026-07-16 | 2026-04-09 | 2026-09-02 | 33
A28950 | Delivery of HDPE Piping GF (Fire Water Lines) | 14 | 2026-07-02 | 2026-07-16 | 2026-04-09 |  | 48
A28940 | Materials Successfully Inspected, Tested / Ex Work | 7 | 2026-06-23 | 2026-07-02 | 2026-04-09 | 2026-05-06 | 34
A28930 | Complete Manufacturing & ready for Final Inspection | 5 | 2026-06-16 | 2026-06-23 | 2026-05-07 | 2026-05-13 | 34
A28920 | Manufacturing / Ex Works | 60 | 2026-04-17 | 2026-06-16 | 2026-05-14 | 2026-06-03 | 48
A28910 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 1 | 2026-04-16 | 2026-04-17 | 2026-06-04 | 2026-06-05 | 48
A28900 | Major Sub-ordered Materials Received by Vendor and Verified | 15 | 2026-03-26 | 2026-04-16 | 2026-06-05 | 2026-08-04 | 34
A28890 | Purchase Order for Major Sub-ordered Materials | 5 | 2026-03-19 | 2026-03-26 | 2026-08-04 | 2026-08-10 | 34
A28880 | Key Vendor Drawings / Data Approved | 20 | 2026-02-20 | 2026-03-19 | 2026-08-11 | 2026-08-19 | 34
A33390 | Start Production | 0 | 2026-02-20 |  | 46254 | 46267 | 48
Piping SP Items (strainer, filters) |  | 109 | 2026-03-27 | 2026-09-04 | 2026-05-25 | 2026-10-31 | 40
Specialized Items (Orifice Flanges) CS 300# 1" - 6" = 08 Nos |  | 103 | 2026-04-01 | 2026-09-01 | 2026-06-02 | 2026-10-31 | 44
A30300 | Delivery of Orifice Flanges | 14 | 2026-08-18 | 2026-09-01 | 2026-06-02 |  | 61
A30290 | Materials Successfully Inspected, Tested / Ex Work | 5 | 2026-08-11 | 2026-08-18 | 2026-06-02 | 2026-06-22 | 44
A30280 | Complete Manufacturing & ready for Final Inspection | 5 | 2026-08-04 | 2026-08-11 | 2026-06-23 | 2026-06-29 | 44
A30270 | Manufacturing / Ex Works (India/UAE) | 75 | 2026-05-21 | 2026-08-04 | 2026-06-30 | 2026-07-20 | 62
A30260 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 1 | 2026-05-20 | 2026-05-21 | 2026-07-21 | 2026-07-22 | 62
A30250 | Major Sub-ordered Materials Received by Vendor and Verified | 15 | 2026-04-29 | 2026-05-20 | 2026-07-22 | 2026-10-05 | 44
A30240 | Purchase Order for Major Sub-ordered Materials | 5 | 2026-04-22 | 2026-04-29 | 2026-10-05 | 2026-10-09 | 44
A30230 | Key Vendor Drawings / Data Approved | 15 | 2026-04-01 | 2026-04-22 | 2026-10-12 | 2026-10-16 | 44
A33720 | Start Production | 0 | 2026-04-01 |  | 46313 | 46326 | 62
Specialized Items (Strainer/Filter) CS & SS 150 # -300# 2" - 26" = 08 Nos |  | 109 | 2026-03-27 | 2026-09-04 | 2026-05-25 | 2026-10-31 | 40
A30390 | Delivery of Strainer/Filters Flanges | 28 | 2026-08-08 | 2026-09-04 | 2026-05-25 |  | 57
A30380 | Materials Successfully Inspected, Tested / Ex Work | 5 | 2026-08-03 | 2026-08-07 | 2026-05-25 | 2026-06-19 | 40
A30370 | Complete Manufacturing & ready for Final Inspection | 5 | 2026-07-27 | 2026-07-31 | 2026-06-22 | 2026-06-26 | 40
A30360 | Manufacturing / Ex Works (India/UAE) | 56 | 2026-05-30 | 2026-07-25 | 2026-06-29 | 2026-07-24 | 57
A30350 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 1 | 2026-05-29 | 2026-05-30 | 2026-07-26 | 2026-07-27 | 57
A30340 | Major Sub-ordered Materials Received by Vendor and Verified | 20 | 2026-05-01 | 2026-05-29 | 2026-07-27 | 2026-09-21 | 40
A30330 | Purchase Order for Major Sub-ordered Materials | 5 | 2026-04-24 | 2026-05-01 | 2026-09-21 | 2026-09-25 | 40
A30320 | Key Vendor Drawings / Data Approved | 20 | 2026-03-30 | 2026-04-24 | 2026-09-28 | 2026-10-02 | 40
A33730 | Start Production | 0 | 2026-03-27 |  | 46299 | 46326 | 58
Pressure / Temperature / Level Instruments, Flowmeters |  | 147 | 20-Dec-25 A | 2026-09-02 | 2026-03-27 | 2026-10-07 | 25
PT, TT & DPT [PT 50 Nos, TT 33 Nos, DPT 20 Nos] |  | 147 | 20-Dec-25 A | 2026-09-02 | 2026-03-27 | 2026-10-07 | 25
A33520 | Delivery of Material in Warehouse for PT,TT & DPT | 8 | 2026-08-25 | 2026-09-02 |  |  | 35
A29570 | Materials Successfully Inspected, Tested / Ex Work | 15 | 2026-08-04 | 2026-08-25 | 2026-03-27 | 2026-04-23 | 25
A29560 | Complete Manufacturing & ready for Final Inspection | 15 | 2026-07-14 | 2026-08-04 | 2026-04-24 | 2026-05-21 | 25
A29550 | Manufacturing / Ex Works (India/UAE) | 60 | 2026-05-15 | 2026-07-14 | 2026-05-22 | 2026-06-18 | 35
A29540 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 1 | 2026-05-14 | 2026-05-15 | 2026-06-19 | 2026-06-20 | 35
A29530 | Major Sub-ordered Materials Received by Vendor and Verified | 20 | 2026-04-16 | 2026-05-14 | 2026-06-20 | 2026-08-19 | 25
A29520 | Purchase Order for Major Sub-ordered Materials | 20 | 2026-03-19 | 2026-04-16 | 2026-08-19 | 2026-09-08 | 25
A29510 | Key Vendor Drawings / Data Approved | 20 | 2026-02-20 | 2026-03-19 | 2026-09-09 | 2026-09-29 | 25
A33510 | Start Production | 0 | 20-Dec-25 A |  | 46295 | 46302
Instrument Bulk Material |  | 237 | 24-May-25 A | 2026-09-24 | 2026-03-12 | 2026-11-28 | 46
Gauges (PG, TG, PDG) PG - 10bar & 40bar = 19 Nos, DP = 05 Nos, TG = 09 Nos |  | 103 | 2026-03-25 | 2026-08-24 | 2026-06-03 | 2026-10-30 | 49
A34350 | Delivery of Magnetic Level Gauges, PG, TG, PDG | 14 | 2026-08-10 | 2026-08-24 | 2026-06-03 |  | 68
A32900 | Materials Successfully Inspected, Tested / Ex Work | 7 | 2026-07-30 | 2026-08-10 | 2026-06-03 | 2026-07-01 | 50
A32890 | Complete Manufacturing & ready for Final Inspection | 7 | 2026-07-21 | 2026-07-30 | 2026-07-02 | 2026-07-22 | 50
A32880 | Manufacturing / Ex Works (India/UAE) | 40 | 2026-06-11 | 2026-07-21 | 2026-07-23 | 2026-08-12 | 70
A32870 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 7 | 2026-06-04 | 2026-06-11 | 2026-08-13 | 2026-08-20 | 70
A32860 | Major Sub-ordered Materials Received by Vendor and Verified | 15 | 2026-05-14 | 2026-06-04 | 2026-08-20 | 2026-09-29 | 50
A32850 | Purchase Order for Major Sub-ordered Materials | 15 | 2026-04-23 | 2026-05-14 | 2026-09-29 | 2026-10-07 | 50
A32840 | Key Vendor Drawings / Data Approved | 21 | 2026-03-25 | 2026-04-23 | 2026-10-08 | 2026-10-16 | 50
A34340 | Start Production | 0 | 2026-03-25 |  | 46312 | 46325 | 70
Analyzers |  | 171 | 24-May-25 A | 12-Jul-25 A | 46354 | 46354
A57730 | Delivery of Material in Warehouse for Analyzer | 21 | 06-Jul-25 A | 12-Jul-25 A
A57720 | Materials Successfully Inspected, Tested / Ex Work | 7 | 29-Jun-25 A | 05-Jul-25 A | 46354 | 46354
A57710 | Complete Manufacturing & ready for Final Inspection | 7 | 29-Jun-25 A | 05-Jul-25 A | 46354 | 46354
A57700 | Manufacturing / Ex Works (India/UAE) | 110 | 22-Jun-25 A | 28-Jun-25 A | 46354 | 46354
A57690 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 1 | 15-Jun-25 A | 21-Jun-25 A | 46354 | 46354
A57680 | Major Sub-ordered Materials Received by Vendor and Verified | 30 | 07-Jun-25 A | 14-Jun-25 A | 46354 | 46354
A57670 | Purchase Order for Major Sub-ordered Materials | 15 | 01-Jun-25 A | 07-Jun-25 A | 46354 | 46354
A57660 | Key Vendor Drawings / Data Approved | 30 | 25-May-25 A | 31-May-25 A | 46354 | 46354
A57650 | Start Production | 0 | 24-May-25 A |  | 46354 | 46354
Flow Elements Venturi |  | 136 | 11-Dec-25 A | 2026-08-27 | 2026-04-30 | 2026-11-04 | 49
A57910 | Delivery of Material in Warehouse for Flow Elements Venturi | 14 | 2026-08-14 | 2026-08-27 | 2026-04-30 |  | 69
A57890 | Materials Successfully Inspected, Tested / Ex Work | 7 | 2026-08-05 | 2026-08-13 | 2026-04-30 | 2026-05-28 | 49
A57880 | Complete Manufacturing & ready for Final Inspection | 7 | 2026-07-27 | 2026-08-04 | 2026-05-08 | 2026-05-28 | 49
A57840 | Manufacturing / Ex Works (India/UAE) | 90 | 2026-04-27 | 2026-07-26 | 2026-05-29 | 2026-06-26 | 67
A57870 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 7 | 2026-04-20 | 2026-04-27 | 2026-06-27 | 2026-07-04 | 67
A57860 | Major Sub-ordered Materials Received by Vendor and Verified | 21 | 2026-03-20 | 2026-04-20 | 2026-07-04 | 2026-10-02 | 49
A57830 | Key Vendor Drawings / Data Approved | 21 | 2026-02-20 | 2026-03-20 | 2026-10-02 | 2026-10-12 | 49
A57850 | Purchase Order for Major Sub-ordered Materials | 15 | 11-Dec-25 A | 2026-03-20 | 2026-10-13 | 2026-10-21 | 49
A57900 | Start Production | 0 | 2026-02-20 |  | 46317 | 46330 | 69
Flow Elements Orifice |  | 103 | 18-Dec-25 A | 2026-07-25 | 2026-07-03 | 2026-11-04 | 72
A57820 | Delivery of Material in Warehouse for Flow Elements Orifice | 12 | 2026-07-13 | 2026-07-25 |  |  | 103
A57810 | Materials Successfully Inspected, Tested / Ex Work | 7 | 2026-07-02 | 2026-07-13 | 2026-07-03 | 2026-07-03 | 75
A57800 | Complete Manufacturing & ready for Final Inspection | 7 | 2026-06-23 | 2026-07-02 | 2026-07-03 | 2026-07-03 | 75
A57790 | Manufacturing / Ex Works (India/UAE) | 90 | 2026-03-25 | 2026-06-23 | 2026-07-03 | 2026-07-03 | 105
A57780 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 5 | 01-Feb-26 A | 2026-02-24 | 2026-07-03 | 2026-07-08 | 133
A57770 | Major Sub-ordered Materials Received by Vendor and Verified | 50 | 23-Jan-26 A | 31-Jan-26 A | 46211 | 46301
A57760 | Purchase Order for Major Sub-ordered Materials | 15 | 09-Jan-26 A | 22-Jan-26 A | 46301 | 46309
A57750 | Key Vendor Drawings / Data Approved | 30 | 18-Dec-25 A | 08-Jan-26 A | 46310 | 46318
A57740 | Start Production | 0 | 18-Dec-25 A |  | 46319 | 46330
Cable Tray and Instrument Junction Box (Perforated Cable tray Heavy duty = 5982 Mtrs, JBs = 73 Nos) |  | 141 | 2026-02-26 | 2026-09-24 | 2026-03-12 | 2026-10-07 | 9
A33500 | Delivery of Material in Warehouse for Cable Tray and Instrument Junction Box | 21 | 2026-09-04 | 2026-09-24 | 2026-03-12 |  | 13
A29480 | Materials Successfully Inspected, Tested / Ex Work | 7 | 2026-08-26 | 2026-09-03 | 2026-03-12 | 2026-05-06 | 9
A29470 | Complete Manufacturing & ready for Final Inspection | 7 | 2026-08-17 | 2026-08-25 | 2026-05-07 | 2026-05-15 | 9
A29460 | Manufacturing / Ex Works (India/UAE) | 60 | 2026-06-16 | 2026-08-15 | 2026-05-18 | 2026-06-26 | 12
A29450 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 1 | 2026-06-15 | 2026-06-16 | 2026-06-28 | 2026-06-29 | 12
A29440 | Major Sub-ordered Materials Received by Vendor and Verified | 30 | 2026-05-04 | 2026-06-15 | 2026-06-29 | 2026-08-28 | 9
A29430 | Purchase Order for Major Sub-ordered Materials | 7 | 2026-04-23 | 2026-05-04 | 2026-08-28 | 2026-09-07 | 9
A29420 | Key Vendor Drawings / Data Approved | 40 | 2026-02-27 | 2026-04-23 | 2026-09-08 | 2026-09-16 | 9
A33490 | Start Production | 0 | 2026-02-26 |  | 46282 | 46302 | 13
Fibre Optic Cable (Armoured, Telecom/IT/MAS) |  | 135 | 18-Aug-25 A | 2026-03-25 | 2026-03-19 | 2026-09-16 | 119
A32790 | Manufacturing / Ex Works (India/UAE) | 100 | 25-Dec-25 A | 23-Jan-26 A
A34330 | Delivery of Fibre Optic Cable | 14 | 2026-03-12 | 2026-03-25 | 2026-03-19 | 2026-03-19 | 175
A32810 | Materials Successfully Inspected, Tested / Ex Work | 7 | 2026-03-03 | 2026-03-11 | 2026-08-14 | 2026-08-14 | 125
A32800 | Complete Manufacturing & ready for Final Inspection | 7 | 2026-02-20 | 2026-03-02 | 2026-08-14 | 2026-08-14 | 125
A32780 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 1 | 25-Dec-25 A | 16-Jan-26 A | 46248 | 46248
A32770 | Major Sub-ordered Materials Received by Vendor and Verified | 30 | 19-Dec-25 A | 26-Dec-25 A | 46248 | 46248
A32760 | Purchase Order for Major Sub-ordered Materials | 15 | 11-Dec-25 A | 19-Dec-25 A | 46248 | 46258
A32750 | Key Vendor Drawings / Data Approved | 20 | 21-Nov-25 A | 10-Dec-25 A | 46259 | 46267
A34320 | Start Production | 0 | 18-Aug-25 A |  | 46268 | 46281
Magnetic Level Gauge ( 09 Nos) |  | 127 | 2026-02-26 | 2026-09-04 | 2026-04-01 | 2026-10-07 | 23
A33580 | Delivery of Material in Warehouse for Magnetic Level Gauge | 21 | 2026-08-14 | 2026-09-04 | 2026-04-01 |  | 33
A29840 | Materials Successfully Inspected, Tested / Ex Work | 7 | 2026-08-05 | 2026-08-14 | 2026-04-01 | 2026-04-29 | 23
A29830 | Complete Manufacturing & ready for Final Inspection | 7 | 2026-07-27 | 2026-08-05 | 2026-04-30 | 2026-05-13 | 23
A29820 | Manufacturing / Ex Works (India/UAE) | 70 | 2026-05-18 | 2026-07-27 | 2026-05-14 | 2026-06-11 | 31
A29810 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 7 | 2026-05-11 | 2026-05-18 | 2026-06-12 | 2026-06-19 | 31
A29800 | Major Sub-ordered Materials Received by Vendor and Verified | 21 | 2026-04-10 | 2026-05-11 | 2026-06-19 | 2026-08-28 | 23
A29790 | Purchase Order for Major Sub-ordered Materials | 10 | 2026-03-27 | 2026-04-10 | 2026-08-28 | 2026-09-07 | 23
A29780 | Key Vendor Drawings / Data Approved | 21 | 2026-02-27 | 2026-03-27 | 2026-09-08 | 2026-09-16 | 23
A33570 | Start Production | 0 | 2026-02-26 |  | 46282 | 46302 | 33
Instrument Bulk Materia l(Single & Multicore = Approx. 78,130 Mtr, FO Cables JB & Cable Trays)) |  | 107 | 11-Dec-25 A | 2026-05-22 | 2026-07-13 | 2026-10-09 | 94
A34460 | Delivery of Material in Warehouse Instrument Bulk (Post TA) | 21 | 2026-05-01 | 2026-05-22 | 2026-07-13 |  | 140
A27950 | Materials Successfully Inspected, Tested / Ex Work | 5 | 2026-04-24 | 2026-05-01 | 2026-07-13 | 2026-08-07 | 100
A27940 | Complete Manufacturing & ready for Final Inspection | 5 | 2026-04-17 | 2026-04-24 | 2026-08-03 | 2026-08-07 | 100
A27930 | Manufacturing / Ex Works (India/UAE) | 21 | 2026-03-27 | 2026-04-17 | 2026-08-10 | 2026-08-14 | 142
A27920 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 1 | 2026-03-26 | 2026-03-27 | 2026-08-16 | 2026-08-17 | 142
A27910 | Major Sub-ordered Materials Received by Vendor and Verified | 5 | 2026-03-19 | 2026-03-26 | 2026-08-17 | 2026-09-07 | 101
A27890 | Key Vendor Drawings / Data Approved | 20 | 2026-02-20 | 2026-03-19 | 2026-09-07 | 2026-09-11 | 101
A34470 | Start Production | 0 | 2026-02-20 |  | 46279 | 46283 | 143
A27900 | Purchase Order for Major Sub-ordered Materials | 5 | 11-Dec-25 A | 2026-03-19 | 2026-09-19 | 2026-10-09 | 101
Earthing & Power Cables |  | 161 | 05-Nov-25 A | 2026-07-17 | 2026-05-22 | 2026-10-18 | 64
Earthing and Power Cables |  | 161 | 05-Nov-25 A | 2026-07-17 | 2026-05-22 | 2026-10-18 | 64
A33320 | Delivery of Earthing and Power Cables | 14 | 2026-07-04 | 2026-07-17 |  |  | 93
A28400 | Materials Successfully Inspected, Tested / Ex Work | 7 | 2026-06-25 | 2026-07-03 | 2026-05-22 | 2026-05-22 | 65
A28360 | Major Sub-ordered Materials Received by Vendor and Verified | 45 | 13-Feb-26 A | 2026-03-10 | 2026-05-22 | 2026-05-22 | 65
A28390 | Complete Manufacturing & ready for Final Inspection | 7 | 2026-06-16 | 2026-06-24 | 2026-05-22 | 2026-06-09 | 65
A28380 | Manufacturing / Ex Works (India/UAE) | 90 | 2026-03-18 | 2026-06-15 | 2026-06-10 | 2026-06-17 | 91
A28350 | Purchase Order for Major Sub-ordered Materials | 30 | 31-Jan-26 A | 12-Feb-26 A | 46190 | 46280
A28340 | Key Vendor Drawings / Data Approved | 20 | 24-Jan-26 A | 30-Jan-26 A | 46280 | 46288
A28370 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 7 | 2026-03-11 | 2026-03-17 | 2026-09-24 | 2026-10-02 | 91
A33310 | Start Production | 0 | 05-Nov-25 A |  | 46300 | 46313
Electrical Bulk |  | 207 | 03-Oct-25 A | 2026-08-28 | 2026-04-30 | 2026-10-26 | 42
Cable Trays, JBs, Conduit Pipe, Cable Lugs, etc |  | 63 | 2026-05-13 | 2026-08-17 | 2026-07-06 | 2026-10-07 | 37
A33440 | Delivery of Material in Warehouse for Cable Trays, JBs, Conduit Pipe, Cable Lugs, etc | 14 | 2026-08-03 | 2026-08-17 | 2026-07-06 |  | 52
A29210 | Materials Successfully Inspected, Tested / Ex Work | 5 | 2026-07-27 | 2026-08-03 | 2026-07-06 | 2026-07-31 | 38
A29200 | Complete Manufacturing & ready for Final Inspection | 5 | 2026-07-20 | 2026-07-27 | 2026-08-03 | 2026-08-07 | 38
A29190 | Manufacturing / Ex Works (India/UAE) | 25 | 2026-06-25 | 2026-07-20 | 2026-08-10 | 2026-08-14 | 52
A29180 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 1 | 2026-06-24 | 2026-06-25 | 2026-08-15 | 2026-08-16 | 52
A29170 | Major Sub-ordered Materials Received by Vendor and Verified | 5 | 2026-06-17 | 2026-06-24 | 2026-08-16 | 2026-09-10 | 37
A29160 | Purchase Order for Major Sub-ordered Materials | 5 | 2026-06-10 | 2026-06-17 | 2026-09-10 | 2026-09-16 | 37
A29150 | Key Vendor Drawings / Data Approved | 20 | 2026-05-14 | 2026-06-10 | 2026-09-17 | 2026-09-23 | 37
A33430 | Start Production | 0 | 2026-05-13 |  | 46289 | 46302 | 53
Power Cables ( 11kV & 33kV) |  | 131 | 03-Oct-25 A | 2026-05-05 | 2026-07-27 | 2026-10-07 | 106
A61540 | Delivery of Material in Warehouse for Cable Trays, JBs, Conduit Pipe, Cable Lugs, etc | 21 | 2026-04-14 | 2026-05-05 | 2026-07-27 | 2026-07-27 | 156
A61530 | Materials Successfully Inspected, Tested / Ex Work | 5 | 2026-04-07 | 2026-04-14 | 2026-07-27 | 2026-07-27 | 112
A61520 | Complete Manufacturing & ready for Final Inspection | 5 | 2026-03-31 | 2026-04-07 |  |  | 112
A61460 | Key Vendor Drawings / Data Approved | 20 | 03-Oct-25 A | 23-Oct-25 A | 46230 | 46234
A61510 | Manufacturing / Ex Works (India/UAE) | 25 | 2026-03-07 | 2026-03-31 | 2026-08-03 | 2026-08-07 | 156
A61500 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 1 | 2026-03-06 | 2026-03-06 | 2026-08-08 | 2026-08-09 | 156
A61490 | Major Sub-ordered Materials Received by Vendor and Verified | 5 | 2026-02-27 | 2026-03-05 | 2026-08-09 | 2026-09-03 | 111
A61470 | Start Production | 0 | 24-Oct-25 A |  | 46268 | 46274
A61480 | Purchase Order for Major Sub-ordered Materials | 5 | 2026-02-20 | 2026-02-26 | 2026-09-10 | 2026-09-16 | 111
A61450 | Power Cables | 5 | 10-Oct-25 A | 17-Oct-25 A | 46282 | 46302
LCS & Snap Switches |  | 62 | 2026-05-29 | 2026-08-28 | 2026-07-28 | 2026-10-26 | 42
A33480 | Delivery of Material in Warehouse for LCS & snap Switches | 7 | 2026-08-21 | 2026-08-28 | 2026-07-28 |  | 60
A29390 | Materials Successfully Inspected, Tested / Ex Work | 5 | 2026-08-14 | 2026-08-21 | 2026-07-28 | 2026-08-17 | 42
A29380 | Complete Manufacturing & ready for Final Inspection | 4 | 2026-08-10 | 2026-08-14 | 2026-08-17 | 2026-08-24 | 42
A29370 | Manufacturing / Ex Works (India/UAE) | 28 | 2026-07-11 | 2026-08-08 | 2026-08-24 | 2026-09-07 | 59
A29360 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 1 | 2026-07-10 | 2026-07-11 | 2026-09-07 | 2026-09-08 | 59
A29350 | Major Sub-ordered Materials Received by Vendor and Verified | 10 | 2026-06-26 | 2026-07-10 | 2026-09-08 | 2026-10-06 | 41
A29340 | Purchase Order for Major Sub-ordered Materials | 5 | 2026-06-19 | 2026-06-26 | 2026-10-06 | 2026-10-12 | 41
A29330 | Key Vendor Drawings / Data Approved | 15 | 2026-06-01 | 2026-06-19 | 2026-10-13 | 2026-10-19 | 41
A33470 | Start Production | 0 | 2026-05-29 |  | 46315 | 46321 | 59
Electrical Bulk Material ( Earthing ,FO, Power Cables) |  | 166 | 21-Nov-25 A | 2026-07-28 | 2026-04-30 | 2026-10-05 | 48
A33300 | Delivery of Electrical Bulk Material (Earthing, FO, 11 KVA Cable) (Post TA) | 21 | 2026-07-08 | 2026-07-28 |  |  | 69
A27500 | Materials Successfully Inspected, Tested / Ex Work | 7 | 2026-06-29 | 2026-07-07 | 2026-04-30 | 2026-04-30 | 49
A27490 | Complete Manufacturing & ready for Final Inspection | 7 | 2026-06-18 | 2026-06-26 | 2026-04-30 | 2026-04-30 | 49
A27480 | Manufacturing / Ex Works (India/UAE) | 75 | 2026-04-04 | 2026-06-17 | 2026-04-30 | 2026-06-10 | 69
A27470 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 1 | 2026-04-03 | 2026-04-03 | 2026-06-11 | 2026-06-12 | 69
A27460 | Major Sub-ordered Materials Received by Vendor and Verified | 30 | 2026-02-20 | 2026-04-02 | 2026-06-12 | 2026-08-26 | 49
A27450 | Purchase Order for Major Sub-ordered Materials | 10 | 11-Dec-25 A | 19-Dec-25 A | 46260 | 46268
A27440 | Key Vendor Drawings / Data Approved | 75 | 21-Nov-25 A | 28-Nov-25 A | 46269 | 46279
A17930 | Start Production | 0 | 21-Nov-25 A |  | 46280 | 46300
Main Automation Equipment |  | 396 | 26-Feb-25 A | 2026-09-29 | 2026-03-18 | 2027-07-20 | 207
On Off Valve / Control Valves |  | 189 | 27-Oct-25 A | 2026-09-27 | 2026-03-25 | 2027-07-20 | 209
ESD Valves |  | 188 | 30-Oct-25 A | 2026-09-27 | 2026-03-25 | 2026-10-30 | 25
A59890 | Delivery of Control Valves | 14 | 2026-09-13 | 2026-09-27 |  |  | 34
A59870 | Materials Successfully Inspected, Tested / Ex Work | 6 | 2026-09-07 | 2026-09-13 | 2026-03-25 | 2026-04-02 | 34
A59860 | Complete Manufacturing & ready for Final Inspection | 6 | 2026-09-02 | 2026-09-07 | 2026-04-17 | 2026-04-18 | 34
A59820 | Manufacturing / Ex Works (India/UAE) | 170 | 2026-03-16 | 2026-09-02 | 2026-04-02 | 2026-04-27 | 34
A59810 | Key Vendor Drawings / Data Approved | 45 | 2026-02-20 | 2026-04-23 | 2026-03-25 | 2026-05-27 | 24
A59840 | Major Sub-ordered Materials Received by Vendor and Verified | 25 | 2026-02-28 | 2026-03-25 | 2026-04-18 | 2026-10-05 | 34
A59850 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 1 | 2026-03-15 | 2026-03-16 | 2026-10-05 | 2026-10-11 | 34
A59830 | Purchase Order for Major Sub-ordered Materials | 8 | 2026-02-20 | 2026-02-28 | 2026-10-11 | 2026-10-16 | 34
A59880 | Start Production | 0 | 30-Oct-25 A |  | 46312 | 46325
Control Valves (1" - 24" Rating 150, 300 & 2500 = 32 Nos) + SDV |  | 155 | 27-Oct-25 A | 2026-08-10 | 2026-05-12 | 2027-07-20 | 243
A33750 | Delivery of Control Valves | 21 | 2026-07-20 | 2026-08-10 |  |  | 82
A30470 | Materials Successfully Inspected, Tested / Ex Work | 6 | 2026-07-14 | 2026-07-20 | 2026-05-12 | 2026-05-12 | 82
A30460 | Complete Manufacturing & ready for Final Inspection | 6 | 2026-07-09 | 2026-07-14 | 2026-05-12 | 2026-05-19 | 82
A30450 | Manufacturing / Ex Works (India/UAE) | 132 | 2026-02-27 | 2026-07-08 | 2027-05-26 | 2027-06-08 | 82
A30410 | Key Vendor Drawings / Data Approved | 50 | 18-Dec-25 A | 20-Feb-26 A | 46547 | 46588
A30430 | Major Sub-ordered Materials Received by Vendor and Verified | 30 | 2026-03-06 | 2026-04-16 | 2026-05-19 | 2026-09-28 | 328
A30420 | Purchase Order for Major Sub-ordered Materials | 10 | 15-Feb-26 A | 2026-03-05 | 2026-09-28 | 2026-10-04 | 328
A30440 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 7 | 2026-02-20 | 2026-02-26 | 2026-10-04 | 2026-10-09 | 82
A33740 | Start Production | 0 | 27-Oct-25 A |  | 46305 | 46325
MOVs |  | 227 | 02-Sep-25 A | 2026-09-24 | 2026-05-11 | 2026-12-10 | 52
MOVs [Ball Type 24" 150# = 01 No] |  | 227 | 02-Sep-25 A | 2026-09-24 | 2026-05-11 | 2026-12-10 | 52
A34310 | Delivery of MOVs | 14 | 2026-09-11 | 2026-09-24 |  |  | 77
A32720 | Materials Successfully Inspected, Tested / Ex Work | 7 | 2026-09-02 | 2026-09-10 | 2026-05-11 | 2026-05-11 | 55
A32710 | Complete Manufacturing & ready for Final Inspection | 7 | 2026-08-24 | 2026-09-01 | 2026-05-11 | 2026-05-11 | 55
A32700 | Manufacturing / Ex Works (India/UAE) | 140 | 2026-04-04 | 2026-08-21 | 2026-05-11 | 2026-06-19 | 79
A32690 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 1 | 2026-04-03 | 2026-04-03 | 2026-06-21 | 2026-06-22 | 79
A32680 | Major Sub-ordered Materials Received by Vendor and Verified | 30 | 2026-02-20 | 2026-04-02 | 2026-06-22 | 2026-11-09 | 56
A32670 | Purchase Order for Major Sub-ordered Materials | 10 | 10-Dec-25 A | 18-Dec-25 A | 46335 | 46343
A32660 | Key Vendor Drawings / Data Approved | 50 | 21-Nov-25 A | 10-Dec-25 A | 46344 | 46352
A34300 | Start Production | 0 | 02-Sep-25 A |  | 46353 | 46366
Machine Condition Monitoring System (MCMS) |  | 163 | 25-May-25 A | 2026-06-05 | 2026-07-15 | 2026-10-26 | 99
Machine Condition Monitoring System |  | 163 | 25-May-25 A | 2026-06-05 | 2026-07-15 | 2026-10-26 | 99
A34140 | Delivery of MCMS | 17 | 2026-05-20 | 2026-06-05 |  |  | 143
A32000 | Materials Successfully Inspected, Tested / Ex Work | 5 | 2026-05-13 | 2026-05-19 | 2026-07-15 | 2026-07-15 | 103
A31990 | Complete Manufacturing & ready for Final Inspection | 5 | 2026-05-06 | 2026-05-12 | 2026-07-15 | 2026-07-15 | 103
A31980 | Manufacturing / Ex Works (India/UAE) | 75 | 2026-02-20 | 2026-05-05 | 2026-07-15 | 2026-07-15 | 145
A31970 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 3 | 01-Jan-26 A | 09-Jan-26 A | 46218 | 46218
A31960 | Major Sub-ordered Materials Received by Vendor and Verified | 30 | 27-Dec-25 A | 02-Jan-26 A | 46218 | 46293
A31950 | Purchase Order for Major Sub-ordered Materials | 10 | 20-Dec-25 A | 26-Dec-25 A | 46293 | 46297
A31940 | Key Vendor Drawings / Data Approved | 50 | 19-Dec-25 A | 19-Dec-25 A | 46300 | 46304
A34130 | Start Production | 0 | 25-May-25 A |  | 46305 | 46321
IPCS Modification (ABB) |  | 280 | 21-Mar-25 A | 2026-07-31 | 2026-03-27 | 2026-10-14 | 52
TA_Integrated Protection and Control System BF - ABB/Hitachi |  | 40 | 21-Mar-25 A | 16-May-25 A | 46108 | 46108
A27780 | Delivery of FOPP (02 Nos) | 7 | 10-May-25 A | 16-May-25 A
A27770 | Materials Successfully Inspected, Tested / Ex Work | 5 | 03-May-25 A | 09-May-25 A | 46108 | 46108
A27760 | Complete Manufacturing & ready for Final Inspection | 5 | 26-Apr-25 A | 02-May-25 A | 46108 | 46108
A27750 | Manufacturing / Ex Works (India/UAE) | 14 | 19-Apr-25 A | 25-Apr-25 A | 46108 | 46108
A27740 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 1 | 12-Apr-25 A | 18-Apr-25 A | 46108 | 46108
A27730 | Major Sub-ordered Materials Received by Vendor and Verified | 5 | 05-Apr-25 A | 11-Apr-25 A | 46108 | 46108
A27720 | Purchase Order for Major Sub-ordered Materials | 5 | 01-Apr-25 A | 04-Apr-25 A | 46108 | 46108
A27710 | Key Vendor Drawings / Data Approved | 5 | 21-Mar-25 A | 28-Mar-25 A | 46108 | 46108
A34480 | Start Production | 0 | 21-Mar-25 A |  | 46108 | 46108
Integrated Protection Control System |  | 214 | 25-Jul-25 A | 2026-07-31 | 2026-05-04 | 2026-10-14 | 52
A33970 | Delivery of IPCS | 21 | 2026-07-10 | 2026-07-31 |  |  | 75
A31280 | Materials Successfully Inspected, Tested / Ex Work | 7 | 2026-07-01 | 2026-07-10 | 2026-05-04 | 2026-05-04 | 53
A31270 | Complete Manufacturing & ready for Final Inspection | 7 | 2026-06-22 | 2026-07-01 | 2026-05-04 | 2026-05-04 | 53
A31260 | Manufacturing / Ex Works (India/UAE) | 120 | 2026-02-22 | 2026-06-22 | 2026-05-04 | 2026-05-04 | 73
A31250 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 3 | 10-Jan-26 A | 2026-02-22 | 2026-05-04 | 2026-05-07 | 73
A31240 | Major Sub-ordered Materials Received by Vendor and Verified | 30 | 28-Dec-25 A | 03-Jan-26 A | 46149 | 46269
A31230 | Purchase Order for Major Sub-ordered Materials | 10 | 21-Dec-25 A | 27-Dec-25 A | 46269 | 46279
A31220 | Key Vendor Drawings / Data Approved | 50 | 10-Sep-25 A | 20-Dec-25 A | 46280 | 46288
A24030 | Start Production | 0 | 25-Jul-25 A |  | 46289 | 46309
OTS |  | 307 | 13-Mar-25 A | 2026-09-16 | 2026-03-20 | 2026-10-14 | 20
TA_SCMS System - Siemens |  | 19 | 13-Mar-25 A | 11-May-25 A | 46108 | 46108
A27690 | Delivery of SCMS | 3 | 05-May-25 A | 11-May-25 A | 46108 | 46108
A27680 | Materials Successfully Inspected, Tested / Ex Work | 2 | 28-Apr-25 A | 04-May-25 A
A27670 | Complete Manufacturing & ready for Final Inspection | 3 | 21-Apr-25 A | 27-Apr-25 A | 46108 | 46108
A27660 | Manufacturing / Ex Works (India/UAE) | 3 | 14-Apr-25 A | 20-Apr-25 A | 46108 | 46108
A27650 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 1 | 07-Apr-25 A | 13-Apr-25 A | 46108 | 46108
A27640 | Major Sub-ordered Materials Received by Vendor and Verified | 3 | 31-Mar-25 A | 06-Apr-25 A | 46108 | 46108
A27630 | Purchase Order for Major Sub-ordered Materials | 3 | 24-Mar-25 A | 30-Mar-25 A | 46108 | 46108
A27620 | Key Vendor Drawings / Data Approved | 3 | 13-Mar-25 A | 16-Mar-25 A | 46108 | 46108
A33290 | Start Production | 0 | 23-Mar-25 A |  | 46108 | 46108
SCMS System |  | 307 | 23-May-25 A | 2026-09-16 | 2026-03-20 | 2026-10-14 | 20
A60180 | Delivery of SCMS | 14 | 2026-09-02 | 2026-09-16 |  |  | 28
A60170 | Materials Successfully Inspected, Tested / Ex Work | 7 | 2026-08-24 | 2026-09-02 | 2026-03-20 | 2026-04-17 | 20
A60160 | Complete Manufacturing & ready for Final Inspection | 7 | 2026-08-13 | 2026-08-24 | 2026-04-20 | 2026-05-01 | 20
A60120 | Manufacturing / Ex Works (India/UAE) | 100 | 2026-05-05 | 2026-08-13 | 2026-05-04 | 2026-06-01 | 28
A60150 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 1 | 2026-05-04 | 2026-05-05 | 2026-06-02 | 2026-06-03 | 28
A60140 | Major Sub-ordered Materials Received by Vendor and Verified | 21 | 2026-04-03 | 2026-05-04 | 2026-06-03 | 2026-09-11 | 20
A60130 | Purchase Order for Major Sub-ordered Materials | 10 | 2026-03-20 | 2026-04-03 | 2026-09-11 | 2026-09-21 | 20
A60110 | Key Vendor Drawings / Data Approved | 50 | 06-Jan-26 A | 2026-03-20 | 2026-09-22 | 2026-09-30 | 20
A60100 | Start Production | 0 | 23-May-25 A |  | 46296 | 46309
ICSS (Integrated Control and Safety System) including sys. Modifications |  | 394 | 20-Mar-25 A | 2026-09-29 | 2026-03-18 | 2026-10-23 | 18
TA_Integrated Control and Safety System BF - Honeywell |  | 99 | 20-Mar-25 A | 17-May-25 A | 46108 | 46108
A27600 | Delivery of loose Material for ICSS Modification | 5 | 11-May-25 A | 17-May-25 A
A27590 | Materials Successfully Inspected, Tested / Ex Work | 5 | 04-May-25 A | 10-May-25 A | 46108 | 46108
A27580 | Complete Manufacturing & ready for Final Inspection | 5 | 27-Apr-25 A | 03-May-25 A | 46108 | 46108
A27570 | Manufacturing / Ex Works (India/UAE) | 7 | 20-Apr-25 A | 26-Apr-25 A | 46108 | 46108
A27560 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 1 | 13-Apr-25 A | 19-Apr-25 A | 46108 | 46108
A27550 | Major Sub-ordered Materials Received by Vendor and Verified | 5 | 06-Apr-25 A | 12-Apr-25 A | 46108 | 46108
A27540 | Purchase Order for Major Sub-ordered Materials | 5 | 29-Mar-25 A | 05-Apr-25 A | 46108 | 46108
A27530 | Key Vendor Drawings / Data Approved | 5 | 20-Mar-25 A | 29-Mar-25 A | 46108 | 46108
A33280 | Start Production | 0 | 22-Mar-25 A |  | 46108 | 46108
Integrated Control and Safety System GF |  | 280 | 20-Jun-25 A | 2026-09-29 | 2026-03-18 | 2026-10-23 | 18
A33960 | Delivery of Material in Warehouse ICSS | 21 | 2026-09-08 | 2026-09-29 |  |  | 24
A31190 | Materials Successfully Inspected, Tested / Ex Work | 7 | 2026-08-28 | 2026-09-08 | 2026-03-18 | 2026-03-18 | 18
A31180 | Complete Manufacturing & ready for Final Inspection | 7 | 2026-08-19 | 2026-08-28 | 2026-03-18 | 2026-03-18 | 18
A31170 | Manufacturing / Ex Works (India/UAE) | 180 | 2026-02-20 | 2026-08-19 | 2026-03-18 | 2026-03-18 | 26
A31160 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 1 | 10-Jan-26 A | 2026-02-20 | 2026-03-18 | 2026-03-19 | 26
A31150 | Major Sub-ordered Materials Received by Vendor and Verified | 30 | 27-Dec-25 A | 03-Jan-26 A | 46100 | 46280
A31130 | Key Vendor Drawings / Data Approved | 50 | 05-Aug-25 A | 20-Dec-25 A | 46280 | 46288
A31140 | Purchase Order for Major Sub-ordered Materials | 10 | 21-Dec-25 A | 27-Dec-25 A | 46289 | 46297
A33950 | Start Production | 0 | 20-Jun-25 A |  | 46298 | 46318
Instrument Cables |  | 119 | 2026-03-12 | 2026-09-08 | 2026-04-13 | 2026-10-07 | 21
Instrument Cable (Single & Multicore = Approx. 78,130 Mtr) |  | 119 | 2026-03-12 | 2026-09-08 | 2026-04-13 | 2026-10-07 | 21
A33560 | Delivery of Material in Warehouse for Instrument Cable | 7 | 2026-09-01 | 2026-09-08 | 2026-04-13 |  | 29
A29750 | Materials Successfully Inspected, Tested / Ex Work | 7 | 2026-08-21 | 2026-09-01 | 2026-04-13 | 2026-05-22 | 21
A29740 | Complete Manufacturing & ready for Final Inspection | 7 | 2026-08-12 | 2026-08-21 | 2026-05-25 | 2026-06-05 | 21
A29730 | Manufacturing / Ex Works (India/UAE) | 75 | 2026-05-29 | 2026-08-12 | 2026-06-08 | 2026-06-26 | 29
A29720 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 1 | 2026-05-28 | 2026-05-29 | 2026-06-27 | 2026-06-28 | 29
A29710 | Major Sub-ordered Materials Received by Vendor and Verified | 15 | 2026-05-07 | 2026-05-28 | 2026-06-28 | 2026-09-11 | 21
A29700 | Purchase Order for Major Sub-ordered Materials | 10 | 2026-04-23 | 2026-05-07 | 2026-09-11 | 2026-09-21 | 21
A29690 | Key Vendor Drawings / Data Approved | 30 | 2026-03-13 | 2026-04-23 | 2026-09-22 | 2026-09-30 | 21
A33550 | Start Production | 0 | 2026-03-12 |  | 46296 | 46302 | 31
Local Fire Control Panel including F&G Detectors |  | 104 | 12-Dec-25 A | 2026-07-27 | 2026-05-05 | 2026-10-07 | 51
Fire Detection Alarm System and Local Fire Control Panel (Clean Agent Unit) |  | 104 | 12-Dec-25 A | 2026-07-27 | 2026-05-05 | 2026-10-07 | 51
A34100 | Delivery of FDAS, LFCP, Clean Agent Unit | 14 | 2026-07-13 | 2026-07-27 |  |  | 72
A31820 | Materials Successfully Inspected, Tested / Ex Work | 7 | 2026-07-02 | 2026-07-13 | 2026-05-05 | 2026-06-01 | 52
A31810 | Complete Manufacturing & ready for Final Inspection | 7 | 2026-06-23 | 2026-07-02 | 2026-06-02 | 2026-06-10 | 52
A31800 | Manufacturing / Ex Works | 75 | 2026-04-09 | 2026-06-23 | 2026-06-11 | 2026-06-19 | 72
A31790 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 1 | 2026-04-08 | 2026-04-09 | 2026-06-20 | 2026-06-21 | 72
A31780 | Major Sub-ordered Materials Received by Vendor and Verified | 7 | 2026-03-30 | 2026-04-08 | 2026-06-21 | 2026-09-04 | 52
A31760 | Key Vendor Drawings / Data Approved | 30 | 24-Jan-26 A | 2026-03-19 | 2026-09-04 | 2026-09-14 | 52
A31770 | Purchase Order for Major Sub-ordered Materials | 7 | 2026-03-19 | 2026-03-30 | 2026-09-15 | 2026-09-23 | 52
A34090 | Start Production | 0 | 12-Dec-25 A |  | 46289 | 46302
PSVs |  | 123 | 2026-03-25 | 2026-09-22 | 2026-04-23 | 2026-10-21 | 21
PSVs (1"x2" upto 8"x10" - CS Rating 150/150, 300/150 = 22 Nos) |  | 123 | 2026-03-25 | 2026-09-22 | 2026-04-23 | 2026-10-21 | 21
A33540 | Delivery of Material in Warehouse for PSVs | 14 | 2026-09-08 | 2026-09-22 | 2026-04-23 |  | 29
A29660 | Materials Successfully Inspected, Tested / Ex Work | 7 | 2026-08-28 | 2026-09-08 | 2026-04-23 | 2026-06-03 | 21
A29650 | Complete Manufacturing & ready for Final Inspection | 7 | 2026-08-19 | 2026-08-28 | 2026-06-04 | 2026-06-12 | 21
A29640 | Manufacturing / Ex Works (India/UAE) | 75 | 2026-06-05 | 2026-08-19 | 2026-06-15 | 2026-07-03 | 29
A29630 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 0 | 2026-06-05 | 2026-06-05 | 2026-07-05 | 2026-07-05 | 29
A29620 | Major Sub-ordered Materials Received by Vendor and Verified | 15 | 2026-05-15 | 2026-06-05 | 2026-07-05 | 2026-09-18 | 20
A29610 | Purchase Order for Major Sub-ordered Materials | 7 | 2026-05-06 | 2026-05-15 | 2026-09-18 | 2026-09-28 | 20
A29600 | Key Vendor Drawings / Data Approved | 30 | 2026-03-26 | 2026-05-06 | 2026-09-29 | 2026-10-07 | 20
A33530 | Start Production | 0 | 2026-03-25 |  | 46302 | 46316 | 28
Sampling System |  | 130 | 26-Feb-25 A | 12-May-25 A | 46357 | 46357
TA_SGM Replacement (Additional Item) |  | 130 | 26-Feb-25 A | 12-May-25 A | 46357 | 46357
A37500 | Delivery of Additional Material to be Procured | 14 | 06-May-25 A | 12-May-25 A
A37490 | Materials Successfully Inspected, Tested / Ex Work | 5 | 29-Apr-25 A | 05-May-25 A | 46357 | 46357
A37480 | Complete Manufacturing & ready for Final Inspection | 5 | 22-Apr-25 A | 28-Apr-25 A | 46357 | 46357
A37470 | Manufacturing / Ex Works (India/UAE) | 28 | 15-Apr-25 A | 21-Apr-25 A | 46357 | 46357
A37460 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 1 | 08-Apr-25 A | 14-Apr-25 A | 46357 | 46357
A37450 | Major Sub-ordered Materials Received by Vendor and Verified | 5 | 01-Apr-25 A | 07-Apr-25 A | 46357 | 46357
A37440 | Purchase Order for Major Sub-ordered Materials | 5 | 25-Mar-25 A | 31-Mar-25 A | 46357 | 46357
A37430 | Key Vendor Drawings / Data Approved | 10 | 26-Feb-25 A | 24-Mar-25 A | 46357 | 46357
A37420 | Start Production | 0 | 17-Mar-25 A |  | 46357 | 46357
F&G Flame Detectors, MCP, Beacon, etc. |  | 103 | 2026-04-02 | 2026-09-02 | 2026-06-01 | 2026-10-31 | 42
F&G Flame Detectors, MCP, Beacon (Nos 324) |  | 103 | 2026-04-02 | 2026-09-02 | 2026-06-01 | 2026-10-31 | 42
A34180 | Delivery of F&G Detectors | 20 | 2026-08-13 | 2026-09-02 | 2026-06-01 |  | 59
A32180 | Materials Successfully Inspected, Tested / Ex Work | 5 | 2026-08-06 | 2026-08-13 | 2026-06-01 | 2026-06-19 | 41
A32170 | Complete Manufacturing & ready for Final Inspection | 7 | 2026-07-28 | 2026-08-06 | 2026-06-22 | 2026-07-03 | 41
A32160 | Manufacturing / Ex Works (India/UAE) | 60 | 2026-05-29 | 2026-07-28 | 2026-07-06 | 2026-07-24 | 57
A32150 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 1 | 2026-05-28 | 2026-05-29 | 2026-07-25 | 2026-07-26 | 57
A32140 | Major Sub-ordered Materials Received by Vendor and Verified | 15 | 2026-05-07 | 2026-05-28 | 2026-07-26 | 2026-09-24 | 41
A32130 | Purchase Order for Major Sub-ordered Materials | 10 | 2026-04-23 | 2026-05-07 | 2026-09-24 | 2026-10-02 | 41
A32120 | Key Vendor Drawings / Data Approved | 15 | 2026-04-02 | 2026-04-23 | 2026-10-05 | 2026-10-09 | 41
A34170 | Start Production | 0 | 2026-04-02 |  | 46307 | 46326 | 59
Main Electrical Equipment |  | 396 | 25-Feb-25 A | 2026-09-28 | 2026-03-27 | 2027-01-03 | 66
DG Set (750 KVA) 01 Nos |  | 256 | 22-Aug-25 A | 2026-08-06 | 2026-05-18 | 2026-11-03 | 62
DG Set |  | 256 | 22-Aug-25 A | 2026-08-06 | 2026-05-18 | 2026-11-03 | 62
A33240 | Manufacturing / Ex Works (India/UAE) | 155 | 10-Dec-25 A | 2026-06-29 |  |  | 87
A34430 | Delivery of Material in Warehouse DG Set | 20 | 2026-07-18 | 2026-08-06 | 2026-05-18 | 2026-05-18 | 89
A33260 | Materials Successfully Inspected, Tested / Ex Work | 7 | 2026-07-09 | 2026-07-17 | 2026-05-18 | 2026-05-18 | 63
A33250 | Complete Manufacturing & ready for Final Inspection | 7 | 2026-06-30 | 2026-07-08 | 2026-05-18 | 2026-05-18 | 63
A33230 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2 | 02-Dec-25 A | 09-Dec-25 A | 46160 | 46160
A33220 | Major Sub-ordered Materials Received by Vendor and Verified | 30 | 26-Nov-25 A | 01-Dec-25 A | 46160 | 46290
A33210 | Purchase Order for Major Sub-ordered Materials | 10 | 30-Nov-25 A | 19-Dec-25 A | 46290 | 46300
A33200 | Key Vendor Drawings / Data Approved | 90 | 01-Sep-25 A | 27-Nov-25 A | 46301 | 46309
A34420 | Start Production | 0 | 22-Aug-25 A |  | 46310 | 46329
UPS (AC - 60 KVA, 20 KVA, DC-UPS 6.5 KVA) 03 Nos. |  | 394 | 25-Feb-25 A | 2026-09-28 | 2026-03-27 | 2027-01-03 | 66
TA_UPS Modification - Chloride Technology |  | 95 | 25-Feb-25 A | 03-May-25 A | 46108 | 46108
A37360 | Delivery of Material for UPS Modification | 5 | 27-Apr-25 A | 03-May-25 A
A37350 | Materials Successfully Inspected, Tested / Ex Work | 5 | 20-Apr-25 A | 26-Apr-25 A | 46108 | 46108
A37340 | Complete Manufacturing & ready for Final Inspection | 1 | 13-Apr-25 A | 19-Apr-25 A | 46108 | 46108
A37330 | Manufacturing / Ex Works (India/UAE) | 21 | 06-Apr-25 A | 12-Apr-25 A | 46108 | 46108
A37320 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 1 | 30-Mar-25 A | 05-Apr-25 A | 46108 | 46108
A37310 | Major Sub-ordered Materials Received by Vendor and Verified | 5 | 23-Mar-25 A | 29-Mar-25 A | 46108 | 46108
A37300 | Purchase Order for Major Sub-ordered Materials | 5 | 06-Mar-25 A | 22-Mar-25 A | 46108 | 46108
A37290 | Key Vendor Drawings / Data Approved | 5 | 27-Feb-25 A | 04-Mar-25 A | 46108 | 46108
A37280 | Start Production | 0 | 25-Feb-25 A |  | 46108 | 46108
UPS (AC - 60 KVA, 20 KVA, DC-UPS 6.5 KVA) Qty 1+1+1 = 03 Nos |  | 198 | 16-Oct-25 A | 2026-09-28 | 2026-05-28 | 2027-01-03 | 66
A34080 | Delivery of Material in Warehouse UPS | 21 | 2026-09-07 | 2026-09-28 |  |  | 97
A31730 | Materials Successfully Inspected, Tested / Ex Work | 7 | 2026-08-27 | 2026-09-07 | 2026-05-28 | 2026-06-18 | 69
A31720 | Complete Manufacturing & ready for Final Inspection | 7 | 2026-08-18 | 2026-08-27 | 2026-06-19 | 2026-07-02 | 69
A31710 | Manufacturing / Ex Works (India/UAE) | 100 | 2026-05-10 | 2026-08-18 | 2026-07-03 | 2026-08-13 | 97
A31700 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2 | 2026-05-08 | 2026-05-10 | 2026-08-14 | 2026-08-16 | 97
A31690 | Major Sub-ordered Materials Received by Vendor and Verified | 30 | 2026-03-27 | 2026-05-08 | 2026-08-16 | 2026-11-24 | 69
A31680 | Purchase Order for Major Sub-ordered Materials | 10 | 2026-03-13 | 2026-03-27 | 2026-11-24 | 2026-12-02 | 69
A31670 | Key Vendor Drawings / Data Approved | 16 | 2026-02-20 | 2026-03-13 | 2026-12-03 | 2026-12-11 | 69
A34070 | Start Production | 0 | 16-Oct-25 A |  | 46370 | 46390
Power Transformer (05 Nos) |  | 243 | 10-Sep-25 A | 2026-08-14 | 2026-05-01 | 2026-10-23 | 49
Power Transformers (Qty 05) |  | 243 | 10-Sep-25 A | 2026-08-14 | 2026-05-01 | 2026-10-23 | 49
A34120 | Delivery of Material in Warehouse Power Transformers | 28 | 2026-07-18 | 2026-08-14 |  |  | 70
A31910 | Materials Successfully Inspected, Tested / Ex Work | 7 | 2026-07-09 | 2026-07-17 | 2026-05-01 | 2026-05-01 | 50
A31900 | Complete Manufacturing & ready for Final Inspection | 7 | 2026-06-30 | 2026-07-08 | 2026-05-01 | 2026-05-01 | 50
A31890 | Manufacturing / Ex Works (India/UAE) | 130 | 2026-02-20 | 2026-06-29 | 2026-05-01 | 2026-05-01 | 70
A31850 | Key Vendor Drawings / Data Approved | 60 | 21-Nov-25 A | 02-Dec-25 A | 46143 | 46143
A31880 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 1 | 01-Jan-26 A | 11-Jan-26 A | 46143 | 46273
A31870 | Major Sub-ordered Materials Received by Vendor and Verified | 30 | 19-Dec-25 A | 03-Jan-26 A | 46273 | 46281
A31860 | Purchase Order for Major Sub-ordered Materials | 10 | 02-Dec-25 A | 19-Dec-25 A | 46282 | 46290
A34110 | Start Production | 0 | 10-Sep-25 A |  | 46291 | 46318
Electrical Heat Tracing |  | 71 | 2026-05-13 | 2026-08-31 | 2026-07-13 | 2026-10-26 | 41
Electrical Heat Tracing (53 Meter for piping + 340 Meter for instrumentation) |  | 71 | 2026-05-13 | 2026-08-31 | 2026-07-13 | 2026-10-26 | 41
A33420 | Delivery of Material in Warehouse for Electrical Heat Tracing | 14 | 2026-08-17 | 2026-08-31 | 2026-07-13 |  | 57
A29120 | Materials Successfully Inspected, Tested / Ex Work | 7 | 2026-08-06 | 2026-08-17 | 2026-07-13 | 2026-08-24 | 41
A29110 | Complete Manufacturing & ready for Final Inspection | 3 | 2026-08-03 | 2026-08-06 | 2026-08-24 | 2026-08-27 | 41
A29100 | Manufacturing / Ex Works (India/UAE) | 25 | 2026-07-07 | 2026-08-01 | 2026-08-27 | 2026-09-03 | 59
A29090 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 1 | 2026-07-06 | 2026-07-07 | 2026-09-03 | 2026-09-04 | 59
A29080 | Major Sub-ordered Materials Received by Vendor and Verified | 5 | 2026-06-29 | 2026-07-06 | 2026-09-04 | 2026-09-28 | 43
A29070 | Purchase Order for Major Sub-ordered Materials | 3 | 2026-06-24 | 2026-06-29 | 2026-09-28 | 2026-10-01 | 43
A29060 | Key Vendor Drawings / Data Approved | 30 | 2026-05-14 | 2026-06-24 | 2026-10-02 | 2026-10-12 | 42
A33410 | Start Production | 0 | 2026-05-13 |  | 46308 | 46321 | 61
CP |  | 103 | 2026-02-27 | 2026-08-03 | 2026-05-25 | 2026-10-26 | 59
Cathodic Protection (CP) Total CS Piping Length - 499 Meters |  | 103 | 2026-02-27 | 2026-08-03 | 2026-05-25 | 2026-10-26 | 59
A33460 | Delivery of Material in Warehouse for Cathodic Protection | 14 | 2026-07-20 | 2026-08-03 | 2026-05-25 |  | 84
A29300 | Materials Successfully Inspected, Tested / Ex Work | 7 | 2026-07-09 | 2026-07-20 | 2026-05-25 | 2026-07-03 | 60
A29290 | Complete Manufacturing & ready for Final Inspection | 7 | 2026-06-30 | 2026-07-09 | 2026-07-06 | 2026-07-10 | 60
A29280 | Manufacturing / Ex Works | 45 | 2026-05-16 | 2026-06-30 | 2026-07-13 | 2026-08-07 | 84
A29270 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 1 | 2026-05-15 | 2026-05-16 | 2026-08-08 | 2026-08-09 | 84
A29260 | Major Sub-ordered Materials Received by Vendor and Verified | 20 | 2026-04-17 | 2026-05-15 | 2026-08-09 | 2026-09-23 | 60
A29250 | Purchase Order for Major Sub-ordered Materials | 5 | 2026-04-10 | 2026-04-17 | 2026-09-23 | 2026-10-01 | 60
A29240 | Key Vendor Drawings / Data Approved | 30 | 2026-03-02 | 2026-04-10 | 2026-10-02 | 2026-10-12 | 60
A33450 | Start Production | 0 | 2026-02-27 |  | 46308 | 46321 | 86
LV & MV Switchgears |  | 232 | 12-Sep-25 A | 2026-08-20 | 2026-04-22 | 2026-10-18 | 40
Switchgear (MV & LV) |  | 232 | 12-Sep-25 A | 2026-08-20 | 2026-04-22 | 2026-10-18 | 40
A34270 | Delivery of Switchgear (MV & LV) | 21 | 2026-07-31 | 2026-08-20 |  |  | 59
A32540 | Materials Successfully Inspected, Tested / Ex Work | 7 | 2026-07-22 | 2026-07-30 | 2026-04-22 | 2026-04-22 | 41
A32530 | Complete Manufacturing & ready for Final Inspection | 7 | 2026-07-13 | 2026-07-21 | 2026-04-22 | 2026-04-22 | 41
A32520 | Manufacturing / Ex Works (India/UAE) | 135 | 2026-02-26 | 2026-07-10 | 2026-04-22 | 2026-04-24 | 59
A32500 | Major Sub-ordered Materials Received by Vendor and Verified | 35 | 20-Jan-26 A | 2026-02-24 | 2026-04-25 | 2026-04-26 | 43
A32510 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 1 | 2026-02-25 | 2026-02-25 | 2026-04-26 | 2026-09-08 | 59
A32490 | Purchase Order for Major Sub-ordered Materials | 10 | 11-Dec-25 A | 19-Dec-25 A | 46273 | 46281
A32480 | Key Vendor Drawings / Data Approved | 50 | 21-Nov-25 A | 02-Dec-25 A | 46282 | 46290
A34260 | Start Production | 0 | 12-Sep-25 A |  | 46293 | 46313
Switch Gear Modification (Siemens) |  | 89 | 17-Mar-25 A | 12-May-25 A | 46108 | 46108
TA_Switchgear (MV Switchgear Modifications) - Siemens |  | 89 | 17-Mar-25 A | 12-May-25 A | 46108 | 46108
A22410 | Delivery of Material For Switchgear Modification | 2 | 06-May-25 A | 12-May-25 A
A22780 | Materials Successfully Inspected, Tested / Ex Work | 2 | 29-Apr-25 A | 05-May-25 A | 46108 | 46108
A22770 | Complete Manufacturing & ready for Final Inspection | 2 | 22-Apr-25 A | 28-Apr-25 A | 46108 | 46108
A22470 | Manufacturing / Ex Works (India/UAE) | 2 | 15-Apr-25 A | 21-Apr-25 A | 46108 | 46108
A24280 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2 | 08-Apr-25 A | 14-Apr-25 A | 46108 | 46108
A22760 | Major Sub-ordered Materials Received by Vendor and Verified | 2 | 01-Apr-25 A | 07-Apr-25 A | 46108 | 46108
A22740 | Purchase Order for Major Sub-ordered Materials | 2 | 25-Mar-25 A | 31-Mar-25 A | 46108 | 46108
A22460 | Key Vendor Drawings / Data Approved | 2 | 18-Mar-25 A | 24-Mar-25 A | 46108 | 46108
A22450 | Start Production | 0 | 17-Mar-25 A |  | 46108 | 46108
MV & LV VFD's |  | 161 | 13-Aug-25 A | 2026-03-19 | 2026-09-22 | 2026-10-19 | 145
Variable Fequency Drives (VFDs) LV Qty = 03 |  | 161 | 13-Aug-25 A | 2026-03-19 | 2026-09-22 | 2026-10-19 | 145
A32580 | Purchase Order for Major Sub-ordered Materials | 10 | 15-Aug-25 A | 16-Aug-25 A
A32570 | Key Vendor Drawings / Data Approved | 50 | 13-Aug-25 A | 14-Aug-25 A | 46287 | 46287
A34290 | Delivery of VFDs | 28 | 2026-02-20 | 2026-03-19 | 2026-09-22 | 2026-09-22 | 214
A32630 | Materials Successfully Inspected, Tested / Ex Work | 7 | 22-Aug-25 A | 22-Aug-25 A | 46287 | 46287
A32610 | Manufacturing / Ex Works (India/UAE) | 120 | 20-Aug-25 A | 20-Aug-25 A | 46287 | 46287
A34280 | Start Production | 0 | 13-Aug-25 A |  | 46287 | 46287
A32600 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 1 | 19-Aug-25 A | 19-Aug-25 A | 46287 | 46287
A32590 | Major Sub-ordered Materials Received by Vendor and Verified | 30 | 17-Aug-25 A | 18-Aug-25 A | 46287 | 46287
A32620 | Complete Manufacturing & ready for Final Inspection | 7 | 20-Aug-25 A | 21-Aug-25 A | 46287 | 46314
HV Capacitor Bay |  | 166 | 27-Oct-25 A | 2026-07-28 | 2026-06-11 | 2026-11-16 | 78
HV Capacitor Bay |  | 166 | 27-Oct-25 A | 2026-07-28 | 2026-06-11 | 2026-11-16 | 78
A34160 | Delivery of Material in Warehouse HV Capacitor Bay | 7 | 2026-07-22 | 2026-07-28 |  |  | 111
A32090 | Materials Successfully Inspected, Tested / Ex Work | 7 | 2026-07-13 | 2026-07-21 | 2026-06-11 | 2026-06-11 | 79
A32080 | Complete Manufacturing & ready for Final Inspection | 7 | 2026-07-02 | 2026-07-10 | 2026-06-11 | 2026-06-24 | 79
A32070 | Manufacturing / Ex Works (India/UAE) | 75 | 2026-04-18 | 2026-07-01 | 2026-06-25 | 2026-08-05 | 111
A32060 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 1 | 2026-04-17 | 2026-04-17 | 2026-08-06 | 2026-08-07 | 111
A32050 | Major Sub-ordered Materials Received by Vendor and Verified | 30 | 2026-03-06 | 2026-04-16 | 2026-08-07 | 2026-10-21 | 79
A32040 | Purchase Order for Major Sub-ordered Materials | 10 | 2026-02-20 | 2026-03-05 | 2026-10-21 | 2026-10-29 | 79
A32030 | Key Vendor Drawings / Data Approved | 50 | 19-Dec-25 A | 26-Feb-26 A | 46325 | 46335
A34150 | Start Production | 0 | 27-Oct-25 A |  | 46336 | 46342
Power Distribution Panel and LCS, Battery & Safety Switch, Resister Bank |  | 288 | 06-Jun-25 A | 2026-04-08 | 2026-09-29 | 2026-11-13 | 151
NGR Panel Qty 02 |  | 288 | 06-Jun-25 A | 2026-04-08 | 2026-09-29 | 2026-11-13 | 151
A33060 | Manufacturing / Ex Works (India/UAE) | 120 | 01-Jan-26 A | 17-Jan-26 A
A33050 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 1 | 02-Jan-26 A | 10-Jan-26 A | 46294 | 46294
A33040 | Major Sub-ordered Materials Received by Vendor and Verified | 30 | 28-Dec-25 A | 03-Jan-26 A | 46294 | 46294
A34390 | Delivery of NGR Panel | 28 | 2026-03-12 | 2026-04-08 | 2026-09-29 | 2026-09-29 | 219
A33030 | Purchase Order for Major Sub-ordered Materials | 10 | 22-Dec-25 A | 27-Dec-25 A | 46294 | 46294
A33080 | Materials Successfully Inspected, Tested / Ex Work | 7 | 2026-03-03 | 2026-03-11 | 2026-09-29 | 2026-09-29 | 157
A33070 | Complete Manufacturing & ready for Final Inspection | 7 | 2026-02-20 | 2026-03-02 | 2026-09-29 | 2026-10-07 | 157
A33020 | Key Vendor Drawings / Data Approved | 50 | 19-Dec-25 A | 20-Dec-25 A | 46303 | 46311
A34380 | Start Production | 0 | 06-Jun-25 A |  | 46312 | 46339
Interposing Relay Panel (IRP) |  | 123 | 2026-03-18 | 2026-09-17 | 2026-05-25 | 2026-11-22 | 46
Interposing Relay Panel |  | 123 | 2026-03-18 | 2026-09-17 | 2026-05-25 | 2026-11-22 | 46
A34410 | Delivery of Interposing relay Panel | 7 | 2026-09-11 | 2026-09-17 | 2026-05-25 |  | 66
A33170 | Materials Successfully Inspected, Tested / Ex Work | 7 | 2026-09-02 | 2026-09-10 | 2026-05-25 | 2026-06-12 | 46
A33160 | Complete Manufacturing & ready for Final Inspection | 7 | 2026-08-24 | 2026-09-01 | 2026-06-15 | 2026-06-26 | 46
A33150 | Manufacturing / Ex Works (India/UAE) | 100 | 2026-05-14 | 2026-08-22 | 2026-06-29 | 2026-07-17 | 65
A33140 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 1 | 2026-05-13 | 2026-05-14 | 2026-07-18 | 2026-07-19 | 65
A33130 | Major Sub-ordered Materials Received by Vendor and Verified | 15 | 2026-04-22 | 2026-05-13 | 2026-07-19 | 2026-10-27 | 47
A33120 | Purchase Order for Major Sub-ordered Materials | 10 | 2026-04-08 | 2026-04-22 | 2026-10-27 | 2026-11-04 | 47
A33110 | Key Vendor Drawings / Data Approved | 15 | 2026-03-19 | 2026-04-08 | 2026-11-05 | 2026-11-13 | 47
A34400 | Start Production | 0 | 2026-03-18 |  | 46342 | 46348 | 67
Construction and Pre-Commissioning |  | 630 | 09-Jan-25 A | 2027-07-01 | 2026-02-21 | 2027-07-20 | 13
Construction/Pre-Commissioning |  | 310 | 10-Jun-25 A | 2026-12-21 | 2026-06-02 | 2027-01-03 | 9
Green Field Works |  | 310 | 10-Jun-25 A | 2026-12-21 | 2026-06-02 | 2027-01-03 | 9
General / Common |  | 148 | 10-Jun-25 A | 15-Oct-25 A | 46256 | 46256
CONS | TSF Construction / Commence on SITE | 100 | 01-Jul-25 A | 15-Oct-25 A
CONS10 | Installation of Isolation Fence Plant Site | 30 | 10-Jun-25 A | 13-Aug-25 A | 46256 | 46256
A3250 | Complete Site Preparation and Grading works | 0 |  | 16-Jun-25 A | 46256 | 46256
Electrical & Instrumentation Works |  | 152 | 2026-05-09 | 2026-12-21 | 2026-06-02 | 2027-01-03 | 9
A3749 | Complete Cable termination and loop test - Overall | 0 |  | 2026-12-21 | 2026-06-02 | 2026-08-15 | 11
A3719 | E&I Works (CCB & SIS) For cable trays and cable laying | 75 | 2026-09-26 | 2026-12-21 |  | 2026-10-26 | 11
A3909 | Instrumentation Works Plant Site (Control/Manual Valves, Gauges, TT, PT, DPT, PSVs, Switches etc) | 44 | 2026-09-27 | 2026-11-17 |  | 2027-01-03 | 29
A3759 | Complete E&I Work at plant site | 0 |  | 2026-11-17 | 2026-09-28 | 2026-12-10 | 29
A3889 | Electrical Works Plant Site (Cable trays, cable laying, termination, DBs, Jbs etc) | 64 | 2026-08-26 | 2026-11-08 |  | 2026-12-20 | 28
A3739 | Complete E&I Equipment / Panels Installation CCB &SIS | 0 |  | 2026-10-18 | 2026-10-31 | 2026-12-20 | 67
A3709 | E&I Bulk & Equipment Deliveries - Plant Site | 0 |  | 2026-09-24 | 2026-10-08 | 2027-01-03 | 32
A18510 | Cable Laying - Trenches | 64 | 2026-05-09 | 2026-07-21 |  | 2027-01-03 | 21
Accommodation and Messing |  | 112 | 15-Apr-25 A | 24-Jul-25 A | 46092 | 46092
Mobilisation of Camp (Accommodation and Messing) |  | 112 | 15-Apr-25 A | 24-Jul-25 A | 46092 | 46092
A62210 | Main Scope - Mobilisation of Camp (Accommodation and messing) | 4 | 22-Apr-25 A | 24-Jul-25 A | 46092 | 46092
A61550 | TA - Mobilisation of Camp (Accommodation and messing) | 4 | 15-Apr-25 A | 20-Apr-25 A | 46092 | 46092
Fabrication, Storage, Workshops (Temporary Facilities) |  | 636 | 01-Apr-25 A | 2027-07-01 | 2026-03-11 | 2027-07-20 | 16
Mobilisation of Temporary Facilities |  | 54 | 01-Apr-25 A | 24-Oct-25 A | 46092 | 46092
A62230 | Mobilisation of Temporary Facilities - Main Scope | 24 | 01-Aug-25 A | 24-Oct-25 A | 46092 | 46092
A61560 | Mobilisation of Temporary Facilities - TA | 24 | 01-Apr-25 A | 31-May-25 A | 46092 | 46092
Maintenance of Temporary Facilities |  | 336 | 01-Nov-25 A | 2027-03-18 | 2026-03-11 | 2027-04-06 | 16
A62280 | Maintenance of Temporary Facilities - Q6 | 24 | 2027-02-20 | 2027-03-18 | 2026-03-11 | 2026-03-11 | 16
A62270 | Maintenance of Temporary Facilities - Q5 | 24 | 2026-11-07 | 2026-12-03 | 2026-03-11 | 2026-03-11 | 16
A62260 | Maintenance of Temporary Facilities - Q4 | 24 | 2026-07-25 | 2026-08-20 | 2026-04-29 | 2026-05-26 | 16
A62250 | Maintenance of Temporary Facilities - Q3 | 24 | 2026-04-11 | 2026-05-07 | 2026-08-12 | 2026-09-08 | 16
A61570 | Maintenance of Temporary Facilities - Q2 | 24 | 01-Jan-26 A | 24-Jan-26 A | 46351 | 46378
A62240 | Maintenance of Temporary Facilities - Q1 | 24 | 01-Nov-25 A | 18-Nov-25 A | 46456 | 46483
Demobilisation of Temporary Facilities |  | 636 | 25-Jun-25 A | 2027-07-01 | 2027-06-23 | 2027-07-20 | 16
A62290 | Demobiisation of Temporary Facilities - Main Scope | 24 | 2027-06-05 | 2027-07-01 | 2027-06-23 | 2027-06-23 | 16
A61580 | Demobiisation of Temporary Facilities - TA | 24 | 25-Jun-25 A | 11-Jul-25 A | 46561 | 46588
Civil Construction |  | 441 | 09-Jan-25 A | 2027-01-11 | 2026-02-21 | 2027-01-20 | 136
Site Preparation |  | 78 | 01-Apr-25 A | 15-Sep-25 A | 46092 | 46092
A62220 | Site Preparation - Main Scope | 24 | 22-Aug-25 A | 15-Sep-25 A | 46092 | 46092
A61590 | Site Preparation - TA | 24 | 01-Apr-25 A | 21-Jun-25 A | 46092 | 46092
Fencing |  | 24 | 17-Apr-25 A | 22-Aug-25 A | 46092 | 46092
A61600 | Fencing | 24 | 17-Apr-25 A | 22-Aug-25 A | 46092 | 46092
Excavation and trenching |  | 143 | 2026-03-02 | 2026-08-15 | 2026-04-11 | 2026-10-04 | 43
GF Sumps and Pits |  | 136 | 2026-03-07 | 2026-08-11 | 2026-05-06 | 2026-09-01 | 18
Accidentally Oily Water Sump 70-TD-1407 |  | 72 | 2026-03-07 | 2026-05-28 | 2026-05-06 | 2026-07-28 | 52
A26700 | Back filling and compaction in layers | 7 | 2026-05-21 | 2026-05-28 | 2026-05-06 | 2026-05-17 | 52
A26690 | Protective Coating | 12 | 2026-05-07 | 2026-05-20 | 2026-05-18 | 2026-05-19 | 52
A26680 | Formwork removal | 14 | 2026-04-21 | 2026-05-06 | 2026-05-20 | 2026-05-21 | 52
A26670 | Concrete Curing | 14 | 2026-04-19 | 2026-05-04 | 2026-05-30 | 2026-06-02 | 52
A26660 | Concrete pouring | 10 | 2026-04-18 | 2026-04-28 | 2026-06-03 | 2026-06-14 | 52
A26650 | Rebar works | 10 | 2026-04-04 | 2026-04-14 | 2026-06-03 | 2026-06-14 | 52
A26640 | Formworks | 10 | 2026-04-04 | 2026-04-14 | 2026-06-17 | 2026-06-28 | 52
A26630 | Water proofing and bitumen coating/sheet | 4 | 2026-03-30 | 2026-04-02 | 2026-06-18 | 2026-07-04 | 52
A26620 | Lean concrete | 2 | 2026-03-21 | 2026-03-22 | 2026-06-21 | 2026-07-06 | 52
A26610 | Surface leveling and compaction | 2 | 2026-03-18 | 2026-03-19 | 2026-07-07 | 2026-07-20 | 52
A26600 | Excavation | 10 | 2026-03-07 | 2026-03-17 | 2026-07-21 | 2026-07-28 | 52
Oil Contaminated Water Sump 70-TD-1408 |  | 72 | 2026-03-25 | 2026-06-16 | 2026-05-06 | 2026-07-28 | 36
A26810 | Back filling and compaction in layers | 7 | 2026-06-09 | 2026-06-16 | 2026-05-06 | 2026-05-17 | 36
A26800 | Protective Coating | 12 | 2026-05-26 | 2026-06-08 | 2026-05-18 | 2026-05-19 | 36
A26790 | Formwork removal | 14 | 2026-05-10 | 2026-05-25 | 2026-05-20 | 2026-05-21 | 36
A26780 | Concrete Curing | 14 | 2026-05-07 | 2026-05-23 | 2026-05-30 | 2026-06-02 | 36
A26770 | Concrete pouring | 10 | 2026-05-06 | 2026-05-17 | 2026-06-03 | 2026-06-14 | 36
A26760 | Rebar works | 10 | 2026-04-22 | 2026-05-03 | 2026-06-03 | 2026-06-14 | 36
A26750 | Formworks | 10 | 2026-04-22 | 2026-05-03 | 2026-06-17 | 2026-06-28 | 36
A26740 | Water proofing and bitumen coating/sheet | 4 | 2026-04-18 | 2026-04-21 | 2026-06-18 | 2026-07-04 | 36
A26730 | Lean concrete | 2 | 2026-04-08 | 2026-04-09 | 2026-06-21 | 2026-07-06 | 36
A26720 | Surface leveling and compaction | 2 | 2026-04-06 | 2026-04-07 | 2026-07-07 | 2026-07-20 | 36
A26710 | Excavation | 10 | 2026-03-25 | 2026-04-05 | 2026-07-21 | 2026-07-28 | 36
Sanitary Waste Water Sump 70-TD-1409 |  | 47 | 2026-05-10 | 2026-07-02 | 2026-06-04 | 2026-07-28 | 22
A26920 | Back filling and compaction in layers | 7 | 2026-06-25 | 2026-07-02 | 2026-06-04 | 2026-06-11 | 22
A26910 | Protective Coating | 7 | 2026-06-17 | 2026-06-24 | 2026-06-13 | 2026-06-13 | 22
A26890 | Concrete Curing | 14 | 2026-06-07 | 2026-06-22 | 2026-06-14 | 2026-06-14 | 22
A26900 | Formwork removal | 7 | 2026-06-09 | 2026-06-16 | 2026-06-22 | 2026-06-23 | 22
A26880 | Concrete pouring | 7 | 2026-06-06 | 2026-06-13 | 2026-06-24 | 2026-07-05 | 22
A26870 | Rebar works | 10 | 2026-05-30 | 2026-06-09 | 2026-06-24 | 2026-07-05 | 22
A26860 | Formworks | 10 | 2026-05-30 | 2026-06-09 | 2026-07-01 | 2026-07-08 | 22
A26850 | Water proofing and bitumen coating/sheet | 2 | 2026-05-27 | 2026-05-28 | 2026-07-05 | 2026-07-12 | 22
A26840 | Lean concrete | 1 | 2026-05-19 | 2026-05-19 | 2026-07-02 | 2026-07-18 | 22
A26830 | Surface leveling and compaction | 1 | 2026-05-18 | 2026-05-18 | 2026-07-13 | 2026-07-20 | 22
A26820 | Excavation | 7 | 2026-05-10 | 2026-05-17 | 2026-07-21 | 2026-07-28 | 22
PSA2 Slope Drum Pit |  | 60 | 2026-03-15 | 2026-05-23 | 2026-05-20 | 2026-07-28 | 57
A27030 | Back filling and compaction in layers | 7 | 2026-05-16 | 2026-05-23 | 2026-05-20 | 2026-05-27 | 57
A27020 | Protective Coating | 7 | 2026-05-07 | 2026-05-14 | 2026-05-28 | 2026-05-30 | 57
A27000 | Concrete Curing | 14 | 2026-04-23 | 2026-05-09 | 2026-05-31 | 2026-06-01 | 57
A27010 | Formwork removal | 10 | 2026-04-26 | 2026-05-06 | 2026-06-09 | 2026-06-13 | 57
A26990 | Concrete pouring | 7 | 2026-04-22 | 2026-04-29 | 2026-06-14 | 2026-06-21 | 57
A26980 | Rebar works | 7 | 2026-04-08 | 2026-04-15 | 2026-06-14 | 2026-06-21 | 57
A26970 | Formworks | 7 | 2026-04-08 | 2026-04-15 | 2026-06-28 | 2026-07-05 | 57
A26960 | Water proofing and bitumen coating/sheet | 4 | 2026-04-04 | 2026-04-07 | 2026-07-01 | 2026-07-12 | 57
A26950 | Lean concrete | 2 | 2026-03-25 | 2026-03-26 | 2026-06-29 | 2026-07-14 | 57
A26940 | Surface leveling and compaction | 2 | 2026-03-23 | 2026-03-24 | 2026-07-13 | 2026-07-20 | 57
A26930 | Excavation | 7 | 2026-03-15 | 2026-03-22 | 2026-07-21 | 2026-07-28 | 57
Cooling Water Valve Pit |  | 57 | 2026-06-07 | 2026-08-11 | 2026-06-28 | 2026-09-01 | 18
A27140 | Back filling and compaction in layers | 7 | 2026-08-04 | 2026-08-11 | 2026-06-28 | 2026-07-05 | 18
A27130 | Protective Coating | 7 | 2026-07-27 | 2026-08-03 | 2026-07-06 | 2026-07-07 | 18
A27110 | Concrete Curing | 14 | 2026-07-16 | 2026-08-01 | 2026-07-08 | 2026-07-09 | 18
A27120 | Formwork removal | 7 | 2026-07-19 | 2026-07-26 | 2026-07-18 | 2026-07-21 | 18
A27100 | Concrete pouring | 7 | 2026-07-15 | 2026-07-22 | 2026-07-22 | 2026-08-02 | 18
A27090 | Rebar works | 10 | 2026-07-01 | 2026-07-12 | 2026-07-22 | 2026-08-02 | 18
A27080 | Formworks | 10 | 2026-07-01 | 2026-07-12 | 2026-08-05 | 2026-08-12 | 18
A27070 | Water proofing and bitumen coating/sheet | 4 | 2026-06-27 | 2026-06-30 | 2026-08-09 | 2026-08-16 | 18
A27060 | Lean concrete | 2 | 2026-06-17 | 2026-06-18 | 2026-08-06 | 2026-08-22 | 18
A27050 | Surface leveling and compaction | 2 | 2026-06-15 | 2026-06-16 | 2026-08-17 | 2026-08-24 | 18
A27040 | Excavation | 7 | 2026-06-07 | 2026-06-14 | 2026-08-25 | 2026-09-01 | 18
GF UG Piping and Trenches |  | 130 | 2026-03-17 | 2026-08-15 | 2026-04-11 | 2026-09-08 | 21
Piping |  | 86 | 2026-04-11 | 2026-07-19 | 2026-04-20 | 2026-07-28 | 8
A3450 | Complete UG Piping & Backfilling | 59 | 2026-05-12 | 2026-07-19 | 2026-04-20 | 2026-05-20 | 8
A18530 | Excavation and Valve Pits for Fire Water Line | 59 | 2026-04-11 | 2026-06-17 | 2026-04-20 | 2026-06-27 | 8
A3440 | Trenching for UG Piping | 27 | 2026-04-11 | 2026-05-11 | 2026-05-21 | 2026-07-28 | 8
Cables |  | 130 | 2026-03-17 | 2026-08-15 | 2026-04-11 | 2026-09-08 | 21
A18480 | Backfilling of E&I trenches | 21 | 2026-07-22 | 2026-08-15 | 2026-05-16 | 2026-06-08 | 21
A3460 | Concrete Trenches for Electrical and Instrumentation Cable | 45 | 2026-03-17 | 2026-05-07 | 2026-04-11 | 2026-06-01 | 21
A18460 | Direct Buried Trenches for Power and Instrumentation cables | 21 | 2026-04-11 | 2026-05-04 | 2026-08-16 | 2026-09-08 | 30
BF Trenches |  | 70 | 2026-03-02 | 2026-05-23 | 2026-07-08 | 2026-10-04 | 116
A21770 | Direct buried trenches - BF | 35 | 2026-04-12 | 2026-05-23 | 2026-07-08 | 2026-08-18 | 116
A21800 | Duct Banks/Road Crossing | 35 | 2026-03-02 | 2026-04-12 | 2026-08-25 | 2026-10-04 | 110
Foundations |  | 308 | 03-Jul-25 A | 2027-01-11 | 2026-02-21 | 2027-01-20 | 136
A62510 | New Activity | 5 | 2026-02-20 | 2026-02-26 |  |  | 351
GF SIS Building Structure Works |  | 163 | 02-Sep-25 A | 2026-05-02 | 2026-03-14 | 2026-05-23 | 18
Sub-Structure |  | 114 | 02-Sep-25 A | 2026-03-09 | 2026-03-14 | 2026-03-30 | 18
A1620 | Plinth Beams | 15 | 16-Dec-25 A | 2026-03-09 | 2026-03-14 | 2026-03-14 | 18
A1610 | Waterproofing & Backfilling | 27 | 16-Dec-25 A | 2026-02-28 | 2026-03-14 | 2026-03-14 | 18
A1600 | RCC Columns and Walls Upto FFL | 48 | 16-Dec-25 A | 16-Jan-26 A | 46095 | 46102
A1590 | Foundation Works (Excavation, PCC & RCC) | 30 | 02-Sep-25 A | 01-Jan-26 A | 46095 | 46111
Super-Structure |  | 46 | 2026-03-10 | 2026-05-02 | 2026-03-31 | 2026-05-23 | 18
A1510 | First Slab and Beams | 30 | 2026-03-29 | 2026-05-02 | 2026-03-31 | 2026-05-04 | 18
A1500 | RCC Columns and Walls Upto First Slab | 30 | 2026-03-10 | 2026-04-13 | 2026-04-19 | 2026-05-23 | 18
GF Sub-Station Sub-Structure |  | 383 | 25-Aug-25 A | 2027-01-04 | 2026-03-14 | 2027-01-20 | 14
A1030 | Plinth Beams (Casting Suti) | 24 | 15-Dec-25 A | 2026-03-26 | 2026-03-14 | 2026-03-14 | 59
A26380 | Waterproofing & Backfilling (handingover to Precast) | 20 | 15-Sep-25 A | 22-Sep-25 A | 46099 | 46099
A26370 | RCC Base & Columns Upto FFL | 20 | 21-Nov-25 A | 10-Feb-26 A | 46099 | 46099
A26360 | Foundation Works (Excavation, PCC & RCC) | 21 | 25-Aug-25 A | 16-Sep-25 A | 46149 | 46176
GF Sub-Station Super-Structure |  | 273 | 24-Jan-26 A | 2027-01-04 | 2026-03-18 | 2027-01-20 | 14
Ground Floor - Cellar Area |  | 30 | 24-Jan-26 A | 2026-03-26 | 2026-03-18 | 2026-04-21 | 22
A26400 | First Slab and Beams | 30 | 2026-02-21 | 2026-03-26 | 2026-03-18 | 2026-04-21 | 22
A26390 | RCC Columns and Walls Upto First Slab | 30 | 24-Jan-26 A | 2026-03-26 | 2026-03-18 | 2026-04-21 | 22
First Floor |  | 257 | 2026-03-11 | 2027-01-04 | 2026-04-06 | 2027-01-20 | 14
C1059 | Punch List Close Out (Construction / Mechanical) | 12 | 2026-12-22 | 2027-01-04 | 2026-04-06 | 2026-05-06 | 14
A26420 | 2nd Slab and Beams | 38 | 2026-03-26 | 2026-05-09 | 2026-04-21 | 2026-06-03 | 22
A26410 | RCC Columns Upto 2nd Slab | 27 | 2026-03-11 | 2026-04-11 | 2027-01-07 | 2027-01-20 | 22
GF Transformers Structure Works |  | 91 | 2026-02-21 | 2026-06-06 | 2026-03-17 | 2026-06-27 | 18
Sub-Structure |  | 70 | 2026-02-21 | 2026-05-12 | 2026-03-17 | 2026-06-27 | 39
A26470 | Waterproofing & Backfilling | 30 | 2026-04-08 | 2026-05-12 | 2026-03-17 | 2026-04-20 | 39
A1150 | RCC Walls Upto FFL | 30 | 2026-03-25 | 2026-04-28 | 2026-04-19 | 2026-05-23 | 21
A26460 | Foundation Works (Excavation, PCC & RCC) | 30 | 2026-02-21 | 2026-03-26 | 2026-05-24 | 2026-06-27 | 21
Super-Structure |  | 30 | 2026-05-03 | 2026-06-06 | 2026-05-24 | 2026-06-27 | 18
A1190 | RCC Walls above Ground | 30 | 2026-05-03 | 2026-06-06 | 2026-05-24 | 2026-06-27 | 18
Roads and Pavement Construction |  | 151 | 2026-07-20 | 2027-01-11 | 2026-07-29 | 2027-01-20 | 8
A6870 | Base Course and Asphalt working | 51 | 2026-11-14 | 2027-01-11 | 2026-07-29 | 2026-09-26 | 8
A6880 | Concrete Flooring on Plant Side | 49 | 2026-09-17 | 2026-11-12 | 2026-09-27 | 2026-11-22 | 8
A6860 | Subgarde and Sub-Base for Road | 51 | 2026-07-20 | 2026-09-16 | 2026-11-23 | 2027-01-20 | 8
BF Foundation |  | 90 | 2026-02-21 | 2026-06-04 | 2026-07-23 | 2026-11-04 | 131
BFW3000 | General Civil Work - Equipment Foundations & Pipe Support (TBC) | 90 | 2026-02-21 | 2026-06-04 | 2026-07-23 | 2026-11-04 | 131
GF Foundations |  | 210 | 03-Jul-25 A | 2026-06-25 | 2026-02-21 | 2026-08-22 | 48
FG/OG Compressor and Shleter Foundation including shelter concrete trench |  | 129 | 31-Jul-25 A | 2026-03-23 | 2026-02-21 | 2026-03-23 | 0
A15890 | Back filling and compaction in layers | 15 | 2026-03-07 | 2026-03-23 | 2026-02-21 | 2026-02-21 | 0
A15880 | Protective Coating | 15 | 2026-02-28 | 2026-03-16 | 2026-02-21 | 2026-02-21 | 0
A15870 | Formwork removal | 15 | 2026-02-21 | 2026-03-09 | 2026-02-21 | 2026-02-21 | 0
A15860 | Concrete Curing | 42 | 27-Dec-25 A | 2026-03-04 | 2026-02-21 | 2026-02-28 | 0
A15850 | Concrete pouring | 36 | 19-Dec-25 A | 2026-03-09 | 2026-02-21 | 2026-02-28 | 0
A15660 | Excavation | 18 | 31-Jul-25 A | 23-Aug-25 A | 46074 | 46081
A15840 | Rebar works | 36 | 15-Dec-25 A | 2026-02-28 | 2026-02-21 | 2026-03-04 | 0
A15790 | Formworks | 36 | 19-Dec-25 A | 2026-02-28 | 2026-02-21 | 2026-03-09 | 0
A15740 | Lean concrete | 18 | 25-Aug-25 A | 30-Aug-25 A | 46074 | 46090
A15750 | Water proofing and bitumen coating/sheet | 18 | 15-Oct-25 A | 2026-02-28 | 2026-02-28 | 2026-03-16 | 0
A15670 | Surface leveling and compaction | 18 | 11-Aug-25 A | 25-Aug-25 A | 46088 | 46104
Pipe Rack (Primary SR81 & Secondary SR80) Foundation |  | 93 | 23-Dec-25 A | 2026-04-09 | 2026-03-02 | 2026-04-19 | 8
A26340 | Back filling and compaction in layers | 21 | 2026-03-17 | 2026-04-09 | 2026-03-02 | 2026-03-02 | 8
A26330 | Protective Coating | 21 | 2026-03-10 | 2026-04-02 | 2026-03-02 | 2026-03-08 | 8
A26320 | Formwork removal | 21 | 2026-03-03 | 2026-03-26 | 2026-03-02 | 2026-03-08 | 8
A26310 | Concrete Curing | 21 | 2026-03-01 | 2026-03-24 | 2026-03-02 | 2026-03-15 | 8
A26300 | Concrete Pouring | 21 | 2026-02-28 | 2026-03-23 | 2026-03-02 | 2026-03-25 | 8
A26290 | Rebar works | 21 | 2026-02-21 | 2026-03-16 | 2026-03-02 | 2026-03-25 | 8
A26280 | Formworks | 21 | 2026-02-21 | 2026-03-16 | 2026-03-09 | 2026-04-01 | 8
A26270 | Water proofing and bitumen coating/sheet | 24 | 13-Jan-26 A | 2026-03-05 | 2026-03-10 | 2026-04-02 | 8
A26260 | Lean concrete | 24 | 06-Jan-26 A | 2026-02-26 | 2026-03-12 | 2026-04-05 | 8
A26250 | Surface leveling and compaction | 24 | 30-Dec-25 A | 2026-02-26 | 2026-03-19 | 2026-04-12 | 8
A26240 | Excavation - Pipe Rack (SR81 & SR80) | 24 | 23-Dec-25 A | 20-Jan-26 A | 46107 | 46131
OG Compressor Discharge Drip Leg (13-SP-7004) |  | 49 | 2026-03-28 | 2026-05-23 | 2026-05-03 | 2026-08-16 | 72
A24910 | Back filling and compaction in layers | 8 | 2026-05-14 | 2026-05-23 | 2026-05-03 | 2026-05-06 | 72
A24900 | Protective Coating | 8 | 2026-05-05 | 2026-05-13 | 2026-06-24 | 2026-06-29 | 72
A24880 | Concrete Curing | 14 | 2026-04-28 | 2026-05-13 | 2026-06-29 | 2026-07-04 | 72
A24890 | Formwork removal | 4 | 2026-04-30 | 2026-05-04 | 2026-07-04 | 2026-07-13 | 72
A24870 | Concrete pouring | 4 | 2026-04-28 | 2026-05-02 | 2026-07-13 | 2026-07-21 | 72
A24860 | Rebar works | 7 | 2026-04-20 | 2026-04-27 | 2026-07-13 | 2026-07-21 | 72
A24850 | Formworks | 7 | 2026-04-20 | 2026-04-27 | 2026-07-21 | 2026-07-26 | 72
A24840 | Water proofing and bitumen coating/sheet | 8 | 2026-04-11 | 2026-04-19 | 2026-07-23 | 2026-07-28 | 72
A24830 | Lean concrete | 4 | 2026-04-06 | 2026-04-09 | 2026-07-21 | 2026-08-06 | 72
A24820 | Surface leveling and compaction | 4 | 2026-04-01 | 2026-04-05 | 2026-07-28 | 2026-08-06 | 72
A24810 | Excavation | 4 | 2026-03-28 | 2026-03-31 | 2026-08-06 | 2026-08-16 | 31
PSA2 Package by Linde ( 10 Vessels) |  | 151 | 03-Jul-25 A | 20-Feb-26 A | 46166 | 46168
A25020 | Back filling and compaction in layers | 21 | 01-Feb-26 A | 20-Feb-26 A | 46166 | 46166
A25000 | Formwork removal | 10 | 05-Feb-26 A | 05-Feb-26 A | 46166 | 46166
A25010 | Protective Coating | 12 | 01-Jan-26 A | 15-Feb-26 A | 46166 | 46166
A24940 | Lean concrete | 6 | 01-Sep-25 A | 18-Sep-25 A | 46166 | 46166
A24930 | Surface leveling and compaction | 12 | 11-Jul-25 A | 25-Jul-25 A | 46168 | 46168
A24990 | Concrete Curing | 6 | 19-Dec-25 A | 16-Feb-26 A | 46168 | 46168
A24970 | Rebar works | 24 | 22-Oct-25 A | 05-Feb-26 A | 46166 | 46166
A24960 | Formworks | 24 | 27-Sep-25 A | 01-Feb-26 A | 46168 | 46168
A24980 | Concrete pouring | 2 | 04-Nov-25 A | 03-Feb-26 A | 46168 | 46168
A24920 | Excavation | 6 | 03-Jul-25 A | 15-Jul-25 A | 46168 | 46168
A24950 | Water proofing and bitumen coating/sheet | 6 | 19-Sep-25 A | 26-Sep-25 A | 46168 | 46168
OG Comp After Cooler ( 13-HE-709) |  | 39 | 2026-04-01 | 2026-05-16 | 2026-05-07 | 2026-08-08 | 71
A25130 | Back filling and compaction in layers | 6 | 2026-05-10 | 2026-05-16 | 2026-05-07 | 2026-05-10 | 71
A25100 | Concrete Curing | 14 | 2026-04-28 | 2026-05-13 | 2026-06-27 | 2026-06-29 | 71
A25120 | Protective Coating | 4 | 2026-05-05 | 2026-05-09 | 2026-06-29 | 2026-07-01 | 71
A25110 | Formwork removal | 7 | 2026-04-30 | 2026-05-07 | 2026-07-08 | 2026-07-11 | 71
A25090 | Concrete pouring | 7 | 2026-04-27 | 2026-05-04 | 2026-07-11 | 2026-07-19 | 71
A25080 | Rebar works | 7 | 2026-04-19 | 2026-04-26 | 2026-07-12 | 2026-07-20 | 72
A25070 | Formworks | 7 | 2026-04-19 | 2026-04-26 | 2026-07-19 | 2026-07-27 | 71
A25060 | Water proofing and bitumen coating/sheet | 2 | 2026-04-16 | 2026-04-18 | 2026-07-22 | 2026-07-30 | 71
A25050 | Lean concrete | 2 | 2026-04-07 | 2026-04-08 | 2026-07-27 | 2026-08-01 | 71
A25040 | Surface leveling and compaction | 2 | 2026-04-05 | 2026-04-06 | 2026-07-20 | 2026-08-05 | 71
A25030 | Excavation | 3 | 2026-04-01 | 2026-04-04 | 2026-08-01 | 2026-08-08 | 31
FG Comp 2nd Stage Discharge Drum(13-VV-707) |  | 51 | 2026-04-05 | 2026-06-02 | 2026-05-11 | 2026-07-23 | 44
A25240 | Back filling and compaction in layers | 7 | 2026-05-26 | 2026-06-02 | 2026-05-11 | 2026-05-13 | 44
A25230 | Protective Coating | 6 | 2026-05-19 | 2026-05-25 | 2026-05-30 | 2026-05-31 | 44
A25210 | Concrete Curing | 14 | 2026-05-09 | 2026-05-24 | 2026-06-01 | 2026-06-01 | 44
A25220 | Formwork removal | 7 | 2026-05-11 | 2026-05-18 | 2026-06-09 | 2026-06-13 | 44
A25200 | Concrete pouring | 7 | 2026-05-07 | 2026-05-14 | 2026-06-14 | 2026-06-21 | 44
A25190 | Rebar works | 7 | 2026-04-23 | 2026-04-30 | 2026-06-14 | 2026-06-21 | 44
A25180 | Formworks | 7 | 2026-04-23 | 2026-04-30 | 2026-06-28 | 2026-07-05 | 44
A25170 | Water proofing and bitumen coating/sheet | 4 | 2026-04-19 | 2026-04-22 | 2026-07-01 | 2026-07-08 | 44
A25160 | Lean concrete | 1 | 2026-04-11 | 2026-04-11 | 2026-06-29 | 2026-07-14 | 44
A25150 | Surface leveling and compaction | 2 | 2026-04-08 | 2026-04-09 | 2026-07-09 | 2026-07-15 | 44
A25140 | Excavation | 3 | 2026-04-05 | 2026-04-07 | 2026-07-16 | 2026-07-23 | 31
FG Comp 1st Stage Suction Drum(13-VV-705) |  | 52 | 2026-04-08 | 2026-06-07 | 2026-05-14 | 2026-08-01 | 47
A25460 | Back filling and compaction in layers | 7 | 2026-05-31 | 2026-06-07 | 2026-05-14 | 2026-05-17 | 47
A25450 | Protective Coating | 6 | 2026-05-24 | 2026-05-30 | 2026-06-06 | 2026-06-07 | 47
A25430 | Concrete Curing | 14 | 2026-05-13 | 2026-05-28 | 2026-06-08 | 2026-06-09 | 47
A25440 | Formwork removal | 7 | 2026-05-16 | 2026-05-23 | 2026-06-17 | 2026-06-21 | 47
A25420 | Concrete pouring | 7 | 2026-05-12 | 2026-05-19 | 2026-06-22 | 2026-06-29 | 47
A25410 | Rebar works | 7 | 2026-04-28 | 2026-05-05 | 2026-06-22 | 2026-06-29 | 47
A25400 | Formworks | 7 | 2026-04-28 | 2026-05-05 | 2026-07-06 | 2026-07-13 | 47
A25390 | Water proofing and bitumen coating/sheet | 4 | 2026-04-23 | 2026-04-27 | 2026-07-09 | 2026-07-16 | 47
A25380 | Lean concrete | 2 | 2026-04-14 | 2026-04-15 | 2026-07-07 | 2026-07-22 | 47
A25370 | Surface leveling and compaction | 2 | 2026-04-12 | 2026-04-13 | 2026-07-18 | 2026-07-23 | 47
A25360 | Excavation | 3 | 2026-04-08 | 2026-04-11 | 2026-07-25 | 2026-08-01 | 31
FG Comp 2nd Stage Suction Drum(13-VV-706) |  | 52 | 2026-04-12 | 2026-06-10 | 2026-05-18 | 2026-07-19 | 33
A25570 | Back filling and compaction in layers | 7 | 2026-06-03 | 2026-06-10 | 2026-05-18 | 2026-05-20 | 33
A25560 | Protective Coating | 6 | 2026-05-27 | 2026-06-02 | 2026-05-24 | 2026-05-25 | 33
A25540 | Concrete Curing | 14 | 2026-05-17 | 2026-06-01 | 2026-05-26 | 2026-05-27 | 33
A25550 | Formwork removal | 7 | 2026-05-19 | 2026-05-26 | 2026-06-04 | 2026-06-08 | 33
A25530 | Concrete pouring | 7 | 2026-05-16 | 2026-05-23 | 2026-06-09 | 2026-06-16 | 33
A25520 | Rebar works | 7 | 2026-05-02 | 2026-05-09 | 2026-06-09 | 2026-06-16 | 33
A25510 | Formworks | 7 | 2026-05-02 | 2026-05-09 | 2026-06-23 | 2026-06-30 | 33
A25500 | Water proofing and bitumen coating/sheet | 4 | 2026-04-27 | 2026-04-30 | 2026-06-27 | 2026-07-04 | 33
A25490 | Lean concrete | 2 | 2026-04-18 | 2026-04-19 | 2026-06-24 | 2026-07-09 | 33
A25480 | Surface leveling and compaction | 2 | 2026-04-15 | 2026-04-16 | 2026-07-05 | 2026-07-11 | 33
A25470 | Excavation | 3 | 2026-04-12 | 2026-04-14 | 2026-07-12 | 2026-07-19 | 31
PSA2 Slope Drum ( 70-VV-1415) |  | 46 | 2026-04-15 | 2026-06-07 | 2026-05-21 | 2026-08-22 | 64
A25680 | Back filling and compaction in layers | 7 | 2026-05-31 | 2026-06-07 | 2026-05-21 | 2026-05-25 | 64
A25650 | Concrete Curing | 14 | 2026-05-16 | 2026-05-31 | 2026-07-04 | 2026-07-08 | 64
A25670 | Protective Coating | 7 | 2026-05-23 | 2026-05-30 | 2026-07-08 | 2026-07-13 | 64
A25660 | Formwork removal | 4 | 2026-05-18 | 2026-05-21 | 2026-07-13 | 2026-07-21 | 64
A25640 | Concrete pouring | 4 | 2026-05-16 | 2026-05-19 | 2026-07-21 | 2026-07-29 | 64
A25630 | Rebar works | 7 | 2026-05-07 | 2026-05-14 | 2026-07-21 | 2026-07-29 | 64
A25620 | Formworks | 7 | 2026-05-07 | 2026-05-14 | 2026-07-29 | 2026-08-03 | 64
A25610 | Water proofing and bitumen coating/sheet | 7 | 2026-04-29 | 2026-05-06 | 2026-08-01 | 2026-08-05 | 64
A25600 | Lean concrete | 4 | 2026-04-25 | 2026-04-28 | 2026-08-05 | 2026-08-13 | 64
A25590 | Surface leveling and compaction | 4 | 2026-04-20 | 2026-04-23 | 2026-07-29 | 2026-08-15 | 64
A25580 | Excavation | 4 | 2026-04-15 | 2026-04-19 | 2026-08-13 | 2026-08-22 | 31
FG Comp After Cooler ( 13-HE-704) |  | 40 | 2026-04-20 | 2026-06-04 | 2026-05-26 | 2026-07-11 | 31
A25790 | Back filling and compaction in layers | 5 | 2026-05-31 | 2026-06-04 | 2026-05-26 | 2026-05-28 | 31
A25760 | Concrete Curing | 14 | 2026-05-16 | 2026-05-31 | 2026-05-30 | 2026-05-31 | 31
A25780 | Protective Coating | 8 | 2026-05-21 | 2026-05-30 | 2026-06-01 | 2026-06-02 | 31
A25770 | Formwork removal | 7 | 2026-05-18 | 2026-05-25 | 2026-06-10 | 2026-06-11 | 31
A25750 | Concrete pouring | 7 | 2026-05-14 | 2026-05-21 | 2026-06-13 | 2026-06-20 | 31
A25740 | Rebar works | 7 | 2026-05-07 | 2026-05-14 | 2026-06-13 | 2026-06-20 | 31
A25730 | Formworks | 7 | 2026-05-07 | 2026-05-14 | 2026-06-20 | 2026-06-27 | 31
A25720 | Water proofing and bitumen coating/sheet | 2 | 2026-05-05 | 2026-05-06 | 2026-06-23 | 2026-06-30 | 31
A25710 | Lean concrete | 2 | 2026-04-26 | 2026-04-27 | 2026-06-27 | 2026-07-05 | 31
A25700 | Surface leveling and compaction | 2 | 2026-04-23 | 2026-04-25 | 2026-06-21 | 2026-07-06 | 31
A25690 | Excavation | 3 | 2026-04-20 | 2026-04-22 | 2026-07-06 | 2026-07-11 | 31
FG Comp Interstage Cooler ( 13-HE-703) |  | 40 | 2026-04-23 | 2026-06-08 | 2026-06-09 | 2026-07-25 | 40
A26590 | Back filling and compaction in layers | 5 | 2026-06-03 | 2026-06-08 | 2026-06-09 | 2026-06-11 | 40
A26560 | Concrete Curing | 14 | 2026-05-19 | 2026-06-03 | 2026-06-13 | 2026-06-14 | 40
A26580 | Protective Coating | 7 | 2026-05-26 | 2026-06-02 | 2026-06-15 | 2026-06-16 | 40
A26570 | Formwork removal | 7 | 2026-05-21 | 2026-05-28 | 2026-06-24 | 2026-06-25 | 41
A26550 | Concrete pouring | 7 | 2026-05-18 | 2026-05-25 | 2026-06-27 | 2026-07-04 | 40
A26540 | Rebar works | 7 | 2026-05-11 | 2026-05-18 | 2026-06-27 | 2026-07-04 | 40
A26530 | Formworks | 7 | 2026-05-11 | 2026-05-18 | 2026-07-04 | 2026-07-11 | 40
A26520 | Water proofing and bitumen coating/sheet | 2 | 2026-05-09 | 2026-05-10 | 2026-07-08 | 2026-07-15 | 40
A26510 | Lean concrete | 2 | 2026-04-29 | 2026-04-30 | 2026-07-12 | 2026-07-19 | 40
A26500 | Surface leveling and compaction | 2 | 2026-04-27 | 2026-04-28 | 2026-07-05 | 2026-07-20 | 40
A26490 | Excavation | 3 | 2026-04-23 | 2026-04-26 | 2026-07-20 | 2026-07-25 | 40
OG Comp 2nd Stage Suction Drum(13-VV-713) |  | 52 | 2026-04-27 | 2026-06-25 | 2026-06-22 | 2026-08-22 | 48
A25900 | Back filling and compaction in layers | 7 | 2026-06-18 | 2026-06-25 | 2026-06-22 | 2026-06-25 | 48
A25890 | Protective Coating | 6 | 2026-06-11 | 2026-06-17 | 2026-06-25 | 2026-06-28 | 48
A25870 | Concrete Curing | 14 | 2026-06-01 | 2026-06-16 | 2026-06-28 | 2026-06-30 | 48
A25880 | Formwork removal | 7 | 2026-06-03 | 2026-06-10 | 2026-07-07 | 2026-07-12 | 48
A25860 | Concrete pouring | 7 | 2026-05-31 | 2026-06-07 | 2026-07-12 | 2026-07-20 | 48
A25850 | Rebar works | 7 | 2026-05-17 | 2026-05-24 | 2026-07-12 | 2026-07-20 | 48
A25840 | Formworks | 7 | 2026-05-17 | 2026-05-24 | 2026-07-26 | 2026-08-03 | 48
A25830 | Water proofing and bitumen coating/sheet | 4 | 2026-05-12 | 2026-05-16 | 2026-07-29 | 2026-08-06 | 48
A25820 | Lean concrete | 2 | 2026-05-03 | 2026-05-04 | 2026-07-27 | 2026-08-12 | 48
A25810 | Surface leveling and compaction | 2 | 2026-04-30 | 2026-05-02 | 2026-08-06 | 2026-08-13 | 48
A25800 | Excavation | 3 | 2026-04-27 | 2026-04-29 | 2026-08-13 | 2026-08-22 | 48
OG Buffer Drum (13-VV-712) |  | 68 | 31-Dec-25 A | 2026-04-16 | 2026-05-14 | 2026-08-22 | 109
A26120 | Back filling and compaction in layers | 7 | 2026-04-08 | 2026-04-16 | 2026-05-14 | 2026-05-14 | 109
A26110 | Protective Coating | 6 | 2026-04-01 | 2026-04-08 | 2026-06-27 | 2026-06-27 | 109
A26100 | Formwork removal | 14 | 2026-03-16 | 2026-04-01 | 2026-06-27 | 2026-06-27 | 109
A26090 | Concrete Curing | 14 | 2026-03-14 | 2026-03-30 | 2026-06-27 | 2026-07-01 | 109
A26080 | Concrete pouring | 7 | 2026-03-14 | 2026-03-22 | 2026-07-01 | 2026-07-19 | 109
A26070 | Rebar works | 15 | 2026-02-24 | 2026-03-14 | 2026-07-01 | 2026-07-19 | 109
A26060 | Formworks | 15 | 2026-02-24 | 2026-03-14 | 2026-07-19 | 2026-07-27 | 109
A26050 | Water proofing and bitumen coating/sheet | 4 | 22-Jan-26 A | 2026-02-24 | 2026-07-19 | 2026-08-04 | 109
A26040 | Lean concrete | 2 | 19-Jan-26 A | 21-Jan-26 A | 46224 | 46240
A26030 | Surface leveling and compaction | 2 | 10-Jan-26 A | 17-Jan-26 A | 46240 | 46247
A26020 | Excavation | 3 | 31-Dec-25 A | 15-Jan-26 A | 46247 | 46256
OG Compressor Interstage Cooler (13-HE-708) |  | 40 | 01-Jan-26 A | 2026-04-02 | 2026-03-29 | 2026-08-09 | 109
A26130 | Excavation | 3 | 01-Jan-26 A | 23-Jan-26 A | 46110 | 46110
A26200 | Concrete Curing | 17 | 2026-03-15 | 2026-04-02 | 2026-03-29 | 2026-03-30 | 109
A26230 | Back filling and compaction in layers | 4 | 2026-03-29 | 2026-04-01 | 2026-03-31 | 2026-04-01 | 109
A26210 | Formwork removal | 12 | 2026-03-17 | 2026-03-30 | 2026-04-09 | 2026-04-11 | 110
A26220 | Protective Coating | 6 | 2026-03-22 | 2026-03-28 | 2026-04-12 | 2026-04-28 | 109
A26190 | Concrete pouring | 12 | 2026-03-14 | 2026-03-26 | 2026-04-12 | 2026-04-28 | 31
A26180 | Rebar works | 15 | 2026-03-07 | 2026-03-23 | 2026-04-19 | 2026-05-02 | 31
A26170 | Formworks | 15 | 2026-03-07 | 2026-03-23 | 2026-07-27 | 2026-08-03 | 31
A26160 | Water proofing and bitumen coating/sheet | 2 | 2026-03-04 | 2026-03-05 | 2026-07-23 | 2026-08-06 | 31
A26150 | Lean concrete | 2 | 2026-02-23 | 2026-02-24 | 2026-08-03 | 2026-08-08 | 31
A26140 | Surface leveling and compaction | 2 | 2026-02-21 | 2026-02-22 | 2026-07-20 | 2026-08-09 | 31
Structural Steel and Shades |  | 451 | 09-Mar-25 A | 2026-09-26 | 2026-03-27 | 2027-01-06 | 88
TA Prefabrication of Steel Structure for BFW |  | 24 | 09-Mar-25 A | 18-May-25 A | 46108 | 46108
A61610 | TA prefabrication of steel structure for BFW | 24 | 09-Mar-25 A | 18-May-25 A | 46108 | 46108
TA Erection of Steel Structure for BFW |  | 20 | 19-Apr-25 A | 24-May-25 A | 46108 | 46108
A23330 | Erection of Steel Structure of BFW Preheater - Pre TA ( By external Subcontractor) | 20 | 19-Apr-25 A | 24-May-25 A | 46108 | 46108
BF Structure Steel |  | 39 | 2026-04-29 | 2026-06-14 | 2026-09-21 | 2026-11-04 | 124
BFW4020 | Structure Installation (Platform on the existing Piperack + strengthen) | 39 | 2026-04-29 | 2026-06-14 | 2026-09-21 | 2026-11-04 | 124
GF Steel Works |  | 112 | 2026-05-19 | 2026-09-26 | 2026-05-19 | 2027-01-06 | 88
A23510 | Transformer Shed - Sub Station Building | 22 | 2026-09-01 | 2026-09-26 | 2026-06-28 | 2026-09-10 | 88
A23500 | Piping Platforms | 26 | 2026-08-12 | 2026-09-10 | 2026-05-19 | 2026-09-10 | 0
A18420 | Secondary Pipe Rack (SR80) Structure installation | 24 | 2026-08-15 | 2026-09-10 | 2026-11-04 | 2026-12-01 | 70
A17810 | Compressors Area- Steel Structure Erection | 99 | 2026-05-19 | 2026-09-10 | 2026-08-12 | 2026-09-10 | 0
A17820 | Pipe Rack SR81 - Structure Installation | 65 | 2026-06-28 | 2026-09-10 | 2026-12-13 | 2027-01-06 | 0
External Finishes |  | 72 | 2026-07-18 | 2026-10-08 | 2026-10-29 | 2027-01-20 | 89
A61620 | External Finishing | 72 | 2026-07-18 | 2026-10-08 | 2026-10-29 | 2027-01-20 | 89
Internal Finishes |  | 209 | 2026-02-21 | 2026-10-21 | 2026-06-25 | 2027-01-20 | 78
GF SIS Building Architectural Works |  | 141 | 2026-02-21 | 2026-08-03 | 2026-07-07 | 2026-10-07 | 56
A1560 | Painting Works | 42 | 2026-06-16 | 2026-08-03 | 2026-07-14 | 2026-08-12 | 56
A1550 | Plaster Works | 47 | 2026-05-24 | 2026-07-16 | 2026-08-13 | 2026-10-07 | 56
A1570 | Roof Treatments | 29 | 2026-05-17 | 2026-06-18 | 2026-07-07 | 2026-08-16 | 95
A1540 | Block Works and E&I Conduiting Works | 35 | 2026-05-03 | 2026-06-11 | 2026-09-05 | 2026-10-07 | 56
A1660 | Floor Finshes (Tiling, Skirting & Dado etc.) | 48 | 2026-03-23 | 2026-05-17 | 2026-07-28 | 2026-09-20 | 123
A1580 | PCC Flooring Works | 26 | 2026-02-21 | 2026-03-22 | 2026-08-20 | 2026-10-07 | 123
GF Transformers Architectural Works |  | 133 | 2026-05-20 | 2026-10-21 | 2026-08-18 | 2027-01-20 | 78
A1270 | Steel Structure / Corrugated Sheet Installation | 24 | 2026-09-24 | 2026-10-21 | 2026-09-13 | 2026-10-07 | 78
A1250 | Foundation for E&I Support Structure | 32 | 2026-06-07 | 2026-07-13 | 2026-08-18 | 2026-10-07 | 74
A1240 | Painting External Works | 44 | 2026-05-20 | 2026-07-09 | 2026-09-01 | 2026-10-07 | 77
A1260 | Installation of Fence and Doors | 22 | 2026-06-07 | 2026-07-01 | 2026-12-24 | 2027-01-20 | 84
GF Sub-Station Architectural Works |  | 102 | 2026-03-28 | 2026-07-23 | 2026-06-25 | 2027-01-20 | 155
Ground Floor - Cellar Area |  | 71 | 2026-03-28 | 2026-06-17 | 2026-10-31 | 2027-01-20 | 186
A1650 | Installation of Fence and Doors | 18 | 2026-05-28 | 2026-06-17 | 2026-10-31 | 2026-11-25 | 186
A1640 | Flooring works | 30 | 2026-04-23 | 2026-05-27 | 2026-11-26 | 2026-12-30 | 186
A1630 | E&I Support Structure | 23 | 2026-03-28 | 2026-04-22 | 2026-12-31 | 2027-01-20 | 186
First Floor |  | 90 | 2026-04-11 | 2026-07-23 | 2026-06-25 | 2026-10-07 | 65
A26450 | Painting Works (Release for Electrical Equipments) | 43 | 2026-06-04 | 2026-07-23 | 2026-06-25 | 2026-08-19 | 65
A1200 | Floor Finshes (Tiling, Skirting & Dado etc.) | 25 | 2026-06-16 | 2026-07-14 | 2026-08-09 | 2026-09-08 | 73
A26440 | Roof Treatments | 34 | 2026-05-23 | 2026-06-30 | 2026-07-11 | 2026-09-03 | 85
A1090 | Plaster Works | 48 | 2026-04-26 | 2026-06-20 | 2026-08-30 | 2026-10-07 | 65
A1180 | PCC Flooring Works | 27 | 2026-05-16 | 2026-06-15 | 2026-09-09 | 2026-10-07 | 73
A26430 | Block Works and E&I Conduiting Works | 48 | 2026-04-11 | 2026-06-04 | 2026-08-19 | 2026-10-07 | 65
Others |  | 231 | 09-Jan-25 A | 20-Jun-25 A | 46074 | 46083
Topographic |  | 71 | 09-Jan-25 A | 23-May-25 A | 46074 | 46074
Topographic/UG Survey |  | 71 | 09-Jan-25 A | 22-May-25 A | 46074 | 46074
E1100 | Reports of Getech Investigation / UG Scanning | 4 | 16-May-25 A | 22-May-25 A | 46074 | 46074
E1060 | Geotech / Survery of Site | 4 | 09-May-25 A | 15-May-25 A | 46074 | 46074
E1090 | Mobilization of Geotech / UG Scanning | 4 | 01-May-25 A | 08-May-25 A | 46074 | 46074
E1110 | CICPA Passes for Geotech Sub Contractor | 8 | 21-Mar-25 A | 17-Apr-25 A | 46074 | 46074
E1070 | Topo/ UG Scanning Survey | 4 | 18-Apr-25 A | 30-Apr-25 A | 46074 | 46074
E1080 | TBE & PO issuance of Geotech / UG Scanning | 6 | 02-Mar-25 A | 20-Mar-25 A | 46074 | 46074
A28960 | TBE for Topo,UG & Getechnical Survey_IFD/IFC | 5 | 11-Feb-25 A | 01-Mar-25 A | 46074 | 46074
A56200 | TBE for Topo,UG & Getechnical Survey_RCC | 13 | 16-Jan-25 A | 10-Feb-25 A | 46074 | 46074
A56190 | TBE for Topo,UG & Getechnical Survey_IFR | 5 | 09-Jan-25 A | 15-Jan-25 A | 46074 | 46074
Geotech/ Topographic/UG Survey |  | 60 | 11-Feb-25 A | 23-May-25 A | 46074 | 46074
E1040 | Reports of Getech Investigation / UG Scanning | 8 | 17-May-25 A | 23-May-25 A | 46074 | 46074
E1030 | Geotech / Survery of Site | 8 | 10-May-25 A | 16-May-25 A | 46074 | 46074
E1020 | Mobilization of Geotech / UG Scanning | 4 | 01-May-25 A | 08-May-25 A | 46074 | 46074
E1050 | CICPA Passes for Geotech Sub Contractor | 12 | 21-Mar-25 A | 17-Apr-25 A | 46074 | 46074
E1010 | TBE & PO issuance of Geotech / UG Scanning | 6 | 02-Mar-25 A | 20-Mar-25 A | 46074 | 46074
E1000 | RFQ of Geotech / UG Scanning | 4 | 11-Feb-25 A | 01-Mar-25 A | 46074 | 46074
Piling (No required) |  | 196 | 20-Jun-25 A | 20-Jun-25 A | 46074 | 46083
Piling Works |  | 196 | 20-Jun-25 A | 20-Jun-25 A | 46074 | 46083
A15550 | Piling Work (Compressors, Sheds & Equipment) | 69 | 20-Jun-25 A | 20-Jun-25 A | 46074 | 46074
A15570 | Piling Works - Pipe Racks and OG Buffer Drum | 28 | 20-Jun-25 A | 20-Jun-25 A | 46083 | 46083
A15610 | Piling work PSA2 Unit (10 Vessels) | 22 | 20-Jun-25 A | 20-Jun-25 A | 46083 | 46083
A23610 | Mobilization for Production Piles | 12 | 20-Jun-25 A | 20-Jun-25 A | 46074 | 46074
A15650 | Test Piles (including curing time) | 23 | 20-Jun-25 A | 20-Jun-25 A
A15730 | Mobilization of piling contractor | 16 | 20-Jun-25 A | 20-Jun-25 A | 46074 | 46074
A15690 | Data for Test pile | 0 |  | 20-Jun-25 A | 46074 | 46074
A15720 | PO for Piling Contractor | 12 | 20-Jun-25 A | 20-Jun-25 A | 46074 | 46074
Mechanical Construction |  | 488 | 05-Mar-25 A | 2027-01-17 | 2026-03-24 | 2027-07-20 | 132
Equipment erection and installation |  | 339 | 19-Apr-25 A | 2026-12-01 | 2026-03-24 | 2027-01-20 | 34
HVAC Works |  | 69 | 2026-07-12 | 2026-09-29 | 2026-11-02 | 2027-01-20 | 97
A18920 | HVAC Testing and Commissioning works | 14 | 2026-09-14 | 2026-09-29 | 2026-11-02 | 2026-12-01 | 97
A18850 | Complete Duct Connection to AHU & Fan | 10 | 2026-09-08 | 2026-09-19 | 2026-11-02 | 2026-12-01 | 102
A18910 | Installation of electrical / power system and HVAC control system | 15 | 2026-08-27 | 2026-09-13 | 2026-11-17 | 2026-12-16 | 97
A18870 | Installation of buffer tank | 6 | 2026-09-07 | 2026-09-13 | 2026-11-18 | 2026-12-17 | 97
A18860 | Installation and alignment of refrigerant cycle and chiller | 6 | 2026-09-07 | 2026-09-13 | 2026-12-02 | 2026-12-15 | 97
A18840 | Installation of Exhaust Fan | 6 | 2026-09-07 | 2026-09-13 | 2026-12-09 | 2026-12-22 | 103
A18830 | Installation and alignment of air handling units (AHU) | 6 | 2026-09-07 | 2026-09-13 | 2026-12-01 | 2027-01-04 | 97
A18890 | Insulation of refrigerant pipework outside the building | 15 | 2026-08-20 | 2026-09-06 | 2026-12-23 | 2026-12-28 | 103
A18820 | Assembly of Air Handling Unit (AHU) | 5 | 2026-09-01 | 2026-09-06 | 2026-12-19 | 2027-01-04 | 97
A18590 | Insulation of ductwork outside the building | 30 | 2026-07-30 | 2026-09-02 | 2026-12-29 | 2027-01-04 | 106
A18790 | Flushing, cleaning, air blowing of Piping | 12 | 2026-08-18 | 2026-08-31 | 2027-01-05 | 2027-01-11 | 97
A18780 | Pressure testing of pipes | 12 | 2026-08-11 | 2026-08-24 | 2026-12-29 | 2027-01-04 | 97
A18760 | Installation of electrical works inside the building (excluding installation of HVAC power control panel) | 26 | 2026-07-19 | 2026-08-17 | 2026-12-29 | 2027-01-04 | 105
A18580 | Fabrication and installation of ductwork outside the building | 26 | 2026-07-16 | 2026-08-15 | 2026-12-19 | 2027-01-04 | 106
A18770 | Installation of piping inside and outside the building | 26 | 2026-07-12 | 2026-08-10 | 2027-01-05 | 2027-01-16 | 97
A18570 | Fabrication and installation of ductwork inside the building | 26 | 2026-07-12 | 2026-08-10 | 2027-01-05 | 2027-01-20 | 97
GF Sanitary Water Sump Pump (01 No) (70-PC-1409) |  | 40 | 2026-07-04 | 2026-08-18 | 2026-10-26 | 2026-12-10 | 99
A22840 | Grouting of Sanitary Water Sump Pump (70-PC-1409) | 10 | 2026-08-08 | 2026-08-18 | 2026-10-26 | 2026-11-09 | 99
A22830 | Alignment of Sanitary Water Sump Pump (70-PC-1409) | 18 | 2026-07-18 | 2026-08-06 | 2026-11-09 | 2026-11-30 | 99
A22600 | Installation of Sanitary Water Sump Pump (70-PC-1409) | 12 | 2026-07-04 | 2026-07-16 | 2026-11-30 | 2026-12-10 | 99
GF Feed Gas Compressor and Auxilary Equipment Errection |  | 217 | 2026-03-24 | 2026-12-01 | 2026-03-24 | 2026-12-01 | 0
FG Comp 1st Stage Suction Drum(13-VV-705) |  | 48 | 2026-06-22 | 2026-08-16 | 2026-08-16 | 2026-10-10 | 47
A23230 | Insulation of FG Comp 1st Stage Suction Drum(13-VV-705) | 14 | 2026-08-01 | 2026-08-16 | 2026-08-16 | 2026-08-23 | 47
A23080 | Internals (Demister) of FG Comp 1st Stage Suction Drum(13-VV-705) | 15 | 2026-07-14 | 2026-07-30 | 2026-08-24 | 2026-08-31 | 47
A23030 | Grouting of FG Comp 1st Stage Suction Drum(13-VV-705) | 5 | 2026-07-08 | 2026-07-13 | 2026-09-01 | 2026-09-06 | 47
A23020 | Alignment of FG Comp 1st Stage Suction Drum(13-VV-705) | 7 | 2026-06-30 | 2026-07-07 | 2026-09-07 | 2026-09-23 | 47
A22480 | Delivery inspection, Unpacked and Installation of FG Comp 1st Stage Suction Drum(13-VV-705) | 7 | 2026-06-22 | 2026-06-29 | 2026-09-24 | 2026-10-10 | 47
FG Compressor Interstage Cooler (13-HE-703) |  | 51 | 2026-06-09 | 2026-08-06 | 2026-07-26 | 2026-09-22 | 40
A23980 | Insulation of FG Compressor Interstage Cooler (13-HE-703) | 21 | 2026-07-14 | 2026-08-06 | 2026-07-26 | 2026-08-05 | 40
A23920 | Grouting of FG Compressor Interstage Cooler (13-HE-703) | 10 | 2026-07-02 | 2026-07-13 | 2026-08-06 | 2026-08-17 | 40
A23910 | Alignment of FG Compressor Interstage Cooler (13-HE-703) | 10 | 2026-06-21 | 2026-07-01 | 2026-08-18 | 2026-08-29 | 40
A23600 | Intallation of FG Compressor Interstage Cooler (13-HE-703) | 10 | 2026-06-09 | 2026-06-20 | 2026-08-30 | 2026-09-22 | 40
FG Comp After Cooler ( 13-HE-704) |  | 51 | 2026-06-20 | 2026-08-17 | 2026-07-26 | 2026-09-22 | 31
A23370 | Insulation of FG Comp After Cooler ( 13-HE-704) | 21 | 2026-07-25 | 2026-08-17 | 2026-07-26 | 2026-08-05 | 31
A23250 | Grouting of FG Comp After Cooler ( 13-HE-704) | 10 | 2026-07-13 | 2026-07-23 | 2026-08-06 | 2026-08-17 | 31
A23240 | Alignment of FG Comp After Cooler ( 13-HE-704) | 10 | 2026-07-01 | 2026-07-12 | 2026-08-18 | 2026-08-29 | 31
A22540 | Installation of FG Comp After Cooler ( 13-HE-704) | 10 | 2026-06-20 | 2026-06-30 | 2026-08-30 | 2026-09-22 | 31
FG Comp 2nd Stage Discharge Drum(13-VV-707) |  | 40 | 2026-07-14 | 2026-08-29 | 2026-08-08 | 2026-09-22 | 21
A23410 | Insulation of FG Comp 2nd Stage Discharge Drum (13-VV-707) | 15 | 2026-08-12 | 2026-08-29 | 2026-08-08 | 2026-08-12 | 21
A23400 | Internals (Demister Pad) of FG Comp 2nd Stage Discharge Drum (13-VV-707) | 10 | 2026-08-01 | 2026-08-11 | 2026-08-13 | 2026-08-18 | 21
A23390 | Grouting of FG Comp 2nd Stage Discharge Drum (13-VV-707) | 5 | 2026-07-26 | 2026-07-30 | 2026-08-19 | 2026-08-24 | 21
A23380 | Alignment of FG Comp 2nd Stage Discharge Drum (13-VV-707) | 5 | 2026-07-20 | 2026-07-25 | 2026-08-25 | 2026-09-05 | 21
A22530 | Installation of FG Comp 2nd Stage Discharge Drum (13-VV-707) | 5 | 2026-07-14 | 2026-07-19 | 2026-09-06 | 2026-09-22 | 21
FG Comp 2nd Stage Suction Drum(13-VV-706) |  | 44 | 2026-06-25 | 2026-08-15 | 2026-08-03 | 2026-09-22 | 33
A23450 | Insulation of FG Comp 2nd Stage Suction Drum (13-VV-706) | 14 | 2026-07-30 | 2026-08-15 | 2026-08-03 | 2026-08-13 | 33
A23440 | Internals (Demister Pad) of FG Comp 2nd Stage Suction Drum (13-VV-706) | 10 | 2026-07-19 | 2026-07-29 | 2026-08-15 | 2026-08-19 | 33
A23430 | Grouting of FG Comp 2nd Stage Suction Drum (13-VV-706) | 5 | 2026-07-13 | 2026-07-18 | 2026-08-20 | 2026-08-25 | 33
A23420 | Alignment of FG Comp 2nd Stage Suction Drum (13-VV-706) | 5 | 2026-07-07 | 2026-07-12 | 2026-08-26 | 2026-09-06 | 33
A22490 | Delivery inspection, Unpacked and Installation of FG Comp 2nd Stage Suction Drum (13-VV-706) | 10 | 2026-06-25 | 2026-07-06 | 2026-09-07 | 2026-09-22 | 33
Feed Gas (FG) Compressor Installation |  | 217 | 2026-03-24 | 2026-12-01 | 2026-03-24 | 2026-12-01 | 0
C1009 | Punch List Close Out FG Compressor | 10 | 2026-11-21 | 2026-12-01 | 2026-03-24 | 2026-04-09 | 0
C1008 | E&I Installation - FG Compressor | 40 | 2026-10-05 | 2026-11-19 | 2026-04-11 | 2026-05-04 | 0
C1007 | Installation of Piping - FG Compressor | 45 | 2026-09-12 | 2026-11-02 | 2026-05-05 | 2026-05-18 | 0
C1006 | Installation of Auxiliary Equipment - FG Compressor | 0 |  | 2026-09-15 | 2026-07-02 | 2026-07-13 | 21
C1005 | Coupling Alignment - FG Compressor | 20 | 2026-06-28 | 2026-07-21 | 2026-07-14 | 2026-07-30 | 44
C1003 | Grouting - FG Compressor | 10 | 2026-06-16 | 2026-06-28 | 2026-08-01 | 2026-08-11 | 38
C1004 | Pre-alignment of FG Compressor | 15 | 2026-05-30 | 2026-06-16 | 2026-08-19 | 2026-09-10 | 38
C1031 | Installation of FG Compressor Main Driver Motor | 10 | 2026-05-19 | 2026-05-30 |  | 2026-10-10 | 38
C1001 | Installation of FG Compressor (Setting of Pad, Preparation, Position and Leveling) | 12 | 2026-05-05 | 2026-05-18 | 2026-09-12 | 2026-11-02 | 0
C1002 | Setting of FG Compressor Base Plate (Temporary settng, Elevation, Level, Tolerance, Position) | 21 | 2026-04-11 | 2026-05-04 | 2026-10-05 | 2026-11-19 | 0
C1000 | FG Foundation Plan - Foundation Check & Dimensional Examination - FG Compressor | 15 | 2026-03-24 | 2026-04-09 | 2026-11-21 | 2026-12-01 | 0
GF Off Gas Compressor and Auxilary Equipment Errection |  | 210 | 2026-03-24 | 2026-11-23 | 2026-06-04 | 2026-12-10 | 15
Off Gas (OG) Compressor Installation |  | 210 | 2026-03-24 | 2026-11-23 | 2026-06-04 | 2026-12-01 | 7
C1159 | Punch List Close Out (Mechanical) - OG Compressor | 13 | 2026-11-08 | 2026-11-23 | 2026-06-04 | 2026-06-22 | 7
C1149 | E&I Installation - OG Compressor | 35 | 2026-09-28 | 2026-11-08 | 2026-06-22 | 2026-07-16 | 7
C1139 | Installation of Piping - OG Compressor | 35 | 2026-09-22 | 2026-11-01 | 2026-07-16 | 2026-07-30 | 7
C1129 | Installation of Auxiliary Equipment - OG Compressor | 0 |  | 2026-08-29 | 2026-07-30 | 2026-08-09 | 32
C1119 | Coupling and Alignment - OG Compressor | 20 | 2026-06-27 | 2026-07-19 | 2026-08-09 | 2026-08-26 | 62
C1099 | Grouting - OG Compressor | 10 | 2026-06-15 | 2026-06-25 | 2026-08-26 | 2026-09-07 | 62
C1109 | Pre-alignment of OG Compressor | 15 | 2026-05-28 | 2026-06-14 | 2026-09-07 | 2026-09-30 | 62
C1169 | Installation of OG Compressor Main Driver Motor | 8 | 2026-05-19 | 2026-05-27 |  | 2026-10-06 | 62
C1079 | Installation of OG Compressor (Setting of Pad, Preparation, Position and Leveling) | 12 | 2026-05-05 | 2026-05-18 | 2026-09-30 | 2026-11-10 | 62
C1089 | Setting of OG Compressor Base Plate (Temporary setting, Elevation, Level, Tolerance, Position) | 21 | 2026-04-11 | 2026-05-04 | 2026-10-07 | 2026-11-16 | 62
C1069 | OG Foundation Plan - Foundation Check & Dimensional Examination | 15 | 2026-03-24 | 2026-04-09 | 2026-11-17 | 2026-12-01 | 62
OG Buffer Drum (13-VV-712) |  | 68 | 2026-06-13 | 2026-08-30 | 2026-09-30 | 2026-12-10 | 88
A22820 | Insulation of OG Buffer Drum (13-VV-712) | 14 | 2026-08-15 | 2026-08-30 | 2026-09-30 | 2026-10-13 | 88
A22810 | Internals (Demister) of OG Buffer Drum (13-VV-712) | 12 | 2026-08-01 | 2026-08-13 | 2026-10-14 | 2026-10-20 | 88
A25280 | Scafolding Works | 18 | 2026-07-11 | 2026-07-30 | 2026-10-28 | 2026-11-03 | 88
A22800 | Grouting of OG Buffer Drum (13-VV-712) | 6 | 2026-07-18 | 2026-07-23 | 2026-11-04 | 2026-11-10 | 94
A22790 | Alignment of OG Buffer Drum (13-VV-712) | 6 | 2026-07-11 | 2026-07-16 | 2026-10-21 | 2026-11-10 | 94
A22500 | Installation of OG Buffer Drum (13-VV-712) | 6 | 2026-07-04 | 2026-07-09 | 2026-11-11 | 2026-11-24 | 88
A25270 | Ground Preparatory Works for Crane | 12 | 2026-06-13 | 2026-06-25 | 2026-11-25 | 2026-12-10 | 94
OG Compressor Interstage Cooler (13-HE-708) |  | 39 | 2026-04-22 | 2026-06-07 | 2026-08-22 | 2026-10-06 | 104
A23480 | Insulation of OG Compressor Interstage Cooler (13-HE-708) | 20 | 2026-05-14 | 2026-06-07 | 2026-08-22 | 2026-08-26 | 104
A23470 | Grouting of OG Compressor Interstage Cooler (13-HE-708) | 10 | 2026-05-03 | 2026-05-14 | 2026-08-26 | 2026-09-01 | 104
A23460 | Alignment of OG Compressor Interstage Cooler (13-HE-708) | 5 | 2026-04-27 | 2026-05-03 | 2026-09-01 | 2026-09-13 | 104
A22570 | Intallation of OG Compressor Interstage Cooler (13-HE-708) | 4 | 2026-04-22 | 2026-04-27 | 2026-09-13 | 2026-10-06 | 104
OG Comp After Cooler ( 13-HE-709) |  | 39 | 2026-06-27 | 2026-08-10 | 2026-08-22 | 2026-10-06 | 48
A23990 | Insulation of OG Comp After Cooler ( 13-HE-709) | 20 | 2026-07-19 | 2026-08-10 | 2026-08-22 | 2026-08-27 | 48
A23930 | Grouting of OG Comp After Cooler ( 13-HE-709) | 10 | 2026-07-07 | 2026-07-18 | 2026-08-27 | 2026-09-01 | 48
A23490 | Alignment of OG Comp After Cooler ( 13-HE-709) | 4 | 2026-07-02 | 2026-07-06 | 2026-09-01 | 2026-09-13 | 48
A22550 | Installation of OG Comp After Cooler ( 13-HE-709) | 5 | 2026-06-27 | 2026-07-01 | 2026-09-13 | 2026-10-06 | 48
OG Compressor Discharge Drip Leg (13-SP-7004) |  | 32 | 2026-07-23 | 2026-08-29 | 2026-08-30 | 2026-10-06 | 32
A3530 | Insulation of OG Compressor Discharge Drip Leg | 10 | 2026-08-18 | 2026-08-29 | 2026-08-30 | 2026-09-03 | 32
A3520 | Internals of OG Compressor Discharge Drip Leg | 10 | 2026-08-06 | 2026-08-17 | 2026-09-03 | 2026-09-08 | 32
A3510 | Grouting of OG Compressor Discharge Drip Leg | 4 | 2026-08-02 | 2026-08-05 | 2026-09-08 | 2026-09-13 | 32
A3500 | Alignment of OG Compressor Discharge Drip Leg | 4 | 2026-07-28 | 2026-08-01 | 2026-09-13 | 2026-09-24 | 32
A3490 | Installation of OG Compressor Discharge Drip Leg | 4 | 2026-07-23 | 2026-07-27 | 2026-09-24 | 2026-10-06 | 32
OG Comp 2nd Stage Suction Drum(13-VV-713) |  | 40 | 2026-06-21 | 2026-08-05 | 2026-08-20 | 2026-10-06 | 52
A25260 | Insulation of OG Comp 2nd Stage Suction Drum (13-VV-713) | 15 | 2026-07-20 | 2026-08-05 | 2026-08-20 | 2026-08-26 | 52
A25250 | Internals (Demster Pad) of OG Comp 2nd Stage Suction Drum (13-VV-713) | 10 | 2026-07-08 | 2026-07-19 | 2026-08-26 | 2026-09-01 | 52
A24010 | Grouting of OG Comp 2nd Stage Suction Drum (13-VV-713) | 5 | 2026-07-02 | 2026-07-07 | 2026-09-01 | 2026-09-07 | 52
A24000 | Alignment of OG Comp 2nd Stage Suction Drum (13-VV-713) | 5 | 2026-06-27 | 2026-07-01 | 2026-09-07 | 2026-09-19 | 52
A22510 | Installation of OG Comp 2nd Stage Suction Drum (13-VV-713) | 5 | 2026-06-21 | 2026-06-25 | 2026-09-19 | 2026-10-06 | 52
TA Boiler Feed Water Installation |  | 3 | 19-Apr-25 A | 24-May-25 A | 46108 | 46108
A3787 | Installation of BFW Preheater | 3 | 19-Apr-25 A | 24-May-25 A | 46108 | 46108
BF Mechanical Equipments |  | 40 | 2026-06-14 | 2026-07-30 | 2026-11-05 | 2027-01-03 | 135
A22560 | Installation of C4 Guard Regeneration Cooler (50-HE-1410) | 40 | 2026-06-14 | 2026-07-30 | 2026-11-05 | 2026-12-21 | 124
A9660 | Installation of Coalescer (1 No) | 40 | 2026-06-14 | 2026-07-30 | 2026-11-18 | 2027-01-03 | 135
A9650 | Installation of Dripleg (1 No) | 40 | 2026-06-14 | 2026-07-30 | 2026-11-05 | 2026-12-21 | 124
GF PSA2 Package by Linde ( 10 Vessels) |  | 183 | 2026-03-22 | 2026-10-20 | 2026-05-26 | 2026-12-10 | 44
A22870 | Internals of PSA2 Package by Linde ( 10 Vessels) | 45 | 2026-08-30 | 2026-10-20 | 2026-05-26 | 2026-08-03 | 44
A22860 | Grouting of PSA2 Package by Linde ( 10 Vessels) | 45 | 2026-06-24 | 2026-08-15 | 2026-08-04 | 2026-09-24 | 56
A22850 | Alignment of PSA2 Package by Linde ( 10 Vessels) | 45 | 2026-05-31 | 2026-07-21 | 2026-08-29 | 2026-10-19 | 56
A22610 | Installation of PSA2 Package by Linde ( 10 Vessels) | 60 | 2026-03-22 | 2026-05-30 | 2026-10-20 | 2026-12-10 | 56
GF Water Sump Pump (02 Nos) (70-PC-1407) |  | 40 | 2026-06-17 | 2026-08-02 | 2026-10-26 | 2026-12-10 | 112
A22890 | Grouting of Water Sump Pump (70-PC-1407) | 10 | 2026-07-22 | 2026-08-02 | 2026-10-26 | 2026-11-08 | 112
A22880 | Alignment of Water Sump Pump (70-PC-1407) | 18 | 2026-07-01 | 2026-07-21 | 2026-11-09 | 2026-11-29 | 112
A22590 | Installation of Water Sump Pump (70-PC-1407) | 12 | 2026-06-17 | 2026-06-30 | 2026-11-30 | 2026-12-10 | 112
GF PSA2 Slope Drum ( 70-VV-1415) |  | 36 | 2026-07-20 | 2026-08-30 | 2026-10-31 | 2026-12-10 | 88
A23010 | Insulation of PSA2 Slope Drum ( 70-VV-1415) | 11 | 2026-08-18 | 2026-08-30 | 2026-10-31 | 2026-11-04 | 88
A22990 | Internals of PSA2 Slope Drum ( 70-VV-1415) | 10 | 2026-08-06 | 2026-08-17 | 2026-11-05 | 2026-11-10 | 88
A22960 | Grouting of PSA2 Slope Drum ( 70-VV-1415) | 5 | 2026-08-01 | 2026-08-05 | 2026-11-11 | 2026-11-16 | 88
A22930 | Alignment of PSA2 Slope Drum ( 70-VV-1415) | 5 | 2026-07-26 | 2026-07-30 | 2026-11-17 | 2026-11-28 | 88
A22520 | Installation of PSA2 Slope Drum ( 70-VV-1415) | 5 | 2026-07-20 | 2026-07-25 | 2026-11-29 | 2026-12-10 | 88
GF EOT Crane for FG Compressor |  | 27 | 2026-09-12 | 2026-10-12 | 2026-10-15 | 2026-11-19 | 33
C1369 | Installation of the platform, hand railing, cabin, ladder, DSL cage and DSL guard | 10 | 2026-10-01 | 2026-10-12 | 2026-10-27 | 2026-10-31 | 33
C1359 | Crab erection | 3 | 2026-09-28 | 2026-09-30 | 2026-10-15 | 2026-10-26 | 33
C1349 | Installation of end carriage & main girder | 4 | 2026-09-23 | 2026-09-27 | 2026-10-20 | 2026-10-31 | 33
C1329 | Assembly of main girders at ground level | 10 | 2026-09-12 | 2026-09-22 | 2026-11-01 | 2026-11-04 | 33
C1319 | LT rail line installation | 10 | 2026-09-12 | 2026-09-22 | 2026-11-05 | 2026-11-08 | 29
C1339 | Installation of electrical equipment | 4 | 2026-09-12 | 2026-09-15 | 2026-11-09 | 2026-11-19 | 39
GF EOT Crane for OG Compressor |  | 22 | 2026-09-19 | 2026-10-13 | 2026-10-22 | 2026-11-16 | 29
C1299 | Installation of the platform, hand railing, cabin, ladder, DSL cage and DSL guard | 8 | 2026-10-05 | 2026-10-13 | 2026-10-29 | 2026-11-02 | 29
C1289 | Cran erection | 2 | 2026-10-05 | 2026-10-06 | 2026-10-22 | 2026-11-02 | 29
C1279 | Installation of end carriage & main girder | 4 | 2026-09-30 | 2026-10-04 | 2026-10-22 | 2026-11-02 | 29
C1269 | Assembly of main girders at ground level | 10 | 2026-09-19 | 2026-09-29 | 2026-11-03 | 2026-11-07 | 29
C1259 | LT rail line installation | 10 | 2026-09-19 | 2026-09-29 | 2026-11-08 | 2026-11-09 | 29
C1309 | Installation of electrical equipment | 4 | 2026-09-19 | 2026-09-22 | 2026-11-08 | 2026-11-16 | 35
Piping Fabrication |  | 138 | 05-Mar-25 A | 18-Apr-25 A | 46108 | 46108
TA Piping Work |  | 138 | 05-Mar-25 A | 18-Apr-25 A | 46108 | 46108
BFW4050 | Sand blastinfg and painting | 45 | 01-Apr-25 A | 15-Apr-25 A | 46108 | 46108
A17730 | Installation of Scaffolding | 24 | 05-Mar-25 A | 08-Apr-25 A | 46108 | 46108
BFW4010 | Prefabrication of Piping Spools for the BFW | 36 | 11-Apr-25 A | 18-Apr-25 A | 46108 | 46108
BFW4000 | Prefabrication of Tie-ins Spools | 36 | 28-Mar-25 A | 04-Apr-25 A | 46108 | 46108
Piping and Valves Installation |  | 441 | 29-Mar-25 A | 2027-01-17 | 2026-03-27 | 2027-03-11 | 39
BF Piping Works |  | 214 | 2026-02-21 | 2026-10-27 | 2026-03-29 | 2026-12-02 | 31
BFW4040 | Piping connections with tie-ins | 41 | 2026-09-10 | 2026-10-27 | 2026-03-29 | 2026-05-06 | 31
BFW4030 | Piping Hydrotesting - BF | 40 | 2026-08-08 | 2026-09-22 | 2026-05-07 | 2026-09-23 | 31
A9670 | Piping Erection / Installation in Brown Field | 120 | 2026-04-01 | 2026-08-18 | 2026-09-13 | 2026-10-28 | 31
A18520 | Scaffolding for Piping errection on Piperack | 34 | 2026-02-21 | 2026-03-31 | 2026-10-17 | 2026-12-02 | 31
TA Tie-In Execution - A/G Tie-Ins |  | 127 | 29-Mar-25 A | 24-May-25 A | 46108 | 46108
Package 1 |  | 125 | 11-Apr-25 A | 24-May-25 A | 46108 | 46108
Tailgas from Tie In point EU3 to EU3 H2 Tag # IP-B-B3-H3-L-2010 |  | 88 | 11-Apr-25 A | 24-May-25 A | 46108 | 46108
A9830 | End of Work | 1 | 16-May-25 A | 17-May-25 A | 46108 | 46108
A9820 | Torquing / flange management & hand-over to Ops | 0 | 25-Apr-25 A | 15-May-25 A | 46108 | 46108
A9810 | Reinstall insulation (if any) | 0 | 25-Apr-25 A | 15-May-25 A | 46108 | 46108
A9800 | Deblinding, remove temporary support / scaffolds | 0 | 25-Apr-25 A | 15-May-25 A | 46108 | 46108
A9790 | Touch-up painting works | 0 | 25-Apr-25 A | 15-May-25 A | 46108 | 46108
A9780 | Reinstall back piping components (TW/TE, TG, PT, PG if any) | 0 | 25-Apr-25 A | 26-Apr-25 A | 46108 | 46108
A38440 | Hydrotest witness inspection (if required) | 0 | 25-Apr-25 A | 26-Apr-25 A | 46108 | 46108
A38430 | Prepare and hydrotest up to XX BarG (if required) | 0 | 25-Apr-25 A | 26-Apr-25 A | 46108 | 46108
A38420 | Install pipe supports (if any) | 0 | 25-Apr-25 A | 26-Apr-25 A | 46108 | 46108
A9740 | Inspection NDT / RT of selected joints | 0 | 25-Apr-25 A | 26-Apr-25 A | 46108 | 46108
A9730 | Full welding of joints & installation of Tie-In spool 45076 | 0 | 25-Apr-25 A | 26-Apr-25 A | 46108 | 46108
A9720 | Grinding, bevelling of old piping & fit-up with new spool | 0 | 11-Apr-25 A | 24-May-25 A | 46108 | 46108
A9710 | Cut old piping (existing line 45024), haul to ground level | 0 | 11-Apr-25 A | 24-May-25 A | 46108 | 46108
A38410 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 0 | 11-Apr-25 A | 24-May-25 A | 46108 | 46108
A38400 | Removal of insulation & Wallthickness measurement | 0 | 11-Apr-25 A | 24-May-25 A | 46108 | 46108
A9680 | Obtain Work Permit | 0 | 11-Apr-25 A | 24-May-25 A | 46108 | 46108
A38390 | Start of Work | 1 | 11-Apr-25 A | 24-May-25 A | 46108 | 46108
Tailgas Tag # IP-B-B3-M3-L-3010 |  | 88 | 11-Apr-25 A | 24-May-25 A | 46108 | 46108
A38380 | End of Work | 1 | 16-May-25 A | 17-May-25 A | 46108 | 46108
A38370 | Torquing / flange management & hand-over to Ops | 0 | 25-Apr-25 A | 15-May-25 A | 46108 | 46108
A9640 | Reinstall insulation (if any) | 0 | 25-Apr-25 A | 15-May-25 A | 46108 | 46108
A9630 | Deblinding, remove temporary support / scaffolds | 0 | 25-Apr-25 A | 15-May-25 A | 46108 | 46108
A9620 | Touch-up painting works | 0 | 25-Apr-25 A | 15-May-25 A | 46108 | 46108
A9610 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 0 | 25-Apr-25 A | 26-Apr-25 A | 46108 | 46108
A9600 | Hydrotest witness inspection (if required) | 0 | 25-Apr-25 A | 26-Apr-25 A | 46108 | 46108
A9590 | Prepare and hydrotest up to XX BarG (if required) | 0 | 25-Apr-25 A | 26-Apr-25 A | 46108 | 46108
A38360 | Install pipe supports (if any) | 0 | 25-Apr-25 A | 26-Apr-25 A | 46108 | 46108
A38350 | Inspection NDT / RT of selected joints | 0 | 25-Apr-25 A | 26-Apr-25 A | 46108 | 46108
A38340 | Full welding of joints & installation of Tie-In spool 45024 | 0 | 25-Apr-25 A | 26-Apr-25 A | 46108 | 46108
A38330 | Grinding, bevelling of old piping & fit-up with new spool | 0 | 11-Apr-25 A | 24-May-25 A | 46108 | 46108
A38320 | Cut old piping (existing line 45024), haul to ground level | 0 | 11-Apr-25 A | 24-May-25 A | 46108 | 46108
A38310 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 0 | 11-Apr-25 A | 24-May-25 A | 46108 | 46108
A38300 | Removal of insulation & Wallthickness measurement | 0 | 11-Apr-25 A | 24-May-25 A | 46108 | 46108
A38290 | Obtain Work Permit | 0 | 11-Apr-25 A | 24-May-25 A | 46108 | 46108
A38280 | Start of Work | 1 | 11-Apr-25 A | 24-May-25 A | 46108 | 46108
Tailgas Tag # IP-B-M3-B3-L-3020 |  | 88 | 11-Apr-25 A | 17-May-25 A | 46108 | 46108
A9490 | End of Work | 1 | 16-May-25 A | 17-May-25 A | 46108 | 46108
A9480 | Torquing / flange management & hand-over to Ops | 0 | 16-May-25 A | 17-May-25 A | 46108 | 46108
A9470 | Reinstall insulation (if any) | 0 | 16-May-25 A | 17-May-25 A | 46108 | 46108
A9460 | Deblinding, remove temporary support / scaffolds | 0 | 16-May-25 A | 17-May-25 A | 46108 | 46108
A38270 | Touch-up painting works | 0 | 16-May-25 A | 17-May-25 A | 46108 | 46108
A9440 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 0 | 16-May-25 A | 17-May-25 A | 46108 | 46108
A9430 | Hydrotest witness inspection (if required) | 0 | 16-May-25 A | 17-May-25 A | 46108 | 46108
A9420 | Prepare and hydrotest up to XX BarG (if required) | 0 | 16-May-25 A | 17-May-25 A | 46108 | 46108
A9410 | Install pipe supports (if any) | 0 | 11-Apr-25 A | 11-Apr-25 A | 46108 | 46108
A9400 | Inspection NDT / RT of selected joints | 0 | 11-Apr-25 A | 11-Apr-25 A | 46108 | 46108
A9390 | Full welding of joints & installation of Tie-In spool 45024 | 0 | 11-Apr-25 A | 11-Apr-25 A | 46108 | 46108
A9380 | Grinding, bevelling of old piping & fit-up with new spool | 0 | 11-Apr-25 A | 11-Apr-25 A | 46108 | 46108
A9370 | Cut old piping (existing line 45024), haul to ground level | 0 | 11-Apr-25 A | 11-Apr-25 A | 46108 | 46108
A9360 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 0 | 11-Apr-25 A | 11-Apr-25 A | 46108 | 46108
A9350 | Removal of insulation & Wallthickness measurement | 0 | 11-Apr-25 A | 11-Apr-25 A | 46108 | 46108
A9340 | Obtain Work Permit | 0 | 11-Apr-25 A | 11-Apr-25 A | 46108 | 46108
A9330 | Start of Work | 1 | 11-Apr-25 A | 11-Apr-25 A | 46108 | 46108
Tailgas Tag # IP-B-B3-M3-L-3030 |  | 88 | 11-Apr-25 A | 17-May-25 A | 46108 | 46108
A9320 | End of Work | 1 | 11-Apr-25 A | 17-May-25 A | 46108 | 46108
A9310 | Torquing / flange management & hand-over to Ops | 0 | 11-Apr-25 A | 17-May-25 A | 46108 | 46108
A9300 | Reinstall insulation (if any) | 0 | 11-Apr-25 A | 17-May-25 A | 46108 | 46108
A9290 | Deblinding, remove temporary support / scaffolds | 0 | 11-Apr-25 A | 17-May-25 A | 46108 | 46108
A9280 | Touch-up painting works | 0 | 11-Apr-25 A | 17-May-25 A | 46108 | 46108
A38260 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 0 | 11-Apr-25 A | 17-May-25 A | 46108 | 46108
A9260 | Hydrotest witness inspection | 0 | 11-Apr-25 A | 17-May-25 A | 46108 | 46108
A9250 | Prepare and hydrotest up to XX BarG | 0 | 11-Apr-25 A | 17-May-25 A | 46108 | 46108
A9240 | Install pipe supports (if any) | 0 | 11-Apr-25 A | 17-May-25 A | 46108 | 46108
A9230 | Inspection NDT / RT of selected joints | 0 | 11-Apr-25 A | 17-May-25 A | 46108 | 46108
A38250 | Full welding of joints & installation of Tie-In spool 45075 | 0 | 11-Apr-25 A | 17-May-25 A | 46108 | 46108
A38240 | Grinding, bevelling of old piping & fit-up with new spool | 0 | 11-Apr-25 A | 17-May-25 A | 46108 | 46108
A38230 | Cut old piping (existing line 45024), haul to ground level | 0 | 11-Apr-25 A | 17-May-25 A | 46108 | 46108
A9190 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 0 | 11-Apr-25 A | 17-May-25 A | 46108 | 46108
A9180 | Removal of insulation & Wall thickness measurement | 0 | 11-Apr-25 A | 17-May-25 A | 46108 | 46108
A9170 | Obtain Work Permit | 0 | 11-Apr-25 A | 17-May-25 A | 46108 | 46108
A9160 | Start of Work | 1 | 11-Apr-25 A | 17-May-25 A | 46108 | 46108
Tailgas Tag # IP-B-B3-M3-L-3050 |  | 86 | 11-Apr-25 A | 17-May-25 A | 46108 | 46108
A9150 | End of Work | 1 | 11-Apr-25 A | 17-May-25 A | 46108 | 46108
A9140 | Torquing / flange management & hand-over to Ops | 0 | 11-Apr-25 A | 17-May-25 A | 46108 | 46108
A9130 | Reinstall insulation (if any) | 0 | 11-Apr-25 A | 17-May-25 A | 46108 | 46108
A9120 | Deblinding, remove temporary support / scaffolds | 0 | 11-Apr-25 A | 17-May-25 A | 46108 | 46108
A9030 | Gas measurement | 0 | 11-Apr-25 A | 17-May-25 A | 46108 | 46108
A9020 | Installation of new valve | 0 | 11-Apr-25 A | 17-May-25 A | 46108 | 46108
A9010 | Removal of existing valve | 0 | 11-Apr-25 A | 17-May-25 A | 46108 | 46108
A9000 | Obtain Work Permit | 0 | 11-Apr-25 A | 17-May-25 A | 46108 | 46108
A8990 | Start of Work | 1 | 11-Apr-25 A | 17-May-25 A | 46108 | 46108
Regeneration gas from 50-HE-1402 Tag # IP-B-B3-M3-L-3090 |  | 88 | 11-Apr-25 A | 17-May-25 A | 46108 | 46108
A8980 | End of Work | 0 | 11-Apr-25 A | 17-May-25 A | 46108 | 46108
A8970 | Torquing / flange management & hand-over to Ops | 0 | 11-Apr-25 A | 17-May-25 A | 46108 | 46108
A8960 | Reinstall insulation (if any) | 0 | 11-Apr-25 A | 17-May-25 A | 46108 | 46108
A8950 | Deblinding, remove temporary support / scaffolds | 0 | 11-Apr-25 A | 17-May-25 A | 46108 | 46108
A8940 | Touch-up painting works | 0 | 11-Apr-25 A | 17-May-25 A | 46108 | 46108
A8930 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 0 | 11-Apr-25 A | 17-May-25 A | 46108 | 46108
A8920 | Hydrotest witness inspection | 0 | 11-Apr-25 A | 17-May-25 A | 46108 | 46108
A8910 | Prepare and hydrotest up to XX BarG | 0 | 11-Apr-25 A | 17-May-25 A | 46108 | 46108
A8900 | Install pipe supports (if any) | 0 | 11-Apr-25 A | 17-May-25 A | 46108 | 46108
A8890 | Inspection NDT / RT of selected joints | 0 | 11-Apr-25 A | 17-May-25 A | 46108 | 46108
A8880 | Full welding of joints & installation of Tie-In spool 140068 | 0 | 11-Apr-25 A | 17-May-25 A | 46108 | 46108
A8870 | Grinding, bevelling of old piping & fit-up with new spool | 0 | 11-Apr-25 A | 17-May-25 A | 46108 | 46108
A8860 | Cut old piping (existing line 140025), haul to ground level | 0 | 11-Apr-25 A | 17-May-25 A | 46108 | 46108
A8850 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 0 | 11-Apr-25 A | 17-May-25 A | 46108 | 46108
A8840 | Wallthickness measurement | 0 | 11-Apr-25 A | 17-May-25 A | 46108 | 46108
A8830 | Obtain Work Permit | 0 | 11-Apr-25 A | 17-May-25 A | 46108 | 46108
A8820 | Start of Work | 0 | 11-Apr-25 A | 17-May-25 A | 46108 | 46108
Tailgas from 13-KX-402 Tag # IP-B-B3-M3-L-3100 |  | 88 | 11-Apr-25 A | 17-May-25 A | 46108 | 46108
A8810 | End of Work | 1 | 11-Apr-25 A | 17-May-25 A | 46108 | 46108
A8800 | Torquing / flange management & hand-over to Ops | 0 | 11-Apr-25 A | 17-May-25 A | 46108 | 46108
A38220 | Reinstall insulation (if any) | 0 | 11-Apr-25 A | 17-May-25 A | 46108 | 46108
A8780 | Deblinding, remove temporary support / scaffolds | 0 | 11-Apr-25 A | 17-May-25 A | 46108 | 46108
A8770 | Touch-up painting works | 0 | 11-Apr-25 A | 17-May-25 A | 46108 | 46108
A8760 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 0 | 11-Apr-25 A | 17-May-25 A | 46108 | 46108
A8750 | Hydrotest witness inspection (if required) | 0 | 11-Apr-25 A | 17-May-25 A | 46108 | 46108
A8740 | Prepare and hydrotest up to XX BarG (if required) | 0 | 11-Apr-25 A | 17-May-25 A | 46108 | 46108
A8730 | Install pipe supports (if any) | 0 | 11-Apr-25 A | 17-May-25 A | 46108 | 46108
A8720 | Inspection NDT / RT of selected joints | 0 | 11-Apr-25 A | 17-May-25 A | 46108 | 46108
A8710 | Full welding of joints & installation of Tie-In spool 45024 | 0 | 11-Apr-25 A | 17-May-25 A | 46108 | 46108
A8700 | Grinding, bevelling of old piping & fit-up with new spool | 0 | 11-Apr-25 A | 17-May-25 A | 46108 | 46108
A8690 | Cut old piping (existing line 45024), haul to ground level | 0 | 11-Apr-25 A | 17-May-25 A | 46108 | 46108
A8680 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 0 | 11-Apr-25 A | 17-May-25 A | 46108 | 46108
A8670 | Removal of insulation & Wallthickness measurement | 0 | 11-Apr-25 A | 17-May-25 A | 46108 | 46108
A8660 | Obtain Work Permit | 0 | 11-Apr-25 A | 17-May-25 A | 46108 | 46108
A8650 | Start of Work | 1 | 11-Apr-25 A | 17-May-25 A | 46108 | 46108
Cooling Water from EU3 Tie In Point to 50-HE-1410 Tag # IP-B-B3-M3-L-3120 |  | 88 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A8640 | End of Work | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A8630 | Torquing / flange management & hand-over to Ops | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A8620 | Reinstall insulation (if any) | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A8610 | Deblinding, remove temporary support / scaffolds | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A8600 | Touch-up painting works | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A8590 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A8580 | Hydrotest witness inspection (if required) | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A8570 | Prepare and hydrotest up to XX BarG (if required) | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A8560 | Install pipe supports (if any) | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A8550 | Inspection NDT / RT of selected joints | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A8540 | Full welding of joints & installation of Tie-In spool 140033 | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A8530 | Grinding, bevelling of old piping & fit-up with new spool | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A8520 | Cut old piping (existing line 140036) , haul to ground level | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A8510 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A8500 | Wallthickness measurement | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A38210 | Obtain Work Permit | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A8480 | Start of Work | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
Regeneration Gas C4 Hydrogenation from 13-VA-804A/B Tag # IP-B-B3-M3-L-3170 |  | 88 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A8470 | End of Work | 1 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A8460 | Torquing / flange management & hand-over to Ops | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A8450 | Reinstall insulation (if any) | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A8440 | Deblinding, remove temporary support / scaffolds | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A38200 | Touch-up painting works | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A8420 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A8410 | Hydrotest witness inspection (if required) | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A8400 | Prepare and hydrotest up to XX BarG (if required) | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A8390 | Install pipe supports (if any) | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A8380 | Inspection NDT / RT of selected joints | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A38190 | Full welding of joints & installation of Tie-In spool 81142 | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A8360 | Grinding, bevelling of old piping & fit-up with new spool | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A8350 | Cut old piping (existing line 41022), haul to ground level | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A38180 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A38170 | Removal of insulation & Wallthickness measurement | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A38160 | Obtain Work Permit | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A38150 | Start of Work | 1 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
Tailgas line bleed Tag # IP-B-B3-M3-L-3180 |  | 88 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A8300 | End of Work | 1 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A8290 | Torquing / flange management & hand-over to Ops | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A8280 | Reinstall insulation (if any) | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A8270 | Deblinding, remove temporary support / scaffolds | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A8260 | Touch-up painting works | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A38140 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A8240 | Hydrotest witness inspection (if required) | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A8230 | Prepare and hydrotest up to XX BarG (if required) | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A8220 | Install pipe supports (if any) | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A8210 | Inspection NDT / RT of selected joints | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A8200 | Full welding of joints & installation of Tie-In spool 45024 | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A8190 | Grinding, bevelling of old piping & fit-up with new spool | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A8180 | Cut old piping (existing line 45024), haul to ground level | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A8170 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A38130 | Removal of insulation & Wallthickness measurement | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A38120 | Obtain Work Permit | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A38110 | Start of Work | 1 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
Treated VHP BFW Preheater 52-HE-1402 bypass valve Tag # IP-B-B3-M3-L-3190 |  | 88 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A38100 | End of Work | 1 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A8120 | Torquing / flange management & hand-over to Ops | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A8110 | Reinstall insulation (if any) | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A8100 | Deblinding, remove temporary support / scaffolds | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A8090 | Touch-up painting works | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A8080 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A8070 | Hydrotest witness inspection (if required) | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A8060 | Prepare and hydrotest up to XX BarG (if required) | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A8050 | Install pipe supports (if any) | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A8040 | Inspection NDT / RT of selected joints | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A8030 | Welding of gate valve & installation of Tie-In spool 140025 | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A8020 | Grinding, bevelling & fit-up of valve with new spool | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A8010 | Cut old piping (existing line 140025), haul to ground level | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A8000 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7990 | Removal of insulation & Wallthickness measurement | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7980 | Obtain Work Permit | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7970 | Start of Work | 1 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
Treated VHP BFW from EU3 to 52-HE-1402 Tag # IP-B-B3-M3-L-3210 |  | 88 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7960 | End of Work | 1 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7950 | Torquing / flange management & hand-over to Ops | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7940 | Reinstall insulation (if any) | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7930 | Deblinding, remove temporary support / scaffolds | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7920 | Touch-up painting works | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7910 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7900 | Hydrotest witness inspection | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7890 | Prepare and hydrotest up to XX BarG | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7880 | Install pipe supports (if any) | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7870 | Inspection NDT / RT of selected joints | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7860 | Full welding of joints & installation of Tie-In spool 140219 | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7850 | Grinding, bevelling of old piping & fit-up with new spool | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7840 | Cut old piping (existing line 140025), haul to ground level | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7830 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7820 | Removal of insulation & Wallthickness measurement | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7810 | Obtain Work Permit | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7800 | Start of Work | 1 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
LP- Steam from EU3 Tie In Point to 52-HE-1402 Tag # IP-B-B3-M3-L-3230 |  | 88 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7790 | End of Work | 1 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7780 | Torquing / flange management & hand-over to Ops | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7770 | Reinstall insulation (if any) | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7760 | Deblinding, remove temporary support / scaffolds | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7750 | Touch-up painting works | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7740 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7730 | Hydrotest witness inspection Iif required) | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7720 | Prepare and hydrotest up to XX BarG Iif required) | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7710 | Install pipe supports (if any) | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7700 | Inspection NDT / RT of selected joints | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7690 | Welding of weldolet and installation of Tie-In spool 140489 | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7680 | Grinding, bevelling of old piping & fit-up with new spool | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7670 | Cut old piping (existing line 140472), haul to ground level | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7660 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7650 | Removal of insulation & Wallthickness measurement | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7640 | Obtain Work Permit | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7630 | Start of Work | 1 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
Package 2 |  | 127 | 29-Mar-25 A | 20-May-25 A | 46108 | 46108
Regeneration Gas from 50-HE-1402 Tag # IP-B-B3-M3-L-3260 |  | 88 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7620 | End of Work | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7610 | Torquing / flange management & hand-over to Ops | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7600 | Reinstall insulation (if any) | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7590 | Deblinding, remove temporary support / scaffolds | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7580 | Touch-up painting works | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7570 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7560 | Hydrotest witness inspection (if required) | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7550 | Prepare and hydrotest up to XX BarG (if required) | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7540 | Install pipe supports (if any) | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7530 | Inspection NDT / RT of selected joints | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7520 | Full welding of joints & installation of Tie-In spool 140025 | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7510 | Grinding, bevelling of old piping & fit-up with new spool | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7500 | Cut old piping (existing line 140025), haul to ground level | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7490 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7480 | Wallthickness measurement | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7470 | Obtain Work Permit | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7460 | Start of Work | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
Nitrogen from EU3 to 64PSV14001 Tag # IP-B-B3-M3-L-3380 |  | 88 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7450 | End of Work | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7440 | Torquing / flange management & hand-over to Ops | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7430 | Reinstall insulation (if any) | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7420 | Deblinding, remove temporary support / scaffolds | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7410 | Touch-up painting works | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7400 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7390 | Hydrotest witness inspection | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7380 | Prepare and hydrotest up to XX BarG | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7370 | Install pipe supports (if any) | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7360 | Inspection NDT / RT of selected joints | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7350 | Full welding of joints & installation of Tie-In spool 140038 | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7340 | Grinding, bevelling of old piping & fit-up with new spool | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7330 | Cut old piping (existing line 140148) , haul to ground level | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7320 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7310 | Wallthickness measurement | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7300 | Obtain Work Permit | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7290 | Start of Work | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
Regeneration Gas C4 Hydrogenation Tag # IP-B-B3-M3-L-3390 |  | 88 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7280 | End of Work | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7270 | Torquing / flange management & hand-over to Ops | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7260 | Reinstall insulation (if any) | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7250 | Deblinding, remove temporary support / scaffolds | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7240 | Touch-up painting works | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7230 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7220 | Hydrotest witness inspection (if required) | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7210 | Prepare and hydrotest up to XX BarG (if required) | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7200 | Install pipe supports (if any) | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7190 | Inspection NDT / RT of selected joints & Additional Testing of Tie-in Valve | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7180 | Full welding of joints & installation of Tie-In spool 81184 | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7170 | Grinding, bevelling of old piping & fit-up with new spool | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7160 | Cut old piping (existing line 81142), haul to ground level | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7150 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7140 | Removal of insulation & Wallthickness measurement | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7130 | Obtain Work Permit | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7120 | Start of Work | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
50AT-14101A sample tap Tag # IP-B-B3-M3-L-3430 |  | 88 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7110 | End of Work | 1 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7100 | Torquing / flange management & hand-over to Ops | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7090 | Reinstall insulation (if any) | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7080 | Deblinding, remove temporary support / scaffolds | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7070 | Touch-up painting works | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7060 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7050 | Hydrotest witness inspection (if required) | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7040 | Prepare and hydrotest up to XX BarG (if required) | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7030 | Install pipe supports (if any) | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7020 | Inspection NDT / RT of selected joints | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7010 | Full welding of joints including weldolet & installation of Tie-In spool | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A7000 | Grinding, bevelling of old piping & fit-up with new spool | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A6990 | Cut old piping & support, haul to ground level | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A6980 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A6970 | Removal of insulation & Wallthickness measurement | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A6960 | Obtain Work Permit | 0 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
A6950 | Start of Work | 1 | 15-Apr-25 A | 20-May-25 A | 46108 | 46108
Regeneration Gas C4 Hydrogenation vent point Tag # P-B-B3-M3-L-3500 |  | 88 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6940 | End of Work | 1 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6930 | Torquing / flange management & hand-over to Ops | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6920 | Reinstall insulation (if any) | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6910 | Deblinding, remove temporary support / scaffolds | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6900 | Touch-up painting works | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6890 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A38090 | Hydrotest witness inspection (if required) | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A38080 | Prepare and hydrotest up to XX BarG (if required) | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A38070 | Install pipe supports (if any) | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6850 | Inspection NDT / RT of selected joints | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6840 | Welding of 8x1" weldolet and flange with valve and instrument | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6830 | Grinding, bevelling of old piping & fit-up with new spool | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6820 | Cut old piping (existing line 81142), haul to ground level | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6810 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6800 | Removal of Insulation & Wallthickness measurement | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6790 | Obtain Work Permit | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6780 | Start of Work | 1 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
Sample point in Regeneration gas cooler outlet Tag # IP-B-B3-M3-L-3510 |  | 88 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6770 | End of Work | 1 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6760 | Torquing / flange management & hand-over to Ops | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6750 | Reinstall insulation (if any) | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6740 | Deblinding, remove temporary support / scaffolds | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6730 | Touch-up painting works | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6720 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6710 | Hydrotest witness inspection (if required) | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6700 | Prepare and hydrotest up to XX BarG (if required) | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6690 | Install pipe supports (if any) | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6680 | Inspection NDT / RT of selected joints | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6670 | Welding of 20x1" weldolet and flange with valve and instrument 50S-14161L | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6660 | Grinding, bevelling of old piping & fit-up with new spool | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6650 | Cut old piping (existing line 140024), haul to ground level | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6640 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6630 | Wallthickness measurement | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6620 | Obtain Work Permit | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6610 | Start of Work | 1 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
Reinforced Branch connection for WG flare (Installation of 5 Tie Ins) Tag # IP-B-B3-M3-L-3520 |  | 88 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6600 | End of Work | 1 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6590 | Torquing / flange management & hand-over to Ops | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6580 | Reinstall insulation (if any) | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6570 | Deblinding, remove temporary support / scaffolds | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6560 | Touch-up painting works | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6550 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6540 | Hydrotest witness inspection (if required) | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6530 | Prepare and hydrotest up to XX BarG (if required) | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6520 | Install pipe supports (if any) | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6510 | Inspection NDT / RT of selected joints | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6500 | Full welding of joints (tie in Tee piece, than the tie in spools) | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6490 | Grinding, bevelling of old piping & fit-up with new spool | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6480 | Cut old piping (existing line 140301), haul to ground level | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6470 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6460 | Wallthickness measurement | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6450 | Obtain Work Permit | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6440 | Start of Work | 1 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
Reinforced Branch connection pipe specification break for WG flare Tag # P-B-B3-M3-L-3530 |  | 88 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6430 | End of Work | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6420 | Torquing / flange management & hand-over to Ops | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6410 | Reinstall insulation (if any) | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6400 | Deblinding, remove temporary support / scaffolds | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6390 | Touch-up painting works | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6380 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6370 | Hydrotest witness inspection (if required) | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6360 | Prepare and hydrotest up to XX BarG (if required) | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6350 | Install pipe supports (if any) | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6340 | Inspection NDT / RT of selected joints | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6330 | Full welding of joints | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6320 | Grinding, bevelling of old piping & fit-up with new spool | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6310 | Cut old piping (existing line 140301), haul to ground level | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6300 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6290 | Wallthickness measurement | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6280 | Obtain Work Permit | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6270 | Start of Work | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
PSA2 Off Gas from EU3 to EU3 Tie In point Tag # IP-B-H3-B3-L-2022 |  | 88 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6260 | End of Work | 1 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6250 | Torquing / flange management & hand-over to Ops | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6240 | Reinstall insulation (if any) | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6230 | Deblinding, remove temporary support / scaffolds | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6220 | Touch-up painting works | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6210 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6200 | Hydrotest witness inspection (if required) | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6190 | Prepare and hydrotest up to XX BarG (if required) | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6180 | Install pipe supports (if any) | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6170 | Inspection NDT / RT of selected joints | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6160 | Full welding of joints, Tee & installation of Tie-In spool 72069 | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6150 | Grinding, bevelling of old piping & fit-up with new spool | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6140 | Cut old piping (existing line 45024) , haul to ground level | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6130 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6120 | Removal of insulation & Wallthickness measurement | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6110 | Obtain Work Permit | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6100 | Start of Work | 1 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
Process Water from EU3 H2 to EU3 Tie In Point Tag # IP-B-H3-B3-L-2042 |  | 88 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6090 | End of Work | 1 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6080 | Torquing / flange management & hand-over to Ops | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6070 | Reinstall insulation (if any) | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6060 | Deblinding, remove temporary support / scaffolds | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6050 | Touch-up painting works | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6040 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6030 | Hydrotest witness inspection (if required) | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6020 | Prepare and hydrotest up to XX BarG (if required) | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6010 | Install pipe supports (if any) | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A6000 | Inspection NDT / RT of selected joints | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A5990 | Welding of Tie-in spool weldolet | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A5980 | Grinding, bevelling of old piping & fit-up with new spool | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A5970 | Cut old piping (existing line 20002), haul to ground level | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A5960 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A5950 | Wallthickness measurement | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A5940 | Obtain Work Permit | 0 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
A5930 | Start of Work | 1 | 29-Mar-25 A | 17-May-25 A | 46108 | 46108
Warm Liquid Flare from EU3 to EU3 Tie In point Tag # IP-B-H3-B3-L-2052 |  | 88 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5920 | End of Work | 1 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5910 | Torquing / flange management & hand-over to Ops | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5900 | Reinstall insulation (if any) | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5890 | Deblinding, remove temporary support / scaffolds | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5880 | Touch-up painting works | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5870 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5860 | Hydrotest witness inspection | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5850 | Prepare and hydrotest up to XX BarG | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5840 | Install pipe supports (if any) | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5830 | Inspection NDT / RT of selected joints | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5820 | Full welding of joints & installation of Tie-In spool 140382 | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5810 | Grinding, bevelling of old piping & fit-up with new spool | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5800 | Cut old piping (existing line 140301), haul to ground level | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5790 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5780 | Wallthickness measurement | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5770 | Obtain Work Permit | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5760 | Start of Work | 1 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
Warm Gas Flare from EU3 to EU3 Tie In point Tag # IP-B-H3-B3-L-2062 |  | 88 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5750 | End of Work | 1 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5740 | Torquing / flange management & hand-over to Ops | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5730 | Reinstall insulation (if any) | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5720 | Deblinding, remove temporary support / scaffolds | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5710 | Touch-up painting works | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5700 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5690 | Hydrotest witness inspection | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5680 | Prepare and hydrotest up to XX BarG | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5670 | Install pipe supports (if any) | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5660 | Inspection NDT / RT of selected joints | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5650 | Full welding of joints & installation of Tie-In spool 140381 | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5640 | Grinding, bevelling of old piping & fit-up with new spool | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5630 | Cut old piping (existing line 140301), haul to ground level | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5620 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5610 | Wallthickness measurement | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5600 | Obtain Work Permit | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5590 | Start of Work | 1 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
LP Condensate from EU3 H2 to EU3 Tie In point Tag # IP-B-H3-B3-L-2072 |  | 88 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5580 | End of Work | 1 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5570 | Torquing / flange management & hand-over to Ops | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5560 | Reinstall insulation (if any) | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5550 | Deblinding, remove temporary support / scaffolds | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5540 | Touch-up painting works | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5530 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5520 | Hydrotest witness inspection (if required) | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5510 | Prepare and hydrotest up to XX BarG (if required) | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5500 | Install pipe supports (if any) | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5490 | Inspection NDT / RT of selected joints | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5480 | Full welding of joints including weldolet & installation of Tie-In spool 140434 | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5470 | Grinding, bevelling of old piping & fit-up with new spool | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5460 | Cut old piping (existing line 140101), haul to ground level | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5450 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5440 | Removal of insulation & Wallthickness measurement | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5430 | Obtain Work Permit | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5420 | Start of Work | 1 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
Package 3 |  | 126 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
Cooling Water Return from EU3 H2 to U&O3 Tie In point Tag # IP-B-H3-U3-L-1101 |  | 88 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5410 | End of Work | 1 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5400 | Torquing / flange management & hand-over to Ops | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5390 | Reinstall insulation (if any) | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5380 | Deblinding, remove temporary support / scaffolds | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5370 | Touch-up painting works | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5360 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5350 | Hydrotest witness inspection (if required) | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5340 | Prepare and hydrotest up to XX BarG (if required) | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5330 | Install pipe supports (if any) | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5320 | Inspection NDT / RT of selected joints | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5310 | Full welding of joints including weldolet & installation of Tie-In spool 00215 | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5300 | Grinding, bevelling of old piping & fit-up with new spool | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5290 | Cut old piping (existing line '00018), haul to ground level | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5280 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5270 | Wall thickness measurement | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5260 | Obtain Work Permit | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5250 | Start of Work | 1 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
PSA2 Off Gas Recycle to CGC Tag # IP-B-M3-B3-L-3040 |  | 88 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5240 | End of Work | 1 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5230 | Torquing / flange management & hand-over to Ops | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5220 | Reinstall insulation (if any) | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A38060 | Deblinding, remove temporary support / scaffolds | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A38050 | Touch-up painting works | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A38040 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A38030 | Hydrotest witness inspection (if required) | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A38020 | Prepare and hydrotest up to XX BarG (if required) | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A38010 | Install pipe supports (if any) | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5150 | Inspection NDT / RT of selected joints | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5140 | Full welding of weldolet & installation of Tie-In spool 72068 | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5130 | Grinding, bevelling of old piping & fit-up with new spool | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5120 | Cut old piping & support, haul to ground level | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5110 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5100 | Removal of insulation & Wall thickness measurement | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5090 | Obtain Work Permit | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5080 | Start of Work | 3 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
Regeneration Gas from 50-HE-1410 to 50-VV-1401 Tag # IP-B-M3-B3-L-3070 |  | 88 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5070 | End of Work | 1 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5060 | Torquing / flange management & hand-over to Ops | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5050 | Reinstall insulation (if any) | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5040 | Deblinding, remove temporary support / scaffolds | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5030 | Touch-up painting works | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5020 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5010 | Hydrotest witness inspection (if required) | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A5000 | Prepare and hydrotest up to XX BarG (if required) | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A4990 | Install pipe supports (if any) | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A4980 | Inspection NDT / RT of selected joints | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A4970 | Full welding of joints & installation of Tie-In spool 140489 | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A4960 | Grinding, bevelling of old piping & fit-up with new spool | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A4950 | Cut old piping (existing line 45024), haul to ground level | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A4940 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A4930 | Removal of insulation & Wall thickness measurement | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A4920 | Obtain Work Permit | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A4910 | Start of Work | 1 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
Regeneration Gas to 50-VV-1401 Tag # IP-B-M3-B3-L-3110 |  | 88 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A4900 | End of Work | 1 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A4890 | Torquing / flange management & hand-over to Ops | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A4880 | Reinstall insulation (if any) | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A4870 | Deblinding, remove temporary support / scaffolds | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A4860 | Touch-up painting works | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A4850 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A4840 | Hydrotest witness inspection (if required) | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A4830 | Prepare and hydrotest up to XX BarG (if required) | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A4820 | Install pipe supports (if any) | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A4810 | Inspection NDT / RT of selected joints | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A4800 | Full welding of joints | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A4790 | Grinding, bevelling of old piping & fit-up with new spool | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A4780 | Cut old piping (existing line 140025) , haul to ground level | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A4770 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A4760 | Wall thickness measurement | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A4750 | Obtain Work Permit | 0 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
A4740 | Start of Work | 1 | 02-Apr-25 A | 17-May-25 A | 46108 | 46108
Cooling Water from 50-HE-1410 to EU3 Tie-In Point Tag # IP-B-M3-B3-L-3130 |  | 88 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A4730 | End of Work | 1 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A4720 | Torquing / flange management & hand-over to Ops | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A4710 | Reinstall insulation (if any) | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A4700 | Deblinding, remove temporary support / scaffolds | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A4690 | Touch-up painting works | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A4680 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A4670 | Hydrotest witness inspection (if required) | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A4660 | Prepare and hydrotest up to XX BarG (if required) | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A4650 | Install pipe supports (if any) | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A4640 | Inspection NDT / RT of selected joints | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A4630 | Full welding of joints & installation of Tie-In spool 140065 | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A4620 | Grinding, bevelling of old piping & fit-up with new spool | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A4610 | Cut old piping (existing line 140034) & support, haul to ground level | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A4600 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A4590 | Wall thickness measurement | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A4580 | Obtain Work Permit | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A4570 | Start of Work | 1 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
Warm Gas Flare from 50-HE-1410 to EU3 Tie In Point Tag # IP-B-M3-B3-L-3140 |  | 88 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A4560 | End of Work | 1 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A4550 | Torquing / flange management & hand-over to Ops | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A4540 | Reinstall insulation (if any) | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A4530 | Deblinding, remove temporary support / scaffolds | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A4520 | Touch-up painting works | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A4510 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A4500 | Hydrotest witness inspection (if required) | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A4490 | Prepare and hydrotest up to XX BarG (if required) | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A4480 | Install pipe supports (if any) | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A4470 | Inspection NDT / RT of selected joints | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A4460 | Full welding of joints & installation of Tie-In spool 140379 | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A4450 | Grinding, bevelling of old piping & fit-up with new spool | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A4440 | Cut old piping (existing line 140301), haul to ground level | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A4430 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A4420 | Wall thickness measurement | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A4410 | Obtain Work Permit | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A4400 | Start of Work | 1 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
Treated VHP BFW from 52-HE-1402 to EU3 Tag # IP-B-M3-B3-L-3220 |  | 88 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A4390 | End of Work | 1 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A4380 | Torquing / flange management & hand-over to Ops | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A4370 | Reinstall insulation (if any) | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A4360 | Deblinding, remove temporary support / scaffolds | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A4350 | Touch-up painting works | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A4340 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A4330 | Hydrotest witness inspection (if required) | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A4320 | Prepare and hydrotest up to XX BarG (if required) | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A4310 | Install pipe supports (if any) | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A4300 | Inspection NDT / RT of selected joints | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A4290 | Full welding of joints (Tee-piece) & installation of Tie-In spool 140218 | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A4280 | Grinding, bevelling of old piping & fit-up with new spool | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A4270 | Cut old piping (existing line 140025) & support, haul to ground level | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A4260 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A4250 | Removal of insulation and wall thickness measurement | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A4240 | Obtain Work Permit | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A4230 | Start of Work | 1 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
LP- Condensate from 52-HE-1402 to 54-VV-1402 Tag # IP-B-M3-B3-L-3240 |  | 87 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A4220 | End of Work | 1 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A4210 | Torquing / flange management & hand-over to Ops | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A4200 | Reinstall insulation (if any) | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A4190 | Deblinding, remove temporary support / scaffolds | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A4110 | Connection of tie in spool | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A4100 | Check of cleanliness of vessel and new pipe | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A4090 | Removal of blind flange 54-VV-1402, N02 & Gas measurement | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A4080 | Removal of insulation | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A4070 | Obtain Work Permit | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A4060 | Start of Work | 1 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
Tailgas to 50-VV-1401 Tag # IP-B-M3-B3-L-3250 |  | 88 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A38000 | End of Work | 1 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A4040 | Torquing / flange management & hand-over to Ops | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A4030 | Reinstall insulation (if any) | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A4020 | Deblinding, remove temporary support / scaffolds | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A4010 | Touch-up painting works | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A4000 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A3990 | Hydrotest witness inspection (if required) | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A3980 | Prepare and hydrotest up to XX BarG (if required) | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A3970 | Install pipe supports (if any) | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A3960 | Inspection NDT / RT of selected joints | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A3950 | Full welding of joints & installation of Tie-In spool 45024 | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A3940 | Grinding, bevelling of old piping & fit-up with new spool | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A3930 | Cut old piping (existing line 45024), haul to ground level | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A3920 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A3910 | Removal of insulation and wall thickness measurement | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A3900 | Obtain Work Permit | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A3890 | Start of Work | 1 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
Regeneration Gas C4 Hydrogenation to 50-HE-1402 Tag # IP-B-M3-B3-L-3280 |  | 89 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A3880 | End of Work | 1 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A3870 | Torquing / flange management & hand-over to Ops | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A3860 | Reinstall insulation (if any) | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A3850 | Deblinding, remove temporary support / scaffolds | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A3840 | Touch-up painting works | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A3830 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A3820 | Hydrotest witness inspection (if required) | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A3810 | Prepare and hydrotest up to XX BarG (if required) | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A3800 | Install pipe supports (if any) | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A3790 | Inspection NDT / RT of selected joints | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A3780 | Full welding of joints & installation of Tie-In spool 81142 | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A3770 | Grinding, bevelling of old piping & fit-up with new spool | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A3760 | Cut old piping (existing line 41022), haul to ground level | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A3750 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A3740 | Removal of insulation and wall thickness measurement | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A3730 | Obtain Work Permit | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A3720 | Start of Work | 1 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
Regeneration Gas C4 Hydrogenation Condensate Tag # IP-B-M3-B3-L-3290 |  | 88 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A3710 | End of Work | 1 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A3700 | Torquing / flange management & hand-over to Ops | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A3690 | Reinstall insulation (if any) | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A3680 | Deblinding, remove temporary support / scaffolds | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A3670 | Touch-up painting works | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A3660 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A3650 | Hydrotest witness inspection (if any) | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A3640 | Prepare and hydrotest up to XX BarG (if any) | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A3630 | Install pipe supports (if any) | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A3620 | Inspection NDT / RT of selected joints | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A3610 | Full welding of joints & installation of Tie-In spool 140066 | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A3600 | Grinding, bevelling of old piping & fit-up with new spool | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A37990 | Cut old piping (existing line 140028) , haul to ground level | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A37980 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A3570 | Wall thickness measurement | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A37970 | Obtain Work Permit | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A3550 | Start of Work | 1 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
Warm Gas Flare from 13-KX-402/50-HE-1402 to EU3 Tie In Point Tag # P-B-M3-B3-L-3300 |  | 88 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A3540 | End of Work | 1 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A37960 | Torquing / flange management & hand-over to Ops | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A37950 | Reinstall insulation (if any) | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A37940 | Deblinding, remove temporary support / scaffolds | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A37930 | Touch-up painting works | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A37920 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A37910 | Hydrotest witness inspection | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A37900 | Prepare and hydrotest up to XX BarG | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A37890 | Install pipe supports (if any) | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A37880 | Inspection NDT / RT of selected joints | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A37870 | Full welding of joints & installation of Tie-In spool 140301 | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A37860 | Grinding, bevelling of old piping & fit-up with new spool | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A37850 | Cut old piping (existing line 140301) , haul to ground level | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A37840 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A37830 | Wall thickness measurement | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A3390 | Obtain Work Permit | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A37820 | Start of Work | 1 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
Cold Gas from 13-PSV-4508 to EU3 Tie In Tag # P-B-M3-B3-L-3410 |  | 88 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A3370 | End of Work | 1 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A3360 | Torquing / flange management & hand-over to Ops | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A37810 | Reinstall insulation (if any) | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A3340 | Deblinding, remove temporary support / scaffolds | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A3330 | Touch-up painting works | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A3320 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A3310 | Hydrotest witness inspection (if required) | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A3300 | Prepare and hydrotest up to XX BarG (if required) | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A3290 | Install pipe supports (if any) | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A3280 | Inspection NDT / RT of selected joints | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A3270 | Purge with 24" balloons & welding of Tie-In spool 144564 | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A3260 | Grinding, bevelling of old piping & fit-up with new spool | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A37800 | Cut old piping (existing line 140321) & support, haul to ground level | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A3240 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A3230 | Wall thickness measurement | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A3220 | Obtain Work Permit | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A3210 | Start of Work | 1 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
Package 4 |  | 110 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
50AT-14101A sample tap vent return to process Tag # IP-B-M3-B3-L-3420 |  | 87 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A3200 | End of Work | 2 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A3170 | Deblinding, remove temporary support / scaffolds | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A3070 | Making tubing connection | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A3060 | Gas measurement | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A3050 | Obtain Work Permit | 0 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
A3040 | Start of Work | 2 | 10-Apr-25 A | 17-May-25 A | 46108 | 46108
Instrument Air from U&O3 Tie In point to EU3 H2 Tag # IP-B-U3-H3-L-1020 |  | 94 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A3030 | End of Work | 10 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A2880 | Obtain Work Permit | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A2870 | Start of Work | 10 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
Plant Air from U&O3 Tie In point to EU3 H2 Tag # IP-B-U3-H3-L-1030 |  | 94 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A2860 | End of Work | 10 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A2710 | Obtain Work Permit | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A2700 | Start of Work | 10 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
Nitrogen from U&O3 Tie In point to EU3 H2 Tag # IP-B-U3-H3-L-1040 |  | 94 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A2690 | End of Work | 10 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A2540 | Obtain Work Permit | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A2530 | Start of Work | 10 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
LP Steam from U&O3 Tie In point to EU3 H2 Tag # IP-B-U3-H3-L-1050 |  | 88 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A2520 | End of Work | 1 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A2510 | Torquing / flange management & hand-over to Ops | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A2500 | Reinstall insulation (if any) | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A2490 | Deblinding, remove temporary support / scaffolds | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A2480 | Touch-up painting works | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A2470 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A2460 | Hydrotest witness inspection | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A2450 | Prepare and hydrotest up to XX BarG | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A2440 | Install pipe supports (if any) | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A2430 | Inspection NDT / RT of selected joints | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A2420 | Full welding of joints & Installation of Tie-In spool '0005 | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A2410 | Grinding, bevelling of old piping & fit-up with new spool | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A2400 | Cut old piping (existing line 00271) & support, haul to ground level | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A2390 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A2380 | Wall thickness measurement | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A2370 | Obtain Work Permit | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A2360 | Start of Work | 1 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
Service water from U&O3 Tie In point to to EU3 H2 Tag # IP-B-U3-H3-L-1060 |  | 88 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A2350 | End of Work | 1 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A2340 | Torquing / flange management & hand-over to Ops | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A2330 | Reinstall insulation (if any) | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A2320 | Deblinding, remove temporary support / scaffolds | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A2310 | Touch-up painting works | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A2300 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A2290 | Hydrotest witness inspection | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A2280 | Prepare and hydrotest up to XX BarG | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A2270 | Install pipe supports (if any) | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A2260 | Inspection NDT / RT of selected joints | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A2250 | Full welding of joints | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A2240 | Grinding, bevelling of old piping & fit-up with new spool | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A2230 | Cut old piping (existing line '00061) & support, haul to ground level | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A2220 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A2210 | Removal of insulation and wall thickness measurement | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A2200 | Obtain Work Permit | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A2190 | Start of Work | 1 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
Potable water from U&O3 Tie In point to EU3 H2 Tag # IP-B-U3-H3-L-1070 |  | 88 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A2180 | End of Work | 1 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A2170 | Torquing / flange management & hand-over to Ops | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A2160 | Reinstall insulation (if any) | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A2150 | Deblinding, remove temporary support / scaffolds | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A2140 | Touch-up painting works | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A2130 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A2120 | Hydrotest witness inspection | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A2110 | Prepare and hydrotest up to XX BarG | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A2100 | Install pipe supports (if any) | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A2090 | Inspection NDT / RT of selected joints | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A2080 | Full welding of joints | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A2070 | Grinding, bevelling of old piping & fit-up with new spool | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A2060 | Cut old piping & support, haul to ground level | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A2050 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A2040 | Wall thickness measurement | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A2030 | Obtain Work Permit | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A2020 | Start of Work | 1 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
Cooling Water Supply from U&O3 Tie In Point to EU3 H2 Tag # P-B-U3-H3-L-1090 |  | 88 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A37650 | End of Work | 1 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A1490 | Torquing / flange management & hand-over to Ops | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A1480 | Reinstall insulation (if any) | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A1470 | Deblinding, remove temporary support / scaffolds | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A1460 | Touch-up painting works (if any) | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A1450 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A1440 | Hydrotest witness inspection (if required) | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A1430 | Prepare and hydrotest up to XX BarG (if required) | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A1420 | Install pipe supports (if any) | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A1410 | Inspection NDT / RT of selected joints | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A1400 | Welding of weldolet | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A1390 | Grinding, bevelling of old piping & fit-up with new spool | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A1380 | Cut old piping (existing line '00234) & support, haul to ground level | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A1370 | Pull-out piping components (Valves, TW/TE, TG, PT, PG if any) | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A1360 | Removal of insulation (if any) & measurement of wall thickness | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A1350 | Obtain Work Permit | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A1340 | Start of Work | 1 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
Oily water from EU3 H2 to U&O3 Tie In point Tag # IP-B-U3-H3-L-1121 |  | 88 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A1330 | End of Work | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A1320 | Torquing / flange management & hand-over to Ops | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A1310 | Reinstall insulation (if any) | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A1300 | Deblinding, remove temporary support / scaffolds | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A1290 | Touch-up painting works | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A1280 | Reinstall back piping components (TW/TE, TG, PT, PG if any) | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A37640 | Hydrotest witness inspection (if required) | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A37630 | Prepare and hydrotest up to XX BarG (if required) | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A37620 | Install pipe supports (if any) | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A37610 | Inspection NDT / RT of selected joints | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A1230 | Full welding of joints | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A1220 | Grinding, bevelling of old piping & fit-up with new spool | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A1210 | Cut old piping (existing line '00018), haul to ground level | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A37600 | Drilling one hole (cold drilling, air-driven) & Gas measurement | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A37590 | Removal of insulation & measurement of wall thickness | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A37580 | Obtain Work Permit | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A37570 | Start of Work | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
TA Tie-In Execution - U/G Tie-Ins |  | 94 | 03-Apr-25 A | 17-May-25 A | 46108 | 46108
Package 4 |  | 94 | 03-Apr-25 A | 17-May-25 A | 46108 | 46108
Fire Water from U&O3 Tie point to EU3 H2 (South west) Tag # IP-B-U3-H3-L-1080 |  | 86 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A2010 | End of Work | 1 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A2000 | Torquing / flange management & hand-over to Ops | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A1990 | Reinstall insulation (if any) | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A1980 | Deblinding, remove temporary support / scaffolds | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A1880 | Install isolation balloon | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A1870 | Install temporary support / scaffolds as site | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A1860 | Obtain Work Permit | 0 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
A1850 | Start of Work | 1 | 08-Apr-25 A | 17-May-25 A | 46108 | 46108
Fire Water from U&O3 Tie point to EU3 H2 (south east) Tag # IP-B-U3-H3-L-1082 |  | 90 | 03-Apr-25 A | 17-May-25 A | 46108 | 46108
A1840 | End of Work | 2 | 03-Apr-25 A | 17-May-25 A | 46108 | 46108
A1830 | Torquing / flange management & hand-over to Ops | 0 | 03-Apr-25 A | 17-May-25 A | 46108 | 46108
A1820 | Reinstall insulation (if any) | 0 | 03-Apr-25 A | 17-May-25 A | 46108 | 46108
A1810 | Deblinding, remove temporary support / scaffolds | 0 | 03-Apr-25 A | 17-May-25 A | 46108 | 46108
A1800 | Touch-up painting works | 0 | 03-Apr-25 A | 17-May-25 A | 46108 | 46108
A1790 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 0 | 03-Apr-25 A | 17-May-25 A | 46108 | 46108
A1780 | Hydrotest witness inspection | 0 | 03-Apr-25 A | 17-May-25 A | 46108 | 46108
A1770 | Prepare and hydrotest up to XX BarG | 0 | 03-Apr-25 A | 17-May-25 A | 46108 | 46108
A1760 | Install pipe supports (if any) | 0 | 03-Apr-25 A | 17-May-25 A | 46108 | 46108
A1750 | Inspection NDT / RT of selected joints | 0 | 03-Apr-25 A | 17-May-25 A | 46108 | 46108
A1740 | Full welding of joints | 0 | 03-Apr-25 A | 17-May-25 A | 46108 | 46108
A1730 | Grinding, bevelling of old piping & fit-up with new spool | 0 | 03-Apr-25 A | 17-May-25 A | 46108 | 46108
A1720 | Cut old piping & support, haul to ground level | 0 | 03-Apr-25 A | 17-May-25 A | 46108 | 46108
A1710 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 0 | 03-Apr-25 A | 17-May-25 A | 46108 | 46108
A1700 | Removal of insulation & wall thickness measurement | 0 | 03-Apr-25 A | 17-May-25 A | 46108 | 46108
A1690 | Obtain Work Permit | 0 | 03-Apr-25 A | 17-May-25 A | 46108 | 46108
A1680 | Start of Work | 2 | 03-Apr-25 A | 17-May-25 A | 46108 | 46108
Fire Water from U&O3 Tie point to EU3 H2 (North east) Tag # IP-B-U3-H3-L-1086 |  | 90 | 03-Apr-25 A | 17-May-25 A | 46108 | 46108
A1670 | End of Work | 2 | 03-Apr-25 A | 17-May-25 A | 46108 | 46108
A37790 | Torquing / flange management & hand-over to Ops | 0 | 03-Apr-25 A | 17-May-25 A | 46108 | 46108
A37780 | Reinstall insulation (if any) | 0 | 03-Apr-25 A | 17-May-25 A | 46108 | 46108
A37770 | Deblinding, remove temporary support / scaffolds | 0 | 03-Apr-25 A | 17-May-25 A | 46108 | 46108
A37760 | Touch-up painting works | 0 | 03-Apr-25 A | 17-May-25 A | 46108 | 46108
A37750 | Reinstall back piping components (TW/TE, TG, PT, PG if any) | 0 | 03-Apr-25 A | 17-May-25 A | 46108 | 46108
A37740 | Hydrotest witness inspection (if any) | 0 | 03-Apr-25 A | 17-May-25 A | 46108 | 46108
A37730 | Prepare and hydrotest up to XX BarG (if any) | 0 | 03-Apr-25 A | 17-May-25 A | 46108 | 46108
A37720 | Install pipe supports (if any) | 0 | 03-Apr-25 A | 17-May-25 A | 46108 | 46108
A37710 | Inspection (all required HDPE welding examinations) of selected joints | 0 | 03-Apr-25 A | 17-May-25 A | 46108 | 46108
A37700 | Installation, alignment and welding of HDPE Tee to existing header 18011 & install. of tie-in spools 18481 & welding | 0 | 03-Apr-25 A | 17-May-25 A | 46108 | 46108
A37690 | Grinding, bevelling of old piping & fit-up with new spool (new HDPE TEE) | 0 | 03-Apr-25 A | 17-May-25 A | 46108 | 46108
A37680 | Cut old piping (20" HDPE Line), haul to ground level | 0 | 03-Apr-25 A | 17-May-25 A | 46108 | 46108
A37670 | Pull-out piping components (Valves, TW/TE, TG, PT, PG if any) | 0 | 03-Apr-25 A | 17-May-25 A | 46108 | 46108
A1530 | Install temporary support / scaffolds as site | 0 | 03-Apr-25 A | 17-May-25 A | 46108 | 46108
A1520 | Obtain Work Permit | 0 | 03-Apr-25 A | 17-May-25 A | 46108 | 46108
A37660 | Start of Work | 2 | 03-Apr-25 A | 17-May-25 A | 46108 | 46108
GF Piping Works |  | 254 | 2026-03-28 | 2027-01-17 | 2026-04-20 | 2027-03-11 | 46
AG |  | 254 | 2026-03-28 | 2027-01-17 | 2026-04-20 | 2027-03-11 | 46
A3410 | Piping Insulation | 86 | 2026-10-10 | 2027-01-17 | 2026-04-20 | 2026-10-11 | 46
A3420 | Final Touch up and painting of joints | 50 | 2026-10-01 | 2026-11-28 | 2026-05-07 | 2026-10-28 | 46
A3430 | Hydro testing and reinstatment | 50 | 2026-09-20 | 2026-11-16 | 2026-05-25 | 2026-11-15 | 46
A3380 | Piping Eection at Site | 150 | 2026-05-02 | 2026-10-22 | 2026-11-12 | 2027-01-09 | 20
A3400 | Painting Piping - Fabrication Shop | 150 | 2026-04-14 | 2026-10-05 | 2026-11-24 | 2027-01-20 | 20
A60800 | Piping - Pre-Fabrication Shop | 150 | 2026-03-28 | 2026-09-17 | 2026-12-02 | 2027-03-11 | 20
UG |  | 156 | 2026-06-06 | 2026-12-03 | 2026-08-16 | 2027-01-20 | 41
A23540 | Piping Erection of Fire water piping (HDPE) UG including hydrotesting | 120 | 2026-07-16 | 2026-12-03 | 2026-12-28 | 2027-01-20 | 41
A3470 | U/G Piping Erection & Hydrotesting Cooling Water Lines (CS) | 100 | 2026-06-06 | 2026-09-29 | 2026-08-16 | 2026-12-09 | 61
A3480 | U/G Piping Erection Oily Water (CS) | 21 | 2026-08-16 | 2026-09-08 | 2026-09-03 | 2027-01-20 | 115
Insulation |  | 90 | 2026-06-23 | 2026-10-05 | 2026-10-08 | 2027-01-20 | 92
A3580 | Complete Insulation, Fire-Proofing and Painting works | 90 | 2026-06-23 | 2026-10-05 | 2026-10-08 | 2027-01-20 | 92
Painting |  | 96 | 2026-08-09 | 2026-11-28 | 2027-03-27 | 2027-07-15 | 197
A61630 | Painting | 96 | 2026-08-09 | 2026-11-28 | 2027-03-27 | 2027-07-15 | 197
Others |  | 4 | 2026-11-29 | 2026-12-02 | 2027-07-17 | 2027-07-20 | 197
A61640 | Painting punch clearing | 4 | 2026-11-29 | 2026-12-02 | 2027-07-17 | 2027-07-20 | 197
Electrical Construction |  | 480 | 01-Mar-25 A | 2026-12-28 | 2026-03-27 | 2027-01-20 | 17
Equipment Installation |  | 431 | 03-Apr-25 A | 2026-12-28 | 2026-03-27 | 2027-01-20 | 17
System and Panels Installation |  | 48 | 2026-04-16 | 2026-06-10 | 2026-11-26 | 2027-01-20 | 192
A61650 | System and Panels Installations | 48 | 2026-04-16 | 2026-06-10 | 2026-11-26 | 2027-01-20 | 192
GF Interposing Relay Panel |  | 51 | 2026-09-19 | 2026-11-16 | 2026-11-23 | 2027-01-20 | 56
A24790 | IRP - Pre Comm | 18 | 2026-10-27 | 2026-11-16 | 2026-11-23 | 2026-12-06 | 56
A24580 | Cable terminations and loop testing - IRP | 21 | 2026-10-03 | 2026-10-26 | 2026-12-07 | 2026-12-30 | 56
A24070 | Installation of Interposting Relay Panel | 12 | 2026-09-19 | 2026-10-01 | 2026-12-31 | 2027-01-20 | 56
GF DG Set |  | 67 | 2026-08-08 | 2026-10-24 | 2026-11-04 | 2027-01-20 | 76
A24800 | DG Set - Pre Comm | 18 | 2026-10-04 | 2026-10-24 | 2026-11-04 | 2026-12-05 | 76
A24590 | Cable terminations and loop testing - DG Set | 22 | 2026-09-08 | 2026-10-03 | 2026-12-06 | 2026-12-30 | 76
A3829 | Installation of DG Set | 27 | 2026-08-08 | 2026-09-07 | 2026-12-31 | 2027-01-20 | 76
GF Electrical Heat Tracing (53 Meter for piping + 340 Meter for instrumentation) |  | 62 | 2026-08-31 | 2026-11-11 | 2026-11-10 | 2027-01-20 | 61
A24660 | Electric Heat Tracing - Pre Comm | 18 | 2026-10-21 | 2026-11-11 | 2026-11-10 | 2026-12-02 | 61
A24410 | Cable terminations and loop testing - Electric Heat Tracing | 24 | 2026-09-23 | 2026-10-21 | 2026-12-03 | 2026-12-30 | 61
A24090 | Electrical Heat Tracing works | 20 | 2026-08-31 | 2026-09-23 | 2026-12-31 | 2027-01-20 | 61
GF Power Transformers (Qty 05) |  | 77 | 2026-08-15 | 2026-11-11 | 2026-10-24 | 2027-01-20 | 60
A24680 | Power Transformers - Pre Comm | 18 | 2026-10-22 | 2026-11-11 | 2026-10-24 | 2026-12-02 | 60
A24470 | Cable terminations and loop testing - Power Transformers | 24 | 2026-09-24 | 2026-10-21 | 2026-12-03 | 2026-12-30 | 60
A24120 | Installation of Power Transformers | 35 | 2026-08-15 | 2026-09-23 | 2026-12-31 | 2027-01-20 | 60
GF HV Capacitor Bay |  | 56 | 2026-08-04 | 2026-10-07 | 2026-11-17 | 2027-01-20 | 90
A24700 | HV Capacitor Bay - Pre Comm | 17 | 2026-09-19 | 2026-10-07 | 2026-11-17 | 2026-12-07 | 90
A24490 | Cable terminations and HV Capacitor Bay | 21 | 2026-08-25 | 2026-09-17 | 2026-12-08 | 2026-12-31 | 90
A24080 | Installation of Capacitor Bay | 18 | 2026-08-04 | 2026-08-24 | 2027-01-02 | 2027-01-20 | 90
GF Switchgear (LV, MV) |  | 81 | 2026-08-22 | 2026-11-23 | 2026-10-19 | 2027-01-20 | 50
A24740 | Switchgear (LV, MV) - Pre Comm | 21 | 2026-10-31 | 2026-11-23 | 2026-10-19 | 2026-11-22 | 50
A24530 | Cable terminations and loop testing - Switchgear (LV, MV) | 30 | 2026-09-26 | 2026-10-29 | 2026-11-23 | 2026-12-27 | 50
A3839 | Installation of Switchgear | 30 | 2026-08-22 | 2026-09-24 | 2026-12-28 | 2027-01-20 | 50
GF Variable Fequency Drives (VFDs) LV Qty = 03 |  | 80 | 2026-08-04 | 2026-11-04 | 2026-10-20 | 2027-01-20 | 66
A24750 | VFDs - Pre Comm | 24 | 2026-10-08 | 2026-11-04 | 2026-10-20 | 2026-11-16 | 66
A24540 | Cable terminations and loop testing - VFD | 32 | 2026-09-01 | 2026-10-07 | 2026-11-17 | 2026-12-23 | 66
A24140 | Installation of VFD | 24 | 2026-08-04 | 2026-08-31 | 2026-12-24 | 2027-01-20 | 66
GF NGR Panel Qty 02 |  | 50 | 2026-08-04 | 2026-09-30 | 2026-11-24 | 2027-01-20 | 96
A24780 | NGR Panel - Pre Comm | 17 | 2026-09-12 | 2026-09-30 | 2026-11-24 | 2026-12-07 | 96
A24570 | Cable terminations and loop testing NGR Panel | 21 | 2026-08-18 | 2026-09-10 | 2026-12-08 | 2026-12-31 | 96
A3869 | Installation of NGR Panel | 12 | 2026-08-04 | 2026-08-17 | 2027-01-02 | 2027-01-20 | 96
GF Cathodic Protection (CP) Total CS Piping Length - 499 Meters |  | 74 | 2026-10-04 | 2026-12-28 | 2026-10-27 | 2027-01-20 | 20
A24670 | Cathodic Protection - Pre Comm | 18 | 2026-12-08 | 2026-12-28 | 2026-10-27 | 2026-12-02 | 20
A24420 | Cable terminations and loop testing - Cathodic Protection | 24 | 2026-11-10 | 2026-12-07 | 2026-12-03 | 2026-12-30 | 20
A24100 | Cathodic Protection for complete CS Piping | 32 | 2026-10-04 | 2026-11-09 | 2026-12-31 | 2027-01-20 | 20
GF UPS (AC - 60 KVA, 20 KVA, DC-UPS 6.5 KVA) Qty 1+1+1 = 03 Nos |  | 62 | 2026-08-15 | 2026-10-25 | 2026-11-10 | 2027-01-20 | 75
A24640 | UPS - Pre Comm | 18 | 2026-10-05 | 2026-10-25 | 2026-11-10 | 2026-12-07 | 75
A24450 | Cable terminations and loop testing - UPS | 20 | 2026-09-12 | 2026-10-04 | 2026-12-08 | 2026-12-30 | 75
A24060 | Installation of UPS | 24 | 2026-08-15 | 2026-09-10 | 2026-12-31 | 2027-01-20 | 75
TA IPCS Modification by ABB |  | 5 | 03-Apr-25 A | 10-May-25 A | 46108 | 46108
A34830 | Installation of FOPP (02 )in existing CCB | 5 | 03-Apr-25 A | 10-May-25 A | 46108 | 46108
TA Switchgear Modification by SIEMENS |  | 11 | 03-Apr-25 A | 10-May-25 A | 46108 | 46108
A17980 | Bus-bar differential testing Bus-B - feeder H16 (TA) | 3 | 03-Apr-25 A | 10-May-25 A | 46108 | 46108
A17970 | Bus-bar differential testing Bus-A - feeder H01 (TA) | 5 | 03-Apr-25 A | 10-May-25 A | 46108 | 46108
A34820 | Installation of Castle key interlock and key exchange box | 5 | 03-Apr-25 A | 10-May-25 A | 46108 | 46108
A34810 | Installation of Dummy Plugs | 5 | 03-Apr-25 A | 10-May-25 A | 46108 | 46108
A34800 | Installation of Surge Arersstor | 5 | 03-Apr-25 A | 10-May-25 A | 46108 | 46108
A34440 | Switchgear Modifications - Siemens | 5 | 03-Apr-25 A | 10-May-25 A | 46108 | 46108
TA SCMS Modification by SIEMENS |  | 10 | 14-Apr-25 A | 14-May-25 A | 46108 | 46108
A34850 | HMI Graphics Update | 3 | 10-May-25 A | 14-May-25 A | 46108 | 46108
A34780 | Mapping of SCMS in IPCS | 3 | 26-Apr-25 A | 30-Apr-25 A | 46108 | 46108
A34840 | Annuciator Panel Modification | 5 | 01-May-25 A | 09-May-25 A | 46108 | 46108
A17990 | SCMS FOPP Modifications - Siemens (By Client) | 5 | 14-Apr-25 A | 25-Apr-25 A | 46108 | 46108
TA UPS Modification |  | 5 | 15-Apr-25 A | 13-May-25 A | 46108 | 46108
A17960 | Modification in DC power supply arrangmeent- UPS | 5 | 15-Apr-25 A | 13-May-25 A | 46108 | 46108
Cabling Work |  | 92 | 2026-07-29 | 2026-11-12 | 2026-10-06 | 2027-01-20 | 59
BF Electrical Works |  | 92 | 2026-07-29 | 2026-11-12 | 2026-10-06 | 2027-01-20 | 59
BFW4080 | Other Electrical Works | 20 | 2026-10-21 | 2026-11-12 | 2026-10-06 | 2026-11-16 | 59
A21980 | FO Cable termination for IPCSS and SCMS | 26 | 2026-09-21 | 2026-10-20 | 2026-10-14 | 2026-11-25 | 59
A18740 | Termination of Power cables and Loop Testing | 26 | 2026-09-09 | 2026-10-08 | 2026-11-17 | 2026-12-16 | 59
A18750 | FO Cable laying for IPCSS and SCMS | 36 | 2026-07-29 | 2026-09-08 | 2026-11-29 | 2026-12-28 | 67
A17740 | Power Cables Laying | 36 | 2026-07-29 | 2026-09-08 | 2026-12-29 | 2027-01-20 | 59
Earthing System Installation |  | 72 | 2026-07-28 | 2026-10-19 | 2026-10-29 | 2027-01-20 | 80
A61670 | Earthing System Testing | 12 | 2026-10-06 | 2026-10-19 | 2026-10-29 | 2027-01-06 | 80
A61660 | Earthing System Installation | 60 | 2026-07-28 | 2026-10-05 | 2027-01-07 | 2027-01-20 | 80
Lightning System Installation |  | 15 | 2026-09-15 | 2026-10-03 | 2027-01-04 | 2027-01-20 | 94
GF Lighting Fixtures (Almost 50% Exd = 354 Nos) |  | 15 | 2026-09-15 | 2026-10-03 | 2027-01-04 | 2027-01-20 | 94
A3590 | Complete Street lighting | 15 | 2026-09-15 | 2026-10-03 | 2027-01-04 | 2027-01-20 | 94
Others |  | 16 | 01-Mar-25 A | 15-Mar-25 A | 46108 | 46108
TA Site Survey AC & DC UPS(Chloride Terchnology) |  | 10 | 01-Mar-25 A | 15-Mar-25 A | 46108 | 46108
A37540 | Site Survey Report for UPS Modification | 4 | 08-Mar-25 A | 15-Mar-25 A | 46108 | 46108
A35010 | Site Survey for UPS Modification | 4 | 01-Mar-25 A | 07-Mar-25 A | 46108 | 46108
TA Site Survey MCMS System (Bently Nevada) |  | 10 | 01-Mar-25 A | 15-Mar-25 A | 46108 | 46108
A37550 | Site Survey Report for MCMS Modification | 4 | 08-Mar-25 A | 15-Mar-25 A | 46108 | 46108
A35020 | Site Survey for MCMS Modification | 4 | 01-Mar-25 A | 07-Mar-25 A | 46108 | 46108
For Switchgear & SCMS(Siemens) |  | 10 | 01-Mar-25 A | 15-Mar-25 A | 46108 | 46108
A35140 | Health Check / Site Survey Report | 4 | 08-Mar-25 A | 15-Mar-25 A | 46108 | 46108
A34980 | Site Survey for SG & SCMS Modification | 4 | 01-Mar-25 A | 07-Mar-25 A | 46108 | 46108
Instrumentation/Telecom Construction |  | 497 | 11-Feb-25 A | 2026-12-28 | 2026-03-27 | 2027-01-20 | 17
MCMS/DCS/ESD/F&G Modification / Installation (as applicable) |  | 345 | 01-May-25 A | 2026-11-23 | 2026-03-27 | 2027-01-20 | 39
GF Fire Fighting Equipment |  | 71 | 2026-08-04 | 2026-10-25 | 2026-10-31 | 2027-01-20 | 75
A24610 | Fire Fighting Equip - Pre Comm | 18 | 2026-10-05 | 2026-10-25 | 2026-10-31 | 2026-12-10 | 75
A24400 | Cable terminations and loop testing - Fire Fighting Equipment | 17 | 2026-09-15 | 2026-10-04 | 2026-12-12 | 2026-12-30 | 75
A3849 | Installation of Fire Fighting Equipment | 36 | 2026-08-04 | 2026-09-14 | 2026-12-31 | 2027-01-20 | 75
BF DCS/ESD Modification by Honeywell |  | 35 | 2026-05-23 | 2026-07-02 | 2026-10-21 | 2026-11-30 | 130
A17750 | DCS modification for integration between brownfield and greenfield | 35 | 2026-05-23 | 2026-07-02 | 2026-10-21 | 2026-11-30 | 130
GF Fire Detection Alarm System, Local Fire Control Panel & Clean Agent Unit |  | 90 | 2026-08-04 | 2026-11-16 | 2026-10-08 | 2027-01-20 | 56
A24650 | FDAS, LFCP & CAU - Pre Comm | 24 | 2026-10-20 | 2026-11-16 | 2026-10-08 | 2026-11-18 | 56
A24460 | Cable terminations and loop testing - FDAS, LFCP and Clean Agent Unit | 30 | 2026-09-15 | 2026-10-19 | 2026-11-19 | 2026-12-23 | 56
A24110 | Installation of Fire Detection Alarm System, LFCP and Clean Agent Unit | 36 | 2026-08-04 | 2026-09-14 | 2026-12-24 | 2027-01-20 | 56
TA EU3 ICSS(DCS/ESD/GDS) Modifications by HONEYWELL |  | 24 | 01-May-25 A | 15-May-25 A | 46108 | 46108
A34970 | Change in the Existing ESD configuration for BF added/ Modified Field Tag(Instrument TieIn-14.1) | 3 | 01-May-25 A | 15-May-25 A | 46108 | 46108
A34960 | Change in the Existing DCS configuration for BF added/ Modified Field Tag (Instrument TieIn-14) | 3 | 01-May-25 A | 15-May-25 A | 46108 | 46108
A34950 | OEM) Vendor loose supplied material installation Including Honeywell, Safetec (Instrument Tie-12) | 8 | 01-May-25 A | 15-May-25 A | 46108 | 46108
A34940 | COLD Section ESD shutdown console switches (Intrument Tie-In- 11) | 8 | 01-May-25 A | 15-May-25 A | 46108 | 46108
A34930 | (OEM) Vendor (Honeywell) loose supplied (Intrument Tie-In- 9.1) | 8 | 01-May-25 A | 15-May-25 A | 46108 | 46108
A34910 | Installation of New Non-IS ESD Cabinet (83-JM3021-D) (Intrument Tie-In-8) | 8 | 01-May-25 A | 15-May-25 A | 46108 | 46108
A34920 | Non-UPS Power &earthing for New Non-IS ESD Cabinet (Intrument Tie-In- 9) | 5 | 01-May-25 A | 15-May-25 A | 46108 | 46108
A21970 | Cross wiring between existing marshalling racks ( Instrument Tie-in No 6,7) | 3 | 01-May-25 A | 15-May-25 A | 46108 | 46108
GF F&G Flame Detectors, MCP, Beacon (Nos 324) |  | 70 | 2026-09-02 | 2026-11-23 | 2026-11-01 | 2027-01-20 | 50
A24710 | F&G, MCP, Beacon - Pre Comm | 18 | 2026-11-02 | 2026-11-23 | 2026-11-01 | 2026-12-03 | 50
A24500 | Cable terminations and loop testing - F&G Detectors, MCP, Beacon | 23 | 2026-10-06 | 2026-11-02 | 2026-12-05 | 2026-12-30 | 50
A24130 | Installation of F&G Detectors, MCP,Beacon | 29 | 2026-09-02 | 2026-10-06 | 2026-12-31 | 2027-01-20 | 50
TA Fire Alarm System Modification by SAFCO+HONEYWELL |  | 11 | 15-May-25 A | 25-May-25 A | 46108 | 46108
A34740 | Existing Deluge Console switches shall be relocated including retesting of existing loops on new dual tier Console | 11 | 15-May-25 A | 25-May-25 A | 46108 | 46108
TA Modification in MCMS System by BENTLY NAVEDA |  | 13 | 01-May-25 A | 15-May-25 A | 46357 | 46357
A34710 | Existing MCMS system 1 will be upgraded with new EVO series servers for EU3 existing network | 13 | 01-May-25 A | 15-May-25 A | 46357 | 46357
Field Instrument Installation |  | 422 | 01-May-25 A | 2026-12-28 | 2026-03-27 | 2027-01-20 | 17
GF Machine Condition Monitoring System |  | 74 | 2026-08-04 | 2026-10-28 | 2026-10-27 | 2027-01-20 | 72
A24690 | MCMS - Pre Comm | 17 | 2026-10-10 | 2026-10-28 | 2026-10-27 | 2026-12-07 | 72
A24480 | Cable terminations and loop testing - MCMS | 21 | 2026-09-15 | 2026-10-08 | 2026-12-08 | 2026-12-31 | 72
A3789 | Installation of MCMS | 36 | 2026-08-04 | 2026-09-14 | 2027-01-02 | 2027-01-20 | 72
TA Replacement of Existing Air Distribution Pot |  | 7 | 01-May-25 A | 15-May-25 A | 46108 | 46108
A34880 | Replacoment of existing ADP (E3-SP-0149) from 6-ways to 10-ways (Intrument Tie-In- 2) | 1 | 01-May-25 A | 15-May-25 A | 46108 | 46108
A34870 | Replacoment of existing ADP (E3-SP-0322) from 6-ways to 10-ways (Intrument Tie-In- 1) | 1 | 01-May-25 A | 15-May-25 A | 46108 | 46108
A34860 | Replacoment of existing ADP (E3-SP-0146) from 6-ways to 10-ways (Intrument Tie-In- 1.1) | 1 | 01-May-25 A | 15-May-25 A | 46108 | 46108
GF Acess Control System |  | 74 | 2026-09-09 | 2026-12-05 | 2026-10-27 | 2027-01-20 | 40
A24620 | ACS - Pre Comm | 18 | 2026-11-14 | 2026-12-05 | 2026-10-27 | 2026-11-23 | 40
A24430 | Cable terminations and loop testing - ACS | 32 | 2026-10-07 | 2026-11-14 | 2026-11-24 | 2026-12-30 | 40
A3859 | Installation of Access Control System | 24 | 2026-09-09 | 2026-10-07 | 2026-12-31 | 2027-01-20 | 40
GF VESDA (Very Early Smoke Detection Apparatus) |  | 68 | 2026-08-04 | 2026-10-21 | 2026-11-03 | 2027-01-20 | 78
A24720 | VESDA - Pre Comm | 18 | 2026-10-01 | 2026-10-21 | 2026-11-03 | 2026-12-03 | 78
A24510 | Cable terminations and loop testing VESDA | 23 | 2026-09-05 | 2026-09-30 | 2026-12-05 | 2026-12-30 | 78
A3799 | Installation of VESDA | 27 | 2026-08-04 | 2026-09-03 | 2026-12-31 | 2027-01-20 | 78
GF MOVs [Ball Type 24" 150# = 01 No] |  | 29 | 2026-09-26 | 2026-10-28 | 2026-12-15 | 2027-01-20 | 72
A24760 | MOVS - Pre Comm | 12 | 2026-10-14 | 2026-10-28 | 2026-12-15 | 2026-12-20 | 72
A24550 | Cable terminations and lop termination - MOVs | 12 | 2026-09-30 | 2026-10-14 | 2026-12-21 | 2027-01-03 | 69
A24160 | Installatrion of MOV | 5 | 2026-09-26 | 2026-09-30 | 2027-01-07 | 2027-01-20 | 69
TA Compresoor CGC Turbine by MHI |  | 8 | 01-Sep-25 A | 10-Sep-25 A | 46108 | 46108
A21840 | Turbine Governor Software modification by MHI (Intrument Tie-In- 15) | 8 | 01-Sep-25 A | 10-Sep-25 A | 46108 | 46108
TA SGM Replacement (EMERSON) |  | 7 | 01-May-25 A | 15-May-25 A | 46357 | 46357
A34720 | Existing Gas density Meter to replaced by SGM (EMERSON) (Intrument Tie-In- 3) | 2 | 01-May-25 A | 15-May-25 A | 46357 | 46357
A34890 | SGM meter connection to nearest Power Distruribution Board (Intrument Tie-In- 3.1) | 1 | 01-May-25 A | 15-May-25 A | 46357 | 46357
A34900 | New Tubing for Votex cooling of sgm Cabinet SGM (EMERSON) ((Intrument Tie-In- 2) | 2 | 01-May-25 A | 15-May-25 A | 46357 | 46357
GF Integrated Control and Safety System GF |  | 77 | 2026-09-29 | 2026-12-28 | 2026-10-24 | 2027-01-20 | 20
A3899 | ICSS - Pre Comm | 21 | 2026-12-03 | 2026-12-28 | 2026-10-24 | 2026-12-02 | 20
A3879 | Cable terminations and loop testing ICSS - GF | 21 | 2026-11-09 | 2026-12-03 | 2026-12-03 | 2026-12-27 | 20
A3729 | Installation of ICSS System | 35 | 2026-09-29 | 2026-11-09 | 2026-12-28 | 2027-01-20 | 20
GF Gauges (PG, TG, PDG, Analzer, FE) PG - 10bar & 40bar = 19 Nos, DP = 05 Nos, TG = 09 Nos |  | 66 | 2026-08-29 | 2026-11-12 | 2026-11-05 | 2027-01-20 | 59
A24770 | Guages (PG, TG, PDG) - Pre Comm (Calibration/Testing) | 18 | 2026-10-24 | 2026-11-12 | 2026-11-05 | 2026-12-02 | 59
A24560 | Cable terminations and loop testing - Gauges (PG, TG, PDG) | 24 | 2026-09-26 | 2026-10-22 | 2026-12-03 | 2026-12-30 | 59
A24150 | Installation of Field Instruments | 24 | 2026-08-29 | 2026-09-24 | 2026-12-31 | 2027-01-20 | 59
TA Field Instrument Modification |  | 10 | 01-May-25 A | 15-May-25 A | 46357 | 46357
A21860 | Replacement of 13-PV-4515 and stroke calibration, loop Testing (Intrument Tie-In- 4) | 10 | 01-May-25 A | 15-May-25 A | 46357 | 46357
A34700 | Flow Element to be re-calibrated ( approx qty- 19 nos.) in existing EU3 plant area | 3 | 01-May-25 A | 15-May-25 A | 46357 | 46357
A21850 | Dp Flow Transmitters to be re-calibrated ( approx qty- 20 nos.) in existing EU3 plant area | 3 | 01-May-25 A | 15-May-25 A | 46357 | 46357
GF Integrated Protection Control System |  | 84 | 2026-09-16 | 2026-12-23 | 2026-10-15 | 2027-01-20 | 24
A24600 | IPCS - Pre Comm | 24 | 2026-11-25 | 2026-12-23 | 2026-10-15 | 2026-11-18 | 24
A24390 | Cable terminations and loop testing - IPCS | 30 | 2026-10-21 | 2026-11-25 | 2026-11-19 | 2026-12-23 | 24
A3769 | Installation of IPCS | 30 | 2026-09-16 | 2026-10-21 | 2026-12-24 | 2027-01-20 | 24
TA Instrumentation Work |  | 25 | 01-May-25 A | 15-May-25 A | 46328 | 46357
A23560 | Heath Check for ICSS Report | 25 | 01-May-25 A | 15-May-25 A | 46357 | 46357
A18330 | Instrument Air Tubing from existing Spare ADP connections to new valves in Brown Field area- @ 7 nos. | 14 | 01-May-25 A | 15-May-25 A | 46328 | 46328
Cabling work |  | 204 | 2026-03-26 | 2026-11-18 | 2026-09-17 | 2027-01-20 | 54
GF Cable Tray and Instrument Junction Box (Perforated Cable tray Heavy duty= 5982 Mtrs, JBs= 73 Nos) |  | 96 | 2026-07-29 | 2026-11-18 | 2026-10-01 | 2027-01-20 | 54
A61680 | GF Cable Tray and Junction Box | 96 | 2026-07-29 | 2026-11-18 | 2026-10-01 | 2027-01-20 | 54
GF Fibre Optic Cable (Armoured, Telecom/IT/MAS) |  | 96 | 2026-03-26 | 2026-07-15 | 2026-09-17 | 2027-01-06 | 150
A61690 | GF Fiber Optic cable | 96 | 2026-03-26 | 2026-07-15 | 2026-09-17 | 2027-01-06 | 150
BF Instrumentation Works |  | 98 | 2026-05-23 | 2026-09-14 | 2026-09-28 | 2027-01-20 | 111
A18730 | Laying UTP/CAT5 cable from B3-CCB Network cabinet (82-JS- 4844) located Ethernet swtich to B3-CCB located SOE PC | 19 | 2026-07-29 | 2026-08-20 | 2026-11-12 | 2026-11-25 | 67
A21790 | Cable tray in EU3 SIS and H2 Extraction Plant SIS | 11 | 2026-05-23 | 2026-06-04 | 2026-10-14 | 2026-11-05 | 149
FO Cable Laying |  | 26 | 2026-05-23 | 2026-06-22 | 2026-10-14 | 2026-12-09 | 147
A21780 | Laying FO cables inside existing trenches/pipe/conduit between B3 CCB to new H2 Plant SIS | 18 | 2026-06-01 | 2026-06-22 | 2026-11-12 | 2026-12-09 | 116
A21880 | Laying PU ASC PLC (TRICONEX) FO cable between new SIS at H2 Green Field area and B3-CCB for TRICONEX PLC | 12 | 2026-06-06 | 2026-06-20 | 2026-10-19 | 2026-11-01 | 116
A17760 | Laying FO cables inside existing trenches/pipe/conduit between EU3 SIS &new H2 Plant SIS | 24 | 2026-05-23 | 2026-06-20 | 2026-10-14 | 2026-11-03 | 149
Hardwired Cable Laying |  | 35 | 2026-05-23 | 2026-07-02 | 2026-09-28 | 2027-01-20 | 174
A17770 | Trench & cable laying | 35 | 2026-05-23 | 2026-07-02 | 2026-09-28 | 2026-10-26 | 174
A18320 | Hardwired multicore/pair cable laying between EU3 SIS to H2 Extraction Plant SIS | 24 | 2026-05-23 | 2026-06-20 | 2026-12-12 | 2027-01-20 | 110
Termination |  | 98 | 2026-05-23 | 2026-09-14 | 2026-10-10 | 2026-11-30 | 67
A21820 | Termination & Testing of FO cables laid between B3-CCB to new H2 Plant SIS | 21 | 2026-08-20 | 2026-09-14 | 2026-10-10 | 2026-11-05 | 67
A21810 | Termination & Testing of various FO cables laid between EU3 SIS to new H2 Plant SIS | 21 | 2026-08-20 | 2026-09-14 | 2026-10-26 | 2026-11-15 | 67
A21890 | Termination at Green Field H2 SIS of' PU ASC PLC (TRICONEX) FO cable between new SIS at H2 Green Field area and B3-CCB | 25 | 2026-06-27 | 2026-07-26 | 2026-11-02 | 2026-11-30 | 110
A21830 | Termination of Hardwiring multicore/pair cable inside existing/new marshalling cabinets | 18 | 2026-06-20 | 2026-07-11 | 2026-11-07 | 2026-11-30 | 110
A17780 | FO Patch cord laying | 24 | 2026-05-23 | 2026-06-18 | 2026-11-07 | 2026-11-30 | 120
Telecommunication System Installation |  | 329 | 01-May-25 A | 2026-10-31 | 2026-03-27 | 2027-01-20 | 55
GF PAGA + Telephone |  | 51 | 2026-08-22 | 2026-10-19 | 2026-11-23 | 2027-01-20 | 80
A24630 | PAGA + Telephone - Pre Comm | 15 | 2026-10-03 | 2026-10-19 | 2026-11-23 | 2026-12-16 | 80
A24440 | Cable terminations and loop testing - PAGA + Telephone | 15 | 2026-09-15 | 2026-10-01 | 2026-12-17 | 2027-01-03 | 80
A3809 | Installation of PAGA+Telephone | 21 | 2026-08-22 | 2026-09-14 | 2027-01-04 | 2027-01-20 | 80
GF CCTV |  | 57 | 2026-08-25 | 2026-10-31 | 2026-11-16 | 2027-01-20 | 70
A24730 | CCTV - Pre Comm | 15 | 2026-10-13 | 2026-10-31 | 2026-11-16 | 2026-12-09 | 70
A24520 | Cable terminations and loop testing - CCTV | 21 | 2026-09-19 | 2026-10-13 | 2026-12-10 | 2027-01-03 | 70
A3819 | Installation of CCTV | 21 | 2026-08-25 | 2026-09-19 | 2027-01-04 | 2027-01-20 | 70
TA Telecom Related |  | 13 | 01-May-25 A | 15-May-25 A | 46108 | 46108
A37380 | Installation of SFP in existing distribution switch (Hemal / Rommel). | 13 | 01-May-25 A | 15-May-25 A | 46108 | 46108
A18010 | Installation of 08 Nos of Cards in existing system | 13 | 01-May-25 A | 15-May-25 A | 46108 | 46108
Testing |  | 36 | 2026-06-20 | 2026-08-01 | 2026-12-10 | 2027-01-20 | 149
A61700 | Fiber Optical Testing | 36 | 2026-06-20 | 2026-08-01 | 2026-12-10 | 2027-01-20 | 149
Others |  | 233 | 11-Feb-25 A | 26-Apr-25 A | 46108 | 46108
TA Site Survey For IPCS (ABB) |  | 10 | 20-Feb-25 A | 18-Mar-25 A | 46108 | 46108
A35150 | Health Check / Site Survey Report | 4 | 26-Feb-25 A | 18-Mar-25 A | 46108 | 46108
A34990 | Site Survey for IPCS Modification | 4 | 20-Feb-25 A | 25-Feb-25 A | 46108 | 46108
TA Site Survey For ICSS (Honeywell) |  | 10 | 20-Feb-25 A | 18-Mar-25 A | 46108 | 46108
A37510 | Health Check / Site Survey Report | 4 | 26-Feb-25 A | 18-Mar-25 A | 46108 | 46108
A35000 | Site Survey for ICSS Modification | 4 | 20-Feb-25 A | 25-Feb-25 A | 46108 | 46108
TA Site Survey For LAN System (CISCO) |  | 10 | 19-Apr-25 A | 26-Apr-25 A | 46108 | 46108
A37520 | Health Check / Site Survey Report | 4 | 23-Apr-25 A | 26-Apr-25 A | 46108 | 46108
A37370 | Site Survey for LAN System Modification | 4 | 19-Apr-25 A | 22-Apr-25 A | 46108 | 46108
TA Site Survey For CGC Turbine Software Upgarde |  | 10 | 11-Feb-25 A | 21-Feb-25 A | 46108 | 46108
A37530 | Site Survey Report for CGC Turbine Software Upgrade | 4 | 17-Feb-25 A | 21-Feb-25 A | 46108 | 46108
A37390 | Site Survey for CGC Turbine Software Upgrade | 4 | 11-Feb-25 A | 14-Feb-25 A | 46108 | 46108
TA Site Survey Fire Alarm System (SAFCO) |  | 10 | 19-Apr-25 A | 26-Apr-25 A | 46108 | 46108
A37560 | Site Survey Report for Fire Alaram System Modification | 4 | 23-Apr-25 A | 26-Apr-25 A | 46108 | 46108
A35030 | Site Survey for Fire Alaram System Modification | 4 | 19-Apr-25 A | 22-Apr-25 A | 46108 | 46108
Pre-commissioning |  | 150 | 2026-07-30 | 2027-01-20 | 2026-12-01 | 2027-01-20 | 0
GF Pre Commissioning FG/OG Compressor |  | 43 | 2026-12-02 | 2027-01-20 | 2026-12-02 | 2027-01-20 | 0
C1014 | Pre-commissioning punchlist clearing | 15 | 2027-01-04 | 2027-01-20 | 2026-12-02 | 2026-12-13 | 0
C1013 | Final compressor/driver alignment | 18 | 2026-12-14 | 2027-01-03 | 2026-12-02 | 2026-12-19 | 0
C1010 | Flushing/Airblowing and inspection of piping | 15 | 2026-12-02 | 2026-12-19 | 2026-12-14 | 2027-01-03 | 0
C1011 | Lube Oil Flushing | 10 | 2026-12-02 | 2026-12-13 | 2027-01-04 | 2027-01-20 | 0
GF Pre-Comm |  | 81 | 2026-10-06 | 2027-01-07 | 2026-12-10 | 2027-01-20 | 11
A23590 | Plant Equipments Pre Commissionning | 35 | 2026-11-29 | 2027-01-07 | 2026-12-10 | 2027-01-20 | 11
A17800 | Overall Plant & CCB/SIS Building Pre-Commissioning | 0 |  | 2027-01-07 |  | 2027-01-20 | 11
A23900 | CCB/SIS systems overall Pre-commissioning | 0 |  | 2026-12-28 |  | 2027-01-20 | 20
A3560 | Piping Cleaning, Flushing & Blowing (Pre Comm) | 36 | 2026-10-06 | 2026-11-16 | 2026-12-12 | 2027-01-20 | 56
BF Pre Commissioning |  | 130 | 2026-07-30 | 2026-12-28 | 2026-12-01 | 2027-01-20 | 20
BFW4090 | Piping Cleaning, Flushing & Blowing (Pre Comm) | 42 | 2026-11-10 | 2026-12-28 | 2026-12-22 | 2027-01-20 | 20
BFW4070 | Pre Commissioning works - Instrumentation & Control | 29 | 2026-09-14 | 2026-10-18 | 2026-12-01 | 2027-01-03 | 67
BFW4100 | Equipment pre commissioning | 26 | 2026-07-30 | 2026-08-30 | 2026-12-03 | 2027-01-20 | 124
Commissioning, RFSU, Start-Up |  | 293 | 2026-05-23 | 2027-04-28 | 2027-02-08 | 2027-07-20 | 71
Commissioning and Start-up |  | 281 | 2026-05-23 | 2027-04-15 | 2027-02-08 | 2027-07-20 | 83
A27420 | PSA2 Off Gas Compression (including all drums & coolers), Drip Leg & Onwards to Interface Battery Limits | 10 | 2027-03-23 | 2027-04-04 | 2027-02-08 | 2027-02-22 | 16
A27410 | PSA2 H2 Extraction Unit, Closed Sampling & Onwards to Interface Battery Limits | 12 | 2027-03-20 | 2027-04-01 | 2027-02-10 | 2027-02-22 | 16
A27400 | PSA2 Feed Gas Compressor | 12 | 2027-03-16 | 2027-03-29 | 2027-02-16 | 2027-02-24 | 16
A27390 | Feed Gas from Existing Fuel Gas, C1/C2 Separation Tail Gas Expander Booster Interface Battery Limits | 12 | 2027-03-13 | 2027-03-25 | 2027-02-13 | 2027-02-24 | 16
A27380 | C4 Guard Bed Adsorber Regeneration Gas Cooler & Drip Leg to Existing Fuel Gas System | 12 | 2027-03-10 | 2027-03-23 | 2027-02-14 | 2027-02-28 | 16
A27350 | Warm & Cold Flare Blowdown System | 12 | 2027-03-08 | 2027-03-21 | 2027-02-23 | 2027-03-01 | 16
A27370 | Cooling Water Distribution System | 7 | 2027-03-06 | 2027-03-13 | 2027-02-18 | 2027-03-02 | 16
A27260 | DCS / ESD / Compressor Control Systems / Machine Monitoring Systems (MMS) | 18 | 2027-02-20 | 2027-03-11 | 2027-02-21 | 2027-03-04 | 16
A26480 | Telecom (PAGA / PABX / LAN / CCTV) | 10 | 2027-02-27 | 2027-03-09 | 2027-02-25 | 2027-03-09 | 16
A27330 | Oily Water System | 5 | 2027-03-03 | 2027-03-08 | 2027-02-28 | 2027-03-11 | 16
A27280 | CP System / Heat Tracing System | 10 | 2027-02-24 | 2027-03-07 | 2027-03-02 | 2027-03-16 | 16
A27270 | Anti-Surge Protection System/ PSA2 PLC Control System / Plant F&G System / Deluge Fire Suppression System / Analyzers | 12 | 2027-02-22 | 2027-03-07 | 2027-03-04 | 2027-03-16 | 16
A27340 | Slop / Drainage System | 5 | 2027-03-01 | 2027-03-06 | 2027-03-07 | 2027-03-18 | 16
A27190 | Plant Lighting System | 10 | 2027-02-17 | 2027-02-28 | 2027-03-18 | 2027-03-24 | 16
A27250 | UPS System | 10 | 2027-02-15 | 2027-02-25 | 2027-03-11 | 2027-03-25 | 16
A27240 | MCC | 12 | 2027-02-13 | 2027-02-25 | 2027-03-14 | 2027-03-25 | 16
A27200 | Power Supply System (Existing 33 KVA) | 10 | 2027-02-10 | 2027-02-21 | 2027-03-21 | 2027-03-27 | 16
A27150 | Emergency Diesel Storage & Power Generation System | 10 | 2027-02-08 | 2027-02-18 | 2027-03-16 | 2027-03-28 | 16
A27360 | LP Condensate Collection System | 10 | 2027-02-03 | 2027-02-14 | 2027-03-09 | 2027-03-30 | 16
A27320 | LP Steam System | 10 | 2027-02-01 | 2027-02-11 | 2027-03-23 | 2027-03-31 | 16
A27170 | Sanitary Waste Water System | 5 | 2027-02-06 | 2027-02-10 | 2027-03-25 | 2027-04-08 | 16
A27300 | Inert Gas / Nitrogen System | 12 | 2027-01-27 | 2027-02-09 | 2027-03-28 | 2027-04-11 | 16
A27290 | Instrument & Plant Air System | 10 | 2027-01-26 | 2027-02-06 | 2027-03-30 | 2027-04-13 | 16
A27160 | Potable & Service Water System | 7 | 2027-01-30 | 2027-02-06 | 2027-04-03 | 2027-04-17 | 16
A27310 | Fire Water & Fire Suppression System | 10 | 2027-01-24 | 2027-02-03 | 2027-04-06 | 2027-04-20 | 16
A27180 | Industrial Buildings (MCC / Control Room including HVAC System / Building Fire Alarm System / Clean Agent etc) | 12 | 2027-01-21 | 2027-02-03 | 2027-04-10 | 2027-04-21 | 16
Commissioning & Handover |  | 233 | 2026-05-23 | 2027-02-17 | 2027-02-23 | 2027-07-20 | 131
C1039 | PSSR | 24 | 2027-01-21 | 2027-02-17 | 2027-03-30 | 2027-07-20 | 28
A9915 | As BuiltUpdation of UG Composite Layouts in B3/U3 areas, Substation Layouts (B3/ U3) under revamp / modification scope | 96 | 2026-05-23 | 2026-09-12 | 2027-02-23 | 2027-03-22 | 268
FG & OG Compressor - Commissioing |  | 42 | 2027-01-21 | 2027-03-10 | 2027-02-17 | 2027-04-06 | 23
C1019 | Control system sequence checks - Part of Dry Commissioning | 18 | 2027-02-18 | 2027-03-10 | 2027-02-17 | 2027-03-09 | 23
C1021 | PSSR | 6 | 2027-02-24 | 2027-03-02 | 2027-02-23 | 2027-03-15 | 23
C1018 | Interlock and Emergency Shutdown Tests - Part of Dry Commissioning (C&E Check) | 18 | 2027-02-09 | 2027-03-01 | 2027-02-28 | 2027-03-20 | 23
C1020 | Compressor Oil Lubrication System Check | 5 | 2027-02-18 | 2027-02-23 | 2027-03-17 | 2027-03-22 | 23
C1017 | Energization and Motor Solo Run | 18 | 2027-02-01 | 2027-02-21 | 2027-03-08 | 2027-03-28 | 23
C1016 | Hot Loop Testing | 18 | 2027-01-27 | 2027-02-16 | 2027-03-23 | 2027-03-29 | 23
C1015 | Compressor UCP Pre-Check / Power | 18 | 2027-01-21 | 2027-02-10 | 2027-03-17 | 2027-04-06 | 23
RFSU & Handover |  | 48 | 2027-02-18 | 2027-04-15 | 2027-03-30 | 2027-07-20 | 83
PC1030 | Issue "AS BUILT STATUS" Maintenance & Safety Manual | 48 | 2027-02-18 | 2027-04-15 |  | 2027-04-21 | 83
PC1050 | Project Close Out ( Handover of Care, Custody & Control of Plant ) | 0 |  | 2027-04-14 |  | 2027-07-20 | 83
PC1010 | Ready for Start-Up | 0 |  | 2027-04-04 | 2027-05-26 | 2027-07-20 | 16
FG & OG Compressor - RFSU |  | 20 | 2027-03-03 | 2027-03-25 | 2027-03-30 | 2027-04-21 | 23
C1025 | Equipment performance data - Mapping | 18 | 2027-03-06 | 2027-03-25 | 2027-03-30 | 2027-04-19 | 23
C1024 | Vibration signatures shall be obtained for all bearings | 18 | 2027-03-03 | 2027-03-23 | 2027-03-30 | 2027-04-19 | 23
C1023 | For motor drives, motor current readings shall be obtained. | 18 | 2027-03-03 | 2027-03-23 | 2027-03-30 | 2027-04-19 | 23
C1022 | Surge Testing | 18 | 2027-03-03 | 2027-03-23 | 2027-04-01 | 2027-04-21 | 23
Commissioning |  | 48 | 2027-01-21 | 2027-03-17 | 2027-04-14 | 2027-06-08 | 71
A61710 | Commissioning | 48 | 2027-01-21 | 2027-03-17 | 2027-04-14 | 2027-06-08 | 71
Start-up |  | 12 | 2027-03-18 | 2027-03-31 | 2027-06-23 | 2027-07-07 | 84
A61720 | Start-Up | 12 | 2027-03-18 | 2027-03-31 | 2027-06-23 | 2027-07-07 | 84
Initial Operations |  | 6 | 2027-04-01 | 2027-04-07 | 2027-07-07 | 2027-07-14 | 84
A61730 | Intial Operations | 6 | 2027-04-01 | 2027-04-07 | 2027-07-07 | 2027-07-14 | 84
Performance Test Run |  | 6 | 2027-04-07 | 2027-04-14 | 2027-07-14 | 2027-07-20 | 84
A61740 | Performance test Run | 6 | 2027-04-07 | 2027-04-14 | 2027-07-14 | 2027-07-20 | 84
Training |  | 36 | 2027-03-18 | 2027-04-28 | 2027-06-09 | 2027-07-20 | 71
A61750 | Training | 36 | 2027-03-18 | 2027-04-28 | 2027-06-09 | 2027-07-20 | 71
Optional Item’s Prices |  | 0 | 10-Sep-25 A | 10-Sep-25 A
Furnace Modification – Optional Scope |  | 0 | 10-Sep-25 A | 10-Sep-25 A
A61080 | COMPANY Activation for Optional Scope | 0 |  | 10-Sep-25 A
Reimbursable Items (Provisional Sums) |  | 48 | 2027-01-21 | 2027-03-09 | 2027-06-03 | 2027-07-20 | 133
Provisional Sum for Two Year Operating Spares |  | 48 | 2027-01-21 | 2027-03-09 | 2027-06-03 | 2027-07-20 | 133
A61760 | Provisional Sum for Two Year Operating Spares | 48 | 2027-01-21 | 2027-03-09 | 2027-06-03 | 2027-07-20 | 133
Provisional Sum for Additional Assistance to Company IPMT’s |  | 48 | 2027-01-21 | 2027-03-09 | 2027-06-03 | 2027-07-20 | 133
A61770 | Provisional Sum for Additional Assistance to Company IPMT’s | 48 | 2027-01-21 | 2027-03-09 | 2027-06-03 | 2027-07-20 | 133
Provisional Sum for Additional Start Up Assistance to COMPANY |  | 48 | 2027-01-21 | 2027-03-09 | 2027-06-03 | 2027-07-20 | 133
A61780 | Provisional Sum for Additional Start Up Assistance to COMPANY | 48 | 2027-01-21 | 2027-03-09 | 2027-06-03 | 2027-07-20 | 133
Training of COMPANY personnel |  | 48 | 2027-01-21 | 2027-03-09 | 2027-06-03 | 2027-07-20 | 133
A61790 | Training of COMPANY personnel | 48 | 2027-01-21 | 2027-03-09 | 2027-06-03 | 2027-07-20 | 133
Initial Fills and / or One (1) full Spare Charge (refer to Addendum to Scope |  | 48 | 2027-01-21 | 2027-03-09 | 2027-06-03 | 2027-07-20 | 133
A61800 | Initial Fills and / or One (1) full Spare Charge (refer to Addendum to Scope | 48 | 2027-01-21 | 2027-03-09 | 2027-06-03 | 2027-07-20 | 133
Feed-gas Compressor Final design configuration (3 Casing design) |  | 48 | 2027-01-21 | 2027-03-09 | 2027-06-03 | 2027-07-20 | 133
A61810 | Feed-gas Compressor Final design configuration (3 Casing design) | 48 | 2027-01-21 | 2027-03-09 | 2027-06-03 | 2027-07-20 | 133
Accommodation for IPMT (Site) |  | 48 | 2027-01-21 | 2027-03-09 | 2027-06-03 | 2027-07-20 | 133
A61820 | Accommodation for IPMT (Site) | 48 | 2027-01-21 | 2027-03-09 | 2027-06-03 | 2027-07-20 | 133
Unforeseen development during Execution for additional services over and above |  | 48 | 2027-01-21 | 2027-03-09 | 2027-06-03 | 2027-07-20 | 133
A61830 | Unforeseen development during Execution for additional services over and above | 48 | 2027-01-21 | 2027-03-09 | 2027-06-03 | 2027-07-20 | 133

## Sheet2
Activity ID | Activity Name | Early Planned Start | Early Planed Finish | Start [Actual] | Finish [Actual] | Late Start | Original Duration | Late Finish | Total Float | Output for Start Delay | Output for Start Delay Flag | Output for Deviation | Output for Deviation Flag
Borouge EU3 H2 Extraction EPC Project - MPR - Feb-2026 |  | 2026-02-20 | 2027-07-20 | 07-Nov-24 A | 2027-07-20 | 2026-02-21 | 699 | 2027-07-20 | 0 | C & D Comparison | on time / late start / Early Start | Diffrence of CD vs EF | Before time/ On time/Delay
COMPANY / PKG 1&2 Interfaces |  | 2026-02-20 | 2027-01-20 | 20-Nov-24 A | 2027-01-20 | 2026-02-27 | 565 | 2027-07-20 | 129
Engineering |  | 2026-02-20 | 2026-05-06 | 20-Nov-24 A | 2026-05-06 | 2026-05-11 | 380 | 2027-07-20 | 314
Required Inputs from COMPANY / Pkg 1&2 |  | 2026-02-20 | 2026-02-20 | 20-Nov-24 A | 2026-02-20 | 2026-05-11 | 326 | 2027-07-20 | 368
A60700 | Receipt of Drawings for all UG systems |  |  |  | 20-Nov-24 A |  | 0
A60720 | Receipt of Native files of 3D model, STAAD model, calculations for brown field - Pkg 1&2 |  |  |  | 15-Jan-25 A |  | 0
A60730 | Receipt of PSCAD native files for electrical studies - Pkg 1&2 |  |  |  | 15-Jan-25 A |  | 0
A60750 | Receipt of FEED datasheets for all telecom systems - Pkg 1&2 |  |  |  | 15-Jan-25 A |  | 0
A60660 | Receipt of SPI database login |  |  |  | 11-Feb-25 A |  | 0
A60740 | Receipt of System architecture & cable block diagram for MCMS, compressor control |  |  |  | 13-Feb-25 A |  | 0
A60760 | Receipt of Piping TA MTO |  |  |  | 20-Feb-25 A |  | 0
A60770 | Receipt of Approved Vendor data - GAD for PSA-2 unit |  |  |  | 17-Mar-25 A |  | 0
A60690 | Receipt of Unit Plot Plan Native File - Pkg 1&2 |  |  |  | 25-Mar-25 A |  | 0
A5200 | TA Construction Dossier (IFC) - Pkg 1&2 |  |  |  | 04-Apr-25 A |  | 0
A60780 | Receipt of Approved vendor data for FG & OG compressor |  |  |  | 24-Apr-25 A |  | 0
A60710 | Receipt of Native files of 3D model building & structural design (FEED stage) - Pkg 1&2 |  |  |  | 20-May-25 A |  | 0
A60790 | Receipt of Design parameters within received line list - Pkg 1&2 |  |  |  | 15-Jun-25 A |  | 0
P&IDs Status |  | 2026-02-20 | 2026-02-20 | 19-Jun-25 A | 2026-02-20 | 2026-05-11 | 220 | 2027-07-20 | 368
A60670 | Receipt of Updated P&ID's - Pkg 1&2 - Pre-HAZOP |  |  |  | 19-Jun-25 A |  | 0
A60680 | Receipt of Updated P&ID's Updated Line List (Tie-in list, PDS etc) - Pkg 1&2 - Pre-60% Model Review |  |  |  | 05-Sep-25 A |  | 0
A61030 | Latest Path of Mark-up P&ID by Pkg 3 |  |  |  | 12-Dec-25 A |  | 0
A61020 | Receipt of Final P&ID's - Pkg 1&2 - IFC |  | 2026-02-20 |  | 2026-02-20 |  | 0 | 2026-05-11 | 54
A62490 | Receipt of Final Process Data for Piping Line list - Pkg 1&2 - IFC |  | 2026-02-20 |  | 2026-02-20 |  | 0 | 2027-07-20 | 356
SP3D Database Status |  |  |  | 25-Apr-25 A | 19-Nov-25 A |  | 237
A60650 | Receipt of SP3D database from COMPANY (Not correct) |  |  |  | 25-Apr-25 A |  | 0
A61010 | Receipt of corrected SP3D database from COMPANY |  |  |  | 19-Nov-25 A |  | 0
Required Inputs from Pkg 3 to Pkg 1&2 |  | 2026-03-19 | 2026-05-06 | 04-Mar-25 A | 2026-05-06 | 2026-09-25 | 318 | 2026-09-25 | 102
A60990 | Selection for Option of MV motor (650% or 500% of rated current) or Starting VFD for Off Comp. |  |  |  | 04-Mar-25 A |  | 0
A60810 | All EPC Contractor G status input (detail refer Main Activities for P&ID) |  |  |  | 13-Mar-25 A |  | 0
A60860 | Cause and effect update |  |  |  | 13-Mar-25 A |  | 0
A60880 | Review & Confirmation on compressor GAD, Foundation plan & Anchor bolt locations |  |  |  | 20-Mar-25 A |  | 0
A61000 | Compressor Motor VDDR Motor datasheet - Electrical Cable list |  |  |  | 20-Mar-25 A |  | 0
A60920 | GF Balance of Plant maturity w.r.t. Compressor & PSA2 model integration |  |  |  | 27-Mar-25 A |  | 0
A60940 | Homerun cable length with its datasheet required for UCP signal IS calculation |  |  |  | 04-Apr-25 A |  | 0
A60930 | H2-SIS layout required + power cable details. |  |  |  | 16-Apr-25 A |  | 0
A60900 | List of inputs required in compressor process loop |  |  |  | 23-Apr-25 A |  | 0
A60910 | By-pass line sizing and routing and hot gas bypass valve details |  |  |  | 23-Apr-25 A |  | 0
A60960 | Follow up HAZOP/LOPA Recommendations report - 13-KC-701 - PSA2 Feed Gas Compressor - Pkg 3 related |  |  |  | 23-Apr-25 A |  | 0
A60980 | Safty Follow up HAZOP/LOPA Recommendations Package 1c - Pkg 3 related |  |  |  | 23-Apr-25 A |  | 0
A60890 | Review and Confirmation by Pkg -3 contractor as per issue 02 for EICT Cables |  |  |  | 15-May-25 A |  | 0
A60970 | HSE Action Tracking Register - Pkg 3 Actions |  |  |  | 20-May-25 A |  | 0
A60820 | All EPC Contractor H status input (detail refer Main Activities for P&ID) |  |  |  | 18-Jun-25 A |  | 0
A60840 | Mechanical data sheet (vendor data sheet) of vessels and exchangers |  |  |  | 20-Jun-25 A |  | 0
A60830 | Piping isos for main process piping and 3D model |  |  |  | 31-Jul-25 A |  | 0
A60870 | Instrument data sheet for level, pressure and temperature |  | 2026-03-19 |  | 2026-03-19 |  | 0 | 2026-09-25 | 136
A60850 | Data sheet of control valve, shut down, PSV, check valve and flow element (vendor data sheet) |  | 2026-05-06 |  | 2026-05-06 |  | 0 | 2026-09-25 | 102
A60950 | Vendor manuals package to be provided by EPC Contractor for Linde's review |  | 2026-05-06 |  | 2026-05-06 |  | 0 | 2026-09-25 | 102
Procurement |  | 2026-02-20 | 2026-10-07 | 15-Apr-25 A | 2026-10-07 | 2026-02-27 | 503 | 2027-01-20 | 105
A5190 | Free Issue TA Material latest delivery |  |  |  | 15-Apr-25 A |  | 0
A5210 | BFW Preheater - Delivery |  |  |  | 15-Apr-25 A |  | 0
A5170 | Key Vendor Data (LLI, Package Details and Design Data) |  | 2026-02-20 |  | 2026-02-20 |  | 0 | 2026-03-11 | 25
A9950 | PSA Unit Delivery - Delivery |  | 2026-02-20 |  | 2026-02-20 |  | 0 | 2026-04-25 | 81
A61070 | Approved Key Vendor Data (LLI, Package Details and Design Data) |  | 2026-02-20 |  | 2026-02-20 |  | 0 | 2026-03-11 | 25
78.D | OG Compressor - Delivery |  | 2026-03-01 |  | 2026-03-01 |  | 0 | 2026-06-04 | 119
76.D | FG Compressor - Delivery |  | 2026-03-03 |  | 2026-03-03 |  | 0 | 2026-03-11 | 10
Feed Gas Compressor - Delivery |  | 2026-02-20 | 2026-05-25 | 13-Feb-26 A | 2026-05-25 | 2026-02-27 | 95 | 2027-01-20 | 240
A62360 | VSD |  |  |  | 13-Feb-26 A |  | 0
A62350 | UCP |  | 2026-02-20 |  | 2026-02-20 |  | 0 | 2026-02-27 | 10
A62300 | Feed Gas Compressor (incl. Baseplate, Gear, Gas seal module & Booster) |  | 2026-03-03 |  | 2026-03-03 |  | 0 | 2026-03-11 | 10
A62330 | Capital Spares |  | 2026-03-09 |  | 2026-03-09 |  | 0 | 2027-01-20 | 396
A62340 | Main Driver (Motor) for FGC |  | 2026-03-09 |  | 2026-03-09 |  | 0 | 2026-06-24 | 134
A62310 | LO Console |  | 2026-03-16 |  | 2026-03-16 |  | 0 | 2026-08-23 | 200
A62370 | Transformer |  | 2026-04-27 |  | 2026-04-27 |  | 0 | 2026-08-23 | 148
A62320 | Anti-surge valve |  | 2026-05-25 |  | 2026-05-25 |  | 0 | 2026-09-27 | 156
Off Gas Compressor: Vendor - Delivery |  | 2026-02-20 | 2026-03-07 | 2026-02-20 | 2026-03-07 | 2026-05-25 | 15 | 2026-08-31 | 177
A62410 | UCP |  | 2026-02-20 |  | 2026-02-20 |  | 0 | 2026-05-25 | 119
A62390 | Capital Spares |  | 2026-02-22 |  | 2026-02-22 |  | 0 | 2026-05-28 | 119
A62380 | Off Gas Compressor |  | 2026-03-01 |  | 2026-03-01 |  | 0 | 2026-06-04 | 119
A62420 | Lube Oil Unit |  | 2026-03-01 |  | 2026-03-01 |  | 0 | 2026-07-01 | 153
A62400 | Main Driver (Motor) for OGC |  | 2026-03-04 |  | 2026-03-04 |  | 0 | 2026-07-04 | 153
A62430 | Seal Gas Unit |  | 2026-03-07 |  | 2026-03-07 |  | 0 | 2026-08-31 | 221
PSA Unit: Vendor - Delivery |  | 2026-02-20 | 2026-10-07 | 03-Sep-25 A | 2026-10-07 | 2026-07-10 | 384 | 2026-12-21 | 75
A62440 | PSA Pressure vessels |  |  |  | 03-Sep-25 A |  | 0
A62460 | PLC Cabinet |  |  |  | 03-Sep-25 A |  | 0
A62450 | PSA Valve Skid |  | 2026-02-20 |  | 2026-02-20 |  | 0 | 2026-07-10 | 176
A62470 | Adsorbent Material (PO pending) |  | 2026-08-21 |  | 2026-08-21 |  | 0 | 2026-10-11 | 64
A62480 | Analyzer (PO pending) |  | 2026-10-07 |  | 2026-10-07 |  | 0 | 2026-12-21 | 94
Construction & Commissioning |  | 2027-01-20 | 2027-01-20 | 2027-01-20 | 2027-01-20 | 2027-04-27 | 0 | 2027-04-27 | 83
A40220 | Potable Water and Service water (Needs) |  | 2027-01-20 |  | 2027-01-20 |  | 0 | 2027-04-27 | 83
A40230 | SANITARY Water system (Needs) |  | 2027-01-20 |  | 2027-01-20 |  | 0 | 2027-04-27 | 83
A40240 | Chilled Water for Safety Shower |  | 2027-01-20 |  | 2027-01-20 |  | 0 | 2027-04-27 | 83
A40250 | Instrument Air (Needs) for Boiler RFSU |  | 2027-01-20 |  | 2027-01-20 |  | 0 | 2027-04-27 | 83
A40260 | Fire Water (Needs) |  | 2027-01-20 |  | 2027-01-20 |  | 0 | 2027-04-27 | 83
A40270 | ETP (Effluent Treatment Package) System (Needs) |  | 2027-01-20 |  | 2027-01-20 |  | 0 | 2027-04-27 | 83
A40280 | Demin water (Needs) |  | 2027-01-20 |  | 2027-01-20 |  | 0 | 2027-04-27 | 83
A40290 | Nitrogen (Needs) |  | 2027-01-20 |  | 2027-01-20 |  | 0 | 2027-04-27 | 83
Project Management |  | 2026-02-20 | 2027-07-20 | 07-Nov-24 A | 2027-07-20 | 2026-03-02 | 672 | 2027-07-20 | 0
Project Management |  | 2026-02-20 | 2027-04-05 | 07-Nov-24 A | 2027-04-05 | 2026-03-27 | 542 | 2027-07-20 | 77
Project Management Deliverables |  | 2026-02-20 | 2026-03-17 | 22-Mar-25 A | 2026-03-17 | 2026-03-27 | 218 | 2027-07-20 | 351
A1-PM-PMD-0002 | PM-002-Project Coordination Procedure |  |  |  | 18-Apr-25 A |  | 0
A1-PM-PMD-0020 | PM-030-Worksite HSE Plan | 2026-02-20 | 2026-02-20 | 25-May-25 A | 28-May-25 A | 2026-06-11 | 5 | 2026-06-11
A1-PM-PMD-0017 | PM-017-HSE Training plan & procedure | 2026-02-20 | 2026-02-20 | 21-Jun-25 A | 12-Jul-25 A | 2026-06-11 | 5 | 2026-06-11
A1-PM-PMD-0019 | PM-029-Recovery Plan | 2026-02-20 | 2026-02-20 | 25-May-25 A | 12-Jul-25 A | 2026-06-11 | 5 | 2026-06-11
A1-PM-PMD-0025 | PM-039-List of Claims for Damage | 2026-02-20 | 2026-02-20 | 25-May-25 A | 12-Jul-25 A | 2026-06-11 | 5 | 2026-06-11
A1-PM-PMD-0031 | PM-048-HSE Audit Procedure | 2026-02-20 | 2026-02-20 | 21-Jun-25 A | 12-Jul-25 A | 2026-06-11 | 5 | 2026-06-11
A1-PM-PMD-0052 | PM-082-Interface Responsibility Philosophy | 2026-02-20 | 2026-02-20 | 21-Jun-25 A | 12-Jul-25 A | 2026-06-11 | 5 | 2026-06-11
A1-PM-PMD-0064 | PM-094-Package 1 Deliverables IFC | 2026-03-12 | 2026-03-12 | 15-May-25 A | 12-Jul-25 A | 2026-06-26 | 5 | 2026-06-26
A1-PM-PMD-0029 | PM-046-Procurement Status Report | 2026-02-20 | 2026-02-20 | 25-May-25 A | 25-Jul-25 A | 2026-06-11 | 5 | 2026-06-11
A1-PM-PMD-0036 | PM-054-Master Document schedule and Status Report | 2026-02-20 | 2026-02-20 | 25-May-25 A | 25-Jul-25 A | 2026-06-11 | 5 | 2026-06-11
A1-PM-PMD-0001 | PM-001-Job Bulletins | 2026-02-20 | 2026-02-20 | 25-May-25 A | 15-Aug-25 A | 2026-03-27 | 5 | 2026-03-27
A1-PM-PMD-0003 | PM-003-Code of accounts | 2026-02-20 | 2026-02-20 | 25-May-25 A | 15-Aug-25 A | 2026-06-11 | 5 | 2026-06-11
A1-PM-PMD-0011 | PM-011-Project Engineering CADD Applications & Deliverables Guideline | 2026-02-20 | 2026-02-20 | 25-May-25 A | 21-Aug-25 A | 2026-06-11 | 5 | 2026-06-11
A1-PM-PMD-0012 | PM-012-PDS / Smart3D Raceways Guideline | 2026-02-20 | 2026-02-20 | 25-May-25 A | 23-Aug-25 A | 2026-06-11 | 5 | 2026-06-11
A1-PM-PMD-0004 | PM-004-PDS / Smart3D 3D Modeling Guideline for End User | 2026-02-20 | 2026-02-20 | 25-May-25 A | 25-Aug-25 A | 2026-06-11 | 5 | 2026-06-11
A1-PM-PMD-0021 | PM-031-Temporary Site Establishment plan | 2026-02-20 | 2026-02-20 | 25-May-25 A | 25-Aug-25 A | 2026-06-11 | 5 | 2026-06-11
A1-PM-PMD-0037 | PM-057-Project Specification | 2026-02-20 | 2026-02-20 | 25-May-25 A | 25-Aug-25 A | 2026-06-11 | 5 | 2026-06-11
A1-PM-PMD-0005 | PM-005-SPI (Smart Plant Instrumentation) INtoos Guideline for End User | 2026-02-20 | 2026-02-20 | 25-May-25 A | 26-Aug-25 A | 2026-06-11 | 5 | 2026-06-11
A1-PM-PMD-0022 | PM-032-Tie-in & Interface Matrix | 2026-02-20 | 2026-02-20 | 25-May-25 A | 26-Aug-25 A | 2026-06-11 | 5 | 2026-06-11
A1-PM-PMD-0034 | PM-052-Contract Trending procedure | 2026-02-20 | 2026-02-20 | 25-May-25 A | 26-Aug-25 A | 2026-06-11 | 5 | 2026-06-11
A1-PM-PMD-0040 | PM-063-Insurance claim status report | 2026-02-20 | 2026-02-20 | 23-Aug-25 A | 26-Aug-25 A | 2026-06-11 | 5 | 2026-06-11
A1-PM-PMD-0013 | PM-013-PDS / Smart3D Generated List of Drawings / Documents | 2026-02-20 | 2026-02-20 | 25-May-25 A | 27-Aug-25 A | 2026-06-11 | 5 | 2026-06-11
A1-PM-PMD-0018 | PM-028-Project Organization Charts | 2026-02-20 | 2026-02-20 | 25-May-25 A | 27-Aug-25 A | 2026-06-11 | 5 | 2026-06-11
A1-PM-PMD-0035 | PM-053-Contract Trend notice / Log | 2026-02-20 | 2026-02-20 | 22-Mar-25 A | 27-Aug-25 A | 2026-06-11 | 6 | 2026-06-11
A1-PM-PMD-0006 | PM-006-SP PID (Smart Plant P&ID ) Guideline for End User | 2026-02-20 | 2026-02-20 | 25-May-25 A | 30-Aug-25 A | 2026-06-11 | 5 | 2026-06-11
A1-PM-PMD-0023 | PM-037-Document/Drawing Index | 2026-02-20 | 2026-02-20 | 25-May-25 A | 30-Aug-25 A | 2026-06-11 | 5 | 2026-06-11
A1-PM-PMD-0041 | PM-064-Claims | 2026-02-20 | 2026-02-20 | 27-Aug-25 A | 30-Aug-25 A | 2026-06-11 | 5 | 2026-06-11
A1-PM-PMD-0014 | PM-014-Documentation and CADD Systems / Database Handover Schedule | 2026-02-20 | 2026-02-20 | 25-May-25 A | 01-Sep-25 A | 2026-06-11 | 5 | 2026-06-11
A1-PM-PMD-0038 | PM-061-Insurance Policies | 2026-02-20 | 2026-02-20 | 25-May-25 A | 01-Sep-25 A | 2026-06-11 | 5 | 2026-06-11
A1-PM-PMD-0007 | PM-007-SPEL (Smart Plant Electrical) Guideline for End Users | 2026-02-20 | 2026-02-20 | 25-May-25 A | 02-Sep-25 A | 2026-06-11 | 5 | 2026-06-11
A1-PM-PMD-0024 | PM-038-Documentation List | 2026-02-20 | 2026-02-20 | 25-May-25 A | 04-Sep-25 A | 2026-06-11 | 5 | 2026-06-11
A1-PM-PMD-0042 | PM-065-Requests for Variation | 2026-02-20 | 2026-02-20 | 01-Sep-25 A | 04-Sep-25 A | 2026-06-11 | 5 | 2026-06-11
A1-PM-PMD-0015 | PM-015-CADD Systems As-built Database and System integrated Deliverables (PDS/IN Tools/SP PID/SPEL/ETAP/ Caesar-II / STA | 2026-02-20 | 2026-02-20 | 25-May-25 A | 05-Sep-25 A | 2026-06-11 | 5 | 2026-06-11
A1-PM-PMD-0039 | PM-062-Insurance Claims | 2026-02-20 | 2026-02-20 | 25-Aug-25 A | 05-Sep-25 A | 2026-06-11 | 5 | 2026-06-11
A1-PM-PMD-0016 | PM-016-Site Mobilization Plan | 2026-02-20 | 2026-02-20 | 25-May-25 A | 07-Sep-25 A | 2026-06-11 | 6 | 2026-06-11
A1-PM-PMD-0008 | PM-008-PDS / Smart3D CADD Area/Model Index/ Plan | 2026-02-20 | 2026-02-20 | 25-May-25 A | 08-Sep-25 A | 2026-06-11 | 5 | 2026-06-11
A1-PM-PMD-0043 | PM-073-Feed Documents | 2026-02-20 | 2026-02-20 | 25-May-25 A | 08-Sep-25 A | 2026-06-11 | 5 | 2026-06-11
A1-PM-PMD-0051 | PM-081-Interface Management Plan - EPC | 2026-02-20 | 2026-02-20 | 25-May-25 A | 10-Sep-25 A | 2026-06-11 | 5 | 2026-06-11
A1-PM-PMD-0009 | PM-009-CADD Project Hierarchy & Setup Guideline (PDS /Intools/ SP PID/ SPEL) | 2026-02-20 | 2026-02-20 | 25-May-25 A | 12-Sep-25 A | 2026-06-11 | 5 | 2026-06-11
A1-PM-PMD-0010 | PM-010-PDS / Smart3D Physical Support Modeling Guideline for End Users | 2026-02-20 | 2026-02-20 | 25-May-25 A | 16-Sep-25 A | 2026-06-11 | 5 | 2026-06-11
A1-PM-PMD-0050 | PM-080-Project IT/EDMS Requirements | 2026-02-20 | 2026-02-20 | 25-May-25 A | 16-Sep-25 A | 2026-06-11 | 5 | 2026-06-11
A1-PM-PMD-0032 | PM-049-Risk Analysis | 2026-02-20 | 2026-02-20 | 25-May-25 A | 17-Sep-25 A | 2026-06-11 | 5 | 2026-06-11
A1-PM-PMD-0030 | PM-047-Project Execution Plan |  |  |  | 12-Nov-25 A |  | 0
A1-PM-PMD-0044 | PM-074-Asset Integrated Management System (AIMS) / Project Integrity Management Plan | 2026-02-20 | 2026-02-20 | 08-Aug-25 A | 18-Dec-25 A | 2027-06-25 | 5 | 2027-06-25
A1-PM-PMD-0054 | PM-084-EPC Responsibility Matrix for ICT & IT/OT | 2026-02-20 | 2026-02-20 | 08-Aug-25 A | 18-Dec-25 A | 2026-06-11 | 5 | 2026-06-11
A1-PM-PMD-0053 | PM-083-EPC Responsibility Matrix for Control Systems | 2026-02-20 | 2026-02-20 | 25-Jul-25 A | 19-Dec-25 A | 2026-06-11 | 5 | 2026-06-11
A1-PM-PMD-0055 | PM-085-Interface Point Registers | 2026-02-20 | 2026-02-20 | 08-Aug-25 A | 19-Dec-25 A | 2026-06-11 | 5 | 2026-06-11
A1-PM-PMD-0056 | PM-086-Interface Dependency Table | 2026-02-20 | 2026-02-20 | 14-Jul-25 A | 19-Dec-25 A | 2026-06-11 | 5 | 2026-06-11
A1-PM-PMD-0057 | PM-087-Master Boundary Interface Layout Drawing | 2026-02-20 | 2026-02-20 | 20-Jun-25 A | 19-Dec-25 A | 2026-06-11 | 5 | 2026-06-11
A1-PM-PMD-0058 | PM-088-Process and Utilities Overall Block Flow Diagram Borouge-4 Facilities | 2026-02-20 | 2026-02-20 | 21-Jul-25 A | 19-Dec-25 A | 2026-06-11 | 5 | 2026-06-11
A1-PM-PMD-0060 | PM-090-Piping External/Internal Connections Layout drawings | 2026-02-20 | 2026-02-20 | 08-Aug-25 A | 19-Dec-25 A | 2026-06-10 | 5 | 2026-06-10
A1-PM-PMD-0045 | PM-075-Constructability Action Closeout Report | 2026-02-20 | 2026-02-20 | 28-Oct-25 A | 2026-02-20 | 2027-06-25 | 5 | 2027-06-25 | 351
A1-PM-PMD-0059 | PM-089-Process and Utilities Block Flow Diagram Interconnecting | 2026-02-20 | 2026-02-20 | 08-Aug-25 A | 2026-02-20 | 2026-06-10 | 5 | 2026-06-11 | 79
A1-PM-PMD-0061 | PM-091-MRB Index | 2026-02-20 | 2026-02-24 | 01-Aug-25 A | 2026-02-24 | 2026-06-08 | 5 | 2026-06-10 | 77
A1-PM-PMD-0026 | PM-040-List of Commissioning Spares | 2026-02-20 | 2026-02-24 | 30-Jul-25 A | 2026-02-24 | 2027-07-07 | 5 | 2027-07-09 | 358
A1-PM-PMD-0049 | PM-079-Synergies Study Report | 2026-02-20 | 2026-02-24 | 08-Sep-25 A | 2026-02-24 | 2026-06-11 | 5 | 2026-06-16 | 80
A1-PM-PMD-0027 | PM-041-List of startup spares | 2026-02-20 | 2026-02-26 | 25-Aug-25 A | 2026-02-26 | 2027-07-07 | 5 | 2027-07-13 | 358
A1-PM-PMD-0046 | PM-076-Project Training Requirements and Training Plan | 2026-02-20 | 2026-02-27 | 2026-02-20 | 2026-02-27 | 2027-06-28 | 5 | 2027-07-02 | 351
A1-PM-PMD-0062 | PM-092-Material Record Book (MRB) | 2026-03-03 | 2026-03-05 | 01-Aug-25 A | 2026-03-05 | 2026-06-18 | 5 | 2026-06-19 | 77
A1-PM-PMD-0028 | PM-045-Project Close out Report | 2026-02-27 | 2026-03-05 | 2026-02-27 | 2026-03-05 | 2027-07-14 | 5 | 2027-07-20 | 358
A1-PM-PMD-0047 | PM-077-Operating Procedure/Guidelines | 2026-02-27 | 2026-03-06 | 2026-02-27 | 2026-03-06 | 2027-07-05 | 5 | 2027-07-09 | 351
A1-PM-PMD-0048 | PM-078-Guidelines for Acceptance of Work | 2026-03-06 | 2026-03-13 | 2026-03-06 | 2026-03-13 | 2027-07-12 | 5 | 2027-07-16 | 351
A1-PM-PMD-0063 | PM-093-QA/QC Dossiers | 2026-03-12 | 2026-03-16 | 01-Aug-25 A | 2026-03-16 | 2026-06-26 | 5 | 2026-06-30 | 77
A1-PM-PMD-0033 | PM-050-Acceptance Certificate | 2026-03-13 | 2026-03-17 | 2026-03-13 | 2026-03-17 | 2027-07-17 | 5 | 2027-07-20 | 613
Project Control Deliverables |  | 2026-02-20 | 2026-02-27 | 15-Feb-25 A | 2026-02-27 | 2026-03-27 | 256 | 2026-11-13 | 185
A1-PM-PCD-0015 | PC-015-Annual Reports | 2026-02-20 | 2026-02-20 | 15-May-25 A | 23-May-25 A | 2026-03-27 | 2 | 2026-03-27
A1-PM-PCD-0009 | PC-009-Detailed Commissioning and Pre Commissioning Schedule | 2026-02-20 | 2026-02-20 | 15-Feb-25 A | 17-Jun-25 A | 2026-03-27 | 2 | 2026-03-27
A1-PM-PCD-0037 | PC-037-Schedule Risk Analysis Reports | 2026-02-20 | 2026-02-20 | 15-Feb-25 A | 28-Jun-25 A | 2026-03-27 | 2 | 2026-03-27
A1-PM-PCD-0010 | PC-010-Variations | 2026-02-20 | 2026-02-20 | 21-Jun-25 A | 12-Jul-25 A | 2026-03-27 | 2 | 2026-03-27
A1-PM-PCD-0011 | PC-011-Document/Drawing Index | 2026-02-20 | 2026-02-20 | 21-Jun-25 A | 12-Jul-25 A | 2026-03-27 | 2 | 2026-03-27
A1-PM-PCD-0013 | PC-013-Spares Lists | 2026-02-20 | 2026-02-20 | 21-Jun-25 A | 12-Jul-25 A | 2026-03-27 | 2 | 2026-03-27
A1-PM-PCD-0035 | PC-035-Back charges Status Report | 2026-02-20 | 2026-02-20 | 21-Jun-25 A | 12-Jul-25 A | 2026-03-27 | 2 | 2026-03-27
A1-PM-PCD-0016 | PC-016-Monthly Reports | 2026-02-20 | 2026-02-20 | 26-May-25 A | 20-Jul-25 A | 2026-03-27 | 2 | 2026-03-27
A1-PM-PCD-0017 | PC-017-Weekly Reports | 2026-02-20 | 2026-02-20 | 25-May-25 A | 19-Aug-25 A | 2026-03-27 | 2 | 2026-03-27
A1-PM-PCD-0014 | PC-014-Suppliers Lists | 2026-02-20 | 2026-02-20 | 19-Aug-25 A | 20-Aug-25 A | 2026-03-27 | 2 | 2026-03-27
A1-PM-PCD-0012 | PC-012-Specialty Item List | 2026-02-20 | 2026-02-20 | 21-Jun-25 A | 21-Aug-25 A | 2026-03-27 | 2 | 2026-03-27
A1-PM-PCD-0018 | PC-018-Forecasts for Completion | 2026-02-20 | 2026-02-20 | 25-May-25 A | 21-Aug-25 A | 2026-03-27 | 2 | 2026-03-27
A1-PM-PCD-0033 | PC-033-Bank Bonds and Guarantees | 2026-02-20 | 2026-02-20 | 25-May-25 A | 26-Aug-25 A | 2026-03-27 | 2 | 2026-03-27
A1-PM-PCD-0030 | PC-030-Technical Queries | 2026-02-20 | 2026-02-20 | 25-May-25 A | 27-Aug-25 A | 2026-03-27 | 2 | 2026-03-27
A1-PM-PCD-0027 | PC-027-Change Orders | 2026-02-20 | 2026-02-20 | 25-Aug-25 A | 29-Aug-25 A | 2026-03-27 | 2 | 2026-03-27
A1-PM-PCD-0029 | PC-029-Site Queries | 2026-02-20 | 2026-02-20 | 27-Aug-25 A | 29-Aug-25 A | 2026-03-27 | 2 | 2026-03-27
A1-PM-PCD-0025 | PC-025-Engineering Document Change Note | 2026-02-20 | 2026-02-20 | 25-May-25 A | 02-Sep-25 A | 2026-03-27 | 2 | 2026-03-27
A1-PM-PCD-0024 | PC-024-P&ID change notes | 2026-02-20 | 2026-02-20 | 06-Sep-25 A | 07-Sep-25 A | 2026-03-27 | 2 | 2026-03-27
A1-PM-PCD-0028 | PC-028-Field Queries | 2026-02-20 | 2026-02-20 | 01-Sep-25 A | 08-Sep-25 A | 2026-03-27 | 2 | 2026-03-27
A1-PM-PCD-0026 | PC-026-Query Form | 2026-02-20 | 2026-02-20 | 25-May-25 A | 09-Sep-25 A | 2026-03-27 | 2 | 2026-03-27
A1-PM-PCD-0036 | PC-036-Progress Review and Certification Procedure | 2026-02-20 | 2026-02-20 | 15-Feb-25 A | 10-Sep-25 A | 2026-03-27 | 2 | 2026-03-27
A1-PM-PCD-0034 | PC-034-Cash Flow Forecast | 2026-02-20 | 2026-02-20 | 25-May-25 A | 14-Oct-25 A | 2026-03-27 | 2 | 2026-03-27
A1-PM-PCD-0002 | PC-002-Distribution Matrix | 2026-02-20 | 2026-02-20 | 04-Mar-25 A | 03-Nov-25 A | 2026-03-27 | 2 | 2026-03-27
A1-PM-PCD-0008 | PC-008-Detailed Control Log / Schedule | 2026-02-20 | 2026-02-20 | 15-Feb-25 A | 08-Nov-25 A | 2026-03-27 | 2 | 2026-03-27
A1-PM-PCD-0005 | PC-005-Detailed Procurement schedule | 2026-02-20 | 2026-02-20 | 15-Feb-25 A | 14-Nov-25 A | 2026-03-27 | 2 | 2026-03-27
A1-PM-PCD-0039 | PC-039-Equipment Deployment Plan | 2026-02-20 | 2026-02-20 | 15-Feb-25 A | 15-Nov-25 A | 2026-03-27 | 2 | 2026-03-27
A1-PM-PCD-0040 | PC-040-Planning Package | 2026-02-20 | 2026-02-20 | 15-Feb-25 A | 15-Nov-25 A | 2026-03-27 | 2 | 2026-03-27
A1-PM-PCD-0001 | PC-001-Procedures | 2026-02-20 | 2026-02-20 | 15-Feb-25 A | 17-Nov-25 A | 2026-03-27 | 2 | 2026-03-27
A1-PM-PCD-0003 | PC-003-Time Schedule / Program | 2026-02-20 | 2026-02-20 | 15-Feb-25 A | 17-Nov-25 A | 2026-03-27 | 2 | 2026-03-27
A1-PM-PCD-0004 | PC-004-Overall Project Schedule | 2026-02-20 | 2026-02-20 | 15-Feb-25 A | 17-Nov-25 A | 2026-03-27 | 2 | 2026-03-27
A1-PM-PCD-0006 | PC-006-Detailed Engineering Schedule | 2026-02-20 | 2026-02-20 | 15-Feb-25 A | 17-Nov-25 A | 2026-03-27 | 2 | 2026-03-27
A1-PM-PCD-0007 | PC-007-Detailed Construction Schedule | 2026-02-20 | 2026-02-20 | 15-Feb-25 A | 17-Nov-25 A | 2026-03-27 | 2 | 2026-03-27
A1-PM-PCD-0019 | PC-019-Project Execution Plan |  |  |  | 17-Nov-25 A |  | 0
A1-PM-PCD-0020 | PC-020-FAT Procedures | 2026-02-20 | 2026-02-20 | 15-Feb-25 A | 17-Nov-25 A | 2026-11-06 | 2 | 2026-11-06
A1-PM-PCD-0038 | PC-038-Manpower Mobilization Plan | 2026-02-20 | 2026-02-20 | 15-Feb-25 A | 19-Nov-25 A | 2026-03-27 | 2 | 2026-03-27
A1-PM-PCD-0031 | PC-031-Invoices | 2026-02-20 | 2026-02-20 | 25-May-25 A | 20-Nov-25 A | 2026-03-27 | 2 | 2026-03-27
A1-PM-PCD-0032 | PC-032-Invoices Status Report | 2026-02-20 | 2026-02-20 | 25-May-25 A | 20-Nov-25 A | 2026-03-27 | 2 | 2026-03-27
A1-PM-PCD-0021 | PC-021-FAT Reports | 2026-02-20 | 2026-02-23 | 2026-02-20 | 2026-02-23 | 2026-11-06 | 2 | 2026-11-09 | 185
A1-PM-PCD-0022 | PC-022-SAT Procedures | 2026-02-24 | 2026-02-25 | 2026-02-24 | 2026-02-25 | 2026-11-10 | 2 | 2026-11-11 | 185
A1-PM-PCD-0023 | PC-023-SAT Reports | 2026-02-26 | 2026-02-27 | 2026-02-26 | 2026-02-27 | 2026-11-12 | 2 | 2026-11-13 | 185
Project Risk Analysis Workshops |  | 2026-03-12 | 2027-03-25 | 25-May-25 A | 2027-03-25 | 2026-06-26 | 460 | 2027-07-09 | 77
A1-PM-PRA-0001 | PRA01-Project Risk Analysis - Risk Identifications Workshop |  |  |  | 25-May-25 A |  | 0
A1-PM-PRA-0002 | PRA02-Project Risk Analysis Workshop - Update - Q01 |  |  |  | 21-Jun-25 A |  | 0
A1-PM-PRA-0003 | PRA03-Project Risk Analysis Workshop - Update - Q02 |  |  |  | 20-Aug-25 A |  | 0
A1-PM-PRA-0004 | PRA04-Project Risk Analysis Workshop - Update - Q03 |  |  |  | 24-Oct-25 A |  | 0
A1-PM-PRA-0005 | PRA05-Project Risk Analysis Workshop - Update - Q04 |  | 2026-03-12 |  | 2026-03-12 |  | 0 | 2026-06-26 | 77
A1-PM-PRA-0006 | PRA06-Project Risk Analysis Workshop - Update - Q05 |  | 2026-07-16 |  | 2026-07-16 |  | 0 | 2026-10-30 | 77
A1-PM-PRA-0007 | PRA07-Project Risk Analysis Workshop - Update - Q06 |  | 2026-11-19 |  | 2026-11-19 |  | 0 | 2027-03-05 | 77
A1-PM-PRA-0008 | PRA08-Project Risk Analysis Workshop - Update - Q07 |  | 2027-03-25 |  | 2027-03-25 |  | 0 | 2027-07-09 | 77
Schedule Risk Analysis Workshops |  | 2026-02-20 | 2027-04-05 | 15-May-25 A | 2027-04-05 | 2026-06-19 | 402 | 2027-07-20 | 77
A1-PM-SRA-0001 | SRA01-Schedule Risk Analysis Workshop - Baseline Schedule |  |  |  | 15-May-25 A |  | 0
A1-PM-SRA-0002 | SRA02-Schedule Risk Analysis Workshop - UpdatedSchedule - Q01 |  |  |  | 10-Jul-25 A |  | 0
A1-PM-SRA-0003 | SRA03-Schedule Risk Analysis Workshop - Updated Schedule - Q02 |  |  |  | 17-Sep-25 A |  | 0
A1-PM-SRA-0004 | SRA04-Schedule Risk Analysis Workshop - Updated Schedule - Q03 |  | 2026-02-20 |  | 2026-02-20 |  | 0 | 2026-06-19 | 86
A1-PM-SRA-0005 | SRA05-Schedule Risk Analysis Workshop - Updated Schedule - Q04 |  | 2026-06-25 |  | 2026-06-25 |  | 0 | 2026-10-23 | 86
A1-PM-SRA-0006 | SRA06-Schedule Risk Analysis Workshop - Updated Schedule - Q05 |  | 2026-10-29 |  | 2026-10-29 |  | 0 | 2027-02-26 | 86
A1-PM-SRA-0007 | SRA07-Schedule Risk Analysis Workshop - Updated Schedule - Q06 |  | 2027-03-04 |  | 2027-03-04 |  | 0 | 2027-07-02 | 86
A1-PM-SRA-0008 | SRA08-Schedule Risk Analysis Workshop - Updated Schedule - Q07 |  | 2027-04-05 |  | 2027-04-05 |  | 0 | 2027-07-20 | 77
Project Lesson Learn Workshops |  | 2026-03-17 | 2027-03-30 | 25-May-25 A | 2027-03-30 | 2026-07-07 | 462 | 2027-07-20 | 81
A1-PM-LLW-0001 | PRA01-Project Lesson Learn Workshop - Lesson Learn Identifications |  |  |  | 25-May-25 A |  | 0
A1-PM-LLW-0002 | PRA02-Project Lesson Learn Workshop - Update - Q01 |  |  |  | 21-Jun-25 A |  | 0
A1-PM-LLW-0003 | PRA03-Project Lesson Learn Workshop - Update - Q02 |  |  |  | 15-Sep-25 A |  | 0
A1-PM-LLW-0004 | PRA04-Project Lesson Learn Workshop - Update - Q03 |  |  |  | 01-Oct-25 A |  | 0
A1-PM-LLW-0005 | PRA05-Project Lesson Learn Workshop - Update - Q04 |  | 2026-03-17 |  | 2026-03-17 |  | 0 | 2026-07-07 | 81
A1-PM-LLW-0006 | PRA06-Project Lesson Learn Workshop - Update - Q05 |  | 2026-07-21 |  | 2026-07-21 |  | 0 | 2026-11-10 | 81
A1-PM-LLW-0007 | PRA07-Project Lesson Learn Workshop - Update - Q06 |  | 2026-11-24 |  | 2026-11-24 |  | 0 | 2027-03-16 | 81
A1-PM-LLW-0008 | PRA08-Project Lesson Learn Workshop - Update - Q07 |  | 2027-03-30 |  | 2027-03-30 |  | 0 | 2027-07-20 | 81
Project Management Interim Milestones |  |  |  | 07-Nov-24 A | 30-Oct-25 A |  | 160
A1-PM-PMM-0001 | Letter of Award (LOA) Recieved - Project Commencement Date |  |  |  | 07-Nov-24 A |  | 0
A1-PM-PMM-0002 | 10.A-Kick-off Meeting Completed |  |  |  | 06-Dec-24 A |  | 0
A1-PM-PMM-0004 | 1.A*-Issue Coordination Procedure |  |  |  | 30-Apr-25 A |  | 0
A1-PM-PMM-0003 | 1.A*-Issue Overall Project Execution Plan |  |  |  | 30-Oct-25 A |  | 0
QAQC Interim Milestones |  |  |  | 26-May-25 A | 26-May-25 A |  | 0
General Project Management |  |  |  | 26-May-25 A | 26-May-25 A |  | 0
A1-PM-QCM-0001 | 1.A*-Issue Project Quality Procedures (Final Issue). |  |  |  | 26-May-25 A |  | 0
HSE Interim Milestones |  |  |  | 30-Apr-25 A | 30-Apr-25 A |  | 0
General Project Management |  |  |  | 30-Apr-25 A | 30-Apr-25 A |  | 0
A1-PM-HSM-0001 | 1.A*-Issue Project HSE Procedure. |  |  |  | 30-Apr-25 A |  | 0
Project Control Interim Milestones |  |  |  | 24-Mar-25 A | 24-Mar-25 A |  | 0
A1-PM-PCM-0002 | 2.A-Issue Progress Measurement & Reporting System |  |  |  | 24-Mar-25 A |  | 0
A1-PM-PCM-0003 | 2.A-Issue Cost Control Procedure |  |  |  | 24-Mar-25 A |  | 0
A1-PM-PCM-0004 | 2.A-Issue Planning Docs |  |  |  | 24-Mar-25 A |  | 0
A1-PM-PCM-0001 | 2.A-Issue Project Control Propcedures |  |  |  | 24-Mar-25 A |  | 0
Moblization of Key Personnel |  |  |  | 15-Nov-24 A | 13-Nov-25 A |  | 155
A1-PM-KPM-0007 | Moblization of Procurement Manager (s) * |  |  |  | 15-Nov-24 A |  | 0
A1-PM-KPM-0010 | Moblization of Project Control Manager* |  |  |  | 15-Nov-24 A |  | 0
A1-PM-KPM-0002 | Moblization of Project Turnaround Manager * |  |  |  | 21-Nov-24 A |  | 0
A1-PM-KPM-0005 | Moblization of Lead Discipline and Supervisory Engineers * - RAD |  |  |  | 01-Dec-24 A |  | 0
A1-PM-KPM-0009 | Moblization of Project Traffic and Logistics Manager |  |  |  | 01-Dec-24 A |  | 0
A1-PM-KPM-0001 | Moblization of Project Director or Project Manager * |  |  |  | 18-Dec-24 A |  | 0
A1-PM-KPM-0017 | Moblization of Project HSE Manager(s) (Home Office/Construction) |  |  |  | 20-Dec-24 A |  | 0
A1-PM-KPM-0008 | Moblization of Project Commercial/Prime Contracts Manager |  |  |  | 01-Jan-25 A |  | 0
A1-PM-KPM-0006 | Moblization of Process Manager (s) * |  |  |  | 01-Feb-25 A |  | 0
A1-PM-KPM-0003 | Moblization of Engineering Manager * |  |  |  | 15-Feb-25 A |  | 0
A1-PM-KPM-0004 | Moblization of Quality Assurance and Quality Control Manager (Home Office/SITE) |  |  |  | 20-Feb-25 A |  | 0
A1-PM-KPM-0015 | Moblization of Project Construction Chief Field Engineer |  |  |  | 01-Mar-25 A |  | 0
A1-PM-KPM-0012 | Moblization of Construction Planner |  |  |  | 27-Mar-25 A |  | 0
A1-PM-KPM-0018 | Moblization of Lead Cost Engineer / Estimator |  |  |  | 01-Apr-25 A |  | 0
A1-PM-KPM-0014 | Moblization of Project Construction Director/Manager(s)* |  |  |  | 14-Apr-25 A |  | 0
A1-PM-KPM-0016 | Moblization of Project Construction Field Superintendent |  |  |  | 15-Apr-25 A |  | 0
A1-PM-KPM-0021 | Moblization of Project IT Manager |  |  |  | 15-May-25 A |  | 0
A1-PM-KPM-0013 | Moblization of Project Contracts/Subcontracts Manager* |  |  |  | 01-Jun-25 A |  | 0
A1-PM-KPM-0011 | Moblization of Lead Planner |  |  |  | 21-Jun-25 A |  | 0
A1-PM-KPM-0022 | Moblization of Field Engineering Manager |  |  |  | 22-Aug-25 A |  | 0
A1-PM-KPM-0019 | Moblization of Project Commissioning Manager* |  |  |  | 13-Nov-25 A |  | 0
A1-PM-KPM-0020 | Moblization of Project Training Manager* |  |  |  | 13-Nov-25 A |  | 0
Detailed Design and Engineering |  | 2026-02-20 | 2027-01-21 | 02-Apr-25 A | 2027-01-21 | 2026-03-27 | 412 | 2027-07-20 | 129
Engineering Workshops |  | 2026-03-06 | 2026-03-06 | 25-May-25 A | 2026-03-06 | 2026-03-27 | 183 | 2026-03-27 | 15
A1-PM-EWS-0001 | Engineering Workshops - 30% Model Review |  |  |  | 25-May-25 A |  | 0
A1-PM-EWS-0002 | Engineering Workshops - 60% Model Review |  |  |  | 19-Sep-25 A |  | 0
A1-PM-EWS-0003 | Engineering Workshops - 90% Model Review |  | 2026-03-06 |  | 2026-03-06 |  | 0 | 2026-03-27 | 15
Engineering Interim Milestones |  | 2026-02-20 | 2027-01-21 | 02-Apr-25 A | 2027-01-21 | 2026-03-27 | 412 | 2027-07-20 | 129
General Project Management |  | 2027-01-21 | 2027-01-21 | 30-Apr-25 A | 2027-01-21 | 2027-07-20 | 403 | 2027-07-20 | 129
A1-PM-EIM-0001 | 1.A*-Issue Engineering Procedure. |  |  |  | 30-Apr-25 A |  | 0
A1-PM-EIM-0002 | 8.A*-As Built drawings handover to COMPANY |  | 2027-01-21 |  | 2027-01-21 |  | 0 | 2027-07-20 | 129
Detail Engineering |  | 2026-02-20 | 2026-06-04 | 02-Apr-25 A | 2026-06-04 | 2026-03-27 | 247 | 2027-07-20 | 294
A1-PM-EIM-0036 | 45.B-Design for Turnaround Works |  |  |  | 02-Apr-25 A |  | 0
A1-PM-EIM-0008 | 14.B*-Issue IFC Plot Plans, Equipment Layouts etc. complete |  |  |  | 06-May-25 A |  | 0
A1-PM-EIM-0019 | 25.B-Complete 30% 3D-CAD model review |  |  |  | 25-May-25 A |  | 0
A1-PM-EIM-0009 | 15.B-Utility Consumption Issued for U&O |  |  |  | 20-Jun-25 A |  | 0
A1-PM-EIM-0004 | 10.B-Issue for COMPANY approval all documents for HAZOP / SIL review |  |  |  | 21-Jun-25 A |  | 0
A1-PM-EIM-0025 | 31.B*-Issue 1st MTO and MRs for piping bulk materials |  |  |  | 21-Jun-25 A |  | 0
A1-PM-EIM-0030 | 36.B-Issue first MTO and MRs for electrical bulk materials |  |  |  | 21-Jun-25 A |  | 0
A1-PM-EIM-0032 | 39.B-Issue first MTO and MRs for instrument bulk materials |  |  |  | 21-Jun-25 A |  | 0
A1-PM-EIM-0006 | 12.B-Process design frozen |  |  |  | 18-Aug-25 A |  | 0
A1-PM-EIM-0018 | 24.B-Issue IFC 95% of Civil / Structural drawings etc. for all Buildings. |  |  |  | 01-Sep-25 A |  | 0
A1-PM-EIM-0005 | 11.B-Complete HAZOP/ SIL Review and submit Close Out Report with all actions closed. |  |  |  | 05-Sep-25 A |  | 0
A1-PM-EIM-0013 | 19.B*-Issue MRs for all Major Equipment & Packages for purchase. |  |  |  | 16-Sep-25 A |  | 0
A1-PM-EIM-0020 | 26.B*-Complete 60% 3D-CAD model review |  |  |  | 18-Sep-25 A |  | 0
A1-PM-EIM-0015 | 21.B*-Issue IFC all underground services drawings |  |  |  | 15-Nov-25 A |  | 0
A1-PM-EIM-0003 | 9.B*-Issue Utility demands, associated line sizes and electrical load data and equipment ratings final. |  | 2026-02-20 |  | 2026-02-20 |  | 0 | 2026-03-27 | 25
A1-PM-EIM-0022 | 28.B*-Start issue piping isometrics IFC |  | 2026-02-20 |  | 2026-02-20 |  | 0 | 2026-03-27 | 25
A1-PM-EIM-0010 | 16.B-Effluent Summary & Flare Loads Frozen for U&O |  | 2026-02-24 |  | 2026-02-24 |  | 0 | 2026-03-27 | 23
A1-PM-EIM-0011 | 17.B-Steam Balance Frozen for U&O |  | 2026-02-24 |  | 2026-02-24 |  | 0 | 2026-03-27 | 23
A1-PM-EIM-0026 | 32.B-Issue Intermediate MTO and MR’s for piping bulk materials |  | 2026-02-24 |  | 2026-02-24 |  | 0 | 2026-03-27 | 23
A1-PM-EIM-0021 | 27.B-Complete 90% 3D-CAD model review |  | 2026-03-06 |  | 2026-03-06 |  | 0 | 2026-05-06 | 44
A1-PM-EIM-0016 | 22.B*-Issue IFC all foundation & superstructure drawings for all Equipment & Packages |  | 2026-03-23 |  | 2026-03-23 |  | 0 | 2027-07-20 | 347
A1-PM-EIM-0027 | 33.B-Issue final MTO and MRs for piping bulk materials |  | 2026-04-08 |  | 2026-04-08 |  | 0 | 2026-06-12 | 47
A1-PM-EIM-0007 | 13.B*-Issue IFC PFDs, P&IDs, Data Sheets, Equipment Lists, Line Lists complete incorporating HAZOP comments |  | 2026-04-14 |  | 2026-04-14 |  | 0 | 2027-01-18 | 200
A1-PM-EIM-0012 | 18.B-Issue IFC all Single Line Diagrams, Hazardous Area classification details for all facilities (complete). |  | 2026-04-14 |  | 2026-04-14 |  | 0 | 2027-01-01 | 189
A1-PM-EIM-0028 | 34.B-Establish piping interface details and finalize procedures with COMPANY |  | 2026-04-21 |  | 2026-04-21 |  | 0 | 2026-10-16 | 128
A1-PM-EIM-0033 | 41.B*-Issue IFC Electrical/Instrument layouts, interconnection diagrams etc. including all building control SYSTEMS, HVA |  | 2026-04-21 |  | 2026-04-21 |  | 0 | 2027-01-01 | 183
A1-PM-EIM-0035 | 44.B-Issue Operating, Maintenance and Safety Manual. |  | 2026-04-21 |  | 2026-04-21 |  | 0 | 2027-01-20 | 196
A1-PM-EIM-0014 | 20.B*-Receipt of key VENDOR data (by major equipment) |  | 2026-04-23 |  | 2026-04-23 |  | 0 | 2026-08-14 | 81
A1-PM-EIM-0024 | 30.B-Complete Piping Isometrics IFC |  | 2026-05-01 |  | 2026-05-01 |  | 0 | 2026-05-22 | 15
A1-PM-EIM-0029 | 35.B*-Issue IFC Electrical cable schedules, cable layouts, equipment layouts earthing layouts, lighting layouts, JB deta |  | 2026-05-06 |  | 2026-05-06 |  | 0 | 2026-10-05 | 108
A1-PM-EIM-0034 | 42.B-Finalize and issue IFC all instrumentation loop diagrams. |  | 2026-05-06 |  | 2026-05-06 |  | 0 | 2027-01-01 | 172
A1-PM-EIM-0017 | 23.B-Issue IFC 95% of Civil / Structural drawings for pipe supports, pipe trestles, sleepers etc. complete. |  | 2026-05-14 |  | 2026-05-14 |  | 0 | 2026-06-26 | 31
A1-PM-EIM-0031 | 38.B*-Issue IFC Instrument cable schedules, cable layouts, equipment layouts, JB details, trench details etc. complete |  | 2026-06-03 |  | 2026-06-03 |  | 0 | 2027-01-18 | 164
A1-PM-EIM-0023 | 29.B-Issue 50% Piping Isometrics IFC |  | 2026-06-04 |  | 2026-06-04 |  | 0 | 2027-01-18 | 162
Procurement |  | 2026-02-20 | 2027-01-20 | 21-Feb-25 A | 2027-01-20 | 2026-05-04 | 461 | 2027-07-20 | 129
Procurement Deliverables |  | 2026-02-20 | 2026-02-24 | 03-Mar-25 A | 2026-02-24 | 2026-07-23 | 154 | 2026-07-27 | 109
A1-PM-PRD-0021 | PM-058-Subcontract technical & commercial bid evaluation | 2026-02-20 | 2026-02-20 | 03-Mar-25 A | 28-May-25 A | 2026-07-23 | 5 | 2026-07-23
A1-PM-PRD-0004 | PM-021-Procurement Plan | 2026-02-20 | 2026-02-20 | 25-May-25 A | 15-Jun-25 A | 2026-07-23 | 5 | 2026-07-23
A1-PM-PRD-0005 | PM-022-Procurement Control Log | 2026-02-20 | 2026-02-20 | 21-Jun-25 A | 12-Jul-25 A | 2026-07-23 | 5 | 2026-07-23
A1-PM-PRD-0007 | PM-024-Shipping Forecast | 2026-02-20 | 2026-02-20 | 21-Jun-25 A | 12-Jul-25 A | 2026-07-23 | 5 | 2026-07-23
A1-PM-PRD-0008 | PM-025-Copy of priced and unpriced Purchase Order | 2026-02-20 | 2026-02-20 | 21-Jun-25 A | 12-Jul-25 A | 2026-07-23 | 5 | 2026-07-23
A1-PM-PRD-0009 | PM-026-Vendor Schedules | 2026-02-20 | 2026-02-20 | 21-Jun-25 A | 12-Jul-25 A | 2026-07-23 | 5 | 2026-07-23
A1-PM-PRD-0010 | PM-027-Shipping Progress Report | 2026-02-20 | 2026-02-20 | 21-Jun-25 A | 12-Jul-25 A | 2026-07-23 | 5 | 2026-07-23
A1-PM-PRD-0011 | PM-033-Commercial Bid Analysis | 2026-02-20 | 2026-02-20 | 21-Jun-25 A | 12-Jul-25 A | 2026-07-23 | 5 | 2026-07-23
A1-PM-PRD-0012 | PM-034-Subcontract Award Recommendation | 2026-02-20 | 2026-02-20 | 21-Jun-25 A | 12-Jul-25 A | 2026-07-23 | 5 | 2026-07-23
A1-PM-PRD-0013 | PM-035-Vendor Prequalification's | 2026-02-20 | 2026-02-20 | 21-Jun-25 A | 12-Jul-25 A | 2026-07-23 | 5 | 2026-07-23
A1-PM-PRD-0014 | PM-036-Vendor Technical Queries /Answers | 2026-02-20 | 2026-02-20 | 21-Jun-25 A | 12-Jul-25 A | 2026-07-23 | 5 | 2026-07-23
A1-PM-PRD-0015 | PM-042-Subcontract Bidders List | 2026-02-20 | 2026-02-20 | 21-Jun-25 A | 12-Jul-25 A | 2026-07-23 | 5 | 2026-07-23
A1-PM-PRD-0016 | PM-043-Vendors List / Bidders Lists | 2026-02-20 | 2026-02-20 | 21-Jun-25 A | 12-Jul-25 A | 2026-07-23 | 5 | 2026-07-23
A1-PM-PRD-0022 | PM-059-Subcontract control log | 2026-02-20 | 2026-02-20 | 21-Jun-25 A | 12-Jul-25 A | 2026-07-23 | 5 | 2026-07-23
A1-PM-PRD-0023 | PM-060-Award Recommendation | 2026-02-20 | 2026-02-20 | 21-Jun-25 A | 12-Jul-25 A | 2026-07-23 | 5 | 2026-07-23
A1-PM-PRD-0024 | PM-066-Copy of Bill of Loading | 2026-02-20 | 2026-02-20 | 21-Jun-25 A | 12-Jul-25 A | 2026-07-23 | 5 | 2026-07-23
A1-PM-PRD-0025 | PM-067-Delivery Certificate on Site | 2026-02-20 | 2026-02-20 | 21-Jun-25 A | 12-Jul-25 A | 2026-07-23 | 5 | 2026-07-23
A1-PM-PRD-0026 | PM-068-Subcontract status report | 2026-02-20 | 2026-02-20 | 21-Jun-25 A | 12-Jul-25 A | 2026-07-23 | 5 | 2026-07-23
A1-PM-PRD-0027 | PM-069-Sub contractor performance feed back report | 2026-02-20 | 2026-02-20 | 21-Jun-25 A | 12-Jul-25 A | 2026-07-23 | 5 | 2026-07-23
A1-PM-PRD-0028 | PM-070-Material Status Report | 2026-02-20 | 2026-02-20 | 21-Jun-25 A | 12-Jul-25 A | 2026-07-23 | 5 | 2026-07-23
A1-PM-PRD-0029 | PM-071-Purchasing Status Report | 2026-02-20 | 2026-02-20 | 21-Jun-25 A | 12-Jul-25 A | 2026-07-23 | 5 | 2026-07-23
A1-PM-PRD-0020 | PM-056-Vendor Manufacturing Quality Plan | 2026-02-20 | 2026-02-20 | 21-Jun-25 A | 23-Jul-25 A | 2026-07-23 | 5 | 2026-07-23
A1-PM-PRD-0001 | PM-018-Equipment Delivery and storage Plan | 2026-02-20 | 2026-02-20 | 25-May-25 A | 25-Aug-25 A | 2026-07-23 | 5 | 2026-07-23
A1-PM-PRD-0003 | PM-020-Procurement Procedures | 2026-02-20 | 2026-02-20 | 01-Jun-25 A | 25-Aug-25 A | 2026-07-23 | 5 | 2026-07-23
A1-PM-PRD-0006 | PM-023-Transportation Plan & Procedure | 2026-02-20 | 2026-02-20 | 24-May-25 A | 25-Aug-25 A | 2026-07-23 | 5 | 2026-07-23
A1-PM-PRD-0017 | PM-044-Vendor List | 2026-02-20 | 2026-02-20 | 12-Jun-25 A | 25-Aug-25 A | 2026-07-23 | 5 | 2026-07-23
A1-PM-PRD-0019 | PM-055-Subcontract Pre Qualification | 2026-02-20 | 2026-02-20 | 19-Jun-25 A | 25-Aug-25 A | 2026-07-23 | 5 | 2026-07-23
A1-PM-PRD-0002 | PM-019-Subcontracting Procedure | 2026-02-20 | 2026-02-20 | 25-May-25 A | 02-Sep-25 A | 2026-07-23 | 5 | 2026-07-23
A1-PM-PRD-0018 | PM-051-Copy of unpriced sub contract agreement | 2026-02-20 | 2026-02-20 | 19-Jun-25 A | 02-Sep-25 A | 2026-07-23 | 5 | 2026-07-23
A1-PM-PRD-0030 | PM-072-Vendor Performance feed back report | 2026-02-20 | 2026-02-24 | 25-Oct-25 A | 2026-02-24 | 2026-07-23 | 5 | 2026-07-27 | 109
Procurement Interim Milestones |  | 2026-02-20 | 2027-01-20 | 21-Feb-25 A | 2027-01-20 | 2026-05-04 | 461 | 2027-07-20 | 129
General Project Management |  | 2026-10-18 | 2026-10-18 | 28-Mar-25 A | 2026-10-18 | 2027-01-03 | 320 | 2027-01-03 | 55
A1-PM-PRM-0001 | 1.A*-Issue Procurement Procedures. |  |  |  | 28-Mar-25 A |  | 0
A1-PM-PRM-0002 | 7.A-VENDOR training and visits planned |  | 2026-10-18 |  | 2026-10-18 |  | 0 | 2027-01-03 | 67
Procurement Equipment & Materials |  | 2026-03-19 | 2026-05-13 | 21-Feb-25 A | 2026-05-13 | 2026-06-12 | 221 | 2027-01-20 | 180
A1-PM-PRM-0015 | 62.C-Issue purchase order Piping MTO for Shut Down Works |  |  |  | 21-Feb-25 A |  | 0
A1-PM-PRM-0013 | 60.C-Issue purchase orders for all Shut Down Materials (Piping, Electrical and Instrumentation |  |  |  | 28-Mar-25 A |  | 0
A1-PM-PRM-0003 | 49.C*-Issue purchase order for Compressors Centrifugal / Reciprocating |  |  |  | 30-May-25 A |  | 0
A1-PM-PRM-0004 | 50.C*-Issue purchase orders for Furnaces |  |  |  | 21-Jun-25 A |  | 0
A1-PM-PRM-0012 | 59.C*-Issue first purchase orders for bulk electrical materials |  |  |  | 21-Jun-25 A |  | 0
A1-PM-PRM-0014 | 61.C*-Issue first purchase orders for bulk instrument materials |  |  |  | 21-Jun-25 A |  | 0
A1-PM-PRM-0005 | 51.C*-Issue purchase orders for all remaining Mechanical / Rotating Equipment & Equipment Packages |  |  |  | 01-Sep-25 A |  | 0
A1-PM-PRM-0008 | 55.C*-Issue first purchase order for piping bulk materials |  |  |  | 19-Sep-25 A |  | 0
A1-PM-PRM-0007 | 54.C*-Issue purchase order for all major instrument control SYSTEMS |  |  |  | 21-Nov-25 A |  | 0
A1-PM-PRM-0009 | 56.C-Issue intermediate purchase order for piping bulk materials |  | 2026-03-19 |  | 2026-03-19 |  | 0 | 2026-06-12 | 61
A1-PM-PRM-0011 | 58.C-Issue purchase orders for all field instrument tagged items |  | 2026-03-25 |  | 2026-03-25 |  | 0 | 2027-01-20 | 216
A1-PM-PRM-0010 | 57.C-Issue final purchase order for piping bulk materials |  | 2026-04-22 |  | 2026-04-22 |  | 0 | 2026-06-12 | 37
A1-PM-PRM-0006 | 52.C*-Issue purchase orders for all major electrical Equipment |  | 2026-05-13 |  | 2026-05-13 |  | 0 | 2027-01-20 | 180
Subcontracts |  |  |  | 30-May-25 A | 01-Sep-25 A |  | 257
A1-PM-PRM-0024 | 71.C*-Buildings subcontract award |  |  |  | 30-May-25 A |  | 0
A1-PM-PRM-0016 | 63.C-Piling subcontract award |  |  |  | 01-Jun-25 A |  | 0
A1-PM-PRM-0017 | 64.C*-Civil subcontract award |  |  |  | 15-Jun-25 A |  | 0
A1-PM-PRM-0019 | 66.C*-Mechanical subcontract award |  |  |  | 15-Jun-25 A |  | 0
A1-PM-PRM-0020 | 67.C-Insulation subcontract award |  |  |  | 15-Jun-25 A |  | 0
A1-PM-PRM-0021 | 68.C-Painting subcontract award |  |  |  | 15-Jun-25 A |  | 0
A1-PM-PRM-0022 | 69.C*-Electrical subcontract award |  |  |  | 15-Jun-25 A |  | 0
A1-PM-PRM-0023 | 70.C*-Instrument subcontract award |  |  |  | 15-Jun-25 A |  | 0
A1-PM-PRM-0018 | 65.C-Steel fabrication/erection subcontract award |  |  |  | 01-Sep-25 A |  | 0
Manufacturing & Delivery |  | 2026-02-20 | 2027-01-20 | 20-Mar-25 A | 2027-01-20 | 2026-05-04 | 441 | 2027-07-20 | 129
A1-PM-PRM-0041 | 94.D-Piping MTO for Shut Down Works Delivered to SITE |  |  |  | 20-Mar-25 A |  | 0
A1-PM-PRM-0026 | 77.D*-Furnaces delivered to SITE |  |  |  | 10-Sep-25 A |  | 0
A1-PM-PRM-0033 | 84.D*-Bulk piping materials initial MTO delivered to SITE |  | 2026-02-20 |  | 2026-02-20 |  | 0 | 2026-05-06 | 95
A1-PM-PRM-0025 | 76.D*-Compressors Centrifugal / Reciprocating delivered to SITE |  | 2026-03-03 |  | 2026-03-03 |  | 0 | 2026-05-04 | 53
A1-PM-PRM-0034 | 85.D*-Bulk piping materials intermediate MTO delivered to SITE |  | 2026-04-18 |  | 2026-04-18 |  | 0 | 2026-07-15 | 77
A1-PM-PRM-0035 | 86.D*-Bulk piping materials final MTO delivered to SITE |  | 2026-08-22 |  | 2026-08-22 |  | 0 | 2026-10-07 | 41
A1-PM-PRM-0029 | 80.D*-HVAC, Fire Detection and Fire Fighting SYSTEMS for all buildings delivered to SITE |  | 2026-08-26 |  | 2026-08-26 |  | 0 | 2026-12-28 | 106
A1-PM-PRM-0036 | 88.D-Bulk electrical materials final MTO delivered to SITE |  | 2026-08-31 |  | 2026-08-31 |  | 0 | 2026-12-10 | 127
A1-PM-PRM-0027 | 78.D*-Remaining Mechanical / Rotating Equipment & Equipment Packages delivered to SITE |  | 2026-09-13 |  | 2026-09-13 |  | 0 | 2027-07-20 | 388
A1-PM-PRM-0037 | 90.D-Bulk instrument materials final MTO delivered to SITE |  | 2026-09-24 |  | 2026-09-24 |  | 0 | 2026-10-07 | 16
A1-PM-PRM-0032 | 83.D-Field instrument tagged items delivered to SITE |  | 2026-09-27 |  | 2026-09-27 |  | 0 | 2026-12-10 | 93
A1-PM-PRM-0028 | 79.D*-All major electrical Equipment delivered to SITE |  | 2026-09-29 |  | 2026-09-29 |  | 0 | 2027-01-03 | 120
A1-PM-PRM-0030 | 81.D*-Major instrument control SYSTEMS delivered to SITE |  | 2026-09-29 |  | 2026-09-29 |  | 0 | 2026-12-10 | 90
A1-PM-PRM-0031 | 82.D-Instrument Control SYSTEMS for CCB delivered to SITE |  | 2026-09-29 |  | 2026-09-29 |  | 0 | 2026-12-10 | 90
A1-PM-PRM-0038 | 91.D-Insurance spares for all equipment & packages arrival at SITE and handover to COMPANY |  | 2027-01-20 |  | 2027-01-20 |  | 0 | 2027-07-20 | 155
A1-PM-PRM-0039 | 92.D*-Operating Spares for all item’s arrival at SITE and handover to COMPANY. |  | 2027-01-20 |  | 2027-01-20 |  | 0 | 2027-07-20 | 155
A1-PM-PRM-0040 | 93.D*-All VENDOR Documentation Handed over to COMPANY |  | 2027-01-20 |  | 2027-01-20 |  | 0 | 2027-07-20 | 155
Construction |  | 2026-02-20 | 2027-03-10 | 10-Mar-25 A | 2027-03-10 | 2026-07-30 | 489 | 2027-07-20 | 94
Construction Deliverables |  | 2026-02-20 | 2027-03-10 | 10-Mar-25 A | 2027-03-10 | 2026-08-14 | 469 | 2027-04-21 | 30
A1-PM-COD-0020 | CS-020-Test Certificate | 2026-02-20 | 2026-02-20 | 10-Mar-25 A | 26-Mar-25 A | 2026-08-14 | 5 | 2026-08-14
A1-PM-COD-0028 | CS-028-Construction execution methodologies (work methods) | 2026-02-20 | 2026-02-20 | 01-Apr-25 A | 07-Apr-25 A | 2026-08-22 | 15 | 2026-08-22
A1-PM-COD-0007 | CS-007-Time Schedule / Programme | 2026-02-20 | 2026-02-20 | 19-Mar-25 A | 19-Jun-25 A | 2026-08-14 | 5 | 2026-08-14
A1-PM-COD-0018 | CS-018-Quality Assurance Docs | 2026-02-20 | 2026-02-20 | 02-Jun-25 A | 19-Jun-25 A | 2026-08-14 | 5 | 2026-08-14
A1-PM-COD-0013 | CS-013-Locking List | 2026-02-20 | 2026-02-20 | 02-Jun-25 A | 20-Jun-25 A | 2026-08-14 | 5 | 2026-08-14
A1-PM-COD-0027 | CS-027-Temporary facilities plan | 2026-02-20 | 2026-02-20 | 21-Jun-25 A | 30-Jun-25 A | 2026-08-14 | 5 | 2026-08-14
A1-PM-COD-0029 | CS-029-Logistics plan | 2026-02-20 | 2026-02-20 | 21-Jun-25 A | 30-Jun-25 A | 2026-08-14 | 5 | 2026-08-14
A1-PM-COD-0004 | CS-004-Procedures | 2026-02-20 | 2026-02-20 | 21-Jun-25 A | 12-Jul-25 A | 2026-08-14 | 5 | 2026-08-14
A1-PM-COD-0006 | CS-006-Method Statements | 2026-02-20 | 2026-02-20 | 21-Jun-25 A | 12-Jul-25 A | 2026-08-14 | 5 | 2026-08-14
A1-PM-COD-0008 | CS-008-Lifting | 2026-02-20 | 2026-02-20 | 21-Jun-25 A | 12-Jul-25 A | 2026-08-14 | 5 | 2026-08-14
A1-PM-COD-0009 | CS-009-Site plans | 2026-02-20 | 2026-02-20 | 21-Jun-25 A | 12-Jul-25 A | 2026-08-14 | 5 | 2026-08-14
A1-PM-COD-0010 | CS-010-Demolition plan | 2026-02-20 | 2026-02-20 | 21-Jun-25 A | 12-Jul-25 A | 2026-08-14 | 5 | 2026-08-14
A1-PM-COD-0011 | CS-011-Temporary Works | 2026-02-20 | 2026-02-20 | 21-Jun-25 A | 12-Jul-25 A | 2026-08-14 | 5 | 2026-08-14
A1-PM-COD-0012 | CS-012-label | 2026-02-20 | 2026-02-20 | 21-Jun-25 A | 12-Jul-25 A | 2026-08-14 | 5 | 2026-08-14
A1-PM-COD-0014 | CS-014-Technical Bid Analysis | 2026-02-20 | 2026-02-20 | 21-Jun-25 A | 12-Jul-25 A | 2026-08-14 | 5 | 2026-08-14
A1-PM-COD-0032 | CS-032-Camp and Accommodation Plan | 2026-02-20 | 2026-02-20 | 21-Jun-25 A | 12-Jul-25 A | 2026-08-14 | 5 | 2026-08-14
A1-PM-COD-0026 | CS-026-Civil Specifications | 2026-02-20 | 2026-02-20 | 21-Jun-25 A | 31-Jul-25 A | 2026-08-14 | 5 | 2026-08-14
A1-PM-COD-0025 | CS-025-Electrical Specifications | 2026-02-20 | 2026-02-20 | 21-Jun-25 A | 20-Aug-25 A | 2026-08-14 | 5 | 2026-08-14
A1-PM-COD-0003 | CS-003-Execution Plan | 2026-02-20 | 2026-02-20 | 25-May-25 A | 15-Nov-25 A | 2026-08-14 | 5 | 2026-08-14
A1-PM-COD-0019 | CS-019-HSE | 2026-02-20 | 2026-02-20 | 01-Oct-25 A | 18-Dec-25 A | 2026-08-14 | 5 | 2026-08-14
A1-PM-COD-0017 | CS-017-Check List | 2026-02-20 | 2026-02-20 | 15-Oct-25 A | 19-Dec-25 A | 2026-08-14 | 5 | 2026-08-14
A1-PM-COD-0021 | CS-021-Quality Control Procedure | 2026-02-20 | 2026-02-20 | 01-Oct-25 A | 19-Dec-25 A | 2026-08-14 | 5 | 2026-08-14
A1-PM-COD-0022 | CS-022-Construction Strategies | 2026-02-20 | 2026-02-20 | 21-Jun-25 A | 19-Dec-25 A | 2026-08-14 | 5 | 2026-08-14
A1-PM-COD-0023 | CS-023-Concession Requests | 2026-02-20 | 2026-02-20 | 01-Sep-25 A | 19-Dec-25 A | 2026-08-14 | 5 | 2026-08-14
A1-PM-COD-0024 | CS-024-Non-Conformance Requests | 2026-02-20 | 2026-02-20 | 01-Sep-25 A | 19-Dec-25 A | 2026-08-14 | 5 | 2026-08-14
A1-PM-COD-0030 | CS-030-mobilisation/demobilisation plan | 2026-02-20 | 2026-02-20 | 01-Jul-25 A | 19-Dec-25 A | 2026-08-14 | 5 | 2026-08-14
A1-PM-COD-0034 | CS-034-Field Construction Execution plan | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 19-Dec-25 A | 2027-02-08 | 21 | 2027-02-08
A1-PM-COD-0005 | CS-005-Field instructions | 2026-02-20 | 2026-02-20 | 01-Sep-25 A | 2026-02-20 | 2026-08-14 | 5 | 2026-08-17 | 126
A1-PM-COD-0016 | CS-016-Punch List | 2026-02-20 | 2026-02-20 | 21-Jun-25 A | 2026-02-20 | 2026-08-14 | 5 | 2026-08-17 | 126
A1-PM-COD-0033 | CS-033-Construction logistic plan | 2026-02-20 | 2026-02-23 | 01-Aug-25 A | 2026-02-23 | 2026-08-14 | 5 | 2026-08-17 | 126
A1-PM-COD-0031 | CS-031-Construction Cleanliness Plant | 2026-02-20 | 2026-02-24 | 01-Aug-25 A | 2026-02-24 | 2026-08-14 | 5 | 2026-08-19 | 126
A1-PM-COD-0015 | CS-015-Insulation / Painting / Fire Proofing | 2026-02-20 | 2026-02-26 | 01-Apr-25 A | 2026-02-26 | 2026-08-14 | 5 | 2026-08-21 | 126
A1-PM-COD-0001 | CS-001-QC Dossier | 2027-01-21 | 2027-01-27 | 2027-01-21 | 2027-01-27 | 2027-03-04 | 5 | 2027-03-10 | 30
A1-PM-COD-0002 | CS-002-Construction Handover Dossier ( ALL Discipline wise) | 2027-03-08 | 2027-03-10 | 22-Jun-25 A | 2027-03-10 | 2027-04-19 | 5 | 2027-04-21 | 30
Construction Interim Milestones |  | 2026-04-09 | 2027-02-21 | 25-Mar-25 A | 2027-02-21 | 2026-07-30 | 456 | 2027-07-20 | 107
General Project Management |  | 2026-04-14 | 2026-04-14 | 31-May-25 A | 2026-04-14 | 2026-12-09 | 212 | 2027-02-08 | 215
A1-PM-CIM-0004 | 3.A-Tie-in/Shutdown philosophy etc. (Excluding Hydrotesting, Drying, Purging, PRE-COMMISSIONING and COMMISSIONING Proced |  |  |  | 31-May-25 A |  | 0
A1-PM-CIM-0001 | 3.A-Issue Construction Execution Plan (Excluding Hydrotesting, Drying, Purging, PRE-COMMISSIONING and COMMISSIONING Proc |  |  |  | 21-Jun-25 A |  | 0
A1-PM-CIM-0002 | 3.A-Issue Construction Execution Procedures (Excluding Hydrotesting, Drying, Purging, PRE-COMMISSIONING and COMMISSIONIN |  |  |  | 21-Jun-25 A |  | 0
A1-PM-CIM-0003 | 3.A-Issue Construction Execution Method Statements (Excluding Hydrotesting, Drying, Purging, PRE-COMMISSIONING and COMMI |  |  |  | 21-Jun-25 A |  | 0
A1-PM-CIM-0005 | 4.A-Issue Hydrotesting Procedures and plan (Final). |  | 2026-04-14 |  | 2026-04-14 |  | 0 | 2027-02-08 | 215
A1-PM-CIM-0006 | 4.A-Issue Drying Procedures and plan (Final). |  | 2026-04-14 |  | 2026-04-14 |  | 0 | 2027-02-08 | 215
A1-PM-CIM-0007 | 4.A-Issue Purging Procedures and plan (Final). |  | 2026-04-14 |  | 2026-04-14 |  | 0 | 2027-02-08 | 215
A1-PM-CIM-0008 | 4.A-Issue PRECOMMISSIONING Procedures and plan (Final). |  | 2026-04-14 |  | 2026-04-14 |  | 0 | 2027-02-08 | 215
A1-PM-CIM-0009 | 4.A-Issue COMMISSIONING Procedures and plan (Final). |  | 2026-04-14 |  | 2026-04-14 |  | 0 | 2027-02-08 | 215
A1-PM-CIM-0010 | 4.A-Issue Handover Procedures and plan (Final). |  | 2026-04-14 |  | 2026-04-14 |  | 0 | 2026-12-09 | 172
Construction & Commissioning |  | 2026-04-09 | 2026-12-21 | 25-Mar-25 A | 2026-12-21 | 2026-07-30 | 412 | 2027-01-20 | 22
A1-PM-CIM-0024 | 113.E-Start Piping Prefabrication |  |  |  | 25-Mar-25 A |  | 0
A1-PM-CIM-0028 | 117.E-Start Piping erection |  |  |  | 15-Apr-25 A |  | 0
A1-PM-CIM-0034 | 123.E-Complete all piping tie-ins (Including Interface Tie-Ins) |  |  |  | 20-May-25 A |  | 0
A1-PM-CIM-0011 | 94.E*-Commence on SITE |  |  |  | 31-May-25 A |  | 0
A1-PM-CIM-0013 | 96.E-Complete SITE preparation and grading works |  |  |  | 21-Jun-25 A |  | 0
A1-PM-CIM-0012 | 95.E-Complete Construction of Temporary Facilities at SITE. |  |  |  | 15-Nov-25 A |  | 0
A1-PM-CIM-0015 | 101.E-Complete all Piperack foundations |  | 2026-04-09 |  | 2026-04-09 |  | 0 | 2027-01-20 | 245
A1-PM-CIM-0017 | 103.E-Complete installation of all underground electrical cabling |  | 2026-05-07 |  | 2026-05-07 |  | 0 | 2026-12-09 | 185
A1-PM-CIM-0019 | 105.E-Trench for data highway cables SIS to Control Building available |  | 2026-05-07 |  | 2026-05-07 |  | 0 | 2027-01-20 | 221
A1-PM-CIM-0039 | 128.E-Trench for Main Electrical Feeder cables Main to Unit Substations available |  | 2026-05-07 |  | 2026-05-07 |  | 0 | 2026-08-15 | 85
A1-PM-CIM-0021 | 110.E-Complete installation of Turbines/Compressors |  | 2026-05-18 |  | 2026-05-18 |  | 0 | 2027-01-20 | 212
A1-PM-CIM-0023 | 112.E-Completion of Heavy Lifts |  | 2026-05-18 |  | 2026-05-18 |  | 0 | 2026-07-30 | 63
A1-PM-CIM-0018 | 104.E-Complete installation of all underground instrument cabling |  | 2026-06-20 |  | 2026-06-20 |  | 0 | 2026-12-09 | 149
A1-PM-CIM-0014 | 100.E-Complete construction of foundations for all remaining mechanical, rotating & packaged equipment |  | 2026-06-25 |  | 2026-06-25 |  | 0 | 2026-08-22 | 48
A1-PM-CIM-0016 | 102.E-Complete all underground piping |  | 2026-07-19 |  | 2026-07-19 |  | 0 | 2027-01-20 | 159
A1-PM-CIM-0020 | 106.E-Complete installation of steel structural works for shelters, and Package Units etc. |  | 2026-09-10 |  | 2026-09-10 |  | 0 | 2027-01-20 | 113
A1-PM-CIM-0037 | 126.E-Complete installation of platforms, walkways, crossovers etc. |  | 2026-09-10 |  | 2026-09-10 |  | 0 | 2027-01-20 | 113
A1-PM-CIM-0025 | 114.E-Complete prefabrication 50% piping. |  | 2026-09-17 |  | 2026-09-17 |  | 0 | 2027-01-20 | 107
A1-PM-CIM-0041 | 130.E-Complete Street lighting |  | 2026-10-03 |  | 2026-10-03 |  | 0 | 2027-01-20 | 94
A1-PM-CIM-0026 | 115.E-Complete prefabrication 98% piping |  | 2026-10-05 |  | 2026-10-05 |  | 0 | 2027-01-20 | 92
A1-PM-CIM-0036 | 125.E-Complete Heat Tracing, Insulation, Fire Proofing and Painting works |  | 2026-10-05 |  | 2026-10-05 |  | 0 | 2027-01-20 | 92
A1-PM-CIM-0038 | 127.E-Complete installation of all Substation electrical equipment |  | 2026-10-18 |  | 2026-10-18 |  | 0 | 2027-01-20 | 82
A1-PM-CIM-0027 | 116.E-Complete installation of pipe supports, sleepers, trestles etc. |  | 2026-10-22 |  | 2026-10-22 |  | 0 | 2027-01-20 | 77
A1-PM-CIM-0029 | 118.E-Piping erection 50% Complete |  | 2026-10-22 |  | 2026-10-22 |  | 0 | 2027-01-20 | 77
A1-PM-CIM-0030 | 119.E-Piping Erection 100% complete |  | 2026-10-22 |  | 2026-10-22 |  | 0 | 2027-01-20 | 77
A1-PM-CIM-0022 | 111.E-Complete installation of all remaining mechanical, rotating & packaged equipment |  | 2026-11-02 |  | 2026-11-02 |  | 0 | 2027-01-20 | 68
A1-PM-CIM-0031 | 120.E-Commence hydrotesting of Pipework |  | 2026-11-16 |  | 2026-11-16 |  | 0 | 2027-01-20 | 56
A1-PM-CIM-0032 | 121.E-Piping Hydrotesting 50% complete |  | 2026-11-16 |  | 2026-11-16 |  | 0 | 2027-01-20 | 56
A1-PM-CIM-0033 | 122.E-Piping Hydrotesting 100% complete |  | 2026-12-03 |  | 2026-12-03 |  | 0 | 2027-01-20 | 41
A1-PM-CIM-0035 | 124.E-Complete Fire Water System including tanks, pumps and piping works up to Mechanical Completion. |  | 2026-12-03 |  | 2026-12-03 |  | 0 | 2027-01-20 | 41
A1-PM-CIM-0040 | 129.E-Complete electrical cabling and termination works (field works) for all plant facilities including continuity chec |  | 2026-12-21 |  | 2026-12-21 |  | 0 | 2027-01-20 | 26
Eelectrical |  | 2027-01-20 | 2027-02-21 | 2027-01-20 | 2027-02-21 | 2027-04-21 | 22 | 2027-07-20 | 107
A1-PM-CIM-0042 | 131.E-Power from TRANSCO (Needs) |  | 2027-01-20 |  | 2027-01-20 |  | 0 | 2027-07-20 | 226
A1-PM-CIM-0043 | 134.E-Complete motor run |  | 2027-02-21 |  | 2027-02-21 |  | 0 | 2027-04-21 | 51
Instrumentation |  | 2026-11-08 | 2026-12-21 | 2026-11-08 | 2026-12-21 | 2027-04-21 | 37 | 2027-04-21 | 104
A1-PM-CIM-0044 | 135.E-Control System Cables including Fiber opticinstalled and tested |  | 2026-11-08 |  | 2026-11-08 |  | 0 | 2027-04-21 | 141
A1-PM-CIM-0045 | 136.E-Complete instrumentation system loop checks and other PRE-COMMISSIONING checks |  | 2026-12-21 |  | 2026-12-21 |  | 0 | 2027-04-21 | 104
Mechanical Completion & Ready for START UP |  | 2027-01-20 | 2027-01-20 | 2027-01-20 | 2027-01-20 | 2027-07-20 | 0 | 2027-07-20 | 181
A1-PM-CIM-0046 | 138.F-Mechanical Completion |  | 2027-01-20 |  | 2027-01-20 |  | 0 | 2027-07-20 | 226
Construction Workshops |  | 2026-02-20 | 2026-02-20 | 27-Aug-25 A | 29-Aug-25 A | 2026-12-22 | 25 | 2026-12-22
A1-PM-CWS-0001 | Constructabilty Workshop | 2026-02-20 | 2026-02-20 | 27-Aug-25 A | 27-Aug-25 A | 2026-12-22 | 5 | 2026-12-22
A1-PM-CWS-0002 | SIMOPS Workshop | 2026-02-20 | 2026-02-20 | 28-Aug-25 A | 29-Aug-25 A | 2026-12-22 | 5 | 2026-12-22
Commissioning |  | 2026-02-20 | 2027-07-20 | 01-Aug-25 A | 2027-07-20 | 2026-08-12 | 433 | 2027-07-20 | 0
Commissioning Deliverables |  | 2026-02-20 | 2026-07-10 | 01-Aug-25 A | 2026-07-10 | 2026-08-12 | 166 | 2026-12-30 | 124
A1-PM-CMD-0001 | CM-001-Performance Test Run Procedure | 2026-02-20 | 2026-03-06 | 01-Aug-25 A | 2026-03-06 | 2026-08-12 | 15 | 2026-08-26 | 124
A1-PM-CMD-0002 | CM-002-Performance Test Run Report | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-27 | 2026-08-27 | 15 | 2026-09-16 | 124
A1-PM-CMD-0003 | CM-003-Commissioning Procedures | 2026-03-27 | 2026-04-17 | 2026-03-27 | 2026-04-17 | 2026-09-17 | 15 | 2026-10-07 | 124
A1-PM-CMD-0004 | CM-004-Pre-Commisioning & Commissioning Schedule | 2026-04-17 | 2026-05-08 | 2026-04-17 | 2026-05-08 | 2026-10-08 | 15 | 2026-10-28 | 124
A1-PM-CMD-0005 | CM-005-Pre-Commisioning & Commissioning systems identification drawings (P&IDs, single line diagram, etc) | 2026-05-08 | 2026-05-29 | 2026-05-08 | 2026-05-29 | 2026-10-29 | 15 | 2026-11-18 | 124
A1-PM-CMD-0006 | CM-006-Pre- Commissioning Procedure | 2026-05-29 | 2026-06-19 | 2026-05-29 | 2026-06-19 | 2026-11-19 | 15 | 2026-12-09 | 124
A1-PM-CMD-0007 | CM-007-Pre-Commisioning & Commissioning Method of Statements | 2026-06-19 | 2026-07-10 | 2026-06-19 | 2026-07-10 | 2026-12-10 | 15 | 2026-12-30 | 124
Commissioning Interim Milestones |  | 2026-09-14 | 2027-07-20 | 2026-09-14 | 2027-07-20 | 2027-04-21 | 222 | 2027-07-20 | 0
General Project Management |  | 2027-01-20 | 2027-01-21 | 2027-01-20 | 2027-01-21 | 2027-04-21 | 0 | 2027-04-21 | 65
A1-PM-CMM-0001 | 6.A-Training program for COMPANY staff issued to COMPANY for APPROVAL |  | 2027-01-20 |  | 2027-01-20 |  | 0 | 2027-04-21 | 114
A1-PM-CMM-0006 | 5.A-Issue SYSTEMS definition IFC & SYSTEMS completion Schedule |  | 2027-01-21 |  | 2027-01-21 |  | 0 | 2027-04-21 | 65
Mechanical Completion & Ready for START UP |  | 2026-09-14 | 2027-07-20 | 2026-09-14 | 2027-07-20 | 2027-07-20 | 222 | 2027-07-20 | 0
A1-PM-CMM-0004 | 143.F-Issue "AS BUILT STATUS”
operating/Maintenance & Safety Manual | 0 |  | 2027-07-20 |  | 2026-09-14 | 2026-09-14 |  | 222
A1-PM-CMM-0003 | 142.F-Commercial Production |  | 2027-04-14 |  | 2027-04-14 |  | 0 | 2027-07-20 | 83
A1-PM-CMM-0002 | 145.F-Ready for Start-Up |  | 2027-04-22 |  | 2027-04-22 |  | 0 | 2027-07-20 | 64
A1-PM-CMM-0005 | 144.F-PROVISIONAL ACCEPTANCE CERTIFICATE |  | 2027-07-20 |  | 2027-07-20 |  | 0 | 2027-07-20 | 0
HSE Management |  | 2026-02-20 | 2026-09-25 | 17-Feb-25 A | 2026-09-25 | 2026-03-02 | 419 | 2027-01-20 | 84
HSE Deliverables |  | 2026-02-20 | 2026-04-21 | 17-Feb-25 A | 2026-04-21 | 2026-04-02 | 306 | 2026-12-09 | 167
A1-PM-HSD-0001 | S-001-Procedures & Management of Change | 2026-02-20 | 2026-02-20 | 17-Feb-25 A | 03-Mar-25 A | 2026-04-02 | 5 | 2026-04-02
A1-PM-HSD-0014 | S-014-Bill of material | 2026-02-20 | 2026-02-20 | 02-Jun-25 A | 09-Jun-25 A | 2026-08-21 | 5 | 2026-08-21
A1-PM-HSD-0015 | S-015-Safety Schedule / Sheets | 2026-02-20 | 2026-02-20 | 09-Jun-25 A | 20-Jun-25 A | 2026-09-04 | 5 | 2026-09-04
A1-PM-HSD-0007 | S-007-Project Construction HSE Plan / House Keeping Plan | 2026-02-20 | 2026-02-20 | 10-Jun-25 A | 11-Jul-25 A | 2026-12-09 | 30 | 2026-12-09
A1-PM-HSD-0005 | S-005-Site Plans / Plot Plans / Key Plans | 2026-02-20 | 2026-02-20 | 21-Jun-25 A | 12-Jul-25 A | 2026-09-04 | 5 | 2026-09-04
A1-PM-HSD-0006 | S-006-Overall Fire Water & Ringman Header Layout | 2026-02-20 | 2026-02-20 | 21-Jun-25 A | 12-Jul-25 A | 2026-09-04 | 5 | 2026-09-04
A1-PM-HSD-0009 | S-009-HSE Layouts | 2026-02-20 | 2026-02-20 | 21-Jun-25 A | 12-Jul-25 A | 2026-09-04 | 5 | 2026-09-04
A1-PM-HSD-0016 | S-016-Technical Bid Analysis | 2026-02-20 | 2026-02-20 | 21-Jun-25 A | 12-Jul-25 A | 2026-09-04 | 5 | 2026-09-04
A1-PM-HSD-0030 | S-030-Risk Assessment | 2026-02-20 | 2026-02-20 | 21-Jun-25 A | 12-Jul-25 A | 2026-08-21 | 5 | 2026-08-21
A1-PM-HSD-0034 | S-034-Specifications | 2026-02-20 | 2026-02-20 | 21-Jun-25 A | 12-Jul-25 A | 2026-08-21 | 5 | 2026-08-21
A1-PM-HSD-0021 | S-021-HAZOP / SIL (LOPA) Reports |  |  |  | 18-Jul-25 A |  | 0
A1-PM-HSD-0018 | S-018-Equipment List | 2026-02-20 | 2026-02-20 | 21-Jun-25 A | 21-Jul-25 A | 2026-09-04 | 5 | 2026-09-04
A1-PM-HSD-0031 | S-031-Process Philosophies & HSE Plan | 2026-02-20 | 2026-02-20 | 14-Jul-25 A | 13-Aug-25 A | 2026-12-09 | 30 | 2026-12-09
A1-PM-HSD-0032 | S-032-Philosophies | 2026-02-20 | 2026-02-20 | 14-Aug-25 A | 19-Aug-25 A | 2026-08-21 | 5 | 2026-08-21
A1-PM-HSD-0033 | S-033-Data sheets (ALL Type of Safety Data sheets) | 2026-02-20 | 2026-02-20 | 20-Aug-25 A | 26-Aug-25 A | 2026-08-21 | 5 | 2026-08-21
A1-PM-HSD-0022 | S-022-Hazard Study / Fire Protection Design Study / Noise Vibration Study/ SIMOPS Study | 2026-02-20 | 2026-02-20 | 11-Aug-25 A | 29-Aug-25 A | 2026-09-04 | 5 | 2026-09-04
A1-PM-HSD-0003 | S-003-HSE Requirements | 2026-02-20 | 2026-02-20 | 03-Mar-25 A | 06-Sep-25 A | 2026-09-04 | 5 | 2026-09-04
A1-PM-HSD-0029 | S-029-COSHH Assessments | 2026-04-17 | 2026-04-17 | 01-Aug-25 A | 25-Sep-25 A | 2026-09-04 | 5 | 2026-09-04
A1-PM-HSD-0039 | S-039-Waste Management Plan | 2026-02-20 | 2026-02-20 | 25-May-25 A | 06-Jan-26 A | 2026-04-02 | 5 | 2026-04-02
A1-PM-HSD-0002 | S-002-Requisition / Supply Specifications/ Technical Specifications | 2026-02-20 | 2026-02-20 | 01-Aug-25 A | 2026-02-20 | 2026-08-21 | 5 | 2026-08-21 | 130
A1-PM-HSD-0004 | S-004-Fire Fighting Diagram / Fire Protection Diagram | 2026-02-20 | 2026-02-20 | 01-Aug-25 A | 2026-02-20 | 2026-09-04 | 5 | 2026-09-04 | 140
A1-PM-HSD-0008 | S-008-Fire Proofing Zone layout (Plant / Area Wise) | 2026-02-20 | 2026-02-20 | 01-Aug-25 A | 2026-02-20 | 2026-09-04 | 5 | 2026-09-04 | 140
A1-PM-HSD-0010 | S-010-Hazardous area Layouts | 2026-02-20 | 2026-02-20 | 22-Jul-25 A | 2026-02-20 | 2026-09-04 | 5 | 2026-09-04 | 140
A1-PM-HSD-0011 | S-011-Fire Exposure Envelop Drawings / Heat Flux Boundary Drawings | 2026-02-20 | 2026-02-20 | 01-Aug-25 A | 2026-02-20 | 2026-09-04 | 5 | 2026-09-04 | 140
A1-PM-HSD-0012 | S-012-Fire Alarm Drawings (Plant) | 2026-02-20 | 2026-02-20 | 01-Aug-25 A | 2026-02-20 | 2026-09-04 | 5 | 2026-09-04 | 140
A1-PM-HSD-0013 | S-013-Fire Alarm Drawings (Building) | 2026-02-20 | 2026-02-20 | 01-Aug-25 A | 2026-02-20 | 2026-09-04 | 5 | 2026-09-04 | 140
A1-PM-HSD-0017 | S-017-Hazard and Effect Register / HSECES Register/ HSE Critical Activities | 2026-02-20 | 2026-02-20 | 01-Aug-25 A | 2026-02-20 | 2026-09-04 | 5 | 2026-09-04 | 140
A1-PM-HSD-0023 | S-023-Quality Assurance Docs | 2026-02-20 | 2026-02-20 | 05-Aug-25 A | 2026-02-20 | 2026-09-04 | 5 | 2026-09-04 | 140
A1-PM-HSD-0019 | S-019-Fire and Safety Calculations / Explosion Over Pressure Calculations / Hydraulic Calculation | 2026-02-20 | 2026-02-23 | 01-Aug-25 A | 2026-02-23 | 2026-09-04 | 5 | 2026-09-07 | 140
A1-PM-HSD-0020 | S-020-Hydraulic Calculations Report | 2026-02-20 | 2026-02-23 | 04-Aug-25 A | 2026-02-23 | 2026-09-04 | 5 | 2026-09-07 | 140
A1-PM-HSD-0026 | S-026-Environmental / Effluent Disposal System/ Gas Dispersion /Environmental Pollution Reports / Fugitive Emissions Rep | 2026-02-20 | 2026-02-23 | 04-Aug-25 A | 2026-02-23 | 2026-09-04 | 5 | 2026-09-07 | 140
A1-PM-HSD-0028 | S-028-QRA Reports | 2026-02-20 | 2026-02-23 | 05-Aug-25 A | 2026-02-23 | 2026-09-04 | 5 | 2026-09-07 | 140
A1-PM-HSD-0036 | S-036-Safety Equipment and safety Routes Layout | 2026-02-20 | 2026-02-23 | 04-Aug-25 A | 2026-02-23 | 2026-08-21 | 5 | 2026-08-24 | 130
A1-PM-HSD-0024 | S-024-Manufacturing Data Report | 2026-02-20 | 2026-02-24 | 04-Aug-25 A | 2026-02-24 | 2026-09-04 | 5 | 2026-09-08 | 140
A1-PM-HSD-0025 | S-025-Installation, Operation and Maintenance | 2026-02-20 | 2026-02-24 | 01-Aug-25 A | 2026-02-24 | 2026-09-04 | 5 | 2026-09-08 | 140
A1-PM-HSD-0027 | S-027-HSE Report / Close out Report/Atmospheric Relief System Report/ HSE- Safety Reviews | 2026-02-20 | 2026-02-24 | 05-Aug-25 A | 2026-02-24 | 2026-09-04 | 5 | 2026-09-08 | 140
A1-PM-HSD-0035 | S-035-Ergonomic Study/ Human Factor Engineering / Assessment | 2026-02-20 | 2026-02-24 | 02-Aug-25 A | 2026-02-24 | 2026-08-21 | 5 | 2026-08-25 | 130
A1-PM-HSD-0037 | S-037-PHSER and Close Out Report | 2026-02-24 | 2026-03-02 | 2026-02-24 | 2026-03-02 | 2026-08-25 | 5 | 2026-08-31 | 130
A1-PM-HSD-0038 | S-038-List of Applicable Regulatory Requirements | 2026-03-03 | 2026-03-09 | 2026-03-03 | 2026-03-09 | 2026-09-01 | 5 | 2026-09-07 | 130
A1-PM-HSD-0040 | S-040-HSEIA Screening/ HSEIA Report/ HSEIA Dossier | 2026-04-14 | 2026-04-21 | 2026-04-14 | 2026-04-21 | 2026-09-01 | 5 | 2026-09-07 | 100
A1-PM-HSD-0041 | S-041-HSE deliverables as per HSE-RM-ST02 EPC deliverable requirements; not limited to : Building Fire and Safety revie | 2026-04-17 | 2026-04-21 | 01-Aug-25 A | 2026-04-21 | 2026-09-04 | 5 | 2026-09-07 | 100
HSE Studies |  | 2026-02-20 | 2026-09-25 | 01-May-25 A | 2026-09-25 | 2026-03-02 | 319 | 2027-01-20 | 84
HAZID/ENVID/OHID |  | 2026-02-20 | 2026-03-16 | 01-May-25 A | 2026-03-16 | 2026-03-02 | 181 | 2026-08-31 | 120
A58780 | HAZID / ENVID / OHID Workshop | 2026-02-20 | 2026-02-20 | 01-May-25 A | 10-May-25 A | 2026-03-02 | 11 | 2026-03-02
A60330 | HAZID / ENVID / OHID /_IFR | 2026-02-20 | 2026-02-20 | 11-May-25 A | 20-May-25 A | 2026-08-07 | 11 | 2026-08-07
A58790 | HAZID / ENVID / OHID /_RCC | 2026-02-20 | 2026-02-20 | 26-May-25 A | 01-Sep-25 A | 2026-08-07 | 17 | 2026-08-07
A58800 | HAZID / ENVID / OHID /_IFA | 2026-02-20 | 2026-02-20 | 02-Sep-25 A | 08-Sep-25 A | 2026-08-07 | 17 | 2026-08-07
A58810 | HAZID / ENVID / OHID /_RCA | 2026-02-20 | 2026-02-20 | 15-Dec-25 A | 22-Dec-25 A | 2026-08-07 | 17 | 2026-08-07
A58820 | HAZID / ENVID / OHID /_IFD/IFC | 2026-02-20 | 2026-03-16 | 2026-02-20 | 2026-03-16 | 2026-08-07 | 17 | 2026-08-31 | 120
Inherent Safer Design Review |  | 2026-02-20 | 2026-04-08 | 23-Jul-25 A | 2026-04-08 | 2026-12-04 | 164 | 2027-01-20 | 205
A59430 | Inherent Safer Design Review Preparation | 2026-02-20 | 2026-02-20 | 23-Jul-25 A | 31-Jul-25 A | 2026-12-04 | 11 | 2026-12-04
A60460 | Inherent Safer Design Review_IFR | 2026-02-20 | 2026-02-20 | 01-Aug-25 A | 28-Aug-25 A | 2026-12-04 | 11 | 2026-12-04
A59440 | Inherent Safer Design Review_RCC | 2026-02-20 | 2026-02-20 | 28-Aug-25 A | 04-Sep-25 A | 2026-12-04 | 17 | 2026-12-04
A59450 | Inherent Safer Design Review_IFA | 2026-02-20 | 2026-02-20 | 05-Sep-25 A | 11-Sep-25 A | 2026-12-04 | 17 | 2026-12-04
A59460 | Inherent Safer Design Review_RCA | 2026-02-20 | 2026-03-16 | 2026-02-20 | 2026-03-16 | 2026-12-04 | 17 | 2026-12-29 | 205
A59470 | Inherent Safer Design Review_IFD/IFC | 2026-03-16 | 2026-04-08 | 2026-03-16 | 2026-04-08 | 2026-12-29 | 17 | 2027-01-20 | 205
Bow-tie Development & HSE Critical Equipment & Systems and Performance Standards |  | 2026-02-20 | 2026-04-08 | 25-Jul-25 A | 2026-04-08 | 2026-03-02 | 164 | 2026-08-31 | 103
A59280 | Bow-tie Development & HSE Critical Equipment & Systems and Performance Standards_Workshop | 2026-02-20 | 2026-02-20 | 25-Jul-25 A | 31-Jul-25 A | 2026-03-02 | 11 | 2026-03-02
A60430 | Bow-tie Development & HSE Critical Equipment & Systems and Performance Standards_IFR | 2026-02-20 | 2026-02-20 | 01-Aug-25 A | 25-Aug-25 A | 2026-07-15 | 11 | 2026-07-15
A59290 | Bow-tie Development & HSE Critical Equipment & Systems and Performance Standards_RCC | 2026-02-20 | 2026-02-20 | 26-Aug-25 A | 04-Sep-25 A | 2026-07-15 | 17 | 2026-07-15
A59300 | Bow-tie Development & HSE Critical Equipment & Systems and Performance Standards_IFA | 2026-02-20 | 2026-02-20 | 05-Sep-25 A | 11-Sep-25 A | 2026-07-15 | 17 | 2026-07-15
A59310 | Bow-tie Development & HSE Critical Equipment & Systems and Performance Standards_RCA | 2026-02-20 | 2026-03-16 | 2026-02-20 | 2026-03-16 | 2026-07-15 | 17 | 2026-08-07 | 103
A59320 | Bow-tie Development & HSE Critical Equipment & Systems and Performance Standards_IFD/IFC | 2026-03-16 | 2026-04-08 | 2026-03-16 | 2026-04-08 | 2026-08-07 | 17 | 2026-08-31 | 103
HSECES and Performance Standards |  | 2026-02-20 | 2026-05-26 | 23-Jul-25 A | 2026-05-26 | 2026-10-19 | 178 | 2027-01-20 | 172
A61970 | HSE Critical Equipment & Systems and Performance Standards_Preparation | 2026-02-20 | 2026-02-20 | 23-Jul-25 A | 31-Jul-25 A | 2026-10-19 | 7 | 2026-10-19
A61980 | HSE Critical Equipment & Systems and Performance Standards_IFR | 2026-02-20 | 2026-02-20 | 01-Aug-25 A | 28-Aug-25 A | 2026-10-19 | 11 | 2026-10-19
A61990 | HSE Critical Equipment & Systems and Performance Standards_RCC | 2026-02-20 | 2026-03-16 | 2026-02-20 | 2026-03-16 | 2026-10-19 | 17 | 2026-11-11 | 172
A62000 | HSE Critical Equipment & Systems and Performance Standards_IFA | 2026-03-16 | 2026-04-08 | 2026-03-16 | 2026-04-08 | 2026-11-11 | 17 | 2026-12-04 | 172
A62010 | HSE Critical Equipment & Systems and Performance Standards_RCA | 2026-04-08 | 2026-05-01 | 2026-04-08 | 2026-05-01 | 2026-12-04 | 17 | 2026-12-29 | 172
A62020 | HSE Critical Equipment & Systems and Performance Standards_IFD/IFC | 2026-05-01 | 2026-05-26 | 2026-05-01 | 2026-05-26 | 2026-12-29 | 17 | 2027-01-20 | 172
HAZOP |  | 2026-02-20 | 2026-02-20 | 01-Jul-25 A | 22-Sep-25 A | 2026-03-25 | 102 | 2026-04-02
A62030 | HAZOP_Workshop | 2026-02-20 | 2026-02-20 | 01-Jul-25 A | 11-Jul-25 A | 2026-03-25 | 11 | 2026-03-25
A62040 | HAZOP_IFR | 2026-02-20 | 2026-02-20 | 12-Jul-25 A | 25-Aug-25 A | 2026-04-02 | 11 | 2026-04-02
A62050 | HAZOP_RCC | 2026-02-20 | 2026-02-20 | 26-Aug-25 A | 01-Sep-25 A | 2026-04-02 | 17 | 2026-04-02
A62060 | HAZOP_IFA | 2026-02-20 | 2026-02-20 | 02-Sep-25 A | 08-Sep-25 A | 2026-04-02 | 17 | 2026-04-02
A62070 | HAZOP_RCA | 2026-02-20 | 2026-02-20 | 09-Sep-25 A | 15-Sep-25 A | 2026-04-02 | 17 | 2026-04-02
A62080 | HAZOP_IFD/IFC | 2026-02-20 | 2026-02-20 | 16-Sep-25 A | 22-Sep-25 A | 2026-04-02 | 17 | 2026-04-02
SIL |  | 2026-02-20 | 2026-02-20 | 15-Aug-25 A | 25-Sep-25 A | 2026-03-25 | 30 | 2026-04-02
A23200 | SIL Review Workshop | 2026-02-20 | 2026-02-20 | 15-Aug-25 A | 17-Aug-25 A | 2026-03-25 | 14 | 2026-03-25
A60510 | Issue for Company Review | 2026-02-20 | 2026-02-20 | 18-Aug-25 A | 28-Aug-25 A | 2026-04-02 | 14 | 2026-04-02
A23210 | Issue for Company Approval | 2026-02-20 | 2026-02-20 | 05-Sep-25 A | 11-Sep-25 A | 2026-04-02 | 11 | 2026-04-02
A23220 | Issue for Construction | 2026-02-20 | 2026-02-20 | 12-Sep-25 A | 25-Sep-25 A | 2026-04-02 | 5 | 2026-04-02
Fire and Explosion Risk Assessment (FERA) |  | 2026-02-20 | 2026-04-14 | 01-Aug-25 A | 2026-04-14 | 2026-07-09 | 167 | 2026-08-31 | 100
A59480 | Fire and Explosion Risk Assessment (FERA)_Preparation | 2026-02-20 | 2026-02-20 | 01-Aug-25 A | 20-Aug-25 A | 2026-07-09 | 6 | 2026-07-09
A60470 | Fire and Explosion Risk Assessment (FERA)_IFR | 2026-02-20 | 2026-02-20 | 22-Aug-25 A | 31-Oct-25 A | 2026-07-09 | 28 | 2026-07-09
A59490 | Fire and Explosion Risk Assessment (FERA)_RCC | 2026-02-20 | 2026-03-13 | 2026-02-20 | 2026-03-13 | 2026-07-09 | 16 | 2026-07-31 | 100
A59500 | Fire and Explosion Risk Assessment (FERA)_IFA | 2026-03-13 | 2026-03-19 | 2026-03-13 | 2026-03-19 | 2026-07-31 | 3 | 2026-08-05 | 100
A59510 | Fire and Explosion Risk Assessment (FERA)_RCA | 2026-03-19 | 2026-04-09 | 2026-03-19 | 2026-04-09 | 2026-08-06 | 16 | 2026-08-27 | 100
A59520 | Fire and Explosion Risk Assessment (FERA)_IFD/IFC | 2026-04-09 | 2026-04-14 | 2026-04-09 | 2026-04-14 | 2026-08-27 | 2 | 2026-08-31 | 100
QRA |  | 2026-02-20 | 2026-04-14 | 07-Jul-25 A | 2026-04-14 | 2026-03-17 | 109 | 2026-08-31 | 100
A60590 | Workshop - QRA | 2026-02-20 | 2026-02-20 | 07-Jul-25 A | 15-Jul-25 A | 2026-03-17 | 15 | 2026-03-17
A60600 | QRA Report_IFR | 2026-02-20 | 2026-02-20 | 16-Jul-25 A | 28-Aug-25 A | 2026-07-09 | 28 | 2026-07-09
A60610 | QRA Report_RCC | 2026-02-20 | 2026-03-13 | 2026-02-20 | 2026-03-13 | 2026-07-09 | 16 | 2026-07-31 | 100
A60620 | QRA Report_IFA | 2026-03-13 | 2026-03-19 | 2026-03-13 | 2026-03-19 | 2026-07-31 | 3 | 2026-08-05 | 100
A60630 | QRA Report_RCA | 2026-03-19 | 2026-04-09 | 2026-03-19 | 2026-04-09 | 2026-08-06 | 16 | 2026-08-27 | 100
A60640 | QRA Report_IFD/IFC | 2026-04-09 | 2026-04-14 | 2026-04-09 | 2026-04-14 | 2026-08-27 | 2 | 2026-08-31 | 100
BRA |  | 2026-02-20 | 2026-04-14 | 07-Jul-25 A | 2026-04-14 | 2026-11-30 | 113 | 2027-01-20 | 202
A23290 | Workshop - BRA | 2026-02-20 | 2026-02-20 | 07-Jul-25 A | 15-Jul-25 A | 2026-11-30 | 15 | 2026-11-30
A60540 | BRA Report_IFR | 2026-02-20 | 2026-02-20 | 16-Jul-25 A | 28-Aug-25 A | 2026-11-30 | 28 | 2026-11-30
A60550 | BRA Report_RCC | 2026-02-20 | 2026-03-13 | 2026-02-20 | 2026-03-13 | 2026-11-30 | 16 | 2026-12-22 | 202
A60560 | BRA Report_IFA | 2026-03-13 | 2026-03-19 | 2026-03-13 | 2026-03-19 | 2026-12-22 | 3 | 2026-12-25 | 202
A60570 | BRA Report_RCA | 2026-03-19 | 2026-04-09 | 2026-03-19 | 2026-04-09 | 2026-12-28 | 16 | 2027-01-18 | 202
A60580 | BRA Report_IFD/IFC | 2026-04-09 | 2026-04-14 | 2026-04-09 | 2026-04-14 | 2027-01-18 | 2 | 2027-01-20 | 202
Escape Evacuation and Rescue Assessment (EERA) |  | 2026-02-20 | 2026-04-14 | 01-Aug-25 A | 2026-04-14 | 2026-07-09 | 113 | 2026-08-31 | 100
A59530 | Escape Evacuation and Rescue Assessment (EERA)_Preparation | 2026-02-20 | 2026-02-20 | 01-Aug-25 A | 15-Aug-25 A | 2026-07-09 | 6 | 2026-07-09
A60480 | Escape Evacuation and Rescue Assessment (EERA)_IFR | 2026-02-20 | 2026-02-20 | 16-Aug-25 A | 31-Oct-25 A | 2026-07-09 | 6 | 2026-07-09
A59540 | Escape Evacuation and Rescue Assessment (EERA)_RCC | 2026-02-20 | 2026-03-13 | 2026-02-20 | 2026-03-13 | 2026-07-09 | 16 | 2026-07-31 | 100
A59550 | Escape Evacuation and Rescue Assessment (EERA)_IFA | 2026-03-13 | 2026-03-19 | 2026-03-13 | 2026-03-19 | 2026-07-31 | 3 | 2026-08-05 | 100
A59560 | Escape Evacuation and Rescue Assessment (EERA)_RCA | 2026-03-19 | 2026-04-09 | 2026-03-19 | 2026-04-09 | 2026-08-06 | 16 | 2026-08-27 | 100
A59570 | Escape Evacuation and Rescue Assessment (EERA)_IFD/IFC | 2026-04-09 | 2026-04-14 | 2026-04-09 | 2026-04-14 | 2026-08-27 | 2 | 2026-08-31 | 100
Emergency Systems Survivability Analysis (ESSA) |  | 2026-02-20 | 2026-04-14 | 01-Aug-25 A | 2026-04-14 | 2026-07-09 | 113 | 2026-08-31 | 100
A60340 | Emergency Systems Survivability Analysis (ESSA)_Preparation | 2026-02-20 | 2026-02-20 | 01-Aug-25 A | 15-Aug-25 A | 2026-07-09 | 6 | 2026-07-09
A58830 | Emergency Systems Survivability Analysis (ESSA)_IFR | 2026-02-20 | 2026-02-20 | 18-Aug-25 A | 31-Oct-25 A | 2026-07-09 | 28 | 2026-07-09
A58840 | Emergency Systems Survivability Analysis (ESSA)_RCC | 2026-02-20 | 2026-03-13 | 2026-02-20 | 2026-03-13 | 2026-07-09 | 16 | 2026-07-31 | 100
A58850 | Emergency Systems Survivability Analysis (ESSA)_IFA | 2026-03-13 | 2026-03-19 | 2026-03-13 | 2026-03-19 | 2026-07-31 | 3 | 2026-08-05 | 100
A58860 | Emergency Systems Survivability Analysis (ESSA)_RCA | 2026-03-19 | 2026-04-09 | 2026-03-19 | 2026-04-09 | 2026-08-06 | 16 | 2026-08-27 | 100
A58870 | Emergency Systems Survivability Analysis (ESSA)_IFD/IFC | 2026-04-09 | 2026-04-14 | 2026-04-09 | 2026-04-14 | 2026-08-27 | 2 | 2026-08-31 | 100
Risk Reduction ALARP Workshop |  | 2026-02-20 | 2026-04-15 | 28-Jul-25 A | 2026-04-15 | 2026-11-27 | 38 | 2027-01-20 | 201
A59130 | Risk Reduction ALARP Workshop | 2026-02-20 | 2026-02-20 | 28-Jul-25 A | 07-Aug-25 A | 2026-11-27 | 6 | 2026-11-27
A60400 | Risk Reduction ALARP Workshop Report_IFR | 2026-02-20 | 2026-02-27 | 2026-02-20 | 2026-02-27 | 2026-11-27 | 6 | 2026-12-07 | 201
A59140 | Risk Reduction ALARP Workshop_Report RCC | 2026-02-27 | 2026-03-16 | 2026-02-27 | 2026-03-16 | 2026-12-07 | 11 | 2026-12-22 | 201
A59150 | Risk Reduction ALARP Workshop Report_IFA | 2026-03-16 | 2026-03-20 | 2026-03-16 | 2026-03-20 | 2026-12-22 | 3 | 2026-12-25 | 201
A59160 | Risk Reduction ALARP Workshop Report_RCA | 2026-03-20 | 2026-04-10 | 2026-03-20 | 2026-04-10 | 2026-12-28 | 16 | 2027-01-18 | 201
A59170 | Risk Reduction ALARP Workshop Report_IFD/IFC | 2026-04-13 | 2026-04-15 | 2026-04-13 | 2026-04-15 | 2027-01-18 | 2 | 2027-01-20 | 201
Air Emission Dispersion Assessment |  | 2026-02-20 | 2026-04-14 | 01-Aug-25 A | 2026-04-14 | 2026-07-09 | 167 | 2026-08-31 | 100
A60390 | Air Emission Dispersion Assessment_Preparation | 2026-02-20 | 2026-02-20 | 01-Aug-25 A | 15-Aug-25 A | 2026-07-09 | 6 | 2026-07-09
A59080 | Air Emission Dispersion Assessment_IFR | 2026-02-20 | 2026-02-20 | 16-Aug-25 A | 25-Sep-25 A | 2026-07-09 | 6 | 2026-07-09
A59090 | Air Emission Dispersion Assessment_RCC | 2026-02-20 | 2026-03-13 | 2026-02-20 | 2026-03-13 | 2026-07-09 | 16 | 2026-07-31 | 100
A59100 | Air Emission Dispersion Assessment_IFA | 2026-03-13 | 2026-03-19 | 2026-03-13 | 2026-03-19 | 2026-07-31 | 3 | 2026-08-05 | 100
A59110 | Air Emission Dispersion Assessment_RCA | 2026-03-19 | 2026-04-09 | 2026-03-19 | 2026-04-09 | 2026-08-06 | 16 | 2026-08-27 | 100
A59120 | Air Emission Dispersion Assessment_IFD/IFC | 2026-04-09 | 2026-04-14 | 2026-04-09 | 2026-04-14 | 2026-08-27 | 2 | 2026-08-31 | 100
Noise Study & Contours Report |  | 2026-02-20 | 2026-04-08 | 01-Aug-25 A | 2026-04-08 | 2026-03-17 | 164 | 2026-08-31 | 103
A62090 | Noise study & control report_Preparation | 2026-02-20 | 2026-02-20 | 01-Aug-25 A | 15-Aug-25 A | 2026-03-17 | 6 | 2026-03-17
A62100 | Noise study & control report_IFR | 2026-02-20 | 2026-02-20 | 16-Aug-25 A | 25-Sep-25 A | 2026-07-15 | 6 | 2026-07-15
A62110 | Noise study & control report_RCC | 2026-02-20 | 2026-03-11 | 2026-02-20 | 2026-03-11 | 2026-07-15 | 14 | 2026-08-04 | 103
A62120 | Noise study & control report_IFA | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-17 | 2026-08-04 | 3 | 2026-08-07 | 103
A62130 | Noise study & control report_RCA | 2026-03-17 | 2026-04-06 | 2026-03-17 | 2026-04-06 | 2026-08-07 | 14 | 2026-08-27 | 103
A62140 | Noise study & control report_IFD/IFC | 2026-04-06 | 2026-04-08 | 2026-04-06 | 2026-04-08 | 2026-08-27 | 2 | 2026-08-31 | 103
Best Available Techniques Study (BAT) |  | 2026-02-20 | 2026-03-23 | 01-Aug-25 A | 2026-03-23 | 2026-03-17 | 86 | 2026-08-31 | 116
A60360 | Best Available Techniques Study_Workshop | 2026-02-20 | 2026-02-20 | 01-Aug-25 A | 20-Aug-25 A | 2026-03-17 | 6 | 2026-03-17
A58940 | Best Available Techniques Study_RCC | 2026-02-20 | 2026-02-20 | 21-Aug-25 A | 29-Aug-25 A | 2026-03-27 | 16 | 2026-03-27
A58930 | Best Available Techniques Study_IFR | 2026-02-20 | 2026-02-20 | 21-Aug-25 A | 18-Sep-25 A | 2026-03-17 | 6 | 2026-03-17
A58950 | Best Available Techniques Study_IFA | 2026-02-20 | 2026-02-25 | 2026-02-20 | 2026-02-25 | 2026-07-31 | 3 | 2026-08-05 | 116
A58960 | Best Available Techniques Study_RCA | 2026-02-25 | 2026-03-19 | 2026-02-25 | 2026-03-19 | 2026-08-06 | 16 | 2026-08-27 | 116
A58970 | Best Available Techniques Study_IFD/IFC | 2026-03-19 | 2026-03-23 | 2026-03-19 | 2026-03-23 | 2026-08-27 | 2 | 2026-08-31 | 116
Energy Review Workshop & Report |  | 2026-02-20 | 2026-04-21 | 01-Sep-25 A | 2026-04-21 | 2026-03-27 | 97 | 2027-01-20 | 196
A59380 | Energy Review Workshop | 2026-02-20 | 2026-02-20 | 01-Sep-25 A | 19-Sep-25 A | 2026-03-27 | 6 | 2026-03-27
A60450 | Energy Review Workshop & Report_IFR | 2026-02-20 | 2026-02-27 | 2026-02-20 | 2026-02-27 | 2026-11-23 | 6 | 2026-11-30 | 196
A59390 | Energy Review Workshop & Report_RCC | 2026-02-27 | 2026-03-23 | 2026-02-27 | 2026-03-23 | 2026-11-30 | 16 | 2026-12-22 | 196
A59400 | Energy Review Workshop & Report_IFA | 2026-03-23 | 2026-03-26 | 2026-03-23 | 2026-03-26 | 2026-12-22 | 3 | 2026-12-25 | 196
A59410 | Energy Review Workshop & Report_RCA | 2026-03-26 | 2026-04-17 | 2026-03-26 | 2026-04-17 | 2026-12-28 | 16 | 2027-01-18 | 196
A59420 | Energy Review Workshop & Report_IFD/IFC | 2026-04-17 | 2026-04-21 | 2026-04-17 | 2026-04-21 | 2027-01-18 | 2 | 2027-01-20 | 196
Vent & Flare Dispersion and Radiation Study |  | 2026-02-20 | 2026-04-14 | 01-Oct-25 A | 2026-04-14 | 2026-03-27 | 102 | 2027-01-20 | 202
A59630 | Vent & Flare Dispersion and Radiation Study Preparation ---- | 2026-02-20 | 2026-02-20 | 01-Oct-25 A | 15-Oct-25 A | 2026-03-27 | 6 | 2026-03-27
A60500 | Vent & Flare Dispersion and Radiation Study_IFR | 2026-02-20 | 2026-02-20 | 16-Oct-25 A | 31-Oct-25 A | 2026-03-27 | 6 | 2026-03-27
A59640 | Vent & Flare Dispersion and Radiation Study_RCC | 2026-02-20 | 2026-03-13 | 2026-02-20 | 2026-03-13 | 2026-11-30 | 16 | 2026-12-22 | 202
A59650 | Vent & Flare Dispersion and Radiation Study_IFA | 2026-03-13 | 2026-03-19 | 2026-03-13 | 2026-03-19 | 2026-12-22 | 3 | 2026-12-25 | 202
A59660 | Vent & Flare Dispersion and Radiation Study_RCA | 2026-03-19 | 2026-04-09 | 2026-03-19 | 2026-04-09 | 2026-12-28 | 16 | 2027-01-18 | 202
A59670 | Vent & Flare Dispersion and Radiation Study_IFD/IFC | 2026-04-09 | 2026-04-14 | 2026-04-09 | 2026-04-14 | 2027-01-18 | 2 | 2027-01-20 | 202
Environment Impact Assessment |  | 2026-02-20 | 2026-04-08 | 28-Aug-25 A | 2026-04-08 | 2026-07-15 | 75 | 2026-08-31 | 103
A60380 | Environment Impact Assessment_Workshop ---- | 2026-02-20 | 2026-02-20 | 28-Aug-25 A | 05-Sep-25 A | 2026-07-15 | 6 | 2026-07-15
A59030 | Environment Impact Assessment_IFR | 2026-02-20 | 2026-02-20 | 06-Sep-25 A | 18-Sep-25 A | 2026-07-15 | 6 | 2026-07-15
A59040 | Environment Impact Assessment_RCC | 2026-02-20 | 2026-03-11 | 2026-02-20 | 2026-03-11 | 2026-07-15 | 14 | 2026-08-04 | 103
A59050 | Environment Impact Assessment_IFA | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-17 | 2026-08-04 | 3 | 2026-08-07 | 103
A59060 | Environment Impact Assessment_RCA | 2026-03-17 | 2026-04-06 | 2026-03-17 | 2026-04-06 | 2026-08-07 | 14 | 2026-08-27 | 103
A59070 | Environment Impact Assessment_IFD/IFC | 2026-04-06 | 2026-04-08 | 2026-04-06 | 2026-04-08 | 2026-08-27 | 2 | 2026-08-31 | 103
Ergonomics and Human Factor Engineering Study |  | 2026-02-20 | 2026-07-01 | 25-Aug-25 A | 2026-07-01 | 2026-09-11 | 112 | 2027-01-20 | 146
A60320 | Ergonomics and Human Factor Engineering Study Workshop | 2026-02-20 | 2026-02-20 | 25-Aug-25 A | 01-Sep-25 A | 2026-09-11 | 5 | 2026-09-11
A58730 | Ergonomics and Human Factor Engineering Study_IFR | 2026-02-20 | 2026-02-27 | 2026-02-20 | 2026-02-27 | 2026-09-11 | 6 | 2026-09-21 | 146
A58740 | Ergonomics and Human Factor Engineering Study_RCC | 2026-02-27 | 2026-04-02 | 2026-02-27 | 2026-04-02 | 2026-09-21 | 24 | 2026-10-22 | 146
A58750 | Ergonomics and Human Factor Engineering Study_IFA | 2026-04-02 | 2026-05-05 | 2026-04-02 | 2026-05-05 | 2026-10-22 | 24 | 2026-11-25 | 146
A58760 | Ergonomics and Human Factor Engineering Study_RCA | 2026-05-05 | 2026-06-08 | 2026-05-05 | 2026-06-08 | 2026-11-25 | 24 | 2026-12-29 | 146
A58770 | Ergonomics and Human Factor Engineering Study_IFD/IFC | 2026-06-08 | 2026-07-01 | 2026-06-08 | 2026-07-01 | 2026-12-29 | 17 | 2027-01-20 | 146
Dropped Objects Study (DOS) |  | 2026-02-20 | 2026-05-19 | 2026-02-20 | 2026-05-19 | 2026-10-26 | 63 | 2027-01-20 | 176
A60350 | Dropped Objects Study (DOS)_Workshop | 2026-02-20 | 2026-02-27 | 2026-02-20 | 2026-02-27 | 2026-10-26 | 6 | 2026-11-02 | 176
A58880 | Dropped Objects Study (DOS)_IFR | 2026-02-27 | 2026-03-27 | 2026-02-27 | 2026-03-27 | 2026-11-02 | 20 | 2026-11-30 | 176
A58890 | Dropped Objects Study (DOS)_RCC | 2026-03-27 | 2026-04-20 | 2026-03-27 | 2026-04-20 | 2026-11-30 | 16 | 2026-12-22 | 176
A58900 | Dropped Objects Study (DOS)_IFA | 2026-04-20 | 2026-04-23 | 2026-04-20 | 2026-04-23 | 2026-12-22 | 3 | 2026-12-25 | 176
A58910 | Dropped Objects Study (DOS)_RCA | 2026-04-24 | 2026-05-15 | 2026-04-24 | 2026-05-15 | 2026-12-28 | 16 | 2027-01-18 | 176
A58920 | Dropped Objects Study (DOS)_IFD/IFC | 2026-05-15 | 2026-05-19 | 2026-05-15 | 2026-05-19 | 2027-01-18 | 2 | 2027-01-20 | 176
3D F&G mapping study |  | 2026-02-20 | 2026-04-29 | 2026-02-20 | 2026-04-29 | 2026-11-13 | 48 | 2027-01-20 | 191
A60370 | 3D F&G mapping study_Preparation | 2026-02-20 | 2026-02-27 | 2026-02-20 | 2026-02-27 | 2026-11-13 | 6 | 2026-11-23 | 191
A58980 | 3D F&G mapping study_IFR | 2026-02-27 | 2026-03-09 | 2026-02-27 | 2026-03-09 | 2026-11-23 | 6 | 2026-11-30 | 191
A58990 | 3D F&G mapping study_RCC | 2026-03-09 | 2026-03-30 | 2026-03-09 | 2026-03-30 | 2026-11-30 | 16 | 2026-12-22 | 191
A59000 | 3D F&G mapping study_IFA | 2026-03-31 | 2026-04-03 | 2026-03-31 | 2026-04-03 | 2026-12-22 | 3 | 2026-12-25 | 191
A59010 | 3D F&G mapping study_RCA | 2026-04-03 | 2026-04-27 | 2026-04-03 | 2026-04-27 | 2026-12-28 | 16 | 2027-01-18 | 191
A59020 | 3D F&G mapping study_IFD/IFC | 2026-04-27 | 2026-04-29 | 2026-04-27 | 2026-04-29 | 2027-01-18 | 2 | 2027-01-20 | 191
E-HAZOP |  | 2026-02-20 | 2026-04-21 | 25-Aug-25 A | 2026-04-21 | 2026-03-17 | 102 | 2027-01-20 | 196
A62150 | E-HAZOP_Workshop | 2026-02-20 | 2026-02-20 | 25-Aug-25 A | 01-Sep-25 A | 2026-03-17 | 3 | 2026-03-17
A62160 | E-HAZOP_IFR | 2026-02-20 | 2026-02-27 | 2026-02-20 | 2026-02-27 | 2026-11-23 | 6 | 2026-11-30 | 196
A62170 | E-HAZOP_RCC | 2026-02-27 | 2026-03-23 | 2026-02-27 | 2026-03-23 | 2026-11-30 | 16 | 2026-12-22 | 196
A62180 | E-HAZOP_IFA | 2026-03-23 | 2026-03-26 | 2026-03-23 | 2026-03-26 | 2026-12-22 | 3 | 2026-12-25 | 196
A62190 | E-HAZOP_RCA | 2026-03-26 | 2026-04-17 | 2026-03-26 | 2026-04-17 | 2026-12-28 | 16 | 2027-01-18 | 196
A62200 | E-HAZOP_IFD/IFC | 2026-04-17 | 2026-04-21 | 2026-04-17 | 2026-04-21 | 2027-01-18 | 2 | 2027-01-20 | 196
Constructability Review |  | 2026-02-20 | 2026-03-23 | 27-Aug-25 A | 2026-03-23 | 2026-12-22 | 146 | 2027-01-20 | 218
A59180 | Constructability Review Workshop | 2026-02-20 | 2026-02-20 | 27-Aug-25 A | 27-Aug-25 A | 2026-12-22 | 6 | 2026-12-22
A60410 | Constructability Review_IFR | 2026-02-20 | 2026-02-20 | 17-Nov-25 A | 30-Nov-25 A | 2026-12-22 | 6 | 2026-12-22
A59190 | Constructability Review_RCC | 2026-02-20 | 2026-02-20 | 01-Dec-25 A | 10-Dec-25 A | 2026-12-22 | 16 | 2026-12-22
A59200 | Constructability Review_IFA | 2026-02-20 | 2026-02-25 | 2026-02-20 | 2026-02-25 | 2026-12-22 | 3 | 2026-12-25 | 218
A59210 | Constructability Review_RCA | 2026-02-25 | 2026-03-19 | 2026-02-25 | 2026-03-19 | 2026-12-28 | 16 | 2027-01-18 | 218
A59220 | Constructability Review_IFD/IFC | 2026-03-19 | 2026-03-23 | 2026-03-19 | 2026-03-23 | 2027-01-18 | 2 | 2027-01-20 | 218
SIMPOS |  | 2026-02-20 | 2026-03-23 | 25-Aug-25 A | 2026-03-23 | 2026-12-22 | 170 | 2027-01-20 | 218
A59680 | SIMOPS Workshop | 2026-02-20 | 2026-02-20 | 25-Aug-25 A | 28-Aug-25 A | 2026-12-22 | 6 | 2026-12-22
A60520 | SIMOPS Report_IFR | 2026-02-20 | 2026-02-20 | 11-Nov-25 A | 30-Nov-25 A | 2026-12-22 | 6 | 2026-12-22
A59690 | SIMOPS Report_RCC | 2026-02-20 | 2026-02-20 | 08-Dec-25 A | 16-Dec-25 A | 2026-12-22 | 16 | 2026-12-22
A59700 | SIMOPS Report_IFA | 2026-02-20 | 2026-02-25 | 2026-02-20 | 2026-02-25 | 2026-12-22 | 3 | 2026-12-25 | 218
A59710 | SIMOPS Report_RCA | 2026-02-25 | 2026-03-19 | 2026-02-25 | 2026-03-19 | 2026-12-28 | 16 | 2027-01-18 | 218
A59720 | SIMOPS Report_IFD/IFC | 2026-03-19 | 2026-03-23 | 2026-03-19 | 2026-03-23 | 2027-01-18 | 2 | 2027-01-20 | 218
HSEIA |  | 2026-02-20 | 2026-03-26 | 24-Dec-25 A | 2026-03-26 | 2026-04-02 | 44 | 2027-01-20 | 214
A61370 | HSEIA Report Preparation | 2026-02-20 | 2026-02-20 | 24-Dec-25 A | 31-Dec-25 A | 2026-04-02 | 6 | 2026-04-02
A61380 | HSEIA Report_IFR | 2026-02-20 | 2026-02-20 | 01-Jan-26 A | 06-Jan-26 A | 2026-04-02 | 6 | 2026-04-02
A61390 | HSEIA Report_RCC | 2026-02-20 | 2026-02-20 | 07-Jan-26 A | 23-Jan-26 A | 2026-12-29 | 16 | 2026-12-29
A62500 | Assesemnt on new requirements by COMPANY | 2026-02-20 | 2026-02-27 | 13-Feb-26 A | 2026-02-27 | 2026-12-29 | 21 | 2027-01-06 | 210
A61400 | HSEIA Report_IFA | 2026-03-02 | 2026-03-05 | 2026-03-02 | 2026-03-05 | 2027-01-06 | 3 | 2027-01-11 | 222
A61410 | HSEIA Report_RCA | 2026-03-05 | 2026-03-12 | 2026-03-05 | 2026-03-12 | 2027-01-11 | 5 | 2027-01-18 | 222
A61420 | HSEIA Report_IFD/IFC | 2026-03-12 | 2026-03-16 | 2026-03-12 | 2026-03-16 | 2027-01-18 | 2 | 2027-01-20 | 222
A61840 | HSEIA Report ADNOC Approval | 2026-02-20 | 2026-03-26 | 2026-02-20 | 2026-03-26 | 2026-04-02 | 25 | 2026-05-06 | 29
PHSER III |  | 2026-03-06 | 2026-05-13 | 2026-03-06 | 2026-05-13 | 2026-07-01 | 48 | 2026-09-08 | 84
A59330 | PHSER III_Workshop | 2026-03-06 | 2026-03-13 | 2026-03-06 | 2026-03-13 | 2026-07-01 | 6 | 2026-07-09 | 84
A60440 | PHSER III_IFR | 2026-03-13 | 2026-03-23 | 2026-03-13 | 2026-03-23 | 2026-07-09 | 6 | 2026-07-17 | 84
A59340 | PHSER III_RCC | 2026-03-23 | 2026-04-14 | 2026-03-23 | 2026-04-14 | 2026-07-17 | 16 | 2026-08-07 | 84
A59350 | PHSER III_IFA | 2026-04-14 | 2026-04-17 | 2026-04-14 | 2026-04-17 | 2026-08-07 | 3 | 2026-08-13 | 84
A59360 | PHSER III_RCA | 2026-04-17 | 2026-05-11 | 2026-04-17 | 2026-05-11 | 2026-08-13 | 16 | 2026-09-03 | 84
A59370 | PHSER III_IFD/IFC | 2026-05-11 | 2026-05-13 | 2026-05-11 | 2026-05-13 | 2026-09-04 | 2 | 2026-09-08 | 84
PHSER IV |  | 2026-05-13 | 2026-07-20 | 2026-05-13 | 2026-07-20 | 2026-09-08 | 48 | 2026-11-13 | 84
A61850 | PHSER IV_Workshop | 2026-05-13 | 2026-05-21 | 2026-05-13 | 2026-05-21 | 2026-09-08 | 6 | 2026-09-15 | 84
A61900 | PHSER IV_IFR | 2026-05-21 | 2026-05-28 | 2026-05-21 | 2026-05-28 | 2026-09-15 | 6 | 2026-09-23 | 84
A61860 | PHSER IV_RCC | 2026-05-28 | 2026-06-19 | 2026-05-28 | 2026-06-19 | 2026-09-23 | 16 | 2026-10-15 | 84
A61870 | PHSER IV_IFA | 2026-06-19 | 2026-06-24 | 2026-06-19 | 2026-06-24 | 2026-10-15 | 3 | 2026-10-20 | 84
A61880 | PHSER IV_RCA | 2026-06-24 | 2026-07-16 | 2026-06-24 | 2026-07-16 | 2026-10-20 | 16 | 2026-11-11 | 84
A61890 | PHSER IV_IFD/IFC | 2026-07-16 | 2026-07-20 | 2026-07-16 | 2026-07-20 | 2026-11-11 | 2 | 2026-11-13 | 84
PHSER V |  | 2026-07-20 | 2026-09-25 | 2026-07-20 | 2026-09-25 | 2026-11-13 | 48 | 2027-01-20 | 84
A61910 | PHSER V_Workshop | 2026-07-20 | 2026-07-28 | 2026-07-20 | 2026-07-28 | 2026-11-13 | 6 | 2026-11-23 | 84
A61960 | PHSER V_IFR | 2026-07-28 | 2026-08-05 | 2026-07-28 | 2026-08-05 | 2026-11-23 | 6 | 2026-11-30 | 84
A61920 | PHSER V_RCC | 2026-08-05 | 2026-08-26 | 2026-08-05 | 2026-08-26 | 2026-11-30 | 16 | 2026-12-22 | 84
A61930 | PHSER V_FA | 2026-08-26 | 2026-09-01 | 2026-08-26 | 2026-09-01 | 2026-12-22 | 3 | 2026-12-25 | 84
A61940 | PHSER V_RCA | 2026-09-01 | 2026-09-22 | 2026-09-01 | 2026-09-22 | 2026-12-28 | 16 | 2027-01-18 | 84
A61950 | PHSER V_IFD/IFC | 2026-09-23 | 2026-09-25 | 2026-09-23 | 2026-09-25 | 2027-01-18 | 2 | 2027-01-20 | 84
QA/QC Management |  | 2026-02-20 | 2026-06-11 | 12-May-25 A | 2026-06-11 | 2026-03-20 | 400 | 2027-07-20 | 288
QAQC Deliverables |  | 2026-02-20 | 2026-06-11 | 25-May-25 A | 2026-06-11 | 2026-03-20 | 275 | 2027-04-21 | 224
A1-PM-QCD-0011 | PCQ-011-Site Contractors Quality Plans | 2026-02-20 | 2026-02-20 | 25-May-25 A | 03-Sep-25 A | 2026-03-27 | 5 | 2026-03-27
A1-PM-QCD-0012 | PCQ-012-Worksite Quality Plan | 2026-02-20 | 2026-02-20 | 03-Sep-25 A | 15-Sep-25 A | 2026-11-06 | 5 | 2026-11-06
A1-PM-QCD-0001 | PCQ-001-Inspection Record | 2026-02-20 | 2026-02-26 | 08-Aug-25 A | 2026-02-26 | 2026-03-20 | 5 | 2026-03-27 | 20
A1-PM-QCD-0002 | PCQ-002-Inspection Check List | 2026-03-03 | 2026-03-09 | 08-Aug-25 A | 2026-03-09 | 2027-01-11 | 5 | 2027-01-15 | 224
A1-PM-QCD-0003 | PCQ-003-Test Certificate | 2026-03-12 | 2026-03-18 | 14-Aug-25 A | 2026-03-18 | 2027-01-20 | 5 | 2027-01-26 | 224
A1-PM-QCD-0004 | PCQ-004-Inspection and Test Plan Vendor | 2026-03-23 | 2026-03-27 | 14-Aug-25 A | 2026-03-27 | 2027-01-29 | 5 | 2027-02-04 | 224
A1-PM-QCD-0005 | PCQ-005-Inspection and Test Plan Site | 2026-04-07 | 2026-04-07 | 16-Jun-25 A | 2026-04-07 | 2027-02-15 | 5 | 2027-02-15 | 224
A1-PM-QCD-0006 | PCQ-006-Inspection and Test Plan | 2026-04-16 | 2026-04-16 | 16-Jun-25 A | 2026-04-16 | 2027-02-24 | 5 | 2027-02-24 | 224
A1-PM-QCD-0007 | PCQ-007-Quality Assurance Docs | 2026-04-27 | 2026-04-27 | 15-Aug-25 A | 2026-04-27 | 2027-03-05 | 5 | 2027-03-05 | 224
A1-PM-QCD-0008 | PCQ-008-Inspection Guidelines (Source and Field) | 2026-05-06 | 2026-05-06 | 15-Aug-25 A | 2026-05-06 | 2027-03-16 | 5 | 2027-03-16 | 224
A1-PM-QCD-0009 | PCQ-009-Inspection / Expediting / Reports | 2026-05-15 | 2026-05-15 | 15-Aug-25 A | 2026-05-15 | 2027-03-25 | 5 | 2027-03-25 | 224
A1-PM-QCD-0010 | PCQ-010-Vendor Shop Inspection & Quality Control Plans | 2026-05-26 | 2026-05-26 | 18-Aug-25 A | 2026-05-26 | 2027-04-05 | 5 | 2027-04-05 | 224
A1-PM-QCD-0013 | PCQ-013-Inspection Plan and Schedule | 2026-06-04 | 2026-06-04 | 15-Aug-25 A | 2026-06-04 | 2027-04-14 | 5 | 2027-04-14 | 224
A1-PM-QCD-0014 | PCQ-014-Inspection Release Report | 2026-06-05 | 2026-06-11 | 2026-06-05 | 2026-06-11 | 2027-04-15 | 5 | 2027-04-21 | 224
QAQC Audit Plan |  | 2026-02-20 | 2026-02-20 | 12-May-25 A | 25-May-25 A | 2027-07-20 | 380 | 2027-07-20
A1-PM-QAP-0001 | QAQC Audit Plan | 2026-02-20 | 2026-02-20 | 12-May-25 A | 25-May-25 A | 2027-07-20 | 380 | 2027-07-20
Contractor's Temporary Facilities |  |  |  | 20-Jan-25 A | 20-Jan-25 A |  | 0
Home Office |  |  |  | 20-Jan-25 A | 20-Jan-25 A |  | 0
A1-PM-CTF-0001 | Home Office Ready for IPMT Moblization |  |  |  | 20-Jan-25 A |  | 0
Others |  | 2026-02-20 | 2027-07-20 | 20-Dec-24 A | 2027-07-20 | 2026-03-27 | 672 | 2027-07-20 | 0
Project Key Milestones |  | 2026-02-20 | 2027-07-20 | 12-Apr-25 A | 2027-07-20 | 2026-03-27 | 739 | 2027-07-20 | 0
A1-PM-PKM-0001 | Turnaround Scope Completion (TA) | 2026-02-20 | 2026-02-20 | 12-Apr-25 A | 17-May-25 A | 2026-03-27 | 47 | 2026-03-27
A1-PM-PKM-0002 | Mechanical Completion (MC) |  | 2027-01-20 |  | 2027-01-20 |  | 0 | 2027-01-20 | 0
A1-PM-PKM-0003 | Ready for Start-up (RFSU) |  | 2027-04-21 |  | 2027-04-21 |  | 0 | 2027-04-21 | 0
A1-PM-PKM-0004 | Provisional Acceptance Certificate (PAC) |  | 2027-07-20 |  | 2027-07-20 |  | 0 | 2027-07-20 | 0
Weekly Progress Report |  | 2026-02-20 | 2027-02-24 | 03-Jan-25 A | 2027-02-24 | 2026-07-16 | 558 | 2027-07-20 | 105
A1-PM-WPR-0001 | Weekly Progress Report Issuance - WPR0001 |  |  |  | 03-Jan-25 A |  | 0
A1-PM-WPR-0002 | Weekly Progress Report Issuance - WPR0002 |  |  |  | 10-Jan-25 A |  | 0
A1-PM-WPR-0003 | Weekly Progress Report Issuance - WPR0003 |  |  |  | 17-Jan-25 A |  | 0
A1-PM-WPR-0004 | Weekly Progress Report Issuance - WPR0004 |  |  |  | 24-Jan-25 A |  | 0
A1-PM-WPR-0005 | Weekly Progress Report Issuance - WPR0005 |  |  |  | 31-Jan-25 A |  | 0
A1-PM-WPR-0006 | Weekly Progress Report Issuance - WPR0006 |  |  |  | 07-Feb-25 A |  | 0
A1-PM-WPR-0007 | Weekly Progress Report Issuance - WPR0007 |  |  |  | 14-Feb-25 A |  | 0
A1-PM-WPR-0008 | Weekly Progress Report Issuance - WPR0008 |  |  |  | 21-Feb-25 A |  | 0
A1-PM-WPR-0009 | Weekly Progress Report Issuance - WPR0009 |  |  |  | 28-Feb-25 A |  | 0
A1-PM-WPR-0016 | Weekly Progress Report Issuance - WPR0016 |  |  |  | 18-Apr-25 A |  | 0
A1-PM-WPR-0010 | Weekly Progress Report Issuance - WPR0010 |  |  |  | 06-May-25 A |  | 0
A1-PM-WPR-0011 | Weekly Progress Report Issuance - WPR0011 |  |  |  | 06-May-25 A |  | 0
A1-PM-WPR-0012 | Weekly Progress Report Issuance - WPR0012 |  |  |  | 06-May-25 A |  | 0
A1-PM-WPR-0013 | Weekly Progress Report Issuance - WPR0013 |  |  |  | 06-May-25 A |  | 0
A1-PM-WPR-0014 | Weekly Progress Report Issuance - WPR0014 |  |  |  | 06-May-25 A |  | 0
A1-PM-WPR-0015 | Weekly Progress Report Issuance - WPR0015 |  |  |  | 06-May-25 A |  | 0
A1-PM-WPR-0017 | Weekly Progress Report Issuance - WPR0017 |  |  |  | 09-May-25 A |  | 0
A1-PM-WPR-0018 | Weekly Progress Report Issuance - WPR0018 |  |  |  | 09-May-25 A |  | 0
A1-PM-WPR-0019 | Weekly Progress Report Issuance - WPR0019 |  |  |  | 13-May-25 A |  | 0
A1-PM-WPR-0020 | Weekly Progress Report Issuance - WPR0020 |  |  |  | 21-May-25 A |  | 0
A1-PM-WPR-0021 | Weekly Progress Report Issuance - WPR0021 |  |  |  | 28-May-25 A |  | 0
A1-PM-WPR-0023 | Weekly Progress Report Issuance - WPR0023 |  |  |  | 06-Jun-25 A |  | 0
A1-PM-WPR-0022 | Weekly Progress Report Issuance - WPR0022 |  |  |  | 08-Jun-25 A |  | 0
A1-PM-WPR-0024 | Weekly Progress Report Issuance - WPR0024 |  |  |  | 13-Jun-25 A |  | 0
A1-PM-WPR-0025 | Weekly Progress Report Issuance - WPR0025 |  |  |  | 21-Jun-25 A |  | 0
A1-PM-WPR-0026 | Weekly Progress Report Issuance - WPR0026 |  |  |  | 30-Jun-25 A |  | 0
A1-PM-WPR-0027 | Weekly Progress Report Issuance - WPR0027 |  |  |  | 10-Jul-25 A |  | 0
A1-PM-WPR-0028 | Weekly Progress Report Issuance - WPR0028 |  |  |  | 18-Jul-25 A |  | 0
A1-PM-WPR-0029 | Weekly Progress Report Issuance - WPR0029 |  |  |  | 22-Aug-25 A |  | 0
A1-PM-WPR-0034 | Weekly Progress Report Issuance - WPR0034 |  |  |  | 27-Aug-25 A |  | 0
A1-PM-WPR-0030 | Weekly Progress Report Issuance - WPR0030 |  |  |  | 27-Aug-25 A |  | 0
A1-PM-WPR-0031 | Weekly Progress Report Issuance - WPR0031 |  |  |  | 02-Sep-25 A |  | 0
A1-PM-WPR-0032 | Weekly Progress Report Issuance - WPR0032 |  |  |  | 07-Sep-25 A |  | 0
A1-PM-WPR-0037 | Weekly Progress Report Issuance - WPR0037 |  |  |  | 12-Sep-25 A |  | 0
A1-PM-WPR-0033 | Weekly Progress Report Issuance - WPR0033 |  |  |  | 13-Sep-25 A |  | 0
A1-PM-WPR-0035 | Weekly Progress Report Issuance - WPR0035 |  |  |  | 15-Sep-25 A |  | 0
A1-PM-WPR-0036 | Weekly Progress Report Issuance - WPR0036 |  |  |  | 15-Sep-25 A |  | 0
A1-PM-WPR-0038 | Weekly Progress Report Issuance - WPR0038 |  |  |  | 19-Sep-25 A |  | 0
A1-PM-WPR-0039 | Weekly Progress Report Issuance - WPR0039 |  |  |  | 03-Oct-25 A |  | 0
A1-PM-WPR-0040 | Weekly Progress Report Issuance - WPR0040 |  |  |  | 10-Oct-25 A |  | 0
A1-PM-WPR-0041 | Weekly Progress Report Issuance - WPR0041 |  |  |  | 17-Oct-25 A |  | 0
A1-PM-WPR-0042 | Weekly Progress Report Issuance - WPR0042 |  |  |  | 24-Oct-25 A |  | 0
A1-PM-WPR-0043 | Weekly Progress Report Issuance - WPR0043 |  |  |  | 30-Oct-25 A |  | 0
A1-PM-WPR-0044 | Weekly Progress Report Issuance - WPR0044 |  |  |  | 04-Nov-25 A |  | 0
A1-PM-WPR-0045 | Weekly Progress Report Issuance - WPR0045 |  |  |  | 12-Nov-25 A |  | 0
A1-PM-WPR-0046 | Weekly Progress Report Issuance - WPR0046 |  |  |  | 18-Nov-25 A |  | 0
A1-PM-WPR-0047 | Weekly Progress Report Issuance - WPR0047 |  | 2026-02-20 |  | 2026-02-20 |  | 0 | 2026-07-16 | 183
A1-PM-WPR-0048 | Weekly Progress Report Issuance - WPR0048 |  | 2026-02-25 |  | 2026-02-25 |  | 0 | 2026-07-21 | 183
A1-PM-WPR-0049 | Weekly Progress Report Issuance - WPR0049 |  | 2026-03-03 |  | 2026-03-03 |  | 0 | 2026-07-27 | 183
A1-PM-WPR-0050 | Weekly Progress Report Issuance - WPR0050 |  | 2026-03-08 |  | 2026-03-08 |  | 0 | 2026-08-02 | 183
A1-PM-WPR-0051 | Weekly Progress Report Issuance - WPR0051 |  | 2026-03-14 |  | 2026-03-14 |  | 0 | 2026-08-07 | 183
A1-PM-WPR-0052 | Weekly Progress Report Issuance - WPR0052 |  | 2026-03-19 |  | 2026-03-19 |  | 0 | 2026-08-13 | 183
A1-PM-WPR-0053 | Weekly Progress Report Issuance - WPR0053 |  | 2026-03-25 |  | 2026-03-25 |  | 0 | 2026-08-18 | 183
A1-PM-WPR-0054 | Weekly Progress Report Issuance - WPR0054 |  | 2026-03-31 |  | 2026-03-31 |  | 0 | 2026-08-24 | 183
A1-PM-WPR-0055 | Weekly Progress Report Issuance - WPR0055 |  | 2026-04-05 |  | 2026-04-05 |  | 0 | 2026-08-30 | 183
A1-PM-WPR-0056 | Weekly Progress Report Issuance - WPR0056 |  | 2026-04-11 |  | 2026-04-11 |  | 0 | 2026-09-04 | 183
A1-PM-WPR-0057 | Weekly Progress Report Issuance - WPR0057 |  | 2026-04-16 |  | 2026-04-16 |  | 0 | 2026-09-10 | 183
A1-PM-WPR-0058 | Weekly Progress Report Issuance - WPR0058 |  | 2026-04-22 |  | 2026-04-22 |  | 0 | 2026-09-15 | 183
A1-PM-WPR-0059 | Weekly Progress Report Issuance - WPR0059 |  | 2026-04-28 |  | 2026-04-28 |  | 0 | 2026-09-21 | 183
A1-PM-WPR-0060 | Weekly Progress Report Issuance - WPR0060 |  | 2026-05-03 |  | 2026-05-03 |  | 0 | 2026-09-27 | 183
A1-PM-WPR-0061 | Weekly Progress Report Issuance - WPR0061 |  | 2026-05-09 |  | 2026-05-09 |  | 0 | 2026-10-02 | 183
A1-PM-WPR-0062 | Weekly Progress Report Issuance - WPR0062 |  | 2026-05-14 |  | 2026-05-14 |  | 0 | 2026-10-08 | 183
A1-PM-WPR-0063 | Weekly Progress Report Issuance - WPR0063 |  | 2026-05-20 |  | 2026-05-20 |  | 0 | 2026-10-13 | 183
A1-PM-WPR-0064 | Weekly Progress Report Issuance - WPR0064 |  | 2026-05-26 |  | 2026-05-26 |  | 0 | 2026-10-19 | 183
A1-PM-WPR-0065 | Weekly Progress Report Issuance - WPR0065 |  | 2026-05-31 |  | 2026-05-31 |  | 0 | 2026-10-25 | 183
A1-PM-WPR-0066 | Weekly Progress Report Issuance - WPR0066 |  | 2026-06-06 |  | 2026-06-06 |  | 0 | 2026-10-30 | 183
A1-PM-WPR-0067 | Weekly Progress Report Issuance - WPR0067 |  | 2026-06-11 |  | 2026-06-11 |  | 0 | 2026-11-05 | 183
A1-PM-WPR-0068 | Weekly Progress Report Issuance - WPR0068 |  | 2026-06-17 |  | 2026-06-17 |  | 0 | 2026-11-10 | 183
A1-PM-WPR-0069 | Weekly Progress Report Issuance - WPR0069 |  | 2026-06-23 |  | 2026-06-23 |  | 0 | 2026-11-16 | 183
A1-PM-WPR-0070 | Weekly Progress Report Issuance - WPR0070 |  | 2026-06-28 |  | 2026-06-28 |  | 0 | 2026-11-22 | 183
A1-PM-WPR-0071 | Weekly Progress Report Issuance - WPR0071 |  | 2026-07-04 |  | 2026-07-04 |  | 0 | 2026-11-27 | 183
A1-PM-WPR-0072 | Weekly Progress Report Issuance - WPR0072 |  | 2026-07-09 |  | 2026-07-09 |  | 0 | 2026-12-03 | 183
A1-PM-WPR-0073 | Weekly Progress Report Issuance - WPR0073 |  | 2026-07-15 |  | 2026-07-15 |  | 0 | 2026-12-08 | 183
A1-PM-WPR-0074 | Weekly Progress Report Issuance - WPR0074 |  | 2026-07-21 |  | 2026-07-21 |  | 0 | 2026-12-14 | 183
A1-PM-WPR-0075 | Weekly Progress Report Issuance - WPR0075 |  | 2026-07-26 |  | 2026-07-26 |  | 0 | 2026-12-20 | 183
A1-PM-WPR-0076 | Weekly Progress Report Issuance - WPR0076 |  | 2026-08-01 |  | 2026-08-01 |  | 0 | 2026-12-25 | 183
A1-PM-WPR-0077 | Weekly Progress Report Issuance - WPR0077 |  | 2026-08-06 |  | 2026-08-06 |  | 0 | 2026-12-31 | 183
A1-PM-WPR-0078 | Weekly Progress Report Issuance - WPR0078 |  | 2026-08-12 |  | 2026-08-12 |  | 0 | 2027-01-05 | 183
A1-PM-WPR-0079 | Weekly Progress Report Issuance - WPR0079 |  | 2026-08-18 |  | 2026-08-18 |  | 0 | 2027-01-11 | 183
A1-PM-WPR-0080 | Weekly Progress Report Issuance - WPR0080 |  | 2026-08-23 |  | 2026-08-23 |  | 0 | 2027-01-17 | 183
A1-PM-WPR-0081 | Weekly Progress Report Issuance - WPR0081 |  | 2026-08-29 |  | 2026-08-29 |  | 0 | 2027-01-22 | 183
A1-PM-WPR-0082 | Weekly Progress Report Issuance - WPR0082 |  | 2026-09-03 |  | 2026-09-03 |  | 0 | 2027-01-28 | 183
A1-PM-WPR-0083 | Weekly Progress Report Issuance - WPR0083 |  | 2026-09-09 |  | 2026-09-09 |  | 0 | 2027-02-02 | 183
A1-PM-WPR-0084 | Weekly Progress Report Issuance - WPR0084 |  | 2026-09-15 |  | 2026-09-15 |  | 0 | 2027-02-08 | 183
A1-PM-WPR-0085 | Weekly Progress Report Issuance - WPR0085 |  | 2026-09-20 |  | 2026-09-20 |  | 0 | 2027-02-14 | 183
A1-PM-WPR-0086 | Weekly Progress Report Issuance - WPR0086 |  | 2026-09-26 |  | 2026-09-26 |  | 0 | 2027-02-19 | 183
A1-PM-WPR-0087 | Weekly Progress Report Issuance - WPR0087 |  | 2026-10-01 |  | 2026-10-01 |  | 0 | 2027-02-25 | 183
A1-PM-WPR-0088 | Weekly Progress Report Issuance - WPR0088 |  | 2026-10-07 |  | 2026-10-07 |  | 0 | 2027-03-02 | 183
A1-PM-WPR-0089 | Weekly Progress Report Issuance - WPR0089 |  | 2026-10-13 |  | 2026-10-13 |  | 0 | 2027-03-08 | 183
A1-PM-WPR-0090 | Weekly Progress Report Issuance - WPR0090 |  | 2026-10-18 |  | 2026-10-18 |  | 0 | 2027-03-14 | 183
A1-PM-WPR-0091 | Weekly Progress Report Issuance - WPR0091 |  | 2026-10-24 |  | 2026-10-24 |  | 0 | 2027-03-19 | 183
A1-PM-WPR-0092 | Weekly Progress Report Issuance - WPR0092 |  | 2026-10-29 |  | 2026-10-29 |  | 0 | 2027-03-25 | 183
A1-PM-WPR-0093 | Weekly Progress Report Issuance - WPR0093 |  | 2026-11-04 |  | 2026-11-04 |  | 0 | 2027-03-30 | 183
A1-PM-WPR-0094 | Weekly Progress Report Issuance - WPR0094 |  | 2026-11-10 |  | 2026-11-10 |  | 0 | 2027-04-05 | 183
A1-PM-WPR-0095 | Weekly Progress Report Issuance - WPR0095 |  | 2026-11-15 |  | 2026-11-15 |  | 0 | 2027-04-11 | 183
A1-PM-WPR-0096 | Weekly Progress Report Issuance - WPR0096 |  | 2026-11-21 |  | 2026-11-21 |  | 0 | 2027-04-16 | 183
A1-PM-WPR-0097 | Weekly Progress Report Issuance - WPR0097 |  | 2026-11-26 |  | 2026-11-26 |  | 0 | 2027-04-22 | 183
A1-PM-WPR-0098 | Weekly Progress Report Issuance - WPR0098 |  | 2026-12-02 |  | 2026-12-02 |  | 0 | 2027-04-27 | 183
A1-PM-WPR-0099 | Weekly Progress Report Issuance - WPR0099 |  | 2026-12-08 |  | 2026-12-08 |  | 0 | 2027-05-03 | 183
A1-PM-WPR-0100 | Weekly Progress Report Issuance - WPR0100 |  | 2026-12-13 |  | 2026-12-13 |  | 0 | 2027-05-09 | 183
A1-PM-WPR-0101 | Weekly Progress Report Issuance - WPR0101 |  | 2026-12-19 |  | 2026-12-19 |  | 0 | 2027-05-14 | 183
A1-PM-WPR-0102 | Weekly Progress Report Issuance - WPR0102 |  | 2026-12-24 |  | 2026-12-24 |  | 0 | 2027-05-20 | 183
A1-PM-WPR-0103 | Weekly Progress Report Issuance - WPR0103 |  | 2026-12-30 |  | 2026-12-30 |  | 0 | 2027-05-25 | 183
A1-PM-WPR-0104 | Weekly Progress Report Issuance - WPR0104 |  | 2027-01-05 |  | 2027-01-05 |  | 0 | 2027-05-31 | 183
A1-PM-WPR-0105 | Weekly Progress Report Issuance - WPR0105 |  | 2027-01-10 |  | 2027-01-10 |  | 0 | 2027-06-06 | 183
A1-PM-WPR-0106 | Weekly Progress Report Issuance - WPR0106 |  | 2027-01-16 |  | 2027-01-16 |  | 0 | 2027-06-11 | 183
A1-PM-WPR-0107 | Weekly Progress Report Issuance - WPR0107 |  | 2027-01-21 |  | 2027-01-21 |  | 0 | 2027-06-17 | 183
A1-PM-WPR-0108 | Weekly Progress Report Issuance - WPR0108 |  | 2027-01-27 |  | 2027-01-27 |  | 0 | 2027-06-22 | 183
A1-PM-WPR-0109 | Weekly Progress Report Issuance - WPR0109 |  | 2027-02-02 |  | 2027-02-02 |  | 0 | 2027-06-28 | 183
A1-PM-WPR-0110 | Weekly Progress Report Issuance - WPR0110 |  | 2027-02-07 |  | 2027-02-07 |  | 0 | 2027-07-04 | 183
A1-PM-WPR-0111 | Weekly Progress Report Issuance - WPR0111 |  | 2027-02-13 |  | 2027-02-13 |  | 0 | 2027-07-09 | 183
A1-PM-WPR-0112 | Weekly Progress Report Issuance - WPR0112 |  | 2027-02-18 |  | 2027-02-18 |  | 0 | 2027-07-15 | 183
A1-PM-WPR-0113 | Weekly Progress Report Issuance - WPR0113 |  | 2027-02-24 |  | 2027-02-24 |  | 0 | 2027-07-20 | 183
Monthly Progress Report |  | 2026-02-20 | 2027-02-18 | 20-Dec-24 A | 2027-02-18 | 2026-07-21 | 790 | 2027-07-20 | 152
A1-PM-MPR-0001 | Monthly Progress Report Issuance - MPR001 |  |  |  | 20-Dec-24 A |  | 0
A1-PM-MPR-0002 | Monthly Progress Report Issuance - MPR002 |  |  |  | 24-Jan-25 A |  | 0
A1-PM-MPR-0004 | Monthly Progress Report Issuance - MPR004 |  |  |  | 14-Apr-25 A |  | 0
A1-PM-MPR-0005 | Monthly Progress Report Issuance - MPR005 |  |  |  | 13-May-25 A |  | 0
A1-PM-MPR-0003 | Monthly Progress Report Issuance - MPR003 |  |  |  | 17-Jun-25 A |  | 0
A1-PM-MPR-0006 | Monthly Progress Report Issuance - MPR006 |  |  |  | 17-Jun-25 A |  | 0
A1-PM-MPR-0007 | Monthly Progress Report Issuance - MPR007 |  |  |  | 01-Jul-25 A |  | 0
A1-PM-MPR-0008 | Monthly Progress Report Issuance - MPR008 |  |  |  | 22-Aug-25 A |  | 0
A1-PM-MPR-0009 | Monthly Progress Report Issuance - MPR009 |  |  |  | 10-Sep-25 A |  | 0
A1-PM-MPR-0010 | Monthly Progress Report Issuance - MPR010 |  |  |  | 30-Oct-25 A |  | 0
A1-PM-MPR-0011 | Monthly Progress Report Issuance - MPR011 |  |  |  | 21-Nov-25 A |  | 0
A1-PM-MPR-0012 | Monthly Progress Report Issuance - MPR012 |  | 2026-02-20 |  | 2026-02-20 |  | 0 | 2026-07-21 | 190
A1-PM-MPR-0013 | Monthly Progress Report Issuance - MPR013 |  | 2026-03-14 |  | 2026-03-14 |  | 0 | 2026-08-13 | 190
A1-PM-MPR-0014 | Monthly Progress Report Issuance - MPR014 |  | 2026-04-11 |  | 2026-04-11 |  | 0 | 2026-09-10 | 190
A1-PM-MPR-0015 | Monthly Progress Report Issuance - MPR015 |  | 2026-05-03 |  | 2026-05-03 |  | 0 | 2026-10-02 | 190
A1-PM-MPR-0016 | Monthly Progress Report Issuance - MPR016 |  | 2026-05-26 |  | 2026-05-26 |  | 0 | 2026-10-25 | 190
A1-PM-MPR-0017 | Monthly Progress Report Issuance - MPR017 |  | 2026-06-17 |  | 2026-06-17 |  | 0 | 2026-11-16 | 190
A1-PM-MPR-0018 | Monthly Progress Report Issuance - MPR018 |  | 2026-07-15 |  | 2026-07-15 |  | 0 | 2026-12-14 | 190
A1-PM-MPR-0019 | Monthly Progress Report Issuance - MPR019 |  | 2026-08-06 |  | 2026-08-06 |  | 0 | 2027-01-05 | 190
A1-PM-MPR-0020 | Monthly Progress Report Issuance - MPR020 |  | 2026-09-03 |  | 2026-09-03 |  | 0 | 2027-02-02 | 190
A1-PM-MPR-0021 | Monthly Progress Report Issuance - MPR021 |  | 2026-09-26 |  | 2026-09-26 |  | 0 | 2027-02-25 | 190
A1-PM-MPR-0022 | Monthly Progress Report Issuance - MPR022 |  | 2026-10-18 |  | 2026-10-18 |  | 0 | 2027-03-19 | 190
A1-PM-MPR-0023 | Monthly Progress Report Issuance - MPR023 |  | 2026-11-15 |  | 2026-11-15 |  | 0 | 2027-04-16 | 190
A1-PM-MPR-0024 | Monthly Progress Report Issuance - MPR024 |  | 2026-12-08 |  | 2026-12-08 |  | 0 | 2027-05-09 | 190
A1-PM-MPR-0025 | Monthly Progress Report Issuance - MPR025 |  | 2026-12-30 |  | 2026-12-30 |  | 0 | 2027-05-31 | 190
A1-PM-MPR-0026 | Monthly Progress Report Issuance - MPR026 |  | 2027-01-27 |  | 2027-01-27 |  | 0 | 2027-06-28 | 190
A1-PM-MPR-0027 | Monthly Progress Report Issuance - MPR027 |  | 2027-02-18 |  | 2027-02-18 |  | 0 | 2027-07-20 | 190
Team Building Workshops |  | 2026-02-20 | 2026-12-04 | 06-Mar-25 A | 2026-12-04 | 2026-10-05 | 561 | 2027-07-20 | 228
A1-PM-TBW-0001 | TBW01-Team Building Event-001 |  |  |  | 06-Mar-25 A |  | 0
A1-PM-TBW-0002 | TBW01-Team Building Event-002 |  |  |  | 21-Jun-25 A |  | 0
A1-PM-TBW-0003 | TBW01-Team Building Event-003 |  |  |  | 12-Aug-25 A |  | 0
A1-PM-TBW-0004 | TBW01-Team Building Event-004 |  | 2026-02-20 |  | 2026-02-20 |  | 0 | 2026-10-05 | 285
A1-PM-TBW-0005 | TBW01-Team Building Event-005 |  | 2026-05-26 |  | 2026-05-26 |  | 0 | 2027-01-09 | 285
A1-PM-TBW-0006 | TBW01-Team Building Event-006 |  | 2026-08-30 |  | 2026-08-30 |  | 0 | 2027-04-15 | 285
A1-PM-TBW-0007 | TBW01-Team Building Event-007 |  | 2026-12-04 |  | 2026-12-04 |  | 0 | 2027-07-20 | 285
Invoicing Plan |  | 2026-02-20 | 2027-04-05 | 07-Feb-25 A | 2027-04-05 | 2026-06-06 | 655 | 2027-07-20 | 106
A1-PM-MIP-0001 | Monthly Invoicing Plan - MIP001 (Advanced Payment) |  |  |  | 07-Feb-25 A |  | 0
A1-PM-MIP-0002 | Monthly Invoicing Plan - MIP002 |  |  |  | 07-Mar-25 A |  | 0
A1-PM-MIP-0003 | Monthly Invoicing Plan - MIP003 |  |  |  | 10-Apr-25 A |  | 0
A1-PM-MIP-0004 | Monthly Invoicing Plan - MIP004 |  |  |  | 10-May-25 A |  | 0
A1-PM-MIP-0005 | Monthly Invoicing Plan - MIP005 |  |  |  | 21-Jun-25 A |  | 0
A1-PM-MIP-0006 | Monthly Invoicing Plan - MIP006 |  |  |  | 21-Jun-25 A |  | 0
A1-PM-MIP-0007 | Monthly Invoicing Plan - MIP007 |  |  |  | 21-Jun-25 A |  | 0
A1-PM-MIP-0008 | Monthly Invoicing Plan - MIP008 |  |  |  | 29-Aug-25 A |  | 0
A1-PM-MIP-0009 | Monthly Invoicing Plan - MIP009 |  |  |  | 19-Sep-25 A |  | 0
A1-PM-MIP-0010 | Monthly Invoicing Plan - MIP010 |  |  |  | 24-Oct-25 A |  | 0
A1-PM-MIP-0011 | Monthly Invoicing Plan - MIP011 |  |  |  | 11-Nov-25 A |  | 0
A1-PM-MIP-0012 | Monthly Invoicing Plan - MIP012 |  | 2026-02-20 |  | 2026-02-20 |  | 0 | 2026-06-06 | 133
A1-PM-MIP-0013 | Monthly Invoicing Plan - MIP013 |  | 2026-03-08 |  | 2026-03-08 |  | 0 | 2026-06-22 | 133
A1-PM-MIP-0014 | Monthly Invoicing Plan - MIP014 |  | 2026-04-05 |  | 2026-04-05 |  | 0 | 2026-07-20 | 133
A1-PM-MIP-0015 | Monthly Invoicing Plan - MIP015 |  | 2026-05-06 |  | 2026-05-06 |  | 0 | 2026-08-20 | 133
A1-PM-MIP-0016 | Monthly Invoicing Plan - MIP016 |  | 2026-06-05 |  | 2026-06-05 |  | 0 | 2026-09-19 | 133
A1-PM-MIP-0017 | Monthly Invoicing Plan - MIP017 |  | 2026-07-06 |  | 2026-07-06 |  | 0 | 2026-10-20 | 133
A1-PM-MIP-0018 | Monthly Invoicing Plan - MIP018 |  | 2026-08-05 |  | 2026-08-05 |  | 0 | 2026-11-19 | 133
A1-PM-MIP-0019 | Monthly Invoicing Plan - MIP019 |  | 2026-08-05 |  | 2026-08-05 |  | 0 | 2026-11-19 | 133
A1-PM-MIP-0020 | Monthly Invoicing Plan - MIP020 |  | 2026-09-05 |  | 2026-09-05 |  | 0 | 2026-12-20 | 133
A1-PM-MIP-0021 | Monthly Invoicing Plan - MIP021 |  | 2026-10-06 |  | 2026-10-06 |  | 0 | 2027-01-20 | 133
A1-PM-MIP-0022 | Monthly Invoicing Plan - MIP022 |  | 2026-11-05 |  | 2026-11-05 |  | 0 | 2027-02-19 | 133
A1-PM-MIP-0023 | Monthly Invoicing Plan - MIP023 |  | 2026-12-06 |  | 2026-12-06 |  | 0 | 2027-03-22 | 133
A1-PM-MIP-0024 | Monthly Invoicing Plan - MIP024 |  | 2027-01-05 |  | 2027-01-05 |  | 0 | 2027-04-21 | 133
A1-PM-MIP-0025 | Monthly Invoicing Plan - MIP025 |  | 2027-02-05 |  | 2027-02-05 |  | 0 | 2027-05-22 | 133
A1-PM-MIP-0026 | Monthly Invoicing Plan - MIP026 |  | 2027-03-08 |  | 2027-03-08 |  | 0 | 2027-06-22 | 133
A1-PM-MIP-0027 | Monthly Invoicing Plan - MIP027 |  | 2027-04-05 |  | 2027-04-05 |  | 0 | 2027-07-20 | 133
Home Office Services |  | 2026-02-20 | 2027-07-14 | 14-Nov-24 A | 2027-07-14 | 2026-02-21 | 695 | 2027-07-20 | 4
Detailed Design - EDDR |  | 2026-02-20 | 2026-09-25 | 27-Nov-24 A | 2026-09-25 | 2026-02-21 | 511 | 2027-07-20 | 213
Package 1&2 |  |  |  | 01-Aug-25 A | 22-Aug-25 A |  | 0
Deliverables to be Recieved from Pkg 1&2 |  |  |  | 01-Aug-25 A | 22-Aug-25 A |  | 0
1B-DE-P12-0001 | Civil / Architecture / Structure - 63 Deleverables |  |  |  | 01-Aug-25 A |  | 0
1B-DE-P12-0011 | Construction - 30 Deleverables |  |  |  | 04-Aug-25 A |  | 0
1B-DE-P12-0021 | Electrical Engineering - 73 Deleverables |  |  |  | 05-Aug-25 A |  | 0
1B-DE-P12-0031 | HVAC - 26 Deleverables |  |  |  | 06-Aug-25 A |  | 0
1B-DE-P12-0041 | Instrument and Control System - 90 Deleverables |  |  |  | 07-Aug-25 A |  | 0
1B-DE-P12-0051 | IT/TELECOM - 69 Deleverables |  |  |  | 08-Aug-25 A |  | 0
1B-DE-P12-0061 | Material and Corrosion - 24 Deleverables |  |  |  | 11-Aug-25 A |  | 0
1B-DE-P12-0071 | Mechanical Rotating - 19 Deleverables |  |  |  | 12-Aug-25 A |  | 0
1B-DE-P12-0081 | Mechanical Rotating/Package - 9 Deleverables |  |  |  | 13-Aug-25 A |  | 0
1B-DE-P12-0091 | MS-Mechanical Static - 9 Deleverables |  |  |  | 14-Aug-25 A |  | 0
1B-DE-P12-0101 | Piping Engineering - 43 Deleverables |  |  |  | 15-Aug-25 A |  | 0
1B-DE-P12-0111 | Process and Safety Engineering - 38 Deleverables |  |  |  | 18-Aug-25 A |  | 0
1B-DE-P12-0121 | Project Control - 29 Deleverables |  |  |  | 19-Aug-25 A |  | 0
1B-DE-P12-0131 | Project Control Quality - 14 Deleverables |  |  |  | 20-Aug-25 A |  | 0
1B-DE-P12-0141 | Project Management - 86 Deleverables |  |  |  | 21-Aug-25 A |  | 0
1B-DE-P12-0151 | Safety - 11 Deleverables |  |  |  | 22-Aug-25 A |  | 0
Package 3 |  | 2026-02-20 | 2026-09-25 | 27-Nov-24 A | 2026-09-25 | 2026-02-21 | 511 | 2027-07-20 | 213
Milestone |  | 2026-09-25 | 2026-09-25 | 11-Dec-24 A | 2026-09-25 | 2027-01-20 | 467 | 2027-01-20 | 84
General |  | 2026-09-25 | 2026-09-25 | 11-Dec-24 A | 2026-09-25 | 2027-01-20 | 467 | 2027-01-20 | 84
Turnaround |  |  |  | 11-Dec-24 A | 11-Dec-24 A |  | 0
A40690 | Commencement of TA Engginering Works |  |  | 11-Dec-24 A |  |  | 0
Balance of Plant |  | 2026-09-25 | 2026-09-25 | 11-Dec-24 A | 2026-09-25 | 2027-01-20 | 467 | 2027-01-20 | 84
A120 | Commencement of BOP Engineering Works |  |  | 11-Dec-24 A |  |  | 0
A40320 | Completion of Engineering | 2026-09-25 |  | 2026-09-25 |  | 2027-01-20 | 0 |  | 84
General / Common |  | 2026-02-20 | 2026-02-20 | 27-Nov-24 A | 21-Jan-25 A | 2026-03-27 | 40 | 2026-03-27
MSE1300 | Site Survey & Data Collection / FEED Verification | 2026-02-20 | 2026-02-20 | 27-Nov-24 A | 21-Jan-25 A | 2026-03-27 | 40 | 2026-03-27
Project Management |  | 2026-02-20 | 2026-06-16 | 04-Dec-24 A | 2026-06-16 | 2026-02-21 | 498 | 2027-07-20 | 285
Preliminaries |  | 2026-02-20 | 2026-02-20 | 04-Dec-24 A | 23-May-25 A | 2026-02-21 | 32 | 2026-03-27
A53280 | Engineering Subcontractor KOM | 2026-02-20 | 2026-02-20 | 04-Dec-24 A | 04-Dec-24 A | 2026-02-21 | 1 | 2026-02-21
A53290 | LOA Request | 2026-02-20 | 2026-02-20 | 05-Dec-24 A | 13-Dec-24 A | 2026-03-02 | 8 | 2026-03-02
A53330 | Medicals and CICPA Passes | 2026-02-20 | 2026-02-20 | 05-Dec-24 A | 24-Dec-24 A | 2026-03-02 | 16 | 2026-03-02
A53340 | Site Visit for BOP | 2026-02-20 | 2026-02-20 | 25-Dec-24 A | 31-Dec-24 A | 2026-03-02 | 6 | 2026-03-02
A40350 | Site Visit for TA Activities (CSA, Piping) | 2026-02-20 | 2026-02-20 | 09-Jan-25 A | 16-Jan-25 A | 2026-03-27 | 6 | 2026-03-27
A40360 | Site Visit Report Before TA | 2026-02-20 | 2026-02-20 | 09-Jan-25 A | 16-Jan-25 A | 2026-03-27 | 6 | 2026-03-27
A53320 | Receipt of Source Data | 2026-02-20 | 2026-02-20 | 05-Dec-24 A | 23-May-25 A | 2026-02-21 | 8 | 2026-02-21
TA related Inputs |  | 2026-02-20 | 2026-06-16 | 12-Dec-24 A | 2026-06-16 | 2026-02-21 | 492 | 2027-07-20 | 285
TA Phase |  | 2026-02-20 | 2026-02-20 | 12-Dec-24 A | 22-Apr-25 A | 2026-02-21 | 202 | 2026-03-27
A55740 | Receipt of HSE third party offers by RAD (Descon) | 2026-02-20 | 2026-02-20 | 12-Dec-24 A | 12-Dec-24 A | 2026-03-02 | 1 | 2026-03-02
A40330 | Receipt of Approved ICT Site Adequacy Report | 2026-02-20 | 2026-02-20 | 12-Feb-25 A | 13-Feb-25 A | 2026-03-27 | 1 | 2026-03-27
A40340 | Receipt of Approved Electrical Site Adequacy Report | 2026-02-20 | 2026-02-20 | 12-Feb-25 A | 13-Feb-25 A | 2026-03-27 | 1 | 2026-03-27
A28140 | Receipt of Approved Topo, UG & geotechnical investigation report | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 22-Apr-25 A | 2026-02-21 | 1 | 2026-02-21
Vendor Offer Receipt (to enable Eng Subcon to perform TBE) |  |  |  | 09-Jan-25 A | 15-Jul-25 A |  | 23
Piping |  |  |  | 03-Feb-25 A | 24-Feb-25 A |  | 8
A53550 | Piping Bulk_All Technical Vendor Offers Receipt |  |  |  | 03-Feb-25 A |  | 0
A53560 | Manual Valves_All Technical Vendor Offers Receipt |  |  |  | 11-Feb-25 A |  | 0
A53590 | Rigid Struts_All Technical Vendor Offers Receipt |  |  |  | 17-Feb-25 A |  | 0
A53580 | Spring Hangers_All Technical Vendor Offers Receipt |  |  |  | 21-Feb-25 A |  | 0
A53570 | Piping Speciality Items_All Technical Vendor Offers Receipt |  |  |  | 24-Feb-25 A |  | 0
Mechanical |  |  |  | 07-Feb-25 A | 07-May-25 A |  | 0
A53440 | Pressure Vessels & Internals_All Technical Vendor Offers Receipt |  |  |  | 07-Feb-25 A |  | 0
A53400 | Heat Exchangers_All Technical Vendor Offers Receipt |  |  |  | 14-Mar-25 A |  | 0
A53410 | Centrifugal Pump_All Technical Vendor Offers Receipt |  |  |  | 21-Mar-25 A |  | 0
A53430 | Coalscer_All Technical Vendor Offers Receipt |  |  |  | 21-Mar-25 A |  | 0
A53420 | EOT Crane_All Technical Vendor Offers Receipt |  |  |  | 07-May-25 A |  | 0
Electrical |  |  |  | 09-Jan-25 A | 13-May-25 A |  | 0
A53600 | Transformer (Power And Distribution)_All Technical Vendor Offers Receipt |  |  |  | 09-Jan-25 A |  | 0
A53670 | Neutral Grounding Resistor_All Technical Vendor Offers Receipt |  |  |  | 17-Jan-25 A |  | 0
A53630 | AC UPS_All Technical Vendor Offers Receipt |  |  |  | 22-Jan-25 A |  | 0
A53680 | Emergency Diesel Generator Set_All Technical Vendor Offers Receipt |  |  |  | 22-Jan-25 A |  | 0
A53640 | DC UPS_All Technical Vendor Offers Receipt |  |  |  | 21-Feb-25 A |  | 0
A53690 | LV Variable Frequency Drive_All Technical Vendor Offers Receipt |  |  |  | 21-Feb-25 A |  | 0
A53620 | LV Switchgear_All Technical Vendor Offers Receipt |  |  |  | 28-Feb-25 A |  | 0
A53610 | 11KV Switchgear_All Technical Vendor Offers Receipt |  |  |  | 06-Mar-25 A |  | 0
A53650 | Capacitor Bank_All Technical Vendor Offers Receipt |  |  |  | 21-Apr-25 A |  | 0
A53660 | Power, Control And Earthing Cables_All Technical Vendor Offers Receipt |  |  |  | 13-May-25 A |  | 0
Instrumentation & Controls |  |  |  | 23-Apr-25 A | 15-Jul-25 A |  | 0
A25950 | Level Gauges (Magnetic Type)_All Technical Vendor Offers Receipt |  |  |  | 23-Apr-25 A |  | 0
A53740 | ICSS System_All Technical Vendor Offers Receipt |  |  |  | 24-Apr-25 A |  | 0
A25960 | Control Valves_All Technical Vendor Offers Receipt |  |  |  | 27-Apr-25 A |  | 0
A25990 | Motor Operated Valves_All Technical Vendor Offers Receipt |  |  |  | 27-Apr-25 A |  | 0
A53700 | Electronic Transmitters_All Technical Vendor Offers Receipt |  |  |  | 28-Apr-25 A |  | 0
A25980 | Level Transmitters (GWR type)_All Technical Vendor Offers Receipt |  |  |  | 28-Apr-25 A |  | 0
A53710 | Flow Element (Orifice Plate)_All Technical Vendor Offers Receipt |  |  |  | 29-Apr-25 A |  | 0
A25910 | Flow Element (Venturi Tube)_All Technical Vendor Offers Receipt |  |  |  | 30-Apr-25 A |  | 0
A25930 | Temperature Gauges / Pressure Gauges_All Technical Vendor Offers Receipt |  |  |  | 30-Apr-25 A |  | 0
A26000 | ESD Valves_All Technical Vendor Offers Receipt |  |  |  | 30-Apr-25 A |  | 0
A26010 | Rotameter_All Technical Vendor Offers Receipt |  |  |  | 01-May-25 A |  | 0
A25920 | Temperature Element / Thermowell_All Technical Vendor Offers Receipt |  |  |  | 07-May-25 A |  | 0
A53750 | Fire Detection System & LFCP_All Technical Vendor Offers Receipt |  |  |  | 12-Jun-25 A |  | 0
A25970 | Fire & Gas Detectors_All Technical Vendor Offers Receipt |  |  |  | 05-Jul-25 A |  | 0
A53720 | Instrument Cables_All Technical Vendor Offers Receipt |  |  |  | 05-Jul-25 A |  | 0
A53730 | Junction Boxes_All Technical Vendor Offers Receipt |  |  |  | 05-Jul-25 A |  | 0
A25940 | Analyzers_All Technical Vendor Offers Receipt |  |  |  | 15-Jul-25 A |  | 0
Telecom |  |  |  | 26-Apr-25 A | 22-May-25 A |  | 0
A53760 | Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_All Technical Vendor Offers Receipt |  |  |  | 26-Apr-25 A |  | 0
A53770 | Telecom Cables_All Technical Vendor Offers Receipt |  |  |  | 22-May-25 A |  | 0
HVAC |  |  |  | 03-Jun-25 A | 03-Jun-25 A |  | 0
A53780 | HVAC Equipments_All Technical Vendor Offers Receipt |  |  |  | 03-Jun-25 A |  | 0
Ist Issuance of Vendor Data Receipt-1 |  | 2026-02-20 | 2026-05-22 | 03-Feb-25 A | 2026-05-22 | 2026-03-19 | 354 | 2027-07-06 | 292
Piping |  | 2026-02-20 | 2026-05-22 | 24-Mar-25 A | 2026-05-22 | 2026-05-15 | 73 | 2027-06-28 | 285
A53830 | Rigid Struts_1st issuance of Vendor Data Receipt |  |  |  | 24-Mar-25 A |  | 0
A53810 | Piping Speciality Items_1st issuance of Vendor Data Receipt |  |  |  | 05-Aug-25 A |  | 0
A53790 | Piping Bulk_1st issuance of Vendor Data Receipt |  | 2026-02-20 |  | 2026-02-20 |  | 0 | 2027-06-28 | 351
A53800 | Manual Valves_1st issuance of Vendor Data Receipt |  | 2026-02-20 |  | 2026-02-20 |  | 0 | 2026-05-15 | 61
A53820 | Spring Hangers_1st issuance of Vendor Data Receipt |  | 2026-05-22 |  | 2026-05-22 |  | 0 | 2027-04-22 | 238
Mechanical |  | 2026-02-27 | 2026-02-27 | 27-Aug-25 A | 2026-02-27 | 2027-06-28 | 116 | 2027-06-28 | 346
A28770 | Compressors (FG & OG)_1st issuance of Vendor Data Receipt |  |  |  | 27-Aug-25 A |  | 0
A53500 | Heat Exchangers_1st issuance of Vendor Data Receipt |  |  |  | 02-Sep-25 A |  | 0
A53540 | Pressure Vessels & Internals_1st issuance of Vendor Data Receipt |  |  |  | 02-Sep-25 A |  | 0
A28780 | PSA Unit_1st issuance of Vendor Data Receipt |  |  |  | 09-Sep-25 A |  | 0
A53510 | Centrifugal Pump_1st issuance of Vendor Data Receipt |  |  |  | 30-Oct-25 A |  | 0
A53520 | EOT Crane_1st issuance of Vendor Data Receipt |  |  |  | 04-Nov-25 A |  | 0
A53530 | Coalscer_1st issuance of Vendor Data Receipt |  | 2026-02-27 |  | 2026-02-27 |  | 0 | 2027-06-28 | 346
Electrical |  | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-03-19 | 0 | 2027-06-28 | 351
A53840 | Transformer (Power And Distribution)_1st issuance of Vendor Data Receipt |  | 2026-02-20 |  | 2026-02-20 |  | 0 | 2026-11-23 | 196
A53850 | 11KV Switchgear_1st issuance of Vendor Data Receipt |  | 2026-02-20 |  | 2026-02-20 |  | 0 | 2027-06-28 | 351
A53860 | LV Switchgear_1st issuance of Vendor Data Receipt |  | 2026-02-20 |  | 2026-02-20 |  | 0 | 2027-06-28 | 351
A53870 | AC UPS_1st issuance of Vendor Data Receipt |  | 2026-02-20 |  | 2026-02-20 |  | 0 | 2027-06-28 | 351
A53880 | DC UPS_1st issuance of Vendor Data Receipt |  | 2026-02-20 |  | 2026-02-20 |  | 0 | 2026-03-19 | 20
A53890 | Capacitor Bank_1st issuance of Vendor Data Receipt |  | 2026-02-20 |  | 2026-02-20 |  | 0 | 2027-06-28 | 351
A53900 | Power, Control And Earthing Cables_1st issuance of Vendor Data Receipt |  | 2026-02-20 |  | 2026-02-20 |  | 0 | 2027-06-28 | 351
A53910 | Neutral Grounding Resistor_1st issuance of Vendor Data Receipt |  | 2026-02-20 |  | 2026-02-20 |  | 0 | 2027-06-28 | 351
A53920 | Emergency Diesel Generator Set_1st issuance of Vendor Data Receipt |  | 2026-02-20 |  | 2026-02-20 |  | 0 | 2027-01-20 | 239
A53930 | LV Variable Frequency Drive_1st issuance of Vendor Data Receipt |  | 2026-02-20 |  | 2026-02-20 |  | 0 | 2027-06-28 | 351
Instrumentation & Controls |  | 2026-02-20 | 2026-03-27 | 03-Feb-25 A | 2026-03-27 | 2026-03-19 | 354 | 2027-07-06 | 332
A53990 | Analyzers_1st issuance of Vendor Data Receipt |  |  |  | 03-Feb-25 A |  | 0
A54020 | Fire & Gas Detectors_1st issuance of Vendor Data Receipt |  |  |  | 17-Mar-25 A |  | 0
A53970 | Temperature Element / Thermowell_1st issuance of Vendor Data Receipt |  |  |  | 18-Mar-25 A |  | 0
A53980 | Temperature Gauges / Pressure Gauges_1st issuance of Vendor Data Receipt |  |  |  | 29-May-25 A |  | 0
A54060 | Rotameter_1st issuance of Vendor Data Receipt |  |  |  | 29-May-25 A |  | 0
A54070 | Instrument Cables_1st issuance of Vendor Data Receipt |  |  |  | 30-Nov-25 A |  | 0
A53950 | Flow Element (Orifice Plate)_1st issuance of Vendor Data Receipt |  | 2026-02-20 |  | 2026-02-20 |  | 0 | 2027-06-28 | 351
A53960 | Flow Element (Venturi Tube)_1st issuance of Vendor Data Receipt |  | 2026-02-20 |  | 2026-02-20 |  | 0 | 2027-06-28 | 351
A54000 | Level Gauges (Magnetic Type)_1st issuance of Vendor Data Receipt |  | 2026-02-20 |  | 2026-02-20 |  | 0 | 2027-06-28 | 351
A54010 | Control Valves_1st issuance of Vendor Data Receipt |  | 2026-02-20 |  | 2026-02-20 |  | 0 | 2027-06-28 | 351
A54030 | Level Transmitters (GWR type)_1st issuance of Vendor Data Receipt |  | 2026-02-20 |  | 2026-02-20 |  | 0 | 2027-06-28 | 351
A54040 | Motor Operated Valves_1st issuance of Vendor Data Receipt |  | 2026-02-20 |  | 2026-02-20 |  | 0 | 2027-06-28 | 351
A54050 | ESD Valves_1st issuance of Vendor Data Receipt |  | 2026-02-20 |  | 2026-02-20 |  | 0 | 2027-06-28 | 351
A54090 | ICSS System_1st issuance of Vendor Data Receipt |  | 2026-02-20 |  | 2026-02-20 |  | 0 | 2027-06-28 | 351
A54100 | Fire Detection System & LFCP_1st issuance of Vendor Data Receipt |  | 2026-02-20 |  | 2026-02-20 |  | 0 | 2026-03-19 | 20
A54080 | Junction Boxes_1st issuance of Vendor Data Receipt |  | 2026-03-12 |  | 2026-03-12 |  | 0 | 2027-07-06 | 343
A53940 | Electronic Transmitters_1st issuance of Vendor Data Receipt |  | 2026-03-27 |  | 2026-03-27 |  | 0 | 2027-06-28 | 325
Telecom |  | 2026-02-20 | 2026-02-20 | 18-Mar-25 A | 2026-02-20 | 2027-06-28 | 2 | 2027-06-28 | 351
A54120 | Telecom Cables_1st issuance of Vendor Data Receipt |  |  |  | 18-Mar-25 A |  | 0
A54110 | Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_1st issuance of Vendor Data Receipt |  | 2026-02-20 |  | 2026-02-20 |  | 0 | 2027-06-28 | 351
HVAC |  | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2027-06-28 | 0 | 2027-06-28 | 351
A54130 | HVAC Equipments_1st issuance of Vendor Data Receipt |  | 2026-02-20 |  | 2026-02-20 |  | 0 | 2027-06-28 | 351
Approved Vender Data Receipt |  | 2026-02-20 | 2026-06-16 | 04-Mar-25 A | 2026-06-16 | 2026-03-19 | 291 | 2027-07-20 | 285
Piping |  | 2026-02-20 | 2026-06-16 | 26-Aug-25 A | 2026-06-16 | 2026-03-19 | 83 | 2027-07-20 | 285
A54160 | Piping Speciality Items_Approved Vendor Data Receipt |  |  |  | 26-Aug-25 A |  | 0
A54180 | Rigid Struts_Approved Vendor Data Receipt |  | 2026-02-20 |  | 2026-02-20 |  | 0 | 2026-03-19 | 20
A54150 | Manual Valves_Approved Vendor Data Receipt |  | 2026-03-05 |  | 2026-03-05 |  | 0 | 2026-05-29 | 61
A54140 | Piping Bulk_Approved Vendor Data Receipt |  | 2026-03-16 |  | 2026-03-16 |  | 0 | 2027-07-20 | 351
A54170 | Spring Hangers_Approved Vendor Data Receipt |  | 2026-06-16 |  | 2026-06-16 |  | 0 | 2027-05-14 | 238
Mechanical |  | 2026-02-20 | 2026-03-24 | 10-Jun-25 A | 2026-03-24 | 2026-03-19 | 130 | 2027-07-20 | 346
A55640 | PSA Unit_Approved Vendor Data Receipt |  |  |  | 10-Jun-25 A |  | 0
A53450 | Heat Exchangers_Approved Vendor Data Receipt |  |  |  | 02-Sep-25 A |  | 0
A53490 | Pressure Vessels & Internals_Approved Vendor Data Receipt |  |  |  | 02-Sep-25 A |  | 0
A28150 | Compressors (FG & OG)_Approved Vendor Data Receipt |  |  |  | 19-Sep-25 A |  | 0
A53460 | Centrifugal Pump_Approved Vendor Data Receipt |  | 2026-02-20 |  | 2026-02-20 |  | 0 | 2026-03-19 | 20
A53470 | EOT Crane_Approved Vendor Data Receipt |  | 2026-02-20 |  | 2026-02-20 |  | 0 | 2026-03-19 | 20
A53480 | Coalscer_Approved Vendor Data Receipt |  | 2026-03-24 |  | 2026-03-24 |  | 0 | 2027-07-20 | 346
Electrical |  | 2026-02-20 | 2026-03-16 | 2026-02-20 | 2026-03-16 | 2026-03-19 | 17 | 2027-07-20 | 351
A54230 | DC UPS_Approved Vendor Data Receipt |  | 2026-02-20 |  | 2026-02-20 |  | 0 | 2026-03-19 | 20
A54270 | Emergency Diesel Generator Set_Approved Vendor Data Receipt |  | 2026-02-20 |  | 2026-02-20 |  | 0 | 2027-01-20 | 239
A55650 | Notice to proceed - All Electrical equipment footprint & load data to freeze Electrical building Equipment layout |  | 2026-02-20 |  | 2026-02-20 |  | 0 | 2027-07-20 | 368
A54190 | Transformer (Power And Distribution)_Approved Vendor Data Receipt |  | 2026-03-16 |  | 2026-03-16 |  | 0 | 2026-12-22 | 201
A54200 | 11KV Switchgear_Approved Vendor Data Receipt |  | 2026-03-16 |  | 2026-03-16 |  | 0 | 2027-07-20 | 351
A54210 | LV Switchgear_Approved Vendor Data Receipt |  | 2026-03-16 |  | 2026-03-16 |  | 0 | 2027-07-20 | 351
A54220 | AC UPS_Approved Vendor Data Receipt |  | 2026-03-16 |  | 2026-03-16 |  | 0 | 2027-07-20 | 351
A54240 | Capacitor Bank_Approved Vendor Data Receipt |  | 2026-03-16 |  | 2026-03-16 |  | 0 | 2027-07-20 | 351
A54250 | Power, Control And Earthing Cables_Approved Vendor Data Receipt |  | 2026-03-16 |  | 2026-03-16 |  | 0 | 2027-07-20 | 351
A54260 | Neutral Grounding Resistor_Approved Vendor Data Receipt |  | 2026-03-16 |  | 2026-03-16 |  | 0 | 2027-07-20 | 351
A54280 | LV Variable Frequency Drive_Approved Vendor Data Receipt |  | 2026-03-16 |  | 2026-03-16 |  | 0 | 2027-07-20 | 351
Instrumentation & Controls |  | 2026-02-20 | 2026-04-21 | 04-Mar-25 A | 2026-04-21 | 2026-03-19 | 291 | 2027-07-20 | 325
A54340 | Analyzers_Approved Vendor Data Receipt |  |  |  | 04-Mar-25 A |  | 0
A54370 | Fire & Gas Detectors_Approved Vendor Data Receipt |  |  |  | 09-Apr-25 A |  | 0
A54410 | Rotameter_Approved Vendor Data Receipt |  |  |  | 23-May-25 A |  | 0
A54330 | Temperature Gauges / Pressure Gauges_Approved Vendor Data Receipt |  |  |  | 29-May-25 A |  | 0
A55660 | Notice to proceed - All ICT equipment footprint & load data to freeze SIS Equipment layout |  |  |  | 23-Jun-25 A |  | 0
A54320 | Temperature Element / Thermowell_Approved Vendor Data Receipt |  | 2026-02-20 |  | 2026-02-20 |  | 0 | 2026-03-19 | 20
A54420 | Instrument Cables_Approved Vendor Data Receipt |  | 2026-02-20 |  | 2026-02-20 |  | 0 | 2026-03-19 | 20
A54450 | Fire Detection System & LFCP_Approved Vendor Data Receipt |  | 2026-02-20 |  | 2026-02-20 |  | 0 | 2026-03-19 | 20
A54300 | Flow Element (Orifice Plate)_Approved Vendor Data Receipt |  | 2026-03-16 |  | 2026-03-16 |  | 0 | 2027-07-20 | 351
A54310 | Flow Element (Venturi Tube)_Approved Vendor Data Receipt |  | 2026-03-16 |  | 2026-03-16 |  | 0 | 2027-07-20 | 351
A54350 | Level Gauges (Magnetic Type)_Approved Vendor Data Receipt |  | 2026-03-16 |  | 2026-03-16 |  | 0 | 2027-07-20 | 351
A54360 | Control Valves_Approved Vendor Data Receipt |  | 2026-03-16 |  | 2026-03-16 |  | 0 | 2027-07-20 | 351
A54380 | Level Transmitters (GWR type)_Approved Vendor Data Receipt |  | 2026-03-16 |  | 2026-03-16 |  | 0 | 2027-07-20 | 351
A54390 | Motor Operated Valves_Approved Vendor Data Receipt |  | 2026-03-16 |  | 2026-03-16 |  | 0 | 2027-07-20 | 351
A54400 | ESD Valves_Approved Vendor Data Receipt |  | 2026-03-16 |  | 2026-03-16 |  | 0 | 2027-07-20 | 351
A54440 | ICSS System_Approved Vendor Data Receipt |  | 2026-03-16 |  | 2026-03-16 |  | 0 | 2027-07-20 | 351
A54430 | Junction Boxes_Approved Vendor Data Receipt |  | 2026-03-26 |  | 2026-03-26 |  | 0 | 2027-07-20 | 343
A54290 | Electronic Transmitters_Approved Vendor Data Receipt |  | 2026-04-21 |  | 2026-04-21 |  | 0 | 2027-07-20 | 325
Telecom |  | 2026-02-20 | 2026-03-16 | 2026-02-20 | 2026-03-16 | 2026-03-19 | 17 | 2027-07-20 | 351
A54470 | Telecom Cables_Approved Vendor Data Receipt |  | 2026-02-20 |  | 2026-02-20 |  | 0 | 2026-03-19 | 20
A54460 | Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_Approved Vendor Data Receipt |  | 2026-03-16 |  | 2026-03-16 |  | 0 | 2027-07-20 | 351
HVAC |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2027-07-20 | 0 | 2027-07-20 | 351
A54480 | HVAC Equipments_Approved Vendor Data Receipt |  | 2026-03-16 |  | 2026-03-16 |  | 0 | 2027-07-20 | 351
Workshops / Studies / Model Reviews |  | 2026-02-20 | 2026-03-16 | 05-May-25 A | 2026-03-16 | 2026-03-02 | 182 | 2026-11-23 | 179
A53350 | Design Review | 2026-02-20 | 2026-02-20 | 05-May-25 A | 09-May-25 A | 2026-03-02 | 3 | 2026-03-02
A53370 | 30% Model Review | 2026-02-20 | 2026-02-20 | 13-May-25 A | 16-May-25 A | 2026-03-02 | 1 | 2026-03-02
A53360 | Plot Plan Review | 2026-02-20 | 2026-02-20 | 13-May-25 A | 21-May-25 A | 2026-03-02 | 1 | 2026-03-02
A25330 | PHA (HAZID/ENVID/OHID) | 2026-02-20 | 2026-02-20 | 03-Jul-25 A | 03-Jul-25 A | 2026-03-02 | 5 | 2026-03-02
A25340 | ISD Workshop | 2026-02-20 | 2026-02-20 | 04-Jul-25 A | 04-Jul-25 A | 2026-04-02 | 1 | 2026-04-02
A25350 | HAZOP | 2026-02-20 | 2026-02-20 | 08-Jul-25 A | 20-Jul-25 A | 2026-03-02 | 7 | 2026-03-02
A55690 | Bow-Tie | 2026-02-20 | 2026-02-20 | 12-Aug-25 A | 12-Aug-25 A | 2026-03-02 | 1 | 2026-03-02
A53260 | SIL/LOPA | 2026-02-20 | 2026-02-20 | 17-Aug-25 A | 20-Aug-25 A | 2026-03-02 | 2 | 2026-03-02
A55730 | Constructability Review | 2026-02-20 | 2026-02-20 | 27-Aug-25 A | 27-Aug-25 A | 2026-03-19 | 1 | 2026-03-19
A55720 | SIMOPS | 2026-02-20 | 2026-02-20 | 28-Aug-25 A | 28-Aug-25 A | 2026-03-19 | 1 | 2026-03-19
A53380 | 60% Model Review | 2026-02-20 | 2026-02-20 | 08-Sep-25 A | 18-Sep-25 A | 2026-03-02 | 17 | 2026-03-02
A55680 | HSEIA Screening | 2026-02-20 | 2026-02-20 | 01-Jan-26 A | 06-Jan-26 A | 2026-04-02 | 1 | 2026-04-02
A55700 | E-HAZOP | 2026-02-20 | 2026-02-23 | 2026-02-20 | 2026-02-23 | 2026-03-17 | 1 | 2026-03-18 | 18
A55710 | ALARP Demonstration | 2026-02-20 | 2026-02-23 | 2026-02-20 | 2026-02-23 | 2026-03-26 | 1 | 2026-03-27 | 24
A53270 | Energy Review | 2026-02-23 | 2026-02-24 | 2026-02-23 | 2026-02-24 | 2026-03-18 | 1 | 2026-03-19 | 18
A53390 | 90% Model Review | 2026-02-26 | 2026-03-06 | 2026-02-26 | 2026-03-06 | 2026-03-19 | 6 | 2026-03-27 | 15
A53250 | PHSER-3 | 2026-03-13 | 2026-03-16 | 2026-03-13 | 2026-03-16 | 2026-11-20 | 1 | 2026-11-23 | 179
Turnaround (TA) |  | 2026-02-20 | 2026-02-20 | 27-Nov-24 A | 21-Jun-25 A | 2026-02-21 | 208 | 2026-03-27
TA - Engineering Workpack |  | 2026-02-20 | 2026-02-20 | 27-Nov-24 A | 12-Apr-25 A | 2026-03-27 | 202 | 2026-03-27
B1-DE-TA-TAD-0001 | Verify TA Dossier & Provid List of Missing Materials to EPC Contractor | 2026-02-20 | 2026-02-20 | 07-Jan-25 A | 27-Mar-25 A | 2026-03-27 | 17 | 2026-03-27
B1-DE-TA-TAD-0002 | Engineering Support During Pre-TA & TA Phase |  |  | 17-Jan-25 A | 12-Apr-25 A |  | 53
Piping Driven - Workpack |  | 2026-02-20 | 2026-02-20 | 27-Nov-24 A | 10-Feb-25 A | 2026-03-27 | 28 | 2026-03-27
Preliminary Workpack |  | 2026-02-20 | 2026-02-20 | 27-Nov-24 A | 13-Jan-25 A | 2026-03-27 | 5 | 2026-03-27
B1-DE-TA-PIP-0001 | Workpack Piping Nos. 0001 Preliminary Issuance | 2026-02-20 | 2026-02-20 | 27-Nov-24 A | 18-Dec-24 A | 2026-03-27 | 1 | 2026-03-27
B1-DE-TA-PIP-0002 | Workpack Piping Nos. 0002 Preliminary Issuance | 2026-02-20 | 2026-02-20 | 27-Nov-24 A | 18-Dec-24 A | 2026-03-27 | 1 | 2026-03-27
B1-DE-TA-PIP-0003 | Workpack Piping Nos. 0003 Preliminary Issuance | 2026-02-20 | 2026-02-20 | 27-Nov-24 A | 18-Dec-24 A | 2026-03-27 | 1 | 2026-03-27
B1-DE-TA-PIP-0004 | Workpack Piping Nos. 0004 Preliminary Issuance | 2026-02-20 | 2026-02-20 | 27-Nov-24 A | 18-Dec-24 A | 2026-03-27 | 1 | 2026-03-27
B1-DE-TA-PIP-0005 | Workpack Piping Nos. 0005 Preliminary Issuance | 2026-02-20 | 2026-02-20 | 27-Nov-24 A | 18-Dec-24 A | 2026-03-27 | 1 | 2026-03-27
B1-DE-TA-PIP-0006 | Workpack Piping Nos. 0006 Preliminary Issuance | 2026-02-20 | 2026-02-20 | 27-Nov-24 A | 18-Dec-24 A | 2026-03-27 | 1 | 2026-03-27
B1-DE-TA-PIP-0007 | Workpack Piping Nos. 0007 Preliminary Issuance | 2026-02-20 | 2026-02-20 | 27-Nov-24 A | 18-Dec-24 A | 2026-03-27 | 1 | 2026-03-27
B1-DE-TA-PIP-0008 | Workpack Piping Nos. 0008 Preliminary Issuance | 2026-02-20 | 2026-02-20 | 27-Nov-24 A | 18-Dec-24 A | 2026-03-27 | 1 | 2026-03-27
B1-DE-TA-PIP-0009 | Workpack Piping Nos. 0009 Preliminary Issuance | 2026-02-20 | 2026-02-20 | 27-Nov-24 A | 18-Dec-24 A | 2026-03-27 | 1 | 2026-03-27
B1-DE-TA-PIP-0010 | Workpack Piping Nos. 0010 Preliminary Issuance | 2026-02-20 | 2026-02-20 | 27-Nov-24 A | 18-Dec-24 A | 2026-03-27 | 1 | 2026-03-27
B1-DE-TA-PIP-0011 | Workpack Piping Nos. 0011 Preliminary Issuance | 2026-02-20 | 2026-02-20 | 27-Nov-24 A | 18-Dec-24 A | 2026-03-27 | 1 | 2026-03-27
B1-DE-TA-PIP-0012 | Workpack Piping Nos. 0012 Preliminary Issuance | 2026-02-20 | 2026-02-20 | 27-Nov-24 A | 18-Dec-24 A | 2026-03-27 | 1 | 2026-03-27
B1-DE-TA-PIP-0013 | Workpack Piping Nos. 0013 Preliminary Issuance | 2026-02-20 | 2026-02-20 | 27-Nov-24 A | 18-Dec-24 A | 2026-03-27 | 1 | 2026-03-27
B1-DE-TA-PIP-0014 | Workpack Piping Nos. 0014 Preliminary Issuance | 2026-02-20 | 2026-02-20 | 27-Nov-24 A | 18-Dec-24 A | 2026-03-27 | 1 | 2026-03-27
B1-DE-TA-PIP-0015 | Workpack Piping Nos. 0015 Preliminary Issuance | 2026-02-20 | 2026-02-20 | 27-Nov-24 A | 18-Dec-24 A | 2026-03-27 | 1 | 2026-03-27
B1-DE-TA-PIP-0016 | Workpack Piping Nos. 0016 Preliminary Issuance | 2026-02-20 | 2026-02-20 | 27-Nov-24 A | 18-Dec-24 A | 2026-03-27 | 1 | 2026-03-27
B1-DE-TA-PIP-0017 | Workpack Piping Nos. 0017 Preliminary Issuance | 2026-02-20 | 2026-02-20 | 27-Nov-24 A | 18-Dec-24 A | 2026-03-27 | 1 | 2026-03-27
B1-DE-TA-PIP-0018 | Workpack Piping Nos. 0018 Preliminary Issuance | 2026-02-20 | 2026-02-20 | 27-Nov-24 A | 18-Dec-24 A | 2026-03-27 | 1 | 2026-03-27
B1-DE-TA-PIP-0019 | Workpack Piping Nos. 0019 Preliminary Issuance | 2026-02-20 | 2026-02-20 | 27-Nov-24 A | 18-Dec-24 A | 2026-03-27 | 1 | 2026-03-27
B1-DE-TA-PIP-0020 | Workpack Piping Nos. 0020 Preliminary Issuance | 2026-02-20 | 2026-02-20 | 27-Nov-24 A | 18-Dec-24 A | 2026-03-27 | 1 | 2026-03-27
B1-DE-TA-PIP-0021 | Workpack Piping Nos. 0021 Preliminary Issuance | 2026-02-20 | 2026-02-20 | 27-Nov-24 A | 18-Dec-24 A | 2026-03-27 | 1 | 2026-03-27
B1-DE-TA-PIP-0022 | Workpack Piping Nos. 0022 Preliminary Issuance | 2026-02-20 | 2026-02-20 | 27-Nov-24 A | 18-Dec-24 A | 2026-03-27 | 1 | 2026-03-27
B1-DE-TA-PIP-0023 | Workpack Piping Nos. 0023 Preliminary Issuance | 2026-02-20 | 2026-02-20 | 27-Nov-24 A | 18-Dec-24 A | 2026-03-27 | 1 | 2026-03-27
B1-DE-TA-PIP-0024 | Workpack Piping Nos. 0024 Preliminary Issuance | 2026-02-20 | 2026-02-20 | 27-Nov-24 A | 18-Dec-24 A | 2026-03-27 | 1 | 2026-03-27
B1-DE-TA-PIP-0025 | Workpack Piping Nos. 0025 Preliminary Issuance | 2026-02-20 | 2026-02-20 | 27-Nov-24 A | 18-Dec-24 A | 2026-03-27 | 1 | 2026-03-27
B1-DE-TA-PIP-0026 | Workpack Piping Nos. 0026 Preliminary Issuance | 2026-02-20 | 2026-02-20 | 27-Nov-24 A | 18-Dec-24 A | 2026-03-27 | 1 | 2026-03-27
B1-DE-TA-PIP-0027 | Workpack Piping Nos. 0025 Preliminary Issuance | 2026-02-20 | 2026-02-20 | 27-Nov-24 A | 18-Dec-24 A | 2026-03-27 | 1 | 2026-03-27
B1-DE-TA-PIP-0028 | Workpack Piping Nos. 0026 Preliminary Issuance | 2026-02-20 | 2026-02-20 | 27-Nov-24 A | 18-Dec-24 A | 2026-03-27 | 1 | 2026-03-27
B1-DE-TA-PIP-0029 | Workpack Piping Nos. 0027 Preliminary Issuance | 2026-02-20 | 2026-02-20 | 27-Nov-24 A | 18-Dec-24 A | 2026-03-27 | 1 | 2026-03-27
B1-DE-TA-PIP-0030 | Workpack Piping Nos. 0028 Preliminary Issuance | 2026-02-20 | 2026-02-20 | 27-Nov-24 A | 18-Dec-24 A | 2026-03-27 | 1 | 2026-03-27
B1-DE-TA-PIP-0031 | Workpack Piping Nos. 0029 Preliminary Issuance | 2026-02-20 | 2026-02-20 | 27-Nov-24 A | 18-Dec-24 A | 2026-03-27 | 1 | 2026-03-27
B1-DE-TA-PIP-0032 | Workpack Piping Nos. 0030 Preliminary Issuance | 2026-02-20 | 2026-02-20 | 17-Dec-24 A | 07-Jan-25 A | 2026-03-27 | 1 | 2026-03-27
B1-DE-TA-PIP-0033 | Workpack Piping Nos. 0031 Preliminary Issuance | 2026-02-20 | 2026-02-20 | 17-Dec-24 A | 07-Jan-25 A | 2026-03-27 | 1 | 2026-03-27
B1-DE-TA-PIP-0034 | Workpack Piping Nos. 0032 Preliminary Issuance | 2026-02-20 | 2026-02-20 | 17-Dec-24 A | 07-Jan-25 A | 2026-03-27 | 1 | 2026-03-27
B1-DE-TA-PIP-0035 | Workpack Piping Nos. 0033 Preliminary Issuance | 2026-02-20 | 2026-02-20 | 17-Dec-24 A | 07-Jan-25 A | 2026-03-27 | 1 | 2026-03-27
B1-DE-TA-PIP-0036 | Workpack Piping Nos. 0034 Preliminary Issuance | 2026-02-20 | 2026-02-20 | 17-Dec-24 A | 07-Jan-25 A | 2026-03-27 | 1 | 2026-03-27
B1-DE-TA-PIP-0037 | Workpack Piping Nos. 0035 Preliminary Issuance | 2026-02-20 | 2026-02-20 | 17-Dec-24 A | 07-Jan-25 A | 2026-03-27 | 1 | 2026-03-27
B1-DE-TA-PIP-0038 | Workpack Piping Nos. 0036 Preliminary Issuance | 2026-02-20 | 2026-02-20 | 17-Dec-24 A | 07-Jan-25 A | 2026-03-27 | 1 | 2026-03-27
B1-DE-TA-PIP-0039 | Workpack Piping Nos. 0037 Preliminary Issuance | 2026-02-20 | 2026-02-20 | 17-Dec-24 A | 07-Jan-25 A | 2026-03-27 | 1 | 2026-03-27
B1-DE-TA-PIP-0040 | Workpack Piping Nos. 0038 Preliminary Issuance | 2026-02-20 | 2026-02-20 | 17-Dec-24 A | 07-Jan-25 A | 2026-03-27 | 1 | 2026-03-27
B1-DE-TA-PIP-0041 | Workpack Piping Nos. 0039 Preliminary Issuance | 2026-02-20 | 2026-02-20 | 17-Dec-24 A | 07-Jan-25 A | 2026-03-27 | 1 | 2026-03-27
B1-DE-TA-PIP-0042 | Workpack Piping Nos. 0040 Preliminary Issuance | 2026-02-20 | 2026-02-20 | 17-Dec-24 A | 07-Jan-25 A | 2026-03-27 | 1 | 2026-03-27
B1-DE-TA-PIP-0043 | Workpack Piping Nos. 0041 Preliminary Issuance | 2026-02-20 | 2026-02-20 | 23-Dec-24 A | 13-Jan-25 A | 2026-03-27 | 1 | 2026-03-27
B1-DE-TA-PIP-0044 | Workpack Piping Nos. 0042 Preliminary Issuance | 2026-02-20 | 2026-02-20 | 23-Dec-24 A | 13-Jan-25 A | 2026-03-27 | 1 | 2026-03-27
B1-DE-TA-PIP-0045 | Workpack Piping Nos. 0003 Preliminary Issuance | 2026-02-20 | 2026-02-20 | 23-Dec-24 A | 13-Jan-25 A | 2026-03-27 | 1 | 2026-03-27
B1-DE-TA-PIP-0046 | Workpack Nos. 41 to 52 - Preliminary Issuance | 2026-02-20 | 2026-02-20 | 23-Dec-24 A | 13-Jan-25 A | 2026-03-27 | 1 | 2026-03-27
B1-DE-TA-PIP-0047 | Workpack Nos. 41 to 52 - Preliminary Issuance | 2026-02-20 | 2026-02-20 | 23-Dec-24 A | 13-Jan-25 A | 2026-03-27 | 1 | 2026-03-27
B1-DE-TA-PIP-0048 | Workpack Nos. 41 to 52 - Preliminary Issuance | 2026-02-20 | 2026-02-20 | 23-Dec-24 A | 13-Jan-25 A | 2026-03-27 | 1 | 2026-03-27
B1-DE-TA-PIP-0049 | Workpack Nos. 41 to 52 - Preliminary Issuance | 2026-02-20 | 2026-02-20 | 23-Dec-24 A | 13-Jan-25 A | 2026-03-27 | 1 | 2026-03-27
B1-DE-TA-PIP-0050 | Workpack Nos. 41 to 52 - Preliminary Issuance | 2026-02-20 | 2026-02-20 | 23-Dec-24 A | 13-Jan-25 A | 2026-03-27 | 1 | 2026-03-27
B1-DE-TA-PIP-0051 | Workpack Nos. 41 to 52 - Preliminary Issuance | 2026-02-20 | 2026-02-20 | 23-Dec-24 A | 13-Jan-25 A | 2026-03-27 | 1 | 2026-03-27
B1-DE-TA-PIP-0052 | Workpack Nos. 41 to 52 - Preliminary Issuance | 2026-02-20 | 2026-02-20 | 23-Dec-24 A | 13-Jan-25 A | 2026-03-27 | 1 | 2026-03-27
Final Workpack |  | 2026-02-20 | 2026-02-20 | 19-Dec-24 A | 10-Feb-25 A | 2026-03-27 | 10 | 2026-03-27
A40430 | Workpack Nos. 1 to 10 - Final Issuance | 2026-02-20 | 2026-02-20 | 19-Dec-24 A | 15-Jan-25 A | 2026-03-27 | 2 | 2026-03-27
A40440 | Workpack Nos. 11 to 20 - Final Issuance | 2026-02-20 | 2026-02-20 | 19-Dec-24 A | 15-Jan-25 A | 2026-03-27 | 2 | 2026-03-27
A40450 | Workpack Nos. 21 to 30 - Final Issuance | 2026-02-20 | 2026-02-20 | 08-Jan-25 A | 06-Feb-25 A | 2026-03-27 | 2 | 2026-03-27
A40460 | Workpack Nos. 31 to 40 - Final Issuance | 2026-02-20 | 2026-02-20 | 08-Jan-25 A | 06-Feb-25 A | 2026-03-27 | 2 | 2026-03-27
A40470 | Workpack Nos. 41 to 52 - Final Issuance | 2026-02-20 | 2026-02-20 | 24-Dec-24 A | 10-Feb-25 A | 2026-03-27 | 2 | 2026-03-27
ICT Driven - Workpack |  | 2026-02-20 | 2026-02-20 | 02-Jan-25 A | 20-Jan-25 A | 2026-03-27 | 40 | 2026-03-27
Preliminary Workpack |  | 2026-02-20 | 2026-02-20 | 02-Jan-25 A | 16-Jan-25 A | 2026-03-27 | 5 | 2026-03-27
A40480 | Workpack Nos. 53 to 56 - Preliminary Issuance | 2026-02-20 | 2026-02-20 | 02-Jan-25 A | 07-Jan-25 A | 2026-03-27 | 1 | 2026-03-27
A40490 | Workpack Nos. 57 to 59 - Preliminary Issuance | 2026-02-20 | 2026-02-20 | 02-Jan-25 A | 07-Jan-25 A | 2026-03-27 | 1 | 2026-03-27
A40500 | Workpack Nos. 60 to 63 - Preliminary Issuance | 2026-02-20 | 2026-02-20 | 02-Jan-25 A | 07-Jan-25 A | 2026-03-27 | 1 | 2026-03-27
A40510 | Workpack Nos. 64 to 67 - Preliminary Issuance | 2026-02-20 | 2026-02-20 | 06-Jan-25 A | 16-Jan-25 A | 2026-03-27 | 1 | 2026-03-27
A40520 | Workpack Nos. 68 to 70 - Preliminary Issuance | 2026-02-20 | 2026-02-20 | 06-Jan-25 A | 16-Jan-25 A | 2026-03-27 | 1 | 2026-03-27
Final Workpack |  | 2026-02-20 | 2026-02-20 | 08-Jan-25 A | 20-Jan-25 A | 2026-03-27 | 10 | 2026-03-27
A40530 | Workpack Nos. 53 to 56 - Final Issuance | 2026-02-20 | 2026-02-20 | 08-Jan-25 A | 16-Jan-25 A | 2026-03-27 | 2 | 2026-03-27
A40540 | Workpack Nos. 57 to 59 - Final Issuance | 2026-02-20 | 2026-02-20 | 08-Jan-25 A | 16-Jan-25 A | 2026-03-27 | 2 | 2026-03-27
A40550 | Workpack Nos. 60 to 63 - Final Issuance | 2026-02-20 | 2026-02-20 | 08-Jan-25 A | 16-Jan-25 A | 2026-03-27 | 2 | 2026-03-27
A40560 | Workpack Nos. 64 to 67 - Final Issuance | 2026-02-20 | 2026-02-20 | 17-Jan-25 A | 20-Jan-25 A | 2026-03-27 | 2 | 2026-03-27
A40570 | Workpack Nos. 68 to 70 - Final Issuance | 2026-02-20 | 2026-02-20 | 17-Jan-25 A | 20-Jan-25 A | 2026-03-27 | 2 | 2026-03-27
Civil/Structural/Architectural Driven - Workpack |  | 2026-02-20 | 2026-02-20 | 31-Dec-24 A | 29-Jan-25 A | 2026-03-27 | 21 | 2026-03-27
Preliminary Workpack |  | 2026-02-20 | 2026-02-20 | 31-Dec-24 A | 06-Jan-25 A | 2026-03-27 | 5 | 2026-03-27
A40580 | Workpack No. 71 - Preliminary Issuance | 2026-02-20 | 2026-02-20 | 31-Dec-24 A | 03-Jan-25 A | 2026-03-27 | 3 | 2026-03-27
A40590 | Workpack Nos. 72 - Preliminary Issuance | 2026-02-20 | 2026-02-20 | 01-Jan-25 A | 06-Jan-25 A | 2026-03-27 | 2 | 2026-03-27
Final Workpack |  | 2026-02-20 | 2026-02-20 | 04-Jan-25 A | 29-Jan-25 A | 2026-03-27 | 5 | 2026-03-27
A40600 | Workpack No. 71 - Final Issuance | 2026-02-20 | 2026-02-20 | 04-Jan-25 A | 16-Jan-25 A | 2026-03-27 | 3 | 2026-03-27
A40610 | Workpack No. 72 - Final Issuance | 2026-02-20 | 2026-02-20 | 29-Jan-25 A | 29-Jan-25 A | 2026-03-27 | 2 | 2026-03-27
Electrical Driven - Workpack |  | 2026-02-20 | 2026-02-20 | 27-Dec-24 A | 17-Jan-25 A | 2026-03-27 | 41 | 2026-03-27
Preliminary Workpack |  | 2026-02-20 | 2026-02-20 | 27-Dec-24 A | 02-Jan-25 A | 2026-03-27 | 5 | 2026-03-27
A40650 | Workpack Nos. 73 - Preliminary Issuance | 2026-02-20 | 2026-02-20 | 27-Dec-24 A | 02-Jan-25 A | 2026-03-27 | 2 | 2026-03-27
A40660 | Workpack Nos. 74 - Preliminary Issuance | 2026-02-20 | 2026-02-20 | 27-Dec-24 A | 02-Jan-25 A | 2026-03-27 | 2 | 2026-03-27
A40670 | Workpack Nos. 75 - Preliminary Issuance | 2026-02-20 | 2026-02-20 | 27-Dec-24 A | 02-Jan-25 A | 2026-03-27 | 1 | 2026-03-27
Final Workpack |  | 2026-02-20 | 2026-02-20 | 03-Jan-25 A | 17-Jan-25 A | 2026-03-27 | 11 | 2026-03-27
A40620 | Workpack No. 73 - Final Issuance | 2026-02-20 | 2026-02-20 | 03-Jan-25 A | 17-Jan-25 A | 2026-03-27 | 3 | 2026-03-27
A40630 | Workpack No. 74 - Final Issuance | 2026-02-20 | 2026-02-20 | 03-Jan-25 A | 17-Jan-25 A | 2026-03-27 | 5 | 2026-03-27
A40640 | Workpack No. 75 - Final Issuance | 2026-02-20 | 2026-02-20 | 03-Jan-25 A | 17-Jan-25 A | 2026-03-27 | 3 | 2026-03-27
Subcontracting Support |  | 2026-02-20 | 2026-02-20 | 01-Jan-25 A | 21-Jun-25 A | 2026-02-21 | 108 | 2026-03-27
SOW & Requisition for ICT System Modification |  | 2026-02-20 | 2026-02-20 | 15-Jan-25 A | 28-Feb-25 A | 2026-03-27 | 23 | 2026-03-27
A56050 | SOW & Requisition for ICT System Modification_IFR | 2026-02-20 | 2026-02-20 | 15-Jan-25 A | 30-Jan-25 A | 2026-03-27 | 6 | 2026-03-27
A56060 | SOW & Requisition for ICT System Modification_RCC | 2026-02-20 | 2026-02-20 | 31-Jan-25 A | 12-Feb-25 A | 2026-03-27 | 16 | 2026-03-27
A56070 | SOW & Requisition for ICT System Modification_IFD/IFC | 2026-02-20 | 2026-02-20 | 13-Feb-25 A | 28-Feb-25 A | 2026-03-27 | 6 | 2026-03-27
SOW & Requisition for Electrical System Modification |  | 2026-02-20 | 2026-02-20 | 07-Jan-25 A | 14-Feb-25 A | 2026-03-27 | 23 | 2026-03-27
A56080 | SOW & Requisition for Electrical System Modification_IFR | 2026-02-20 | 2026-02-20 | 07-Jan-25 A | 22-Jan-25 A | 2026-03-27 | 6 | 2026-03-27
A56090 | SOW & Requisition for Electrical System Modification_RCC | 2026-02-20 | 2026-02-20 | 23-Jan-25 A | 31-Jan-25 A | 2026-03-27 | 16 | 2026-03-27
A56100 | SOW & Requisition for Electrical System Modification_IFD/IFC | 2026-02-20 | 2026-02-20 | 03-Feb-25 A | 14-Feb-25 A | 2026-03-27 | 6 | 2026-03-27
SOW & Requisition for Topo & UG survey |  | 2026-02-20 | 2026-02-20 | 01-Jan-25 A | 05-Feb-25 A | 2026-02-21 | 23 | 2026-02-21
A56110 | SOW & Requisition for Topo & UG survey_IFR | 2026-02-20 | 2026-02-20 | 01-Jan-25 A | 09-Jan-25 A | 2026-02-21 | 6 | 2026-02-21
A56120 | SOW & Requisition for Topo & UG survey_RCC | 2026-02-20 | 2026-02-20 | 13-Jan-25 A | 24-Jan-25 A | 2026-02-21 | 16 | 2026-02-21
A28870 | SOW & Requisition for Topo & UG survey_IFD/IFC | 2026-02-20 | 2026-02-20 | 27-Jan-25 A | 05-Feb-25 A | 2026-02-21 | 6 | 2026-02-21
SOW & Requisition for Geotechnical investigation |  | 2026-02-20 | 2026-02-20 | 01-Jan-25 A | 05-Feb-25 A | 2026-02-21 | 23 | 2026-02-21
A56130 | SOW & Requisition for Geotechnical investigation_IFR | 2026-02-20 | 2026-02-20 | 01-Jan-25 A | 09-Jan-25 A | 2026-02-21 | 6 | 2026-02-21
A56140 | SOW & Requisition for Geotechnical investigation_RCC | 2026-02-20 | 2026-02-20 | 13-Jan-25 A | 24-Jan-25 A | 2026-02-21 | 16 | 2026-02-21
A56150 | SOW & Requisition for Geotechnical investigation_IFD/IFC | 2026-02-20 | 2026-02-20 | 27-Jan-25 A | 05-Feb-25 A | 2026-02-21 | 6 | 2026-02-21
SOW & Requisition for Third party HSE studies |  | 2026-02-20 | 2026-02-20 | 30-Jan-25 A | 01-Jun-25 A | 2026-03-02 | 39 | 2026-03-02
A56160 | SOW & Requisition for HSE third party studies_IFR | 2026-02-20 | 2026-02-20 | 30-Jan-25 A | 20-Feb-25 A | 2026-03-02 | 6 | 2026-03-02
A56170 | SOW & Requisition for HSE third party studies_RCC | 2026-02-20 | 2026-02-20 | 21-Feb-25 A | 27-Feb-25 A | 2026-03-02 | 16 | 2026-03-02
A56180 | SOW & Requisition for HSE third party studies_IFD/IFC | 2026-02-20 | 2026-02-20 | 28-Feb-25 A | 01-Jun-25 A | 2026-03-02 | 17 | 2026-03-02
Technical Bid Evaluation for Third Party HSE Studies |  | 2026-02-20 | 2026-02-20 | 25-Feb-25 A | 21-Jun-25 A | 2026-03-02 | 31 | 2026-03-02
A55950 | Technical Bid Evaluation for Third Party HSE Studies_IFR | 2026-02-20 | 2026-02-20 | 25-Feb-25 A | 18-Mar-25 A | 2026-03-02 | 6 | 2026-03-02
A55960 | Technical Bid Evaluation for Third Party HSE Studies_RCA | 2026-02-20 | 2026-02-20 | 19-Mar-25 A | 04-Jun-25 A | 2026-03-02 | 16 | 2026-03-02
A55970 | Technical Bid Evaluation for Third Party HSE Studies_IFD/IFC | 2026-02-20 | 2026-02-20 | 05-Jun-25 A | 21-Jun-25 A | 2026-03-02 | 11 | 2026-03-02
MTO Support |  | 2026-02-20 | 2026-02-20 | 01-Feb-25 A | 07-Mar-25 A | 2026-03-19 | 122 | 2026-03-27
A40730 | Issue Preliminary MTO for ICT Bulks | 2026-02-20 | 2026-02-20 | 01-Feb-25 A | 07-Feb-25 A | 2026-03-27 | 6 | 2026-03-27
A40750 | Issue Final MTO for Piping Bulks | 2026-02-20 | 2026-02-20 | 10-Feb-25 A | 19-Feb-25 A | 2026-03-27 | 6 | 2026-03-27
A40740 | Issue Preliminary MTO for Electrical Bulks | 2026-02-20 | 2026-02-20 | 13-Feb-25 A | 26-Feb-25 A | 2026-03-27 | 6 | 2026-03-27
A40780 | Issue Final MTO for Electrical Bulks | 2026-02-20 | 2026-02-20 | 17-Feb-25 A | 27-Feb-25 A | 2026-03-27 | 6 | 2026-03-27
A40710 | Issue Preliminary MTO for Piping Bulks | 2026-02-20 | 2026-02-20 | 18-Feb-25 A | 28-Feb-25 A | 2026-03-27 | 6 | 2026-03-27
A40720 | Issue Preliminary MTO for Structural Steel Bulks | 2026-02-20 | 2026-02-20 | 17-Feb-25 A | 28-Feb-25 A | 2026-03-19 | 6 | 2026-03-19
A40760 | Issue Final MTO for Structural Steel Bulks | 2026-02-20 | 2026-02-20 | 24-Feb-25 A | 28-Feb-25 A | 2026-03-27 | 7 | 2026-03-27
A40770 | Issue Final MTO for ICT Bulks | 2026-02-20 | 2026-02-20 | 14-Feb-25 A | 07-Mar-25 A | 2026-03-27 | 6 | 2026-03-27
Balance of Plant |  | 2026-02-20 | 2026-06-08 | 28-Nov-24 A | 2026-06-08 | 2026-02-21 | 500 | 2027-01-20 | 162
General |  | 2026-02-20 | 2026-05-14 | 28-Nov-24 A | 2026-05-14 | 2026-03-02 | 371 | 2027-01-20 | 179
Master Deliverable Register (MDR) |  | 2026-02-20 | 2026-02-20 | 28-Nov-24 A | 16-Jan-25 A | 2026-03-02 | 39 | 2027-01-20
A40790 | Master Deliverable Register (MDR)_IFR | 2026-02-20 | 2026-02-20 | 28-Nov-24 A | 19-Dec-24 A | 2026-03-02 | 6 | 2026-03-02
A40800 | Master Deliverable Register (MDR)_RCC | 2026-02-20 | 2026-02-20 | 19-Dec-24 A | 26-Dec-24 A | 2027-01-20 | 16 | 2027-01-20
A40810 | Master Deliverable Register (MDR)_IFA | 2026-02-20 | 2026-02-20 | 27-Dec-24 A | 02-Jan-25 A | 2027-01-20 | 3 | 2027-01-20
A40820 | Master Deliverable Register (MDR)_RCA | 2026-02-20 | 2026-02-20 | 03-Jan-25 A | 09-Jan-25 A | 2027-01-20 | 16 | 2027-01-20
A40830 | Master Deliverable Register (MDR)_IFD/IFC | 2026-02-20 | 2026-02-20 | 10-Jan-25 A | 16-Jan-25 A | 2027-01-20 | 2 | 2027-01-20
Planning Package / EDDR |  | 2026-02-20 | 2026-02-20 | 01-Jan-25 A | 13-Apr-25 A | 2027-01-20 | 81 | 2027-01-20
A40840 | Planning Package / EDDR_IFR | 2026-02-20 | 2026-02-20 | 01-Jan-25 A | 22-Jan-25 A | 2027-01-20 | 6 | 2027-01-20
A40850 | Planning Package / EDDR_RCC | 2026-02-20 | 2026-02-20 | 23-Jan-25 A | 21-Mar-25 A | 2027-01-20 | 16 | 2027-01-20
A40860 | Planning Package / EDDR_IFA | 2026-02-20 | 2026-02-20 | 22-Mar-25 A | 29-Mar-25 A | 2027-01-20 | 3 | 2027-01-20
A40870 | Planning Package / EDDR_RCA | 2026-02-20 | 2026-02-20 | 30-Mar-25 A | 04-Apr-25 A | 2027-01-20 | 58 | 2027-01-20
A40880 | Planning Package / EDDR_IFD/IFC | 2026-02-20 | 2026-02-20 | 07-Apr-25 A | 13-Apr-25 A | 2027-01-20 | 2 | 2027-01-20
Project Execution Plan |  | 2026-02-20 | 2026-02-20 | 03-Mar-25 A | 01-Sep-25 A | 2026-06-26 | 193 | 2026-06-26
A40890 | Project Execution Plan_IFR | 2026-02-20 | 2026-02-20 | 03-Mar-25 A | 22-Mar-25 A | 2026-06-26 | 6 | 2026-06-26
A40900 | Project Execution Plan_RCC | 2026-02-20 | 2026-02-20 | 23-Mar-25 A | 29-Mar-25 A | 2026-06-26 | 16 | 2026-06-26
A40910 | Project Execution Plan_IFA | 2026-02-20 | 2026-02-20 | 30-Mar-25 A | 05-Apr-25 A | 2026-06-26 | 3 | 2026-06-26
A40920 | Project Execution Plan_RCA | 2026-02-20 | 2026-02-20 | 31-Mar-25 A | 06-Apr-25 A | 2026-06-26 | 6 | 2026-06-26
A40930 | Project Execution Plan_IFD/IFC | 2026-02-20 | 2026-02-20 | 31-Aug-25 A | 01-Sep-25 A | 2026-06-26 | 2 | 2026-06-26
FEED Verification Report |  | 2026-02-20 | 2026-02-20 | 27-Mar-25 A | 15-May-25 A | 2026-03-02 | 117 | 2027-01-20
A40940 | FEED Verification Report_IFR | 2026-02-20 | 2026-02-20 | 27-Mar-25 A | 04-Apr-25 A | 2026-03-02 | 6 | 2026-03-02
A40950 | FEED Verification Report_RCC | 2026-02-20 | 2026-02-20 | 07-Apr-25 A | 18-Apr-25 A | 2026-03-02 | 11 | 2026-03-02
A40960 | FEED Verification Report_IFA | 2026-02-20 | 2026-02-20 | 21-Apr-25 A | 30-Apr-25 A | 2027-01-20 | 3 | 2027-01-20
A40970 | FEED Verification Report_RCA | 2026-02-20 | 2026-02-20 | 01-May-25 A | 08-May-25 A | 2027-01-20 | 16 | 2027-01-20
A40980 | FEED Verification Report_IFD/IFC | 2026-02-20 | 2026-02-20 | 02-May-25 A | 15-May-25 A | 2027-01-20 | 2 | 2027-01-20
Site Visit Report for BOP |  | 2026-02-20 | 2026-02-20 | 15-Mar-25 A | 20-Jun-25 A | 2026-03-02 | 42 | 2026-03-02
A40990 | Site Visit Report for BOP_IFR | 2026-02-20 | 2026-02-20 | 15-Mar-25 A | 22-Mar-25 A | 2026-03-02 | 6 | 2026-03-02
A41000 | Site Visit Report for BOP_RCC | 2026-02-20 | 2026-02-20 | 23-Mar-25 A | 29-Mar-25 A | 2026-03-02 | 16 | 2026-03-02
A41010 | Site Visit Report for BOP_IFA | 2026-02-20 | 2026-02-20 | 30-Mar-25 A | 05-Apr-25 A | 2026-03-02 | 3 | 2026-03-02
A41020 | Site Visit Report for BOP_RCA | 2026-02-20 | 2026-02-20 | 06-Apr-25 A | 13-Jun-25 A | 2026-03-02 | 16 | 2026-03-02
A41030 | Site Visit Report for BOP_IFD/IFC | 2026-02-20 | 2026-02-20 | 14-Jun-25 A | 20-Jun-25 A | 2026-03-02 | 2 | 2026-03-02
Project Risk Register |  | 2026-02-20 | 2026-02-20 | 21-Feb-25 A | 13-Sep-25 A | 2027-01-20 | 173 | 2027-01-20
A41040 | Project Risk Register_IFR | 2026-02-20 | 2026-02-20 | 21-Feb-25 A | 10-Jun-25 A | 2027-01-20 | 17 | 2027-01-20
A41050 | Project Risk Register_RCC | 2026-02-20 | 2026-02-20 | 30-Jul-25 A | 24-Aug-25 A | 2027-01-20 | 24 | 2027-01-20
A41060 | Project Risk Register_IFA | 2026-02-20 | 2026-02-20 | 13-Aug-25 A | 31-Aug-25 A | 2027-01-20 | 17 | 2027-01-20
A41070 | Project Risk Register_RCA | 2026-02-20 | 2026-02-20 | 20-Aug-25 A | 06-Sep-25 A | 2027-01-20 | 16 | 2027-01-20
A41080 | Project Risk Register_IFD/IFC | 2026-02-20 | 2026-02-20 | 26-Aug-25 A | 13-Sep-25 A | 2027-01-20 | 17 | 2027-01-20
Project Lesson Learnt Register |  | 2026-02-20 | 2026-02-20 | 09-Jan-25 A | 14-Sep-25 A | 2027-01-20 | 137 | 2027-01-20
A41090 | Project Lesson Learnt Register_IFR | 2026-02-20 | 2026-02-20 | 09-Jan-25 A | 10-Jun-25 A | 2027-01-20 | 6 | 2027-01-20
A1890 | Project Lesson Learnt Register_RCC | 2026-02-20 | 2026-02-20 | 01-Aug-25 A | 24-Aug-25 A | 2027-01-20 | 16 | 2027-01-20
A1900 | Project Lesson Learnt Register_IFA | 2026-02-20 | 2026-02-20 | 08-Aug-25 A | 30-Aug-25 A | 2027-01-20 | 3 | 2027-01-20
A1910 | Project Lesson Learnt Register_RCA | 2026-02-20 | 2026-02-20 | 28-Aug-25 A | 06-Sep-25 A | 2027-01-20 | 16 | 2027-01-20
A1920 | Project Lesson Learnt Register_IFD/IFC | 2026-02-20 | 2026-02-20 | 10-Sep-25 A | 14-Sep-25 A | 2027-01-20 | 2 | 2027-01-20
Criticality Rating Report |  | 2026-02-20 | 2026-02-20 | 21-Jun-25 A | 13-Sep-25 A | 2027-01-20 | 127 | 2027-01-20
A1930 | Criticality Rating Report_IFR | 2026-02-20 | 2026-02-20 | 21-Jun-25 A | 12-Jul-25 A | 2027-01-20 | 6 | 2027-01-20
A1940 | Criticality Rating Report_RCC | 2026-02-20 | 2026-02-20 | 08-Aug-25 A | 24-Aug-25 A | 2027-01-20 | 16 | 2027-01-20
A1950 | Criticality Rating Report_IFA | 2026-02-20 | 2026-02-20 | 21-Aug-25 A | 30-Aug-25 A | 2027-01-20 | 3 | 2027-01-20
A1960 | Criticality Rating Report_RCA | 2026-02-20 | 2026-02-20 | 20-Aug-25 A | 06-Sep-25 A | 2027-01-20 | 16 | 2027-01-20
A1970 | Criticality Rating Report_IFD/IFC | 2026-02-20 | 2026-02-20 | 10-Sep-25 A | 13-Sep-25 A | 2027-01-20 | 2 | 2027-01-20
Project Close Out Report |  | 2026-03-23 | 2026-05-14 | 2026-03-23 | 2026-05-14 | 2026-11-27 | 38 | 2027-01-20 | 179
A41100 | Project Close Out Report_IFR | 2026-03-23 | 2026-03-25 | 2026-03-23 | 2026-03-25 | 2026-11-27 | 2 | 2026-12-01 | 179
A41110 | Project Close Out Report_RCC | 2026-03-25 | 2026-04-16 | 2026-03-25 | 2026-04-16 | 2026-12-02 | 16 | 2026-12-23 | 179
A41120 | Project Close Out Report_IFA | 2026-04-16 | 2026-04-21 | 2026-04-16 | 2026-04-21 | 2026-12-23 | 3 | 2026-12-29 | 179
A41130 | Project Close Out Report_RCA | 2026-04-21 | 2026-05-13 | 2026-04-21 | 2026-05-13 | 2026-12-29 | 16 | 2027-01-19 | 179
A41140 | Project Close Out Report_IFD/IFC | 2026-05-13 | 2026-05-14 | 2026-05-13 | 2026-05-14 | 2027-01-19 | 1 | 2027-01-20 | 179
Energy Review Closeout Report |  | 2026-02-24 | 2026-05-01 | 2026-02-24 | 2026-05-01 | 2026-11-13 | 48 | 2027-01-20 | 188
A41150 | Energy Review Closeout Report_IFR | 2026-02-24 | 2026-03-11 | 2026-02-24 | 2026-03-11 | 2026-11-13 | 11 | 2026-11-30 | 188
A41160 | Energy Review Closeout Report_RCC | 2026-03-11 | 2026-04-02 | 2026-03-11 | 2026-04-02 | 2026-11-30 | 16 | 2026-12-22 | 188
A41170 | Energy Review Closeout Report_IFA | 2026-04-02 | 2026-04-07 | 2026-04-02 | 2026-04-07 | 2026-12-22 | 3 | 2026-12-25 | 188
A41180 | Energy Review Closeout Report_RCA | 2026-04-07 | 2026-04-29 | 2026-04-07 | 2026-04-29 | 2026-12-28 | 16 | 2027-01-18 | 188
A41190 | Energy Review Closeout Report_IFD/IFC | 2026-04-29 | 2026-05-01 | 2026-04-29 | 2026-05-01 | 2027-01-18 | 2 | 2027-01-20 | 188
Process |  | 2026-02-20 | 2026-04-23 | 27-Dec-24 A | 2026-04-23 | 2026-03-02 | 354 | 2027-01-20 | 194
Utility Design Basis |  | 2026-02-20 | 2026-02-20 | 27-Dec-24 A | 18-Aug-25 A | 2026-03-19 | 260 | 2027-01-20
A41200 | Utility Design Basis_IFR | 2026-02-20 | 2026-02-20 | 27-Dec-24 A | 17-Jan-25 A | 2026-03-19 | 6 | 2026-03-19
A41210 | Utility Design Basis_RCC | 2026-02-20 | 2026-02-20 | 18-Jan-25 A | 31-Jan-25 A | 2027-01-20 | 16 | 2027-01-20
A41220 | Utility Design Basis_IFA | 2026-02-20 | 2026-02-20 | 01-Aug-25 A | 04-Aug-25 A | 2027-01-20 | 3 | 2027-01-20
A41230 | Utility Design Basis_RCA | 2026-02-20 | 2026-02-20 | 05-Aug-25 A | 12-Aug-25 A | 2027-01-20 | 16 | 2027-01-20
A41240 | Utility Design Basis_IFD/IFC | 2026-02-20 | 2026-02-20 | 13-Aug-25 A | 18-Aug-25 A | 2027-01-20 | 2 | 2027-01-20
Criticality Rating of System |  | 2026-02-20 | 2026-04-14 | 10-Jan-25 A | 2026-04-14 | 2026-11-30 | 341 | 2027-01-20 | 202
A41250 | Criticality Rating of System_IFR | 2026-02-20 | 2026-02-20 | 10-Jan-25 A | 06-Jun-25 A | 2026-11-30 | 6 | 2026-11-30
A41260 | Criticality Rating of System_RCC | 2026-02-20 | 2026-03-13 | 2026-02-20 | 2026-03-13 | 2026-11-30 | 16 | 2026-12-22 | 202
A41270 | Criticality Rating of System_IFA | 2026-03-13 | 2026-03-19 | 2026-03-13 | 2026-03-19 | 2026-12-22 | 3 | 2026-12-25 | 202
A41280 | Criticality Rating of System_RCA | 2026-03-19 | 2026-04-09 | 2026-03-19 | 2026-04-09 | 2026-12-28 | 16 | 2027-01-18 | 202
A41290 | Criticality Rating of System_IFD/IFC | 2026-04-09 | 2026-04-14 | 2026-04-09 | 2026-04-14 | 2027-01-18 | 2 | 2027-01-20 | 202
List Of Process Simulation Cases |  | 2026-02-20 | 2026-02-20 | 27-Dec-24 A | 12-Jul-25 A | 2027-01-20 | 256 | 2027-01-20
A41300 | List Of Process Simulation Cases_IFR | 2026-02-20 | 2026-02-20 | 27-Dec-24 A | 17-Jan-25 A | 2027-01-20 | 6 | 2027-01-20
A41310 | List Of Process Simulation Cases_RCC | 2026-02-20 | 2026-02-20 | 03-Jun-25 A | 21-Jun-25 A | 2027-01-20 | 16 | 2027-01-20
A41320 | List Of Process Simulation Cases_IFA | 2026-02-20 | 2026-02-20 | 23-Jun-25 A | 28-Jun-25 A | 2027-01-20 | 3 | 2027-01-20
A41330 | List Of Process Simulation Cases_RCA | 2026-02-20 | 2026-02-20 | 20-Jun-25 A | 05-Jul-25 A | 2027-01-20 | 16 | 2027-01-20
A41340 | List Of Process Simulation Cases_IFD/IFC | 2026-02-20 | 2026-02-20 | 09-Jul-25 A | 12-Jul-25 A | 2027-01-20 | 2 | 2027-01-20
Isolation Philosophy |  | 2026-02-20 | 2026-02-20 | 03-Jan-25 A | 23-Dec-25 A | 2026-11-19 | 263 | 2027-01-20
A3180 | Isolation Philosophy_IFR | 2026-02-20 | 2026-02-20 | 03-Jan-25 A | 24-Jan-25 A | 2026-11-19 | 6 | 2026-11-19
A3190 | Isolation Philosophy_RCC | 2026-02-20 | 2026-02-20 | 18-Apr-25 A | 19-Apr-25 A | 2027-01-20 | 16 | 2027-01-20
A41790 | Isolation Philosophy_IFA | 2026-02-20 | 2026-02-20 | 20-Apr-25 A | 13-Jun-25 A | 2027-01-20 | 3 | 2027-01-20
A41800 | Isolation Philosophy_RCA | 2026-02-20 | 2026-02-20 | 14-Jun-25 A | 21-Jun-25 A | 2027-01-20 | 16 | 2027-01-20
A41810 | Isolation Philosophy_IFD/IFC | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 23-Dec-25 A | 2027-01-20 | 2 | 2027-01-20
Relief and Blowdown Philosophy |  | 2026-02-20 | 2026-03-17 | 09-Jan-25 A | 2026-03-17 | 2026-11-19 | 319 | 2027-01-20 | 221
A41820 | Relief and Blowdown Philosophy_IFR | 2026-02-20 | 2026-02-20 | 09-Jan-25 A | 30-Jan-25 A | 2026-11-19 | 6 | 2026-11-19
A41830 | Relief and Blowdown Philosophy_RCC | 2026-02-20 | 2026-02-20 | 31-Jan-25 A | 20-Apr-25 A | 2026-12-28 | 16 | 2026-12-28
A41840 | Relief and Blowdown Philosophy_IFA | 2026-02-20 | 2026-02-20 | 10-Dec-25 A | 19-Dec-25 A | 2026-12-28 | 3 | 2026-12-28
A41850 | Relief and Blowdown Philosophy_RCA | 2026-02-20 | 2026-03-13 | 2026-02-20 | 2026-03-13 | 2026-12-28 | 16 | 2027-01-18 | 221
A41860 | Relief and Blowdown Philosophy_IFD/IFC | 2026-03-13 | 2026-03-17 | 2026-03-13 | 2026-03-17 | 2027-01-18 | 2 | 2027-01-20 | 221
Vent and Drain Philosophy |  | 2026-02-20 | 2026-04-23 | 03-Jan-25 A | 2026-04-23 | 2026-11-19 | 340 | 2027-01-20 | 194
A41870 | Vent and Drain Philosophy_IFR | 2026-02-20 | 2026-02-20 | 03-Jan-25 A | 24-Jan-25 A | 2026-11-19 | 6 | 2026-11-19
A41880 | Vent and Drain Philosophy_RCC | 2026-02-20 | 2026-02-20 | 25-Jan-25 A | 20-Apr-25 A | 2027-01-18 | 16 | 2027-01-18
A41890 | Vent and Drain Philosophy_IFA | 2026-02-20 | 2026-02-20 | 21-Apr-25 A | 17-Jun-25 A | 2027-01-18 | 3 | 2027-01-18
A41900 | Vent and Drain Philosophy_RCA | 2026-02-20 | 2026-02-20 | 31-Jul-25 A | 15-Aug-25 A | 2027-01-18 | 16 | 2027-01-18
A41910 | Vent and Drain Philosophy_IFD/IFC | 2026-04-21 | 2026-04-23 | 2026-04-21 | 2026-04-23 | 2027-01-18 | 2 | 2027-01-20 | 194
Operating manual including operating procedure/guidelines including startup and shutdown procedure |  | 2026-02-20 | 2026-04-21 | 2026-02-20 | 2026-04-21 | 2026-11-19 | 43 | 2027-01-18 | 194
A55980 | Operating manual including operating procedure/guidelines including startup and shutdown procedure_IFR | 2026-02-20 | 2026-02-27 | 2026-02-20 | 2026-02-27 | 2026-11-19 | 6 | 2026-11-26 | 194
A55990 | Operating manual including operating procedure/guidelines including startup and shutdown procedure_RCC | 2026-02-27 | 2026-03-23 | 2026-02-27 | 2026-03-23 | 2026-11-26 | 16 | 2026-12-18 | 194
A56000 | Operating manual including operating procedure/guidelines including startup and shutdown procedure_IFA | 2026-03-23 | 2026-03-26 | 2026-03-23 | 2026-03-26 | 2026-12-18 | 3 | 2026-12-23 | 194
A56010 | Operating manual including operating procedure/guidelines including startup and shutdown procedure_RCA | 2026-03-26 | 2026-04-17 | 2026-03-26 | 2026-04-17 | 2026-12-23 | 16 | 2027-01-14 | 194
A56020 | Operating manual including operating procedure/guidelines including startup and shutdown procedure_IFD/IFC | 2026-04-17 | 2026-04-21 | 2026-04-17 | 2026-04-21 | 2027-01-14 | 2 | 2027-01-18 | 194
Process Safeguarding Diagram: List |  | 2026-02-20 | 2026-02-20 | 04-Jan-25 A | 28-Jun-25 A | 2026-03-02 | 217 | 2026-11-19
A41920 | Process Safeguarding Diagram: List_IFR | 2026-02-20 | 2026-02-20 | 04-Jan-25 A | 25-Jan-25 A | 2026-03-02 | 11 | 2026-03-02
A41930 | Process Safeguarding Diagram: List_RCC | 2026-02-20 | 2026-02-20 | 26-Jan-25 A | 20-Feb-25 A | 2026-03-02 | 16 | 2026-03-02
A41940 | Process Safeguarding Diagram: List_IFH | 2026-02-20 | 2026-02-20 | 21-Feb-25 A | 27-May-25 A | 2026-03-02 | 11 | 2026-03-02
A41950 | Process Safeguarding Diagram: List_RCA | 2026-02-20 | 2026-02-20 | 28-May-25 A | 21-Jun-25 A | 2026-11-19 | 16 | 2026-11-19
A41960 | Process Safeguarding Diagram: List_IFD/IFC | 2026-02-20 | 2026-02-20 | 22-Jun-25 A | 28-Jun-25 A | 2026-11-19 | 2 | 2026-11-19
Process Safeguarding Diagram: Feed Pretreatment |  | 2026-02-20 | 2026-02-20 | 04-Jan-25 A | 28-Jun-25 A | 2026-03-02 | 217 | 2027-01-20
A41970 | Process Safeguarding Diagram: Feed Pretreatment_IFR | 2026-02-20 | 2026-02-20 | 04-Jan-25 A | 25-Jan-25 A | 2026-03-02 | 11 | 2026-03-02
A41980 | Process Safeguarding Diagram: Feed Pretreatment_RCC | 2026-02-20 | 2026-02-20 | 26-Jan-25 A | 20-Feb-25 A | 2026-03-02 | 16 | 2026-03-02
A41990 | Process Safeguarding Diagram: Feed Pretreatment_IFH | 2026-02-20 | 2026-02-20 | 21-Feb-25 A | 27-May-25 A | 2026-03-02 | 11 | 2026-03-02
A42000 | Process Safeguarding Diagram: Feed Pretreatment_RCA | 2026-02-20 | 2026-02-20 | 28-May-25 A | 21-Jun-25 A | 2027-01-20 | 16 | 2027-01-20
A42010 | Process Safeguarding Diagram: Feed Pretreatment_IFD/IFC | 2026-02-20 | 2026-02-20 | 22-Jun-25 A | 28-Jun-25 A | 2027-01-20 | 2 | 2027-01-20
Process Safeguarding Diagram: Wash Water System |  | 2026-02-20 | 2026-02-20 | 04-Jan-25 A | 28-Jun-25 A | 2026-03-02 | 217 | 2027-01-20
A42020 | Process Safeguarding Diagram: Wash Water System_IFR | 2026-02-20 | 2026-02-20 | 04-Jan-25 A | 25-Jan-25 A | 2026-03-02 | 11 | 2026-03-02
A42030 | Process Safeguarding Diagram: Wash Water System_RCC | 2026-02-20 | 2026-02-20 | 26-Jan-25 A | 20-Feb-25 A | 2026-03-02 | 16 | 2026-03-02
A42040 | Process Safeguarding Diagram: Wash Water System_IFH | 2026-02-20 | 2026-02-20 | 21-Feb-25 A | 27-May-25 A | 2026-03-02 | 11 | 2026-03-02
A42050 | Process Safeguarding Diagram: Wash Water System_RCA | 2026-02-20 | 2026-02-20 | 28-May-25 A | 21-Jun-25 A | 2027-01-20 | 16 | 2027-01-20
A42060 | Process Safeguarding Diagram: Wash Water System_IFD/IFC | 2026-02-20 | 2026-02-20 | 22-Jun-25 A | 28-Jun-25 A | 2027-01-20 | 2 | 2027-01-20
Process Safeguarding Diagram: Cracked Gas Compression |  | 2026-02-20 | 2026-02-20 | 04-Jan-25 A | 28-Jun-25 A | 2026-03-02 | 217 | 2027-01-20
A42070 | Process Safeguarding Diagram: Cracked Gas Compression_IFR | 2026-02-20 | 2026-02-20 | 04-Jan-25 A | 25-Jan-25 A | 2026-03-02 | 11 | 2026-03-02
A42080 | Process Safeguarding Diagram: Cracked Gas Compression_RCC | 2026-02-20 | 2026-02-20 | 26-Jan-25 A | 20-Feb-25 A | 2026-03-02 | 16 | 2026-03-02
A42090 | Process Safeguarding Diagram: Cracked Gas Compression_IFH | 2026-02-20 | 2026-02-20 | 21-Feb-25 A | 27-May-25 A | 2026-03-02 | 11 | 2026-03-02
A42100 | Process Safeguarding Diagram: Cracked Gas Compression_RCA | 2026-02-20 | 2026-02-20 | 28-May-25 A | 21-Jun-25 A | 2027-01-20 | 16 | 2027-01-20
A42110 | Process Safeguarding Diagram: Cracked Gas Compression_IFD/IFC | 2026-02-20 | 2026-02-20 | 22-Jun-25 A | 28-Jun-25 A | 2027-01-20 | 2 | 2027-01-20
Process Safeguarding Diagram: C1/C2 Separation |  | 2026-02-20 | 2026-02-20 | 04-Jan-25 A | 28-Jun-25 A | 2026-03-02 | 217 | 2027-01-20
A42120 | Process Safeguarding Diagram: C1/C2 Separation_IFR | 2026-02-20 | 2026-02-20 | 04-Jan-25 A | 25-Jan-25 A | 2026-03-02 | 11 | 2026-03-02
A42130 | Process Safeguarding Diagram: C1/C2 Separation_RCC | 2026-02-20 | 2026-02-20 | 26-Jan-25 A | 20-Feb-25 A | 2026-03-02 | 16 | 2026-03-02
A42140 | Process Safeguarding Diagram: C1/C2 Separation_IFH | 2026-02-20 | 2026-02-20 | 21-Feb-25 A | 27-May-25 A | 2026-03-02 | 11 | 2026-03-02
A42150 | Process Safeguarding Diagram: C1/C2 Separation_RCA | 2026-02-20 | 2026-02-20 | 28-May-25 A | 21-Jun-25 A | 2027-01-20 | 16 | 2027-01-20
A42160 | Process Safeguarding Diagram: C1/C2 Separation_IFD/IFC | 2026-02-20 | 2026-02-20 | 22-Jun-25 A | 28-Jun-25 A | 2027-01-20 | 2 | 2027-01-20
Process Safeguarding Diagram: H2 Extraction Unit |  | 2026-02-20 | 2026-02-20 | 04-Jan-25 A | 28-Jun-25 A | 2026-03-02 | 217 | 2027-01-20
A42170 | Process Safeguarding Diagram: H2 Extraction Unit_IFR | 2026-02-20 | 2026-02-20 | 04-Jan-25 A | 25-Jan-25 A | 2026-03-02 | 11 | 2026-03-02
A42180 | Process Safeguarding Diagram: H2 Extraction Unit_RCC | 2026-02-20 | 2026-02-20 | 26-Jan-25 A | 20-Feb-25 A | 2026-03-02 | 16 | 2026-03-02
A42190 | Process Safeguarding Diagram: H2 Extraction Unit_IFH | 2026-02-20 | 2026-02-20 | 21-Feb-25 A | 27-May-25 A | 2026-03-02 | 11 | 2026-03-02
A42200 | Process Safeguarding Diagram: H2 Extraction Unit_RCA | 2026-02-20 | 2026-02-20 | 28-May-25 A | 21-Jun-25 A | 2027-01-20 | 16 | 2027-01-20
A42210 | Process Safeguarding Diagram: H2 Extraction Unit_IFD/IFC | 2026-02-20 | 2026-02-20 | 22-Jun-25 A | 28-Jun-25 A | 2027-01-20 | 2 | 2027-01-20
Process Safeguarding Diagram: H2 Extraction Unit II |  | 2026-02-20 | 2026-02-20 | 04-Jan-25 A | 28-Jun-25 A | 2026-03-02 | 217 | 2027-01-20
A42220 | Process Safeguarding Diagram: H2 Extraction Unit II_IFR | 2026-02-20 | 2026-02-20 | 04-Jan-25 A | 25-Jan-25 A | 2026-03-02 | 11 | 2026-03-02
A42230 | Process Safeguarding Diagram: H2 Extraction Unit II_RCC | 2026-02-20 | 2026-02-20 | 26-Jan-25 A | 20-Feb-25 A | 2026-03-02 | 16 | 2026-03-02
A42240 | Process Safeguarding Diagram: H2 Extraction Unit II_IFH | 2026-02-20 | 2026-02-20 | 21-Feb-25 A | 27-May-25 A | 2026-03-02 | 11 | 2026-03-02
A42250 | Process Safeguarding Diagram: H2 Extraction Unit II_RCA | 2026-02-20 | 2026-02-20 | 28-May-25 A | 21-Jun-25 A | 2027-01-20 | 16 | 2027-01-20
A42260 | Process Safeguarding Diagram: H2 Extraction Unit II_IFD/IFC | 2026-02-20 | 2026-02-20 | 22-Jun-25 A | 28-Jun-25 A | 2027-01-20 | 2 | 2027-01-20
Process Safeguarding Diagram: C4 Selective Hydrogenation IV |  | 2026-02-20 | 2026-02-20 | 04-Jan-25 A | 28-Jun-25 A | 2026-03-02 | 217 | 2027-01-20
A42270 | Process Safeguarding Diagram: C4 Selective Hydrogenation IV_IFR | 2026-02-20 | 2026-02-20 | 04-Jan-25 A | 25-Jan-25 A | 2026-03-02 | 11 | 2026-03-02
A42280 | Process Safeguarding Diagram: C4 Selective Hydrogenation IV_RCC | 2026-02-20 | 2026-02-20 | 26-Jan-25 A | 20-Feb-25 A | 2026-03-02 | 16 | 2026-03-02
A42290 | Process Safeguarding Diagram: C4 Selective Hydrogenation IV_IFH | 2026-02-20 | 2026-02-20 | 21-Feb-25 A | 27-May-25 A | 2026-03-02 | 11 | 2026-03-02
A42300 | Process Safeguarding Diagram: C4 Selective Hydrogenation IV_RCA | 2026-02-20 | 2026-02-20 | 28-May-25 A | 21-Jun-25 A | 2027-01-20 | 16 | 2027-01-20
A42310 | Process Safeguarding Diagram: C4 Selective Hydrogenation IV_IFD/IFC | 2026-02-20 | 2026-02-20 | 22-Jun-25 A | 28-Jun-25 A | 2027-01-20 | 2 | 2027-01-20
Process Safeguarding Diagram: Fuel Gas System |  | 2026-02-20 | 2026-02-20 | 04-Jan-25 A | 28-Jun-25 A | 2026-03-02 | 217 | 2027-01-20
A42320 | Process Safeguarding Diagram: Fuel Gas System_IFR | 2026-02-20 | 2026-02-20 | 04-Jan-25 A | 25-Jan-25 A | 2026-03-02 | 11 | 2026-03-02
A42330 | Process Safeguarding Diagram: Fuel Gas System_RCC | 2026-02-20 | 2026-02-20 | 26-Jan-25 A | 20-Feb-25 A | 2026-03-02 | 16 | 2026-03-02
A42340 | Process Safeguarding Diagram: Fuel Gas System_IFH | 2026-02-20 | 2026-02-20 | 21-Feb-25 A | 27-May-25 A | 2026-03-02 | 11 | 2026-03-02
A42350 | Process Safeguarding Diagram: Fuel Gas System_RCA | 2026-02-20 | 2026-02-20 | 28-May-25 A | 21-Jun-25 A | 2027-01-20 | 16 | 2027-01-20
A42360 | Process Safeguarding Diagram: Fuel Gas System_IFD/IFC | 2026-02-20 | 2026-02-20 | 22-Jun-25 A | 28-Jun-25 A | 2027-01-20 | 2 | 2027-01-20
Process Safeguarding Diagram: Regeneration System |  | 2026-02-20 | 2026-02-20 | 04-Jan-25 A | 28-Jun-25 A | 2026-03-02 | 217 | 2027-01-20
A42370 | Process Safeguarding Diagram: Regeneration System_IFR | 2026-02-20 | 2026-02-20 | 04-Jan-25 A | 25-Jan-25 A | 2026-03-02 | 11 | 2026-03-02
A42380 | Process Safeguarding Diagram: Regeneration System_RCC | 2026-02-20 | 2026-02-20 | 26-Jan-25 A | 20-Feb-25 A | 2026-03-02 | 16 | 2026-03-02
A42390 | Process Safeguarding Diagram: Regeneration System_IFH | 2026-02-20 | 2026-02-20 | 21-Feb-25 A | 27-May-25 A | 2026-03-02 | 11 | 2026-03-02
A42400 | Process Safeguarding Diagram: Regeneration System_RCA | 2026-02-20 | 2026-02-20 | 28-May-25 A | 21-Jun-25 A | 2027-01-20 | 16 | 2027-01-20
A42410 | Process Safeguarding Diagram: Regeneration System_IFD/IFC | 2026-02-20 | 2026-02-20 | 22-Jun-25 A | 28-Jun-25 A | 2027-01-20 | 2 | 2027-01-20
Process Safeguarding Diagram: Boiler Feed Water System |  | 2026-02-20 | 2026-02-20 | 04-Jan-25 A | 28-Jun-25 A | 2026-03-02 | 217 | 2027-01-20
A42420 | Process Safeguarding Diagram: Boiler Feed Water System_IFR | 2026-02-20 | 2026-02-20 | 04-Jan-25 A | 25-Jan-25 A | 2026-03-02 | 11 | 2026-03-02
A42430 | Process Safeguarding Diagram: Boiler Feed Water System_RCC | 2026-02-20 | 2026-02-20 | 26-Jan-25 A | 20-Feb-25 A | 2026-03-02 | 16 | 2026-03-02
A42440 | Process Safeguarding Diagram: Boiler Feed Water System_IFH | 2026-02-20 | 2026-02-20 | 21-Feb-25 A | 27-May-25 A | 2026-03-02 | 11 | 2026-03-02
A42450 | Process Safeguarding Diagram: Boiler Feed Water System_RCA | 2026-02-20 | 2026-02-20 | 28-May-25 A | 21-Jun-25 A | 2027-01-20 | 16 | 2027-01-20
A42460 | Process Safeguarding Diagram: Boiler Feed Water System_IFD/IFC | 2026-02-20 | 2026-02-20 | 22-Jun-25 A | 28-Jun-25 A | 2027-01-20 | 2 | 2027-01-20
Process Safeguarding Diagram: Condensate Collection System |  | 2026-02-20 | 2026-02-20 | 04-Jan-25 A | 28-Jun-25 A | 2026-03-02 | 217 | 2027-01-20
A42470 | Process Safeguarding Diagram: Condensate Collection System_IFR | 2026-02-20 | 2026-02-20 | 04-Jan-25 A | 25-Jan-25 A | 2026-03-02 | 11 | 2026-03-02
A42480 | Process Safeguarding Diagram: Condensate Collection System_RCC | 2026-02-20 | 2026-02-20 | 26-Jan-25 A | 20-Feb-25 A | 2026-03-02 | 16 | 2026-03-02
A42490 | Process Safeguarding Diagram: Condensate Collection System_IFH | 2026-02-20 | 2026-02-20 | 21-Feb-25 A | 27-May-25 A | 2026-03-02 | 11 | 2026-03-02
A42500 | Process Safeguarding Diagram: Condensate Collection System_RCA | 2026-02-20 | 2026-02-20 | 28-May-25 A | 21-Jun-25 A | 2027-01-20 | 16 | 2027-01-20
A42510 | Process Safeguarding Diagram: Condensate Collection System_IFD/IFC | 2026-02-20 | 2026-02-20 | 22-Jun-25 A | 28-Jun-25 A | 2027-01-20 | 2 | 2027-01-20
Process Safeguarding Diagram: Cooling Water System |  | 2026-02-20 | 2026-02-20 | 04-Jan-25 A | 28-Jun-25 A | 2026-03-02 | 217 | 2027-01-20
A42520 | Process Safeguarding Diagram: Cooling Water System_IFR | 2026-02-20 | 2026-02-20 | 04-Jan-25 A | 25-Jan-25 A | 2026-03-02 | 11 | 2026-03-02
A42530 | Process Safeguarding Diagram: Cooling Water System_RCC | 2026-02-20 | 2026-02-20 | 26-Jan-25 A | 20-Feb-25 A | 2026-03-02 | 16 | 2026-03-02
A42540 | Process Safeguarding Diagram: Cooling Water System_IFH | 2026-02-20 | 2026-02-20 | 21-Feb-25 A | 27-May-25 A | 2026-03-02 | 11 | 2026-03-02
A42550 | Process Safeguarding Diagram: Cooling Water System_RCA | 2026-02-20 | 2026-02-20 | 28-May-25 A | 21-Jun-25 A | 2027-01-20 | 16 | 2027-01-20
A42560 | Process Safeguarding Diagram: Cooling Water System_IFD/IFC | 2026-02-20 | 2026-02-20 | 22-Jun-25 A | 28-Jun-25 A | 2027-01-20 | 2 | 2027-01-20
Process Safeguarding Diagram: Utility System For H2 Extraction Unit |  | 2026-02-20 | 2026-02-20 | 04-Jan-25 A | 28-Jun-25 A | 2026-03-02 | 217 | 2027-01-20
A42570 | Process Safeguarding Diagram: Utility System For H2 Extraction Unit_IFR | 2026-02-20 | 2026-02-20 | 04-Jan-25 A | 25-Jan-25 A | 2026-03-02 | 11 | 2026-03-02
A42580 | Process Safeguarding Diagram: Utility System For H2 Extraction Unit_RCC | 2026-02-20 | 2026-02-20 | 26-Jan-25 A | 20-Feb-25 A | 2026-03-02 | 16 | 2026-03-02
A42590 | Process Safeguarding Diagram: Utility System For H2 Extraction Unit_IFH | 2026-02-20 | 2026-02-20 | 21-Feb-25 A | 27-May-25 A | 2026-03-02 | 11 | 2026-03-02
A42600 | Process Safeguarding Diagram: Utility System For H2 Extraction Unit_RCA | 2026-02-20 | 2026-02-20 | 28-May-25 A | 21-Jun-25 A | 2027-01-20 | 16 | 2027-01-20
A42610 | Process Safeguarding Diagram: Utility System For H2 Extraction Unit_IFD/IFC | 2026-02-20 | 2026-02-20 | 22-Jun-25 A | 28-Jun-25 A | 2027-01-20 | 2 | 2027-01-20
Process Safeguarding Diagram: Blowdown Vessels And Acid Gas Flare |  | 2026-02-20 | 2026-02-20 | 04-Jan-25 A | 28-Jun-25 A | 2026-03-02 | 217 | 2027-01-20
A42620 | Process Safeguarding Diagram: Blowdown Vessels And Acid Gas Flare_IFR | 2026-02-20 | 2026-02-20 | 04-Jan-25 A | 25-Jan-25 A | 2026-03-02 | 11 | 2026-03-02
A42630 | Process Safeguarding Diagram: Blowdown Vessels And Acid Gas Flare_RCC | 2026-02-20 | 2026-02-20 | 26-Jan-25 A | 20-Feb-25 A | 2026-03-02 | 16 | 2026-03-02
A42640 | Process Safeguarding Diagram: Blowdown Vessels And Acid Gas Flare_IFH | 2026-02-20 | 2026-02-20 | 21-Feb-25 A | 27-May-25 A | 2026-03-02 | 11 | 2026-03-02
A42650 | Process Safeguarding Diagram: Blowdown Vessels And Acid Gas Flare_RCA | 2026-02-20 | 2026-02-20 | 28-May-25 A | 21-Jun-25 A | 2027-01-20 | 16 | 2027-01-20
A42660 | Process Safeguarding Diagram: Blowdown Vessels And Acid Gas Flare_IFD/IFC | 2026-02-20 | 2026-02-20 | 22-Jun-25 A | 28-Jun-25 A | 2027-01-20 | 2 | 2027-01-20
Process Safeguarding Diagram: Slop,Sewer And Drainage System |  | 2026-02-20 | 2026-02-20 | 04-Jan-25 A | 28-Jun-25 A | 2026-03-02 | 217 | 2027-01-20
A42670 | Process Safeguarding Diagram: Slop,Sewer And Drainage System_IFR | 2026-02-20 | 2026-02-20 | 04-Jan-25 A | 25-Jan-25 A | 2026-03-02 | 11 | 2026-03-02
A42680 | Process Safeguarding Diagram: Slop,Sewer And Drainage System_RCC | 2026-02-20 | 2026-02-20 | 26-Jan-25 A | 20-Feb-25 A | 2026-03-02 | 16 | 2026-03-02
A42690 | Process Safeguarding Diagram: Slop,Sewer And Drainage System_IFH | 2026-02-20 | 2026-02-20 | 21-Feb-25 A | 27-May-25 A | 2026-03-02 | 11 | 2026-03-02
A42700 | Process Safeguarding Diagram: Slop,Sewer And Drainage System_RCA | 2026-02-20 | 2026-02-20 | 28-May-25 A | 21-Jun-25 A | 2027-01-20 | 16 | 2027-01-20
A42710 | Process Safeguarding Diagram: Slop,Sewer And Drainage System_IFD/IFC | 2026-02-20 | 2026-02-20 | 22-Jun-25 A | 28-Jun-25 A | 2027-01-20 | 2 | 2027-01-20
Process Safeguarding Diagram: Slop,Sewer And Drainage System II |  | 2026-02-20 | 2026-02-20 | 04-Jan-25 A | 28-Jun-25 A | 2026-03-02 | 217 | 2027-01-20
A4130 | Process Safeguarding Diagram: Slop,Sewer And Drainage System II_IFR | 2026-02-20 | 2026-02-20 | 04-Jan-25 A | 25-Jan-25 A | 2026-03-02 | 11 | 2026-03-02
A4140 | Process Safeguarding Diagram: Slop,Sewer And Drainage System II_RCC | 2026-02-20 | 2026-02-20 | 26-Jan-25 A | 20-Feb-25 A | 2026-03-02 | 16 | 2026-03-02
A4150 | Process Safeguarding Diagram: Slop,Sewer And Drainage System II_IFH | 2026-02-20 | 2026-02-20 | 21-Feb-25 A | 27-May-25 A | 2026-03-02 | 11 | 2026-03-02
A4160 | Process Safeguarding Diagram: Slop,Sewer And Drainage System II_RCA | 2026-02-20 | 2026-02-20 | 28-May-25 A | 21-Jun-25 A | 2026-03-02 | 16 | 2026-03-02
A4170 | Process Safeguarding Diagram: Slop,Sewer And Drainage System II_IFD/IFC | 2026-02-20 | 2026-02-20 | 22-Jun-25 A | 28-Jun-25 A | 2027-01-20 | 2 | 2027-01-20
Utility Consumption |  | 2026-02-20 | 2026-02-24 | 21-Jun-25 A | 2026-02-24 | 2026-03-25 | 87 | 2026-03-27 | 23
A42760 | Utility Consumption_IFR | 2026-02-20 | 2026-02-20 | 21-Jun-25 A | 12-Jul-25 A | 2026-03-25 | 6 | 2026-03-25
A42770 | Utility Consumption_RCC | 2026-02-20 | 2026-02-20 | 02-Oct-25 A | 22-Oct-25 A | 2026-03-25 | 16 | 2026-03-25
A42780 | Utility Consumption_IFA | 2026-02-20 | 2026-02-20 | 16-Dec-25 A | 26-Dec-25 A | 2026-03-25 | 3 | 2026-03-25
A42790 | Utility Consumption_RCA | 2026-02-20 | 2026-02-20 | 16-Dec-25 A | 26-Dec-25 A | 2026-03-25 | 16 | 2026-03-25
A42800 | Utility Consumption_IFD/IFC | 2026-02-20 | 2026-02-24 | 2026-02-20 | 2026-02-24 | 2026-03-25 | 2 | 2026-03-27 | 23
Safeguarding Memorendum |  | 2026-02-20 | 2026-02-24 | 02-Sep-25 A | 2026-02-24 | 2027-01-18 | 72 | 2027-01-20 | 237
A4180 | Safeguarding Memorandum_IFR | 2026-02-20 | 2026-02-20 | 02-Sep-25 A | 13-Sep-25 A | 2027-01-18 | 6 | 2027-01-18
A42720 | Safeguarding Memorandum_RCC | 2026-02-20 | 2026-02-20 | 17-Sep-25 A | 06-Oct-25 A | 2027-01-18 | 16 | 2027-01-18
A42730 | Safeguarding Memorandum_IFA | 2026-02-20 | 2026-02-20 | 06-Oct-25 A | 25-Nov-25 A | 2027-01-18 | 3 | 2027-01-18
A42740 | Safeguarding Memorandum_RCA | 2026-02-20 | 2026-02-20 | 25-Nov-25 A | 29-Dec-25 A | 2027-01-18 | 16 | 2027-01-18
A42750 | Safeguarding Memorandum_IFD/IFC | 2026-02-20 | 2026-02-24 | 2026-02-20 | 2026-02-24 | 2027-01-18 | 2 | 2027-01-20 | 237
Process Utility Adequacy Check Report |  | 2026-02-20 | 2026-02-20 | 10-Oct-25 A | 19-Jan-26 A | 2026-03-27 | 61 | 2026-03-27
A43210 | Process Utility Adequacy Check Report_IFR | 2026-02-20 | 2026-02-20 | 10-Oct-25 A | 17-Oct-25 A | 2026-03-27 | 6 | 2026-03-27
A43220 | Process Utility Adequacy Check Report_RCC | 2026-02-20 | 2026-02-20 | 11-Oct-25 A | 24-Oct-25 A | 2026-03-27 | 16 | 2026-03-27
A43230 | Process Utility Adequacy Check Report_IFA | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 24-Dec-25 A | 2026-03-27 | 3 | 2026-03-27
A43240 | Process Utility Adequacy Check Report_RCA | 2026-02-20 | 2026-02-20 | 24-Dec-25 A | 15-Jan-26 A | 2026-03-27 | 16 | 2026-03-27
A43250 | Process Utility Adequacy Check Report_IFD/IFC | 2026-02-20 | 2026-02-20 | 15-Jan-26 A | 19-Jan-26 A | 2026-03-27 | 2 | 2026-03-27
Process Datasheet for PSA2 Feed Gas Compressor 1st Stage Suction Drum |  | 2026-02-20 | 2026-02-20 | 31-Dec-24 A | 21-May-25 A | 2026-03-02 | 124 | 2027-01-20
A41350 | Process Datasheet for PSA2 Feed Gas Compressor 1st Stage Suction Drum_IFR | 2026-02-20 | 2026-02-20 | 31-Dec-24 A | 24-Jan-25 A | 2026-03-02 | 2 | 2026-03-02
A41360 | Process Datasheet for PSA2 Feed Gas Compressor 1st Stage Suction Drum_RCC | 2026-02-20 | 2026-02-20 | 25-Jan-25 A | 18-Mar-25 A | 2027-01-20 | 16 | 2027-01-20
A41370 | Process Datasheet for PSA2 Feed Gas Compressor 1st Stage Suction Drum_IFA | 2026-02-20 | 2026-02-20 | 19-Mar-25 A | 19-Apr-25 A | 2027-01-20 | 2 | 2027-01-20
A41380 | Process Datasheet for PSA2 Feed Gas Compressor 1st Stage Suction Drum_RCA | 2026-02-20 | 2026-02-20 | 20-Apr-25 A | 14-May-25 A | 2027-01-20 | 16 | 2027-01-20
A41390 | Process Datasheet for PSA2 Feed Gas Compressor 1st Stage Suction Drum_IFD/IFC | 2026-02-20 | 2026-02-20 | 15-May-25 A | 21-May-25 A | 2027-01-20 | 2 | 2027-01-20
Process Datasheet for PSA2 Feed Gas Compressor 1st Stage Cooler |  | 2026-02-20 | 2026-02-20 | 01-Jan-25 A | 21-Jun-25 A | 2026-03-02 | 131 | 2027-01-20
A41400 | Process Datasheet for PSA2 Feed Gas Compressor 1st Stage Cooler_IFR | 2026-02-20 | 2026-02-20 | 01-Jan-25 A | 26-Jan-25 A | 2026-03-02 | 2 | 2026-03-02
A41410 | Process Datasheet for PSA2 Feed Gas Compressor 1st Stage Cooler_RCC | 2026-02-20 | 2026-02-20 | 27-Jan-25 A | 19-Mar-25 A | 2027-01-20 | 16 | 2027-01-20
A41420 | Process Datasheet for PSA2 Feed Gas Compressor 1st Stage Cooler_IFA | 2026-02-20 | 2026-02-20 | 20-Mar-25 A | 20-May-25 A | 2027-01-20 | 2 | 2027-01-20
A41430 | Process Datasheet for PSA2 Feed Gas Compressor 1st Stage Cooler_RCA | 2026-02-20 | 2026-02-20 | 21-May-25 A | 02-Jun-25 A | 2027-01-20 | 16 | 2027-01-20
A41440 | Process Datasheet for PSA2 Feed Gas Compressor 1st Stage Cooler_IFD/IFC | 2026-02-20 | 2026-02-20 | 03-Jun-25 A | 21-Jun-25 A | 2027-01-20 | 2 | 2027-01-20
Process Datasheet for PSA2 Feed Gas Compressor 2nd Stage Suction Drum |  | 2026-02-20 | 2026-02-20 | 31-Dec-24 A | 21-May-25 A | 2026-03-02 | 123 | 2027-01-20
A41450 | Process Datasheet for PSA2 Feed Gas Compressor 2nd Stage Suction Drum_IFR | 2026-02-20 | 2026-02-20 | 31-Dec-24 A | 24-Jan-25 A | 2026-03-02 | 2 | 2026-03-02
A41460 | Process Datasheet for PSA2 Feed Gas Compressor 2nd Stage Suction Drum_RCC | 2026-02-20 | 2026-02-20 | 25-Jan-25 A | 18-Mar-25 A | 2027-01-20 | 16 | 2027-01-20
A41470 | Process Datasheet for PSA2 Feed Gas Compressor 2nd Stage Suction Drum_IFA | 2026-02-20 | 2026-02-20 | 19-Mar-25 A | 19-Apr-25 A | 2027-01-20 | 2 | 2027-01-20
A41480 | Process Datasheet for PSA2 Feed Gas Compressor 2nd Stage Suction Drum_RCA | 2026-02-20 | 2026-02-20 | 20-Apr-25 A | 14-May-25 A | 2027-01-20 | 16 | 2027-01-20
A41490 | Process Datasheet for PSA2 Feed Gas Compressor 2nd Stage Suction Drum_IFD/IFC | 2026-02-20 | 2026-02-20 | 15-May-25 A | 21-May-25 A | 2027-01-20 | 2 | 2027-01-20
Process Datasheet for PSA2 Feed Gas Compressor 2nd Stage Cooler |  | 2026-02-20 | 2026-02-20 | 01-Jan-25 A | 21-Jun-25 A | 2026-03-02 | 131 | 2027-01-20
A41500 | Process Datasheet for PSA2 Feed Gas Compressor 2nd Stage Cooler_IFR | 2026-02-20 | 2026-02-20 | 01-Jan-25 A | 26-Jan-25 A | 2026-03-02 | 2 | 2026-03-02
A41510 | Process Datasheet for PSA2 Feed Gas Compressor 2nd Stage Cooler_RCC | 2026-02-20 | 2026-02-20 | 27-Jan-25 A | 19-Mar-25 A | 2027-01-20 | 16 | 2027-01-20
A41520 | Process Datasheet for PSA2 Feed Gas Compressor 2nd Stage Cooler_IFA | 2026-02-20 | 2026-02-20 | 20-Mar-25 A | 20-May-25 A | 2027-01-20 | 2 | 2027-01-20
A41530 | Process Datasheet for PSA2 Feed Gas Compressor 2nd Stage Cooler_RCA | 2026-02-20 | 2026-02-20 | 21-May-25 A | 02-Jun-25 A | 2027-01-20 | 16 | 2027-01-20
A41540 | Process Datasheet for PSA2 Feed Gas Compressor 2nd Stage Cooler_IFD/IFC | 2026-02-20 | 2026-02-20 | 03-Jun-25 A | 21-Jun-25 A | 2027-01-20 | 2 | 2027-01-20
Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Suction Drum |  | 2026-02-20 | 2026-02-20 | 31-Dec-24 A | 20-May-25 A | 2026-03-02 | 123 | 2027-01-20
A41550 | Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Suction Drum_IFR | 2026-02-20 | 2026-02-20 | 31-Dec-24 A | 24-Jan-25 A | 2026-03-02 | 2 | 2026-03-02
A41560 | Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Suction Drum_RCC | 2026-02-20 | 2026-02-20 | 25-Jan-25 A | 18-Mar-25 A | 2027-01-20 | 16 | 2027-01-20
A41570 | Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Suction Drum_IFA | 2026-02-20 | 2026-02-20 | 19-Mar-25 A | 19-Apr-25 A | 2027-01-20 | 2 | 2027-01-20
A41580 | Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Suction Drum_RCA | 2026-02-20 | 2026-02-20 | 20-Apr-25 A | 13-May-25 A | 2027-01-20 | 16 | 2027-01-20
A41590 | Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Suction Drum_IFD/IFC | 2026-02-20 | 2026-02-20 | 14-May-25 A | 20-May-25 A | 2027-01-20 | 2 | 2027-01-20
Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Cooler |  | 2026-02-20 | 2026-02-20 | 01-Jan-25 A | 20-Jul-25 A | 2026-03-02 | 232 | 2027-01-20
A41600 | Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Cooler_IFR | 2026-02-20 | 2026-02-20 | 01-Jan-25 A | 26-Jan-25 A | 2026-03-02 | 2 | 2026-03-02
A41610 | Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Cooler_RCC | 2026-02-20 | 2026-02-20 | 27-Jan-25 A | 19-Mar-25 A | 2027-01-20 | 16 | 2027-01-20
A41620 | Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Cooler_IFA | 2026-02-20 | 2026-02-20 | 20-Mar-25 A | 21-Jun-25 A | 2027-01-20 | 2 | 2027-01-20
A41630 | Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Cooler_RCA | 2026-02-20 | 2026-02-20 | 28-Jun-25 A | 14-Jul-25 A | 2027-01-20 | 16 | 2027-01-20
A41640 | Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Cooler_IFD/IFC | 2026-02-20 | 2026-02-20 | 16-Jul-25 A | 20-Jul-25 A | 2027-01-20 | 2 | 2027-01-20
Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Discharge Drum |  | 2026-02-20 | 2026-02-20 | 31-Dec-24 A | 20-May-25 A | 2026-03-02 | 37 | 2027-01-20
A41650 | Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Discharge Drum_IFR | 2026-02-20 | 2026-02-20 | 31-Dec-24 A | 24-Jan-25 A | 2026-03-02 | 2 | 2026-03-02
A41660 | Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Discharge Drum_RCC | 2026-02-20 | 2026-02-20 | 25-Jan-25 A | 18-Mar-25 A | 2027-01-20 | 16 | 2027-01-20
A2550 | Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Discharge Drum_IFA | 2026-02-20 | 2026-02-20 | 19-Mar-25 A | 19-Apr-25 A | 2027-01-20 | 2 | 2027-01-20
A2560 | Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Discharge Drum_RCA | 2026-02-20 | 2026-02-20 | 20-Apr-25 A | 13-May-25 A | 2027-01-20 | 16 | 2027-01-20
A2570 | Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Discharge Drum_IFD/IFC | 2026-02-20 | 2026-02-20 | 14-May-25 A | 20-May-25 A | 2027-01-20 | 2 | 2027-01-20
Process Datasheet for PSA2 Off Gas Buffer Drum - 13-VV-712 |  | 2026-02-20 | 2026-02-20 | 31-Dec-24 A | 12-Jun-25 A | 2026-03-02 | 132 | 2027-01-20
A2580 | Process Datasheet for PSA2 Off Gas Buffer Drum - 13-VV-712_IFR | 2026-02-20 | 2026-02-20 | 31-Dec-24 A | 24-Jan-25 A | 2026-03-02 | 2 | 2026-03-02
A2590 | Process Datasheet for PSA2 Off Gas Buffer Drum - 13-VV-712_RCC | 2026-02-20 | 2026-02-20 | 25-Jan-25 A | 14-May-25 A | 2027-01-20 | 16 | 2027-01-20
A2600 | Process Datasheet for PSA2 Off Gas Buffer Drum - 13-VV-712_IFA | 2026-02-20 | 2026-02-20 | 15-May-25 A | 21-May-25 A | 2027-01-20 | 2 | 2027-01-20
A2610 | Process Datasheet for PSA2 Off Gas Buffer Drum - 13-VV-712_RCA | 2026-02-20 | 2026-02-20 | 22-May-25 A | 02-Jun-25 A | 2027-01-20 | 16 | 2027-01-20
A2620 | Process Datasheet for PSA2 Off Gas Buffer Drum - 13-VV-712_IFD/IFC | 2026-02-20 | 2026-02-20 | 03-Jun-25 A | 12-Jun-25 A | 2027-01-20 | 2 | 2027-01-20
Process Datasheet for PSA2 Off Gas Compressor Interstage Cooler - 13-HE-708 |  | 2026-02-20 | 2026-02-20 | 01-Jan-25 A | 21-Jun-25 A | 2026-03-02 | 131 | 2027-01-20
A2630 | Process Datasheet for PSA2 Off Gas Compressor Interstage Cooler - 13-HE-708_IFR | 2026-02-20 | 2026-02-20 | 01-Jan-25 A | 26-Jan-25 A | 2026-03-02 | 2 | 2026-03-02
A2640 | Process Datasheet for PSA2 Off Gas Compressor Interstage Cooler - 13-HE-708_RCC | 2026-02-20 | 2026-02-20 | 27-Jan-25 A | 19-Mar-25 A | 2027-01-20 | 16 | 2027-01-20
A2650 | Process Datasheet for PSA2 Off Gas Compressor Interstage Cooler - 13-HE-708_IFA | 2026-02-20 | 2026-02-20 | 20-Mar-25 A | 20-May-25 A | 2027-01-20 | 2 | 2027-01-20
A2660 | Process Datasheet for PSA2 Off Gas Compressor Interstage Cooler - 13-HE-708_RCA | 2026-02-20 | 2026-02-20 | 21-May-25 A | 11-Jun-25 A | 2027-01-20 | 16 | 2027-01-20
A2670 | Process Datasheet for PSA2 Off Gas Compressor Interstage Cooler - 13-HE-708_IFD/IFC | 2026-02-20 | 2026-02-20 | 12-Jun-25 A | 21-Jun-25 A | 2027-01-20 | 2 | 2027-01-20
Process Datasheet for PSA2 Off Gas Compressor 2Nd Stage Suction Drum 13-VV-713 |  | 2026-02-20 | 2026-02-20 | 31-Dec-24 A | 13-Jun-25 A | 2026-03-02 | 132 | 2027-01-20
A2680 | Process Datasheet for PSA2 Off Gas Compressor 2Nd Stage Suction Drum 13-VV-713_IFR | 2026-02-20 | 2026-02-20 | 31-Dec-24 A | 24-Jan-25 A | 2026-03-02 | 2 | 2026-03-02
A41670 | Process Datasheet for PSA2 Off Gas Compressor 2Nd Stage Suction Drum 13-VV-713_RCC | 2026-02-20 | 2026-02-20 | 25-Jan-25 A | 14-May-25 A | 2027-01-20 | 16 | 2027-01-20
A41680 | Process Datasheet for PSA2 Off Gas Compressor 2Nd Stage Suction Drum 13-VV-713_IFA | 2026-02-20 | 2026-02-20 | 15-May-25 A | 21-May-25 A | 2027-01-20 | 2 | 2027-01-20
A41690 | Process Datasheet for PSA2 Off Gas Compressor 2Nd Stage Suction Drum 13-VV-713_RCA | 2026-02-20 | 2026-02-20 | 22-May-25 A | 02-Jun-25 A | 2027-01-20 | 16 | 2027-01-20
A2720 | Process Datasheet for PSA2 Off Gas Compressor 2Nd Stage Suction Drum 13-VV-713_IFD/IFC | 2026-02-20 | 2026-02-20 | 03-Jun-25 A | 13-Jun-25 A | 2027-01-20 | 2 | 2027-01-20
Process Datasheet for PSA2 Off Gas Compressor Aftercooler - 13-HE-709 |  | 2026-02-20 | 2026-02-24 | 01-Jan-25 A | 2026-02-24 | 2026-03-02 | 301 | 2027-01-20 | 237
A2730 | Process Datasheet for PSA2 Off Gas Compressor Aftercooler - 13-HE-709_IFR | 2026-02-20 | 2026-02-20 | 01-Jan-25 A | 26-Jan-25 A | 2026-03-02 | 2 | 2026-03-02
A2740 | Process Datasheet for PSA2 Off Gas Compressor Aftercooler - 13-HE-709_RCC | 2026-02-20 | 2026-02-20 | 27-Jan-25 A | 19-Mar-25 A | 2027-01-18 | 16 | 2027-01-18
A2750 | Process Datasheet for PSA2 Off Gas Compressor Aftercooler - 13-HE-709_IFA | 2026-02-20 | 2026-02-20 | 20-Mar-25 A | 20-May-25 A | 2027-01-18 | 2 | 2027-01-18
A2760 | Process Datasheet for PSA2 Off Gas Compressor Aftercooler - 13-HE-709_RCA | 2026-02-20 | 2026-02-20 | 21-May-25 A | 11-Jun-25 A | 2027-01-18 | 16 | 2027-01-18
A2770 | Process Datasheet for PSA2 Off Gas Compressor Aftercooler - 13-HE-709_IFD/IFC | 2026-02-20 | 2026-02-24 | 2026-02-20 | 2026-02-24 | 2027-01-18 | 2 | 2027-01-20 | 237
Process Datasheet for PSA2 Off Gas Compressor Discharge Dripleg - 13-SP-7004* |  | 2026-02-20 | 2026-02-20 | 01-Jan-25 A | 25-Jun-25 A | 2026-03-02 | 220 | 2027-01-18
A2780 | Process Datasheet for PSA2 Off Gas Compressor Discharge Dripleg - 13-SP-7004_IFR | 2026-02-20 | 2026-02-20 | 01-Jan-25 A | 24-Jan-25 A | 2026-03-02 | 2 | 2026-03-02
A2790 | Process Datasheet for PSA2 Off Gas Compressor Discharge Dripleg - 13-SP-7004_RCC | 2026-02-20 | 2026-02-20 | 25-Jan-25 A | 05-May-25 A | 2027-01-18 | 16 | 2027-01-18
A2800 | Process Datasheet for PSA2 Off Gas Compressor Discharge Dripleg - 13-SP-7004_IFA | 2026-02-20 | 2026-02-20 | 06-May-25 A | 11-Jun-25 A | 2027-01-18 | 2 | 2027-01-18
A2810 | Process Datasheet for PSA2 Off Gas Compressor Discharge Dripleg - 13-SP-7004_RCA | 2026-02-20 | 2026-02-20 | 12-Jun-25 A | 21-Jun-25 A | 2027-01-18 | 16 | 2027-01-18
A55750 | Process Datasheet for PSA2 Off Gas Compressor Discharge Dripleg - 13-SP-7004_IFD/IFC | 2026-02-20 | 2026-02-20 | 23-Jun-25 A | 25-Jun-25 A | 2027-01-18 | 6 | 2027-01-18
Process Datasheet for 52-SP-14067 Vhp Boiler Feed Water Preheater Dripleg |  | 2026-02-20 | 2026-04-10 | 01-Jan-25 A | 2026-04-10 | 2026-03-02 | 335 | 2027-01-20 | 203
A2830 | Process Datasheet for 52-SP-14067 Vhp Boiler Feed Water Preheater Dripleg_IFR | 2026-02-20 | 2026-02-20 | 01-Jan-25 A | 06-Jun-25 A | 2026-03-02 | 2 | 2026-03-02
A2840 | Process Datasheet for 52-SP-14067 Vhp Boiler Feed Water Preheater Dripleg_RCC | 2026-02-20 | 2026-03-13 | 2026-02-20 | 2026-03-13 | 2026-12-02 | 16 | 2026-12-23 | 203
A2850 | Process Datasheet for 52-SP-14067 Vhp Boiler Feed Water Preheater Dripleg_IFA | 2026-03-13 | 2026-03-17 | 2026-03-13 | 2026-03-17 | 2026-12-23 | 2 | 2026-12-25 | 203
A41700 | Process Datasheet for 52-SP-14067 Vhp Boiler Feed Water Preheater Dripleg_RCA | 2026-03-18 | 2026-04-08 | 2026-03-18 | 2026-04-08 | 2026-12-28 | 16 | 2027-01-18 | 203
A41710 | Process Datasheet for 52-SP-14067 Vhp Boiler Feed Water Preheater Dripleg_IFD/IFC | 2026-04-08 | 2026-04-10 | 2026-04-08 | 2026-04-10 | 2027-01-18 | 2 | 2027-01-20 | 203
Process Datasheet for 50-HE-1410 C4 Guard Adsorber Regeneration Gas Cooler |  | 2026-02-20 | 2026-02-24 | 01-Jan-25 A | 2026-02-24 | 2026-03-02 | 215 | 2027-01-20 | 237
A41720 | Process Datasheet for 50-HE-1410 C4 Guard Adsorber Regeneration Gas Cooler_IFR | 2026-02-20 | 2026-02-20 | 01-Jan-25 A | 27-Apr-25 A | 2026-03-02 | 2 | 2026-03-02
A2890 | Process Datasheet for 50-HE-1410 C4 Guard Adsorber Regeneration Gas Cooler_RCC | 2026-02-20 | 2026-02-20 | 28-Apr-25 A | 04-May-25 A | 2027-01-18 | 16 | 2027-01-18
A2900 | Process Datasheet for 50-HE-1410 C4 Guard Adsorber Regeneration Gas Cooler_IFA | 2026-02-20 | 2026-02-20 | 05-May-25 A | 30-May-25 A | 2027-01-18 | 2 | 2027-01-18
A2910 | Process Datasheet for 50-HE-1410 C4 Guard Adsorber Regeneration Gas Cooler_RCA | 2026-02-20 | 2026-02-20 | 01-Jun-25 A | 21-Jun-25 A | 2027-01-18 | 16 | 2027-01-18
A2920 | Process Datasheet for 50-HE-1410 C4 Guard Adsorber Regeneration Gas Cooler_IFD/IFC | 2026-02-20 | 2026-02-24 | 2026-02-20 | 2026-02-24 | 2027-01-18 | 2 | 2027-01-20 | 237
Process Datasheet for 50-VV-1403 C4 Guard Adsorber Regeneration Gas Coalescer |  | 2026-02-20 | 2026-03-20 | 01-Jan-25 A | 2026-03-20 | 2026-03-02 | 319 | 2027-01-20 | 219
A2980 | Process Datasheet for 50-VV-1403 C4 Guard Adsorber Regeneration Gas Coalescer_IFR | 2026-02-20 | 2026-02-20 | 01-Jan-25 A | 30-Jan-25 A | 2026-03-02 | 2 | 2026-03-02
A2990 | Process Datasheet for 50-VV-1403 C4 Guard Adsorber Regeneration Gas Coalescer_RCC | 2026-02-20 | 2026-02-20 | 31-Jan-25 A | 20-Apr-25 A | 2026-12-23 | 16 | 2026-12-23
A3000 | Process Datasheet for 50-VV-1403 C4 Guard Adsorber Regeneration Gas Coalescer_IFA | 2026-02-20 | 2026-02-24 | 2026-02-20 | 2026-02-24 | 2026-12-23 | 2 | 2026-12-25 | 219
A3010 | Process Datasheet for 50-VV-1403 C4 Guard Adsorber Regeneration Gas Coalescer_RCA | 2026-02-24 | 2026-03-17 | 2026-02-24 | 2026-03-17 | 2026-12-28 | 16 | 2027-01-18 | 219
A3020 | Process Datasheet for 50-VV-1403 C4 Guard Adsorber Regeneration Gas Coalescer_IFD/IFC | 2026-03-18 | 2026-03-20 | 2026-03-18 | 2026-03-20 | 2027-01-18 | 2 | 2027-01-20 | 219
Process Datasheet for 70-PC-1407 Water Collection Sump Pump II |  | 2026-02-20 | 2026-02-20 | 01-Jan-25 A | 13-Jan-26 A | 2026-03-02 | 272 | 2027-01-20
A41730 | Process Datasheet for 70-PC-1407 Water Collection Sump Pump II_IFR | 2026-02-20 | 2026-02-20 | 01-Jan-25 A | 24-Jan-25 A | 2026-03-02 | 2 | 2026-03-02
A41740 | Process Datasheet for 70-PC-1407 Water Collection Sump Pump II_RCC | 2026-02-20 | 2026-02-20 | 25-Jan-25 A | 02-May-25 A | 2027-01-20 | 16 | 2027-01-20
A41750 | Process Datasheet for 70-PC-1407 Water Collection Sump Pump II_IFA | 2026-02-20 | 2026-02-20 | 03-May-25 A | 19-Sep-25 A | 2027-01-20 | 2 | 2027-01-20
A41760 | Process Datasheet for 70-PC-1407 Water Collection Sump Pump II_RCA | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 09-Jan-26 A | 2027-01-20 | 16 | 2027-01-20
A41770 | Process Datasheet for 70-PC-1407 Water Collection Sump Pump II_IFD/IFC | 2026-02-20 | 2026-02-20 | 09-Jan-26 A | 13-Jan-26 A | 2027-01-20 | 2 | 2027-01-20
Process Datasheet for 70-PC-1409 A/B Sanitary Waste Water Sump Pump |  | 2026-02-20 | 2026-02-20 | 01-Jan-25 A | 12-Nov-25 A | 2026-03-02 | 297 | 2027-01-20
A3080 | Process Datasheet for 70-PC-1409 A/B Sanitary Waste Water Sump Pump_IFR | 2026-02-20 | 2026-02-20 | 01-Jan-25 A | 24-Jan-25 A | 2026-03-02 | 2 | 2026-03-02
A3090 | Process Datasheet for 70-PC-1409 A/B Sanitary Waste Water Sump Pump_RCC | 2026-02-20 | 2026-02-20 | 25-Jan-25 A | 02-May-25 A | 2027-01-20 | 16 | 2027-01-20
A3100 | Process Datasheet for 70-PC-1409 A/B Sanitary Waste Water Sump Pump_IFA | 2026-02-20 | 2026-02-20 | 01-Aug-25 A | 05-Aug-25 A | 2027-01-20 | 2 | 2027-01-20
A3110 | Process Datasheet for 70-PC-1409 A/B Sanitary Waste Water Sump Pump_RCA | 2026-02-20 | 2026-02-20 | 05-Aug-25 A | 25-Aug-25 A | 2027-01-20 | 16 | 2027-01-20
A3120 | Process Datasheet for 70-PC-1409 A/B Sanitary Waste Water Sump Pump_IFD/IFC | 2026-02-20 | 2026-02-20 | 02-Sep-25 A | 12-Nov-25 A | 2027-01-20 | 2 | 2027-01-20
Process Datasheet for 70-VV-1415 PSA2 Slop Drum |  | 2026-02-20 | 2026-02-20 | 01-Jan-25 A | 03-Nov-25 A | 2026-03-02 | 216 | 2027-01-20
A3130 | Process Datasheet for 70-VV-1415 PSA2 Slop Drum_IFR | 2026-02-20 | 2026-02-20 | 01-Jan-25 A | 24-Jan-25 A | 2026-03-02 | 2 | 2026-03-02
A3140 | Process Datasheet for 70-VV-1415 PSA2 Slop Drum_RCC | 2026-02-20 | 2026-02-20 | 25-Jan-25 A | 05-May-25 A | 2027-01-20 | 16 | 2027-01-20
A3150 | Process Datasheet for 70-VV-1415 PSA2 Slop Drum_IFA | 2026-02-20 | 2026-02-20 | 06-May-25 A | 11-Jun-25 A | 2027-01-20 | 2 | 2027-01-20
A3160 | Process Datasheet for 70-VV-1415 PSA2 Slop Drum_RCA | 2026-02-20 | 2026-02-20 | 12-Jun-25 A | 21-Jun-25 A | 2027-01-20 | 16 | 2027-01-20
A41780 | Process Datasheet for 70-VV-1415 PSA2 Slop Drum_IFD/IFC | 2026-02-20 | 2026-02-20 | 24-Oct-25 A | 03-Nov-25 A | 2027-01-20 | 2 | 2027-01-20
Process Datasheet of Off-Gas Compressor Coalescer |  | 2026-02-20 | 2026-02-20 | 05-Jun-25 A | 12-Jul-25 A | 2027-01-20 | 252 | 2027-01-20
A28230 | Process Datasheet of Off-Gas Compressor Coalescer_IFR | 2026-02-20 | 2026-02-20 | 18-Jun-25 A | 21-Jun-25 A | 2027-01-20 | 2 | 2027-01-20
A28240 | Process Datasheet of Off-Gas Compressor Coalescer_RCC | 2026-02-20 | 2026-02-20 | 05-Jun-25 A | 25-Jun-25 A | 2027-01-20 | 16 | 2027-01-20
A55760 | Process Datasheet of Off-Gas Compressor Coalescer_IFA | 2026-02-20 | 2026-02-20 | 26-Jun-25 A | 28-Jun-25 A | 2027-01-20 | 2 | 2027-01-20
A55770 | Process Datasheet of Off-Gas Compressor Coalescer_RCA | 2026-02-20 | 2026-02-20 | 20-Jun-25 A | 05-Jul-25 A | 2027-01-20 | 16 | 2027-01-20
A55780 | Process Datasheet of Off-Gas Compressor Coalescer_IFD/IFC | 2026-02-20 | 2026-02-20 | 10-Jul-25 A | 12-Jul-25 A | 2027-01-20 | 2 | 2027-01-20
Sample Point /Connection Lists |  | 2026-02-20 | 2026-02-24 | 21-Jun-25 A | 2026-02-24 | 2027-01-18 | 139 | 2027-01-20 | 237
A43060 | Sample Point /Connection Lists_IFR | 2026-02-20 | 2026-02-20 | 21-Jun-25 A | 12-Jul-25 A | 2027-01-18 | 6 | 2027-01-18
A43070 | Sample Point /Connection Lists_RCC | 2026-02-20 | 2026-02-20 | 01-Oct-25 A | 27-Oct-25 A | 2027-01-18 | 16 | 2027-01-18
A43080 | Sample Point /Connection Lists_IFA | 2026-02-20 | 2026-02-20 | 28-Oct-25 A | 31-Oct-25 A | 2027-01-18 | 3 | 2027-01-18
A43090 | Sample Point /Connection Lists_RCA | 2026-02-20 | 2026-02-20 | 01-Nov-25 A | 05-Nov-25 A | 2027-01-18 | 16 | 2027-01-18
A43100 | Sample Point /Connection Lists_IFD/IFC | 2026-02-20 | 2026-02-24 | 2026-02-20 | 2026-02-24 | 2027-01-18 | 2 | 2027-01-20 | 237
Process Calculation Report |  | 2026-02-20 | 2026-03-23 | 20-Feb-25 A | 2026-03-23 | 2026-12-22 | 282 | 2027-01-20 | 218
A42960 | Process Calculation Report_IFR | 2026-02-20 | 2026-02-20 | 20-Feb-25 A | 26-Dec-25 A | 2026-12-22 | 6 | 2026-12-22
A42970 | Process Calculation Report_RCC | 2026-02-20 | 2026-02-20 | 26-Dec-25 A | 10-Jan-26 A | 2026-12-22 | 16 | 2026-12-22
A42980 | Process Calculation Report_IFA | 2026-02-20 | 2026-02-25 | 2026-02-20 | 2026-02-25 | 2026-12-22 | 3 | 2026-12-25 | 218
A42990 | Process Calculation Report_RCA | 2026-02-25 | 2026-03-19 | 2026-02-25 | 2026-03-19 | 2026-12-28 | 16 | 2027-01-18 | 218
A43000 | Process Calculation Report_IFD/IFC | 2026-03-19 | 2026-03-23 | 2026-03-19 | 2026-03-23 | 2027-01-18 | 2 | 2027-01-20 | 218
Process Datasheet for Control Valve |  | 2026-02-20 | 2026-02-20 | 20-Feb-25 A | 12-Jul-25 A | 2026-03-02 | 158 | 2027-01-20
A42810 | Process Datasheet for Control Valve_IFR | 2026-02-20 | 2026-02-20 | 20-Feb-25 A | 27-Apr-25 A | 2026-03-02 | 6 | 2026-03-02
A42820 | Process Datasheet for Control Valve_RCC | 2026-02-20 | 2026-02-20 | 28-Apr-25 A | 21-Jun-25 A | 2027-01-20 | 16 | 2027-01-20
A42830 | Process Datasheet for Control Valve_IFA | 2026-02-20 | 2026-02-20 | 22-Jun-25 A | 28-Jun-25 A | 2027-01-20 | 3 | 2027-01-20
A42840 | Process Datasheet for Control Valve_RCA | 2026-02-20 | 2026-02-20 | 29-Jun-25 A | 05-Jul-25 A | 2027-01-20 | 16 | 2027-01-20
A42850 | Process Datasheet for Control Valve_IFD/IFC | 2026-02-20 | 2026-02-20 | 06-Jul-25 A | 12-Jul-25 A | 2027-01-20 | 2 | 2027-01-20
Process Datasheet for Relief Valve |  | 2026-02-20 | 2026-02-20 | 25-Jan-25 A | 19-Jan-26 A | 2026-03-02 | 275 | 2027-01-20
A42860 | Process Datasheet for Relief Valve_IFR | 2026-02-20 | 2026-02-20 | 25-Jan-25 A | 20-Apr-25 A | 2026-03-02 | 6 | 2026-03-02
A42870 | Process Datasheet for Relief Valve_RCC | 2026-02-20 | 2026-02-20 | 16-Jul-25 A | 01-Aug-25 A | 2027-01-20 | 16 | 2027-01-20
A42880 | Process Datasheet for Relief Valve_IFA | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 24-Dec-25 A | 2027-01-20 | 3 | 2027-01-20
A42890 | Process Datasheet for Relief Valve_RCA | 2026-02-20 | 2026-02-20 | 24-Dec-25 A | 15-Jan-26 A | 2027-01-20 | 16 | 2027-01-20
A42900 | Process Datasheet for Relief Valve_IFD/IFC | 2026-02-20 | 2026-02-20 | 15-Jan-26 A | 19-Jan-26 A | 2027-01-20 | 2 | 2027-01-20
Process Datasheet for Flow Instrument |  | 2026-02-20 | 2026-03-23 | 20-Feb-25 A | 2026-03-23 | 2026-03-02 | 320 | 2027-01-20 | 218
A42910 | Process Datasheet for Flow Instrument_IFR | 2026-02-20 | 2026-02-20 | 20-Feb-25 A | 25-Apr-25 A | 2026-03-02 | 6 | 2026-03-02
A42920 | Process Datasheet for Flow Instrument_RCC | 2026-02-20 | 2026-02-20 | 26-Apr-25 A | 26-May-25 A | 2026-12-22 | 16 | 2026-12-22
A42930 | Process Datasheet for Flow Instrument_IFA | 2026-02-20 | 2026-02-25 | 2026-02-20 | 2026-02-25 | 2026-12-22 | 3 | 2026-12-25 | 218
A42940 | Process Datasheet for Flow Instrument_RCA | 2026-02-25 | 2026-03-19 | 2026-02-25 | 2026-03-19 | 2026-12-28 | 16 | 2027-01-18 | 218
A42950 | Process Datasheet for Flow Instrument_IFD/IFC | 2026-03-19 | 2026-03-23 | 2026-03-19 | 2026-03-23 | 2027-01-18 | 2 | 2027-01-20 | 218
Flare Relief Load Summary |  | 2026-02-20 | 2026-02-24 | 31-Jan-25 A | 2026-02-24 | 2026-03-25 | 278 | 2026-03-27 | 23
A43160 | Flare Relief Load Summary_IFR | 2026-02-20 | 2026-02-20 | 31-Jan-25 A | 11-Mar-25 A | 2026-03-25 | 6 | 2026-03-25
A43170 | Flare Relief Load Summary_RCC | 2026-02-20 | 2026-02-20 | 12-Mar-25 A | 20-Apr-25 A | 2026-03-25 | 16 | 2026-03-25
A43180 | Flare Relief Load Summary_IFA | 2026-02-20 | 2026-02-20 | 09-Dec-25 A | 19-Dec-25 A | 2026-03-25 | 3 | 2026-03-25
A43190 | Flare Relief Load Summary_RCA | 2026-02-20 | 2026-02-20 | 16-Dec-25 A | 13-Feb-26 A | 2026-03-25 | 16 | 2026-03-25
A43200 | Flare Relief Load Summary_IFD/IFC | 2026-02-20 | 2026-02-24 | 2026-02-20 | 2026-02-24 | 2026-03-25 | 2 | 2026-03-27 | 23
Flare Relief & Blowdown Report |  | 2026-02-20 | 2026-03-17 | 03-May-25 A | 2026-03-17 | 2026-11-23 | 103 | 2027-01-20 | 221
A43110 | Flare Relief & Blowdown Report_IFR | 2026-02-20 | 2026-02-20 | 03-May-25 A | 11-May-25 A | 2026-11-23 | 6 | 2026-11-23
A43120 | Flare Relief & Blowdown Report_RCC | 2026-02-20 | 2026-02-20 | 05-May-25 A | 18-May-25 A | 2026-12-28 | 16 | 2026-12-28
A43130 | Flare Relief & Blowdown Report_IFA | 2026-02-20 | 2026-02-20 | 05-Dec-25 A | 19-Dec-25 A | 2026-12-28 | 3 | 2026-12-28
A43140 | Flare Relief & Blowdown Report_RCA | 2026-02-20 | 2026-03-13 | 2026-02-20 | 2026-03-13 | 2026-12-28 | 16 | 2027-01-18 | 221
A43150 | Flare Relief & Blowdown Report_IFD/IFC | 2026-03-13 | 2026-03-17 | 2026-03-13 | 2026-03-17 | 2027-01-18 | 2 | 2027-01-20 | 221
Dynamic Flare Simulation Study |  | 2026-02-20 | 2026-04-21 | 2026-02-20 | 2026-04-21 | 2026-11-23 | 43 | 2027-01-20 | 196
A43010 | Dynamic Flare Simulation Study_IFR | 2026-02-20 | 2026-02-27 | 2026-02-20 | 2026-02-27 | 2026-11-23 | 6 | 2026-11-30 | 196
A43020 | Dynamic Flare Simulation Study_RCC | 2026-02-27 | 2026-03-23 | 2026-02-27 | 2026-03-23 | 2026-11-30 | 16 | 2026-12-22 | 196
A43030 | Dynamic Flare Simulation Study_IFA | 2026-03-23 | 2026-03-26 | 2026-03-23 | 2026-03-26 | 2026-12-22 | 3 | 2026-12-25 | 196
A43040 | Dynamic Flare Simulation Study_RCA | 2026-03-26 | 2026-04-17 | 2026-03-26 | 2026-04-17 | 2026-12-28 | 16 | 2027-01-18 | 196
A43050 | Dynamic Flare Simulation Study_IFD/IFC | 2026-04-17 | 2026-04-21 | 2026-04-17 | 2026-04-21 | 2027-01-18 | 2 | 2027-01-20 | 196
Piping |  | 2026-02-20 | 2026-06-08 | 16-Jan-25 A | 2026-06-08 | 2026-03-02 | 376 | 2027-01-20 | 162
3D Modelling Procedure |  | 2026-02-20 | 2026-02-20 | 01-Mar-25 A | 15-Oct-25 A | 2026-03-02 | 224 | 2027-01-20
A43260 | 3D Modelling Procedure_IFR | 2026-02-20 | 2026-02-20 | 01-Mar-25 A | 20-Apr-25 A | 2026-03-02 | 6 | 2026-03-02
A43270 | 3D Modelling Procedure_RCC | 2026-02-20 | 2026-02-20 | 21-Apr-25 A | 28-Apr-25 A | 2027-01-20 | 16 | 2027-01-20
A43280 | 3D Modelling Procedure_IFA | 2026-02-20 | 2026-02-20 | 29-Apr-25 A | 21-Jun-25 A | 2027-01-20 | 3 | 2027-01-20
A43290 | 3D Modelling Procedure_RCA | 2026-02-20 | 2026-02-20 | 01-Aug-25 A | 23-Aug-25 A | 2027-01-20 | 16 | 2027-01-20
A43300 | 3D Modelling Procedure_IFD/IFC | 2026-02-20 | 2026-02-20 | 12-Oct-25 A | 15-Oct-25 A | 2027-01-20 | 2 | 2027-01-20
3D Model Execution Philosophy |  | 2026-02-20 | 2026-02-20 | 25-Mar-25 A | 14-Oct-25 A | 2026-10-19 | 224 | 2027-01-20
A55400 | 3D Model Execution Philosophy_IFR | 2026-02-20 | 2026-02-20 | 25-Mar-25 A | 15-Apr-25 A | 2026-10-19 | 6 | 2026-10-19
A55410 | 3D Model Execution Philosophy_RCC | 2026-02-20 | 2026-02-20 | 16-Apr-25 A | 28-Apr-25 A | 2027-01-20 | 16 | 2027-01-20
A55420 | 3D Model Execution Philosophy_IFA | 2026-02-20 | 2026-02-20 | 29-Apr-25 A | 21-Jun-25 A | 2027-01-20 | 3 | 2027-01-20
A55430 | 3D Model Execution Philosophy_RCA | 2026-02-20 | 2026-02-20 | 20-Jul-25 A | 08-Aug-25 A | 2027-01-20 | 16 | 2027-01-20
A55440 | 3D Model Execution Philosophy_IFD/IFC | 2026-02-20 | 2026-02-20 | 11-Oct-25 A | 14-Oct-25 A | 2027-01-20 | 2 | 2027-01-20
3D Model Review Procedure |  | 2026-02-20 | 2026-02-20 | 25-Mar-25 A | 23-Dec-25 A | 2027-01-20 | 248 | 2027-01-20
A43310 | 3D Model Review Procedure_IFR | 2026-02-20 | 2026-02-20 | 25-Mar-25 A | 15-Apr-25 A | 2027-01-20 | 6 | 2027-01-20
A43320 | 3D Model Review Procedure_RCC | 2026-02-20 | 2026-02-20 | 16-Apr-25 A | 28-Apr-25 A | 2027-01-20 | 16 | 2027-01-20
A43330 | 3D Model Review Procedure_IFA | 2026-02-20 | 2026-02-20 | 29-Apr-25 A | 21-Jun-25 A | 2027-01-20 | 3 | 2027-01-20
A43340 | 3D Model Review Procedure_RCA | 2026-02-20 | 2026-02-20 | 22-Jun-25 A | 05-Sep-25 A | 2027-01-20 | 16 | 2027-01-20
A43350 | 3D Model Review Procedure_IFD/IFC | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 23-Dec-25 A | 2027-01-20 | 2 | 2027-01-20
Clash Check Procedure |  | 2026-02-20 | 2026-02-20 | 22-Mar-25 A | 11-May-25 A | 2026-10-19 | 117 | 2027-01-20
A55450 | Clash Check Procedure_IFR | 2026-02-20 | 2026-02-20 | 22-Mar-25 A | 12-Apr-25 A | 2026-10-19 | 6 | 2026-10-19
A27870 | Clash Check Procedure_RCC | 2026-02-20 | 2026-02-20 | 13-Apr-25 A | 20-Apr-25 A | 2027-01-20 | 16 | 2027-01-20
A27880 | Clash Check Procedure_IFA | 2026-02-20 | 2026-02-20 | 21-Apr-25 A | 27-Apr-25 A | 2027-01-20 | 3 | 2027-01-20
A55460 | Clash Check Procedure_RCA | 2026-02-20 | 2026-02-20 | 28-Apr-25 A | 04-May-25 A | 2027-01-20 | 16 | 2027-01-20
A55470 | Clash Check Procedure_IFD/IFC | 2026-02-20 | 2026-02-20 | 05-May-25 A | 11-May-25 A | 2027-01-20 | 2 | 2027-01-20
Deliverables Extraction Procedure |  | 2026-02-20 | 2026-02-20 | 23-Jan-25 A | 12-Mar-25 A | 2026-10-19 | 38 | 2027-01-20
A55480 | Deliverables Extraction Procedure_IFR | 2026-02-20 | 2026-02-20 | 23-Jan-25 A | 12-Feb-25 A | 2026-10-19 | 6 | 2026-10-19
A55490 | Deliverables Extraction Procedure_RCC | 2026-02-20 | 2026-02-20 | 13-Feb-25 A | 19-Feb-25 A | 2027-01-20 | 16 | 2027-01-20
A55500 | Deliverables Extraction Procedure_IFA | 2026-02-20 | 2026-02-20 | 20-Feb-25 A | 26-Feb-25 A | 2027-01-20 | 3 | 2027-01-20
A55510 | Deliverables Extraction Procedure_RCA | 2026-02-20 | 2026-02-20 | 27-Feb-25 A | 05-Mar-25 A | 2027-01-20 | 16 | 2027-01-20
A55520 | Deliverables Extraction Procedure_IFD/IFC | 2026-02-20 | 2026-02-20 | 06-Mar-25 A | 12-Mar-25 A | 2027-01-20 | 2 | 2027-01-20
Data Handover Procedure |  | 2026-02-20 | 2026-04-14 | 21-Jun-25 A | 2026-04-14 | 2026-10-19 | 212 | 2026-12-09 | 172
A27960 | Data Handover Procedure_IFR | 2026-02-20 | 2026-02-20 | 21-Jun-25 A | 12-Jul-25 A | 2026-10-19 | 6 | 2026-10-19
A27970 | Data Handover Procedure_RCC | 2026-02-20 | 2026-03-13 | 2026-02-20 | 2026-03-13 | 2026-10-19 | 16 | 2026-11-10 | 172
A55530 | Data Handover Procedure_IFA | 2026-03-13 | 2026-03-19 | 2026-03-13 | 2026-03-19 | 2026-11-10 | 3 | 2026-11-13 | 172
A55540 | Data Handover Procedure_RCA | 2026-03-19 | 2026-04-09 | 2026-03-19 | 2026-04-09 | 2026-11-16 | 16 | 2026-12-07 | 172
A55550 | Data Handover Procedure_IFD/IFC | 2026-04-09 | 2026-04-14 | 2026-04-09 | 2026-04-14 | 2026-12-07 | 2 | 2026-12-09 | 172
Stress Critical Line List |  | 2026-02-20 | 2026-03-17 | 15-Apr-25 A | 2026-03-17 | 2026-12-28 | 287 | 2027-01-20 | 221
A43460 | Stress Critical Line List_IFR | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 06-May-25 A | 2026-12-28 | 11 | 2026-12-28
A43470 | Stress Critical Line List_RCC | 2026-02-20 | 2026-02-20 | 07-May-25 A | 13-May-25 A | 2026-12-28 | 16 | 2026-12-28
A43480 | Stress Critical Line List_IFA | 2026-02-20 | 2026-02-20 | 04-Dec-25 A | 19-Dec-25 A | 2026-12-28 | 3 | 2026-12-28
A43490 | Stress Critical Line List_RCA | 2026-02-20 | 2026-03-13 | 2026-02-20 | 2026-03-13 | 2026-12-28 | 16 | 2027-01-18 | 221
A43500 | Stress Critical Line List_IFD/IFC | 2026-03-13 | 2026-03-17 | 2026-03-13 | 2026-03-17 | 2027-01-18 | 2 | 2027-01-20 | 221
Datasheets for Ball Valves |  | 2026-02-20 | 2026-02-20 | 16-Jan-25 A | 21-Nov-25 A | 2026-03-17 | 255 | 2026-03-17
A43660 | Datasheets for Ball Valves_IFR | 2026-02-20 | 2026-02-20 | 16-Jan-25 A | 14-May-25 A | 2026-03-17 | 6 | 2026-03-17
A43670 | Datasheets for Ball Valves_RCC | 2026-02-20 | 2026-02-20 | 01-Aug-25 A | 25-Aug-25 A | 2026-03-17 | 16 | 2026-03-17
A43680 | Datasheets for Ball Valves_IFA | 2026-02-20 | 2026-02-20 | 22-Oct-25 A | 30-Oct-25 A | 2026-03-17 | 3 | 2026-03-17
A43690 | Datasheets for Ball Valves_RCA | 2026-02-20 | 2026-02-20 | 31-Oct-25 A | 07-Nov-25 A | 2026-03-17 | 16 | 2026-03-17
A43700 | Datasheets for Ball Valves_IFD/IFC | 2026-02-20 | 2026-02-20 | 10-Nov-25 A | 21-Nov-25 A | 2026-03-17 | 2 | 2026-03-17
Datasheets for Double Block & Bleed Valves |  | 2026-02-20 | 2026-02-20 | 27-Jan-25 A | 22-Aug-25 A | 2026-03-17 | 208 | 2026-03-19
A43760 | Datasheets for Double Block & Bleed Valves_IFR | 2026-02-20 | 2026-02-20 | 27-Jan-25 A | 01-Aug-25 A | 2026-03-17 | 6 | 2026-03-17
A43770 | Datasheets for Double Block & Bleed Valves_RCC | 2026-02-20 | 2026-02-20 | 02-Aug-25 A | 10-Aug-25 A | 2026-03-19 | 16 | 2026-03-19
A43780 | Datasheets for Double Block & Bleed Valves_IFA | 2026-02-20 | 2026-02-20 | 11-Aug-25 A | 15-Aug-25 A | 2026-03-19 | 3 | 2026-03-19
A43790 | Datasheets for Double Block & Bleed Valves_RCA | 2026-02-20 | 2026-02-20 | 16-Aug-25 A | 20-Aug-25 A | 2026-03-19 | 16 | 2026-03-19
A43800 | Datasheets for Double Block & Bleed Valves_IFD/IFC | 2026-02-20 | 2026-02-20 | 21-Aug-25 A | 22-Aug-25 A | 2026-03-19 | 2 | 2026-03-19
Datasheets for Check Valves |  | 2026-02-20 | 2026-02-20 | 23-Jan-25 A | 17-Nov-25 A | 2026-03-17 | 232 | 2026-03-19
A43710 | Datasheets for Check Valves_IFR | 2026-02-20 | 2026-02-20 | 23-Jan-25 A | 14-May-25 A | 2026-03-17 | 2 | 2026-03-17
A43720 | Datasheets for Check Valves_RCC | 2026-02-20 | 2026-02-20 | 15-May-25 A | 21-Jun-25 A | 2026-03-19 | 16 | 2026-03-19
A43730 | Datasheets for Check Valves_IFA | 2026-02-20 | 2026-02-20 | 06-Aug-25 A | 12-Aug-25 A | 2026-03-19 | 3 | 2026-03-19
A43740 | Datasheets for Check Valves_RCA | 2026-02-20 | 2026-02-20 | 02-Sep-25 A | 03-Nov-25 A | 2026-03-19 | 16 | 2026-03-19
A43750 | Datasheets for Check Valves_IFD/IFC | 2026-02-20 | 2026-02-20 | 04-Nov-25 A | 17-Nov-25 A | 2026-03-19 | 2 | 2026-03-19
Datasheets for Butterfly Valves |  | 2026-02-20 | 2026-02-20 | 16-Jan-25 A | 20-Nov-25 A | 2026-03-17 | 246 | 2026-03-19
A43810 | Datasheets for Butterfly Valves_IFR | 2026-02-20 | 2026-02-20 | 16-Jan-25 A | 12-Jun-25 A | 2026-03-17 | 2 | 2026-03-17
A43820 | Datasheets for Butterfly Valves_RCC | 2026-02-20 | 2026-02-20 | 04-Aug-25 A | 27-Aug-25 A | 2026-03-19 | 16 | 2026-03-19
A43830 | Datasheets for Butterfly Valves_IFA | 2026-02-20 | 2026-02-20 | 31-Aug-25 A | 03-Sep-25 A | 2026-03-19 | 3 | 2026-03-19
A43840 | Datasheets for Butterfly Valves_RCA | 2026-02-20 | 2026-02-20 | 20-Sep-25 A | 13-Oct-25 A | 2026-03-19 | 16 | 2026-03-19
A43850 | Datasheets for Butterfly Valves_IFD/IFC | 2026-02-20 | 2026-02-20 | 10-Nov-25 A | 20-Nov-25 A | 2026-03-19 | 2 | 2026-03-19
Datasheets for Needle Valves |  | 2026-02-20 | 2026-02-20 | 01-Aug-25 A | 22-Aug-25 A | 2026-03-17 | 200 | 2026-03-19
A43860 | Datasheets for Needle Valves_IFR | 2026-02-20 | 2026-02-20 | 01-Aug-25 A | 05-Aug-25 A | 2026-03-17 | 2 | 2026-03-17
A43870 | Datasheets for Needle Valves_RCC | 2026-02-20 | 2026-02-20 | 06-Aug-25 A | 12-Aug-25 A | 2026-03-19 | 16 | 2026-03-19
A43880 | Datasheets for Needle Valves_IFA | 2026-02-20 | 2026-02-20 | 13-Aug-25 A | 15-Aug-25 A | 2026-03-19 | 3 | 2026-03-19
A43890 | Datasheets for Needle Valves_RCA | 2026-02-20 | 2026-02-20 | 16-Aug-25 A | 20-Aug-25 A | 2026-03-19 | 16 | 2026-03-19
A43900 | Datasheets for Needle Valves_IFD/IFC | 2026-02-20 | 2026-02-20 | 20-Aug-25 A | 22-Aug-25 A | 2026-03-19 | 2 | 2026-03-19
Datasheets for Insulating Gaskets |  | 2026-02-20 | 2026-02-20 | 22-Sep-25 A | 13-Jan-26 A | 2026-03-17 | 58 | 2026-03-17
A43910 | Datasheets for Insulating Gaskets_IFR | 2026-02-20 | 2026-02-20 | 22-Sep-25 A | 29-Sep-25 A | 2026-03-17 | 2 | 2026-03-17
A43920 | Datasheets for Insulating Gaskets_RCC | 2026-02-20 | 2026-02-20 | 23-Sep-25 A | 06-Oct-25 A | 2026-03-17 | 16 | 2026-03-17
A43930 | Datasheets for Insulating Gaskets_IFA | 2026-02-20 | 2026-02-20 | 03-Dec-25 A | 18-Dec-25 A | 2026-03-17 | 3 | 2026-03-17
A43940 | Datasheets for Insulating Gaskets_RCA | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 09-Jan-26 A | 2026-03-17 | 16 | 2026-03-17
A43950 | Datasheets for Insulating Gaskets_IFD/IFC | 2026-02-20 | 2026-02-20 | 09-Jan-26 A | 13-Jan-26 A | 2026-03-17 | 2 | 2026-03-17
Datasheets for Flame Arrestors |  | 2026-02-20 | 2026-02-20 | 20-Apr-25 A | 23-Dec-25 A | 2026-04-17 | 125 | 2027-01-20
A43960 | Datasheets for Flame Arrestors_IFR | 2026-02-20 | 2026-02-20 | 20-Apr-25 A | 11-May-25 A | 2026-04-17 | 2 | 2026-04-17
A43970 | Datasheets for Flame Arrestors_RCC | 2026-02-20 | 2026-02-20 | 12-May-25 A | 18-May-25 A | 2027-01-20 | 16 | 2027-01-20
A43980 | Datasheets for Flame Arrestors_IFA | 2026-02-20 | 2026-02-20 | 19-May-25 A | 25-May-25 A | 2027-01-20 | 3 | 2027-01-20
A43990 | Datasheets for Flame Arrestors_RCA | 2026-02-20 | 2026-02-20 | 26-May-25 A | 14-Oct-25 A | 2027-01-20 | 16 | 2027-01-20
A44000 | Datasheets for Flame Arrestors_IFD/IFC | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 23-Dec-25 A | 2027-01-20 | 2 | 2027-01-20
Datasheets for Flame Bird Screen |  | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 23-Dec-25 A | 2026-04-17 | 193 | 2027-01-20
A44010 | Datasheets for Flame Bird Screen_IFR | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 06-May-25 A | 2026-04-17 | 2 | 2026-04-17
A44020 | Datasheets for Flame Bird Screen_RCC | 2026-02-20 | 2026-02-20 | 07-May-25 A | 13-May-25 A | 2027-01-20 | 16 | 2027-01-20
A44030 | Datasheets for Flame Bird Screen_IFA | 2026-02-20 | 2026-02-20 | 20-Aug-25 A | 27-Aug-25 A | 2027-01-20 | 3 | 2027-01-20
A44040 | Datasheets for Flame Bird Screen_RCA | 2026-02-20 | 2026-02-20 | 01-Oct-25 A | 27-Oct-25 A | 2027-01-20 | 16 | 2027-01-20
A44050 | Datasheets for Flame Bird Screen_IFD/IFC | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 23-Dec-25 A | 2027-01-20 | 2 | 2027-01-20
Datasheets for Hose Coupling |  | 2026-02-20 | 2026-02-20 | 01-Jul-25 A | 23-Dec-25 A | 2026-03-17 | 128 | 2026-03-17
A44060 | Datasheets for Hose Coupling_IFR | 2026-02-20 | 2026-02-20 | 01-Jul-25 A | 12-Jul-25 A | 2026-03-17 | 6 | 2026-03-17
A44070 | Datasheets for Hose Coupling_RCC | 2026-02-20 | 2026-02-20 | 05-Jul-25 A | 25-Jul-25 A | 2026-03-17 | 16 | 2026-03-17
A44080 | Datasheets for Hose Coupling_IFA | 2026-02-20 | 2026-02-20 | 05-Aug-25 A | 12-Aug-25 A | 2026-03-17 | 3 | 2026-03-17
A44090 | Datasheets for Hose Coupling_RCA | 2026-02-20 | 2026-02-20 | 09-Aug-25 A | 27-Aug-25 A | 2026-03-17 | 16 | 2026-03-17
A44100 | Datasheets for Hose Coupling_IFD/IFC | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 23-Dec-25 A | 2026-03-17 | 2 | 2026-03-17
Datasheets for Strainers |  | 2026-02-20 | 2026-02-20 | 14-Apr-25 A | 23-Dec-25 A | 2026-04-17 | 188 | 2027-01-20
A44110 | Datasheets for Strainers_IFR | 2026-02-20 | 2026-02-20 | 14-Apr-25 A | 05-May-25 A | 2026-04-17 | 6 | 2026-04-17
A44120 | Datasheets for Strainers_RCC | 2026-02-20 | 2026-02-20 | 06-May-25 A | 12-May-25 A | 2027-01-20 | 16 | 2027-01-20
A44130 | Datasheets for Strainers_IFA | 2026-02-20 | 2026-02-20 | 13-May-25 A | 01-Sep-25 A | 2027-01-20 | 3 | 2027-01-20
A44140 | Datasheets for Strainers_RCA | 2026-02-20 | 2026-02-20 | 02-Sep-25 A | 08-Sep-25 A | 2027-01-20 | 16 | 2027-01-20
A44150 | Datasheets for Strainers_IFD/IFC | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 23-Dec-25 A | 2027-01-20 | 2 | 2027-01-20
Datasheets for Spring Hangers |  | 2026-02-20 | 2026-03-23 | 25-Apr-25 A | 2026-03-23 | 2026-03-19 | 306 | 2027-01-18 | 215
A44160 | Datasheets for Spring Hangers_IFR | 2026-02-20 | 2026-02-20 | 25-Apr-25 A | 30-Apr-25 A | 2026-03-19 | 2 | 2026-03-19
A44170 | Datasheets for Spring Hangers_RCC | 2026-02-20 | 2026-02-20 | 01-May-25 A | 15-May-25 A | 2026-12-18 | 16 | 2026-12-18
A44180 | Datasheets for Spring Hangers_IFA | 2026-02-20 | 2026-02-25 | 2026-02-20 | 2026-02-25 | 2026-12-18 | 3 | 2026-12-23 | 215
A44190 | Datasheets for Spring Hangers_RCA | 2026-02-25 | 2026-03-19 | 2026-02-25 | 2026-03-19 | 2026-12-23 | 16 | 2027-01-14 | 215
A44200 | Datasheets for Spring Hangers_IFD/IFC | 2026-03-19 | 2026-03-23 | 2026-03-19 | 2026-03-23 | 2027-01-14 | 2 | 2027-01-18 | 215
Datasheets for Rigid Struts |  | 2026-02-20 | 2026-03-17 | 15-Apr-25 A | 2026-03-17 | 2026-12-23 | 301 | 2027-01-18 | 219
A44210 | Datasheets for Rigid Struts_IFR | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 06-May-25 A | 2026-12-23 | 2 | 2026-12-23
A44220 | Datasheets for Rigid Struts_RCC | 2026-02-20 | 2026-02-20 | 07-May-25 A | 13-May-25 A | 2026-12-23 | 16 | 2026-12-23
A44230 | Datasheets for Rigid Struts_IFA | 2026-02-20 | 2026-02-20 | 10-Dec-25 A | 17-Dec-25 A | 2026-12-23 | 3 | 2026-12-23
A44240 | Datasheets for Rigid Struts_RCA | 2026-02-20 | 2026-03-13 | 2026-02-20 | 2026-03-13 | 2026-12-23 | 16 | 2027-01-14 | 219
A44250 | Datasheets for Rigid Struts_IFD/IFC | 2026-03-13 | 2026-03-17 | 2026-03-13 | 2026-03-17 | 2027-01-14 | 2 | 2027-01-18 | 219
Datasheet for Piping Speciality Items |  | 2026-02-20 | 2026-03-23 | 01-Sep-25 A | 2026-03-23 | 2026-04-17 | 131 | 2027-01-18 | 215
A54490 | Datasheet for Piping Speciality Items_IFR | 2026-02-20 | 2026-02-20 | 01-Sep-25 A | 12-Sep-25 A | 2026-04-17 | 2 | 2026-04-17
A54500 | Datasheet for Piping Speciality Items_RCC | 2026-02-20 | 2026-02-20 | 15-Sep-25 A | 19-Sep-25 A | 2026-12-17 | 16 | 2026-12-17
A54510 | Datasheet for Piping Speciality Items_IFA | 2026-02-20 | 2026-02-25 | 2026-02-20 | 2026-02-25 | 2026-12-17 | 3 | 2026-12-22 | 214
A54520 | Datasheet for Piping Speciality Items_RCA | 2026-02-25 | 2026-03-19 | 2026-02-25 | 2026-03-19 | 2026-12-23 | 16 | 2027-01-14 | 215
A54530 | Datasheet for Piping Speciality Items_IFD/IFC | 2026-03-19 | 2026-03-23 | 2026-03-19 | 2026-03-23 | 2027-01-14 | 2 | 2027-01-18 | 215
Material Requisition for Piping Bulk |  | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 16-Jan-26 A | 2026-03-19 | 260 | 2026-03-19
A44720 | Material Requisition for Piping Bulk_IFR | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 06-May-25 A | 2026-03-19 | 6 | 2026-03-19
A44730 | Material Requisition for Piping Bulk_RCC | 2026-02-20 | 2026-02-20 | 20-Jul-25 A | 10-Aug-25 A | 2026-03-19 | 16 | 2026-03-19
A44740 | Material Requisition for Piping Bulk_IFA | 2026-02-20 | 2026-02-20 | 15-Oct-25 A | 29-Oct-25 A | 2026-03-19 | 3 | 2026-03-19
A44750 | Material Requisition for Piping Bulk_RCA | 2026-02-20 | 2026-02-20 | 30-Oct-25 A | 10-Nov-25 A | 2026-03-19 | 16 | 2026-03-19
A44760 | Material Requisition for Piping Bulk_IFD/IFC | 2026-02-20 | 2026-02-20 | 14-Jan-26 A | 16-Jan-26 A | 2026-03-19 | 2 | 2026-03-19
Material Requisition for HDPE Piping Bulk |  | 2026-02-20 | 2026-02-24 | 15-Oct-25 A | 2026-02-24 | 2026-03-17 | 100 | 2026-03-19 | 18
A60050 | Material Requisition for HDPE Piping Bulk_IFR | 2026-02-20 | 2026-02-20 | 15-Oct-25 A | 26-Oct-25 A | 2026-03-17 | 6 | 2026-03-17
A60060 | Material Requisition for HDPE Piping Bulk_RCC | 2026-02-20 | 2026-02-20 | 26-Oct-25 A | 10-Nov-25 A | 2026-03-17 | 16 | 2026-03-17
A60070 | Material Requisition for HDPE Piping Bulk_IFA | 2026-02-20 | 2026-02-20 | 10-Nov-25 A | 27-Nov-25 A | 2026-03-17 | 3 | 2026-03-17
A60080 | Material Requisition for HDPE Piping Bulk_RCA | 2026-02-20 | 2026-02-20 | 27-Nov-25 A | 16-Dec-25 A | 2026-03-17 | 16 | 2026-03-17
A60090 | Material Requisition for HDPE Piping Bulk_IFD/IFC | 2026-02-20 | 2026-02-24 | 2026-02-20 | 2026-02-24 | 2026-03-17 | 2 | 2026-03-19 | 18
Material Requisition for Manual Valves |  | 2026-02-20 | 2026-02-20 | 01-Jul-25 A | 10-Oct-25 A | 2026-03-19 | 129 | 2026-03-19
A44770 | Material Requisition for Manual Valves_IFR | 2026-02-20 | 2026-02-20 | 01-Jul-25 A | 12-Jul-25 A | 2026-03-19 | 1 | 2026-03-19
A44780 | Material Requisition for Manual Valves_RCC | 2026-02-20 | 2026-02-20 | 21-Aug-25 A | 31-Aug-25 A | 2026-03-19 | 6 | 2026-03-19
A44790 | Material Requisition for Manual Valves_IFA | 2026-02-20 | 2026-02-20 | 01-Sep-25 A | 10-Sep-25 A | 2026-03-19 | 1 | 2026-03-19
A44800 | Material Requisition for Manual Valves_RCA | 2026-02-20 | 2026-02-20 | 11-Sep-25 A | 15-Sep-25 A | 2026-03-19 | 16 | 2026-03-19
A44810 | Material Requisition for Manual Valves_IFD/IFC | 2026-02-20 | 2026-02-20 | 22-Sep-25 A | 10-Oct-25 A | 2026-03-19 | 2 | 2026-03-19
Material Requisition for Piping Speciality Items |  | 2026-02-20 | 2026-04-14 | 15-Sep-25 A | 2026-04-14 | 2026-04-17 | 147 | 2027-01-20 | 202
A44820 | Material Requisition for Piping Speciality Items_IFR | 2026-02-20 | 2026-02-20 | 15-Sep-25 A | 16-Sep-25 A | 2026-04-17 | 6 | 2026-04-17
A44830 | Material Requisition for Piping Speciality Items_RCC | 2026-02-20 | 2026-03-13 | 2026-02-20 | 2026-03-13 | 2026-11-30 | 16 | 2026-12-22 | 202
A44840 | Material Requisition for Piping Speciality Items_IFA | 2026-03-13 | 2026-03-19 | 2026-03-13 | 2026-03-19 | 2026-12-22 | 3 | 2026-12-25 | 202
A44850 | Material Requisition for Piping Speciality Items_RCA | 2026-03-19 | 2026-04-09 | 2026-03-19 | 2026-04-09 | 2026-12-28 | 16 | 2027-01-18 | 202
A44860 | Material Requisition for Piping Speciality Items_IFD/IFC | 2026-04-09 | 2026-04-14 | 2026-04-09 | 2026-04-14 | 2027-01-18 | 2 | 2027-01-20 | 202
Material Requisition for Spring Hangers |  | 2026-02-20 | 2026-03-25 | 22-Apr-25 A | 2026-03-25 | 2026-03-19 | 222 | 2027-01-20 | 215
A44870 | Material Requisition for Spring Hangers_IFR | 2026-02-20 | 2026-02-20 | 22-Apr-25 A | 13-May-25 A | 2026-03-19 | 2 | 2026-03-19
A44880 | Material Requisition for Spring Hangers_RCC | 2026-02-20 | 2026-02-20 | 14-May-25 A | 20-May-25 A | 2026-03-30 | 16 | 2026-03-30
A44890 | Material Requisition for Spring Hangers_IFA | 2026-02-20 | 2026-02-20 | 04-Dec-25 A | 18-Dec-25 A | 2026-12-28 | 3 | 2026-12-28
A44900 | Material Requisition for Spring Hangers_RCA | 2026-02-20 | 2026-03-13 | 2026-02-20 | 2026-03-13 | 2026-12-28 | 16 | 2027-01-18 | 221
A44910 | Material Requisition for Spring Hangers_IFD/IFC | 2026-03-23 | 2026-03-25 | 2026-03-23 | 2026-03-25 | 2027-01-18 | 2 | 2027-01-20 | 215
Material Requisition for Rigid Struts |  | 2026-02-20 | 2026-03-20 | 22-Apr-25 A | 2026-03-20 | 2026-12-28 | 216 | 2027-01-20 | 219
A44920 | Material Requisition for Rigid Struts_IFR | 2026-02-20 | 2026-02-20 | 22-Apr-25 A | 13-May-25 A | 2026-12-28 | 6 | 2026-12-28
A44930 | Material Requisition for Rigid Struts_RCC | 2026-02-20 | 2026-02-20 | 14-May-25 A | 20-May-25 A | 2026-12-28 | 16 | 2026-12-28
A44940 | Material Requisition for Rigid Struts_IFA | 2026-02-20 | 2026-02-20 | 01-Dec-25 A | 12-Dec-25 A | 2026-12-28 | 3 | 2026-12-28
A44950 | Material Requisition for Rigid Struts_RCA | 2026-02-20 | 2026-03-13 | 2026-02-20 | 2026-03-13 | 2026-12-28 | 16 | 2027-01-18 | 221
A44960 | Material Requisition for Rigid Struts_IFD/IFC | 2026-03-18 | 2026-03-20 | 2026-03-18 | 2026-03-20 | 2027-01-18 | 2 | 2027-01-20 | 219
Utility Station Location Plan |  | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 19-Jan-26 A | 2027-01-20 | 231 | 2027-01-20
A43510 | Utility Station Location Plan_IFR | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 06-May-25 A | 2027-01-20 | 6 | 2027-01-20
A43520 | Utility Station Location Plan_RCC | 2026-02-20 | 2026-02-20 | 20-Jul-25 A | 08-Aug-25 A | 2027-01-20 | 16 | 2027-01-20
A43530 | Utility Station Location Plan_IFA | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 24-Dec-25 A | 2027-01-20 | 3 | 2027-01-20
A43540 | Utility Station Location Plan_RCA | 2026-02-20 | 2026-02-20 | 24-Dec-25 A | 15-Jan-26 A | 2027-01-20 | 16 | 2027-01-20
A43550 | Utility Station Location Plan_IFD/IFC | 2026-02-20 | 2026-02-20 | 15-Jan-26 A | 19-Jan-26 A | 2027-01-20 | 2 | 2027-01-20
30% 3D Model Review Report |  | 2026-02-20 | 2026-02-20 | 25-Apr-25 A | 21-Aug-25 A | 2026-03-02 | 108 | 2026-03-17
A43560 | 30% 3D Model Review Report_IFR | 2026-02-20 | 2026-02-20 | 25-Apr-25 A | 16-May-25 A | 2026-03-02 | 6 | 2026-03-02
A43570 | 30% 3D Model Review Report_RCC | 2026-02-20 | 2026-02-20 | 17-May-25 A | 23-May-25 A | 2026-03-17 | 16 | 2026-03-17
A43580 | 30% 3D Model Review Report_IFA | 2026-02-20 | 2026-02-20 | 24-May-25 A | 10-Aug-25 A | 2026-03-17 | 3 | 2026-03-17
A43590 | 30% 3D Model Review Report_RCA | 2026-02-20 | 2026-02-20 | 11-Aug-25 A | 15-Aug-25 A | 2026-03-17 | 16 | 2026-03-17
A43600 | 30% 3D Model Review Report_IFD/IFC | 2026-02-20 | 2026-02-20 | 16-Aug-25 A | 21-Aug-25 A | 2026-03-17 | 2 | 2026-03-17
30% 3D Model Review Closeout Report |  | 2026-02-20 | 2026-02-20 | 01-Jul-25 A | 19-Dec-25 A | 2026-03-02 | 120 | 2026-03-18
A43610 | 30% 3D Model Review Closeout Report_IFR | 2026-02-20 | 2026-02-20 | 01-Jul-25 A | 12-Jul-25 A | 2026-03-02 | 6 | 2026-03-02
A43620 | 30% 3D Model Review Closeout Report_RCC | 2026-02-20 | 2026-02-20 | 27-Aug-25 A | 27-Nov-25 A | 2026-03-18 | 16 | 2026-03-18
A43630 | 30% 3D Model Review Closeout Report_IFA | 2026-02-20 | 2026-02-20 | 27-Nov-25 A | 02-Dec-25 A | 2026-03-18 | 3 | 2026-03-18
A43640 | 30% 3D Model Review Closeout Report_RCA | 2026-02-20 | 2026-02-20 | 02-Dec-25 A | 15-Dec-25 A | 2026-03-18 | 16 | 2026-03-18
A43650 | 30% 3D Model Review Closeout Report_IFD/IFC | 2026-02-20 | 2026-02-20 | 10-Dec-25 A | 19-Dec-25 A | 2026-03-18 | 2 | 2026-03-18
Plot Plan |  | 2026-02-20 | 2026-02-20 | 09-Mar-25 A | 25-Oct-25 A | 2026-03-02 | 228 | 2026-10-16
A55670 | Plot Plan_Preliminary issuance for Plot plan workshop | 2026-02-20 | 2026-02-20 | 09-Mar-25 A | 12-Mar-25 A | 2026-03-02 | 6 | 2026-03-02
A45220 | Plot Plan_IFR | 2026-02-20 | 2026-02-20 | 14-Mar-25 A | 27-Apr-25 A | 2026-03-02 | 6 | 2026-03-02
A45230 | Plot Plan_RCC | 2026-02-20 | 2026-02-20 | 28-Apr-25 A | 11-Jun-25 A | 2026-03-19 | 16 | 2026-03-19
A45240 | Plot Plan_IFA | 2026-02-20 | 2026-02-20 | 03-Oct-25 A | 10-Oct-25 A | 2026-03-19 | 3 | 2026-03-19
A45250 | Plot Plan_RCA | 2026-02-20 | 2026-02-20 | 02-Oct-25 A | 24-Oct-25 A | 2026-10-16 | 16 | 2026-10-16
A45260 | Plot Plan_IFD/IFC | 2026-02-20 | 2026-02-20 | 23-Oct-25 A | 25-Oct-25 A | 2026-10-16 | 2 | 2026-10-16
Plot Plan Review Report |  | 2026-02-20 | 2026-02-20 | 19-Apr-25 A | 16-Oct-25 A | 2027-01-20 | 121 | 2027-01-20
A43360 | Plot Plan Review Report_IFR | 2026-02-20 | 2026-02-20 | 19-Apr-25 A | 10-May-25 A | 2027-01-20 | 6 | 2027-01-20
A43370 | Plot Plan Review Report_RCC | 2026-02-20 | 2026-02-20 | 11-May-25 A | 17-May-25 A | 2027-01-20 | 16 | 2027-01-20
A43380 | Plot Plan Review Report_IFA | 2026-02-20 | 2026-02-20 | 18-May-25 A | 21-Jun-25 A | 2027-01-20 | 3 | 2027-01-20
A43390 | Plot Plan Review Report_RCA | 2026-02-20 | 2026-02-20 | 22-Jun-25 A | 28-Jun-25 A | 2027-01-20 | 16 | 2027-01-20
A43400 | Plot Plan Review Report_IFD/IFC | 2026-02-20 | 2026-02-20 | 10-Oct-25 A | 16-Oct-25 A | 2027-01-20 | 2 | 2027-01-20
First Material Take Off |  | 2026-02-20 | 2026-02-20 | 02-Jun-25 A | 27-Jun-25 A | 2026-04-22 | 21 | 2026-04-22
A45270 | First Material Take Off_IFR | 2026-02-20 | 2026-02-20 | 02-Jun-25 A | 06-Jun-25 A | 2026-04-22 | 6 | 2026-04-22
A45280 | First Material Take Off_RCC | 2026-02-20 | 2026-02-20 | 09-Jun-25 A | 20-Jun-25 A | 2026-04-22 | 16 | 2026-04-22
A45290 | First Material Take Off_IFD/IFC | 2026-02-20 | 2026-02-20 | 23-Jun-25 A | 27-Jun-25 A | 2026-04-22 | 2 | 2026-04-22
Plot Plan Close Out Report |  | 2026-02-20 | 2026-02-20 | 19-Apr-25 A | 18-Dec-25 A | 2027-01-20 | 136 | 2027-01-20
A43410 | Plot Plan Close Out report_IFR | 2026-02-20 | 2026-02-20 | 19-Apr-25 A | 10-May-25 A | 2027-01-20 | 6 | 2027-01-20
A43420 | Plot Plan Close Out report_RCC | 2026-02-20 | 2026-02-20 | 11-May-25 A | 17-May-25 A | 2027-01-20 | 16 | 2027-01-20
A43430 | Plot Plan Close Out report_IFA | 2026-02-20 | 2026-02-20 | 10-Oct-25 A | 14-Oct-25 A | 2027-01-20 | 3 | 2027-01-20
A43440 | Plot Plan Close Out report_RCA | 2026-02-20 | 2026-02-20 | 10-Oct-25 A | 27-Oct-25 A | 2027-01-20 | 16 | 2027-01-20
A43450 | Plot Plan Close Out report_IFD/IFC | 2026-02-20 | 2026-02-20 | 15-Dec-25 A | 18-Dec-25 A | 2027-01-20 | 2 | 2027-01-20
Manual Valves List (Valves MTOs) |  | 2026-02-20 | 2026-02-20 | 25-Feb-25 A | 23-Dec-25 A | 2027-01-20 | 231 | 2027-01-20
A44690 | Manual Valves List (Valves MTOs)_IFR | 2026-02-20 | 2026-02-20 | 25-Feb-25 A | 10-Apr-25 A | 2027-01-20 | 6 | 2027-01-20
A44700 | Manual Valves List (Valves MTOs)_RCC | 2026-02-20 | 2026-02-20 | 02-Aug-25 A | 25-Aug-25 A | 2027-01-20 | 16 | 2027-01-20
A44710 | Manual Valves List (Valves MTOs)_IFD/IFC | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 23-Dec-25 A | 2027-01-20 | 2 | 2027-01-20
Technical Bid Evaluation (TBE) for Rigid Struts |  | 2026-02-20 | 2026-04-21 | 2026-02-20 | 2026-04-21 | 2026-11-23 | 43 | 2027-01-20 | 196
A45170 | Technical Bid Evaluation (TBE) for Rigid Struts_IFR | 2026-02-20 | 2026-02-27 | 2026-02-20 | 2026-02-27 | 2026-11-23 | 6 | 2026-11-30 | 196
A45180 | Technical Bid Evaluation (TBE) for Rigid Struts_RCC | 2026-02-27 | 2026-03-23 | 2026-02-27 | 2026-03-23 | 2026-11-30 | 16 | 2026-12-22 | 196
A45190 | Technical Bid Evaluation (TBE) for Rigid Struts_IFA | 2026-03-23 | 2026-03-26 | 2026-03-23 | 2026-03-26 | 2026-12-22 | 3 | 2026-12-25 | 196
A45200 | Technical Bid Evaluation (TBE) for Rigid Struts_RCA | 2026-03-26 | 2026-04-17 | 2026-03-26 | 2026-04-17 | 2026-12-28 | 16 | 2027-01-18 | 196
A45210 | Technical Bid Evaluation (TBE) for Rigid Struts_IFD/IFC | 2026-04-17 | 2026-04-21 | 2026-04-17 | 2026-04-21 | 2027-01-18 | 2 | 2027-01-20 | 196
60% 3D Model Review Report |  | 2026-02-20 | 2026-02-20 | 26-Sep-25 A | 21-Jan-26 A | 2026-03-19 | 64 | 2027-01-20
A44260 | 60% 3D Model Review Report_IFR | 2026-02-20 | 2026-02-20 | 26-Sep-25 A | 02-Oct-25 A | 2026-03-19 | 6 | 2026-03-19
A44270 | 60% 3D Model Review Report_RCC | 2026-02-20 | 2026-02-20 | 13-Oct-25 A | 04-Nov-25 A | 2027-01-20 | 16 | 2027-01-20
A44280 | 60% 3D Model Review Report_IFA | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 24-Dec-25 A | 2027-01-20 | 3 | 2027-01-20
A44290 | 60% 3D Model Review Report_RCA | 2026-02-20 | 2026-02-20 | 24-Dec-25 A | 15-Jan-26 A | 2027-01-20 | 16 | 2027-01-20
A44300 | 60% 3D Model Review Report_IFD/IFC | 2026-02-20 | 2026-02-20 | 19-Jan-26 A | 21-Jan-26 A | 2027-01-20 | 2 | 2027-01-20
60% 3D Model Review Closeout Report |  | 2026-02-20 | 2026-04-29 | 2026-02-20 | 2026-04-29 | 2026-07-22 | 48 | 2027-01-20 | 191
A44310 | 60% 3D Model Review Closeout Report_IFR | 2026-02-20 | 2026-03-09 | 2026-02-20 | 2026-03-09 | 2026-07-22 | 11 | 2026-08-06 | 108
A44320 | 60% 3D Model Review Closeout Report_RCC | 2026-03-09 | 2026-03-30 | 2026-03-09 | 2026-03-30 | 2026-10-22 | 16 | 2026-11-13 | 164
A44330 | 60% 3D Model Review Closeout Report_IFA | 2026-03-31 | 2026-04-03 | 2026-03-31 | 2026-04-03 | 2026-11-13 | 3 | 2026-11-18 | 164
A44340 | 60% 3D Model Review Closeout Report_RCA | 2026-04-03 | 2026-04-27 | 2026-04-03 | 2026-04-27 | 2026-12-28 | 16 | 2027-01-18 | 191
A44350 | 60% 3D Model Review Closeout Report_IFD/IFC | 2026-04-27 | 2026-04-29 | 2026-04-27 | 2026-04-29 | 2027-01-18 | 2 | 2027-01-20 | 191
Piping Stress Analysis Reports |  | 2026-02-20 | 2026-02-20 | 06-Jul-25 A | 23-Jan-26 A | 2026-05-20 | 127 | 2026-05-20
A44640 | Piping Stress Analysis Reports_IFR | 2026-02-20 | 2026-02-20 | 06-Jul-25 A | 31-Jul-25 A | 2026-05-20 | 23 | 2026-05-20
A44650 | Piping Stress Analysis Reports_RCC | 2026-02-20 | 2026-02-20 | 20-Jul-25 A | 07-Aug-25 A | 2026-05-20 | 16 | 2026-05-20
A44660 | Piping Stress Analysis Reports_IFA | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 05-Jan-26 A | 2026-05-20 | 11 | 2026-05-20
A44670 | Piping Stress Analysis Reports_RCA | 2026-02-20 | 2026-02-20 | 05-Jan-26 A | 14-Jan-26 A | 2026-05-20 | 16 | 2026-05-20
A44680 | Piping Stress Analysis Reports_IFD/IFC | 2026-02-20 | 2026-02-20 | 15-Jan-26 A | 23-Jan-26 A | 2026-05-20 | 6 | 2026-05-20
Piping GA Drawings & Key Plan for Piping GADs |  | 2026-02-20 | 2026-04-07 | 01-Dec-25 A | 2026-04-07 | 2026-03-19 | 88 | 2027-01-20 | 206
A44550 | Piping GA Drawings & Key Plan for Piping GADs_RCC | 2026-02-20 | 2026-02-20 | 01-Dec-25 A | 02-Dec-25 A | 2026-03-19 | 16 | 2026-03-19
A44540 | Piping GA Drawings & Key Plan for Piping GADs_IFR | 2026-02-20 | 2026-02-20 | 05-Dec-25 A | 18-Dec-25 A | 2026-03-19 | 37 | 2026-03-19
A44560 | Piping GA Drawings & Key Plan for Piping GADs_IFA | 2026-02-20 | 2026-03-09 | 2026-02-20 | 2026-03-09 | 2026-12-07 | 11 | 2026-12-22 | 206
A44570 | Piping GA Drawings & Key Plan for Piping GADs_RCA | 2026-03-09 | 2026-03-30 | 2026-03-09 | 2026-03-30 | 2026-12-22 | 16 | 2027-01-13 | 206
A44580 | Piping GA Drawings & Key Plan for Piping GADs_IFD/IFC | 2026-03-31 | 2026-04-07 | 2026-03-31 | 2026-04-07 | 2027-01-13 | 6 | 2027-01-20 | 206
Piping Isometrics (large bore) |  | 2026-02-20 | 2026-06-04 | 14-Jan-26 A | 2026-06-04 | 2026-03-13 | 94 | 2026-08-28 | 62
A44360 | Piping Isometrics (large bore)_IFR | 2026-02-20 | 2026-03-27 | 14-Jan-26 A | 2026-03-27 | 2026-03-13 | 34 | 2026-04-17 | 15
A44370 | Piping Isometrics (large bore)_RCC | 2026-03-30 | 2026-04-20 | 2026-03-30 | 2026-04-20 | 2026-06-23 | 16 | 2026-07-15 | 62
A44380 | Piping Isometrics (large bore)_IFA | 2026-04-20 | 2026-05-05 | 2026-04-20 | 2026-05-05 | 2026-07-15 | 11 | 2026-07-30 | 62
A44390 | Piping Isometrics (large bore)_RCA | 2026-05-06 | 2026-05-27 | 2026-05-06 | 2026-05-27 | 2026-07-30 | 16 | 2026-08-21 | 62
A44400 | Piping Isometrics (large bore)_IFD/IFC | 2026-05-27 | 2026-06-04 | 2026-05-27 | 2026-06-04 | 2026-08-21 | 6 | 2026-08-28 | 62
Second Material Take Off |  | 2026-02-20 | 2026-02-24 | 23-Dec-25 A | 2026-02-24 | 2026-03-25 | 24 | 2026-03-27 | 23
A45300 | Second Material Take Off_IFR | 2026-02-20 | 2026-02-20 | 23-Dec-25 A | 15-Jan-26 A | 2026-03-25 | 6 | 2026-03-25
A45310 | Second Material Take Off_RCC | 2026-02-20 | 2026-02-20 | 16-Jan-26 A | 23-Jan-26 A | 2026-03-25 | 16 | 2026-03-25
A45320 | Second Material Take Off_IFD/IFC | 2026-02-20 | 2026-02-24 | 23-Jan-26 A | 2026-02-24 | 2026-03-25 | 2 | 2026-03-27 | 23
90% 3D Model Review Report |  | 2026-03-06 | 2026-06-08 | 2026-03-06 | 2026-06-08 | 2026-11-12 | 67 | 2027-01-20 | 162
A44410 | 90% 3D Model Review Report_IFR | 2026-03-06 | 2026-03-13 | 2026-03-06 | 2026-03-13 | 2026-11-12 | 6 | 2026-11-20 | 179
A44420 | 90% 3D Model Review Report_RCC | 2026-03-13 | 2026-04-06 | 2026-03-13 | 2026-04-06 | 2026-11-30 | 16 | 2026-12-22 | 186
A44430 | 90% 3D Model Review Report_IFA | 2026-04-06 | 2026-04-09 | 2026-04-06 | 2026-04-09 | 2026-12-22 | 3 | 2026-12-25 | 186
A44440 | 90% 3D Model Review Report_RCA | 2026-04-09 | 2026-05-01 | 2026-04-09 | 2026-05-01 | 2026-12-28 | 16 | 2027-01-18 | 186
A44450 | 90% 3D Model Review Report_IFD/IFC | 2026-06-04 | 2026-06-08 | 2026-06-04 | 2026-06-08 | 2027-01-18 | 2 | 2027-01-20 | 162
Piping Isometrics(Small Bore) |  | 2026-03-06 | 2026-05-01 | 2026-03-06 | 2026-05-01 | 2026-03-27 | 41 | 2026-05-22 | 15
A44510 | Piping Isometrics(Small Bore)_IFR | 2026-03-06 | 2026-04-07 | 2026-03-06 | 2026-04-07 | 2026-03-27 | 23 | 2026-04-28 | 15
A44520 | Piping Isometrics(Small Bore)_RCC | 2026-04-07 | 2026-04-29 | 2026-04-07 | 2026-04-29 | 2026-04-29 | 16 | 2026-05-20 | 15
A44530 | Piping Isometrics(Small Bore)_IFD/IFC | 2026-04-29 | 2026-05-01 | 2026-04-29 | 2026-05-01 | 2026-05-20 | 2 | 2026-05-22 | 15
Piping Tie-Ins Schedule |  | 2026-02-20 | 2026-04-21 | 2026-02-20 | 2026-04-21 | 2026-08-19 | 43 | 2026-10-16 | 128
A44590 | Piping Tie-Ins Schedule_IFR | 2026-02-20 | 2026-02-27 | 2026-02-20 | 2026-02-27 | 2026-08-19 | 6 | 2026-08-26 | 128
A44600 | Piping Tie-Ins Schedule_RCC | 2026-02-27 | 2026-03-23 | 2026-02-27 | 2026-03-23 | 2026-08-26 | 16 | 2026-09-17 | 128
A44610 | Piping Tie-Ins Schedule_IFA | 2026-03-23 | 2026-03-26 | 2026-03-23 | 2026-03-26 | 2026-09-17 | 3 | 2026-09-22 | 128
A44620 | Piping Tie-Ins Schedule_RCA | 2026-03-26 | 2026-04-17 | 2026-03-26 | 2026-04-17 | 2026-09-23 | 16 | 2026-10-14 | 128
A44630 | Piping Tie-Ins Schedule_IFD/IFC | 2026-04-17 | 2026-04-21 | 2026-04-17 | 2026-04-21 | 2026-10-14 | 2 | 2026-10-16 | 128
90% 3D Model Review Closeout Report |  | 2026-03-13 | 2026-05-13 | 2026-03-13 | 2026-05-13 | 2026-11-20 | 43 | 2027-01-20 | 181
A44460 | 90% 3D Model Review Closeout Report_IFR | 2026-03-13 | 2026-03-23 | 2026-03-13 | 2026-03-23 | 2026-11-20 | 6 | 2026-11-27 | 179
A44470 | 90% 3D Model Review Closeout Report_RCC | 2026-03-23 | 2026-04-14 | 2026-03-23 | 2026-04-14 | 2026-11-30 | 16 | 2026-12-22 | 181
A44480 | 90% 3D Model Review Closeout Report_IFA | 2026-04-14 | 2026-04-17 | 2026-04-14 | 2026-04-17 | 2026-12-22 | 3 | 2026-12-25 | 181
A44490 | 90% 3D Model Review Closeout Report_RCA | 2026-04-17 | 2026-05-11 | 2026-04-17 | 2026-05-11 | 2026-12-28 | 16 | 2027-01-18 | 181
A44500 | 90% 3D Model Review Closeout Report_IFD/IFC | 2026-05-11 | 2026-05-13 | 2026-05-11 | 2026-05-13 | 2027-01-18 | 2 | 2027-01-20 | 181
Final Material Take Off |  | 2026-03-06 | 2026-04-08 | 2026-03-06 | 2026-04-08 | 2026-03-27 | 24 | 2026-05-04 | 18
A45330 | Final Material Take Off_IFR | 2026-03-06 | 2026-03-13 | 2026-03-06 | 2026-03-13 | 2026-03-27 | 6 | 2026-04-03 | 15
A45340 | Final Material Take Off_RCC | 2026-03-13 | 2026-04-06 | 2026-03-13 | 2026-04-06 | 2026-04-09 | 16 | 2026-04-30 | 18
A45350 | Final Material Take Off_IFD/IFC | 2026-04-06 | 2026-04-08 | 2026-04-06 | 2026-04-08 | 2026-04-30 | 2 | 2026-05-04 | 18
Mechanical |  | 2026-02-20 | 2026-04-14 | 31-Dec-24 A | 2026-04-14 | 2026-03-02 | 346 | 2027-01-20 | 202
Mechanical Static |  | 2026-02-20 | 2026-04-14 | 31-Dec-24 A | 2026-04-14 | 2026-03-02 | 346 | 2027-01-20 | 202
Mechanical Datasheet For Psa2 Feed Gas Compressor 1St Stage Suction Drum (Tag No. 13-Vv-705) |  | 2026-02-20 | 2026-02-20 | 31-Dec-24 A | 10-May-25 A | 2026-03-02 | 132 | 2027-01-20
A54590 | Mechanical Datasheet For Psa2 Feed Gas Compressor 1St Stage Suction Drum (Tag No. 13-Vv-705)_IFR | 2026-02-20 | 2026-02-20 | 31-Dec-24 A | 06-Feb-25 A | 2026-03-02 | 1 | 2026-03-02
A54600 | Mechanical Datasheet For Psa2 Feed Gas Compressor 1St Stage Suction Drum (Tag No. 13-Vv-705)_RCC | 2026-02-20 | 2026-02-20 | 07-Feb-25 A | 19-Apr-25 A | 2027-01-20 | 16 | 2027-01-20
A54610 | Mechanical Datasheet For Psa2 Feed Gas Compressor 1St Stage Suction Drum (Tag No. 13-Vv-705)_IFA | 2026-02-20 | 2026-02-20 | 20-Apr-25 A | 26-Apr-25 A | 2027-01-20 | 3 | 2027-01-20
A54620 | Mechanical Datasheet For Psa2 Feed Gas Compressor 1St Stage Suction Drum (Tag No. 13-Vv-705)_RCA | 2026-02-20 | 2026-02-20 | 27-Apr-25 A | 03-May-25 A | 2027-01-20 | 16 | 2027-01-20
A54630 | Mechanical Datasheet For Psa2 Feed Gas Compressor 1St Stage Suction Drum (Tag No. 13-Vv-705)_IFD/IFC | 2026-02-20 | 2026-02-20 | 04-May-25 A | 10-May-25 A | 2027-01-20 | 2 | 2027-01-20
Mechanical Datasheet For Psa2 Feed Gas Compressor 2Nd Stage Suction Drum (Tag No. 13-Vv-706) |  | 2026-02-20 | 2026-02-20 | 31-Dec-24 A | 10-May-25 A | 2026-03-02 | 131 | 2027-01-20
A54640 | Mechanical Datasheet For Psa2 Feed Gas Compressor 2Nd Stage Suction Drum (Tag No. 13-Vv-706)_IFR | 2026-02-20 | 2026-02-20 | 31-Dec-24 A | 06-Feb-25 A | 2026-03-02 | 1 | 2026-03-02
A54650 | Mechanical Datasheet For Psa2 Feed Gas Compressor 2Nd Stage Suction Drum (Tag No. 13-Vv-706)_RCC | 2026-02-20 | 2026-02-20 | 07-Feb-25 A | 19-Apr-25 A | 2027-01-20 | 16 | 2027-01-20
A54660 | Mechanical Datasheet For Psa2 Feed Gas Compressor 2Nd Stage Suction Drum (Tag No. 13-Vv-706)_IFA | 2026-02-20 | 2026-02-20 | 20-Apr-25 A | 26-Apr-25 A | 2027-01-20 | 3 | 2027-01-20
A54670 | Mechanical Datasheet For Psa2 Feed Gas Compressor 2Nd Stage Suction Drum (Tag No. 13-Vv-706)_RCA | 2026-02-20 | 2026-02-20 | 27-Apr-25 A | 03-May-25 A | 2027-01-20 | 16 | 2027-01-20
A54680 | Mechanical Datasheet For Psa2 Feed Gas Compressor 2Nd Stage Suction Drum (Tag No. 13-Vv-706)_IFD/IFC | 2026-02-20 | 2026-02-20 | 04-May-25 A | 10-May-25 A | 2027-01-20 | 2 | 2027-01-20
Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Suction Drum (Tag No. 13-Vv-707) |  | 2026-02-20 | 2026-02-20 | 31-Dec-24 A | 10-May-25 A | 2026-03-02 | 130 | 2027-01-20
A54690 | Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Suction Drum (Tag No. 13-Vv-707)_IFR | 2026-02-20 | 2026-02-20 | 31-Dec-24 A | 06-Feb-25 A | 2026-03-02 | 1 | 2026-03-02
A54700 | Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Suction Drum (Tag No. 13-Vv-707)_RCC | 2026-02-20 | 2026-02-20 | 07-Feb-25 A | 19-Apr-25 A | 2027-01-20 | 16 | 2027-01-20
A54710 | Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Suction Drum (Tag No. 13-Vv-707)_IFA | 2026-02-20 | 2026-02-20 | 20-Apr-25 A | 26-Apr-25 A | 2027-01-20 | 3 | 2027-01-20
A54720 | Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Suction Drum (Tag No. 13-Vv-707)_RCA | 2026-02-20 | 2026-02-20 | 27-Apr-25 A | 03-May-25 A | 2027-01-20 | 16 | 2027-01-20
A54730 | Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Suction Drum (Tag No. 13-Vv-707)_IFD/IFC | 2026-02-20 | 2026-02-20 | 04-May-25 A | 10-May-25 A | 2027-01-20 | 2 | 2027-01-20
Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Discharge Drum (Tag No. 13-Vv-Xxx) |  | 2026-02-20 | 2026-02-20 | 31-Dec-24 A | 05-Jul-25 A | 2026-03-02 | 148 | 2027-01-20
A54740 | Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Discharge Drum (Tag No. 13-Vv-Xxx)_IFR | 2026-02-20 | 2026-02-20 | 31-Dec-24 A | 24-Jan-25 A | 2026-03-02 | 1 | 2026-03-02
A54750 | Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Discharge Drum (Tag No. 13-Vv-Xxx)_RCC | 2026-02-20 | 2026-02-20 | 25-Jan-25 A | 19-Apr-25 A | 2027-01-20 | 16 | 2027-01-20
A54760 | Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Discharge Drum (Tag No. 13-Vv-Xxx)_IFA | 2026-02-20 | 2026-02-20 | 20-Apr-25 A | 21-Jun-25 A | 2027-01-20 | 3 | 2027-01-20
A54770 | Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Discharge Drum (Tag No. 13-Vv-Xxx)_RCA | 2026-02-20 | 2026-02-20 | 22-Jun-25 A | 28-Jun-25 A | 2027-01-20 | 16 | 2027-01-20
A54780 | Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Discharge Drum (Tag No. 13-Vv-Xxx)_IFD/IFC | 2026-02-20 | 2026-02-20 | 29-Jun-25 A | 05-Jul-25 A | 2027-01-20 | 2 | 2027-01-20
Mechanical Datasheet For Psa2 Off Gas Buffer Drum (Tag No. 13-Vv-712) |  | 2026-02-20 | 2026-02-20 | 31-Dec-24 A | 10-May-25 A | 2026-03-02 | 128 | 2027-01-20
A54790 | Mechanical Datasheet For Psa2 Off Gas Buffer Drum (Tag No. 13-Vv-712)_IFR | 2026-02-20 | 2026-02-20 | 31-Dec-24 A | 06-Feb-25 A | 2026-03-02 | 1 | 2026-03-02
A54800 | Mechanical Datasheet For Psa2 Off Gas Buffer Drum (Tag No. 13-Vv-712)_RCC | 2026-02-20 | 2026-02-20 | 07-Feb-25 A | 19-Apr-25 A | 2027-01-20 | 16 | 2027-01-20
A54810 | Mechanical Datasheet For Psa2 Off Gas Buffer Drum (Tag No. 13-Vv-712)_IFA | 2026-02-20 | 2026-02-20 | 20-Apr-25 A | 26-Apr-25 A | 2027-01-20 | 3 | 2027-01-20
A54820 | Mechanical Datasheet For Psa2 Off Gas Buffer Drum (Tag No. 13-Vv-712)_RCA | 2026-02-20 | 2026-02-20 | 27-Apr-25 A | 03-May-25 A | 2027-01-20 | 16 | 2027-01-20
A54830 | Mechanical Datasheet For Psa2 Off Gas Buffer Drum (Tag No. 13-Vv-712)_IFD/IFC | 2026-02-20 | 2026-02-20 | 04-May-25 A | 10-May-25 A | 2027-01-20 | 2 | 2027-01-20
Mechanical Datasheet For Psa2 Off Gas Compressor 2Nd Stage Suction Drum (Tag No. 13-Vv-713) |  | 2026-02-20 | 2026-02-20 | 31-Dec-24 A | 10-May-25 A | 2026-03-02 | 127 | 2027-01-20
A54840 | Mechanical Datasheet For Psa2 Off Gas Compressor 2Nd Stage Suction Drum (Tag No. 13-Vv-713)_IFR | 2026-02-20 | 2026-02-20 | 31-Dec-24 A | 06-Feb-25 A | 2026-03-02 | 1 | 2026-03-02
A54850 | Mechanical Datasheet For Psa2 Off Gas Compressor 2Nd Stage Suction Drum (Tag No. 13-Vv-713)_RCC | 2026-02-20 | 2026-02-20 | 07-Feb-25 A | 19-Apr-25 A | 2027-01-20 | 16 | 2027-01-20
A54860 | Mechanical Datasheet For Psa2 Off Gas Compressor 2Nd Stage Suction Drum (Tag No. 13-Vv-713)_IFA | 2026-02-20 | 2026-02-20 | 20-Apr-25 A | 26-Apr-25 A | 2027-01-20 | 3 | 2027-01-20
A54870 | Mechanical Datasheet For Psa2 Off Gas Compressor 2Nd Stage Suction Drum (Tag No. 13-Vv-713)_RCA | 2026-02-20 | 2026-02-20 | 27-Apr-25 A | 03-May-25 A | 2027-01-20 | 16 | 2027-01-20
A54880 | Mechanical Datasheet For Psa2 Off Gas Compressor 2Nd Stage Suction Drum (Tag No. 13-Vv-713)_IFD/IFC | 2026-02-20 | 2026-02-20 | 04-May-25 A | 10-May-25 A | 2027-01-20 | 2 | 2027-01-20
Mechanical Datasheet For Psa2 Slop Drum (Tag No. 70-Vv-1415) |  | 2026-02-20 | 2026-02-20 | 01-Jan-25 A | 10-May-25 A | 2026-03-02 | 126 | 2027-01-20
A27210 | Mechanical Datasheet For Psa2 Slop Drum (Tag No. 70-Vv-1415)_IFR | 2026-02-20 | 2026-02-20 | 01-Jan-25 A | 06-Feb-25 A | 2026-03-02 | 1 | 2026-03-02
A27220 | Mechanical Datasheet For Psa2 Slop Drum (Tag No. 70-Vv-1415)_RCC | 2026-02-20 | 2026-02-20 | 07-Feb-25 A | 19-Apr-25 A | 2027-01-20 | 16 | 2027-01-20
A27230 | Mechanical Datasheet For Psa2 Slop Drum (Tag No. 70-Vv-1415)_IFA | 2026-02-20 | 2026-02-20 | 20-Apr-25 A | 26-Apr-25 A | 2027-01-20 | 3 | 2027-01-20
A54890 | Mechanical Datasheet For Psa2 Slop Drum (Tag No. 70-Vv-1415)_RCA | 2026-02-20 | 2026-02-20 | 27-Apr-25 A | 03-May-25 A | 2027-01-20 | 16 | 2027-01-20
A54900 | Mechanical Datasheet For Psa2 Slop Drum (Tag No. 70-Vv-1415)_IFD/IFC | 2026-02-20 | 2026-02-20 | 04-May-25 A | 10-May-25 A | 2027-01-20 | 2 | 2027-01-20
Mechanical Datasheet For Psa2 Feed Gas Compressor 1St Stage Cooler (Tag No. 13-He-703) |  | 2026-02-20 | 2026-02-20 | 07-Jan-25 A | 10-May-25 A | 2026-03-02 | 125 | 2026-03-02
A54910 | Mechanical Datasheet For Psa2 Feed Gas Compressor 1St Stage Cooler (Tag No. 13-He-703)_IFR | 2026-02-20 | 2026-02-20 | 07-Jan-25 A | 06-Feb-25 A | 2026-03-02 | 1 | 2026-03-02
A54920 | Mechanical Datasheet For Psa2 Feed Gas Compressor 1St Stage Cooler (Tag No. 13-He-703)_RCC | 2026-02-20 | 2026-02-20 | 07-Feb-25 A | 19-Apr-25 A | 2026-03-02 | 16 | 2026-03-02
A54930 | Mechanical Datasheet For Psa2 Feed Gas Compressor 1St Stage Cooler (Tag No. 13-He-703)_IFA | 2026-02-20 | 2026-02-20 | 20-Apr-25 A | 26-Apr-25 A | 2026-03-02 | 3 | 2026-03-02
A54940 | Mechanical Datasheet For Psa2 Feed Gas Compressor 1St Stage Cooler (Tag No. 13-He-703)_RCA | 2026-02-20 | 2026-02-20 | 27-Apr-25 A | 03-May-25 A | 2026-03-02 | 16 | 2026-03-02
A54950 | Mechanical Datasheet For Psa2 Feed Gas Compressor 1St Stage Cooler (Tag No. 13-He-703)_IFD/IFC | 2026-02-20 | 2026-02-20 | 04-May-25 A | 10-May-25 A | 2026-03-02 | 2 | 2026-03-02
Mechanical Datasheet For Psa2 Feed Gas Compressor 2Nd Stage Cooler (Tag No. 13-He-704) |  | 2026-02-20 | 2026-02-20 | 14-Feb-25 A | 03-May-25 A | 2026-03-02 | 104 | 2026-03-02
A54960 | Mechanical Datasheet For Psa2 Feed Gas Compressor 2Nd Stage Cooler (Tag No. 13-He-704)_IFR | 2026-02-20 | 2026-02-20 | 14-Feb-25 A | 07-Mar-25 A | 2026-03-02 | 1 | 2026-03-02
A54970 | Mechanical Datasheet For Psa2 Feed Gas Compressor 2Nd Stage Cooler (Tag No. 13-He-704)_RCC | 2026-02-20 | 2026-02-20 | 08-Mar-25 A | 14-Mar-25 A | 2026-03-02 | 16 | 2026-03-02
A54980 | Mechanical Datasheet For Psa2 Feed Gas Compressor 2Nd Stage Cooler (Tag No. 13-He-704)_IFA | 2026-02-20 | 2026-02-20 | 15-Mar-25 A | 21-Mar-25 A | 2026-03-02 | 3 | 2026-03-02
A54990 | Mechanical Datasheet For Psa2 Feed Gas Compressor 2Nd Stage Cooler (Tag No. 13-He-704)_RCA | 2026-02-20 | 2026-02-20 | 22-Mar-25 A | 30-Apr-25 A | 2026-03-02 | 16 | 2026-03-02
A55000 | Mechanical Datasheet For Psa2 Feed Gas Compressor 2Nd Stage Cooler (Tag No. 13-He-704)_IFD/IFC | 2026-02-20 | 2026-02-20 | 01-May-25 A | 03-May-25 A | 2026-03-02 | 2 | 2026-03-02
Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Cooler (Tag No. 13-He-703) |  | 2026-02-20 | 2026-02-20 | 20-Jan-25 A | 14-Jun-25 A | 2026-03-02 | 142 | 2026-03-02
A55010 | Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Cooler (Tag No. 13-He-703)_IFR | 2026-02-20 | 2026-02-20 | 20-Jan-25 A | 26-Feb-25 A | 2026-03-02 | 1 | 2026-03-02
A55020 | Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Cooler (Tag No. 13-He-703)_RCC | 2026-02-20 | 2026-02-20 | 27-Feb-25 A | 19-Apr-25 A | 2026-03-02 | 16 | 2026-03-02
A55030 | Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Cooler (Tag No. 13-He-703)_IFA | 2026-02-20 | 2026-02-20 | 20-Apr-25 A | 26-Apr-25 A | 2026-03-02 | 3 | 2026-03-02
A55040 | Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Cooler (Tag No. 13-He-703)_RCA | 2026-02-20 | 2026-02-20 | 08-Jun-25 A | 10-Jun-25 A | 2026-03-02 | 16 | 2026-03-02
A55050 | Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Cooler (Tag No. 13-He-703)_IFD/IFC | 2026-02-20 | 2026-02-20 | 11-Jun-25 A | 14-Jun-25 A | 2026-03-02 | 2 | 2026-03-02
Mechanical Datasheet For Psa2 Off Gas Compressor Interstage Cooler(Tag No. 13-He-708) |  | 2026-02-20 | 2026-02-20 | 25-Feb-25 A | 09-May-25 A | 2026-03-02 | 119 | 2026-03-02
A55060 | Mechanical Datasheet For Psa2 Off Gas Compressor Interstage Cooler(Tag No. 13-He-708)_IFR | 2026-02-20 | 2026-02-20 | 25-Feb-25 A | 26-Feb-25 A | 2026-03-02 | 1 | 2026-03-02
A55070 | Mechanical Datasheet For Psa2 Off Gas Compressor Interstage Cooler(Tag No. 13-He-708)_RCC | 2026-02-20 | 2026-02-20 | 27-Feb-25 A | 04-Mar-25 A | 2026-03-02 | 16 | 2026-03-02
A27430 | Mechanical Datasheet For Psa2 Off Gas Compressor Interstage Cooler(Tag No. 13-He-708)_IFA | 2026-02-20 | 2026-02-20 | 05-Mar-25 A | 25-Apr-25 A | 2026-03-02 | 3 | 2026-03-02
A55080 | Mechanical Datasheet For Psa2 Off Gas Compressor Interstage Cooler(Tag No. 13-He-708)_RCA | 2026-02-20 | 2026-02-20 | 26-Apr-25 A | 02-May-25 A | 2026-03-02 | 16 | 2026-03-02
A55090 | Mechanical Datasheet For Psa2 Off Gas Compressor Interstage Cooler(Tag No. 13-He-708)_IFD/IFC | 2026-02-20 | 2026-02-20 | 03-May-25 A | 09-May-25 A | 2026-03-02 | 2 | 2026-03-02
Mechanical Datasheet For Psa2 Off Gas Compressor Aftercooler(Tag No. 13-He-709) |  | 2026-02-20 | 2026-02-20 | 25-Feb-25 A | 09-May-25 A | 2026-03-02 | 104 | 2026-03-02
A55100 | Mechanical Datasheet For Psa2 Off Gas Compressor Aftercooler(Tag No. 13-He-709)_IFR | 2026-02-20 | 2026-02-20 | 25-Feb-25 A | 26-Feb-25 A | 2026-03-02 | 1 | 2026-03-02
A55110 | Mechanical Datasheet For Psa2 Off Gas Compressor Aftercooler(Tag No. 13-He-709)_RCC | 2026-02-20 | 2026-02-20 | 27-Feb-25 A | 04-Mar-25 A | 2026-03-02 | 16 | 2026-03-02
A55120 | Mechanical Datasheet For Psa2 Off Gas Compressor Aftercooler(Tag No. 13-He-709)_IFA | 2026-02-20 | 2026-02-20 | 05-Mar-25 A | 25-Apr-25 A | 2026-03-02 | 3 | 2026-03-02
A55130 | Mechanical Datasheet For Psa2 Off Gas Compressor Aftercooler(Tag No. 13-He-709)_RCA | 2026-02-20 | 2026-02-20 | 26-Apr-25 A | 02-May-25 A | 2026-03-02 | 16 | 2026-03-02
A55140 | Mechanical Datasheet For Psa2 Off Gas Compressor Aftercooler(Tag No. 13-He-709)_IFD/IFC | 2026-02-20 | 2026-02-20 | 03-May-25 A | 09-May-25 A | 2026-03-02 | 2 | 2026-03-02
Mechanical Datasheet For Psa2 Off Gas Compressor Discharge Dripleg -13-Sp-7004 |  | 2026-02-20 | 2026-02-20 | 01-Jan-25 A | 10-May-25 A | 2026-03-02 | 119 | 2027-01-20
A27510 | Mechanical Datasheet For Psa2 Off Gas Compressor Discharge Dripleg -13-Sp-7004_IFR | 2026-02-20 | 2026-02-20 | 01-Jan-25 A | 24-Jan-25 A | 2026-03-02 | 1 | 2026-03-02
A27520 | Mechanical Datasheet For Psa2 Off Gas Compressor Discharge Dripleg -13-Sp-7004_RCC | 2026-02-20 | 2026-02-20 | 25-Jan-25 A | 19-Apr-25 A | 2027-01-20 | 16 | 2027-01-20
A55150 | Mechanical Datasheet For Psa2 Off Gas Compressor Discharge Dripleg -13-Sp-7004_IFA | 2026-02-20 | 2026-02-20 | 20-Apr-25 A | 26-Apr-25 A | 2027-01-20 | 3 | 2027-01-20
A55160 | Mechanical Datasheet For Psa2 Off Gas Compressor Discharge Dripleg -13-Sp-7004_RCA | 2026-02-20 | 2026-02-20 | 27-Apr-25 A | 03-May-25 A | 2027-01-20 | 16 | 2027-01-20
A55170 | Mechanical Datasheet For Psa2 Off Gas Compressor Discharge Dripleg -13-Sp-7004_IFD/IFC | 2026-02-20 | 2026-02-20 | 04-May-25 A | 10-May-25 A | 2027-01-20 | 2 | 2027-01-20
Mechanical Datasheet For C4 Guard Adsorber Regeneration Gas Cooler(Tag No. 50-He-1410) |  | 2026-02-20 | 2026-02-20 | 27-Feb-25 A | 10-May-25 A | 2026-03-02 | 118 | 2026-03-02
A55180 | Mechanical Datasheet For C4 Guard Adsorber Regeneration Gas Cooler(Tag No. 50-He-1410)_IFR | 2026-02-20 | 2026-02-20 | 27-Feb-25 A | 20-Mar-25 A | 2026-03-02 | 1 | 2026-03-02
A55190 | Mechanical Datasheet For C4 Guard Adsorber Regeneration Gas Cooler(Tag No. 50-He-1410)_RCC | 2026-02-20 | 2026-02-20 | 21-Mar-25 A | 19-Apr-25 A | 2026-03-02 | 16 | 2026-03-02
A55200 | Mechanical Datasheet For C4 Guard Adsorber Regeneration Gas Cooler(Tag No. 50-He-1410)_IFA | 2026-02-20 | 2026-02-20 | 20-Apr-25 A | 26-Apr-25 A | 2026-03-02 | 3 | 2026-03-02
A55210 | Mechanical Datasheet For C4 Guard Adsorber Regeneration Gas Cooler(Tag No. 50-He-1410)_RCA | 2026-02-20 | 2026-02-20 | 27-Apr-25 A | 03-May-25 A | 2026-03-02 | 16 | 2026-03-02
A55220 | Mechanical Datasheet For C4 Guard Adsorber Regeneration Gas Cooler(Tag No. 50-He-1410)_IFD/IFC | 2026-02-20 | 2026-02-20 | 04-May-25 A | 10-May-25 A | 2026-03-02 | 2 | 2026-03-02
Mechanical Datasheet For Vhp Boiler Feed Water Preheater Dripleg |  | 2026-02-20 | 2026-04-14 | 01-Jul-25 A | 2026-04-14 | 2026-03-02 | 212 | 2027-01-20 | 202
A27610 | Mechanical Datasheet For Vhp Boiler Feed Water Preheater Dripleg_IFR | 2026-02-20 | 2026-02-20 | 01-Jul-25 A | 12-Jul-25 A | 2026-03-02 | 1 | 2026-03-02
A55230 | Mechanical Datasheet For Vhp Boiler Feed Water Preheater Dripleg_RCC | 2026-02-20 | 2026-03-13 | 2026-02-20 | 2026-03-13 | 2026-11-30 | 16 | 2026-12-22 | 202
A55240 | Mechanical Datasheet For Vhp Boiler Feed Water Preheater Dripleg_IFA | 2026-03-13 | 2026-03-19 | 2026-03-13 | 2026-03-19 | 2026-12-22 | 3 | 2026-12-25 | 202
A55250 | Mechanical Datasheet For Vhp Boiler Feed Water Preheater Dripleg_RCA | 2026-03-19 | 2026-04-09 | 2026-03-19 | 2026-04-09 | 2026-12-28 | 16 | 2027-01-18 | 202
A55260 | Mechanical Datasheet For Vhp Boiler Feed Water Preheater Dripleg_IFD/IFC | 2026-04-09 | 2026-04-14 | 2026-04-09 | 2026-04-14 | 2027-01-18 | 2 | 2027-01-20 | 202
Mechanical Datasheet For Off-Gas Compressor Coalescer |  | 2026-02-20 | 2026-02-20 | 13-Jan-25 A | 03-Mar-25 A | 2026-03-02 | 34 | 2026-03-02
A55270 | Mechanical Datasheet For Off-Gas Compressor Coalescer_IFR | 2026-02-20 | 2026-02-20 | 13-Jan-25 A | 03-Feb-25 A | 2026-03-02 | 1 | 2026-03-02
A55280 | Mechanical Datasheet For Off-Gas Compressor Coalescer_RCC | 2026-02-20 | 2026-02-20 | 04-Feb-25 A | 10-Feb-25 A | 2026-03-02 | 16 | 2026-03-02
A55290 | Mechanical Datasheet For Off-Gas Compressor Coalescer_IFA | 2026-02-20 | 2026-02-20 | 11-Feb-25 A | 17-Feb-25 A | 2026-03-02 | 3 | 2026-03-02
A55300 | Mechanical Datasheet For Off-Gas Compressor Coalescer_RCA | 2026-02-20 | 2026-02-20 | 18-Feb-25 A | 24-Feb-25 A | 2026-03-02 | 16 | 2026-03-02
A27700 | Mechanical Datasheet For Off-Gas Compressor Coalescer_IFD/IFC | 2026-02-20 | 2026-02-20 | 25-Feb-25 A | 03-Mar-25 A | 2026-03-02 | 2 | 2026-03-02
Mechanical Datasheet For Guard Adsorber Regeneration Gas Coalescer |  | 2026-02-20 | 2026-02-20 | 06-Jan-25 A | 10-May-25 A | 2026-03-02 | 116 | 2026-03-02
A55310 | Mechanical Datasheet For Guard Adsorber Regeneration Gas Coalescer_IFR | 2026-02-20 | 2026-02-20 | 06-Jan-25 A | 14-Mar-25 A | 2026-03-02 | 1 | 2026-03-02
A55320 | Mechanical Datasheet For Guard Adsorber Regeneration Gas Coalescer_RCC | 2026-02-20 | 2026-02-20 | 15-Mar-25 A | 19-Apr-25 A | 2026-03-02 | 16 | 2026-03-02
A55330 | Mechanical Datasheet For Guard Adsorber Regeneration Gas Coalescer_IFA | 2026-02-20 | 2026-02-20 | 20-Apr-25 A | 26-Apr-25 A | 2026-03-02 | 3 | 2026-03-02
A55340 | Mechanical Datasheet For Guard Adsorber Regeneration Gas Coalescer_RCA | 2026-02-20 | 2026-02-20 | 27-Apr-25 A | 03-May-25 A | 2026-03-02 | 16 | 2026-03-02
A55350 | Mechanical Datasheet For Guard Adsorber Regeneration Gas Coalescer_IFD/IFC | 2026-02-20 | 2026-02-20 | 04-May-25 A | 10-May-25 A | 2026-03-02 | 2 | 2026-03-02
Mechanical Datasheet For Tail Gas Silencer |  | 2026-02-20 | 2026-04-14 | 01-Jul-25 A | 2026-04-14 | 2026-11-30 | 211 | 2027-01-20 | 202
A55360 | Mechanical Datasheet For Tail Gas Silencer_IFR | 2026-02-20 | 2026-02-20 | 01-Jul-25 A | 12-Jul-25 A | 2026-11-30 | 1 | 2026-11-30
A55370 | Mechanical Datasheet For Tail Gas Silencer_RCC | 2026-02-20 | 2026-03-13 | 2026-02-20 | 2026-03-13 | 2026-11-30 | 16 | 2026-12-22 | 202
A55380 | Mechanical Datasheet For Tail Gas Silencer_IFA | 2026-03-13 | 2026-03-19 | 2026-03-13 | 2026-03-19 | 2026-12-22 | 3 | 2026-12-25 | 202
A27790 | Mechanical Datasheet For Tail Gas Silencer_RCA | 2026-03-19 | 2026-04-09 | 2026-03-19 | 2026-04-09 | 2026-12-28 | 16 | 2027-01-18 | 202
A55390 | Mechanical Datasheet For Tail Gas Silencer_IFD/IFC | 2026-04-09 | 2026-04-14 | 2026-04-09 | 2026-04-14 | 2027-01-18 | 2 | 2027-01-20 | 202
Material Requisiton for Coalscer |  | 2026-02-20 | 2026-02-20 | 28-Feb-25 A | 14-May-25 A | 2026-03-02 | 118 | 2026-03-02
A45410 | Material Requisiton for Coalscer_IFR | 2026-02-20 | 2026-02-20 | 28-Feb-25 A | 21-Mar-25 A | 2026-03-02 | 6 | 2026-03-02
A45420 | Material Requisiton for Coalscer_RCC | 2026-02-20 | 2026-02-20 | 22-Mar-25 A | 21-Apr-25 A | 2026-03-02 | 16 | 2026-03-02
A45430 | Material Requisiton for Coalscer_IFA | 2026-02-20 | 2026-02-20 | 22-Apr-25 A | 30-Apr-25 A | 2026-03-02 | 3 | 2026-03-02
A45440 | Material Requisiton for Coalscer_RCA | 2026-02-20 | 2026-02-20 | 01-May-25 A | 07-May-25 A | 2026-03-02 | 16 | 2026-03-02
A45450 | Material Requisiton for Coalscer_IFD/IFC | 2026-02-20 | 2026-02-20 | 08-May-25 A | 14-May-25 A | 2026-03-02 | 2 | 2026-03-02
Material Requisiton for Shell and Tube Heat Exchangers |  | 2026-02-20 | 2026-02-20 | 21-Feb-25 A | 20-Jun-25 A | 2026-03-02 | 153 | 2026-03-02
A45360 | Material Requisiton for Heat Exchangers_IFR | 2026-02-20 | 2026-02-20 | 21-Feb-25 A | 14-Mar-25 A | 2026-03-02 | 6 | 2026-03-02
A45370 | Material Requisiton for Heat Exchangers_RCC | 2026-02-20 | 2026-02-20 | 01-Jun-25 A | 05-Jun-25 A | 2026-03-02 | 16 | 2026-03-02
A45380 | Material Requisiton for Heat Exchangers_IFA | 2026-02-20 | 2026-02-20 | 06-Jun-25 A | 10-Jun-25 A | 2026-03-02 | 3 | 2026-03-02
A45390 | Material Requisiton for Heat Exchangers_RCA | 2026-02-20 | 2026-02-20 | 11-Jun-25 A | 15-Jun-25 A | 2026-03-02 | 16 | 2026-03-02
A45400 | Material Requisiton for Heat Exchangers_IFD/IFC | 2026-02-20 | 2026-02-20 | 16-Jun-25 A | 20-Jun-25 A | 2026-03-02 | 2 | 2026-03-02
Material Requisiton for Pressure Vessels & Internals |  | 2026-02-20 | 2026-02-20 | 17-Jan-25 A | 09-May-25 A | 2026-03-02 | 122 | 2026-03-02
A45910 | Material Requisiton for Pressure Vessels & Internals_IFR | 2026-02-20 | 2026-02-20 | 17-Jan-25 A | 07-Feb-25 A | 2026-03-02 | 6 | 2026-03-02
A45920 | Material Requisiton for Pressure Vessels & Internals_RCC | 2026-02-20 | 2026-02-20 | 08-Feb-25 A | 14-Feb-25 A | 2026-03-02 | 16 | 2026-03-02
A45930 | Material Requisiton for Pressure Vessels & Internals_IFA | 2026-02-20 | 2026-02-20 | 15-Feb-25 A | 25-Apr-25 A | 2026-03-02 | 3 | 2026-03-02
A45940 | Material Requisiton for Pressure Vessels & Internals_RCA | 2026-02-20 | 2026-02-20 | 26-Apr-25 A | 02-May-25 A | 2026-03-02 | 16 | 2026-03-02
A45950 | Material Requisiton for Pressure Vessels & Internals_IFD/IFC | 2026-02-20 | 2026-02-20 | 03-May-25 A | 09-May-25 A | 2026-03-02 | 2 | 2026-03-02
Mechanical Rotating |  | 2026-02-20 | 2026-02-20 | 04-Jan-25 A | 28-Jun-25 A | 2026-03-02 | 151 | 2026-03-02
Mechanical Datasheet For Sanitary Water Collection Pump |  | 2026-02-20 | 2026-02-20 | 05-Feb-25 A | 10-May-25 A | 2026-03-02 | 132 | 2026-03-02
A54540 | Mechanical Datasheet For Sanitary Water Collection Pump_IFR | 2026-02-20 | 2026-02-20 | 05-Feb-25 A | 26-Feb-25 A | 2026-03-02 | 2 | 2026-03-02
A54550 | Mechanical Datasheet For Sanitary Water Collection Pump_RCC | 2026-02-20 | 2026-02-20 | 27-Feb-25 A | 19-Apr-25 A | 2026-03-02 | 16 | 2026-03-02
A54560 | Mechanical Datasheet For Sanitary Water Collection Pump_IFA | 2026-02-20 | 2026-02-20 | 20-Apr-25 A | 26-Apr-25 A | 2026-03-02 | 3 | 2026-03-02
A54570 | Mechanical Datasheet For Sanitary Water Collection Pump_RCA | 2026-02-20 | 2026-02-20 | 27-Apr-25 A | 03-May-25 A | 2026-03-02 | 16 | 2026-03-02
A54580 | Mechanical Datasheet For Sanitary Water Collection Pump_IFD/IFC | 2026-02-20 | 2026-02-20 | 04-May-25 A | 10-May-25 A | 2026-03-02 | 2 | 2026-03-02
Mechanical Data Sheet for EOT Crane for Feed Gas Compressor |  | 2026-02-20 | 2026-02-20 | 27-Jan-25 A | 28-Jun-25 A | 2026-03-02 | 151 | 2026-03-02
A45610 | Mechanical Data Sheet for EOT Crane for Feed Gas Compressor_IFR | 2026-02-20 | 2026-02-20 | 27-Jan-25 A | 26-Feb-25 A | 2026-03-02 | 6 | 2026-03-02
A45620 | Mechanical Data Sheet for EOT Crane for Feed Gas Compressor_RCC | 2026-02-20 | 2026-02-20 | 27-Feb-25 A | 19-Apr-25 A | 2026-03-02 | 16 | 2026-03-02
A45630 | Mechanical Data Sheet for EOT Crane for Feed Gas Compressor_IFA | 2026-02-20 | 2026-02-20 | 20-Apr-25 A | 10-Jun-25 A | 2026-03-02 | 3 | 2026-03-02
A45640 | Mechanical Data Sheet for EOT Crane for Feed Gas Compressor_RCA | 2026-02-20 | 2026-02-20 | 11-Jun-25 A | 21-Jun-25 A | 2026-03-02 | 16 | 2026-03-02
A45650 | Mechanical Data Sheet for EOT Crane for Feed Gas Compressor_IFD/IFC | 2026-02-20 | 2026-02-20 | 22-Jun-25 A | 28-Jun-25 A | 2026-03-02 | 2 | 2026-03-02
Mechanical Data Sheet EOT Crane for Off Gas Compressor |  | 2026-02-20 | 2026-02-20 | 27-Jan-25 A | 28-Jun-25 A | 2026-03-02 | 151 | 2026-03-02
A45660 | Mechanical Data Sheet EOT Crane for Off Gas Compressor_IFR | 2026-02-20 | 2026-02-20 | 27-Jan-25 A | 26-Feb-25 A | 2026-03-02 | 6 | 2026-03-02
A45670 | Mechanical Data Sheet EOT Crane for Off Gas Compressor_RCC | 2026-02-20 | 2026-02-20 | 27-Feb-25 A | 18-Mar-25 A | 2026-03-02 | 16 | 2026-03-02
A45680 | Mechanical Data Sheet EOT Crane for Off Gas Compressor_IFA | 2026-02-20 | 2026-02-20 | 19-Mar-25 A | 10-Jun-25 A | 2026-03-02 | 3 | 2026-03-02
A45690 | Mechanical Data Sheet EOT Crane for Off Gas Compressor_RCA | 2026-02-20 | 2026-02-20 | 11-Jun-25 A | 21-Jun-25 A | 2026-03-02 | 16 | 2026-03-02
A45700 | Mechanical Data Sheet EOT Crane for Off Gas Compressor_IFD/IFC | 2026-02-20 | 2026-02-20 | 22-Jun-25 A | 28-Jun-25 A | 2026-03-02 | 2 | 2026-03-02
Mechanical Datasheet for Water Collection Sump Pump |  | 2026-02-20 | 2026-02-20 | 04-Jan-25 A | 10-May-25 A | 2026-03-02 | 130 | 2026-03-02
A45560 | Mechanical Datasheet for Water Collection Sump Pump_IFR | 2026-02-20 | 2026-02-20 | 04-Jan-25 A | 25-Jan-25 A | 2026-03-02 | 2 | 2026-03-02
A45570 | Mechanical Datasheet for Water Collection Sump Pump_RCC | 2026-02-20 | 2026-02-20 | 26-Jan-25 A | 19-Apr-25 A | 2026-03-02 | 16 | 2026-03-02
A45580 | Mechanical Datasheet for Water Collection Sump Pump_IFA | 2026-02-20 | 2026-02-20 | 20-Apr-25 A | 26-Apr-25 A | 2026-03-02 | 3 | 2026-03-02
A45590 | Mechanical Datasheet for Water Collection Sump Pump_RCA | 2026-02-20 | 2026-02-20 | 27-Apr-25 A | 03-May-25 A | 2026-03-02 | 16 | 2026-03-02
A45600 | Mechanical Datasheet for Water Collection Sump Pump_IFD/IFC | 2026-02-20 | 2026-02-20 | 04-May-25 A | 10-May-25 A | 2026-03-02 | 2 | 2026-03-02
Material Requisiton for EOT Crane |  | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 13-Jun-25 A | 2026-03-02 | 141 | 2026-03-02
A45760 | Material Requisiton for EOT Crane_IFR | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 06-May-25 A | 2026-03-02 | 3 | 2026-03-02
A45770 | Material Requisiton for EOT Crane_RCC | 2026-02-20 | 2026-02-20 | 07-May-25 A | 13-May-25 A | 2026-03-02 | 16 | 2026-03-02
A45780 | Material Requisiton for EOT Crane_IFA | 2026-02-20 | 2026-02-20 | 14-May-25 A | 20-May-25 A | 2026-03-02 | 3 | 2026-03-02
A45790 | Material Requisiton for EOT Crane_RCA | 2026-02-20 | 2026-02-20 | 21-May-25 A | 02-Jun-25 A | 2026-03-02 | 16 | 2026-03-02
A45800 | Material Requisiton for EOT Crane_IFD/IFC | 2026-02-20 | 2026-02-20 | 03-Jun-25 A | 13-Jun-25 A | 2026-03-02 | 2 | 2026-03-02
Material Requisiton for Centrifugal Pump |  | 2026-02-20 | 2026-02-20 | 27-Jan-25 A | 21-Jun-25 A | 2026-03-02 | 136 | 2026-03-02
A45710 | Material Requisiton for Centrifugal Pump_IFR | 2026-02-20 | 2026-02-20 | 27-Jan-25 A | 21-Mar-25 A | 2026-03-02 | 6 | 2026-03-02
A45720 | Material Requisiton for Centrifugal Pump_RCC | 2026-02-20 | 2026-02-20 | 22-Mar-25 A | 19-Apr-25 A | 2026-03-02 | 16 | 2026-03-02
A45730 | Material Requisiton for Centrifugal Pump_IFA | 2026-02-20 | 2026-02-20 | 20-Apr-25 A | 01-May-25 A | 2026-03-02 | 3 | 2026-03-02
A45740 | Material Requisiton for Centrifugal Pump_RCA | 2026-02-20 | 2026-02-20 | 02-May-25 A | 26-May-25 A | 2026-03-02 | 16 | 2026-03-02
A45750 | Material Requisiton for Centrifugal Pump_IFD/IFC | 2026-02-20 | 2026-02-20 | 27-May-25 A | 21-Jun-25 A | 2026-03-02 | 2 | 2026-03-02
Safety |  | 2026-02-20 | 2026-05-14 | 31-Dec-24 A | 2026-05-14 | 2026-03-02 | 369 | 2027-01-20 | 179
Engineering HSE Plan |  | 2026-02-20 | 2026-02-20 | 30-Jan-25 A | 19-May-25 A | 2026-03-02 | 103 | 2027-01-20
A46010 | Engineering HSE Plan_IFR | 2026-02-20 | 2026-02-20 | 30-Jan-25 A | 20-Feb-25 A | 2026-03-02 | 6 | 2026-03-02
A46020 | Engineering HSE Plan_RCC | 2026-02-20 | 2026-02-20 | 21-Feb-25 A | 27-Feb-25 A | 2027-01-20 | 16 | 2027-01-20
A46030 | Engineering HSE Plan_IFA | 2026-02-20 | 2026-02-20 | 28-Feb-25 A | 06-Mar-25 A | 2027-01-20 | 3 | 2027-01-20
A46040 | Engineering HSE Plan_RCA | 2026-02-20 | 2026-02-20 | 07-Mar-25 A | 12-May-25 A | 2027-01-20 | 16 | 2027-01-20
A46050 | Engineering HSE Plan_IFD/IFC | 2026-02-20 | 2026-02-20 | 13-May-25 A | 19-May-25 A | 2027-01-20 | 2 | 2027-01-20
Project HSE Philosophy |  | 2026-02-20 | 2026-02-20 | 31-Dec-24 A | 20-May-25 A | 2026-03-02 | 112 | 2027-01-20
A46060 | Project HSE Philosophy_IFR | 2026-02-20 | 2026-02-20 | 31-Dec-24 A | 23-Jan-25 A | 2026-03-02 | 6 | 2026-03-02
A46070 | Project HSE Philosophy_RCC | 2026-02-20 | 2026-02-20 | 24-Jan-25 A | 03-Mar-25 A | 2026-04-02 | 16 | 2026-04-02
A46080 | Project HSE Philosophy_IFA | 2026-02-20 | 2026-02-20 | 04-Mar-25 A | 10-Mar-25 A | 2026-04-02 | 3 | 2026-04-02
A46090 | Project HSE Philosophy_RCA | 2026-02-20 | 2026-02-20 | 11-Mar-25 A | 13-Mar-25 A | 2027-01-20 | 16 | 2027-01-20
A46100 | Project HSE Philosophy_IFD/IFC | 2026-02-20 | 2026-02-20 | 14-Mar-25 A | 20-May-25 A | 2027-01-20 | 2 | 2027-01-20
Fire Protection and Detection Philosophy |  | 2026-02-20 | 2026-02-20 | 07-Feb-25 A | 19-Nov-25 A | 2026-03-02 | 246 | 2027-01-20
A46110 | Fire Protection and Detection Philosophy_IFR | 2026-02-20 | 2026-02-20 | 07-Feb-25 A | 28-Feb-25 A | 2026-03-02 | 6 | 2026-03-02
A46120 | Fire Protection and Detection Philosophy_RCC | 2026-02-20 | 2026-02-20 | 01-Mar-25 A | 21-Jun-25 A | 2027-01-20 | 16 | 2027-01-20
A46130 | Fire Protection and Detection Philosophy_IFA | 2026-02-20 | 2026-02-20 | 22-Jun-25 A | 28-Jun-25 A | 2027-01-20 | 3 | 2027-01-20
A46140 | Fire Protection and Detection Philosophy_RCA | 2026-02-20 | 2026-02-20 | 28-Aug-25 A | 16-Oct-25 A | 2027-01-20 | 16 | 2027-01-20
A46150 | Fire Protection and Detection Philosophy_IFD/IFC | 2026-02-20 | 2026-02-20 | 10-Nov-25 A | 19-Nov-25 A | 2027-01-20 | 2 | 2027-01-20
Hazardous Area Classification Schedule |  | 2026-02-20 | 2026-02-20 | 17-Jan-25 A | 23-Dec-25 A | 2026-03-19 | 256 | 2027-01-20
A46160 | Hazardous Area Classification Schedule_IFR | 2026-02-20 | 2026-02-20 | 17-Jan-25 A | 07-Feb-25 A | 2026-03-19 | 6 | 2026-03-19
A46170 | Hazardous Area Classification Schedule_RCC | 2026-02-20 | 2026-02-20 | 08-Feb-25 A | 06-May-25 A | 2026-03-19 | 16 | 2026-03-19
A46180 | Hazardous Area Classification Schedule_IFA | 2026-02-20 | 2026-02-20 | 07-May-25 A | 20-May-25 A | 2026-03-19 | 3 | 2026-03-19
A46190 | Hazardous Area Classification Schedule_RCA | 2026-02-20 | 2026-02-20 | 23-Jun-25 A | 22-Aug-25 A | 2027-01-20 | 16 | 2027-01-20
A46200 | Hazardous Area Classification Schedule_IFD/IFC | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 23-Dec-25 A | 2027-01-20 | 2 | 2027-01-20
Fire Protection and Safety Equipment Layouts (Building) |  | 2026-02-20 | 2026-02-20 | 27-Feb-25 A | 23-Dec-25 A | 2026-04-20 | 241 | 2027-01-20
A46360 | Fire Protection and Safety Equipment Layouts (Building)_IFR | 2026-02-20 | 2026-02-20 | 27-Feb-25 A | 20-Mar-25 A | 2026-04-20 | 6 | 2026-04-20
A46370 | Fire Protection and Safety Equipment Layouts (Building)_RCC | 2026-02-20 | 2026-02-20 | 21-Mar-25 A | 21-Jun-25 A | 2027-01-20 | 16 | 2027-01-20
A46380 | Fire Protection and Safety Equipment Layouts (Building)_IFA | 2026-02-20 | 2026-02-20 | 22-Jun-25 A | 28-Jul-25 A | 2027-01-20 | 3 | 2027-01-20
A46390 | Fire Protection and Safety Equipment Layouts (Building)_RCA | 2026-02-20 | 2026-02-20 | 29-Jul-25 A | 27-Aug-25 A | 2027-01-20 | 16 | 2027-01-20
A46400 | Fire Protection and Safety Equipment Layouts (Building)_IFD/IFC | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 23-Dec-25 A | 2027-01-20 | 2 | 2027-01-20
Escape Route and Safety Signs Layouts (Building) |  | 2026-02-20 | 2026-02-20 | 27-Feb-25 A | 23-Dec-25 A | 2026-04-20 | 241 | 2027-01-20
A46460 | Escape Route and Safety Signs Layouts (Building)_IFR | 2026-02-20 | 2026-02-20 | 27-Feb-25 A | 20-Mar-25 A | 2026-04-20 | 6 | 2026-04-20
A46470 | Escape Route and Safety Signs Layouts (Building)_RCC | 2026-02-20 | 2026-02-20 | 21-Mar-25 A | 21-Jun-25 A | 2027-01-20 | 16 | 2027-01-20
A46480 | Escape Route and Safety Signs Layouts (Building)_IFA | 2026-02-20 | 2026-02-20 | 01-Oct-25 A | 07-Oct-25 A | 2027-01-20 | 3 | 2027-01-20
A46490 | Escape Route and Safety Signs Layouts (Building)_RCA | 2026-02-20 | 2026-02-20 | 03-Oct-25 A | 14-Oct-25 A | 2027-01-20 | 16 | 2027-01-20
A46500 | Escape Route and Safety Signs Layouts (Building)_IFD/IFC | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 23-Dec-25 A | 2027-01-20 | 2 | 2027-01-20
Fire & Gas Detectors Layouts (Building) |  | 2026-02-20 | 2026-02-20 | 27-Feb-25 A | 23-Dec-25 A | 2026-04-20 | 241 | 2027-01-20
A46560 | Fire & Gas Detectors Layouts (Building)_IFR | 2026-02-20 | 2026-02-20 | 27-Feb-25 A | 20-Mar-25 A | 2026-04-20 | 6 | 2026-04-20
A46570 | Fire & Gas Detectors Layouts (Building)_RCC | 2026-02-20 | 2026-02-20 | 21-Mar-25 A | 21-Jun-25 A | 2027-01-20 | 16 | 2027-01-20
A46580 | Fire & Gas Detectors Layouts (Building)_IFA | 2026-02-20 | 2026-02-20 | 22-Jun-25 A | 16-Jul-25 A | 2027-01-20 | 3 | 2027-01-20
A46590 | Fire & Gas Detectors Layouts (Building)_RCA | 2026-02-20 | 2026-02-20 | 08-Sep-25 A | 07-Oct-25 A | 2027-01-20 | 16 | 2027-01-20
A46600 | Fire & Gas Detectors Layouts (Building)_IFD/IFC | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 23-Dec-25 A | 2027-01-20 | 2 | 2027-01-20
F&G Cause and Effects Matrix |  | 2026-02-20 | 2026-04-21 | 2026-02-20 | 2026-04-21 | 2026-11-23 | 43 | 2027-01-20 | 196
A46610 | F&G Cause and Effects Matrix_IFR | 2026-02-20 | 2026-02-27 | 2026-02-20 | 2026-02-27 | 2026-11-23 | 6 | 2026-11-30 | 196
A46620 | F&G Cause and Effects Matrix_RCC | 2026-02-27 | 2026-03-23 | 2026-02-27 | 2026-03-23 | 2026-11-30 | 16 | 2026-12-22 | 196
A46630 | F&G Cause and Effects Matrix_IFA | 2026-03-23 | 2026-03-26 | 2026-03-23 | 2026-03-26 | 2026-12-22 | 3 | 2026-12-25 | 196
A46640 | F&G Cause and Effects Matrix_RCA | 2026-03-26 | 2026-04-17 | 2026-03-26 | 2026-04-17 | 2026-12-28 | 16 | 2027-01-18 | 196
A46650 | F&G Cause and Effects Matrix_IFD/IFC | 2026-04-17 | 2026-04-21 | 2026-04-17 | 2026-04-21 | 2027-01-18 | 2 | 2027-01-20 | 196
Specification for Fire Protection and Safety Equipment |  | 2026-02-20 | 2026-02-20 | 07-Feb-25 A | 23-Dec-25 A | 2026-04-20 | 259 | 2027-01-20
A46760 | Specification for Fire Protection and Safety Equipment_IFR | 2026-02-20 | 2026-02-20 | 07-Feb-25 A | 28-Feb-25 A | 2026-04-20 | 6 | 2026-04-20
A46770 | Specification for Fire Protection and Safety Equipment_RCC | 2026-02-20 | 2026-02-20 | 01-Mar-25 A | 31-Jul-25 A | 2027-01-20 | 16 | 2027-01-20
A46780 | Specification for Fire Protection and Safety Equipment_IFA | 2026-02-20 | 2026-02-20 | 01-Oct-25 A | 07-Oct-25 A | 2027-01-20 | 3 | 2027-01-20
A46790 | Specification for Fire Protection and Safety Equipment_RCA | 2026-02-20 | 2026-02-20 | 03-Oct-25 A | 14-Oct-25 A | 2027-01-20 | 16 | 2027-01-20
A46800 | Specification for Fire Protection and Safety Equipment_IFD/IFC | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 23-Dec-25 A | 2027-01-20 | 2 | 2027-01-20
Specification for Clean Agent System |  | 2026-02-20 | 2026-02-20 | 11-Feb-25 A | 10-Oct-25 A | 2026-05-05 | 189 | 2027-01-20
A46810 | Specification for Clean Agent System_IFR | 2026-02-20 | 2026-02-20 | 11-Feb-25 A | 04-Mar-25 A | 2026-05-05 | 6 | 2026-05-05
A46820 | Specification for Clean Agent System_RCC | 2026-02-20 | 2026-02-20 | 05-Mar-25 A | 21-Jun-25 A | 2027-01-20 | 16 | 2027-01-20
A46830 | Specification for Clean Agent System_IFA | 2026-02-20 | 2026-02-20 | 22-Jun-25 A | 30-Jun-25 A | 2027-01-20 | 3 | 2027-01-20
A46840 | Specification for Clean Agent System_RCA | 2026-02-20 | 2026-02-20 | 12-Jul-25 A | 30-Jul-25 A | 2027-01-20 | 16 | 2027-01-20
A46850 | Specification for Clean Agent System_IFD/IFC | 2026-02-20 | 2026-02-20 | 01-Oct-25 A | 10-Oct-25 A | 2027-01-20 | 2 | 2027-01-20
MR for Clean Agent System |  | 2026-02-20 | 2026-02-20 | 28-Feb-25 A | 10-Oct-25 A | 2026-05-05 | 213 | 2026-05-05
A47230 | MR for Clean Agent System_IFR | 2026-02-20 | 2026-02-20 | 28-Feb-25 A | 21-Mar-25 A | 2026-05-05 | 6 | 2026-05-05
A47240 | MR for Clean Agent System_RCC | 2026-02-20 | 2026-02-20 | 22-Mar-25 A | 21-Jun-25 A | 2026-05-05 | 16 | 2026-05-05
A47250 | MR for Clean Agent System_IFA | 2026-02-20 | 2026-02-20 | 22-Jun-25 A | 23-Aug-25 A | 2026-05-05 | 3 | 2026-05-05
A47260 | MR for Clean Agent System_RCA | 2026-02-20 | 2026-02-20 | 24-Aug-25 A | 30-Aug-25 A | 2026-05-05 | 16 | 2026-05-05
A47270 | MR for Clean Agent System_IFD/IFC | 2026-02-20 | 2026-02-20 | 01-Oct-25 A | 10-Oct-25 A | 2026-05-05 | 2 | 2026-05-05
Firewater Line List |  | 2026-02-20 | 2026-04-17 | 28-Feb-25 A | 2026-04-17 | 2026-11-30 | 286 | 2027-01-20 | 199
A47130 | Firewater Line List_IFR | 2026-02-20 | 2026-02-20 | 28-Feb-25 A | 21-Mar-25 A | 2026-11-30 | 6 | 2026-11-30
A47140 | Firewater Line List_RCC | 2026-02-20 | 2026-03-13 | 2026-02-20 | 2026-03-13 | 2026-11-30 | 16 | 2026-12-22 | 202
A47150 | Firewater Line List_IFA | 2026-03-19 | 2026-03-24 | 2026-03-19 | 2026-03-24 | 2026-12-22 | 3 | 2026-12-25 | 199
A47160 | Firewater Line List_RCA | 2026-03-24 | 2026-04-15 | 2026-03-24 | 2026-04-15 | 2026-12-28 | 16 | 2027-01-18 | 199
A47170 | Firewater Line List_IFD/IFC | 2026-04-15 | 2026-04-17 | 2026-04-15 | 2026-04-17 | 2027-01-18 | 2 | 2027-01-20 | 199
Passive Fire Protection schedule |  | 2026-02-20 | 2026-02-20 | 28-Feb-25 A | 23-Dec-25 A | 2027-01-20 | 250 | 2027-01-20
A46660 | Passive Fire Protection schedule_IFR | 2026-02-20 | 2026-02-20 | 28-Feb-25 A | 21-Mar-25 A | 2027-01-20 | 6 | 2027-01-20
A46670 | Passive Fire Protection schedule_RCC | 2026-02-20 | 2026-02-20 | 22-Mar-25 A | 21-Jun-25 A | 2027-01-20 | 16 | 2027-01-20
A46680 | Passive Fire Protection schedule_IFA | 2026-02-20 | 2026-02-20 | 22-Jun-25 A | 18-Jul-25 A | 2027-01-20 | 3 | 2027-01-20
A46690 | Passive Fire Protection schedule_RCA | 2026-02-20 | 2026-02-20 | 08-Sep-25 A | 07-Oct-25 A | 2027-01-20 | 16 | 2027-01-20
A46700 | Passive Fire Protection schedule_IFD/IFC | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 23-Dec-25 A | 2027-01-20 | 2 | 2027-01-20
Firewater Demand Report |  | 2026-02-20 | 2026-02-20 | 17-Jan-25 A | 03-Nov-25 A | 2026-11-30 | 230 | 2027-01-20
A9080 | Firewater Demand Report_IFR | 2026-02-20 | 2026-02-20 | 17-Jan-25 A | 11-Mar-25 A | 2026-11-30 | 6 | 2026-11-30
A9090 | Firewater Demand Report_RCC | 2026-02-20 | 2026-02-20 | 12-Mar-25 A | 21-Jul-25 A | 2027-01-20 | 16 | 2027-01-20
A9100 | Firewater Demand Report_IFA | 2026-02-20 | 2026-02-20 | 22-Jul-25 A | 06-Sep-25 A | 2027-01-20 | 3 | 2027-01-20
A9110 | Firewater Demand Report_RCA | 2026-02-20 | 2026-02-20 | 07-Sep-25 A | 13-Sep-25 A | 2027-01-20 | 16 | 2027-01-20
A47070 | Firewater Demand Report_IFD/IFC | 2026-02-20 | 2026-02-20 | 30-Oct-25 A | 03-Nov-25 A | 2027-01-20 | 2 | 2027-01-20
HAZID ENVID OHID Closeout Report |  | 2026-02-20 | 2026-03-17 | 01-Sep-25 A | 2026-03-17 | 2026-04-02 | 103 | 2027-01-20 | 221
A47330 | HAZID ENVID OHID Closeout Report_IFR | 2026-02-20 | 2026-02-20 | 01-Sep-25 A | 12-Sep-25 A | 2026-04-02 | 6 | 2026-04-02
A47340 | HAZID ENVID OHID Closeout Report_RCC | 2026-02-20 | 2026-02-20 | 05-Sep-25 A | 20-Sep-25 A | 2026-11-20 | 16 | 2026-11-20
A47350 | HAZID ENVID OHID Closeout Report_IFA | 2026-02-20 | 2026-02-20 | 28-Nov-25 A | 19-Dec-25 A | 2026-11-20 | 3 | 2026-11-20
A47360 | HAZID ENVID OHID Closeout Report_RCA | 2026-02-20 | 2026-03-13 | 2026-02-20 | 2026-03-13 | 2026-12-28 | 16 | 2027-01-18 | 221
A47370 | HAZID ENVID OHID Closeout Report_IFD/IFC | 2026-03-13 | 2026-03-17 | 2026-03-13 | 2026-03-17 | 2027-01-18 | 2 | 2027-01-20 | 221
Escape Route and Safety Signs Layouts (Plant) |  | 2026-02-20 | 2026-02-20 | 16-Apr-25 A | 23-Dec-25 A | 2026-04-20 | 222 | 2027-01-20
A46410 | Escape Route and Safety Signs Layouts (Plant)_IFR | 2026-02-20 | 2026-02-20 | 16-Apr-25 A | 07-May-25 A | 2026-04-20 | 6 | 2026-04-20
A46420 | Escape Route and Safety Signs Layouts (Plant)_RCC | 2026-02-20 | 2026-02-20 | 08-May-25 A | 21-Jun-25 A | 2027-01-20 | 16 | 2027-01-20
A46430 | Escape Route and Safety Signs Layouts (Plant)_IFA | 2026-02-20 | 2026-02-20 | 22-Jun-25 A | 28-Jul-25 A | 2027-01-20 | 3 | 2027-01-20
A46440 | Escape Route and Safety Signs Layouts (Plant)_RCA | 2026-02-20 | 2026-02-20 | 29-Jul-25 A | 30-Aug-25 A | 2027-01-20 | 16 | 2027-01-20
A46450 | Escape Route and Safety Signs Layouts (Plant)_IFD/IFC | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 23-Dec-25 A | 2027-01-20 | 2 | 2027-01-20
Fire & Gas Detectors Layouts (Plant) |  | 2026-02-20 | 2026-02-20 | 06-Apr-25 A | 23-Dec-25 A | 2026-04-20 | 222 | 2027-01-20
A46510 | Fire & Gas Detectors Layouts (Plant)_IFR | 2026-02-20 | 2026-02-20 | 06-Apr-25 A | 27-Apr-25 A | 2026-04-20 | 6 | 2026-04-20
A46520 | Fire & Gas Detectors Layouts (Plant)_RCC | 2026-02-20 | 2026-02-20 | 28-Apr-25 A | 21-Jun-25 A | 2027-01-20 | 16 | 2027-01-20
A46530 | Fire & Gas Detectors Layouts (Plant)_IFA | 2026-02-20 | 2026-02-20 | 22-Jun-25 A | 28-Jun-25 A | 2027-01-20 | 3 | 2027-01-20
A46540 | Fire & Gas Detectors Layouts (Plant)_RCA | 2026-02-20 | 2026-02-20 | 01-Sep-25 A | 07-Oct-25 A | 2027-01-20 | 16 | 2027-01-20
A46550 | Fire & Gas Detectors Layouts (Plant)_IFD/IFC | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 23-Dec-25 A | 2027-01-20 | 2 | 2027-01-20
Passive Fire Protection Layouts |  | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 23-Dec-25 A | 2027-01-20 | 245 | 2027-01-20
A46710 | Passive Fire Protection Layouts_IFR | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 29-Apr-25 A | 2027-01-20 | 6 | 2027-01-20
A46720 | Passive Fire Protection Layouts_RCC | 2026-02-20 | 2026-02-20 | 30-Apr-25 A | 21-Jun-25 A | 2027-01-20 | 16 | 2027-01-20
A46730 | Passive Fire Protection Layouts_IFA | 2026-02-20 | 2026-02-20 | 22-Jun-25 A | 29-Jul-25 A | 2027-01-20 | 3 | 2027-01-20
A46740 | Passive Fire Protection Layouts_RCA | 2026-02-20 | 2026-02-20 | 08-Sep-25 A | 07-Oct-25 A | 2027-01-20 | 16 | 2027-01-20
A46750 | Passive Fire Protection Layouts_IFD/IFC | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 23-Dec-25 A | 2027-01-20 | 2 | 2027-01-20
HAZOP Closeout Report |  | 2026-02-20 | 2026-02-20 | 01-Aug-25 A | 04-Sep-25 A | 2026-03-19 | 86 | 2026-03-19
A47430 | HAZOP Closeout Report_IFR | 2026-02-20 | 2026-02-20 | 01-Aug-25 A | 16-Aug-25 A | 2026-03-19 | 6 | 2026-03-19
A47440 | HAZOP Closeout Report_RCC | 2026-02-20 | 2026-02-20 | 04-Aug-25 A | 25-Aug-25 A | 2026-03-19 | 16 | 2026-03-19
A47450 | HAZOP Closeout Report_IFA | 2026-02-20 | 2026-02-20 | 25-Aug-25 A | 28-Aug-25 A | 2026-03-19 | 3 | 2026-03-19
A47460 | HAZOP Closeout Report_RCA | 2026-02-20 | 2026-02-20 | 29-Aug-25 A | 31-Aug-25 A | 2026-03-19 | 16 | 2026-03-19
A47470 | HAZOP Closeout Report_IFD/IFC | 2026-02-20 | 2026-02-20 | 01-Sep-25 A | 04-Sep-25 A | 2026-03-19 | 2 | 2026-03-19
Fire Protection and Safety Equipment Layouts (Plant) |  | 2026-02-20 | 2026-02-24 | 28-Mar-25 A | 2026-02-24 | 2026-04-20 | 267 | 2027-01-20 | 237
A46310 | Fire Protection and Safety Equipment Layouts (Plant)_IFR | 2026-02-20 | 2026-02-20 | 28-Mar-25 A | 21-Apr-25 A | 2026-04-20 | 6 | 2026-04-20
A46320 | Fire Protection and Safety Equipment Layouts (Plant)_RCC | 2026-02-20 | 2026-02-20 | 22-Apr-25 A | 21-Jun-25 A | 2027-01-18 | 16 | 2027-01-18
A46330 | Fire Protection and Safety Equipment Layouts (Plant)_IFA | 2026-02-20 | 2026-02-20 | 22-Jun-25 A | 28-Jul-25 A | 2027-01-18 | 3 | 2027-01-18
A46340 | Fire Protection and Safety Equipment Layouts (Plant)_RCA | 2026-02-20 | 2026-02-20 | 29-Jul-25 A | 30-Aug-25 A | 2027-01-18 | 16 | 2027-01-18
A46350 | Fire Protection and Safety Equipment Layouts (Plant)_IFD/IFC | 2026-02-20 | 2026-02-24 | 2026-02-20 | 2026-02-24 | 2027-01-18 | 2 | 2027-01-20 | 237
Firewater Hydraulic Report |  | 2026-02-20 | 2026-04-14 | 02-Jul-25 A | 2026-04-14 | 2026-11-30 | 212 | 2027-01-20 | 202
A47080 | Firewater Hydraulic Report_IFR | 2026-02-20 | 2026-02-20 | 02-Jul-25 A | 11-Jul-25 A | 2026-11-30 | 6 | 2026-11-30
A47090 | Firewater Hydraulic Report_RCC | 2026-02-20 | 2026-03-13 | 2026-02-20 | 2026-03-13 | 2026-11-30 | 16 | 2026-12-22 | 202
A47100 | Firewater Hydraulic Report_IFA | 2026-03-13 | 2026-03-19 | 2026-03-13 | 2026-03-19 | 2026-12-22 | 3 | 2026-12-25 | 202
A47110 | Firewater Hydraulic Report_RCA | 2026-03-19 | 2026-04-09 | 2026-03-19 | 2026-04-09 | 2026-12-28 | 16 | 2027-01-18 | 202
A47120 | Firewater Hydraulic Report_IFD/IFC | 2026-04-09 | 2026-04-14 | 2026-04-09 | 2026-04-14 | 2027-01-18 | 2 | 2027-01-20 | 202
Datasheets for Fire Protection and Safety Equipment |  | 2026-02-20 | 2026-02-20 | 17-Apr-25 A | 23-Dec-25 A | 2026-04-20 | 217 | 2026-06-12
A46860 | Datasheets for Fire Protection and Safety Equipment_IFR | 2026-02-20 | 2026-02-20 | 17-Apr-25 A | 08-May-25 A | 2026-04-20 | 6 | 2026-04-20
A46870 | Datasheets for Fire Protection and Safety Equipment_RCC | 2026-02-20 | 2026-02-20 | 09-May-25 A | 21-Jun-25 A | 2026-06-12 | 16 | 2026-06-12
A46880 | Datasheets for Fire Protection and Safety Equipment_IFA | 2026-02-20 | 2026-02-20 | 18-Aug-25 A | 25-Aug-25 A | 2026-06-12 | 3 | 2026-06-12
A46890 | Datasheets for Fire Protection and Safety Equipment_RCA | 2026-02-20 | 2026-02-20 | 01-Sep-25 A | 07-Oct-25 A | 2026-06-12 | 16 | 2026-06-12
A46900 | Datasheets for Fire Protection and Safety Equipment_IFD/IFC | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 23-Dec-25 A | 2026-06-12 | 2 | 2026-06-12
Fire Zone Layout |  | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 10-Sep-25 A | 2027-01-20 | 278 | 2027-01-20
A46260 | Fire Zone Layout_IFR | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 23-Apr-25 A | 2027-01-20 | 6 | 2027-01-20
A46270 | Fire Zone Layout_RCC | 2026-02-20 | 2026-02-20 | 24-Apr-25 A | 12-Aug-25 A | 2027-01-20 | 16 | 2027-01-20
A46280 | Fire Zone Layout_IFA | 2026-02-20 | 2026-02-20 | 13-Aug-25 A | 15-Aug-25 A | 2027-01-20 | 3 | 2027-01-20
A46290 | Fire Zone Layout_RCA | 2026-02-20 | 2026-02-20 | 16-Aug-25 A | 07-Sep-25 A | 2027-01-20 | 16 | 2027-01-20
A46300 | Fire Zone Layout_IFD/IFC | 2026-02-20 | 2026-02-20 | 08-Sep-25 A | 10-Sep-25 A | 2027-01-20 | 2 | 2027-01-20
Hazardous Area Classification Layouts |  | 2026-02-20 | 2026-02-20 | 06-Apr-25 A | 13-Jan-26 A | 2027-01-20 | 228 | 2027-01-20
A46210 | Hazardous Area Classification Layouts_IFR | 2026-02-20 | 2026-02-20 | 06-Apr-25 A | 27-Apr-25 A | 2027-01-20 | 6 | 2027-01-20
A46220 | Hazardous Area Classification Layouts_RCC | 2026-02-20 | 2026-02-20 | 28-Apr-25 A | 21-Jun-25 A | 2027-01-20 | 16 | 2027-01-20
A46230 | Hazardous Area Classification Layouts_IFA | 2026-02-20 | 2026-02-20 | 22-Jun-25 A | 29-Aug-25 A | 2027-01-20 | 3 | 2027-01-20
A46240 | Hazardous Area Classification Layouts_RCA | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 09-Jan-26 A | 2027-01-20 | 16 | 2027-01-20
A46250 | Hazardous Area Classification Layouts_IFD/IFC | 2026-02-20 | 2026-02-20 | 09-Jan-26 A | 13-Jan-26 A | 2027-01-20 | 2 | 2027-01-20
MR for Fire Protection and Safety Equipment |  | 2026-02-20 | 2026-02-20 | 14-May-25 A | 25-Dec-25 A | 2026-05-22 | 146 | 2026-06-12
A47180 | MR for Fire Protection and Safety Equipment_IFR | 2026-02-20 | 2026-02-20 | 04-Jun-25 A | 13-Jun-25 A | 2026-05-22 | 6 | 2026-05-22
A47190 | MR for Fire Protection and Safety Equipment_RCC | 2026-02-20 | 2026-02-20 | 14-May-25 A | 21-Jun-25 A | 2026-06-12 | 16 | 2026-06-12
A47200 | MR for Fire Protection and Safety Equipment_IFA | 2026-02-20 | 2026-02-20 | 23-Jun-25 A | 21-Jul-25 A | 2026-06-12 | 3 | 2026-06-12
A47210 | MR for Fire Protection and Safety Equipment_RCA | 2026-02-20 | 2026-02-20 | 01-Jul-25 A | 28-Jul-25 A | 2026-06-12 | 16 | 2026-06-12
A47220 | MR for Fire Protection and Safety Equipment_IFD/IFC | 2026-02-20 | 2026-02-20 | 23-Dec-25 A | 25-Dec-25 A | 2026-06-12 | 2 | 2026-06-12
Fire Water Layout |  | 2026-02-20 | 2026-02-20 | 17-Apr-25 A | 23-Dec-25 A | 2027-01-20 | 215 | 2027-01-20
A46910 | Fire Water Layout_IFR | 2026-02-20 | 2026-02-20 | 17-Apr-25 A | 08-May-25 A | 2027-01-20 | 6 | 2027-01-20
A46920 | Fire Water Layout_RCC | 2026-02-20 | 2026-02-20 | 09-May-25 A | 21-Jun-25 A | 2027-01-20 | 16 | 2027-01-20
A46930 | Fire Water Layout_IFA | 2026-02-20 | 2026-02-20 | 27-Jun-25 A | 21-Jul-25 A | 2027-01-20 | 3 | 2027-01-20
A46940 | Fire Water Layout_RCA | 2026-02-20 | 2026-02-20 | 01-Jul-25 A | 28-Jul-25 A | 2027-01-20 | 16 | 2027-01-20
A46950 | Fire Water Layout_IFD/IFC | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 23-Dec-25 A | 2027-01-20 | 2 | 2027-01-20
P&ID - Firewater Network |  | 2026-02-20 | 2026-04-14 | 21-Feb-25 A | 2026-04-14 | 2026-11-25 | 292 | 2027-01-18 | 200
A46960 | P&ID - Firewater Network_IFR | 2026-02-20 | 2026-02-20 | 21-Feb-25 A | 14-Mar-25 A | 2026-11-25 | 11 | 2026-11-25
A46970 | P&ID - Firewater Network_RCC | 2026-02-20 | 2026-03-13 | 2026-02-20 | 2026-03-13 | 2026-11-25 | 16 | 2026-12-17 | 199
A46980 | P&ID - Firewater Network_IFA | 2026-03-13 | 2026-03-19 | 2026-03-13 | 2026-03-19 | 2026-12-17 | 3 | 2026-12-22 | 199
A46990 | P&ID - Firewater Network_RCA | 2026-03-19 | 2026-04-09 | 2026-03-19 | 2026-04-09 | 2026-12-23 | 16 | 2027-01-14 | 200
A47000 | P&ID - Firewater Network_IFD/IFC | 2026-04-09 | 2026-04-14 | 2026-04-09 | 2026-04-14 | 2027-01-14 | 2 | 2027-01-18 | 200
P&ID - Deluge Spray System |  | 2026-02-20 | 2026-04-14 | 19-Apr-25 A | 2026-04-14 | 2026-11-26 | 223 | 2027-01-18 | 200
A47010 | P&ID - Deluge Spray System_IFR | 2026-02-20 | 2026-02-20 | 19-Apr-25 A | 10-May-25 A | 2026-11-26 | 11 | 2026-11-26
A47020 | P&ID - Deluge Spray System_RCC | 2026-02-20 | 2026-03-13 | 2026-02-20 | 2026-03-13 | 2026-11-26 | 16 | 2026-12-18 | 200
A47030 | P&ID - Deluge Spray System_IFA | 2026-03-13 | 2026-03-19 | 2026-03-13 | 2026-03-19 | 2026-12-18 | 3 | 2026-12-23 | 200
A47040 | P&ID - Deluge Spray System_RCA | 2026-03-19 | 2026-04-09 | 2026-03-19 | 2026-04-09 | 2026-12-23 | 16 | 2027-01-14 | 200
A47050 | P&ID - Deluge Spray System_IFD/IFC | 2026-04-09 | 2026-04-14 | 2026-04-09 | 2026-04-14 | 2027-01-14 | 2 | 2027-01-18 | 200
P&ID - Clean Agent System |  | 2026-02-20 | 2026-04-14 | 21-Feb-25 A | 2026-04-14 | 2026-11-26 | 292 | 2027-01-18 | 200
A47060 | P&ID - Clean Agent System_IFR | 2026-02-20 | 2026-02-20 | 21-Feb-25 A | 14-Mar-25 A | 2026-11-26 | 11 | 2026-11-26
A9040 | P&ID - Clean Agent System_RCC | 2026-02-20 | 2026-03-13 | 2026-02-20 | 2026-03-13 | 2026-11-26 | 16 | 2026-12-18 | 200
A9050 | P&ID - Clean Agent System_IFA | 2026-03-13 | 2026-03-19 | 2026-03-13 | 2026-03-19 | 2026-12-18 | 3 | 2026-12-23 | 200
A9060 | P&ID - Clean Agent System_RCA | 2026-03-19 | 2026-04-09 | 2026-03-19 | 2026-04-09 | 2026-12-23 | 16 | 2027-01-14 | 200
A9070 | P&ID - Clean Agent System_IFD/IFC | 2026-04-09 | 2026-04-14 | 2026-04-09 | 2026-04-14 | 2027-01-14 | 2 | 2027-01-18 | 200
ISD Closeout Report |  | 2026-02-20 | 2026-03-23 | 01-Oct-25 A | 2026-03-23 | 2026-12-22 | 106 | 2027-01-20 | 218
A47380 | ISD Closeout Report_IFR | 2026-02-20 | 2026-02-20 | 01-Oct-25 A | 09-Oct-25 A | 2026-12-22 | 6 | 2026-12-22
A47390 | ISD Closeout Report_RCC | 2026-02-20 | 2026-02-20 | 20-Oct-25 A | 17-Nov-25 A | 2026-12-22 | 16 | 2026-12-22
A47400 | ISD Closeout Report_IFA | 2026-02-20 | 2026-02-25 | 2026-02-20 | 2026-02-25 | 2026-12-22 | 3 | 2026-12-25 | 218
A47410 | ISD Closeout Report_RCA | 2026-02-25 | 2026-03-19 | 2026-02-25 | 2026-03-19 | 2026-12-28 | 16 | 2027-01-18 | 218
A47420 | ISD Closeout Report_IFD/IFC | 2026-03-19 | 2026-03-23 | 2026-03-19 | 2026-03-23 | 2027-01-18 | 2 | 2027-01-20 | 218
PHSER 3 Closeout Report |  | 2026-03-16 | 2026-05-14 | 2026-03-16 | 2026-05-14 | 2026-11-23 | 43 | 2027-01-20 | 179
A47480 | PHSER 3 Closeout Report_IFR | 2026-03-16 | 2026-03-24 | 2026-03-16 | 2026-03-24 | 2026-11-23 | 6 | 2026-11-30 | 179
A47490 | PHSER 3 Closeout Report_RCC | 2026-03-24 | 2026-04-15 | 2026-03-24 | 2026-04-15 | 2026-11-30 | 16 | 2026-12-22 | 179
A47500 | PHSER 3 Closeout Report_IFA | 2026-04-15 | 2026-04-20 | 2026-04-15 | 2026-04-20 | 2026-12-22 | 3 | 2026-12-25 | 179
A47510 | PHSER 3 Closeout Report_RCA | 2026-04-20 | 2026-05-12 | 2026-04-20 | 2026-05-12 | 2026-12-28 | 16 | 2027-01-18 | 179
A47520 | PHSER 3 Closeout Report_IFD/IFC | 2026-05-12 | 2026-05-14 | 2026-05-12 | 2026-05-14 | 2027-01-18 | 2 | 2027-01-20 | 179
HSE Action Tracking Register |  | 2026-02-20 | 2026-03-23 | 03-Nov-25 A | 2026-03-23 | 2026-12-22 | 71 | 2027-01-20 | 218
A47280 | HSE Action Tracking Register_IFR | 2026-02-20 | 2026-02-20 | 03-Nov-25 A | 17-Nov-25 A | 2026-12-22 | 6 | 2026-12-22
A47290 | HSE Action Tracking Register_RCC | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 09-Jan-26 A | 2026-12-22 | 16 | 2026-12-22
A47300 | HSE Action Tracking Register_IFA | 2026-02-20 | 2026-02-25 | 2026-02-20 | 2026-02-25 | 2026-12-22 | 3 | 2026-12-25 | 218
A47310 | HSE Action Tracking Register_RCA | 2026-02-25 | 2026-03-19 | 2026-02-25 | 2026-03-19 | 2026-12-28 | 16 | 2027-01-18 | 218
A47320 | HSE Action Tracking Register_IFD/IFC | 2026-03-19 | 2026-03-23 | 2026-03-19 | 2026-03-23 | 2027-01-18 | 2 | 2027-01-20 | 218
Electrical |  | 2026-02-20 | 2026-05-06 | 13-Dec-24 A | 2026-05-06 | 2026-03-02 | 365 | 2027-01-20 | 185
Scope Of Work For Cathodic Protection |  | 2026-02-20 | 2026-02-20 | 08-Aug-25 A | 23-Dec-25 A | 2026-05-15 | 97 | 2027-01-20
A10630 | Scope Of Work For Cathodic Protection_IFR | 2026-02-20 | 2026-02-20 | 08-Aug-25 A | 14-Aug-25 A | 2026-05-15 | 6 | 2026-05-15
A10640 | Scope Of Work For Cathodic Protection_RCC | 2026-02-20 | 2026-02-20 | 15-Aug-25 A | 19-Sep-25 A | 2026-05-15 | 16 | 2026-05-15
A10650 | Scope Of Work For Cathodic Protection_IFA | 2026-02-20 | 2026-02-20 | 03-Nov-25 A | 10-Nov-25 A | 2026-05-15 | 3 | 2026-05-15
A10660 | Scope Of Work For Cathodic Protection_RCA | 2026-02-20 | 2026-02-20 | 11-Nov-25 A | 20-Nov-25 A | 2027-01-20 | 16 | 2027-01-20
A10670 | Scope Of Work For Cathodic Protection_IFD/IFC | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 23-Dec-25 A | 2027-01-20 | 2 | 2027-01-20
Electrical System Operating Philosophy |  | 2026-02-20 | 2026-04-21 | 2026-02-20 | 2026-04-21 | 2026-11-23 | 43 | 2027-01-20 | 196
A47530 | Electrical System Operating Philosophy_IFR | 2026-02-20 | 2026-02-27 | 2026-02-20 | 2026-02-27 | 2026-11-23 | 6 | 2026-11-30 | 196
A47540 | Electrical System Operating Philosophy_RCC | 2026-02-27 | 2026-03-23 | 2026-02-27 | 2026-03-23 | 2026-11-30 | 16 | 2026-12-22 | 196
A47550 | Electrical System Operating Philosophy_IFA | 2026-03-23 | 2026-03-26 | 2026-03-23 | 2026-03-26 | 2026-12-22 | 3 | 2026-12-25 | 196
A47560 | Electrical System Operating Philosophy_RCA | 2026-03-26 | 2026-04-17 | 2026-03-26 | 2026-04-17 | 2026-12-28 | 16 | 2027-01-18 | 196
A47570 | Electrical System Operating Philosophy_IFD/IFC | 2026-04-17 | 2026-04-21 | 2026-04-17 | 2026-04-21 | 2027-01-18 | 2 | 2027-01-20 | 196
Technical Data Sheet For Transformer (Power and Distribution) |  | 2026-02-20 | 2026-02-20 | 23-Dec-24 A | 03-Jul-25 A | 2026-03-02 | 146 | 2026-03-02
A47580 | Technical Data Sheet For Transformer (Power and Distribution)_IFR | 2026-02-20 | 2026-02-20 | 23-Dec-24 A | 13-Jan-25 A | 2026-03-02 | 2 | 2026-03-02
A47590 | Technical Data Sheet For Transformer (Power and Distribution)_RCC | 2026-02-20 | 2026-02-20 | 14-Jan-25 A | 06-May-25 A | 2026-03-02 | 16 | 2026-03-02
A47600 | Technical Data Sheet For Transformer (Power and Distribution)_IFA | 2026-02-20 | 2026-02-20 | 07-May-25 A | 19-Jun-25 A | 2026-03-02 | 3 | 2026-03-02
A47610 | Technical Data Sheet For Transformer (Power and Distribution)_RCA | 2026-02-20 | 2026-02-20 | 20-Jun-25 A | 26-Jun-25 A | 2026-03-02 | 16 | 2026-03-02
A47620 | Technical Data Sheet For Transformer (Power and Distribution)_IFD/IFC | 2026-02-20 | 2026-02-20 | 27-Jun-25 A | 03-Jul-25 A | 2026-03-02 | 2 | 2026-03-02
Technical Data Sheet For LV Motors |  | 2026-02-20 | 2026-02-20 | 01-Jan-25 A | 03-May-25 A | 2026-03-02 | 106 | 2027-01-20
A47630 | Technical Data Sheet For LV Motors_IFR | 2026-02-20 | 2026-02-20 | 01-Jan-25 A | 22-Jan-25 A | 2026-03-02 | 2 | 2026-03-02
A9840 | Technical Data Sheet For LV Motors_RCC | 2026-02-20 | 2026-02-20 | 23-Jan-25 A | 28-Feb-25 A | 2027-01-20 | 16 | 2027-01-20
A9850 | Technical Data Sheet For LV Motors_IFA | 2026-02-20 | 2026-02-20 | 01-Mar-25 A | 19-Apr-25 A | 2027-01-20 | 3 | 2027-01-20
A9860 | Technical Data Sheet For LV Motors_RCA | 2026-02-20 | 2026-02-20 | 20-Apr-25 A | 26-Apr-25 A | 2027-01-20 | 16 | 2027-01-20
A9870 | Technical Data Sheet For LV Motors_IFD/IFC | 2026-02-20 | 2026-02-20 | 27-Apr-25 A | 03-May-25 A | 2027-01-20 | 2 | 2027-01-20
Technical Data Sheet For Emergency Diesel Generator |  | 2026-02-20 | 2026-02-20 | 09-Jan-25 A | 10-Sep-25 A | 2026-03-02 | 208 | 2026-03-02
A9880 | Technical Data Sheet For Emergency Diesel Generator_IFR | 2026-02-20 | 2026-02-20 | 09-Jan-25 A | 02-Mar-25 A | 2026-03-02 | 2 | 2026-03-02
A9890 | Technical Data Sheet For Emergency Diesel Generator_RCC | 2026-02-20 | 2026-02-20 | 03-Mar-25 A | 02-May-25 A | 2026-03-02 | 16 | 2026-03-02
A9900 | Technical Data Sheet For Emergency Diesel Generator_IFA | 2026-02-20 | 2026-02-20 | 03-May-25 A | 16-May-25 A | 2026-03-02 | 3 | 2026-03-02
A9910 | Technical Data Sheet For Emergency Diesel Generator_RCA | 2026-02-20 | 2026-02-20 | 19-Aug-25 A | 08-Sep-25 A | 2026-03-02 | 16 | 2026-03-02
A9920 | Technical Data Sheet For Emergency Diesel Generator_IFD/IFC | 2026-02-20 | 2026-02-20 | 09-Sep-25 A | 10-Sep-25 A | 2026-03-02 | 2 | 2026-03-02
Technical Data Sheet For Intergrated Protection Control Panel |  | 2026-02-20 | 2026-02-20 | 01-May-25 A | 06-Jun-25 A | 2026-03-02 | 97 | 2026-03-02
A58390 | Technical Data Sheet For IPCS_IFR | 2026-02-20 | 2026-02-20 | 01-May-25 A | 05-May-25 A | 2026-03-02 | 2 | 2026-03-02
A58400 | Technical Data Sheet For IPCS_RCC | 2026-02-20 | 2026-02-20 | 06-May-25 A | 16-May-25 A | 2026-03-02 | 16 | 2026-03-02
A58410 | Technical Data Sheet For IPCS_IFA | 2026-02-20 | 2026-02-20 | 19-May-25 A | 23-May-25 A | 2026-03-02 | 3 | 2026-03-02
A58420 | Technical Data Sheet For IPCS_RCA | 2026-02-20 | 2026-02-20 | 26-May-25 A | 30-May-25 A | 2026-03-02 | 16 | 2026-03-02
A58430 | Technical Data Sheet For IPCS_IFD/IFC | 2026-02-20 | 2026-02-20 | 02-Jun-25 A | 06-Jun-25 A | 2026-03-02 | 2 | 2026-03-02
Technical Data Sheet For SCMS |  | 2026-02-20 | 2026-02-20 | 05-May-25 A | 13-Jun-25 A | 2026-03-02 | 97 | 2026-03-02
A59900 | Technical Data Sheet For SCMS_IFR | 2026-02-20 | 2026-02-20 | 05-May-25 A | 09-May-25 A | 2026-03-02 | 2 | 2026-03-02
A59910 | Technical Data Sheet For SCMS_RCC | 2026-02-20 | 2026-02-20 | 12-May-25 A | 23-May-25 A | 2026-03-02 | 16 | 2026-03-02
A59920 | Technical Data Sheet For SCMS_IFA | 2026-02-20 | 2026-02-20 | 26-May-25 A | 30-May-25 A | 2026-03-02 | 3 | 2026-03-02
A59930 | Technical Data Sheet For SCMS_RCA | 2026-02-20 | 2026-02-20 | 02-Jun-25 A | 06-Jun-25 A | 2026-03-02 | 16 | 2026-03-02
A59940 | Technical Data Sheet For SCMS_IFD/IFC | 2026-02-20 | 2026-02-20 | 09-Jun-25 A | 13-Jun-25 A | 2026-03-02 | 2 | 2026-03-02
Technical Data Sheet For 11KV Switchgear |  | 2026-02-20 | 2026-02-20 | 19-Dec-24 A | 21-Jun-25 A | 2026-03-02 | 140 | 2026-03-02
A9930 | Technical Data Sheet For 11KV Switchgear_IFR | 2026-02-20 | 2026-02-20 | 19-Dec-24 A | 09-Jan-25 A | 2026-03-02 | 2 | 2026-03-02
A9940 | Technical Data Sheet For 11KV Switchgear_RCC | 2026-02-20 | 2026-02-20 | 10-Jan-25 A | 14-Feb-25 A | 2026-03-02 | 16 | 2026-03-02
A47640 | Technical Data Sheet For 11KV Switchgear_IFA | 2026-02-20 | 2026-02-20 | 15-Feb-25 A | 21-Mar-25 A | 2026-03-02 | 3 | 2026-03-02
A9960 | Technical Data Sheet For 11KV Switchgear_RCA | 2026-02-20 | 2026-02-20 | 22-Mar-25 A | 02-Jun-25 A | 2026-03-02 | 16 | 2026-03-02
A9970 | Technical Data Sheet For 11KV Switchgear_IFD/IFC | 2026-02-20 | 2026-02-20 | 03-Jun-25 A | 21-Jun-25 A | 2026-03-02 | 2 | 2026-03-02
Technical Data Sheet For LV Switchgear |  | 2026-02-20 | 2026-02-20 | 27-Dec-24 A | 11-May-25 A | 2026-03-02 | 127 | 2026-03-02
A9980 | Technical Data Sheet For LV Switchgear_IFR | 2026-02-20 | 2026-02-20 | 27-Dec-24 A | 17-Jan-25 A | 2026-03-02 | 2 | 2026-03-02
A9990 | Technical Data Sheet For LV Switchgear_RCC | 2026-02-20 | 2026-02-20 | 18-Jan-25 A | 20-Apr-25 A | 2026-03-02 | 16 | 2026-03-02
A10000 | Technical Data Sheet For LV Switchgear_IFA | 2026-02-20 | 2026-02-20 | 21-Apr-25 A | 27-Apr-25 A | 2026-03-02 | 3 | 2026-03-02
A10010 | Technical Data Sheet For LV Switchgear_RCA | 2026-02-20 | 2026-02-20 | 28-Apr-25 A | 04-May-25 A | 2026-03-02 | 16 | 2026-03-02
A10020 | Technical Data Sheet For LV Switchgear_IFD/IFC | 2026-02-20 | 2026-02-20 | 06-May-25 A | 11-May-25 A | 2026-03-02 | 2 | 2026-03-02
Technical Data Sheet For LV Variable Frequency Drive |  | 2026-02-20 | 2026-02-20 | 31-Jan-25 A | 05-Jul-25 A | 2026-03-02 | 145 | 2026-03-02
A10030 | Technical Data Sheet For LV Variable Frequency Drive_IFR | 2026-02-20 | 2026-02-20 | 31-Jan-25 A | 21-Feb-25 A | 2026-03-02 | 2 | 2026-03-02
A10040 | Technical Data Sheet For LV Variable Frequency Drive_RCC | 2026-02-20 | 2026-02-20 | 22-Feb-25 A | 20-Apr-25 A | 2026-03-02 | 16 | 2026-03-02
A10050 | Technical Data Sheet For LV Variable Frequency Drive_IFA | 2026-02-20 | 2026-02-20 | 21-Apr-25 A | 21-Jun-25 A | 2026-03-02 | 3 | 2026-03-02
A10060 | Technical Data Sheet For LV Variable Frequency Drive_RCA | 2026-02-20 | 2026-02-20 | 22-Jun-25 A | 28-Jun-25 A | 2026-03-02 | 16 | 2026-03-02
A10070 | Technical Data Sheet For LV Variable Frequency Drive_IFD/IFC | 2026-02-20 | 2026-02-20 | 29-Jun-25 A | 05-Jul-25 A | 2026-03-02 | 2 | 2026-03-02
Technical Data Sheet For Neutral Earthing Resistor |  | 2026-02-20 | 2026-02-20 | 19-Dec-24 A | 21-Jun-25 A | 2026-03-02 | 133 | 2026-03-02
A10080 | Technical Data Sheet For Neutral Earthing Resistor_IFR | 2026-02-20 | 2026-02-20 | 19-Dec-24 A | 09-Jan-25 A | 2026-03-02 | 2 | 2026-03-02
A10090 | Technical Data Sheet For Neutral Earthing Resistor_RCC | 2026-02-20 | 2026-02-20 | 10-Jan-25 A | 21-Feb-25 A | 2026-03-02 | 16 | 2026-03-02
A10100 | Technical Data Sheet For Neutral Earthing Resistor_IFA | 2026-02-20 | 2026-02-20 | 22-Feb-25 A | 06-Mar-25 A | 2026-03-02 | 3 | 2026-03-02
A10110 | Technical Data Sheet For Neutral Earthing Resistor_RCA | 2026-02-20 | 2026-02-20 | 07-Mar-25 A | 29-May-25 A | 2026-03-02 | 16 | 2026-03-02
A10120 | Technical Data Sheet For Neutral Earthing Resistor_IFD/IFC | 2026-02-20 | 2026-02-20 | 30-May-25 A | 21-Jun-25 A | 2026-03-02 | 2 | 2026-03-02
Technical Data Sheet For Interposting Relay Panel |  | 2026-02-20 | 2026-02-20 | 01-Aug-25 A | 17-Sep-25 A | 2026-04-28 | 39 | 2027-01-20
A58240 | Technical Data Sheet For Interpopsting Relay Panel _IFR | 2026-02-20 | 2026-02-20 | 01-Aug-25 A | 08-Aug-25 A | 2026-04-28 | 2 | 2026-04-28
A58250 | Technical Data Sheet For Interpopsting Relay Panel_RCC | 2026-02-20 | 2026-02-20 | 11-Aug-25 A | 22-Aug-25 A | 2027-01-20 | 16 | 2027-01-20
A58260 | Technical Data Sheet For Interpopsting Relay Panel_IFA | 2026-02-20 | 2026-02-20 | 25-Aug-25 A | 29-Aug-25 A | 2027-01-20 | 3 | 2027-01-20
A58270 | Technical Data Sheet For Interpopsting Relay Panel_RCA | 2026-02-20 | 2026-02-20 | 01-Sep-25 A | 12-Sep-25 A | 2027-01-20 | 16 | 2027-01-20
A58280 | Technical Data Sheet For Interpopsting Relay Panel_IFD/IFC | 2026-02-20 | 2026-02-20 | 15-Sep-25 A | 17-Sep-25 A | 2027-01-20 | 2 | 2027-01-20
Technical Data Sheet For Power, Control And Earthing Cables |  | 2026-02-20 | 2026-02-20 | 10-Jan-25 A | 05-Sep-25 A | 2026-03-19 | 201 | 2026-03-19
A10130 | Technical Data Sheet For Power, Control And Earthing Cables_IFR | 2026-02-20 | 2026-02-20 | 10-Jan-25 A | 20-Apr-25 A | 2026-03-19 | 2 | 2026-03-19
A10140 | Technical Data Sheet For Power, Control And Earthing Cables_RCC | 2026-02-20 | 2026-02-20 | 21-Apr-25 A | 19-May-25 A | 2026-03-19 | 16 | 2026-03-19
A10150 | Technical Data Sheet For Power, Control And Earthing Cables_IFA | 2026-02-20 | 2026-02-20 | 20-May-25 A | 11-Jun-25 A | 2026-03-19 | 3 | 2026-03-19
A10160 | Technical Data Sheet For Power, Control And Earthing Cables_RCA | 2026-02-20 | 2026-02-20 | 25-Aug-25 A | 29-Aug-25 A | 2026-03-19 | 16 | 2026-03-19
A10170 | Technical Data Sheet For Power, Control And Earthing Cables_IFD/IFC | 2026-02-20 | 2026-02-20 | 01-Sep-25 A | 05-Sep-25 A | 2026-03-19 | 2 | 2026-03-19
Technical Data Sheet For Direct Current UPS System |  | 2026-02-20 | 2026-02-20 | 01-Jan-25 A | 21-Jun-25 A | 2026-03-02 | 103 | 2026-03-02
A10180 | Technical Data Sheet For Direct Current UPS System_IFR | 2026-02-20 | 2026-02-20 | 01-Jan-25 A | 22-Jan-25 A | 2026-03-02 | 2 | 2026-03-02
A10190 | Technical Data Sheet For Direct Current UPS System_RCC | 2026-02-20 | 2026-02-20 | 23-Jan-25 A | 07-Mar-25 A | 2026-03-02 | 16 | 2026-03-02
A10200 | Technical Data Sheet For Direct Current UPS System_IFA | 2026-02-20 | 2026-02-20 | 08-Mar-25 A | 21-Mar-25 A | 2026-03-02 | 3 | 2026-03-02
A10210 | Technical Data Sheet For Direct Current UPS System_RCA | 2026-02-20 | 2026-02-20 | 22-Mar-25 A | 02-Jun-25 A | 2026-03-02 | 16 | 2026-03-02
A10220 | Technical Data Sheet For Direct Current UPS System_IFD/IFC | 2026-02-20 | 2026-02-20 | 03-Jun-25 A | 21-Jun-25 A | 2026-03-02 | 2 | 2026-03-02
Technical Data Sheet For Static AC UPS System |  | 2026-02-20 | 2026-02-20 | 27-Dec-24 A | 28-Jun-25 A | 2026-03-02 | 27 | 2026-03-02
A10230 | Technical Data Sheet For Static AC UPS System_IFR | 2026-02-20 | 2026-02-20 | 27-Dec-24 A | 17-Jan-25 A | 2026-03-02 | 2 | 2026-03-02
A10240 | Technical Data Sheet For Static AC UPS System_RCC | 2026-02-20 | 2026-02-20 | 18-Jan-25 A | 18-Feb-25 A | 2026-03-02 | 16 | 2026-03-02
A10250 | Technical Data Sheet For Static AC UPS System_IFA | 2026-02-20 | 2026-02-20 | 19-Feb-25 A | 12-Jun-25 A | 2026-03-02 | 3 | 2026-03-02
A10260 | Technical Data Sheet For Static AC UPS System_RCA | 2026-02-20 | 2026-02-20 | 13-Jun-25 A | 21-Jun-25 A | 2026-03-02 | 16 | 2026-03-02
A10270 | Technical Data Sheet For Static AC UPS System_IFD/IFC | 2026-02-20 | 2026-02-20 | 22-Jun-25 A | 28-Jun-25 A | 2026-03-02 | 2 | 2026-03-02
Technical Data Sheet For Power Factor Correction Capacitor |  | 2026-02-20 | 2026-02-20 | 20-Jan-25 A | 28-Aug-25 A | 2026-03-02 | 191 | 2026-03-02
A10280 | Technical Data Sheet For Power Factor Correction Capacitor_IFR | 2026-02-20 | 2026-02-20 | 20-Jan-25 A | 21-Feb-25 A | 2026-03-02 | 2 | 2026-03-02
A10290 | Technical Data Sheet For Power Factor Correction Capacitor_RCC | 2026-02-20 | 2026-02-20 | 19-Jul-25 A | 08-Aug-25 A | 2026-03-02 | 16 | 2026-03-02
A10300 | Technical Data Sheet For Power Factor Correction Capacitor_IFA | 2026-02-20 | 2026-02-20 | 09-Aug-25 A | 12-Aug-25 A | 2026-03-02 | 3 | 2026-03-02
A10310 | Technical Data Sheet For Power Factor Correction Capacitor_RCA | 2026-02-20 | 2026-02-20 | 12-Aug-25 A | 26-Aug-25 A | 2026-03-02 | 16 | 2026-03-02
A10320 | Technical Data Sheet For Power Factor Correction Capacitor_IFD/IFC | 2026-02-20 | 2026-02-20 | 26-Aug-25 A | 28-Aug-25 A | 2026-03-02 | 2 | 2026-03-02
Neutral Earthing Resistor Sizing Calculation |  | 2026-02-20 | 2026-02-20 | 13-Dec-24 A | 13-May-25 A | 2026-04-02 | 134 | 2027-01-20
A10380 | Neutral Earthing Resistor Sizing Calculation_IFR | 2026-02-20 | 2026-02-20 | 13-Dec-24 A | 09-Jan-25 A | 2026-04-02 | 6 | 2026-04-02
A10390 | Neutral Earthing Resistor Sizing Calculation_RCC | 2026-02-20 | 2026-02-20 | 10-Jan-25 A | 21-Feb-25 A | 2027-01-20 | 16 | 2027-01-20
A10400 | Neutral Earthing Resistor Sizing Calculation_IFA | 2026-02-20 | 2026-02-20 | 22-Feb-25 A | 12-Mar-25 A | 2027-01-20 | 3 | 2027-01-20
A10410 | Neutral Earthing Resistor Sizing Calculation_RCA | 2026-02-20 | 2026-02-20 | 13-Mar-25 A | 06-May-25 A | 2027-01-20 | 16 | 2027-01-20
A10420 | Neutral Earthing Resistor Sizing Calculation_IFD/IFC | 2026-02-20 | 2026-02-20 | 07-May-25 A | 13-May-25 A | 2027-01-20 | 2 | 2027-01-20
Interposting Relay Panel Sizing Calculation |  | 2026-02-20 | 2026-04-21 | 2026-02-20 | 2026-04-21 | 2026-05-14 | 43 | 2027-01-20 | 196
A58290 | Interpopsting Relay Panel Sizing Calculation_IFR | 2026-02-20 | 2026-02-27 | 2026-02-20 | 2026-02-27 | 2026-05-14 | 6 | 2026-05-22 | 60
A58300 | Interpopsting Relay Panel Sizing Calculation_RCC | 2026-02-27 | 2026-03-23 | 2026-02-27 | 2026-03-23 | 2026-05-22 | 16 | 2026-06-15 | 60
A58310 | Interpopsting Relay Panel Sizing Calculation_IFA | 2026-03-23 | 2026-03-26 | 2026-03-23 | 2026-03-26 | 2026-06-15 | 3 | 2026-06-18 | 60
A58320 | Interpopsting Relay Panel Sizing Calculation_RCA | 2026-03-26 | 2026-04-17 | 2026-03-26 | 2026-04-17 | 2026-12-28 | 16 | 2027-01-18 | 196
A58330 | Interpopsting Relay Panel Sizing Calculation_IFD/IFC | 2026-04-17 | 2026-04-21 | 2026-04-17 | 2026-04-21 | 2027-01-18 | 2 | 2027-01-20 | 196
Transformer Sizing Calculation |  | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 28-Jun-25 A | 2026-03-02 | 151 | 2027-01-20
A10680 | Transformer Sizing Calculation_IFR | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 06-Apr-25 A | 2026-03-02 | 6 | 2026-03-02
A10690 | Transformer Sizing Calculation_RCC | 2026-02-20 | 2026-02-20 | 30-Mar-25 A | 13-Apr-25 A | 2027-01-20 | 16 | 2027-01-20
A10700 | Transformer Sizing Calculation_IFA | 2026-02-20 | 2026-02-20 | 14-Apr-25 A | 20-Apr-25 A | 2027-01-20 | 3 | 2027-01-20
A10710 | Transformer Sizing Calculation_RCA | 2026-02-20 | 2026-02-20 | 21-Apr-25 A | 21-Jun-25 A | 2027-01-20 | 16 | 2027-01-20
A10720 | Transformer Sizing Calculation_IFD/IFC | 2026-02-20 | 2026-02-20 | 22-Jun-25 A | 28-Jun-25 A | 2027-01-20 | 2 | 2027-01-20
Electrical Load List - EU3 H2 Extraction Unit |  | 2026-02-20 | 2026-02-20 | 19-Dec-24 A | 30-Apr-25 A | 2026-03-02 | 227 | 2026-03-27
A10330 | Electrical Load List - EU3 H2 Extraction Unit_IFR | 2026-02-20 | 2026-02-20 | 19-Dec-24 A | 09-Jan-25 A | 2026-03-02 | 6 | 2026-03-02
A10340 | Electrical Load List - EU3 H2 Extraction Unit_RCC | 2026-02-20 | 2026-02-20 | 10-Jan-25 A | 18-Feb-25 A | 2026-03-02 | 16 | 2026-03-02
A10350 | Electrical Load List - EU3 H2 Extraction Unit_IFA | 2026-02-20 | 2026-02-20 | 25-Feb-25 A | 13-Mar-25 A | 2026-03-27 | 3 | 2026-03-27
A10360 | Electrical Load List - EU3 H2 Extraction Unit_RCA | 2026-02-20 | 2026-02-20 | 14-Mar-25 A | 29-Apr-25 A | 2026-03-27 | 16 | 2026-03-27
A10370 | Electrical Load List - EU3 H2 Extraction Unit_IFD/IFC | 2026-02-20 | 2026-02-20 | 30-Apr-25 A | 30-Apr-25 A | 2026-03-27 | 2 | 2026-03-27
Electrical Load Summary for Utilities & Offsites Area |  | 2026-02-20 | 2026-02-20 | 14-Feb-25 A | 19-Jan-26 A | 2026-03-27 | 280 | 2026-03-27
A55790 | Electrical Load Summary for Utilities & Offsites Area_IFR | 2026-02-20 | 2026-02-20 | 14-Feb-25 A | 20-Mar-25 A | 2026-03-27 | 6 | 2026-03-27
A55800 | Electrical Load Summary for Utilities & Offsites Area_RCC | 2026-02-20 | 2026-02-20 | 30-Sep-25 A | 16-Oct-25 A | 2026-03-27 | 16 | 2026-03-27
A55810 | Electrical Load Summary for Utilities & Offsites Area_IFA | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 24-Dec-25 A | 2026-03-27 | 3 | 2026-03-27
A55820 | Electrical Load Summary for Utilities & Offsites Area_RCA | 2026-02-20 | 2026-02-20 | 24-Dec-25 A | 15-Jan-26 A | 2026-03-27 | 16 | 2026-03-27
A28320 | Electrical Load Summary for Utilities & Offsites Area_IFD/IFC | 2026-02-20 | 2026-02-20 | 15-Jan-26 A | 19-Jan-26 A | 2026-03-27 | 2 | 2026-03-27
AC UPS Sizing Calculation |  | 2026-02-20 | 2026-02-20 | 01-Aug-25 A | 23-Dec-25 A | 2026-04-02 | 266 | 2027-01-20
A10930 | AC UPS Sizing Calculation_IFR | 2026-02-20 | 2026-02-20 | 01-Aug-25 A | 15-Aug-25 A | 2026-04-02 | 6 | 2026-04-02
A10940 | AC UPS Sizing Calculation_RCC | 2026-02-20 | 2026-02-20 | 04-Aug-25 A | 22-Aug-25 A | 2027-01-20 | 16 | 2027-01-20
A10950 | AC UPS Sizing Calculation_IFA | 2026-02-20 | 2026-02-20 | 17-Sep-25 A | 09-Oct-25 A | 2027-01-20 | 3 | 2027-01-20
A10960 | AC UPS Sizing Calculation_RCA | 2026-02-20 | 2026-02-20 | 24-Sep-25 A | 16-Oct-25 A | 2027-01-20 | 16 | 2027-01-20
A10970 | AC UPS Sizing Calculation_IFD/IFC | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 23-Dec-25 A | 2027-01-20 | 2 | 2027-01-20
DC UPS Sizing Calculation |  | 2026-02-20 | 2026-02-20 | 30-Mar-25 A | 23-Dec-25 A | 2026-04-02 | 261 | 2027-01-20
A10980 | DC UPS Sizing Calculation_IFR | 2026-02-20 | 2026-02-20 | 30-Mar-25 A | 13-Apr-25 A | 2026-04-02 | 6 | 2026-04-02
A10990 | DC UPS Sizing Calculation_RCC | 2026-02-20 | 2026-02-20 | 01-Apr-25 A | 20-Apr-25 A | 2027-01-20 | 16 | 2027-01-20
A11000 | DC UPS Sizing Calculation_IFA | 2026-02-20 | 2026-02-20 | 21-Apr-25 A | 27-Apr-25 A | 2027-01-20 | 3 | 2027-01-20
A11010 | DC UPS Sizing Calculation_RCA | 2026-02-20 | 2026-02-20 | 15-May-25 A | 21-Jun-25 A | 2027-01-20 | 16 | 2027-01-20
A11020 | DC UPS Sizing Calculation_IFD/IFC | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 23-Dec-25 A | 2027-01-20 | 2 | 2027-01-20
EDG Sizing Calculation |  | 2026-02-20 | 2026-02-20 | 19-Dec-24 A | 28-Jun-25 A | 2026-03-02 | 166 | 2027-01-20
A11030 | EDG Sizing Calculation_IFR | 2026-02-20 | 2026-02-20 | 19-Dec-24 A | 09-Jan-25 A | 2026-03-02 | 6 | 2026-03-02
A11040 | EDG Sizing Calculation_RCC | 2026-02-20 | 2026-02-20 | 10-Jan-25 A | 20-Feb-25 A | 2027-01-20 | 16 | 2027-01-20
A11050 | EDG Sizing Calculation_IFA | 2026-02-20 | 2026-02-20 | 21-Feb-25 A | 20-Apr-25 A | 2027-01-20 | 3 | 2027-01-20
A11060 | EDG Sizing Calculation_RCA | 2026-02-20 | 2026-02-20 | 21-Apr-25 A | 21-Jun-25 A | 2027-01-20 | 16 | 2027-01-20
A11070 | EDG Sizing Calculation_IFD/IFC | 2026-02-20 | 2026-02-20 | 22-Jun-25 A | 28-Jun-25 A | 2027-01-20 | 2 | 2027-01-20
IO List For IPCS |  | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 18-Sep-25 A | 2027-01-20 | 192 | 2027-01-20
A11080 | IO List For IPCS_IFR | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 06-Apr-25 A | 2027-01-20 | 6 | 2027-01-20
A11090 | IO List For IPCS_RCC | 2026-02-20 | 2026-02-20 | 01-Apr-25 A | 13-Apr-25 A | 2027-01-20 | 16 | 2027-01-20
A11100 | IO List For IPCS_IFA | 2026-02-20 | 2026-02-20 | 14-Apr-25 A | 20-Apr-25 A | 2027-01-20 | 3 | 2027-01-20
A11110 | IO List For IPCS_RCA | 2026-02-20 | 2026-02-20 | 30-Apr-25 A | 21-Jun-25 A | 2027-01-20 | 16 | 2027-01-20
A11120 | IO List For IPCS_IFD/IFC | 2026-02-20 | 2026-02-20 | 22-Jun-25 A | 18-Sep-25 A | 2027-01-20 | 2 | 2027-01-20
IO List For SCMS |  | 2026-02-20 | 2026-02-20 | 24-Jan-25 A | 23-Dec-25 A | 2027-01-20 | 192 | 2027-01-20
A11130 | IO List For SCMS_IFR | 2026-02-20 | 2026-02-20 | 24-Jan-25 A | 24-Feb-25 A | 2027-01-20 | 6 | 2027-01-20
A11140 | IO List For SCMS_RCC | 2026-02-20 | 2026-02-20 | 25-Feb-25 A | 20-Apr-25 A | 2027-01-20 | 16 | 2027-01-20
A11150 | IO List For SCMS_IFA | 2026-02-20 | 2026-02-20 | 21-Apr-25 A | 27-Apr-25 A | 2027-01-20 | 3 | 2027-01-20
A11160 | IO List For SCMS_RCA | 2026-02-20 | 2026-02-20 | 21-Apr-25 A | 21-Jun-25 A | 2027-01-20 | 16 | 2027-01-20
A11170 | IO List For SCMS_IFD/IFC | 2026-02-20 | 2026-02-20 | 22-Jun-25 A | 23-Dec-25 A | 2027-01-20 | 2 | 2027-01-20
Power System Study Report - ARC Flash, Harmonics Resonance |  | 2026-02-20 | 2026-02-20 | 18-Jul-25 A | 23-Dec-25 A | 2026-03-02 | 112 | 2027-01-20
A11230 | Power System Study Report - ARC Flash, Harmonics Resonance_IFR | 2026-02-20 | 2026-02-20 | 18-Jul-25 A | 11-Aug-25 A | 2026-03-02 | 6 | 2026-03-02
A11240 | Power System Study Report - ARC Flash, Harmonics Resonance_RCC | 2026-02-20 | 2026-02-20 | 12-Aug-25 A | 28-Aug-25 A | 2027-01-20 | 16 | 2027-01-20
A11250 | Power System Study Report - ARC Flash, Harmonics Resonance_IFA | 2026-02-20 | 2026-02-20 | 04-Sep-25 A | 10-Oct-25 A | 2027-01-20 | 3 | 2027-01-20
A11260 | Power System Study Report - ARC Flash, Harmonics Resonance_RCA | 2026-02-20 | 2026-02-20 | 20-Sep-25 A | 17-Oct-25 A | 2027-01-20 | 16 | 2027-01-20
A11270 | Power System Study Report - ARC Flash, Harmonics Resonance_IFD/IFC | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 23-Dec-25 A | 2027-01-20 | 2 | 2027-01-20
Power System Study Report - Load Flow, Short Circuit and Motor Starting |  | 2026-02-20 | 2026-02-20 | 28-Apr-25 A | 23-Dec-25 A | 2026-03-02 | 165 | 2027-01-20
A11180 | Power System Study Report - Load Flow, Short Circuit and Motor Starting_IFR | 2026-02-20 | 2026-02-20 | 28-Apr-25 A | 19-May-25 A | 2026-03-02 | 6 | 2026-03-02
A11190 | Power System Study Report - Load Flow, Short Circuit and Motor Starting_RCC | 2026-02-20 | 2026-02-20 | 25-Jun-25 A | 25-Jul-25 A | 2027-01-20 | 16 | 2027-01-20
A11200 | Power System Study Report - Load Flow, Short Circuit and Motor Starting_IFA | 2026-02-20 | 2026-02-20 | 26-Jul-25 A | 28-Aug-25 A | 2027-01-20 | 3 | 2027-01-20
A11210 | Power System Study Report - Load Flow, Short Circuit and Motor Starting_RCA | 2026-02-20 | 2026-02-20 | 20-Aug-25 A | 04-Sep-25 A | 2027-01-20 | 16 | 2027-01-20
A11220 | Power System Study Report - Load Flow, Short Circuit and Motor Starting_IFD/IFC | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 23-Dec-25 A | 2027-01-20 | 2 | 2027-01-20
PSCAD Study Report - Transient Stability And Insulation Coordination |  | 2026-02-20 | 2026-02-20 | 01-May-25 A | 23-Dec-25 A | 2026-11-23 | 160 | 2027-01-20
A11280 | Pscad Study Report - Transient Stability And Insulation Coordination_IFR | 2026-02-20 | 2026-02-20 | 01-May-25 A | 22-May-25 A | 2026-11-23 | 6 | 2026-11-23
A11290 | Pscad Study Report - Transient Stability And Insulation Coordination_RCC | 2026-02-20 | 2026-02-20 | 11-Jun-25 A | 25-Jul-25 A | 2027-01-20 | 16 | 2027-01-20
A11300 | Pscad Study Report - Transient Stability And Insulation Coordination_IFA | 2026-02-20 | 2026-02-20 | 31-Jul-25 A | 26-Sep-25 A | 2027-01-20 | 3 | 2027-01-20
A11310 | Pscad Study Report - Transient Stability And Insulation Coordination_RCA | 2026-02-20 | 2026-02-20 | 10-Sep-25 A | 03-Oct-25 A | 2027-01-20 | 16 | 2027-01-20
A11320 | Pscad Study Report - Transient Stability And Insulation Coordination_IFD/IFC | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 23-Dec-25 A | 2027-01-20 | 2 | 2027-01-20
Power System Study Report - Protection Coordination and Relay Setting |  | 2026-02-20 | 2026-04-21 | 2026-02-20 | 2026-04-21 | 2026-11-23 | 43 | 2027-01-20 | 196
A11330 | Power System Study Report - Protection Coordination and Relay Setting_IFR | 2026-02-20 | 2026-02-27 | 2026-02-20 | 2026-02-27 | 2026-11-23 | 6 | 2026-11-30 | 196
A11340 | Power System Study Report - Protection Coordination and Relay Setting_RCC | 2026-02-27 | 2026-03-23 | 2026-02-27 | 2026-03-23 | 2026-11-30 | 16 | 2026-12-22 | 196
A11350 | Power System Study Report - Protection Coordination and Relay Setting_IFA | 2026-03-23 | 2026-03-26 | 2026-03-23 | 2026-03-26 | 2026-12-22 | 3 | 2026-12-25 | 196
A11360 | Power System Study Report - Protection Coordination and Relay Setting_RCA | 2026-03-26 | 2026-04-17 | 2026-03-26 | 2026-04-17 | 2026-12-28 | 16 | 2027-01-18 | 196
A11370 | Power System Study Report - Protection Coordination and Relay Setting_IFD/IFC | 2026-04-17 | 2026-04-21 | 2026-04-17 | 2026-04-21 | 2027-01-18 | 2 | 2027-01-20 | 196
Material Requisition For Transformer (Power And Distribution) |  | 2026-02-20 | 2026-02-20 | 19-Dec-24 A | 28-Jun-25 A | 2026-03-02 | 146 | 2026-03-02
A12430 | Material Requisition For Transformer (Power And Distribution)_IFR | 2026-02-20 | 2026-02-20 | 19-Dec-24 A | 09-Jan-25 A | 2026-03-02 | 6 | 2026-03-02
A12440 | Material Requisition For Transformer (Power And Distribution)_RCC | 2026-02-20 | 2026-02-20 | 10-Jan-25 A | 18-Feb-25 A | 2026-03-02 | 16 | 2026-03-02
A12450 | Material Requisition For Transformer (Power And Distribution)_IFA | 2026-02-20 | 2026-02-20 | 19-Feb-25 A | 21-Mar-25 A | 2026-03-02 | 3 | 2026-03-02
A12460 | Material Requisition For Transformer (Power And Distribution)_RCA | 2026-02-20 | 2026-02-20 | 22-Mar-25 A | 21-Jun-25 A | 2026-03-02 | 16 | 2026-03-02
A12470 | Material Requisition For Transformer (Power And Distribution)_IFD/IFC | 2026-02-20 | 2026-02-20 | 22-Jun-25 A | 28-Jun-25 A | 2026-03-02 | 2 | 2026-03-02
Material Requisition For 11KV Switchgear |  | 2026-02-20 | 2026-02-20 | 13-Feb-25 A | 12-May-25 A | 2026-03-02 | 120 | 2026-03-02
A12480 | Material Requisition For 11KV Switchgear_IFR | 2026-02-20 | 2026-02-20 | 13-Feb-25 A | 06-Mar-25 A | 2026-03-02 | 6 | 2026-03-02
A12490 | Material Requisition For 11KV Switchgear_RCC | 2026-02-20 | 2026-02-20 | 07-Mar-25 A | 21-Apr-25 A | 2026-03-02 | 16 | 2026-03-02
A12500 | Material Requisition For 11KV Switchgear_IFA | 2026-02-20 | 2026-02-20 | 22-Apr-25 A | 28-Apr-25 A | 2026-03-02 | 3 | 2026-03-02
A12510 | Material Requisition For 11KV Switchgear_RCA | 2026-02-20 | 2026-02-20 | 29-Apr-25 A | 05-May-25 A | 2026-03-02 | 16 | 2026-03-02
A12520 | Material Requisition For 11KV Switchgear_IFD/IFC | 2026-02-20 | 2026-02-20 | 06-May-25 A | 12-May-25 A | 2026-03-02 | 2 | 2026-03-02
Material Requisition For LV Switchgear |  | 2026-02-20 | 2026-02-20 | 20-Jan-25 A | 11-Jul-25 A | 2026-03-02 | 195 | 2026-03-02
A12530 | Material Requisition For LV Switchgear_IFR | 2026-02-20 | 2026-02-20 | 20-Jan-25 A | 28-Feb-25 A | 2026-03-02 | 6 | 2026-03-02
A12540 | Material Requisition For LV Switchgear_RCC | 2026-02-20 | 2026-02-20 | 01-Mar-25 A | 06-May-25 A | 2026-03-02 | 16 | 2026-03-02
A12550 | Material Requisition For LV Switchgear_IFA | 2026-02-20 | 2026-02-20 | 07-May-25 A | 21-Jun-25 A | 2026-03-02 | 3 | 2026-03-02
A12560 | Material Requisition For LV Switchgear_RCA | 2026-02-20 | 2026-02-20 | 23-Jun-25 A | 04-Jul-25 A | 2026-03-02 | 16 | 2026-03-02
A12570 | Material Requisition For LV Switchgear_IFD/IFC | 2026-02-20 | 2026-02-20 | 07-Jul-25 A | 11-Jul-25 A | 2026-03-02 | 2 | 2026-03-02
Material Requisition For Capacitor Bank |  | 2026-02-20 | 2026-02-20 | 03-Mar-25 A | 04-Sep-25 A | 2026-03-02 | 173 | 2026-03-02
A12580 | Material Requisition For Capacitor Bank_IFR | 2026-02-20 | 2026-02-20 | 03-Mar-25 A | 27-Apr-25 A | 2026-03-02 | 6 | 2026-03-02
A12590 | Material Requisition For Capacitor Bank_RCC | 2026-02-20 | 2026-02-20 | 28-Apr-25 A | 04-May-25 A | 2026-03-02 | 16 | 2026-03-02
A12600 | Material Requisition For Capacitor Bank_IFA | 2026-02-20 | 2026-02-20 | 05-May-25 A | 21-Jun-25 A | 2026-03-02 | 3 | 2026-03-02
A12610 | Material Requisition For Capacitor Bank_RCA | 2026-02-20 | 2026-02-20 | 22-Jun-25 A | 28-Aug-25 A | 2026-03-02 | 16 | 2026-03-02
A12620 | Material Requisition For Capacitor Bank_IFD/IFC | 2026-02-20 | 2026-02-20 | 29-Aug-25 A | 04-Sep-25 A | 2026-03-02 | 2 | 2026-03-02
Material Requisition For Power, Control And Earthing Cables |  | 2026-02-20 | 2026-02-20 | 22-Apr-25 A | 2026-02-20 | 2026-03-19 | 118 | 2026-03-19 | 20
A12630 | Material Requisition For Power, Control And Earthing Cables_IFR | 2026-02-20 | 2026-02-20 | 22-Apr-25 A | 13-May-25 A | 2026-03-19 | 6 | 2026-03-19
A12640 | Material Requisition For Power, Control And Earthing Cables_RCC | 2026-02-20 | 2026-02-20 | 26-May-25 A | 31-Jul-25 A | 2026-03-19 | 16 | 2026-03-19
A12650 | Material Requisition For Power, Control And Earthing Cables_IFA | 2026-02-20 | 2026-02-20 | 01-Aug-25 A | 20-Aug-25 A | 2026-03-19 | 3 | 2026-03-19
A12660 | Material Requisition For Power, Control And Earthing Cables_RCA | 2026-02-20 | 2026-02-20 | 15-Sep-25 A | 15-Oct-25 A | 2026-03-19 | 16 | 2026-03-19
A12670 | Material Requisition For Power, Control And Earthing Cables_IFD/IFC | 2026-02-20 | 2026-02-20 | 20-Sep-25 A | 2026-02-20 | 2026-03-19 | 2 | 2026-03-19 | 20
Material Requisition For Emergency Diesel Generator |  | 2026-02-20 | 2026-02-20 | 01-Jan-25 A | 28-Jun-25 A | 2026-03-02 | 144 | 2026-03-02
A12680 | Material Requisition For Emergency Diesel Generator_IFR | 2026-02-20 | 2026-02-20 | 01-Jan-25 A | 22-Jan-25 A | 2026-03-02 | 6 | 2026-03-02
A12690 | Material Requisition For Emergency Diesel Generator_RCC | 2026-02-20 | 2026-02-20 | 23-Jan-25 A | 07-Mar-25 A | 2026-03-02 | 16 | 2026-03-02
A12700 | Material Requisition For Emergency Diesel Generator_IFA | 2026-02-20 | 2026-02-20 | 08-Mar-25 A | 20-Apr-25 A | 2026-03-02 | 3 | 2026-03-02
A12710 | Material Requisition For Emergency Diesel Generator_RCA | 2026-02-20 | 2026-02-20 | 21-Apr-25 A | 21-Jun-25 A | 2026-03-02 | 16 | 2026-03-02
A12720 | Material Requisition For Emergency Diesel Generator_IFD/IFC | 2026-02-20 | 2026-02-20 | 22-Jun-25 A | 28-Jun-25 A | 2026-03-02 | 2 | 2026-03-02
Material Requisition For AC UPS |  | 2026-02-20 | 2026-02-20 | 01-Jan-25 A | 30-Apr-25 A | 2026-03-02 | 172 | 2026-03-02
A12730 | Material Requisition For AC UPS_IFR | 2026-02-20 | 2026-02-20 | 01-Jan-25 A | 22-Jan-25 A | 2026-03-02 | 6 | 2026-03-02
A12740 | Material Requisition For AC UPS_RCC | 2026-02-20 | 2026-02-20 | 25-Feb-25 A | 07-Mar-25 A | 2026-03-02 | 16 | 2026-03-02
A12750 | Material Requisition For AC UPS_IFA | 2026-02-20 | 2026-02-20 | 10-Mar-25 A | 21-Mar-25 A | 2026-03-02 | 3 | 2026-03-02
A12760 | Material Requisition For AC UPS_RCA | 2026-02-20 | 2026-02-20 | 24-Mar-25 A | 04-Apr-25 A | 2026-03-02 | 16 | 2026-03-02
A12770 | Material Requisition For AC UPS_IFD/IFC | 2026-02-20 | 2026-02-20 | 07-Apr-25 A | 30-Apr-25 A | 2026-03-02 | 2 | 2026-03-02
Material Requisition For DC UPS |  | 2026-02-20 | 2026-02-20 | 31-Jan-25 A | 28-Jun-25 A | 2026-03-02 | 112 | 2026-03-02
A12780 | Material Requisition For DC UPS_IFR | 2026-02-20 | 2026-02-20 | 31-Jan-25 A | 21-Feb-25 A | 2026-03-02 | 6 | 2026-03-02
A12790 | Material Requisition For DC UPS_RCC | 2026-02-20 | 2026-02-20 | 21-Feb-25 A | 14-Mar-25 A | 2026-03-02 | 16 | 2026-03-02
A12800 | Material Requisition For DC UPS_IFA | 2026-02-20 | 2026-02-20 | 13-Mar-25 A | 21-Mar-25 A | 2026-03-02 | 3 | 2026-03-02
A12810 | Material Requisition For DC UPS_RCA | 2026-02-20 | 2026-02-20 | 22-Mar-25 A | 21-Jun-25 A | 2026-03-02 | 16 | 2026-03-02
A12820 | Material Requisition For DC UPS_IFD/IFC | 2026-02-20 | 2026-02-20 | 22-Jun-25 A | 28-Jun-25 A | 2026-03-02 | 2 | 2026-03-02
Material Requisition For LV Variable Frequency Drive |  | 2026-02-20 | 2026-02-20 | 31-Jan-25 A | 12-Jul-25 A | 2026-03-02 | 154 | 2026-03-02
A12830 | Material Requisition For LV Variable Frequency Drive_IFR | 2026-02-20 | 2026-02-20 | 31-Jan-25 A | 21-Feb-25 A | 2026-03-02 | 6 | 2026-03-02
A12840 | Material Requisition For LV Variable Frequency Drive_RCC | 2026-02-20 | 2026-02-20 | 22-Feb-25 A | 21-Jun-25 A | 2026-03-02 | 16 | 2026-03-02
A12850 | Material Requisition For LV Variable Frequency Drive_IFA | 2026-02-20 | 2026-02-20 | 22-Jun-25 A | 28-Jun-25 A | 2026-03-02 | 3 | 2026-03-02
A12860 | Material Requisition For LV Variable Frequency Drive_RCA | 2026-02-20 | 2026-02-20 | 27-Jun-25 A | 05-Jul-25 A | 2026-03-02 | 16 | 2026-03-02
A12870 | Material Requisition For LV Variable Frequency Drive_IFD/IFC | 2026-02-20 | 2026-02-20 | 06-Jul-25 A | 12-Jul-25 A | 2026-03-02 | 2 | 2026-03-02
Material Requisition For Neutral Grounding Resistor |  | 2026-02-20 | 2026-02-20 | 13-Dec-24 A | 15-Oct-25 A | 2026-03-02 | 105 | 2026-03-02
A12880 | Material Requisition For Neutral Grounding Resistor_IFR | 2026-02-20 | 2026-02-20 | 13-Dec-24 A | 17-Jan-25 A | 2026-03-02 | 6 | 2026-03-02
A12890 | Material Requisition For Neutral Grounding Resistor_RCC | 2026-02-20 | 2026-02-20 | 08-Jan-25 A | 10-Feb-25 A | 2026-03-02 | 16 | 2026-03-02
A12900 | Material Requisition For Neutral Grounding Resistor_IFA | 2026-02-20 | 2026-02-20 | 11-Feb-25 A | 14-Mar-25 A | 2026-03-02 | 3 | 2026-03-02
A12910 | Material Requisition For Neutral Grounding Resistor_RCA | 2026-02-20 | 2026-02-20 | 15-Mar-25 A | 06-May-25 A | 2026-03-02 | 16 | 2026-03-02
A12920 | Material Requisition For Neutral Grounding Resistor_IFD/IFC | 2026-02-20 | 2026-02-20 | 01-Sep-25 A | 15-Oct-25 A | 2026-03-02 | 2 | 2026-03-02
Material Requisition For Interposting Relay Panel |  | 2026-02-20 | 2026-04-27 | 01-Sep-25 A | 2026-04-27 | 2026-04-28 | 154 | 2026-07-17 | 60
A58340 | Material Requisition For Interpopsting Relay Panel_IFR | 2026-02-20 | 2026-02-20 | 01-Sep-25 A | 05-Sep-25 A | 2026-04-28 | 6 | 2026-04-28
A58350 | Material Requisition For Interpopsting Relay Panel_RCC | 2026-02-20 | 2026-03-13 | 2026-02-20 | 2026-03-13 | 2026-05-27 | 16 | 2026-06-18 | 69
A58360 | Material Requisition For Interpopsting Relay Panel_IFA | 2026-03-26 | 2026-04-01 | 2026-03-26 | 2026-04-01 | 2026-06-18 | 3 | 2026-06-23 | 60
A58370 | Material Requisition For Interpopsting Relay Panel_RCA | 2026-04-01 | 2026-04-22 | 2026-04-01 | 2026-04-22 | 2026-06-24 | 16 | 2026-07-15 | 60
A58380 | Material Requisition For Interpopsting Relay Panel_IFD/IFC | 2026-04-22 | 2026-04-27 | 2026-04-22 | 2026-04-27 | 2026-07-15 | 2 | 2026-07-17 | 60
Material Requisition For Integrated Protection Control Panel |  | 2026-02-20 | 2026-02-20 | 19-Jul-25 A | 04-Sep-25 A | 2026-05-04 | 36 | 2027-01-20
A58140 | Material Requisition For IPCS_IFR | 2026-02-20 | 2026-02-20 | 19-Jul-25 A | 25-Jul-25 A | 2026-05-04 | 6 | 2026-05-04
A58150 | Material Requisition For IPCS_RCC | 2026-02-20 | 2026-02-20 | 26-Jul-25 A | 14-Aug-25 A | 2027-01-20 | 16 | 2027-01-20
A58160 | Material Requisition For IPCS_IFA | 2026-02-20 | 2026-02-20 | 14-Aug-25 A | 17-Aug-25 A | 2027-01-20 | 3 | 2027-01-20
A58170 | Material Requisition For IPCS_RCA | 2026-02-20 | 2026-02-20 | 17-Aug-25 A | 30-Aug-25 A | 2027-01-20 | 16 | 2027-01-20
A58180 | Material Requisition For IPCS_IFD/IFC | 2026-02-20 | 2026-02-20 | 30-Aug-25 A | 04-Sep-25 A | 2027-01-20 | 2 | 2027-01-20
Material Requisition For SCMS |  | 2026-02-20 | 2026-02-20 | 19-Jul-25 A | 04-Sep-25 A | 2026-03-20 | 36 | 2026-03-20
A59950 | Material Requisition For SCMS_IFR | 2026-02-20 | 2026-02-20 | 19-Jul-25 A | 25-Jul-25 A | 2026-03-20 | 6 | 2026-03-20
A59960 | Material Requisition For SCMS_RCC | 2026-02-20 | 2026-02-20 | 26-Jul-25 A | 14-Aug-25 A | 2026-03-20 | 16 | 2026-03-20
A59970 | Material Requisition For SCMS_IFA | 2026-02-20 | 2026-02-20 | 14-Aug-25 A | 17-Aug-25 A | 2026-03-20 | 3 | 2026-03-20
A59980 | Material Requisition For SCMS_RCA | 2026-02-20 | 2026-02-20 | 17-Aug-25 A | 30-Aug-25 A | 2026-03-20 | 16 | 2026-03-20
A59990 | Material Requisition For SCMS_IFD/IFC | 2026-02-20 | 2026-02-20 | 30-Aug-25 A | 04-Sep-25 A | 2026-03-20 | 2 | 2026-03-20
Key Single Line Diagram - Hydrogen Extraction Unit |  | 2026-02-20 | 2026-02-20 | 28-May-25 A | 23-Dec-25 A | 2026-03-02 | 261 | 2027-01-20
A11380 | Key Single Line Diagram - Hydrogen Extraction Unit_IFR | 2026-02-20 | 2026-02-20 | 28-May-25 A | 07-Jun-25 A | 2026-03-02 | 6 | 2026-03-02
A11390 | Key Single Line Diagram - Hydrogen Extraction Unit_RCC | 2026-02-20 | 2026-02-20 | 30-May-25 A | 14-Jun-25 A | 2027-01-20 | 16 | 2027-01-20
A11400 | Key Single Line Diagram - Hydrogen Extraction Unit_IFA | 2026-02-20 | 2026-02-20 | 15-Jun-25 A | 21-Jun-25 A | 2027-01-20 | 3 | 2027-01-20
A11410 | Key Single Line Diagram - Hydrogen Extraction Unit_RCA | 2026-02-20 | 2026-02-20 | 01-Jul-25 A | 10-Sep-25 A | 2027-01-20 | 16 | 2027-01-20
A11420 | Key Single Line Diagram - Hydrogen Extraction Unit_IFD/IFC | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 23-Dec-25 A | 2027-01-20 | 2 | 2027-01-20
Single Line Diagram For Integrated Protection Control Panel |  | 2026-02-20 | 2026-04-14 | 19-Aug-25 A | 2026-04-14 | 2026-03-20 | 147 | 2027-01-01 | 189
A58440 | Single Line Diagram For IPCS_IFR | 2026-02-20 | 2026-02-20 | 19-Aug-25 A | 25-Aug-25 A | 2026-03-20 | 6 | 2026-03-20
A58450 | Single Line Diagram For IPCS_RCC | 2026-02-20 | 2026-03-13 | 2026-02-20 | 2026-03-13 | 2026-11-11 | 16 | 2026-12-03 | 189
A58460 | Single Line Diagram For IPCS_IFA | 2026-03-13 | 2026-03-19 | 2026-03-13 | 2026-03-19 | 2026-12-03 | 3 | 2026-12-08 | 189
A58470 | Single Line Diagram For IPCS_RCA | 2026-03-19 | 2026-04-09 | 2026-03-19 | 2026-04-09 | 2026-12-09 | 16 | 2026-12-30 | 189
A58480 | Single Line Diagram For IPCS_IFD/IFC | 2026-04-09 | 2026-04-14 | 2026-04-09 | 2026-04-14 | 2026-12-30 | 2 | 2027-01-01 | 189
Single Line Diagram For SCMS |  | 2026-02-20 | 2026-04-14 | 19-Aug-25 A | 2026-04-14 | 2026-03-20 | 147 | 2027-01-01 | 189
A60000 | Single Line Diagram For SCMS_IFR | 2026-02-20 | 2026-02-20 | 19-Aug-25 A | 25-Aug-25 A | 2026-03-20 | 6 | 2026-03-20
A60010 | Single Line Diagram For SCMS_RCC | 2026-02-20 | 2026-03-13 | 2026-02-20 | 2026-03-13 | 2026-11-11 | 16 | 2026-12-03 | 189
A60020 | Single Line Diagram For SCMS_IFA | 2026-03-13 | 2026-03-19 | 2026-03-13 | 2026-03-19 | 2026-12-03 | 3 | 2026-12-08 | 189
A60030 | Single Line Diagram For SCMS_RCA | 2026-03-19 | 2026-04-09 | 2026-03-19 | 2026-04-09 | 2026-12-09 | 16 | 2026-12-30 | 189
A60040 | Single Line Diagram For SCMS_IFD/IFC | 2026-04-09 | 2026-04-14 | 2026-04-09 | 2026-04-14 | 2026-12-30 | 2 | 2027-01-01 | 189
Single Line Diagram For 11KV Switchgear |  | 2026-02-20 | 2026-02-20 | 31-Jan-25 A | 23-Aug-25 A | 2026-03-02 | 224 | 2027-01-01
A11530 | Single Line Diagram For 11KV Switchgear_IFR | 2026-02-20 | 2026-02-20 | 31-Jan-25 A | 21-Feb-25 A | 2026-03-02 | 6 | 2026-03-02
A11540 | Single Line Diagram For 11KV Switchgear_RCC | 2026-02-20 | 2026-02-20 | 22-Feb-25 A | 20-Apr-25 A | 2027-01-01 | 16 | 2027-01-01
A11550 | Single Line Diagram For 11KV Switchgear_IFA | 2026-02-20 | 2026-02-20 | 21-Apr-25 A | 27-Apr-25 A | 2027-01-01 | 3 | 2027-01-01
A11560 | Single Line Diagram For 11KV Switchgear_RCA | 2026-02-20 | 2026-02-20 | 28-Apr-25 A | 21-Jun-25 A | 2027-01-01 | 16 | 2027-01-01
A11570 | Single Line Diagram For 11KV Switchgear_IFD/IFC | 2026-02-20 | 2026-02-20 | 22-Jun-25 A | 23-Aug-25 A | 2027-01-01 | 2 | 2027-01-01
Single Line Diagram For AC UPS |  | 2026-02-20 | 2026-02-20 | 26-Aug-25 A | 23-Dec-25 A | 2026-12-08 | 67 | 2027-01-01
A11580 | Single Line Diagram For AC UPS_IFR | 2026-02-20 | 2026-02-20 | 26-Aug-25 A | 02-Sep-25 A | 2026-12-08 | 6 | 2026-12-08
A11590 | Single Line Diagram For AC UPS_RCC | 2026-02-20 | 2026-02-20 | 02-Sep-25 A | 05-Sep-25 A | 2027-01-01 | 16 | 2027-01-01
A11600 | Single Line Diagram For AC UPS_IFA | 2026-02-20 | 2026-02-20 | 08-Sep-25 A | 12-Sep-25 A | 2027-01-01 | 3 | 2027-01-01
A11610 | Single Line Diagram For AC UPS_RCA | 2026-02-20 | 2026-02-20 | 01-Nov-25 A | 21-Nov-25 A | 2027-01-01 | 16 | 2027-01-01
A11620 | Single Line Diagram For AC UPS_IFD/IFC | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 23-Dec-25 A | 2027-01-01 | 2 | 2027-01-01
Single Line Diagram For DC UPS |  | 2026-02-20 | 2026-02-20 | 03-Feb-25 A | 25-Dec-25 A | 2026-12-08 | 248 | 2027-01-01
A11630 | Single Line Diagram For DC UPS_IFR | 2026-02-20 | 2026-02-20 | 03-Feb-25 A | 24-Feb-25 A | 2026-12-08 | 6 | 2026-12-08
A11640 | Single Line Diagram For DC UPS_RCC | 2026-02-20 | 2026-02-20 | 25-Feb-25 A | 18-Mar-25 A | 2026-12-08 | 16 | 2026-12-08
A11650 | Single Line Diagram For DC UPS_IFA | 2026-02-20 | 2026-02-20 | 19-Mar-25 A | 29-Apr-25 A | 2027-01-01 | 3 | 2027-01-01
A11660 | Single Line Diagram For DC UPS_RCA | 2026-02-20 | 2026-02-20 | 30-Apr-25 A | 02-Jun-25 A | 2027-01-01 | 16 | 2027-01-01
A11670 | Single Line Diagram For DC UPS_IFD/IFC | 2026-02-20 | 2026-02-20 | 23-Dec-25 A | 25-Dec-25 A | 2027-01-01 | 2 | 2027-01-01
Single Line Diagram For LV Switchgear |  | 2026-02-20 | 2026-02-20 | 20-Jan-25 A | 23-Dec-25 A | 2027-01-01 | 256 | 2027-01-01
A11680 | Single Line Diagram For LV Switchgear_IFR | 2026-02-20 | 2026-02-20 | 20-Jan-25 A | 21-Feb-25 A | 2027-01-01 | 6 | 2027-01-01
A11690 | Single Line Diagram For LV Switchgear_RCC | 2026-02-20 | 2026-02-20 | 22-Feb-25 A | 06-May-25 A | 2027-01-01 | 16 | 2027-01-01
A11700 | Single Line Diagram For LV Switchgear_IFA | 2026-02-20 | 2026-02-20 | 07-May-25 A | 21-Jun-25 A | 2027-01-01 | 3 | 2027-01-01
A11710 | Single Line Diagram For LV Switchgear_RCA | 2026-02-20 | 2026-02-20 | 15-Jul-25 A | 10-Sep-25 A | 2027-01-01 | 16 | 2027-01-01
A11720 | Single Line Diagram For LV Switchgear_IFD/IFC | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 23-Dec-25 A | 2027-01-01 | 2 | 2027-01-01
Single Line Diagram For Lighting And Small Power |  | 2026-02-20 | 2026-03-17 | 28-Oct-25 A | 2026-03-17 | 2026-12-08 | 38 | 2027-01-01 | 208
A11730 | Single Line Diagram For Lighting And Small Power_IFR | 2026-02-20 | 2026-02-20 | 28-Oct-25 A | 05-Nov-25 A | 2026-12-08 | 6 | 2026-12-08
A11740 | Single Line Diagram For Lighting And Small Power_RCC | 2026-02-20 | 2026-02-20 | 05-Nov-25 A | 14-Nov-25 A | 2026-12-08 | 16 | 2026-12-08
A11750 | Single Line Diagram For Lighting And Small Power_IFA | 2026-02-20 | 2026-02-20 | 23-Jan-26 A | 2026-02-20 | 2026-12-08 | 3 | 2026-12-08 | 208
A11760 | Single Line Diagram For Lighting And Small Power_RCA | 2026-02-20 | 2026-03-13 | 2026-02-20 | 2026-03-13 | 2026-12-09 | 16 | 2026-12-30 | 208
A11770 | Single Line Diagram For Lighting And Small Power_IFD/IFC | 2026-03-13 | 2026-03-17 | 2026-03-13 | 2026-03-17 | 2026-12-30 | 2 | 2027-01-01 | 208
One Line Diagram 220/33 KV Main Substation (Unit No-80) - Update |  | 2026-02-20 | 2026-02-20 | 25-Mar-25 A | 28-Jun-25 A | 2027-01-20 | 172 | 2027-01-20
A28330 | One Line Diagram 220/33 KV Main Substation (Unit No-80) - Update_IFR | 2026-02-20 | 2026-02-20 | 25-Mar-25 A | 28-Apr-25 A | 2027-01-20 | 6 | 2027-01-20
A55830 | One Line Diagram 220/33 KV Main Substation (Unit No-80) - Update_RCC | 2026-02-20 | 2026-02-20 | 29-Apr-25 A | 15-May-25 A | 2027-01-20 | 16 | 2027-01-20
A55840 | One Line Diagram 220/33 KV Main Substation (Unit No-80) - Update_IFA | 2026-02-20 | 2026-02-20 | 16-May-25 A | 04-Jun-25 A | 2027-01-20 | 3 | 2027-01-20
A55850 | One Line Diagram 220/33 KV Main Substation (Unit No-80) - Update_RCA | 2026-02-20 | 2026-02-20 | 05-Jun-25 A | 21-Jun-25 A | 2027-01-20 | 16 | 2027-01-20
A55860 | One Line Diagram 220/33 KV Main Substation (Unit No-80) - Update_IFD/IFC | 2026-02-20 | 2026-02-20 | 22-Jun-25 A | 28-Jun-25 A | 2027-01-20 | 2 | 2027-01-20
Protection and Metering One Line Diagram 220/33 KV Main Substation 33 KV Switchgear 80-ES-1802 - Upd |  | 2026-02-20 | 2026-02-20 | 18-Feb-25 A | 13-Jan-26 A | 2027-01-20 | 232 | 2027-01-20
A55870 | Protection and Metering One Line Diagram 220/33 KV Main Substation 33 KV Switchgear 80-ES-1802 - Update_IFR | 2026-02-20 | 2026-02-20 | 18-Feb-25 A | 11-Mar-25 A | 2027-01-20 | 6 | 2027-01-20
A55880 | Protection and Metering One Line Diagram 220/33 KV Main Substation 33 KV Switchgear 80-ES-1802 - Update_RCC | 2026-02-20 | 2026-02-20 | 12-Mar-25 A | 18-Mar-25 A | 2027-01-20 | 16 | 2027-01-20
A55890 | Protection and Metering One Line Diagram 220/33 KV Main Substation 33 KV Switchgear 80-ES-1802 - Update_IFA | 2026-02-20 | 2026-02-20 | 16-May-25 A | 21-Jun-25 A | 2027-01-20 | 3 | 2027-01-20
A28410 | Protection and Metering One Line Diagram 220/33 KV Main Substation 33 KV Switchgear 80-ES-1802 - Update_RCA | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 09-Jan-26 A | 2027-01-20 | 16 | 2027-01-20
A28420 | Protection and Metering One Line Diagram 220/33 KV Main Substation 33 KV Switchgear 80-ES-1802 - Update_IFD/IFC | 2026-02-20 | 2026-02-20 | 09-Jan-26 A | 13-Jan-26 A | 2027-01-20 | 2 | 2027-01-20
Electrical Legend Sheet |  | 2026-02-20 | 2026-02-20 | 28-Mar-25 A | 28-Jun-25 A | 2026-11-30 | 161 | 2027-01-20
A12130 | Electrical Legend Sheet_IFR | 2026-02-20 | 2026-02-20 | 28-Mar-25 A | 06-Apr-25 A | 2026-11-30 | 6 | 2026-11-30
A12140 | Electrical Legend Sheet_RCC | 2026-02-20 | 2026-02-20 | 31-Mar-25 A | 13-Apr-25 A | 2027-01-20 | 16 | 2027-01-20
A12150 | Electrical Legend Sheet_IFA | 2026-02-20 | 2026-02-20 | 14-Apr-25 A | 20-Apr-25 A | 2027-01-20 | 3 | 2027-01-20
A12160 | Electrical Legend Sheet_RCA | 2026-02-20 | 2026-02-20 | 21-Apr-25 A | 21-Jun-25 A | 2027-01-20 | 16 | 2027-01-20
A12170 | Electrical Legend Sheet_IFD/IFC | 2026-02-20 | 2026-02-20 | 22-Jun-25 A | 28-Jun-25 A | 2027-01-20 | 2 | 2027-01-20
Electrical Equipment And Motor List |  | 2026-02-20 | 2026-02-20 | 28-Mar-25 A | 04-May-25 A | 2026-11-30 | 217 | 2027-01-20
A12230 | Electrical Equipment And Motor List_IFR | 2026-02-20 | 2026-02-20 | 28-Mar-25 A | 06-Apr-25 A | 2026-11-30 | 6 | 2026-11-30
A12240 | Electrical Equipment And Motor List_RCC | 2026-02-20 | 2026-02-20 | 31-Mar-25 A | 13-Apr-25 A | 2027-01-20 | 16 | 2027-01-20
A12250 | Electrical Equipment And Motor List_IFA | 2026-02-20 | 2026-02-20 | 14-Apr-25 A | 20-Apr-25 A | 2027-01-20 | 3 | 2027-01-20
A12260 | Electrical Equipment And Motor List_RCA | 2026-02-20 | 2026-02-20 | 18-Apr-25 A | 27-Apr-25 A | 2027-01-20 | 16 | 2027-01-20
A12270 | Electrical Equipment And Motor List_IFD/IFC | 2026-02-20 | 2026-02-20 | 28-Apr-25 A | 04-May-25 A | 2027-01-20 | 2 | 2027-01-20
System Architecture Diagram For IPCS |  | 2026-02-20 | 2026-02-20 | 12-Feb-25 A | 23-Dec-25 A | 2027-01-20 | 236 | 2027-01-20
A12280 | System Architecture Diagram For IPCS_IFR | 2026-02-20 | 2026-02-20 | 12-Feb-25 A | 05-Mar-25 A | 2027-01-20 | 6 | 2027-01-20
A12290 | System Architecture Diagram For IPCS_RCC | 2026-02-20 | 2026-02-20 | 06-Mar-25 A | 20-Apr-25 A | 2027-01-20 | 16 | 2027-01-20
A12300 | System Architecture Diagram For IPCS_IFA | 2026-02-20 | 2026-02-20 | 21-Apr-25 A | 27-Apr-25 A | 2027-01-20 | 3 | 2027-01-20
A12310 | System Architecture Diagram For IPCS_RCA | 2026-02-20 | 2026-02-20 | 15-Aug-25 A | 04-Sep-25 A | 2027-01-20 | 16 | 2027-01-20
A12320 | System Architecture Diagram For IPCS_IFD/IFC | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 23-Dec-25 A | 2027-01-20 | 2 | 2027-01-20
System Architecture Diagram For SCMS - Update |  | 2026-02-20 | 2026-02-20 | 01-Jul-25 A | 08-Sep-25 A | 2027-01-20 | 39 | 2027-01-20
A12330 | System Architecture Diagram For SCMS - Update_IFR | 2026-02-20 | 2026-02-20 | 01-Jul-25 A | 08-Jul-25 A | 2027-01-20 | 6 | 2027-01-20
A12340 | System Architecture Diagram For SCMS - Update_RCC | 2026-02-20 | 2026-02-20 | 09-Jul-25 A | 30-Jul-25 A | 2027-01-20 | 16 | 2027-01-20
A12350 | System Architecture Diagram For SCMS - Update_IFA | 2026-02-20 | 2026-02-20 | 31-Jul-25 A | 20-Aug-25 A | 2027-01-20 | 3 | 2027-01-20
A12360 | System Architecture Diagram For SCMS - Update_RCA | 2026-02-20 | 2026-02-20 | 21-Aug-25 A | 01-Sep-25 A | 2027-01-20 | 16 | 2027-01-20
A12370 | System Architecture Diagram For SCMS - Update_IFD/IFC | 2026-02-20 | 2026-02-20 | 02-Sep-25 A | 08-Sep-25 A | 2027-01-20 | 2 | 2027-01-20
Capacitor Bank Sizing Calculation |  | 2026-02-20 | 2026-02-20 | 22-Mar-25 A | 16-Oct-25 A | 2026-03-02 | 207 | 2027-01-20
A10780 | Capacitor Bank Sizing Calculation_IFR | 2026-02-20 | 2026-02-20 | 30-Apr-25 A | 19-May-25 A | 2026-03-02 | 6 | 2026-03-02
A10790 | Capacitor Bank Sizing Calculation_RCC | 2026-02-20 | 2026-02-20 | 22-Mar-25 A | 26-May-25 A | 2027-01-20 | 16 | 2027-01-20
A10800 | Capacitor Bank Sizing Calculation_IFA | 2026-02-20 | 2026-02-20 | 27-May-25 A | 21-Jun-25 A | 2027-01-20 | 3 | 2027-01-20
A10810 | Capacitor Bank Sizing Calculation_RCA | 2026-02-20 | 2026-02-20 | 20-Jul-25 A | 22-Aug-25 A | 2027-01-20 | 16 | 2027-01-20
A10820 | Capacitor Bank Sizing Calculation_IFD/IFC | 2026-02-20 | 2026-02-20 | 10-Oct-25 A | 16-Oct-25 A | 2027-01-20 | 2 | 2027-01-20
Technical Bid Evaluation For 11KV Switchgear |  | 2026-02-20 | 2026-02-20 | 01-Jul-25 A | 23-Dec-25 A | 2027-01-20 | 132 | 2027-01-20
A12980 | Technical Bid Evaluation For 11KV Switchgear_IFR | 2026-02-20 | 2026-02-20 | 01-Jul-25 A | 18-Jul-25 A | 2027-01-20 | 6 | 2027-01-20
A12990 | Technical Bid Evaluation For 11KV Switchgear_RCC | 2026-02-20 | 2026-02-20 | 21-Jul-25 A | 22-Aug-25 A | 2027-01-20 | 16 | 2027-01-20
A13000 | Technical Bid Evaluation For 11KV Switchgear_IFA | 2026-02-20 | 2026-02-20 | 27-Oct-25 A | 05-Nov-25 A | 2027-01-20 | 3 | 2027-01-20
A13010 | Technical Bid Evaluation For 11KV Switchgear_RCA | 2026-02-20 | 2026-02-20 | 06-Nov-25 A | 17-Nov-25 A | 2027-01-20 | 16 | 2027-01-20
A13020 | Technical Bid Evaluation For 11KV Switchgear_IFD/IFC | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 23-Dec-25 A | 2027-01-20 | 2 | 2027-01-20
Technical Bid Evaluation For DC UPS |  | 2026-02-20 | 2026-02-20 | 01-Oct-25 A | 19-Jan-26 A | 2026-03-19 | 61 | 2027-01-20
A13130 | Technical Bid Evaluation For DC UPS_IFR | 2026-02-20 | 2026-02-20 | 01-Oct-25 A | 10-Oct-25 A | 2026-03-19 | 6 | 2026-03-19
A13140 | Technical Bid Evaluation For DC UPS_RCC | 2026-02-20 | 2026-02-20 | 08-Oct-25 A | 24-Oct-25 A | 2026-03-19 | 16 | 2026-03-19
A13150 | Technical Bid Evaluation For DC UPS_IFA | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 24-Dec-25 A | 2026-03-19 | 3 | 2026-03-19
A13160 | Technical Bid Evaluation For DC UPS_RCA | 2026-02-20 | 2026-02-20 | 24-Dec-25 A | 15-Jan-26 A | 2027-01-20 | 16 | 2027-01-20
A13170 | Technical Bid Evaluation For DC UPS_IFD/IFC | 2026-02-20 | 2026-02-20 | 15-Jan-26 A | 19-Jan-26 A | 2027-01-20 | 2 | 2027-01-20
Cable (MV and LV) Sizing Calculation |  | 2026-02-20 | 2026-02-20 | 19-Feb-25 A | 16-Oct-25 A | 2026-10-05 | 95 | 2027-01-20
A10730 | Cable (MV and LV) Sizing Calculation_IFR | 2026-02-20 | 2026-02-20 | 19-Feb-25 A | 12-Mar-25 A | 2026-10-05 | 6 | 2026-10-05
A10740 | Cable (MV and LV) Sizing Calculation_RCC | 2026-02-20 | 2026-02-20 | 13-Mar-25 A | 06-May-25 A | 2027-01-20 | 16 | 2027-01-20
A10750 | Cable (MV and LV) Sizing Calculation_IFA | 2026-02-20 | 2026-02-20 | 07-May-25 A | 19-Jun-25 A | 2027-01-20 | 3 | 2027-01-20
A10760 | Cable (MV and LV) Sizing Calculation_RCA | 2026-02-20 | 2026-02-20 | 20-Jun-25 A | 26-Jun-25 A | 2027-01-20 | 16 | 2027-01-20
A10770 | Cable (MV and LV) Sizing Calculation_IFD/IFC | 2026-02-20 | 2026-02-20 | 10-Oct-25 A | 16-Oct-25 A | 2027-01-20 | 2 | 2027-01-20
Lighting Design Calculation |  | 2026-02-20 | 2026-02-20 | 31-Jul-25 A | 23-Dec-25 A | 2027-01-20 | 143 | 2027-01-20
A10830 | Lighting Design Calculation_IFR | 2026-02-20 | 2026-02-20 | 31-Jul-25 A | 15-Aug-25 A | 2027-01-20 | 6 | 2027-01-20
A10840 | Lighting Design Calculation_RCC | 2026-02-20 | 2026-02-20 | 02-Aug-25 A | 22-Aug-25 A | 2027-01-20 | 16 | 2027-01-20
A10850 | Lighting Design Calculation_IFA | 2026-02-20 | 2026-02-20 | 01-Oct-25 A | 09-Oct-25 A | 2027-01-20 | 3 | 2027-01-20
A10860 | Lighting Design Calculation_RCA | 2026-02-20 | 2026-02-20 | 01-Oct-25 A | 17-Oct-25 A | 2027-01-20 | 16 | 2027-01-20
A10870 | Lighting Design Calculation_IFD/IFC | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 23-Dec-25 A | 2027-01-20 | 2 | 2027-01-20
Earthing and Lightning Protection Calculation |  | 2026-02-20 | 2026-02-24 | 31-Jul-25 A | 2026-02-24 | 2027-01-18 | 87 | 2027-01-20 | 237
A10880 | Earthing and Lightning Protection Calculation_IFR | 2026-02-20 | 2026-02-20 | 31-Jul-25 A | 11-Aug-25 A | 2027-01-18 | 6 | 2027-01-18
A10890 | Earthing and Lightning Protection Calculation_RCC | 2026-02-20 | 2026-02-20 | 10-Aug-25 A | 30-Aug-25 A | 2027-01-18 | 16 | 2027-01-18
A10900 | Earthing and Lightning Protection Calculation_IFA | 2026-02-20 | 2026-02-20 | 24-Sep-25 A | 09-Oct-25 A | 2027-01-18 | 3 | 2027-01-18
A10910 | Earthing and Lightning Protection Calculation_RCA | 2026-02-20 | 2026-02-20 | 28-Sep-25 A | 16-Oct-25 A | 2027-01-18 | 16 | 2027-01-18
A10920 | Earthing and Lightning Protection Calculation_IFD/IFC | 2026-02-20 | 2026-02-24 | 2026-02-20 | 2026-02-24 | 2027-01-18 | 2 | 2027-01-20 | 237
Power And Control Cable Schedule |  | 2026-02-20 | 2026-02-20 | 01-Aug-25 A | 19-Jan-26 A | 2026-10-05 | 61 | 2026-10-05
A12180 | Power And Control Cable Schedule_IFR | 2026-02-20 | 2026-02-20 | 01-Aug-25 A | 15-Aug-25 A | 2026-10-05 | 6 | 2026-10-05
A12190 | Power And Control Cable Schedule_RCC | 2026-02-20 | 2026-02-20 | 08-Aug-25 A | 22-Aug-25 A | 2026-10-05 | 16 | 2026-10-05
A12200 | Power And Control Cable Schedule_IFA | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 24-Dec-25 A | 2026-10-05 | 3 | 2026-10-05
A12210 | Power And Control Cable Schedule_RCA | 2026-02-20 | 2026-02-20 | 24-Dec-25 A | 15-Jan-26 A | 2026-10-05 | 16 | 2026-10-05
A12220 | Power And Control Cable Schedule_IFD/IFC | 2026-02-20 | 2026-02-20 | 15-Jan-26 A | 19-Jan-26 A | 2026-10-05 | 2 | 2026-10-05
Interconnection Schedule |  | 2026-02-20 | 2026-04-21 | 2026-02-20 | 2026-04-21 | 2026-11-04 | 43 | 2027-01-01 | 183
A12380 | Interconnection Schedule_IFR | 2026-02-20 | 2026-02-27 | 2026-02-20 | 2026-02-27 | 2026-11-04 | 6 | 2026-11-11 | 183
A12390 | Interconnection Schedule_RCC | 2026-02-27 | 2026-03-23 | 2026-02-27 | 2026-03-23 | 2026-11-11 | 16 | 2026-12-03 | 183
A12400 | Interconnection Schedule_IFA | 2026-03-23 | 2026-03-26 | 2026-03-23 | 2026-03-26 | 2026-12-03 | 3 | 2026-12-08 | 183
A12410 | Interconnection Schedule_RCA | 2026-03-26 | 2026-04-17 | 2026-03-26 | 2026-04-17 | 2026-12-09 | 16 | 2026-12-30 | 183
A12420 | Interconnection Schedule_IFD/IFC | 2026-04-17 | 2026-04-21 | 2026-04-17 | 2026-04-21 | 2026-12-30 | 2 | 2027-01-01 | 183
Electrical Substation Building Layout |  | 2026-02-20 | 2026-02-20 | 03-Jan-25 A | 30-Dec-25 A | 2026-03-14 | 274 | 2027-01-20
A11930 | Electrical Substation Building Layout_IFR | 2026-02-20 | 2026-02-20 | 03-Jan-25 A | 24-Jan-25 A | 2026-03-14 | 6 | 2026-03-14
A11940 | Electrical Substation Building Layout_RCC | 2026-02-20 | 2026-02-20 | 25-Jan-25 A | 15-May-25 A | 2026-03-14 | 16 | 2026-03-14
A11950 | Electrical Substation Building Layout_IFA | 2026-02-20 | 2026-02-20 | 16-May-25 A | 23-Aug-25 A | 2026-03-14 | 3 | 2026-03-14
A11960 | Electrical Substation Building Layout_RCA | 2026-02-20 | 2026-02-20 | 24-Aug-25 A | 30-Aug-25 A | 2027-01-20 | 16 | 2027-01-20
A11970 | Electrical Substation Building Layout_IFD/IFC | 2026-02-20 | 2026-02-20 | 26-Dec-25 A | 30-Dec-25 A | 2027-01-20 | 2 | 2027-01-20
Cable and Tray Routing Layout - Outdoor |  | 2026-02-20 | 2026-04-15 | 01-Oct-25 A | 2026-04-15 | 2026-09-01 | 92 | 2026-10-05 | 124
A11830 | Cable and Tray Routing Layout - Outdoor_IFR | 2026-02-20 | 2026-02-20 | 01-Oct-25 A | 10-Oct-25 A | 2026-09-01 | 6 | 2026-09-01
A11840 | Cable and Tray Routing Layout - Outdoor_RCC | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 21-Jan-26 A | 2026-09-01 | 16 | 2026-09-01
A11850 | Cable and Tray Routing Layout - Outdoor_IFA | 2026-02-20 | 2026-02-25 | 2026-02-20 | 2026-02-25 | 2026-09-01 | 3 | 2026-09-04 | 137
A11860 | Cable and Tray Routing Layout - Outdoor_RCA | 2026-02-25 | 2026-03-19 | 2026-02-25 | 2026-03-19 | 2026-09-04 | 16 | 2026-09-28 | 137
A11870 | Cable and Tray Routing Layout - Outdoor_IFD/IFC | 2026-04-07 | 2026-04-15 | 2026-04-07 | 2026-04-15 | 2026-09-28 | 6 | 2026-10-05 | 124
Underground 33KV Cable Routing Layout Overall - Update |  | 2026-02-20 | 2026-04-15 | 17-Oct-25 A | 2026-04-15 | 2026-09-10 | 122 | 2026-10-05 | 124
A55900 | Underground 33KV Cable Routing Layout Overall - Update_IFR | 2026-02-20 | 2026-02-20 | 17-Oct-25 A | 25-Oct-25 A | 2026-09-10 | 6 | 2026-09-10
A55910 | Underground 33KV Cable Routing Layout Overall - Update_RCC | 2026-02-20 | 2026-02-20 | 27-Oct-25 A | 06-Nov-25 A | 2026-09-10 | 16 | 2026-09-10
A55920 | Underground 33KV Cable Routing Layout Overall - Update_IFA | 2026-02-20 | 2026-02-20 | 10-Dec-25 A | 19-Dec-25 A | 2026-09-10 | 3 | 2026-09-10
A55930 | Underground 33KV Cable Routing Layout Overall - Update_RCA | 2026-02-20 | 2026-03-13 | 2026-02-20 | 2026-03-13 | 2026-09-10 | 16 | 2026-10-01 | 144
A55940 | Underground 33KV Cable Routing Layout Overall - Update_IFD/IFC | 2026-04-13 | 2026-04-15 | 2026-04-13 | 2026-04-15 | 2026-10-01 | 2 | 2026-10-05 | 124
Cable and Tray Routing Layout - Indoor |  | 2026-03-09 | 2026-05-06 | 2026-03-09 | 2026-05-06 | 2026-08-06 | 43 | 2026-10-05 | 108
A11880 | Cable and Tray Routing Layout - Indoor_IFR | 2026-03-09 | 2026-03-16 | 2026-03-09 | 2026-03-16 | 2026-08-06 | 6 | 2026-08-13 | 108
A11890 | Cable and Tray Routing Layout - Indoor_RCC | 2026-03-16 | 2026-04-07 | 2026-03-16 | 2026-04-07 | 2026-08-13 | 16 | 2026-09-04 | 108
A11900 | Cable and Tray Routing Layout - Indoor_IFA | 2026-04-07 | 2026-04-10 | 2026-04-07 | 2026-04-10 | 2026-09-04 | 3 | 2026-09-09 | 108
A11910 | Cable and Tray Routing Layout - Indoor_RCA | 2026-04-13 | 2026-05-04 | 2026-04-13 | 2026-05-04 | 2026-09-10 | 16 | 2026-10-01 | 108
A11920 | Cable and Tray Routing Layout - Indoor_IFD/IFC | 2026-05-04 | 2026-05-06 | 2026-05-04 | 2026-05-06 | 2026-10-01 | 2 | 2026-10-05 | 108
Overall Lighting & Small Power Layout |  | 2026-02-20 | 2026-02-20 | 23-Aug-25 A | 23-Jan-26 A | 2026-10-05 | 118 | 2026-10-05
A11980 | Overall Lighting & Small Power Layout_IFR | 2026-02-20 | 2026-02-20 | 23-Aug-25 A | 13-Sep-25 A | 2026-10-05 | 6 | 2026-10-05
A11990 | Overall Lighting & Small Power Layout_RCC | 2026-02-20 | 2026-02-20 | 28-Aug-25 A | 20-Sep-25 A | 2026-10-05 | 16 | 2026-10-05
A12000 | Overall Lighting & Small Power Layout_IFA | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 24-Dec-25 A | 2026-10-05 | 3 | 2026-10-05
A12010 | Overall Lighting & Small Power Layout_RCA | 2026-02-20 | 2026-02-20 | 24-Dec-25 A | 15-Jan-26 A | 2026-10-05 | 16 | 2026-10-05
A12020 | Overall Lighting & Small Power Layout_IFD/IFC | 2026-02-20 | 2026-02-20 | 15-Jan-26 A | 23-Jan-26 A | 2026-10-05 | 6 | 2026-10-05
Earthing And Lightning Protection System Layout |  | 2026-02-20 | 2026-03-26 | 20-Dec-25 A | 2026-03-26 | 2026-09-01 | 59 | 2026-10-05 | 137
A12030 | Earthing And Lightning Protection System Layout_IFR | 2026-02-20 | 2026-02-20 | 20-Dec-25 A | 12-Jan-26 A | 2026-09-01 | 6 | 2026-09-01
A12040 | Earthing And Lightning Protection System Layout_RCC | 2026-02-20 | 2026-02-20 | 12-Jan-26 A | 17-Jan-26 A | 2026-09-01 | 16 | 2026-09-01
A12050 | Earthing And Lightning Protection System Layout_IFA | 2026-02-20 | 2026-02-25 | 2026-02-20 | 2026-02-25 | 2026-09-01 | 3 | 2026-09-04 | 137
A12060 | Earthing And Lightning Protection System Layout_RCA | 2026-02-25 | 2026-03-19 | 2026-02-25 | 2026-03-19 | 2026-09-04 | 16 | 2026-09-28 | 137
A12070 | Earthing And Lightning Protection System Layout_IFD/IFC | 2026-03-19 | 2026-03-26 | 2026-03-19 | 2026-03-26 | 2026-09-28 | 6 | 2026-10-05 | 137
Updation of Earthing Layout Butene 1, EU3, B3/EU3 |  | 2026-02-20 | 2026-04-17 | 10-Sep-25 A | 2026-04-17 | 2026-04-14 | 136 | 2027-01-20 | 199
A12080 | Updation of Earthing Layout Butene 1, EU3, B3/EU3_IFR | 2026-02-20 | 2026-02-20 | 10-Sep-25 A | 15-Sep-25 A | 2026-04-14 | 6 | 2026-04-14
A12090 | Updation of Earthing Layout Butene 1, EU3, B3/EU3_RCC | 2026-02-20 | 2026-03-13 | 2026-02-20 | 2026-03-13 | 2026-11-25 | 16 | 2026-12-17 | 199
A12100 | Updation of Earthing Layout Butene 1, EU3, B3/EU3_IFA | 2026-03-13 | 2026-03-19 | 2026-03-13 | 2026-03-19 | 2026-12-17 | 3 | 2026-12-22 | 199
A12110 | Updation of Earthing Layout Butene 1, EU3, B3/EU3_RCA | 2026-03-19 | 2026-04-09 | 2026-03-19 | 2026-04-09 | 2026-12-22 | 16 | 2027-01-13 | 199
A12120 | Updation of Earthing Layout Butene 1, EU3, B3/EU3_IFD/IFC | 2026-04-09 | 2026-04-17 | 2026-04-09 | 2026-04-17 | 2027-01-13 | 6 | 2027-01-20 | 199
Electrical Bulk MTO |  | 2026-02-20 | 2026-02-20 | 20-Apr-25 A | 25-May-25 A | 2026-04-14 | 73 | 2026-05-26
A13430 | Electrical Bulk MTO_IFR | 2026-02-20 | 2026-02-20 | 20-Apr-25 A | 11-May-25 A | 2026-04-14 | 6 | 2026-04-14
A13440 | Electrical Bulk MTO_RCC | 2026-02-20 | 2026-02-20 | 12-May-25 A | 18-May-25 A | 2026-04-14 | 16 | 2026-04-14
A13470 | Electrical Bulk MTO_IFD/IFC | 2026-02-20 | 2026-02-20 | 19-May-25 A | 25-May-25 A | 2026-05-26 | 2 | 2026-05-26
Instrumentation |  | 2026-02-20 | 2026-06-03 | 31-Dec-24 A | 2026-06-03 | 2026-03-02 | 384 | 2027-01-20 | 166
Scope of Work for the ICSS System |  | 2026-02-20 | 2026-04-14 | 01-Jul-25 A | 2026-04-14 | 2026-03-19 | 212 | 2027-01-20 | 202
A14530 | Scope of Work for the ICSS System_IFR | 2026-02-20 | 2026-02-20 | 01-Jul-25 A | 12-Jul-25 A | 2026-03-19 | 6 | 2026-03-19
A14540 | Scope of Work for the ICSS System_RCC | 2026-02-20 | 2026-03-13 | 2026-02-20 | 2026-03-13 | 2026-11-30 | 16 | 2026-12-22 | 202
A14550 | Scope of Work for the ICSS System_IFA | 2026-03-13 | 2026-03-19 | 2026-03-13 | 2026-03-19 | 2026-12-22 | 3 | 2026-12-25 | 202
A14560 | Scope of Work for the ICSS System_RCA | 2026-03-19 | 2026-04-09 | 2026-03-19 | 2026-04-09 | 2026-12-28 | 16 | 2027-01-18 | 202
A14570 | Scope of Work for the ICSS System_IFD/IFC | 2026-04-09 | 2026-04-14 | 2026-04-09 | 2026-04-14 | 2027-01-18 | 2 | 2027-01-20 | 202
Scope of Work for the MCMS System |  | 2026-02-20 | 2026-04-14 | 01-Mar-25 A | 2026-04-14 | 2026-03-19 | 212 | 2027-01-20 | 202
A58490 | Scope of Work for the MCMS System_IFR | 2026-02-20 | 2026-02-20 | 01-Mar-25 A | 10-Mar-25 A | 2026-03-19 | 6 | 2026-03-19
A58500 | Scope of Work for the MCMS System_RCC | 2026-02-20 | 2026-03-13 | 2026-02-20 | 2026-03-13 | 2026-11-30 | 16 | 2026-12-22 | 202
A58510 | Scope of Work for the MCMS System_IFA | 2026-03-13 | 2026-03-19 | 2026-03-13 | 2026-03-19 | 2026-12-22 | 3 | 2026-12-25 | 202
A58520 | Scope of Work for the MCMSSystem_RCA | 2026-03-19 | 2026-04-09 | 2026-03-19 | 2026-04-09 | 2026-12-28 | 16 | 2027-01-18 | 202
A58530 | Scope of Work for the MCMS System_IFD/IFC | 2026-04-09 | 2026-04-14 | 2026-04-09 | 2026-04-14 | 2027-01-18 | 2 | 2027-01-20 | 202
Instrument Datasheet for ESD Valves |  | 2026-02-20 | 2026-02-24 | 13-Mar-25 A | 2026-02-24 | 2026-03-02 | 293 | 2026-03-19 | 18
A14430 | Instrument Datasheet for ESD Valves_IFR | 2026-02-20 | 2026-02-20 | 13-Mar-25 A | 27-Apr-25 A | 2026-03-02 | 1 | 2026-03-02
A14440 | Instrument Datasheet for ESD Valves_RCC | 2026-02-20 | 2026-02-20 | 28-Apr-25 A | 13-Jun-25 A | 2026-03-17 | 16 | 2026-03-17
A14450 | Instrument Datasheet for ESD Valves_IFA | 2026-02-20 | 2026-02-20 | 14-Jun-25 A | 21-Jun-25 A | 2026-03-17 | 3 | 2026-03-17
A14460 | Instrument Datasheet for ESD Valves_RCA | 2026-02-20 | 2026-02-20 | 24-Nov-25 A | 22-Jan-26 A | 2026-03-17 | 16 | 2026-03-17
A14470 | Instrument Datasheet for ESD Valves_IFD/IFC | 2026-02-20 | 2026-02-24 | 2026-02-20 | 2026-02-24 | 2026-03-17 | 2 | 2026-03-19 | 18
Instrument Datasheet for Control Valves |  | 2026-02-20 | 2026-02-20 | 13-Mar-25 A | 10-Sep-25 A | 2026-03-19 | 196 | 2026-03-19
A14280 | Instrument Datasheet for Control Valves_IFR | 2026-02-20 | 2026-02-20 | 13-Mar-25 A | 27-Apr-25 A | 2026-03-19 | 1 | 2026-03-19
A14290 | Instrument Datasheet for Control Valves_RCC | 2026-02-20 | 2026-02-20 | 28-Apr-25 A | 21-Jun-25 A | 2026-03-19 | 16 | 2026-03-19
A14300 | Instrument Datasheet for Control Valves_IFA | 2026-02-20 | 2026-02-20 | 22-Jun-25 A | 28-Jun-25 A | 2026-03-19 | 3 | 2026-03-19
A14310 | Instrument Datasheet for Control Valves_RCA | 2026-02-20 | 2026-02-20 | 19-Aug-25 A | 08-Sep-25 A | 2026-03-19 | 16 | 2026-03-19
A14320 | Instrument Datasheet for Control Valves_IFD/IFC | 2026-02-20 | 2026-02-20 | 09-Sep-25 A | 10-Sep-25 A | 2026-03-19 | 2 | 2026-03-19
Instrument Datasheet for Motor Operated Valves |  | 2026-02-20 | 2026-02-20 | 13-Mar-25 A | 10-Sep-25 A | 2026-03-19 | 195 | 2026-03-19
A14330 | Instrument Datasheet for Motor Operated Valves_IFR | 2026-02-20 | 2026-02-20 | 13-Mar-25 A | 27-Apr-25 A | 2026-03-19 | 1 | 2026-03-19
A14340 | Instrument Datasheet for Motor Operated Valves_RCC | 2026-02-20 | 2026-02-20 | 28-Apr-25 A | 13-Jun-25 A | 2026-03-19 | 16 | 2026-03-19
A14350 | Instrument Datasheet for Motor Operated Valves_IFA | 2026-02-20 | 2026-02-20 | 14-Jun-25 A | 21-Jun-25 A | 2026-03-19 | 3 | 2026-03-19
A14360 | Instrument Datasheet for Motor Operated Valves_RCA | 2026-02-20 | 2026-02-20 | 19-Aug-25 A | 08-Sep-25 A | 2026-03-19 | 16 | 2026-03-19
A14370 | Instrument Datasheet for Motor Operated Valves_IFD/IFC | 2026-02-20 | 2026-02-20 | 09-Sep-25 A | 10-Sep-25 A | 2026-03-19 | 2 | 2026-03-19
Instrument Datasheet for Analyzers |  | 2026-02-20 | 2026-02-24 | 01-Jul-25 A | 2026-02-24 | 2026-03-02 | 166 | 2026-03-17 | 15
A14130 | Instrument Datasheet for Analyzers_IFR | 2026-02-20 | 2026-02-20 | 01-Jul-25 A | 12-Jul-25 A | 2026-03-02 | 1 | 2026-03-02
A14140 | Instrument Datasheet for Analyzers_RCC | 2026-02-20 | 2026-02-20 | 04-Aug-25 A | 25-Aug-25 A | 2026-03-13 | 16 | 2026-03-13
A14150 | Instrument Datasheet for Analyzers_IFA | 2026-02-20 | 2026-02-20 | 22-Aug-25 A | 30-Aug-25 A | 2026-03-13 | 3 | 2026-03-13
A14160 | Instrument Datasheet for Analyzers_RCA | 2026-02-20 | 2026-02-20 | 25-Aug-25 A | 06-Sep-25 A | 2026-03-13 | 16 | 2026-03-13
A14170 | Instrument Datasheet for Analyzers_IFD/IFC | 2026-02-20 | 2026-02-24 | 2026-02-20 | 2026-02-24 | 2026-03-13 | 2 | 2026-03-17 | 15
Instrument Datasheet for Flow Element (Orifice Plate) |  | 2026-02-20 | 2026-02-20 | 07-Apr-25 A | 23-Dec-25 A | 2026-03-02 | 244 | 2027-01-20
A13830 | Instrument Datasheet for Flow Element (Orifice Plate)_IFR | 2026-02-20 | 2026-02-20 | 07-Apr-25 A | 28-Apr-25 A | 2026-03-02 | 1 | 2026-03-02
A13840 | Instrument Datasheet for Flow Element (Orifice Plate)_RCC | 2026-02-20 | 2026-02-20 | 29-Apr-25 A | 21-Jun-25 A | 2027-01-20 | 16 | 2027-01-20
A13850 | Instrument Datasheet for Flow Element (Orifice Plate)_IFA | 2026-02-20 | 2026-02-20 | 22-Jun-25 A | 28-Jun-25 A | 2027-01-20 | 3 | 2027-01-20
A13860 | Instrument Datasheet for Flow Element (Orifice Plate)_RCA | 2026-02-20 | 2026-02-20 | 29-Jun-25 A | 05-Jul-25 A | 2027-01-20 | 16 | 2027-01-20
A13870 | Instrument Datasheet for Flow Element (Orifice Plate)_IFD/IFC | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 23-Dec-25 A | 2027-01-20 | 2 | 2027-01-20
Instrument Datasheet for Flow Element (Venturi Tube) |  | 2026-02-20 | 2026-02-20 | 13-Mar-25 A | 22-Aug-25 A | 2026-03-02 | 178 | 2026-03-02
A13880 | Instrument Datasheet for Flow Element (Venturi Tube)_IFR | 2026-02-20 | 2026-02-20 | 13-Mar-25 A | 27-Apr-25 A | 2026-03-02 | 1 | 2026-03-02
A13890 | Instrument Datasheet for Flow Element (Venturi Tube)_RCC | 2026-02-20 | 2026-02-20 | 28-Apr-25 A | 13-Jun-25 A | 2026-03-02 | 16 | 2026-03-02
A13900 | Instrument Datasheet for Flow Element (Venturi Tube)_IFA | 2026-02-20 | 2026-02-20 | 14-Jun-25 A | 21-Jun-25 A | 2026-03-02 | 3 | 2026-03-02
A13910 | Instrument Datasheet for Flow Element (Venturi Tube)_RCA | 2026-02-20 | 2026-02-20 | 22-Jun-25 A | 28-Jun-25 A | 2026-03-02 | 16 | 2026-03-02
A13920 | Instrument Datasheet for Flow Element (Venturi Tube)_IFD/IFC | 2026-02-20 | 2026-02-20 | 19-Aug-25 A | 22-Aug-25 A | 2026-03-02 | 2 | 2026-03-02
Instrument Datasheet for Rotameter |  | 2026-02-20 | 2026-02-20 | 13-Mar-25 A | 21-Nov-25 A | 2026-03-02 | 222 | 2026-03-19
A14480 | Instrument Datasheet for Rotameter_IFR | 2026-02-20 | 2026-02-20 | 13-Mar-25 A | 27-Apr-25 A | 2026-03-02 | 1 | 2026-03-02
A14490 | Instrument Datasheet for Rotameter_RCC | 2026-02-20 | 2026-02-20 | 28-Apr-25 A | 13-Jun-25 A | 2026-03-19 | 16 | 2026-03-19
A14500 | Instrument Datasheet for Rotameter_IFA | 2026-02-20 | 2026-02-20 | 14-Jun-25 A | 21-Jun-25 A | 2026-03-19 | 3 | 2026-03-19
A14510 | Instrument Datasheet for Rotameter_RCA | 2026-02-20 | 2026-02-20 | 22-Jun-25 A | 08-Sep-25 A | 2026-03-19 | 16 | 2026-03-19
A14520 | Instrument Datasheet for Rotameter_IFD/IFC | 2026-02-20 | 2026-02-20 | 14-Nov-25 A | 21-Nov-25 A | 2026-03-19 | 2 | 2026-03-19
Instrument Datasheet for Electronic Transmitters (Pressure / Level / DP) |  | 2026-02-20 | 2026-02-20 | 26-Mar-25 A | 23-Dec-25 A | 2026-03-02 | 241 | 2026-03-19
A13680 | Instrument Datasheet for Electronic Transmitters (Pressure / Level / DP)_IFR | 2026-02-20 | 2026-02-20 | 26-Mar-25 A | 16-Apr-25 A | 2026-03-02 | 1 | 2026-03-02
A13690 | Instrument Datasheet for Electronic Transmitters (Pressure / Level / DP)_RCC | 2026-02-20 | 2026-02-20 | 17-Apr-25 A | 02-May-25 A | 2026-03-19 | 16 | 2026-03-19
A13700 | Instrument Datasheet for Electronic Transmitters (Pressure / Level / DP)_IFA | 2026-02-20 | 2026-02-20 | 19-Aug-25 A | 23-Aug-25 A | 2026-03-19 | 3 | 2026-03-19
A13710 | Instrument Datasheet for Electronic Transmitters (Pressure / Level / DP)_RCA | 2026-02-20 | 2026-02-20 | 16-Aug-25 A | 30-Aug-25 A | 2026-03-19 | 16 | 2026-03-19
A13720 | Instrument Datasheet for Electronic Transmitters (Pressure / Level / DP)_IFD/IFC | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 23-Dec-25 A | 2026-03-19 | 2 | 2026-03-19
Instrument Datasheet for Electronic Transmitters (Flow) |  | 2026-02-20 | 2026-02-20 | 13-Mar-25 A | 23-Dec-25 A | 2026-03-02 | 240 | 2026-03-19
A13730 | Instrument Datasheet for Electronic Transmitters (Flow)_IFR | 2026-02-20 | 2026-02-20 | 13-Mar-25 A | 27-Apr-25 A | 2026-03-02 | 1 | 2026-03-02
A13740 | Instrument Datasheet for Electronic Transmitters (Flow)_RCC | 2026-02-20 | 2026-02-20 | 28-Apr-25 A | 04-May-25 A | 2026-03-19 | 16 | 2026-03-19
A13750 | Instrument Datasheet for Electronic Transmitters (Flow)_IFA | 2026-02-20 | 2026-02-20 | 05-May-25 A | 21-Jun-25 A | 2026-03-19 | 3 | 2026-03-19
A13760 | Instrument Datasheet for Electronic Transmitters (Flow)_RCA | 2026-02-20 | 2026-02-20 | 22-Jun-25 A | 10-Sep-25 A | 2026-03-19 | 16 | 2026-03-19
A13770 | Instrument Datasheet for Electronic Transmitters (Flow)_IFD/IFC | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 23-Dec-25 A | 2026-03-19 | 2 | 2026-03-19
Instrument Datasheet for Temperature Transmitters (Head mounted) |  | 2026-02-20 | 2026-02-24 | 25-Mar-25 A | 2026-02-24 | 2026-03-02 | 284 | 2027-01-20 | 237
A14380 | Instrument Datasheet for Temperature Transmitters (Head mounted)_IFR | 2026-02-20 | 2026-02-20 | 25-Mar-25 A | 21-Jun-25 A | 2026-03-02 | 1 | 2026-03-02
A14390 | Instrument Datasheet for Temperature Transmitters (Head mounted)_RCC | 2026-02-20 | 2026-02-20 | 22-Jun-25 A | 28-Jun-25 A | 2027-01-18 | 16 | 2027-01-18
A14400 | Instrument Datasheet for Temperature Transmitters (Head mounted)_IFA | 2026-02-20 | 2026-02-20 | 29-Jun-25 A | 05-Jul-25 A | 2027-01-18 | 3 | 2027-01-18
A14410 | Instrument Datasheet for Temperature Transmitters (Head mounted)_RCA | 2026-02-20 | 2026-02-20 | 06-Jul-25 A | 12-Jul-25 A | 2027-01-18 | 16 | 2027-01-18
A14420 | Instrument Datasheet for Temperature Transmitters (Head mounted)_IFD/IFC | 2026-02-20 | 2026-02-24 | 2026-02-20 | 2026-02-24 | 2027-01-18 | 2 | 2027-01-20 | 237
Instrument Datasheet for Level Transmitters (GWR type) |  | 2026-02-20 | 2026-02-20 | 13-Mar-25 A | 18-Dec-25 A | 2026-03-02 | 232 | 2027-01-20
A14080 | Instrument Datasheet for Level Transmitters (GWR type)_IFR | 2026-02-20 | 2026-02-20 | 13-Mar-25 A | 27-Apr-25 A | 2026-03-02 | 1 | 2026-03-02
A14090 | Instrument Datasheet for Level Transmitters (GWR type)_RCC | 2026-02-20 | 2026-02-20 | 28-Apr-25 A | 23-Jun-25 A | 2026-03-19 | 16 | 2026-03-19
A14100 | Instrument Datasheet for Level Transmitters (GWR type)_IFA | 2026-02-20 | 2026-02-20 | 19-Aug-25 A | 23-Aug-25 A | 2026-03-19 | 3 | 2026-03-19
A14110 | Instrument Datasheet for Level Transmitters (GWR type)_RCA | 2026-02-20 | 2026-02-20 | 03-Nov-25 A | 21-Nov-25 A | 2027-01-20 | 16 | 2027-01-20
A14120 | Instrument Datasheet for Level Transmitters (GWR type)_IFD/IFC | 2026-02-20 | 2026-02-20 | 08-Dec-25 A | 18-Dec-25 A | 2027-01-20 | 2 | 2027-01-20
Instrument Datasheet for Temperature Element / Thermowell |  | 2026-02-20 | 2026-02-20 | 29-May-25 A | 23-Dec-25 A | 2026-03-02 | 237 | 2026-03-19
A13930 | Instrument Datasheet for Temperature Element / Thermowell_IFR | 2026-02-20 | 2026-02-20 | 29-May-25 A | 20-Jun-25 A | 2026-03-02 | 1 | 2026-03-02
A13940 | Instrument Datasheet for Temperature Element / Thermowell_RCC | 2026-02-20 | 2026-02-20 | 30-May-25 A | 28-Jun-25 A | 2026-03-19 | 16 | 2026-03-19
A13950 | Instrument Datasheet for Temperature Element / Thermowell_IFA | 2026-02-20 | 2026-02-20 | 30-Jun-25 A | 07-Jul-25 A | 2026-03-19 | 3 | 2026-03-19
A13960 | Instrument Datasheet for Temperature Element / Thermowell_RCA | 2026-02-20 | 2026-02-20 | 02-Jul-25 A | 18-Jul-25 A | 2026-03-19 | 16 | 2026-03-19
A13970 | Instrument Datasheet for Temperature Element / Thermowell_IFD/IFC | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 23-Dec-25 A | 2026-03-19 | 2 | 2026-03-19
Instrument Datasheet for Temperature Gauges / Thermowell |  | 2026-02-20 | 2026-02-20 | 13-Mar-25 A | 23-Dec-25 A | 2026-03-02 | 236 | 2027-01-20
A14030 | Instrument Datasheet for Temperature Gauges / Thermowell_IFR | 2026-02-20 | 2026-02-20 | 13-Mar-25 A | 28-Apr-25 A | 2026-03-02 | 1 | 2026-03-02
A14040 | Instrument Datasheet for Temperature Gauges / Thermowell_RCC | 2026-02-20 | 2026-02-20 | 19-Apr-25 A | 13-Jun-25 A | 2027-01-20 | 16 | 2027-01-20
A14050 | Instrument Datasheet for Temperature Gauges / Thermowell_IFA | 2026-02-20 | 2026-02-20 | 11-Jul-25 A | 28-Jul-25 A | 2027-01-20 | 3 | 2027-01-20
A14060 | Instrument Datasheet for Temperature Gauges / Thermowell_RCA | 2026-02-20 | 2026-02-20 | 20-Oct-25 A | 12-Nov-25 A | 2027-01-20 | 16 | 2027-01-20
A14070 | Instrument Datasheet for Temperature Gauges / Thermowell_IFD/IFC | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 23-Dec-25 A | 2027-01-20 | 2 | 2027-01-20
Instrument Datasheet for Pressure Gauges |  | 2026-02-20 | 2026-02-20 | 21-Apr-25 A | 23-Dec-25 A | 2026-03-02 | 235 | 2027-01-18
A13980 | Instrument Datasheet for Pressure Gauges_IFR | 2026-02-20 | 2026-02-20 | 21-Apr-25 A | 27-Apr-25 A | 2026-03-02 | 1 | 2026-03-02
A13990 | Instrument Datasheet for Pressure Gauges_RCC | 2026-02-20 | 2026-02-20 | 26-Jun-25 A | 20-Jul-25 A | 2026-12-22 | 16 | 2026-12-22
A14000 | Instrument Datasheet for Pressure Gauges_IFA | 2026-02-20 | 2026-02-20 | 31-Jul-25 A | 13-Aug-25 A | 2026-12-22 | 3 | 2026-12-22
A14010 | Instrument Datasheet for Pressure Gauges_RCA | 2026-02-20 | 2026-02-20 | 01-Nov-25 A | 21-Nov-25 A | 2027-01-18 | 16 | 2027-01-18
A14020 | Instrument Datasheet for Pressure Gauges_IFD/IFC | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 23-Dec-25 A | 2027-01-18 | 2 | 2027-01-18
Instrument Datasheet for Level Gauges (Magnetic Type) |  | 2026-02-20 | 2026-02-20 | 13-Mar-25 A | 22-Aug-25 A | 2026-03-02 | 169 | 2026-03-02
A14180 | Instrument Datasheet for Level Gauges (Magnetic Type)_IFR | 2026-02-20 | 2026-02-20 | 13-Mar-25 A | 27-Apr-25 A | 2026-03-02 | 1 | 2026-03-02
A14190 | Instrument Datasheet for Level Gauges (Magnetic Type)_RCC | 2026-02-20 | 2026-02-20 | 24-Apr-25 A | 13-Jun-25 A | 2026-03-02 | 16 | 2026-03-02
A14200 | Instrument Datasheet for Level Gauges (Magnetic Type)_IFA | 2026-02-20 | 2026-02-20 | 14-Jun-25 A | 21-Jun-25 A | 2026-03-02 | 3 | 2026-03-02
A14210 | Instrument Datasheet for Level Gauges (Magnetic Type)_RCA | 2026-02-20 | 2026-02-20 | 22-Jun-25 A | 28-Jun-25 A | 2026-03-02 | 16 | 2026-03-02
A14220 | Instrument Datasheet for Level Gauges (Magnetic Type)_IFD/IFC | 2026-02-20 | 2026-02-20 | 19-Aug-25 A | 22-Aug-25 A | 2026-03-02 | 2 | 2026-03-02
Instrument Datasheet for Fire & Gas Detectors |  | 2026-02-20 | 2026-02-20 | 26-May-25 A | 23-Dec-25 A | 2026-03-19 | 122 | 2026-03-19
A14230 | Instrument Datasheet for Fire & Gas Detectors_IFR | 2026-02-20 | 2026-02-20 | 26-May-25 A | 05-Jul-25 A | 2026-03-19 | 1 | 2026-03-19
A14240 | Instrument Datasheet for Fire & Gas Detectors_RCC | 2026-02-20 | 2026-02-20 | 07-Aug-25 A | 01-Sep-25 A | 2026-03-19 | 11 | 2026-03-19
A14250 | Instrument Datasheet for Fire & Gas Detectors_IFA | 2026-02-20 | 2026-02-20 | 26-Sep-25 A | 13-Oct-25 A | 2026-03-19 | 3 | 2026-03-19
A14260 | Instrument Datasheet for Fire & Gas Detectors_RCA | 2026-02-20 | 2026-02-20 | 10-Oct-25 A | 25-Oct-25 A | 2026-03-19 | 16 | 2026-03-19
A14270 | Instrument Datasheet for Fire & Gas Detectors_IFD/IFC | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 23-Dec-25 A | 2026-03-19 | 2 | 2026-03-19
Instrument Datasheet for Loop Powered Indicator |  | 2026-02-20 | 2026-02-20 | 07-Apr-25 A | 05-Jul-25 A | 2027-01-20 | 132 | 2027-01-20
A13780 | Instrument Datasheet for Loop Powered Indicator_IFR | 2026-02-20 | 2026-02-20 | 07-Apr-25 A | 28-Apr-25 A | 2027-01-20 | 1 | 2027-01-20
A13790 | Instrument Datasheet for Loop Powered Indicator_RCC | 2026-02-20 | 2026-02-20 | 29-Apr-25 A | 30-May-25 A | 2027-01-20 | 16 | 2027-01-20
A13800 | Instrument Datasheet for Loop Powered Indicator_IFA | 2026-02-20 | 2026-02-20 | 01-Jun-25 A | 21-Jun-25 A | 2027-01-20 | 3 | 2027-01-20
A13810 | Instrument Datasheet for Loop Powered Indicator_RCA | 2026-02-20 | 2026-02-20 | 22-Jun-25 A | 28-Jun-25 A | 2027-01-20 | 16 | 2027-01-20
A13820 | Instrument Datasheet for Loop Powered Indicator_IFD/IFC | 2026-02-20 | 2026-02-20 | 29-Jun-25 A | 05-Jul-25 A | 2027-01-20 | 2 | 2027-01-20
Material Requisition for ESD Valves |  | 2026-02-20 | 2026-02-20 | 24-Mar-25 A | 03-Sep-25 A | 2026-03-02 | 225 | 2026-03-19
A15130 | Material Requisition for ESD Valves_IFR | 2026-02-20 | 2026-02-20 | 24-Mar-25 A | 30-Apr-25 A | 2026-03-02 | 2 | 2026-03-02
A15140 | Material Requisition for ESD Valves_RCC | 2026-02-20 | 2026-02-20 | 01-May-25 A | 21-Jun-25 A | 2026-03-19 | 16 | 2026-03-19
A15150 | Material Requisition for ESD Valves_IFA | 2026-02-20 | 2026-02-20 | 22-Jun-25 A | 28-Jun-25 A | 2026-03-19 | 3 | 2026-03-19
A15160 | Material Requisition for ESD Valves_RCA | 2026-02-20 | 2026-02-20 | 29-Jun-25 A | 27-Aug-25 A | 2026-03-19 | 16 | 2026-03-19
A15170 | Material Requisition for ESD Valves_IFD/IFC | 2026-02-20 | 2026-02-20 | 28-Aug-25 A | 03-Sep-25 A | 2026-03-19 | 2 | 2026-03-19
Material Requisition for Control Valves |  | 2026-02-20 | 2026-02-20 | 13-Mar-25 A | 19-Sep-25 A | 2026-03-19 | 197 | 2026-03-19
A14980 | Material Requisition for Control Valves_IFR | 2026-02-20 | 2026-02-20 | 13-Mar-25 A | 27-Apr-25 A | 2026-03-19 | 2 | 2026-03-19
A14990 | Material Requisition for Control Valves_RCC | 2026-02-20 | 2026-02-20 | 28-Apr-25 A | 21-Jun-25 A | 2026-03-19 | 16 | 2026-03-19
A15000 | Material Requisition for Control Valves_IFA | 2026-02-20 | 2026-02-20 | 22-Jun-25 A | 28-Jun-25 A | 2026-03-19 | 3 | 2026-03-19
A15010 | Material Requisition for Control Valves_RCA | 2026-02-20 | 2026-02-20 | 29-Jun-25 A | 02-Sep-25 A | 2026-03-19 | 16 | 2026-03-19
A15020 | Material Requisition for Control Valves_IFD/IFC | 2026-02-20 | 2026-02-20 | 10-Sep-25 A | 19-Sep-25 A | 2026-03-19 | 2 | 2026-03-19
Material Requisition for Motor Operated Valves |  | 2026-02-20 | 2026-02-20 | 24-Mar-25 A | 13-Sep-25 A | 2026-03-19 | 196 | 2026-03-19
A15080 | Material Requisition for Motor Operated Valves_IFR | 2026-02-20 | 2026-02-20 | 24-Mar-25 A | 27-Apr-25 A | 2026-03-19 | 2 | 2026-03-19
A15090 | Material Requisition for Motor Operated Valves_RCC | 2026-02-20 | 2026-02-20 | 28-Apr-25 A | 13-Jun-25 A | 2026-03-19 | 16 | 2026-03-19
A15100 | Material Requisition for Motor Operated Valves_IFA | 2026-02-20 | 2026-02-20 | 14-Jun-25 A | 21-Jun-25 A | 2026-03-19 | 3 | 2026-03-19
A15110 | Material Requisition for Motor Operated Valves_RCA | 2026-02-20 | 2026-02-20 | 22-Jun-25 A | 08-Sep-25 A | 2026-03-19 | 16 | 2026-03-19
A15120 | Material Requisition for Motor Operated Valves_IFD/IFC | 2026-02-20 | 2026-02-20 | 11-Sep-25 A | 13-Sep-25 A | 2026-03-19 | 2 | 2026-03-19
Material Requisition for Analyzers |  | 2026-02-20 | 2026-02-26 | 01-Jul-25 A | 2026-02-26 | 2026-03-17 | 168 | 2026-03-19 | 15
A14830 | Material Requisition for Analyzers_IFR | 2026-02-20 | 2026-02-20 | 01-Jul-25 A | 15-Jul-25 A | 2026-03-17 | 2 | 2026-03-17
A14840 | Material Requisition for Analyzers_RCC | 2026-02-20 | 2026-02-20 | 01-Aug-25 A | 25-Aug-25 A | 2026-03-17 | 16 | 2026-03-17
A14850 | Material Requisition for Analyzers_IFA | 2026-02-20 | 2026-02-20 | 26-Aug-25 A | 30-Aug-25 A | 2026-03-17 | 3 | 2026-03-17
A14860 | Material Requisition for Analyzers_RCA | 2026-02-20 | 2026-02-20 | 20-Aug-25 A | 11-Sep-25 A | 2026-03-17 | 16 | 2026-03-17
A14870 | Material Requisition for Analyzers_IFD/IFC | 2026-02-24 | 2026-02-26 | 2026-02-24 | 2026-02-26 | 2026-03-17 | 2 | 2026-03-19 | 15
Material Requisition for Flow Element (Orifice Plate) |  | 2026-02-20 | 2026-02-20 | 14-Mar-25 A | 25-Dec-25 A | 2026-06-04 | 246 | 2027-01-20
A14630 | Material Requisition for Flow Element (Orifice Plate)_IFR | 2026-02-20 | 2026-02-20 | 14-Mar-25 A | 29-Apr-25 A | 2026-06-04 | 2 | 2026-06-04
A14640 | Material Requisition for Flow Element (Orifice Plate)_RCC | 2026-02-20 | 2026-02-20 | 30-Apr-25 A | 21-Jun-25 A | 2027-01-20 | 16 | 2027-01-20
A14650 | Material Requisition for Flow Element (Orifice Plate)_IFA | 2026-02-20 | 2026-02-20 | 22-Jun-25 A | 28-Jun-25 A | 2027-01-20 | 3 | 2027-01-20
A14660 | Material Requisition for Flow Element (Orifice Plate)_RCA | 2026-02-20 | 2026-02-20 | 29-Jun-25 A | 05-Jul-25 A | 2027-01-20 | 16 | 2027-01-20
A14670 | Material Requisition for Flow Element (Orifice Plate)_IFD/IFC | 2026-02-20 | 2026-02-20 | 23-Dec-25 A | 25-Dec-25 A | 2027-01-20 | 2 | 2027-01-20
Material Requisition for Flow Element (Venturi Tube) |  | 2026-02-20 | 2026-02-20 | 13-Mar-25 A | 15-Sep-25 A | 2026-03-02 | 172 | 2026-03-02
A14680 | Material Requisition for Flow Element (Venturi Tube)_IFR | 2026-02-20 | 2026-02-20 | 13-Mar-25 A | 30-Apr-25 A | 2026-03-02 | 2 | 2026-03-02
A14690 | Material Requisition for Flow Element (Venturi Tube)_RCC | 2026-02-20 | 2026-02-20 | 01-May-25 A | 21-Jun-25 A | 2026-03-02 | 16 | 2026-03-02
A14700 | Material Requisition for Flow Element (Venturi Tube)_IFA | 2026-02-20 | 2026-02-20 | 22-Jun-25 A | 28-Jun-25 A | 2026-03-02 | 3 | 2026-03-02
A14710 | Material Requisition for Flow Element (Venturi Tube)_RCA | 2026-02-20 | 2026-02-20 | 22-Aug-25 A | 11-Sep-25 A | 2026-03-02 | 16 | 2026-03-02
A14720 | Material Requisition for Flow Element (Venturi Tube)_IFD/IFC | 2026-02-20 | 2026-02-20 | 12-Sep-25 A | 15-Sep-25 A | 2026-03-02 | 2 | 2026-03-02
Material Requisition for Rotameter |  | 2026-02-20 | 2026-02-20 | 25-Mar-25 A | 04-Oct-25 A | 2026-03-19 | 204 | 2026-03-19
A15180 | Material Requisition for Rotameter_IFR | 2026-02-20 | 2026-02-20 | 25-Mar-25 A | 01-May-25 A | 2026-03-19 | 1 | 2026-03-19
A15190 | Material Requisition for Rotameter_RCC | 2026-02-20 | 2026-02-20 | 02-May-25 A | 21-Jun-25 A | 2026-03-19 | 16 | 2026-03-19
A15200 | Material Requisition for Rotameter_IFA | 2026-02-20 | 2026-02-20 | 14-Jun-25 A | 28-Jun-25 A | 2026-03-19 | 3 | 2026-03-19
A15210 | Material Requisition for Rotameter_RCA | 2026-02-20 | 2026-02-20 | 22-Jun-25 A | 07-Jul-25 A | 2026-03-19 | 16 | 2026-03-19
A15220 | Material Requisition for Rotameter_IFD/IFC | 2026-02-20 | 2026-02-20 | 26-Sep-25 A | 04-Oct-25 A | 2026-03-19 | 2 | 2026-03-19
Material Requisition for Electronic Transmitters |  | 2026-02-20 | 2026-02-20 | 25-Mar-25 A | 25-Dec-25 A | 2026-03-19 | 241 | 2026-03-19
A14580 | Material Requisition for Electronic Transmitters_IFR | 2026-02-20 | 2026-02-20 | 25-Mar-25 A | 28-Apr-25 A | 2026-03-19 | 2 | 2026-03-19
A14590 | Material Requisition for Electronic Transmitters_RCC | 2026-02-20 | 2026-02-20 | 29-Apr-25 A | 30-Jul-25 A | 2026-03-19 | 16 | 2026-03-19
A14600 | Material Requisition for Electronic Transmitters_IFA | 2026-02-20 | 2026-02-20 | 31-Jul-25 A | 23-Aug-25 A | 2026-03-19 | 3 | 2026-03-19
A14610 | Material Requisition for Electronic Transmitters_RCA | 2026-02-20 | 2026-02-20 | 24-Aug-25 A | 06-Sep-25 A | 2026-03-19 | 16 | 2026-03-19
A14620 | Material Requisition for Electronic Transmitters_IFD/IFC | 2026-02-20 | 2026-02-20 | 23-Dec-25 A | 25-Dec-25 A | 2026-03-19 | 2 | 2026-03-19
Material Requisition for Level Transmitters (GWR type) |  | 2026-02-20 | 2026-02-20 | 26-Mar-25 A | 28-Aug-25 A | 2026-03-19 | 215 | 2026-03-19
A14880 | Material Requisition for Level Transmitters (GWR type)_IFR | 2026-02-20 | 2026-02-20 | 26-Mar-25 A | 28-Apr-25 A | 2026-03-19 | 2 | 2026-03-19
A14890 | Material Requisition for Level Transmitters (GWR type)_RCC | 2026-02-20 | 2026-02-20 | 04-Jul-25 A | 28-Jul-25 A | 2026-03-19 | 16 | 2026-03-19
A14900 | Material Requisition for Level Transmitters (GWR type)_IFA | 2026-02-20 | 2026-02-20 | 31-Jul-25 A | 11-Aug-25 A | 2026-03-19 | 3 | 2026-03-19
A14910 | Material Requisition for Level Transmitters (GWR type)_RCA | 2026-02-20 | 2026-02-20 | 01-Aug-25 A | 19-Aug-25 A | 2026-03-19 | 16 | 2026-03-19
A14920 | Material Requisition for Level Transmitters (GWR type)_IFD/IFC | 2026-02-20 | 2026-02-20 | 20-Aug-25 A | 28-Aug-25 A | 2026-03-19 | 2 | 2026-03-19
Material Requisition for Temperature Element / Thermowell |  | 2026-02-20 | 2026-02-20 | 13-Mar-25 A | 23-Jan-26 A | 2026-03-19 | 176 | 2026-03-19
A14730 | Material Requisition for Temperature Element / Thermowell_IFR | 2026-02-20 | 2026-02-20 | 13-Mar-25 A | 07-May-25 A | 2026-03-19 | 2 | 2026-03-19
A14740 | Material Requisition for Temperature Element / Thermowell_RCC | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 09-Jan-26 A | 2026-03-19 | 16 | 2026-03-19
A14750 | Material Requisition for Temperature Element / Thermowell_IFA | 2026-02-20 | 2026-02-20 | 09-Jan-26 A | 15-Jan-26 A | 2026-03-19 | 3 | 2026-03-19
A14760 | Material Requisition for Temperature Element / Thermowell_RCA | 2026-02-20 | 2026-02-20 | 15-Jan-26 A | 20-Jan-26 A | 2026-03-19 | 16 | 2026-03-19
A14770 | Material Requisition for Temperature Element / Thermowell_IFD/IFC | 2026-02-20 | 2026-02-20 | 20-Jan-26 A | 23-Jan-26 A | 2026-03-19 | 2 | 2026-03-19
Material Requisition for Temperature Gauges / Pressure Gauges |  | 2026-02-20 | 2026-03-23 | 25-Mar-25 A | 2026-03-23 | 2026-03-19 | 298 | 2027-01-20 | 218
A14780 | Material Requisition for Temperature Gauges / Pressure Gauges_IFR | 2026-02-20 | 2026-02-20 | 25-Mar-25 A | 30-Apr-25 A | 2026-03-19 | 2 | 2026-03-19
A14790 | Material Requisition for Temperature Gauges / Pressure Gauges_RCC | 2026-02-20 | 2026-02-20 | 01-May-25 A | 21-Jun-25 A | 2026-03-19 | 16 | 2026-03-19
A14800 | Material Requisition for Temperature Gauges / Pressure Gauges_IFA | 2026-02-20 | 2026-02-25 | 2026-02-20 | 2026-02-25 | 2026-12-22 | 3 | 2026-12-25 | 218
A14810 | Material Requisition for Temperature Gauges / Pressure Gauges_RCA | 2026-02-25 | 2026-03-19 | 2026-02-25 | 2026-03-19 | 2026-12-28 | 16 | 2027-01-18 | 218
A14820 | Material Requisition for Temperature Gauges / Pressure Gauges_IFD/IFC | 2026-03-19 | 2026-03-23 | 2026-03-19 | 2026-03-23 | 2027-01-18 | 2 | 2027-01-20 | 218
Material Requisition for Level Gauges (Magnetic Type) |  | 2026-02-20 | 2026-02-20 | 25-Mar-25 A | 17-Sep-25 A | 2026-03-02 | 180 | 2026-03-02
A14930 | Material Requisition for Level Gauges (Magnetic Type)_IFR | 2026-02-20 | 2026-02-20 | 25-Mar-25 A | 23-Apr-25 A | 2026-03-02 | 2 | 2026-03-02
A14940 | Material Requisition for Level Gauges (Magnetic Type)_RCC | 2026-02-20 | 2026-02-20 | 24-Apr-25 A | 30-Jul-25 A | 2026-03-02 | 16 | 2026-03-02
A14950 | Material Requisition for Level Gauges (Magnetic Type)_IFA | 2026-02-20 | 2026-02-20 | 31-Jul-25 A | 26-Aug-25 A | 2026-03-02 | 3 | 2026-03-02
A14960 | Material Requisition for Level Gauges (Magnetic Type)_RCA | 2026-02-20 | 2026-02-20 | 27-Aug-25 A | 02-Sep-25 A | 2026-03-02 | 16 | 2026-03-02
A14970 | Material Requisition for Level Gauges (Magnetic Type)_IFD/IFC | 2026-02-20 | 2026-02-20 | 03-Sep-25 A | 17-Sep-25 A | 2026-03-02 | 2 | 2026-03-02
Material Requisition for Fire & Gas Detectors |  | 2026-02-20 | 2026-02-20 | 27-May-25 A | 25-Dec-25 A | 2026-03-19 | 124 | 2026-03-19
A15030 | Material Requisition for Fire & Gas Detectors_IFR | 2026-02-20 | 2026-02-20 | 27-May-25 A | 05-Jul-25 A | 2026-03-19 | 2 | 2026-03-19
A15040 | Material Requisition for Fire & Gas Detectors_RCC | 2026-02-20 | 2026-02-20 | 07-Jul-25 A | 30-Jul-25 A | 2026-03-19 | 16 | 2026-03-19
A15050 | Material Requisition for Fire & Gas Detectors_IFA | 2026-02-20 | 2026-02-20 | 26-Sep-25 A | 06-Oct-25 A | 2026-03-19 | 3 | 2026-03-19
A15060 | Material Requisition for Fire & Gas Detectors_RCA | 2026-02-20 | 2026-02-20 | 29-Sep-25 A | 20-Oct-25 A | 2026-03-19 | 11 | 2026-03-19
A15070 | Material Requisition for Fire & Gas Detectors_IFD/IFC | 2026-02-20 | 2026-02-20 | 23-Dec-25 A | 25-Dec-25 A | 2026-03-19 | 2 | 2026-03-19
Material Requisition for Instrument Cables |  | 2026-02-20 | 2026-02-20 | 27-May-25 A | 08-Aug-25 A | 2026-03-19 | 81 | 2026-03-19
A47660 | Material Requisition for Instrument Cables_IFA | 2026-02-20 | 2026-02-20 | 02-Jun-25 A | 06-Jun-25 A | 2026-03-19 | 3 | 2026-03-19
A15230 | Material Requisition for Instrument Cables_IFR | 2026-02-20 | 2026-02-20 | 27-May-25 A | 05-Jul-25 A | 2026-03-19 | 2 | 2026-03-19
A47650 | Material Requisition for Instrument Cables_RCC | 2026-02-20 | 2026-02-20 | 07-Jul-25 A | 18-Jul-25 A | 2026-03-19 | 16 | 2026-03-19
A47670 | Material Requisition for Instrument Cables_RCA | 2026-02-20 | 2026-02-20 | 21-Jul-25 A | 01-Aug-25 A | 2026-03-19 | 16 | 2026-03-19
A47680 | Material Requisition for Instrument Cables_IFD/IFC | 2026-02-20 | 2026-02-20 | 04-Aug-25 A | 08-Aug-25 A | 2026-03-19 | 2 | 2026-03-19
Material Requisition for Junction Boxes |  | 2026-02-20 | 2026-02-20 | 27-May-25 A | 19-Dec-25 A | 2026-03-05 | 127 | 2026-03-19
A47690 | Material Requisition for Junction Boxes_IFR | 2026-02-20 | 2026-02-20 | 27-May-25 A | 05-Jul-25 A | 2026-03-05 | 2 | 2026-03-05
A47700 | Material Requisition for Junction Boxes_RCC | 2026-02-20 | 2026-02-20 | 22-Sep-25 A | 09-Oct-25 A | 2026-03-19 | 16 | 2026-03-19
A47710 | Material Requisition for Junction Boxes_IFA | 2026-02-20 | 2026-02-20 | 21-Oct-25 A | 03-Nov-25 A | 2026-03-19 | 3 | 2026-03-19
A47720 | Material Requisition for Junction Boxes_RCA | 2026-02-20 | 2026-02-20 | 03-Nov-25 A | 13-Nov-25 A | 2026-03-19 | 16 | 2026-03-19
A47730 | Material Requisition for Junction Boxes_IFD/IFC | 2026-02-20 | 2026-02-20 | 30-Nov-25 A | 19-Dec-25 A | 2026-03-19 | 2 | 2026-03-19
Material Requisition for ICSS System |  | 2026-02-20 | 2026-02-20 | 31-Dec-24 A | 14-Aug-25 A | 2026-03-02 | 157 | 2026-03-02
A47740 | Material Requisition for ICSS System_IFR | 2026-02-20 | 2026-02-20 | 31-Dec-24 A | 23-Jan-25 A | 2026-03-02 | 2 | 2026-03-02
A47750 | Material Requisition for ICSS System_RCC | 2026-02-20 | 2026-02-20 | 01-May-25 A | 30-May-25 A | 2026-03-02 | 16 | 2026-03-02
A47760 | Material Requisition for ICSS System_IFA | 2026-02-20 | 2026-02-20 | 02-Jun-25 A | 21-Jun-25 A | 2026-03-02 | 3 | 2026-03-02
A47770 | Material Requisition for ICSS System_RCA | 2026-02-20 | 2026-02-20 | 22-Jun-25 A | 28-Jun-25 A | 2026-03-02 | 16 | 2026-03-02
A15370 | Material Requisition for ICSS System_IFD/IFC | 2026-02-20 | 2026-02-20 | 04-Aug-25 A | 14-Aug-25 A | 2026-03-02 | 2 | 2026-03-02
Material Requisition for MCMS System |  | 2026-02-20 | 2026-02-20 | 20-Apr-25 A | 07-May-25 A | 2026-03-02 | 36 | 2026-03-02
A58190 | Material Requisition for MCMS System_IFR | 2026-02-20 | 2026-02-20 | 20-Apr-25 A | 24-Apr-25 A | 2026-03-02 | 2 | 2026-03-02
A58200 | Material Requisition for MCMS System_RCC | 2026-02-20 | 2026-02-20 | 25-Apr-25 A | 27-Apr-25 A | 2026-03-02 | 16 | 2026-03-02
A58210 | Material Requisition for MCMS System_IFA | 2026-02-20 | 2026-02-20 | 28-Apr-25 A | 01-May-25 A | 2026-03-02 | 3 | 2026-03-02
A58220 | Material Requisition for MCMS System_RCA | 2026-02-20 | 2026-02-20 | 02-May-25 A | 05-May-25 A | 2026-03-02 | 16 | 2026-03-02
A58230 | Material Requisition for MCMS System_IFD/IFC | 2026-02-20 | 2026-02-20 | 05-May-25 A | 07-May-25 A | 2026-03-02 | 2 | 2026-03-02
Technical Bid Evaluation for ESD Valves |  | 2026-02-20 | 2026-03-17 | 01-Oct-25 A | 2026-03-17 | 2026-12-28 | 103 | 2027-01-20 | 221
A16680 | Technical Bid Evaluation for ESD Valves_IFR | 2026-02-20 | 2026-02-20 | 01-Oct-25 A | 07-Oct-25 A | 2026-12-28 | 6 | 2026-12-28
A48240 | Technical Bid Evaluation for ESD Valves_RCC | 2026-02-20 | 2026-02-20 | 03-Oct-25 A | 14-Oct-25 A | 2026-12-28 | 16 | 2026-12-28
A16700 | Technical Bid Evaluation for ESD Valves_IFA | 2026-02-20 | 2026-02-20 | 28-Nov-25 A | 11-Dec-25 A | 2026-12-28 | 3 | 2026-12-28
A16710 | Technical Bid Evaluation for ESD Valves_RCA | 2026-02-20 | 2026-03-13 | 2026-02-20 | 2026-03-13 | 2026-12-28 | 16 | 2027-01-18 | 221
A16720 | Technical Bid Evaluation for ESD Valves_IFD/IFC | 2026-03-13 | 2026-03-17 | 2026-03-13 | 2026-03-17 | 2027-01-18 | 2 | 2027-01-20 | 221
Technical Bid Evaluation for Rotameter |  | 2026-02-20 | 2026-03-23 | 30-Nov-25 A | 2026-03-23 | 2026-12-22 | 86 | 2027-01-20 | 218
A16730 | Technical Bid Evaluation for Rotameter_IFR | 2026-02-20 | 2026-02-20 | 30-Nov-25 A | 08-Dec-25 A | 2026-12-22 | 6 | 2026-12-22
A16740 | Technical Bid Evaluation for Rotameter_RCC | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 09-Jan-26 A | 2026-12-22 | 16 | 2026-12-22
A48250 | Technical Bid Evaluation for Rotameter_IFA | 2026-02-20 | 2026-02-25 | 2026-02-20 | 2026-02-25 | 2026-12-22 | 3 | 2026-12-25 | 218
A16760 | Technical Bid Evaluation for Rotameter_RCA | 2026-02-25 | 2026-03-19 | 2026-02-25 | 2026-03-19 | 2026-12-28 | 16 | 2027-01-18 | 218
A16770 | Technical Bid Evaluation for Rotameter_IFD/IFC | 2026-03-19 | 2026-03-23 | 2026-03-19 | 2026-03-23 | 2027-01-18 | 2 | 2027-01-20 | 218
Technical Bid Evaluation for Level Transmitters (GWR type) |  | 2026-02-20 | 2026-02-20 | 23-Aug-25 A | 13-Jan-26 A | 2027-01-20 | 103 | 2027-01-20
A16580 | Technical Bid Evaluation for Level Transmitters (GWR type)_IFR | 2026-02-20 | 2026-02-20 | 23-Aug-25 A | 18-Sep-25 A | 2027-01-20 | 6 | 2027-01-20
A16590 | Technical Bid Evaluation for Level Transmitters (GWR type)_RCC | 2026-02-20 | 2026-02-20 | 05-Sep-25 A | 29-Sep-25 A | 2027-01-20 | 16 | 2027-01-20
A16600 | Technical Bid Evaluation for Level Transmitters (GWR type)_IFA | 2026-02-20 | 2026-02-20 | 28-Nov-25 A | 18-Dec-25 A | 2027-01-20 | 3 | 2027-01-20
A16610 | Technical Bid Evaluation for Level Transmitters (GWR type)_RCA | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 09-Jan-26 A | 2027-01-20 | 16 | 2027-01-20
A16620 | Technical Bid Evaluation for Level Transmitters (GWR type)_IFD/IFC | 2026-02-20 | 2026-02-20 | 09-Jan-26 A | 13-Jan-26 A | 2027-01-20 | 2 | 2027-01-20
Technical Bid Evaluation for Temperature Element / Thermowell |  | 2026-02-20 | 2026-03-23 | 19-Dec-25 A | 2026-03-23 | 2026-12-22 | 66 | 2027-01-20 | 218
A16280 | Technical Bid Evaluation for Temperature Element / Thermowell_IFR | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 26-Dec-25 A | 2026-12-22 | 6 | 2026-12-22
A16290 | Technical Bid Evaluation for Temperature Element / Thermowell_RCC | 2026-02-20 | 2026-02-20 | 26-Dec-25 A | 19-Jan-26 A | 2026-12-22 | 16 | 2026-12-22
A16300 | Technical Bid Evaluation for Temperature Element / Thermowell_IFA | 2026-02-20 | 2026-02-25 | 2026-02-20 | 2026-02-25 | 2026-12-22 | 3 | 2026-12-25 | 218
A16310 | Technical Bid Evaluation for Temperature Element / Thermowell_RCA | 2026-02-25 | 2026-03-19 | 2026-02-25 | 2026-03-19 | 2026-12-28 | 16 | 2027-01-18 | 218
A16320 | Technical Bid Evaluation for Temperature Element / Thermowell_IFD/IFC | 2026-03-19 | 2026-03-23 | 2026-03-19 | 2026-03-23 | 2027-01-18 | 2 | 2027-01-20 | 218
SIL/LOPA CLoseout Report |  | 2026-02-20 | 2026-04-21 | 2026-02-20 | 2026-04-21 | 2026-11-12 | 43 | 2027-01-20 | 196
A13480 | SIL/LOPA Closeout Report_IFR | 2026-02-20 | 2026-02-27 | 2026-02-20 | 2026-02-27 | 2026-11-12 | 6 | 2026-11-20 | 190
A13490 | SIL/LOPA Closeout Report_RCC | 2026-02-27 | 2026-03-23 | 2026-02-27 | 2026-03-23 | 2026-11-30 | 16 | 2026-12-22 | 196
A13500 | SIL/LOPA Closeout Report_IFA | 2026-03-23 | 2026-03-26 | 2026-03-23 | 2026-03-26 | 2026-12-22 | 3 | 2026-12-25 | 196
A13510 | SIL/LOPA Closeout Report_RCA | 2026-03-26 | 2026-04-17 | 2026-03-26 | 2026-04-17 | 2026-12-28 | 16 | 2027-01-18 | 196
A13520 | SIL/LOPA Closeout Report_IFD/IFC | 2026-04-17 | 2026-04-21 | 2026-04-17 | 2026-04-21 | 2027-01-18 | 2 | 2027-01-20 | 196
Overall Control System Architecture Drawing |  | 2026-02-20 | 2026-02-20 | 09-Jun-25 A | 23-Dec-25 A | 2026-11-23 | 130 | 2027-01-20
A15430 | Overall Control System Architecture Drawing_IFR | 2026-02-20 | 2026-02-20 | 09-Jun-25 A | 05-Jul-25 A | 2026-11-23 | 6 | 2026-11-23
A15440 | Overall Control System Architecture Drawing_RCC | 2026-02-20 | 2026-02-20 | 06-Jul-25 A | 30-Jul-25 A | 2027-01-20 | 16 | 2027-01-20
A15450 | Overall Control System Architecture Drawing_IFA | 2026-02-20 | 2026-02-20 | 31-Jul-25 A | 09-Sep-25 A | 2027-01-20 | 3 | 2027-01-20
A15460 | Overall Control System Architecture Drawing_RCA | 2026-02-20 | 2026-02-20 | 10-Sep-25 A | 16-Sep-25 A | 2027-01-20 | 16 | 2027-01-20
A15470 | Overall Control System Architecture Drawing_IFD/IFC | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 23-Dec-25 A | 2027-01-20 | 2 | 2027-01-20
Instrument Index |  | 2026-02-20 | 2026-03-17 | 10-Jun-25 A | 2026-03-17 | 2026-11-23 | 172 | 2027-01-20 | 221
A15480 | Instrument Index_IFR | 2026-02-20 | 2026-02-20 | 10-Jun-25 A | 05-Jul-25 A | 2026-11-23 | 6 | 2026-11-23
A15490 | Instrument Index_RCC | 2026-02-20 | 2026-02-20 | 01-Aug-25 A | 25-Aug-25 A | 2026-12-28 | 16 | 2026-12-28
A15500 | Instrument Index_IFA | 2026-02-20 | 2026-02-20 | 22-Aug-25 A | 30-Aug-25 A | 2026-12-28 | 3 | 2026-12-28
A15510 | Instrument Index_RCA | 2026-02-20 | 2026-03-13 | 2026-02-20 | 2026-03-13 | 2026-12-28 | 16 | 2027-01-18 | 221
A15520 | Instrument Index_IFD/IFC | 2026-03-13 | 2026-03-17 | 2026-03-13 | 2026-03-17 | 2027-01-18 | 2 | 2027-01-20 | 221
Instrument & F&G I/O list |  | 2026-02-20 | 2026-02-20 | 26-May-25 A | 23-Dec-25 A | 2026-11-23 | 119 | 2027-01-20
A15530 | Instrument & F&G I/O list_IFR | 2026-02-20 | 2026-02-20 | 26-May-25 A | 05-Jul-25 A | 2026-11-23 | 6 | 2026-11-23
A15540 | Instrument & F&G I/O list_RCC | 2026-02-20 | 2026-02-20 | 06-Jul-25 A | 10-Aug-25 A | 2027-01-20 | 16 | 2027-01-20
A47820 | Instrument & F&G I/O list_IFA | 2026-02-20 | 2026-02-20 | 11-Aug-25 A | 20-Aug-25 A | 2027-01-20 | 3 | 2027-01-20
A47830 | Instrument & F&G I/O list_RCA | 2026-02-20 | 2026-02-20 | 21-Aug-25 A | 01-Sep-25 A | 2027-01-20 | 16 | 2027-01-20
A47840 | Instrument & F&G I/O list_IFD/IFC | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 23-Dec-25 A | 2027-01-20 | 2 | 2027-01-20
Cable Block Diagram |  | 2026-02-20 | 2026-02-24 | 08-May-25 A | 2026-02-24 | 2026-11-23 | 183 | 2027-01-20 | 237
A15580 | Cable Block Diagram_IFR | 2026-02-20 | 2026-02-20 | 08-May-25 A | 06-Aug-25 A | 2026-11-23 | 17 | 2026-11-23
A15600 | Cable Block Diagram_IFA | 2026-02-20 | 2026-02-20 | 14-Aug-25 A | 20-Aug-25 A | 2027-01-18 | 3 | 2027-01-18
A47850 | Cable Block Diagram_RCA | 2026-02-20 | 2026-02-20 | 21-Aug-25 A | 01-Sep-25 A | 2027-01-18 | 16 | 2027-01-18
A15590 | Cable Block Diagram_RCC | 2026-02-20 | 2026-02-20 | 07-Aug-25 A | 13-Sep-25 A | 2027-01-18 | 16 | 2027-01-18
A15620 | Cable Block Diagram_IFD/IFC | 2026-02-20 | 2026-02-24 | 2026-02-20 | 2026-02-24 | 2027-01-18 | 2 | 2027-01-20 | 237
Process & Pneumatic Hookup Drawings |  | 2026-02-20 | 2026-04-21 | 2026-02-20 | 2026-04-21 | 2026-11-23 | 43 | 2027-01-20 | 196
A15630 | Process & Pneumatic Hookup Drawings_IFR | 2026-02-20 | 2026-02-27 | 2026-02-20 | 2026-02-27 | 2026-11-23 | 6 | 2026-11-30 | 196
A47860 | Process & Pneumatic Hookup Drawings_RCC | 2026-02-27 | 2026-03-23 | 2026-02-27 | 2026-03-23 | 2026-11-30 | 16 | 2026-12-22 | 196
A47870 | Process & Pneumatic Hookup Drawings_IFA | 2026-03-23 | 2026-03-26 | 2026-03-23 | 2026-03-26 | 2026-12-22 | 3 | 2026-12-25 | 196
A47880 | Process & Pneumatic Hookup Drawings_RCA | 2026-03-26 | 2026-04-17 | 2026-03-26 | 2026-04-17 | 2026-12-28 | 16 | 2027-01-18 | 196
A47890 | Process & Pneumatic Hookup Drawings_IFD/IFC | 2026-04-17 | 2026-04-21 | 2026-04-17 | 2026-04-21 | 2027-01-18 | 2 | 2027-01-20 | 196
Junction Box Schedule |  | 2026-02-20 | 2026-04-14 | 26-May-25 A | 2026-04-14 | 2026-11-26 | 174 | 2027-01-20 | 202
A15680 | Junction Box Schedule_IFR | 2026-02-20 | 2026-02-20 | 26-May-25 A | 07-Jul-25 A | 2026-11-26 | 6 | 2026-11-26
A47900 | Junction Box Schedule_RCC | 2026-02-20 | 2026-03-13 | 2026-02-20 | 2026-03-13 | 2026-11-30 | 16 | 2026-12-22 | 202
A47910 | Junction Box Schedule_IFA | 2026-03-13 | 2026-03-19 | 2026-03-13 | 2026-03-19 | 2026-12-22 | 3 | 2026-12-25 | 202
A47920 | Junction Box Schedule_RCA | 2026-03-19 | 2026-04-09 | 2026-03-19 | 2026-04-09 | 2026-12-28 | 16 | 2027-01-18 | 202
A47930 | Junction Box Schedule_IFD/IFC | 2026-04-09 | 2026-04-14 | 2026-04-09 | 2026-04-14 | 2027-01-18 | 2 | 2027-01-20 | 202
Instrument Cable Schedule |  | 2026-02-20 | 2026-04-14 | 27-Jun-25 A | 2026-04-14 | 2026-11-26 | 169 | 2027-01-18 | 200
A47940 | Instrument Cable Schedule_IFR | 2026-02-20 | 2026-02-20 | 27-Jun-25 A | 05-Jul-25 A | 2026-11-26 | 6 | 2026-11-26
A47950 | Instrument Cable Schedule_RCC | 2026-02-20 | 2026-03-13 | 2026-02-20 | 2026-03-13 | 2026-11-26 | 16 | 2026-12-18 | 200
A47960 | Instrument Cable Schedule_IFA | 2026-03-13 | 2026-03-19 | 2026-03-13 | 2026-03-19 | 2026-12-18 | 3 | 2026-12-23 | 200
A47970 | Instrument Cable Schedule_RCA | 2026-03-19 | 2026-04-09 | 2026-03-19 | 2026-04-09 | 2026-12-23 | 16 | 2027-01-14 | 200
A47980 | Instrument Cable Schedule_IFD/IFC | 2026-04-09 | 2026-04-14 | 2026-04-09 | 2026-04-14 | 2027-01-14 | 2 | 2027-01-18 | 200
SIS Building Equipment Layout |  | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 27-Jun-25 A | 2026-03-14 | 223 | 2026-03-14
A48040 | SIS Building Equipment Layout_IFR | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 29-Apr-25 A | 2026-03-14 | 6 | 2026-03-14
A48050 | SIS Building Equipment Layout_RCC | 2026-02-20 | 2026-02-20 | 30-Apr-25 A | 30-May-25 A | 2026-03-14 | 16 | 2026-03-14
A48060 | SIS Building Equipment Layout_IFA | 2026-02-20 | 2026-02-20 | 02-Jun-25 A | 06-Jun-25 A | 2026-03-14 | 3 | 2026-03-14
A48070 | SIS Building Equipment Layout_RCA | 2026-02-20 | 2026-02-20 | 09-Jun-25 A | 20-Jun-25 A | 2026-03-14 | 16 | 2026-03-14
A48080 | SIS Building Equipment Layout_IFD/IFC | 2026-02-20 | 2026-02-20 | 23-Jun-25 A | 27-Jun-25 A | 2026-03-14 | 2 | 2026-03-14
Instrument & JB Wiring Diagram |  | 2026-02-20 | 2026-03-23 | 20-Dec-25 A | 2026-03-23 | 2026-12-18 | 55 | 2027-01-18 | 215
A47990 | Instrument & JB wiring Diagram_IFR | 2026-02-20 | 2026-02-20 | 20-Dec-25 A | 12-Jan-26 A | 2026-12-18 | 6 | 2026-12-18
A48000 | Instrument & JB wiring Diagram_RCC | 2026-02-20 | 2026-02-20 | 12-Jan-26 A | 17-Jan-26 A | 2026-12-18 | 16 | 2026-12-18
A48010 | Instrument & JB wiring Diagram_IFA | 2026-02-20 | 2026-02-25 | 2026-02-20 | 2026-02-25 | 2026-12-18 | 3 | 2026-12-23 | 215
A48020 | Instrument & JB wiring Diagram_RCA | 2026-02-25 | 2026-03-19 | 2026-02-25 | 2026-03-19 | 2026-12-23 | 16 | 2027-01-14 | 215
A48030 | Instrument & JB wiring Diagram_IFD/IFC | 2026-03-19 | 2026-03-23 | 2026-03-19 | 2026-03-23 | 2027-01-14 | 2 | 2027-01-18 | 215
Instrument Loop Diagram |  | 2026-03-09 | 2026-05-06 | 2026-03-09 | 2026-05-06 | 2026-11-04 | 43 | 2027-01-01 | 172
A16080 | Instrument Loop Diagram_IFR | 2026-03-09 | 2026-03-16 | 2026-03-09 | 2026-03-16 | 2026-11-04 | 6 | 2026-11-11 | 172
A48140 | Instrument Loop Diagram_RCC | 2026-03-16 | 2026-04-07 | 2026-03-16 | 2026-04-07 | 2026-11-11 | 16 | 2026-12-03 | 172
A16100 | Instrument Loop Diagram_IFA | 2026-04-07 | 2026-04-10 | 2026-04-07 | 2026-04-10 | 2026-12-03 | 3 | 2026-12-08 | 172
A16110 | Instrument Loop Diagram_RCA | 2026-04-13 | 2026-05-04 | 2026-04-13 | 2026-05-04 | 2026-12-09 | 16 | 2026-12-30 | 172
A16120 | Instrument Loop Diagram_IFD/IFC | 2026-05-04 | 2026-05-06 | 2026-05-04 | 2026-05-06 | 2026-12-30 | 2 | 2027-01-01 | 172
Instrument Location Layout |  | 2026-04-03 | 2026-06-03 | 2026-04-03 | 2026-06-03 | 2026-11-19 | 43 | 2027-01-18 | 164
A48090 | Instrument Location Layout_IFR | 2026-04-03 | 2026-04-10 | 2026-04-03 | 2026-04-10 | 2026-11-19 | 6 | 2026-11-26 | 164
A48100 | Instrument Location Layout_RCC | 2026-04-13 | 2026-05-04 | 2026-04-13 | 2026-05-04 | 2026-11-26 | 16 | 2026-12-18 | 164
A15900 | Instrument Location Layout_IFA | 2026-05-04 | 2026-05-08 | 2026-05-04 | 2026-05-08 | 2026-12-18 | 3 | 2026-12-23 | 164
A48110 | Instrument Location Layout_RCA | 2026-05-08 | 2026-05-29 | 2026-05-08 | 2026-05-29 | 2026-12-23 | 16 | 2027-01-14 | 164
A15920 | Instrument Location Layout_IFD/IFC | 2026-05-29 | 2026-06-03 | 2026-05-29 | 2026-06-03 | 2027-01-14 | 2 | 2027-01-18 | 164
Instrument Cable & trench routing layout |  | 2026-02-20 | 2026-03-23 | 20-Dec-25 A | 2026-03-23 | 2026-12-18 | 36 | 2027-01-18 | 215
A15930 | Instrument Cable & trench routing layout_IFR | 2026-02-20 | 2026-02-20 | 20-Dec-25 A | 01-Jan-26 A | 2026-12-18 | 6 | 2026-12-18
A15940 | Instrument Cable & trench routing layout_RCC | 2026-02-20 | 2026-02-20 | 01-Jan-26 A | 17-Jan-26 A | 2026-12-18 | 16 | 2026-12-18
A15950 | Instrument Cable & trench routing layout_IFA | 2026-02-20 | 2026-02-25 | 2026-02-20 | 2026-02-25 | 2026-12-18 | 3 | 2026-12-23 | 215
A15960 | Instrument Cable & trench routing layout_RCA | 2026-02-25 | 2026-03-19 | 2026-02-25 | 2026-03-19 | 2026-12-23 | 16 | 2027-01-14 | 215
A48120 | Instrument Cable & trench routing layout_IFD/IFC | 2026-03-19 | 2026-03-23 | 2026-03-19 | 2026-03-23 | 2027-01-14 | 2 | 2027-01-18 | 215
MCT Installation Drawing |  | 2026-02-20 | 2026-03-23 | 10-Nov-25 A | 2026-03-23 | 2026-12-22 | 86 | 2027-01-20 | 218
A15980 | MCT Installation Drawing_IFR | 2026-02-20 | 2026-02-20 | 10-Nov-25 A | 21-Nov-25 A | 2026-12-22 | 6 | 2026-12-22
A15990 | MCT Installation Drawing_RCC | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 09-Jan-26 A | 2026-12-22 | 16 | 2026-12-22
A16000 | MCT Installation Drawing_IFA | 2026-02-20 | 2026-02-25 | 2026-02-20 | 2026-02-25 | 2026-12-22 | 3 | 2026-12-25 | 218
A16010 | MCT Installation Drawing_RCA | 2026-02-25 | 2026-03-19 | 2026-02-25 | 2026-03-19 | 2026-12-28 | 16 | 2027-01-18 | 218
A16020 | MCT Installation Drawing_IFD/IFC | 2026-03-19 | 2026-03-23 | 2026-03-19 | 2026-03-23 | 2027-01-18 | 2 | 2027-01-20 | 218
Instrumentation & Control Material Take Off |  | 2026-02-20 | 2026-02-24 | 19-Dec-25 A | 2026-02-24 | 2026-04-07 | 47 | 2027-01-20 | 237
A48130 | Instrumentation & Control Material Take Off_IFR | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 26-Dec-25 A | 2026-04-07 | 6 | 2026-04-07
A16040 | Instrumentation & Control Material Take Off_RCC | 2026-02-20 | 2026-02-20 | 26-Dec-25 A | 19-Jan-26 A | 2027-01-18 | 16 | 2027-01-18
A16070 | Instrumentation & Control Material Take Off_IFD/IFC | 2026-02-20 | 2026-02-24 | 2026-02-20 | 2026-02-24 | 2027-01-18 | 2 | 2027-01-20 | 237
SPI |  | 2026-02-20 | 2026-04-14 | 25-Mar-25 A | 2026-04-14 | 2026-11-30 | 242 | 2027-01-20 | 202
SPI Execution Philoshpy |  | 2026-02-20 | 2026-04-14 | 25-Mar-25 A | 2026-04-14 | 2026-11-30 | 242 | 2027-01-20 | 202
A55560 | SPI Execution Philoshpy_IFR | 2026-02-20 | 2026-02-20 | 25-Mar-25 A | 28-Apr-25 A | 2026-11-30 | 6 | 2026-11-30
A55570 | SPI Execution Philoshpy_RCC | 2026-02-20 | 2026-03-13 | 2026-02-20 | 2026-03-13 | 2026-11-30 | 16 | 2026-12-22 | 202
A55580 | SPI Execution Philoshpy_IFA | 2026-03-13 | 2026-03-19 | 2026-03-13 | 2026-03-19 | 2026-12-22 | 3 | 2026-12-25 | 202
A55590 | SPI Execution Philoshpy_RCA | 2026-03-19 | 2026-04-09 | 2026-03-19 | 2026-04-09 | 2026-12-28 | 16 | 2027-01-18 | 202
A28050 | SPI Execution Philoshpy_IFD/IFC | 2026-04-09 | 2026-04-14 | 2026-04-09 | 2026-04-14 | 2027-01-18 | 2 | 2027-01-20 | 202
SPI Extraction Procedure |  | 2026-02-20 | 2026-04-14 | 01-Jul-25 A | 2026-04-14 | 2026-11-30 | 212 | 2027-01-20 | 202
A28060 | SPI Extraction Procedure_IFR | 2026-02-20 | 2026-02-20 | 01-Jul-25 A | 12-Jul-25 A | 2026-11-30 | 6 | 2026-11-30
A55600 | SPI Extraction Procedure_RCC | 2026-02-20 | 2026-03-13 | 2026-02-20 | 2026-03-13 | 2026-11-30 | 16 | 2026-12-22 | 202
A55610 | SPI Extraction Procedure_IFA | 2026-03-13 | 2026-03-19 | 2026-03-13 | 2026-03-19 | 2026-12-22 | 3 | 2026-12-25 | 202
A55620 | SPI Extraction Procedure_RCA | 2026-03-19 | 2026-04-09 | 2026-03-19 | 2026-04-09 | 2026-12-28 | 16 | 2027-01-18 | 202
A55630 | SPI Extraction Procedure_IFD/IFC | 2026-04-09 | 2026-04-14 | 2026-04-09 | 2026-04-14 | 2027-01-18 | 2 | 2027-01-20 | 202
Civil/Structural/Architectural |  | 2026-02-20 | 2026-05-14 | 16-Jan-25 A | 2026-05-14 | 2026-02-21 | 485 | 2027-01-20 | 179
Structure & Foundation design - Piperack & other pipe supports |  | 2026-02-20 | 2026-05-14 | 21-Apr-25 A | 2026-05-14 | 2026-03-02 | 194 | 2027-01-20 | 179
Structural GA, Section and Details - Pipe Rack SR8001 |  | 2026-02-20 | 2026-02-20 | 02-Jun-25 A | 08-Aug-25 A | 2026-03-02 | 65 | 2026-03-02
A48510 | Structural GA, Section and Details - Pipe Rack SR8001_IFR | 2026-02-20 | 2026-02-20 | 02-Jun-25 A | 20-Jun-25 A | 2026-03-02 | 17 | 2026-03-02
A48520 | Structural GA, Section and Details - Pipe Rack SR8001_RCC | 2026-02-20 | 2026-02-20 | 23-Jun-25 A | 04-Jul-25 A | 2026-03-02 | 16 | 2026-03-02
A18000 | Structural GA, Section and Details - Pipe Rack SR8001_IFA | 2026-02-20 | 2026-02-20 | 07-Jul-25 A | 18-Jul-25 A | 2026-03-02 | 11 | 2026-03-02
A48530 | Structural GA, Section and Details - Pipe Rack SR8001_RCA | 2026-02-20 | 2026-02-20 | 21-Jul-25 A | 01-Aug-25 A | 2026-03-02 | 16 | 2026-03-02
A48540 | Structural GA, Section and Details - Pipe Rack SR8001_IFD/IFC | 2026-02-20 | 2026-02-20 | 04-Aug-25 A | 08-Aug-25 A | 2026-03-02 | 6 | 2026-03-02
Design Calculation Report for Structural Steel - Pipe Rack SR8001 |  | 2026-02-20 | 2026-02-20 | 02-Jun-25 A | 01-Aug-25 A | 2026-03-02 | 65 | 2027-01-20
A48550 | Design Calculation Report for Structural Steel - Pipe Rack SR8001_IFR | 2026-02-20 | 2026-02-20 | 02-Jun-25 A | 13-Jun-25 A | 2026-03-02 | 17 | 2026-03-02
A48560 | Design Calculation Report for Structural Steel - Pipe Rack SR8001_RCC | 2026-02-20 | 2026-02-20 | 16-Jun-25 A | 27-Jun-25 A | 2027-01-20 | 16 | 2027-01-20
A18050 | Design Calculation Report for Structural Steel - Pipe Rack SR8001_IFA | 2026-02-20 | 2026-02-20 | 30-Jun-25 A | 11-Jul-25 A | 2027-01-20 | 11 | 2027-01-20
A18060 | Design Calculation Report for Structural Steel - Pipe Rack SR8001_RCA | 2026-02-20 | 2026-02-20 | 14-Jul-25 A | 25-Jul-25 A | 2027-01-20 | 16 | 2027-01-20
A18070 | Design Calculation Report for Structural Steel - Pipe Rack SR8001_IFD/IFC | 2026-02-20 | 2026-02-20 | 28-Jul-25 A | 01-Aug-25 A | 2027-01-20 | 6 | 2027-01-20
Foundation layout, Section and Details - Pipe Rack SR8001 |  | 2026-02-20 | 2026-02-20 | 25-Jun-25 A | 23-Dec-25 A | 2026-03-02 | 91 | 2026-03-02
A48570 | Foundation layout, Section and Details - Pipe Rack SR8001_IFR | 2026-02-20 | 2026-02-20 | 25-Jun-25 A | 12-Jul-25 A | 2026-03-02 | 6 | 2026-03-02
A48580 | Foundation layout, Section and Details - Pipe Rack SR8001_RCC | 2026-02-20 | 2026-02-20 | 14-Jul-25 A | 22-Aug-25 A | 2026-03-02 | 16 | 2026-03-02
A48590 | Foundation layout, Section and Details - Pipe Rack SR8001_IFA | 2026-02-20 | 2026-02-20 | 31-Oct-25 A | 11-Nov-25 A | 2026-03-02 | 3 | 2026-03-02
A18110 | Foundation layout, Section and Details - Pipe Rack SR8001_RCA | 2026-02-20 | 2026-02-20 | 13-Nov-25 A | 21-Nov-25 A | 2026-03-02 | 16 | 2026-03-02
A18120 | Foundation layout, Section and Details - Pipe Rack SR8001_IFD/IFC | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 23-Dec-25 A | 2026-03-02 | 2 | 2026-03-02
Design Calculation Report for Foundations - Pipe Rack SR8001 |  | 2026-02-20 | 2026-02-20 | 01-Jul-25 A | 23-Dec-25 A | 2027-01-20 | 91 | 2027-01-20
A18130 | Design Calculation Report for Foundations - Pipe Rack SR8001_IFR | 2026-02-20 | 2026-02-20 | 01-Jul-25 A | 12-Jul-25 A | 2027-01-20 | 6 | 2027-01-20
A48600 | Design Calculation Report for Foundations - Pipe Rack SR8001_RCC | 2026-02-20 | 2026-02-20 | 14-Jul-25 A | 22-Aug-25 A | 2027-01-20 | 16 | 2027-01-20
A48610 | Design Calculation Report for Foundations - Pipe Rack SR8001_IFA | 2026-02-20 | 2026-02-20 | 31-Oct-25 A | 11-Nov-25 A | 2027-01-20 | 3 | 2027-01-20
A48620 | Design Calculation Report for Foundations - Pipe Rack SR8001_RCA | 2026-02-20 | 2026-02-20 | 12-Nov-25 A | 21-Nov-25 A | 2027-01-20 | 16 | 2027-01-20
A18170 | Design Calculation Report for Foundations - Pipe Rack SR8001_IFD/IFC | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 23-Dec-25 A | 2027-01-20 | 2 | 2027-01-20
Structural GA, Section and Details - Pipe Rack 13-I-08001 |  | 2026-02-20 | 2026-02-20 | 01-Aug-25 A | 24-Dec-25 A | 2026-03-02 | 68 | 2026-06-28
A18180 | Structural GA, Section and Details - Pipe Rack 13-I-08001_IFR | 2026-02-20 | 2026-02-20 | 01-Aug-25 A | 15-Aug-25 A | 2026-03-02 | 11 | 2026-03-02
A18190 | Structural GA, Section and Details - Pipe Rack 13-I-08001_RCC | 2026-02-20 | 2026-02-20 | 04-Aug-25 A | 22-Aug-25 A | 2026-03-02 | 16 | 2026-03-02
A48630 | Structural GA, Section and Details - Pipe Rack 13-I-08001_IFA | 2026-02-20 | 2026-02-20 | 25-Aug-25 A | 29-Aug-25 A | 2026-03-02 | 6 | 2026-03-02
A48640 | Structural GA, Section and Details - Pipe Rack 13-I-08001_RCA | 2026-02-20 | 2026-02-20 | 01-Sep-25 A | 22-Oct-25 A | 2026-06-28 | 16 | 2026-06-28
A48650 | Structural GA, Section and Details - Pipe Rack 13-I-08001_IFD/IFC | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 24-Dec-25 A | 2026-06-28 | 3 | 2026-06-28
Design Calculation Report for Structural Steel - Pipe Rack 13-I-08001 |  | 2026-02-20 | 2026-02-20 | 07-Jul-25 A | 12-Sep-25 A | 2026-03-02 | 52 | 2026-03-02
A18230 | Design Calculation Report for Structural Steel - Pipe Rack 13-I-08001_IFR | 2026-02-20 | 2026-02-20 | 07-Jul-25 A | 18-Jul-25 A | 2026-03-02 | 11 | 2026-03-02
A18240 | Design Calculation Report for Structural Steel - Pipe Rack 13-I-08001_RCC | 2026-02-20 | 2026-02-20 | 21-Jul-25 A | 08-Aug-25 A | 2026-03-02 | 16 | 2026-03-02
A18250 | Design Calculation Report for Structural Steel - Pipe Rack 13-I-08001_IFA | 2026-02-20 | 2026-02-20 | 11-Aug-25 A | 19-Aug-25 A | 2026-03-02 | 6 | 2026-03-02
A48660 | Design Calculation Report for Structural Steel - Pipe Rack 13-I-08001_RCA | 2026-02-20 | 2026-02-20 | 20-Aug-25 A | 05-Sep-25 A | 2026-03-02 | 16 | 2026-03-02
A48670 | Design Calculation Report for Structural Steel - Pipe Rack 13-I-08001_IFD/IFC | 2026-02-20 | 2026-02-20 | 08-Sep-25 A | 12-Sep-25 A | 2026-03-02 | 3 | 2026-03-02
Foundation layout, Section and Details - Pipe Rack 13-I-08001 |  | 2026-02-20 | 2026-02-20 | 30-Jun-25 A | 23-Dec-25 A | 2026-03-02 | 80 | 2026-03-02
A48680 | Foundation layout, Section and Details - Pipe Rack 13-I-08001_IFR | 2026-02-20 | 2026-02-20 | 30-Jun-25 A | 15-Jul-25 A | 2026-03-02 | 6 | 2026-03-02
A18290 | Foundation layout, Section and Details - Pipe Rack 13-I-08001_RCC | 2026-02-20 | 2026-02-20 | 16-Jul-25 A | 22-Aug-25 A | 2026-03-02 | 16 | 2026-03-02
A18300 | Foundation layout, Section and Details - Pipe Rack 13-I-08001_IFA | 2026-02-20 | 2026-02-20 | 25-Aug-25 A | 29-Aug-25 A | 2026-03-02 | 3 | 2026-03-02
A18310 | Foundation layout, Section and Details - Pipe Rack 13-I-08001_RCA | 2026-02-20 | 2026-02-20 | 11-Aug-25 A | 05-Sep-25 A | 2026-03-02 | 16 | 2026-03-02
A48690 | Foundation layout, Section and Details - Pipe Rack 13-I-08001_IFD/IFC | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 23-Dec-25 A | 2026-03-02 | 2 | 2026-03-02
Design Calculation Report for Foundations - Pipe Rack 13-I-08001 |  | 2026-02-20 | 2026-02-20 | 02-Jul-25 A | 23-Dec-25 A | 2026-03-02 | 80 | 2026-03-02
A48700 | Design Calculation Report for Foundations - Pipe Rack 13-I-08001_IFR | 2026-02-20 | 2026-02-20 | 02-Jul-25 A | 12-Jul-25 A | 2026-03-02 | 6 | 2026-03-02
A48710 | Design Calculation Report for Foundations - Pipe Rack 13-I-08001_RCC | 2026-02-20 | 2026-02-20 | 14-Jul-25 A | 22-Aug-25 A | 2026-03-02 | 16 | 2026-03-02
A18350 | Design Calculation Report for Foundations - Pipe Rack 13-I-08001_IFA | 2026-02-20 | 2026-02-20 | 25-Aug-25 A | 29-Aug-25 A | 2026-03-02 | 3 | 2026-03-02
A48720 | Design Calculation Report for Foundations - Pipe Rack 13-I-08001_RCA | 2026-02-20 | 2026-02-20 | 18-Aug-25 A | 05-Sep-25 A | 2026-03-02 | 16 | 2026-03-02
A48730 | Design Calculation Report for Foundations - Pipe Rack 13-I-08001_IFD/IFC | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 23-Dec-25 A | 2026-03-02 | 2 | 2026-03-02
Structral steel GA and details Field Supports SF8200 |  | 2026-02-20 | 2026-03-23 | 03-Jul-25 A | 2026-03-23 | 2026-05-28 | 115 | 2026-06-26 | 70
A20980 | Structral steel GA and details Field Supports SF8200_IFR | 2026-02-20 | 2026-02-20 | 03-Jul-25 A | 20-Jul-25 A | 2026-05-28 | 6 | 2026-05-28
A20990 | Structral steel GA and details Field Supports SF8200_RCC | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 09-Jan-26 A | 2026-05-28 | 16 | 2026-05-28
A21000 | Structral steel GA and details Field Supports SF8200_IFA | 2026-02-20 | 2026-02-25 | 2026-02-20 | 2026-02-25 | 2026-05-28 | 3 | 2026-06-02 | 70
A21010 | Structral steel GA and details Field Supports SF8200_RCA | 2026-02-25 | 2026-03-19 | 2026-02-25 | 2026-03-19 | 2026-06-03 | 16 | 2026-06-24 | 70
A21020 | Structral steel GA and details Field Supports SF8200_IFD/IFC | 2026-03-19 | 2026-03-23 | 2026-03-19 | 2026-03-23 | 2026-06-24 | 2 | 2026-06-26 | 70
Design Calculation Report for structural steel Field Supports SF8200 |  | 2026-02-20 | 2026-03-23 | 19-Aug-25 A | 2026-03-23 | 2026-04-16 | 131 | 2026-06-18 | 63
A49960 | Design Calculation Report for structural steel Field Supports SF8200_IFR | 2026-02-20 | 2026-02-20 | 19-Aug-25 A | 25-Aug-25 A | 2026-04-16 | 6 | 2026-04-16
A49970 | Design Calculation Report for structural steel Field Supports SF8200_RCC | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 09-Jan-26 A | 2026-05-14 | 16 | 2026-05-14
A49980 | Design Calculation Report for structural steel Field Supports SF8200_IFA | 2026-02-20 | 2026-02-25 | 2026-02-20 | 2026-02-25 | 2026-05-14 | 3 | 2026-05-19 | 60
A49990 | Design Calculation Report for structural steel Field Supports SF8200_RCA | 2026-02-25 | 2026-03-19 | 2026-02-25 | 2026-03-19 | 2026-05-25 | 16 | 2026-06-15 | 63
A21070 | Design Calculation Report for structural steel Field Supports SF8200_IFD/IFC | 2026-03-19 | 2026-03-23 | 2026-03-19 | 2026-03-23 | 2026-06-16 | 2 | 2026-06-18 | 63
Foundation Layout, Section and details Field Supports SF8200 |  | 2026-02-20 | 2026-03-26 | 19-Dec-25 A | 2026-03-26 | 2026-12-22 | 70 | 2027-01-20 | 214
A21080 | Foundation Layout, Section and details Field Supports SF8200_IFR | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 26-Dec-25 A | 2026-12-22 | 6 | 2026-12-22
A21090 | Foundation Layout, Section and details Field Supports SF8200_RCC | 2026-02-20 | 2026-02-20 | 26-Dec-25 A | 19-Jan-26 A | 2026-12-22 | 16 | 2026-12-22
A21100 | Foundation Layout, Section and details Field Supports SF8200_IFA | 2026-02-25 | 2026-03-02 | 2026-02-25 | 2026-03-02 | 2026-12-22 | 3 | 2026-12-25 | 214
A50000 | Foundation Layout, Section and details Field Supports SF8200_RCA | 2026-03-02 | 2026-03-24 | 2026-03-02 | 2026-03-24 | 2026-12-28 | 16 | 2027-01-18 | 214
A50010 | Foundation Layout, Section and details Field Supports SF8200_IFD/IFC | 2026-03-24 | 2026-03-26 | 2026-03-24 | 2026-03-26 | 2027-01-18 | 2 | 2027-01-20 | 214
Design Calculation Report for Foundations Field Supports SF8200 |  | 2026-02-20 | 2026-03-26 | 19-Dec-25 A | 2026-03-26 | 2026-12-22 | 70 | 2027-01-20 | 214
A50020 | Design Calculation Report for Foundations Field Supports SF8200_IFR | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 26-Dec-25 A | 2026-12-22 | 6 | 2026-12-22
A50030 | Design Calculation Report for Foundations Field Supports SF8200_RCC | 2026-02-20 | 2026-02-20 | 26-Dec-25 A | 19-Jan-26 A | 2026-12-22 | 16 | 2026-12-22
A21150 | Design Calculation Report for Foundations Field Supports SF8200_IFA | 2026-02-25 | 2026-03-02 | 2026-02-25 | 2026-03-02 | 2026-12-22 | 3 | 2026-12-25 | 214
A21160 | Design Calculation Report for Foundations Field Supports SF8200_RCA | 2026-03-02 | 2026-03-24 | 2026-03-02 | 2026-03-24 | 2026-12-28 | 16 | 2027-01-18 | 214
A21170 | Design Calculation Report for Foundations Field Supports SF8200_IFD/IFC | 2026-03-24 | 2026-03-26 | 2026-03-24 | 2026-03-26 | 2027-01-18 | 2 | 2027-01-20 | 214
Structural GA and Details, Field supports in CA37 |  | 2026-02-20 | 2026-04-21 | 2026-02-20 | 2026-04-21 | 2026-04-16 | 43 | 2026-06-22 | 44
A50430 | Structural GA and Details, Field supports in CA37_IFR | 2026-02-20 | 2026-02-27 | 2026-02-20 | 2026-02-27 | 2026-04-16 | 6 | 2026-04-23 | 39
A50440 | Structural GA and Details, Field supports in CA37_RCC | 2026-02-27 | 2026-03-23 | 2026-02-27 | 2026-03-23 | 2026-04-28 | 16 | 2026-05-19 | 42
A21900 | Structural GA and Details, Field supports in CA37_IFA | 2026-03-23 | 2026-03-26 | 2026-03-23 | 2026-03-26 | 2026-05-19 | 3 | 2026-05-25 | 42
A50450 | Structural GA and Details, Field supports in CA37_RCA | 2026-03-26 | 2026-04-17 | 2026-03-26 | 2026-04-17 | 2026-05-27 | 16 | 2026-06-18 | 44
A50460 | Structural GA and Details, Field supports in CA37_IFD/IFC | 2026-04-17 | 2026-04-21 | 2026-04-17 | 2026-04-21 | 2026-06-18 | 2 | 2026-06-22 | 44
Design Calculation report of structural steel Field supports CA37 |  | 2026-02-20 | 2026-04-21 | 2026-02-20 | 2026-04-21 | 2026-04-16 | 43 | 2026-06-22 | 44
A50500 | Design Calculation report of structural steel Field supports CA37_IFR | 2026-02-20 | 2026-02-27 | 2026-02-20 | 2026-02-27 | 2026-04-16 | 6 | 2026-04-23 | 39
A21990 | Design Calculation report of structural steel Field supports CA37_RCC | 2026-02-27 | 2026-03-23 | 2026-02-27 | 2026-03-23 | 2026-04-28 | 16 | 2026-05-19 | 42
A50510 | Design Calculation report of structural steel Field supports CA37_IFA | 2026-03-23 | 2026-03-26 | 2026-03-23 | 2026-03-26 | 2026-05-19 | 3 | 2026-05-25 | 42
A50520 | Design Calculation report of structural steel Field supports CA37_RCA | 2026-03-26 | 2026-04-17 | 2026-03-26 | 2026-04-17 | 2026-05-27 | 16 | 2026-06-18 | 44
A22020 | Design Calculation report of structural steel Field supports CA37_IFD/IFC | 2026-04-17 | 2026-04-21 | 2026-04-17 | 2026-04-21 | 2026-06-18 | 2 | 2026-06-22 | 44
Design Calculation report of Foundations Field supports CA37 |  | 2026-02-27 | 2026-04-29 | 2026-02-27 | 2026-04-29 | 2026-11-23 | 43 | 2027-01-20 | 191
A50530 | Design Calculation report of Foundations Field supports CA37_IFR | 2026-02-27 | 2026-03-09 | 2026-02-27 | 2026-03-09 | 2026-11-23 | 6 | 2026-11-30 | 191
A50540 | Design Calculation report of Foundations Field supports CA37_RCC | 2026-03-09 | 2026-03-30 | 2026-03-09 | 2026-03-30 | 2026-11-30 | 16 | 2026-12-22 | 191
A50550 | Design Calculation report of Foundations Field supports CA37_IFA | 2026-03-31 | 2026-04-03 | 2026-03-31 | 2026-04-03 | 2026-12-22 | 3 | 2026-12-25 | 191
A22060 | Design Calculation report of Foundations Field supports CA37_RCA | 2026-04-03 | 2026-04-27 | 2026-04-03 | 2026-04-27 | 2026-12-28 | 16 | 2027-01-18 | 191
A50560 | Design Calculation report of Foundations Field supports CA37_IFD/IFC | 2026-04-27 | 2026-04-29 | 2026-04-27 | 2026-04-29 | 2027-01-18 | 2 | 2027-01-20 | 191
Foundation layout and details, Field supports in CA37 |  | 2026-02-27 | 2026-04-29 | 2026-02-27 | 2026-04-29 | 2026-11-23 | 43 | 2027-01-20 | 191
A50470 | Foundation layout and details, Field supports in CA37_IFR | 2026-02-27 | 2026-03-09 | 2026-02-27 | 2026-03-09 | 2026-11-23 | 6 | 2026-11-30 | 191
A50480 | Foundation layout and details, Field supports in CA37_RCC | 2026-03-09 | 2026-03-30 | 2026-03-09 | 2026-03-30 | 2026-11-30 | 16 | 2026-12-22 | 191
A21950 | Foundation layout and details, Field supports in CA37_IFA | 2026-03-31 | 2026-04-03 | 2026-03-31 | 2026-04-03 | 2026-12-22 | 3 | 2026-12-25 | 191
A21960 | Foundation layout and details, Field supports in CA37_RCA | 2026-04-03 | 2026-04-27 | 2026-04-03 | 2026-04-27 | 2026-12-28 | 16 | 2027-01-18 | 191
A50490 | Foundation layout and details, Field supports in CA37_IFD/IFC | 2026-04-27 | 2026-04-29 | 2026-04-27 | 2026-04-29 | 2027-01-18 | 2 | 2027-01-20 | 191
Structural GA, Section and Details - Pipe Bridge SR81 |  | 2026-02-20 | 2026-02-20 | 23-Jun-25 A | 14-Aug-25 A | 2026-03-02 | 43 | 2026-03-02
A48740 | Structural GA, Section and Details - Pipe Bridge SR81_IFR | 2026-02-20 | 2026-02-20 | 23-Jun-25 A | 02-Jul-25 A | 2026-03-02 | 6 | 2026-03-02
A18390 | Structural GA, Section and Details - Pipe Bridge SR81_RCC | 2026-02-20 | 2026-02-20 | 03-Jul-25 A | 18-Jul-25 A | 2026-03-02 | 16 | 2026-03-02
A18400 | Structural GA, Section and Details - Pipe Bridge SR81_IFA | 2026-02-20 | 2026-02-20 | 21-Jul-25 A | 25-Jul-25 A | 2026-03-02 | 3 | 2026-03-02
A18410 | Structural GA, Section and Details - Pipe Bridge SR81_RCA | 2026-02-20 | 2026-02-20 | 28-Jul-25 A | 08-Aug-25 A | 2026-03-02 | 16 | 2026-03-02
A48750 | Structural GA, Section and Details - Pipe Bridge SR81_IFD/IFC | 2026-02-20 | 2026-02-20 | 11-Aug-25 A | 14-Aug-25 A | 2026-03-02 | 2 | 2026-03-02
Design Calculation Report for Structural Steel - Pipe Bridge SR81 |  | 2026-02-20 | 2026-02-20 | 03-Jul-25 A | 12-Sep-25 A | 2026-03-02 | 50 | 2026-03-02
A48760 | Design Calculation Report for Structural Steel - Pipe Bridge SR81_IFR | 2026-02-20 | 2026-02-20 | 03-Jul-25 A | 20-Jul-25 A | 2026-03-02 | 6 | 2026-03-02
A18440 | Design Calculation Report for Structural Steel - Pipe Bridge SR81_RCC | 2026-02-20 | 2026-02-20 | 21-Jul-25 A | 08-Aug-25 A | 2026-03-02 | 16 | 2026-03-02
A18450 | Design Calculation Report for Structural Steel - Pipe Bridge SR81_IFA | 2026-02-20 | 2026-02-20 | 11-Aug-25 A | 15-Aug-25 A | 2026-03-02 | 3 | 2026-03-02
A48770 | Design Calculation Report for Structural Steel - Pipe Bridge SR81_RCA | 2026-02-20 | 2026-02-20 | 18-Aug-25 A | 05-Sep-25 A | 2026-03-02 | 16 | 2026-03-02
A18470 | Design Calculation Report for Structural Steel - Pipe Bridge SR81_IFD/IFC | 2026-02-20 | 2026-02-20 | 08-Sep-25 A | 12-Sep-25 A | 2026-03-02 | 2 | 2026-03-02
Design Calculation Report for Foundations - Pipe Bridge SR81 |  | 2026-02-20 | 2026-02-20 | 21-Apr-25 A | 17-Jul-25 A | 2026-03-02 | 47 | 2026-03-02
A48830 | Design Calculation Report for Foundations - Pipe Bridge SR81_IFR | 2026-02-20 | 2026-02-20 | 21-Apr-25 A | 12-May-25 A | 2026-03-02 | 6 | 2026-03-02
A48840 | Design Calculation Report for Foundations - Pipe Bridge SR81_RCC | 2026-02-20 | 2026-02-20 | 13-May-25 A | 19-May-25 A | 2026-03-02 | 16 | 2026-03-02
A48850 | Design Calculation Report for Foundations - Pipe Bridge SR81_IFA | 2026-02-20 | 2026-02-20 | 20-May-25 A | 20-Jun-25 A | 2026-03-02 | 3 | 2026-03-02
A48860 | Design Calculation Report for Foundations - Pipe Bridge SR81_RCA | 2026-02-20 | 2026-02-20 | 23-Jun-25 A | 11-Jul-25 A | 2026-03-02 | 16 | 2026-03-02
A48870 | Design Calculation Report for Foundations - Pipe Bridge SR81_IFD/IFC | 2026-02-20 | 2026-02-20 | 14-Jul-25 A | 17-Jul-25 A | 2026-03-02 | 2 | 2026-03-02
Foundation layout, Section and Details - Pipe Bridge SR81 |  | 2026-02-20 | 2026-02-20 | 21-Apr-25 A | 13-Sep-25 A | 2026-03-02 | 47 | 2026-03-02
A48780 | Foundation layout, Section and Details - Pipe Bridge SR81_IFR | 2026-02-20 | 2026-02-20 | 21-Apr-25 A | 12-May-25 A | 2026-03-02 | 6 | 2026-03-02
A48790 | Foundation layout, Section and Details - Pipe Bridge SR81_RCC | 2026-02-20 | 2026-02-20 | 13-May-25 A | 19-May-25 A | 2026-03-02 | 16 | 2026-03-02
A48800 | Foundation layout, Section and Details - Pipe Bridge SR81_IFA | 2026-02-20 | 2026-02-20 | 20-May-25 A | 20-Jun-25 A | 2026-03-02 | 3 | 2026-03-02
A48810 | Foundation layout, Section and Details - Pipe Bridge SR81_RCA | 2026-02-20 | 2026-02-20 | 21-Jun-25 A | 06-Sep-25 A | 2026-03-02 | 16 | 2026-03-02
A48820 | Foundation layout, Section and Details - Pipe Bridge SR81_IFD/IFC | 2026-02-20 | 2026-02-20 | 08-Sep-25 A | 13-Sep-25 A | 2026-03-02 | 2 | 2026-03-02
Structral steel GA and details Field Supports SF8300 |  | 2026-02-27 | 2026-04-29 | 2026-02-27 | 2026-04-29 | 2026-04-23 | 43 | 2026-06-24 | 40
A21180 | Structral steel GA and details Field Supports SF8300_IFR | 2026-02-27 | 2026-03-09 | 2026-02-27 | 2026-03-09 | 2026-04-23 | 6 | 2026-05-01 | 39
A50040 | Structral steel GA and details Field Supports SF8300_RCC | 2026-03-09 | 2026-03-30 | 2026-03-09 | 2026-03-30 | 2026-05-01 | 16 | 2026-05-25 | 39
A50050 | Structral steel GA and details Field Supports SF8300_IFA | 2026-03-31 | 2026-04-03 | 2026-03-31 | 2026-04-03 | 2026-05-25 | 3 | 2026-05-28 | 39
A50060 | Structral steel GA and details Field Supports SF8300_RCA | 2026-04-03 | 2026-04-27 | 2026-04-03 | 2026-04-27 | 2026-05-29 | 16 | 2026-06-22 | 40
A50070 | Structral steel GA and details Field Supports SF8300_IFD/IFC | 2026-04-27 | 2026-04-29 | 2026-04-27 | 2026-04-29 | 2026-06-22 | 2 | 2026-06-24 | 40
Design Calculation Report for structural steel Field Supports SF8300 |  | 2026-02-27 | 2026-04-29 | 2026-02-27 | 2026-04-29 | 2026-11-23 | 43 | 2027-01-20 | 191
A21230 | Design Calculation Report for structural steel Field Supports SF8300_IFR | 2026-02-27 | 2026-03-09 | 2026-02-27 | 2026-03-09 | 2026-11-23 | 6 | 2026-11-30 | 191
A21240 | Design Calculation Report for structural steel Field Supports SF8300_RCC | 2026-03-09 | 2026-03-30 | 2026-03-09 | 2026-03-30 | 2026-11-30 | 16 | 2026-12-22 | 191
A21250 | Design Calculation Report for structural steel Field Supports SF8300_IFA | 2026-03-31 | 2026-04-03 | 2026-03-31 | 2026-04-03 | 2026-12-22 | 3 | 2026-12-25 | 191
A21260 | Design Calculation Report for structural steel Field Supports SF8300_RCA | 2026-04-03 | 2026-04-27 | 2026-04-03 | 2026-04-27 | 2026-12-28 | 16 | 2027-01-18 | 191
A50080 | Design Calculation Report for structural steel Field Supports SF8300_IFD/IFC | 2026-04-27 | 2026-04-29 | 2026-04-27 | 2026-04-29 | 2027-01-18 | 2 | 2027-01-20 | 191
Design Calculation Report for Foundations Field Supports SF8300 |  | 2026-02-20 | 2026-05-04 | 20-Dec-25 A | 2026-05-04 | 2026-12-22 | 88 | 2027-01-20 | 187
A21330 | Design Calculation Report for Foundations Field Supports SF8300_IFR | 2026-02-20 | 2026-02-20 | 20-Dec-25 A | 01-Jan-26 A | 2026-12-22 | 6 | 2026-12-22
A21340 | Design Calculation Report for Foundations Field Supports SF8300_RCC | 2026-02-20 | 2026-02-20 | 01-Jan-26 A | 16-Jan-26 A | 2026-12-22 | 16 | 2026-12-22
A50120 | Design Calculation Report for Foundations Field Supports SF8300_IFA | 2026-04-03 | 2026-04-08 | 2026-04-03 | 2026-04-08 | 2026-12-22 | 3 | 2026-12-25 | 187
A50130 | Design Calculation Report for Foundations Field Supports SF8300_RCA | 2026-04-08 | 2026-04-30 | 2026-04-08 | 2026-04-30 | 2026-12-28 | 16 | 2027-01-18 | 187
A50140 | Design Calculation Report for Foundations Field Supports SF8300_IFD/IFC | 2026-04-30 | 2026-05-04 | 2026-04-30 | 2026-05-04 | 2027-01-18 | 2 | 2027-01-20 | 187
Foundation Layout, Section and details Field Supports SF8300 |  | 2026-02-20 | 2026-05-04 | 20-Dec-25 A | 2026-05-04 | 2026-12-22 | 86 | 2027-01-20 | 187
A50090 | Foundation Layout, Section and details Field Supports SF8300_IFR | 2026-02-20 | 2026-02-20 | 20-Dec-25 A | 01-Jan-26 A | 2026-12-22 | 6 | 2026-12-22
A50100 | Foundation Layout, Section and details Field Supports SF8300_RCC | 2026-02-20 | 2026-02-20 | 01-Jan-26 A | 15-Jan-26 A | 2026-12-22 | 16 | 2026-12-22
A50110 | Foundation Layout, Section and details Field Supports SF8300_IFA | 2026-04-03 | 2026-04-08 | 2026-04-03 | 2026-04-08 | 2026-12-22 | 3 | 2026-12-25 | 187
A21310 | Foundation Layout, Section and details Field Supports SF8300_RCA | 2026-04-08 | 2026-04-30 | 2026-04-08 | 2026-04-30 | 2026-12-28 | 16 | 2027-01-18 | 187
A21320 | Foundation Layout, Section and details Field Supports SF8300_IFD/IFC | 2026-04-30 | 2026-05-04 | 2026-04-30 | 2026-05-04 | 2027-01-18 | 2 | 2027-01-20 | 187
Structral steel GA and details Field Supports SF8100 |  | 2026-02-20 | 2026-05-04 | 20-Dec-25 A | 2026-05-04 | 2026-05-28 | 86 | 2026-06-26 | 39
A20780 | Structral steel GA and details Field Supports SF8100_IFR | 2026-02-20 | 2026-02-20 | 20-Dec-25 A | 12-Jan-26 A | 2026-05-28 | 6 | 2026-05-28
A49900 | Structral steel GA and details Field Supports SF8100_RCC | 2026-02-20 | 2026-02-20 | 12-Jan-26 A | 15-Jan-26 A | 2026-05-28 | 16 | 2026-05-28
A49910 | Structral steel GA and details Field Supports SF8100_IFA | 2026-04-03 | 2026-04-08 | 2026-04-03 | 2026-04-08 | 2026-05-28 | 3 | 2026-06-02 | 39
A49920 | Structral steel GA and details Field Supports SF8100_RCA | 2026-04-08 | 2026-04-30 | 2026-04-08 | 2026-04-30 | 2026-06-03 | 16 | 2026-06-24 | 39
A49930 | Structral steel GA and details Field Supports SF8100_IFD/IFC | 2026-04-30 | 2026-05-04 | 2026-04-30 | 2026-05-04 | 2026-06-24 | 2 | 2026-06-26 | 39
Design Calculation Report for structural steel Field Supports SF8100 |  | 2026-02-20 | 2026-05-04 | 20-Dec-25 A | 2026-05-04 | 2026-12-17 | 86 | 2027-01-18 | 185
A20830 | Design Calculation Report for structural steel Field Supports SF8100_IFR | 2026-02-20 | 2026-02-20 | 20-Dec-25 A | 12-Jan-26 A | 2026-12-17 | 6 | 2026-12-17
A20840 | Design Calculation Report for structural steel Field Supports SF8100_RCC | 2026-02-20 | 2026-02-20 | 12-Jan-26 A | 15-Jan-26 A | 2026-12-17 | 16 | 2026-12-17
A20850 | Design Calculation Report for structural steel Field Supports SF8100_IFA | 2026-04-03 | 2026-04-08 | 2026-04-03 | 2026-04-08 | 2026-12-17 | 3 | 2026-12-22 | 184
A20860 | Design Calculation Report for structural steel Field Supports SF8100_RCA | 2026-04-08 | 2026-04-30 | 2026-04-08 | 2026-04-30 | 2026-12-23 | 16 | 2027-01-14 | 185
A20870 | Design Calculation Report for structural steel Field Supports SF8100_IFD/IFC | 2026-04-30 | 2026-05-04 | 2026-04-30 | 2026-05-04 | 2027-01-14 | 2 | 2027-01-18 | 185
Design Calculation Report for Foundations Field Supports SF8100 |  | 2026-02-20 | 2026-05-08 | 20-Dec-25 A | 2026-05-08 | 2026-12-22 | 83 | 2027-01-20 | 184
A20930 | Design Calculation Report for Foundations Field Supports SF8100_IFR | 2026-02-20 | 2026-02-20 | 20-Dec-25 A | 01-Jan-26 A | 2026-12-22 | 6 | 2026-12-22
A20940 | Design Calculation Report for Foundations Field Supports SF8100_RCC | 2026-02-20 | 2026-02-20 | 01-Jan-26 A | 15-Jan-26 A | 2026-12-22 | 16 | 2026-12-22
A49940 | Design Calculation Report for Foundations Field Supports SF8100_IFA | 2026-04-08 | 2026-04-14 | 2026-04-08 | 2026-04-14 | 2026-12-22 | 3 | 2026-12-25 | 184
A49950 | Design Calculation Report for Foundations Field Supports SF8100_RCA | 2026-04-14 | 2026-05-05 | 2026-04-14 | 2026-05-05 | 2026-12-28 | 16 | 2027-01-18 | 184
A20970 | Design Calculation Report for Foundations Field Supports SF8100_IFD/IFC | 2026-05-05 | 2026-05-08 | 2026-05-05 | 2026-05-08 | 2027-01-18 | 2 | 2027-01-20 | 184
Foundation Layout, Section and details Field Supports SF8100 |  | 2026-02-20 | 2026-05-08 | 20-Dec-25 A | 2026-05-08 | 2026-12-22 | 83 | 2027-01-20 | 184
A20880 | Foundation Layout, Section and details Field Supports SF8100_IFR | 2026-02-20 | 2026-02-20 | 20-Dec-25 A | 01-Jan-26 A | 2026-12-22 | 6 | 2026-12-22
A20890 | Foundation Layout, Section and details Field Supports SF8100_RCC | 2026-02-20 | 2026-02-20 | 01-Jan-26 A | 15-Jan-26 A | 2026-12-22 | 16 | 2026-12-22
A20900 | Foundation Layout, Section and details Field Supports SF8100_IFA | 2026-04-08 | 2026-04-14 | 2026-04-08 | 2026-04-14 | 2026-12-22 | 3 | 2026-12-25 | 184
A20910 | Foundation Layout, Section and details Field Supports SF8100_RCA | 2026-04-14 | 2026-05-05 | 2026-04-14 | 2026-05-05 | 2026-12-28 | 16 | 2027-01-18 | 184
A20920 | Foundation Layout, Section and details Field Supports SF8100_IFD/IFC | 2026-05-05 | 2026-05-08 | 2026-05-05 | 2026-05-08 | 2027-01-18 | 2 | 2027-01-20 | 184
Adequacy check of Pipe rack SR70 |  | 2026-02-20 | 2026-04-21 | 2026-02-20 | 2026-04-21 | 2026-04-06 | 43 | 2026-06-18 | 42
A22130 | Adequacy check of Pipe rack SR70_IFR | 2026-02-20 | 2026-02-27 | 2026-02-20 | 2026-02-27 | 2026-04-06 | 6 | 2026-04-13 | 31
A22140 | Adequacy check of Pipe rack SR70_RCC | 2026-02-27 | 2026-03-23 | 2026-02-27 | 2026-03-23 | 2026-04-22 | 16 | 2026-05-14 | 38
A50610 | Adequacy check of Pipe rack SR70_IFA | 2026-03-23 | 2026-03-26 | 2026-03-23 | 2026-03-26 | 2026-05-14 | 3 | 2026-05-19 | 38
A50620 | Adequacy check of Pipe rack SR70_RCA | 2026-03-26 | 2026-04-17 | 2026-03-26 | 2026-04-17 | 2026-05-25 | 16 | 2026-06-15 | 42
A50630 | Adequacy check of Pipe rack SR70_IFD/IFC | 2026-04-17 | 2026-04-21 | 2026-04-17 | 2026-04-21 | 2026-06-16 | 2 | 2026-06-18 | 42
Structural GA and Details, Pipe Rack SR70 |  | 2026-02-27 | 2026-04-29 | 2026-02-27 | 2026-04-29 | 2026-04-29 | 43 | 2026-06-26 | 43
A50570 | Structural GA and Details, Pipe Rack SR70_IFR | 2026-02-27 | 2026-03-09 | 2026-02-27 | 2026-03-09 | 2026-04-29 | 6 | 2026-05-06 | 43
A50580 | Structural GA and Details, Pipe Rack SR70_RCC | 2026-03-09 | 2026-03-30 | 2026-03-09 | 2026-03-30 | 2026-05-06 | 16 | 2026-05-28 | 43
A50590 | Structural GA and Details, Pipe Rack SR70_IFA | 2026-03-31 | 2026-04-03 | 2026-03-31 | 2026-04-03 | 2026-05-28 | 3 | 2026-06-02 | 43
A50600 | Structural GA and Details, Pipe Rack SR70_RCA | 2026-04-03 | 2026-04-27 | 2026-04-03 | 2026-04-27 | 2026-06-03 | 16 | 2026-06-24 | 43
A22120 | Structural GA and Details, Pipe Rack SR70_IFD/IFC | 2026-04-27 | 2026-04-29 | 2026-04-27 | 2026-04-29 | 2026-06-24 | 2 | 2026-06-26 | 43
Adequacy check of Pipe rack SR73 |  | 2026-02-27 | 2026-04-29 | 2026-02-27 | 2026-04-29 | 2026-04-14 | 43 | 2026-06-22 | 38
A50660 | Adequacy check of Pipe rack SR73_IFR | 2026-02-27 | 2026-03-09 | 2026-02-27 | 2026-03-09 | 2026-04-14 | 6 | 2026-04-21 | 31
A22240 | Adequacy check of Pipe rack SR73_RCC | 2026-03-09 | 2026-03-30 | 2026-03-09 | 2026-03-30 | 2026-04-28 | 16 | 2026-05-19 | 36
A22250 | Adequacy check of Pipe rack SR73_IFA | 2026-03-31 | 2026-04-03 | 2026-03-31 | 2026-04-03 | 2026-05-19 | 3 | 2026-05-25 | 36
A22260 | Adequacy check of Pipe rack SR73_RCA | 2026-04-03 | 2026-04-27 | 2026-04-03 | 2026-04-27 | 2026-05-27 | 16 | 2026-06-18 | 38
A50670 | Adequacy check of Pipe rack SR73_IFD/IFC | 2026-04-27 | 2026-04-29 | 2026-04-27 | 2026-04-29 | 2026-06-18 | 2 | 2026-06-22 | 38
Structural GA and Details, Pipe Rack SR73 |  | 2026-03-16 | 2026-05-14 | 2026-03-16 | 2026-05-14 | 2026-04-29 | 43 | 2026-06-26 | 31
A22180 | Structural GA and Details, Pipe Rack SR73_IFR | 2026-03-16 | 2026-03-24 | 2026-03-16 | 2026-03-24 | 2026-04-29 | 6 | 2026-05-06 | 31
A22190 | Structural GA and Details, Pipe Rack SR73_RCC | 2026-03-24 | 2026-04-15 | 2026-03-24 | 2026-04-15 | 2026-05-06 | 16 | 2026-05-28 | 31
A22200 | Structural GA and Details, Pipe Rack SR73_IFA | 2026-04-15 | 2026-04-20 | 2026-04-15 | 2026-04-20 | 2026-05-28 | 3 | 2026-06-02 | 31
A50640 | Structural GA and Details, Pipe Rack SR73_RCA | 2026-04-20 | 2026-05-12 | 2026-04-20 | 2026-05-12 | 2026-06-03 | 16 | 2026-06-24 | 31
A50650 | Structural GA and Details, Pipe Rack SR73_IFD/IFC | 2026-05-12 | 2026-05-14 | 2026-05-12 | 2026-05-14 | 2026-06-24 | 2 | 2026-06-26 | 31
Adequacy check of U&O Rack SR37 |  | 2026-03-09 | 2026-05-06 | 2026-03-09 | 2026-05-06 | 2026-04-21 | 43 | 2026-06-24 | 35
A50700 | Adequacy check of U&O Rack SR37_IFR | 2026-03-09 | 2026-03-16 | 2026-03-09 | 2026-03-16 | 2026-04-21 | 6 | 2026-04-29 | 31
A50710 | Adequacy check of U&O Rack SR37_RCC | 2026-03-16 | 2026-04-07 | 2026-03-16 | 2026-04-07 | 2026-05-01 | 16 | 2026-05-25 | 34
A50720 | Adequacy check of U&O Rack SR37_IFA | 2026-04-07 | 2026-04-10 | 2026-04-07 | 2026-04-10 | 2026-05-25 | 3 | 2026-05-28 | 34
A22360 | Adequacy check of U&O Rack SR37_RCA | 2026-04-13 | 2026-05-04 | 2026-04-13 | 2026-05-04 | 2026-05-29 | 16 | 2026-06-22 | 35
A22370 | Adequacy check of U&O Rack SR37_IFD/IFC | 2026-05-04 | 2026-05-06 | 2026-05-04 | 2026-05-06 | 2026-06-22 | 2 | 2026-06-24 | 35
Structural GA and Details, U&O Rack SR37 |  | 2026-03-16 | 2026-05-14 | 2026-03-16 | 2026-05-14 | 2026-04-29 | 43 | 2026-06-26 | 31
A50680 | Structural GA and Details, U&O Rack SR37_IFR | 2026-03-16 | 2026-03-24 | 2026-03-16 | 2026-03-24 | 2026-04-29 | 6 | 2026-05-06 | 31
A50690 | Structural GA and Details, U&O Rack SR37_RCC | 2026-03-24 | 2026-04-15 | 2026-03-24 | 2026-04-15 | 2026-05-06 | 16 | 2026-05-28 | 31
A22300 | Structural GA and Details, U&O Rack SR37_IFA | 2026-04-15 | 2026-04-20 | 2026-04-15 | 2026-04-20 | 2026-05-28 | 3 | 2026-06-02 | 31
A22310 | Structural GA and Details, U&O Rack SR37_RCA | 2026-04-20 | 2026-05-12 | 2026-04-20 | 2026-05-12 | 2026-06-03 | 16 | 2026-06-24 | 31
A22320 | Structural GA and Details, U&O Rack SR37_IFD/IFC | 2026-05-12 | 2026-05-14 | 2026-05-12 | 2026-05-14 | 2026-06-24 | 2 | 2026-06-26 | 31
Structure & Foundation design - Mechanical |  | 2026-02-20 | 2026-03-23 | 10-Apr-25 A | 2026-03-23 | 2026-02-21 | 268 | 2027-01-20 | 218
Foundation Drawing- Lube Oil unit for PSA-2 FeedGas Compressor |  | 2026-02-20 | 2026-02-20 | 12-Apr-25 A | 23-Dec-25 A | 2027-01-20 | 204 | 2027-01-20
A18980 | Foundation Drawing- Lube Oil unit for PSA-2 FeedGas Compressor_IFR | 2026-02-20 | 2026-02-20 | 12-Apr-25 A | 03-May-25 A | 2027-01-20 | 6 | 2027-01-20
A18990 | Foundation Drawing- Lube Oil unit for PSA-2 FeedGas Compressor_RCC | 2026-02-20 | 2026-02-20 | 04-May-25 A | 10-May-25 A | 2027-01-20 | 16 | 2027-01-20
A19000 | Foundation Drawing- Lube Oil unit for PSA-2 FeedGas Compressor_IFA | 2026-02-20 | 2026-02-20 | 11-May-25 A | 21-Jun-25 A | 2027-01-20 | 3 | 2027-01-20
A19010 | Foundation Drawing- Lube Oil unit for PSA-2 FeedGas Compressor_RCA | 2026-02-20 | 2026-02-20 | 27-Jun-25 A | 15-Aug-25 A | 2027-01-20 | 16 | 2027-01-20
A19020 | Foundation Drawing- Lube Oil unit for PSA-2 FeedGas Compressor_IFD/IFC | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 23-Dec-25 A | 2027-01-20 | 2 | 2027-01-20
Design Calculation report for foundation of Lube Oil unit for PSA-2 FeedGas Compressor |  | 2026-02-20 | 2026-02-20 | 13-Apr-25 A | 23-Dec-25 A | 2027-01-20 | 204 | 2027-01-20
A19030 | Design Calculation report for foundation of Lube Oil unit for PSA-2 FeedGas Compressor_IFR | 2026-02-20 | 2026-02-20 | 13-Apr-25 A | 03-May-25 A | 2027-01-20 | 6 | 2027-01-20
A19040 | Design Calculation report for foundation of Lube Oil unit for PSA-2 FeedGas Compressor_RCC | 2026-02-20 | 2026-02-20 | 04-May-25 A | 10-May-25 A | 2027-01-20 | 16 | 2027-01-20
A19050 | Design Calculation report for foundation of Lube Oil unit for PSA-2 FeedGas Compressor_IFA | 2026-02-20 | 2026-02-20 | 11-May-25 A | 21-Jun-25 A | 2027-01-20 | 3 | 2027-01-20
A19060 | Design Calculation report for foundation of Lube Oil unit for PSA-2 FeedGas Compressor_RCA | 2026-02-20 | 2026-02-20 | 27-Jun-25 A | 15-Aug-25 A | 2027-01-20 | 16 | 2027-01-20
A19070 | Design Calculation report for foundation of Lube Oil unit for PSA-2 FeedGas Compressor_IFD/IFC | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 23-Dec-25 A | 2027-01-20 | 2 | 2027-01-20
Foundation Drawing- Lube Oil unit for PSA-2 OffGas Compressor |  | 2026-02-20 | 2026-02-20 | 26-May-25 A | 23-Dec-25 A | 2027-01-20 | 101 | 2027-01-20
A19080 | Foundation Drawing- Lube Oil unit for PSA-2 OffGas Compressor_IFR | 2026-02-20 | 2026-02-20 | 26-May-25 A | 05-Jul-25 A | 2027-01-20 | 6 | 2027-01-20
A19090 | Foundation Drawing- Lube Oil unit for PSA-2 OffGas Compressor_RCC | 2026-02-20 | 2026-02-20 | 07-Jul-25 A | 01-Aug-25 A | 2027-01-20 | 16 | 2027-01-20
A19100 | Foundation Drawing- Lube Oil unit for PSA-2 OffGas Compressor_IFA | 2026-02-20 | 2026-02-20 | 04-Aug-25 A | 08-Aug-25 A | 2027-01-20 | 3 | 2027-01-20
A49150 | Foundation Drawing- Lube Oil unit for PSA-2 OffGas Compressor_RCA | 2026-02-20 | 2026-02-20 | 07-Aug-25 A | 15-Aug-25 A | 2027-01-20 | 16 | 2027-01-20
A49160 | Foundation Drawing- Lube Oil unit for PSA-2 OffGas Compressor_IFD/IFC | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 23-Dec-25 A | 2027-01-20 | 2 | 2027-01-20
Design Calculation report for foundation of Lube Oil unit for PSA-2 OffGas Compressor |  | 2026-02-20 | 2026-02-20 | 26-May-25 A | 23-Dec-25 A | 2027-01-20 | 101 | 2027-01-20
A49170 | Design Calculation report for foundation of Lube Oil unit for PSA-2 OffGas Compressor_IFR | 2026-02-20 | 2026-02-20 | 26-May-25 A | 05-Jul-25 A | 2027-01-20 | 6 | 2027-01-20
A19140 | Design Calculation report for foundation of Lube Oil unit for PSA-2 OffGas Compressor_RCC | 2026-02-20 | 2026-02-20 | 07-Jul-25 A | 01-Aug-25 A | 2027-01-20 | 16 | 2027-01-20
A19150 | Design Calculation report for foundation of Lube Oil unit for PSA-2 OffGas Compressor_IFA | 2026-02-20 | 2026-02-20 | 04-Aug-25 A | 08-Aug-25 A | 2027-01-20 | 3 | 2027-01-20
A19160 | Design Calculation report for foundation of Lube Oil unit for PSA-2 OffGas Compressor_RCA | 2026-02-20 | 2026-02-20 | 07-Aug-25 A | 15-Aug-25 A | 2027-01-20 | 16 | 2027-01-20
A49180 | Design Calculation report for foundation of Lube Oil unit for PSA-2 OffGas Compressor_IFD/IFC | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 23-Dec-25 A | 2027-01-20 | 2 | 2027-01-20
Foundation drawing PSA-2 FeedGas Compressor 13-KC-701 |  | 2026-02-20 | 2026-03-17 | 19-Jul-25 A | 2026-03-17 | 2026-02-21 | 156 | 2027-01-20 | 221
A49020 | Foundation drawing PSA-2 FeedGas Compressor 13-KC-701_IFR | 2026-02-20 | 2026-02-20 | 19-Jul-25 A | 22-Aug-25 A | 2026-02-21 | 11 | 2026-02-21
A49030 | Foundation drawing PSA-2 FeedGas Compressor 13-KC-701_RCC | 2026-02-20 | 2026-02-20 | 01-Aug-25 A | 29-Aug-25 A | 2026-12-28 | 16 | 2026-12-28
A18800 | Foundation drawing PSA-2 FeedGas Compressor 13-KC-701_IFA | 2026-02-20 | 2026-02-20 | 01-Sep-25 A | 05-Sep-25 A | 2026-12-28 | 3 | 2026-12-28
A49040 | Foundation drawing PSA-2 FeedGas Compressor 13-KC-701_RCA | 2026-02-20 | 2026-03-13 | 2026-02-20 | 2026-03-13 | 2026-12-28 | 16 | 2027-01-18 | 221
A49050 | Foundation drawing PSA-2 FeedGas Compressor 13-KC-701_IFD/IFC | 2026-03-13 | 2026-03-17 | 2026-03-13 | 2026-03-17 | 2027-01-18 | 2 | 2027-01-20 | 221
Design Calculation Report PSA-2 FeedGas Compressor 13-KC-701 |  | 2026-02-20 | 2026-02-20 | 12-Apr-25 A | 13-Jan-26 A | 2027-01-20 | 210 | 2027-01-20
A49060 | Design Calculation Report PSA-2 FeedGas Compressor 13-KC-701_IFR | 2026-02-20 | 2026-02-20 | 12-Apr-25 A | 27-Jul-25 A | 2027-01-20 | 11 | 2027-01-20
A49070 | Design Calculation Report PSA-2 FeedGas Compressor 13-KC-701_RCC | 2026-02-20 | 2026-02-20 | 28-Jul-25 A | 15-Aug-25 A | 2027-01-20 | 16 | 2027-01-20
A49080 | Design Calculation Report PSA-2 FeedGas Compressor 13-KC-701_IFA | 2026-02-20 | 2026-02-20 | 18-Aug-25 A | 22-Aug-25 A | 2027-01-20 | 3 | 2027-01-20
A49090 | Design Calculation Report PSA-2 FeedGas Compressor 13-KC-701_RCA | 2026-02-20 | 2026-02-20 | 19-Aug-25 A | 29-Aug-25 A | 2027-01-20 | 16 | 2027-01-20
A49100 | Design Calculation Report PSA-2 FeedGas Compressor 13-KC-701_IFD/IFC | 2026-02-20 | 2026-02-20 | 09-Jan-26 A | 13-Jan-26 A | 2027-01-20 | 2 | 2027-01-20
Foundation drawing PSA-2 OffGas Compressor 13-KC-702 |  | 2026-02-20 | 2026-02-20 | 30-Jun-25 A | 05-Sep-25 A | 2026-02-21 | 57 | 2026-02-21
A18880 | Foundation drawing PSA-2 OffGas Compressor 13-KC-702_IFR | 2026-02-20 | 2026-02-20 | 30-Jun-25 A | 10-Jul-25 A | 2026-02-21 | 11 | 2026-02-21
A49110 | Foundation drawing PSA-2 OffGas Compressor 13-KC-702_RCC | 2026-02-20 | 2026-02-20 | 11-Jul-25 A | 15-Aug-25 A | 2026-02-21 | 16 | 2026-02-21
A49120 | Foundation drawing PSA-2 OffGas Compressor 13-KC-702_IFA | 2026-02-20 | 2026-02-20 | 16-Aug-25 A | 22-Aug-25 A | 2026-02-21 | 3 | 2026-02-21
A49130 | Foundation drawing PSA-2 OffGas Compressor 13-KC-702_RCA | 2026-02-20 | 2026-02-20 | 23-Aug-25 A | 29-Aug-25 A | 2026-02-21 | 16 | 2026-02-21
A49140 | Foundation drawing PSA-2 OffGas Compressor 13-KC-702_IFD/IFC | 2026-02-20 | 2026-02-20 | 30-Aug-25 A | 05-Sep-25 A | 2026-02-21 | 2 | 2026-02-21
Design Calculation Report PSA-2 OffGas Compressor 13-KC-702 |  | 2026-02-20 | 2026-02-24 | 01-Sep-25 A | 2026-02-24 | 2027-01-18 | 87 | 2027-01-20 | 237
A18930 | Design Calculation Report PSA-2 OffGas Compressor 13-KC-702_IFR | 2026-02-20 | 2026-02-20 | 01-Sep-25 A | 13-Sep-25 A | 2027-01-18 | 11 | 2027-01-18
A18940 | Design Calculation Report PSA-2 OffGas Compressor 13-KC-702_RCC | 2026-02-20 | 2026-02-20 | 05-Sep-25 A | 20-Sep-25 A | 2027-01-18 | 16 | 2027-01-18
A18950 | Design Calculation Report PSA-2 OffGas Compressor 13-KC-702_IFA | 2026-02-20 | 2026-02-20 | 22-Sep-25 A | 26-Sep-25 A | 2027-01-18 | 3 | 2027-01-18
A18960 | Design Calculation Report PSA-2 OffGas Compressor 13-KC-702_RCA | 2026-02-20 | 2026-02-20 | 24-Sep-25 A | 04-Oct-25 A | 2027-01-18 | 16 | 2027-01-18
A18970 | Design Calculation Report PSA-2 OffGas Compressor 13-KC-702_IFD/IFC | 2026-02-20 | 2026-02-24 | 2026-02-20 | 2026-02-24 | 2027-01-18 | 2 | 2027-01-20 | 237
Foundation Drawing PSA-2 Unit - Hydrogen Purification 13-XA-710 |  | 2026-02-20 | 2026-02-20 | 05-May-25 A | 10-Jul-25 A | 2027-01-20 | 87 | 2027-01-20
A49600 | Foundation Drawing PSA-2 Unit - Hydrogen Purification 13-XA-710_IFR | 2026-02-20 | 2026-02-20 | 05-May-25 A | 14-May-25 A | 2027-01-20 | 6 | 2027-01-20
A49610 | Foundation Drawing PSA-2 Unit - Hydrogen Purification 13-XA-710_RCC | 2026-02-20 | 2026-02-20 | 08-May-25 A | 21-May-25 A | 2027-01-20 | 16 | 2027-01-20
A20200 | Foundation Drawing PSA-2 Unit - Hydrogen Purification 13-XA-710_IFA | 2026-02-20 | 2026-02-20 | 22-May-25 A | 28-May-25 A | 2027-01-20 | 3 | 2027-01-20
A20210 | Foundation Drawing PSA-2 Unit - Hydrogen Purification 13-XA-710_RCA | 2026-02-20 | 2026-02-20 | 21-May-25 A | 04-Jun-25 A | 2027-01-20 | 16 | 2027-01-20
A20220 | Foundation Drawing PSA-2 Unit - Hydrogen Purification 13-XA-710_IFD/IFC | 2026-02-20 | 2026-02-20 | 09-Jun-25 A | 10-Jul-25 A | 2027-01-20 | 2 | 2027-01-20
Design Calculation Report for foundation of PSA-2 Unit - Hydrogen Purification 13-XA-710 |  | 2026-02-20 | 2026-02-20 | 26-May-25 A | 05-Sep-25 A | 2027-01-20 | 87 | 2027-01-20
A49620 | Design Calculation Report for foundation of PSA-2 Unit - Hydrogen Purification 13-XA-710_IFR | 2026-02-20 | 2026-02-20 | 26-May-25 A | 07-Jul-25 A | 2027-01-20 | 6 | 2027-01-20
A49630 | Design Calculation Report for foundation of PSA-2 Unit - Hydrogen Purification 13-XA-710_RCC | 2026-02-20 | 2026-02-20 | 08-Jul-25 A | 15-Aug-25 A | 2027-01-20 | 16 | 2027-01-20
A49640 | Design Calculation Report for foundation of PSA-2 Unit - Hydrogen Purification 13-XA-710_IFA | 2026-02-20 | 2026-02-20 | 18-Aug-25 A | 22-Aug-25 A | 2027-01-20 | 3 | 2027-01-20
A20260 | Design Calculation Report for foundation of PSA-2 Unit - Hydrogen Purification 13-XA-710_RCA | 2026-02-20 | 2026-02-20 | 11-Aug-25 A | 29-Aug-25 A | 2027-01-20 | 16 | 2027-01-20
A20270 | Design Calculation Report for foundation of PSA-2 Unit - Hydrogen Purification 13-XA-710_IFD/IFC | 2026-02-20 | 2026-02-20 | 01-Sep-25 A | 05-Sep-25 A | 2027-01-20 | 2 | 2027-01-20
Foundation drawing for Equipment 50-HE-1410 |  | 2026-02-20 | 2026-02-24 | 02-May-25 A | 2026-02-24 | 2026-03-29 | 215 | 2027-01-20 | 237
A50340 | Foundation drawing for Equipment 50-HE-1410_IFR | 2026-02-20 | 2026-02-20 | 02-May-25 A | 23-May-25 A | 2026-03-29 | 6 | 2026-03-29
A50350 | Foundation drawing for Equipment 50-HE-1410_RCC | 2026-02-20 | 2026-02-20 | 24-May-25 A | 29-May-25 A | 2027-01-18 | 16 | 2027-01-18
A50360 | Foundation drawing for Equipment 50-HE-1410_IFA | 2026-02-20 | 2026-02-20 | 01-Aug-25 A | 22-Aug-25 A | 2027-01-18 | 3 | 2027-01-18
A50370 | Foundation drawing for Equipment 50-HE-1410_RCA | 2026-02-20 | 2026-02-20 | 11-Aug-25 A | 29-Aug-25 A | 2027-01-18 | 16 | 2027-01-18
A50380 | Foundation drawing for Equipment 50-HE-1410_IFD/IFC | 2026-02-20 | 2026-02-24 | 2026-02-20 | 2026-02-24 | 2027-01-18 | 2 | 2027-01-20 | 237
Design calculation for foundation of Equipment 50-HE-1410 |  | 2026-02-20 | 2026-02-20 | 02-May-25 A | 23-Dec-25 A | 2027-01-20 | 123 | 2027-01-20
A50390 | Design calculation for foundation of Equipment 50-HE-1410_IFR | 2026-02-20 | 2026-02-20 | 02-May-25 A | 23-May-25 A | 2027-01-20 | 6 | 2027-01-20
A50400 | Design calculation for foundation of Equipment 50-HE-1410_RCC | 2026-02-20 | 2026-02-20 | 24-May-25 A | 21-Jun-25 A | 2027-01-20 | 16 | 2027-01-20
A50410 | Design calculation for foundation of Equipment 50-HE-1410_IFA | 2026-02-20 | 2026-02-20 | 15-Jul-25 A | 22-Aug-25 A | 2027-01-20 | 3 | 2027-01-20
A50420 | Design calculation for foundation of Equipment 50-HE-1410_RCA | 2026-02-20 | 2026-02-20 | 29-Sep-25 A | 24-Oct-25 A | 2027-01-20 | 16 | 2027-01-20
A21870 | Design calculation for foundation of Equipment 50-HE-1410_IFD/IFC | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 23-Dec-25 A | 2027-01-20 | 2 | 2027-01-20
Foundation Drawing PSA-2 OffGas Compressor Interstage Cooler 13-HE-708 |  | 2026-02-20 | 2026-02-20 | 01-May-25 A | 10-Oct-25 A | 2026-03-29 | 108 | 2026-03-29
A20080 | Foundation Drawing PSA-2 OffGas Compressor Interstage Cooler 13-HE-708_IFR | 2026-02-20 | 2026-02-20 | 01-May-25 A | 15-May-25 A | 2026-03-29 | 6 | 2026-03-29
A20090 | Foundation Drawing PSA-2 OffGas Compressor Interstage Cooler 13-HE-708_RCC | 2026-02-20 | 2026-02-20 | 16-May-25 A | 22-May-25 A | 2026-03-29 | 16 | 2026-03-29
A20100 | Foundation Drawing PSA-2 OffGas Compressor Interstage Cooler 13-HE-708_IFA | 2026-02-20 | 2026-02-20 | 23-May-25 A | 21-Jun-25 A | 2026-03-29 | 3 | 2026-03-29
A49560 | Foundation Drawing PSA-2 OffGas Compressor Interstage Cooler 13-HE-708_RCA | 2026-02-20 | 2026-02-20 | 01-Aug-25 A | 21-Aug-25 A | 2026-03-29 | 16 | 2026-03-29
A49570 | Foundation Drawing PSA-2 OffGas Compressor Interstage Cooler 13-HE-708_IFD/IFC | 2026-02-20 | 2026-02-20 | 26-Sep-25 A | 10-Oct-25 A | 2026-03-29 | 2 | 2026-03-29
Design Calculation Report for foundation of PSA-2 OffGas Compressor Interstage Cooler 13-HE-708 |  | 2026-02-20 | 2026-02-20 | 28-Apr-25 A | 10-Oct-25 A | 2027-01-20 | 82 | 2027-01-20
A49580 | Design Calculation Report for foundation of PSA-2 OffGas Compressor Interstage Cooler 13-HE-708_IFR | 2026-02-20 | 2026-02-20 | 28-Apr-25 A | 19-May-25 A | 2027-01-20 | 6 | 2027-01-20
A20140 | Design Calculation Report for foundation of PSA-2 OffGas Compressor Interstage Cooler 13-HE-708_RCC | 2026-02-20 | 2026-02-20 | 20-May-25 A | 21-Jun-25 A | 2027-01-20 | 16 | 2027-01-20
A20150 | Design Calculation Report for foundation of PSA-2 OffGas Compressor Interstage Cooler 13-HE-708_IFA | 2026-02-20 | 2026-02-20 | 22-Jun-25 A | 28-Jun-25 A | 2027-01-20 | 3 | 2027-01-20
A20160 | Design Calculation Report for foundation of PSA-2 OffGas Compressor Interstage Cooler 13-HE-708_RCA | 2026-02-20 | 2026-02-20 | 21-Jul-25 A | 21-Aug-25 A | 2027-01-20 | 16 | 2027-01-20
A49590 | Design Calculation Report for foundation of PSA-2 OffGas Compressor Interstage Cooler 13-HE-708_IFD/IFC | 2026-02-20 | 2026-02-20 | 22-Sep-25 A | 10-Oct-25 A | 2027-01-20 | 2 | 2027-01-20
Foundation Drawing PSA-2 Feed Gas Compressor AfterCooler 13-HE-704 |  | 2026-02-20 | 2026-02-20 | 28-Apr-25 A | 25-Jul-25 A | 2026-05-03 | 111 | 2026-05-26
A19280 | Foundation Drawing PSA-2 Feed Gas Compressor AfterCooler 13-HE-704_IFR | 2026-02-20 | 2026-02-20 | 28-Apr-25 A | 19-May-25 A | 2026-05-03 | 6 | 2026-05-03
A19290 | Foundation Drawing PSA-2 Feed Gas Compressor AfterCooler 13-HE-704_RCC | 2026-02-20 | 2026-02-20 | 20-May-25 A | 21-Jun-25 A | 2026-05-26 | 16 | 2026-05-26
A19300 | Foundation Drawing PSA-2 Feed Gas Compressor AfterCooler 13-HE-704_IFA | 2026-02-20 | 2026-02-20 | 22-Jun-25 A | 28-Jun-25 A | 2026-05-26 | 3 | 2026-05-26
A19310 | Foundation Drawing PSA-2 Feed Gas Compressor AfterCooler 13-HE-704_RCA | 2026-02-20 | 2026-02-20 | 30-Jun-25 A | 18-Jul-25 A | 2026-05-26 | 16 | 2026-05-26
A19320 | Foundation Drawing PSA-2 Feed Gas Compressor AfterCooler 13-HE-704_IFD/IFC | 2026-02-20 | 2026-02-20 | 21-Jul-25 A | 25-Jul-25 A | 2026-05-26 | 2 | 2026-05-26
Design Calculation Report for foundation of PSA-2 Feed Gas Compressor AfterCooler 13-HE-704 |  | 2026-02-20 | 2026-02-20 | 28-Apr-25 A | 08-Sep-25 A | 2027-01-20 | 36 | 2027-01-20
A19330 | Design Calculation Report for foundation of PSA-2 Feed Gas Compressor AfterCooler 13-HE-704_IFR | 2026-02-20 | 2026-02-20 | 28-Apr-25 A | 03-May-25 A | 2027-01-20 | 6 | 2027-01-20
A19340 | Design Calculation Report for foundation of PSA-2 Feed Gas Compressor AfterCooler 13-HE-704_RCC | 2026-02-20 | 2026-02-20 | 04-May-25 A | 19-May-25 A | 2027-01-20 | 16 | 2027-01-20
A49240 | Design Calculation Report for foundation of PSA-2 Feed Gas Compressor AfterCooler 13-HE-704_IFA | 2026-02-20 | 2026-02-20 | 20-May-25 A | 21-Jun-25 A | 2027-01-20 | 3 | 2027-01-20
A49250 | Design Calculation Report for foundation of PSA-2 Feed Gas Compressor AfterCooler 13-HE-704_RCA | 2026-02-20 | 2026-02-20 | 22-Jun-25 A | 28-Jun-25 A | 2027-01-20 | 16 | 2027-01-20
A49260 | Design Calculation Report for foundation of PSA-2 Feed Gas Compressor AfterCooler 13-HE-704_IFD/IFC | 2026-02-20 | 2026-02-20 | 29-Jun-25 A | 08-Sep-25 A | 2027-01-20 | 2 | 2027-01-20
Foundation Drawing PSA-2 Feed Gas Compressor Interstage Cooler 13-HE-703 |  | 2026-02-20 | 2026-02-20 | 24-Apr-25 A | 15-Sep-25 A | 2026-05-03 | 103 | 2026-05-24
A49310 | Foundation Drawing PSA-2 Feed Gas Compressor Interstage Cooler 13-HE-703_IFR | 2026-02-20 | 2026-02-20 | 24-Apr-25 A | 15-May-25 A | 2026-05-03 | 6 | 2026-05-03
A49320 | Foundation Drawing PSA-2 Feed Gas Compressor Interstage Cooler 13-HE-703_RCC | 2026-02-20 | 2026-02-20 | 16-May-25 A | 22-May-25 A | 2026-05-24 | 16 | 2026-05-24
A19500 | Foundation Drawing PSA-2 Feed Gas Compressor Interstage Cooler 13-HE-703_IFA | 2026-02-20 | 2026-02-20 | 23-May-25 A | 01-Sep-25 A | 2026-05-24 | 3 | 2026-05-24
A19510 | Foundation Drawing PSA-2 Feed Gas Compressor Interstage Cooler 13-HE-703_RCA | 2026-02-20 | 2026-02-20 | 02-Sep-25 A | 08-Sep-25 A | 2026-05-24 | 16 | 2026-05-24
A19520 | Foundation Drawing PSA-2 Feed Gas Compressor Interstage Cooler 13-HE-703_IFD/IFC | 2026-02-20 | 2026-02-20 | 09-Sep-25 A | 15-Sep-25 A | 2026-05-24 | 2 | 2026-05-24
Design Calculation Report for foundation of PSA-2 Feed Gas Compressor Interstage Cooler 13-HE-703 |  | 2026-02-20 | 2026-02-20 | 24-Apr-25 A | 15-Sep-25 A | 2027-01-20 | 53 | 2027-01-20
A49330 | Design Calculation Report for foundation of PSA-2 Feed Gas Compressor Interstage Cooler 13-HE-703_IFR | 2026-02-20 | 2026-02-20 | 24-Apr-25 A | 15-May-25 A | 2027-01-20 | 6 | 2027-01-20
A49340 | Design Calculation Report for foundation of PSA-2 Feed Gas Compressor Interstage Cooler 13-HE-703_RCC | 2026-02-20 | 2026-02-20 | 16-May-25 A | 22-May-25 A | 2027-01-20 | 16 | 2027-01-20
A49350 | Design Calculation Report for foundation of PSA-2 Feed Gas Compressor Interstage Cooler 13-HE-703_IFA | 2026-02-20 | 2026-02-20 | 23-May-25 A | 01-Sep-25 A | 2027-01-20 | 3 | 2027-01-20
A19560 | Design Calculation Report for foundation of PSA-2 Feed Gas Compressor Interstage Cooler 13-HE-703_RCA | 2026-02-20 | 2026-02-20 | 02-Sep-25 A | 09-Sep-25 A | 2027-01-20 | 16 | 2027-01-20
A19570 | Design Calculation Report for foundation of PSA-2 Feed Gas Compressor Interstage Cooler 13-HE-703_IFD/IFC | 2026-02-20 | 2026-02-20 | 10-Sep-25 A | 15-Sep-25 A | 2027-01-20 | 2 | 2027-01-20
Foundation Drawing PSA-2 OffGas Compressor AfterCooler 13-HE-709 |  | 2026-02-20 | 2026-02-20 | 20-May-25 A | 10-Oct-25 A | 2026-05-03 | 101 | 2026-05-07
A49430 | Foundation Drawing PSA-2 OffGas Compressor AfterCooler 13-HE-709_IFR | 2026-02-20 | 2026-02-20 | 30-May-25 A | 13-Jun-25 A | 2026-05-03 | 6 | 2026-05-03
A19790 | Foundation Drawing PSA-2 OffGas Compressor AfterCooler 13-HE-709_RCC | 2026-02-20 | 2026-02-20 | 20-May-25 A | 21-Jun-25 A | 2026-05-07 | 16 | 2026-05-07
A19800 | Foundation Drawing PSA-2 OffGas Compressor AfterCooler 13-HE-709_IFA | 2026-02-20 | 2026-02-20 | 22-Jun-25 A | 28-Jun-25 A | 2026-05-07 | 3 | 2026-05-07
A19810 | Foundation Drawing PSA-2 OffGas Compressor AfterCooler 13-HE-709_RCA | 2026-02-20 | 2026-02-20 | 30-Jun-25 A | 15-Sep-25 A | 2026-05-07 | 16 | 2026-05-07
A19820 | Foundation Drawing PSA-2 OffGas Compressor AfterCooler 13-HE-709_IFD/IFC | 2026-02-20 | 2026-02-20 | 16-Sep-25 A | 10-Oct-25 A | 2026-05-07 | 2 | 2026-05-07
Design Calculation Report for foundation of PSA-2 OffGas Compressor AfterCooler 13-HE-709 |  | 2026-02-20 | 2026-02-20 | 28-Apr-25 A | 08-Oct-25 A | 2027-01-20 | 36 | 2027-01-20
A19830 | Design Calculation Report for foundation of PSA-2 OffGas Compressor AfterCooler 13-HE-709_IFR | 2026-02-20 | 2026-02-20 | 28-Apr-25 A | 19-May-25 A | 2027-01-20 | 6 | 2027-01-20
A19840 | Design Calculation Report for foundation of PSA-2 OffGas Compressor AfterCooler 13-HE-709_RCC | 2026-02-20 | 2026-02-20 | 20-May-25 A | 21-Jun-25 A | 2027-01-20 | 16 | 2027-01-20
A19850 | Design Calculation Report for foundation of PSA-2 OffGas Compressor AfterCooler 13-HE-709_IFA | 2026-02-20 | 2026-02-20 | 22-Jun-25 A | 28-Jun-25 A | 2027-01-20 | 3 | 2027-01-20
A19860 | Design Calculation Report for foundation of PSA-2 OffGas Compressor AfterCooler 13-HE-709_RCA | 2026-02-20 | 2026-02-20 | 29-Jun-25 A | 08-Sep-25 A | 2027-01-20 | 16 | 2027-01-20
A49440 | Design Calculation Report for foundation of PSA-2 OffGas Compressor AfterCooler 13-HE-709_IFD/IFC | 2026-02-20 | 2026-02-20 | 09-Sep-25 A | 08-Oct-25 A | 2027-01-20 | 2 | 2027-01-20
Foundation Drawing PSA-2 OffGas Compressor Discharge Dripleg 13-SP-7004 |  | 2026-02-20 | 2026-02-20 | 16-Apr-25 A | 04-Sep-25 A | 2026-05-03 | 44 | 2026-05-03
A19980 | Foundation Drawing PSA-2 OffGas Compressor Discharge Dripleg 13-SP-7004_IFR | 2026-02-20 | 2026-02-20 | 16-Apr-25 A | 07-May-25 A | 2026-05-03 | 6 | 2026-05-03
A49500 | Foundation Drawing PSA-2 OffGas Compressor Discharge Dripleg 13-SP-7004_RCC | 2026-02-20 | 2026-02-20 | 08-May-25 A | 14-May-25 A | 2026-05-03 | 16 | 2026-05-03
A49510 | Foundation Drawing PSA-2 OffGas Compressor Discharge Dripleg 13-SP-7004_IFA | 2026-02-20 | 2026-02-20 | 15-May-25 A | 03-Jun-25 A | 2026-05-03 | 3 | 2026-05-03
A49520 | Foundation Drawing PSA-2 OffGas Compressor Discharge Dripleg 13-SP-7004_RCA | 2026-02-20 | 2026-02-20 | 04-Jun-25 A | 21-Jun-25 A | 2026-05-03 | 16 | 2026-05-03
A20020 | Foundation Drawing PSA-2 OffGas Compressor Discharge Dripleg 13-SP-7004_IFD/IFC | 2026-02-20 | 2026-02-20 | 22-Jun-25 A | 04-Sep-25 A | 2026-05-03 | 2 | 2026-05-03
Design Calculation Report for foundation of PSA-2 OffGas Compressor Discharge Dripleg 13-SP-7004 |  | 2026-02-20 | 2026-02-20 | 16-Apr-25 A | 10-Oct-25 A | 2027-01-20 | 47 | 2027-01-20
A20030 | Design Calculation Report for foundation of PSA-2 OffGas Compressor Discharge Dripleg 13-SP-7004_IFR | 2026-02-20 | 2026-02-20 | 16-Apr-25 A | 07-May-25 A | 2027-01-20 | 6 | 2027-01-20
A20040 | Design Calculation Report for foundation of PSA-2 OffGas Compressor Discharge Dripleg 13-SP-7004_RCC | 2026-02-20 | 2026-02-20 | 08-May-25 A | 14-May-25 A | 2027-01-20 | 16 | 2027-01-20
A49530 | Design Calculation Report for foundation of PSA-2 OffGas Compressor Discharge Dripleg 13-SP-7004_IFA | 2026-02-20 | 2026-02-20 | 15-May-25 A | 03-Jun-25 A | 2027-01-20 | 3 | 2027-01-20
A49540 | Design Calculation Report for foundation of PSA-2 OffGas Compressor Discharge Dripleg 13-SP-7004_RCA | 2026-02-20 | 2026-02-20 | 04-Jun-25 A | 21-Jun-25 A | 2027-01-20 | 16 | 2027-01-20
A49550 | Design Calculation Report for foundation of PSA-2 OffGas Compressor Discharge Dripleg 13-SP-7004_IFD/IFC | 2026-02-20 | 2026-02-20 | 29-Sep-25 A | 10-Oct-25 A | 2027-01-20 | 2 | 2027-01-20
Foundation Drawing PSA-2 Slop Drum 70-VV-1415 |  | 2026-02-20 | 2026-03-23 | 24-Apr-25 A | 2026-03-23 | 2026-05-11 | 146 | 2027-01-20 | 218
A20280 | Foundation Drawing PSA-2 Slop Drum 70-VV-1415_IFR | 2026-02-20 | 2026-02-20 | 24-Apr-25 A | 15-May-25 A | 2026-05-11 | 6 | 2026-05-11
A49650 | Foundation Drawing PSA-2 Slop Drum 70-VV-1415_RCC | 2026-02-20 | 2026-02-20 | 16-May-25 A | 22-May-25 A | 2026-05-21 | 16 | 2026-05-21
A49660 | Foundation Drawing PSA-2 Slop Drum 70-VV-1415_IFA | 2026-02-20 | 2026-02-25 | 2026-02-20 | 2026-02-25 | 2026-12-22 | 3 | 2026-12-25 | 218
A49670 | Foundation Drawing PSA-2 Slop Drum 70-VV-1415_RCA | 2026-02-25 | 2026-03-19 | 2026-02-25 | 2026-03-19 | 2026-12-28 | 16 | 2027-01-18 | 218
A20320 | Foundation Drawing PSA-2 Slop Drum 70-VV-1415_IFD/IFC | 2026-03-19 | 2026-03-23 | 2026-03-19 | 2026-03-23 | 2027-01-18 | 2 | 2027-01-20 | 218
Design Calculation Report for foundation of PSA-2 Slop Drum 70-VV-1415 |  | 2026-02-20 | 2026-02-20 | 01-Aug-25 A | 19-Jan-26 A | 2027-01-20 | 74 | 2027-01-20
A20330 | Design Calculation Report for foundation of PSA-2 Slop Drum 70-VV-1415_IFR | 2026-02-20 | 2026-02-20 | 01-Aug-25 A | 22-Aug-25 A | 2027-01-20 | 6 | 2027-01-20
A20340 | Design Calculation Report for foundation of PSA-2 Slop Drum 70-VV-1415_RCC | 2026-02-20 | 2026-02-20 | 08-Aug-25 A | 26-Aug-25 A | 2027-01-20 | 16 | 2027-01-20
A49680 | Design Calculation Report for foundation of PSA-2 Slop Drum 70-VV-1415_IFA | 2026-02-20 | 2026-02-20 | 27-Aug-25 A | 02-Sep-25 A | 2027-01-20 | 3 | 2027-01-20
A49690 | Design Calculation Report for foundation of PSA-2 Slop Drum 70-VV-1415_RCA | 2026-02-20 | 2026-02-20 | 25-Aug-25 A | 09-Sep-25 A | 2027-01-20 | 16 | 2027-01-20
A49700 | Design Calculation Report for foundation of PSA-2 Slop Drum 70-VV-1415_IFD/IFC | 2026-02-20 | 2026-02-20 | 15-Jan-26 A | 19-Jan-26 A | 2027-01-20 | 2 | 2027-01-20
Foundation Drawing PSA-2 Feed Gas Compressor 2nd Stage Discharge Drum 13-VV-707 |  | 2026-02-20 | 2026-02-20 | 20-Apr-25 A | 23-Dec-25 A | 2026-05-11 | 76 | 2026-05-11
A49190 | Foundation Drawing PSA-2 Feed Gas Compressor 2nd Stage Discharge Drum 13-VV-707_IFR | 2026-02-20 | 2026-02-20 | 20-Apr-25 A | 11-May-25 A | 2026-05-11 | 6 | 2026-05-11
A49200 | Foundation Drawing PSA-2 Feed Gas Compressor 2nd Stage Discharge Drum 13-VV-707_RCC | 2026-02-20 | 2026-02-20 | 12-May-25 A | 18-May-25 A | 2026-05-11 | 16 | 2026-05-11
A19200 | Foundation Drawing PSA-2 Feed Gas Compressor 2nd Stage Discharge Drum 13-VV-707_IFA | 2026-02-20 | 2026-02-20 | 19-May-25 A | 11-Jun-25 A | 2026-05-11 | 3 | 2026-05-11
A19210 | Foundation Drawing PSA-2 Feed Gas Compressor 2nd Stage Discharge Drum 13-VV-707_RCA | 2026-02-20 | 2026-02-20 | 22-Sep-25 A | 10-Oct-25 A | 2026-05-11 | 16 | 2026-05-11
A19220 | Foundation Drawing PSA-2 Feed Gas Compressor 2nd Stage Discharge Drum 13-VV-707_IFD/IFC | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 23-Dec-25 A | 2026-05-11 | 2 | 2026-05-11
Design Calculation Report-Foundation of PSA-2 FeedGas Compressor 2ndStage DischargeDrum 13-VV-707 |  | 2026-02-20 | 2026-02-20 | 20-Apr-25 A | 23-Dec-25 A | 2027-01-20 | 76 | 2027-01-20
A49210 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 FEED GAS COMPRESSOR 2ND STAGE DISCHARGE DRUM 13-VV-707_IFR | 2026-02-20 | 2026-02-20 | 20-Apr-25 A | 11-May-25 A | 2027-01-20 | 6 | 2027-01-20
A49220 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 FEED GAS COMPRESSOR 2ND STAGE DISCHARGE DRUM 13-VV-707_RCC | 2026-02-20 | 2026-02-20 | 12-May-25 A | 18-May-25 A | 2027-01-20 | 16 | 2027-01-20
A49230 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 FEED GAS COMPRESSOR 2ND STAGE DISCHARGE DRUM 13-VV-707_IFA | 2026-02-20 | 2026-02-20 | 19-May-25 A | 11-Jun-25 A | 2027-01-20 | 3 | 2027-01-20
A19260 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 FEED GAS COMPRESSOR 2ND STAGE DISCHARGE DRUM 13-VV-707_RCA | 2026-02-20 | 2026-02-20 | 22-Sep-25 A | 10-Oct-25 A | 2027-01-20 | 16 | 2027-01-20
A19270 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 FEED GAS COMPRESSOR 2ND STAGE DISCHARGE DRUM 13-VV-707_IFD/IFC | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 23-Dec-25 A | 2027-01-20 | 2 | 2027-01-20
Foundation Drawing PSA-2 Feed Gas Compressor 2nd Stage Suction Drum 13-VV-706 |  | 2026-02-20 | 2026-02-20 | 16-Apr-25 A | 16-Sep-25 A | 2026-05-14 | 43 | 2026-05-18
A19380 | Foundation Drawing PSA-2 Feed Gas Compressor 2nd Stage Suction Drum 13-VV-706_IFR | 2026-02-20 | 2026-02-20 | 16-Apr-25 A | 03-May-25 A | 2026-05-14 | 6 | 2026-05-14
A19390 | Foundation Drawing PSA-2 Feed Gas Compressor 2nd Stage Suction Drum 13-VV-706_RCC | 2026-02-20 | 2026-02-20 | 04-May-25 A | 10-May-25 A | 2026-05-18 | 16 | 2026-05-18
A19400 | Foundation Drawing PSA-2 Feed Gas Compressor 2nd Stage Suction Drum 13-VV-706_IFA | 2026-02-20 | 2026-02-20 | 11-May-25 A | 11-Jun-25 A | 2026-05-18 | 3 | 2026-05-18
A49270 | Foundation Drawing PSA-2 Feed Gas Compressor 2nd Stage Suction Drum 13-VV-706_RCA | 2026-02-20 | 2026-02-20 | 12-Jun-25 A | 01-Sep-25 A | 2026-05-18 | 16 | 2026-05-18
A49280 | Foundation Drawing PSA-2 Feed Gas Compressor 2nd Stage Suction Drum 13-VV-706_IFD/IFC | 2026-02-20 | 2026-02-20 | 02-Sep-25 A | 16-Sep-25 A | 2026-05-18 | 2 | 2026-05-18
Design Calculation Report Foundation of PSA-2 FeedGas Compressor 2ndStage Suction Drum 13-VV-706 |  | 2026-02-20 | 2026-02-20 | 16-Apr-25 A | 08-Sep-25 A | 2027-01-20 | 29 | 2027-01-20
A49290 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 FEED GAS COMPRESSOR 2ND STAGE SUCTION DRUM 13-VV-706_IFR | 2026-02-20 | 2026-02-20 | 16-Apr-25 A | 03-May-25 A | 2027-01-20 | 6 | 2027-01-20
A19440 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 FEED GAS COMPRESSOR 2ND STAGE SUCTION DRUM 13-VV-706_RCC | 2026-02-20 | 2026-02-20 | 04-May-25 A | 10-May-25 A | 2027-01-20 | 16 | 2027-01-20
A19450 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 FEED GAS COMPRESSOR 2ND STAGE SUCTION DRUM 13-VV-706_IFA | 2026-02-20 | 2026-02-20 | 11-May-25 A | 11-Jun-25 A | 2027-01-20 | 3 | 2027-01-20
A19460 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 FEED GAS COMPRESSOR 2ND STAGE SUCTION DRUM 13-VV-706_RCA | 2026-02-20 | 2026-02-20 | 12-Jun-25 A | 21-Jun-25 A | 2027-01-20 | 16 | 2027-01-20
A49300 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 FEED GAS COMPRESSOR 2ND STAGE SUCTION DRUM 13-VV-706_IFD/IFC | 2026-02-20 | 2026-02-20 | 22-Jun-25 A | 08-Sep-25 A | 2027-01-20 | 2 | 2027-01-20
Foundation Drawing PSA-2 Feed Gas Compressor 1st Stage Suction Drum 13-VV-705 |  | 2026-02-20 | 2026-02-20 | 24-Apr-25 A | 23-Dec-25 A | 2026-05-14 | 66 | 2026-05-14
A19580 | Foundation Drawing PSA-2 Feed Gas Compressor 1st Stage Suction Drum 13-VV-705_IFR | 2026-02-20 | 2026-02-20 | 24-Apr-25 A | 15-May-25 A | 2026-05-14 | 6 | 2026-05-14
A49360 | Foundation Drawing PSA-2 Feed Gas Compressor 1st Stage Suction Drum 13-VV-705_RCC | 2026-02-20 | 2026-02-20 | 16-May-25 A | 22-May-25 A | 2026-05-14 | 16 | 2026-05-14
A49370 | Foundation Drawing PSA-2 Feed Gas Compressor 1st Stage Suction Drum 13-VV-705_IFA | 2026-02-20 | 2026-02-20 | 23-May-25 A | 04-Jun-25 A | 2026-05-14 | 3 | 2026-05-14
A49380 | Foundation Drawing PSA-2 Feed Gas Compressor 1st Stage Suction Drum 13-VV-705_RCA | 2026-02-20 | 2026-02-20 | 05-Jun-25 A | 21-Jun-25 A | 2026-05-14 | 16 | 2026-05-14
A19620 | Foundation Drawing PSA-2 Feed Gas Compressor 1st Stage Suction Drum 13-VV-705_IFD/IFC | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 23-Dec-25 A | 2026-05-14 | 2 | 2026-05-14
Design Calculation Report Foundation of PSA-2 FeedGas Compressor 1stStage Suction Drum 13-VV-705 |  | 2026-02-20 | 2026-02-20 | 24-Apr-25 A | 23-Dec-25 A | 2027-01-20 | 66 | 2027-01-20
A19630 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 FEED GAS COMPRESSOR 1ST STAGE SUCTION DRUM 13-VV-705_IFR | 2026-02-20 | 2026-02-20 | 24-Apr-25 A | 15-May-25 A | 2027-01-20 | 6 | 2027-01-20
A19640 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 FEED GAS COMPRESSOR 1ST STAGE SUCTION DRUM 13-VV-705_RCC | 2026-02-20 | 2026-02-20 | 16-May-25 A | 22-May-25 A | 2027-01-20 | 16 | 2027-01-20
A49390 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 FEED GAS COMPRESSOR 1ST STAGE SUCTION DRUM 13-VV-705_IFA | 2026-02-20 | 2026-02-20 | 23-May-25 A | 03-Jun-25 A | 2027-01-20 | 3 | 2027-01-20
A49400 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 FEED GAS COMPRESSOR 1ST STAGE SUCTION DRUM 13-VV-705_RCA | 2026-02-20 | 2026-02-20 | 04-Jun-25 A | 21-Jun-25 A | 2027-01-20 | 16 | 2027-01-20
A49410 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 FEED GAS COMPRESSOR 1ST STAGE SUCTION DRUM 13-VV-705_IFD/IFC | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 23-Dec-25 A | 2027-01-20 | 2 | 2027-01-20
Foundation Drawing PSA-2 OffGas Compressor 2nd Stage Suction Drum 13-VV-713 |  | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 29-Jul-25 A | 2026-05-14 | 47 | 2026-06-22
A19680 | Foundation Drawing PSA-2 OffGas Compressor 2nd Stage Suction Drum 13-VV-713_IFR | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 06-May-25 A | 2026-05-14 | 6 | 2026-05-14
A19690 | Foundation Drawing PSA-2 OffGas Compressor 2nd Stage Suction Drum 13-VV-713_RCC | 2026-02-20 | 2026-02-20 | 07-May-25 A | 13-Jun-25 A | 2026-06-22 | 16 | 2026-06-22
A19700 | Foundation Drawing PSA-2 OffGas Compressor 2nd Stage Suction Drum 13-VV-713_IFA | 2026-02-20 | 2026-02-20 | 16-Jun-25 A | 30-Jun-25 A | 2026-06-22 | 3 | 2026-06-22
A19710 | Foundation Drawing PSA-2 OffGas Compressor 2nd Stage Suction Drum 13-VV-713_RCA | 2026-02-20 | 2026-02-20 | 16-Jun-25 A | 14-Jul-25 A | 2026-06-22 | 16 | 2026-06-22
A19720 | Foundation Drawing PSA-2 OffGas Compressor 2nd Stage Suction Drum 13-VV-713_IFD/IFC | 2026-02-20 | 2026-02-20 | 15-Jul-25 A | 29-Jul-25 A | 2026-06-22 | 2 | 2026-06-22
Design Calculation Report Foundation of PSA-2 OffGas Compressor 2ndStage Suction Drum 13-VV-713 |  | 2026-02-20 | 2026-02-20 | 20-Apr-25 A | 10-Oct-25 A | 2027-01-20 | 50 | 2027-01-20
A19730 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 OFFGAS COMPRESSOR 2ND STAGE SUCTION DRUM 13-VV-713_IFR | 2026-02-20 | 2026-02-20 | 20-Apr-25 A | 11-May-25 A | 2027-01-20 | 6 | 2027-01-20
A19740 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 OFFGAS COMPRESSOR 2ND STAGE SUCTION DRUM 13-VV-713_RCC | 2026-02-20 | 2026-02-20 | 12-May-25 A | 21-Jun-25 A | 2027-01-20 | 16 | 2027-01-20
A19750 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 OFFGAS COMPRESSOR 2ND STAGE SUCTION DRUM 13-VV-713_IFA | 2026-02-20 | 2026-02-20 | 22-Jun-25 A | 28-Jun-25 A | 2027-01-20 | 3 | 2027-01-20
A19760 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 OFFGAS COMPRESSOR 2ND STAGE SUCTION DRUM 13-VV-713_RCA | 2026-02-20 | 2026-02-20 | 01-Jul-25 A | 04-Sep-25 A | 2027-01-20 | 16 | 2027-01-20
A49420 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 OFFGAS COMPRESSOR 2ND STAGE SUCTION DRUM 13-VV-713_IFD/IFC | 2026-02-20 | 2026-02-20 | 08-Sep-25 A | 10-Oct-25 A | 2027-01-20 | 2 | 2027-01-20
Foundation Drawing PSA-2 OffGas Buffer Drum 13-VV-712 |  | 2026-02-20 | 2026-02-20 | 22-Apr-25 A | 10-Oct-25 A | 2026-05-14 | 21 | 2026-05-14
A49450 | Foundation Drawing PSA-2 OffGas Buffer Drum 13-VV-712_IFR | 2026-02-20 | 2026-02-20 | 22-Apr-25 A | 13-May-25 A | 2026-05-14 | 6 | 2026-05-14
A49460 | Foundation Drawing PSA-2 OffGas Buffer Drum 13-VV-712_RCC | 2026-02-20 | 2026-02-20 | 14-May-25 A | 29-May-25 A | 2026-05-14 | 16 | 2026-05-14
A19900 | Foundation Drawing PSA-2 OffGas Buffer Drum 13-VV-712_IFA | 2026-02-20 | 2026-02-20 | 30-May-25 A | 21-Jun-25 A | 2026-05-14 | 3 | 2026-05-14
A19910 | Foundation Drawing PSA-2 OffGas Buffer Drum 13-VV-712_RCA | 2026-02-20 | 2026-02-20 | 22-Jun-25 A | 28-Jun-25 A | 2026-05-14 | 16 | 2026-05-14
A19920 | Foundation Drawing PSA-2 OffGas Buffer Drum 13-VV-712_IFD/IFC | 2026-02-20 | 2026-02-20 | 26-Sep-25 A | 10-Oct-25 A | 2026-05-14 | 2 | 2026-05-14
Design Calculation Report for foundation of PSA-2 OffGas Buffer Drum 13-VV-712 |  | 2026-02-20 | 2026-02-20 | 22-Apr-25 A | 10-Oct-25 A | 2027-01-20 | 47 | 2027-01-20
A49470 | Design Calculation Report for foundation of PSA-2 OffGas Buffer Drum 13-VV-712_IFR | 2026-02-20 | 2026-02-20 | 22-Apr-25 A | 13-May-25 A | 2027-01-20 | 6 | 2027-01-20
A49480 | Design Calculation Report for foundation of PSA-2 OffGas Buffer Drum 13-VV-712_RCC | 2026-02-20 | 2026-02-20 | 14-May-25 A | 03-Jun-25 A | 2027-01-20 | 16 | 2027-01-20
A49490 | Design Calculation Report for foundation of PSA-2 OffGas Buffer Drum 13-VV-712_IFA | 2026-02-20 | 2026-02-20 | 04-Jun-25 A | 21-Jun-25 A | 2027-01-20 | 3 | 2027-01-20
A19960 | Design Calculation Report for foundation of PSA-2 OffGas Buffer Drum 13-VV-712_RCA | 2026-02-20 | 2026-02-20 | 22-Jun-25 A | 06-Sep-25 A | 2027-01-20 | 16 | 2027-01-20
A19970 | Design Calculation Report for foundation of PSA-2 OffGas Buffer Drum 13-VV-712_IFD/IFC | 2026-02-20 | 2026-02-20 | 26-Sep-25 A | 10-Oct-25 A | 2027-01-20 | 2 | 2027-01-20
Pile Layout Compressor Shelter & SR8001 |  | 2026-02-20 | 2026-02-20 | 01-Jul-25 A | 13-Sep-25 A | 2026-02-21 | 39 | 2026-02-21
A17630 | Pile Layout Compressor Shelter & SR8001_IFR | 2026-02-20 | 2026-02-20 | 01-Jul-25 A | 12-Jul-25 A | 2026-02-21 | 6 | 2026-02-21
A17640 | Pile Layout Compressor Shelter & SR8001_RCC | 2026-02-20 | 2026-02-20 | 14-Jul-25 A | 22-Aug-25 A | 2026-02-21 | 16 | 2026-02-21
A17650 | Pile Layout Compressor Shelter & SR8001_IFA | 2026-02-20 | 2026-02-20 | 25-Aug-25 A | 30-Aug-25 A | 2026-02-21 | 3 | 2026-02-21
A17660 | Pile Layout Compressor Shelter & SR8001_RCA | 2026-02-20 | 2026-02-20 | 25-Aug-25 A | 06-Sep-25 A | 2026-02-21 | 16 | 2026-02-21
A17670 | Pile Layout Compressor Shelter & SR8001_IFD/IFC | 2026-02-20 | 2026-02-20 | 08-Sep-25 A | 13-Sep-25 A | 2026-02-21 | 2 | 2026-02-21
Pile Reinforcement Drawing |  | 2026-02-20 | 2026-02-20 | 01-Jul-25 A | 18-Jul-25 A | 2026-02-21 | 39 | 2027-01-20
A17480 | Pile Reinforcement Drawing_IFR | 2026-02-20 | 2026-02-20 | 01-Jul-25 A | 18-Jul-25 A | 2026-02-21 | 6 | 2026-02-21
A17490 | Pile Reinforcement Drawing_RCC | 2026-02-20 | 2026-02-20 | 01-Jul-25 A | 18-Jul-25 A | 2027-01-20 | 16 | 2027-01-20
A17500 | Pile Reinforcement Drawing_IFA | 2026-02-20 | 2026-02-20 | 01-Jul-25 A | 18-Jul-25 A | 2027-01-20 | 3 | 2027-01-20
A17510 | Pile Reinforcement Drawing_RCA | 2026-02-20 | 2026-02-20 | 01-Jul-25 A | 18-Jul-25 A | 2027-01-20 | 16 | 2027-01-20
A17520 | Pile Reinforcement Drawing_IFD/IFC | 2026-02-20 | 2026-02-20 | 01-Jul-25 A | 18-Jul-25 A | 2027-01-20 | 2 | 2027-01-20
Pile Layout PSA-2 FeedGas Compressor 13-KC-701 |  | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 15-Sep-25 A | 2026-02-21 | 149 | 2026-02-21
A17530 | Pile Layout PSA-2 FeedGas Compressor 13-KC-701_IFR | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 15-Aug-25 A | 2026-02-21 | 6 | 2026-02-21
A48320 | Pile Layout PSA-2 FeedGas Compressor 13-KC-701_RCC | 2026-02-20 | 2026-02-20 | 16-Aug-25 A | 22-Aug-25 A | 2026-02-21 | 16 | 2026-02-21
A17550 | Pile Layout PSA-2 FeedGas Compressor 13-KC-701_IFA | 2026-02-20 | 2026-02-20 | 22-Aug-25 A | 29-Aug-25 A | 2026-02-21 | 3 | 2026-02-21
A17560 | Pile Layout PSA-2 FeedGas Compressor 13-KC-701_RCA | 2026-02-20 | 2026-02-20 | 18-Aug-25 A | 05-Sep-25 A | 2026-02-21 | 16 | 2026-02-21
A17570 | Pile Layout PSA-2 FeedGas Compressor 13-KC-701_IFD/IFC | 2026-02-20 | 2026-02-20 | 08-Sep-25 A | 15-Sep-25 A | 2026-02-21 | 2 | 2026-02-21
Pile Layout PSA-2 OffGas Compressor 13-KC-702 |  | 2026-02-20 | 2026-02-20 | 01-Jul-25 A | 15-Sep-25 A | 2026-02-21 | 39 | 2026-02-21
A17580 | Pile Layout PSA-2 OffGas Compressor 13-KC-702_IFR | 2026-02-20 | 2026-02-20 | 01-Jul-25 A | 11-Jul-25 A | 2026-02-21 | 6 | 2026-02-21
A17590 | Pile Layout PSA-2 OffGas Compressor 13-KC-702_RCC | 2026-02-20 | 2026-02-20 | 14-Jul-25 A | 22-Aug-25 A | 2026-02-21 | 16 | 2026-02-21
A17600 | Pile Layout PSA-2 OffGas Compressor 13-KC-702_IFA | 2026-02-20 | 2026-02-20 | 25-Aug-25 A | 30-Aug-25 A | 2026-02-21 | 3 | 2026-02-21
A17610 | Pile Layout PSA-2 OffGas Compressor 13-KC-702_RCA | 2026-02-20 | 2026-02-20 | 01-Aug-25 A | 06-Sep-25 A | 2026-02-21 | 16 | 2026-02-21
A17620 | Pile Layout PSA-2 OffGas Compressor 13-KC-702_IFD/IFC | 2026-02-20 | 2026-02-20 | 08-Sep-25 A | 15-Sep-25 A | 2026-02-21 | 2 | 2026-02-21
Pile Layout PSA-2 Unit - Hydrogen Purification 13-XA-710 |  | 2026-02-20 | 2026-02-20 | 30-Jun-25 A | 13-Sep-25 A | 2026-03-02 | 38 | 2026-03-02
A48330 | Pile Layout PSA-2 Unit - Hydrogen Purification 13-XA-710_IFR | 2026-02-20 | 2026-02-20 | 30-Jun-25 A | 11-Jul-25 A | 2026-03-02 | 6 | 2026-03-02
A48340 | Pile Layout PSA-2 Unit - Hydrogen Purification 13-XA-710_RCC | 2026-02-20 | 2026-02-20 | 14-Jul-25 A | 22-Aug-25 A | 2026-03-02 | 16 | 2026-03-02
A48350 | Pile Layout PSA-2 Unit - Hydrogen Purification 13-XA-710_IFA | 2026-02-20 | 2026-02-20 | 25-Aug-25 A | 30-Aug-25 A | 2026-03-02 | 3 | 2026-03-02
A48360 | Pile Layout PSA-2 Unit - Hydrogen Purification 13-XA-710_RCA | 2026-02-20 | 2026-02-20 | 19-Aug-25 A | 06-Sep-25 A | 2026-03-02 | 16 | 2026-03-02
A48370 | Pile Layout PSA-2 Unit - Hydrogen Purification 13-XA-710_IFD/IFC | 2026-02-20 | 2026-02-20 | 08-Sep-25 A | 13-Sep-25 A | 2026-03-02 | 2 | 2026-03-02
Pile Layout PSA-2 OffGas Buffer Drum 13-VV-712 |  | 2026-02-20 | 2026-02-20 | 02-Jun-25 A | 05-Jul-25 A | 2026-03-02 | 39 | 2026-03-02
A17680 | Pile Layout PSA-2 OffGas Buffer Drum 13-VV-712_IFR | 2026-02-20 | 2026-02-20 | 02-Jun-25 A | 07-Jun-25 A | 2026-03-02 | 6 | 2026-03-02
A17690 | Pile Layout PSA-2 OffGas Buffer Drum 13-VV-712_RCC | 2026-02-20 | 2026-02-20 | 06-Jun-25 A | 16-Jun-25 A | 2026-03-02 | 16 | 2026-03-02
A17700 | Pile Layout PSA-2 OffGas Buffer Drum 13-VV-712_IFA | 2026-02-20 | 2026-02-20 | 17-Jun-25 A | 23-Jun-25 A | 2026-03-02 | 3 | 2026-03-02
A17710 | Pile Layout PSA-2 OffGas Buffer Drum 13-VV-712_RCA | 2026-02-20 | 2026-02-20 | 17-Jun-25 A | 28-Jun-25 A | 2026-03-02 | 16 | 2026-03-02
A17720 | Pile Layout PSA-2 OffGas Buffer Drum 13-VV-712_IFD/IFC | 2026-02-20 | 2026-02-20 | 30-Jun-25 A | 05-Jul-25 A | 2026-03-02 | 2 | 2026-03-02
Structure & Foundation design - Buildings/Shelters/Electrical |  | 2026-02-20 | 2026-04-07 | 05-Feb-25 A | 2026-04-07 | 2026-03-14 | 321 | 2027-01-20 | 206
Structural GA, Section and Details - Compressor Shelter |  | 2026-02-20 | 2026-02-20 | 01-Oct-25 A | 19-Jan-26 A | 2026-05-19 | 61 | 2026-05-19
A48880 | Structural GA, Section and Details - Compressor Shelter_IFR | 2026-02-20 | 2026-02-20 | 01-Oct-25 A | 07-Oct-25 A | 2026-05-19 | 17 | 2026-05-19
A48890 | Structural GA, Section and Details - Compressor Shelter_RCC | 2026-02-20 | 2026-02-20 | 08-Oct-25 A | 23-Oct-25 A | 2026-05-19 | 16 | 2026-05-19
A48900 | Structural GA, Section and Details - Compressor Shelter_IFA | 2026-02-20 | 2026-02-20 | 23-Oct-25 A | 24-Oct-25 A | 2026-05-19 | 11 | 2026-05-19
A48910 | Structural GA, Section and Details - Compressor Shelter_RCA | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 09-Jan-26 A | 2026-05-19 | 16 | 2026-05-19
A48920 | Structural GA, Section and Details - Compressor Shelter_IFD/IFC | 2026-02-20 | 2026-02-20 | 09-Jan-26 A | 19-Jan-26 A | 2026-05-19 | 6 | 2026-05-19
Design Calculation Report for structural steel- Compressor Shelter |  | 2026-02-20 | 2026-04-07 | 01-Sep-25 A | 2026-04-07 | 2026-12-07 | 118 | 2027-01-20 | 206
A48950 | Design Calculation Report for structural steel- Compressor Shelter_IFR | 2026-02-20 | 2026-02-20 | 01-Sep-25 A | 13-Sep-25 A | 2026-12-07 | 17 | 2026-12-07
A18690 | Design Calculation Report for structural steel- Compressor Shelter_RCC | 2026-02-20 | 2026-02-20 | 10-Sep-25 A | 01-Oct-25 A | 2026-12-07 | 16 | 2026-12-07
A18700 | Design Calculation Report for structural steel- Compressor Shelter_IFA | 2026-02-20 | 2026-03-09 | 2026-02-20 | 2026-03-09 | 2026-12-07 | 11 | 2026-12-22 | 206
A18710 | Design Calculation Report for structural steel- Compressor Shelter_RCA | 2026-03-09 | 2026-03-30 | 2026-03-09 | 2026-03-30 | 2026-12-22 | 16 | 2027-01-13 | 206
A48960 | Design Calculation Report for structural steel- Compressor Shelter_IFD/IFC | 2026-03-31 | 2026-04-07 | 2026-03-31 | 2026-04-07 | 2027-01-13 | 6 | 2027-01-20 | 206
Foundation Drawing- Compressor Shelter |  | 2026-02-20 | 2026-02-20 | 01-Jul-25 A | 21-Jan-26 A | 2027-01-20 | 107 | 2027-01-20
A18630 | Foundation Drawing- Compressor Shelter_IFR | 2026-02-20 | 2026-02-20 | 01-Jul-25 A | 12-Jul-25 A | 2027-01-20 | 6 | 2027-01-20
A18640 | Foundation Drawing- Compressor Shelter_RCC | 2026-02-20 | 2026-02-20 | 15-Jul-25 A | 22-Aug-25 A | 2027-01-20 | 16 | 2027-01-20
A18650 | Foundation Drawing- Compressor Shelter_IFA | 2026-02-20 | 2026-02-20 | 20-Oct-25 A | 30-Oct-25 A | 2027-01-20 | 3 | 2027-01-20
A48930 | Foundation Drawing- Compressor Shelter_RCA | 2026-02-20 | 2026-02-20 | 31-Oct-25 A | 14-Nov-25 A | 2027-01-20 | 16 | 2027-01-20
A48940 | Foundation Drawing- Compressor Shelter_IFD/IFC | 2026-02-20 | 2026-02-20 | 19-Jan-26 A | 21-Jan-26 A | 2027-01-20 | 2 | 2027-01-20
Design Calculation Report for Foundations- Compressor Shelter |  | 2026-02-20 | 2026-02-20 | 28-Jun-25 A | 21-Jan-26 A | 2027-01-20 | 104 | 2027-01-20
A48970 | Design Calculation Report for Foundations- Compressor Shelter_IFR | 2026-02-20 | 2026-02-20 | 28-Jun-25 A | 15-Jul-25 A | 2027-01-20 | 6 | 2027-01-20
A48980 | Design Calculation Report for Foundations- Compressor Shelter_RCC | 2026-02-20 | 2026-02-20 | 16-Jul-25 A | 22-Aug-25 A | 2027-01-20 | 16 | 2027-01-20
A48990 | Design Calculation Report for Foundations- Compressor Shelter_IFA | 2026-02-20 | 2026-02-20 | 25-Aug-25 A | 29-Aug-25 A | 2027-01-20 | 3 | 2027-01-20
A49000 | Design Calculation Report for Foundations- Compressor Shelter_RCA | 2026-02-20 | 2026-02-20 | 20-Aug-25 A | 05-Sep-25 A | 2027-01-20 | 16 | 2027-01-20
A49010 | Design Calculation Report for Foundations- Compressor Shelter_IFD/IFC | 2026-02-20 | 2026-02-20 | 19-Jan-26 A | 21-Jan-26 A | 2027-01-20 | 2 | 2027-01-20
Architectural Drawing- Substation, SIS Building |  | 2026-02-20 | 2026-02-20 | 05-Feb-25 A | 18-Sep-25 A | 2026-03-14 | 218 | 2026-03-14
A48380 | Architectural Drawing- Substation, SIS Building_IFR | 2026-02-20 | 2026-02-20 | 05-Feb-25 A | 11-Mar-25 A | 2026-03-14 | 6 | 2026-03-14
A17790 | Architectural Drawing- Substation, SIS Building_RCC | 2026-02-20 | 2026-02-20 | 12-Mar-25 A | 20-Apr-25 A | 2026-03-14 | 16 | 2026-03-14
A48390 | Architectural Drawing- Substation, SIS Building_IFA | 2026-02-20 | 2026-02-20 | 21-Apr-25 A | 19-Jun-25 A | 2026-03-14 | 6 | 2026-03-14
A48400 | Architectural Drawing- Substation, SIS Building_RCA | 2026-02-20 | 2026-02-20 | 20-Jun-25 A | 04-Sep-25 A | 2026-03-14 | 16 | 2026-03-14
A48410 | Architectural Drawing- Substation, SIS Building_IFD/IFC | 2026-02-20 | 2026-02-20 | 08-Sep-25 A | 18-Sep-25 A | 2026-03-14 | 2 | 2026-03-14
Structural Concrete GA, Section and Details- Substation, SIS Building |  | 2026-02-20 | 2026-02-20 | 21-Apr-25 A | 29-Aug-25 A | 2026-03-14 | 80 | 2026-03-14
A17880 | Structural Concrete GA, Section and Details- Substation, SIS Building_IFR | 2026-02-20 | 2026-02-20 | 21-Apr-25 A | 12-May-25 A | 2026-03-14 | 17 | 2026-03-14
A48430 | Structural Concrete GA, Section and Details- Substation, SIS Building_RCC | 2026-02-20 | 2026-02-20 | 13-May-25 A | 03-Jun-25 A | 2026-03-14 | 16 | 2026-03-14
A48440 | Structural Concrete GA, Section and Details- Substation, SIS Building_IFA | 2026-02-20 | 2026-02-20 | 04-Jun-25 A | 15-Aug-25 A | 2026-03-14 | 6 | 2026-03-14
A48450 | Structural Concrete GA, Section and Details- Substation, SIS Building_RCA | 2026-02-20 | 2026-02-20 | 07-Aug-25 A | 22-Aug-25 A | 2026-03-14 | 16 | 2026-03-14
A48460 | Structural Concrete GA, Section and Details- Substation, SIS Building_IFD/IFC | 2026-02-20 | 2026-02-20 | 22-Aug-25 A | 29-Aug-25 A | 2026-03-14 | 2 | 2026-03-14
Design Calculation report for Substation, SIS Building |  | 2026-02-20 | 2026-02-20 | 20-Apr-25 A | 29-Aug-25 A | 2026-03-14 | 105 | 2026-03-14
A48470 | Design Calculation report for Substation, SIS Building_IFR | 2026-02-20 | 2026-02-20 | 20-Apr-25 A | 11-May-25 A | 2026-03-14 | 17 | 2026-03-14
A17940 | Design Calculation report for Substation, SIS Building_RCC | 2026-02-20 | 2026-02-20 | 12-May-25 A | 05-Jun-25 A | 2026-03-14 | 16 | 2026-03-14
A48480 | Design Calculation report for Substation, SIS Building_IFA | 2026-02-20 | 2026-02-20 | 06-Jun-25 A | 15-Aug-25 A | 2026-03-14 | 6 | 2026-03-14
A48490 | Design Calculation report for Substation, SIS Building_RCA | 2026-02-20 | 2026-02-20 | 16-Jun-25 A | 22-Aug-25 A | 2026-03-14 | 16 | 2026-03-14
A48500 | Design Calculation report for Substation, SIS Building_IFD/IFC | 2026-02-20 | 2026-02-20 | 25-Aug-25 A | 29-Aug-25 A | 2026-03-14 | 2 | 2026-03-14
Foundation Layout, Section and Details- Substation, SIS Building |  | 2026-02-20 | 2026-02-20 | 21-Apr-25 A | 29-Aug-25 A | 2026-03-14 | 107 | 2026-03-14
A48420 | Foundation Layout, Section and Details- Substation, SIS Building_IFR | 2026-02-20 | 2026-02-20 | 21-Apr-25 A | 12-May-25 A | 2026-03-14 | 17 | 2026-03-14
A17840 | Foundation Layout, Section and Details- Substation, SIS Building_RCC | 2026-02-20 | 2026-02-20 | 13-May-25 A | 29-May-25 A | 2026-03-14 | 16 | 2026-03-14
A17850 | Foundation Layout, Section and Details- Substation, SIS Building_IFA | 2026-02-20 | 2026-02-20 | 30-May-25 A | 21-Jun-25 A | 2026-03-14 | 6 | 2026-03-14
A17860 | Foundation Layout, Section and Details- Substation, SIS Building_RCA | 2026-02-20 | 2026-02-20 | 23-Jun-25 A | 22-Aug-25 A | 2026-03-14 | 16 | 2026-03-14
A17870 | Foundation Layout, Section and Details- Substation, SIS Building_IFD/IFC | 2026-02-20 | 2026-02-20 | 25-Aug-25 A | 29-Aug-25 A | 2026-03-14 | 2 | 2026-03-14
Structure design - U/G facilities |  | 2026-02-20 | 2026-04-21 | 10-Jun-25 A | 2026-04-21 | 2026-03-19 | 190 | 2027-01-20 | 196
Sump Pit plan and details Accidentally Oil contaminated water collection 70-TD-1407 |  | 2026-02-20 | 2026-02-20 | 18-Aug-25 A | 23-Dec-25 A | 2026-05-06 | 87 | 2026-05-06
A20380 | Sump Pit plan and details Accidentally Oil contaminated water collection 70-TD-1407_IFR | 2026-02-20 | 2026-02-20 | 18-Aug-25 A | 22-Aug-25 A | 2026-05-06 | 6 | 2026-05-06
A20390 | Sump Pit plan and details Accidentally Oil contaminated water collection 70-TD-1407_RCC | 2026-02-20 | 2026-02-20 | 20-Aug-25 A | 27-Aug-25 A | 2026-05-06 | 16 | 2026-05-06
A20400 | Sump Pit plan and details Accidentally Oil contaminated water collection 70-TD-1407_IFA | 2026-02-20 | 2026-02-20 | 28-Aug-25 A | 02-Sep-25 A | 2026-05-06 | 3 | 2026-05-06
A49710 | Sump Pit plan and details Accidentally Oil contaminated water collection 70-TD-1407_RCA | 2026-02-20 | 2026-02-20 | 27-Aug-25 A | 09-Sep-25 A | 2026-05-06 | 16 | 2026-05-06
A49720 | Sump Pit plan and details Accidentally Oil contaminated water collection 70-TD-1407_IFD/IFC | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 23-Dec-25 A | 2026-05-06 | 2 | 2026-05-06
Design Calculation Report for Accidentally Oil contaminated water collection Sump Pit 70-TD-1407 |  | 2026-02-20 | 2026-02-20 | 23-Aug-25 A | 23-Dec-25 A | 2026-05-06 | 86 | 2026-05-06
A49730 | Design Calculation Report for Accidentally Oil contaminated water collection Sump Pit 70-TD-1407_IFR | 2026-02-20 | 2026-02-20 | 23-Aug-25 A | 13-Sep-25 A | 2026-05-06 | 6 | 2026-05-06
A20440 | Design Calculation Report for Accidentally Oil contaminated water collection Sump Pit 70-TD-1407_RCC | 2026-02-20 | 2026-02-20 | 29-Aug-25 A | 22-Sep-25 A | 2026-05-06 | 16 | 2026-05-06
A20450 | Design Calculation Report for Accidentally Oil contaminated water collection Sump Pit 70-TD-1407_IFA | 2026-02-20 | 2026-02-20 | 23-Sep-25 A | 29-Sep-25 A | 2026-05-06 | 3 | 2026-05-06
A20460 | Design Calculation Report for Accidentally Oil contaminated water collection Sump Pit 70-TD-1407_RCA | 2026-02-20 | 2026-02-20 | 25-Sep-25 A | 04-Oct-25 A | 2026-05-06 | 16 | 2026-05-06
A49740 | Design Calculation Report for Accidentally Oil contaminated water collection Sump Pit 70-TD-1407_IFD/IFC | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 23-Dec-25 A | 2026-05-06 | 2 | 2026-05-06
Sump Pit plan and details Oily Water 70-TD-1408 |  | 2026-02-20 | 2026-02-20 | 01-Aug-25 A | 13-Jan-26 A | 2026-05-06 | 98 | 2026-05-06
A49750 | Sump Pit plan and details Oily Water 70-TD-1408_IFR | 2026-02-20 | 2026-02-20 | 01-Aug-25 A | 22-Aug-25 A | 2026-05-06 | 6 | 2026-05-06
A49760 | Sump Pit plan and details Oily Water 70-TD-1408_RCC | 2026-02-20 | 2026-02-20 | 15-Aug-25 A | 26-Aug-25 A | 2026-05-06 | 16 | 2026-05-06
A20500 | Sump Pit plan and details Oily Water 70-TD-1408_IFA | 2026-02-20 | 2026-02-20 | 29-Aug-25 A | 02-Sep-25 A | 2026-05-06 | 3 | 2026-05-06
A20510 | Sump Pit plan and details Oily Water 70-TD-1408_RCA | 2026-02-20 | 2026-02-20 | 01-Sep-25 A | 09-Sep-25 A | 2026-05-06 | 16 | 2026-05-06
A20520 | Sump Pit plan and details Oily Water 70-TD-1408_IFD/IFC | 2026-02-20 | 2026-02-20 | 09-Jan-26 A | 13-Jan-26 A | 2026-05-06 | 2 | 2026-05-06
Design Calculation Report for Oily Water Sump Pit 70-TD-1408 |  | 2026-02-20 | 2026-02-20 | 23-Aug-25 A | 13-Jan-26 A | 2026-05-06 | 102 | 2026-05-06
A49770 | Design Calculation Report for Oily Water Sump Pit 70-TD-1408_IFR | 2026-02-20 | 2026-02-20 | 23-Aug-25 A | 13-Sep-25 A | 2026-05-06 | 6 | 2026-05-06
A49780 | Design Calculation Report for Oily Water Sump Pit 70-TD-1408_RCC | 2026-02-20 | 2026-02-20 | 15-Sep-25 A | 16-Oct-25 A | 2026-05-06 | 16 | 2026-05-06
A49790 | Design Calculation Report for Oily Water Sump Pit 70-TD-1408_IFA | 2026-02-20 | 2026-02-20 | 17-Oct-25 A | 23-Oct-25 A | 2026-05-06 | 3 | 2026-05-06
A20560 | Design Calculation Report for Oily Water Sump Pit 70-TD-1408_RCA | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 09-Jan-26 A | 2026-05-06 | 16 | 2026-05-06
A20570 | Design Calculation Report for Oily Water Sump Pit 70-TD-1408_IFD/IFC | 2026-02-20 | 2026-02-20 | 09-Jan-26 A | 13-Jan-26 A | 2026-05-06 | 2 | 2026-05-06
Sump Pit plan and details Sanitary Waste Water 70-TD-1409 |  | 2026-02-20 | 2026-02-20 | 23-Aug-25 A | 23-Dec-25 A | 2026-10-26 | 82 | 2026-10-26
A20580 | Sump Pit plan and details Sanitary Waste Water 70-TD-1409_IFR | 2026-02-20 | 2026-02-20 | 23-Aug-25 A | 13-Sep-25 A | 2026-10-26 | 6 | 2026-10-26
A49800 | Sump Pit plan and details Sanitary Waste Water 70-TD-1409_RCC | 2026-02-20 | 2026-02-20 | 01-Sep-25 A | 24-Sep-25 A | 2026-10-26 | 16 | 2026-10-26
A49810 | Sump Pit plan and details Sanitary Waste Water 70-TD-1409_IFA | 2026-02-20 | 2026-02-20 | 25-Sep-25 A | 01-Oct-25 A | 2026-10-26 | 3 | 2026-10-26
A49820 | Sump Pit plan and details Sanitary Waste Water 70-TD-1409_RCA | 2026-02-20 | 2026-02-20 | 29-Sep-25 A | 08-Oct-25 A | 2026-10-26 | 16 | 2026-10-26
A20620 | Sump Pit plan and details Sanitary Waste Water 70-TD-1409_IFD/IFC | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 23-Dec-25 A | 2026-10-26 | 2 | 2026-10-26
Design Calculation Report for Sanitary Waste Water Sump Pit 70-TD-1409 |  | 2026-02-20 | 2026-02-20 | 23-Aug-25 A | 23-Dec-25 A | 2026-10-26 | 82 | 2026-10-26
A20630 | Design Calculation Report for Sanitary Waste Water Sump Pit 70-TD-1409_IFR | 2026-02-20 | 2026-02-20 | 23-Aug-25 A | 13-Sep-25 A | 2026-10-26 | 6 | 2026-10-26
A20640 | Design Calculation Report for Sanitary Waste Water Sump Pit 70-TD-1409_RCC | 2026-02-20 | 2026-02-20 | 15-Sep-25 A | 13-Oct-25 A | 2026-10-26 | 16 | 2026-10-26
A49830 | Design Calculation Report for Sanitary Waste Water Sump Pit 70-TD-1409_IFA | 2026-02-20 | 2026-02-20 | 14-Oct-25 A | 20-Oct-25 A | 2026-10-26 | 3 | 2026-10-26
A49840 | Design Calculation Report for Sanitary Waste Water Sump Pit 70-TD-1409_RCA | 2026-02-20 | 2026-02-20 | 15-Oct-25 A | 24-Oct-25 A | 2026-10-26 | 16 | 2026-10-26
A49850 | Design Calculation Report for Sanitary Waste Water Sump Pit 70-TD-1409_IFD/IFC | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 23-Dec-25 A | 2026-10-26 | 2 | 2026-10-26
Transformer Foundation Drawing for Bay-A to Bay-E |  | 2026-02-20 | 2026-04-21 | 2026-02-20 | 2026-04-21 | 2026-11-23 | 43 | 2027-01-20 | 196
A20680 | Transformer Foundation Drawing for Bay-A to Bay-E_IFR | 2026-02-20 | 2026-02-27 | 2026-02-20 | 2026-02-27 | 2026-11-23 | 6 | 2026-11-30 | 196
A20690 | Transformer Foundation Drawing for Bay-A to Bay-E_RCC | 2026-02-27 | 2026-03-23 | 2026-02-27 | 2026-03-23 | 2026-11-30 | 16 | 2026-12-22 | 196
A20700 | Transformer Foundation Drawing for Bay-A to Bay-E_IFA | 2026-03-23 | 2026-03-26 | 2026-03-23 | 2026-03-26 | 2026-12-22 | 3 | 2026-12-25 | 196
A49860 | Transformer Foundation Drawing for Bay-A to Bay-E_RCA | 2026-03-26 | 2026-04-17 | 2026-03-26 | 2026-04-17 | 2026-12-28 | 16 | 2027-01-18 | 196
A49870 | Transformer Foundation Drawing for Bay-A to Bay-E_IFD/IFC | 2026-04-17 | 2026-04-21 | 2026-04-17 | 2026-04-21 | 2027-01-18 | 2 | 2027-01-20 | 196
Design Calculation Report for Foundation- Transformer for Bay-A to Bay-E |  | 2026-02-20 | 2026-04-21 | 2026-02-20 | 2026-04-21 | 2026-11-23 | 43 | 2027-01-20 | 196
A49880 | Design Calculation Report for Foundation- Transformer for Bay-A to Bay-E_IFR | 2026-02-20 | 2026-02-27 | 2026-02-20 | 2026-02-27 | 2026-11-23 | 6 | 2026-11-30 | 196
A49890 | Design Calculation Report for Foundation- Transformer for Bay-A to Bay-E_RCC | 2026-02-27 | 2026-03-23 | 2026-02-27 | 2026-03-23 | 2026-11-30 | 16 | 2026-12-22 | 196
A20750 | Design Calculation Report for Foundation- Transformer for Bay-A to Bay-E_IFA | 2026-03-23 | 2026-03-26 | 2026-03-23 | 2026-03-26 | 2026-12-22 | 3 | 2026-12-25 | 196
A20760 | Design Calculation Report for Foundation- Transformer for Bay-A to Bay-E_RCA | 2026-03-26 | 2026-04-17 | 2026-03-26 | 2026-04-17 | 2026-12-28 | 16 | 2027-01-18 | 196
A20770 | Design Calculation Report for Foundation- Transformer for Bay-A to Bay-E_IFD/IFC | 2026-04-17 | 2026-04-21 | 2026-04-17 | 2026-04-21 | 2027-01-18 | 2 | 2027-01-20 | 196
Firewater Valve Pit Plan, Section and Details |  | 2026-02-20 | 2026-02-20 | 01-Oct-25 A | 23-Dec-25 A | 2026-04-20 | 42 | 2026-04-20
A21380 | Firewater Valve Pit Plan, Section and Details_IFR | 2026-02-20 | 2026-02-20 | 01-Oct-25 A | 10-Oct-25 A | 2026-04-20 | 6 | 2026-04-20
A21390 | Firewater Valve Pit Plan, Section and Details_RCC | 2026-02-20 | 2026-02-20 | 06-Oct-25 A | 17-Oct-25 A | 2026-04-20 | 16 | 2026-04-20
A21400 | Firewater Valve Pit Plan, Section and Details_IFA | 2026-02-20 | 2026-02-20 | 20-Oct-25 A | 27-Oct-25 A | 2026-04-20 | 3 | 2026-04-20
A50150 | Firewater Valve Pit Plan, Section and Details_RCA | 2026-02-20 | 2026-02-20 | 28-Oct-25 A | 21-Nov-25 A | 2026-04-20 | 16 | 2026-04-20
A50160 | Firewater Valve Pit Plan, Section and Details_IFD/IFC | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 23-Dec-25 A | 2026-04-20 | 2 | 2026-04-20
Cooling water Valve Pit Plan, Section and Details |  | 2026-02-20 | 2026-02-20 | 01-Oct-25 A | 23-Dec-25 A | 2026-06-28 | 55 | 2026-06-28
A50170 | Cooling water Valve Pit Plan, Section and Details_IFR | 2026-02-20 | 2026-02-20 | 01-Oct-25 A | 10-Oct-25 A | 2026-06-28 | 6 | 2026-06-28
A21440 | Cooling water Valve Pit Plan, Section and Details_RCC | 2026-02-20 | 2026-02-20 | 11-Oct-25 A | 24-Oct-25 A | 2026-06-28 | 16 | 2026-06-28
A21450 | Cooling water Valve Pit Plan, Section and Details_IFA | 2026-02-20 | 2026-02-20 | 25-Oct-25 A | 20-Nov-25 A | 2026-06-28 | 3 | 2026-06-28
A21460 | Cooling water Valve Pit Plan, Section and Details_RCA | 2026-02-20 | 2026-02-20 | 31-Oct-25 A | 21-Nov-25 A | 2026-06-28 | 16 | 2026-06-28
A50180 | Cooling water Valve Pit Plan, Section and Details_IFD/IFC | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 23-Dec-25 A | 2026-06-28 | 2 | 2026-06-28
Underground Layout |  | 2026-02-20 | 2026-02-20 | 10-Jun-25 A | 22-Oct-25 A | 2026-03-19 | 116 | 2026-03-27
A50210 | Underground Layout_IFR | 2026-02-20 | 2026-02-20 | 10-Jun-25 A | 08-Jul-25 A | 2026-03-19 | 6 | 2026-03-19
A50230 | Underground Layout_IFA | 2026-02-20 | 2026-02-20 | 11-Aug-25 A | 15-Aug-25 A | 2026-03-19 | 3 | 2026-03-19
A50220 | Underground Layout_RCC | 2026-02-20 | 2026-02-20 | 18-Aug-25 A | 12-Sep-25 A | 2026-03-19 | 16 | 2026-03-19
A50240 | Underground Layout_RCA | 2026-02-20 | 2026-02-20 | 15-Sep-25 A | 10-Oct-25 A | 2026-03-27 | 16 | 2026-03-27
A21570 | Underground Layout_IFD/IFC | 2026-02-20 | 2026-02-20 | 14-Oct-25 A | 22-Oct-25 A | 2026-03-27 | 2 | 2026-03-27
Composite Underground drawing |  | 2026-02-20 | 2026-03-23 | 22-Sep-25 A | 2026-03-23 | 2026-03-19 | 101 | 2026-04-17 | 20
A21580 | Composite Underground drawing_IFR | 2026-02-20 | 2026-02-20 | 22-Sep-25 A | 30-Sep-25 A | 2026-03-19 | 6 | 2026-03-19
A21590 | Composite Underground drawing_RCC | 2026-02-20 | 2026-02-20 | 24-Sep-25 A | 07-Oct-25 A | 2026-03-19 | 16 | 2026-03-19
A21600 | Composite Underground drawing_IFA | 2026-02-20 | 2026-02-25 | 2026-02-20 | 2026-02-25 | 2026-03-19 | 3 | 2026-03-24 | 20
A50250 | Composite Underground drawing_RCA | 2026-02-25 | 2026-03-19 | 2026-02-25 | 2026-03-19 | 2026-03-25 | 16 | 2026-04-15 | 20
A50260 | Composite Underground drawing_IFD/IFC | 2026-03-19 | 2026-03-23 | 2026-03-19 | 2026-03-23 | 2026-04-15 | 2 | 2026-04-17 | 20
Underground Trench Layout drawing and details |  | 2026-02-20 | 2026-02-20 | 01-Oct-25 A | 19-Jan-26 A | 2026-03-19 | 61 | 2026-04-11
A50270 | Underground Trench Layout drawing and details_IFR | 2026-02-20 | 2026-02-20 | 01-Oct-25 A | 09-Oct-25 A | 2026-03-19 | 6 | 2026-03-19
A50280 | Underground Trench Layout drawing and details_RCC | 2026-02-20 | 2026-02-20 | 10-Oct-25 A | 10-Nov-25 A | 2026-03-19 | 16 | 2026-03-19
A21650 | Underground Trench Layout drawing and details_IFA | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 24-Dec-25 A | 2026-03-19 | 3 | 2026-03-19
A21660 | Underground Trench Layout drawing and details_RCA | 2026-02-20 | 2026-02-20 | 24-Dec-25 A | 15-Jan-26 A | 2026-04-11 | 16 | 2026-04-11
A21670 | Underground Trench Layout drawing and details_IFD/IFC | 2026-02-20 | 2026-02-20 | 15-Jan-26 A | 19-Jan-26 A | 2026-04-11 | 2 | 2026-04-11
Design Calculation for Concrete Trenches and Duct Banks (If Required) |  | 2026-02-20 | 2026-03-23 | 19-Dec-25 A | 2026-03-23 | 2026-12-22 | 66 | 2027-01-20 | 218
A21680 | Design Calculation for Concrete Trenches and Duct Banks (If Required)_IFR | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 26-Dec-25 A | 2026-12-22 | 6 | 2026-12-22
A50290 | Design Calculation for Concrete Trenches and Duct Banks (If Required)_RCC | 2026-02-20 | 2026-02-20 | 26-Dec-25 A | 19-Jan-26 A | 2026-12-22 | 16 | 2026-12-22
A50300 | Design Calculation for Concrete Trenches and Duct Banks (If Required)_IFA | 2026-02-20 | 2026-02-25 | 2026-02-20 | 2026-02-25 | 2026-12-22 | 3 | 2026-12-25 | 218
A50310 | Design Calculation for Concrete Trenches and Duct Banks (If Required)_RCA | 2026-02-25 | 2026-03-19 | 2026-02-25 | 2026-03-19 | 2026-12-28 | 16 | 2027-01-18 | 218
A50320 | Design Calculation for Concrete Trenches and Duct Banks (If Required)_IFD/IFC | 2026-03-19 | 2026-03-23 | 2026-03-19 | 2026-03-23 | 2027-01-18 | 2 | 2027-01-20 | 218
Calculation for UG Hydraulics |  | 2026-02-20 | 2026-02-20 | 10-Jun-25 A | 23-Dec-25 A | 2027-01-20 | 99 | 2027-01-20
A21730 | Calculation for UG Hydraulics_IFR | 2026-02-20 | 2026-02-20 | 10-Jun-25 A | 04-Jul-25 A | 2027-01-20 | 6 | 2027-01-20
A21740 | Calculation for UG Hydraulics_RCC | 2026-02-20 | 2026-02-20 | 07-Jul-25 A | 15-Aug-25 A | 2027-01-20 | 16 | 2027-01-20
A21750 | Calculation for UG Hydraulics_IFA | 2026-02-20 | 2026-02-20 | 18-Aug-25 A | 22-Aug-25 A | 2027-01-20 | 3 | 2027-01-20
A21760 | Calculation for UG Hydraulics_RCA | 2026-02-20 | 2026-02-20 | 20-Aug-25 A | 29-Aug-25 A | 2027-01-20 | 16 | 2027-01-20
A50330 | Calculation for UG Hydraulics_IFD/IFC | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 23-Dec-25 A | 2027-01-20 | 2 | 2027-01-20
Other Civil deliverables |  | 2026-02-20 | 2026-04-21 | 16-Jan-25 A | 2026-04-21 | 2026-02-23 | 485 | 2027-01-20 | 196
General notes for Civil and Concrete Works |  | 2026-02-20 | 2026-02-20 | 30-Jan-25 A | 10-May-25 A | 2027-01-20 | 112 | 2027-01-20
A17180 | General notes for Civil and Concrete Works_IFR | 2026-02-20 | 2026-02-20 | 30-Jan-25 A | 20-Feb-25 A | 2027-01-20 | 6 | 2027-01-20
A17190 | General notes for Civil and Concrete Works_RCC | 2026-02-20 | 2026-02-20 | 21-Feb-25 A | 19-Apr-25 A | 2027-01-20 | 16 | 2027-01-20
A17200 | General notes for Civil and Concrete Works_IFA | 2026-02-20 | 2026-02-20 | 20-Apr-25 A | 26-Apr-25 A | 2027-01-20 | 3 | 2027-01-20
A17210 | General notes for Civil and Concrete Works_RCA | 2026-02-20 | 2026-02-20 | 27-Apr-25 A | 03-May-25 A | 2027-01-20 | 16 | 2027-01-20
A17220 | General notes for Civil and Concrete Works_IFD/IFC | 2026-02-20 | 2026-02-20 | 04-May-25 A | 10-May-25 A | 2027-01-20 | 2 | 2027-01-20
Standard details for stair and ladder foundation |  | 2026-02-20 | 2026-02-20 | 01-Jul-25 A | 08-Oct-25 A | 2026-11-30 | 127 | 2027-01-20
A17280 | Standard details for stair and ladder foundation_IFR | 2026-02-20 | 2026-02-20 | 01-Jul-25 A | 11-Jul-25 A | 2026-11-30 | 6 | 2026-11-30
A48280 | Standard details for stair and ladder foundation_RCC | 2026-02-20 | 2026-02-20 | 31-Jul-25 A | 17-Sep-25 A | 2027-01-20 | 16 | 2027-01-20
A17300 | Standard details for stair and ladder foundation_IFA | 2026-02-20 | 2026-02-20 | 18-Sep-25 A | 24-Sep-25 A | 2027-01-20 | 3 | 2027-01-20
A17310 | Standard details for stair and ladder foundation_RCA | 2026-02-20 | 2026-02-20 | 15-Sep-25 A | 01-Oct-25 A | 2027-01-20 | 16 | 2027-01-20
A17320 | Standard details for stair and ladder foundation_IFD/IFC | 2026-02-20 | 2026-02-20 | 02-Oct-25 A | 08-Oct-25 A | 2027-01-20 | 2 | 2027-01-20
Site Grading Layout |  | 2026-02-20 | 2026-02-20 | 03-Sep-25 A | 23-Dec-25 A | 2027-01-20 | 42 | 2027-01-20
A17430 | Site Grading Layout_IFR | 2026-02-20 | 2026-02-20 | 03-Sep-25 A | 15-Sep-25 A | 2027-01-20 | 6 | 2027-01-20
A17440 | Site Grading Layout_RCC | 2026-02-20 | 2026-02-20 | 06-Sep-25 A | 22-Sep-25 A | 2027-01-20 | 16 | 2027-01-20
A17450 | Site Grading Layout_IFA | 2026-02-20 | 2026-02-20 | 31-Oct-25 A | 06-Nov-25 A | 2027-01-20 | 3 | 2027-01-20
A17460 | Site Grading Layout_RCA | 2026-02-20 | 2026-02-20 | 07-Nov-25 A | 20-Nov-25 A | 2027-01-20 | 16 | 2027-01-20
A48310 | Site Grading Layout_IFD/IFC | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 23-Dec-25 A | 2027-01-20 | 2 | 2027-01-20
General notes for Structural steel Works |  | 2026-02-20 | 2026-02-20 | 16-Jan-25 A | 03-May-25 A | 2026-11-30 | 95 | 2027-01-20
A48270 | General notes for Structural steel Works_IFR | 2026-02-20 | 2026-02-20 | 16-Jan-25 A | 20-Feb-25 A | 2026-11-30 | 6 | 2026-11-30
A17240 | General notes for Structural steel Works_RCC | 2026-02-20 | 2026-02-20 | 21-Feb-25 A | 13-Mar-25 A | 2027-01-20 | 16 | 2027-01-20
A17250 | General notes for Structural steel Works_IFA | 2026-02-20 | 2026-02-20 | 14-Mar-25 A | 19-Apr-25 A | 2027-01-20 | 3 | 2027-01-20
A17260 | General notes for Structural steel Works_RCA | 2026-02-20 | 2026-02-20 | 20-Apr-25 A | 26-Apr-25 A | 2027-01-20 | 16 | 2027-01-20
A17270 | General notes for Structural steel Works_IFD/IFC | 2026-02-20 | 2026-02-20 | 27-Apr-25 A | 03-May-25 A | 2027-01-20 | 2 | 2027-01-20
Typical Road Details |  | 2026-02-20 | 2026-04-14 | 02-Jul-25 A | 2026-04-14 | 2026-11-30 | 206 | 2027-01-20 | 202
A17330 | Typical Road Details_IFR | 2026-02-20 | 2026-02-20 | 02-Jul-25 A | 09-Jul-25 A | 2026-11-30 | 6 | 2026-11-30
A17340 | Typical Road Details_RCC | 2026-02-20 | 2026-03-13 | 2026-02-20 | 2026-03-13 | 2026-11-30 | 16 | 2026-12-22 | 202
A48290 | Typical Road Details_IFA | 2026-03-13 | 2026-03-19 | 2026-03-13 | 2026-03-19 | 2026-12-22 | 3 | 2026-12-25 | 202
A17360 | Typical Road Details_RCA | 2026-03-19 | 2026-04-09 | 2026-03-19 | 2026-04-09 | 2026-12-28 | 16 | 2027-01-18 | 202
A17370 | Typical Road Details_IFD/IFC | 2026-04-09 | 2026-04-14 | 2026-04-09 | 2026-04-14 | 2027-01-18 | 2 | 2027-01-20 | 202
MTO for Civil Works |  | 2026-02-20 | 2026-02-20 | 05-May-25 A | 10-Jun-25 A | 2026-11-23 | 299 | 2027-01-20
A22430 | MTO for Civil Works_IFR | 2026-02-20 | 2026-02-20 | 05-May-25 A | 16-May-25 A | 2026-11-23 | 11 | 2026-11-23
A22440 | MTO for Civil Works_RCC | 2026-02-20 | 2026-02-20 | 19-May-25 A | 05-Jun-25 A | 2027-01-20 | 16 | 2027-01-20
A50770 | MTO for Civil Works_IFD/IFC | 2026-02-20 | 2026-02-20 | 08-Jun-25 A | 10-Jun-25 A | 2027-01-20 | 2 | 2027-01-20
MTO for Structural Steel |  | 2026-02-20 | 2026-02-20 | 25-Aug-25 A | 12-Sep-25 A | 2026-02-23 | 21 | 2026-07-24
A50780 | MTO for Structural Steel_IFR | 2026-02-20 | 2026-02-20 | 25-Aug-25 A | 29-Aug-25 A | 2026-02-23 | 6 | 2026-02-23
A50790 | MTO for Structural Steel_RCC | 2026-02-20 | 2026-02-20 | 01-Sep-25 A | 05-Sep-25 A | 2026-07-24 | 16 | 2026-07-24
A50800 | MTO for Structural Steel_IFD/IFC | 2026-02-20 | 2026-02-20 | 08-Sep-25 A | 12-Sep-25 A | 2026-07-24 | 2 | 2026-07-24
Tie-in Manhole modification drawing |  | 2026-02-20 | 2026-04-21 | 2026-02-20 | 2026-04-21 | 2026-11-23 | 43 | 2027-01-20 | 196
A22380 | Tie-in Manhole modification drawing_IFR | 2026-02-20 | 2026-02-27 | 2026-02-20 | 2026-02-27 | 2026-11-23 | 6 | 2026-11-30 | 196
A50730 | Tie-in Manhole modification drawing_RCC | 2026-02-27 | 2026-03-23 | 2026-02-27 | 2026-03-23 | 2026-11-30 | 16 | 2026-12-22 | 196
A50740 | Tie-in Manhole modification drawing_IFA | 2026-03-23 | 2026-03-26 | 2026-03-23 | 2026-03-26 | 2026-12-22 | 3 | 2026-12-25 | 196
A50750 | Tie-in Manhole modification drawing_RCA | 2026-03-26 | 2026-04-17 | 2026-03-26 | 2026-04-17 | 2026-12-28 | 16 | 2027-01-18 | 196
A50760 | Tie-in Manhole modification drawing_IFD/IFC | 2026-04-17 | 2026-04-21 | 2026-04-17 | 2026-04-21 | 2027-01-18 | 2 | 2027-01-20 | 196
Fence and Gate Layout |  | 2026-02-20 | 2026-02-20 | 01-May-25 A | 23-Jan-26 A | 2027-01-20 | 199 | 2027-01-20
A17380 | Fence and Gate Layout_IFR | 2026-02-20 | 2026-02-20 | 01-May-25 A | 22-May-25 A | 2027-01-20 | 6 | 2027-01-20
A17390 | Fence and Gate Layout_RCC | 2026-02-20 | 2026-02-20 | 23-May-25 A | 17-Jun-25 A | 2027-01-20 | 16 | 2027-01-20
A17400 | Fence and Gate Layout_IFA | 2026-02-20 | 2026-02-20 | 18-Jun-25 A | 24-Jun-25 A | 2027-01-20 | 3 | 2027-01-20
A48300 | Fence and Gate Layout_RCA | 2026-02-20 | 2026-02-20 | 25-Jun-25 A | 16-Sep-25 A | 2027-01-20 | 16 | 2027-01-20
A17420 | Fence and Gate Layout_IFD/IFC | 2026-02-20 | 2026-02-20 | 30-Dec-25 A | 23-Jan-26 A | 2027-01-20 | 2 | 2027-01-20
Road and Paving Layout |  | 2026-02-20 | 2026-02-20 | 02-Jun-25 A | 23-Jan-26 A | 2026-07-29 | 45 | 2026-07-29
A50190 | Road and Paving Layout_IFR | 2026-02-20 | 2026-02-20 | 02-Jun-25 A | 07-Jul-25 A | 2026-07-29 | 6 | 2026-07-29
A50200 | Road and Paving Layout_RCC | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 09-Jan-26 A | 2026-07-29 | 16 | 2026-07-29
A56270 | Road and Paving Layout_IFA | 2026-02-20 | 2026-02-20 | 09-Jan-26 A | 15-Jan-26 A | 2026-07-29 | 3 | 2026-07-29
A56280 | Road and Paving Layout_RCA | 2026-02-20 | 2026-02-20 | 15-Jan-26 A | 19-Jan-26 A | 2026-07-29 | 16 | 2026-07-29
A21520 | Road and Paving Layout_IFD/IFC | 2026-02-20 | 2026-02-20 | 19-Jan-26 A | 23-Jan-26 A | 2026-07-29 | 2 | 2026-07-29
Telecom |  | 2026-02-20 | 2026-04-21 | 30-Dec-24 A | 2026-04-21 | 2026-03-19 | 352 | 2027-01-20 | 196
Block Diagram For Process CCTV |  | 2026-02-20 | 2026-02-20 | 30-Dec-24 A | 19-Sep-25 A | 2026-03-19 | 196 | 2027-01-20
A51060 | Block Diagram For Process CCTV_IFR | 2026-02-20 | 2026-02-20 | 30-Dec-24 A | 20-Jan-25 A | 2026-03-19 | 6 | 2026-03-19
A51070 | Block Diagram For Process CCTV_RCC | 2026-02-20 | 2026-02-20 | 21-Jan-25 A | 14-Feb-25 A | 2027-01-20 | 16 | 2027-01-20
A51080 | Block Diagram For Process CCTV_IFA | 2026-02-20 | 2026-02-20 | 15-Feb-25 A | 22-Apr-25 A | 2027-01-20 | 3 | 2027-01-20
A51090 | Block Diagram For Process CCTV_RCA | 2026-02-20 | 2026-02-20 | 23-Apr-25 A | 12-Sep-25 A | 2027-01-20 | 16 | 2027-01-20
A51100 | Block Diagram For Process CCTV_IFD/IFC | 2026-02-20 | 2026-02-20 | 13-Sep-25 A | 19-Sep-25 A | 2027-01-20 | 2 | 2027-01-20
Block Diagram For PAGA |  | 2026-02-20 | 2026-02-20 | 30-Dec-24 A | 15-Oct-25 A | 2026-03-19 | 221 | 2027-01-20
A51110 | Block Diagram For PAGA_IFR | 2026-02-20 | 2026-02-20 | 30-Dec-24 A | 20-Jan-25 A | 2026-03-19 | 6 | 2026-03-19
A51120 | Block Diagram For PAGA_RCC | 2026-02-20 | 2026-02-20 | 21-Jan-25 A | 14-Feb-25 A | 2027-01-20 | 16 | 2027-01-20
A51130 | Block Diagram For PAGA_IFA | 2026-02-20 | 2026-02-20 | 15-Feb-25 A | 22-Apr-25 A | 2027-01-20 | 3 | 2027-01-20
A51140 | Block Diagram For PAGA_RCA | 2026-02-20 | 2026-02-20 | 23-Apr-25 A | 10-Sep-25 A | 2027-01-20 | 16 | 2027-01-20
A51150 | Block Diagram For PAGA_IFD/IFC | 2026-02-20 | 2026-02-20 | 15-Sep-25 A | 15-Oct-25 A | 2027-01-20 | 2 | 2027-01-20
Block Diagram For Digital Network And Telephone System |  | 2026-02-20 | 2026-02-20 | 01-Aug-25 A | 22-Oct-25 A | 2026-03-19 | 216 | 2027-01-20
A51160 | Block Diagram For Digital Network And Telephone System_IFR | 2026-02-20 | 2026-02-20 | 01-Aug-25 A | 15-Aug-25 A | 2026-03-19 | 6 | 2026-03-19
A51170 | Block Diagram For Digital Network And Telephone System_RCC | 2026-02-20 | 2026-02-20 | 04-Aug-25 A | 22-Aug-25 A | 2027-01-20 | 16 | 2027-01-20
A51180 | Block Diagram For Digital Network And Telephone System_IFA | 2026-02-20 | 2026-02-20 | 25-Aug-25 A | 29-Aug-25 A | 2027-01-20 | 3 | 2027-01-20
A51190 | Block Diagram For Digital Network And Telephone System_RCA | 2026-02-20 | 2026-02-20 | 25-Aug-25 A | 11-Sep-25 A | 2027-01-20 | 16 | 2027-01-20
A51200 | Block Diagram For Digital Network And Telephone System_IFD/IFC | 2026-02-20 | 2026-02-20 | 01-Oct-25 A | 22-Oct-25 A | 2027-01-20 | 2 | 2027-01-20
Block Diagram For Access Control System |  | 2026-02-20 | 2026-02-20 | 30-Dec-24 A | 19-Sep-25 A | 2026-03-19 | 165 | 2027-01-20
A51210 | Block Diagram For Access Control System_IFR | 2026-02-20 | 2026-02-20 | 30-Dec-24 A | 20-Jan-25 A | 2026-03-19 | 6 | 2026-03-19
A51220 | Block Diagram For Access Control System_RCC | 2026-02-20 | 2026-02-20 | 21-Jan-25 A | 14-Feb-25 A | 2027-01-20 | 16 | 2027-01-20
A51230 | Block Diagram For Access Control System_IFA | 2026-02-20 | 2026-02-20 | 15-Feb-25 A | 22-Apr-25 A | 2027-01-20 | 3 | 2027-01-20
A51240 | Block Diagram For Access Control System_RCA | 2026-02-20 | 2026-02-20 | 23-Apr-25 A | 21-Jun-25 A | 2027-01-20 | 16 | 2027-01-20
A51250 | Block Diagram For Access Control System_IFD/IFC | 2026-02-20 | 2026-02-20 | 22-Jun-25 A | 19-Sep-25 A | 2027-01-20 | 2 | 2027-01-20
Overall Telecom System Block Diagram |  | 2026-02-20 | 2026-02-24 | 25-Jan-25 A | 2026-02-24 | 2027-01-18 | 290 | 2027-01-20 | 237
A51260 | Overall Telecom System Block Diagram_IFR | 2026-02-20 | 2026-02-20 | 25-Jan-25 A | 27-Apr-25 A | 2027-01-18 | 6 | 2027-01-18
A51270 | Overall Telecom System Block Diagram_RCC | 2026-02-20 | 2026-02-20 | 01-Jul-25 A | 29-Jul-25 A | 2027-01-18 | 16 | 2027-01-18
A51280 | Overall Telecom System Block Diagram_IFA | 2026-02-20 | 2026-02-20 | 31-Jul-25 A | 23-Sep-25 A | 2027-01-18 | 3 | 2027-01-18
A51290 | Overall Telecom System Block Diagram_RCA | 2026-02-20 | 2026-02-20 | 22-Sep-25 A | 07-Oct-25 A | 2027-01-18 | 16 | 2027-01-18
A51300 | Overall Telecom System Block Diagram_IFD/IFC | 2026-02-20 | 2026-02-24 | 2026-02-20 | 2026-02-24 | 2027-01-18 | 2 | 2027-01-20 | 237
Telecom Tie-In Schedule |  | 2026-02-20 | 2026-02-20 | 13-Mar-25 A | 01-Sep-25 A | 2027-01-20 | 206 | 2027-01-20
A51800 | Telecom Tie-In Schedule_IFR | 2026-02-20 | 2026-02-20 | 13-Mar-25 A | 27-Apr-25 A | 2027-01-20 | 11 | 2027-01-20
A51810 | Telecom Tie-In Schedule_RCC | 2026-02-20 | 2026-02-20 | 28-Apr-25 A | 04-May-25 A | 2027-01-20 | 16 | 2027-01-20
A51820 | Telecom Tie-In Schedule_IFA | 2026-02-20 | 2026-02-20 | 05-May-25 A | 11-May-25 A | 2027-01-20 | 3 | 2027-01-20
A23660 | Telecom Tie-In Schedule_RCA | 2026-02-20 | 2026-02-20 | 12-May-25 A | 25-Aug-25 A | 2027-01-20 | 16 | 2027-01-20
A51830 | Telecom Tie-In Schedule_IFD/IFC | 2026-02-20 | 2026-02-20 | 26-Aug-25 A | 01-Sep-25 A | 2027-01-20 | 2 | 2027-01-20
Datasheet For Fiber Optic Cable |  | 2026-02-20 | 2026-02-20 | 30-Jan-25 A | 11-May-25 A | 2026-03-19 | 116 | 2027-01-20
A50810 | Datasheet For Fiber Optic Cable_IFR | 2026-02-20 | 2026-02-20 | 30-Jan-25 A | 20-Feb-25 A | 2026-03-19 | 6 | 2026-03-19
A50820 | Datasheet For Fiber Optic Cable_RCC | 2026-02-20 | 2026-02-20 | 21-Feb-25 A | 20-Apr-25 A | 2027-01-20 | 16 | 2027-01-20
A50830 | Datasheet For Fiber Optic Cable_IFA | 2026-02-20 | 2026-02-20 | 21-Apr-25 A | 27-Apr-25 A | 2027-01-20 | 3 | 2027-01-20
A50840 | Datasheet For Fiber Optic Cable_RCA | 2026-02-20 | 2026-02-20 | 28-Apr-25 A | 04-May-25 A | 2027-01-20 | 16 | 2027-01-20
A50850 | Datasheet For Fiber Optic Cable_IFD/IFC | 2026-02-20 | 2026-02-20 | 05-May-25 A | 11-May-25 A | 2027-01-20 | 2 | 2027-01-20
Datasheet For Process CCTV |  | 2026-02-20 | 2026-02-20 | 01-Aug-25 A | 19-Jan-26 A | 2026-03-19 | 269 | 2026-03-19
A50860 | Datasheet For Process CCTV_IFR | 2026-02-20 | 2026-02-20 | 01-Aug-25 A | 15-Aug-25 A | 2026-03-19 | 6 | 2026-03-19
A50870 | Datasheet For Process CCTV_RCC | 2026-02-20 | 2026-02-20 | 15-Sep-25 A | 15-Oct-25 A | 2026-03-19 | 16 | 2026-03-19
A50880 | Datasheet For Process CCTV_IFA | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 24-Dec-25 A | 2026-03-19 | 3 | 2026-03-19
A50890 | Datasheet For Process CCTV_RCA | 2026-02-20 | 2026-02-20 | 24-Dec-25 A | 15-Jan-26 A | 2026-03-19 | 16 | 2026-03-19
A50900 | Datasheet For Process CCTV_IFD/IFC | 2026-02-20 | 2026-02-20 | 15-Jan-26 A | 19-Jan-26 A | 2026-03-19 | 2 | 2026-03-19
Datasheet For PAGA |  | 2026-02-20 | 2026-02-20 | 10-Jan-25 A | 23-Dec-25 A | 2026-03-19 | 250 | 2026-03-19
A50910 | Datasheet For PAGA_IFR | 2026-02-20 | 2026-02-20 | 10-Jan-25 A | 20-Mar-25 A | 2026-03-19 | 6 | 2026-03-19
A50920 | Datasheet For PAGA_RCC | 2026-02-20 | 2026-02-20 | 21-Mar-25 A | 20-Apr-25 A | 2026-03-19 | 16 | 2026-03-19
A50930 | Datasheet For PAGA_IFA | 2026-02-20 | 2026-02-20 | 21-Apr-25 A | 30-May-25 A | 2026-03-19 | 3 | 2026-03-19
A50940 | Datasheet For PAGA_RCA | 2026-02-20 | 2026-02-20 | 01-Jun-25 A | 21-Jun-25 A | 2026-03-19 | 16 | 2026-03-19
A50950 | Datasheet For PAGA_IFD/IFC | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 23-Dec-25 A | 2026-03-19 | 2 | 2026-03-19
Datasheet For Access Control System |  | 2026-02-20 | 2026-02-20 | 15-Jan-25 A | 23-Dec-25 A | 2026-03-19 | 245 | 2026-03-19
A50960 | Datasheet For Access Control System_IFR | 2026-02-20 | 2026-02-20 | 15-Jan-25 A | 27-Apr-25 A | 2026-03-19 | 6 | 2026-03-19
A50970 | Datasheet For Access Control System_RCC | 2026-02-20 | 2026-02-20 | 28-Apr-25 A | 04-May-25 A | 2026-03-19 | 16 | 2026-03-19
A50980 | Datasheet For Access Control System_IFA | 2026-02-20 | 2026-02-20 | 05-May-25 A | 09-Jun-25 A | 2026-03-19 | 3 | 2026-03-19
A50990 | Datasheet For Access Control System_RCA | 2026-02-20 | 2026-02-20 | 10-Jun-25 A | 19-Sep-25 A | 2026-03-19 | 16 | 2026-03-19
A51000 | Datasheet For Access Control System_IFD/IFC | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 23-Dec-25 A | 2026-03-19 | 2 | 2026-03-19
Datasheet For Digital Network And Telephone System |  | 2026-02-20 | 2026-02-20 | 15-Jan-25 A | 23-Dec-25 A | 2026-03-19 | 245 | 2026-03-19
A51010 | Datasheet For Digital Network And Telephone System_IFR | 2026-02-20 | 2026-02-20 | 15-Jan-25 A | 27-Apr-25 A | 2026-03-19 | 6 | 2026-03-19
A51020 | Datasheet For Digital Network And Telephone System_RCC | 2026-02-20 | 2026-02-20 | 28-Apr-25 A | 04-May-25 A | 2026-03-19 | 16 | 2026-03-19
A51030 | Datasheet For Digital Network And Telephone System_IFA | 2026-02-20 | 2026-02-20 | 05-May-25 A | 10-Jun-25 A | 2026-03-19 | 3 | 2026-03-19
A51040 | Datasheet For Digital Network And Telephone System_RCA | 2026-02-20 | 2026-02-20 | 11-Jun-25 A | 28-Aug-25 A | 2026-03-19 | 16 | 2026-03-19
A51050 | Datasheet For Digital Network And Telephone System_IFD/IFC | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 23-Dec-25 A | 2026-03-19 | 2 | 2026-03-19
Wiring Diagram For Process Cctv |  | 2026-02-20 | 2026-02-20 | 08-Jan-25 A | 23-Dec-25 A | 2027-01-20 | 261 | 2027-01-20
A51310 | Wiring Diagram For Process Cctv_IFR | 2026-02-20 | 2026-02-20 | 08-Jan-25 A | 12-Feb-25 A | 2027-01-20 | 6 | 2027-01-20
A51320 | Wiring Diagram For Process Cctv_RCC | 2026-02-20 | 2026-02-20 | 13-Feb-25 A | 13-Mar-25 A | 2027-01-20 | 16 | 2027-01-20
A51330 | Wiring Diagram For Process Cctv_IFA | 2026-02-20 | 2026-02-20 | 27-Oct-25 A | 03-Nov-25 A | 2027-01-20 | 3 | 2027-01-20
A51340 | Wiring Diagram For Process Cctv_RCA | 2026-02-20 | 2026-02-20 | 04-Nov-25 A | 18-Nov-25 A | 2027-01-20 | 16 | 2027-01-20
A51350 | Wiring Diagram For Process Cctv_IFD/IFC | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 23-Dec-25 A | 2027-01-20 | 2 | 2027-01-20
Wiring Diagram For Paga |  | 2026-02-20 | 2026-02-20 | 09-Jan-25 A | 19-Jan-26 A | 2027-01-20 | 275 | 2027-01-20
A51360 | Wiring Diagram For Paga_IFR | 2026-02-20 | 2026-02-20 | 09-Jan-25 A | 12-Feb-25 A | 2027-01-20 | 6 | 2027-01-20
A51370 | Wiring Diagram For Paga_RCC | 2026-02-20 | 2026-02-20 | 13-Feb-25 A | 13-Mar-25 A | 2027-01-20 | 16 | 2027-01-20
A51380 | Wiring Diagram For Paga_IFA | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 24-Dec-25 A | 2027-01-20 | 3 | 2027-01-20
A51390 | Wiring Diagram For Paga_RCA | 2026-02-20 | 2026-02-20 | 24-Dec-25 A | 15-Jan-26 A | 2027-01-20 | 16 | 2027-01-20
A51400 | Wiring Diagram For Paga_IFD/IFC | 2026-02-20 | 2026-02-20 | 15-Jan-26 A | 19-Jan-26 A | 2027-01-20 | 2 | 2027-01-20
Wiring Diagram For Digital Network And Telephone System |  | 2026-02-20 | 2026-04-21 | 22-Jan-25 A | 2026-04-21 | 2026-11-23 | 336 | 2027-01-20 | 196
A51410 | Wiring Diagram For Digital Network And Telephone System_IFR | 2026-02-20 | 2026-02-27 | 22-Jan-25 A | 2026-02-27 | 2026-11-23 | 6 | 2026-11-30 | 196
A51420 | Wiring Diagram For Digital Network And Telephone System_RCC | 2026-02-27 | 2026-03-23 | 2026-02-27 | 2026-03-23 | 2026-11-30 | 16 | 2026-12-22 | 196
A51430 | Wiring Diagram For Digital Network And Telephone System_IFA | 2026-03-23 | 2026-03-26 | 2026-03-23 | 2026-03-26 | 2026-12-22 | 3 | 2026-12-25 | 196
A51440 | Wiring Diagram For Digital Network And Telephone System_RCA | 2026-03-26 | 2026-04-17 | 2026-03-26 | 2026-04-17 | 2026-12-28 | 16 | 2027-01-18 | 196
A51450 | Wiring Diagram For Digital Network And Telephone System_IFD/IFC | 2026-04-17 | 2026-04-21 | 2026-04-17 | 2026-04-21 | 2027-01-18 | 2 | 2027-01-20 | 196
Wiring Diagram For Access Control System |  | 2026-02-20 | 2026-04-21 | 22-Jan-25 A | 2026-04-21 | 2026-11-23 | 331 | 2027-01-20 | 196
A51460 | Wiring Diagram For Access Control System_IFR | 2026-02-20 | 2026-02-27 | 22-Jan-25 A | 2026-02-27 | 2026-11-23 | 6 | 2026-11-30 | 196
A51470 | Wiring Diagram For Access Control System_RCC | 2026-02-27 | 2026-03-23 | 2026-02-27 | 2026-03-23 | 2026-11-30 | 16 | 2026-12-22 | 196
A51480 | Wiring Diagram For Access Control System_IFA | 2026-03-23 | 2026-03-26 | 2026-03-23 | 2026-03-26 | 2026-12-22 | 3 | 2026-12-25 | 196
A51490 | Wiring Diagram For Access Control System_RCA | 2026-03-26 | 2026-04-17 | 2026-03-26 | 2026-04-17 | 2026-12-28 | 16 | 2027-01-18 | 196
A51500 | Wiring Diagram For Access Control System_IFD/IFC | 2026-04-17 | 2026-04-21 | 2026-04-17 | 2026-04-21 | 2027-01-18 | 2 | 2027-01-20 | 196
Material Requisitions For Telecom System (Paga, CCTV, ACS, Telephone & LAN System) |  | 2026-02-20 | 2026-02-20 | 14-Mar-25 A | 22-Jan-26 A | 2026-03-19 | 263 | 2026-03-19
A23780 | Material Requisitions For Telecom System (Paga, Cctv, Acs, Telephone & Lan System)_IFR | 2026-02-20 | 2026-02-20 | 14-Mar-25 A | 26-Apr-25 A | 2026-03-19 | 6 | 2026-03-19
A23790 | Material Requisitions For Telecom System (Paga, Cctv, Acs, Telephone & Lan System)_RCC | 2026-02-20 | 2026-02-20 | 01-Jul-25 A | 29-Jul-25 A | 2026-03-19 | 16 | 2026-03-19
A23800 | Material Requisitions For Telecom System (Paga, Cctv, Acs, Telephone & Lan System)_IFA | 2026-02-20 | 2026-02-20 | 24-Dec-25 A | 29-Dec-25 A | 2026-03-19 | 3 | 2026-03-19
A23810 | Material Requisitions For Telecom System (Paga, Cctv, Acs, Telephone & Lan System)_RCA | 2026-02-20 | 2026-02-20 | 29-Dec-25 A | 20-Jan-26 A | 2026-03-19 | 16 | 2026-03-19
A51910 | Material Requisitions For Telecom System (Paga, Cctv, Acs, Telephone & Lan System)_IFD/IFC | 2026-02-20 | 2026-02-20 | 20-Jan-26 A | 22-Jan-26 A | 2026-03-19 | 2 | 2026-03-19
Material Requisitions For Telecom Cables |  | 2026-02-20 | 2026-02-20 | 01-May-25 A | 23-Dec-25 A | 2026-11-23 | 161 | 2027-01-20
A51920 | Material Requisitions For Telecom Cables_IFR | 2026-02-20 | 2026-02-20 | 01-May-25 A | 22-May-25 A | 2026-11-23 | 6 | 2026-11-23
A51930 | Material Requisitions For Telecom Cables_RCC | 2026-02-20 | 2026-02-20 | 01-Jul-25 A | 29-Jul-25 A | 2027-01-20 | 16 | 2027-01-20
A51940 | Material Requisitions For Telecom Cables_IFA | 2026-02-20 | 2026-02-20 | 27-Oct-25 A | 11-Nov-25 A | 2027-01-20 | 3 | 2027-01-20
A23860 | Material Requisitions For Telecom Cables_RCA | 2026-02-20 | 2026-02-20 | 12-Nov-25 A | 21-Nov-25 A | 2027-01-20 | 16 | 2027-01-20
A23870 | Material Requisitions For Telecom Cables_IFD/IFC | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 23-Dec-25 A | 2027-01-20 | 2 | 2027-01-20
Telecom Equipment List |  | 2026-02-20 | 2026-02-20 | 10-Mar-25 A | 18-Dec-25 A | 2027-01-20 | 220 | 2027-01-20
A23580 | Telecom Equipment List_IFR | 2026-02-20 | 2026-02-20 | 10-Mar-25 A | 27-Apr-25 A | 2027-01-20 | 6 | 2027-01-20
A51760 | Telecom Equipment List_RCC | 2026-02-20 | 2026-02-20 | 28-Apr-25 A | 04-May-25 A | 2027-01-20 | 16 | 2027-01-20
A51770 | Telecom Equipment List_IFA | 2026-02-20 | 2026-02-20 | 25-Aug-25 A | 15-Sep-25 A | 2027-01-20 | 3 | 2027-01-20
A51780 | Telecom Equipment List_RCA | 2026-02-20 | 2026-02-20 | 10-Sep-25 A | 29-Sep-25 A | 2027-01-20 | 16 | 2027-01-20
A51790 | Telecom Equipment List_IFD/IFC | 2026-02-20 | 2026-02-20 | 04-Dec-25 A | 18-Dec-25 A | 2027-01-20 | 2 | 2027-01-20
Telecom Cable Schedule |  | 2026-02-20 | 2026-03-23 | 14-Apr-25 A | 2026-03-23 | 2026-12-22 | 276 | 2027-01-20 | 218
A51640 | Telecom Cable Schedule_IFR | 2026-02-20 | 2026-02-20 | 14-Apr-25 A | 05-May-25 A | 2026-12-22 | 6 | 2026-12-22
A51650 | Telecom Cable Schedule_RCC | 2026-02-20 | 2026-02-20 | 06-May-25 A | 29-Jul-25 A | 2026-12-22 | 16 | 2026-12-22
A51660 | Telecom Cable Schedule_IFA | 2026-02-20 | 2026-02-25 | 2026-02-20 | 2026-02-25 | 2026-12-22 | 3 | 2026-12-25 | 218
A51670 | Telecom Cable Schedule_RCA | 2026-02-25 | 2026-03-19 | 2026-02-25 | 2026-03-19 | 2026-12-28 | 16 | 2027-01-18 | 218
A51680 | Telecom Cable Schedule_IFD/IFC | 2026-03-19 | 2026-03-23 | 2026-03-19 | 2026-03-23 | 2027-01-18 | 2 | 2027-01-20 | 218
Telecom Junction Box Schedule |  | 2026-02-20 | 2026-02-20 | 01-Aug-25 A | 23-Dec-25 A | 2027-01-20 | 143 | 2027-01-20
A51690 | Telecom Junction Box Schedule_IFR | 2026-02-20 | 2026-02-20 | 01-Aug-25 A | 15-Aug-25 A | 2027-01-20 | 6 | 2027-01-20
A51700 | Telecom Junction Box Schedule_RCC | 2026-02-20 | 2026-02-20 | 04-Aug-25 A | 22-Aug-25 A | 2027-01-20 | 16 | 2027-01-20
A51710 | Telecom Junction Box Schedule_IFA | 2026-02-20 | 2026-02-20 | 03-Nov-25 A | 11-Nov-25 A | 2027-01-20 | 3 | 2027-01-20
A51720 | Telecom Junction Box Schedule_RCA | 2026-02-20 | 2026-02-20 | 12-Nov-25 A | 21-Nov-25 A | 2027-01-20 | 16 | 2027-01-20
A23520 | Telecom Junction Box Schedule_IFD/IFC | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 23-Dec-25 A | 2027-01-20 | 2 | 2027-01-20
Voltage Drop Calculation For Paga System |  | 2026-02-20 | 2026-04-21 | 2026-02-20 | 2026-04-21 | 2026-11-23 | 43 | 2027-01-20 | 196
A51730 | Voltage Drop Calculation For Paga System_IFR | 2026-02-20 | 2026-02-27 | 2026-02-20 | 2026-02-27 | 2026-11-23 | 6 | 2026-11-30 | 196
A51740 | Voltage Drop Calculation For Paga System_RCC | 2026-02-27 | 2026-03-23 | 2026-02-27 | 2026-03-23 | 2026-11-30 | 16 | 2026-12-22 | 196
A23550 | Voltage Drop Calculation For Paga System_IFA | 2026-03-23 | 2026-03-26 | 2026-03-23 | 2026-03-26 | 2026-12-22 | 3 | 2026-12-25 | 196
A51750 | Voltage Drop Calculation For Paga System_RCA | 2026-03-26 | 2026-04-17 | 2026-03-26 | 2026-04-17 | 2026-12-28 | 16 | 2027-01-18 | 196
A23570 | Voltage Drop Calculation For Paga System_IFD/IFC | 2026-04-17 | 2026-04-21 | 2026-04-17 | 2026-04-21 | 2027-01-18 | 2 | 2027-01-20 | 196
Technical Bid Evaluation For Telecom Cables |  | 2026-02-20 | 2026-04-21 | 2026-02-20 | 2026-04-21 | 2026-11-23 | 43 | 2027-01-20 | 196
A51980 | Technical Bid Evaluation For Telecom Cables_IFR | 2026-02-20 | 2026-02-27 | 2026-02-20 | 2026-02-27 | 2026-11-23 | 6 | 2026-11-30 | 196
A51990 | Technical Bid Evaluation For Telecom Cables_RCC | 2026-02-27 | 2026-03-23 | 2026-02-27 | 2026-03-23 | 2026-11-30 | 16 | 2026-12-22 | 196
A52000 | Technical Bid Evaluation For Telecom Cables_IFA | 2026-03-23 | 2026-03-26 | 2026-03-23 | 2026-03-26 | 2026-12-22 | 3 | 2026-12-25 | 196
A52010 | Technical Bid Evaluation For Telecom Cables_RCA | 2026-03-26 | 2026-04-17 | 2026-03-26 | 2026-04-17 | 2026-12-28 | 16 | 2027-01-18 | 196
A52020 | Technical Bid Evaluation For Telecom Cables_IFD/IFC | 2026-04-17 | 2026-04-21 | 2026-04-17 | 2026-04-21 | 2027-01-18 | 2 | 2027-01-20 | 196
Central Control Room Equipment Layout For Telecom |  | 2026-02-20 | 2026-03-17 | 01-Jul-25 A | 2026-03-17 | 2026-12-28 | 193 | 2027-01-20 | 221
A51840 | Central Control Room Equipment Layout For Telecom_IFR | 2026-02-20 | 2026-02-20 | 01-Jul-25 A | 13-Jul-25 A | 2026-12-28 | 6 | 2026-12-28
A51850 | Central Control Room Equipment Layout For Telecom_RCC | 2026-02-20 | 2026-02-20 | 15-Aug-25 A | 15-Sep-25 A | 2026-12-28 | 16 | 2026-12-28
A51860 | Central Control Room Equipment Layout For Telecom_IFA | 2026-02-20 | 2026-02-20 | 16-Sep-25 A | 29-Sep-25 A | 2026-12-28 | 3 | 2026-12-28
A51870 | Central Control Room Equipment Layout For Telecom_RCA | 2026-02-20 | 2026-03-13 | 2026-02-20 | 2026-03-13 | 2026-12-28 | 16 | 2027-01-18 | 221
A51880 | Central Control Room Equipment Layout For Telecom_IFD/IFC | 2026-03-13 | 2026-03-17 | 2026-03-13 | 2026-03-17 | 2027-01-18 | 2 | 2027-01-20 | 221
Telecommunication Core Allocation Drawing For Fiber Optic Cable |  | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 23-Jan-26 A | 2027-01-20 | 78 | 2027-01-20
A51890 | Telecommunication Core Allocation Drawing For Fiber Optic Cable_IFR | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 28-Apr-25 A | 2027-01-20 | 6 | 2027-01-20
A51900 | Telecommunication Core Allocation Drawing For Fiber Optic Cable_RCC | 2026-02-20 | 2026-02-20 | 29-Apr-25 A | 21-Jul-25 A | 2027-01-20 | 16 | 2027-01-20
A23750 | Telecommunication Core Allocation Drawing For Fiber Optic Cable_IFA | 2026-02-20 | 2026-02-20 | 03-Nov-25 A | 11-Nov-25 A | 2027-01-20 | 3 | 2027-01-20
A23760 | Telecommunication Core Allocation Drawing For Fiber Optic Cable_RCA | 2026-02-20 | 2026-02-20 | 10-Nov-25 A | 21-Nov-25 A | 2027-01-20 | 16 | 2027-01-20
A23770 | Telecommunication Core Allocation Drawing For Fiber Optic Cable_IFD/IFC | 2026-02-20 | 2026-02-20 | 23-Dec-25 A | 23-Jan-26 A | 2027-01-20 | 2 | 2027-01-20
Overall Telecom Cable Routing Layout Drawing For H2 Extraction Unit |  | 2026-02-20 | 2026-02-20 | 01-May-25 A | 23-Jan-26 A | 2026-11-23 | 78 | 2027-01-20
A51560 | Overall Telecom Cable Routing Layout Drawing For H2 Extraction Unit_IFR | 2026-02-20 | 2026-02-20 | 01-May-25 A | 08-May-25 A | 2026-11-23 | 11 | 2026-11-23
A51570 | Overall Telecom Cable Routing Layout Drawing For H2 Extraction Unit_RCC | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 25-Dec-25 A | 2027-01-20 | 16 | 2027-01-20
A51580 | Overall Telecom Cable Routing Layout Drawing For H2 Extraction Unit_IFA | 2026-02-20 | 2026-02-20 | 25-Dec-25 A | 06-Jan-26 A | 2027-01-20 | 3 | 2027-01-20
A51590 | Overall Telecom Cable Routing Layout Drawing For H2 Extraction Unit_RCA | 2026-02-20 | 2026-02-20 | 06-Jan-26 A | 14-Jan-26 A | 2027-01-20 | 16 | 2027-01-20
A51600 | Overall Telecom Cable Routing Layout Drawing For H2 Extraction Unit_IFD/IFC | 2026-02-20 | 2026-02-20 | 10-Jan-26 A | 23-Jan-26 A | 2027-01-20 | 2 | 2027-01-20
Overall Telecom Equipment Layout Drawing For H2 Extraction Unit |  | 2026-02-20 | 2026-02-20 | 01-May-25 A | 16-Jan-26 A | 2026-11-23 | 98 | 2027-01-20
A51510 | Overall Telecom Equipment Layout Drawing For H2 Extraction Unit_IFR | 2026-02-20 | 2026-02-20 | 01-May-25 A | 20-May-25 A | 2026-11-23 | 11 | 2026-11-23
A51520 | Overall Telecom Equipment Layout Drawing For H2 Extraction Unit_RCC | 2026-02-20 | 2026-02-20 | 21-May-25 A | 04-Jun-25 A | 2026-12-22 | 16 | 2026-12-22
A51530 | Overall Telecom Equipment Layout Drawing For H2 Extraction Unit_IFA | 2026-02-20 | 2026-02-20 | 10-Oct-25 A | 16-Oct-25 A | 2026-12-22 | 3 | 2026-12-22
A51540 | Overall Telecom Equipment Layout Drawing For H2 Extraction Unit_RCA | 2026-02-20 | 2026-02-20 | 17-Oct-25 A | 01-Nov-25 A | 2027-01-20 | 16 | 2027-01-20
A51550 | Overall Telecom Equipment Layout Drawing For H2 Extraction Unit_IFD/IFC | 2026-02-20 | 2026-02-20 | 31-Dec-25 A | 16-Jan-26 A | 2027-01-20 | 2 | 2027-01-20
Telecom System Material Take Off |  | 2026-02-20 | 2026-02-20 | 02-Jul-25 A | 23-Dec-25 A | 2027-01-20 | 116 | 2027-01-20
A51610 | Telecom System Material Take Off_IFR | 2026-02-20 | 2026-02-20 | 02-Jul-25 A | 18-Jul-25 A | 2027-01-20 | 6 | 2027-01-20
A51620 | Telecom System Material Take Off_RCC | 2026-02-20 | 2026-02-20 | 07-Jul-25 A | 29-Jul-25 A | 2027-01-20 | 16 | 2027-01-20
A51630 | Telecom System Material Take Off_IFD/IFC | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 23-Dec-25 A | 2027-01-20 | 2 | 2027-01-20
Material/Corrosion |  | 2026-02-20 | 2026-03-23 | 15-Apr-25 A | 2026-03-23 | 2026-12-22 | 320 | 2027-01-20 | 218
Material Selection & Corrosion Control Report |  | 2026-02-20 | 2026-03-23 | 15-Apr-25 A | 2026-03-23 | 2026-12-22 | 320 | 2027-01-20 | 218
A52070 | Material Selection & Corrosion Control Report_IFR | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 07-May-25 A | 2026-12-22 | 6 | 2026-12-22
A24040 | Material Selection & Corrosion Control Report_RCC | 2026-02-20 | 2026-02-20 | 08-May-25 A | 03-Jun-25 A | 2026-12-22 | 16 | 2026-12-22
A24050 | Material Selection & Corrosion Control Report_IFA | 2026-02-20 | 2026-02-25 | 2026-02-20 | 2026-02-25 | 2026-12-22 | 3 | 2026-12-25 | 218
A52080 | Material Selection & Corrosion Control Report_RCA | 2026-02-25 | 2026-03-19 | 2026-02-25 | 2026-03-19 | 2026-12-28 | 16 | 2027-01-18 | 218
A52090 | Material Selection & Corrosion Control Report_IFD/IFC | 2026-03-19 | 2026-03-23 | 2026-03-19 | 2026-03-23 | 2027-01-18 | 2 | 2027-01-20 | 218
Material Selection Diagrams (MSD) |  | 2026-02-20 | 2026-03-17 | 16-Apr-25 A | 2026-03-17 | 2026-12-28 | 311 | 2027-01-20 | 221
A52030 | Material Selection Diagrams (MSD)_IFR | 2026-02-20 | 2026-02-20 | 16-Apr-25 A | 25-Jul-25 A | 2026-12-28 | 6 | 2026-12-28
A52040 | Material Selection Diagrams (MSD)_RCC | 2026-02-20 | 2026-02-20 | 25-Jul-25 A | 01-Aug-25 A | 2026-12-28 | 16 | 2026-12-28
A52050 | Material Selection Diagrams (MSD)_IFA | 2026-02-20 | 2026-02-20 | 29-Nov-25 A | 18-Dec-25 A | 2026-12-28 | 3 | 2026-12-28
A52060 | Material Selection Diagrams (MSD)_RCA | 2026-02-20 | 2026-03-13 | 2026-02-20 | 2026-03-13 | 2026-12-28 | 16 | 2027-01-18 | 221
A24020 | Material Selection Diagrams (MSD)_IFD/IFC | 2026-03-13 | 2026-03-17 | 2026-03-13 | 2026-03-17 | 2027-01-18 | 2 | 2027-01-20 | 221
HVAC |  | 2026-02-20 | 2026-04-21 | 13-Mar-25 A | 2026-04-21 | 2026-03-19 | 342 | 2027-01-20 | 196
HVAC Design Basis |  | 2026-02-20 | 2026-02-20 | 13-Mar-25 A | 24-May-25 A | 2027-01-20 | 137 | 2027-01-20
A52100 | HVAC Design Basis_IFR | 2026-02-20 | 2026-02-20 | 13-Mar-25 A | 26-Apr-25 A | 2027-01-20 | 6 | 2027-01-20
A52110 | HVAC Design Basis_RCC | 2026-02-20 | 2026-02-20 | 27-Apr-25 A | 03-May-25 A | 2027-01-20 | 16 | 2027-01-20
A52120 | HVAC Design Basis_IFA | 2026-02-20 | 2026-02-20 | 04-May-25 A | 10-May-25 A | 2027-01-20 | 3 | 2027-01-20
A52130 | HVAC Design Basis_RCA | 2026-02-20 | 2026-02-20 | 11-May-25 A | 18-May-25 A | 2027-01-20 | 16 | 2027-01-20
A52140 | HVAC Design Basis_IFD/IFC | 2026-02-20 | 2026-02-20 | 19-May-25 A | 24-May-25 A | 2027-01-20 | 2 | 2027-01-20
HVAC Equipment And Accessories Specifications |  | 2026-02-20 | 2026-02-20 | 23-Mar-25 A | 19-May-25 A | 2027-01-20 | 133 | 2027-01-20
A52150 | HVAC Equipment And Accessories Specifications_IFR | 2026-02-20 | 2026-02-20 | 23-Mar-25 A | 13-Apr-25 A | 2027-01-20 | 6 | 2027-01-20
A52160 | HVAC Equipment And Accessories Specifications_RCC | 2026-02-20 | 2026-02-20 | 14-Apr-25 A | 22-Apr-25 A | 2027-01-20 | 16 | 2027-01-20
A52170 | HVAC Equipment And Accessories Specifications_IFA | 2026-02-20 | 2026-02-20 | 23-Apr-25 A | 05-May-25 A | 2027-01-20 | 3 | 2027-01-20
A52180 | HVAC Equipment And Accessories Specifications_RCA | 2026-02-20 | 2026-02-20 | 06-May-25 A | 12-May-25 A | 2027-01-20 | 16 | 2027-01-20
A52190 | HVAC Equipment And Accessories Specifications_IFD/IFC | 2026-02-20 | 2026-02-20 | 13-May-25 A | 19-May-25 A | 2027-01-20 | 2 | 2027-01-20
HVAC Cooling Load Calculation And Equipment Sizing |  | 2026-02-20 | 2026-02-20 | 20-Apr-25 A | 03-Jun-25 A | 2026-03-19 | 66 | 2026-03-19
A52200 | HVAC Cooling Load Calculation And Equipment Sizing_IFR | 2026-02-20 | 2026-02-20 | 20-Apr-25 A | 11-May-25 A | 2026-03-19 | 11 | 2026-03-19
A52210 | HVAC Cooling Load Calculation And Equipment Sizing_RCC | 2026-02-20 | 2026-02-20 | 12-May-25 A | 18-May-25 A | 2026-03-19 | 16 | 2026-03-19
A52220 | HVAC Cooling Load Calculation And Equipment Sizing_IFA | 2026-02-20 | 2026-02-20 | 23-May-25 A | 25-May-25 A | 2026-03-19 | 3 | 2026-03-19
A24210 | HVAC Cooling Load Calculation And Equipment Sizing_RCA | 2026-02-20 | 2026-02-20 | 26-May-25 A | 31-May-25 A | 2026-03-19 | 16 | 2026-03-19
A24220 | HVAC Cooling Load Calculation And Equipment Sizing_IFD/IFC | 2026-02-20 | 2026-02-20 | 01-Jun-25 A | 03-Jun-25 A | 2026-03-19 | 2 | 2026-03-19
HVAC Airflow Schematic Diagrams |  | 2026-02-20 | 2026-02-20 | 25-Apr-25 A | 25-Oct-25 A | 2026-11-02 | 67 | 2027-01-20
A52540 | HVAC Airflow Schematic Diagrams_IFR | 2026-02-20 | 2026-02-20 | 25-Apr-25 A | 16-May-25 A | 2026-11-02 | 6 | 2026-11-02
A52550 | HVAC Airflow Schematic Diagrams_RCC | 2026-02-20 | 2026-02-20 | 15-Jul-25 A | 01-Aug-25 A | 2027-01-20 | 16 | 2027-01-20
A52560 | HVAC Airflow Schematic Diagrams_IFA | 2026-02-20 | 2026-02-20 | 29-Sep-25 A | 07-Oct-25 A | 2027-01-20 | 3 | 2027-01-20
A52570 | HVAC Airflow Schematic Diagrams_RCA | 2026-02-20 | 2026-02-20 | 30-Sep-25 A | 20-Oct-25 A | 2027-01-20 | 16 | 2027-01-20
A52580 | HVAC Airflow Schematic Diagrams_IFD/IFC | 2026-02-20 | 2026-02-20 | 21-Oct-25 A | 25-Oct-25 A | 2027-01-20 | 2 | 2027-01-20
HVAC Chilled Water Piping Schematic Diagrams |  | 2026-02-20 | 2026-04-14 | 20-Jun-25 A | 2026-04-14 | 2026-11-02 | 189 | 2027-01-20 | 202
A52590 | HVAC Chilled Water Piping Schematic Diagrams_IFR | 2026-02-20 | 2026-02-20 | 20-Jun-25 A | 05-Jul-25 A | 2026-11-02 | 2 | 2026-11-02
A52600 | HVAC Chilled Water Piping Schematic Diagrams_RCC | 2026-02-20 | 2026-03-13 | 2026-02-20 | 2026-03-13 | 2026-11-30 | 16 | 2026-12-22 | 202
A52610 | HVAC Chilled Water Piping Schematic Diagrams_IFA | 2026-03-13 | 2026-03-19 | 2026-03-13 | 2026-03-19 | 2026-12-22 | 3 | 2026-12-25 | 202
A52620 | HVAC Chilled Water Piping Schematic Diagrams_RCA | 2026-03-19 | 2026-04-09 | 2026-03-19 | 2026-04-09 | 2026-12-28 | 16 | 2027-01-18 | 202
A52630 | HVAC Chilled Water Piping Schematic Diagrams_IFD/IFC | 2026-04-09 | 2026-04-14 | 2026-04-09 | 2026-04-14 | 2027-01-18 | 2 | 2027-01-20 | 202
HVAC Chilled Water Piping And Instrumentation Diagrams |  | 2026-02-20 | 2026-02-24 | 02-Jun-25 A | 2026-02-24 | 2026-11-02 | 169 | 2027-01-20 | 237
A52840 | HVAC Chilled Water Piping And Instrumentation Diagrams_IFR | 2026-02-20 | 2026-02-20 | 02-Jun-25 A | 05-Jul-25 A | 2026-11-02 | 6 | 2026-11-02
A52850 | HVAC Chilled Water Piping And Instrumentation Diagrams_RCC | 2026-02-20 | 2026-02-20 | 11-Jul-25 A | 15-Aug-25 A | 2027-01-18 | 16 | 2027-01-18
A52860 | HVAC Chilled Water Piping And Instrumentation Diagrams_IFH | 2026-02-20 | 2026-02-20 | 15-Aug-25 A | 22-Aug-25 A | 2027-01-18 | 3 | 2027-01-18
A52870 | HVAC Chilled Water Piping And Instrumentation Diagrams_RCA | 2026-02-20 | 2026-02-20 | 25-Aug-25 A | 07-Oct-25 A | 2027-01-18 | 16 | 2027-01-18
A52880 | HVAC Chilled Water Piping And Instrumentation Diagrams_IFD/IFC | 2026-02-20 | 2026-02-24 | 2026-02-20 | 2026-02-24 | 2027-01-18 | 2 | 2027-01-20 | 237
HVAC Ducting and Instrumentation Diagrams |  | 2026-02-20 | 2026-02-20 | 17-Jun-25 A | 14-Oct-25 A | 2026-11-02 | 114 | 2027-01-20
A52790 | HVAC Ducting and Instrumentation Diagrams_IFR | 2026-02-20 | 2026-02-20 | 17-Jun-25 A | 08-Jul-25 A | 2026-11-02 | 6 | 2026-11-02
A52800 | HVAC Ducting and Instrumentation Diagrams_RCC | 2026-02-20 | 2026-02-20 | 09-Jul-25 A | 15-Aug-25 A | 2027-01-20 | 16 | 2027-01-20
A52810 | HVAC Ducting and Instrumentation Diagrams_IFH | 2026-02-20 | 2026-02-20 | 18-Aug-25 A | 22-Aug-25 A | 2027-01-20 | 3 | 2027-01-20
A52820 | HVAC Ducting and Instrumentation Diagrams_RCA | 2026-02-20 | 2026-02-20 | 29-Aug-25 A | 07-Oct-25 A | 2027-01-20 | 16 | 2027-01-20
A52830 | HVAC Ducting and Instrumentation Diagrams_IFD/IFC | 2026-02-20 | 2026-02-20 | 08-Oct-25 A | 14-Oct-25 A | 2027-01-20 | 2 | 2027-01-20
HVAC Equipment Schedules |  | 2026-02-20 | 2026-03-23 | 09-Jun-25 A | 2026-03-23 | 2026-12-22 | 131 | 2027-01-20 | 218
A52890 | HVAC Equipment Schedules_IFR | 2026-02-20 | 2026-02-20 | 09-Jun-25 A | 12-Jul-25 A | 2026-12-22 | 6 | 2026-12-22
A52900 | HVAC Equipment Schedules_RCC | 2026-02-20 | 2026-02-20 | 17-Jun-25 A | 19-Jul-25 A | 2026-12-22 | 16 | 2026-12-22
A52910 | HVAC Equipment Schedules_IFA | 2026-02-20 | 2026-02-25 | 2026-02-20 | 2026-02-25 | 2026-12-22 | 3 | 2026-12-25 | 218
A52920 | HVAC Equipment Schedules_RCA | 2026-02-25 | 2026-03-19 | 2026-02-25 | 2026-03-19 | 2026-12-28 | 16 | 2027-01-18 | 218
A52930 | HVAC Equipment Schedules_IFD/IFC | 2026-03-19 | 2026-03-23 | 2026-03-19 | 2026-03-23 | 2027-01-18 | 2 | 2027-01-20 | 218
HVAC System Cause & Effect |  | 2026-02-20 | 2026-02-20 | 21-Nov-25 A | 13-Jan-26 A | 2027-01-20 | 38 | 2027-01-20
A52990 | HVAC System Cause & Effect_IFR | 2026-02-20 | 2026-02-20 | 21-Nov-25 A | 28-Nov-25 A | 2027-01-20 | 6 | 2027-01-20
A53000 | HVAC System Cause & Effect_RCC | 2026-02-20 | 2026-02-20 | 27-Nov-25 A | 18-Dec-25 A | 2027-01-20 | 16 | 2027-01-20
A53010 | HVAC System Cause & Effect_IFA | 2026-02-20 | 2026-02-20 | 18-Dec-25 A | 19-Dec-25 A | 2027-01-20 | 3 | 2027-01-20
A53020 | HVAC System Cause & Effect_RCA | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 09-Jan-26 A | 2027-01-20 | 16 | 2027-01-20
A53030 | HVAC System Cause & Effect_IFD/IFC | 2026-02-20 | 2026-02-20 | 09-Jan-26 A | 13-Jan-26 A | 2027-01-20 | 2 | 2027-01-20
HVAC Chilled Water Pump Head Calculation |  | 2026-02-20 | 2026-02-20 | 01-Oct-25 A | 10-Nov-25 A | 2027-01-20 | 61 | 2027-01-20
A53090 | HVAC Chilled Water Pump Head Calculation_IFR | 2026-02-20 | 2026-02-20 | 01-Oct-25 A | 13-Oct-25 A | 2027-01-20 | 6 | 2027-01-20
A53100 | HVAC Chilled Water Pump Head Calculation_RCC | 2026-02-20 | 2026-02-20 | 14-Oct-25 A | 25-Oct-25 A | 2027-01-20 | 16 | 2027-01-20
A53110 | HVAC Chilled Water Pump Head Calculation_IFA | 2026-02-20 | 2026-02-20 | 24-Oct-25 A | 28-Oct-25 A | 2027-01-20 | 3 | 2027-01-20
A53120 | HVAC Chilled Water Pump Head Calculation_RCA | 2026-02-20 | 2026-02-20 | 28-Oct-25 A | 31-Oct-25 A | 2027-01-20 | 16 | 2027-01-20
A53130 | HVAC Chilled Water Pump Head Calculation_IFD/IFC | 2026-02-20 | 2026-02-20 | 01-Nov-25 A | 10-Nov-25 A | 2027-01-20 | 2 | 2027-01-20
HVAC Technical Data Sheet For Air Handling Unit |  | 2026-02-20 | 2026-02-20 | 01-May-25 A | 10-Oct-25 A | 2026-03-19 | 102 | 2026-03-19
A52240 | HVAC Technical Data Sheet For Air Handling Unit_IFR | 2026-02-20 | 2026-02-20 | 01-May-25 A | 22-May-25 A | 2026-03-19 | 2 | 2026-03-19
A52250 | HVAC Technical Data Sheet For Air Handling Unit_RCC | 2026-02-20 | 2026-02-20 | 23-May-25 A | 10-Jun-25 A | 2026-03-19 | 16 | 2026-03-19
A52260 | HVAC Technical Data Sheet For Air Handling Unit_IFA | 2026-02-20 | 2026-02-20 | 11-Jun-25 A | 26-Jun-25 A | 2026-03-19 | 3 | 2026-03-19
A52270 | HVAC Technical Data Sheet For Air Handling Unit_RCA | 2026-02-20 | 2026-02-20 | 27-Jun-25 A | 10-Sep-25 A | 2026-03-19 | 16 | 2026-03-19
A52280 | HVAC Technical Data Sheet For Air Handling Unit_IFD/IFC | 2026-02-20 | 2026-02-20 | 15-Sep-25 A | 10-Oct-25 A | 2026-03-19 | 2 | 2026-03-19
HVAC Technical Data Sheet For Air Cooled Chiller |  | 2026-02-20 | 2026-02-20 | 26-May-25 A | 10-Jun-25 A | 2026-03-19 | 53 | 2026-03-19
A24230 | HVAC Technical Data Sheet For Air Cooled Chiller_IFR | 2026-02-20 | 2026-02-20 | 26-May-25 A | 28-May-25 A | 2026-03-19 | 2 | 2026-03-19
A24240 | HVAC Technical Data Sheet For Air Cooled Chiller_RCC | 2026-02-20 | 2026-02-20 | 29-May-25 A | 31-May-25 A | 2026-03-19 | 16 | 2026-03-19
A24250 | HVAC Technical Data Sheet For Air Cooled Chiller_IFA | 2026-02-20 | 2026-02-20 | 01-Jun-25 A | 04-Jun-25 A | 2026-03-19 | 3 | 2026-03-19
A24260 | HVAC Technical Data Sheet For Air Cooled Chiller_RCA | 2026-02-20 | 2026-02-20 | 05-Jun-25 A | 07-Jun-25 A | 2026-03-19 | 16 | 2026-03-19
A52230 | HVAC Technical Data Sheet For Air Cooled Chiller_IFD/IFC | 2026-02-20 | 2026-02-20 | 08-Jun-25 A | 10-Jun-25 A | 2026-03-19 | 2 | 2026-03-19
HVAC Technical Data Sheet For Chilled Water Pump |  | 2026-02-20 | 2026-02-20 | 26-May-25 A | 10-Oct-25 A | 2026-03-19 | 84 | 2026-03-19
A52290 | HVAC Technical Data Sheet For Chilled Water Pump_IFR | 2026-02-20 | 2026-02-20 | 26-May-25 A | 05-Jul-25 A | 2026-03-19 | 2 | 2026-03-19
A52300 | HVAC Technical Data Sheet For Chilled Water Pump_RCC | 2026-02-20 | 2026-02-20 | 06-Jul-25 A | 01-Aug-25 A | 2026-03-19 | 16 | 2026-03-19
A52310 | HVAC Technical Data Sheet For Chilled Water Pump_IFA | 2026-02-20 | 2026-02-20 | 02-Aug-25 A | 27-Aug-25 A | 2026-03-19 | 3 | 2026-03-19
A52320 | HVAC Technical Data Sheet For Chilled Water Pump_RCA | 2026-02-20 | 2026-02-20 | 28-Aug-25 A | 10-Sep-25 A | 2026-03-19 | 16 | 2026-03-19
A52330 | HVAC Technical Data Sheet For Chilled Water Pump_IFD/IFC | 2026-02-20 | 2026-02-20 | 15-Sep-25 A | 10-Oct-25 A | 2026-03-19 | 2 | 2026-03-19
HVAC Technical Data Sheet For Chemical Filter Unit |  | 2026-02-20 | 2026-02-20 | 26-May-25 A | 10-Oct-25 A | 2026-03-19 | 82 | 2026-03-19
A52340 | HVAC Technical Data Sheet For Chemical Filter Unit_IFR | 2026-02-20 | 2026-02-20 | 26-May-25 A | 05-Jul-25 A | 2026-03-19 | 2 | 2026-03-19
A52350 | HVAC Technical Data Sheet For Chemical Filter Unit_RCC | 2026-02-20 | 2026-02-20 | 06-Jul-25 A | 01-Aug-25 A | 2026-03-19 | 16 | 2026-03-19
A52360 | HVAC Technical Data Sheet For Chemical Filter Unit_IFA | 2026-02-20 | 2026-02-20 | 02-Aug-25 A | 29-Aug-25 A | 2026-03-19 | 3 | 2026-03-19
A52370 | HVAC Technical Data Sheet For Chemical Filter Unit_RCA | 2026-02-20 | 2026-02-20 | 30-Aug-25 A | 12-Sep-25 A | 2026-03-19 | 16 | 2026-03-19
A52380 | HVAC Technical Data Sheet For Chemical Filter Unit_IFD/IFC | 2026-02-20 | 2026-02-20 | 15-Sep-25 A | 10-Oct-25 A | 2026-03-19 | 2 | 2026-03-19
HVAC Technical Data Sheet For Inertia Filter With Bleed Fan |  | 2026-02-20 | 2026-02-20 | 26-May-25 A | 21-Nov-25 A | 2026-03-19 | 100 | 2026-03-19
A52390 | HVAC Technical Data Sheet For Inertia Filter With Bleed Fan_IFR | 2026-02-20 | 2026-02-20 | 26-May-25 A | 05-Jul-25 A | 2026-03-19 | 2 | 2026-03-19
A52400 | HVAC Technical Data Sheet For Inertia Filter With Bleed Fan_RCC | 2026-02-20 | 2026-02-20 | 06-Jul-25 A | 30-Jul-25 A | 2026-03-19 | 16 | 2026-03-19
A52410 | HVAC Technical Data Sheet For Inertia Filter With Bleed Fan_IFA | 2026-02-20 | 2026-02-20 | 31-Jul-25 A | 22-Aug-25 A | 2026-03-19 | 3 | 2026-03-19
A52420 | HVAC Technical Data Sheet For Inertia Filter With Bleed Fan_RCA | 2026-02-20 | 2026-02-20 | 23-Aug-25 A | 10-Sep-25 A | 2026-03-19 | 16 | 2026-03-19
A52430 | HVAC Technical Data Sheet For Inertia Filter With Bleed Fan_IFD/IFC | 2026-02-20 | 2026-02-20 | 17-Nov-25 A | 21-Nov-25 A | 2026-03-19 | 2 | 2026-03-19
HVAC Technical Data Sheet For Exhaust Air Fans |  | 2026-02-20 | 2026-02-20 | 26-May-25 A | 15-Sep-25 A | 2026-03-19 | 65 | 2026-03-19
A52440 | HVAC Technical Data Sheet For Exhaust Air Fans_IFR | 2026-02-20 | 2026-02-20 | 26-May-25 A | 05-Jul-25 A | 2026-03-19 | 2 | 2026-03-19
A52450 | HVAC Technical Data Sheet For Exhaust Air Fans_RCC | 2026-02-20 | 2026-02-20 | 06-Jul-25 A | 01-Aug-25 A | 2026-03-19 | 16 | 2026-03-19
A52460 | HVAC Technical Data Sheet For Exhaust Air Fans_IFA | 2026-02-20 | 2026-02-20 | 02-Aug-25 A | 01-Sep-25 A | 2026-03-19 | 3 | 2026-03-19
A52470 | HVAC Technical Data Sheet For Exhaust Air Fans_RCA | 2026-02-20 | 2026-02-20 | 02-Sep-25 A | 08-Sep-25 A | 2026-03-19 | 16 | 2026-03-19
A52480 | HVAC Technical Data Sheet For Exhaust Air Fans_IFD/IFC | 2026-02-20 | 2026-02-20 | 09-Sep-25 A | 15-Sep-25 A | 2026-03-19 | 2 | 2026-03-19
HVAC Technical Data Sheet For Electric Duct Heater |  | 2026-02-20 | 2026-02-20 | 26-May-25 A | 15-Sep-25 A | 2026-03-19 | 46 | 2026-03-19
A52490 | HVAC Technical Data Sheet For Electric Duct Heater_IFR | 2026-02-20 | 2026-02-20 | 26-May-25 A | 01-Jun-25 A | 2026-03-19 | 2 | 2026-03-19
A52500 | HVAC Technical Data Sheet For Electric Duct Heater_RCC | 2026-02-20 | 2026-02-20 | 02-Jun-25 A | 15-Jun-25 A | 2026-03-19 | 16 | 2026-03-19
A52510 | HVAC Technical Data Sheet For Electric Duct Heater_IFA | 2026-02-20 | 2026-02-20 | 16-Jun-25 A | 20-Jun-25 A | 2026-03-19 | 3 | 2026-03-19
A52520 | HVAC Technical Data Sheet For Electric Duct Heater_RCA | 2026-02-20 | 2026-02-20 | 21-Jun-25 A | 08-Sep-25 A | 2026-03-19 | 16 | 2026-03-19
A52530 | HVAC Technical Data Sheet For Electric Duct Heater_IFD/IFC | 2026-02-20 | 2026-02-20 | 09-Sep-25 A | 15-Sep-25 A | 2026-03-19 | 2 | 2026-03-19
HVAC Chilled Water Piping Layouts & Sections |  | 2026-02-20 | 2026-02-20 | 10-Jul-25 A | 13-Jan-26 A | 2027-01-20 | 101 | 2027-01-20
A52740 | HVAC Chilled Water Piping Layouts & Sections_IFR | 2026-02-20 | 2026-02-20 | 10-Jul-25 A | 07-Oct-25 A | 2027-01-20 | 6 | 2027-01-20
A52750 | HVAC Chilled Water Piping Layouts & Sections_RCC | 2026-02-20 | 2026-02-20 | 08-Oct-25 A | 31-Oct-25 A | 2027-01-20 | 16 | 2027-01-20
A52760 | HVAC Chilled Water Piping Layouts & Sections_IFA | 2026-02-20 | 2026-02-20 | 28-Nov-25 A | 10-Dec-25 A | 2027-01-20 | 3 | 2027-01-20
A52770 | HVAC Chilled Water Piping Layouts & Sections_RCA | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 09-Jan-26 A | 2027-01-20 | 16 | 2027-01-20
A52780 | HVAC Chilled Water Piping Layouts & Sections_IFD/IFC | 2026-02-20 | 2026-02-20 | 09-Jan-26 A | 13-Jan-26 A | 2027-01-20 | 2 | 2027-01-20
HVAC System Sequence Of Operation And Control Philosophy |  | 2026-02-20 | 2026-02-20 | 01-Jul-25 A | 04-Dec-25 A | 2027-01-20 | 110 | 2027-01-20
A52940 | HVAC System Sequence Of Operation And Control Philosophy_IFR | 2026-02-20 | 2026-02-20 | 01-Jul-25 A | 16-Jul-25 A | 2027-01-20 | 6 | 2027-01-20
A52950 | HVAC System Sequence Of Operation And Control Philosophy_RCC | 2026-02-20 | 2026-02-20 | 17-Jul-25 A | 22-Aug-25 A | 2027-01-20 | 16 | 2027-01-20
A52960 | HVAC System Sequence Of Operation And Control Philosophy_IFA | 2026-02-20 | 2026-02-20 | 01-Oct-25 A | 28-Oct-25 A | 2027-01-20 | 3 | 2027-01-20
A52970 | HVAC System Sequence Of Operation And Control Philosophy_RCA | 2026-02-20 | 2026-02-20 | 29-Oct-25 A | 17-Nov-25 A | 2027-01-20 | 16 | 2027-01-20
A52980 | HVAC System Sequence Of Operation And Control Philosophy_IFD/IFC | 2026-02-20 | 2026-02-20 | 24-Nov-25 A | 04-Dec-25 A | 2027-01-20 | 2 | 2027-01-20
Material Requisition For HVAC Equipments |  | 2026-02-20 | 2026-02-20 | 02-Jun-25 A | 19-Nov-25 A | 2026-03-19 | 97 | 2026-03-19
A53190 | Material Requisition For HVAC Equipments_IFR | 2026-02-20 | 2026-02-20 | 02-Jun-25 A | 05-Jul-25 A | 2026-03-19 | 6 | 2026-03-19
A53200 | Material Requisition For HVAC Equipments_RCC | 2026-02-20 | 2026-02-20 | 04-Jul-25 A | 30-Jul-25 A | 2026-03-19 | 16 | 2026-03-19
A53210 | Material Requisition For HVAC Equipments_IFA | 2026-02-20 | 2026-02-20 | 29-Aug-25 A | 01-Oct-25 A | 2026-03-19 | 3 | 2026-03-19
A53220 | Material Requisition For HVAC Equipments_RCA | 2026-02-20 | 2026-02-20 | 01-Oct-25 A | 24-Oct-25 A | 2026-03-19 | 16 | 2026-03-19
A53230 | Material Requisition For HVAC Equipments_IFD/IFC | 2026-02-20 | 2026-02-20 | 27-Oct-25 A | 19-Nov-25 A | 2026-03-19 | 2 | 2026-03-19
Material Requisition for Fire Detection System & LFCP |  | 2026-02-20 | 2026-02-20 | 09-Jun-25 A | 25-Dec-25 A | 2026-03-19 | 137 | 2026-03-19
A47780 | Material Requisition for Fire Detection System & LFCP_IFR | 2026-02-20 | 2026-02-20 | 09-Jun-25 A | 05-Jul-25 A | 2026-03-19 | 2 | 2026-03-19
A47790 | Material Requisition for Fire Detection System & LFCP_RCC | 2026-02-20 | 2026-02-20 | 07-Jul-25 A | 30-Jul-25 A | 2026-03-19 | 16 | 2026-03-19
A47800 | Material Requisition for Fire Detection System & LFCP_IFA | 2026-02-20 | 2026-02-20 | 31-Jul-25 A | 26-Aug-25 A | 2026-03-19 | 3 | 2026-03-19
A47810 | Material Requisition for Fire Detection System & LFCP_RCA | 2026-02-20 | 2026-02-20 | 15-Aug-25 A | 10-Sep-25 A | 2026-03-19 | 16 | 2026-03-19
A15420 | Material Requisition for Fire Detection System & LFCP_IFD/IFC | 2026-02-20 | 2026-02-20 | 23-Dec-25 A | 25-Dec-25 A | 2026-03-19 | 2 | 2026-03-19
HVAC Equipment And Ducting Layouts |  | 2026-02-20 | 2026-02-20 | 29-Jun-25 A | 18-Dec-25 A | 2026-11-02 | 94 | 2026-11-02
A52640 | HVAC Equipment And Ducting Layouts_IFR | 2026-02-20 | 2026-02-20 | 29-Jun-25 A | 18-Jul-25 A | 2026-11-02 | 6 | 2026-11-02
A52650 | HVAC Equipment And Ducting Layouts_RCC | 2026-02-20 | 2026-02-20 | 01-Aug-25 A | 14-Oct-25 A | 2026-11-02 | 16 | 2026-11-02
A52660 | HVAC Equipment And Ducting Layouts_IFA | 2026-02-20 | 2026-02-20 | 01-Oct-25 A | 24-Oct-25 A | 2026-11-02 | 3 | 2026-11-02
A52670 | HVAC Equipment And Ducting Layouts_RCA | 2026-02-20 | 2026-02-20 | 27-Oct-25 A | 21-Nov-25 A | 2026-11-02 | 16 | 2026-11-02
A52680 | HVAC Equipment And Ducting Layouts_IFD/IFC | 2026-02-20 | 2026-02-20 | 02-Dec-25 A | 18-Dec-25 A | 2026-11-02 | 2 | 2026-11-02
HVAC Ducting Section Layout |  | 2026-02-20 | 2026-02-20 | 03-Aug-25 A | 23-Dec-25 A | 2027-01-20 | 95 | 2027-01-20
A52690 | HVAC Ducting Section Layout_IFR | 2026-02-20 | 2026-02-20 | 03-Aug-25 A | 18-Aug-25 A | 2027-01-20 | 6 | 2027-01-20
A52700 | HVAC Ducting Section Layout_RCC | 2026-02-20 | 2026-02-20 | 19-Aug-25 A | 22-Aug-25 A | 2027-01-20 | 16 | 2027-01-20
A52710 | HVAC Ducting Section Layout_IFA | 2026-02-20 | 2026-02-20 | 25-Aug-25 A | 26-Sep-25 A | 2027-01-20 | 3 | 2027-01-20
A52720 | HVAC Ducting Section Layout_RCA | 2026-02-20 | 2026-02-20 | 15-Sep-25 A | 14-Oct-25 A | 2027-01-20 | 16 | 2027-01-20
A52730 | HVAC Ducting Section Layout_IFD/IFC | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 23-Dec-25 A | 2027-01-20 | 2 | 2027-01-20
HVAC External Static Pressure Calculation |  | 2026-02-20 | 2026-04-21 | 2026-02-20 | 2026-04-21 | 2026-11-23 | 43 | 2027-01-20 | 196
A53040 | HVAC External Static Pressure Calculation_IFR | 2026-02-20 | 2026-02-27 | 2026-02-20 | 2026-02-27 | 2026-11-23 | 6 | 2026-11-30 | 196
A53050 | HVAC External Static Pressure Calculation_RCC | 2026-02-27 | 2026-03-23 | 2026-02-27 | 2026-03-23 | 2026-11-30 | 16 | 2026-12-22 | 196
A53060 | HVAC External Static Pressure Calculation_IFA | 2026-03-23 | 2026-03-26 | 2026-03-23 | 2026-03-26 | 2026-12-22 | 3 | 2026-12-25 | 196
A53070 | HVAC External Static Pressure Calculation_RCA | 2026-03-26 | 2026-04-17 | 2026-03-26 | 2026-04-17 | 2026-12-28 | 16 | 2027-01-18 | 196
A53080 | HVAC External Static Pressure Calculation_IFD/IFC | 2026-04-17 | 2026-04-21 | 2026-04-17 | 2026-04-21 | 2027-01-18 | 2 | 2027-01-20 | 196
HVAC Standard Installation Details |  | 2026-02-20 | 2026-02-20 | 25-Apr-25 A | 07-Oct-25 A | 2027-01-20 | 121 | 2027-01-20
A53140 | HVAC Standard Installation Details_IFR | 2026-02-20 | 2026-02-20 | 25-Apr-25 A | 16-May-25 A | 2027-01-20 | 6 | 2027-01-20
A53150 | HVAC Standard Installation Details_RCC | 2026-02-20 | 2026-02-20 | 17-May-25 A | 10-Jun-25 A | 2027-01-20 | 16 | 2027-01-20
A53160 | HVAC Standard Installation Details_IFA | 2026-02-20 | 2026-02-20 | 11-Jun-25 A | 20-Jun-25 A | 2027-01-20 | 3 | 2027-01-20
A53170 | HVAC Standard Installation Details_RCA | 2026-02-20 | 2026-02-20 | 13-Jun-25 A | 30-Jun-25 A | 2027-01-20 | 16 | 2027-01-20
A53180 | HVAC Standard Installation Details_IFD/IFC | 2026-02-20 | 2026-02-20 | 30-Jul-25 A | 07-Oct-25 A | 2027-01-20 | 2 | 2027-01-20
Technical Bid Evaluation for Fire Detection System & LFCP |  | 2026-02-20 | 2026-02-20 | 01-Oct-25 A | 19-Jan-26 A | 2026-03-19 | 61 | 2027-01-20
A48260 | Technical Bid Evaluation for Fire Detection System & LFCP_IFR | 2026-02-20 | 2026-02-20 | 01-Oct-25 A | 09-Oct-25 A | 2026-03-19 | 6 | 2026-03-19
A16940 | Technical Bid Evaluation for Fire Detection System & LFCP_RCC | 2026-02-20 | 2026-02-20 | 20-Oct-25 A | 06-Nov-25 A | 2026-03-19 | 11 | 2026-03-19
A16950 | Technical Bid Evaluation for Fire Detection System & LFCP_IFA | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 24-Dec-25 A | 2026-03-19 | 3 | 2026-03-19
A16960 | Technical Bid Evaluation for Fire Detection System & LFCP_RCA | 2026-02-20 | 2026-02-20 | 24-Dec-25 A | 15-Jan-26 A | 2027-01-20 | 16 | 2027-01-20
A16970 | Technical Bid Evaluation for Fire Detection System & LFCP_IFD/IFC | 2026-02-20 | 2026-02-20 | 15-Jan-26 A | 19-Jan-26 A | 2027-01-20 | 2 | 2027-01-20
Procurement - HO Services |  | 2026-02-20 | 2026-07-24 | 01-Jan-25 A | 2026-07-24 | 2026-02-23 | 399 | 2027-07-20 | 257
Equipment Packages |  | 2026-02-20 | 2026-02-20 | 01-Jan-25 A | 15-Oct-25 A | 2026-03-19 | 210 | 2026-07-15
Vessels |  | 2026-02-20 | 2026-02-20 | 01-Jan-25 A | 20-Jun-25 A | 2026-03-19 | 210 | 2026-07-15
C4 Guard Adsorber Cooler - (BF) |  | 2026-02-20 | 2026-02-20 | 01-Jan-25 A | 20-Jun-25 A | 2026-03-19 | 68 | 2026-07-15
A8310 | Issue RFQ to Bidders | 2026-02-20 | 2026-02-20 | 01-Jan-25 A | 14-Jan-25 A | 2026-03-19 | 20 | 2026-03-19
A57190 | Technical Bid Evaluation for Pressure Vessels & Internals_IFR | 2026-02-20 | 2026-02-20 | 28-Apr-25 A | 03-May-25 A | 2026-03-19 | 6 | 2026-03-19
A57200 | Technical Bid Evaluation for Pressure Vessels & Internals_RCC | 2026-02-20 | 2026-02-20 | 04-May-25 A | 03-Jun-25 A | 2026-03-19 | 16 | 2026-03-19
A57210 | Technical Bid Evaluation for Pressure Vessels & Internals_IFA | 2026-02-20 | 2026-02-20 | 04-Jun-25 A | 08-Jun-25 A | 2026-03-19 | 3 | 2026-03-19
A57220 | Technical Bid Evaluation for Pressure Vessels & Internals_RCA | 2026-02-20 | 2026-02-20 | 09-Jun-25 A | 14-Jun-25 A | 2026-07-15 | 16 | 2026-07-15
A8340 | Issue Purchase Order to Vendor | 2026-02-20 | 2026-02-20 | 20-Jun-25 A | 20-Jun-25 A | 2026-07-15 | 30 | 2026-07-15
A57230 | Technical Bid Evaluation for Pressure Vessels & Internals_IFD/IFC | 2026-02-20 | 2026-02-20 | 15-Jun-25 A | 20-Jun-25 A | 2026-07-15 | 11 | 2026-07-15
Vessel's Internals (05 Dimister pads) |  | 2026-02-20 | 2026-02-20 | 01-Jan-25 A | 20-Jun-25 A | 2026-03-19 | 106 | 2026-05-14
A15970 | Issue RFQ to Bidders | 2026-02-20 | 2026-02-20 | 01-Jan-25 A | 14-Jan-25 A | 2026-03-19 | 20 | 2026-03-19
A56540 | Technical Bid Evaluation for Pressure Vessels & Internals_IFR | 2026-02-20 | 2026-02-20 | 28-Apr-25 A | 03-May-25 A | 2026-03-19 | 11 | 2026-03-19
A56550 | Technical Bid Evaluation for Pressure Vessels & Internals_RCC | 2026-02-20 | 2026-02-20 | 04-May-25 A | 03-Jun-25 A | 2026-03-19 | 16 | 2026-03-19
A56560 | Technical Bid Evaluation for Pressure Vessels & Internals_IFA | 2026-02-20 | 2026-02-20 | 04-Jun-25 A | 08-Jun-25 A | 2026-03-19 | 11 | 2026-03-19
A56570 | Technical Bid Evaluation for Pressure Vessels & Internals_RCA | 2026-02-20 | 2026-02-20 | 09-Jun-25 A | 14-Jun-25 A | 2026-05-14 | 16 | 2026-05-14
A56580 | Technical Bid Evaluation for Pressure Vessels & Internals_IFD/IFC | 2026-02-20 | 2026-02-20 | 09-Jun-25 A | 14-Jun-25 A | 2026-05-14 | 8 | 2026-05-14
A18020 | Issue Purchase Order to Vendor | 2026-02-20 | 2026-02-20 | 20-Jun-25 A | 20-Jun-25 A | 2026-05-14 | 21 | 2026-05-14
A18040 | Commercial Bid Evaluation(Completion) | 2026-02-20 | 2026-02-20 | 15-Jun-25 A | 20-Jun-25 A | 2026-05-14 | 30 | 2026-05-14
Vessels/Drums |  | 2026-02-20 | 2026-02-20 | 01-Jan-25 A | 20-Jun-25 A | 2026-03-19 | 124 | 2026-05-26
FG Comp. 2nd Stage Suc. Drum (13-VV-706) |  | 2026-02-20 | 2026-02-20 | 01-Jan-25 A | 20-Jun-25 A | 2026-03-19 | 104 | 2026-04-17
A35900 | Issue RFQ to Bidders | 2026-02-20 | 2026-02-20 | 01-Jan-25 A | 14-Jan-25 A | 2026-03-19 | 15 | 2026-03-19
A45970 | Technical Bid Evaluation for Pressure Vessels & Internals_RCC | 2026-02-20 | 2026-02-20 | 25-Mar-25 A | 27-Mar-25 A | 2026-03-19 | 16 | 2026-03-19
A45980 | Technical Bid Evaluation for Pressure Vessels & Internals_IFA | 2026-02-20 | 2026-02-20 | 28-Mar-25 A | 29-Mar-25 A | 2026-03-19 | 11 | 2026-03-19
A45990 | Technical Bid Evaluation for Pressure Vessels & Internals_RCA | 2026-02-20 | 2026-02-20 | 30-Mar-25 A | 31-Mar-25 A | 2026-04-17 | 16 | 2026-04-17
A46000 | Technical Bid Evaluation for Pressure Vessels & Internals_IFD/IFC | 2026-02-20 | 2026-02-20 | 31-Mar-25 A | 01-Apr-25 A | 2026-04-17 | 8 | 2026-04-17
A45960 | Technical Bid Evaluation for Pressure Vessels & Internals_IFR | 2026-02-20 | 2026-02-20 | 28-Apr-25 A | 03-May-25 A | 2026-03-19 | 11 | 2026-03-19
A35930 | Issue Purchase Order to Vendor | 2026-02-20 | 2026-02-20 | 20-Jun-25 A | 20-Jun-25 A | 2026-04-17 | 10 | 2026-04-17
A35920 | Commercial Bid Evaluation(Completion) | 2026-02-20 | 2026-02-20 | 15-Jun-25 A | 20-Jun-25 A | 2026-04-17 | 21 | 2026-04-17
FG Comp.1st Stage Suc. Drum (13-VV-705) |  | 2026-02-20 | 2026-02-20 | 01-Jan-25 A | 07-Apr-25 A | 2026-03-19 | 104 | 2026-04-17
A17540 | Issue RFQ to Bidders | 2026-02-20 | 2026-02-20 | 01-Jan-25 A | 14-Jan-25 A | 2026-03-19 | 15 | 2026-03-19
A56290 | Technical Bid Evaluation for Pressure Vessels & Internals_IFR | 2026-02-20 | 2026-02-20 | 23-Mar-25 A | 24-Mar-25 A | 2026-03-19 | 11 | 2026-03-19
A56300 | Technical Bid Evaluation for Pressure Vessels & Internals_RCC | 2026-02-20 | 2026-02-20 | 25-Mar-25 A | 27-Mar-25 A | 2026-03-19 | 16 | 2026-03-19
A56310 | Technical Bid Evaluation for Pressure Vessels & Internals_IFA | 2026-02-20 | 2026-02-20 | 28-Mar-25 A | 29-Mar-25 A | 2026-03-19 | 11 | 2026-03-19
A56320 | Technical Bid Evaluation for Pressure Vessels & Internals_RCA | 2026-02-20 | 2026-02-20 | 30-Mar-25 A | 31-Mar-25 A | 2026-04-17 | 16 | 2026-04-17
A56330 | Technical Bid Evaluation for Pressure Vessels & Internals_IFD/IFC | 2026-02-20 | 2026-02-20 | 01-Apr-25 A | 02-Apr-25 A | 2026-04-17 | 8 | 2026-04-17
A9220 | Commercial Bid Evaluation(Completion) | 2026-02-20 | 2026-02-20 | 03-Apr-25 A | 04-Apr-25 A | 2026-04-17 | 21 | 2026-04-17
A9200 | Issue Purchase Order to Vendor | 2026-02-20 | 2026-02-20 | 04-Apr-25 A | 07-Apr-25 A | 2026-04-17 | 10 | 2026-04-17
PSA2 Slop Drum (70-VV-1415) |  | 2026-02-20 | 2026-02-20 | 01-Jan-25 A | 12-Apr-25 A | 2026-03-19 | 124 | 2026-05-26
A35940 | Issue RFQ to Bidders | 2026-02-20 | 2026-02-20 | 01-Jan-25 A | 14-Jan-25 A | 2026-03-19 | 15 | 2026-03-19
A56340 | Technical Bid Evaluation for Pressure Vessels & Internals_IFR | 2026-02-20 | 2026-02-20 | 23-Mar-25 A | 24-Mar-25 A | 2026-03-19 | 11 | 2026-03-19
A56350 | Technical Bid Evaluation for Pressure Vessels & Internals_RCC | 2026-02-20 | 2026-02-20 | 25-Mar-25 A | 27-Mar-25 A | 2026-03-19 | 16 | 2026-03-19
A56360 | Technical Bid Evaluation for Pressure Vessels & Internals_IFA | 2026-02-20 | 2026-02-20 | 28-Mar-25 A | 29-Mar-25 A | 2026-03-19 | 11 | 2026-03-19
A56370 | Technical Bid Evaluation for Pressure Vessels & Internals_RCA | 2026-02-20 | 2026-02-20 | 30-Mar-25 A | 31-Mar-25 A | 2026-05-26 | 16 | 2026-05-26
A56380 | Technical Bid Evaluation for Pressure Vessels & Internals_IFD/IFC | 2026-02-20 | 2026-02-20 | 31-Mar-25 A | 01-Apr-25 A | 2026-05-26 | 8 | 2026-05-26
A35960 | Commercial Bid Evaluation(Completion) | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 03-Apr-25 A | 2026-05-26 | 30 | 2026-05-26
A35970 | Issue Purchase Order to Vendor | 2026-02-20 | 2026-02-20 | 04-Apr-25 A | 12-Apr-25 A | 2026-05-26 | 21 | 2026-05-26
OG Comp. 2nd Stage Suc. Drum (13-VV-713) |  | 2026-02-20 | 2026-02-20 | 01-Jan-25 A | 12-Apr-25 A | 2026-03-19 | 97 | 2026-04-22
A35980 | Issue RFQ to Bidders | 2026-02-20 | 2026-02-20 | 01-Jan-25 A | 14-Jan-25 A | 2026-03-19 | 15 | 2026-03-19
A56390 | Technical Bid Evaluation for Pressure Vessels & Internals_IFR | 2026-02-20 | 2026-02-20 | 23-Mar-25 A | 24-Mar-25 A | 2026-03-19 | 11 | 2026-03-19
A56400 | Technical Bid Evaluation for Pressure Vessels & Internals_RCC | 2026-02-20 | 2026-02-20 | 25-Mar-25 A | 27-Mar-25 A | 2026-03-19 | 16 | 2026-03-19
A56410 | Technical Bid Evaluation for Pressure Vessels & Internals_IFA | 2026-02-20 | 2026-02-20 | 28-Mar-25 A | 29-Mar-25 A | 2026-03-19 | 11 | 2026-03-19
A56420 | Technical Bid Evaluation for Pressure Vessels & Internals_RCA | 2026-02-20 | 2026-02-20 | 30-Mar-25 A | 31-Mar-25 A | 2026-04-22 | 16 | 2026-04-22
A56430 | Technical Bid Evaluation for Pressure Vessels & Internals_IFD/IFC | 2026-02-20 | 2026-02-20 | 31-Mar-25 A | 01-Apr-25 A | 2026-04-22 | 8 | 2026-04-22
A36000 | Commercial Bid Evaluation(Completion) | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 03-Apr-25 A | 2026-04-22 | 14 | 2026-04-22
A36010 | Issue Purchase Order to Vendor | 2026-02-20 | 2026-02-20 | 04-Apr-25 A | 12-Apr-25 A | 2026-04-22 | 10 | 2026-04-22
FG Comp. 2nd Stage Dis. Drum (13-VV-707) |  | 2026-02-20 | 2026-02-20 | 01-Jan-25 A | 12-Apr-25 A | 2026-03-19 | 100 | 2026-04-16
A36020 | Issue RFQ to Bidders | 2026-02-20 | 2026-02-20 | 01-Jan-25 A | 14-Jan-25 A | 2026-03-19 | 14 | 2026-03-19
A56440 | Technical Bid Evaluation for Pressure Vessels & Internals_IFR | 2026-02-20 | 2026-02-20 | 23-Mar-25 A | 24-Mar-25 A | 2026-03-19 | 11 | 2026-03-19
A56450 | Technical Bid Evaluation for Pressure Vessels & Internals_RCC | 2026-02-20 | 2026-02-20 | 25-Mar-25 A | 27-Mar-25 A | 2026-03-19 | 16 | 2026-03-19
A56460 | Technical Bid Evaluation for Pressure Vessels & Internals_IFA | 2026-02-20 | 2026-02-20 | 28-Mar-25 A | 29-Mar-25 A | 2026-03-19 | 11 | 2026-03-19
A56470 | Technical Bid Evaluation for Pressure Vessels & Internals_RCA | 2026-02-20 | 2026-02-20 | 30-Mar-25 A | 31-Mar-25 A | 2026-04-16 | 16 | 2026-04-16
A56480 | Technical Bid Evaluation for Pressure Vessels & Internals_IFD/IFC | 2026-02-20 | 2026-02-20 | 31-Mar-25 A | 01-Apr-25 A | 2026-04-16 | 8 | 2026-04-16
A36040 | Commercial Bid Evaluation(Completion) | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 03-Apr-25 A | 2026-04-16 | 14 | 2026-04-16
A36050 | Issue Purchase Order to Vendor | 2026-02-20 | 2026-02-20 | 04-Apr-25 A | 12-Apr-25 A | 2026-04-16 | 14 | 2026-04-16
OG Buffer Drum (13-VV-712) |  | 2026-02-20 | 2026-02-20 | 01-Jan-25 A | 12-Apr-25 A | 2026-03-19 | 108 | 2026-05-26
A36060 | Issue RFQ to Bidders | 2026-02-20 | 2026-02-20 | 01-Jan-25 A | 22-Mar-25 A | 2026-03-19 | 15 | 2026-03-19
A56490 | Technical Bid Evaluation for Pressure Vessels & Internals_IFR | 2026-02-20 | 2026-02-20 | 23-Mar-25 A | 24-Mar-25 A | 2026-03-19 | 11 | 2026-03-19
A56500 | Technical Bid Evaluation for Pressure Vessels & Internals_RCC | 2026-02-20 | 2026-02-20 | 25-Mar-25 A | 27-Mar-25 A | 2026-03-19 | 16 | 2026-03-19
A56510 | Technical Bid Evaluation for Pressure Vessels & Internals_IFA | 2026-02-20 | 2026-02-20 | 28-Mar-25 A | 29-Mar-25 A | 2026-03-19 | 11 | 2026-03-19
A56520 | Technical Bid Evaluation for Pressure Vessels & Internals_RCA | 2026-02-20 | 2026-02-20 | 30-Mar-25 A | 31-Mar-25 A | 2026-05-26 | 16 | 2026-05-26
A56530 | Technical Bid Evaluation for Pressure Vessels & Internals_IFD/IFC | 2026-02-20 | 2026-02-20 | 31-Mar-25 A | 01-Apr-25 A | 2026-05-26 | 8 | 2026-05-26
A36080 | Commercial Bid Evaluation(Completion) | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 03-Apr-25 A | 2026-05-26 | 21 | 2026-05-26
A36090 | Issue Purchase Order to Vendor | 2026-02-20 | 2026-02-20 | 04-Apr-25 A | 12-Apr-25 A | 2026-05-26 | 14 | 2026-05-26
Water Collection & Sanitary Wastewater Pumps |  | 2026-02-20 | 2026-02-20 | 01-Apr-25 A | 15-Oct-25 A | 2026-05-26 | 85 | 2026-05-26
Sanitary Waste Water Sump Pump |  | 2026-02-20 | 2026-02-20 | 01-Apr-25 A | 15-Oct-25 A | 2026-05-26 | 83 | 2026-05-26
A8430 | RFQs to Bid Receipt | 2026-02-20 | 2026-02-20 | 01-Apr-25 A | 10-Apr-25 A | 2026-05-26 | 21 | 2026-05-26
A45810 | Technical Bid Evaluation for Centrifugal Pump_IFR | 2026-02-20 | 2026-02-20 | 10-Jun-25 A | 12-Jun-25 A | 2026-05-26 | 3 | 2026-05-26
A45820 | Technical Bid Evaluation for Centrifugal Pump_RCC | 2026-02-20 | 2026-02-20 | 13-Jun-25 A | 18-Jun-25 A | 2026-05-26 | 3 | 2026-05-26
A45830 | Technical Bid Evaluation for Centrifugal Pump_IFA | 2026-02-20 | 2026-02-20 | 04-Jul-25 A | 23-Aug-25 A | 2026-05-26 | 7 | 2026-05-26
A45840 | Technical Bid Evaluation for Centrifugal Pump_RCA | 2026-02-20 | 2026-02-20 | 24-Aug-25 A | 30-Aug-25 A | 2026-05-26 | 3 | 2026-05-26
A19490 | Commercial Bid Evaluation(Completion) | 2026-02-20 | 2026-02-20 | 08-Sep-25 A | 12-Sep-25 A | 2026-05-26 | 3 | 2026-05-26
A19470 | Issue Purchase Order to Vendor | 2026-02-20 | 2026-02-20 | 15-Sep-25 A | 17-Sep-25 A | 2026-05-26 | 3 | 2026-05-26
A45850 | Technical Bid Evaluation for Centrifugal Pump_IFD/IFC | 2026-02-20 | 2026-02-20 | 01-Sep-25 A | 15-Oct-25 A | 2026-05-26 | 3 | 2026-05-26
Water Collection Sump Pump ll |  | 2026-02-20 | 2026-02-20 | 01-Apr-25 A | 05-Aug-25 A | 2026-05-26 | 37 | 2026-05-26
A8490 | RFQs to Bid Receipt | 2026-02-20 | 2026-02-20 | 01-Apr-25 A | 10-Apr-25 A | 2026-05-26 | 21 | 2026-05-26
A56890 | Technical Bid Evaluation for Centrifugal Pump_IFR | 2026-02-20 | 2026-02-20 | 10-Jun-25 A | 12-Jun-25 A | 2026-05-26 | 3 | 2026-05-26
A56900 | Technical Bid Evaluation for Centrifugal Pump_RCC | 2026-02-20 | 2026-02-20 | 13-Jun-25 A | 18-Jun-25 A | 2026-05-26 | 5 | 2026-05-26
A56910 | Technical Bid Evaluation for Centrifugal Pump_IFA | 2026-02-20 | 2026-02-20 | 19-Jun-25 A | 23-Jun-25 A | 2026-05-26 | 3 | 2026-05-26
A56920 | Technical Bid Evaluation for Centrifugal Pump_RCA | 2026-02-20 | 2026-02-20 | 24-Jun-25 A | 29-Jun-25 A | 2026-05-26 | 3 | 2026-05-26
A56930 | Technical Bid Evaluation for Centrifugal Pump_IFD/IFC | 2026-02-20 | 2026-02-20 | 30-Jun-25 A | 03-Jul-25 A | 2026-05-26 | 3 | 2026-05-26
A19430 | Commercial Bid Evaluation(Completion) | 2026-02-20 | 2026-02-20 | 18-Jul-25 A | 29-Jul-25 A | 2026-05-26 | 3 | 2026-05-26
A19410 | Issue Purchase Order to Vendor | 2026-02-20 | 2026-02-20 | 30-Jul-25 A | 05-Aug-25 A | 2026-05-26 | 3 | 2026-05-26
EOT Cranes |  | 2026-02-20 | 2026-02-20 | 01-May-25 A | 18-Sep-25 A | 2026-03-19 | 124 | 2026-04-28
EOT Crane for FG Compressor (1 = 60 Ton) |  | 2026-02-20 | 2026-02-20 | 01-May-25 A | 13-Aug-25 A | 2026-03-19 | 92 | 2026-04-21
A8370 | Issue RFQ to Bidders | 2026-02-20 | 2026-02-20 | 01-May-25 A | 15-May-25 A | 2026-03-19 | 21 | 2026-03-19
A45860 | Technical Bid Evaluation for EOT Crane_IFR | 2026-02-20 | 2026-02-20 | 20-Jun-25 A | 24-Jun-25 A | 2026-03-19 | 11 | 2026-03-19
A45870 | Technical Bid Evaluation for EOT Crane_RCC | 2026-02-20 | 2026-02-20 | 25-Jun-25 A | 30-Jun-25 A | 2026-03-19 | 5 | 2026-03-19
A45880 | Technical Bid Evaluation for EOT Crane_IFA | 2026-02-20 | 2026-02-20 | 30-Jun-25 A | 06-Jul-25 A | 2026-03-19 | 6 | 2026-03-19
A45890 | Technical Bid Evaluation for EOT Crane_RCA | 2026-02-20 | 2026-02-20 | 06-Jul-25 A | 12-Jul-25 A | 2026-04-21 | 6 | 2026-04-21
A45900 | Technical Bid Evaluation for EOT Crane_IFD/IFC | 2026-02-20 | 2026-02-20 | 13-Jul-25 A | 22-Jul-25 A | 2026-04-21 | 6 | 2026-04-21
A20490 | Commercial Bid Evaluation(Completion) | 2026-02-20 | 2026-02-20 | 23-Jul-25 A | 06-Aug-25 A | 2026-04-21 | 3 | 2026-04-21
A20470 | Issue Purchase Order to Vendor | 2026-02-20 | 2026-02-20 | 07-Aug-25 A | 13-Aug-25 A | 2026-04-21 | 10 | 2026-04-21
EOT Crane for OG Compressor (1 = 25 Ton) |  | 2026-02-20 | 2026-02-20 | 01-May-25 A | 18-Sep-25 A | 2026-03-19 | 98 | 2026-04-28
A8250 | Issue RFQ to Bidders | 2026-02-20 | 2026-02-20 | 01-May-25 A | 20-Jun-25 A | 2026-03-19 | 21 | 2026-03-19
A56940 | Technical Bid Evaluation for EOT Crane_IFR | 2026-02-20 | 2026-02-20 | 20-Jun-25 A | 15-Aug-25 A | 2026-03-19 | 11 | 2026-03-19
A56950 | Technical Bid Evaluation for EOT Crane_RCC | 2026-02-20 | 2026-02-20 | 16-Aug-25 A | 22-Aug-25 A | 2026-03-19 | 5 | 2026-03-19
A56960 | Technical Bid Evaluation for EOT Crane_IFA | 2026-02-20 | 2026-02-20 | 23-Aug-25 A | 30-Aug-25 A | 2026-03-19 | 6 | 2026-03-19
A56970 | Technical Bid Evaluation for EOT Crane_RCA | 2026-02-20 | 2026-02-20 | 01-Sep-25 A | 05-Sep-25 A | 2026-04-28 | 6 | 2026-04-28
A56980 | Technical Bid Evaluation for EOT Crane_IFD/IFC | 2026-02-20 | 2026-02-20 | 01-Sep-25 A | 12-Sep-25 A | 2026-04-28 | 6 | 2026-04-28
A20550 | Commercial Bid Evaluation(Completion) | 2026-02-20 | 2026-02-20 | 15-Sep-25 A | 17-Sep-25 A | 2026-04-28 | 3 | 2026-04-28
A20530 | Issue Purchase Order to Vendor | 2026-02-20 | 2026-02-20 | 17-Sep-25 A | 18-Sep-25 A | 2026-04-28 | 10 | 2026-04-28
Heat Exchangers |  | 2026-02-20 | 2026-02-20 | 01-Jun-25 A | 02-Jul-25 A | 2026-05-14 | 36 | 2026-05-26
Heat Exchanger (Type S & T = 06 Nos) |  | 2026-02-20 | 2026-02-20 | 01-Jun-25 A | 02-Jul-25 A | 2026-05-14 | 36 | 2026-05-26
FG Comp. Interstage Cooler (BEM) - Tag# 13-HE-703 |  | 2026-02-20 | 2026-02-20 | 01-Jun-25 A | 27-Jun-25 A | 2026-05-14 | 26 | 2026-05-14
A36100 | Issue RFQ to Bidders | 2026-02-20 | 2026-02-20 | 01-Jun-25 A | 03-Jun-25 A | 2026-05-14 | 6 | 2026-05-14
A45460 | Technical Bid Evaluation for Heat Exchangers_IFR | 2026-02-20 | 2026-02-20 | 04-Jun-25 A | 07-Jun-25 A | 2026-05-14 | 6 | 2026-05-14
A45470 | Technical Bid Evaluation for Heat Exchangers_RCC | 2026-02-20 | 2026-02-20 | 08-Jun-25 A | 11-Jun-25 A | 2026-05-14 | 5 | 2026-05-14
A45480 | Technical Bid Evaluation for Heat Exchangers_IFA | 2026-02-20 | 2026-02-20 | 12-Jun-25 A | 14-Jun-25 A | 2026-05-14 | 6 | 2026-05-14
A45490 | Technical Bid Evaluation for Heat Exchangers_RCA | 2026-02-20 | 2026-02-20 | 15-Jun-25 A | 17-Jun-25 A | 2026-05-14 | 6 | 2026-05-14
A45500 | Technical Bid Evaluation for Heat Exchangers_IFD/IFC | 2026-02-20 | 2026-02-20 | 18-Jun-25 A | 20-Jun-25 A | 2026-05-14 | 3 | 2026-05-14
A36120 | Commercial Bid Evaluation(Completion) | 2026-02-20 | 2026-02-20 | 20-Jun-25 A | 24-Jun-25 A | 2026-05-14 | 6 | 2026-05-14
A36130 | Issue Purchase Order to Vendor | 2026-02-20 | 2026-02-20 | 25-Jun-25 A | 27-Jun-25 A | 2026-05-14 | 3 | 2026-05-14
OG Comp. After Cooler (BEU) - Tag# 13-HE-709 |  | 2026-02-20 | 2026-02-20 | 01-Jun-25 A | 27-Jun-25 A | 2026-05-26 | 36 | 2026-05-26
A36140 | Issue RFQ to Bidders | 2026-02-20 | 2026-02-20 | 01-Jun-25 A | 03-Jun-25 A | 2026-05-26 | 21 | 2026-05-26
A56640 | Technical Bid Evaluation for Heat Exchangers_IFR | 2026-02-20 | 2026-02-20 | 04-Jun-25 A | 07-Jun-25 A | 2026-05-26 | 6 | 2026-05-26
A56650 | Technical Bid Evaluation for Heat Exchangers_RCC | 2026-02-20 | 2026-02-20 | 08-Jun-25 A | 11-Jun-25 A | 2026-05-26 | 5 | 2026-05-26
A56660 | Technical Bid Evaluation for Heat Exchangers_IFA | 2026-02-20 | 2026-02-20 | 12-Jun-25 A | 14-Jun-25 A | 2026-05-26 | 6 | 2026-05-26
A56670 | Technical Bid Evaluation for Heat Exchangers_RCA | 2026-02-20 | 2026-02-20 | 15-Jun-25 A | 17-Jun-25 A | 2026-05-26 | 6 | 2026-05-26
A56680 | Technical Bid Evaluation for Heat Exchangers_IFD/IFC | 2026-02-20 | 2026-02-20 | 18-Jun-25 A | 20-Jun-25 A | 2026-05-26 | 3 | 2026-05-26
A36160 | Commercial Bid Evaluation(Completion) | 2026-02-20 | 2026-02-20 | 20-Jun-25 A | 24-Jun-25 A | 2026-05-26 | 6 | 2026-05-26
A36170 | Issue Purchase Order to Vendor | 2026-02-20 | 2026-02-20 | 25-Jun-25 A | 27-Jun-25 A | 2026-05-26 | 3 | 2026-05-26
FG Comp. After Cooler (BEM) - Tag# 13-HE-704 |  | 2026-02-20 | 2026-02-20 | 01-Jun-25 A | 27-Jun-25 A | 2026-05-17 | 35 | 2026-05-17
A36950 | Issue RFQ to Bidders | 2026-02-20 | 2026-02-20 | 01-Jun-25 A | 03-Jun-25 A | 2026-05-17 | 20 | 2026-05-17
A56690 | Technical Bid Evaluation for Heat Exchangers_IFR | 2026-02-20 | 2026-02-20 | 04-Jun-25 A | 07-Jun-25 A | 2026-05-17 | 6 | 2026-05-17
A56700 | Technical Bid Evaluation for Heat Exchangers_RCC | 2026-02-20 | 2026-02-20 | 08-Jun-25 A | 11-Jun-25 A | 2026-05-17 | 5 | 2026-05-17
A56710 | Technical Bid Evaluation for Heat Exchangers_IFA | 2026-02-20 | 2026-02-20 | 12-Jun-25 A | 14-Jun-25 A | 2026-05-17 | 6 | 2026-05-17
A56720 | Technical Bid Evaluation for Heat Exchangers_RCA | 2026-02-20 | 2026-02-20 | 15-Jun-25 A | 17-Jun-25 A | 2026-05-17 | 6 | 2026-05-17
A56730 | Technical Bid Evaluation for Heat Exchangers_IFD/IFC | 2026-02-20 | 2026-02-20 | 18-Jun-25 A | 20-Jun-25 A | 2026-05-17 | 3 | 2026-05-17
A36970 | Commercial Bid Evaluation(Completion) | 2026-02-20 | 2026-02-20 | 20-Jun-25 A | 24-Jun-25 A | 2026-05-17 | 6 | 2026-05-17
A36980 | Issue Purchase Order to Vendor | 2026-02-20 | 2026-02-20 | 25-Jun-25 A | 27-Jun-25 A | 2026-05-17 | 3 | 2026-05-17
OG Comp. Interstage Cooler (BEU) (13-HE-708) |  | 2026-02-20 | 2026-02-20 | 01-Jun-25 A | 27-Jun-25 A | 2026-05-26 | 36 | 2026-05-26
A36990 | Issue RFQ to Bidders | 2026-02-20 | 2026-02-20 | 01-Jun-25 A | 03-Jun-25 A | 2026-05-26 | 21 | 2026-05-26
A56740 | Technical Bid Evaluation for Heat Exchangers_IFR | 2026-02-20 | 2026-02-20 | 04-Jun-25 A | 07-Jun-25 A | 2026-05-26 | 6 | 2026-05-26
A56750 | Technical Bid Evaluation for Heat Exchangers_RCC | 2026-02-20 | 2026-02-20 | 08-Jun-25 A | 11-Jun-25 A | 2026-05-26 | 5 | 2026-05-26
A56760 | Technical Bid Evaluation for Heat Exchangers_IFA | 2026-02-20 | 2026-02-20 | 12-Jun-25 A | 14-Jun-25 A | 2026-05-26 | 6 | 2026-05-26
A56770 | Technical Bid Evaluation for Heat Exchangers_RCA | 2026-02-20 | 2026-02-20 | 15-Jun-25 A | 17-Jun-25 A | 2026-05-26 | 6 | 2026-05-26
A56780 | Technical Bid Evaluation for Heat Exchangers_IFD/IFC | 2026-02-20 | 2026-02-20 | 18-Jun-25 A | 20-Jun-25 A | 2026-05-26 | 3 | 2026-05-26
A37010 | Commercial Bid Evaluation(Completion) | 2026-02-20 | 2026-02-20 | 20-Jun-25 A | 24-Jun-25 A | 2026-05-26 | 6 | 2026-05-26
A37020 | Issue Purchase Order to Vendor | 2026-02-20 | 2026-02-20 | 25-Jun-25 A | 27-Jun-25 A | 2026-05-26 | 3 | 2026-05-26
C4 Guard Regen. Gas Cooler (BEU) (Tag#50-HE-1410) |  | 2026-02-20 | 2026-02-20 | 01-Jun-25 A | 02-Jul-25 A | 2026-05-26 | 36 | 2026-05-26
A37030 | Issue RFQ to Bidders | 2026-02-20 | 2026-02-20 | 01-Jun-25 A | 03-Jun-25 A | 2026-05-26 | 21 | 2026-05-26
A56790 | Technical Bid Evaluation for Heat Exchangers_IFR | 2026-02-20 | 2026-02-20 | 04-Jun-25 A | 07-Jun-25 A | 2026-05-26 | 6 | 2026-05-26
A56800 | Technical Bid Evaluation for Heat Exchangers_RCC | 2026-02-20 | 2026-02-20 | 08-Jun-25 A | 11-Jun-25 A | 2026-05-26 | 5 | 2026-05-26
A56810 | Technical Bid Evaluation for Heat Exchangers_IFA | 2026-02-20 | 2026-02-20 | 12-Jun-25 A | 14-Jun-25 A | 2026-05-26 | 6 | 2026-05-26
A56820 | Technical Bid Evaluation for Heat Exchangers_RCA | 2026-02-20 | 2026-02-20 | 15-Jun-25 A | 17-Jun-25 A | 2026-05-26 | 6 | 2026-05-26
A56830 | Technical Bid Evaluation for Heat Exchangers_IFD/IFC | 2026-02-20 | 2026-02-20 | 18-Jun-25 A | 20-Jun-25 A | 2026-05-26 | 3 | 2026-05-26
A37050 | Commercial Bid Evaluation(Completion) | 2026-02-20 | 2026-02-20 | 20-Jun-25 A | 27-Jun-25 A | 2026-05-26 | 3 | 2026-05-26
A37060 | Issue Purchase Order to Vendor | 2026-02-20 | 2026-02-20 | 30-Jun-25 A | 02-Jul-25 A | 2026-05-26 | 3 | 2026-05-26
HVAC |  | 2026-02-20 | 2026-02-20 | 25-May-25 A | 29-Aug-25 A | 2026-06-15 | 66 | 2026-06-15
HVAC |  | 2026-02-20 | 2026-02-20 | 25-May-25 A | 29-Aug-25 A | 2026-06-15 | 66 | 2026-06-15
A16510 | Issue RFQ to Bidders | 2026-02-20 | 2026-02-20 | 25-May-25 A | 03-Jun-25 A | 2026-06-15 | 20 | 2026-06-15
A53240 | Technical Bid Evaluation For HVAC Equipments_IFR | 2026-02-20 | 2026-02-20 | 04-Jun-25 A | 19-Jun-25 A | 2026-06-15 | 11 | 2026-06-15
A25290 | Technical Bid Evaluation For HVAC Equipments_RCC | 2026-02-20 | 2026-02-20 | 20-Jun-25 A | 25-Jun-25 A | 2026-06-15 | 1 | 2026-06-15
A25300 | Technical Bid Evaluation For HVAC Equipments_IFA | 2026-02-20 | 2026-02-20 | 26-Jun-25 A | 02-Jul-25 A | 2026-06-15 | 5 | 2026-06-15
A25310 | Technical Bid Evaluation For HVAC Equipments_RCA | 2026-02-20 | 2026-02-20 | 03-Jul-25 A | 08-Jul-25 A | 2026-06-15 | 5 | 2026-06-15
A25320 | Technical Bid Evaluation For HVAC Equipments_IFD/IFC | 2026-02-20 | 2026-02-20 | 09-Jul-25 A | 14-Jul-25 A | 2026-06-15 | 5 | 2026-06-15
A19890 | Commercial Bid Evaluation(Completion) | 2026-02-20 | 2026-02-20 | 15-Jul-25 A | 31-Jul-25 A | 2026-06-15 | 1 | 2026-06-15
A19870 | Issue Purchase Order to Vendor | 2026-02-20 | 2026-02-20 | 20-Aug-25 A | 29-Aug-25 A | 2026-06-15 | 1 | 2026-06-15
Bulk Materials |  | 2026-02-20 | 2026-07-24 | 15-Jan-25 A | 2026-07-24 | 2026-02-23 | 326 | 2027-07-20 | 257
Drip Leg |  | 2026-02-20 | 2026-02-20 | 01-Aug-25 A | 09-Sep-25 A | 2026-03-19 | 71 | 2026-03-31
OG Comp. Dis. Drip leg (02 Nos) |  | 2026-02-20 | 2026-02-20 | 01-Aug-25 A | 09-Sep-25 A | 2026-03-19 | 71 | 2026-03-31
A8790 | Issue RFQ to Bidders | 2026-02-20 | 2026-02-20 | 01-Aug-25 A | 05-Aug-25 A | 2026-03-19 | 15 | 2026-03-19
A56840 | Technical Bid Evaluation for Pressure Vessels & Internals_IFR | 2026-02-20 | 2026-02-20 | 06-Aug-25 A | 07-Aug-25 A | 2026-03-19 | 8 | 2026-03-19
A56850 | Technical Bid Evaluation for Pressure Vessels & Internals_RCC | 2026-02-20 | 2026-02-20 | 08-Aug-25 A | 13-Aug-25 A | 2026-03-19 | 8 | 2026-03-19
A56860 | Technical Bid Evaluation for Pressure Vessels & Internals_IFA | 2026-02-20 | 2026-02-20 | 14-Aug-25 A | 19-Aug-25 A | 2026-03-19 | 8 | 2026-03-19
A56870 | Technical Bid Evaluation for Pressure Vessels & Internals_RCA | 2026-02-20 | 2026-02-20 | 20-Aug-25 A | 25-Aug-25 A | 2026-03-31 | 8 | 2026-03-31
A56880 | Technical Bid Evaluation for Pressure Vessels & Internals_IFD/IFC | 2026-02-20 | 2026-02-20 | 26-Aug-25 A | 29-Aug-25 A | 2026-03-31 | 8 | 2026-03-31
A19370 | Commercial Bid Evaluation(Completion) | 2026-02-20 | 2026-02-20 | 30-Aug-25 A | 03-Sep-25 A | 2026-03-31 | 15 | 2026-03-31
A19350 | Issue Purchase Order to Vendor | 2026-02-20 | 2026-02-20 | 04-Sep-25 A | 09-Sep-25 A | 2026-03-31 | 11 | 2026-03-31
Fire Fighting Equipment |  | 2026-02-20 | 2026-03-19 | 11-Feb-25 A | 2026-03-19 | 2026-03-27 | 197 | 2026-06-18 | 65
TA_Fire Alarm System Modification - SAFCO |  | 2026-02-20 | 2026-02-20 | 11-Feb-25 A | 31-Mar-25 A | 2026-03-27 | 48 | 2026-03-27
A37120 | Issue RFQ to Bidders | 2026-02-20 | 2026-02-20 | 11-Feb-25 A | 28-Feb-25 A | 2026-03-27 | 20 | 2026-03-27
A37150 | Issue Purchase Order to Vendor | 2026-02-20 | 2026-02-20 | 03-Mar-25 A | 21-Mar-25 A | 2026-03-27 | 10 | 2026-03-27
A57240 | TBE for ICT System Modification_Free Issue Material | 2026-02-20 | 2026-02-20 | 24-Mar-25 A | 31-Mar-25 A | 2026-03-27 | 23 | 2026-03-27
VESDA (Very Early Smoke Detection Apparatus) |  | 2026-02-20 | 2026-02-20 | 01-May-25 A | 01-Oct-25 A | 2026-06-02 | 127 | 2026-06-02
A20710 | Issue RFQ to Bidders | 2026-02-20 | 2026-02-20 | 01-May-25 A | 20-Jun-25 A | 2026-06-02 | 21 | 2026-06-02
A20730 | Bid Evaluation(Completion) | 2026-02-20 | 2026-02-20 | 25-Aug-25 A | 29-Aug-25 A | 2026-06-02 | 40 | 2026-06-02
A20740 | Commercial Bid Evaluation(Completion) | 2026-02-20 | 2026-02-20 | 01-Sep-25 A | 12-Sep-25 A | 2026-06-02 | 20 | 2026-06-02
A20720 | Issue Purchase Order to Vendor for VESDA | 2026-02-20 | 2026-02-20 | 15-Sep-25 A | 01-Oct-25 A | 2026-06-02 | 10 | 2026-06-02
Fire Fighting Equipment |  | 2026-02-20 | 2026-03-19 | 20-Oct-25 A | 2026-03-19 | 2026-05-22 | 95 | 2026-06-18 | 65
A17470 | Issue RFQ to Bidders | 2026-02-20 | 2026-02-20 | 20-Oct-25 A | 27-Oct-25 A | 2026-05-22 | 5 | 2026-05-22
A18090 | Bid Evaluation(Completion) | 2026-02-20 | 2026-02-20 | 01-Feb-26 A | 11-Mar-26 A | 2026-05-22 | 15 | 2026-05-22
A18100 | Commercial Bid Evaluation(Completion) | 2026-02-20 | 2026-03-12 | 12-Feb-26 A | 2026-03-12 | 2026-05-22 | 15 | 2026-06-11 | 65
A18080 | Issue Purchase Order to Vendor for Fire Fighting Equipment | 2026-03-13 | 2026-03-19 | 2026-03-13 | 2026-03-19 | 2026-06-12 | 5 | 2026-06-18 | 65
Tail Gas Filter/Silencer/Colesor |  | 2026-02-20 | 2026-03-02 | 01-Apr-25 A | 2026-03-02 | 2026-11-09 | 187 | 2026-11-18 | 186
Coalescer - (BF) |  | 2026-02-20 | 2026-03-02 | 01-Apr-25 A | 2026-03-02 | 2026-11-09 | 187 | 2026-11-18 | 186
A8130 | Issue RFQ to Bidders | 2026-02-20 | 2026-02-20 | 01-Apr-25 A | 10-Apr-25 A | 2026-11-09 | 20 | 2026-11-09
A45510 | Technical Bid Evaluation for Coalscer_IFR | 2026-02-20 | 2026-02-20 | 24-Jan-26 A | 25-Jan-26 A | 2026-11-09 | 3 | 2026-11-09
A45520 | Technical Bid Evaluation for Coalscer_RCC | 2026-02-20 | 2026-02-20 | 25-Jan-26 A | 26-Jan-26 A | 2026-11-09 | 3 | 2026-11-09
A45530 | Technical Bid Evaluation for Coalscer_IFA | 2026-02-20 | 2026-02-20 | 27-Jan-26 A | 28-Jan-26 A | 2026-11-09 | 3 | 2026-11-09
A8160 | Issue Purchase Order to Vendor | 2026-02-20 | 2026-02-20 | 29-Jan-26 A | 29-Jan-26 A | 2026-11-18 | 3 | 2026-11-18
A45540 | Technical Bid Evaluation for Coalscer_RCA | 2026-02-20 | 2026-02-25 | 2026-02-20 | 2026-02-25 | 2026-11-09 | 3 | 2026-11-12 | 186
A45550 | Technical Bid Evaluation for Coalscer_IFD/IFC | 2026-02-25 | 2026-03-02 | 2026-02-25 | 2026-03-02 | 2026-11-12 | 3 | 2026-11-17 | 186
Steel Structure (material +sandwitch Panel) |  | 2026-02-20 | 2026-03-09 | 01-Mar-25 A | 2026-03-09 | 2026-02-23 | 181 | 2026-11-23 | 185
Civil Bulk Material |  | 2026-02-20 | 2026-02-20 | 16-May-25 A | 10-Jul-25 A | 2026-11-23 | 54 | 2026-11-23
A9550 | Issue RFQ to Bidders | 2026-02-20 | 2026-02-20 | 16-May-25 A | 01-Jun-25 A | 2026-11-23 | 21 | 2026-11-23
A9580 | Issue Purchase Order to Vendor | 2026-02-20 | 2026-02-20 | 09-Jun-25 A | 20-Jun-25 A | 2026-11-23 | 21 | 2026-11-23
A9560 | Vendor Quote Received | 2026-02-20 | 2026-02-20 | 02-Jun-25 A | 01-Jul-25 A | 2026-11-23 | 30 | 2026-11-23
A9570 | Technical Bid Evaluation | 2026-02-20 | 2026-02-20 | 02-Jul-25 A | 10-Jul-25 A | 2026-11-23 | 21 | 2026-11-23
TA_Steel Structure (Additional Steel Structure required for BFW) |  | 2026-02-20 | 2026-02-20 | 01-Mar-25 A | 20-Mar-25 A | 2026-03-27 | 30 | 2026-03-27
A21910 | Issue RFQs to Bidders (Remaining Steel Structure for TA) | 2026-02-20 | 2026-02-20 | 01-Mar-25 A | 05-Mar-25 A | 2026-03-27 | 5 | 2026-03-27
A21920 | Vendor Quote Received | 2026-02-20 | 2026-02-20 | 05-Mar-25 A | 10-Mar-25 A | 2026-03-27 | 10 | 2026-03-27
A21940 | TBE for Steel Structure (TA) | 2026-02-20 | 2026-02-20 | 11-Mar-25 A | 15-Mar-25 A | 2026-03-27 | 10 | 2026-03-27
A21930 | Issue Purchase Order to Vendor | 2026-02-20 | 2026-02-20 | 16-Mar-25 A | 20-Mar-25 A | 2026-03-27 | 5 | 2026-03-27
Steel Structure - Post TA |  | 2026-02-20 | 2026-02-20 | 01-Jun-25 A | 03-Oct-25 A | 2026-02-23 | 95 | 2026-07-24
122 | Issue RFQ to Bidders | 2026-02-20 | 2026-02-20 | 01-Jun-25 A | 25-Jul-25 A | 2026-02-23 | 10 | 2026-02-23
A34530 | Bid Evaluation(Completion) | 2026-02-20 | 2026-02-20 | 25-Aug-25 A | 05-Sep-25 A | 2026-04-20 | 10 | 2026-04-20
A34540 | Commercial Bid Evaluation(Completion) | 2026-02-20 | 2026-02-20 | 08-Sep-25 A | 22-Sep-25 A | 2026-04-20 | 10 | 2026-04-20
A34550 | Issue Purchase Order to Vendor | 2026-02-20 | 2026-02-20 | 23-Sep-25 A | 03-Oct-25 A | 2026-07-24 | 10 | 2026-07-24
Structural Steel |  | 2026-02-20 | 2026-03-09 | 01-Jun-25 A | 2026-03-09 | 2026-02-23 | 181 | 2026-03-13 | 5
A23620 | Issue RFQ to Bidders | 2026-02-20 | 2026-02-20 | 01-Jun-25 A | 25-Jun-25 A | 2026-02-23 | 10 | 2026-02-23
A23630 | Vendor Quote Received | 2026-02-20 | 2026-02-20 | 25-Aug-25 A | 05-Sep-25 A | 2026-02-23 | 10 | 2026-02-23
A57960 | Technical Bid Evaluation for Structural Steel_IFR | 2026-02-20 | 2026-02-20 | 08-Sep-25 A | 12-Sep-25 A | 2026-02-23 | 6 | 2026-02-23
A57970 | Technical Bid Evaluation for Structural Steel_RCC | 2026-02-20 | 2026-02-20 | 15-Sep-25 A | 19-Sep-25 A | 2026-02-23 | 6 | 2026-02-23
A57980 | Technical Bid Evaluation for Structural Steel_IFA | 2026-02-20 | 2026-02-20 | 19-Sep-25 A | 01-Oct-25 A | 2026-02-23 | 6 | 2026-02-23
A23640 | Issue Purchase Order to Vendor | 2026-02-20 | 2026-02-20 | 15-Sep-25 A | 03-Oct-25 A | 2026-02-23 | 10 | 2026-02-23
A57990 | Technical Bid Evaluation for Structural Steel_RCA | 2026-02-20 | 2026-02-27 | 2026-02-20 | 2026-02-27 | 2026-02-26 | 6 | 2026-03-06 | 5
A58000 | Technical Bid Evaluation for Structural Steel_IFD/IFC | 2026-02-27 | 2026-03-09 | 2026-02-27 | 2026-03-09 | 2026-03-06 | 6 | 2026-03-13 | 5
Turbing Material [SS tubes, Connectors, unions, plugs etc.] |  | 2026-02-20 | 2026-04-16 | 2026-02-20 | 2026-04-16 | 2026-04-07 | 40 | 2026-06-01 | 32
Turbing Material [SS tubes, Connectors, unions, plugs etc] |  | 2026-02-20 | 2026-04-16 | 2026-02-20 | 2026-04-16 | 2026-04-07 | 40 | 2026-06-01 | 32
A17410 | Issue RFQ to Bidders | 2026-02-20 | 2026-03-05 | 2026-02-20 | 2026-03-05 | 2026-04-07 | 10 | 2026-04-20 | 32
A18210 | Bid Evaluation(Completion) | 2026-03-06 | 2026-03-19 | 2026-03-06 | 2026-03-19 | 2026-04-21 | 10 | 2026-05-04 | 32
A18220 | Commercial Bid Evaluation(Completion) | 2026-03-20 | 2026-04-02 | 2026-03-20 | 2026-04-02 | 2026-05-05 | 10 | 2026-05-18 | 32
A18200 | Issue Purchase Order to Vendor | 2026-04-03 | 2026-04-16 | 2026-04-03 | 2026-04-16 | 2026-05-19 | 10 | 2026-06-01 | 32
Telecom (ACS+LAN +CCTV+PAGA) |  | 2026-02-20 | 2026-02-27 | 11-Mar-25 A | 2026-02-27 | 2026-03-27 | 111 | 2027-01-20 | 233
Acess Control System |  | 2026-02-20 | 2026-02-27 | 01-Aug-25 A | 2026-02-27 | 2026-04-08 | 91 | 2027-01-20 | 233
A18720 | RFQs to Bid Receipt | 2026-02-20 | 2026-02-20 | 01-Aug-25 A | 06-Aug-25 A | 2026-04-08 | 3 | 2026-04-08
A23880 | Technical Bid Evaluation For Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_IFR | 2026-02-20 | 2026-02-20 | 31-Oct-25 A | 14-Nov-25 A | 2026-04-08 | 3 | 2026-04-08
A23890 | Technical Bid Evaluation For Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_RCC | 2026-02-20 | 2026-02-20 | 26-Nov-25 A | 28-Nov-25 A | 2026-04-08 | 3 | 2026-04-08
A22340 | Commercial Bid Evaluation(Completion) | 2026-02-20 | 2026-02-20 | 01-Dec-25 A | 03-Dec-25 A | 2026-04-08 | 3 | 2026-04-08
A51950 | Technical Bid Evaluation For Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_IFA | 2026-02-20 | 2026-02-20 | 01-Dec-25 A | 03-Dec-25 A | 2026-04-08 | 3 | 2026-04-08
A22350 | Issue Purchase Order to Vendor for ACS | 2026-02-20 | 2026-02-20 | 13-Dec-25 A | 19-Dec-25 A | 2026-04-08 | 3 | 2026-04-08
A51960 | Technical Bid Evaluation For Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_RCA | 2026-02-20 | 2026-02-24 | 2026-02-20 | 2026-02-24 | 2027-01-13 | 3 | 2027-01-15 | 233
A51970 | Technical Bid Evaluation For Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_IFD/IFC | 2026-02-25 | 2026-02-27 | 2026-02-25 | 2026-02-27 | 2027-01-18 | 3 | 2027-01-20 | 233
TA_LAN System Modification - CISCO |  | 2026-02-20 | 2026-02-20 | 11-Mar-25 A | 10-Apr-25 A | 2026-03-27 | 48 | 2026-03-27
A37200 | Issue RFQ to Bidders | 2026-02-20 | 2026-02-20 | 11-Mar-25 A | 27-Mar-25 A | 2026-03-27 | 20 | 2026-03-27
A57480 | TBE for Electrical System Modification_Free Issue Material | 2026-02-20 | 2026-02-20 | 28-Mar-25 A | 03-Apr-25 A | 2026-03-27 | 23 | 2026-03-27
A37230 | Issue Purchase Order to Vendor | 2026-02-20 | 2026-02-20 | 03-Apr-25 A | 10-Apr-25 A | 2026-03-27 | 10 | 2026-03-27
PAGA + Telephone |  | 2026-02-20 | 2026-02-27 | 01-Aug-25 A | 2026-02-27 | 2026-05-22 | 91 | 2027-01-20 | 233
A18810 | RFQs to Bid Receipt | 2026-02-20 | 2026-02-20 | 01-Aug-25 A | 06-Aug-25 A | 2026-05-22 | 3 | 2026-05-22
A56990 | Technical Bid Evaluation For Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_IFR | 2026-02-20 | 2026-02-20 | 24-Nov-25 A | 26-Nov-25 A | 2026-05-22 | 3 | 2026-05-22
A57000 | Technical Bid Evaluation For Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_RCC | 2026-02-20 | 2026-02-20 | 27-Nov-25 A | 01-Dec-25 A | 2026-05-22 | 3 | 2026-05-22
A57010 | Technical Bid Evaluation For Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_IFA | 2026-02-20 | 2026-02-20 | 03-Dec-25 A | 05-Dec-25 A | 2026-05-22 | 3 | 2026-05-22
A19130 | Commercial Bid Evaluation(Completion) | 2026-02-20 | 2026-02-20 | 11-Dec-25 A | 15-Dec-25 A | 2026-05-22 | 3 | 2026-05-22
A19110 | Issue Purchase Order to Vendor for PAGA + Telephone | 2026-02-20 | 2026-02-20 | 11-Dec-25 A | 19-Dec-25 A | 2026-05-22 | 3 | 2026-05-22
A57020 | Technical Bid Evaluation For Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_RCA | 2026-02-20 | 2026-02-24 | 2026-02-20 | 2026-02-24 | 2027-01-13 | 3 | 2027-01-15 | 233
A57030 | Technical Bid Evaluation For Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_IFD/IFC | 2026-02-25 | 2026-02-27 | 2026-02-25 | 2026-02-27 | 2027-01-18 | 3 | 2027-01-20 | 233
CCTV |  | 2026-02-20 | 2026-02-27 | 01-Aug-25 A | 2026-02-27 | 2026-05-13 | 91 | 2027-01-20 | 233
A18900 | RFQs to Bid Receipt | 2026-02-20 | 2026-02-20 | 01-Aug-25 A | 06-Aug-25 A | 2026-05-13 | 3 | 2026-05-13
A57040 | Technical Bid Evaluation For Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_IFR | 2026-02-20 | 2026-02-20 | 21-Nov-25 A | 25-Nov-25 A | 2026-05-13 | 3 | 2026-05-13
A57050 | Technical Bid Evaluation For Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_RCC | 2026-02-20 | 2026-02-20 | 26-Nov-25 A | 28-Nov-25 A | 2026-05-13 | 3 | 2026-05-13
A57060 | Technical Bid Evaluation For Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_IFA | 2026-02-20 | 2026-02-20 | 01-Dec-25 A | 03-Dec-25 A | 2026-05-13 | 3 | 2026-05-13
A19190 | Commercial Bid Evaluation(Completion) | 2026-02-20 | 2026-02-20 | 11-Dec-25 A | 15-Dec-25 A | 2026-05-13 | 3 | 2026-05-13
A19170 | Issue Purchase Order to Vendor for CCTV | 2026-02-20 | 2026-02-20 | 11-Dec-25 A | 19-Dec-25 A | 2026-05-13 | 3 | 2026-05-13
A57070 | Technical Bid Evaluation For Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_RCA | 2026-02-20 | 2026-02-24 | 2026-02-20 | 2026-02-24 | 2027-01-13 | 3 | 2027-01-15 | 233
A57080 | Technical Bid Evaluation For Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_IFD/IFC | 2026-02-25 | 2026-02-27 | 2026-02-25 | 2026-02-27 | 2027-01-18 | 3 | 2027-01-20 | 233
Telecom (ACS + CCTV + PAGA) Integration |  | 2026-02-20 | 2026-02-20 | 01-Aug-25 A | 19-Dec-25 A | 2026-06-11 | 48 | 2026-06-11
A16990 | Issue RFQ to Bidders | 2026-02-20 | 2026-02-20 | 01-Aug-25 A | 06-Aug-25 A | 2026-06-11 | 3 | 2026-06-11
A22270 | Bid Evaluation(Completion) | 2026-02-20 | 2026-02-20 | 01-Dec-25 A | 03-Dec-25 A | 2026-06-11 | 3 | 2026-06-11
A22280 | Commercial Bid Evaluation(Completion) | 2026-02-20 | 2026-02-20 | 02-Dec-25 A | 04-Dec-25 A | 2026-06-11 | 3 | 2026-06-11
A22290 | Issue Purchase Order to Vendor for Telecom (ACS+CCTV+PAGA) Integration | 2026-02-20 | 2026-02-20 | 12-Dec-25 A | 19-Dec-25 A | 2026-06-11 | 3 | 2026-06-11
Lighting Fixtures |  | 2026-02-20 | 2026-05-22 | 2026-02-20 | 2026-05-22 | 2026-06-11 | 66 | 2026-09-10 | 79
Lighting Fixtures (Almost 50% Exd = 354 Nos) |  | 2026-02-20 | 2026-05-22 | 2026-02-20 | 2026-05-22 | 2026-06-11 | 66 | 2026-09-10 | 79
A16390 | Issue RFQ to Bidders | 2026-02-20 | 2026-03-20 | 2026-02-20 | 2026-03-20 | 2026-06-11 | 21 | 2026-07-09 | 79
A19600 | Bid Evaluation(Completion) | 2026-03-23 | 2026-04-10 | 2026-03-23 | 2026-04-10 | 2026-07-10 | 15 | 2026-07-30 | 79
A19610 | Commercial Bid Evaluation(Completion) | 2026-04-13 | 2026-05-01 | 2026-04-13 | 2026-05-01 | 2026-07-31 | 15 | 2026-08-20 | 79
A19590 | Issue Purchase Order to Vendor for Lighting Fixtures | 2026-05-04 | 2026-05-22 | 2026-05-04 | 2026-05-22 | 2026-08-21 | 15 | 2026-09-10 | 79
Manual Valve |  | 2026-02-20 | 2026-02-20 | 20-May-25 A | 21-Nov-25 A | 2026-05-15 | 152 | 2026-05-18
Manual Valves (Gate 9 Nos, Check 6 Nos, Globe Valves 64 Nos) |  | 2026-02-20 | 2026-02-20 | 20-May-25 A | 21-Nov-25 A | 2026-05-15 | 152 | 2026-05-18
A9270 | Issue RFQ to Bidders | 2026-02-20 | 2026-02-20 | 20-May-25 A | 24-Jul-25 A | 2026-05-15 | 21 | 2026-05-15
A45020 | Technical Bid Evaluation (TBE) for Manual Valves_IFR | 2026-02-20 | 2026-02-20 | 19-Sep-25 A | 25-Sep-25 A | 2026-05-15 | 6 | 2026-05-15
A45030 | Technical Bid Evaluation (TBE) for Manual Valves_RCC | 2026-02-20 | 2026-02-20 | 26-Sep-25 A | 02-Oct-25 A | 2026-05-15 | 6 | 2026-05-15
A45050 | Technical Bid Evaluation (TBE) for Manual Valves_RCA | 2026-02-20 | 2026-02-20 | 08-Oct-25 A | 10-Oct-25 A | 2026-05-18 | 6 | 2026-05-18
A45060 | Technical Bid Evaluation (TBE) for Manual Valves_IFD/IFC | 2026-02-20 | 2026-02-20 | 10-Oct-25 A | 14-Oct-25 A | 2026-05-18 | 6 | 2026-05-18
A18160 | Commercial Bid Evaluation(Completion) | 2026-02-20 | 2026-02-20 | 15-Oct-25 A | 24-Oct-25 A | 2026-05-18 | 6 | 2026-05-18
A45040 | Technical Bid Evaluation (TBE) for Manual Valves_IFA | 2026-02-20 | 2026-02-20 | 03-Oct-25 A | 07-Nov-25 A | 2026-05-15 | 6 | 2026-05-15
A18140 | Issue Purchase Order to Vendor for Manual Valves | 2026-02-20 | 2026-02-20 | 27-Oct-25 A | 21-Nov-25 A | 2026-05-18 | 21 | 2026-05-18
Piping Bulk |  | 2026-02-20 | 2026-07-24 | 01-Jul-25 A | 2026-07-24 | 2026-03-30 | 241 | 2027-05-14 | 210
Piping Lot for Post TA |  | 2026-02-20 | 2026-02-20 | 01-Jul-25 A | 17-Nov-25 A | 2026-04-22 | 80 | 2026-04-22
112 | Issue RFQ to Bidders | 2026-02-20 | 2026-02-20 | 01-Jul-25 A | 21-Jul-25 A | 2026-04-22 | 15 | 2026-04-22
A23680 | Issue Purchase Order to Vendor | 2026-02-20 | 2026-02-20 | 01-Sep-25 A | 06-Sep-25 A | 2026-04-22 | 6 | 2026-04-22
A57090 | Technical Bid Evaluation (TBE) for Piping Bulk_IFR | 2026-02-20 | 2026-02-20 | 22-Jul-25 A | 15-Sep-25 A | 2026-04-22 | 6 | 2026-04-22
A57100 | Technical Bid Evaluation (TBE) for Piping Bulk_RCC | 2026-02-20 | 2026-02-20 | 15-Sep-25 A | 15-Oct-25 A | 2026-04-22 | 8 | 2026-04-22
A23700 | Commercial Bid Evaluation(Completion) | 2026-02-20 | 2026-02-20 | 15-Oct-25 A | 24-Oct-25 A | 2026-04-22 | 6 | 2026-04-22
A57110 | Technical Bid Evaluation (TBE) for Piping Bulk_IFA | 2026-02-20 | 2026-02-20 | 25-Oct-25 A | 29-Oct-25 A | 2026-04-22 | 7 | 2026-04-22
A57120 | Technical Bid Evaluation (TBE) for Piping Bulk_RCA | 2026-02-20 | 2026-02-20 | 30-Oct-25 A | 14-Nov-25 A | 2026-04-22 | 8 | 2026-04-22
A57130 | Technical Bid Evaluation (TBE) for Piping Bulk_IFD/IFC | 2026-02-20 | 2026-02-20 | 14-Nov-25 A | 17-Nov-25 A | 2026-04-22 | 6 | 2026-04-22
Piping Supports (Swing Hangers) for Post TA |  | 2026-02-20 | 2026-02-20 | 04-Aug-25 A | 08-Sep-25 A | 2026-03-30 | 83 | 2026-05-25
A23710 | Issue RFQ to Bidders | 2026-02-20 | 2026-02-20 | 04-Aug-25 A | 08-Aug-25 A | 2026-03-30 | 20 | 2026-03-30
A57140 | Technical Bid Evaluation (TBE) for Spring Hangers_IFR | 2026-02-20 | 2026-02-20 | 09-Aug-25 A | 14-Aug-25 A | 2026-03-30 | 11 | 2026-03-30
A57150 | Technical Bid Evaluation (TBE) for Spring Hangers_RCC | 2026-02-20 | 2026-02-20 | 15-Aug-25 A | 16-Aug-25 A | 2026-03-30 | 16 | 2026-03-30
A57160 | Technical Bid Evaluation (TBE) for Spring Hangers_IFA | 2026-02-20 | 2026-02-20 | 18-Aug-25 A | 19-Aug-25 A | 2026-03-30 | 8 | 2026-03-30
A57170 | Technical Bid Evaluation (TBE) for Spring Hangers_RCA | 2026-02-20 | 2026-02-20 | 20-Aug-25 A | 22-Aug-25 A | 2026-05-25 | 16 | 2026-05-25
A57180 | Technical Bid Evaluation (TBE) for Spring Hangers_IFD/IFC | 2026-02-20 | 2026-02-20 | 25-Aug-25 A | 26-Aug-25 A | 2026-05-25 | 8 | 2026-05-25
A23740 | Commercial Bid Evaluation(Completion) | 2026-02-20 | 2026-02-20 | 06-Aug-25 A | 30-Aug-25 A | 2026-03-30 | 21 | 2026-03-30
A23720 | Issue Purchase Order to Vendor | 2026-02-20 | 2026-02-20 | 01-Sep-25 A | 08-Sep-25 A | 2026-03-30 | 7 | 2026-03-30
Piping 1st Lot for GF |  | 2026-02-20 | 2026-03-13 | 01-Jul-25 A | 2026-03-13 | 2026-04-20 | 146 | 2027-01-20 | 223
100 | Issue RFQ to Bidders | 2026-02-20 | 2026-02-20 | 01-Jul-25 A | 21-Jul-25 A | 2026-04-20 | 21 | 2026-04-20
A44970 | Technical Bid Evaluation (TBE) for Piping Bulk_IFR | 2026-02-20 | 2026-02-20 | 19-Aug-25 A | 29-Aug-25 A | 2026-04-20 | 8 | 2026-04-20
A21370 | Commercial Bid Evaluation(Completion) | 2026-02-20 | 2026-02-20 | 25-Aug-25 A | 05-Sep-25 A | 2026-04-20 | 15 | 2026-04-20
A44980 | Technical Bid Evaluation (TBE) for Piping Bulk_RCC | 2026-02-20 | 2026-02-20 | 30-Aug-25 A | 08-Sep-25 A | 2026-04-20 | 8 | 2026-04-20
A44990 | Technical Bid Evaluation (TBE) for Piping Bulk_IFA | 2026-02-20 | 2026-02-20 | 09-Sep-25 A | 16-Sep-25 A | 2026-04-20 | 8 | 2026-04-20
A21350 | Issue Purchase Order to Vendor | 2026-02-20 | 2026-02-20 | 08-Sep-25 A | 19-Sep-25 A | 2026-04-20 | 14 | 2026-04-20
A45000 | Technical Bid Evaluation (TBE) for Piping Bulk_RCA | 2026-02-20 | 2026-03-03 | 2026-02-20 | 2026-03-03 | 2026-12-30 | 8 | 2027-01-11 | 223
A45010 | Technical Bid Evaluation (TBE) for Piping Bulk_IFD/IFC | 2026-03-03 | 2026-03-13 | 2026-03-03 | 2026-03-13 | 2027-01-11 | 8 | 2027-01-20 | 223
Piping 2nd Lot for GF (CS Material) |  | 2026-02-20 | 2026-03-19 | 2026-02-20 | 2026-03-19 | 2026-05-18 | 20 | 2026-06-12 | 61
101 | Issue RFQ to Bidders | 2026-02-20 | 2026-02-26 | 2026-02-20 | 2026-02-26 | 2026-05-18 | 5 | 2026-05-22 | 61
A21420 | Bid Evaluation(Completion) | 2026-02-27 | 2026-03-05 | 2026-02-27 | 2026-03-05 | 2026-05-25 | 5 | 2026-05-29 | 61
A21430 | Commercial Bid Evaluation(Completion) | 2026-03-06 | 2026-03-12 | 2026-03-06 | 2026-03-12 | 2026-06-01 | 5 | 2026-06-05 | 61
A21410 | Issue Purchase Order to Vendor | 2026-03-13 | 2026-03-19 | 2026-03-13 | 2026-03-19 | 2026-06-08 | 5 | 2026-06-12 | 61
Piping 3rd Lot GF (CS Material) |  | 2026-03-13 | 2026-04-22 | 2026-03-13 | 2026-04-22 | 2026-04-06 | 28 | 2026-05-13 | 15
102 | Issue RFQ to Bidders | 2026-03-13 | 2026-03-24 | 2026-03-13 | 2026-03-24 | 2026-04-06 | 7 | 2026-04-14 | 15
A21480 | Bid Evaluation(Completion) | 2026-03-24 | 2026-04-02 | 2026-03-24 | 2026-04-02 | 2026-04-15 | 7 | 2026-04-23 | 15
A21490 | Commercial Bid Evaluation(Completion) | 2026-04-02 | 2026-04-13 | 2026-04-02 | 2026-04-13 | 2026-04-24 | 7 | 2026-05-04 | 15
A21470 | Issue Purchase Order to Vendor | 2026-04-13 | 2026-04-22 | 2026-04-13 | 2026-04-22 | 2026-05-05 | 7 | 2026-05-13 | 15
Piping Supports (Swing Hangers) for GF |  | 2026-02-20 | 2026-07-24 | 2026-02-20 | 2026-07-24 | 2026-10-20 | 111 | 2027-05-14 | 210
A21610 | Issue RFQ to Bidders | 2026-02-20 | 2026-02-26 | 2026-02-20 | 2026-02-26 | 2026-10-20 | 5 | 2026-10-27 | 172
A45120 | Technical Bid Evaluation (TBE) for Spring Hangers_IFR | 2026-02-27 | 2026-03-16 | 2026-02-27 | 2026-03-16 | 2026-10-27 | 11 | 2026-11-11 | 172
A45130 | Technical Bid Evaluation (TBE) for Spring Hangers_RCC | 2026-03-16 | 2026-04-06 | 2026-03-16 | 2026-04-06 | 2026-11-11 | 16 | 2026-12-03 | 172
A45140 | Technical Bid Evaluation (TBE) for Spring Hangers_IFA | 2026-04-07 | 2026-04-22 | 2026-04-07 | 2026-04-22 | 2026-12-03 | 11 | 2026-12-18 | 172
A45150 | Technical Bid Evaluation (TBE) for Spring Hangers_RCA | 2026-04-22 | 2026-05-13 | 2026-04-22 | 2026-05-13 | 2026-12-18 | 16 | 2027-01-11 | 172
A45160 | Technical Bid Evaluation (TBE) for Spring Hangers_IFD/IFC | 2026-05-14 | 2026-05-25 | 2026-05-14 | 2026-05-25 | 2027-01-11 | 8 | 2027-01-20 | 172
A21640 | Commercial Bid Evaluation(Completion) | 2026-05-25 | 2026-07-06 | 2026-05-25 | 2026-07-06 | 2027-03-16 | 30 | 2027-04-26 | 210
A21620 | Issue Purchase Order to Vendor | 2026-07-06 | 2026-07-24 | 2026-07-06 | 2026-07-24 | 2027-04-27 | 14 | 2027-05-14 | 210
HDPE Piping |  | 2026-02-20 | 2026-02-20 | 01-Aug-25 A | 19-Dec-25 A | 2026-04-09 | 59 | 2026-06-05
HDPE Piping GF (Fire Water Lines) |  | 2026-02-20 | 2026-02-20 | 01-Aug-25 A | 19-Dec-25 A | 2026-04-09 | 59 | 2026-06-05
A21530 | Issue RFQ to Bidders | 2026-02-20 | 2026-02-20 | 01-Aug-25 A | 08-Aug-25 A | 2026-04-09 | 10 | 2026-04-09
A60270 | Technical Bid Evaluation (TBE) for Piping Bulk_IFR | 2026-02-20 | 2026-02-20 | 09-Aug-25 A | 12-Aug-25 A | 2026-04-09 | 8 | 2026-04-09
A60280 | Technical Bid Evaluation (TBE) for Piping Bulk_RCC | 2026-02-20 | 2026-02-20 | 13-Aug-25 A | 15-Aug-25 A | 2026-04-09 | 16 | 2026-04-09
A60290 | Technical Bid Evaluation (TBE) for Piping Bulk_IFA | 2026-02-20 | 2026-02-20 | 16-Aug-25 A | 18-Aug-25 A | 2026-04-09 | 8 | 2026-04-09
A60300 | Technical Bid Evaluation (TBE) for Piping Bulk_RCA | 2026-02-20 | 2026-02-20 | 18-Aug-25 A | 19-Aug-25 A | 2026-06-05 | 8 | 2026-06-05
A60310 | Technical Bid Evaluation (TBE) for Piping Bulk_IFD/IFC | 2026-02-20 | 2026-02-20 | 19-Aug-25 A | 21-Aug-25 A | 2026-06-05 | 8 | 2026-06-05
A21560 | Commercial Bid Evaluation(Completion) | 2026-02-20 | 2026-02-20 | 22-Aug-25 A | 30-Aug-25 A | 2026-04-09 | 21 | 2026-04-09
A21540 | Issue Purchase Order to Vendor | 2026-02-20 | 2026-02-20 | 18-Dec-25 A | 19-Dec-25 A | 2026-04-09 | 10 | 2026-04-09
Piping SP Items (strainer, filters) |  | 2026-02-20 | 2026-04-09 | 23-Jan-26 A | 2026-04-09 | 2026-04-17 | 78 | 2026-07-24 | 76
Specialized Items (Orifice Flanges) CS 300# 1" - 6" = 08 Nos |  | 2026-02-20 | 2026-04-01 | 2026-02-20 | 2026-04-01 | 2026-04-22 | 29 | 2026-07-20 | 79
A18340 | Issue RFQ to Bidders | 2026-02-20 | 2026-02-26 | 2026-02-20 | 2026-02-26 | 2026-04-22 | 5 | 2026-04-29 | 44
A45070 | Technical Bid Evaluation (TBE) for Piping Speciality Items_IFR | 2026-02-27 | 2026-03-05 | 2026-02-27 | 2026-03-05 | 2026-04-29 | 5 | 2026-05-05 | 44
A45080 | Technical Bid Evaluation (TBE) for Piping Speciality Items_RCC | 2026-03-05 | 2026-03-11 | 2026-03-05 | 2026-03-11 | 2026-05-06 | 5 | 2026-05-12 | 44
A45090 | Technical Bid Evaluation (TBE) for Piping Speciality Items_IFA | 2026-03-12 | 2026-03-18 | 2026-03-12 | 2026-03-18 | 2026-05-12 | 5 | 2026-05-18 | 44
A45100 | Technical Bid Evaluation (TBE) for Piping Speciality Items_RCA | 2026-03-18 | 2026-03-24 | 2026-03-18 | 2026-03-24 | 2026-07-08 | 5 | 2026-07-14 | 80
A18380 | Commercial Bid Evaluation(Completion) | 2026-03-18 | 2026-03-25 | 2026-03-18 | 2026-03-25 | 2026-05-19 | 5 | 2026-05-25 | 44
A45110 | Technical Bid Evaluation (TBE) for Piping Speciality Items_IFD/IFC | 2026-03-25 | 2026-03-31 | 2026-03-25 | 2026-03-31 | 2026-07-14 | 5 | 2026-07-20 | 80
A18360 | Issue Purchase Order to Vendor | 2026-03-25 | 2026-04-01 | 2026-03-25 | 2026-04-01 | 2026-05-26 | 5 | 2026-06-01 | 44
Specialized Items (Strainer/Filter) CS & SS 150 # -300# 2" - 26" = 08 Nos |  | 2026-02-20 | 2026-04-09 | 23-Jan-26 A | 2026-04-09 | 2026-04-17 | 78 | 2026-07-24 | 76
A15910 | Issue RFQ to Bidders | 2026-02-20 | 2026-02-20 | 23-Jan-26 A | 04-Feb-26 A | 2026-04-17 | 21 | 2026-04-17
A56590 | Technical Bid Evaluation (TBE) for Piping Speciality Items_IFR | 2026-02-20 | 2026-02-20 | 05-Feb-26 A | 10-Feb-26 A | 2026-04-17 | 11 | 2026-04-17
A56600 | Technical Bid Evaluation (TBE) for Piping Speciality Items_RCC | 2026-02-20 | 2026-02-20 | 11-Feb-26 A | 17-Feb-26 A | 2026-04-17 | 16 | 2026-04-17
A18280 | Commercial Bid Evaluation(Completion) | 2026-02-20 | 2026-02-26 | 17-Feb-26 A | 2026-02-26 | 2026-04-17 | 30 | 2026-04-23 | 40
A56610 | Technical Bid Evaluation (TBE) for Piping Speciality Items_IFA | 2026-02-20 | 2026-03-09 | 2026-02-20 | 2026-03-09 | 2026-06-08 | 11 | 2026-06-23 | 76
A18260 | Issue Purchase Order to Vendor | 2026-02-27 | 2026-03-27 | 2026-02-27 | 2026-03-27 | 2026-04-24 | 21 | 2026-05-22 | 40
A56620 | Technical Bid Evaluation (TBE) for Piping Speciality Items_RCA | 2026-03-09 | 2026-03-30 | 2026-03-09 | 2026-03-30 | 2026-06-23 | 16 | 2026-07-15 | 76
A56630 | Technical Bid Evaluation (TBE) for Piping Speciality Items_IFD/IFC | 2026-03-31 | 2026-04-09 | 2026-03-31 | 2026-04-09 | 2026-07-15 | 8 | 2026-07-24 | 76
Pressure / Temperature / Level Instruments, Flowmeters |  | 2026-02-20 | 2026-03-25 | 18-Apr-25 A | 2026-03-25 | 2026-04-30 | 235 | 2027-07-20 | 344
Gauges (PG, TG, PDG) PG - 10bar & 40bar = 19 Nos, DP = 05 Nos, TG = 09 Nos |  | 2026-02-20 | 2026-03-25 | 15-Aug-25 A | 2026-03-25 | 2026-04-30 | 88 | 2026-06-02 | 50
A17290 | RFQs to Bid Receipt | 2026-02-20 | 2026-02-20 | 15-Aug-25 A | 27-Aug-25 A | 2026-04-30 | 2 | 2026-04-30
A48180 | Technical Bid Evaluation for Temperature Gauges / Pressure Gauges_IFR | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 26-Dec-25 A | 2026-04-30 | 6 | 2026-04-30
A16340 | Technical Bid Evaluation for Temperature Gauges / Pressure Gauges_RCC | 2026-02-20 | 2026-02-20 | 26-Dec-25 A | 23-Jan-26 A | 2026-04-30 | 6 | 2026-04-30
A16350 | Technical Bid Evaluation for Temperature Gauges / Pressure Gauges_IFA | 2026-02-20 | 2026-02-27 | 2026-02-20 | 2026-02-27 | 2026-04-30 | 6 | 2026-05-08 | 50
A19250 | Commercial Bid Evaluation(Completion) | 2026-02-27 | 2026-03-09 | 2026-02-27 | 2026-03-09 | 2026-05-08 | 6 | 2026-05-15 | 50
A16360 | Technical Bid Evaluation for Temperature Gauges / Pressure Gauges_RCA | 2026-02-27 | 2026-03-09 | 2026-02-27 | 2026-03-09 | 2026-05-18 | 6 | 2026-05-26 | 56
A16370 | Technical Bid Evaluation for Temperature Gauges / Pressure Gauges_IFD/IFC | 2026-03-09 | 2026-03-16 | 2026-03-09 | 2026-03-16 | 2026-05-26 | 6 | 2026-06-02 | 56
A19230 | Issue Purchase Order to Vendor Guages (PG, TG, PDG) | 2026-03-09 | 2026-03-25 | 2026-03-09 | 2026-03-25 | 2026-05-18 | 12 | 2026-06-02 | 50
Flow Elements Venturi |  | 2026-02-20 | 2026-02-20 | 01-Jun-25 A | 11-Dec-25 A | 2026-04-30 | 139 | 2026-04-30
A57610 | Issue RFQ to Bidders | 2026-02-20 | 2026-02-20 | 01-Jun-25 A | 22-Jun-25 A | 2026-04-30 | 20 | 2026-04-30
A16230 | Technical Bid Evaluation for Flow Element (Venturi Tube)_IFR | 2026-02-20 | 2026-02-20 | 01-Sep-25 A | 10-Sep-25 A | 2026-04-30 | 8 | 2026-04-30
A16240 | Technical Bid Evaluation for Flow Element (Venturi Tube)_RCC | 2026-02-20 | 2026-02-20 | 11-Sep-25 A | 15-Sep-25 A | 2026-04-30 | 8 | 2026-04-30
A16250 | Technical Bid Evaluation for Flow Element (Venturi Tube)_IFA | 2026-02-20 | 2026-02-20 | 16-Sep-25 A | 25-Sep-25 A | 2026-04-30 | 8 | 2026-04-30
A16260 | Technical Bid Evaluation for Flow Element (Venturi Tube)_RCA | 2026-02-20 | 2026-02-20 | 01-Oct-25 A | 15-Oct-25 A | 2026-04-30 | 16 | 2026-04-30
A48170 | Technical Bid Evaluation for Flow Element (Venturi Tube)_IFD/IFC | 2026-02-20 | 2026-02-20 | 16-Oct-25 A | 31-Oct-25 A | 2026-04-30 | 8 | 2026-04-30
A57630 | Commercial Bid Evaluation | 2026-02-20 | 2026-02-20 | 01-Nov-25 A | 17-Nov-25 A | 2026-04-30 | 10 | 2026-04-30
A57640 | Issue Purchase Order to Vendor | 2026-02-20 | 2026-02-20 | 27-Nov-25 A | 11-Dec-25 A | 2026-04-30 | 10 | 2026-04-30
Flow Elements Orifice |  | 2026-02-20 | 2026-03-25 | 01-May-25 A | 2026-03-25 | 2026-06-04 | 235 | 2026-07-07 | 74
A57920 | Issue RFQ to Bidders | 2026-02-20 | 2026-02-20 | 01-May-25 A | 15-May-25 A | 2026-06-04 | 20 | 2026-06-04
A16180 | Technical Bid Evaluation for Flow Element (Orifice Plate)_IFR | 2026-02-20 | 2026-02-20 | 01-Sep-25 A | 23-Sep-25 A | 2026-06-04 | 8 | 2026-06-04
A16190 | Technical Bid Evaluation for Flow Element (Orifice Plate)_RCC | 2026-02-20 | 2026-02-20 | 19-Sep-25 A | 30-Sep-25 A | 2026-06-04 | 8 | 2026-06-04
A16200 | Technical Bid Evaluation for Flow Element (Orifice Plate)_IFA | 2026-02-20 | 2026-02-20 | 27-Nov-25 A | 02-Dec-25 A | 2026-06-04 | 8 | 2026-06-04
A57950 | Commercial Bid Evaluation | 2026-02-20 | 2026-02-20 | 01-Dec-25 A | 12-Dec-25 A | 2026-07-03 | 10 | 2026-07-03
A57930 | Issue Purchase Order to Vendor | 2026-02-20 | 2026-02-20 | 16-Dec-25 A | 18-Dec-25 A | 2026-07-03 | 10 | 2026-07-03
A48160 | Technical Bid Evaluation for Flow Element (Orifice Plate)_RCA | 2026-02-20 | 2026-03-13 | 2026-02-20 | 2026-03-13 | 2026-06-04 | 16 | 2026-06-26 | 74
A16220 | Technical Bid Evaluation for Flow Element (Orifice Plate)_IFD/IFC | 2026-03-13 | 2026-03-25 | 2026-03-13 | 2026-03-25 | 2026-06-26 | 8 | 2026-07-07 | 74
PT, TT & DPT [PT 50 Nos, TT 33 Nos, DPT 20 Nos] |  | 2026-02-20 | 2026-03-23 | 18-Apr-25 A | 2026-03-23 | 2027-01-06 | 186 | 2027-07-20 | 347
A21030 | Issue RFQ to Bidders | 2026-02-20 | 2026-02-20 | 18-Apr-25 A | 09-May-25 A | 2027-01-06 | 21 | 2027-01-06
A16130 | Technical Bid Evaluation for Electronic Transmitters_IFR | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 24-Dec-25 A | 2027-01-06 | 3 | 2027-01-06
A16140 | Technical Bid Evaluation for Electronic Transmitters_RCC | 2026-02-20 | 2026-02-20 | 24-Dec-25 A | 17-Jan-26 A | 2027-01-06 | 3 | 2027-01-06
A48150 | Technical Bid Evaluation for Electronic Transmitters_IFA | 2026-02-20 | 2026-02-25 | 2026-02-20 | 2026-02-25 | 2027-01-06 | 3 | 2027-01-12 | 229
A16160 | Technical Bid Evaluation for Electronic Transmitters_RCA | 2026-02-25 | 2026-03-02 | 2026-02-25 | 2026-03-02 | 2027-01-12 | 3 | 2027-01-15 | 229
A16170 | Technical Bid Evaluation for Electronic Transmitters_IFD/IFC | 2026-03-02 | 2026-03-06 | 2026-03-02 | 2026-03-06 | 2027-01-15 | 3 | 2027-01-20 | 229
A21060 | Commercial Bid Evaluation(Completion) | 2026-03-06 | 2026-03-11 | 2026-03-06 | 2026-03-11 | 2027-07-05 | 3 | 2027-07-08 | 347
A21040 | Issue Purchase Order to Vendor | 2026-03-11 | 2026-03-23 | 2026-03-11 | 2026-03-23 | 2027-07-09 | 8 | 2027-07-20 | 347
Instrument Bulk Material |  | 2026-02-20 | 2026-03-12 | 01-Feb-25 A | 2026-03-12 | 2026-03-05 | 230 | 2027-01-20 | 224
TA_Instrument Bulk Materia l(Single & Multicore = Approx. 78,130 Mtr, FO Cables JB & Cable Trays)) |  | 2026-02-20 | 2026-02-20 | 01-Feb-25 A | 19-Mar-25 A | 2026-03-27 | 53 | 2026-03-27
A22030 | Issue RFQs to Bidders | 2026-02-20 | 2026-02-20 | 01-Feb-25 A | 11-Feb-25 A | 2026-03-27 | 21 | 2026-03-27
A22050 | TBE for Instrument Bulk Material (TA) | 2026-02-20 | 2026-02-20 | 12-Feb-25 A | 21-Feb-25 A | 2026-03-27 | 15 | 2026-03-27
A22040 | Vendor Quote Received | 2026-02-20 | 2026-02-20 | 24-Feb-25 A | 04-Mar-25 A | 2026-03-27 | 10 | 2026-03-27
A22070 | Issue Purchase Order to Vendor | 2026-02-20 | 2026-02-20 | 05-Mar-25 A | 19-Mar-25 A | 2026-03-27 | 7 | 2026-03-27
Analyzer |  | 2026-02-20 | 2026-02-20 | 01-May-25 A | 08-Jun-25 A | 2026-11-28 | 116 | 2026-11-28
A48190 | Technical Bid Evaluation for Analyzers_RCC | 2026-02-20 | 2026-02-20 | 01-May-25 A | 23-May-25 A | 2026-11-28 | 19 | 2026-11-28
A16400 | Technical Bid Evaluation for Analyzers_IFA | 2026-02-20 | 2026-02-20 | 01-May-25 A | 23-May-25 A | 2026-11-28 | 19 | 2026-11-28
A16410 | Technical Bid Evaluation for Analyzers_RCA | 2026-02-20 | 2026-02-20 | 01-May-25 A | 23-May-25 A | 2026-11-28 | 19 | 2026-11-28
A16420 | Technical Bid Evaluation for Analyzers_IFD/IFC | 2026-02-20 | 2026-02-20 | 01-May-25 A | 23-May-25 A | 2026-11-28 | 19 | 2026-11-28
A16380 | Technical Bid Evaluation for Analyzers_IFR | 2026-02-20 | 2026-02-20 | 01-May-25 A | 25-May-25 A | 2026-11-28 | 8 | 2026-11-28
A57570 | Issue RFQ to Bidders | 2026-02-20 | 2026-02-20 | 01-May-25 A | 25-May-25 A | 2026-11-28 | 20 | 2026-11-28
A57590 | Commercial Bid Evaluation | 2026-02-20 | 2026-02-20 | 25-May-25 A | 01-Jun-25 A | 2026-11-28 | 15 | 2026-11-28
A57600 | Issue Purchase Order to Vendor | 2026-02-20 | 2026-02-20 | 02-Jun-25 A | 08-Jun-25 A | 2026-11-28 | 14 | 2026-11-28
Cable Tray and Instrument Junction Box (Perforated Cable tray Heavy duty = 5982 Mtrs, JBs = 73 Nos) |  | 2026-02-20 | 2026-03-12 | 20-Jul-25 A | 2026-03-12 | 2026-03-05 | 168 | 2027-01-20 | 224
A17230 | Issue RFQ to Bidders | 2026-02-20 | 2026-02-20 | 20-Jul-25 A | 25-Oct-25 A | 2026-03-05 | 21 | 2026-03-05
A16830 | Technical Bid Evaluation for Junction Boxes_IFR | 2026-02-20 | 2026-02-20 | 28-Nov-25 A | 12-Dec-25 A | 2026-03-05 | 5 | 2026-03-05
A16840 | Technical Bid Evaluation for Junction Boxes_RCC | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 10-Jan-26 A | 2026-03-05 | 5 | 2026-03-05
A20070 | Commercial Bid Evaluation(Completion) | 2026-02-26 | 2026-02-26 | 05-Jan-26 A | 14-Jan-26 A | 2026-03-12 | 5 | 2026-03-12
A20050 | Issue Purchase Order to Vendor | 2026-02-26 | 2026-02-26 | 15-Jan-26 A | 21-Jan-26 A | 2026-03-12 | 5 | 2026-03-12
A16850 | Technical Bid Evaluation for Junction Boxes_IFA | 2026-02-20 | 2026-02-26 | 2026-02-20 | 2026-02-26 | 2026-03-05 | 5 | 2026-03-11 | 9
A16860 | Technical Bid Evaluation for Junction Boxes_RCA | 2026-02-27 | 2026-03-05 | 2026-02-27 | 2026-03-05 | 2027-01-07 | 5 | 2027-01-13 | 224
A16870 | Technical Bid Evaluation for Junction Boxes_IFD/IFC | 2026-03-06 | 2026-03-12 | 2026-03-06 | 2026-03-12 | 2027-01-14 | 5 | 2027-01-20 | 224
Magnetic Level Gauge ( 09 Nos) |  | 2026-02-20 | 2026-02-26 | 18-Jul-25 A | 2026-02-26 | 2026-03-25 | 160 | 2026-03-31 | 23
A21270 | Issue RFQ to Bidders | 2026-02-20 | 2026-02-20 | 18-Jul-25 A | 06-Aug-25 A | 2026-03-25 | 3 | 2026-03-25
A16430 | Technical Bid Evaluation for Level Gauges (Magnetic Type)_IFR | 2026-02-20 | 2026-02-20 | 07-Aug-25 A | 20-Aug-25 A | 2026-03-25 | 3 | 2026-03-25
A16440 | Technical Bid Evaluation for Level Gauges (Magnetic Type)_RCC | 2026-02-20 | 2026-02-20 | 21-Aug-25 A | 29-Aug-25 A | 2026-03-25 | 3 | 2026-03-25
A48200 | Technical Bid Evaluation for Level Gauges (Magnetic Type)_IFA | 2026-02-20 | 2026-02-20 | 30-Aug-25 A | 15-Sep-25 A | 2026-03-25 | 3 | 2026-03-25
A16460 | Technical Bid Evaluation for Level Gauges (Magnetic Type)_RCA | 2026-02-20 | 2026-02-20 | 16-Sep-25 A | 30-Sep-25 A | 2026-03-25 | 3 | 2026-03-25
A16470 | Technical Bid Evaluation for Level Gauges (Magnetic Type)_IFD/IFC | 2026-02-20 | 2026-02-20 | 01-Oct-25 A | 30-Oct-25 A | 2026-03-25 | 3 | 2026-03-25
A21300 | Commercial Bid Evaluation(Completion) | 2026-02-20 | 2026-02-20 | 10-Nov-25 A | 21-Nov-25 A | 2026-03-25 | 3 | 2026-03-25
A21280 | Issue Purchase Order to Vendor | 2026-02-20 | 2026-02-26 | 2026-02-20 | 2026-02-26 | 2026-03-25 | 5 | 2026-03-31 | 23
Fibre Optic Cable (Armoured, Telecom/IT/MAS) |  | 2026-02-20 | 2026-02-20 | 01-Jun-25 A | 18-Aug-25 A | 2026-03-19 | 56 | 2026-03-19
A17170 | RFQs to Bid receipt | 2026-02-20 | 2026-02-20 | 01-Jun-25 A | 21-Jun-25 A | 2026-03-19 | 21 | 2026-03-19
A57550 | Technical Bid Evaluation for Instrument Cables_IFD/IFC | 2026-02-20 | 2026-02-20 | 30-Jul-25 A | 31-Jul-25 A | 2026-03-19 | 6 | 2026-03-19
A57510 | Technical Bid Evaluation for Instrument Cables_IFR | 2026-02-20 | 2026-02-20 | 30-Jul-25 A | 31-Jul-25 A | 2026-03-19 | 6 | 2026-03-19
A57520 | Technical Bid Evaluation for Instrument Cables_RCC | 2026-02-20 | 2026-02-20 | 30-Jul-25 A | 31-Jul-25 A | 2026-03-19 | 6 | 2026-03-19
A57530 | Technical Bid Evaluation for Instrument Cables_IFA | 2026-02-20 | 2026-02-20 | 30-Jul-25 A | 31-Jul-25 A | 2026-03-19 | 6 | 2026-03-19
A57540 | Technical Bid Evaluation for Instrument Cables_RCA | 2026-02-20 | 2026-02-20 | 30-Jul-25 A | 31-Jul-25 A | 2026-03-19 | 6 | 2026-03-19
A18680 | Commercial Bid Evaluation(Completion) | 2026-02-20 | 2026-02-20 | 01-Aug-25 A | 08-Aug-25 A | 2026-03-19 | 6 | 2026-03-19
A18660 | Issue Purchase Order to Vendor | 2026-02-20 | 2026-02-20 | 09-Aug-25 A | 18-Aug-25 A | 2026-03-19 | 6 | 2026-03-19
Earthing & Power Cables |  | 2026-02-20 | 2026-02-20 | 18-Jul-25 A | 24-Oct-25 A | 2026-05-22 | 139 | 2026-07-13
Power Cables ( 11kV & 33kV) |  | 2026-02-20 | 2026-02-20 | 01-Aug-25 A | 03-Sep-25 A | 2026-07-13 | 129 | 2026-07-13
A58690 | Issue RFQ to Bidders | 2026-02-20 | 2026-02-20 | 01-Aug-25 A | 20-Aug-25 A | 2026-07-13 | 21 | 2026-07-13
A58700 | Bid Evaluation(Completion) | 2026-02-20 | 2026-02-20 | 04-Aug-25 A | 25-Aug-25 A | 2026-07-13 | 30 | 2026-07-13
A58710 | Commercial Bid Evaluation(Completion) | 2026-02-20 | 2026-02-20 | 06-Aug-25 A | 27-Aug-25 A | 2026-07-13 | 25 | 2026-07-13
A58720 | Issue Purchase Order to Vendor | 2026-02-20 | 2026-02-20 | 25-Aug-25 A | 03-Sep-25 A | 2026-07-13 | 14 | 2026-07-13
Earthing and Power Cables |  | 2026-02-20 | 2026-02-20 | 18-Jul-25 A | 24-Oct-25 A | 2026-05-22 | 100 | 2026-06-10
A16450 | Issue RFQ to Bidders | 2026-02-20 | 2026-02-20 | 18-Jul-25 A | 20-Aug-25 A | 2026-05-22 | 21 | 2026-05-22
A13230 | Technical Bid Evaluation For Power, Control And Earthing Cables_IFR | 2026-02-20 | 2026-02-20 | 21-Aug-25 A | 29-Aug-25 A | 2026-05-22 | 3 | 2026-05-22
A13240 | Technical Bid Evaluation For Power, Control And Earthing Cables_RCC | 2026-02-20 | 2026-02-20 | 30-Aug-25 A | 10-Sep-25 A | 2026-05-22 | 3 | 2026-05-22
A13250 | Technical Bid Evaluation For Power, Control And Earthing Cables_IFA | 2026-02-20 | 2026-02-20 | 11-Sep-25 A | 17-Sep-25 A | 2026-06-10 | 3 | 2026-06-10
A13260 | Technical Bid Evaluation For Power, Control And Earthing Cables_RCA | 2026-02-20 | 2026-02-20 | 19-Sep-25 A | 30-Sep-25 A | 2026-06-10 | 3 | 2026-06-10
A13270 | Technical Bid Evaluation For Power, Control And Earthing Cables_IFD/IFC | 2026-02-20 | 2026-02-20 | 01-Oct-25 A | 07-Oct-25 A | 2026-06-10 | 3 | 2026-06-10
A20610 | Commercial Bid Evaluation(Completion) | 2026-02-20 | 2026-02-20 | 07-Oct-25 A | 14-Oct-25 A | 2026-05-22 | 3 | 2026-05-22
A20590 | Issue Purchase Order to Vendor | 2026-02-20 | 2026-02-20 | 15-Oct-25 A | 24-Oct-25 A | 2026-05-22 | 3 | 2026-05-22
Electrical Bulk |  | 2026-02-20 | 2026-05-29 | 15-Jan-25 A | 2026-05-29 | 2026-04-14 | 196 | 2026-07-27 | 41
TA_Electrical Bulk Material (Earthing ,FO, Power Cables) |  | 2026-02-20 | 2026-02-20 | 15-Jan-25 A | 09-Mar-25 A | 2026-04-30 | 91 | 2026-04-30
A17890 | Issue RFQ to Bidders | 2026-02-20 | 2026-02-20 | 15-Jan-25 A | 08-Feb-25 A | 2026-04-30 | 20 | 2026-04-30
A17900 | Vendor Quote Received | 2026-02-20 | 2026-02-20 | 10-Feb-25 A | 19-Feb-25 A | 2026-04-30 | 30 | 2026-04-30
A17920 | TBE | 2026-02-20 | 2026-02-20 | 20-Feb-25 A | 28-Feb-25 A | 2026-04-30 | 30 | 2026-04-30
A17910 | Negotiations and PO Placement (33 KVA) | 2026-02-20 | 2026-02-20 | 03-Mar-25 A | 09-Mar-25 A | 2026-04-30 | 15 | 2026-04-30
Cable Trays, JBs, Conduit Pipe, Cable Lugs, etc |  | 2026-02-20 | 2026-05-13 | 2026-02-20 | 2026-05-13 | 2026-04-14 | 59 | 2026-07-03 | 37
A9450 | Issue RFQ to Bidders | 2026-02-20 | 2026-03-12 | 2026-02-20 | 2026-03-12 | 2026-04-14 | 15 | 2026-05-04 | 37
A20660 | Bid Evaluation(Completion) | 2026-03-13 | 2026-04-02 | 2026-03-13 | 2026-04-02 | 2026-05-05 | 15 | 2026-05-25 | 37
A20670 | Commercial Bid Evaluation(Completion) | 2026-04-03 | 2026-04-23 | 2026-04-03 | 2026-04-23 | 2026-05-26 | 15 | 2026-06-15 | 37
A20650 | Issue Purchase Order to Vendor | 2026-04-24 | 2026-05-13 | 2026-04-24 | 2026-05-13 | 2026-06-16 | 14 | 2026-07-03 | 37
LCS & Snap Switches |  | 2026-02-20 | 2026-05-29 | 2026-02-20 | 2026-05-29 | 2026-04-20 | 71 | 2026-07-27 | 41
A21690 | Issue RFQ to Bidders | 2026-02-20 | 2026-03-20 | 2026-02-20 | 2026-03-20 | 2026-04-20 | 21 | 2026-05-18 | 41
A21710 | Bid Evaluation(Completion) | 2026-03-23 | 2026-04-20 | 2026-03-23 | 2026-04-20 | 2026-05-19 | 21 | 2026-06-16 | 41
A21720 | Commercial Bid Evaluation(Completion) | 2026-04-21 | 2026-05-11 | 2026-04-21 | 2026-05-11 | 2026-06-17 | 15 | 2026-07-07 | 41
A21700 | Issue Purchase Order to Vendor | 2026-05-12 | 2026-05-29 | 2026-05-12 | 2026-05-29 | 2026-07-08 | 14 | 2026-07-27 | 41
Main Automation Equipment |  | 2026-02-20 | 2026-04-02 | 01-Feb-25 A | 2026-04-02 | 2026-03-18 | 245 | 2026-07-15 | 73
On Off Valve / Control Valves |  | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 20-Oct-25 A | 2026-03-25 | 181 | 2026-05-12
ESD Valve |  | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 16-May-25 A | 2026-03-25 | 181 | 2026-04-18
A59730 | Issue RFQ to Bidders | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 02-May-25 A | 2026-03-25 | 21 | 2026-03-25
A59760 | Technical Bid Evaluation for ESD_IFR | 2026-02-20 | 2026-02-20 | 02-May-25 A | 05-May-25 A | 2026-03-25 | 11 | 2026-03-25
A59770 | Technical Bid Evaluation for ESD_RCC | 2026-02-20 | 2026-02-20 | 05-May-25 A | 07-May-25 A | 2026-03-25 | 16 | 2026-03-25
A59780 | Technical Bid Evaluation for ESD_IFA | 2026-02-20 | 2026-02-20 | 08-May-25 A | 09-May-25 A | 2026-03-25 | 11 | 2026-03-25
A59790 | Technical Bid Evaluation for ESD_RCA | 2026-02-20 | 2026-02-20 | 10-May-25 A | 12-May-25 A | 2026-04-18 | 16 | 2026-04-18
A59800 | Technical Bid Evaluation for ESD_IFD/IFC | 2026-02-20 | 2026-02-20 | 13-May-25 A | 14-May-25 A | 2026-04-18 | 8 | 2026-04-18
A59750 | Commercial Bid Evaluation(Completion) | 2026-02-20 | 2026-02-20 | 14-May-25 A | 15-May-25 A | 2026-03-25 | 21 | 2026-03-25
A59740 | Issue Purchase Order to Vendor for ESD | 2026-02-20 | 2026-02-20 | 15-May-25 A | 16-May-25 A | 2026-03-25 | 21 | 2026-03-25
Control Valves (1" - 24" Rating 150, 300 & 2500 = 32 Nos) + SDV |  | 2026-02-20 | 2026-02-20 | 21-Apr-25 A | 20-Oct-25 A | 2026-03-25 | 171 | 2026-05-12
A16750 | Issue RFQ to Bidders | 2026-02-20 | 2026-02-20 | 21-Apr-25 A | 15-May-25 A | 2026-03-25 | 21 | 2026-03-25
A22100 | Commercial Bid Evaluation(Completion) | 2026-02-20 | 2026-02-20 | 17-Sep-25 A | 18-Sep-25 A | 2026-03-25 | 21 | 2026-03-25
A16480 | Technical Bid Evaluation for Control Valves_IFR | 2026-02-20 | 2026-02-20 | 23-Aug-25 A | 18-Sep-25 A | 2026-03-25 | 8 | 2026-03-25
A16490 | Technical Bid Evaluation for Control Valves_RCC | 2026-02-20 | 2026-02-20 | 23-Aug-25 A | 18-Sep-25 A | 2026-03-25 | 8 | 2026-03-25
A16500 | Technical Bid Evaluation for Control Valves_IFA | 2026-02-20 | 2026-02-20 | 23-Aug-25 A | 18-Sep-25 A | 2026-03-25 | 8 | 2026-03-25
A48210 | Technical Bid Evaluation for Control Valves_RCA | 2026-02-20 | 2026-02-20 | 23-Aug-25 A | 18-Sep-25 A | 2026-03-25 | 8 | 2026-03-25
A16520 | Technical Bid Evaluation for Control Valves_IFD/IFC | 2026-02-20 | 2026-02-20 | 23-Aug-25 A | 18-Sep-25 A | 2026-03-25 | 8 | 2026-03-25
A22110 | Issue Purchase Order to Vendor for Control Valves | 2026-02-20 | 2026-02-20 | 01-Oct-25 A | 20-Oct-25 A | 2026-05-12 | 21 | 2026-05-12
MOVs |  | 2026-02-20 | 2026-02-20 | 21-Apr-25 A | 10-Sep-25 A | 2026-05-11 | 121 | 2026-05-11
MOVs [Ball Type 24" 150# = 01 No] |  | 2026-02-20 | 2026-02-20 | 21-Apr-25 A | 10-Sep-25 A | 2026-05-11 | 121 | 2026-05-11
A17050 | RFQs to Bid Receipt | 2026-02-20 | 2026-02-20 | 21-Apr-25 A | 15-May-25 A | 2026-05-11 | 21 | 2026-05-11
A48230 | Technical Bid Evaluation for Motor Operated Valves_IFR | 2026-02-20 | 2026-02-20 | 16-May-25 A | 22-Aug-25 A | 2026-05-11 | 11 | 2026-05-11
A16650 | Technical Bid Evaluation for Motor Operated Valves_IFA | 2026-02-20 | 2026-02-20 | 19-Aug-25 A | 29-Aug-25 A | 2026-05-11 | 8 | 2026-05-11
A18620 | Commercial Bid Evaluation(Completion) | 2026-02-20 | 2026-02-20 | 19-Aug-25 A | 01-Sep-25 A | 2026-05-11 | 5 | 2026-05-11
A18600 | Issue Purchase Order to Vendor for MOVs | 2026-02-20 | 2026-02-20 | 26-Aug-25 A | 02-Sep-25 A | 2026-05-11 | 14 | 2026-05-11
A16640 | Technical Bid Evaluation for Motor Operated Valves_RCC | 2026-02-20 | 2026-02-20 | 22-Aug-25 A | 02-Sep-25 A | 2026-05-11 | 6 | 2026-05-11
A16660 | Technical Bid Evaluation for Motor Operated Valves_RCA | 2026-02-20 | 2026-02-20 | 30-Aug-25 A | 06-Sep-25 A | 2026-05-11 | 6 | 2026-05-11
A16670 | Technical Bid Evaluation for Motor Operated Valves_IFD/IFC | 2026-02-20 | 2026-02-20 | 07-Sep-25 A | 10-Sep-25 A | 2026-05-11 | 5 | 2026-05-11
Machine Condition Monitoring System (MCMS) |  | 2026-02-20 | 2026-02-20 | 01-Feb-25 A | 01-Jun-25 A | 2026-03-27 | 117 | 2026-07-15
TA_MCMS System Modification - Bently Nevada |  | 2026-02-20 | 2026-02-20 | 01-Feb-25 A | 15-Mar-25 A | 2026-03-27 | 48 | 2026-03-27
A37160 | Issue RFQ to Bidders | 2026-02-20 | 2026-02-20 | 01-Feb-25 A | 22-Feb-25 A | 2026-03-27 | 20 | 2026-03-27
A57450 | TBE for ICT System Modification_Free Issue Material | 2026-02-20 | 2026-02-20 | 23-Feb-25 A | 09-Mar-25 A | 2026-03-27 | 23 | 2026-03-27
A37190 | Issue Purchase Order to Vendor | 2026-02-20 | 2026-02-20 | 10-Mar-25 A | 15-Mar-25 A | 2026-03-27 | 5 | 2026-03-27
Machine Condition Monitoring System |  | 2026-02-20 | 2026-02-20 | 01-Apr-25 A | 01-Jun-25 A | 2026-07-15 | 99 | 2026-07-15
A17110 | Issue RFQ to Bidders | 2026-02-20 | 2026-02-20 | 01-Apr-25 A | 20-Apr-25 A | 2026-07-15 | 20 | 2026-07-15
A19930 | Issue Purchase Order to Vendor for MCMS | 2026-02-20 | 2026-02-20 | 08-May-25 A | 15-May-25 A | 2026-07-15 | 21 | 2026-07-15
A58590 | Technical Bid Evaluation for MCMS System_IFR | 2026-02-20 | 2026-02-20 | 01-May-25 A | 15-May-25 A | 2026-07-15 | 11 | 2026-07-15
A58600 | Technical Bid Evaluation for MCMS System_RCC | 2026-02-20 | 2026-02-20 | 16-May-25 A | 19-May-25 A | 2026-07-15 | 16 | 2026-07-15
A58610 | Technical Bid Evaluation for MCMSSystem_IFA | 2026-02-20 | 2026-02-20 | 16-May-25 A | 19-May-25 A | 2026-07-15 | 11 | 2026-07-15
A58620 | Technical Bid Evaluation for MCMS System_RCA | 2026-02-20 | 2026-02-20 | 16-May-25 A | 19-May-25 A | 2026-07-15 | 16 | 2026-07-15
A58630 | Technical Bid Evaluation for MCMS System_IFD/IFC | 2026-02-20 | 2026-02-20 | 20-May-25 A | 25-May-25 A | 2026-07-15 | 8 | 2026-07-15
A19950 | Commercial Bid Evaluation(Completion) | 2026-02-20 | 2026-02-20 | 26-May-25 A | 01-Jun-25 A | 2026-07-15 | 21 | 2026-07-15
IPCS Modification (ABB) |  | 2026-02-20 | 2026-02-20 | 01-Feb-25 A | 25-Jul-25 A | 2026-03-27 | 94 | 2026-05-04
TA_Integrated Protection and Control System - ABB/Hitachi |  | 2026-02-20 | 2026-02-20 | 01-Feb-25 A | 18-Mar-25 A | 2026-03-27 | 37 | 2026-03-27
A20950 | Issue RFQ to Bidders | 2026-02-20 | 2026-02-20 | 01-Feb-25 A | 25-Feb-25 A | 2026-03-27 | 20 | 2026-03-27
A57390 | TBE for Electrical System Modification_ Free Issue Material | 2026-02-20 | 2026-02-20 | 26-Feb-25 A | 09-Mar-25 A | 2026-03-27 | 8 | 2026-03-27
A20960 | Issue Purchase Order to Vendor | 2026-02-20 | 2026-02-20 | 10-Mar-25 A | 18-Mar-25 A | 2026-03-27 | 7 | 2026-03-27
Integrated Protection and Control System |  | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 25-Jul-25 A | 2026-05-04 | 82 | 2026-05-04
A23820 | Issue RFQ to Bidders | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 01-May-25 A | 2026-05-04 | 20 | 2026-05-04
A58540 | Technical Bid Evaluation for IPCS_IFR | 2026-02-20 | 2026-02-20 | 02-May-25 A | 10-May-25 A | 2026-05-04 | 8 | 2026-05-04
A58550 | Technical Bid Evaluation for IPCS_RCC | 2026-02-20 | 2026-02-20 | 11-May-25 A | 20-May-25 A | 2026-05-04 | 16 | 2026-05-04
A58560 | Technical Bid Evaluation for IPCS_IFA | 2026-02-20 | 2026-02-20 | 21-May-25 A | 26-May-25 A | 2026-05-04 | 11 | 2026-05-04
A58570 | Technical Bid Evaluation for IPCS_RCA | 2026-02-20 | 2026-02-20 | 27-May-25 A | 31-May-25 A | 2026-05-04 | 16 | 2026-05-04
A58580 | Technical Bid Evaluation for IPCS_IFD/IFC | 2026-02-20 | 2026-02-20 | 01-Jun-25 A | 04-Jun-25 A | 2026-05-04 | 8 | 2026-05-04
A23850 | Commercial Bid Evaluation(Completion) | 2026-02-20 | 2026-02-20 | 07-Jul-25 A | 16-Jul-25 A | 2026-05-04 | 10 | 2026-05-04
A23830 | Issue Purchase Order to Vendor for IPCS | 2026-02-20 | 2026-02-20 | 17-Jul-25 A | 25-Jul-25 A | 2026-05-04 | 5 | 2026-05-04
OTS |  | 2026-02-20 | 2026-02-20 | 01-Feb-25 A | 20-Aug-25 A | 2026-03-20 | 98 | 2026-03-27
TA_SCMS Modification - Siemens |  | 2026-02-20 | 2026-02-20 | 01-Feb-25 A | 03-Mar-25 A | 2026-03-27 | 27 | 2026-03-27
A24190 | Issue RFQ to Bidders | 2026-02-20 | 2026-02-20 | 01-Feb-25 A | 10-Feb-25 A | 2026-03-27 | 10 | 2026-03-27
A57360 | TBE for Electrical System Modification_ Free Issue Material | 2026-02-20 | 2026-02-20 | 11-Feb-25 A | 24-Feb-25 A | 2026-03-27 | 11 | 2026-03-27
A24200 | Issue Purchase Order to Vendor | 2026-02-20 | 2026-02-20 | 25-Feb-25 A | 03-Mar-25 A | 2026-03-27 | 7 | 2026-03-27
SCMS |  | 2026-02-20 | 2026-02-20 | 19-Mar-25 A | 20-Aug-25 A | 2026-03-20 | 98 | 2026-03-20
A60190 | Issue RFQ to Bidders | 2026-02-20 | 2026-02-20 | 19-Mar-25 A | 20-May-25 A | 2026-03-20 | 21 | 2026-03-20
A60220 | Technical Bid Evaluation for SCMS_IFR | 2026-02-20 | 2026-02-20 | 21-May-25 A | 01-Jun-25 A | 2026-03-20 | 11 | 2026-03-20
A60230 | Technical Bid Evaluation for SCMS_RCC | 2026-02-20 | 2026-02-20 | 02-Jun-25 A | 12-Jun-25 A | 2026-03-20 | 6 | 2026-03-20
A60240 | Technical Bid Evaluation for SCMS_IFA | 2026-02-20 | 2026-02-20 | 13-Jun-25 A | 19-Jun-25 A | 2026-03-20 | 6 | 2026-03-20
A60250 | Technical Bid Evaluation for SCMS_RCA | 2026-02-20 | 2026-02-20 | 20-Jun-25 A | 26-Jun-25 A | 2026-03-20 | 6 | 2026-03-20
A60260 | Technical Bid Evaluation for SCMS_IFD/IFC | 2026-02-20 | 2026-02-20 | 27-Jun-25 A | 03-Jul-25 A | 2026-03-20 | 6 | 2026-03-20
A60210 | Commercial Bid Evaluation(Completion) | 2026-02-20 | 2026-02-20 | 04-Jul-25 A | 15-Jul-25 A | 2026-03-20 | 6 | 2026-03-20
A60200 | Issue Purchase Order to Vendor for SCMS | 2026-02-20 | 2026-02-20 | 16-Jul-25 A | 20-Aug-25 A | 2026-03-20 | 6 | 2026-03-20
ICSS (Integrated Control and Safety System) including sys. Modifications |  | 2026-02-20 | 2026-02-20 | 07-Feb-25 A | 20-Jun-25 A | 2026-03-18 | 128 | 2026-03-27
Integrated Control and Safety System GF |  | 2026-02-20 | 2026-02-20 | 15-May-25 A | 20-Jun-25 A | 2026-03-18 | 105 | 2026-03-18
A16880 | Technical Bid Evaluation for ICSS System_IFR | 2026-02-20 | 2026-02-20 | 26-May-25 A | 28-May-25 A | 2026-03-18 | 11 | 2026-03-18
A23940 | Issue RFQ to Bidders | 2026-02-20 | 2026-02-20 | 15-May-25 A | 30-May-25 A | 2026-03-18 | 14 | 2026-03-18
A16890 | Technical Bid Evaluation for ICSS System_RCC | 2026-02-20 | 2026-02-20 | 29-May-25 A | 30-May-25 A | 2026-03-18 | 16 | 2026-03-18
A16900 | Technical Bid Evaluation for ICSS System_IFA | 2026-02-20 | 2026-02-20 | 30-May-25 A | 31-May-25 A | 2026-03-18 | 11 | 2026-03-18
A16910 | Technical Bid Evaluation for ICSS System_RCA | 2026-02-20 | 2026-02-20 | 31-May-25 A | 01-Jun-25 A | 2026-03-18 | 16 | 2026-03-18
A16920 | Technical Bid Evaluation for ICSS System_IFD/IFC | 2026-02-20 | 2026-02-20 | 01-Jun-25 A | 06-Jun-25 A | 2026-03-18 | 8 | 2026-03-18
A23970 | Commercial Bid Evaluation(Completion) | 2026-02-20 | 2026-02-20 | 07-Jun-25 A | 13-Jun-25 A | 2026-03-18 | 21 | 2026-03-18
A23950 | Issue Purchase Order to Vendor for ICSS | 2026-02-20 | 2026-02-20 | 14-Jun-25 A | 20-Jun-25 A | 2026-03-18 | 14 | 2026-03-18
TA_Integrated Control & Safety System BF - Honeywell |  | 2026-02-20 | 2026-02-20 | 07-Feb-25 A | 10-Mar-25 A | 2026-03-27 | 27 | 2026-03-27
A19770 | Issue RFQ to Bidders | 2026-02-20 | 2026-02-20 | 07-Feb-25 A | 17-Feb-25 A | 2026-03-27 | 10 | 2026-03-27
A56210 | TBE for ICT System Modification_Free Issue Material | 2026-02-20 | 2026-02-20 | 18-Feb-25 A | 28-Feb-25 A | 2026-03-27 | 11 | 2026-03-27
A19780 | Issue Purchase Order to Vendor | 2026-02-20 | 2026-02-20 | 01-Mar-25 A | 10-Mar-25 A | 2026-03-27 | 7 | 2026-03-27
Instrument Cables |  | 2026-02-20 | 2026-03-12 | 01-Nov-25 A | 2026-03-12 | 2026-03-23 | 80 | 2026-04-10 | 21
Instrument Cable (Single & Multicore = Approx. 78,130 Mtr) |  | 2026-02-20 | 2026-03-12 | 01-Nov-25 A | 2026-03-12 | 2026-03-23 | 80 | 2026-04-10 | 21
A21190 | Issue RFQ to Bidders | 2026-02-20 | 2026-02-20 | 01-Nov-25 A | 11-Nov-25 A | 2026-03-23 | 5 | 2026-03-23
A16780 | Technical Bid Evaluation for Instrument Cables_IFR | 2026-02-20 | 2026-02-20 | 26-Jan-26 A | 31-Jan-26 A | 2026-03-23 | 5 | 2026-03-23
A16790 | Technical Bid Evaluation for Instrument Cables_RCC | 2026-02-20 | 2026-02-20 | 02-Feb-26 A | 06-Feb-26 A | 2026-03-23 | 5 | 2026-03-23
A16800 | Technical Bid Evaluation for Instrument Cables_IFA | 2026-02-20 | 2026-02-26 | 06-Feb-26 A | 2026-02-26 | 2026-03-23 | 5 | 2026-03-27 | 21
A21220 | Commercial Bid Evaluation(Completion) | 2026-02-27 | 2026-03-05 | 2026-02-27 | 2026-03-05 | 2026-03-30 | 5 | 2026-04-03 | 21
A16810 | Technical Bid Evaluation for Instrument Cables_RCA | 2026-02-27 | 2026-03-05 | 2026-02-27 | 2026-03-05 | 2026-03-30 | 5 | 2026-04-03 | 21
A21200 | Issue Purchase Order to Vendor | 2026-03-06 | 2026-03-12 | 2026-03-06 | 2026-03-12 | 2026-04-06 | 5 | 2026-04-10 | 21
A16820 | Technical Bid Evaluation for Instrument Cables_IFD/IFC | 2026-03-06 | 2026-03-12 | 2026-03-06 | 2026-03-12 | 2026-04-06 | 5 | 2026-04-10 | 21
Local Fire Control Panel including F & G Detectors |  | 2026-02-20 | 2026-02-20 | 20-Jun-25 A | 12-Dec-25 A | 2026-05-05 | 173 | 2026-05-05
Fire Detection Alarm System and Local Fire Control Panel (Clean Agent Unit) |  | 2026-02-20 | 2026-02-20 | 20-Jun-25 A | 12-Dec-25 A | 2026-05-05 | 173 | 2026-05-05
A16930 | Issue RFQ to Bidders | 2026-02-20 | 2026-02-20 | 20-Jun-25 A | 14-Aug-25 A | 2026-05-05 | 20 | 2026-05-05
A19660 | Bid Evaluation(Completion) | 2026-02-20 | 2026-02-20 | 01-Nov-25 A | 14-Nov-25 A | 2026-05-05 | 15 | 2026-05-05
A19670 | Commercial Bid Evaluation(Completion) | 2026-02-20 | 2026-02-20 | 28-Nov-25 A | 10-Dec-25 A | 2026-05-05 | 18 | 2026-05-05
A19650 | Issue Purchase Order to Vendor for Fire Detection, Local Fire Control and Clean Agent | 2026-02-20 | 2026-02-20 | 01-Dec-25 A | 12-Dec-25 A | 2026-05-05 | 6 | 2026-05-05
PSVs |  | 2026-02-20 | 2026-03-25 | 15-Oct-25 A | 2026-03-25 | 2026-03-20 | 89 | 2026-04-22 | 20
PSVs (1"x2" upto 8"x10" - CS Rating 150/150, 300/150 = 22 Nos) |  | 2026-02-20 | 2026-03-25 | 15-Oct-25 A | 2026-03-25 | 2026-03-20 | 89 | 2026-04-22 | 20
A21110 | Issue RFQ to Bidders | 2026-02-20 | 2026-02-20 | 15-Oct-25 A | 27-Oct-25 A | 2026-03-20 | 5 | 2026-03-20
A21130 | Bid Evaluation(Completion) | 2026-02-20 | 2026-03-05 | 15-Feb-26 A | 2026-03-05 | 2026-03-20 | 10 | 2026-04-02 | 20
A21140 | Commercial Bid Evaluation(Completion) | 2026-03-06 | 2026-03-16 | 2026-03-06 | 2026-03-16 | 2026-04-03 | 7 | 2026-04-13 | 20
A21120 | Issue Purchase Order to Vendor | 2026-03-17 | 2026-03-25 | 2026-03-17 | 2026-03-25 | 2026-04-14 | 7 | 2026-04-22 | 20
Sampling System |  | 2026-02-20 | 2026-02-20 | 12-Feb-25 A | 18-Mar-25 A | 2026-03-27 | 53 | 2026-03-27
TA_CGC Turbine Software Upgrade - HMI |  | 2026-02-20 | 2026-02-20 | 15-Feb-25 A | 18-Mar-25 A | 2026-03-27 | 31 | 2026-03-27
A37240 | Issue RFQ to Bidders | 2026-02-20 | 2026-02-20 | 15-Feb-25 A | 25-Feb-25 A | 2026-03-27 | 10 | 2026-03-27
A57300 | TBE for ICT System Modification_Free Issue Material | 2026-02-20 | 2026-02-20 | 26-Feb-25 A | 07-Mar-25 A | 2026-03-27 | 11 | 2026-03-27
A37270 | Issue Purchase Order to Vendor | 2026-02-20 | 2026-02-20 | 08-Mar-25 A | 18-Mar-25 A | 2026-03-27 | 10 | 2026-03-27
TA_SGM Replacement (Additional Item) |  | 2026-02-20 | 2026-02-20 | 12-Feb-25 A | 15-Mar-25 A | 2026-03-27 | 53 | 2026-03-27
A37400 | Issue RFQ to Bidders | 2026-02-20 | 2026-02-20 | 12-Feb-25 A | 22-Feb-25 A | 2026-03-27 | 20 | 2026-03-27
A57330 | TBE for ICT System Modification_Free Issue Material | 2026-02-20 | 2026-02-20 | 23-Feb-25 A | 04-Mar-25 A | 2026-03-27 | 23 | 2026-03-27
A37410 | Issue Purchase Order to Vendor | 2026-02-20 | 2026-02-20 | 05-Mar-25 A | 15-Mar-25 A | 2026-03-27 | 10 | 2026-03-27
F&G [324 Nos] Flame Detectors, MCP, Beacon, etc. |  | 2026-02-20 | 2026-04-02 | 18-Jul-25 A | 2026-04-02 | 2026-04-20 | 185 | 2026-05-29 | 41
F&G Flame Detectors, MCP, Beacon (Nos 324) |  | 2026-02-20 | 2026-04-02 | 18-Jul-25 A | 2026-04-02 | 2026-04-20 | 185 | 2026-05-29 | 41
A17350 | Issue RFQ to Bidders | 2026-02-20 | 2026-02-20 | 18-Jul-25 A | 14-Aug-25 A | 2026-04-20 | 4 | 2026-04-20
A16530 | Technical Bid Evaluation for Fire & Gas Detectors_IFR | 2026-02-20 | 2026-02-20 | 01-Dec-25 A | 13-Feb-26 A | 2026-04-20 | 14 | 2026-04-20
A16540 | Technical Bid Evaluation for Fire & Gas Detectors_RCC | 2026-02-20 | 2026-03-03 | 14-Feb-26 A | 2026-03-03 | 2026-04-20 | 8 | 2026-04-29 | 41
A16550 | Technical Bid Evaluation for Fire & Gas Detectors_IFA | 2026-03-03 | 2026-03-11 | 2026-03-03 | 2026-03-11 | 2026-05-04 | 6 | 2026-05-12 | 44
A20130 | Commercial Bid Evaluation(Completion) | 2026-03-03 | 2026-03-17 | 2026-03-03 | 2026-03-17 | 2026-04-30 | 10 | 2026-05-13 | 41
A16560 | Technical Bid Evaluation for Fire & Gas Detectors_RCA | 2026-03-11 | 2026-03-19 | 2026-03-11 | 2026-03-19 | 2026-05-12 | 6 | 2026-05-20 | 44
A48220 | Technical Bid Evaluation for Fire & Gas Detectors_IFD/IFC | 2026-03-19 | 2026-03-30 | 2026-03-19 | 2026-03-30 | 2026-05-20 | 8 | 2026-05-29 | 44
A20110 | Issue Purchase Order to Vendor F&G Flames Detectors, MCP, Beacon (nos 324) | 2026-03-17 | 2026-04-02 | 2026-03-17 | 2026-04-02 | 2026-05-14 | 12 | 2026-05-29 | 41
Main Electrical Equipment |  | 2026-02-20 | 2026-05-13 | 01-Feb-25 A | 2026-05-13 | 2026-03-27 | 309 | 2026-09-29 | 98
DG Set (750 KVA) |  | 2026-02-20 | 2026-02-20 | 01-Feb-25 A | 25-Sep-25 A | 2026-05-18 | 78 | 2026-05-18
DG Set |  | 2026-02-20 | 2026-02-20 | 01-Feb-25 A | 25-Sep-25 A | 2026-05-18 | 78 | 2026-05-18
A16030 | Issue RFQ to Bidders | 2026-02-20 | 2026-02-20 | 01-Feb-25 A | 07-Feb-25 A | 2026-05-18 | 21 | 2026-05-18
A13330 | Technical Bid Evaluation For Emergency Diesel Generator Set_IFR | 2026-02-20 | 2026-02-20 | 03-May-25 A | 21-May-25 A | 2026-05-18 | 11 | 2026-05-18
A20430 | Commercial Bid Evaluation(Completion) | 2026-02-20 | 2026-02-20 | 18-Jul-25 A | 08-Aug-25 A | 2026-05-18 | 5 | 2026-05-18
A20410 | Issue Purchase Order to Vendor for DG Set | 2026-02-20 | 2026-02-20 | 09-Aug-25 A | 22-Aug-25 A | 2026-05-18 | 5 | 2026-05-18
A13340 | Technical Bid Evaluation For Emergency Diesel Generator Set_RCC | 2026-02-20 | 2026-02-20 | 14-Jul-25 A | 22-Aug-25 A | 2026-05-18 | 16 | 2026-05-18
A13350 | Technical Bid Evaluation For Emergency Diesel Generator Set_IFA | 2026-02-20 | 2026-02-20 | 23-Aug-25 A | 08-Sep-25 A | 2026-05-18 | 11 | 2026-05-18
A13360 | Technical Bid Evaluation For Emergency Diesel Generator Set_RCA | 2026-02-20 | 2026-02-20 | 20-Aug-25 A | 15-Sep-25 A | 2026-05-18 | 16 | 2026-05-18
A13370 | Technical Bid Evaluation For Emergency Diesel Generator Set_IFD/IFC | 2026-02-20 | 2026-02-20 | 10-Sep-25 A | 25-Sep-25 A | 2026-05-18 | 8 | 2026-05-18
UPS (AC - 60 KVA, 20 KVA, DC-UPS 6.5 KVA) |  | 2026-02-20 | 2026-03-09 | 12-Feb-25 A | 2026-03-09 | 2026-03-27 | 226 | 2026-08-13 | 114
TA_UPS Modification (Additional Item) - Chloride Technology |  | 2026-02-20 | 2026-02-20 | 12-Feb-25 A | 15-Mar-25 A | 2026-03-27 | 50 | 2026-03-27
A37080 | Issue RFQs to Bidders | 2026-02-20 | 2026-02-20 | 12-Feb-25 A | 22-Feb-25 A | 2026-03-27 | 20 | 2026-03-27
A57420 | TBE for Electrical System Modification_ Free Issue Material | 2026-02-20 | 2026-02-20 | 23-Feb-25 A | 04-Mar-25 A | 2026-03-27 | 23 | 2026-03-27
A37090 | Issue Purchase Order to Vendor | 2026-02-20 | 2026-02-20 | 05-Mar-25 A | 15-Mar-25 A | 2026-03-27 | 7 | 2026-03-27
UPS (AC - 60 KVA, 20 KVA, DC-UPS 6.5 KVA) Qty 1+1+1 = 03 Nos |  | 2026-02-20 | 2026-03-09 | 07-Jul-25 A | 2026-03-09 | 2026-05-28 | 177 | 2026-08-13 | 114
A16090 | Issue RFQ to Bidders | 2026-02-20 | 2026-02-20 | 07-Jul-25 A | 04-Aug-25 A | 2026-05-28 | 21 | 2026-05-28
A13080 | Technical Bid Evaluation For AC UPS_IFR | 2026-02-20 | 2026-02-20 | 06-Sep-25 A | 13-Sep-25 A | 2026-05-28 | 11 | 2026-05-28
A13090 | Technical Bid Evaluation For AC UPS_RCC | 2026-02-20 | 2026-02-20 | 14-Sep-25 A | 20-Sep-25 A | 2026-05-28 | 6 | 2026-05-28
A19550 | Commercial Bid Evaluation(Completion) | 2026-02-20 | 2026-02-20 | 01-Sep-25 A | 26-Sep-25 A | 2026-05-28 | 6 | 2026-05-28
A19530 | Issue Purchase Order to Vendor for UPS (GF) | 2026-02-20 | 2026-02-20 | 29-Sep-25 A | 16-Oct-25 A | 2026-05-28 | 6 | 2026-05-28
A13100 | Technical Bid Evaluation For AC UPS_IFA | 2026-02-20 | 2026-02-20 | 20-Oct-25 A | 03-Nov-25 A | 2026-07-29 | 6 | 2026-07-29
A13110 | Technical Bid Evaluation For AC UPS_RCA | 2026-02-20 | 2026-02-20 | 04-Nov-25 A | 12-Nov-25 A | 2026-07-29 | 6 | 2026-07-29
A13120 | Technical Bid Evaluation For AC UPS_IFD/IFC | 2026-02-20 | 2026-03-09 | 2026-02-20 | 2026-03-09 | 2026-07-29 | 11 | 2026-08-13 | 114
Power Transformer |  | 2026-02-20 | 2026-02-20 | 10-May-25 A | 17-Sep-25 A | 2026-05-01 | 97 | 2026-05-01
Power Transformers (Qty 05) |  | 2026-02-20 | 2026-02-20 | 10-May-25 A | 17-Sep-25 A | 2026-05-01 | 97 | 2026-05-01
A12930 | Technical Bid Evaluation For Transformer (Power And Distribution)_IFR | 2026-02-20 | 2026-02-20 | 10-May-25 A | 22-May-25 A | 2026-05-01 | 11 | 2026-05-01
A16150 | Issue RFQ to Bidders | 2026-02-20 | 2026-02-20 | 15-May-25 A | 25-May-25 A | 2026-05-01 | 20 | 2026-05-01
A12970 | Technical Bid Evaluation For Transformer (Power And Distribution)_IFD/IFC | 2026-02-20 | 2026-02-20 | 25-May-25 A | 01-Jun-25 A | 2026-05-01 | 8 | 2026-05-01
A12940 | Technical Bid Evaluation For Transformer (Power And Distribution)_RCC | 2026-02-20 | 2026-02-20 | 15-May-25 A | 03-Jun-25 A | 2026-05-01 | 16 | 2026-05-01
A20190 | Commercial Bid Evaluation(Completion) | 2026-02-20 | 2026-02-20 | 02-Jun-25 A | 08-Jun-25 A | 2026-05-01 | 21 | 2026-05-01
A20170 | Issue Purchase Order to Vendor for Power Transformers | 2026-02-20 | 2026-02-20 | 09-Jun-25 A | 29-Jul-25 A | 2026-05-01 | 5 | 2026-05-01
A12950 | Technical Bid Evaluation For Transformer (Power And Distribution)_IFA | 2026-02-20 | 2026-02-20 | 01-Aug-25 A | 10-Sep-25 A | 2026-05-01 | 11 | 2026-05-01
A12960 | Technical Bid Evaluation For Transformer (Power And Distribution)_RCA | 2026-02-20 | 2026-02-20 | 30-Aug-25 A | 17-Sep-25 A | 2026-05-01 | 16 | 2026-05-01
Electrical Heat Tracing |  | 2026-02-20 | 2026-05-13 | 2026-02-20 | 2026-05-13 | 2026-04-21 | 59 | 2026-07-13 | 42
Electrical Heat Tracing (53 Meter for piping + 340 Meter for instrumentation) |  | 2026-02-20 | 2026-05-13 | 2026-02-20 | 2026-05-13 | 2026-04-21 | 59 | 2026-07-13 | 42
A16270 | Issue RFQ to Bidders | 2026-02-20 | 2026-03-12 | 2026-02-20 | 2026-03-12 | 2026-04-21 | 15 | 2026-05-12 | 42
A22210 | Bid Evaluation(Completion) | 2026-03-13 | 2026-04-02 | 2026-03-13 | 2026-04-02 | 2026-05-12 | 15 | 2026-06-02 | 42
A22220 | Commercial Bid Evaluation(Completion) | 2026-04-03 | 2026-04-23 | 2026-04-03 | 2026-04-23 | 2026-06-02 | 15 | 2026-06-23 | 42
A22230 | Issue Purchase Order to Vendor | 2026-04-24 | 2026-05-13 | 2026-04-24 | 2026-05-13 | 2026-06-23 | 14 | 2026-07-13 | 42
CP |  | 2026-02-20 | 2026-02-27 | 21-Nov-25 A | 2026-02-27 | 2026-05-15 | 155 | 2026-05-22 | 60
Cathodic Protection (CP) Total CS Piping Length - 499 Meters |  | 2026-02-20 | 2026-02-27 | 21-Nov-25 A | 2026-02-27 | 2026-05-15 | 155 | 2026-05-22 | 60
A16210 | Issue RFQ to Bidders | 2026-02-20 | 2026-02-20 | 21-Nov-25 A | 18-Dec-25 A | 2026-05-15 | 20 | 2026-05-15
A22150 | Bid Evaluation(Completion) | 2026-02-20 | 2026-02-20 | 24-Jan-26 A | 31-Jan-26 A | 2026-05-15 | 45 | 2026-05-15
A22160 | Commercial Bid Evaluation(Completion) | 2026-02-20 | 2026-02-20 | 01-Feb-26 A | 20-Feb-26 A | 2026-05-15 | 15 | 2026-05-15
A22170 | Issue Purchase Order to Vendor | 2026-02-20 | 2026-02-27 | 20-Feb-26 A | 2026-02-27 | 2026-05-15 | 30 | 2026-05-22 | 60
LV & MV Switchgears |  | 2026-02-20 | 2026-02-20 | 18-Mar-25 A | 01-Nov-25 A | 2026-04-22 | 125 | 2026-04-22
Switchgear (LV, MV) |  | 2026-02-20 | 2026-02-20 | 18-Mar-25 A | 01-Nov-25 A | 2026-04-22 | 125 | 2026-04-22
A16330 | Issue RFQ to Bidders | 2026-02-20 | 2026-02-20 | 18-Mar-25 A | 14-Apr-25 A | 2026-04-22 | 21 | 2026-04-22
A13030 | Technical Bid Evaluation For LV Switchgear_IFR | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-Apr-25 A | 2026-04-22 | 11 | 2026-04-22
A13040 | Technical Bid Evaluation For LV Switchgear_RCC | 2026-02-20 | 2026-02-20 | 21-Apr-25 A | 25-Apr-25 A | 2026-04-22 | 16 | 2026-04-22
A13050 | Technical Bid Evaluation For LV Switchgear_IFA | 2026-02-20 | 2026-02-20 | 28-Apr-25 A | 01-May-25 A | 2026-04-22 | 5 | 2026-04-22
A13060 | Technical Bid Evaluation For LV Switchgear_RCA | 2026-02-20 | 2026-02-20 | 02-May-25 A | 10-May-25 A | 2026-04-22 | 16 | 2026-04-22
A13070 | Technical Bid Evaluation For LV Switchgear_IFD/IFC | 2026-02-20 | 2026-02-20 | 30-May-25 A | 18-Jul-25 A | 2026-04-22 | 8 | 2026-04-22
A20250 | Commercial Bid Evaluation(Completion) | 2026-02-20 | 2026-02-20 | 19-Jul-25 A | 29-Jul-25 A | 2026-04-22 | 2 | 2026-04-22
A20230 | Issue Purchase Order to Vendor for switchgear (LV, MV) | 2026-02-20 | 2026-02-20 | 24-Sep-25 A | 01-Nov-25 A | 2026-04-22 | 16 | 2026-04-22
Switch Gear Modification (Siemens) |  | 2026-02-20 | 2026-02-20 | 20-Feb-25 A | 18-Mar-25 A | 2026-03-27 | 25 | 2026-03-27
TA_Switchgear (MV Switchgear Modifications) - Siemens |  | 2026-02-20 | 2026-02-20 | 20-Feb-25 A | 18-Mar-25 A | 2026-03-27 | 25 | 2026-03-27
A22400 | Issue RFQ to Bidders | 2026-02-20 | 2026-02-20 | 20-Feb-25 A | 25-Feb-25 A | 2026-03-27 | 5 | 2026-03-27
A56240 | TBE for Electrical System Modification_Free Issue Material | 2026-02-20 | 2026-02-20 | 26-Feb-25 A | 09-Mar-25 A | 2026-03-27 | 11 | 2026-03-27
A22420 | Issue Purchase Order to Vendor | 2026-02-20 | 2026-02-20 | 10-Mar-25 A | 18-Mar-25 A | 2026-03-27 | 7 | 2026-03-27
MV & LV VFD's |  | 2026-02-20 | 2026-02-20 | 18-Jul-25 A | 12-Aug-25 A | 2026-09-22 | 105 | 2026-09-22
Variable Fequency Drives (VFDs) LV Qty = 03 |  | 2026-02-20 | 2026-02-20 | 18-Jul-25 A | 12-Aug-25 A | 2026-09-22 | 105 | 2026-09-22
A20790 | Issue RFQ to Bidders | 2026-02-20 | 2026-02-20 | 18-Jul-25 A | 20-Jul-25 A | 2026-09-22 | 20 | 2026-09-22
A13380 | Technical Bid Evaluation For LV Variable Frequency Drive_IFR | 2026-02-20 | 2026-02-20 | 21-Jul-25 A | 23-Jul-25 A | 2026-09-22 | 11 | 2026-09-22
A13390 | Technical Bid Evaluation For LV Variable Frequency Drive_RCC | 2026-02-20 | 2026-02-20 | 24-Jul-25 A | 25-Jul-25 A | 2026-09-22 | 16 | 2026-09-22
A13400 | Technical Bid Evaluation For LV Variable Frequency Drive_IFA | 2026-02-20 | 2026-02-20 | 28-Jul-25 A | 30-Jul-25 A | 2026-09-22 | 11 | 2026-09-22
A13410 | Technical Bid Evaluation For LV Variable Frequency Drive_RCA | 2026-02-20 | 2026-02-20 | 31-Jul-25 A | 01-Aug-25 A | 2026-09-22 | 16 | 2026-09-22
A13420 | Technical Bid Evaluation For LV Variable Frequency Drive_IFD/IFC | 2026-02-20 | 2026-02-20 | 04-Aug-25 A | 06-Aug-25 A | 2026-09-22 | 8 | 2026-09-22
A20820 | Commercial Bid Evaluation(Completion) | 2026-02-20 | 2026-02-20 | 07-Aug-25 A | 08-Aug-25 A | 2026-09-22 | 21 | 2026-09-22
A20800 | Issue Purchase Order to Vendor for VFDs | 2026-02-20 | 2026-02-20 | 11-Aug-25 A | 12-Aug-25 A | 2026-09-22 | 14 | 2026-09-22
HV Capacitor Bay |  | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 15-Oct-25 A | 2026-06-11 | 140 | 2026-08-06
HV Capacitor Bay |  | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 15-Oct-25 A | 2026-06-11 | 140 | 2026-08-06
A16570 | Issue RFQ to Bidders | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 06-May-25 A | 2026-06-11 | 21 | 2026-06-11
A13180 | Technical Bid Evaluation For Capacitor Bank_IFR | 2026-02-20 | 2026-02-20 | 01-Sep-25 A | 05-Sep-25 A | 2026-06-11 | 3 | 2026-06-11
A13190 | Technical Bid Evaluation For Capacitor Bank_RCC | 2026-02-20 | 2026-02-20 | 06-Sep-25 A | 10-Sep-25 A | 2026-06-11 | 3 | 2026-06-11
A13200 | Technical Bid Evaluation For Capacitor Bank_IFA | 2026-02-20 | 2026-02-20 | 11-Sep-25 A | 15-Sep-25 A | 2026-08-06 | 3 | 2026-08-06
A13210 | Technical Bid Evaluation For Capacitor Bank_RCA | 2026-02-20 | 2026-02-20 | 16-Sep-25 A | 20-Sep-25 A | 2026-08-06 | 3 | 2026-08-06
A13220 | Technical Bid Evaluation For Capacitor Bank_IFD/IFC | 2026-02-20 | 2026-02-20 | 22-Sep-25 A | 25-Sep-25 A | 2026-08-06 | 3 | 2026-08-06
A20010 | Commercial Bid Evaluation(Completion) | 2026-02-20 | 2026-02-20 | 01-Sep-25 A | 29-Sep-25 A | 2026-06-11 | 3 | 2026-06-11
A19990 | Issue Purchase Order to Vendor for HV Capacitor Bay | 2026-02-20 | 2026-02-20 | 30-Sep-25 A | 15-Oct-25 A | 2026-06-11 | 3 | 2026-06-11
Power Distribution Panel and LCS, Battery & Safety Switch, Resister Bank |  | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 20-Jun-25 A | 2026-09-29 | 109 | 2026-09-29
NGR Panel Qty 02 |  | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 20-Jun-25 A | 2026-09-29 | 109 | 2026-09-29
A16630 | Issue RFQ to Bidders | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 01-May-25 A | 2026-09-29 | 21 | 2026-09-29
A13280 | Technical Bid Evaluation For Neutral Grounding Resistor_IFR | 2026-02-20 | 2026-02-20 | 02-May-25 A | 13-May-25 A | 2026-09-29 | 11 | 2026-09-29
A13290 | Technical Bid Evaluation For Neutral Grounding Resistor_RCC | 2026-02-20 | 2026-02-20 | 14-May-25 A | 15-May-25 A | 2026-09-29 | 16 | 2026-09-29
A13300 | Technical Bid Evaluation For Neutral Grounding Resistor_IFA | 2026-02-20 | 2026-02-20 | 14-May-25 A | 15-May-25 A | 2026-09-29 | 11 | 2026-09-29
A13310 | Technical Bid Evaluation For Neutral Grounding Resistor_RCA | 2026-02-20 | 2026-02-20 | 14-May-25 A | 15-May-25 A | 2026-09-29 | 16 | 2026-09-29
A13320 | Technical Bid Evaluation For Neutral Grounding Resistor_IFD/IFC | 2026-02-20 | 2026-02-20 | 15-May-25 A | 20-May-25 A | 2026-09-29 | 8 | 2026-09-29
A20310 | Commercial Bid Evaluation(Completion) | 2026-02-20 | 2026-02-20 | 21-May-25 A | 13-Jun-25 A | 2026-09-29 | 21 | 2026-09-29
A20290 | Issue Purchase Order to Vendor for NGR Panel | 2026-02-20 | 2026-02-20 | 14-Jun-25 A | 20-Jun-25 A | 2026-09-29 | 14 | 2026-09-29
Interposing Relay Panel (IRP) |  | 2026-02-20 | 2026-03-18 | 2026-02-20 | 2026-03-18 | 2026-04-28 | 19 | 2026-07-17 | 87
Interposing Relay Panel |  | 2026-02-20 | 2026-03-18 | 2026-02-20 | 2026-03-18 | 2026-04-28 | 19 | 2026-07-17 | 87
A16690 | Issue RFQ to Bidders | 2026-02-20 | 2026-02-24 | 2026-02-20 | 2026-02-24 | 2026-04-28 | 3 | 2026-04-30 | 47
A58640 | Technical Bid Evaluation for Interposting Relay Panel_IFR | 2026-02-25 | 2026-02-27 | 2026-02-25 | 2026-02-27 | 2026-05-01 | 3 | 2026-05-05 | 47
A58650 | Technical Bid Evaluation for Interposting Relay Panel_RCC | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | 2026-05-06 | 3 | 2026-05-08 | 47
A58660 | Technical Bid Evaluation for Interposting Relay Panel_IFA | 2026-03-05 | 2026-03-09 | 2026-03-05 | 2026-03-09 | 2026-05-11 | 3 | 2026-05-13 | 47
A20370 | Commercial Bid Evaluation(Completion) | 2026-03-10 | 2026-03-12 | 2026-03-10 | 2026-03-12 | 2026-05-14 | 3 | 2026-05-18 | 47
A58670 | Technical Bid Evaluation for Interposting Relay Panel_RCA | 2026-03-10 | 2026-03-12 | 2026-03-10 | 2026-03-12 | 2026-07-10 | 3 | 2026-07-14 | 88
A58680 | Technical Bid Evaluation for Interposting Relay Panel_IFD/IFC | 2026-03-13 | 2026-03-17 | 2026-03-13 | 2026-03-17 | 2026-07-15 | 3 | 2026-07-17 | 88
A20350 | Issue Purchase Order to Vendor for Interposing Relay Panel | 2026-03-13 | 2026-03-18 | 2026-03-13 | 2026-03-18 | 2026-05-19 | 4 | 2026-05-22 | 47
Subcontract Services |  | 2026-02-20 | 2026-02-20 | 14-Nov-24 A | 11-Jun-25 A | 2026-02-21 | 198 | 2026-03-27
Detail Engineering Subcontract |  | 2026-02-20 | 2026-02-20 | 14-Nov-24 A | 06-Dec-24 A | 2026-02-21 | 12 | 2026-02-21
A61090 | Issue RFQ to CONTRACTORs | 2026-02-20 | 2026-02-20 | 14-Nov-24 A | 15-Nov-24 A | 2026-02-21 | 3 | 2026-02-21
A61100 | Technical Bid analysis and clarifications | 2026-02-20 | 2026-02-20 | 19-Nov-24 A | 22-Nov-24 A | 2026-02-21 | 3 | 2026-02-21
A61110 | Bid analysis and clarifications | 2026-02-20 | 2026-02-20 | 23-Nov-24 A | 29-Nov-24 A | 2026-02-21 | 3 | 2026-02-21
A61120 | Subcontract Awarded/Signed | 2026-02-20 | 2026-02-20 | 29-Nov-24 A | 06-Dec-24 A | 2026-02-21 | 3 | 2026-02-21
TA Construction |  | 2026-02-20 | 2026-02-20 | 09-Dec-24 A | 07-Mar-25 A | 2026-03-11 | 85 | 2026-03-11
A61130 | Issue RFQ to CONTRACTORs | 2026-02-20 | 2026-02-20 | 09-Dec-24 A | 09-Dec-24 A | 2026-03-11 | 21 | 2026-03-11
A61140 | Technical Bid analysis and clarifications | 2026-02-20 | 2026-02-20 | 08-Jan-25 A | 08-Jan-25 A | 2026-03-11 | 21 | 2026-03-11
A61150 | Bid analysis and clarifications | 2026-02-20 | 2026-02-20 | 06-Feb-25 A | 06-Feb-25 A | 2026-03-11 | 21 | 2026-03-11
A61160 | Subcontract Awarded/Signed | 2026-02-20 | 2026-02-20 | 07-Mar-25 A | 07-Mar-25 A | 2026-03-11 | 21 | 2026-03-11
Main Construction |  | 2026-02-20 | 2026-02-20 | 09-Dec-24 A | 10-Mar-25 A | 2026-02-21 | 85 | 2026-02-21
A61170 | Issue RFQ to CONTRACTORs | 2026-02-20 | 2026-02-20 | 09-Dec-24 A | 01-Feb-25 A | 2026-02-21 | 21 | 2026-02-21
A61180 | Technical Bid analysis and clarifications | 2026-02-20 | 2026-02-20 | 02-Feb-25 A | 15-Feb-25 A | 2026-02-21 | 21 | 2026-02-21
A61190 | Bid analysis and clarifications | 2026-02-20 | 2026-02-20 | 16-Feb-25 A | 25-Feb-25 A | 2026-02-21 | 21 | 2026-02-21
A61200 | Subcontract Awarded/Signed | 2026-02-20 | 2026-02-20 | 07-Mar-25 A | 10-Mar-25 A | 2026-02-21 | 21 | 2026-02-21
Topgraphic |  | 2026-02-20 | 2026-02-20 | 01-Jan-25 A | 20-Mar-25 A | 2026-02-21 | 85 | 2026-02-21
A61210 | Issue RFQ to CONTRACTORs | 2026-02-20 | 2026-02-20 | 01-Jan-25 A | 03-Jan-25 A | 2026-02-21 | 21 | 2026-02-21
A61220 | Technical Bid analysis and clarifications | 2026-02-20 | 2026-02-20 | 04-Jan-25 A | 03-Feb-25 A | 2026-02-21 | 21 | 2026-02-21
A61230 | Bid analysis and clarifications | 2026-02-20 | 2026-02-20 | 04-Feb-25 A | 01-Mar-25 A | 2026-02-21 | 21 | 2026-02-21
A61240 | Subcontract Awarded/Signed | 2026-02-20 | 2026-02-20 | 02-Mar-25 A | 20-Mar-25 A | 2026-02-21 | 21 | 2026-02-21
Piling |  | 2026-02-20 | 2026-02-20 | 01-Apr-25 A | 11-May-25 A | 2026-02-21 | 87 | 2026-02-21
A61250 | Issue RFQ to CONTRACTORs | 2026-02-20 | 2026-02-20 | 01-Apr-25 A | 20-Apr-25 A | 2026-02-21 | 21 | 2026-02-21
A61260 | Technical Bid analysis and clarifications | 2026-02-20 | 2026-02-20 | 21-Apr-25 A | 27-Apr-25 A | 2026-02-21 | 21 | 2026-02-21
A61270 | Bid analysis and clarifications | 2026-02-20 | 2026-02-20 | 28-Apr-25 A | 04-May-25 A | 2026-02-21 | 21 | 2026-02-21
A61280 | Subcontract Awarded/Signed | 2026-02-20 | 2026-02-20 | 05-May-25 A | 11-May-25 A | 2026-02-21 | 21 | 2026-02-21
HSE Studies |  | 2026-02-20 | 2026-02-20 | 10-Feb-25 A | 11-Jun-25 A | 2026-03-02 | 175 | 2026-03-02
A61290 | Issue RFQ to CONTRACTORs | 2026-02-20 | 2026-02-20 | 10-Feb-25 A | 01-Mar-25 A | 2026-03-02 | 21 | 2026-03-02
A61300 | Technical Bid analysis and clarifications | 2026-02-20 | 2026-02-20 | 02-Mar-25 A | 15-Mar-25 A | 2026-03-02 | 21 | 2026-03-02
A61310 | Bid analysis and clarifications | 2026-02-20 | 2026-02-20 | 16-Mar-25 A | 18-Apr-25 A | 2026-03-02 | 21 | 2026-03-02
A61320 | Subcontract Awarded/Signed | 2026-02-20 | 2026-02-20 | 19-Apr-25 A | 11-Jun-25 A | 2026-03-02 | 21 | 2026-03-02
VSM Services Agreements |  | 2026-02-20 | 2026-02-20 | 01-Feb-25 A | 08-Mar-25 A | 2026-03-27 | 85 | 2026-03-27
A61330 | Issue RFQ to CONTRACTORs | 2026-02-20 | 2026-02-20 | 01-Feb-25 A | 15-Feb-25 A | 2026-03-27 | 21 | 2026-03-27
A61340 | Technical Bid analysis and clarifications | 2026-02-20 | 2026-02-20 | 16-Feb-25 A | 22-Feb-25 A | 2026-03-27 | 21 | 2026-03-27
A61350 | Bid analysis and clarifications | 2026-02-20 | 2026-02-20 | 23-Feb-25 A | 01-Mar-25 A | 2026-03-27 | 21 | 2026-03-27
A61360 | Subcontract Awarded/Signed | 2026-02-20 | 2026-02-20 | 02-Mar-25 A | 08-Mar-25 A | 2026-03-27 | 21 | 2026-03-27
As-Built & Package handover |  | 2026-02-20 | 2027-07-14 | 01-Jun-25 A | 2027-07-14 | 2026-03-27 | 463 | 2027-07-20 | 4
TA |  | 2026-02-20 | 2026-02-20 | 01-Jun-25 A | 15-Jul-25 A | 2026-03-27 | 30 | 2026-03-27
A61430 | TA As-Built | 2026-02-20 | 2026-02-20 | 01-Jun-25 A | 15-Jul-25 A | 2026-03-27 | 30 | 2026-03-27
Main Scope |  | 2027-04-22 | 2027-07-14 | 2027-04-22 | 2027-07-14 | 2027-04-28 | 60 | 2027-07-20 | 4
A61440 | Main Scope As-Built | 2027-04-22 | 2027-07-14 | 2027-04-22 | 2027-07-14 | 2027-04-28 | 60 | 2027-07-20 | 4
Manufacturing and Delivery |  | 2026-02-20 | 2026-09-29 | 25-Feb-25 A | 2026-09-29 | 2026-02-23 | 510 | 2027-07-20 | 210
51.C | Issue purchase orders for all remaining Mechanical / Rotating EQT. & EQT. Pkgs |  |  |  | 31-Dec-25 A |  | 0
54.C | Issue purchase order for all major Instruments Control System |  |  |  | 07-Jan-26 A |  | 0
52.C | Issue purchase orders for all major Electrical Equipments |  |  |  | 14-Jan-26 A |  | 0
79.D | All major electrical Equipment delivered to Site |  | 2026-08-20 |  | 2026-08-20 |  | 0 | 2027-01-03 | 170
Equipment Packages |  | 2026-02-20 | 2026-08-26 | 20-Jun-25 A | 2026-08-26 | 2026-04-16 | 303 | 2027-07-20 | 234
Vessels |  | 2026-02-20 | 2026-06-12 | 20-Jun-25 A | 2026-06-12 | 2026-04-16 | 231 | 2026-10-30 | 100
Vessels / Drums (by Linde) |  | 2026-02-20 | 2026-06-12 | 20-Jun-25 A | 2026-06-12 | 2026-04-16 | 231 | 2026-10-30 | 100
FG Comp. 2nd Stage Dis. Drum (13-VV-707) |  | 2026-02-20 | 2026-06-08 | 20-Jun-25 A | 2026-06-08 | 2026-04-16 | 186 | 2026-08-01 | 40
A35210 | Key Vendor Drawings / Data Approved | 2026-02-20 | 2026-02-20 | 20-Jun-25 A | 23-Aug-25 A | 2026-04-16 | 30 | 2026-04-16
A35220 | Purchase Order for Major Sub-ordered Materials | 2026-02-20 | 2026-02-20 | 25-Aug-25 A | 02-Sep-25 A | 2026-04-16 | 5 | 2026-04-16
A35230 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-02-20 | 2026-02-20 | 11-Aug-25 A | 12-Sep-25 A | 2026-04-16 | 30 | 2026-04-16
A35200 | Start Production (13-VV-707) |  |  | 19-Sep-25 A |  |  | 0
A35240 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-02-20 | 2026-02-20 | 15-Sep-25 A | 26-Sep-25 A | 2026-04-16 | 1 | 2026-04-16
A35250 | Manufacturing / Ex Works (India/UAE) | 2026-02-20 | 2026-04-10 | 02-Dec-25 A | 2026-04-10 | 2026-04-16 | 138 | 2026-06-05 | 70
A35260 | Complete Manufacturing & ready for Final Inspection | 2026-04-13 | 2026-04-22 | 2026-04-13 | 2026-04-22 | 2026-06-05 | 7 | 2026-06-16 | 40
A35270 | Materials Successfully Inspected, Tested / Ex Work | 2026-04-22 | 2026-05-01 | 2026-04-22 | 2026-05-01 | 2026-06-17 | 7 | 2026-06-25 | 40
A35320 | Delivery of FG Comp. 2nd Stage Dis. Drum Tag# 13-VV-707 | 2026-05-11 | 2026-06-08 | 2026-05-11 | 2026-06-08 | 2026-07-05 | 35 | 2026-08-01 | 69
OG Comp. 2nd Stage Suc. Drum (13-VV-713) |  | 2026-02-20 | 2026-06-05 | 20-Jun-25 A | 2026-06-05 | 2026-04-22 | 186 | 2026-08-06 | 43
A35060 | Start Production (13-VV-713) |  |  | 20-Jun-25 A |  |  | 0
A35070 | Key Vendor Drawings / Data Approved | 2026-02-20 | 2026-02-20 | 20-Jun-25 A | 23-Aug-25 A | 2026-04-22 | 30 | 2026-04-22
A35080 | Purchase Order for Major Sub-ordered Materials | 2026-02-20 | 2026-02-20 | 25-Aug-25 A | 02-Sep-25 A | 2026-04-22 | 5 | 2026-04-22
A35090 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-02-20 | 2026-02-20 | 11-Aug-25 A | 12-Sep-25 A | 2026-04-22 | 30 | 2026-04-22
A35100 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-02-20 | 2026-02-20 | 15-Sep-25 A | 26-Oct-25 A | 2026-04-22 | 1 | 2026-04-22
A35110 | Manufacturing / Ex Works (India/UAE) | 2026-02-20 | 2026-04-15 | 21-Nov-25 A | 2026-04-15 | 2026-04-22 | 138 | 2026-06-16 | 77
A35120 | Complete Manufacturing & ready for Final Inspection | 2026-04-16 | 2026-04-22 | 2026-04-16 | 2026-04-22 | 2026-06-16 | 5 | 2026-06-23 | 43
A35130 | Materials Successfully Inspected, Tested / Ex Work | 2026-04-23 | 2026-05-01 | 2026-04-23 | 2026-05-01 | 2026-06-23 | 7 | 2026-07-02 | 43
A35170 | Delivery of OG Comp. 2nd Stage Suc. Drum Tag# 13-VV-713 | 2026-05-09 | 2026-06-05 | 2026-05-09 | 2026-06-05 | 2026-07-09 | 35 | 2026-08-06 | 77
OG Buffer Drum (13-VV-712) |  | 2026-02-20 | 2026-06-12 | 20-Jun-25 A | 2026-06-12 | 2026-06-02 | 191 | 2026-09-22 | 72
A35340 | Start Production (13-VV-712) |  |  | 20-Jun-25 A |  |  | 0
A35350 | Key Vendor Drawings / Data Approved | 2026-02-20 | 2026-02-20 | 20-Jun-25 A | 23-Aug-25 A | 2026-06-02 | 30 | 2026-06-02
A35360 | Purchase Order for Major Sub-ordered Materials | 2026-02-20 | 2026-02-20 | 25-Aug-25 A | 02-Sep-25 A | 2026-06-02 | 5 | 2026-06-02
A35370 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-02-20 | 2026-02-20 | 11-Aug-25 A | 12-Sep-25 A | 2026-06-02 | 30 | 2026-06-02
A35380 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-02-20 | 2026-02-20 | 15-Sep-25 A | 26-Oct-25 A | 2026-06-02 | 1 | 2026-06-02
A35390 | Manufacturing / Ex Works (India/UAE) | 2026-02-20 | 2026-04-15 | 21-Nov-25 A | 2026-04-15 | 2026-06-02 | 138 | 2026-07-27 | 128
A35400 | Complete Manufacturing & ready for Final Inspection | 2026-04-16 | 2026-04-22 | 2026-04-16 | 2026-04-22 | 2026-07-27 | 5 | 2026-07-31 | 72
A35410 | Materials Successfully Inspected, Tested / Ex Work | 2026-04-23 | 2026-05-01 | 2026-04-23 | 2026-05-01 | 2026-08-03 | 7 | 2026-08-11 | 72
A35470 | Delivery of OG Buffer Drum - Tag# 13-VV-712 | 2026-05-16 | 2026-06-12 | 2026-05-16 | 2026-06-12 | 2026-08-26 | 35 | 2026-09-22 | 128
PSA2 Slop Drum (70-VV-1415) |  | 2026-02-20 | 2026-06-04 | 20-Jun-25 A | 2026-06-04 | 2026-07-18 | 185 | 2026-10-30 | 106
A35480 | Start Production (70-VV-1415) |  |  | 20-Jun-25 A |  |  | 0
A35490 | Key Vendor Drawings / Data Approved | 2026-02-20 | 2026-02-20 | 20-Jun-25 A | 23-Aug-25 A | 2026-07-18 | 30 | 2026-07-18
A35500 | Purchase Order for Major Sub-ordered Materials | 2026-02-20 | 2026-02-20 | 25-Aug-25 A | 02-Sep-25 A | 2026-07-18 | 5 | 2026-07-18
A35510 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-02-20 | 2026-02-20 | 11-Aug-25 A | 12-Sep-25 A | 2026-07-18 | 30 | 2026-07-18
A35520 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-02-20 | 2026-02-20 | 15-Sep-25 A | 26-Oct-25 A | 2026-07-18 | 1 | 2026-07-18
A35530 | Manufacturing / Ex Works (India/UAE) | 2026-02-20 | 2026-04-15 | 21-Nov-25 A | 2026-04-15 | 2026-07-18 | 138 | 2026-09-11 | 185
A35540 | Complete Manufacturing & ready for Final Inspection | 2026-04-16 | 2026-04-22 | 2026-04-16 | 2026-04-22 | 2026-09-11 | 5 | 2026-09-17 | 106
A35550 | Materials Successfully Inspected, Tested / Ex Work | 2026-04-23 | 2026-05-01 | 2026-04-23 | 2026-05-01 | 2026-09-18 | 7 | 2026-09-28 | 106
A35580 | Delivery of PSA2 Slop Drum Tag# 70-VV-1415 | 2026-05-08 | 2026-06-04 | 2026-05-08 | 2026-06-04 | 2026-10-03 | 35 | 2026-10-30 | 185
FG Comp. 2nd Stage Suc. Drum (13-VV-706) |  | 2026-02-20 | 2026-06-02 | 20-Jun-25 A | 2026-06-02 | 2026-04-17 | 183 | 2026-07-28 | 40
A35620 | Start Production (13-VV-706) |  |  | 20-Jun-25 A |  |  | 0
A35630 | Key Vendor Drawings / Data Approved | 2026-02-20 | 2026-02-20 | 20-Jun-25 A | 23-Aug-25 A | 2026-04-17 | 30 | 2026-04-17
A35640 | Purchase Order for Major Sub-ordered Materials | 2026-02-20 | 2026-02-20 | 25-Aug-25 A | 02-Sep-25 A | 2026-04-17 | 5 | 2026-04-17
A35650 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-02-20 | 2026-02-20 | 11-Aug-25 A | 12-Sep-25 A | 2026-04-17 | 30 | 2026-04-17
A35660 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-02-20 | 2026-02-20 | 15-Sep-25 A | 26-Oct-25 A | 2026-04-17 | 1 | 2026-04-17
A35670 | Manufacturing / Ex Works (India/UAE) | 2026-02-20 | 2026-04-15 | 21-Nov-25 A | 2026-04-15 | 2026-04-17 | 138 | 2026-06-11 | 70
A35680 | Complete Manufacturing & ready for Final Inspection | 2026-04-16 | 2026-04-24 | 2026-04-16 | 2026-04-24 | 2026-06-11 | 7 | 2026-06-19 | 40
A35690 | Materials Successfully Inspected, Tested / Ex Work | 2026-04-27 | 2026-05-05 | 2026-04-27 | 2026-05-05 | 2026-06-22 | 7 | 2026-06-30 | 40
A35710 | Delivery of FG Comp. 2nd Stage Suc. Drum Tag# 13-VV-706 | 2026-05-06 | 2026-06-02 | 2026-05-06 | 2026-06-02 | 2026-07-01 | 35 | 2026-07-28 | 70
FG Comp.1st Stage Suc. Drum (13-VV-705) |  | 2026-02-20 | 2026-06-01 | 20-Jun-25 A | 2026-06-01 | 2026-05-07 | 222 | 2026-08-15 | 54
A35760 | Start Production (13-VV-705) |  |  | 20-Jun-25 A |  |  | 0
A35770 | Key Vendor Drawings / Data Approved | 2026-02-20 | 2026-02-20 | 20-Jun-25 A | 23-Aug-25 A | 2026-05-07 | 30 | 2026-05-07
A35780 | Purchase Order for Major Sub-ordered Materials | 2026-02-20 | 2026-02-20 | 25-Aug-25 A | 02-Sep-25 A | 2026-05-07 | 5 | 2026-05-07
A35790 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-02-20 | 2026-02-20 | 11-Aug-25 A | 12-Sep-25 A | 2026-05-07 | 30 | 2026-05-07
A35800 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-02-20 | 2026-02-20 | 15-Sep-25 A | 26-Oct-25 A | 2026-05-07 | 26 | 2026-05-07
A35810 | Manufacturing / Ex Works (India/UAE) | 2026-02-20 | 2026-04-15 | 21-Nov-25 A | 2026-04-15 | 2026-05-07 | 138 | 2026-07-01 | 95
A35820 | Complete Manufacturing & ready for Final Inspection | 2026-04-16 | 2026-04-23 | 2026-04-16 | 2026-04-23 | 2026-07-01 | 6 | 2026-07-08 | 54
A35830 | Materials Successfully Inspected, Tested / Ex Work | 2026-04-24 | 2026-05-04 | 2026-04-24 | 2026-05-04 | 2026-07-09 | 7 | 2026-07-17 | 54
A35840 | Delivery of FG Comp.1st Stage Suc. Drum (13-VV-705) | 2026-05-05 | 2026-06-01 | 2026-05-05 | 2026-06-01 | 2026-07-19 | 35 | 2026-08-15 | 94
Vessel's Internals (05 Dimister pads) |  | 2026-02-20 | 2026-06-02 | 20-Jun-25 A | 2026-06-02 | 2026-05-14 | 213 | 2026-08-24 | 59
A33660 | Start Production |  |  | 20-Jun-25 A |  |  | 0
A29960 | Key Vendor Drawings / Data Approved | 2026-02-20 | 2026-02-20 | 20-Jun-25 A | 23-Aug-25 A | 2026-05-14 | 30 | 2026-05-14
A29970 | Purchase Order for Major Sub-ordered Materials | 2026-02-20 | 2026-02-20 | 25-Aug-25 A | 02-Sep-25 A | 2026-05-14 | 5 | 2026-05-14
A29980 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-02-20 | 2026-02-20 | 11-Aug-25 A | 12-Sep-25 A | 2026-05-14 | 20 | 2026-05-14
A29990 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-02-20 | 2026-02-20 | 15-Sep-25 A | 26-Oct-25 A | 2026-05-14 | 1 | 2026-05-14
A30000 | Manufacturing / Ex Works (India/UAE) | 2026-02-20 | 2026-04-15 | 21-Nov-25 A | 2026-04-15 | 2026-05-14 | 138 | 2026-07-08 | 104
A30010 | Complete Manufacturing & ready for Final Inspection | 2026-04-16 | 2026-04-24 | 2026-04-16 | 2026-04-24 | 2026-07-08 | 7 | 2026-07-16 | 59
A30020 | Materials Successfully Inspected, Tested / Ex Work | 2026-04-27 | 2026-05-05 | 2026-04-27 | 2026-05-05 | 2026-07-17 | 7 | 2026-07-27 | 59
A33670 | Delivery of Vessel's Internals (05 Dimister Pads) in Warehouse | 2026-05-06 | 2026-06-02 | 2026-05-06 | 2026-06-02 | 2026-07-28 | 35 | 2026-08-24 | 104
C4 Guard Adsorber Cooler Dripleg - (BF) |  | 2026-02-20 | 2026-06-02 | 20-Jun-25 A | 2026-06-02 | 2026-07-15 | 200 | 2026-10-25 | 103
A34660 | Start Production |  |  | 20-Jun-25 A |  |  | 0
A28160 | Key Vendor Drawings / Data Approved | 2026-02-20 | 2026-02-20 | 20-Jun-25 A | 23-Aug-25 A | 2026-07-15 | 60 | 2026-07-15
A28170 | Purchase Order for Major Sub-ordered Materials | 2026-02-20 | 2026-02-20 | 25-Aug-25 A | 02-Sep-25 A | 2026-07-15 | 30 | 2026-07-15
A28180 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-02-20 | 2026-02-20 | 11-Aug-25 A | 12-Sep-25 A | 2026-07-15 | 21 | 2026-07-15
A28190 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-02-20 | 2026-02-20 | 15-Sep-25 A | 26-Oct-25 A | 2026-07-15 | 9 | 2026-07-15
A28200 | Manufacturing / Ex Works (India/UAE) | 2026-02-20 | 2026-04-15 | 21-Nov-25 A | 2026-04-15 | 2026-07-15 | 150 | 2026-09-08 | 181
A28210 | Complete Manufacturing & ready for Final Inspection | 2026-04-16 | 2026-04-24 | 2026-04-16 | 2026-04-24 | 2026-09-08 | 7 | 2026-09-16 | 103
A28220 | Materials Successfully Inspected, Tested / Ex Work | 2026-04-27 | 2026-05-05 | 2026-04-27 | 2026-05-05 | 2026-09-17 | 7 | 2026-09-25 | 103
A34670 | Delivery of C4 Guard Absorber Cooler Dripleg (Post - TA) | 2026-05-06 | 2026-06-02 | 2026-05-06 | 2026-06-02 | 2026-09-28 | 35 | 2026-10-25 | 181
Water Collection & Sanitary Waste Water Pumps |  | 2026-02-20 | 2026-06-05 | 10-Sep-25 A | 2026-06-05 | 2026-06-20 | 248 | 2026-10-18 | 95
Sanitary Waste Water Sump Pump |  | 2026-02-20 | 2026-06-05 | 10-Sep-25 A | 2026-06-05 | 2026-06-20 | 217 | 2026-10-06 | 87
A33850 | Start Production |  |  | 10-Sep-25 A |  |  | 0
A30680 | Key Vendor Drawings / Data Approved | 2026-02-20 | 2026-02-20 | 21-Nov-25 A | 04-Dec-25 A | 2026-06-20 | 30 | 2026-06-20
A30690 | Purchase Order for Major Sub-ordered Materials | 2026-02-20 | 2026-02-20 | 08-Dec-25 A | 19-Dec-25 A | 2026-06-20 | 5 | 2026-06-20
A30700 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 02-Jan-26 A | 2026-06-20 | 40 | 2026-06-20
A30710 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-02-20 | 2026-02-20 | 01-Jan-26 A | 15-Jan-26 A | 2026-06-20 | 1 | 2026-06-20
A30720 | Manufacturing / Ex Works (India/UAE) | 2026-02-20 | 2026-04-20 | 01-Jan-26 A | 2026-04-20 | 2026-06-20 | 175 | 2026-08-19 | 151
A30730 | Complete Manufacturing & ready for Final Inspection | 2026-04-21 | 2026-04-29 | 2026-04-21 | 2026-04-29 | 2026-08-19 | 7 | 2026-08-28 | 87
A30740 | Materials Successfully Inspected, Tested / Ex Work | 2026-04-30 | 2026-05-08 | 2026-04-30 | 2026-05-08 | 2026-08-28 | 7 | 2026-09-08 | 87
A33860 | Delivery of Sanitary Waste Water Sump Pump (01) | 2026-05-09 | 2026-06-05 | 2026-05-09 | 2026-06-05 | 2026-09-08 | 35 | 2026-10-06 | 153
Water Collection Sump Pump ll |  | 2026-02-20 | 2026-06-05 | 10-Sep-25 A | 2026-06-05 | 2026-07-03 | 224 | 2026-10-18 | 95
A33870 | Start Production |  |  | 10-Sep-25 A |  |  | 0
A30770 | Key Vendor Drawings / Data Approved | 2026-02-20 | 2026-02-20 | 21-Nov-25 A | 10-Dec-25 A | 2026-07-03 | 30 | 2026-07-03
A30780 | Purchase Order for Major Sub-ordered Materials | 2026-02-20 | 2026-02-20 | 11-Dec-25 A | 19-Dec-25 A | 2026-07-03 | 5 | 2026-07-03
A30790 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 02-Jan-26 A | 2026-07-03 | 40 | 2026-07-03
A30800 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-02-20 | 2026-02-20 | 01-Jan-26 A | 15-Jan-26 A | 2026-07-03 | 1 | 2026-07-03
A30810 | Manufacturing / Ex Works (India/UAE) | 2026-02-20 | 2026-04-20 | 01-Jan-26 A | 2026-04-20 | 2026-07-03 | 75 | 2026-09-01 | 166
A30820 | Complete Manufacturing & ready for Final Inspection | 2026-04-21 | 2026-04-29 | 2026-04-21 | 2026-04-29 | 2026-09-01 | 7 | 2026-09-09 | 95
A30830 | Materials Successfully Inspected, Tested / Ex Work | 2026-04-30 | 2026-05-08 | 2026-04-30 | 2026-05-08 | 2026-09-10 | 7 | 2026-09-18 | 95
A33880 | Delivery of Water Sump Pump (02) | 2026-05-09 | 2026-06-05 | 2026-05-09 | 2026-06-05 | 2026-09-21 | 35 | 2026-10-18 | 169
EOT Cranes |  | 2026-02-20 | 2026-08-13 | 15-Aug-25 A | 2026-08-13 | 2026-04-21 | 239 | 2027-07-20 | 243
EOT Crane for FG Compressor (1 = 60 Ton) |  | 2026-02-20 | 2026-08-13 | 15-Aug-25 A | 2026-08-13 | 2026-04-21 | 239 | 2027-07-20 | 243
A33910 | Start Production |  |  | 15-Aug-25 A |  |  | 0
A30960 | Purchase Order for Major Sub-ordered Materials | 2026-03-26 | 2026-03-26 | 01-Feb-26 A | 12-Feb-26 A | 2027-06-09 | 5 | 2027-06-09
A30950 | Key Vendor Drawings / Data Approved | 2026-02-20 | 2026-03-26 | 23-Jan-26 A | 2026-03-26 | 2026-04-21 | 50 | 2026-05-25 | 42
A30980 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-03-26 | 2026-03-27 | 2026-03-26 | 2026-03-27 | 2026-05-26 | 1 | 2026-05-27 | 75
A30970 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-03-26 | 2026-05-07 | 2026-03-26 | 2026-05-07 | 2027-06-09 | 30 | 2027-07-20 | 313
A30990 | Manufacturing / Ex Works (India/UAE) | 2026-03-27 | 2026-07-05 | 2026-03-27 | 2026-07-05 | 2026-05-27 | 125 | 2026-09-04 | 75
A31000 | Complete Manufacturing & ready for Final Inspection | 2026-07-06 | 2026-07-14 | 2026-07-06 | 2026-07-14 | 2026-09-04 | 7 | 2026-09-14 | 44
A31010 | Materials Successfully Inspected, Tested / Ex Work | 2026-07-15 | 2026-07-23 | 2026-07-15 | 2026-07-23 | 2026-09-15 | 7 | 2026-09-23 | 44
A33920 | Delivery of Material in Warehouse (FG) Crane | 2026-07-24 | 2026-08-13 | 2026-07-24 | 2026-08-13 | 2026-09-24 | 26 | 2026-10-14 | 78
EOT Crane for OG Compressor (1 = 25 Ton) |  | 2026-02-20 | 2026-08-13 | 10-Sep-25 A | 2026-08-13 | 2026-04-28 | 217 | 2027-07-20 | 243
A33930 | Start Production |  |  | 10-Sep-25 A |  |  | 0
A31050 | Purchase Order for Major Sub-ordered Materials | 2026-03-26 | 2026-03-26 | 01-Feb-26 A | 12-Feb-26 A | 2027-06-09 | 5 | 2027-06-09
A31040 | Key Vendor Drawings / Data Approved | 2026-02-20 | 2026-03-26 | 23-Jan-26 A | 2026-03-26 | 2026-04-28 | 35 | 2026-06-01 | 47
A31070 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-03-26 | 2026-03-27 | 2026-03-26 | 2026-03-27 | 2026-06-02 | 1 | 2026-06-03 | 84
A31060 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-03-26 | 2026-05-07 | 2026-03-26 | 2026-05-07 | 2027-06-09 | 30 | 2027-07-20 | 313
A31080 | Manufacturing / Ex Works (India/UAE) | 2026-03-27 | 2026-07-05 | 2026-03-27 | 2026-07-05 | 2026-06-03 | 125 | 2026-09-11 | 84
A31090 | Complete Manufacturing & ready for Final Inspection | 2026-07-06 | 2026-07-14 | 2026-07-06 | 2026-07-14 | 2026-09-11 | 7 | 2026-09-21 | 49
A31100 | Materials Successfully Inspected, Tested / Ex Work | 2026-07-15 | 2026-07-23 | 2026-07-15 | 2026-07-23 | 2026-09-22 | 7 | 2026-09-30 | 49
A33940 | Delivery of (OG) Crane | 2026-07-24 | 2026-08-13 | 2026-07-24 | 2026-08-13 | 2026-10-01 | 26 | 2026-10-21 | 86
Heat Exchangers |  | 2026-02-20 | 2026-04-27 | 11-Jul-25 A | 2026-04-27 | 2026-05-14 | 216 | 2026-11-04 | 138
Heat Exchanger (Type S & T = 06 Nos) |  | 2026-02-20 | 2026-04-27 | 11-Jul-25 A | 2026-04-27 | 2026-05-14 | 216 | 2026-11-04 | 138
FG Comp. Interstage Cooler (BEM) - Tag# 13-HE-703 |  | 2026-02-20 | 2026-04-27 | 11-Jul-25 A | 2026-04-27 | 2026-05-14 | 216 | 2026-07-18 | 60
A36300 | Start Production (13-HE-703) |  |  | 11-Jul-25 A |  |  | 0
A36310 | Key Vendor Drawings / Data Approved | 2026-02-20 | 2026-02-20 | 18-Jul-25 A | 28-Aug-25 A | 2026-05-14 | 30 | 2026-05-14
A36320 | Purchase Order for Major Sub-ordered Materials | 2026-02-20 | 2026-02-20 | 29-Aug-25 A | 02-Sep-25 A | 2026-05-14 | 35 | 2026-05-14
A36330 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-02-20 | 2026-02-20 | 11-Aug-25 A | 12-Sep-25 A | 2026-05-14 | 35 | 2026-05-14
A36340 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-02-20 | 2026-02-20 | 15-Sep-25 A | 26-Oct-25 A | 2026-05-14 | 13 | 2026-05-14
A36350 | Manufacturing / Ex Works (India/UAE) | 2026-02-20 | 2026-02-27 | 21-Nov-25 A | 2026-02-27 | 2026-05-14 | 188 | 2026-05-22 | 105
A36360 | Complete Manufacturing & ready for Final Inspection | 2026-02-27 | 2026-03-13 | 2026-02-27 | 2026-03-13 | 2026-05-22 | 10 | 2026-06-04 | 60
A36370 | Materials Successfully Inspected, Tested / Ex Work | 2026-03-13 | 2026-03-30 | 2026-03-13 | 2026-03-30 | 2026-06-05 | 11 | 2026-06-19 | 60
A36380 | Delivery of FG Comp. Interstage Cooler (BEM) - Tag# 13-HE-703 | 2026-03-30 | 2026-04-27 | 2026-03-30 | 2026-04-27 | 2026-06-21 | 35 | 2026-07-18 | 103
OG Comp. After Cooler (BEU) - Tag# 13-HE-709 |  | 2026-02-20 | 2026-04-22 | 11-Jul-25 A | 2026-04-22 | 2026-06-21 | 213 | 2026-08-22 | 87
A36430 | Start Production (13-HE-709) |  |  | 11-Jul-25 A |  |  | 0
A36440 | Key Vendor Drawings / Data Approved | 2026-02-20 | 2026-02-20 | 18-Jul-25 A | 28-Aug-25 A | 2026-06-21 | 30 | 2026-06-21
A36450 | Purchase Order for Major Sub-ordered Materials | 2026-02-20 | 2026-02-20 | 29-Aug-25 A | 02-Sep-25 A | 2026-06-21 | 35 | 2026-06-21
A36460 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-02-20 | 2026-02-20 | 11-Aug-25 A | 12-Sep-25 A | 2026-06-21 | 35 | 2026-06-21
A36470 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-02-20 | 2026-02-20 | 15-Sep-25 A | 26-Oct-25 A | 2026-06-21 | 13 | 2026-06-21
A36480 | Manufacturing / Ex Works (India/UAE) | 2026-02-20 | 2026-02-24 | 21-Nov-25 A | 2026-02-24 | 2026-06-21 | 119 | 2026-06-26 | 152
A36490 | Complete Manufacturing & ready for Final Inspection | 2026-02-24 | 2026-03-10 | 2026-02-24 | 2026-03-10 | 2026-06-26 | 10 | 2026-07-09 | 87
A36500 | Materials Successfully Inspected, Tested / Ex Work | 2026-03-10 | 2026-03-25 | 2026-03-10 | 2026-03-25 | 2026-07-10 | 11 | 2026-07-24 | 87
A36520 | Delivery of OG Comp. After Cooler (BEU) - Tag# 13-HE-709 | 2026-03-25 | 2026-04-22 | 2026-03-25 | 2026-04-22 | 2026-07-25 | 35 | 2026-08-22 | 152
FG Comp. After Cooler (BEM) - Tag# 13-HE-704 |  | 2026-02-20 | 2026-04-22 | 11-Jul-25 A | 2026-04-22 | 2026-05-17 | 213 | 2026-07-18 | 62
A36560 | Start Production (13-HE-704) |  |  | 11-Jul-25 A |  |  | 0
A36570 | Key Vendor Drawings / Data Approved | 2026-02-20 | 2026-02-20 | 18-Jul-25 A | 28-Aug-25 A | 2026-05-17 | 30 | 2026-05-17
A36580 | Purchase Order for Major Sub-ordered Materials | 2026-02-20 | 2026-02-20 | 29-Aug-25 A | 02-Sep-25 A | 2026-05-17 | 35 | 2026-05-17
A36590 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-02-20 | 2026-02-20 | 11-Aug-25 A | 12-Sep-25 A | 2026-05-17 | 35 | 2026-05-17
A36600 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-02-20 | 2026-02-20 | 15-Sep-25 A | 26-Oct-25 A | 2026-05-17 | 13 | 2026-05-17
A36610 | Manufacturing / Ex Works (India/UAE) | 2026-02-20 | 2026-02-24 | 21-Nov-25 A | 2026-02-24 | 2026-05-17 | 119 | 2026-05-22 | 108
A36620 | Complete Manufacturing & ready for Final Inspection | 2026-02-24 | 2026-03-10 | 2026-02-24 | 2026-03-10 | 2026-05-22 | 10 | 2026-06-04 | 62
A36630 | Materials Successfully Inspected, Tested / Ex Work | 2026-03-10 | 2026-03-25 | 2026-03-10 | 2026-03-25 | 2026-06-05 | 11 | 2026-06-19 | 62
A36660 | Delivery of FG Comp. After Cooler (BEM) - Tag# 13-HE-704 | 2026-03-25 | 2026-04-22 | 2026-03-25 | 2026-04-22 | 2026-06-21 | 35 | 2026-07-18 | 109
OG Comp. Interstage Cooler (BEU) (13-HE-708) |  | 2026-02-20 | 2026-04-22 | 11-Jul-25 A | 2026-04-22 | 2026-06-21 | 213 | 2026-08-22 | 87
A36690 | Start Production (13-HE-708) |  |  | 11-Jul-25 A |  |  | 0
A36700 | Key Vendor Drawings / Data Approved | 2026-02-20 | 2026-02-20 | 18-Jul-25 A | 28-Aug-25 A | 2026-06-21 | 30 | 2026-06-21
A36710 | Purchase Order for Major Sub-ordered Materials | 2026-02-20 | 2026-02-20 | 29-Aug-25 A | 02-Sep-25 A | 2026-06-21 | 35 | 2026-06-21
A36720 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-02-20 | 2026-02-20 | 11-Aug-25 A | 12-Sep-25 A | 2026-06-21 | 35 | 2026-06-21
A36730 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-02-20 | 2026-02-20 | 15-Sep-25 A | 26-Oct-25 A | 2026-06-21 | 13 | 2026-06-21
A36740 | Manufacturing / Ex Works (India/UAE) | 2026-02-20 | 2026-02-24 | 21-Nov-25 A | 2026-02-24 | 2026-06-21 | 119 | 2026-06-26 | 152
A36750 | Complete Manufacturing & ready for Final Inspection | 2026-02-24 | 2026-03-10 | 2026-02-24 | 2026-03-10 | 2026-06-26 | 10 | 2026-07-09 | 87
A36760 | Materials Successfully Inspected, Tested / Ex Work | 2026-03-10 | 2026-03-25 | 2026-03-10 | 2026-03-25 | 2026-07-10 | 11 | 2026-07-24 | 87
A36800 | Delivery of GG Comp. Interstage Cooler (BEU) (13-HE-708) | 2026-03-25 | 2026-04-22 | 2026-03-25 | 2026-04-22 | 2026-07-25 | 35 | 2026-08-22 | 152
C4 Guard Regen. Gas Cooler (BEU) (Tag#50-HE-1410) |  | 2026-02-20 | 2026-04-26 | 11-Jul-25 A | 2026-04-26 | 2026-08-29 | 212 | 2026-11-04 | 138
A36820 | Start Production (50-HE-1410) |  |  | 11-Jul-25 A |  |  | 0
A36830 | Key Vendor Drawings / Data Approved | 2026-02-20 | 2026-02-20 | 18-Jul-25 A | 28-Aug-25 A | 2026-08-29 | 30 | 2026-08-29
A36840 | Purchase Order for Major Sub-ordered Materials | 2026-02-20 | 2026-02-20 | 29-Aug-25 A | 02-Sep-25 A | 2026-08-29 | 35 | 2026-08-29
A36850 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-02-20 | 2026-02-20 | 11-Aug-25 A | 12-Sep-25 A | 2026-08-29 | 35 | 2026-08-29
A36860 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-02-20 | 2026-02-20 | 15-Sep-25 A | 26-Oct-25 A | 2026-08-29 | 13 | 2026-08-29
A36870 | Manufacturing / Ex Works (India/UAE) | 2026-02-20 | 2026-02-23 | 21-Nov-25 A | 2026-02-23 | 2026-08-29 | 100 | 2026-09-02 | 238
A36880 | Complete Manufacturing & ready for Final Inspection | 2026-02-24 | 2026-03-09 | 2026-02-24 | 2026-03-09 | 2026-09-02 | 10 | 2026-09-15 | 136
A36890 | Materials Successfully Inspected, Tested / Ex Work | 2026-03-10 | 2026-03-24 | 2026-03-10 | 2026-03-24 | 2026-09-16 | 11 | 2026-09-30 | 136
A36940 | Delivery of C4 Guard Regen. Gas Cooler (BEU) (Tag#50-HE-1410) | 2026-04-03 | 2026-04-26 | 2026-04-03 | 2026-04-26 | 2026-10-12 | 30 | 2026-11-04 | 240
HVAC |  | 2026-02-20 | 2026-08-26 | 29-Aug-25 A | 2026-08-26 | 2026-06-15 | 244 | 2026-12-18 | 82
HVAC |  | 2026-02-20 | 2026-08-26 | 29-Aug-25 A | 2026-08-26 | 2026-06-15 | 244 | 2026-12-18 | 82
A33890 | Start Production |  |  | 29-Aug-25 A |  |  | 0
A30860 | Key Vendor Drawings / Data Approved | 2026-02-20 | 2026-02-20 | 03-Sep-25 A | 01-Dec-25 A | 2026-06-15 | 60 | 2026-06-15
A30870 | Purchase Order for Major Sub-ordered Materials | 2026-02-20 | 2026-02-20 | 02-Dec-25 A | 19-Dec-25 A | 2026-06-15 | 10 | 2026-06-15
A30880 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 01-Jan-26 A | 2026-06-15 | 45 | 2026-06-15
A30890 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-02-20 | 2026-02-20 | 01-Jan-26 A | 15-Jan-26 A | 2026-06-15 | 1 | 2026-06-15
A30900 | Manufacturing / Ex Works (India/UAE) | 2026-02-20 | 2026-07-09 | 2026-02-20 | 2026-07-09 | 2026-06-15 | 175 | 2026-11-02 | 144
A30910 | Complete Manufacturing & ready for Final Inspection | 2026-07-10 | 2026-07-20 | 2026-07-10 | 2026-07-20 | 2026-11-02 | 7 | 2026-11-10 | 81
A30920 | Materials Successfully Inspected, Tested / Ex Work | 2026-07-21 | 2026-07-29 | 2026-07-21 | 2026-07-29 | 2026-11-11 | 7 | 2026-11-19 | 81
A34770 | Delivery of HVAC Ducts, E&I Material , Clading, Piping, Insulation, Supports & Accessories | 2026-07-30 | 2026-08-10 | 2026-07-30 | 2026-08-10 | 2026-11-20 | 15 | 2026-12-01 | 141
A33900 | Delivery of Material HVAC (Main Equipments) | 2026-07-30 | 2026-08-26 | 2026-07-30 | 2026-08-26 | 2026-11-21 | 35 | 2026-12-18 | 143
Bulk Materials |  | 2026-02-20 | 2026-09-29 | 15-Mar-25 A | 2026-09-29 | 2026-02-23 | 510 | 2027-07-20 | 210
Drip Leg |  | 2026-02-20 | 2026-07-22 | 03-Sep-25 A | 2026-07-22 | 2026-03-31 | 219 | 2026-08-30 | 27
OG Comp. Dis. Drip leg (02 Nos) |  | 2026-02-20 | 2026-07-22 | 03-Sep-25 A | 2026-07-22 | 2026-03-31 | 219 | 2026-08-30 | 27
A33830 | Start Production |  |  | 03-Sep-25 A |  |  | 0
A30590 | Key Vendor Drawings / Data Approved | 2026-02-20 | 2026-02-20 | 01-Oct-25 A | 03-Nov-25 A | 2026-03-31 | 60 | 2026-03-31
A30600 | Purchase Order for Major Sub-ordered Materials | 2026-02-20 | 2026-02-20 | 03-Nov-25 A | 09-Nov-25 A | 2026-03-31 | 8 | 2026-03-31
A30610 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-02-20 | 2026-02-20 | 10-Nov-25 A | 17-Nov-25 A | 2026-03-31 | 25 | 2026-03-31
A30620 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-03-31 | 1 | 2026-04-01 | 49
A30630 | Manufacturing / Ex Works (India/UAE) | 2026-02-21 | 2026-05-21 | 2026-02-21 | 2026-05-21 | 2026-04-01 | 113 | 2026-06-30 | 49
A30640 | Complete Manufacturing & ready for Final Inspection | 2026-05-22 | 2026-06-01 | 2026-05-22 | 2026-06-01 | 2026-06-30 | 7 | 2026-07-08 | 27
A30650 | Materials Successfully Inspected, Tested / Ex Work | 2026-06-02 | 2026-06-10 | 2026-06-02 | 2026-06-10 | 2026-07-09 | 7 | 2026-07-17 | 27
A33840 | Delivery of OG Compressor Discharge Drip Leg (02) | 2026-06-11 | 2026-07-22 | 2026-06-11 | 2026-07-22 | 2026-07-19 | 53 | 2026-08-30 | 48
Fire Fighting Equipment |  | 2026-02-20 | 2026-07-27 | 27-Oct-25 A | 2026-07-27 | 2026-06-02 | 177 | 2026-11-02 | 70
VESDA (Very Early Smoke Detection Apparatus) |  | 2026-02-20 | 2026-07-23 | 27-Oct-25 A | 2026-07-23 | 2026-06-02 | 175 | 2026-11-02 | 72
A34190 | Start Production |  |  | 27-Oct-25 A |  |  | 0
A32210 | Key Vendor Drawings / Data Approved | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 26-Dec-25 A | 2026-06-02 | 50 | 2026-06-02
A32230 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-02-20 | 2026-02-20 | 29-Dec-25 A | 02-Jan-26 A | 2026-06-02 | 40 | 2026-06-02
A32220 | Purchase Order for Major Sub-ordered Materials | 2026-02-20 | 2026-02-20 | 23-Dec-25 A | 04-Jan-26 A | 2026-06-02 | 10 | 2026-06-02
A32240 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-02-20 | 2026-02-20 | 06-Jan-26 A | 09-Jan-26 A | 2026-06-02 | 1 | 2026-06-02
A32250 | Manufacturing / Ex Works (India/UAE) | 2026-02-20 | 2026-06-04 | 2026-02-20 | 2026-06-04 | 2026-06-02 | 131 | 2026-09-15 | 128
A32260 | Complete Manufacturing & ready for Final Inspection | 2026-06-05 | 2026-06-16 | 2026-06-05 | 2026-06-16 | 2026-09-15 | 8 | 2026-09-24 | 72
A32270 | Materials Successfully Inspected, Tested / Ex Work | 2026-06-16 | 2026-06-25 | 2026-06-16 | 2026-06-25 | 2026-09-24 | 8 | 2026-10-05 | 72
A34200 | Delivery and Manufacturing VESDA | 2026-06-26 | 2026-07-23 | 2026-06-26 | 2026-07-23 | 2026-10-06 | 35 | 2026-11-02 | 128
Fire Fighting Equipment |  | 2026-03-19 | 2026-07-27 | 2026-03-19 | 2026-07-27 | 2026-06-19 | 92 | 2026-10-26 | 65
A33990 | Start Production | 2026-03-19 |  | 2026-03-19 |  | 2026-06-19 | 0 |  | 114
A31310 | Key Vendor Drawings / Data Approved | 2026-03-20 | 2026-04-09 | 2026-03-20 | 2026-04-09 | 2026-06-19 | 15 | 2026-07-09 | 65
A31320 | Purchase Order for Major Sub-ordered Materials | 2026-04-09 | 2026-04-20 | 2026-04-09 | 2026-04-20 | 2026-07-10 | 7 | 2026-07-20 | 65
A31330 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-04-20 | 2026-05-11 | 2026-04-20 | 2026-05-11 | 2026-07-21 | 15 | 2026-08-10 | 65
A31340 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-05-11 | 2026-05-12 | 2026-05-11 | 2026-05-12 | 2026-08-11 | 1 | 2026-08-12 | 114
A31350 | Manufacturing / Ex Works (India/UAE) | 2026-05-12 | 2026-06-16 | 2026-05-12 | 2026-06-16 | 2026-08-12 | 44 | 2026-09-16 | 114
A31360 | Complete Manufacturing & ready for Final Inspection | 2026-06-16 | 2026-06-25 | 2026-06-16 | 2026-06-25 | 2026-09-16 | 7 | 2026-09-24 | 65
A31370 | Materials Successfully Inspected, Tested / Ex Work | 2026-06-25 | 2026-07-06 | 2026-06-25 | 2026-07-06 | 2026-09-25 | 7 | 2026-10-05 | 65
A34000 | Delivery of Fire Fighting Equipments | 2026-07-06 | 2026-07-27 | 2026-07-06 | 2026-07-27 | 2026-10-06 | 26 | 2026-10-26 | 114
Tail Gas Filter/Silencer/Colesor |  | 2026-02-20 | 2026-03-02 | 30-Jan-26 A | 14-Feb-26 A | 2026-11-18 | 223 | 2026-11-18
Coalescer - (BF) |  | 2026-02-20 | 2026-03-02 | 30-Jan-26 A | 14-Feb-26 A | 2026-11-18 | 223 | 2026-11-18
A34680 | Start Production |  |  | 30-Jan-26 A |  |  | 0
A28250 | Key Vendor Drawings / Data Approved | 2026-02-20 | 2026-02-20 | 30-Jan-26 A | 31-Jan-26 A | 2026-11-18 | 50 | 2026-11-18
A28260 | Purchase Order for Major Sub-ordered Materials | 2026-02-20 | 2026-02-20 | 01-Feb-26 A | 02-Feb-26 A | 2026-11-18 | 15 | 2026-11-18
A28270 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-02-20 | 2026-02-20 | 03-Feb-26 A | 04-Feb-26 A | 2026-11-18 | 45 | 2026-11-18
A28280 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-03-02 | 2026-03-02 | 05-Feb-26 A | 06-Feb-26 A | 2026-11-18 | 9 | 2026-11-18
A28290 | Manufacturing / Ex Works (India/UAE) | 2026-03-02 | 2026-03-02 | 07-Feb-26 A | 08-Feb-26 A | 2026-11-18 | 125 | 2026-11-18
A28300 | Complete Manufacturing & ready for Final Inspection | 2026-03-02 | 2026-03-02 | 09-Feb-26 A | 10-Feb-26 A | 2026-11-18 | 7 | 2026-11-18
A28310 | Materials Successfully Inspected, Tested / Ex Work | 2026-03-02 | 2026-03-02 | 11-Feb-26 A | 12-Feb-26 A | 2026-11-18 | 7 | 2026-11-18
A34690 | Delivery of Coalescer (Post TA) | 2026-03-02 | 2026-03-02 | 13-Feb-26 A | 14-Feb-26 A | 2026-11-18 | 38 | 2026-11-18
Steel Structure Greenfield (material +sandwitch Panel) |  | 2026-02-20 | 2026-05-17 | 21-Jun-25 A | 2026-05-17 | 2026-02-23 | 146 | 2026-11-23 | 135
Civil Bulk Material |  | 2026-02-20 | 2026-02-20 | 21-Jun-25 A | 06-Oct-25 A | 2026-11-23 | 129 | 2026-11-23
A33330 | Start Production |  |  | 21-Jun-25 A |  |  | 0
A28430 | Key Vendor Drawings / Data Approved | 2026-02-20 | 2026-02-20 | 23-Jun-25 A | 28-Jul-25 A | 2026-11-23 | 25 | 2026-11-23
A28440 | Purchase Order for Major Sub-ordered Materials | 2026-02-20 | 2026-02-20 | 29-Jul-25 A | 23-Aug-25 A | 2026-11-23 | 30 | 2026-11-23
A28450 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-02-20 | 2026-02-20 | 25-Aug-25 A | 30-Aug-25 A | 2026-11-23 | 15 | 2026-11-23
A28460 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-02-20 | 2026-02-20 | 01-Sep-25 A | 06-Sep-25 A | 2026-11-23 | 9 | 2026-11-23
A28470 | Manufacturing / Ex Works (India/UAE) | 2026-02-20 | 2026-02-20 | 18-Aug-25 A | 15-Sep-25 A | 2026-11-23 | 38 | 2026-11-23
A28480 | Complete Manufacturing & ready for Final Inspection | 2026-02-20 | 2026-02-20 | 08-Sep-25 A | 20-Sep-25 A | 2026-11-23 | 15 | 2026-11-23
A28490 | Materials Successfully Inspected, Tested / Ex Work | 2026-02-20 | 2026-02-20 | 22-Sep-25 A | 29-Sep-25 A | 2026-11-23 | 7 | 2026-11-23
A28500 | Delivery of Civil Bulk Material | 2026-02-20 | 2026-02-20 | 30-Sep-25 A | 06-Oct-25 A | 2026-11-23 | 19 | 2026-11-23
Structural Steel |  | 2026-02-20 | 2026-05-17 | 18-Sep-25 A | 2026-05-17 | 2026-02-23 | 131 | 2026-05-18 | 1
A33350 | Start Production |  |  | 18-Sep-25 A |  |  | 0
A28590 | COMPANY Final decision on Compressor Shelter Height |  |  |  | 15-Dec-25 A |  | 0
A28520 | Key Vendor Drawings / Data Approved | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 24-Jan-26 A | 2026-02-23 | 20 | 2026-02-23
A28530 | Purchase Order for Major Sub-ordered Materials | 2026-02-20 | 2026-02-20 | 25-Jan-26 A | 16-Feb-26 A | 2026-02-23 | 5 | 2026-02-23
A28550 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-03-12 | 2026-03-12 | 17-Feb-26 A | 17-Feb-26 A | 2026-03-14 | 9 | 2026-03-14
A28540 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-02-20 | 2026-03-12 | 17-Feb-26 A | 2026-03-12 | 2026-02-23 | 14 | 2026-03-13 | 1
A28560 | Manufacturing / Ex Works | 2026-03-13 | 2026-04-28 | 2026-03-13 | 2026-04-28 | 2026-03-14 | 59 | 2026-04-30 | 1
A28570 | Complete Manufacturing & ready for Final Inspection | 2026-04-29 | 2026-05-05 | 2026-04-29 | 2026-05-05 | 2026-04-30 | 5 | 2026-05-06 | 1
A28580 | Materials Successfully Inspected, Tested / Ex Work | 2026-05-06 | 2026-05-12 | 2026-05-06 | 2026-05-12 | 2026-05-07 | 5 | 2026-05-13 | 1
A33340 | Delivery of Structural Steel GF | 2026-05-13 | 2026-05-17 | 2026-05-13 | 2026-05-17 | 2026-05-14 | 6 | 2026-05-18 | 1
Tubing Material [SS tubes, Connectors, unions, plugs etc.] |  | 2026-04-16 | 2026-09-13 | 2026-04-16 | 2026-09-13 | 2026-06-02 | 106 | 2026-10-30 | 35
Tubing Material [SS tubes, Connectors, unions, plugs etc] |  | 2026-04-16 | 2026-09-13 | 2026-04-16 | 2026-09-13 | 2026-06-02 | 106 | 2026-10-30 | 35
A33700 | Start Production | 2026-04-16 |  | 2026-04-16 |  | 2026-06-02 | 0 |  | 58
A30140 | Key Vendor Drawings / Data Approved | 2026-04-17 | 2026-05-14 | 2026-04-17 | 2026-05-14 | 2026-06-02 | 20 | 2026-06-29 | 32
A30150 | Purchase Order for Major Sub-ordered Materials | 2026-05-14 | 2026-06-04 | 2026-05-14 | 2026-06-04 | 2026-06-30 | 15 | 2026-07-20 | 32
A30160 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-06-04 | 2026-06-25 | 2026-06-04 | 2026-06-25 | 2026-07-21 | 15 | 2026-08-10 | 32
A30170 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-06-25 | 2026-06-26 | 2026-06-25 | 2026-06-26 | 2026-08-11 | 1 | 2026-08-12 | 58
A30180 | Manufacturing / Ex Works (India/UAE) | 2026-06-26 | 2026-08-15 | 2026-06-26 | 2026-08-15 | 2026-08-12 | 63 | 2026-10-01 | 58
A30190 | Complete Manufacturing & ready for Final Inspection | 2026-08-17 | 2026-08-25 | 2026-08-17 | 2026-08-25 | 2026-10-01 | 7 | 2026-10-09 | 33
A30200 | Materials Successfully Inspected, Tested / Ex Work | 2026-08-26 | 2026-09-03 | 2026-08-26 | 2026-09-03 | 2026-10-12 | 7 | 2026-10-20 | 33
A33710 | Delivery at site - (Tubing Material) | 2026-09-04 | 2026-09-13 | 2026-09-04 | 2026-09-13 | 2026-10-21 | 13 | 2026-10-30 | 59
Steel Structure Brownfield |  | 2026-02-20 | 2026-04-19 | 15-Mar-25 A | 2026-04-19 | 2026-03-27 | 362 | 2026-09-20 | 110
Steel Structure - Post TA - BF |  | 2026-02-20 | 2026-04-19 | 18-Sep-25 A | 2026-04-19 | 2026-07-24 | 163 | 2026-09-20 | 110
A34560 | Start Production |  |  | 18-Sep-25 A |  |  | 0
A34570 | Key Vendor Drawings / Data Approved | 2026-02-20 | 2026-02-20 | 01-Feb-26 A | 06-Feb-26 A | 2026-07-24 | 20 | 2026-07-24
A34580 | Purchase Order for Major Sub-ordered Materials | 2026-02-20 | 2026-02-20 | 09-Feb-26 A | 13-Feb-26 A | 2026-07-24 | 14 | 2026-07-24
A34590 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-02-20 | 2026-02-20 | 16-Feb-26 A | 16-Feb-26 A | 2026-07-24 | 21 | 2026-07-24
A34600 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-02-20 | 2026-02-20 | 17-Feb-26 A | 17-Feb-26 A | 2026-07-24 | 9 | 2026-07-24
A34610 | Manufacturing / Ex Works | 2026-02-20 | 2026-03-31 | 18-Feb-26 A | 2026-03-31 | 2026-07-24 | 50 | 2026-09-02 | 193
A34620 | Complete Manufacturing & ready for Final Inspection | 2026-04-01 | 2026-04-07 | 2026-04-01 | 2026-04-07 | 2026-09-02 | 5 | 2026-09-08 | 110
A34630 | Materials Successfully Inspected, Tested / Ex Work | 2026-04-08 | 2026-04-14 | 2026-04-08 | 2026-04-14 | 2026-09-09 | 5 | 2026-09-15 | 110
A34650 | Delivery of (Steel Structure - PostTA) | 2026-04-15 | 2026-04-19 | 2026-04-15 | 2026-04-19 | 2026-09-16 | 6 | 2026-09-20 | 193
TA_Steel Structure ( Additional Steel Structure required for BFW) |  | 2026-02-20 | 2026-02-20 | 15-Mar-25 A | 09-May-25 A | 2026-03-27 | 102 | 2026-03-27
A34490 | Start Production |  |  | 15-Mar-25 A |  |  | 0
A27800 | Key Vendor Drawings / Data Approved | 2026-02-20 | 2026-02-20 | 15-Mar-25 A | 20-Mar-25 A | 2026-03-27 | 5 | 2026-03-27
A27810 | Purchase Order for Major Sub-ordered Materials | 2026-02-20 | 2026-02-20 | 17-Mar-25 A | 21-Mar-25 A | 2026-03-27 | 5 | 2026-03-27
A27820 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-02-20 | 2026-02-20 | 22-Mar-25 A | 28-Mar-25 A | 2026-03-27 | 5 | 2026-03-27
A27830 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 04-Apr-25 A | 2026-03-27 | 1 | 2026-03-27
A27840 | Manufacturing / Ex Works (India/UAE) | 2026-02-20 | 2026-02-20 | 05-Apr-25 A | 11-Apr-25 A | 2026-03-27 | 56 | 2026-03-27
A27850 | Complete Manufacturing & ready for Final Inspection | 2026-02-20 | 2026-02-20 | 12-Apr-25 A | 18-Apr-25 A | 2026-03-27 | 2 | 2026-03-27
A27860 | Materials Successfully Inspected, Tested / Ex Work | 2026-02-20 | 2026-02-20 | 19-Apr-25 A | 25-Apr-25 A | 2026-03-27 | 5 | 2026-03-27
A34450 | Delivery at Site by EPC ( Fabricated, Painted & Galvanized TA Steel Structure ) | 2026-02-20 | 2026-02-20 | 26-Apr-25 A | 09-May-25 A | 2026-03-27 | 5 | 2026-03-27
Telecom (ACS+LAN +CCTV+PAGA) |  | 2026-02-20 | 2026-09-09 | 11-Dec-25 A | 2026-09-09 | 2026-04-08 | 195 | 2026-12-10 | 66
Telecom (ACS + CCTV + PAGA) Integration |  | 2026-02-20 | 2026-08-21 | 11-Dec-25 A | 2026-08-21 | 2026-06-11 | 131 | 2026-12-10 | 79
A34010 | Start Production |  |  | 19-Dec-25 A |  |  | 0
A31400 | Key Vendor Drawings / Data Approved | 2026-02-20 | 2026-03-20 | 20-Feb-26 A | 2026-03-20 | 2026-06-11 | 40 | 2026-07-09 | 79
A31410 | Purchase Order for Major Sub-ordered Materials | 2026-03-09 | 2026-03-20 | 11-Dec-25 A | 2026-03-20 | 2026-06-29 | 10 | 2026-07-09 | 79
A31420 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-03-20 | 2026-04-20 | 2026-03-20 | 2026-04-20 | 2026-07-10 | 21 | 2026-08-07 | 79
A31430 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-04-20 | 2026-04-21 | 2026-04-20 | 2026-04-21 | 2026-08-10 | 1 | 2026-08-11 | 139
A31440 | Manufacturing / Ex Works (India/UAE) | 2026-04-21 | 2026-07-20 | 2026-04-21 | 2026-07-20 | 2026-08-11 | 113 | 2026-11-09 | 139
A31450 | Complete Manufacturing & ready for Final Inspection | 2026-07-20 | 2026-07-29 | 2026-07-20 | 2026-07-29 | 2026-11-09 | 7 | 2026-11-17 | 79
A31460 | Materials Successfully Inspected, Tested / Ex Work | 2026-07-29 | 2026-08-07 | 2026-07-29 | 2026-08-07 | 2026-11-18 | 7 | 2026-11-26 | 79
A34020 | Delivery of Telecom (ACS + CCTV + PAGA) Integration | 2026-08-07 | 2026-08-21 | 2026-08-07 | 2026-08-21 | 2026-11-27 | 18 | 2026-12-10 | 139
Acess Control System |  | 2026-02-20 | 2026-09-09 | 12-Dec-25 A | 2026-09-09 | 2026-04-08 | 194 | 2026-10-26 | 33
A34030 | Start Production |  |  | 12-Dec-25 A |  |  | 0
A31500 | Purchase Order for Major Sub-ordered Materials | 2026-04-09 | 2026-04-09 | 12-Dec-25 A | 25-Dec-25 A | 2026-05-27 | 10 | 2026-05-27
A31490 | Key Vendor Drawings / Data Approved | 2026-02-20 | 2026-04-09 | 20-Feb-26 A | 2026-04-09 | 2026-04-08 | 50 | 2026-05-26 | 33
A31510 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-04-09 | 2026-05-07 | 2026-04-09 | 2026-05-07 | 2026-05-27 | 20 | 2026-06-23 | 33
A31520 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-05-07 | 2026-05-08 | 2026-05-07 | 2026-05-08 | 2026-06-24 | 1 | 2026-06-25 | 59
A31530 | Manufacturing / Ex Works (India/UAE) | 2026-05-08 | 2026-08-06 | 2026-05-08 | 2026-08-06 | 2026-06-25 | 113 | 2026-09-23 | 59
A31540 | Complete Manufacturing & ready for Final Inspection | 2026-08-06 | 2026-08-17 | 2026-08-06 | 2026-08-17 | 2026-09-23 | 7 | 2026-10-01 | 33
A31550 | Materials Successfully Inspected, Tested / Ex Work | 2026-08-17 | 2026-08-26 | 2026-08-17 | 2026-08-26 | 2026-10-02 | 7 | 2026-10-12 | 33
A34040 | Delivery of ACS | 2026-08-26 | 2026-09-09 | 2026-08-26 | 2026-09-09 | 2026-10-13 | 18 | 2026-10-26 | 59
CCTV |  | 2026-02-20 | 2026-08-25 | 19-Dec-25 A | 2026-08-25 | 2026-05-13 | 133 | 2026-11-15 | 58
A34210 | Start Production |  |  | 19-Dec-25 A |  |  | 0
A32310 | Purchase Order for Major Sub-ordered Materials | 2026-03-19 | 2026-04-02 | 2026-03-19 | 2026-04-02 | 2026-06-10 | 10 | 2026-06-23 | 58
A34220 | Key Vendor Drawings / Data Approved | 2026-02-20 | 2026-04-02 | 2026-02-20 | 2026-04-02 | 2026-05-13 | 30 | 2026-06-23 | 58
A32320 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-04-02 | 2026-05-14 | 2026-04-02 | 2026-05-14 | 2026-06-24 | 30 | 2026-08-04 | 58
A32330 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-05-14 | 2026-05-15 | 2026-05-14 | 2026-05-15 | 2026-08-05 | 1 | 2026-08-06 | 103
A32340 | Manufacturing / Ex Works (India/UAE) | 2026-05-15 | 2026-07-29 | 2026-05-15 | 2026-07-29 | 2026-08-06 | 94 | 2026-10-20 | 103
A32350 | Complete Manufacturing & ready for Final Inspection | 2026-07-29 | 2026-08-07 | 2026-07-29 | 2026-08-07 | 2026-10-20 | 7 | 2026-10-28 | 58
A32360 | Materials Successfully Inspected, Tested / Ex Work | 2026-08-07 | 2026-08-18 | 2026-08-07 | 2026-08-18 | 2026-10-29 | 7 | 2026-11-06 | 58
A34250 | Delivery of CCTV | 2026-08-18 | 2026-08-25 | 2026-08-18 | 2026-08-25 | 2026-11-09 | 9 | 2026-11-15 | 103
PAGA + Telephone |  | 2026-02-20 | 2026-08-21 | 11-Dec-25 A | 2026-08-21 | 2026-05-22 | 182 | 2026-11-22 | 65
A34050 | Start Production |  |  | 19-Dec-25 A |  |  | 0
A31580 | Key Vendor Drawings / Data Approved | 2026-02-20 | 2026-03-20 | 19-Dec-25 A | 2026-03-20 | 2026-05-22 | 50 | 2026-06-19 | 65
A31590 | Purchase Order for Major Sub-ordered Materials | 2026-03-09 | 2026-03-20 | 11-Dec-25 A | 2026-03-20 | 2026-06-09 | 10 | 2026-06-19 | 65
A31600 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-03-20 | 2026-04-20 | 2026-03-20 | 2026-04-20 | 2026-06-22 | 21 | 2026-07-20 | 65
A31610 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-04-20 | 2026-04-21 | 2026-04-20 | 2026-04-21 | 2026-07-21 | 1 | 2026-07-22 | 114
A31620 | Manufacturing / Ex Works (India/UAE) | 2026-04-21 | 2026-07-20 | 2026-04-21 | 2026-07-20 | 2026-07-22 | 113 | 2026-10-20 | 114
A31630 | Complete Manufacturing & ready for Final Inspection | 2026-07-20 | 2026-07-29 | 2026-07-20 | 2026-07-29 | 2026-10-20 | 7 | 2026-10-28 | 65
A31640 | Materials Successfully Inspected, Tested / Ex Work | 2026-07-29 | 2026-08-07 | 2026-07-29 | 2026-08-07 | 2026-10-29 | 7 | 2026-11-06 | 65
A34060 | Delivery of PAGA + Telephone | 2026-08-07 | 2026-08-21 | 2026-08-07 | 2026-08-21 | 2026-11-09 | 18 | 2026-11-22 | 116
Lighting Fixtures |  | 2026-05-22 | 2026-09-22 | 2026-05-22 | 2026-09-22 | 2026-09-11 | 87 | 2027-01-10 | 78
Lighting Fixtures (Almost 50% Exd = 354 Nos) |  | 2026-05-22 | 2026-09-22 | 2026-05-22 | 2026-09-22 | 2026-09-11 | 87 | 2027-01-10 | 78
A34230 | Start Production | 2026-05-22 |  | 2026-05-22 |  | 2026-09-11 | 0 |  | 139
A32390 | Key Vendor Drawings / Data Approved | 2026-05-25 | 2026-06-22 | 2026-05-25 | 2026-06-22 | 2026-09-11 | 21 | 2026-10-09 | 79
A32400 | Purchase Order for Major Sub-ordered Materials | 2026-06-22 | 2026-07-06 | 2026-06-22 | 2026-07-06 | 2026-10-12 | 10 | 2026-10-23 | 79
A32410 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-07-06 | 2026-07-27 | 2026-07-06 | 2026-07-27 | 2026-10-26 | 15 | 2026-11-13 | 79
A32420 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-07-27 | 2026-07-28 | 2026-07-27 | 2026-07-28 | 2026-11-15 | 1 | 2026-11-16 | 138
A32430 | Manufacturing / Ex Works (India/UAE) | 2026-07-28 | 2026-09-01 | 2026-07-28 | 2026-09-01 | 2026-11-16 | 44 | 2026-12-21 | 138
A32440 | Complete Manufacturing & ready for Final Inspection | 2026-09-01 | 2026-09-08 | 2026-09-01 | 2026-09-08 | 2026-12-21 | 5 | 2026-12-25 | 78
A32450 | Materials Successfully Inspected, Tested / Ex Work | 2026-09-08 | 2026-09-15 | 2026-09-08 | 2026-09-15 | 2026-12-28 | 5 | 2027-01-01 | 78
A34240 | Delivery of Material in Warehouse Lighting Fixtures | 2026-09-15 | 2026-09-22 | 2026-09-15 | 2026-09-22 | 2027-01-04 | 9 | 2027-01-10 | 138
Manual Valve |  | 2026-02-20 | 2026-07-30 | 20-Nov-25 A | 2026-07-30 | 2026-05-18 | 180 | 2026-10-26 | 62
Manual Valves (Gate 9 Nos, Check 6 Nos, Globe Valves 64 Nos) |  | 2026-02-20 | 2026-07-30 | 20-Nov-25 A | 2026-07-30 | 2026-05-18 | 180 | 2026-10-26 | 62
A33680 | Start Production |  |  | 20-Nov-25 A |  |  | 0
A30050 | Key Vendor Drawings / Data Approved | 2026-02-20 | 2026-03-05 | 20-Feb-26 A | 2026-03-05 | 2026-05-18 | 30 | 2026-05-29 | 61
A30060 | Purchase Order for Major Sub-ordered Materials | 2026-03-05 | 2026-03-12 | 2026-03-05 | 2026-03-12 | 2026-06-01 | 5 | 2026-06-05 | 61
A30080 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-03-12 | 2026-03-13 | 2026-03-12 | 2026-03-13 | 2026-06-07 | 1 | 2026-06-08 | 108
A30070 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-03-12 | 2026-04-23 | 2026-03-12 | 2026-04-23 | 2026-06-05 | 30 | 2026-07-17 | 61
A30090 | Manufacturing / Ex Works (India/UAE) | 2026-03-13 | 2026-06-21 | 2026-03-13 | 2026-06-21 | 2026-06-08 | 125 | 2026-09-16 | 108
A30100 | Complete Manufacturing & ready for Final Inspection | 2026-06-22 | 2026-06-30 | 2026-06-22 | 2026-06-30 | 2026-09-16 | 7 | 2026-09-24 | 62
A30110 | Materials Successfully Inspected, Tested / Ex Work | 2026-07-01 | 2026-07-09 | 2026-07-01 | 2026-07-09 | 2026-09-25 | 7 | 2026-10-05 | 62
A33690 | Delivery at site warehouse for Manual Valves (Gate 9 Nos, Check 6 Nos, Globe Valves 64 Nos) | 2026-07-10 | 2026-07-30 | 2026-07-10 | 2026-07-30 | 2026-10-06 | 26 | 2026-10-26 | 110
Piping Bulk |  | 2026-02-20 | 2026-09-29 | 01-Sep-25 A | 2026-09-29 | 2026-03-30 | 243 | 2027-07-20 | 210
Piping Lot for Post TA |  | 2026-02-20 | 2026-03-06 | 01-Sep-25 A | 2026-03-06 | 2026-04-22 | 146 | 2026-05-06 | 43
A34500 | Start Production |  |  | 01-Sep-25 A |  |  | 0
A27990 | Purchase Order for Major Sub-ordered Materials | 2026-02-20 | 2026-02-20 | 02-Sep-25 A | 08-Sep-25 A | 2026-04-22 | 5 | 2026-04-22
A28000 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-02-20 | 2026-02-20 | 22-Oct-25 A | 31-Oct-25 A | 2026-04-22 | 15 | 2026-04-22
A28010 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-02-20 | 2026-02-20 | 03-Nov-25 A | 25-Dec-25 A | 2026-04-22 | 9 | 2026-04-22
A28020 | Manufacturing / Ex Works (India/UAE) | 2026-02-20 | 2026-02-20 | 26-Dec-25 A | 18-Jan-26 A | 2026-04-22 | 100 | 2026-04-22
A28030 | Complete Manufacturing & ready for Final Inspection | 2026-02-20 | 2026-02-20 | 26-Jan-26 A | 30-Jan-26 A | 2026-04-22 | 7 | 2026-04-22
A28040 | Materials Successfully Inspected, Tested / Ex Work | 2026-02-20 | 2026-02-20 | 02-Feb-26 A | 06-Feb-26 A | 2026-04-22 | 10 | 2026-04-22
84.D50 | Delivery of Piping Material in Warehouse (1st Lot, GF) | 2026-02-20 | 2026-03-06 | 10-Feb-26 A | 2026-03-06 | 2026-04-22 | 13 | 2026-05-06 | 76
Piping Supports (Swing Hangers) for Post TA |  | 2026-02-20 | 2026-07-16 | 2026-02-20 | 2026-07-16 | 2026-03-30 | 105 | 2026-09-08 | 38
A34510 | Start Production | 2026-02-20 |  | 2026-02-20 |  | 2026-03-30 | 0 |  | 48
A28070 | Key Vendor Drawings / Data Approved | 2026-02-20 | 2026-03-19 | 2026-02-20 | 2026-03-19 | 2026-03-30 | 20 | 2026-04-24 | 26
A28080 | Purchase Order for Major Sub-ordered Materials | 2026-03-19 | 2026-03-26 | 2026-03-19 | 2026-03-26 | 2026-04-27 | 5 | 2026-05-01 | 26
A28090 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-03-26 | 2026-04-16 | 2026-03-26 | 2026-04-16 | 2026-05-04 | 15 | 2026-05-22 | 26
A28100 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-04-16 | 2026-04-23 | 2026-04-16 | 2026-04-23 | 2026-05-25 | 9 | 2026-06-01 | 48
A28110 | Manufacturing / Ex Works | 2026-04-23 | 2026-06-18 | 2026-04-23 | 2026-06-18 | 2026-06-01 | 70 | 2026-07-27 | 48
A28120 | Complete Manufacturing & ready for Final Inspection | 2026-06-18 | 2026-07-02 | 2026-06-18 | 2026-07-02 | 2026-07-27 | 10 | 2026-08-07 | 26
A28130 | Materials Successfully Inspected, Tested / Ex Work | 2026-07-02 | 2026-07-09 | 2026-07-02 | 2026-07-09 | 2026-08-10 | 5 | 2026-08-14 | 26
A34520 | Delivery of Material in Warehouse ( Piping Swing Hangers - PostTA) | 2026-07-09 | 2026-07-16 | 2026-07-09 | 2026-07-16 | 2026-09-02 | 9 | 2026-09-08 | 68
Piping 1st Lot for GF |  | 2026-02-20 | 2026-02-20 | 01-Sep-25 A | 31-Jan-26 A | 2026-04-20 | 96 | 2026-04-20
A33360 | Start Production |  |  | 01-Sep-25 A |  |  | 0
A28620 | Purchase Order for Major Sub-ordered Materials | 2026-02-20 | 2026-02-20 | 02-Sep-25 A | 08-Sep-25 A | 2026-04-20 | 5 | 2026-04-20
A28630 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-02-20 | 2026-02-20 | 03-Sep-25 A | 15-Sep-25 A | 2026-04-20 | 10 | 2026-04-20
A28640 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 25-Dec-25 A | 2026-04-20 | 9 | 2026-04-20
A28650 | Manufacturing / Ex Works (India/UAE) | 2026-02-20 | 2026-02-20 | 26-Dec-25 A | 18-Jan-26 A | 2026-04-20 | 75 | 2026-04-20
A28660 | Complete Manufacturing & ready for Final Inspection | 2026-02-20 | 2026-02-20 | 19-Jan-26 A | 23-Jan-26 A | 2026-04-20 | 2 | 2026-04-20
A28670 | Materials Successfully Inspected, Tested / Ex Work | 2026-02-20 | 2026-02-20 | 19-Jan-26 A | 23-Jan-26 A | 2026-04-20 | 5 | 2026-04-20
84.D40 | Delivery of Piping Material in Warehouse (1st Lot, GF) | 2026-02-20 | 2026-02-20 | 26-Jan-26 A | 31-Jan-26 A | 2026-04-20 | 9 | 2026-04-20
Piping 2nd Lot for GF (CS Material) |  | 2026-02-20 | 2026-04-17 | 26-Dec-25 A | 2026-04-17 | 2026-05-19 | 72 | 2026-07-15 | 63
A33370 | Start Production |  |  | 26-Dec-25 A |  |  | 0
A28710 | Purchase Order for Major Sub-ordered Materials | 2026-02-20 | 2026-02-20 | 28-Dec-25 A | 02-Jan-26 A | 2026-05-19 | 10 | 2026-05-19
A28720 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-02-20 | 2026-02-20 | 26-Dec-25 A | 09-Jan-26 A | 2026-05-19 | 15 | 2026-05-19
A28730 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-02-20 | 2026-02-20 | 09-Jan-26 A | 16-Jan-26 A | 2026-05-19 | 9 | 2026-05-19
A28740 | Manufacturing / Ex Works (India/UAE) | 2026-02-20 | 2026-03-21 | 15-Jan-26 A | 2026-03-21 | 2026-05-19 | 75 | 2026-06-18 | 110
A28750 | Complete Manufacturing & ready for Final Inspection | 2026-03-23 | 2026-03-27 | 2026-03-23 | 2026-03-27 | 2026-06-18 | 5 | 2026-06-24 | 63
A28760 | Materials Successfully Inspected, Tested / Ex Work | 2026-03-30 | 2026-04-03 | 2026-03-30 | 2026-04-03 | 2026-06-25 | 5 | 2026-07-01 | 63
85.D10 | Delivery of Piping Material in Warehouse (2nd Lot) | 2026-04-04 | 2026-04-17 | 2026-04-04 | 2026-04-17 | 2026-07-02 | 18 | 2026-07-15 | 111
Piping 3rd Lot GF (CS Material) |  | 2026-04-22 | 2026-08-21 | 2026-04-22 | 2026-08-21 | 2026-05-14 | 87 | 2026-09-11 | 15
A33380 | Start Production | 2026-04-22 |  | 2026-04-22 |  | 2026-05-14 | 0 |  | 27
A28800 | Purchase Order for Major Sub-ordered Materials | 2026-04-22 | 2026-04-29 | 2026-04-22 | 2026-04-29 | 2026-05-14 | 5 | 2026-05-20 | 15
A28810 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-04-29 | 2026-05-20 | 2026-04-29 | 2026-05-20 | 2026-05-21 | 15 | 2026-06-10 | 15
A28820 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-05-20 | 2026-05-23 | 2026-05-20 | 2026-05-23 | 2026-06-11 | 4 | 2026-06-14 | 27
A28830 | Manufacturing / Ex Works (India/UAE) | 2026-05-23 | 2026-07-22 | 2026-05-23 | 2026-07-22 | 2026-06-14 | 75 | 2026-08-13 | 27
A28840 | Complete Manufacturing & ready for Final Inspection | 2026-07-22 | 2026-07-29 | 2026-07-22 | 2026-07-29 | 2026-08-13 | 5 | 2026-08-19 | 15
A28850 | Materials Successfully Inspected, Tested / Ex Work | 2026-07-29 | 2026-08-07 | 2026-07-29 | 2026-08-07 | 2026-08-20 | 7 | 2026-08-28 | 15
A28860 | Delivery of Piping Material in Warehouse (Final Lot) | 2026-08-07 | 2026-08-21 | 2026-08-07 | 2026-08-21 | 2026-08-29 | 18 | 2026-09-11 | 27
Piping Supports (Swing Hangers) for GF |  | 2026-07-24 | 2026-09-29 | 2026-07-24 | 2026-09-29 | 2027-05-17 | 47 | 2027-07-20 | 210
A33400 | Start Production | 2026-07-24 |  | 2026-07-24 |  | 2027-05-17 | 0 |  | 370
A28970 | Key Vendor Drawings / Data Approved | 2026-07-24 | 2026-07-31 | 2026-07-24 | 2026-07-31 | 2027-05-17 | 5 | 2027-05-21 | 210
A28980 | Purchase Order for Major Sub-ordered Materials | 2026-07-31 | 2026-08-07 | 2026-07-31 | 2026-08-07 | 2027-05-24 | 5 | 2027-05-28 | 210
A28990 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-08-07 | 2026-08-14 | 2026-08-07 | 2026-08-14 | 2027-05-31 | 5 | 2027-06-04 | 210
A29000 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-08-14 | 2026-08-19 | 2026-08-14 | 2026-08-19 | 2027-06-06 | 6 | 2027-06-11 | 369
A29010 | Manufacturing / Ex Works (India/UAE) | 2026-08-19 | 2026-08-29 | 2026-08-19 | 2026-08-29 | 2027-06-11 | 13 | 2027-06-21 | 369
A29020 | Complete Manufacturing & ready for Final Inspection | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | 2027-06-21 | 5 | 2027-06-25 | 210
A29030 | Materials Successfully Inspected, Tested / Ex Work | 2026-09-07 | 2026-09-14 | 2026-09-07 | 2026-09-14 | 2027-06-28 | 6 | 2027-07-05 | 210
A29040 | Delivery of Pipng Supports | 2026-09-15 | 2026-09-29 | 2026-09-15 | 2026-09-29 | 2027-07-06 | 19 | 2027-07-20 | 368
HDPE Piping |  | 2026-02-20 | 2026-07-16 | 2026-02-20 | 2026-07-16 | 2026-04-09 | 105 | 2026-09-02 | 34
HDPE Piping GF (Fire Water Lines) |  | 2026-02-20 | 2026-07-16 | 2026-02-20 | 2026-07-16 | 2026-04-09 | 105 | 2026-09-02 | 34
A33390 | Start Production | 2026-02-20 |  | 2026-02-20 |  | 2026-04-09 | 0 |  | 60
A28880 | Key Vendor Drawings / Data Approved | 2026-02-20 | 2026-03-19 | 2026-02-20 | 2026-03-19 | 2026-04-09 | 20 | 2026-05-06 | 34
A28890 | Purchase Order for Major Sub-ordered Materials | 2026-03-19 | 2026-03-26 | 2026-03-19 | 2026-03-26 | 2026-05-07 | 5 | 2026-05-13 | 34
A28900 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-03-26 | 2026-04-16 | 2026-03-26 | 2026-04-16 | 2026-05-14 | 15 | 2026-06-03 | 34
A28910 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-04-16 | 2026-04-17 | 2026-04-16 | 2026-04-17 | 2026-06-04 | 1 | 2026-06-05 | 60
A28920 | Manufacturing / Ex Works | 2026-04-17 | 2026-06-16 | 2026-04-17 | 2026-06-16 | 2026-06-05 | 75 | 2026-08-04 | 60
A28930 | Complete Manufacturing & ready for Final Inspection | 2026-06-16 | 2026-06-23 | 2026-06-16 | 2026-06-23 | 2026-08-04 | 5 | 2026-08-10 | 34
A28940 | Materials Successfully Inspected, Tested / Ex Work | 2026-06-23 | 2026-07-02 | 2026-06-23 | 2026-07-02 | 2026-08-11 | 7 | 2026-08-19 | 34
A28950 | Delivery of HDPE Piping GF (Fire Water Lines) | 2026-07-02 | 2026-07-16 | 2026-07-02 | 2026-07-16 | 2026-08-20 | 18 | 2026-09-02 | 60
Piping SP Items (strainer, filters) |  | 2026-03-27 | 2026-09-04 | 2026-03-27 | 2026-09-04 | 2026-05-25 | 115 | 2026-10-31 | 40
Specialized Items (Orifice Flanges) CS 300# 1" - 6" = 08 Nos |  | 2026-04-01 | 2026-09-01 | 2026-04-01 | 2026-09-01 | 2026-06-02 | 109 | 2026-10-31 | 44
A33720 | Start Production | 2026-04-01 |  | 2026-04-01 |  | 2026-06-02 | 0 |  | 77
A30230 | Key Vendor Drawings / Data Approved | 2026-04-01 | 2026-04-22 | 2026-04-01 | 2026-04-22 | 2026-06-02 | 15 | 2026-06-22 | 44
A30240 | Purchase Order for Major Sub-ordered Materials | 2026-04-22 | 2026-04-29 | 2026-04-22 | 2026-04-29 | 2026-06-23 | 5 | 2026-06-29 | 44
A30250 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-04-29 | 2026-05-20 | 2026-04-29 | 2026-05-20 | 2026-06-30 | 15 | 2026-07-20 | 44
A30260 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-05-20 | 2026-05-21 | 2026-05-20 | 2026-05-21 | 2026-07-21 | 1 | 2026-07-22 | 77
A30270 | Manufacturing / Ex Works (India/UAE) | 2026-05-21 | 2026-08-04 | 2026-05-21 | 2026-08-04 | 2026-07-22 | 94 | 2026-10-05 | 77
A30280 | Complete Manufacturing & ready for Final Inspection | 2026-08-04 | 2026-08-11 | 2026-08-04 | 2026-08-11 | 2026-10-05 | 5 | 2026-10-09 | 44
A30290 | Materials Successfully Inspected, Tested / Ex Work | 2026-08-11 | 2026-08-18 | 2026-08-11 | 2026-08-18 | 2026-10-12 | 5 | 2026-10-16 | 44
A30300 | Delivery of Orifice Flanges | 2026-08-18 | 2026-09-01 | 2026-08-18 | 2026-09-01 | 2026-10-18 | 18 | 2026-10-31 | 76
Specialized Items (Strainer/Filter) CS & SS 150 # -300# 2" - 26" = 08 Nos |  | 2026-03-27 | 2026-09-04 | 2026-03-27 | 2026-09-04 | 2026-05-25 | 115 | 2026-10-31 | 40
A33730 | Start Production | 2026-03-27 |  | 2026-03-27 |  | 2026-05-25 | 0 |  | 73
A30320 | Key Vendor Drawings / Data Approved | 2026-03-30 | 2026-04-24 | 2026-03-30 | 2026-04-24 | 2026-05-25 | 20 | 2026-06-19 | 40
A30330 | Purchase Order for Major Sub-ordered Materials | 2026-04-24 | 2026-05-01 | 2026-04-24 | 2026-05-01 | 2026-06-22 | 5 | 2026-06-26 | 40
A30340 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-05-01 | 2026-05-29 | 2026-05-01 | 2026-05-29 | 2026-06-29 | 20 | 2026-07-24 | 40
A30350 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-05-29 | 2026-05-30 | 2026-05-29 | 2026-05-30 | 2026-07-26 | 1 | 2026-07-27 | 72
A30360 | Manufacturing / Ex Works (India/UAE) | 2026-05-30 | 2026-07-25 | 2026-05-30 | 2026-07-25 | 2026-07-27 | 70 | 2026-09-21 | 72
A30370 | Complete Manufacturing & ready for Final Inspection | 2026-07-27 | 2026-07-31 | 2026-07-27 | 2026-07-31 | 2026-09-21 | 5 | 2026-09-25 | 40
A30380 | Materials Successfully Inspected, Tested / Ex Work | 2026-08-03 | 2026-08-07 | 2026-08-03 | 2026-08-07 | 2026-09-28 | 5 | 2026-10-02 | 40
A30390 | Delivery of Strainer/Filters Flanges | 2026-08-08 | 2026-09-04 | 2026-08-08 | 2026-09-04 | 2026-10-04 | 35 | 2026-10-31 | 71
Pressure / Temperature / Level Instruments, Flowmeters |  | 2026-02-20 | 2026-09-02 | 20-Dec-25 A | 2026-09-02 | 2026-03-27 | 156 | 2026-10-07 | 25
PT, TT & DPT [PT 50 Nos, TT 33 Nos, DPT 20 Nos] |  | 2026-02-20 | 2026-09-02 | 20-Dec-25 A | 2026-09-02 | 2026-03-27 | 156 | 2026-10-07 | 25
A33510 | Start Production |  |  | 20-Dec-25 A |  |  | 0
A29510 | Key Vendor Drawings / Data Approved | 2026-02-20 | 2026-03-19 | 2026-02-20 | 2026-03-19 | 2026-03-27 | 20 | 2026-04-23 | 25
A29520 | Purchase Order for Major Sub-ordered Materials | 2026-03-19 | 2026-04-16 | 2026-03-19 | 2026-04-16 | 2026-04-24 | 20 | 2026-05-21 | 25
A29530 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-04-16 | 2026-05-14 | 2026-04-16 | 2026-05-14 | 2026-05-22 | 20 | 2026-06-18 | 25
A29540 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-05-14 | 2026-05-15 | 2026-05-14 | 2026-05-15 | 2026-06-19 | 1 | 2026-06-20 | 44
A29550 | Manufacturing / Ex Works (India/UAE) | 2026-05-15 | 2026-07-14 | 2026-05-15 | 2026-07-14 | 2026-06-20 | 75 | 2026-08-19 | 44
A29560 | Complete Manufacturing & ready for Final Inspection | 2026-07-14 | 2026-08-04 | 2026-07-14 | 2026-08-04 | 2026-08-19 | 15 | 2026-09-08 | 25
A29570 | Materials Successfully Inspected, Tested / Ex Work | 2026-08-04 | 2026-08-25 | 2026-08-04 | 2026-08-25 | 2026-09-09 | 15 | 2026-09-29 | 25
A33520 | Delivery of Material in Warehouse for PT,TT & DPT | 2026-08-25 | 2026-09-02 | 2026-08-25 | 2026-09-02 | 2026-09-30 | 10 | 2026-10-07 | 44
Instrument Bulk Material |  | 2026-02-20 | 2026-09-24 | 24-May-25 A | 2026-09-24 | 2026-03-12 | 250 | 2026-11-28 | 46
Gauges (PG, TG, PDG) PG - 10bar & 40bar = 19 Nos, DP = 05 Nos, TG = 09 Nos |  | 2026-03-25 | 2026-08-24 | 2026-03-25 | 2026-08-24 | 2026-06-03 | 108 | 2026-10-30 | 50
A34340 | Start Production | 2026-03-25 |  | 2026-03-25 |  | 2026-06-03 | 0 |  | 87
A32840 | Key Vendor Drawings / Data Approved | 2026-03-25 | 2026-04-23 | 2026-03-25 | 2026-04-23 | 2026-06-03 | 21 | 2026-07-01 | 50
A32850 | Purchase Order for Major Sub-ordered Materials | 2026-04-23 | 2026-05-14 | 2026-04-23 | 2026-05-14 | 2026-07-02 | 15 | 2026-07-22 | 50
A32860 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-05-14 | 2026-06-04 | 2026-05-14 | 2026-06-04 | 2026-07-23 | 15 | 2026-08-12 | 50
A32870 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-06-04 | 2026-06-11 | 2026-06-04 | 2026-06-11 | 2026-08-13 | 9 | 2026-08-20 | 87
A32880 | Manufacturing / Ex Works (India/UAE) | 2026-06-11 | 2026-07-21 | 2026-06-11 | 2026-07-21 | 2026-08-20 | 50 | 2026-09-29 | 87
A32890 | Complete Manufacturing & ready for Final Inspection | 2026-07-21 | 2026-07-30 | 2026-07-21 | 2026-07-30 | 2026-09-29 | 7 | 2026-10-07 | 50
A32900 | Materials Successfully Inspected, Tested / Ex Work | 2026-07-30 | 2026-08-10 | 2026-07-30 | 2026-08-10 | 2026-10-08 | 7 | 2026-10-16 | 50
A34350 | Delivery of Magnetic Level Gauges, PG, TG, PDG | 2026-08-10 | 2026-08-24 | 2026-08-10 | 2026-08-24 | 2026-10-17 | 18 | 2026-10-30 | 85
Analyzers |  | 2026-02-20 | 2026-02-20 | 24-May-25 A | 12-Jul-25 A | 2026-11-28 | 183 | 2026-11-28
A57650 | Start Production |  |  | 24-May-25 A |  |  | 0
A57660 | Key Vendor Drawings / Data Approved | 2026-02-20 | 2026-02-20 | 25-May-25 A | 31-May-25 A | 2026-11-28 | 30 | 2026-11-28
A57670 | Purchase Order for Major Sub-ordered Materials | 2026-02-20 | 2026-02-20 | 01-Jun-25 A | 07-Jun-25 A | 2026-11-28 | 15 | 2026-11-28
A57680 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-02-20 | 2026-02-20 | 07-Jun-25 A | 14-Jun-25 A | 2026-11-28 | 30 | 2026-11-28
A57690 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-02-20 | 2026-02-20 | 15-Jun-25 A | 21-Jun-25 A | 2026-11-28 | 1 | 2026-11-28
A57700 | Manufacturing / Ex Works (India/UAE) | 2026-02-20 | 2026-02-20 | 22-Jun-25 A | 28-Jun-25 A | 2026-11-28 | 138 | 2026-11-28
A57710 | Complete Manufacturing & ready for Final Inspection | 2026-02-20 | 2026-02-20 | 29-Jun-25 A | 05-Jul-25 A | 2026-11-28 | 7 | 2026-11-28
A57720 | Materials Successfully Inspected, Tested / Ex Work | 2026-02-20 | 2026-02-20 | 29-Jun-25 A | 05-Jul-25 A | 2026-11-28 | 7 | 2026-11-28
A57730 | Delivery of Material in Warehouse for Analyzer | 2026-02-20 | 2026-02-20 | 06-Jul-25 A | 12-Jul-25 A | 2026-11-28 | 26 | 2026-11-28
Flow Elements Venturi |  | 2026-02-20 | 2026-08-27 | 11-Dec-25 A | 2026-08-27 | 2026-04-30 | 145 | 2026-11-04 | 49
A57900 | Start Production | 2026-02-20 |  | 2026-02-20 |  | 2026-04-30 | 0 |  | 86
A57830 | Key Vendor Drawings / Data Approved | 2026-02-20 | 2026-03-20 | 2026-02-20 | 2026-03-20 | 2026-04-30 | 21 | 2026-05-28 | 49
A57850 | Purchase Order for Major Sub-ordered Materials | 2026-02-27 | 2026-03-20 | 11-Dec-25 A | 2026-03-20 | 2026-05-08 | 15 | 2026-05-28 | 49
A57860 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-03-20 | 2026-04-20 | 2026-03-20 | 2026-04-20 | 2026-05-29 | 21 | 2026-06-26 | 49
A57870 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-04-20 | 2026-04-27 | 2026-04-20 | 2026-04-27 | 2026-06-27 | 9 | 2026-07-04 | 84
A57840 | Manufacturing / Ex Works (India/UAE) | 2026-04-27 | 2026-07-26 | 2026-04-27 | 2026-07-26 | 2026-07-04 | 113 | 2026-10-02 | 84
A57880 | Complete Manufacturing & ready for Final Inspection | 2026-07-27 | 2026-08-04 | 2026-07-27 | 2026-08-04 | 2026-10-02 | 7 | 2026-10-12 | 49
A57890 | Materials Successfully Inspected, Tested / Ex Work | 2026-08-05 | 2026-08-13 | 2026-08-05 | 2026-08-13 | 2026-10-13 | 7 | 2026-10-21 | 49
A57910 | Delivery of Material in Warehouse for Flow Elements Venturi | 2026-08-14 | 2026-08-27 | 2026-08-14 | 2026-08-27 | 2026-10-22 | 18 | 2026-11-04 | 86
Flow Elements Orifice |  | 2026-02-20 | 2026-07-25 | 18-Dec-25 A | 2026-07-25 | 2026-07-03 | 111 | 2026-11-04 | 73
A57740 | Start Production |  |  | 18-Dec-25 A |  |  | 0
A57750 | Key Vendor Drawings / Data Approved | 2026-02-20 | 2026-02-20 | 18-Dec-25 A | 08-Jan-26 A | 2026-07-03 | 30 | 2026-07-03
A57760 | Purchase Order for Major Sub-ordered Materials | 2026-02-20 | 2026-02-20 | 09-Jan-26 A | 22-Jan-26 A | 2026-07-03 | 15 | 2026-07-03
A57770 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-02-20 | 2026-02-20 | 23-Jan-26 A | 31-Jan-26 A | 2026-07-03 | 50 | 2026-07-03
A57780 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-02-20 | 2026-02-24 | 01-Feb-26 A | 2026-02-24 | 2026-07-03 | 6 | 2026-07-08 | 166
A57790 | Manufacturing / Ex Works (India/UAE) | 2026-03-25 | 2026-06-23 | 2026-03-25 | 2026-06-23 | 2026-07-08 | 113 | 2026-10-06 | 131
A57800 | Complete Manufacturing & ready for Final Inspection | 2026-06-23 | 2026-07-02 | 2026-06-23 | 2026-07-02 | 2026-10-06 | 7 | 2026-10-14 | 75
A57810 | Materials Successfully Inspected, Tested / Ex Work | 2026-07-02 | 2026-07-13 | 2026-07-02 | 2026-07-13 | 2026-10-15 | 7 | 2026-10-23 | 75
A57820 | Delivery of Material in Warehouse for Flow Elements Orifice | 2026-07-13 | 2026-07-25 | 2026-07-13 | 2026-07-25 | 2026-10-24 | 15 | 2026-11-04 | 128
Cable Tray and Instrument Junction Box (Perforated Cable tray Heavy duty = 5982 Mtrs, JBs = 73 Nos) |  | 2026-02-26 | 2026-09-24 | 2026-02-26 | 2026-09-24 | 2026-03-12 | 150 | 2026-10-07 | 9
A33490 | Start Production | 2026-02-26 |  | 2026-02-26 |  | 2026-03-12 | 0 |  | 17
A29420 | Key Vendor Drawings / Data Approved | 2026-02-27 | 2026-04-23 | 2026-02-27 | 2026-04-23 | 2026-03-12 | 40 | 2026-05-06 | 9
A29430 | Purchase Order for Major Sub-ordered Materials | 2026-04-23 | 2026-05-04 | 2026-04-23 | 2026-05-04 | 2026-05-07 | 7 | 2026-05-15 | 9
A29440 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-05-04 | 2026-06-15 | 2026-05-04 | 2026-06-15 | 2026-05-18 | 30 | 2026-06-26 | 9
A29450 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-06-15 | 2026-06-16 | 2026-06-15 | 2026-06-16 | 2026-06-28 | 1 | 2026-06-29 | 15
A29460 | Manufacturing / Ex Works (India/UAE) | 2026-06-16 | 2026-08-15 | 2026-06-16 | 2026-08-15 | 2026-06-29 | 75 | 2026-08-28 | 15
A29470 | Complete Manufacturing & ready for Final Inspection | 2026-08-17 | 2026-08-25 | 2026-08-17 | 2026-08-25 | 2026-08-28 | 7 | 2026-09-07 | 9
A29480 | Materials Successfully Inspected, Tested / Ex Work | 2026-08-26 | 2026-09-03 | 2026-08-26 | 2026-09-03 | 2026-09-08 | 7 | 2026-09-16 | 9
A33500 | Delivery of Material in Warehouse for Cable Tray and Instrument Junction Box | 2026-09-04 | 2026-09-24 | 2026-09-04 | 2026-09-24 | 2026-09-17 | 26 | 2026-10-07 | 16
Fibre Optic Cable (Armoured, Telecom/IT/MAS) |  | 2026-02-20 | 2026-03-25 | 18-Aug-25 A | 2026-03-25 | 2026-03-19 | 142 | 2026-09-16 | 125
A34320 | Start Production |  |  | 18-Aug-25 A |  |  | 0
A32750 | Key Vendor Drawings / Data Approved | 2026-02-20 | 2026-02-20 | 21-Nov-25 A | 10-Dec-25 A | 2026-03-19 | 20 | 2026-03-19
A32760 | Purchase Order for Major Sub-ordered Materials | 2026-02-20 | 2026-02-20 | 11-Dec-25 A | 19-Dec-25 A | 2026-08-14 | 15 | 2026-08-14
A32770 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 26-Dec-25 A | 2026-08-14 | 30 | 2026-08-14
A32780 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-02-20 | 2026-02-20 | 25-Dec-25 A | 16-Jan-26 A | 2026-08-14 | 1 | 2026-08-14
A32790 | Manufacturing / Ex Works (India/UAE) | 2026-02-20 | 2026-02-20 | 25-Dec-25 A | 23-Jan-26 A | 2026-08-14 | 125 | 2026-08-14
A32800 | Complete Manufacturing & ready for Final Inspection | 2026-02-20 | 2026-03-02 | 2026-02-20 | 2026-03-02 | 2026-08-14 | 7 | 2026-08-24 | 125
A32810 | Materials Successfully Inspected, Tested / Ex Work | 2026-03-03 | 2026-03-11 | 2026-03-03 | 2026-03-11 | 2026-08-25 | 7 | 2026-09-02 | 125
A34330 | Delivery of Fibre Optic Cable | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-25 | 2026-09-03 | 18 | 2026-09-16 | 219
Magnetic Level Gauge ( 09 Nos) |  | 2026-02-26 | 2026-09-04 | 2026-02-26 | 2026-09-04 | 2026-04-01 | 136 | 2026-10-07 | 23
A33570 | Start Production | 2026-02-26 |  | 2026-02-26 |  | 2026-04-01 | 0 |  | 42
A29780 | Key Vendor Drawings / Data Approved | 2026-02-27 | 2026-03-27 | 2026-02-27 | 2026-03-27 | 2026-04-01 | 21 | 2026-04-29 | 23
A29790 | Purchase Order for Major Sub-ordered Materials | 2026-03-27 | 2026-04-10 | 2026-03-27 | 2026-04-10 | 2026-04-30 | 10 | 2026-05-13 | 23
A29800 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-04-10 | 2026-05-11 | 2026-04-10 | 2026-05-11 | 2026-05-14 | 21 | 2026-06-11 | 23
A29810 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-05-11 | 2026-05-18 | 2026-05-11 | 2026-05-18 | 2026-06-12 | 9 | 2026-06-19 | 39
A29820 | Manufacturing / Ex Works (India/UAE) | 2026-05-18 | 2026-07-27 | 2026-05-18 | 2026-07-27 | 2026-06-19 | 88 | 2026-08-28 | 39
A29830 | Complete Manufacturing & ready for Final Inspection | 2026-07-27 | 2026-08-05 | 2026-07-27 | 2026-08-05 | 2026-08-28 | 7 | 2026-09-07 | 23
A29840 | Materials Successfully Inspected, Tested / Ex Work | 2026-08-05 | 2026-08-14 | 2026-08-05 | 2026-08-14 | 2026-09-08 | 7 | 2026-09-16 | 23
A33580 | Delivery of Material in Warehouse for Magnetic Level Gauge | 2026-08-14 | 2026-09-04 | 2026-08-14 | 2026-09-04 | 2026-09-17 | 26 | 2026-10-07 | 41
Instrument Bulk Materia l(Single & Multicore = Approx. 78,130 Mtr, FO Cables JB & Cable Trays)) |  | 2026-02-20 | 2026-05-22 | 11-Dec-25 A | 2026-05-22 | 2026-07-13 | 111 | 2026-10-09 | 100
A34470 | Start Production | 2026-02-20 |  | 2026-02-20 |  | 2026-07-13 | 0 |  | 179
A27890 | Key Vendor Drawings / Data Approved | 2026-02-20 | 2026-03-19 | 2026-02-20 | 2026-03-19 | 2026-07-13 | 20 | 2026-08-07 | 101
A27900 | Purchase Order for Major Sub-ordered Materials | 2026-03-12 | 2026-03-19 | 11-Dec-25 A | 2026-03-19 | 2026-08-03 | 5 | 2026-08-07 | 101
A27910 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-03-19 | 2026-03-26 | 2026-03-19 | 2026-03-26 | 2026-08-10 | 5 | 2026-08-14 | 101
A27920 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-03-26 | 2026-03-27 | 2026-03-26 | 2026-03-27 | 2026-08-16 | 1 | 2026-08-17 | 178
A27930 | Manufacturing / Ex Works (India/UAE) | 2026-03-27 | 2026-04-17 | 2026-03-27 | 2026-04-17 | 2026-08-17 | 26 | 2026-09-07 | 178
A27940 | Complete Manufacturing & ready for Final Inspection | 2026-04-17 | 2026-04-24 | 2026-04-17 | 2026-04-24 | 2026-09-07 | 5 | 2026-09-11 | 100
A27950 | Materials Successfully Inspected, Tested / Ex Work | 2026-04-24 | 2026-05-01 | 2026-04-24 | 2026-05-01 | 2026-09-14 | 5 | 2026-09-18 | 100
A34460 | Delivery of Material in Warehouse Instrument Bulk (Post TA) | 2026-05-01 | 2026-05-22 | 2026-05-01 | 2026-05-22 | 2026-09-19 | 26 | 2026-10-09 | 175
Earthing & Power Cables |  | 2026-02-20 | 2026-07-17 | 05-Nov-25 A | 2026-07-17 | 2026-05-22 | 173 | 2026-10-18 | 65
Earthing and Power Cables |  | 2026-02-20 | 2026-07-17 | 05-Nov-25 A | 2026-07-17 | 2026-05-22 | 173 | 2026-10-18 | 65
A33310 | Start Production |  |  | 05-Nov-25 A |  |  | 0
A28340 | Key Vendor Drawings / Data Approved | 2026-02-20 | 2026-02-20 | 24-Jan-26 A | 30-Jan-26 A | 2026-05-22 | 20 | 2026-05-22
A28350 | Purchase Order for Major Sub-ordered Materials | 2026-02-20 | 2026-02-20 | 31-Jan-26 A | 12-Feb-26 A | 2026-05-22 | 30 | 2026-05-22
A28360 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-02-20 | 2026-03-10 | 13-Feb-26 A | 2026-03-10 | 2026-05-22 | 45 | 2026-06-09 | 65
A28370 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-03-11 | 2026-03-17 | 2026-03-11 | 2026-03-17 | 2026-06-10 | 9 | 2026-06-17 | 114
A28380 | Manufacturing / Ex Works (India/UAE) | 2026-03-18 | 2026-06-15 | 2026-03-18 | 2026-06-15 | 2026-06-17 | 113 | 2026-09-15 | 114
A28390 | Complete Manufacturing & ready for Final Inspection | 2026-06-16 | 2026-06-24 | 2026-06-16 | 2026-06-24 | 2026-09-15 | 7 | 2026-09-23 | 65
A28400 | Materials Successfully Inspected, Tested / Ex Work | 2026-06-25 | 2026-07-03 | 2026-06-25 | 2026-07-03 | 2026-09-24 | 7 | 2026-10-02 | 65
A33320 | Delivery of Earthing and Power Cables | 2026-07-04 | 2026-07-17 | 2026-07-04 | 2026-07-17 | 2026-10-05 | 18 | 2026-10-18 | 116
Electrical Bulk |  | 2026-02-20 | 2026-08-28 | 03-Oct-25 A | 2026-08-28 | 2026-04-30 | 220 | 2026-10-26 | 42
Cable Trays, JBs, Conduit Pipe, Cable Lugs, etc |  | 2026-05-13 | 2026-08-17 | 2026-05-13 | 2026-08-17 | 2026-07-06 | 68 | 2026-10-07 | 38
A33430 | Start Production | 2026-05-13 |  | 2026-05-13 |  | 2026-07-06 | 0 |  | 67
A29150 | Key Vendor Drawings / Data Approved | 2026-05-14 | 2026-06-10 | 2026-05-14 | 2026-06-10 | 2026-07-06 | 20 | 2026-07-31 | 37
A29160 | Purchase Order for Major Sub-ordered Materials | 2026-06-10 | 2026-06-17 | 2026-06-10 | 2026-06-17 | 2026-08-03 | 5 | 2026-08-07 | 37
A29170 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-06-17 | 2026-06-24 | 2026-06-17 | 2026-06-24 | 2026-08-10 | 5 | 2026-08-14 | 37
A29180 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-06-24 | 2026-06-25 | 2026-06-24 | 2026-06-25 | 2026-08-15 | 1 | 2026-08-16 | 65
A29190 | Manufacturing / Ex Works (India/UAE) | 2026-06-25 | 2026-07-20 | 2026-06-25 | 2026-07-20 | 2026-08-16 | 31 | 2026-09-10 | 65
A29200 | Complete Manufacturing & ready for Final Inspection | 2026-07-20 | 2026-07-27 | 2026-07-20 | 2026-07-27 | 2026-09-10 | 5 | 2026-09-16 | 38
A29210 | Materials Successfully Inspected, Tested / Ex Work | 2026-07-27 | 2026-08-03 | 2026-07-27 | 2026-08-03 | 2026-09-17 | 5 | 2026-09-23 | 38
A33440 | Delivery of Material in Warehouse for Cable Trays, JBs, Conduit Pipe, Cable Lugs, etc | 2026-08-03 | 2026-08-17 | 2026-08-03 | 2026-08-17 | 2026-09-24 | 18 | 2026-10-07 | 65
Power Cables ( 11kV & 33kV) |  | 2026-02-20 | 2026-05-05 | 03-Oct-25 A | 2026-05-05 | 2026-07-27 | 138 | 2026-10-07 | 112
A61450 | Power Cables | 2026-02-20 | 2026-02-20 | 10-Oct-25 A | 17-Oct-25 A | 2026-07-27 | 5 | 2026-07-27
A61460 | Key Vendor Drawings / Data Approved | 2026-02-20 | 2026-02-20 | 03-Oct-25 A | 23-Oct-25 A | 2026-07-27 | 20 | 2026-07-27
A61470 | Start Production |  |  | 24-Oct-25 A |  |  | 0
A61480 | Purchase Order for Major Sub-ordered Materials | 2026-02-20 | 2026-02-26 | 2026-02-20 | 2026-02-26 | 2026-07-27 | 5 | 2026-07-31 | 111
A61490 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-02-27 | 2026-03-05 | 2026-02-27 | 2026-03-05 | 2026-08-03 | 5 | 2026-08-07 | 111
A61500 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-08-08 | 1 | 2026-08-09 | 195
A61510 | Manufacturing / Ex Works (India/UAE) | 2026-03-07 | 2026-03-31 | 2026-03-07 | 2026-03-31 | 2026-08-09 | 31 | 2026-09-03 | 195
A61520 | Complete Manufacturing & ready for Final Inspection | 2026-03-31 | 2026-04-07 | 2026-03-31 | 2026-04-07 | 2026-09-03 | 5 | 2026-09-09 | 112
A61530 | Materials Successfully Inspected, Tested / Ex Work | 2026-04-07 | 2026-04-14 | 2026-04-07 | 2026-04-14 | 2026-09-10 | 5 | 2026-09-16 | 112
A61540 | Delivery of Material in Warehouse for Cable Trays, JBs, Conduit Pipe, Cable Lugs, etc | 2026-04-14 | 2026-05-05 | 2026-04-14 | 2026-05-05 | 2026-09-17 | 26 | 2026-10-07 | 194
LCS & Snap Switches |  | 2026-05-29 | 2026-08-28 | 2026-05-29 | 2026-08-28 | 2026-07-28 | 64 | 2026-10-26 | 42
A33470 | Start Production | 2026-05-29 |  | 2026-05-29 |  | 2026-07-28 | 0 |  | 74
A29330 | Key Vendor Drawings / Data Approved | 2026-06-01 | 2026-06-19 | 2026-06-01 | 2026-06-19 | 2026-07-28 | 15 | 2026-08-17 | 41
A29340 | Purchase Order for Major Sub-ordered Materials | 2026-06-19 | 2026-06-26 | 2026-06-19 | 2026-06-26 | 2026-08-17 | 5 | 2026-08-24 | 41
A29350 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-06-26 | 2026-07-10 | 2026-06-26 | 2026-07-10 | 2026-08-24 | 10 | 2026-09-07 | 41
A29360 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-07-10 | 2026-07-11 | 2026-07-10 | 2026-07-11 | 2026-09-07 | 1 | 2026-09-08 | 74
A29370 | Manufacturing / Ex Works (India/UAE) | 2026-07-11 | 2026-08-08 | 2026-07-11 | 2026-08-08 | 2026-09-08 | 35 | 2026-10-06 | 74
A29380 | Complete Manufacturing & ready for Final Inspection | 2026-08-10 | 2026-08-14 | 2026-08-10 | 2026-08-14 | 2026-10-06 | 4 | 2026-10-12 | 42
A29390 | Materials Successfully Inspected, Tested / Ex Work | 2026-08-14 | 2026-08-21 | 2026-08-14 | 2026-08-21 | 2026-10-13 | 5 | 2026-10-19 | 42
A33480 | Delivery of Material in Warehouse for LCS & snap Switches | 2026-08-21 | 2026-08-28 | 2026-08-21 | 2026-08-28 | 2026-10-20 | 9 | 2026-10-26 | 75
Electrical Bulk Material ( Earthing ,FO, Power Cables) |  | 2026-02-20 | 2026-07-28 | 21-Nov-25 A | 2026-07-28 | 2026-04-30 | 178 | 2026-10-05 | 49
A17930 | Start Production |  |  | 21-Nov-25 A |  |  | 0
A27440 | Key Vendor Drawings / Data Approved | 2026-02-20 | 2026-02-20 | 21-Nov-25 A | 28-Nov-25 A | 2026-04-30 | 75 | 2026-04-30
A27450 | Purchase Order for Major Sub-ordered Materials | 2026-02-20 | 2026-02-20 | 11-Dec-25 A | 19-Dec-25 A | 2026-04-30 | 10 | 2026-04-30
A27460 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-02-20 | 2026-04-02 | 2026-02-20 | 2026-04-02 | 2026-04-30 | 30 | 2026-06-10 | 49
A27470 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-04-03 | 2026-04-03 | 2026-04-03 | 2026-04-03 | 2026-06-11 | 1 | 2026-06-12 | 86
A27480 | Manufacturing / Ex Works (India/UAE) | 2026-04-04 | 2026-06-17 | 2026-04-04 | 2026-06-17 | 2026-06-12 | 94 | 2026-08-26 | 86
A27490 | Complete Manufacturing & ready for Final Inspection | 2026-06-18 | 2026-06-26 | 2026-06-18 | 2026-06-26 | 2026-08-26 | 7 | 2026-09-03 | 49
A27500 | Materials Successfully Inspected, Tested / Ex Work | 2026-06-29 | 2026-07-07 | 2026-06-29 | 2026-07-07 | 2026-09-04 | 7 | 2026-09-14 | 49
A33300 | Delivery of Electrical Bulk Material (Earthing, FO, 11 KVA Cable) (Post TA) | 2026-07-08 | 2026-07-28 | 2026-07-08 | 2026-07-28 | 2026-09-15 | 26 | 2026-10-05 | 86
Main Automation Equipment |  | 2026-02-20 | 2026-09-29 | 26-Feb-25 A | 2026-09-29 | 2026-03-18 | 414 | 2027-07-20 | 210
On Off Valve / Control Valves |  | 2026-02-20 | 2026-09-27 | 27-Oct-25 A | 2026-09-27 | 2026-03-25 | 199 | 2027-07-20 | 212
ESD Valves |  | 2026-02-20 | 2026-09-27 | 30-Oct-25 A | 2026-09-27 | 2026-03-25 | 198 | 2026-10-30 | 25
A59880 | Start Production |  |  | 30-Oct-25 A |  |  | 0
A59830 | Purchase Order for Major Sub-ordered Materials | 2026-02-20 | 2026-02-28 | 2026-02-20 | 2026-02-28 | 2026-03-25 | 10 | 2026-04-02 | 42
A59850 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-03-15 | 2026-03-16 | 2026-03-15 | 2026-03-16 | 2026-04-17 | 1 | 2026-04-18 | 42
A59840 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-02-28 | 2026-03-25 | 2026-02-28 | 2026-03-25 | 2026-04-02 | 31 | 2026-04-27 | 42
A59810 | Key Vendor Drawings / Data Approved | 2026-02-20 | 2026-04-23 | 2026-02-20 | 2026-04-23 | 2026-03-25 | 45 | 2026-05-27 | 24
A59820 | Manufacturing / Ex Works (India/UAE) | 2026-03-16 | 2026-09-02 | 2026-03-16 | 2026-09-02 | 2026-04-18 | 213 | 2026-10-05 | 42
A59860 | Complete Manufacturing & ready for Final Inspection | 2026-09-02 | 2026-09-07 | 2026-09-02 | 2026-09-07 | 2026-10-05 | 7 | 2026-10-11 | 42
A59870 | Materials Successfully Inspected, Tested / Ex Work | 2026-09-07 | 2026-09-13 | 2026-09-07 | 2026-09-13 | 2026-10-11 | 7 | 2026-10-16 | 42
A59890 | Delivery of Control Valves | 2026-09-13 | 2026-09-27 | 2026-09-13 | 2026-09-27 | 2026-10-17 | 18 | 2026-10-30 | 42
Control Valves (1" - 24" Rating 150, 300 & 2500 = 32 Nos) + SDV |  | 2026-02-20 | 2026-08-10 | 27-Oct-25 A | 2026-08-10 | 2026-05-12 | 164 | 2027-07-20 | 247
A33740 | Start Production |  |  | 27-Oct-25 A |  |  | 0
A30410 | Key Vendor Drawings / Data Approved | 2026-02-20 | 2026-02-20 | 18-Dec-25 A | 20-Feb-26 A | 2026-05-12 | 50 | 2026-05-12
A30440 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-02-20 | 2026-02-26 | 2026-02-20 | 2026-02-26 | 2026-05-12 | 9 | 2026-05-19 | 102
A30420 | Purchase Order for Major Sub-ordered Materials | 2026-02-20 | 2026-03-05 | 15-Feb-26 A | 2026-03-05 | 2027-05-26 | 10 | 2027-06-08 | 328
A30430 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-03-06 | 2026-04-16 | 2026-03-06 | 2026-04-16 | 2027-06-09 | 30 | 2027-07-20 | 328
A30450 | Manufacturing / Ex Works (India/UAE) | 2026-02-27 | 2026-07-08 | 2026-02-27 | 2026-07-08 | 2026-05-19 | 165 | 2026-09-28 | 102
A30460 | Complete Manufacturing & ready for Final Inspection | 2026-07-09 | 2026-07-14 | 2026-07-09 | 2026-07-14 | 2026-09-28 | 7 | 2026-10-04 | 102
A30470 | Materials Successfully Inspected, Tested / Ex Work | 2026-07-14 | 2026-07-20 | 2026-07-14 | 2026-07-20 | 2026-10-04 | 7 | 2026-10-09 | 102
A33750 | Delivery of Control Valves | 2026-07-20 | 2026-08-10 | 2026-07-20 | 2026-08-10 | 2026-10-10 | 26 | 2026-10-30 | 102
MOVs |  | 2026-02-20 | 2026-09-24 | 02-Sep-25 A | 2026-09-24 | 2026-05-11 | 240 | 2026-12-10 | 55
MOVs [Ball Type 24" 150# = 01 No] |  | 2026-02-20 | 2026-09-24 | 02-Sep-25 A | 2026-09-24 | 2026-05-11 | 240 | 2026-12-10 | 55
A34300 | Start Production |  |  | 02-Sep-25 A |  |  | 0
A32660 | Key Vendor Drawings / Data Approved | 2026-02-20 | 2026-02-20 | 21-Nov-25 A | 10-Dec-25 A | 2026-05-11 | 50 | 2026-05-11
A32670 | Purchase Order for Major Sub-ordered Materials | 2026-02-20 | 2026-02-20 | 10-Dec-25 A | 18-Dec-25 A | 2026-05-11 | 10 | 2026-05-11
A32680 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-02-20 | 2026-04-02 | 2026-02-20 | 2026-04-02 | 2026-05-11 | 30 | 2026-06-19 | 56
A32690 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-04-03 | 2026-04-03 | 2026-04-03 | 2026-04-03 | 2026-06-21 | 1 | 2026-06-22 | 99
A32700 | Manufacturing / Ex Works (India/UAE) | 2026-04-04 | 2026-08-21 | 2026-04-04 | 2026-08-21 | 2026-06-22 | 175 | 2026-11-09 | 99
A32710 | Complete Manufacturing & ready for Final Inspection | 2026-08-24 | 2026-09-01 | 2026-08-24 | 2026-09-01 | 2026-11-09 | 7 | 2026-11-17 | 55
A32720 | Materials Successfully Inspected, Tested / Ex Work | 2026-09-02 | 2026-09-10 | 2026-09-02 | 2026-09-10 | 2026-11-18 | 7 | 2026-11-26 | 55
A34310 | Delivery of MOVs | 2026-09-11 | 2026-09-24 | 2026-09-11 | 2026-09-24 | 2026-11-27 | 18 | 2026-12-10 | 96
Machine Condition Monitoring System (MCMS) |  | 2026-02-20 | 2026-06-05 | 25-May-25 A | 2026-06-05 | 2026-07-15 | 174 | 2026-10-26 | 101
Machine Condition Monitoring System |  | 2026-02-20 | 2026-06-05 | 25-May-25 A | 2026-06-05 | 2026-07-15 | 174 | 2026-10-26 | 101
A34130 | Start Production |  |  | 25-May-25 A |  |  | 0
A31940 | Key Vendor Drawings / Data Approved | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 19-Dec-25 A | 2026-07-15 | 50 | 2026-07-15
A31950 | Purchase Order for Major Sub-ordered Materials | 2026-02-20 | 2026-02-20 | 20-Dec-25 A | 26-Dec-25 A | 2026-07-15 | 10 | 2026-07-15
A31960 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-02-20 | 2026-02-20 | 27-Dec-25 A | 02-Jan-26 A | 2026-07-15 | 30 | 2026-07-15
A31970 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-02-20 | 2026-02-20 | 01-Jan-26 A | 09-Jan-26 A | 2026-07-15 | 4 | 2026-07-15
A31980 | Manufacturing / Ex Works (India/UAE) | 2026-02-20 | 2026-05-05 | 2026-02-20 | 2026-05-05 | 2026-07-15 | 94 | 2026-09-28 | 181
A31990 | Complete Manufacturing & ready for Final Inspection | 2026-05-06 | 2026-05-12 | 2026-05-06 | 2026-05-12 | 2026-09-28 | 5 | 2026-10-02 | 103
A32000 | Materials Successfully Inspected, Tested / Ex Work | 2026-05-13 | 2026-05-19 | 2026-05-13 | 2026-05-19 | 2026-10-05 | 5 | 2026-10-09 | 103
A34140 | Delivery of MCMS | 2026-05-20 | 2026-06-05 | 2026-05-20 | 2026-06-05 | 2026-10-10 | 21 | 2026-10-26 | 179
IPCS Modification (ABB) |  | 2026-02-20 | 2026-07-31 | 21-Mar-25 A | 2026-07-31 | 2026-03-27 | 294 | 2026-10-14 | 53
TA_Integrated Protection and Control System BF - ABB/Hitachi |  | 2026-02-20 | 2026-02-20 | 21-Mar-25 A | 16-May-25 A | 2026-03-27 | 41 | 2026-03-27
A34480 | Start Production |  |  | 21-Mar-25 A |  |  | 0
A27710 | Key Vendor Drawings / Data Approved | 2026-02-20 | 2026-02-20 | 21-Mar-25 A | 28-Mar-25 A | 2026-03-27 | 5 | 2026-03-27
A27720 | Purchase Order for Major Sub-ordered Materials | 2026-02-20 | 2026-02-20 | 01-Apr-25 A | 04-Apr-25 A | 2026-03-27 | 5 | 2026-03-27
A27730 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-02-20 | 2026-02-20 | 05-Apr-25 A | 11-Apr-25 A | 2026-03-27 | 5 | 2026-03-27
A27740 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-02-20 | 2026-02-20 | 12-Apr-25 A | 18-Apr-25 A | 2026-03-27 | 1 | 2026-03-27
A27750 | Manufacturing / Ex Works (India/UAE) | 2026-02-20 | 2026-02-20 | 19-Apr-25 A | 25-Apr-25 A | 2026-03-27 | 18 | 2026-03-27
A27760 | Complete Manufacturing & ready for Final Inspection | 2026-02-20 | 2026-02-20 | 26-Apr-25 A | 02-May-25 A | 2026-03-27 | 5 | 2026-03-27
A27770 | Materials Successfully Inspected, Tested / Ex Work | 2026-02-20 | 2026-02-20 | 03-May-25 A | 09-May-25 A | 2026-03-27 | 5 | 2026-03-27
A27780 | Delivery of FOPP (02 Nos) | 2026-02-20 | 2026-02-20 | 10-May-25 A | 16-May-25 A | 2026-03-27 | 9 | 2026-03-27
Integrated Protection Control System |  | 2026-02-20 | 2026-07-31 | 25-Jul-25 A | 2026-07-31 | 2026-05-04 | 226 | 2026-10-14 | 53
A24030 | Start Production |  |  | 25-Jul-25 A |  |  | 0
A31220 | Key Vendor Drawings / Data Approved | 2026-02-20 | 2026-02-20 | 10-Sep-25 A | 20-Dec-25 A | 2026-05-04 | 50 | 2026-05-04
A31230 | Purchase Order for Major Sub-ordered Materials | 2026-02-20 | 2026-02-20 | 21-Dec-25 A | 27-Dec-25 A | 2026-05-04 | 10 | 2026-05-04
A31240 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-02-20 | 2026-02-20 | 28-Dec-25 A | 03-Jan-26 A | 2026-05-04 | 30 | 2026-05-04
A31250 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-02-20 | 2026-02-22 | 10-Jan-26 A | 2026-02-22 | 2026-05-04 | 4 | 2026-05-07 | 92
A31260 | Manufacturing / Ex Works (India/UAE) | 2026-02-22 | 2026-06-22 | 2026-02-22 | 2026-06-22 | 2026-05-07 | 150 | 2026-09-04 | 92
A31270 | Complete Manufacturing & ready for Final Inspection | 2026-06-22 | 2026-07-01 | 2026-06-22 | 2026-07-01 | 2026-09-04 | 7 | 2026-09-14 | 53
A31280 | Materials Successfully Inspected, Tested / Ex Work | 2026-07-01 | 2026-07-10 | 2026-07-01 | 2026-07-10 | 2026-09-15 | 7 | 2026-09-23 | 53
A33970 | Delivery of IPCS | 2026-07-10 | 2026-07-31 | 2026-07-10 | 2026-07-31 | 2026-09-24 | 26 | 2026-10-14 | 94
OTS |  | 2026-02-20 | 2026-09-16 | 13-Mar-25 A | 2026-09-16 | 2026-03-20 | 322 | 2026-10-14 | 20
TA_SCMS System - Siemens |  | 2026-02-20 | 2026-02-20 | 13-Mar-25 A | 11-May-25 A | 2026-03-27 | 19 | 2026-03-27
A27620 | Key Vendor Drawings / Data Approved | 2026-02-20 | 2026-02-20 | 13-Mar-25 A | 16-Mar-25 A | 2026-03-27 | 3 | 2026-03-27
A33290 | Start Production |  |  | 23-Mar-25 A |  |  | 0
A27630 | Purchase Order for Major Sub-ordered Materials | 2026-02-20 | 2026-02-20 | 24-Mar-25 A | 30-Mar-25 A | 2026-03-27 | 3 | 2026-03-27
A27640 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-02-20 | 2026-02-20 | 31-Mar-25 A | 06-Apr-25 A | 2026-03-27 | 3 | 2026-03-27
A27650 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-02-20 | 2026-02-20 | 07-Apr-25 A | 13-Apr-25 A | 2026-03-27 | 1 | 2026-03-27
A27660 | Manufacturing / Ex Works (India/UAE) | 2026-02-20 | 2026-02-20 | 14-Apr-25 A | 20-Apr-25 A | 2026-03-27 | 4 | 2026-03-27
A27670 | Complete Manufacturing & ready for Final Inspection | 2026-02-20 | 2026-02-20 | 21-Apr-25 A | 27-Apr-25 A | 2026-03-27 | 3 | 2026-03-27
A27680 | Materials Successfully Inspected, Tested / Ex Work | 2026-02-20 | 2026-02-20 | 28-Apr-25 A | 04-May-25 A | 2026-03-27 | 2 | 2026-03-27
A27690 | Delivery of SCMS | 2026-02-20 | 2026-02-20 | 05-May-25 A | 11-May-25 A | 2026-03-27 | 4 | 2026-03-27
SCMS System |  | 2026-02-20 | 2026-09-16 | 23-May-25 A | 2026-09-16 | 2026-03-20 | 322 | 2026-10-14 | 20
A60100 | Start Production |  |  | 23-May-25 A |  |  | 0
A60110 | Key Vendor Drawings / Data Approved | 2026-02-20 | 2026-03-20 | 06-Jan-26 A | 2026-03-20 | 2026-03-20 | 50 | 2026-04-17 | 20
A60130 | Purchase Order for Major Sub-ordered Materials | 2026-03-20 | 2026-04-03 | 2026-03-20 | 2026-04-03 | 2026-04-20 | 10 | 2026-05-01 | 20
A60140 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-04-03 | 2026-05-04 | 2026-04-03 | 2026-05-04 | 2026-05-04 | 21 | 2026-06-01 | 20
A60150 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-05-04 | 2026-05-05 | 2026-05-04 | 2026-05-05 | 2026-06-02 | 1 | 2026-06-03 | 35
A60120 | Manufacturing / Ex Works (India/UAE) | 2026-05-05 | 2026-08-13 | 2026-05-05 | 2026-08-13 | 2026-06-03 | 125 | 2026-09-11 | 35
A60160 | Complete Manufacturing & ready for Final Inspection | 2026-08-13 | 2026-08-24 | 2026-08-13 | 2026-08-24 | 2026-09-11 | 7 | 2026-09-21 | 20
A60170 | Materials Successfully Inspected, Tested / Ex Work | 2026-08-24 | 2026-09-02 | 2026-08-24 | 2026-09-02 | 2026-09-22 | 7 | 2026-09-30 | 20
A60180 | Delivery of SCMS | 2026-09-02 | 2026-09-16 | 2026-09-02 | 2026-09-16 | 2026-10-01 | 18 | 2026-10-14 | 35
ICSS (Integrated Control and Safety System) including sys. Modifications |  | 2026-02-20 | 2026-09-29 | 20-Mar-25 A | 2026-09-29 | 2026-03-18 | 412 | 2026-10-23 | 18
TA_Integrated Control and Safety System BF - Honeywell |  | 2026-02-20 | 2026-02-20 | 20-Mar-25 A | 17-May-25 A | 2026-03-27 | 103 | 2026-03-27
A33280 | Start Production |  |  | 22-Mar-25 A |  |  | 0
A27530 | Key Vendor Drawings / Data Approved | 2026-02-20 | 2026-02-20 | 20-Mar-25 A | 29-Mar-25 A | 2026-03-27 | 5 | 2026-03-27
A27540 | Purchase Order for Major Sub-ordered Materials | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 05-Apr-25 A | 2026-03-27 | 5 | 2026-03-27
A27550 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-02-20 | 2026-02-20 | 06-Apr-25 A | 12-Apr-25 A | 2026-03-27 | 5 | 2026-03-27
A27560 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-02-20 | 2026-02-20 | 13-Apr-25 A | 19-Apr-25 A | 2026-03-27 | 1 | 2026-03-27
A27570 | Manufacturing / Ex Works (India/UAE) | 2026-02-20 | 2026-02-20 | 20-Apr-25 A | 26-Apr-25 A | 2026-03-27 | 9 | 2026-03-27
A27580 | Complete Manufacturing & ready for Final Inspection | 2026-02-20 | 2026-02-20 | 27-Apr-25 A | 03-May-25 A | 2026-03-27 | 5 | 2026-03-27
A27590 | Materials Successfully Inspected, Tested / Ex Work | 2026-02-20 | 2026-02-20 | 04-May-25 A | 10-May-25 A | 2026-03-27 | 5 | 2026-03-27
A27600 | Delivery of loose Material for ICSS Modification | 2026-02-20 | 2026-02-20 | 11-May-25 A | 17-May-25 A | 2026-03-27 | 6 | 2026-03-27
Integrated Control and Safety System GF |  | 2026-02-20 | 2026-09-29 | 20-Jun-25 A | 2026-09-29 | 2026-03-18 | 294 | 2026-10-23 | 18
A33950 | Start Production |  |  | 20-Jun-25 A |  |  | 0
A31130 | Key Vendor Drawings / Data Approved | 2026-02-20 | 2026-02-20 | 05-Aug-25 A | 20-Dec-25 A | 2026-03-18 | 50 | 2026-03-18
A31140 | Purchase Order for Major Sub-ordered Materials | 2026-02-20 | 2026-02-20 | 21-Dec-25 A | 27-Dec-25 A | 2026-03-18 | 10 | 2026-03-18
A31150 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-02-20 | 2026-02-20 | 27-Dec-25 A | 03-Jan-26 A | 2026-03-18 | 30 | 2026-03-18
A31160 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-02-20 | 2026-02-20 | 10-Jan-26 A | 2026-02-20 | 2026-03-18 | 1 | 2026-03-19 | 33
A31170 | Manufacturing / Ex Works (India/UAE) | 2026-02-20 | 2026-08-19 | 2026-02-20 | 2026-08-19 | 2026-03-19 | 225 | 2026-09-15 | 33
A31180 | Complete Manufacturing & ready for Final Inspection | 2026-08-19 | 2026-08-28 | 2026-08-19 | 2026-08-28 | 2026-09-15 | 7 | 2026-09-23 | 18
A31190 | Materials Successfully Inspected, Tested / Ex Work | 2026-08-28 | 2026-09-08 | 2026-08-28 | 2026-09-08 | 2026-09-24 | 7 | 2026-10-02 | 18
A33960 | Delivery of Material in Warehouse ICSS | 2026-09-08 | 2026-09-29 | 2026-09-08 | 2026-09-29 | 2026-10-03 | 26 | 2026-10-23 | 30
Instrument Cables |  | 2026-03-12 | 2026-09-08 | 2026-03-12 | 2026-09-08 | 2026-04-13 | 128 | 2026-10-07 | 21
Instrument Cable (Single & Multicore = Approx. 78,130 Mtr) |  | 2026-03-12 | 2026-09-08 | 2026-03-12 | 2026-09-08 | 2026-04-13 | 128 | 2026-10-07 | 21
A33550 | Start Production | 2026-03-12 |  | 2026-03-12 |  | 2026-04-13 | 0 |  | 39
A29690 | Key Vendor Drawings / Data Approved | 2026-03-13 | 2026-04-23 | 2026-03-13 | 2026-04-23 | 2026-04-13 | 30 | 2026-05-22 | 21
A29700 | Purchase Order for Major Sub-ordered Materials | 2026-04-23 | 2026-05-07 | 2026-04-23 | 2026-05-07 | 2026-05-25 | 10 | 2026-06-05 | 21
A29710 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-05-07 | 2026-05-28 | 2026-05-07 | 2026-05-28 | 2026-06-08 | 15 | 2026-06-26 | 21
A29720 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-05-28 | 2026-05-29 | 2026-05-28 | 2026-05-29 | 2026-06-27 | 1 | 2026-06-28 | 37
A29730 | Manufacturing / Ex Works (India/UAE) | 2026-05-29 | 2026-08-12 | 2026-05-29 | 2026-08-12 | 2026-06-28 | 94 | 2026-09-11 | 37
A29740 | Complete Manufacturing & ready for Final Inspection | 2026-08-12 | 2026-08-21 | 2026-08-12 | 2026-08-21 | 2026-09-11 | 7 | 2026-09-21 | 21
A29750 | Materials Successfully Inspected, Tested / Ex Work | 2026-08-21 | 2026-09-01 | 2026-08-21 | 2026-09-01 | 2026-09-22 | 7 | 2026-09-30 | 21
A33560 | Delivery of Material in Warehouse for Instrument Cable | 2026-09-01 | 2026-09-08 | 2026-09-01 | 2026-09-08 | 2026-10-01 | 9 | 2026-10-07 | 36
Local Fire Control Panel including F&G Detectors |  | 2026-02-20 | 2026-07-27 | 12-Dec-25 A | 2026-07-27 | 2026-05-05 | 112 | 2026-10-07 | 52
Fire Detection Alarm System and Local Fire Control Panel (Clean Agent Unit) |  | 2026-02-20 | 2026-07-27 | 12-Dec-25 A | 2026-07-27 | 2026-05-05 | 112 | 2026-10-07 | 52
A34090 | Start Production |  |  | 12-Dec-25 A |  |  | 0
A31760 | Key Vendor Drawings / Data Approved | 2026-02-20 | 2026-03-19 | 24-Jan-26 A | 2026-03-19 | 2026-05-05 | 30 | 2026-06-01 | 52
A31770 | Purchase Order for Major Sub-ordered Materials | 2026-03-19 | 2026-03-30 | 2026-03-19 | 2026-03-30 | 2026-06-02 | 7 | 2026-06-10 | 52
A31780 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-03-30 | 2026-04-08 | 2026-03-30 | 2026-04-08 | 2026-06-11 | 7 | 2026-06-19 | 52
A31790 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-04-08 | 2026-04-09 | 2026-04-08 | 2026-04-09 | 2026-06-20 | 1 | 2026-06-21 | 90
A31800 | Manufacturing / Ex Works | 2026-04-09 | 2026-06-23 | 2026-04-09 | 2026-06-23 | 2026-06-21 | 94 | 2026-09-04 | 90
A31810 | Complete Manufacturing & ready for Final Inspection | 2026-06-23 | 2026-07-02 | 2026-06-23 | 2026-07-02 | 2026-09-04 | 7 | 2026-09-14 | 52
A31820 | Materials Successfully Inspected, Tested / Ex Work | 2026-07-02 | 2026-07-13 | 2026-07-02 | 2026-07-13 | 2026-09-15 | 7 | 2026-09-23 | 52
A34100 | Delivery of FDAS, LFCP, Clean Agent Unit | 2026-07-13 | 2026-07-27 | 2026-07-13 | 2026-07-27 | 2026-09-24 | 18 | 2026-10-07 | 90
PSVs |  | 2026-03-25 | 2026-09-22 | 2026-03-25 | 2026-09-22 | 2026-04-23 | 129 | 2026-10-21 | 21
PSVs (1"x2" upto 8"x10" - CS Rating 150/150, 300/150 = 22 Nos) |  | 2026-03-25 | 2026-09-22 | 2026-03-25 | 2026-09-22 | 2026-04-23 | 129 | 2026-10-21 | 21
A33530 | Start Production | 2026-03-25 |  | 2026-03-25 |  | 2026-04-23 | 0 |  | 35
A29600 | Key Vendor Drawings / Data Approved | 2026-03-26 | 2026-05-06 | 2026-03-26 | 2026-05-06 | 2026-04-23 | 30 | 2026-06-03 | 20
A29610 | Purchase Order for Major Sub-ordered Materials | 2026-05-06 | 2026-05-15 | 2026-05-06 | 2026-05-15 | 2026-06-04 | 7 | 2026-06-12 | 20
A29620 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-05-15 | 2026-06-05 | 2026-05-15 | 2026-06-05 | 2026-06-15 | 15 | 2026-07-03 | 20
A29630 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-07-05 | 0 | 2026-07-05 | 37
A29640 | Manufacturing / Ex Works (India/UAE) | 2026-06-05 | 2026-08-19 | 2026-06-05 | 2026-08-19 | 2026-07-05 | 94 | 2026-09-18 | 37
A29650 | Complete Manufacturing & ready for Final Inspection | 2026-08-19 | 2026-08-28 | 2026-08-19 | 2026-08-28 | 2026-09-18 | 7 | 2026-09-28 | 21
A29660 | Materials Successfully Inspected, Tested / Ex Work | 2026-08-28 | 2026-09-08 | 2026-08-28 | 2026-09-08 | 2026-09-29 | 7 | 2026-10-07 | 21
A33540 | Delivery of Material in Warehouse for PSVs | 2026-09-08 | 2026-09-22 | 2026-09-08 | 2026-09-22 | 2026-10-07 | 18 | 2026-10-21 | 36
Sampling System |  | 2026-02-20 | 2026-02-20 | 26-Feb-25 A | 12-May-25 A | 2026-12-01 | 134 | 2026-12-01
TA_SGM Replacement (Additional Item) |  | 2026-02-20 | 2026-02-20 | 26-Feb-25 A | 12-May-25 A | 2026-12-01 | 134 | 2026-12-01
A37420 | Start Production |  |  | 17-Mar-25 A |  |  | 0
A37430 | Key Vendor Drawings / Data Approved | 2026-02-20 | 2026-02-20 | 26-Feb-25 A | 24-Mar-25 A | 2026-12-01 | 10 | 2026-12-01
A37440 | Purchase Order for Major Sub-ordered Materials | 2026-02-20 | 2026-02-20 | 25-Mar-25 A | 31-Mar-25 A | 2026-12-01 | 5 | 2026-12-01
A37450 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-02-20 | 2026-02-20 | 01-Apr-25 A | 07-Apr-25 A | 2026-12-01 | 5 | 2026-12-01
A37460 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 14-Apr-25 A | 2026-12-01 | 1 | 2026-12-01
A37470 | Manufacturing / Ex Works (India/UAE) | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 21-Apr-25 A | 2026-12-01 | 35 | 2026-12-01
A37480 | Complete Manufacturing & ready for Final Inspection | 2026-02-20 | 2026-02-20 | 22-Apr-25 A | 28-Apr-25 A | 2026-12-01 | 5 | 2026-12-01
A37490 | Materials Successfully Inspected, Tested / Ex Work | 2026-02-20 | 2026-02-20 | 29-Apr-25 A | 05-May-25 A | 2026-12-01 | 5 | 2026-12-01
A37500 | Delivery of Additional Material to be Procured | 2026-02-20 | 2026-02-20 | 06-May-25 A | 12-May-25 A | 2026-12-01 | 18 | 2026-12-01
F&G Flame Detectors, MCP, Beacon, etc. |  | 2026-04-02 | 2026-09-02 | 2026-04-02 | 2026-09-02 | 2026-06-01 | 109 | 2026-10-31 | 42
F&G Flame Detectors, MCP, Beacon (Nos 324) |  | 2026-04-02 | 2026-09-02 | 2026-04-02 | 2026-09-02 | 2026-06-01 | 109 | 2026-10-31 | 42
A34170 | Start Production | 2026-04-02 |  | 2026-04-02 |  | 2026-06-01 | 0 |  | 74
A32120 | Key Vendor Drawings / Data Approved | 2026-04-02 | 2026-04-23 | 2026-04-02 | 2026-04-23 | 2026-06-01 | 15 | 2026-06-19 | 41
A32130 | Purchase Order for Major Sub-ordered Materials | 2026-04-23 | 2026-05-07 | 2026-04-23 | 2026-05-07 | 2026-06-22 | 10 | 2026-07-03 | 41
A32140 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-05-07 | 2026-05-28 | 2026-05-07 | 2026-05-28 | 2026-07-06 | 15 | 2026-07-24 | 41
A32150 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-05-28 | 2026-05-29 | 2026-05-28 | 2026-05-29 | 2026-07-25 | 1 | 2026-07-26 | 72
A32160 | Manufacturing / Ex Works (India/UAE) | 2026-05-29 | 2026-07-28 | 2026-05-29 | 2026-07-28 | 2026-07-26 | 75 | 2026-09-24 | 72
A32170 | Complete Manufacturing & ready for Final Inspection | 2026-07-28 | 2026-08-06 | 2026-07-28 | 2026-08-06 | 2026-09-24 | 7 | 2026-10-02 | 41
A32180 | Materials Successfully Inspected, Tested / Ex Work | 2026-08-06 | 2026-08-13 | 2026-08-06 | 2026-08-13 | 2026-10-05 | 5 | 2026-10-09 | 41
A34180 | Delivery of F&G Detectors | 2026-08-13 | 2026-09-02 | 2026-08-13 | 2026-09-02 | 2026-10-12 | 25 | 2026-10-31 | 74
Main Electrical Equipment |  | 2026-02-20 | 2026-09-28 | 25-Feb-25 A | 2026-09-28 | 2026-03-27 | 414 | 2027-01-03 | 69
DG Set (750 KVA) 01 Nos |  | 2026-02-20 | 2026-08-06 | 22-Aug-25 A | 2026-08-06 | 2026-05-18 | 270 | 2026-11-03 | 63
DG Set |  | 2026-02-20 | 2026-08-06 | 22-Aug-25 A | 2026-08-06 | 2026-05-18 | 270 | 2026-11-03 | 63
A34420 | Start Production |  |  | 22-Aug-25 A |  |  | 0
A33200 | Key Vendor Drawings / Data Approved | 2026-02-20 | 2026-02-20 | 01-Sep-25 A | 27-Nov-25 A | 2026-05-18 | 90 | 2026-05-18
A33220 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-02-20 | 2026-02-20 | 26-Nov-25 A | 01-Dec-25 A | 2026-05-18 | 30 | 2026-05-18
A33230 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-02-20 | 2026-02-20 | 02-Dec-25 A | 09-Dec-25 A | 2026-05-18 | 3 | 2026-05-18
A33210 | Purchase Order for Major Sub-ordered Materials | 2026-02-20 | 2026-02-20 | 30-Nov-25 A | 19-Dec-25 A | 2026-05-18 | 10 | 2026-05-18
A33240 | Manufacturing / Ex Works (India/UAE) | 2026-02-20 | 2026-06-29 | 10-Dec-25 A | 2026-06-29 | 2026-05-18 | 194 | 2026-09-25 | 109
A33250 | Complete Manufacturing & ready for Final Inspection | 2026-06-30 | 2026-07-08 | 2026-06-30 | 2026-07-08 | 2026-09-25 | 7 | 2026-10-05 | 63
A33260 | Materials Successfully Inspected, Tested / Ex Work | 2026-07-09 | 2026-07-17 | 2026-07-09 | 2026-07-17 | 2026-10-06 | 7 | 2026-10-14 | 63
A34430 | Delivery of Material in Warehouse DG Set | 2026-07-18 | 2026-08-06 | 2026-07-18 | 2026-08-06 | 2026-10-15 | 25 | 2026-11-03 | 111
UPS (AC - 60 KVA, 20 KVA, DC-UPS 6.5 KVA) 03 Nos. |  | 2026-02-20 | 2026-09-28 | 25-Feb-25 A | 2026-09-28 | 2026-03-27 | 412 | 2027-01-03 | 69
TA_UPS Modification - Chloride Technology |  | 2026-02-20 | 2026-02-20 | 25-Feb-25 A | 03-May-25 A | 2026-03-27 | 99 | 2026-03-27
A37280 | Start Production |  |  | 25-Feb-25 A |  |  | 0
A37290 | Key Vendor Drawings / Data Approved | 2026-02-20 | 2026-02-20 | 27-Feb-25 A | 04-Mar-25 A | 2026-03-27 | 5 | 2026-03-27
A37300 | Purchase Order for Major Sub-ordered Materials | 2026-02-20 | 2026-02-20 | 06-Mar-25 A | 22-Mar-25 A | 2026-03-27 | 5 | 2026-03-27
A37310 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-02-20 | 2026-02-20 | 23-Mar-25 A | 29-Mar-25 A | 2026-03-27 | 5 | 2026-03-27
A37320 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-02-20 | 2026-02-20 | 30-Mar-25 A | 05-Apr-25 A | 2026-03-27 | 1 | 2026-03-27
A37330 | Manufacturing / Ex Works (India/UAE) | 2026-02-20 | 2026-02-20 | 06-Apr-25 A | 12-Apr-25 A | 2026-03-27 | 26 | 2026-03-27
A37340 | Complete Manufacturing & ready for Final Inspection | 2026-02-20 | 2026-02-20 | 13-Apr-25 A | 19-Apr-25 A | 2026-03-27 | 1 | 2026-03-27
A37350 | Materials Successfully Inspected, Tested / Ex Work | 2026-02-20 | 2026-02-20 | 20-Apr-25 A | 26-Apr-25 A | 2026-03-27 | 5 | 2026-03-27
A37360 | Delivery of Material for UPS Modification | 2026-02-20 | 2026-02-20 | 27-Apr-25 A | 03-May-25 A | 2026-03-27 | 6 | 2026-03-27
UPS (AC - 60 KVA, 20 KVA, DC-UPS 6.5 KVA) Qty 1+1+1 = 03 Nos |  | 2026-02-20 | 2026-09-28 | 16-Oct-25 A | 2026-09-28 | 2026-05-28 | 208 | 2027-01-03 | 69
A34070 | Start Production |  |  | 16-Oct-25 A |  |  | 0
A31670 | Key Vendor Drawings / Data Approved | 2026-02-20 | 2026-03-13 | 2026-02-20 | 2026-03-13 | 2026-05-28 | 16 | 2026-06-18 | 69
A31680 | Purchase Order for Major Sub-ordered Materials | 2026-03-13 | 2026-03-27 | 2026-03-13 | 2026-03-27 | 2026-06-19 | 10 | 2026-07-02 | 69
A31690 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-03-27 | 2026-05-08 | 2026-03-27 | 2026-05-08 | 2026-07-03 | 30 | 2026-08-13 | 69
A31700 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-05-08 | 2026-05-10 | 2026-05-08 | 2026-05-10 | 2026-08-14 | 3 | 2026-08-16 | 122
A31710 | Manufacturing / Ex Works (India/UAE) | 2026-05-10 | 2026-08-18 | 2026-05-10 | 2026-08-18 | 2026-08-16 | 125 | 2026-11-24 | 122
A31720 | Complete Manufacturing & ready for Final Inspection | 2026-08-18 | 2026-08-27 | 2026-08-18 | 2026-08-27 | 2026-11-24 | 7 | 2026-12-02 | 69
A31730 | Materials Successfully Inspected, Tested / Ex Work | 2026-08-27 | 2026-09-07 | 2026-08-27 | 2026-09-07 | 2026-12-03 | 7 | 2026-12-11 | 69
A34080 | Delivery of Material in Warehouse UPS | 2026-09-07 | 2026-09-28 | 2026-09-07 | 2026-09-28 | 2026-12-14 | 26 | 2027-01-03 | 121
Power Transformer (05 Nos) |  | 2026-02-20 | 2026-08-14 | 10-Sep-25 A | 2026-08-14 | 2026-05-01 | 256 | 2026-10-23 | 50
Power Transformers (Qty 05) |  | 2026-02-20 | 2026-08-14 | 10-Sep-25 A | 2026-08-14 | 2026-05-01 | 256 | 2026-10-23 | 50
A34110 | Start Production |  |  | 10-Sep-25 A |  |  | 0
A31850 | Key Vendor Drawings / Data Approved | 2026-02-20 | 2026-02-20 | 21-Nov-25 A | 02-Dec-25 A | 2026-05-01 | 60 | 2026-05-01
A31860 | Purchase Order for Major Sub-ordered Materials | 2026-02-20 | 2026-02-20 | 02-Dec-25 A | 19-Dec-25 A | 2026-05-01 | 10 | 2026-05-01
A31870 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 03-Jan-26 A | 2026-05-01 | 30 | 2026-05-01
A31880 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-02-20 | 2026-02-20 | 01-Jan-26 A | 11-Jan-26 A | 2026-05-01 | 1 | 2026-05-01
A31890 | Manufacturing / Ex Works (India/UAE) | 2026-02-20 | 2026-06-29 | 2026-02-20 | 2026-06-29 | 2026-05-01 | 163 | 2026-09-08 | 88
A31900 | Complete Manufacturing & ready for Final Inspection | 2026-06-30 | 2026-07-08 | 2026-06-30 | 2026-07-08 | 2026-09-08 | 7 | 2026-09-16 | 50
A31910 | Materials Successfully Inspected, Tested / Ex Work | 2026-07-09 | 2026-07-17 | 2026-07-09 | 2026-07-17 | 2026-09-17 | 7 | 2026-09-25 | 50
A34120 | Delivery of Material in Warehouse Power Transformers | 2026-07-18 | 2026-08-14 | 2026-07-18 | 2026-08-14 | 2026-09-26 | 35 | 2026-10-23 | 88
Electrical Heat Tracing |  | 2026-05-13 | 2026-08-31 | 2026-05-13 | 2026-08-31 | 2026-07-13 | 77 | 2026-10-26 | 41
Electrical Heat Tracing (53 Meter for piping + 340 Meter for instrumentation) |  | 2026-05-13 | 2026-08-31 | 2026-05-13 | 2026-08-31 | 2026-07-13 | 77 | 2026-10-26 | 41
A33410 | Start Production | 2026-05-13 |  | 2026-05-13 |  | 2026-07-13 | 0 |  | 76
A29060 | Key Vendor Drawings / Data Approved | 2026-05-14 | 2026-06-24 | 2026-05-14 | 2026-06-24 | 2026-07-13 | 30 | 2026-08-24 | 42
A29070 | Purchase Order for Major Sub-ordered Materials | 2026-06-24 | 2026-06-29 | 2026-06-24 | 2026-06-29 | 2026-08-24 | 3 | 2026-08-27 | 43
A29080 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-06-29 | 2026-07-06 | 2026-06-29 | 2026-07-06 | 2026-08-27 | 5 | 2026-09-03 | 43
A29090 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-07-06 | 2026-07-07 | 2026-07-06 | 2026-07-07 | 2026-09-03 | 1 | 2026-09-04 | 73
A29100 | Manufacturing / Ex Works (India/UAE) | 2026-07-07 | 2026-08-01 | 2026-07-07 | 2026-08-01 | 2026-09-04 | 31 | 2026-09-28 | 73
A29110 | Complete Manufacturing & ready for Final Inspection | 2026-08-03 | 2026-08-06 | 2026-08-03 | 2026-08-06 | 2026-09-28 | 3 | 2026-10-01 | 41
A29120 | Materials Successfully Inspected, Tested / Ex Work | 2026-08-06 | 2026-08-17 | 2026-08-06 | 2026-08-17 | 2026-10-02 | 7 | 2026-10-12 | 41
A33420 | Delivery of Material in Warehouse for Electrical Heat Tracing | 2026-08-17 | 2026-08-31 | 2026-08-17 | 2026-08-31 | 2026-10-13 | 18 | 2026-10-26 | 71
CP |  | 2026-02-27 | 2026-08-03 | 2026-02-27 | 2026-08-03 | 2026-05-25 | 111 | 2026-10-26 | 60
Cathodic Protection (CP) Total CS Piping Length - 499 Meters |  | 2026-02-27 | 2026-08-03 | 2026-02-27 | 2026-08-03 | 2026-05-25 | 111 | 2026-10-26 | 60
A33450 | Start Production | 2026-02-27 |  | 2026-02-27 |  | 2026-05-25 | 0 |  | 108
A29240 | Key Vendor Drawings / Data Approved | 2026-03-02 | 2026-04-10 | 2026-03-02 | 2026-04-10 | 2026-05-25 | 30 | 2026-07-03 | 60
A29250 | Purchase Order for Major Sub-ordered Materials | 2026-04-10 | 2026-04-17 | 2026-04-10 | 2026-04-17 | 2026-07-06 | 5 | 2026-07-10 | 60
A29260 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-04-17 | 2026-05-15 | 2026-04-17 | 2026-05-15 | 2026-07-13 | 20 | 2026-08-07 | 60
A29270 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-05-15 | 2026-05-16 | 2026-05-15 | 2026-05-16 | 2026-08-08 | 1 | 2026-08-09 | 105
A29280 | Manufacturing / Ex Works | 2026-05-16 | 2026-06-30 | 2026-05-16 | 2026-06-30 | 2026-08-09 | 56 | 2026-09-23 | 105
A29290 | Complete Manufacturing & ready for Final Inspection | 2026-06-30 | 2026-07-09 | 2026-06-30 | 2026-07-09 | 2026-09-23 | 7 | 2026-10-01 | 60
A29300 | Materials Successfully Inspected, Tested / Ex Work | 2026-07-09 | 2026-07-20 | 2026-07-09 | 2026-07-20 | 2026-10-02 | 7 | 2026-10-12 | 60
A33460 | Delivery of Material in Warehouse for Cathodic Protection | 2026-07-20 | 2026-08-03 | 2026-07-20 | 2026-08-03 | 2026-10-13 | 18 | 2026-10-26 | 105
LV & MV Switchgears |  | 2026-02-20 | 2026-08-20 | 12-Sep-25 A | 2026-08-20 | 2026-04-22 | 244 | 2026-10-18 | 41
Switchgear (MV & LV) |  | 2026-02-20 | 2026-08-20 | 12-Sep-25 A | 2026-08-20 | 2026-04-22 | 244 | 2026-10-18 | 41
A34260 | Start Production |  |  | 12-Sep-25 A |  |  | 0
A32480 | Key Vendor Drawings / Data Approved | 2026-02-20 | 2026-02-20 | 21-Nov-25 A | 02-Dec-25 A | 2026-04-22 | 50 | 2026-04-22
A32490 | Purchase Order for Major Sub-ordered Materials | 2026-02-20 | 2026-02-20 | 11-Dec-25 A | 19-Dec-25 A | 2026-04-22 | 10 | 2026-04-22
A32500 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-02-20 | 2026-02-24 | 20-Jan-26 A | 2026-02-24 | 2026-04-22 | 35 | 2026-04-24 | 43
A32510 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-02-25 | 2026-02-25 | 2026-02-25 | 2026-02-25 | 2026-04-25 | 1 | 2026-04-26 | 74
A32520 | Manufacturing / Ex Works (India/UAE) | 2026-02-26 | 2026-07-10 | 2026-02-26 | 2026-07-10 | 2026-04-26 | 169 | 2026-09-08 | 74
A32530 | Complete Manufacturing & ready for Final Inspection | 2026-07-13 | 2026-07-21 | 2026-07-13 | 2026-07-21 | 2026-09-08 | 7 | 2026-09-16 | 41
A32540 | Materials Successfully Inspected, Tested / Ex Work | 2026-07-22 | 2026-07-30 | 2026-07-22 | 2026-07-30 | 2026-09-17 | 7 | 2026-09-25 | 41
A34270 | Delivery of Switchgear (MV & LV) | 2026-07-31 | 2026-08-20 | 2026-07-31 | 2026-08-20 | 2026-09-28 | 26 | 2026-10-18 | 74
Switch Gear Modification (Siemens) |  | 2026-02-20 | 2026-02-20 | 17-Mar-25 A | 12-May-25 A | 2026-03-27 | 93 | 2026-03-27
TA_Switchgear (MV Switchgear Modifications) - Siemens |  | 2026-02-20 | 2026-02-20 | 17-Mar-25 A | 12-May-25 A | 2026-03-27 | 93 | 2026-03-27
A22450 | Start Production |  |  | 17-Mar-25 A |  |  | 0
A22460 | Key Vendor Drawings / Data Approved | 2026-02-20 | 2026-02-20 | 18-Mar-25 A | 24-Mar-25 A | 2026-03-27 | 2 | 2026-03-27
A22740 | Purchase Order for Major Sub-ordered Materials | 2026-02-20 | 2026-02-20 | 25-Mar-25 A | 31-Mar-25 A | 2026-03-27 | 2 | 2026-03-27
A22760 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-02-20 | 2026-02-20 | 01-Apr-25 A | 07-Apr-25 A | 2026-03-27 | 2 | 2026-03-27
A24280 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 14-Apr-25 A | 2026-03-27 | 3 | 2026-03-27
A22470 | Manufacturing / Ex Works (India/UAE) | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 21-Apr-25 A | 2026-03-27 | 3 | 2026-03-27
A22770 | Complete Manufacturing & ready for Final Inspection | 2026-02-20 | 2026-02-20 | 22-Apr-25 A | 28-Apr-25 A | 2026-03-27 | 2 | 2026-03-27
A22780 | Materials Successfully Inspected, Tested / Ex Work | 2026-02-20 | 2026-02-20 | 29-Apr-25 A | 05-May-25 A | 2026-03-27 | 2 | 2026-03-27
A22410 | Delivery of Material For Switchgear Modification | 2026-02-20 | 2026-02-20 | 06-May-25 A | 12-May-25 A | 2026-03-27 | 3 | 2026-03-27
MV & LV VFD's |  | 2026-02-20 | 2026-03-19 | 13-Aug-25 A | 2026-03-19 | 2026-09-22 | 169 | 2026-10-19 | 152
Variable Fequency Drives (VFDs) LV Qty = 03 |  | 2026-02-20 | 2026-03-19 | 13-Aug-25 A | 2026-03-19 | 2026-09-22 | 169 | 2026-10-19 | 152
A34280 | Start Production |  |  | 13-Aug-25 A |  |  | 0
A32570 | Key Vendor Drawings / Data Approved | 2026-02-20 | 2026-02-20 | 13-Aug-25 A | 14-Aug-25 A | 2026-09-22 | 50 | 2026-09-22
A32580 | Purchase Order for Major Sub-ordered Materials | 2026-02-20 | 2026-02-20 | 15-Aug-25 A | 16-Aug-25 A | 2026-09-22 | 10 | 2026-09-22
A32590 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-02-20 | 2026-02-20 | 17-Aug-25 A | 18-Aug-25 A | 2026-09-22 | 30 | 2026-09-22
A32600 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-02-20 | 2026-02-20 | 19-Aug-25 A | 19-Aug-25 A | 2026-09-22 | 1 | 2026-09-22
A32610 | Manufacturing / Ex Works (India/UAE) | 2026-02-20 | 2026-02-20 | 20-Aug-25 A | 20-Aug-25 A | 2026-09-22 | 150 | 2026-09-22
A32620 | Complete Manufacturing & ready for Final Inspection | 2026-02-20 | 2026-02-20 | 20-Aug-25 A | 21-Aug-25 A | 2026-09-22 | 7 | 2026-09-22
A32630 | Materials Successfully Inspected, Tested / Ex Work | 2026-02-20 | 2026-02-20 | 22-Aug-25 A | 22-Aug-25 A | 2026-09-22 | 7 | 2026-09-22
A34290 | Delivery of VFDs | 2026-02-20 | 2026-03-19 | 2026-02-20 | 2026-03-19 | 2026-09-22 | 35 | 2026-10-19 | 268
HV Capacitor Bay |  | 2026-02-20 | 2026-07-28 | 27-Oct-25 A | 2026-07-28 | 2026-06-11 | 178 | 2026-11-16 | 79
HV Capacitor Bay |  | 2026-02-20 | 2026-07-28 | 27-Oct-25 A | 2026-07-28 | 2026-06-11 | 178 | 2026-11-16 | 79
A34150 | Start Production |  |  | 27-Oct-25 A |  |  | 0
A32030 | Key Vendor Drawings / Data Approved | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 26-Feb-26 A | 2026-06-11 | 50 | 2026-06-11
A32040 | Purchase Order for Major Sub-ordered Materials | 2026-02-20 | 2026-03-05 | 2026-02-20 | 2026-03-05 | 2026-06-11 | 10 | 2026-06-24 | 79
A32050 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-03-06 | 2026-04-16 | 2026-03-06 | 2026-04-16 | 2026-06-25 | 30 | 2026-08-05 | 79
A32060 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-08-06 | 1 | 2026-08-07 | 139
A32070 | Manufacturing / Ex Works (India/UAE) | 2026-04-18 | 2026-07-01 | 2026-04-18 | 2026-07-01 | 2026-08-07 | 94 | 2026-10-21 | 139
A32080 | Complete Manufacturing & ready for Final Inspection | 2026-07-02 | 2026-07-10 | 2026-07-02 | 2026-07-10 | 2026-10-21 | 7 | 2026-10-29 | 79
A32090 | Materials Successfully Inspected, Tested / Ex Work | 2026-07-13 | 2026-07-21 | 2026-07-13 | 2026-07-21 | 2026-10-30 | 7 | 2026-11-09 | 79
A34160 | Delivery of Material in Warehouse HV Capacitor Bay | 2026-07-22 | 2026-07-28 | 2026-07-22 | 2026-07-28 | 2026-11-10 | 9 | 2026-11-16 | 139
Power Distribution Panel and LCS, Battery & Safety Switch, Resister Bank |  | 2026-02-20 | 2026-04-08 | 06-Jun-25 A | 2026-04-08 | 2026-09-29 | 302 | 2026-11-13 | 157
NGR Panel Qty 02 |  | 2026-02-20 | 2026-04-08 | 06-Jun-25 A | 2026-04-08 | 2026-09-29 | 302 | 2026-11-13 | 157
A34380 | Start Production |  |  | 06-Jun-25 A |  |  | 0
A33020 | Key Vendor Drawings / Data Approved | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 20-Dec-25 A | 2026-09-29 | 50 | 2026-09-29
A33030 | Purchase Order for Major Sub-ordered Materials | 2026-02-20 | 2026-02-20 | 22-Dec-25 A | 27-Dec-25 A | 2026-09-29 | 10 | 2026-09-29
A33040 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-02-20 | 2026-02-20 | 28-Dec-25 A | 03-Jan-26 A | 2026-09-29 | 30 | 2026-09-29
A33050 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-02-20 | 2026-02-20 | 02-Jan-26 A | 10-Jan-26 A | 2026-09-29 | 1 | 2026-09-29
A33060 | Manufacturing / Ex Works (India/UAE) | 2026-02-20 | 2026-02-20 | 01-Jan-26 A | 17-Jan-26 A | 2026-09-29 | 150 | 2026-09-29
A33070 | Complete Manufacturing & ready for Final Inspection | 2026-02-20 | 2026-03-02 | 2026-02-20 | 2026-03-02 | 2026-09-29 | 7 | 2026-10-07 | 157
A33080 | Materials Successfully Inspected, Tested / Ex Work | 2026-03-03 | 2026-03-11 | 2026-03-03 | 2026-03-11 | 2026-10-08 | 7 | 2026-10-16 | 157
A34390 | Delivery of NGR Panel | 2026-03-12 | 2026-04-08 | 2026-03-12 | 2026-04-08 | 2026-10-17 | 35 | 2026-11-13 | 274
Interposing Relay Panel (IRP) |  | 2026-03-18 | 2026-09-17 | 2026-03-18 | 2026-09-17 | 2026-05-25 | 131 | 2026-11-22 | 46
Interposing Relay Panel |  | 2026-03-18 | 2026-09-17 | 2026-03-18 | 2026-09-17 | 2026-05-25 | 131 | 2026-11-22 | 46
A34400 | Start Production | 2026-03-18 |  | 2026-03-18 |  | 2026-05-25 | 0 |  | 84
A33110 | Key Vendor Drawings / Data Approved | 2026-03-19 | 2026-04-08 | 2026-03-19 | 2026-04-08 | 2026-05-25 | 15 | 2026-06-12 | 47
A33120 | Purchase Order for Major Sub-ordered Materials | 2026-04-08 | 2026-04-22 | 2026-04-08 | 2026-04-22 | 2026-06-15 | 10 | 2026-06-26 | 47
A33130 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-04-22 | 2026-05-13 | 2026-04-22 | 2026-05-13 | 2026-06-29 | 15 | 2026-07-17 | 47
A33140 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-05-13 | 2026-05-14 | 2026-05-13 | 2026-05-14 | 2026-07-18 | 1 | 2026-07-19 | 82
A33150 | Manufacturing / Ex Works (India/UAE) | 2026-05-14 | 2026-08-22 | 2026-05-14 | 2026-08-22 | 2026-07-19 | 125 | 2026-10-27 | 82
A33160 | Complete Manufacturing & ready for Final Inspection | 2026-08-24 | 2026-09-01 | 2026-08-24 | 2026-09-01 | 2026-10-27 | 7 | 2026-11-04 | 46
A33170 | Materials Successfully Inspected, Tested / Ex Work | 2026-09-02 | 2026-09-10 | 2026-09-02 | 2026-09-10 | 2026-11-05 | 7 | 2026-11-13 | 46
A34410 | Delivery of Interposing relay Panel | 2026-09-11 | 2026-09-17 | 2026-09-11 | 2026-09-17 | 2026-11-16 | 9 | 2026-11-22 | 83
Construction and Pre-Commissioning |  | 2026-02-20 | 2027-07-01 | 09-Jan-25 A | 2027-07-01 | 2026-02-21 | 651 | 2027-07-20 | 13
Construction/Pre-Commissioning |  | 2026-02-20 | 2026-12-21 | 10-Jun-25 A | 2026-12-21 | 2026-06-02 | 326 | 2027-01-03 | 9
Green Field Works |  | 2026-02-20 | 2026-12-21 | 10-Jun-25 A | 2026-12-21 | 2026-06-02 | 326 | 2027-01-03 | 9
General / Common |  | 2026-02-20 | 2026-02-20 | 10-Jun-25 A | 15-Oct-25 A | 2026-08-22 | 148 | 2026-08-22
A3250 | Complete Site Preparation and Grading works |  |  |  | 16-Jun-25 A |  | 0
CONS10 | Installation of Isolation Fence Plant Site | 2026-02-20 | 2026-02-20 | 10-Jun-25 A | 13-Aug-25 A | 2026-08-22 | 30 | 2026-08-22
CONS | TSF Construction / Commence on SITE | 2026-02-20 | 2026-02-20 | 01-Jul-25 A | 15-Oct-25 A | 2026-08-22 | 100 | 2026-08-22
Electrical & Instrumentation Works |  | 2026-05-09 | 2026-12-21 | 2026-05-09 | 2026-12-21 | 2026-06-02 | 161 | 2027-01-03 | 9
A18510 | Cable Laying - Trenches | 2026-05-09 | 2026-07-21 | 2026-05-09 | 2026-07-21 | 2026-06-02 | 64 | 2026-08-15 | 21
A3709 | E&I Bulk & Equipment Deliveries - Plant Site |  | 2026-09-24 |  | 2026-09-24 |  | 0 | 2026-10-26 | 40
A3739 | Complete E&I Equipment / Panels Installation CCB &SIS |  | 2026-10-18 |  | 2026-10-18 |  | 0 | 2027-01-03 | 67
A3889 | Electrical Works Plant Site (Cable trays, cable laying, termination, DBs, Jbs etc) | 2026-08-26 | 2026-11-08 | 2026-08-26 | 2026-11-08 | 2026-09-28 | 64 | 2026-12-10 | 28
A3759 | Complete E&I Work at plant site |  | 2026-11-17 |  | 2026-11-17 |  | 0 | 2026-12-20 | 29
A3909 | Instrumentation Works Plant Site (Control/Manual Valves, Gauges, TT, PT, DPT, PSVs, Switches etc) | 2026-09-27 | 2026-11-17 | 2026-09-27 | 2026-11-17 | 2026-10-31 | 44 | 2026-12-20 | 29
A3719 | E&I Works (CCB & SIS) For cable trays and cable laying | 2026-09-26 | 2026-12-21 | 2026-09-26 | 2026-12-21 | 2026-10-08 | 75 | 2027-01-03 | 11
A3749 | Complete Cable termination and loop test - Overall |  | 2026-12-21 |  | 2026-12-21 |  | 0 | 2027-01-03 | 11
Accommodation and Messing |  | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 24-Jul-25 A | 2026-03-11 | 112 | 2026-03-11
Mobilisation of Camp (Accommodation and Messing) |  | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 24-Jul-25 A | 2026-03-11 | 112 | 2026-03-11
A61550 | TA - Mobilisation of Camp (Accommodation and messing) | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-Apr-25 A | 2026-03-11 | 4 | 2026-03-11
A62210 | Main Scope - Mobilisation of Camp (Accommodation and messing) | 2026-02-20 | 2026-02-20 | 22-Apr-25 A | 24-Jul-25 A | 2026-03-11 | 4 | 2026-03-11
Fabrication, Storage, Workshops (Temporary Facilities) |  | 2026-02-20 | 2027-07-01 | 01-Apr-25 A | 2027-07-01 | 2026-03-11 | 636 | 2027-07-20 | 16
Mobilisation of Temporary Facilities |  | 2026-02-20 | 2026-02-20 | 01-Apr-25 A | 24-Oct-25 A | 2026-03-11 | 54 | 2026-03-11
A61560 | Mobilisation of Temporary Facilities - TA | 2026-02-20 | 2026-02-20 | 01-Apr-25 A | 31-May-25 A | 2026-03-11 | 24 | 2026-03-11
A62230 | Mobilisation of Temporary Facilities - Main Scope | 2026-02-20 | 2026-02-20 | 01-Aug-25 A | 24-Oct-25 A | 2026-03-11 | 24 | 2026-03-11
Maintenance of Temporary Facilities |  | 2026-02-20 | 2027-03-18 | 01-Nov-25 A | 2027-03-18 | 2026-03-11 | 336 | 2027-04-06 | 16
A62240 | Maintenance of Temporary Facilities - Q1 | 2026-02-20 | 2026-02-20 | 01-Nov-25 A | 18-Nov-25 A | 2026-03-11 | 24 | 2026-03-11
A61570 | Maintenance of Temporary Facilities - Q2 | 2026-02-20 | 2026-02-20 | 01-Jan-26 A | 24-Jan-26 A | 2026-03-11 | 24 | 2026-03-11
A62250 | Maintenance of Temporary Facilities - Q3 | 2026-04-11 | 2026-05-07 | 2026-04-11 | 2026-05-07 | 2026-04-29 | 24 | 2026-05-26 | 16
A62260 | Maintenance of Temporary Facilities - Q4 | 2026-07-25 | 2026-08-20 | 2026-07-25 | 2026-08-20 | 2026-08-12 | 24 | 2026-09-08 | 16
A62270 | Maintenance of Temporary Facilities - Q5 | 2026-11-07 | 2026-12-03 | 2026-11-07 | 2026-12-03 | 2026-11-25 | 24 | 2026-12-22 | 16
A62280 | Maintenance of Temporary Facilities - Q6 | 2027-02-20 | 2027-03-18 | 2027-02-20 | 2027-03-18 | 2027-03-10 | 24 | 2027-04-06 | 16
Demobilisation of Temporary Facilities |  | 2026-02-20 | 2027-07-01 | 25-Jun-25 A | 2027-07-01 | 2027-06-23 | 636 | 2027-07-20 | 16
A61580 | Demobiisation of Temporary Facilities - TA | 2026-02-20 | 2026-02-20 | 25-Jun-25 A | 11-Jul-25 A | 2027-06-23 | 24 | 2027-06-23
A62290 | Demobiisation of Temporary Facilities - Main Scope | 2027-06-05 | 2027-07-01 | 2027-06-05 | 2027-07-01 | 2027-06-23 | 24 | 2027-07-20 | 16
Civil Construction |  | 2026-02-20 | 2027-01-11 | 09-Jan-25 A | 2027-01-11 | 2026-02-21 | 461 | 2027-01-20 | 7
Site Preparation |  | 2026-02-20 | 2026-02-20 | 01-Apr-25 A | 15-Sep-25 A | 2026-03-11 | 78 | 2026-03-11
A61590 | Site Preparation - TA | 2026-02-20 | 2026-02-20 | 01-Apr-25 A | 21-Jun-25 A | 2026-03-11 | 24 | 2026-03-11
A62220 | Site Preparation - Main Scope | 2026-02-20 | 2026-02-20 | 22-Aug-25 A | 15-Sep-25 A | 2026-03-11 | 24 | 2026-03-11
Fencing |  | 2026-02-20 | 2026-02-20 | 17-Apr-25 A | 22-Aug-25 A | 2026-03-11 | 24 | 2026-03-11
A61600 | Fencing | 2026-02-20 | 2026-02-20 | 17-Apr-25 A | 22-Aug-25 A | 2026-03-11 | 24 | 2026-03-11
Excavation and trenching |  | 2026-03-02 | 2026-08-15 | 2026-03-02 | 2026-08-15 | 2026-04-11 | 143 | 2026-10-04 | 43
GF Sumps and Pits |  | 2026-03-07 | 2026-08-11 | 2026-03-07 | 2026-08-11 | 2026-05-06 | 136 | 2026-09-01 | 18
Accidentally Oily Water Sump 70-TD-1407 |  | 2026-03-07 | 2026-05-28 | 2026-03-07 | 2026-05-28 | 2026-05-06 | 72 | 2026-07-28 | 52
A26600 | Excavation | 2026-03-07 | 2026-03-17 | 2026-03-07 | 2026-03-17 | 2026-05-06 | 10 | 2026-05-17 | 52
A26610 | Surface leveling and compaction | 2026-03-18 | 2026-03-19 | 2026-03-18 | 2026-03-19 | 2026-05-18 | 2 | 2026-05-19 | 52
A26620 | Lean concrete | 2026-03-21 | 2026-03-22 | 2026-03-21 | 2026-03-22 | 2026-05-20 | 2 | 2026-05-21 | 52
A26630 | Water proofing and bitumen coating/sheet | 2026-03-30 | 2026-04-02 | 2026-03-30 | 2026-04-02 | 2026-05-30 | 4 | 2026-06-02 | 52
A26640 | Formworks | 2026-04-04 | 2026-04-14 | 2026-04-04 | 2026-04-14 | 2026-06-03 | 10 | 2026-06-14 | 52
A26650 | Rebar works | 2026-04-04 | 2026-04-14 | 2026-04-04 | 2026-04-14 | 2026-06-03 | 10 | 2026-06-14 | 52
A26660 | Concrete pouring | 2026-04-18 | 2026-04-28 | 2026-04-18 | 2026-04-28 | 2026-06-17 | 10 | 2026-06-28 | 52
A26670 | Concrete Curing | 2026-04-19 | 2026-05-04 | 2026-04-19 | 2026-05-04 | 2026-06-18 | 14 | 2026-07-04 | 52
A26680 | Formwork removal | 2026-04-21 | 2026-05-06 | 2026-04-21 | 2026-05-06 | 2026-06-21 | 14 | 2026-07-06 | 52
A26690 | Protective Coating | 2026-05-07 | 2026-05-20 | 2026-05-07 | 2026-05-20 | 2026-07-07 | 12 | 2026-07-20 | 52
A26700 | Back filling and compaction in layers | 2026-05-21 | 2026-05-28 | 2026-05-21 | 2026-05-28 | 2026-07-21 | 7 | 2026-07-28 | 52
Oil Contaminated Water Sump 70-TD-1408 |  | 2026-03-25 | 2026-06-16 | 2026-03-25 | 2026-06-16 | 2026-05-06 | 72 | 2026-07-28 | 36
A26710 | Excavation | 2026-03-25 | 2026-04-05 | 2026-03-25 | 2026-04-05 | 2026-05-06 | 10 | 2026-05-17 | 36
A26720 | Surface leveling and compaction | 2026-04-06 | 2026-04-07 | 2026-04-06 | 2026-04-07 | 2026-05-18 | 2 | 2026-05-19 | 36
A26730 | Lean concrete | 2026-04-08 | 2026-04-09 | 2026-04-08 | 2026-04-09 | 2026-05-20 | 2 | 2026-05-21 | 36
A26740 | Water proofing and bitumen coating/sheet | 2026-04-18 | 2026-04-21 | 2026-04-18 | 2026-04-21 | 2026-05-30 | 4 | 2026-06-02 | 36
A26750 | Formworks | 2026-04-22 | 2026-05-03 | 2026-04-22 | 2026-05-03 | 2026-06-03 | 10 | 2026-06-14 | 36
A26760 | Rebar works | 2026-04-22 | 2026-05-03 | 2026-04-22 | 2026-05-03 | 2026-06-03 | 10 | 2026-06-14 | 36
A26770 | Concrete pouring | 2026-05-06 | 2026-05-17 | 2026-05-06 | 2026-05-17 | 2026-06-17 | 10 | 2026-06-28 | 36
A26780 | Concrete Curing | 2026-05-07 | 2026-05-23 | 2026-05-07 | 2026-05-23 | 2026-06-18 | 14 | 2026-07-04 | 36
A26790 | Formwork removal | 2026-05-10 | 2026-05-25 | 2026-05-10 | 2026-05-25 | 2026-06-21 | 14 | 2026-07-06 | 36
A26800 | Protective Coating | 2026-05-26 | 2026-06-08 | 2026-05-26 | 2026-06-08 | 2026-07-07 | 12 | 2026-07-20 | 36
A26810 | Back filling and compaction in layers | 2026-06-09 | 2026-06-16 | 2026-06-09 | 2026-06-16 | 2026-07-21 | 7 | 2026-07-28 | 36
Sanitary Waste Water Sump 70-TD-1409 |  | 2026-05-10 | 2026-07-02 | 2026-05-10 | 2026-07-02 | 2026-06-04 | 47 | 2026-07-28 | 22
A26820 | Excavation | 2026-05-10 | 2026-05-17 | 2026-05-10 | 2026-05-17 | 2026-06-04 | 7 | 2026-06-11 | 22
A26830 | Surface leveling and compaction | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-06-13 | 1 | 2026-06-13 | 22
A26840 | Lean concrete | 2026-05-19 | 2026-05-19 | 2026-05-19 | 2026-05-19 | 2026-06-14 | 1 | 2026-06-14 | 22
A26850 | Water proofing and bitumen coating/sheet | 2026-05-27 | 2026-05-28 | 2026-05-27 | 2026-05-28 | 2026-06-22 | 2 | 2026-06-23 | 22
A26860 | Formworks | 2026-05-30 | 2026-06-09 | 2026-05-30 | 2026-06-09 | 2026-06-24 | 10 | 2026-07-05 | 22
A26870 | Rebar works | 2026-05-30 | 2026-06-09 | 2026-05-30 | 2026-06-09 | 2026-06-24 | 10 | 2026-07-05 | 22
A26880 | Concrete pouring | 2026-06-06 | 2026-06-13 | 2026-06-06 | 2026-06-13 | 2026-07-01 | 7 | 2026-07-08 | 22
A26900 | Formwork removal | 2026-06-09 | 2026-06-16 | 2026-06-09 | 2026-06-16 | 2026-07-05 | 7 | 2026-07-12 | 22
A26890 | Concrete Curing | 2026-06-07 | 2026-06-22 | 2026-06-07 | 2026-06-22 | 2026-07-02 | 14 | 2026-07-18 | 22
A26910 | Protective Coating | 2026-06-17 | 2026-06-24 | 2026-06-17 | 2026-06-24 | 2026-07-13 | 7 | 2026-07-20 | 22
A26920 | Back filling and compaction in layers | 2026-06-25 | 2026-07-02 | 2026-06-25 | 2026-07-02 | 2026-07-21 | 7 | 2026-07-28 | 22
PSA2 Slope Drum Pit |  | 2026-03-15 | 2026-05-23 | 2026-03-15 | 2026-05-23 | 2026-05-20 | 60 | 2026-07-28 | 57
A26930 | Excavation | 2026-03-15 | 2026-03-22 | 2026-03-15 | 2026-03-22 | 2026-05-20 | 7 | 2026-05-27 | 57
A26940 | Surface leveling and compaction | 2026-03-23 | 2026-03-24 | 2026-03-23 | 2026-03-24 | 2026-05-28 | 2 | 2026-05-30 | 57
A26950 | Lean concrete | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 2026-05-31 | 2 | 2026-06-01 | 57
A26960 | Water proofing and bitumen coating/sheet | 2026-04-04 | 2026-04-07 | 2026-04-04 | 2026-04-07 | 2026-06-09 | 4 | 2026-06-13 | 57
A26970 | Formworks | 2026-04-08 | 2026-04-15 | 2026-04-08 | 2026-04-15 | 2026-06-14 | 7 | 2026-06-21 | 57
A26980 | Rebar works | 2026-04-08 | 2026-04-15 | 2026-04-08 | 2026-04-15 | 2026-06-14 | 7 | 2026-06-21 | 57
A26990 | Concrete pouring | 2026-04-22 | 2026-04-29 | 2026-04-22 | 2026-04-29 | 2026-06-28 | 7 | 2026-07-05 | 57
A27010 | Formwork removal | 2026-04-26 | 2026-05-06 | 2026-04-26 | 2026-05-06 | 2026-07-01 | 10 | 2026-07-12 | 57
A27000 | Concrete Curing | 2026-04-23 | 2026-05-09 | 2026-04-23 | 2026-05-09 | 2026-06-29 | 14 | 2026-07-14 | 57
A27020 | Protective Coating | 2026-05-07 | 2026-05-14 | 2026-05-07 | 2026-05-14 | 2026-07-13 | 7 | 2026-07-20 | 57
A27030 | Back filling and compaction in layers | 2026-05-16 | 2026-05-23 | 2026-05-16 | 2026-05-23 | 2026-07-21 | 7 | 2026-07-28 | 57
Cooling Water Valve Pit |  | 2026-06-07 | 2026-08-11 | 2026-06-07 | 2026-08-11 | 2026-06-28 | 57 | 2026-09-01 | 18
A27040 | Excavation | 2026-06-07 | 2026-06-14 | 2026-06-07 | 2026-06-14 | 2026-06-28 | 7 | 2026-07-05 | 18
A27050 | Surface leveling and compaction | 2026-06-15 | 2026-06-16 | 2026-06-15 | 2026-06-16 | 2026-07-06 | 2 | 2026-07-07 | 18
A27060 | Lean concrete | 2026-06-17 | 2026-06-18 | 2026-06-17 | 2026-06-18 | 2026-07-08 | 2 | 2026-07-09 | 18
A27070 | Water proofing and bitumen coating/sheet | 2026-06-27 | 2026-06-30 | 2026-06-27 | 2026-06-30 | 2026-07-18 | 4 | 2026-07-21 | 18
A27080 | Formworks | 2026-07-01 | 2026-07-12 | 2026-07-01 | 2026-07-12 | 2026-07-22 | 10 | 2026-08-02 | 18
A27090 | Rebar works | 2026-07-01 | 2026-07-12 | 2026-07-01 | 2026-07-12 | 2026-07-22 | 10 | 2026-08-02 | 18
A27100 | Concrete pouring | 2026-07-15 | 2026-07-22 | 2026-07-15 | 2026-07-22 | 2026-08-05 | 7 | 2026-08-12 | 18
A27120 | Formwork removal | 2026-07-19 | 2026-07-26 | 2026-07-19 | 2026-07-26 | 2026-08-09 | 7 | 2026-08-16 | 18
A27110 | Concrete Curing | 2026-07-16 | 2026-08-01 | 2026-07-16 | 2026-08-01 | 2026-08-06 | 14 | 2026-08-22 | 18
A27130 | Protective Coating | 2026-07-27 | 2026-08-03 | 2026-07-27 | 2026-08-03 | 2026-08-17 | 7 | 2026-08-24 | 18
A27140 | Back filling and compaction in layers | 2026-08-04 | 2026-08-11 | 2026-08-04 | 2026-08-11 | 2026-08-25 | 7 | 2026-09-01 | 18
GF UG Piping and Trenches |  | 2026-03-17 | 2026-08-15 | 2026-03-17 | 2026-08-15 | 2026-04-11 | 130 | 2026-09-08 | 21
Piping |  | 2026-04-11 | 2026-07-19 | 2026-04-11 | 2026-07-19 | 2026-04-20 | 86 | 2026-07-28 | 8
A3440 | Trenching for UG Piping | 2026-04-11 | 2026-05-11 | 2026-04-11 | 2026-05-11 | 2026-04-20 | 27 | 2026-05-20 | 8
A18530 | Excavation and Valve Pits for Fire Water Line | 2026-04-11 | 2026-06-17 | 2026-04-11 | 2026-06-17 | 2026-04-20 | 59 | 2026-06-27 | 8
A3450 | Complete UG Piping & Backfilling | 2026-05-12 | 2026-07-19 | 2026-05-12 | 2026-07-19 | 2026-05-21 | 59 | 2026-07-28 | 8
Cables |  | 2026-03-17 | 2026-08-15 | 2026-03-17 | 2026-08-15 | 2026-04-11 | 130 | 2026-09-08 | 21
A18460 | Direct Buried Trenches for Power and Instrumentation cables | 2026-04-11 | 2026-05-04 | 2026-04-11 | 2026-05-04 | 2026-05-16 | 21 | 2026-06-08 | 30
A3460 | Concrete Trenches for Electrical and Instrumentation Cable | 2026-03-17 | 2026-05-07 | 2026-03-17 | 2026-05-07 | 2026-04-11 | 45 | 2026-06-01 | 21
A18480 | Backfilling of E&I trenches | 2026-07-22 | 2026-08-15 | 2026-07-22 | 2026-08-15 | 2026-08-16 | 21 | 2026-09-08 | 21
BF Trenches |  | 2026-03-02 | 2026-05-23 | 2026-03-02 | 2026-05-23 | 2026-07-08 | 70 | 2026-10-04 | 116
A21800 | Duct Banks/Road Crossing | 2026-03-02 | 2026-04-12 | 2026-03-02 | 2026-04-12 | 2026-07-08 | 35 | 2026-08-18 | 110
A21770 | Direct buried trenches - BF | 2026-04-12 | 2026-05-23 | 2026-04-12 | 2026-05-23 | 2026-08-25 | 35 | 2026-10-04 | 116
Foundations |  | 2026-02-20 | 2027-01-11 | 03-Jul-25 A | 2027-01-11 | 2026-02-21 | 324 | 2027-01-20 | 7
A62510 | New Activity |  |  | 2026-02-20 | 2026-02-26 |  | 5
GF SIS Building Structure Works |  | 2026-02-20 | 2026-05-02 | 02-Sep-25 A | 2026-05-02 | 2026-03-14 | 163 | 2026-05-23 | 18
Sub-Structure |  | 2026-02-20 | 2026-03-09 | 02-Sep-25 A | 2026-03-09 | 2026-03-14 | 114 | 2026-03-30 | 18
A1590 | Foundation Works (Excavation, PCC & RCC) | 2026-02-20 | 2026-02-20 | 02-Sep-25 A | 01-Jan-26 A | 2026-03-14 | 30 | 2026-03-14
A1600 | RCC Columns and Walls Upto FFL | 2026-02-20 | 2026-02-20 | 16-Dec-25 A | 16-Jan-26 A | 2026-03-14 | 48 | 2026-03-14
A1610 | Waterproofing & Backfilling | 2026-02-21 | 2026-02-28 | 16-Dec-25 A | 2026-02-28 | 2026-03-14 | 27 | 2026-03-21 | 18
A1620 | Plinth Beams | 2026-02-21 | 2026-03-09 | 16-Dec-25 A | 2026-03-09 | 2026-03-14 | 15 | 2026-03-30 | 18
Super-Structure |  | 2026-03-10 | 2026-05-02 | 2026-03-10 | 2026-05-02 | 2026-03-31 | 46 | 2026-05-23 | 18
A1500 | RCC Columns and Walls Upto First Slab | 2026-03-10 | 2026-04-13 | 2026-03-10 | 2026-04-13 | 2026-03-31 | 30 | 2026-05-04 | 18
A1510 | First Slab and Beams | 2026-03-29 | 2026-05-02 | 2026-03-29 | 2026-05-02 | 2026-04-19 | 30 | 2026-05-23 | 18
GF Sub-Station Sub-Structure |  | 2026-02-20 | 2027-01-04 | 25-Aug-25 A | 2027-01-04 | 2026-03-14 | 383 | 2027-01-20 | 14
A26360 | Foundation Works (Excavation, PCC & RCC) | 2026-02-20 | 2026-02-20 | 25-Aug-25 A | 16-Sep-25 A | 2026-03-14 | 21 | 2026-03-14
A26380 | Waterproofing & Backfilling (handingover to Precast) | 2026-02-20 | 2026-02-20 | 15-Sep-25 A | 22-Sep-25 A | 2026-03-18 | 20 | 2026-03-18
A26370 | RCC Base & Columns Upto FFL | 2026-02-20 | 2026-02-20 | 21-Nov-25 A | 10-Feb-26 A | 2026-03-18 | 20 | 2026-03-18
A1030 | Plinth Beams (Casting Suti) | 2026-02-28 | 2026-03-26 | 15-Dec-25 A | 2026-03-26 | 2026-05-07 | 24 | 2026-06-03 | 59
GF Sub-Station Super-Structure |  | 2026-02-21 | 2027-01-04 | 24-Jan-26 A | 2027-01-04 | 2026-03-18 | 273 | 2027-01-20 | 14
Ground Floor - Cellar Area |  | 2026-02-21 | 2026-03-26 | 24-Jan-26 A | 2026-03-26 | 2026-03-18 | 30 | 2026-04-21 | 22
A26390 | RCC Columns and Walls Upto First Slab | 2026-02-21 | 2026-03-26 | 24-Jan-26 A | 2026-03-26 | 2026-03-18 | 30 | 2026-04-21 | 22
A26400 | First Slab and Beams | 2026-02-21 | 2026-03-26 | 2026-02-21 | 2026-03-26 | 2026-03-18 | 30 | 2026-04-21 | 22
First Floor |  | 2026-03-11 | 2027-01-04 | 2026-03-11 | 2027-01-04 | 2026-04-06 | 257 | 2027-01-20 | 14
A26410 | RCC Columns Upto 2nd Slab | 2026-03-11 | 2026-04-11 | 2026-03-11 | 2026-04-11 | 2026-04-06 | 27 | 2026-05-06 | 22
A26420 | 2nd Slab and Beams | 2026-03-26 | 2026-05-09 | 2026-03-26 | 2026-05-09 | 2026-04-21 | 38 | 2026-06-03 | 22
C1059 | Punch List Close Out (Construction / Mechanical) | 2026-12-22 | 2027-01-04 | 2026-12-22 | 2027-01-04 | 2027-01-07 | 12 | 2027-01-20 | 14
GF Transformers Structure Works |  | 2026-02-21 | 2026-06-06 | 2026-02-21 | 2026-06-06 | 2026-03-17 | 91 | 2026-06-27 | 18
Sub-Structure |  | 2026-02-21 | 2026-05-12 | 2026-02-21 | 2026-05-12 | 2026-03-17 | 70 | 2026-06-27 | 39
A26460 | Foundation Works (Excavation, PCC & RCC) | 2026-02-21 | 2026-03-26 | 2026-02-21 | 2026-03-26 | 2026-03-17 | 30 | 2026-04-20 | 21
A1150 | RCC Walls Upto FFL | 2026-03-25 | 2026-04-28 | 2026-03-25 | 2026-04-28 | 2026-04-19 | 30 | 2026-05-23 | 21
A26470 | Waterproofing & Backfilling | 2026-04-08 | 2026-05-12 | 2026-04-08 | 2026-05-12 | 2026-05-24 | 30 | 2026-06-27 | 39
Super-Structure |  | 2026-05-03 | 2026-06-06 | 2026-05-03 | 2026-06-06 | 2026-05-24 | 30 | 2026-06-27 | 18
A1190 | RCC Walls above Ground | 2026-05-03 | 2026-06-06 | 2026-05-03 | 2026-06-06 | 2026-05-24 | 30 | 2026-06-27 | 18
Roads and Pavement Construction |  | 2026-07-20 | 2027-01-11 | 2026-07-20 | 2027-01-11 | 2026-07-29 | 151 | 2027-01-20 | 8
A6860 | Subgarde and Sub-Base for Road | 2026-07-20 | 2026-09-16 | 2026-07-20 | 2026-09-16 | 2026-07-29 | 51 | 2026-09-26 | 8
A6880 | Concrete Flooring on Plant Side | 2026-09-17 | 2026-11-12 | 2026-09-17 | 2026-11-12 | 2026-09-27 | 49 | 2026-11-22 | 8
A6870 | Base Course and Asphalt working | 2026-11-14 | 2027-01-11 | 2026-11-14 | 2027-01-11 | 2026-11-23 | 51 | 2027-01-20 | 8
BF Foundation |  | 2026-02-21 | 2026-06-04 | 2026-02-21 | 2026-06-04 | 2026-07-23 | 90 | 2026-11-04 | 131
BFW3000 | General Civil Work - Equipment Foundations & Pipe Support (TBC) | 2026-02-21 | 2026-06-04 | 2026-02-21 | 2026-06-04 | 2026-07-23 | 90 | 2026-11-04 | 131
GF Foundations |  | 2026-02-20 | 2026-06-25 | 03-Jul-25 A | 2026-06-25 | 2026-02-21 | 210 | 2026-08-22 | 48
FG/OG Compressor and Shleter Foundation including shelter concrete trench |  | 2026-02-20 | 2026-03-23 | 31-Jul-25 A | 2026-03-23 | 2026-02-21 | 129 | 2026-03-23 | 0
A15660 | Excavation | 2026-02-20 | 2026-02-20 | 31-Jul-25 A | 23-Aug-25 A | 2026-02-21 | 18 | 2026-02-21
A15670 | Surface leveling and compaction | 2026-02-20 | 2026-02-20 | 11-Aug-25 A | 25-Aug-25 A | 2026-02-21 | 18 | 2026-02-21
A15740 | Lean concrete | 2026-02-20 | 2026-02-20 | 25-Aug-25 A | 30-Aug-25 A | 2026-02-21 | 18 | 2026-02-21
A15750 | Water proofing and bitumen coating/sheet | 2026-02-21 | 2026-02-28 | 15-Oct-25 A | 2026-02-28 | 2026-02-21 | 18 | 2026-02-28 | 0
A15790 | Formworks | 2026-02-21 | 2026-02-28 | 19-Dec-25 A | 2026-02-28 | 2026-02-21 | 36 | 2026-02-28 | 0
A15840 | Rebar works | 2026-02-21 | 2026-02-28 | 15-Dec-25 A | 2026-02-28 | 2026-02-21 | 36 | 2026-02-28 | 0
A15860 | Concrete Curing | 2026-02-21 | 2026-03-04 | 27-Dec-25 A | 2026-03-04 | 2026-02-21 | 42 | 2026-03-04 | 0
A15850 | Concrete pouring | 2026-02-21 | 2026-03-09 | 19-Dec-25 A | 2026-03-09 | 2026-02-21 | 36 | 2026-03-09 | 0
A15870 | Formwork removal | 2026-02-21 | 2026-03-09 | 2026-02-21 | 2026-03-09 | 2026-02-21 | 15 | 2026-03-09 | 0
A15880 | Protective Coating | 2026-02-28 | 2026-03-16 | 2026-02-28 | 2026-03-16 | 2026-02-28 | 15 | 2026-03-16 | 0
A15890 | Back filling and compaction in layers | 2026-03-07 | 2026-03-23 | 2026-03-07 | 2026-03-23 | 2026-03-07 | 15 | 2026-03-23 | 0
Pipe Rack (Primary SR81 & Secondary SR80) Foundation |  | 2026-02-20 | 2026-04-09 | 23-Dec-25 A | 2026-04-09 | 2026-03-02 | 93 | 2026-04-19 | 8
A26240 | Excavation - Pipe Rack (SR81 & SR80) | 2026-02-20 | 2026-02-20 | 23-Dec-25 A | 20-Jan-26 A | 2026-03-02 | 24 | 2026-03-02
A26250 | Surface leveling and compaction | 2026-02-21 | 2026-02-26 | 30-Dec-25 A | 2026-02-26 | 2026-03-02 | 24 | 2026-03-08 | 8
A26260 | Lean concrete | 2026-02-21 | 2026-02-26 | 06-Jan-26 A | 2026-02-26 | 2026-03-02 | 24 | 2026-03-08 | 8
A26270 | Water proofing and bitumen coating/sheet | 2026-02-21 | 2026-03-05 | 13-Jan-26 A | 2026-03-05 | 2026-03-02 | 24 | 2026-03-15 | 8
A26280 | Formworks | 2026-02-21 | 2026-03-16 | 2026-02-21 | 2026-03-16 | 2026-03-02 | 21 | 2026-03-25 | 8
A26290 | Rebar works | 2026-02-21 | 2026-03-16 | 2026-02-21 | 2026-03-16 | 2026-03-02 | 21 | 2026-03-25 | 8
A26300 | Concrete Pouring | 2026-02-28 | 2026-03-23 | 2026-02-28 | 2026-03-23 | 2026-03-09 | 21 | 2026-04-01 | 8
A26310 | Concrete Curing | 2026-03-01 | 2026-03-24 | 2026-03-01 | 2026-03-24 | 2026-03-10 | 21 | 2026-04-02 | 8
A26320 | Formwork removal | 2026-03-03 | 2026-03-26 | 2026-03-03 | 2026-03-26 | 2026-03-12 | 21 | 2026-04-05 | 8
A26330 | Protective Coating | 2026-03-10 | 2026-04-02 | 2026-03-10 | 2026-04-02 | 2026-03-19 | 21 | 2026-04-12 | 8
A26340 | Back filling and compaction in layers | 2026-03-17 | 2026-04-09 | 2026-03-17 | 2026-04-09 | 2026-03-26 | 21 | 2026-04-19 | 8
OG Compressor Discharge Drip Leg (13-SP-7004) |  | 2026-03-28 | 2026-05-23 | 2026-03-28 | 2026-05-23 | 2026-05-03 | 49 | 2026-08-16 | 72
A24810 | Excavation | 2026-03-28 | 2026-03-31 | 2026-03-28 | 2026-03-31 | 2026-05-03 | 4 | 2026-05-06 | 31
A24820 | Surface leveling and compaction | 2026-04-01 | 2026-04-05 | 2026-04-01 | 2026-04-05 | 2026-06-24 | 4 | 2026-06-29 | 72
A24830 | Lean concrete | 2026-04-06 | 2026-04-09 | 2026-04-06 | 2026-04-09 | 2026-06-29 | 4 | 2026-07-04 | 72
A24840 | Water proofing and bitumen coating/sheet | 2026-04-11 | 2026-04-19 | 2026-04-11 | 2026-04-19 | 2026-07-04 | 8 | 2026-07-13 | 72
A24850 | Formworks | 2026-04-20 | 2026-04-27 | 2026-04-20 | 2026-04-27 | 2026-07-13 | 7 | 2026-07-21 | 72
A24860 | Rebar works | 2026-04-20 | 2026-04-27 | 2026-04-20 | 2026-04-27 | 2026-07-13 | 7 | 2026-07-21 | 72
A24870 | Concrete pouring | 2026-04-28 | 2026-05-02 | 2026-04-28 | 2026-05-02 | 2026-07-21 | 4 | 2026-07-26 | 72
A24890 | Formwork removal | 2026-04-30 | 2026-05-04 | 2026-04-30 | 2026-05-04 | 2026-07-23 | 4 | 2026-07-28 | 72
A24880 | Concrete Curing | 2026-04-28 | 2026-05-13 | 2026-04-28 | 2026-05-13 | 2026-07-21 | 14 | 2026-08-06 | 72
A24900 | Protective Coating | 2026-05-05 | 2026-05-13 | 2026-05-05 | 2026-05-13 | 2026-07-28 | 8 | 2026-08-06 | 72
A24910 | Back filling and compaction in layers | 2026-05-14 | 2026-05-23 | 2026-05-14 | 2026-05-23 | 2026-08-06 | 8 | 2026-08-16 | 72
PSA2 Package by Linde ( 10 Vessels) |  | 2026-02-20 | 2026-02-20 | 03-Jul-25 A | 20-Feb-26 A | 2026-05-24 | 151 | 2026-05-26
A24920 | Excavation | 2026-02-20 | 2026-02-20 | 03-Jul-25 A | 15-Jul-25 A | 2026-05-24 | 6 | 2026-05-24
A24930 | Surface leveling and compaction | 2026-02-20 | 2026-02-20 | 11-Jul-25 A | 25-Jul-25 A | 2026-05-24 | 12 | 2026-05-24
A24940 | Lean concrete | 2026-02-20 | 2026-02-20 | 01-Sep-25 A | 18-Sep-25 A | 2026-05-24 | 6 | 2026-05-24
A24950 | Water proofing and bitumen coating/sheet | 2026-02-20 | 2026-02-20 | 19-Sep-25 A | 26-Sep-25 A | 2026-05-24 | 6 | 2026-05-24
A24960 | Formworks | 2026-02-20 | 2026-02-20 | 27-Sep-25 A | 01-Feb-26 A | 2026-05-26 | 24 | 2026-05-26
A24980 | Concrete pouring | 2026-02-20 | 2026-02-20 | 04-Nov-25 A | 03-Feb-26 A | 2026-05-26 | 2 | 2026-05-26
A24970 | Rebar works | 2026-02-20 | 2026-02-20 | 22-Oct-25 A | 05-Feb-26 A | 2026-05-24 | 24 | 2026-05-24
A25000 | Formwork removal | 2026-02-20 | 2026-02-20 | 05-Feb-26 A | 05-Feb-26 A | 2026-05-26 | 10 | 2026-05-26
A25010 | Protective Coating | 2026-02-20 | 2026-02-20 | 01-Jan-26 A | 15-Feb-26 A | 2026-05-26 | 12 | 2026-05-26
A24990 | Concrete Curing | 2026-02-20 | 2026-02-20 | 19-Dec-25 A | 16-Feb-26 A | 2026-05-26 | 6 | 2026-05-26
A25020 | Back filling and compaction in layers | 2026-02-20 | 2026-02-20 | 01-Feb-26 A | 20-Feb-26 A | 2026-05-26 | 21 | 2026-05-26
OG Comp After Cooler ( 13-HE-709) |  | 2026-04-01 | 2026-05-16 | 2026-04-01 | 2026-05-16 | 2026-05-07 | 39 | 2026-08-08 | 71
A25030 | Excavation | 2026-04-01 | 2026-04-04 | 2026-04-01 | 2026-04-04 | 2026-05-07 | 3 | 2026-05-10 | 31
A25040 | Surface leveling and compaction | 2026-04-05 | 2026-04-06 | 2026-04-05 | 2026-04-06 | 2026-06-27 | 2 | 2026-06-29 | 71
A25050 | Lean concrete | 2026-04-07 | 2026-04-08 | 2026-04-07 | 2026-04-08 | 2026-06-29 | 2 | 2026-07-01 | 71
A25060 | Water proofing and bitumen coating/sheet | 2026-04-16 | 2026-04-18 | 2026-04-16 | 2026-04-18 | 2026-07-08 | 2 | 2026-07-11 | 71
A25070 | Formworks | 2026-04-19 | 2026-04-26 | 2026-04-19 | 2026-04-26 | 2026-07-11 | 7 | 2026-07-19 | 71
A25080 | Rebar works | 2026-04-19 | 2026-04-26 | 2026-04-19 | 2026-04-26 | 2026-07-12 | 7 | 2026-07-20 | 72
A25090 | Concrete pouring | 2026-04-27 | 2026-05-04 | 2026-04-27 | 2026-05-04 | 2026-07-19 | 7 | 2026-07-27 | 71
A25110 | Formwork removal | 2026-04-30 | 2026-05-07 | 2026-04-30 | 2026-05-07 | 2026-07-22 | 7 | 2026-07-30 | 71
A25120 | Protective Coating | 2026-05-05 | 2026-05-09 | 2026-05-05 | 2026-05-09 | 2026-07-27 | 4 | 2026-08-01 | 71
A25100 | Concrete Curing | 2026-04-28 | 2026-05-13 | 2026-04-28 | 2026-05-13 | 2026-07-20 | 14 | 2026-08-05 | 71
A25130 | Back filling and compaction in layers | 2026-05-10 | 2026-05-16 | 2026-05-10 | 2026-05-16 | 2026-08-01 | 6 | 2026-08-08 | 71
FG Comp 2nd Stage Discharge Drum(13-VV-707) |  | 2026-04-05 | 2026-06-02 | 2026-04-05 | 2026-06-02 | 2026-05-11 | 51 | 2026-07-23 | 44
A25140 | Excavation | 2026-04-05 | 2026-04-07 | 2026-04-05 | 2026-04-07 | 2026-05-11 | 3 | 2026-05-13 | 31
A25150 | Surface leveling and compaction | 2026-04-08 | 2026-04-09 | 2026-04-08 | 2026-04-09 | 2026-05-30 | 2 | 2026-05-31 | 44
A25160 | Lean concrete | 2026-04-11 | 2026-04-11 | 2026-04-11 | 2026-04-11 | 2026-06-01 | 1 | 2026-06-01 | 44
A25170 | Water proofing and bitumen coating/sheet | 2026-04-19 | 2026-04-22 | 2026-04-19 | 2026-04-22 | 2026-06-09 | 4 | 2026-06-13 | 44
A25180 | Formworks | 2026-04-23 | 2026-04-30 | 2026-04-23 | 2026-04-30 | 2026-06-14 | 7 | 2026-06-21 | 44
A25190 | Rebar works | 2026-04-23 | 2026-04-30 | 2026-04-23 | 2026-04-30 | 2026-06-14 | 7 | 2026-06-21 | 44
A25200 | Concrete pouring | 2026-05-07 | 2026-05-14 | 2026-05-07 | 2026-05-14 | 2026-06-28 | 7 | 2026-07-05 | 44
A25220 | Formwork removal | 2026-05-11 | 2026-05-18 | 2026-05-11 | 2026-05-18 | 2026-07-01 | 7 | 2026-07-08 | 44
A25210 | Concrete Curing | 2026-05-09 | 2026-05-24 | 2026-05-09 | 2026-05-24 | 2026-06-29 | 14 | 2026-07-14 | 44
A25230 | Protective Coating | 2026-05-19 | 2026-05-25 | 2026-05-19 | 2026-05-25 | 2026-07-09 | 6 | 2026-07-15 | 44
A25240 | Back filling and compaction in layers | 2026-05-26 | 2026-06-02 | 2026-05-26 | 2026-06-02 | 2026-07-16 | 7 | 2026-07-23 | 44
FG Comp 1st Stage Suction Drum(13-VV-705) |  | 2026-04-08 | 2026-06-07 | 2026-04-08 | 2026-06-07 | 2026-05-14 | 52 | 2026-08-01 | 47
A25360 | Excavation | 2026-04-08 | 2026-04-11 | 2026-04-08 | 2026-04-11 | 2026-05-14 | 3 | 2026-05-17 | 31
A25370 | Surface leveling and compaction | 2026-04-12 | 2026-04-13 | 2026-04-12 | 2026-04-13 | 2026-06-06 | 2 | 2026-06-07 | 47
A25380 | Lean concrete | 2026-04-14 | 2026-04-15 | 2026-04-14 | 2026-04-15 | 2026-06-08 | 2 | 2026-06-09 | 47
A25390 | Water proofing and bitumen coating/sheet | 2026-04-23 | 2026-04-27 | 2026-04-23 | 2026-04-27 | 2026-06-17 | 4 | 2026-06-21 | 47
A25400 | Formworks | 2026-04-28 | 2026-05-05 | 2026-04-28 | 2026-05-05 | 2026-06-22 | 7 | 2026-06-29 | 47
A25410 | Rebar works | 2026-04-28 | 2026-05-05 | 2026-04-28 | 2026-05-05 | 2026-06-22 | 7 | 2026-06-29 | 47
A25420 | Concrete pouring | 2026-05-12 | 2026-05-19 | 2026-05-12 | 2026-05-19 | 2026-07-06 | 7 | 2026-07-13 | 47
A25440 | Formwork removal | 2026-05-16 | 2026-05-23 | 2026-05-16 | 2026-05-23 | 2026-07-09 | 7 | 2026-07-16 | 47
A25430 | Concrete Curing | 2026-05-13 | 2026-05-28 | 2026-05-13 | 2026-05-28 | 2026-07-07 | 14 | 2026-07-22 | 47
A25450 | Protective Coating | 2026-05-24 | 2026-05-30 | 2026-05-24 | 2026-05-30 | 2026-07-18 | 6 | 2026-07-23 | 47
A25460 | Back filling and compaction in layers | 2026-05-31 | 2026-06-07 | 2026-05-31 | 2026-06-07 | 2026-07-25 | 7 | 2026-08-01 | 47
FG Comp 2nd Stage Suction Drum(13-VV-706) |  | 2026-04-12 | 2026-06-10 | 2026-04-12 | 2026-06-10 | 2026-05-18 | 52 | 2026-07-19 | 33
A25470 | Excavation | 2026-04-12 | 2026-04-14 | 2026-04-12 | 2026-04-14 | 2026-05-18 | 3 | 2026-05-20 | 31
A25480 | Surface leveling and compaction | 2026-04-15 | 2026-04-16 | 2026-04-15 | 2026-04-16 | 2026-05-24 | 2 | 2026-05-25 | 33
A25490 | Lean concrete | 2026-04-18 | 2026-04-19 | 2026-04-18 | 2026-04-19 | 2026-05-26 | 2 | 2026-05-27 | 33
A25500 | Water proofing and bitumen coating/sheet | 2026-04-27 | 2026-04-30 | 2026-04-27 | 2026-04-30 | 2026-06-04 | 4 | 2026-06-08 | 33
A25510 | Formworks | 2026-05-02 | 2026-05-09 | 2026-05-02 | 2026-05-09 | 2026-06-09 | 7 | 2026-06-16 | 33
A25520 | Rebar works | 2026-05-02 | 2026-05-09 | 2026-05-02 | 2026-05-09 | 2026-06-09 | 7 | 2026-06-16 | 33
A25530 | Concrete pouring | 2026-05-16 | 2026-05-23 | 2026-05-16 | 2026-05-23 | 2026-06-23 | 7 | 2026-06-30 | 33
A25550 | Formwork removal | 2026-05-19 | 2026-05-26 | 2026-05-19 | 2026-05-26 | 2026-06-27 | 7 | 2026-07-04 | 33
A25540 | Concrete Curing | 2026-05-17 | 2026-06-01 | 2026-05-17 | 2026-06-01 | 2026-06-24 | 14 | 2026-07-09 | 33
A25560 | Protective Coating | 2026-05-27 | 2026-06-02 | 2026-05-27 | 2026-06-02 | 2026-07-05 | 6 | 2026-07-11 | 33
A25570 | Back filling and compaction in layers | 2026-06-03 | 2026-06-10 | 2026-06-03 | 2026-06-10 | 2026-07-12 | 7 | 2026-07-19 | 33
PSA2 Slope Drum ( 70-VV-1415) |  | 2026-04-15 | 2026-06-07 | 2026-04-15 | 2026-06-07 | 2026-05-21 | 46 | 2026-08-22 | 64
A25580 | Excavation | 2026-04-15 | 2026-04-19 | 2026-04-15 | 2026-04-19 | 2026-05-21 | 4 | 2026-05-25 | 31
A25590 | Surface leveling and compaction | 2026-04-20 | 2026-04-23 | 2026-04-20 | 2026-04-23 | 2026-07-04 | 4 | 2026-07-08 | 64
A25600 | Lean concrete | 2026-04-25 | 2026-04-28 | 2026-04-25 | 2026-04-28 | 2026-07-08 | 4 | 2026-07-13 | 64
A25610 | Water proofing and bitumen coating/sheet | 2026-04-29 | 2026-05-06 | 2026-04-29 | 2026-05-06 | 2026-07-13 | 7 | 2026-07-21 | 64
A25620 | Formworks | 2026-05-07 | 2026-05-14 | 2026-05-07 | 2026-05-14 | 2026-07-21 | 7 | 2026-07-29 | 64
A25630 | Rebar works | 2026-05-07 | 2026-05-14 | 2026-05-07 | 2026-05-14 | 2026-07-21 | 7 | 2026-07-29 | 64
A25640 | Concrete pouring | 2026-05-16 | 2026-05-19 | 2026-05-16 | 2026-05-19 | 2026-07-29 | 4 | 2026-08-03 | 64
A25660 | Formwork removal | 2026-05-18 | 2026-05-21 | 2026-05-18 | 2026-05-21 | 2026-08-01 | 4 | 2026-08-05 | 64
A25670 | Protective Coating | 2026-05-23 | 2026-05-30 | 2026-05-23 | 2026-05-30 | 2026-08-05 | 7 | 2026-08-13 | 64
A25650 | Concrete Curing | 2026-05-16 | 2026-05-31 | 2026-05-16 | 2026-05-31 | 2026-07-29 | 14 | 2026-08-15 | 64
A25680 | Back filling and compaction in layers | 2026-05-31 | 2026-06-07 | 2026-05-31 | 2026-06-07 | 2026-08-13 | 7 | 2026-08-22 | 64
FG Comp After Cooler ( 13-HE-704) |  | 2026-04-20 | 2026-06-04 | 2026-04-20 | 2026-06-04 | 2026-05-26 | 40 | 2026-07-11 | 31
A25690 | Excavation | 2026-04-20 | 2026-04-22 | 2026-04-20 | 2026-04-22 | 2026-05-26 | 3 | 2026-05-28 | 31
A25700 | Surface leveling and compaction | 2026-04-23 | 2026-04-25 | 2026-04-23 | 2026-04-25 | 2026-05-30 | 2 | 2026-05-31 | 31
A25710 | Lean concrete | 2026-04-26 | 2026-04-27 | 2026-04-26 | 2026-04-27 | 2026-06-01 | 2 | 2026-06-02 | 31
A25720 | Water proofing and bitumen coating/sheet | 2026-05-05 | 2026-05-06 | 2026-05-05 | 2026-05-06 | 2026-06-10 | 2 | 2026-06-11 | 31
A25730 | Formworks | 2026-05-07 | 2026-05-14 | 2026-05-07 | 2026-05-14 | 2026-06-13 | 7 | 2026-06-20 | 31
A25740 | Rebar works | 2026-05-07 | 2026-05-14 | 2026-05-07 | 2026-05-14 | 2026-06-13 | 7 | 2026-06-20 | 31
A25750 | Concrete pouring | 2026-05-14 | 2026-05-21 | 2026-05-14 | 2026-05-21 | 2026-06-20 | 7 | 2026-06-27 | 31
A25770 | Formwork removal | 2026-05-18 | 2026-05-25 | 2026-05-18 | 2026-05-25 | 2026-06-23 | 7 | 2026-06-30 | 31
A25780 | Protective Coating | 2026-05-21 | 2026-05-30 | 2026-05-21 | 2026-05-30 | 2026-06-27 | 8 | 2026-07-05 | 31
A25760 | Concrete Curing | 2026-05-16 | 2026-05-31 | 2026-05-16 | 2026-05-31 | 2026-06-21 | 14 | 2026-07-06 | 31
A25790 | Back filling and compaction in layers | 2026-05-31 | 2026-06-04 | 2026-05-31 | 2026-06-04 | 2026-07-06 | 5 | 2026-07-11 | 31
FG Comp Interstage Cooler ( 13-HE-703) |  | 2026-04-23 | 2026-06-08 | 2026-04-23 | 2026-06-08 | 2026-06-09 | 40 | 2026-07-25 | 40
A26490 | Excavation | 2026-04-23 | 2026-04-26 | 2026-04-23 | 2026-04-26 | 2026-06-09 | 3 | 2026-06-11 | 40
A26500 | Surface leveling and compaction | 2026-04-27 | 2026-04-28 | 2026-04-27 | 2026-04-28 | 2026-06-13 | 2 | 2026-06-14 | 40
A26510 | Lean concrete | 2026-04-29 | 2026-04-30 | 2026-04-29 | 2026-04-30 | 2026-06-15 | 2 | 2026-06-16 | 40
A26520 | Water proofing and bitumen coating/sheet | 2026-05-09 | 2026-05-10 | 2026-05-09 | 2026-05-10 | 2026-06-24 | 2 | 2026-06-25 | 40
A26530 | Formworks | 2026-05-11 | 2026-05-18 | 2026-05-11 | 2026-05-18 | 2026-06-27 | 7 | 2026-07-04 | 40
A26540 | Rebar works | 2026-05-11 | 2026-05-18 | 2026-05-11 | 2026-05-18 | 2026-06-27 | 7 | 2026-07-04 | 40
A26550 | Concrete pouring | 2026-05-18 | 2026-05-25 | 2026-05-18 | 2026-05-25 | 2026-07-04 | 7 | 2026-07-11 | 40
A26570 | Formwork removal | 2026-05-21 | 2026-05-28 | 2026-05-21 | 2026-05-28 | 2026-07-08 | 7 | 2026-07-15 | 41
A26580 | Protective Coating | 2026-05-26 | 2026-06-02 | 2026-05-26 | 2026-06-02 | 2026-07-12 | 7 | 2026-07-19 | 40
A26560 | Concrete Curing | 2026-05-19 | 2026-06-03 | 2026-05-19 | 2026-06-03 | 2026-07-05 | 14 | 2026-07-20 | 40
A26590 | Back filling and compaction in layers | 2026-06-03 | 2026-06-08 | 2026-06-03 | 2026-06-08 | 2026-07-20 | 5 | 2026-07-25 | 40
OG Comp 2nd Stage Suction Drum(13-VV-713) |  | 2026-04-27 | 2026-06-25 | 2026-04-27 | 2026-06-25 | 2026-06-22 | 52 | 2026-08-22 | 48
A25800 | Excavation | 2026-04-27 | 2026-04-29 | 2026-04-27 | 2026-04-29 | 2026-06-22 | 3 | 2026-06-25 | 48
A25810 | Surface leveling and compaction | 2026-04-30 | 2026-05-02 | 2026-04-30 | 2026-05-02 | 2026-06-25 | 2 | 2026-06-28 | 48
A25820 | Lean concrete | 2026-05-03 | 2026-05-04 | 2026-05-03 | 2026-05-04 | 2026-06-28 | 2 | 2026-06-30 | 48
A25830 | Water proofing and bitumen coating/sheet | 2026-05-12 | 2026-05-16 | 2026-05-12 | 2026-05-16 | 2026-07-07 | 4 | 2026-07-12 | 48
A25840 | Formworks | 2026-05-17 | 2026-05-24 | 2026-05-17 | 2026-05-24 | 2026-07-12 | 7 | 2026-07-20 | 48
A25850 | Rebar works | 2026-05-17 | 2026-05-24 | 2026-05-17 | 2026-05-24 | 2026-07-12 | 7 | 2026-07-20 | 48
A25860 | Concrete pouring | 2026-05-31 | 2026-06-07 | 2026-05-31 | 2026-06-07 | 2026-07-26 | 7 | 2026-08-03 | 48
A25880 | Formwork removal | 2026-06-03 | 2026-06-10 | 2026-06-03 | 2026-06-10 | 2026-07-29 | 7 | 2026-08-06 | 48
A25870 | Concrete Curing | 2026-06-01 | 2026-06-16 | 2026-06-01 | 2026-06-16 | 2026-07-27 | 14 | 2026-08-12 | 48
A25890 | Protective Coating | 2026-06-11 | 2026-06-17 | 2026-06-11 | 2026-06-17 | 2026-08-06 | 6 | 2026-08-13 | 48
A25900 | Back filling and compaction in layers | 2026-06-18 | 2026-06-25 | 2026-06-18 | 2026-06-25 | 2026-08-13 | 7 | 2026-08-22 | 48
OG Buffer Drum (13-VV-712) |  | 2026-02-20 | 2026-04-16 | 31-Dec-25 A | 2026-04-16 | 2026-05-14 | 68 | 2026-08-22 | 109
A26020 | Excavation | 2026-02-20 | 2026-02-20 | 31-Dec-25 A | 15-Jan-26 A | 2026-05-14 | 3 | 2026-05-14
A26030 | Surface leveling and compaction | 2026-02-20 | 2026-02-20 | 10-Jan-26 A | 17-Jan-26 A | 2026-06-27 | 2 | 2026-06-27
A26040 | Lean concrete | 2026-02-20 | 2026-02-20 | 19-Jan-26 A | 21-Jan-26 A | 2026-06-27 | 2 | 2026-06-27
A26050 | Water proofing and bitumen coating/sheet | 2026-02-21 | 2026-02-24 | 22-Jan-26 A | 2026-02-24 | 2026-06-27 | 4 | 2026-07-01 | 109
A26060 | Formworks | 2026-02-24 | 2026-03-14 | 2026-02-24 | 2026-03-14 | 2026-07-01 | 15 | 2026-07-19 | 109
A26070 | Rebar works | 2026-02-24 | 2026-03-14 | 2026-02-24 | 2026-03-14 | 2026-07-01 | 15 | 2026-07-19 | 109
A26080 | Concrete pouring | 2026-03-14 | 2026-03-22 | 2026-03-14 | 2026-03-22 | 2026-07-19 | 7 | 2026-07-27 | 109
A26090 | Concrete Curing | 2026-03-14 | 2026-03-30 | 2026-03-14 | 2026-03-30 | 2026-07-19 | 14 | 2026-08-04 | 109
A26100 | Formwork removal | 2026-03-16 | 2026-04-01 | 2026-03-16 | 2026-04-01 | 2026-07-21 | 14 | 2026-08-06 | 109
A26110 | Protective Coating | 2026-04-01 | 2026-04-08 | 2026-04-01 | 2026-04-08 | 2026-08-06 | 6 | 2026-08-13 | 109
A26120 | Back filling and compaction in layers | 2026-04-08 | 2026-04-16 | 2026-04-08 | 2026-04-16 | 2026-08-13 | 7 | 2026-08-22 | 109
OG Compressor Interstage Cooler (13-HE-708) |  | 2026-02-20 | 2026-04-02 | 01-Jan-26 A | 2026-04-02 | 2026-03-29 | 40 | 2026-08-09 | 109
A26130 | Excavation | 2026-02-20 | 2026-02-20 | 01-Jan-26 A | 23-Jan-26 A | 2026-03-29 | 3 | 2026-03-29
A26140 | Surface leveling and compaction | 2026-02-21 | 2026-02-22 | 2026-02-21 | 2026-02-22 | 2026-03-29 | 2 | 2026-03-30 | 31
A26150 | Lean concrete | 2026-02-23 | 2026-02-24 | 2026-02-23 | 2026-02-24 | 2026-03-31 | 2 | 2026-04-01 | 31
A26160 | Water proofing and bitumen coating/sheet | 2026-03-04 | 2026-03-05 | 2026-03-04 | 2026-03-05 | 2026-04-09 | 2 | 2026-04-11 | 31
A26170 | Formworks | 2026-03-07 | 2026-03-23 | 2026-03-07 | 2026-03-23 | 2026-04-12 | 15 | 2026-04-28 | 31
A26180 | Rebar works | 2026-03-07 | 2026-03-23 | 2026-03-07 | 2026-03-23 | 2026-04-12 | 15 | 2026-04-28 | 31
A26190 | Concrete pouring | 2026-03-14 | 2026-03-26 | 2026-03-14 | 2026-03-26 | 2026-04-19 | 12 | 2026-05-02 | 31
A26220 | Protective Coating | 2026-03-22 | 2026-03-28 | 2026-03-22 | 2026-03-28 | 2026-07-27 | 6 | 2026-08-03 | 109
A26210 | Formwork removal | 2026-03-17 | 2026-03-30 | 2026-03-17 | 2026-03-30 | 2026-07-23 | 12 | 2026-08-06 | 110
A26230 | Back filling and compaction in layers | 2026-03-29 | 2026-04-01 | 2026-03-29 | 2026-04-01 | 2026-08-03 | 4 | 2026-08-08 | 109
A26200 | Concrete Curing | 2026-03-15 | 2026-04-02 | 2026-03-15 | 2026-04-02 | 2026-07-20 | 17 | 2026-08-09 | 109
Structural Steel and Shades |  | 2026-02-20 | 2026-09-26 | 09-Mar-25 A | 2026-09-26 | 2026-03-27 | 451 | 2027-01-06 | 88
TA Prefabrication of Steel Structure for BFW |  | 2026-02-20 | 2026-02-20 | 09-Mar-25 A | 18-May-25 A | 2026-03-27 | 24 | 2026-03-27
A61610 | TA prefabrication of steel structure for BFW | 2026-02-20 | 2026-02-20 | 09-Mar-25 A | 18-May-25 A | 2026-03-27 | 24 | 2026-03-27
TA Erection of Steel Structure for BFW |  | 2026-02-20 | 2026-02-20 | 19-Apr-25 A | 24-May-25 A | 2026-03-27 | 20 | 2026-03-27
A23330 | Erection of Steel Structure of BFW Preheater - Pre TA ( By external Subcontractor) | 2026-02-20 | 2026-02-20 | 19-Apr-25 A | 24-May-25 A | 2026-03-27 | 20 | 2026-03-27
BF Structure Steel |  | 2026-04-29 | 2026-06-14 | 2026-04-29 | 2026-06-14 | 2026-09-21 | 39 | 2026-11-04 | 124
BFW4020 | Structure Installation (Platform on the existing Piperack + strengthen) | 2026-04-29 | 2026-06-14 | 2026-04-29 | 2026-06-14 | 2026-09-21 | 39 | 2026-11-04 | 124
GF Steel Works |  | 2026-05-19 | 2026-09-26 | 2026-05-19 | 2026-09-26 | 2026-05-19 | 112 | 2027-01-06 | 88
A17820 | Pipe Rack SR81 - Structure Installation | 2026-06-28 | 2026-09-10 | 2026-06-28 | 2026-09-10 | 2026-06-28 | 65 | 2026-09-10 | 0
A17810 | Compressors Area- Steel Structure Erection | 2026-05-19 | 2026-09-10 | 2026-05-19 | 2026-09-10 | 2026-05-19 | 99 | 2026-09-10 | 0
A18420 | Secondary Pipe Rack (SR80) Structure installation | 2026-08-15 | 2026-09-10 | 2026-08-15 | 2026-09-10 | 2026-11-04 | 24 | 2026-12-01 | 70
A23500 | Piping Platforms | 2026-08-12 | 2026-09-10 | 2026-08-12 | 2026-09-10 | 2026-08-12 | 26 | 2026-09-10 | 0
A23510 | Transformer Shed - Sub Station Building | 2026-09-01 | 2026-09-26 | 2026-09-01 | 2026-09-26 | 2026-12-13 | 22 | 2027-01-06 | 88
External Finishes |  | 2026-07-18 | 2026-10-08 | 2026-07-18 | 2026-10-08 | 2026-10-29 | 72 | 2027-01-20 | 89
A61620 | External Finishing | 2026-07-18 | 2026-10-08 | 2026-07-18 | 2026-10-08 | 2026-10-29 | 72 | 2027-01-20 | 89
Internal Finishes |  | 2026-02-21 | 2026-10-21 | 2026-02-21 | 2026-10-21 | 2026-06-25 | 209 | 2027-01-20 | 78
GF SIS Building Architectural Works |  | 2026-02-21 | 2026-08-03 | 2026-02-21 | 2026-08-03 | 2026-07-07 | 141 | 2026-10-07 | 56
A1580 | PCC Flooring Works | 2026-02-21 | 2026-03-22 | 2026-02-21 | 2026-03-22 | 2026-07-14 | 26 | 2026-08-12 | 123
A1660 | Floor Finshes (Tiling, Skirting & Dado etc.) | 2026-03-23 | 2026-05-17 | 2026-03-23 | 2026-05-17 | 2026-08-13 | 48 | 2026-10-07 | 123
A1540 | Block Works and E&I Conduiting Works | 2026-05-03 | 2026-06-11 | 2026-05-03 | 2026-06-11 | 2026-07-07 | 35 | 2026-08-16 | 56
A1570 | Roof Treatments | 2026-05-17 | 2026-06-18 | 2026-05-17 | 2026-06-18 | 2026-09-05 | 29 | 2026-10-07 | 95
A1550 | Plaster Works | 2026-05-24 | 2026-07-16 | 2026-05-24 | 2026-07-16 | 2026-07-28 | 47 | 2026-09-20 | 56
A1560 | Painting Works | 2026-06-16 | 2026-08-03 | 2026-06-16 | 2026-08-03 | 2026-08-20 | 42 | 2026-10-07 | 56
GF Transformers Architectural Works |  | 2026-05-20 | 2026-10-21 | 2026-05-20 | 2026-10-21 | 2026-08-18 | 133 | 2027-01-20 | 78
A1260 | Installation of Fence and Doors | 2026-06-07 | 2026-07-01 | 2026-06-07 | 2026-07-01 | 2026-09-13 | 22 | 2026-10-07 | 84
A1240 | Painting External Works | 2026-05-20 | 2026-07-09 | 2026-05-20 | 2026-07-09 | 2026-08-18 | 44 | 2026-10-07 | 77
A1250 | Foundation for E&I Support Structure | 2026-06-07 | 2026-07-13 | 2026-06-07 | 2026-07-13 | 2026-09-01 | 32 | 2026-10-07 | 74
A1270 | Steel Structure / Corrugated Sheet Installation | 2026-09-24 | 2026-10-21 | 2026-09-24 | 2026-10-21 | 2026-12-24 | 24 | 2027-01-20 | 78
GF Sub-Station Architectural Works |  | 2026-03-28 | 2026-07-23 | 2026-03-28 | 2026-07-23 | 2026-06-25 | 102 | 2027-01-20 | 155
Ground Floor - Cellar Area |  | 2026-03-28 | 2026-06-17 | 2026-03-28 | 2026-06-17 | 2026-10-31 | 71 | 2027-01-20 | 186
A1630 | E&I Support Structure | 2026-03-28 | 2026-04-22 | 2026-03-28 | 2026-04-22 | 2026-10-31 | 23 | 2026-11-25 | 186
A1640 | Flooring works | 2026-04-23 | 2026-05-27 | 2026-04-23 | 2026-05-27 | 2026-11-26 | 30 | 2026-12-30 | 186
A1650 | Installation of Fence and Doors | 2026-05-28 | 2026-06-17 | 2026-05-28 | 2026-06-17 | 2026-12-31 | 18 | 2027-01-20 | 186
First Floor |  | 2026-04-11 | 2026-07-23 | 2026-04-11 | 2026-07-23 | 2026-06-25 | 90 | 2026-10-07 | 65
A26430 | Block Works and E&I Conduiting Works | 2026-04-11 | 2026-06-04 | 2026-04-11 | 2026-06-04 | 2026-06-25 | 48 | 2026-08-19 | 65
A1180 | PCC Flooring Works | 2026-05-16 | 2026-06-15 | 2026-05-16 | 2026-06-15 | 2026-08-09 | 27 | 2026-09-08 | 73
A1090 | Plaster Works | 2026-04-26 | 2026-06-20 | 2026-04-26 | 2026-06-20 | 2026-07-11 | 48 | 2026-09-03 | 65
A26440 | Roof Treatments | 2026-05-23 | 2026-06-30 | 2026-05-23 | 2026-06-30 | 2026-08-30 | 34 | 2026-10-07 | 85
A1200 | Floor Finshes (Tiling, Skirting & Dado etc.) | 2026-06-16 | 2026-07-14 | 2026-06-16 | 2026-07-14 | 2026-09-09 | 25 | 2026-10-07 | 73
A26450 | Painting Works (Release for Electrical Equipments) | 2026-06-04 | 2026-07-23 | 2026-06-04 | 2026-07-23 | 2026-08-19 | 43 | 2026-10-07 | 65
Others |  | 2026-02-20 | 2026-02-20 | 09-Jan-25 A | 20-Jun-25 A | 2026-02-21 | 231 | 2026-03-02
Topographic |  | 2026-02-20 | 2026-02-20 | 09-Jan-25 A | 23-May-25 A | 2026-02-21 | 71 | 2026-02-21
Topographic/UG Survey |  | 2026-02-20 | 2026-02-20 | 09-Jan-25 A | 22-May-25 A | 2026-02-21 | 71 | 2026-02-21
A56190 | TBE for Topo,UG & Getechnical Survey_IFR | 2026-02-20 | 2026-02-20 | 09-Jan-25 A | 15-Jan-25 A | 2026-02-21 | 5 | 2026-02-21
A56200 | TBE for Topo,UG & Getechnical Survey_RCC | 2026-02-20 | 2026-02-20 | 16-Jan-25 A | 10-Feb-25 A | 2026-02-21 | 13 | 2026-02-21
A28960 | TBE for Topo,UG & Getechnical Survey_IFD/IFC | 2026-02-20 | 2026-02-20 | 11-Feb-25 A | 01-Mar-25 A | 2026-02-21 | 5 | 2026-02-21
E1080 | TBE & PO issuance of Geotech / UG Scanning | 2026-02-20 | 2026-02-20 | 02-Mar-25 A | 20-Mar-25 A | 2026-02-21 | 6 | 2026-02-21
E1110 | CICPA Passes for Geotech Sub Contractor | 2026-02-20 | 2026-02-20 | 21-Mar-25 A | 17-Apr-25 A | 2026-02-21 | 8 | 2026-02-21
E1070 | Topo/ UG Scanning Survey | 2026-02-20 | 2026-02-20 | 18-Apr-25 A | 30-Apr-25 A | 2026-02-21 | 4 | 2026-02-21
E1090 | Mobilization of Geotech / UG Scanning | 2026-02-20 | 2026-02-20 | 01-May-25 A | 08-May-25 A | 2026-02-21 | 4 | 2026-02-21
E1060 | Geotech / Survery of Site | 2026-02-20 | 2026-02-20 | 09-May-25 A | 15-May-25 A | 2026-02-21 | 4 | 2026-02-21
E1100 | Reports of Getech Investigation / UG Scanning | 2026-02-20 | 2026-02-20 | 16-May-25 A | 22-May-25 A | 2026-02-21 | 4 | 2026-02-21
Geotech/ Topographic/UG Survey |  | 2026-02-20 | 2026-02-20 | 11-Feb-25 A | 23-May-25 A | 2026-02-21 | 60 | 2026-02-21
E1000 | RFQ of Geotech / UG Scanning | 2026-02-20 | 2026-02-20 | 11-Feb-25 A | 01-Mar-25 A | 2026-02-21 | 4 | 2026-02-21
E1010 | TBE & PO issuance of Geotech / UG Scanning | 2026-02-20 | 2026-02-20 | 02-Mar-25 A | 20-Mar-25 A | 2026-02-21 | 6 | 2026-02-21
E1050 | CICPA Passes for Geotech Sub Contractor | 2026-02-20 | 2026-02-20 | 21-Mar-25 A | 17-Apr-25 A | 2026-02-21 | 12 | 2026-02-21
E1020 | Mobilization of Geotech / UG Scanning | 2026-02-20 | 2026-02-20 | 01-May-25 A | 08-May-25 A | 2026-02-21 | 4 | 2026-02-21
E1030 | Geotech / Survery of Site | 2026-02-20 | 2026-02-20 | 10-May-25 A | 16-May-25 A | 2026-02-21 | 8 | 2026-02-21
E1040 | Reports of Getech Investigation / UG Scanning | 2026-02-20 | 2026-02-20 | 17-May-25 A | 23-May-25 A | 2026-02-21 | 8 | 2026-02-21
Piling (No required) |  | 2026-02-20 | 2026-02-20 | 20-Jun-25 A | 20-Jun-25 A | 2026-02-21 | 196 | 2026-03-02
Piling Works |  | 2026-02-20 | 2026-02-20 | 20-Jun-25 A | 20-Jun-25 A | 2026-02-21 | 196 | 2026-03-02
A15550 | Piling Work (Compressors, Sheds & Equipment) | 2026-02-20 | 2026-02-20 | 20-Jun-25 A | 20-Jun-25 A | 2026-02-21 | 69 | 2026-02-21
A15570 | Piling Works - Pipe Racks and OG Buffer Drum | 2026-02-20 | 2026-02-20 | 20-Jun-25 A | 20-Jun-25 A | 2026-03-02 | 28 | 2026-03-02
A15610 | Piling work PSA2 Unit (10 Vessels) | 2026-02-20 | 2026-02-20 | 20-Jun-25 A | 20-Jun-25 A | 2026-03-02 | 22 | 2026-03-02
A15650 | Test Piles (including curing time) | 2026-02-20 | 2026-02-20 | 20-Jun-25 A | 20-Jun-25 A | 2026-02-21 | 23 | 2026-02-21
A15690 | Data for Test pile |  |  |  | 20-Jun-25 A |  | 0
A15720 | PO for Piling Contractor | 2026-02-20 | 2026-02-20 | 20-Jun-25 A | 20-Jun-25 A | 2026-02-21 | 12 | 2026-02-21
A15730 | Mobilization of piling contractor | 2026-02-20 | 2026-02-20 | 20-Jun-25 A | 20-Jun-25 A | 2026-02-21 | 16 | 2026-02-21
A23610 | Mobilization for Production Piles | 2026-02-20 | 2026-02-20 | 20-Jun-25 A | 20-Jun-25 A | 2026-02-21 | 12 | 2026-02-21
Mechanical Construction |  | 2026-02-20 | 2027-01-17 | 05-Mar-25 A | 2027-01-17 | 2026-03-24 | 509 | 2027-07-20 | 132
Equipment erection and installation |  | 2026-02-20 | 2026-12-01 | 19-Apr-25 A | 2026-12-01 | 2026-03-24 | 354 | 2027-01-20 | 36
HVAC Works |  | 2026-07-12 | 2026-09-29 | 2026-07-12 | 2026-09-29 | 2026-11-02 | 69 | 2027-01-20 | 97
A18570 | Fabrication and installation of ductwork inside the building | 2026-07-12 | 2026-08-10 | 2026-07-12 | 2026-08-10 | 2026-11-02 | 26 | 2026-12-01 | 97
A18770 | Installation of piping inside and outside the building | 2026-07-12 | 2026-08-10 | 2026-07-12 | 2026-08-10 | 2026-11-02 | 26 | 2026-12-01 | 97
A18580 | Fabrication and installation of ductwork outside the building | 2026-07-16 | 2026-08-15 | 2026-07-16 | 2026-08-15 | 2026-11-17 | 26 | 2026-12-16 | 106
A18760 | Installation of electrical works inside the building (excluding installation of HVAC power control panel) | 2026-07-19 | 2026-08-17 | 2026-07-19 | 2026-08-17 | 2026-11-18 | 26 | 2026-12-17 | 105
A18780 | Pressure testing of pipes | 2026-08-11 | 2026-08-24 | 2026-08-11 | 2026-08-24 | 2026-12-02 | 12 | 2026-12-15 | 97
A18790 | Flushing, cleaning, air blowing of Piping | 2026-08-18 | 2026-08-31 | 2026-08-18 | 2026-08-31 | 2026-12-09 | 12 | 2026-12-22 | 97
A18590 | Insulation of ductwork outside the building | 2026-07-30 | 2026-09-02 | 2026-07-30 | 2026-09-02 | 2026-12-01 | 30 | 2027-01-04 | 106
A18820 | Assembly of Air Handling Unit (AHU) | 2026-09-01 | 2026-09-06 | 2026-09-01 | 2026-09-06 | 2026-12-23 | 5 | 2026-12-28 | 97
A18890 | Insulation of refrigerant pipework outside the building | 2026-08-20 | 2026-09-06 | 2026-08-20 | 2026-09-06 | 2026-12-19 | 15 | 2027-01-04 | 103
A18830 | Installation and alignment of air handling units (AHU) | 2026-09-07 | 2026-09-13 | 2026-09-07 | 2026-09-13 | 2026-12-29 | 6 | 2027-01-04 | 97
A18840 | Installation of Exhaust Fan | 2026-09-07 | 2026-09-13 | 2026-09-07 | 2026-09-13 | 2027-01-05 | 6 | 2027-01-11 | 103
A18860 | Installation and alignment of refrigerant cycle and chiller | 2026-09-07 | 2026-09-13 | 2026-09-07 | 2026-09-13 | 2026-12-29 | 6 | 2027-01-04 | 97
A18870 | Installation of buffer tank | 2026-09-07 | 2026-09-13 | 2026-09-07 | 2026-09-13 | 2026-12-29 | 6 | 2027-01-04 | 97
A18910 | Installation of electrical / power system and HVAC control system | 2026-08-27 | 2026-09-13 | 2026-08-27 | 2026-09-13 | 2026-12-19 | 15 | 2027-01-04 | 97
A18850 | Complete Duct Connection to AHU & Fan | 2026-09-08 | 2026-09-19 | 2026-09-08 | 2026-09-19 | 2027-01-05 | 10 | 2027-01-16 | 102
A18920 | HVAC Testing and Commissioning works | 2026-09-14 | 2026-09-29 | 2026-09-14 | 2026-09-29 | 2027-01-05 | 14 | 2027-01-20 | 97
GF Sanitary Water Sump Pump (01 No) (70-PC-1409) |  | 2026-07-04 | 2026-08-18 | 2026-07-04 | 2026-08-18 | 2026-10-26 | 40 | 2026-12-10 | 99
A22600 | Installation of Sanitary Water Sump Pump (70-PC-1409) | 2026-07-04 | 2026-07-16 | 2026-07-04 | 2026-07-16 | 2026-10-26 | 12 | 2026-11-09 | 99
A22830 | Alignment of Sanitary Water Sump Pump (70-PC-1409) | 2026-07-18 | 2026-08-06 | 2026-07-18 | 2026-08-06 | 2026-11-09 | 18 | 2026-11-30 | 99
A22840 | Grouting of Sanitary Water Sump Pump (70-PC-1409) | 2026-08-08 | 2026-08-18 | 2026-08-08 | 2026-08-18 | 2026-11-30 | 10 | 2026-12-10 | 99
GF Feed Gas Compressor and Auxilary Equipment Errection |  | 2026-03-24 | 2026-12-01 | 2026-03-24 | 2026-12-01 | 2026-03-24 | 217 | 2026-12-01 | 0
FG Comp 1st Stage Suction Drum(13-VV-705) |  | 2026-06-22 | 2026-08-16 | 2026-06-22 | 2026-08-16 | 2026-08-16 | 48 | 2026-10-10 | 47
A22480 | Delivery inspection, Unpacked and Installation of FG Comp 1st Stage Suction Drum(13-VV-705) | 2026-06-22 | 2026-06-29 | 2026-06-22 | 2026-06-29 | 2026-08-16 | 7 | 2026-08-23 | 47
A23020 | Alignment of FG Comp 1st Stage Suction Drum(13-VV-705) | 2026-06-30 | 2026-07-07 | 2026-06-30 | 2026-07-07 | 2026-08-24 | 7 | 2026-08-31 | 47
A23030 | Grouting of FG Comp 1st Stage Suction Drum(13-VV-705) | 2026-07-08 | 2026-07-13 | 2026-07-08 | 2026-07-13 | 2026-09-01 | 5 | 2026-09-06 | 47
A23080 | Internals (Demister) of FG Comp 1st Stage Suction Drum(13-VV-705) | 2026-07-14 | 2026-07-30 | 2026-07-14 | 2026-07-30 | 2026-09-07 | 15 | 2026-09-23 | 47
A23230 | Insulation of FG Comp 1st Stage Suction Drum(13-VV-705) | 2026-08-01 | 2026-08-16 | 2026-08-01 | 2026-08-16 | 2026-09-24 | 14 | 2026-10-10 | 47
FG Compressor Interstage Cooler (13-HE-703) |  | 2026-06-09 | 2026-08-06 | 2026-06-09 | 2026-08-06 | 2026-07-26 | 51 | 2026-09-22 | 40
A23600 | Intallation of FG Compressor Interstage Cooler (13-HE-703) | 2026-06-09 | 2026-06-20 | 2026-06-09 | 2026-06-20 | 2026-07-26 | 10 | 2026-08-05 | 40
A23910 | Alignment of FG Compressor Interstage Cooler (13-HE-703) | 2026-06-21 | 2026-07-01 | 2026-06-21 | 2026-07-01 | 2026-08-06 | 10 | 2026-08-17 | 40
A23920 | Grouting of FG Compressor Interstage Cooler (13-HE-703) | 2026-07-02 | 2026-07-13 | 2026-07-02 | 2026-07-13 | 2026-08-18 | 10 | 2026-08-29 | 40
A23980 | Insulation of FG Compressor Interstage Cooler (13-HE-703) | 2026-07-14 | 2026-08-06 | 2026-07-14 | 2026-08-06 | 2026-08-30 | 21 | 2026-09-22 | 40
FG Comp After Cooler ( 13-HE-704) |  | 2026-06-20 | 2026-08-17 | 2026-06-20 | 2026-08-17 | 2026-07-26 | 51 | 2026-09-22 | 31
A22540 | Installation of FG Comp After Cooler ( 13-HE-704) | 2026-06-20 | 2026-06-30 | 2026-06-20 | 2026-06-30 | 2026-07-26 | 10 | 2026-08-05 | 31
A23240 | Alignment of FG Comp After Cooler ( 13-HE-704) | 2026-07-01 | 2026-07-12 | 2026-07-01 | 2026-07-12 | 2026-08-06 | 10 | 2026-08-17 | 31
A23250 | Grouting of FG Comp After Cooler ( 13-HE-704) | 2026-07-13 | 2026-07-23 | 2026-07-13 | 2026-07-23 | 2026-08-18 | 10 | 2026-08-29 | 31
A23370 | Insulation of FG Comp After Cooler ( 13-HE-704) | 2026-07-25 | 2026-08-17 | 2026-07-25 | 2026-08-17 | 2026-08-30 | 21 | 2026-09-22 | 31
FG Comp 2nd Stage Discharge Drum(13-VV-707) |  | 2026-07-14 | 2026-08-29 | 2026-07-14 | 2026-08-29 | 2026-08-08 | 40 | 2026-09-22 | 21
A22530 | Installation of FG Comp 2nd Stage Discharge Drum (13-VV-707) | 2026-07-14 | 2026-07-19 | 2026-07-14 | 2026-07-19 | 2026-08-08 | 5 | 2026-08-12 | 21
A23380 | Alignment of FG Comp 2nd Stage Discharge Drum (13-VV-707) | 2026-07-20 | 2026-07-25 | 2026-07-20 | 2026-07-25 | 2026-08-13 | 5 | 2026-08-18 | 21
A23390 | Grouting of FG Comp 2nd Stage Discharge Drum (13-VV-707) | 2026-07-26 | 2026-07-30 | 2026-07-26 | 2026-07-30 | 2026-08-19 | 5 | 2026-08-24 | 21
A23400 | Internals (Demister Pad) of FG Comp 2nd Stage Discharge Drum (13-VV-707) | 2026-08-01 | 2026-08-11 | 2026-08-01 | 2026-08-11 | 2026-08-25 | 10 | 2026-09-05 | 21
A23410 | Insulation of FG Comp 2nd Stage Discharge Drum (13-VV-707) | 2026-08-12 | 2026-08-29 | 2026-08-12 | 2026-08-29 | 2026-09-06 | 15 | 2026-09-22 | 21
FG Comp 2nd Stage Suction Drum(13-VV-706) |  | 2026-06-25 | 2026-08-15 | 2026-06-25 | 2026-08-15 | 2026-08-03 | 44 | 2026-09-22 | 33
A22490 | Delivery inspection, Unpacked and Installation of FG Comp 2nd Stage Suction Drum (13-VV-706) | 2026-06-25 | 2026-07-06 | 2026-06-25 | 2026-07-06 | 2026-08-03 | 10 | 2026-08-13 | 33
A23420 | Alignment of FG Comp 2nd Stage Suction Drum (13-VV-706) | 2026-07-07 | 2026-07-12 | 2026-07-07 | 2026-07-12 | 2026-08-15 | 5 | 2026-08-19 | 33
A23430 | Grouting of FG Comp 2nd Stage Suction Drum (13-VV-706) | 2026-07-13 | 2026-07-18 | 2026-07-13 | 2026-07-18 | 2026-08-20 | 5 | 2026-08-25 | 33
A23440 | Internals (Demister Pad) of FG Comp 2nd Stage Suction Drum (13-VV-706) | 2026-07-19 | 2026-07-29 | 2026-07-19 | 2026-07-29 | 2026-08-26 | 10 | 2026-09-06 | 33
A23450 | Insulation of FG Comp 2nd Stage Suction Drum (13-VV-706) | 2026-07-30 | 2026-08-15 | 2026-07-30 | 2026-08-15 | 2026-09-07 | 14 | 2026-09-22 | 33
Feed Gas (FG) Compressor Installation |  | 2026-03-24 | 2026-12-01 | 2026-03-24 | 2026-12-01 | 2026-03-24 | 217 | 2026-12-01 | 0
C1000 | FG Foundation Plan - Foundation Check & Dimensional Examination - FG Compressor | 2026-03-24 | 2026-04-09 | 2026-03-24 | 2026-04-09 | 2026-03-24 | 15 | 2026-04-09 | 0
C1002 | Setting of FG Compressor Base Plate (Temporary settng, Elevation, Level, Tolerance, Position) | 2026-04-11 | 2026-05-04 | 2026-04-11 | 2026-05-04 | 2026-04-11 | 21 | 2026-05-04 | 0
C1001 | Installation of FG Compressor (Setting of Pad, Preparation, Position and Leveling) | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 12 | 2026-05-18 | 0
C1031 | Installation of FG Compressor Main Driver Motor | 2026-05-19 | 2026-05-30 | 2026-05-19 | 2026-05-30 | 2026-07-02 | 10 | 2026-07-13 | 38
C1004 | Pre-alignment of FG Compressor | 2026-05-30 | 2026-06-16 | 2026-05-30 | 2026-06-16 | 2026-07-14 | 15 | 2026-07-30 | 38
C1003 | Grouting - FG Compressor | 2026-06-16 | 2026-06-28 | 2026-06-16 | 2026-06-28 | 2026-08-01 | 10 | 2026-08-11 | 38
C1005 | Coupling Alignment - FG Compressor | 2026-06-28 | 2026-07-21 | 2026-06-28 | 2026-07-21 | 2026-08-19 | 20 | 2026-09-10 | 44
C1006 | Installation of Auxiliary Equipment - FG Compressor |  | 2026-09-15 |  | 2026-09-15 |  | 0 | 2026-10-10 | 21
C1007 | Installation of Piping - FG Compressor | 2026-09-12 | 2026-11-02 | 2026-09-12 | 2026-11-02 | 2026-09-12 | 45 | 2026-11-02 | 0
C1008 | E&I Installation - FG Compressor | 2026-10-05 | 2026-11-19 | 2026-10-05 | 2026-11-19 | 2026-10-05 | 40 | 2026-11-19 | 0
C1009 | Punch List Close Out FG Compressor | 2026-11-21 | 2026-12-01 | 2026-11-21 | 2026-12-01 | 2026-11-21 | 10 | 2026-12-01 | 0
GF Off Gas Compressor and Auxilary Equipment Errection |  | 2026-03-24 | 2026-11-23 | 2026-03-24 | 2026-11-23 | 2026-06-04 | 210 | 2026-12-10 | 15
Off Gas (OG) Compressor Installation |  | 2026-03-24 | 2026-11-23 | 2026-03-24 | 2026-11-23 | 2026-06-04 | 210 | 2026-12-01 | 7
C1069 | OG Foundation Plan - Foundation Check & Dimensional Examination | 2026-03-24 | 2026-04-09 | 2026-03-24 | 2026-04-09 | 2026-06-04 | 15 | 2026-06-22 | 62
C1089 | Setting of OG Compressor Base Plate (Temporary setting, Elevation, Level, Tolerance, Position) | 2026-04-11 | 2026-05-04 | 2026-04-11 | 2026-05-04 | 2026-06-22 | 21 | 2026-07-16 | 62
C1079 | Installation of OG Compressor (Setting of Pad, Preparation, Position and Leveling) | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-07-16 | 12 | 2026-07-30 | 62
C1169 | Installation of OG Compressor Main Driver Motor | 2026-05-19 | 2026-05-27 | 2026-05-19 | 2026-05-27 | 2026-07-30 | 8 | 2026-08-09 | 62
C1109 | Pre-alignment of OG Compressor | 2026-05-28 | 2026-06-14 | 2026-05-28 | 2026-06-14 | 2026-08-09 | 15 | 2026-08-26 | 62
C1099 | Grouting - OG Compressor | 2026-06-15 | 2026-06-25 | 2026-06-15 | 2026-06-25 | 2026-08-26 | 10 | 2026-09-07 | 62
C1119 | Coupling and Alignment - OG Compressor | 2026-06-27 | 2026-07-19 | 2026-06-27 | 2026-07-19 | 2026-09-07 | 20 | 2026-09-30 | 62
C1129 | Installation of Auxiliary Equipment - OG Compressor |  | 2026-08-29 |  | 2026-08-29 |  | 0 | 2026-10-06 | 32
C1139 | Installation of Piping - OG Compressor | 2026-09-22 | 2026-11-01 | 2026-09-22 | 2026-11-01 | 2026-09-30 | 35 | 2026-11-10 | 7
C1149 | E&I Installation - OG Compressor | 2026-09-28 | 2026-11-08 | 2026-09-28 | 2026-11-08 | 2026-10-07 | 35 | 2026-11-16 | 7
C1159 | Punch List Close Out (Mechanical) - OG Compressor | 2026-11-08 | 2026-11-23 | 2026-11-08 | 2026-11-23 | 2026-11-17 | 13 | 2026-12-01 | 7
OG Buffer Drum (13-VV-712) |  | 2026-06-13 | 2026-08-30 | 2026-06-13 | 2026-08-30 | 2026-09-30 | 68 | 2026-12-10 | 88
A25270 | Ground Preparatory Works for Crane | 2026-06-13 | 2026-06-25 | 2026-06-13 | 2026-06-25 | 2026-09-30 | 12 | 2026-10-13 | 94
A22500 | Installation of OG Buffer Drum (13-VV-712) | 2026-07-04 | 2026-07-09 | 2026-07-04 | 2026-07-09 | 2026-10-14 | 6 | 2026-10-20 | 88
A22790 | Alignment of OG Buffer Drum (13-VV-712) | 2026-07-11 | 2026-07-16 | 2026-07-11 | 2026-07-16 | 2026-10-28 | 6 | 2026-11-03 | 94
A22800 | Grouting of OG Buffer Drum (13-VV-712) | 2026-07-18 | 2026-07-23 | 2026-07-18 | 2026-07-23 | 2026-11-04 | 6 | 2026-11-10 | 94
A25280 | Scafolding Works | 2026-07-11 | 2026-07-30 | 2026-07-11 | 2026-07-30 | 2026-10-21 | 18 | 2026-11-10 | 88
A22810 | Internals (Demister) of OG Buffer Drum (13-VV-712) | 2026-08-01 | 2026-08-13 | 2026-08-01 | 2026-08-13 | 2026-11-11 | 12 | 2026-11-24 | 88
A22820 | Insulation of OG Buffer Drum (13-VV-712) | 2026-08-15 | 2026-08-30 | 2026-08-15 | 2026-08-30 | 2026-11-25 | 14 | 2026-12-10 | 88
OG Compressor Interstage Cooler (13-HE-708) |  | 2026-04-22 | 2026-06-07 | 2026-04-22 | 2026-06-07 | 2026-08-22 | 39 | 2026-10-06 | 104
A22570 | Intallation of OG Compressor Interstage Cooler (13-HE-708) | 2026-04-22 | 2026-04-27 | 2026-04-22 | 2026-04-27 | 2026-08-22 | 4 | 2026-08-26 | 104
A23460 | Alignment of OG Compressor Interstage Cooler (13-HE-708) | 2026-04-27 | 2026-05-03 | 2026-04-27 | 2026-05-03 | 2026-08-26 | 5 | 2026-09-01 | 104
A23470 | Grouting of OG Compressor Interstage Cooler (13-HE-708) | 2026-05-03 | 2026-05-14 | 2026-05-03 | 2026-05-14 | 2026-09-01 | 10 | 2026-09-13 | 104
A23480 | Insulation of OG Compressor Interstage Cooler (13-HE-708) | 2026-05-14 | 2026-06-07 | 2026-05-14 | 2026-06-07 | 2026-09-13 | 20 | 2026-10-06 | 104
OG Comp After Cooler ( 13-HE-709) |  | 2026-06-27 | 2026-08-10 | 2026-06-27 | 2026-08-10 | 2026-08-22 | 39 | 2026-10-06 | 48
A22550 | Installation of OG Comp After Cooler ( 13-HE-709) | 2026-06-27 | 2026-07-01 | 2026-06-27 | 2026-07-01 | 2026-08-22 | 5 | 2026-08-27 | 48
A23490 | Alignment of OG Comp After Cooler ( 13-HE-709) | 2026-07-02 | 2026-07-06 | 2026-07-02 | 2026-07-06 | 2026-08-27 | 4 | 2026-09-01 | 48
A23930 | Grouting of OG Comp After Cooler ( 13-HE-709) | 2026-07-07 | 2026-07-18 | 2026-07-07 | 2026-07-18 | 2026-09-01 | 10 | 2026-09-13 | 48
A23990 | Insulation of OG Comp After Cooler ( 13-HE-709) | 2026-07-19 | 2026-08-10 | 2026-07-19 | 2026-08-10 | 2026-09-13 | 20 | 2026-10-06 | 48
OG Compressor Discharge Drip Leg (13-SP-7004) |  | 2026-07-23 | 2026-08-29 | 2026-07-23 | 2026-08-29 | 2026-08-30 | 32 | 2026-10-06 | 32
A3490 | Installation of OG Compressor Discharge Drip Leg | 2026-07-23 | 2026-07-27 | 2026-07-23 | 2026-07-27 | 2026-08-30 | 4 | 2026-09-03 | 32
A3500 | Alignment of OG Compressor Discharge Drip Leg | 2026-07-28 | 2026-08-01 | 2026-07-28 | 2026-08-01 | 2026-09-03 | 4 | 2026-09-08 | 32
A3510 | Grouting of OG Compressor Discharge Drip Leg | 2026-08-02 | 2026-08-05 | 2026-08-02 | 2026-08-05 | 2026-09-08 | 4 | 2026-09-13 | 32
A3520 | Internals of OG Compressor Discharge Drip Leg | 2026-08-06 | 2026-08-17 | 2026-08-06 | 2026-08-17 | 2026-09-13 | 10 | 2026-09-24 | 32
A3530 | Insulation of OG Compressor Discharge Drip Leg | 2026-08-18 | 2026-08-29 | 2026-08-18 | 2026-08-29 | 2026-09-24 | 10 | 2026-10-06 | 32
OG Comp 2nd Stage Suction Drum(13-VV-713) |  | 2026-06-21 | 2026-08-05 | 2026-06-21 | 2026-08-05 | 2026-08-20 | 40 | 2026-10-06 | 52
A22510 | Installation of OG Comp 2nd Stage Suction Drum (13-VV-713) | 2026-06-21 | 2026-06-25 | 2026-06-21 | 2026-06-25 | 2026-08-20 | 5 | 2026-08-26 | 52
A24000 | Alignment of OG Comp 2nd Stage Suction Drum (13-VV-713) | 2026-06-27 | 2026-07-01 | 2026-06-27 | 2026-07-01 | 2026-08-26 | 5 | 2026-09-01 | 52
A24010 | Grouting of OG Comp 2nd Stage Suction Drum (13-VV-713) | 2026-07-02 | 2026-07-07 | 2026-07-02 | 2026-07-07 | 2026-09-01 | 5 | 2026-09-07 | 52
A25250 | Internals (Demster Pad) of OG Comp 2nd Stage Suction Drum (13-VV-713) | 2026-07-08 | 2026-07-19 | 2026-07-08 | 2026-07-19 | 2026-09-07 | 10 | 2026-09-19 | 52
A25260 | Insulation of OG Comp 2nd Stage Suction Drum (13-VV-713) | 2026-07-20 | 2026-08-05 | 2026-07-20 | 2026-08-05 | 2026-09-19 | 15 | 2026-10-06 | 52
TA Boiler Feed Water Installation |  | 2026-02-20 | 2026-02-20 | 19-Apr-25 A | 24-May-25 A | 2026-03-27 | 3 | 2026-03-27
A3787 | Installation of BFW Preheater | 2026-02-20 | 2026-02-20 | 19-Apr-25 A | 24-May-25 A | 2026-03-27 | 3 | 2026-03-27
BF Mechanical Equipments |  | 2026-06-14 | 2026-07-30 | 2026-06-14 | 2026-07-30 | 2026-11-05 | 40 | 2027-01-03 | 135
A9650 | Installation of Dripleg (1 No) | 2026-06-14 | 2026-07-30 | 2026-06-14 | 2026-07-30 | 2026-11-05 | 40 | 2026-12-21 | 124
A9660 | Installation of Coalescer (1 No) | 2026-06-14 | 2026-07-30 | 2026-06-14 | 2026-07-30 | 2026-11-18 | 40 | 2027-01-03 | 135
A22560 | Installation of C4 Guard Regeneration Cooler (50-HE-1410) | 2026-06-14 | 2026-07-30 | 2026-06-14 | 2026-07-30 | 2026-11-05 | 40 | 2026-12-21 | 124
GF PSA2 Package by Linde ( 10 Vessels) |  | 2026-03-22 | 2026-10-20 | 2026-03-22 | 2026-10-20 | 2026-05-26 | 183 | 2026-12-10 | 44
A22610 | Installation of PSA2 Package by Linde ( 10 Vessels) | 2026-03-22 | 2026-05-30 | 2026-03-22 | 2026-05-30 | 2026-05-26 | 60 | 2026-08-03 | 56
A22850 | Alignment of PSA2 Package by Linde ( 10 Vessels) | 2026-05-31 | 2026-07-21 | 2026-05-31 | 2026-07-21 | 2026-08-04 | 45 | 2026-09-24 | 56
A22860 | Grouting of PSA2 Package by Linde ( 10 Vessels) | 2026-06-24 | 2026-08-15 | 2026-06-24 | 2026-08-15 | 2026-08-29 | 45 | 2026-10-19 | 56
A22870 | Internals of PSA2 Package by Linde ( 10 Vessels) | 2026-08-30 | 2026-10-20 | 2026-08-30 | 2026-10-20 | 2026-10-20 | 45 | 2026-12-10 | 44
GF Water Sump Pump (02 Nos) (70-PC-1407) |  | 2026-06-17 | 2026-08-02 | 2026-06-17 | 2026-08-02 | 2026-10-26 | 40 | 2026-12-10 | 112
A22590 | Installation of Water Sump Pump (70-PC-1407) | 2026-06-17 | 2026-06-30 | 2026-06-17 | 2026-06-30 | 2026-10-26 | 12 | 2026-11-08 | 112
A22880 | Alignment of Water Sump Pump (70-PC-1407) | 2026-07-01 | 2026-07-21 | 2026-07-01 | 2026-07-21 | 2026-11-09 | 18 | 2026-11-29 | 112
A22890 | Grouting of Water Sump Pump (70-PC-1407) | 2026-07-22 | 2026-08-02 | 2026-07-22 | 2026-08-02 | 2026-11-30 | 10 | 2026-12-10 | 112
GF PSA2 Slope Drum ( 70-VV-1415) |  | 2026-07-20 | 2026-08-30 | 2026-07-20 | 2026-08-30 | 2026-10-31 | 36 | 2026-12-10 | 88
A22520 | Installation of PSA2 Slope Drum ( 70-VV-1415) | 2026-07-20 | 2026-07-25 | 2026-07-20 | 2026-07-25 | 2026-10-31 | 5 | 2026-11-04 | 88
A22930 | Alignment of PSA2 Slope Drum ( 70-VV-1415) | 2026-07-26 | 2026-07-30 | 2026-07-26 | 2026-07-30 | 2026-11-05 | 5 | 2026-11-10 | 88
A22960 | Grouting of PSA2 Slope Drum ( 70-VV-1415) | 2026-08-01 | 2026-08-05 | 2026-08-01 | 2026-08-05 | 2026-11-11 | 5 | 2026-11-16 | 88
A22990 | Internals of PSA2 Slope Drum ( 70-VV-1415) | 2026-08-06 | 2026-08-17 | 2026-08-06 | 2026-08-17 | 2026-11-17 | 10 | 2026-11-28 | 88
A23010 | Insulation of PSA2 Slope Drum ( 70-VV-1415) | 2026-08-18 | 2026-08-30 | 2026-08-18 | 2026-08-30 | 2026-11-29 | 11 | 2026-12-10 | 88
GF EOT Crane for FG Compressor |  | 2026-09-12 | 2026-10-12 | 2026-09-12 | 2026-10-12 | 2026-10-15 | 27 | 2026-11-19 | 33
C1339 | Installation of electrical equipment | 2026-09-12 | 2026-09-15 | 2026-09-12 | 2026-09-15 | 2026-10-27 | 4 | 2026-10-31 | 39
C1319 | LT rail line installation | 2026-09-12 | 2026-09-22 | 2026-09-12 | 2026-09-22 | 2026-10-15 | 10 | 2026-10-26 | 29
C1329 | Assembly of main girders at ground level | 2026-09-12 | 2026-09-22 | 2026-09-12 | 2026-09-22 | 2026-10-20 | 10 | 2026-10-31 | 33
C1349 | Installation of end carriage & main girder | 2026-09-23 | 2026-09-27 | 2026-09-23 | 2026-09-27 | 2026-11-01 | 4 | 2026-11-04 | 33
C1359 | Crab erection | 2026-09-28 | 2026-09-30 | 2026-09-28 | 2026-09-30 | 2026-11-05 | 3 | 2026-11-08 | 33
C1369 | Installation of the platform, hand railing, cabin, ladder, DSL cage and DSL guard | 2026-10-01 | 2026-10-12 | 2026-10-01 | 2026-10-12 | 2026-11-09 | 10 | 2026-11-19 | 33
GF EOT Crane for OG Compressor |  | 2026-09-19 | 2026-10-13 | 2026-09-19 | 2026-10-13 | 2026-10-22 | 22 | 2026-11-16 | 29
C1309 | Installation of electrical equipment | 2026-09-19 | 2026-09-22 | 2026-09-19 | 2026-09-22 | 2026-10-29 | 4 | 2026-11-02 | 35
C1259 | LT rail line installation | 2026-09-19 | 2026-09-29 | 2026-09-19 | 2026-09-29 | 2026-10-22 | 10 | 2026-11-02 | 29
C1269 | Assembly of main girders at ground level | 2026-09-19 | 2026-09-29 | 2026-09-19 | 2026-09-29 | 2026-10-22 | 10 | 2026-11-02 | 29
C1279 | Installation of end carriage & main girder | 2026-09-30 | 2026-10-04 | 2026-09-30 | 2026-10-04 | 2026-11-03 | 4 | 2026-11-07 | 29
C1289 | Cran erection | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | 2026-11-08 | 2 | 2026-11-09 | 29
C1299 | Installation of the platform, hand railing, cabin, ladder, DSL cage and DSL guard | 2026-10-05 | 2026-10-13 | 2026-10-05 | 2026-10-13 | 2026-11-08 | 8 | 2026-11-16 | 29
Piping Fabrication |  | 2026-02-20 | 2026-02-20 | 05-Mar-25 A | 18-Apr-25 A | 2026-03-27 | 138 | 2026-03-27
TA Piping Work |  | 2026-02-20 | 2026-02-20 | 05-Mar-25 A | 18-Apr-25 A | 2026-03-27 | 138 | 2026-03-27
BFW4000 | Prefabrication of Tie-ins Spools | 2026-02-20 | 2026-02-20 | 28-Mar-25 A | 04-Apr-25 A | 2026-03-27 | 36 | 2026-03-27
A17730 | Installation of Scaffolding | 2026-02-20 | 2026-02-20 | 05-Mar-25 A | 08-Apr-25 A | 2026-03-27 | 24 | 2026-03-27
BFW4050 | Sand blastinfg and painting | 2026-02-20 | 2026-02-20 | 01-Apr-25 A | 15-Apr-25 A | 2026-03-27 | 45 | 2026-03-27
BFW4010 | Prefabrication of Piping Spools for the BFW | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 18-Apr-25 A | 2026-03-27 | 36 | 2026-03-27
Piping and Valves Installation |  | 2026-02-20 | 2027-01-17 | 29-Mar-25 A | 2027-01-17 | 2026-03-27 | 461 | 2027-03-11 | 39
BF Piping Works |  | 2026-02-21 | 2026-10-27 | 2026-02-21 | 2026-10-27 | 2026-03-29 | 214 | 2026-12-02 | 31
A18520 | Scaffolding for Piping errection on Piperack | 2026-02-21 | 2026-03-31 | 2026-02-21 | 2026-03-31 | 2026-03-29 | 34 | 2026-05-06 | 31
A9670 | Piping Erection / Installation in Brown Field | 2026-04-01 | 2026-08-18 | 2026-04-01 | 2026-08-18 | 2026-05-07 | 120 | 2026-09-23 | 31
BFW4030 | Piping Hydrotesting - BF | 2026-08-08 | 2026-09-22 | 2026-08-08 | 2026-09-22 | 2026-09-13 | 40 | 2026-10-28 | 31
BFW4040 | Piping connections with tie-ins | 2026-09-10 | 2026-10-27 | 2026-09-10 | 2026-10-27 | 2026-10-17 | 41 | 2026-12-02 | 31
TA Tie-In Execution - A/G Tie-Ins |  | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 24-May-25 A | 2026-03-27 | 127 | 2026-03-27
Package 1 |  | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 24-May-25 A | 2026-03-27 | 125 | 2026-03-27
Tailgas from Tie In point EU3 to EU3 H2 Tag # IP-B-B3-H3-L-2010 |  | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 24-May-25 A | 2026-03-27 | 88 | 2026-03-27
A9730 | Full welding of joints & installation of Tie-In spool 45076 | 2026-02-20 | 2026-02-20 | 25-Apr-25 A | 26-Apr-25 A | 2026-03-27 | 0 | 2026-03-27
A9740 | Inspection NDT / RT of selected joints | 2026-02-20 | 2026-02-20 | 25-Apr-25 A | 26-Apr-25 A | 2026-03-27 | 0 | 2026-03-27
A38420 | Install pipe supports (if any) | 2026-02-20 | 2026-02-20 | 25-Apr-25 A | 26-Apr-25 A | 2026-03-27 | 0 | 2026-03-27
A38430 | Prepare and hydrotest up to XX BarG (if required) | 2026-02-20 | 2026-02-20 | 25-Apr-25 A | 26-Apr-25 A | 2026-03-27 | 0 | 2026-03-27
A38440 | Hydrotest witness inspection (if required) | 2026-02-20 | 2026-02-20 | 25-Apr-25 A | 26-Apr-25 A | 2026-03-27 | 0 | 2026-03-27
A9780 | Reinstall back piping components (TW/TE, TG, PT, PG if any) | 2026-02-20 | 2026-02-20 | 25-Apr-25 A | 26-Apr-25 A | 2026-03-27 | 0 | 2026-03-27
A9790 | Touch-up painting works | 2026-02-20 | 2026-02-20 | 25-Apr-25 A | 15-May-25 A | 2026-03-27 | 0 | 2026-03-27
A9800 | Deblinding, remove temporary support / scaffolds | 2026-02-20 | 2026-02-20 | 25-Apr-25 A | 15-May-25 A | 2026-03-27 | 0 | 2026-03-27
A9810 | Reinstall insulation (if any) | 2026-02-20 | 2026-02-20 | 25-Apr-25 A | 15-May-25 A | 2026-03-27 | 0 | 2026-03-27
A9820 | Torquing / flange management & hand-over to Ops | 2026-02-20 | 2026-02-20 | 25-Apr-25 A | 15-May-25 A | 2026-03-27 | 0 | 2026-03-27
A9830 | End of Work | 2026-02-20 | 2026-02-20 | 16-May-25 A | 17-May-25 A | 2026-03-27 | 1 | 2026-03-27
A38390 | Start of Work | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 24-May-25 A | 2026-03-27 | 1 | 2026-03-27
A9680 | Obtain Work Permit | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 24-May-25 A | 2026-03-27 | 0 | 2026-03-27
A38400 | Removal of insulation & Wallthickness measurement | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 24-May-25 A | 2026-03-27 | 0 | 2026-03-27
A38410 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 24-May-25 A | 2026-03-27 | 0 | 2026-03-27
A9710 | Cut old piping (existing line 45024), haul to ground level | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 24-May-25 A | 2026-03-27 | 0 | 2026-03-27
A9720 | Grinding, bevelling of old piping & fit-up with new spool | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 24-May-25 A | 2026-03-27 | 0 | 2026-03-27
Tailgas Tag # IP-B-B3-M3-L-3010 |  | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 24-May-25 A | 2026-03-27 | 88 | 2026-03-27
A38340 | Full welding of joints & installation of Tie-In spool 45024 | 2026-02-20 | 2026-02-20 | 25-Apr-25 A | 26-Apr-25 A | 2026-03-27 | 0 | 2026-03-27
A38350 | Inspection NDT / RT of selected joints | 2026-02-20 | 2026-02-20 | 25-Apr-25 A | 26-Apr-25 A | 2026-03-27 | 0 | 2026-03-27
A38360 | Install pipe supports (if any) | 2026-02-20 | 2026-02-20 | 25-Apr-25 A | 26-Apr-25 A | 2026-03-27 | 0 | 2026-03-27
A9590 | Prepare and hydrotest up to XX BarG (if required) | 2026-02-20 | 2026-02-20 | 25-Apr-25 A | 26-Apr-25 A | 2026-03-27 | 0 | 2026-03-27
A9600 | Hydrotest witness inspection (if required) | 2026-02-20 | 2026-02-20 | 25-Apr-25 A | 26-Apr-25 A | 2026-03-27 | 0 | 2026-03-27
A9610 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 2026-02-20 | 2026-02-20 | 25-Apr-25 A | 26-Apr-25 A | 2026-03-27 | 0 | 2026-03-27
A9620 | Touch-up painting works | 2026-02-20 | 2026-02-20 | 25-Apr-25 A | 15-May-25 A | 2026-03-27 | 0 | 2026-03-27
A9630 | Deblinding, remove temporary support / scaffolds | 2026-02-20 | 2026-02-20 | 25-Apr-25 A | 15-May-25 A | 2026-03-27 | 0 | 2026-03-27
A9640 | Reinstall insulation (if any) | 2026-02-20 | 2026-02-20 | 25-Apr-25 A | 15-May-25 A | 2026-03-27 | 0 | 2026-03-27
A38370 | Torquing / flange management & hand-over to Ops | 2026-02-20 | 2026-02-20 | 25-Apr-25 A | 15-May-25 A | 2026-03-27 | 0 | 2026-03-27
A38380 | End of Work | 2026-02-20 | 2026-02-20 | 16-May-25 A | 17-May-25 A | 2026-03-27 | 1 | 2026-03-27
A38280 | Start of Work | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 24-May-25 A | 2026-03-27 | 1 | 2026-03-27
A38290 | Obtain Work Permit | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 24-May-25 A | 2026-03-27 | 0 | 2026-03-27
A38300 | Removal of insulation & Wallthickness measurement | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 24-May-25 A | 2026-03-27 | 0 | 2026-03-27
A38310 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 24-May-25 A | 2026-03-27 | 0 | 2026-03-27
A38320 | Cut old piping (existing line 45024), haul to ground level | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 24-May-25 A | 2026-03-27 | 0 | 2026-03-27
A38330 | Grinding, bevelling of old piping & fit-up with new spool | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 24-May-25 A | 2026-03-27 | 0 | 2026-03-27
Tailgas Tag # IP-B-M3-B3-L-3020 |  | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 17-May-25 A | 2026-03-27 | 88 | 2026-03-27
A9330 | Start of Work | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 11-Apr-25 A | 2026-03-27 | 1 | 2026-03-27
A9340 | Obtain Work Permit | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 11-Apr-25 A | 2026-03-27 | 0 | 2026-03-27
A9350 | Removal of insulation & Wallthickness measurement | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 11-Apr-25 A | 2026-03-27 | 0 | 2026-03-27
A9360 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 11-Apr-25 A | 2026-03-27 | 0 | 2026-03-27
A9370 | Cut old piping (existing line 45024), haul to ground level | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 11-Apr-25 A | 2026-03-27 | 0 | 2026-03-27
A9380 | Grinding, bevelling of old piping & fit-up with new spool | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 11-Apr-25 A | 2026-03-27 | 0 | 2026-03-27
A9390 | Full welding of joints & installation of Tie-In spool 45024 | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 11-Apr-25 A | 2026-03-27 | 0 | 2026-03-27
A9400 | Inspection NDT / RT of selected joints | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 11-Apr-25 A | 2026-03-27 | 0 | 2026-03-27
A9410 | Install pipe supports (if any) | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 11-Apr-25 A | 2026-03-27 | 0 | 2026-03-27
A9420 | Prepare and hydrotest up to XX BarG (if required) | 2026-02-20 | 2026-02-20 | 16-May-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A9430 | Hydrotest witness inspection (if required) | 2026-02-20 | 2026-02-20 | 16-May-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A9440 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 2026-02-20 | 2026-02-20 | 16-May-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A38270 | Touch-up painting works | 2026-02-20 | 2026-02-20 | 16-May-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A9460 | Deblinding, remove temporary support / scaffolds | 2026-02-20 | 2026-02-20 | 16-May-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A9470 | Reinstall insulation (if any) | 2026-02-20 | 2026-02-20 | 16-May-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A9480 | Torquing / flange management & hand-over to Ops | 2026-02-20 | 2026-02-20 | 16-May-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A9490 | End of Work | 2026-02-20 | 2026-02-20 | 16-May-25 A | 17-May-25 A | 2026-03-27 | 1 | 2026-03-27
Tailgas Tag # IP-B-B3-M3-L-3030 |  | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 17-May-25 A | 2026-03-27 | 88 | 2026-03-27
A9160 | Start of Work | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 17-May-25 A | 2026-03-27 | 1 | 2026-03-27
A9170 | Obtain Work Permit | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A9180 | Removal of insulation & Wall thickness measurement | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A9190 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A38230 | Cut old piping (existing line 45024), haul to ground level | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A38240 | Grinding, bevelling of old piping & fit-up with new spool | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A38250 | Full welding of joints & installation of Tie-In spool 45075 | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A9230 | Inspection NDT / RT of selected joints | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A9240 | Install pipe supports (if any) | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A9250 | Prepare and hydrotest up to XX BarG | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A9260 | Hydrotest witness inspection | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A38260 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A9280 | Touch-up painting works | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A9290 | Deblinding, remove temporary support / scaffolds | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A9300 | Reinstall insulation (if any) | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A9310 | Torquing / flange management & hand-over to Ops | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A9320 | End of Work | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 17-May-25 A | 2026-03-27 | 1 | 2026-03-27
Tailgas Tag # IP-B-B3-M3-L-3050 |  | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 17-May-25 A | 2026-03-27 | 86 | 2026-03-27
A8990 | Start of Work | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 17-May-25 A | 2026-03-27 | 1 | 2026-03-27
A9000 | Obtain Work Permit | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A9010 | Removal of existing valve | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A9020 | Installation of new valve | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A9030 | Gas measurement | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A9120 | Deblinding, remove temporary support / scaffolds | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A9130 | Reinstall insulation (if any) | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A9140 | Torquing / flange management & hand-over to Ops | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A9150 | End of Work | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 17-May-25 A | 2026-03-27 | 1 | 2026-03-27
Regeneration gas from 50-HE-1402 Tag # IP-B-B3-M3-L-3090 |  | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 17-May-25 A | 2026-03-27 | 88 | 2026-03-27
A8820 | Start of Work | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A8830 | Obtain Work Permit | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A8840 | Wallthickness measurement | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A8850 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A8860 | Cut old piping (existing line 140025), haul to ground level | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A8870 | Grinding, bevelling of old piping & fit-up with new spool | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A8880 | Full welding of joints & installation of Tie-In spool 140068 | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A8890 | Inspection NDT / RT of selected joints | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A8900 | Install pipe supports (if any) | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A8910 | Prepare and hydrotest up to XX BarG | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A8920 | Hydrotest witness inspection | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A8930 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A8940 | Touch-up painting works | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A8950 | Deblinding, remove temporary support / scaffolds | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A8960 | Reinstall insulation (if any) | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A8970 | Torquing / flange management & hand-over to Ops | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A8980 | End of Work | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
Tailgas from 13-KX-402 Tag # IP-B-B3-M3-L-3100 |  | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 17-May-25 A | 2026-03-27 | 88 | 2026-03-27
A8650 | Start of Work | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 17-May-25 A | 2026-03-27 | 1 | 2026-03-27
A8660 | Obtain Work Permit | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A8670 | Removal of insulation & Wallthickness measurement | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A8680 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A8690 | Cut old piping (existing line 45024), haul to ground level | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A8700 | Grinding, bevelling of old piping & fit-up with new spool | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A8710 | Full welding of joints & installation of Tie-In spool 45024 | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A8720 | Inspection NDT / RT of selected joints | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A8730 | Install pipe supports (if any) | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A8740 | Prepare and hydrotest up to XX BarG (if required) | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A8750 | Hydrotest witness inspection (if required) | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A8760 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A8770 | Touch-up painting works | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A8780 | Deblinding, remove temporary support / scaffolds | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A38220 | Reinstall insulation (if any) | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A8800 | Torquing / flange management & hand-over to Ops | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A8810 | End of Work | 2026-02-20 | 2026-02-20 | 11-Apr-25 A | 17-May-25 A | 2026-03-27 | 1 | 2026-03-27
Cooling Water from EU3 Tie In Point to 50-HE-1410 Tag # IP-B-B3-M3-L-3120 |  | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 88 | 2026-03-27
A8480 | Start of Work | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A38210 | Obtain Work Permit | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A8500 | Wallthickness measurement | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A8510 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A8520 | Cut old piping (existing line 140036) , haul to ground level | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A8530 | Grinding, bevelling of old piping & fit-up with new spool | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A8540 | Full welding of joints & installation of Tie-In spool 140033 | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A8550 | Inspection NDT / RT of selected joints | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A8560 | Install pipe supports (if any) | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A8570 | Prepare and hydrotest up to XX BarG (if required) | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A8580 | Hydrotest witness inspection (if required) | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A8590 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A8600 | Touch-up painting works | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A8610 | Deblinding, remove temporary support / scaffolds | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A8620 | Reinstall insulation (if any) | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A8630 | Torquing / flange management & hand-over to Ops | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A8640 | End of Work | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
Regeneration Gas C4 Hydrogenation from 13-VA-804A/B Tag # IP-B-B3-M3-L-3170 |  | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 88 | 2026-03-27
A38150 | Start of Work | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 1 | 2026-03-27
A38160 | Obtain Work Permit | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A38170 | Removal of insulation & Wallthickness measurement | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A38180 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A8350 | Cut old piping (existing line 41022), haul to ground level | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A8360 | Grinding, bevelling of old piping & fit-up with new spool | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A38190 | Full welding of joints & installation of Tie-In spool 81142 | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A8380 | Inspection NDT / RT of selected joints | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A8390 | Install pipe supports (if any) | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A8400 | Prepare and hydrotest up to XX BarG (if required) | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A8410 | Hydrotest witness inspection (if required) | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A8420 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A38200 | Touch-up painting works | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A8440 | Deblinding, remove temporary support / scaffolds | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A8450 | Reinstall insulation (if any) | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A8460 | Torquing / flange management & hand-over to Ops | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A8470 | End of Work | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 1 | 2026-03-27
Tailgas line bleed Tag # IP-B-B3-M3-L-3180 |  | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 88 | 2026-03-27
A38110 | Start of Work | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 1 | 2026-03-27
A38120 | Obtain Work Permit | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A38130 | Removal of insulation & Wallthickness measurement | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A8170 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A8180 | Cut old piping (existing line 45024), haul to ground level | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A8190 | Grinding, bevelling of old piping & fit-up with new spool | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A8200 | Full welding of joints & installation of Tie-In spool 45024 | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A8210 | Inspection NDT / RT of selected joints | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A8220 | Install pipe supports (if any) | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A8230 | Prepare and hydrotest up to XX BarG (if required) | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A8240 | Hydrotest witness inspection (if required) | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A38140 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A8260 | Touch-up painting works | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A8270 | Deblinding, remove temporary support / scaffolds | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A8280 | Reinstall insulation (if any) | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A8290 | Torquing / flange management & hand-over to Ops | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A8300 | End of Work | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 1 | 2026-03-27
Treated VHP BFW Preheater 52-HE-1402 bypass valve Tag # IP-B-B3-M3-L-3190 |  | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 88 | 2026-03-27
A7970 | Start of Work | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 1 | 2026-03-27
A7980 | Obtain Work Permit | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7990 | Removal of insulation & Wallthickness measurement | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A8000 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A8010 | Cut old piping (existing line 140025), haul to ground level | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A8020 | Grinding, bevelling & fit-up of valve with new spool | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A8030 | Welding of gate valve & installation of Tie-In spool 140025 | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A8040 | Inspection NDT / RT of selected joints | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A8050 | Install pipe supports (if any) | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A8060 | Prepare and hydrotest up to XX BarG (if required) | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A8070 | Hydrotest witness inspection (if required) | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A8080 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A8090 | Touch-up painting works | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A8100 | Deblinding, remove temporary support / scaffolds | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A8110 | Reinstall insulation (if any) | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A8120 | Torquing / flange management & hand-over to Ops | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A38100 | End of Work | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 1 | 2026-03-27
Treated VHP BFW from EU3 to 52-HE-1402 Tag # IP-B-B3-M3-L-3210 |  | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 88 | 2026-03-27
A7800 | Start of Work | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 1 | 2026-03-27
A7810 | Obtain Work Permit | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7820 | Removal of insulation & Wallthickness measurement | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7830 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7840 | Cut old piping (existing line 140025), haul to ground level | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7850 | Grinding, bevelling of old piping & fit-up with new spool | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7860 | Full welding of joints & installation of Tie-In spool 140219 | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7870 | Inspection NDT / RT of selected joints | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7880 | Install pipe supports (if any) | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7890 | Prepare and hydrotest up to XX BarG | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7900 | Hydrotest witness inspection | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7910 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7920 | Touch-up painting works | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7930 | Deblinding, remove temporary support / scaffolds | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7940 | Reinstall insulation (if any) | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7950 | Torquing / flange management & hand-over to Ops | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7960 | End of Work | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 1 | 2026-03-27
LP- Steam from EU3 Tie In Point to 52-HE-1402 Tag # IP-B-B3-M3-L-3230 |  | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 88 | 2026-03-27
A7630 | Start of Work | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 1 | 2026-03-27
A7640 | Obtain Work Permit | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7650 | Removal of insulation & Wallthickness measurement | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7660 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7670 | Cut old piping (existing line 140472), haul to ground level | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7680 | Grinding, bevelling of old piping & fit-up with new spool | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7690 | Welding of weldolet and installation of Tie-In spool 140489 | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7700 | Inspection NDT / RT of selected joints | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7710 | Install pipe supports (if any) | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7720 | Prepare and hydrotest up to XX BarG Iif required) | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7730 | Hydrotest witness inspection Iif required) | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7740 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7750 | Touch-up painting works | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7760 | Deblinding, remove temporary support / scaffolds | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7770 | Reinstall insulation (if any) | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7780 | Torquing / flange management & hand-over to Ops | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7790 | End of Work | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 1 | 2026-03-27
Package 2 |  | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 20-May-25 A | 2026-03-27 | 127 | 2026-03-27
Regeneration Gas from 50-HE-1402 Tag # IP-B-B3-M3-L-3260 |  | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 88 | 2026-03-27
A7460 | Start of Work | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7470 | Obtain Work Permit | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7480 | Wallthickness measurement | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7490 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7500 | Cut old piping (existing line 140025), haul to ground level | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7510 | Grinding, bevelling of old piping & fit-up with new spool | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7520 | Full welding of joints & installation of Tie-In spool 140025 | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7530 | Inspection NDT / RT of selected joints | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7540 | Install pipe supports (if any) | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7550 | Prepare and hydrotest up to XX BarG (if required) | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7560 | Hydrotest witness inspection (if required) | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7570 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7580 | Touch-up painting works | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7590 | Deblinding, remove temporary support / scaffolds | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7600 | Reinstall insulation (if any) | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7610 | Torquing / flange management & hand-over to Ops | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7620 | End of Work | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
Nitrogen from EU3 to 64PSV14001 Tag # IP-B-B3-M3-L-3380 |  | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 88 | 2026-03-27
A7290 | Start of Work | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7300 | Obtain Work Permit | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7310 | Wallthickness measurement | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7320 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7330 | Cut old piping (existing line 140148) , haul to ground level | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7340 | Grinding, bevelling of old piping & fit-up with new spool | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7350 | Full welding of joints & installation of Tie-In spool 140038 | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7360 | Inspection NDT / RT of selected joints | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7370 | Install pipe supports (if any) | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7380 | Prepare and hydrotest up to XX BarG | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7390 | Hydrotest witness inspection | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7400 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7410 | Touch-up painting works | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7420 | Deblinding, remove temporary support / scaffolds | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7430 | Reinstall insulation (if any) | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7440 | Torquing / flange management & hand-over to Ops | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7450 | End of Work | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
Regeneration Gas C4 Hydrogenation Tag # IP-B-B3-M3-L-3390 |  | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 88 | 2026-03-27
A7120 | Start of Work | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7130 | Obtain Work Permit | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7140 | Removal of insulation & Wallthickness measurement | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7150 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7160 | Cut old piping (existing line 81142), haul to ground level | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7170 | Grinding, bevelling of old piping & fit-up with new spool | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7180 | Full welding of joints & installation of Tie-In spool 81184 | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7190 | Inspection NDT / RT of selected joints & Additional Testing of Tie-in Valve | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7200 | Install pipe supports (if any) | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7210 | Prepare and hydrotest up to XX BarG (if required) | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7220 | Hydrotest witness inspection (if required) | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7230 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7240 | Touch-up painting works | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7250 | Deblinding, remove temporary support / scaffolds | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7260 | Reinstall insulation (if any) | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7270 | Torquing / flange management & hand-over to Ops | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7280 | End of Work | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
50AT-14101A sample tap Tag # IP-B-B3-M3-L-3430 |  | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 88 | 2026-03-27
A6950 | Start of Work | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 1 | 2026-03-27
A6960 | Obtain Work Permit | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6970 | Removal of insulation & Wallthickness measurement | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6980 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6990 | Cut old piping & support, haul to ground level | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7000 | Grinding, bevelling of old piping & fit-up with new spool | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7010 | Full welding of joints including weldolet & installation of Tie-In spool | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7020 | Inspection NDT / RT of selected joints | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7030 | Install pipe supports (if any) | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7040 | Prepare and hydrotest up to XX BarG (if required) | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7050 | Hydrotest witness inspection (if required) | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7060 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7070 | Touch-up painting works | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7080 | Deblinding, remove temporary support / scaffolds | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7090 | Reinstall insulation (if any) | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7100 | Torquing / flange management & hand-over to Ops | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 0 | 2026-03-27
A7110 | End of Work | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 20-May-25 A | 2026-03-27 | 1 | 2026-03-27
Regeneration Gas C4 Hydrogenation vent point Tag # P-B-B3-M3-L-3500 |  | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 88 | 2026-03-27
A6780 | Start of Work | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 1 | 2026-03-27
A6790 | Obtain Work Permit | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6800 | Removal of Insulation & Wallthickness measurement | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6810 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6820 | Cut old piping (existing line 81142), haul to ground level | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6830 | Grinding, bevelling of old piping & fit-up with new spool | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6840 | Welding of 8x1" weldolet and flange with valve and instrument | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6850 | Inspection NDT / RT of selected joints | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A38070 | Install pipe supports (if any) | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A38080 | Prepare and hydrotest up to XX BarG (if required) | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A38090 | Hydrotest witness inspection (if required) | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6890 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6900 | Touch-up painting works | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6910 | Deblinding, remove temporary support / scaffolds | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6920 | Reinstall insulation (if any) | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6930 | Torquing / flange management & hand-over to Ops | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6940 | End of Work | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 1 | 2026-03-27
Sample point in Regeneration gas cooler outlet Tag # IP-B-B3-M3-L-3510 |  | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 88 | 2026-03-27
A6610 | Start of Work | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 1 | 2026-03-27
A6620 | Obtain Work Permit | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6630 | Wallthickness measurement | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6640 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6650 | Cut old piping (existing line 140024), haul to ground level | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6660 | Grinding, bevelling of old piping & fit-up with new spool | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6670 | Welding of 20x1" weldolet and flange with valve and instrument 50S-14161L | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6680 | Inspection NDT / RT of selected joints | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6690 | Install pipe supports (if any) | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6700 | Prepare and hydrotest up to XX BarG (if required) | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6710 | Hydrotest witness inspection (if required) | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6720 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6730 | Touch-up painting works | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6740 | Deblinding, remove temporary support / scaffolds | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6750 | Reinstall insulation (if any) | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6760 | Torquing / flange management & hand-over to Ops | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6770 | End of Work | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 1 | 2026-03-27
Reinforced Branch connection for WG flare (Installation of 5 Tie Ins) Tag # IP-B-B3-M3-L-3520 |  | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 88 | 2026-03-27
A6440 | Start of Work | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 1 | 2026-03-27
A6450 | Obtain Work Permit | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6460 | Wallthickness measurement | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6470 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6480 | Cut old piping (existing line 140301), haul to ground level | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6490 | Grinding, bevelling of old piping & fit-up with new spool | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6500 | Full welding of joints (tie in Tee piece, than the tie in spools) | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6510 | Inspection NDT / RT of selected joints | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6520 | Install pipe supports (if any) | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6530 | Prepare and hydrotest up to XX BarG (if required) | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6540 | Hydrotest witness inspection (if required) | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6550 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6560 | Touch-up painting works | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6570 | Deblinding, remove temporary support / scaffolds | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6580 | Reinstall insulation (if any) | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6590 | Torquing / flange management & hand-over to Ops | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6600 | End of Work | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 1 | 2026-03-27
Reinforced Branch connection pipe specification break for WG flare Tag # P-B-B3-M3-L-3530 |  | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 88 | 2026-03-27
A6270 | Start of Work | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6280 | Obtain Work Permit | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6290 | Wallthickness measurement | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6300 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6310 | Cut old piping (existing line 140301), haul to ground level | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6320 | Grinding, bevelling of old piping & fit-up with new spool | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6330 | Full welding of joints | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6340 | Inspection NDT / RT of selected joints | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6350 | Install pipe supports (if any) | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6360 | Prepare and hydrotest up to XX BarG (if required) | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6370 | Hydrotest witness inspection (if required) | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6380 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6390 | Touch-up painting works | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6400 | Deblinding, remove temporary support / scaffolds | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6410 | Reinstall insulation (if any) | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6420 | Torquing / flange management & hand-over to Ops | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6430 | End of Work | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
PSA2 Off Gas from EU3 to EU3 Tie In point Tag # IP-B-H3-B3-L-2022 |  | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 88 | 2026-03-27
A6100 | Start of Work | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 1 | 2026-03-27
A6110 | Obtain Work Permit | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6120 | Removal of insulation & Wallthickness measurement | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6130 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6140 | Cut old piping (existing line 45024) , haul to ground level | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6150 | Grinding, bevelling of old piping & fit-up with new spool | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6160 | Full welding of joints, Tee & installation of Tie-In spool 72069 | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6170 | Inspection NDT / RT of selected joints | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6180 | Install pipe supports (if any) | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6190 | Prepare and hydrotest up to XX BarG (if required) | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6200 | Hydrotest witness inspection (if required) | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6210 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6220 | Touch-up painting works | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6230 | Deblinding, remove temporary support / scaffolds | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6240 | Reinstall insulation (if any) | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6250 | Torquing / flange management & hand-over to Ops | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6260 | End of Work | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 1 | 2026-03-27
Process Water from EU3 H2 to EU3 Tie In Point Tag # IP-B-H3-B3-L-2042 |  | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 88 | 2026-03-27
A5930 | Start of Work | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 1 | 2026-03-27
A5940 | Obtain Work Permit | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A5950 | Wallthickness measurement | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A5960 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A5970 | Cut old piping (existing line 20002), haul to ground level | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A5980 | Grinding, bevelling of old piping & fit-up with new spool | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A5990 | Welding of Tie-in spool weldolet | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6000 | Inspection NDT / RT of selected joints | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6010 | Install pipe supports (if any) | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6020 | Prepare and hydrotest up to XX BarG (if required) | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6030 | Hydrotest witness inspection (if required) | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6040 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6050 | Touch-up painting works | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6060 | Deblinding, remove temporary support / scaffolds | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6070 | Reinstall insulation (if any) | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6080 | Torquing / flange management & hand-over to Ops | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A6090 | End of Work | 2026-02-20 | 2026-02-20 | 29-Mar-25 A | 17-May-25 A | 2026-03-27 | 1 | 2026-03-27
Warm Liquid Flare from EU3 to EU3 Tie In point Tag # IP-B-H3-B3-L-2052 |  | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 88 | 2026-03-27
A5760 | Start of Work | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 1 | 2026-03-27
A5770 | Obtain Work Permit | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A5780 | Wallthickness measurement | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A5790 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A5800 | Cut old piping (existing line 140301), haul to ground level | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A5810 | Grinding, bevelling of old piping & fit-up with new spool | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A5820 | Full welding of joints & installation of Tie-In spool 140382 | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A5830 | Inspection NDT / RT of selected joints | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A5840 | Install pipe supports (if any) | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A5850 | Prepare and hydrotest up to XX BarG | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A5860 | Hydrotest witness inspection | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A5870 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A5880 | Touch-up painting works | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A5890 | Deblinding, remove temporary support / scaffolds | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A5900 | Reinstall insulation (if any) | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A5910 | Torquing / flange management & hand-over to Ops | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A5920 | End of Work | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 1 | 2026-03-27
Warm Gas Flare from EU3 to EU3 Tie In point Tag # IP-B-H3-B3-L-2062 |  | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 88 | 2026-03-27
A5590 | Start of Work | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 1 | 2026-03-27
A5600 | Obtain Work Permit | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A5610 | Wallthickness measurement | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A5620 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A5630 | Cut old piping (existing line 140301), haul to ground level | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A5640 | Grinding, bevelling of old piping & fit-up with new spool | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A5650 | Full welding of joints & installation of Tie-In spool 140381 | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A5660 | Inspection NDT / RT of selected joints | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A5670 | Install pipe supports (if any) | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A5680 | Prepare and hydrotest up to XX BarG | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A5690 | Hydrotest witness inspection | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A5700 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A5710 | Touch-up painting works | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A5720 | Deblinding, remove temporary support / scaffolds | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A5730 | Reinstall insulation (if any) | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A5740 | Torquing / flange management & hand-over to Ops | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A5750 | End of Work | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 1 | 2026-03-27
LP Condensate from EU3 H2 to EU3 Tie In point Tag # IP-B-H3-B3-L-2072 |  | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 88 | 2026-03-27
A5420 | Start of Work | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 1 | 2026-03-27
A5430 | Obtain Work Permit | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A5440 | Removal of insulation & Wallthickness measurement | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A5450 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A5460 | Cut old piping (existing line 140101), haul to ground level | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A5470 | Grinding, bevelling of old piping & fit-up with new spool | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A5480 | Full welding of joints including weldolet & installation of Tie-In spool 140434 | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A5490 | Inspection NDT / RT of selected joints | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A5500 | Install pipe supports (if any) | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A5510 | Prepare and hydrotest up to XX BarG (if required) | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A5520 | Hydrotest witness inspection (if required) | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A5530 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A5540 | Touch-up painting works | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A5550 | Deblinding, remove temporary support / scaffolds | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A5560 | Reinstall insulation (if any) | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A5570 | Torquing / flange management & hand-over to Ops | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A5580 | End of Work | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 1 | 2026-03-27
Package 3 |  | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 126 | 2026-03-27
Cooling Water Return from EU3 H2 to U&O3 Tie In point Tag # IP-B-H3-U3-L-1101 |  | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 88 | 2026-03-27
A5250 | Start of Work | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 1 | 2026-03-27
A5260 | Obtain Work Permit | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A5270 | Wall thickness measurement | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A5280 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A5290 | Cut old piping (existing line '00018), haul to ground level | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A5300 | Grinding, bevelling of old piping & fit-up with new spool | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A5310 | Full welding of joints including weldolet & installation of Tie-In spool 00215 | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A5320 | Inspection NDT / RT of selected joints | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A5330 | Install pipe supports (if any) | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A5340 | Prepare and hydrotest up to XX BarG (if required) | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A5350 | Hydrotest witness inspection (if required) | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A5360 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A5370 | Touch-up painting works | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A5380 | Deblinding, remove temporary support / scaffolds | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A5390 | Reinstall insulation (if any) | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A5400 | Torquing / flange management & hand-over to Ops | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A5410 | End of Work | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 1 | 2026-03-27
PSA2 Off Gas Recycle to CGC Tag # IP-B-M3-B3-L-3040 |  | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 88 | 2026-03-27
A5080 | Start of Work | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 3 | 2026-03-27
A5090 | Obtain Work Permit | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A5100 | Removal of insulation & Wall thickness measurement | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A5110 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A5120 | Cut old piping & support, haul to ground level | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A5130 | Grinding, bevelling of old piping & fit-up with new spool | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A5140 | Full welding of weldolet & installation of Tie-In spool 72068 | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A5150 | Inspection NDT / RT of selected joints | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A38010 | Install pipe supports (if any) | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A38020 | Prepare and hydrotest up to XX BarG (if required) | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A38030 | Hydrotest witness inspection (if required) | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A38040 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A38050 | Touch-up painting works | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A38060 | Deblinding, remove temporary support / scaffolds | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A5220 | Reinstall insulation (if any) | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A5230 | Torquing / flange management & hand-over to Ops | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A5240 | End of Work | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 1 | 2026-03-27
Regeneration Gas from 50-HE-1410 to 50-VV-1401 Tag # IP-B-M3-B3-L-3070 |  | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 88 | 2026-03-27
A4910 | Start of Work | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 1 | 2026-03-27
A4920 | Obtain Work Permit | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A4930 | Removal of insulation & Wall thickness measurement | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A4940 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A4950 | Cut old piping (existing line 45024), haul to ground level | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A4960 | Grinding, bevelling of old piping & fit-up with new spool | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A4970 | Full welding of joints & installation of Tie-In spool 140489 | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A4980 | Inspection NDT / RT of selected joints | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A4990 | Install pipe supports (if any) | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A5000 | Prepare and hydrotest up to XX BarG (if required) | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A5010 | Hydrotest witness inspection (if required) | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A5020 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A5030 | Touch-up painting works | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A5040 | Deblinding, remove temporary support / scaffolds | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A5050 | Reinstall insulation (if any) | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A5060 | Torquing / flange management & hand-over to Ops | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A5070 | End of Work | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 1 | 2026-03-27
Regeneration Gas to 50-VV-1401 Tag # IP-B-M3-B3-L-3110 |  | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 88 | 2026-03-27
A4740 | Start of Work | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 1 | 2026-03-27
A4750 | Obtain Work Permit | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A4760 | Wall thickness measurement | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A4770 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A4780 | Cut old piping (existing line 140025) , haul to ground level | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A4790 | Grinding, bevelling of old piping & fit-up with new spool | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A4800 | Full welding of joints | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A4810 | Inspection NDT / RT of selected joints | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A4820 | Install pipe supports (if any) | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A4830 | Prepare and hydrotest up to XX BarG (if required) | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A4840 | Hydrotest witness inspection (if required) | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A4850 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A4860 | Touch-up painting works | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A4870 | Deblinding, remove temporary support / scaffolds | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A4880 | Reinstall insulation (if any) | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A4890 | Torquing / flange management & hand-over to Ops | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A4900 | End of Work | 2026-02-20 | 2026-02-20 | 02-Apr-25 A | 17-May-25 A | 2026-03-27 | 1 | 2026-03-27
Cooling Water from 50-HE-1410 to EU3 Tie-In Point Tag # IP-B-M3-B3-L-3130 |  | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 88 | 2026-03-27
A4570 | Start of Work | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 1 | 2026-03-27
A4580 | Obtain Work Permit | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A4590 | Wall thickness measurement | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A4600 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A4610 | Cut old piping (existing line 140034) & support, haul to ground level | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A4620 | Grinding, bevelling of old piping & fit-up with new spool | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A4630 | Full welding of joints & installation of Tie-In spool 140065 | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A4640 | Inspection NDT / RT of selected joints | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A4650 | Install pipe supports (if any) | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A4660 | Prepare and hydrotest up to XX BarG (if required) | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A4670 | Hydrotest witness inspection (if required) | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A4680 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A4690 | Touch-up painting works | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A4700 | Deblinding, remove temporary support / scaffolds | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A4710 | Reinstall insulation (if any) | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A4720 | Torquing / flange management & hand-over to Ops | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A4730 | End of Work | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 1 | 2026-03-27
Warm Gas Flare from 50-HE-1410 to EU3 Tie In Point Tag # IP-B-M3-B3-L-3140 |  | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 88 | 2026-03-27
A4400 | Start of Work | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 1 | 2026-03-27
A4410 | Obtain Work Permit | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A4420 | Wall thickness measurement | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A4430 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A4440 | Cut old piping (existing line 140301), haul to ground level | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A4450 | Grinding, bevelling of old piping & fit-up with new spool | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A4460 | Full welding of joints & installation of Tie-In spool 140379 | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A4470 | Inspection NDT / RT of selected joints | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A4480 | Install pipe supports (if any) | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A4490 | Prepare and hydrotest up to XX BarG (if required) | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A4500 | Hydrotest witness inspection (if required) | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A4510 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A4520 | Touch-up painting works | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A4530 | Deblinding, remove temporary support / scaffolds | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A4540 | Reinstall insulation (if any) | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A4550 | Torquing / flange management & hand-over to Ops | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A4560 | End of Work | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 1 | 2026-03-27
Treated VHP BFW from 52-HE-1402 to EU3 Tag # IP-B-M3-B3-L-3220 |  | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 88 | 2026-03-27
A4230 | Start of Work | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 1 | 2026-03-27
A4240 | Obtain Work Permit | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A4250 | Removal of insulation and wall thickness measurement | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A4260 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A4270 | Cut old piping (existing line 140025) & support, haul to ground level | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A4280 | Grinding, bevelling of old piping & fit-up with new spool | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A4290 | Full welding of joints (Tee-piece) & installation of Tie-In spool 140218 | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A4300 | Inspection NDT / RT of selected joints | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A4310 | Install pipe supports (if any) | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A4320 | Prepare and hydrotest up to XX BarG (if required) | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A4330 | Hydrotest witness inspection (if required) | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A4340 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A4350 | Touch-up painting works | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A4360 | Deblinding, remove temporary support / scaffolds | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A4370 | Reinstall insulation (if any) | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A4380 | Torquing / flange management & hand-over to Ops | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A4390 | End of Work | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 1 | 2026-03-27
LP- Condensate from 52-HE-1402 to 54-VV-1402 Tag # IP-B-M3-B3-L-3240 |  | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 87 | 2026-03-27
A4060 | Start of Work | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 1 | 2026-03-27
A4070 | Obtain Work Permit | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A4080 | Removal of insulation | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A4090 | Removal of blind flange 54-VV-1402, N02 & Gas measurement | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A4100 | Check of cleanliness of vessel and new pipe | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A4110 | Connection of tie in spool | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A4190 | Deblinding, remove temporary support / scaffolds | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A4200 | Reinstall insulation (if any) | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A4210 | Torquing / flange management & hand-over to Ops | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A4220 | End of Work | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 1 | 2026-03-27
Tailgas to 50-VV-1401 Tag # IP-B-M3-B3-L-3250 |  | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 88 | 2026-03-27
A3890 | Start of Work | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 1 | 2026-03-27
A3900 | Obtain Work Permit | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A3910 | Removal of insulation and wall thickness measurement | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A3920 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A3930 | Cut old piping (existing line 45024), haul to ground level | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A3940 | Grinding, bevelling of old piping & fit-up with new spool | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A3950 | Full welding of joints & installation of Tie-In spool 45024 | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A3960 | Inspection NDT / RT of selected joints | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A3970 | Install pipe supports (if any) | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A3980 | Prepare and hydrotest up to XX BarG (if required) | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A3990 | Hydrotest witness inspection (if required) | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A4000 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A4010 | Touch-up painting works | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A4020 | Deblinding, remove temporary support / scaffolds | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A4030 | Reinstall insulation (if any) | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A4040 | Torquing / flange management & hand-over to Ops | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A38000 | End of Work | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 1 | 2026-03-27
Regeneration Gas C4 Hydrogenation to 50-HE-1402 Tag # IP-B-M3-B3-L-3280 |  | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 89 | 2026-03-27
A3720 | Start of Work | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 1 | 2026-03-27
A3730 | Obtain Work Permit | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A3740 | Removal of insulation and wall thickness measurement | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A3750 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A3760 | Cut old piping (existing line 41022), haul to ground level | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A3770 | Grinding, bevelling of old piping & fit-up with new spool | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A3780 | Full welding of joints & installation of Tie-In spool 81142 | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A3790 | Inspection NDT / RT of selected joints | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A3800 | Install pipe supports (if any) | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A3810 | Prepare and hydrotest up to XX BarG (if required) | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A3820 | Hydrotest witness inspection (if required) | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A3830 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A3840 | Touch-up painting works | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A3850 | Deblinding, remove temporary support / scaffolds | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A3860 | Reinstall insulation (if any) | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A3870 | Torquing / flange management & hand-over to Ops | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A3880 | End of Work | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 1 | 2026-03-27
Regeneration Gas C4 Hydrogenation Condensate Tag # IP-B-M3-B3-L-3290 |  | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 88 | 2026-03-27
A3550 | Start of Work | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 1 | 2026-03-27
A37970 | Obtain Work Permit | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A3570 | Wall thickness measurement | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A37980 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A37990 | Cut old piping (existing line 140028) , haul to ground level | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A3600 | Grinding, bevelling of old piping & fit-up with new spool | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A3610 | Full welding of joints & installation of Tie-In spool 140066 | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A3620 | Inspection NDT / RT of selected joints | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A3630 | Install pipe supports (if any) | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A3640 | Prepare and hydrotest up to XX BarG (if any) | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A3650 | Hydrotest witness inspection (if any) | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A3660 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A3670 | Touch-up painting works | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A3680 | Deblinding, remove temporary support / scaffolds | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A3690 | Reinstall insulation (if any) | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A3700 | Torquing / flange management & hand-over to Ops | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A3710 | End of Work | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 1 | 2026-03-27
Warm Gas Flare from 13-KX-402/50-HE-1402 to EU3 Tie In Point Tag # P-B-M3-B3-L-3300 |  | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 88 | 2026-03-27
A37820 | Start of Work | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 1 | 2026-03-27
A3390 | Obtain Work Permit | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A37830 | Wall thickness measurement | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A37840 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A37850 | Cut old piping (existing line 140301) , haul to ground level | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A37860 | Grinding, bevelling of old piping & fit-up with new spool | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A37870 | Full welding of joints & installation of Tie-In spool 140301 | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A37880 | Inspection NDT / RT of selected joints | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A37890 | Install pipe supports (if any) | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A37900 | Prepare and hydrotest up to XX BarG | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A37910 | Hydrotest witness inspection | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A37920 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A37930 | Touch-up painting works | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A37940 | Deblinding, remove temporary support / scaffolds | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A37950 | Reinstall insulation (if any) | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A37960 | Torquing / flange management & hand-over to Ops | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A3540 | End of Work | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 1 | 2026-03-27
Cold Gas from 13-PSV-4508 to EU3 Tie In Tag # P-B-M3-B3-L-3410 |  | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 88 | 2026-03-27
A3210 | Start of Work | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 1 | 2026-03-27
A3220 | Obtain Work Permit | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A3230 | Wall thickness measurement | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A3240 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A37800 | Cut old piping (existing line 140321) & support, haul to ground level | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A3260 | Grinding, bevelling of old piping & fit-up with new spool | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A3270 | Purge with 24" balloons & welding of Tie-In spool 144564 | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A3280 | Inspection NDT / RT of selected joints | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A3290 | Install pipe supports (if any) | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A3300 | Prepare and hydrotest up to XX BarG (if required) | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A3310 | Hydrotest witness inspection (if required) | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A3320 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A3330 | Touch-up painting works | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A3340 | Deblinding, remove temporary support / scaffolds | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A37810 | Reinstall insulation (if any) | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A3360 | Torquing / flange management & hand-over to Ops | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A3370 | End of Work | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 1 | 2026-03-27
Package 4 |  | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 110 | 2026-03-27
50AT-14101A sample tap vent return to process Tag # IP-B-M3-B3-L-3420 |  | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 87 | 2026-03-27
A3040 | Start of Work | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 2 | 2026-03-27
A3050 | Obtain Work Permit | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A3060 | Gas measurement | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A3070 | Making tubing connection | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A3170 | Deblinding, remove temporary support / scaffolds | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A3200 | End of Work | 2026-02-20 | 2026-02-20 | 10-Apr-25 A | 17-May-25 A | 2026-03-27 | 2 | 2026-03-27
Instrument Air from U&O3 Tie In point to EU3 H2 Tag # IP-B-U3-H3-L-1020 |  | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 94 | 2026-03-27
A2870 | Start of Work | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 10 | 2026-03-27
A2880 | Obtain Work Permit | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A3030 | End of Work | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 10 | 2026-03-27
Plant Air from U&O3 Tie In point to EU3 H2 Tag # IP-B-U3-H3-L-1030 |  | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 94 | 2026-03-27
A2700 | Start of Work | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 10 | 2026-03-27
A2710 | Obtain Work Permit | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A2860 | End of Work | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 10 | 2026-03-27
Nitrogen from U&O3 Tie In point to EU3 H2 Tag # IP-B-U3-H3-L-1040 |  | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 94 | 2026-03-27
A2530 | Start of Work | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 10 | 2026-03-27
A2540 | Obtain Work Permit | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A2690 | End of Work | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 10 | 2026-03-27
LP Steam from U&O3 Tie In point to EU3 H2 Tag # IP-B-U3-H3-L-1050 |  | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 88 | 2026-03-27
A2360 | Start of Work | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 1 | 2026-03-27
A2370 | Obtain Work Permit | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A2380 | Wall thickness measurement | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A2390 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A2400 | Cut old piping (existing line 00271) & support, haul to ground level | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A2410 | Grinding, bevelling of old piping & fit-up with new spool | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A2420 | Full welding of joints & Installation of Tie-In spool '0005 | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A2430 | Inspection NDT / RT of selected joints | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A2440 | Install pipe supports (if any) | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A2450 | Prepare and hydrotest up to XX BarG | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A2460 | Hydrotest witness inspection | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A2470 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A2480 | Touch-up painting works | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A2490 | Deblinding, remove temporary support / scaffolds | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A2500 | Reinstall insulation (if any) | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A2510 | Torquing / flange management & hand-over to Ops | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A2520 | End of Work | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 1 | 2026-03-27
Service water from U&O3 Tie In point to to EU3 H2 Tag # IP-B-U3-H3-L-1060 |  | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 88 | 2026-03-27
A2190 | Start of Work | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 1 | 2026-03-27
A2200 | Obtain Work Permit | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A2210 | Removal of insulation and wall thickness measurement | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A2220 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A2230 | Cut old piping (existing line '00061) & support, haul to ground level | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A2240 | Grinding, bevelling of old piping & fit-up with new spool | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A2250 | Full welding of joints | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A2260 | Inspection NDT / RT of selected joints | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A2270 | Install pipe supports (if any) | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A2280 | Prepare and hydrotest up to XX BarG | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A2290 | Hydrotest witness inspection | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A2300 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A2310 | Touch-up painting works | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A2320 | Deblinding, remove temporary support / scaffolds | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A2330 | Reinstall insulation (if any) | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A2340 | Torquing / flange management & hand-over to Ops | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A2350 | End of Work | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 1 | 2026-03-27
Potable water from U&O3 Tie In point to EU3 H2 Tag # IP-B-U3-H3-L-1070 |  | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 88 | 2026-03-27
A2020 | Start of Work | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 1 | 2026-03-27
A2030 | Obtain Work Permit | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A2040 | Wall thickness measurement | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A2050 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A2060 | Cut old piping & support, haul to ground level | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A2070 | Grinding, bevelling of old piping & fit-up with new spool | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A2080 | Full welding of joints | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A2090 | Inspection NDT / RT of selected joints | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A2100 | Install pipe supports (if any) | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A2110 | Prepare and hydrotest up to XX BarG | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A2120 | Hydrotest witness inspection | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A2130 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A2140 | Touch-up painting works | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A2150 | Deblinding, remove temporary support / scaffolds | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A2160 | Reinstall insulation (if any) | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A2170 | Torquing / flange management & hand-over to Ops | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A2180 | End of Work | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 1 | 2026-03-27
Cooling Water Supply from U&O3 Tie In Point to EU3 H2 Tag # P-B-U3-H3-L-1090 |  | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 88 | 2026-03-27
A1340 | Start of Work | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 1 | 2026-03-27
A1350 | Obtain Work Permit | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A1360 | Removal of insulation (if any) & measurement of wall thickness | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A1370 | Pull-out piping components (Valves, TW/TE, TG, PT, PG if any) | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A1380 | Cut old piping (existing line '00234) & support, haul to ground level | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A1390 | Grinding, bevelling of old piping & fit-up with new spool | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A1400 | Welding of weldolet | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A1410 | Inspection NDT / RT of selected joints | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A1420 | Install pipe supports (if any) | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A1430 | Prepare and hydrotest up to XX BarG (if required) | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A1440 | Hydrotest witness inspection (if required) | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A1450 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A1460 | Touch-up painting works (if any) | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A1470 | Deblinding, remove temporary support / scaffolds | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A1480 | Reinstall insulation (if any) | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A1490 | Torquing / flange management & hand-over to Ops | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A37650 | End of Work | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 1 | 2026-03-27
Oily water from EU3 H2 to U&O3 Tie In point Tag # IP-B-U3-H3-L-1121 |  | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 88 | 2026-03-27
A37570 | Start of Work | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A37580 | Obtain Work Permit | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A37590 | Removal of insulation & measurement of wall thickness | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A37600 | Drilling one hole (cold drilling, air-driven) & Gas measurement | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A1210 | Cut old piping (existing line '00018), haul to ground level | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A1220 | Grinding, bevelling of old piping & fit-up with new spool | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A1230 | Full welding of joints | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A37610 | Inspection NDT / RT of selected joints | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A37620 | Install pipe supports (if any) | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A37630 | Prepare and hydrotest up to XX BarG (if required) | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A37640 | Hydrotest witness inspection (if required) | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A1280 | Reinstall back piping components (TW/TE, TG, PT, PG if any) | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A1290 | Touch-up painting works | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A1300 | Deblinding, remove temporary support / scaffolds | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A1310 | Reinstall insulation (if any) | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A1320 | Torquing / flange management & hand-over to Ops | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A1330 | End of Work | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
TA Tie-In Execution - U/G Tie-Ins |  | 2026-02-20 | 2026-02-20 | 03-Apr-25 A | 17-May-25 A | 2026-03-27 | 94 | 2026-03-27
Package 4 |  | 2026-02-20 | 2026-02-20 | 03-Apr-25 A | 17-May-25 A | 2026-03-27 | 94 | 2026-03-27
Fire Water from U&O3 Tie point to EU3 H2 (South west) Tag # IP-B-U3-H3-L-1080 |  | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 86 | 2026-03-27
A1850 | Start of Work | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 1 | 2026-03-27
A1860 | Obtain Work Permit | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A1870 | Install temporary support / scaffolds as site | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A1880 | Install isolation balloon | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A1980 | Deblinding, remove temporary support / scaffolds | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A1990 | Reinstall insulation (if any) | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A2000 | Torquing / flange management & hand-over to Ops | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A2010 | End of Work | 2026-02-20 | 2026-02-20 | 08-Apr-25 A | 17-May-25 A | 2026-03-27 | 1 | 2026-03-27
Fire Water from U&O3 Tie point to EU3 H2 (south east) Tag # IP-B-U3-H3-L-1082 |  | 2026-02-20 | 2026-02-20 | 03-Apr-25 A | 17-May-25 A | 2026-03-27 | 90 | 2026-03-27
A1680 | Start of Work | 2026-02-20 | 2026-02-20 | 03-Apr-25 A | 17-May-25 A | 2026-03-27 | 2 | 2026-03-27
A1690 | Obtain Work Permit | 2026-02-20 | 2026-02-20 | 03-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A1700 | Removal of insulation & wall thickness measurement | 2026-02-20 | 2026-02-20 | 03-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A1710 | Drilling one hole (cold drilling, airdriven) & Gas measurement | 2026-02-20 | 2026-02-20 | 03-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A1720 | Cut old piping & support, haul to ground level | 2026-02-20 | 2026-02-20 | 03-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A1730 | Grinding, bevelling of old piping & fit-up with new spool | 2026-02-20 | 2026-02-20 | 03-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A1740 | Full welding of joints | 2026-02-20 | 2026-02-20 | 03-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A1750 | Inspection NDT / RT of selected joints | 2026-02-20 | 2026-02-20 | 03-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A1760 | Install pipe supports (if any) | 2026-02-20 | 2026-02-20 | 03-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A1770 | Prepare and hydrotest up to XX BarG | 2026-02-20 | 2026-02-20 | 03-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A1780 | Hydrotest witness inspection | 2026-02-20 | 2026-02-20 | 03-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A1790 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) | 2026-02-20 | 2026-02-20 | 03-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A1800 | Touch-up painting works | 2026-02-20 | 2026-02-20 | 03-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A1810 | Deblinding, remove temporary support / scaffolds | 2026-02-20 | 2026-02-20 | 03-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A1820 | Reinstall insulation (if any) | 2026-02-20 | 2026-02-20 | 03-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A1830 | Torquing / flange management & hand-over to Ops | 2026-02-20 | 2026-02-20 | 03-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A1840 | End of Work | 2026-02-20 | 2026-02-20 | 03-Apr-25 A | 17-May-25 A | 2026-03-27 | 2 | 2026-03-27
Fire Water from U&O3 Tie point to EU3 H2 (North east) Tag # IP-B-U3-H3-L-1086 |  | 2026-02-20 | 2026-02-20 | 03-Apr-25 A | 17-May-25 A | 2026-03-27 | 90 | 2026-03-27
A37660 | Start of Work | 2026-02-20 | 2026-02-20 | 03-Apr-25 A | 17-May-25 A | 2026-03-27 | 2 | 2026-03-27
A1520 | Obtain Work Permit | 2026-02-20 | 2026-02-20 | 03-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A1530 | Install temporary support / scaffolds as site | 2026-02-20 | 2026-02-20 | 03-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A37670 | Pull-out piping components (Valves, TW/TE, TG, PT, PG if any) | 2026-02-20 | 2026-02-20 | 03-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A37680 | Cut old piping (20" HDPE Line), haul to ground level | 2026-02-20 | 2026-02-20 | 03-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A37690 | Grinding, bevelling of old piping & fit-up with new spool (new HDPE TEE) | 2026-02-20 | 2026-02-20 | 03-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A37700 | Installation, alignment and welding of HDPE Tee to existing header 18011 & install. of tie-in spools 18481 & welding | 2026-02-20 | 2026-02-20 | 03-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A37710 | Inspection (all required HDPE welding examinations) of selected joints | 2026-02-20 | 2026-02-20 | 03-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A37720 | Install pipe supports (if any) | 2026-02-20 | 2026-02-20 | 03-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A37730 | Prepare and hydrotest up to XX BarG (if any) | 2026-02-20 | 2026-02-20 | 03-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A37740 | Hydrotest witness inspection (if any) | 2026-02-20 | 2026-02-20 | 03-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A37750 | Reinstall back piping components (TW/TE, TG, PT, PG if any) | 2026-02-20 | 2026-02-20 | 03-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A37760 | Touch-up painting works | 2026-02-20 | 2026-02-20 | 03-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A37770 | Deblinding, remove temporary support / scaffolds | 2026-02-20 | 2026-02-20 | 03-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A37780 | Reinstall insulation (if any) | 2026-02-20 | 2026-02-20 | 03-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A37790 | Torquing / flange management & hand-over to Ops | 2026-02-20 | 2026-02-20 | 03-Apr-25 A | 17-May-25 A | 2026-03-27 | 0 | 2026-03-27
A1670 | End of Work | 2026-02-20 | 2026-02-20 | 03-Apr-25 A | 17-May-25 A | 2026-03-27 | 2 | 2026-03-27
GF Piping Works |  | 2026-03-28 | 2027-01-17 | 2026-03-28 | 2027-01-17 | 2026-04-20 | 254 | 2027-03-11 | 46
AG |  | 2026-03-28 | 2027-01-17 | 2026-03-28 | 2027-01-17 | 2026-04-20 | 254 | 2027-03-11 | 46
A60800 | Piping - Pre-Fabrication Shop | 2026-03-28 | 2026-09-17 | 2026-03-28 | 2026-09-17 | 2026-04-20 | 150 | 2026-10-11 | 20
A3400 | Painting Piping - Fabrication Shop | 2026-04-14 | 2026-10-05 | 2026-04-14 | 2026-10-05 | 2026-05-07 | 150 | 2026-10-28 | 20
A3380 | Piping Eection at Site | 2026-05-02 | 2026-10-22 | 2026-05-02 | 2026-10-22 | 2026-05-25 | 150 | 2026-11-15 | 20
A3430 | Hydro testing and reinstatment | 2026-09-20 | 2026-11-16 | 2026-09-20 | 2026-11-16 | 2026-11-12 | 50 | 2027-01-09 | 46
A3420 | Final Touch up and painting of joints | 2026-10-01 | 2026-11-28 | 2026-10-01 | 2026-11-28 | 2026-11-24 | 50 | 2027-01-20 | 46
A3410 | Piping Insulation | 2026-10-10 | 2027-01-17 | 2026-10-10 | 2027-01-17 | 2026-12-02 | 86 | 2027-03-11 | 46
UG |  | 2026-06-06 | 2026-12-03 | 2026-06-06 | 2026-12-03 | 2026-08-16 | 156 | 2027-01-20 | 41
A3480 | U/G Piping Erection Oily Water (CS) | 2026-08-16 | 2026-09-08 | 2026-08-16 | 2026-09-08 | 2026-12-28 | 21 | 2027-01-20 | 115
A3470 | U/G Piping Erection & Hydrotesting Cooling Water Lines (CS) | 2026-06-06 | 2026-09-29 | 2026-06-06 | 2026-09-29 | 2026-08-16 | 100 | 2026-12-09 | 61
A23540 | Piping Erection of Fire water piping (HDPE) UG including hydrotesting | 2026-07-16 | 2026-12-03 | 2026-07-16 | 2026-12-03 | 2026-09-03 | 120 | 2027-01-20 | 41
Insulation |  | 2026-06-23 | 2026-10-05 | 2026-06-23 | 2026-10-05 | 2026-10-08 | 90 | 2027-01-20 | 92
A3580 | Complete Insulation, Fire-Proofing and Painting works | 2026-06-23 | 2026-10-05 | 2026-06-23 | 2026-10-05 | 2026-10-08 | 90 | 2027-01-20 | 92
Painting |  | 2026-08-09 | 2026-11-28 | 2026-08-09 | 2026-11-28 | 2027-03-27 | 96 | 2027-07-15 | 197
A61630 | Painting | 2026-08-09 | 2026-11-28 | 2026-08-09 | 2026-11-28 | 2027-03-27 | 96 | 2027-07-15 | 197
Others |  | 2026-11-29 | 2026-12-02 | 2026-11-29 | 2026-12-02 | 2027-07-17 | 4 | 2027-07-20 | 197
A61640 | Painting punch clearing | 2026-11-29 | 2026-12-02 | 2026-11-29 | 2026-12-02 | 2027-07-17 | 4 | 2027-07-20 | 197
Electrical Construction |  | 2026-02-20 | 2026-12-28 | 01-Mar-25 A | 2026-12-28 | 2026-03-27 | 501 | 2027-01-20 | 17
Equipment Installation |  | 2026-02-20 | 2026-12-28 | 03-Apr-25 A | 2026-12-28 | 2026-03-27 | 451 | 2027-01-20 | 17
System and Panels Installation |  | 2026-04-16 | 2026-06-10 | 2026-04-16 | 2026-06-10 | 2026-11-26 | 48 | 2027-01-20 | 192
A61650 | System and Panels Installations | 2026-04-16 | 2026-06-10 | 2026-04-16 | 2026-06-10 | 2026-11-26 | 48 | 2027-01-20 | 192
GF Interposing Relay Panel |  | 2026-09-19 | 2026-11-16 | 2026-09-19 | 2026-11-16 | 2026-11-23 | 51 | 2027-01-20 | 56
A24070 | Installation of Interposting Relay Panel | 2026-09-19 | 2026-10-01 | 2026-09-19 | 2026-10-01 | 2026-11-23 | 12 | 2026-12-06 | 56
A24580 | Cable terminations and loop testing - IRP | 2026-10-03 | 2026-10-26 | 2026-10-03 | 2026-10-26 | 2026-12-07 | 21 | 2026-12-30 | 56
A24790 | IRP - Pre Comm | 2026-10-27 | 2026-11-16 | 2026-10-27 | 2026-11-16 | 2026-12-31 | 18 | 2027-01-20 | 56
GF DG Set |  | 2026-08-08 | 2026-10-24 | 2026-08-08 | 2026-10-24 | 2026-11-04 | 67 | 2027-01-20 | 76
A3829 | Installation of DG Set | 2026-08-08 | 2026-09-07 | 2026-08-08 | 2026-09-07 | 2026-11-04 | 27 | 2026-12-05 | 76
A24590 | Cable terminations and loop testing - DG Set | 2026-09-08 | 2026-10-03 | 2026-09-08 | 2026-10-03 | 2026-12-06 | 22 | 2026-12-30 | 76
A24800 | DG Set - Pre Comm | 2026-10-04 | 2026-10-24 | 2026-10-04 | 2026-10-24 | 2026-12-31 | 18 | 2027-01-20 | 76
GF Electrical Heat Tracing (53 Meter for piping + 340 Meter for instrumentation) |  | 2026-08-31 | 2026-11-11 | 2026-08-31 | 2026-11-11 | 2026-11-10 | 62 | 2027-01-20 | 61
A24090 | Electrical Heat Tracing works | 2026-08-31 | 2026-09-23 | 2026-08-31 | 2026-09-23 | 2026-11-10 | 20 | 2026-12-02 | 61
A24410 | Cable terminations and loop testing - Electric Heat Tracing | 2026-09-23 | 2026-10-21 | 2026-09-23 | 2026-10-21 | 2026-12-03 | 24 | 2026-12-30 | 61
A24660 | Electric Heat Tracing - Pre Comm | 2026-10-21 | 2026-11-11 | 2026-10-21 | 2026-11-11 | 2026-12-31 | 18 | 2027-01-20 | 61
GF Power Transformers (Qty 05) |  | 2026-08-15 | 2026-11-11 | 2026-08-15 | 2026-11-11 | 2026-10-24 | 77 | 2027-01-20 | 60
A24120 | Installation of Power Transformers | 2026-08-15 | 2026-09-23 | 2026-08-15 | 2026-09-23 | 2026-10-24 | 35 | 2026-12-02 | 60
A24470 | Cable terminations and loop testing - Power Transformers | 2026-09-24 | 2026-10-21 | 2026-09-24 | 2026-10-21 | 2026-12-03 | 24 | 2026-12-30 | 60
A24680 | Power Transformers - Pre Comm | 2026-10-22 | 2026-11-11 | 2026-10-22 | 2026-11-11 | 2026-12-31 | 18 | 2027-01-20 | 60
GF HV Capacitor Bay |  | 2026-08-04 | 2026-10-07 | 2026-08-04 | 2026-10-07 | 2026-11-17 | 56 | 2027-01-20 | 90
A24080 | Installation of Capacitor Bay | 2026-08-04 | 2026-08-24 | 2026-08-04 | 2026-08-24 | 2026-11-17 | 18 | 2026-12-07 | 90
A24490 | Cable terminations and HV Capacitor Bay | 2026-08-25 | 2026-09-17 | 2026-08-25 | 2026-09-17 | 2026-12-08 | 21 | 2026-12-31 | 90
A24700 | HV Capacitor Bay - Pre Comm | 2026-09-19 | 2026-10-07 | 2026-09-19 | 2026-10-07 | 2027-01-02 | 17 | 2027-01-20 | 90
GF Switchgear (LV, MV) |  | 2026-08-22 | 2026-11-23 | 2026-08-22 | 2026-11-23 | 2026-10-19 | 81 | 2027-01-20 | 50
A3839 | Installation of Switchgear | 2026-08-22 | 2026-09-24 | 2026-08-22 | 2026-09-24 | 2026-10-19 | 30 | 2026-11-22 | 50
A24530 | Cable terminations and loop testing - Switchgear (LV, MV) | 2026-09-26 | 2026-10-29 | 2026-09-26 | 2026-10-29 | 2026-11-23 | 30 | 2026-12-27 | 50
A24740 | Switchgear (LV, MV) - Pre Comm | 2026-10-31 | 2026-11-23 | 2026-10-31 | 2026-11-23 | 2026-12-28 | 21 | 2027-01-20 | 50
GF Variable Fequency Drives (VFDs) LV Qty = 03 |  | 2026-08-04 | 2026-11-04 | 2026-08-04 | 2026-11-04 | 2026-10-20 | 80 | 2027-01-20 | 66
A24140 | Installation of VFD | 2026-08-04 | 2026-08-31 | 2026-08-04 | 2026-08-31 | 2026-10-20 | 24 | 2026-11-16 | 66
A24540 | Cable terminations and loop testing - VFD | 2026-09-01 | 2026-10-07 | 2026-09-01 | 2026-10-07 | 2026-11-17 | 32 | 2026-12-23 | 66
A24750 | VFDs - Pre Comm | 2026-10-08 | 2026-11-04 | 2026-10-08 | 2026-11-04 | 2026-12-24 | 24 | 2027-01-20 | 66
GF NGR Panel Qty 02 |  | 2026-08-04 | 2026-09-30 | 2026-08-04 | 2026-09-30 | 2026-11-24 | 50 | 2027-01-20 | 96
A3869 | Installation of NGR Panel | 2026-08-04 | 2026-08-17 | 2026-08-04 | 2026-08-17 | 2026-11-24 | 12 | 2026-12-07 | 96
A24570 | Cable terminations and loop testing NGR Panel | 2026-08-18 | 2026-09-10 | 2026-08-18 | 2026-09-10 | 2026-12-08 | 21 | 2026-12-31 | 96
A24780 | NGR Panel - Pre Comm | 2026-09-12 | 2026-09-30 | 2026-09-12 | 2026-09-30 | 2027-01-02 | 17 | 2027-01-20 | 96
GF Cathodic Protection (CP) Total CS Piping Length - 499 Meters |  | 2026-10-04 | 2026-12-28 | 2026-10-04 | 2026-12-28 | 2026-10-27 | 74 | 2027-01-20 | 20
A24100 | Cathodic Protection for complete CS Piping | 2026-10-04 | 2026-11-09 | 2026-10-04 | 2026-11-09 | 2026-10-27 | 32 | 2026-12-02 | 20
A24420 | Cable terminations and loop testing - Cathodic Protection | 2026-11-10 | 2026-12-07 | 2026-11-10 | 2026-12-07 | 2026-12-03 | 24 | 2026-12-30 | 20
A24670 | Cathodic Protection - Pre Comm | 2026-12-08 | 2026-12-28 | 2026-12-08 | 2026-12-28 | 2026-12-31 | 18 | 2027-01-20 | 20
GF UPS (AC - 60 KVA, 20 KVA, DC-UPS 6.5 KVA) Qty 1+1+1 = 03 Nos |  | 2026-08-15 | 2026-10-25 | 2026-08-15 | 2026-10-25 | 2026-11-10 | 62 | 2027-01-20 | 75
A24060 | Installation of UPS | 2026-08-15 | 2026-09-10 | 2026-08-15 | 2026-09-10 | 2026-11-10 | 24 | 2026-12-07 | 75
A24450 | Cable terminations and loop testing - UPS | 2026-09-12 | 2026-10-04 | 2026-09-12 | 2026-10-04 | 2026-12-08 | 20 | 2026-12-30 | 75
A24640 | UPS - Pre Comm | 2026-10-05 | 2026-10-25 | 2026-10-05 | 2026-10-25 | 2026-12-31 | 18 | 2027-01-20 | 75
TA IPCS Modification by ABB |  | 2026-02-20 | 2026-02-20 | 03-Apr-25 A | 10-May-25 A | 2026-03-27 | 5 | 2026-03-27
A34830 | Installation of FOPP (02 )in existing CCB | 2026-02-20 | 2026-02-20 | 03-Apr-25 A | 10-May-25 A | 2026-03-27 | 5 | 2026-03-27
TA Switchgear Modification by SIEMENS |  | 2026-02-20 | 2026-02-20 | 03-Apr-25 A | 10-May-25 A | 2026-03-27 | 11 | 2026-03-27
A17970 | Bus-bar differential testing Bus-A - feeder H01 (TA) | 2026-02-20 | 2026-02-20 | 03-Apr-25 A | 10-May-25 A | 2026-03-27 | 5 | 2026-03-27
A17980 | Bus-bar differential testing Bus-B - feeder H16 (TA) | 2026-02-20 | 2026-02-20 | 03-Apr-25 A | 10-May-25 A | 2026-03-27 | 3 | 2026-03-27
A34440 | Switchgear Modifications - Siemens | 2026-02-20 | 2026-02-20 | 03-Apr-25 A | 10-May-25 A | 2026-03-27 | 5 | 2026-03-27
A34800 | Installation of Surge Arersstor | 2026-02-20 | 2026-02-20 | 03-Apr-25 A | 10-May-25 A | 2026-03-27 | 5 | 2026-03-27
A34810 | Installation of Dummy Plugs | 2026-02-20 | 2026-02-20 | 03-Apr-25 A | 10-May-25 A | 2026-03-27 | 5 | 2026-03-27
A34820 | Installation of Castle key interlock and key exchange box | 2026-02-20 | 2026-02-20 | 03-Apr-25 A | 10-May-25 A | 2026-03-27 | 5 | 2026-03-27
TA SCMS Modification by SIEMENS |  | 2026-02-20 | 2026-02-20 | 14-Apr-25 A | 14-May-25 A | 2026-03-27 | 10 | 2026-03-27
A17990 | SCMS FOPP Modifications - Siemens (By Client) | 2026-02-20 | 2026-02-20 | 14-Apr-25 A | 25-Apr-25 A | 2026-03-27 | 5 | 2026-03-27
A34780 | Mapping of SCMS in IPCS | 2026-02-20 | 2026-02-20 | 26-Apr-25 A | 30-Apr-25 A | 2026-03-27 | 3 | 2026-03-27
A34840 | Annuciator Panel Modification | 2026-02-20 | 2026-02-20 | 01-May-25 A | 09-May-25 A | 2026-03-27 | 5 | 2026-03-27
A34850 | HMI Graphics Update | 2026-02-20 | 2026-02-20 | 10-May-25 A | 14-May-25 A | 2026-03-27 | 3 | 2026-03-27
TA UPS Modification |  | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 13-May-25 A | 2026-03-27 | 5 | 2026-03-27
A17960 | Modification in DC power supply arrangmeent- UPS | 2026-02-20 | 2026-02-20 | 15-Apr-25 A | 13-May-25 A | 2026-03-27 | 5 | 2026-03-27
Cabling Work |  | 2026-07-29 | 2026-11-12 | 2026-07-29 | 2026-11-12 | 2026-10-06 | 92 | 2027-01-20 | 59
BF Electrical Works |  | 2026-07-29 | 2026-11-12 | 2026-07-29 | 2026-11-12 | 2026-10-06 | 92 | 2027-01-20 | 59
A17740 | Power Cables Laying | 2026-07-29 | 2026-09-08 | 2026-07-29 | 2026-09-08 | 2026-10-06 | 36 | 2026-11-16 | 59
A18750 | FO Cable laying for IPCSS and SCMS | 2026-07-29 | 2026-09-08 | 2026-07-29 | 2026-09-08 | 2026-10-14 | 36 | 2026-11-25 | 67
A18740 | Termination of Power cables and Loop Testing | 2026-09-09 | 2026-10-08 | 2026-09-09 | 2026-10-08 | 2026-11-17 | 26 | 2026-12-16 | 59
A21980 | FO Cable termination for IPCSS and SCMS | 2026-09-21 | 2026-10-20 | 2026-09-21 | 2026-10-20 | 2026-11-29 | 26 | 2026-12-28 | 59
BFW4080 | Other Electrical Works | 2026-10-21 | 2026-11-12 | 2026-10-21 | 2026-11-12 | 2026-12-29 | 20 | 2027-01-20 | 59
Earthing System Installation |  | 2026-07-28 | 2026-10-19 | 2026-07-28 | 2026-10-19 | 2026-10-29 | 72 | 2027-01-20 | 80
A61660 | Earthing System Installation | 2026-07-28 | 2026-10-05 | 2026-07-28 | 2026-10-05 | 2026-10-29 | 60 | 2027-01-06 | 80
A61670 | Earthing System Testing | 2026-10-06 | 2026-10-19 | 2026-10-06 | 2026-10-19 | 2027-01-07 | 12 | 2027-01-20 | 80
Lightning System Installation |  | 2026-09-15 | 2026-10-03 | 2026-09-15 | 2026-10-03 | 2027-01-04 | 15 | 2027-01-20 | 94
GF Lighting Fixtures (Almost 50% Exd = 354 Nos) |  | 2026-09-15 | 2026-10-03 | 2026-09-15 | 2026-10-03 | 2027-01-04 | 15 | 2027-01-20 | 94
A3590 | Complete Street lighting | 2026-09-15 | 2026-10-03 | 2026-09-15 | 2026-10-03 | 2027-01-04 | 15 | 2027-01-20 | 94
Others |  | 2026-02-20 | 2026-02-20 | 01-Mar-25 A | 15-Mar-25 A | 2026-03-27 | 16 | 2026-03-27
TA Site Survey AC & DC UPS(Chloride Terchnology) |  | 2026-02-20 | 2026-02-20 | 01-Mar-25 A | 15-Mar-25 A | 2026-03-27 | 10 | 2026-03-27
A35010 | Site Survey for UPS Modification | 2026-02-20 | 2026-02-20 | 01-Mar-25 A | 07-Mar-25 A | 2026-03-27 | 4 | 2026-03-27
A37540 | Site Survey Report for UPS Modification | 2026-02-20 | 2026-02-20 | 08-Mar-25 A | 15-Mar-25 A | 2026-03-27 | 4 | 2026-03-27
TA Site Survey MCMS System (Bently Nevada) |  | 2026-02-20 | 2026-02-20 | 01-Mar-25 A | 15-Mar-25 A | 2026-03-27 | 10 | 2026-03-27
A35020 | Site Survey for MCMS Modification | 2026-02-20 | 2026-02-20 | 01-Mar-25 A | 07-Mar-25 A | 2026-03-27 | 4 | 2026-03-27
A37550 | Site Survey Report for MCMS Modification | 2026-02-20 | 2026-02-20 | 08-Mar-25 A | 15-Mar-25 A | 2026-03-27 | 4 | 2026-03-27
For Switchgear & SCMS(Siemens) |  | 2026-02-20 | 2026-02-20 | 01-Mar-25 A | 15-Mar-25 A | 2026-03-27 | 10 | 2026-03-27
A34980 | Site Survey for SG & SCMS Modification | 2026-02-20 | 2026-02-20 | 01-Mar-25 A | 07-Mar-25 A | 2026-03-27 | 4 | 2026-03-27
A35140 | Health Check / Site Survey Report | 2026-02-20 | 2026-02-20 | 08-Mar-25 A | 15-Mar-25 A | 2026-03-27 | 4 | 2026-03-27
Instrumentation/Telecom Construction |  | 2026-02-20 | 2026-12-28 | 11-Feb-25 A | 2026-12-28 | 2026-03-27 | 518 | 2027-01-20 | 17
MCMS/DCS/ESD/F&G Modification / Installation (as applicable) |  | 2026-02-20 | 2026-11-23 | 01-May-25 A | 2026-11-23 | 2026-03-27 | 359 | 2027-01-20 | 42
GF Fire Fighting Equipment |  | 2026-08-04 | 2026-10-25 | 2026-08-04 | 2026-10-25 | 2026-10-31 | 71 | 2027-01-20 | 75
A3849 | Installation of Fire Fighting Equipment | 2026-08-04 | 2026-09-14 | 2026-08-04 | 2026-09-14 | 2026-10-31 | 36 | 2026-12-10 | 75
A24400 | Cable terminations and loop testing - Fire Fighting Equipment | 2026-09-15 | 2026-10-04 | 2026-09-15 | 2026-10-04 | 2026-12-12 | 17 | 2026-12-30 | 75
A24610 | Fire Fighting Equip - Pre Comm | 2026-10-05 | 2026-10-25 | 2026-10-05 | 2026-10-25 | 2026-12-31 | 18 | 2027-01-20 | 75
BF DCS/ESD Modification by Honeywell |  | 2026-05-23 | 2026-07-02 | 2026-05-23 | 2026-07-02 | 2026-10-21 | 35 | 2026-11-30 | 130
A17750 | DCS modification for integration between brownfield and greenfield | 2026-05-23 | 2026-07-02 | 2026-05-23 | 2026-07-02 | 2026-10-21 | 35 | 2026-11-30 | 130
GF Fire Detection Alarm System, Local Fire Control Panel & Clean Agent Unit |  | 2026-08-04 | 2026-11-16 | 2026-08-04 | 2026-11-16 | 2026-10-08 | 90 | 2027-01-20 | 56
A24110 | Installation of Fire Detection Alarm System, LFCP and Clean Agent Unit | 2026-08-04 | 2026-09-14 | 2026-08-04 | 2026-09-14 | 2026-10-08 | 36 | 2026-11-18 | 56
A24460 | Cable terminations and loop testing - FDAS, LFCP and Clean Agent Unit | 2026-09-15 | 2026-10-19 | 2026-09-15 | 2026-10-19 | 2026-11-19 | 30 | 2026-12-23 | 56
A24650 | FDAS, LFCP & CAU - Pre Comm | 2026-10-20 | 2026-11-16 | 2026-10-20 | 2026-11-16 | 2026-12-24 | 24 | 2027-01-20 | 56
TA EU3 ICSS(DCS/ESD/GDS) Modifications by HONEYWELL |  | 2026-02-20 | 2026-02-20 | 01-May-25 A | 15-May-25 A | 2026-03-27 | 24 | 2026-03-27
A21970 | Cross wiring between existing marshalling racks ( Instrument Tie-in No 6,7) | 2026-02-20 | 2026-02-20 | 01-May-25 A | 15-May-25 A | 2026-03-27 | 3 | 2026-03-27
A34910 | Installation of New Non-IS ESD Cabinet (83-JM3021-D) (Intrument Tie-In-8) | 2026-02-20 | 2026-02-20 | 01-May-25 A | 15-May-25 A | 2026-03-27 | 8 | 2026-03-27
A34920 | Non-UPS Power &earthing for New Non-IS ESD Cabinet (Intrument Tie-In- 9) | 2026-02-20 | 2026-02-20 | 01-May-25 A | 15-May-25 A | 2026-03-27 | 5 | 2026-03-27
A34930 | (OEM) Vendor (Honeywell) loose supplied (Intrument Tie-In- 9.1) | 2026-02-20 | 2026-02-20 | 01-May-25 A | 15-May-25 A | 2026-03-27 | 8 | 2026-03-27
A34940 | COLD Section ESD shutdown console switches (Intrument Tie-In- 11) | 2026-02-20 | 2026-02-20 | 01-May-25 A | 15-May-25 A | 2026-03-27 | 8 | 2026-03-27
A34950 | OEM) Vendor loose supplied material installation Including Honeywell, Safetec (Instrument Tie-12) | 2026-02-20 | 2026-02-20 | 01-May-25 A | 15-May-25 A | 2026-03-27 | 8 | 2026-03-27
A34960 | Change in the Existing DCS configuration for BF added/ Modified Field Tag (Instrument TieIn-14) | 2026-02-20 | 2026-02-20 | 01-May-25 A | 15-May-25 A | 2026-03-27 | 3 | 2026-03-27
A34970 | Change in the Existing ESD configuration for BF added/ Modified Field Tag(Instrument TieIn-14.1) | 2026-02-20 | 2026-02-20 | 01-May-25 A | 15-May-25 A | 2026-03-27 | 3 | 2026-03-27
GF F&G Flame Detectors, MCP, Beacon (Nos 324) |  | 2026-09-02 | 2026-11-23 | 2026-09-02 | 2026-11-23 | 2026-11-01 | 70 | 2027-01-20 | 50
A24130 | Installation of F&G Detectors, MCP,Beacon | 2026-09-02 | 2026-10-06 | 2026-09-02 | 2026-10-06 | 2026-11-01 | 29 | 2026-12-03 | 50
A24500 | Cable terminations and loop testing - F&G Detectors, MCP, Beacon | 2026-10-06 | 2026-11-02 | 2026-10-06 | 2026-11-02 | 2026-12-05 | 23 | 2026-12-30 | 50
A24710 | F&G, MCP, Beacon - Pre Comm | 2026-11-02 | 2026-11-23 | 2026-11-02 | 2026-11-23 | 2026-12-31 | 18 | 2027-01-20 | 50
TA Fire Alarm System Modification by SAFCO+HONEYWELL |  | 2026-02-20 | 2026-02-20 | 15-May-25 A | 25-May-25 A | 2026-03-27 | 11 | 2026-03-27
A34740 | Existing Deluge Console switches shall be relocated including retesting of existing loops on new dual tier Console | 2026-02-20 | 2026-02-20 | 15-May-25 A | 25-May-25 A | 2026-03-27 | 11 | 2026-03-27
TA Modification in MCMS System by BENTLY NAVEDA |  | 2026-02-20 | 2026-02-20 | 01-May-25 A | 15-May-25 A | 2026-12-01 | 13 | 2026-12-01
A34710 | Existing MCMS system 1 will be upgraded with new EVO series servers for EU3 existing network | 2026-02-20 | 2026-02-20 | 01-May-25 A | 15-May-25 A | 2026-12-01 | 13 | 2026-12-01
Field Instrument Installation |  | 2026-02-20 | 2026-12-28 | 01-May-25 A | 2026-12-28 | 2026-03-27 | 442 | 2027-01-20 | 17
GF Machine Condition Monitoring System |  | 2026-08-04 | 2026-10-28 | 2026-08-04 | 2026-10-28 | 2026-10-27 | 74 | 2027-01-20 | 72
A3789 | Installation of MCMS | 2026-08-04 | 2026-09-14 | 2026-08-04 | 2026-09-14 | 2026-10-27 | 36 | 2026-12-07 | 72
A24480 | Cable terminations and loop testing - MCMS | 2026-09-15 | 2026-10-08 | 2026-09-15 | 2026-10-08 | 2026-12-08 | 21 | 2026-12-31 | 72
A24690 | MCMS - Pre Comm | 2026-10-10 | 2026-10-28 | 2026-10-10 | 2026-10-28 | 2027-01-02 | 17 | 2027-01-20 | 72
TA Replacement of Existing Air Distribution Pot |  | 2026-02-20 | 2026-02-20 | 01-May-25 A | 15-May-25 A | 2026-03-27 | 7 | 2026-03-27
A34860 | Replacoment of existing ADP (E3-SP-0146) from 6-ways to 10-ways (Intrument Tie-In- 1.1) | 2026-02-20 | 2026-02-20 | 01-May-25 A | 15-May-25 A | 2026-03-27 | 1 | 2026-03-27
A34870 | Replacoment of existing ADP (E3-SP-0322) from 6-ways to 10-ways (Intrument Tie-In- 1) | 2026-02-20 | 2026-02-20 | 01-May-25 A | 15-May-25 A | 2026-03-27 | 1 | 2026-03-27
A34880 | Replacoment of existing ADP (E3-SP-0149) from 6-ways to 10-ways (Intrument Tie-In- 2) | 2026-02-20 | 2026-02-20 | 01-May-25 A | 15-May-25 A | 2026-03-27 | 1 | 2026-03-27
GF Acess Control System |  | 2026-09-09 | 2026-12-05 | 2026-09-09 | 2026-12-05 | 2026-10-27 | 74 | 2027-01-20 | 40
A3859 | Installation of Access Control System | 2026-09-09 | 2026-10-07 | 2026-09-09 | 2026-10-07 | 2026-10-27 | 24 | 2026-11-23 | 40
A24430 | Cable terminations and loop testing - ACS | 2026-10-07 | 2026-11-14 | 2026-10-07 | 2026-11-14 | 2026-11-24 | 32 | 2026-12-30 | 40
A24620 | ACS - Pre Comm | 2026-11-14 | 2026-12-05 | 2026-11-14 | 2026-12-05 | 2026-12-31 | 18 | 2027-01-20 | 40
GF VESDA (Very Early Smoke Detection Apparatus) |  | 2026-08-04 | 2026-10-21 | 2026-08-04 | 2026-10-21 | 2026-11-03 | 68 | 2027-01-20 | 78
A3799 | Installation of VESDA | 2026-08-04 | 2026-09-03 | 2026-08-04 | 2026-09-03 | 2026-11-03 | 27 | 2026-12-03 | 78
A24510 | Cable terminations and loop testing VESDA | 2026-09-05 | 2026-09-30 | 2026-09-05 | 2026-09-30 | 2026-12-05 | 23 | 2026-12-30 | 78
A24720 | VESDA - Pre Comm | 2026-10-01 | 2026-10-21 | 2026-10-01 | 2026-10-21 | 2026-12-31 | 18 | 2027-01-20 | 78
GF MOVs [Ball Type 24" 150# = 01 No] |  | 2026-09-26 | 2026-10-28 | 2026-09-26 | 2026-10-28 | 2026-12-15 | 29 | 2027-01-20 | 72
A24160 | Installatrion of MOV | 2026-09-26 | 2026-09-30 | 2026-09-26 | 2026-09-30 | 2026-12-15 | 5 | 2026-12-20 | 69
A24550 | Cable terminations and lop termination - MOVs | 2026-09-30 | 2026-10-14 | 2026-09-30 | 2026-10-14 | 2026-12-21 | 12 | 2027-01-03 | 69
A24760 | MOVS - Pre Comm | 2026-10-14 | 2026-10-28 | 2026-10-14 | 2026-10-28 | 2027-01-07 | 12 | 2027-01-20 | 72
TA Compresoor CGC Turbine by MHI |  | 2026-02-20 | 2026-02-20 | 01-Sep-25 A | 10-Sep-25 A | 2026-03-27 | 8 | 2026-03-27
A21840 | Turbine Governor Software modification by MHI (Intrument Tie-In- 15) | 2026-02-20 | 2026-02-20 | 01-Sep-25 A | 10-Sep-25 A | 2026-03-27 | 8 | 2026-03-27
TA SGM Replacement (EMERSON) |  | 2026-02-20 | 2026-02-20 | 01-May-25 A | 15-May-25 A | 2026-12-01 | 7 | 2026-12-01
A34720 | Existing Gas density Meter to replaced by SGM (EMERSON) (Intrument Tie-In- 3) | 2026-02-20 | 2026-02-20 | 01-May-25 A | 15-May-25 A | 2026-12-01 | 2 | 2026-12-01
A34890 | SGM meter connection to nearest Power Distruribution Board (Intrument Tie-In- 3.1) | 2026-02-20 | 2026-02-20 | 01-May-25 A | 15-May-25 A | 2026-12-01 | 1 | 2026-12-01
A34900 | New Tubing for Votex cooling of sgm Cabinet SGM (EMERSON) ((Intrument Tie-In- 2) | 2026-02-20 | 2026-02-20 | 01-May-25 A | 15-May-25 A | 2026-12-01 | 2 | 2026-12-01
GF Integrated Control and Safety System GF |  | 2026-09-29 | 2026-12-28 | 2026-09-29 | 2026-12-28 | 2026-10-24 | 77 | 2027-01-20 | 20
A3729 | Installation of ICSS System | 2026-09-29 | 2026-11-09 | 2026-09-29 | 2026-11-09 | 2026-10-24 | 35 | 2026-12-02 | 20
A3879 | Cable terminations and loop testing ICSS - GF | 2026-11-09 | 2026-12-03 | 2026-11-09 | 2026-12-03 | 2026-12-03 | 21 | 2026-12-27 | 20
A3899 | ICSS - Pre Comm | 2026-12-03 | 2026-12-28 | 2026-12-03 | 2026-12-28 | 2026-12-28 | 21 | 2027-01-20 | 20
GF Gauges (PG, TG, PDG, Analzer, FE) PG - 10bar & 40bar = 19 Nos, DP = 05 Nos, TG = 09 Nos |  | 2026-08-29 | 2026-11-12 | 2026-08-29 | 2026-11-12 | 2026-11-05 | 66 | 2027-01-20 | 59
A24150 | Installation of Field Instruments | 2026-08-29 | 2026-09-24 | 2026-08-29 | 2026-09-24 | 2026-11-05 | 24 | 2026-12-02 | 59
A24560 | Cable terminations and loop testing - Gauges (PG, TG, PDG) | 2026-09-26 | 2026-10-22 | 2026-09-26 | 2026-10-22 | 2026-12-03 | 24 | 2026-12-30 | 59
A24770 | Guages (PG, TG, PDG) - Pre Comm (Calibration/Testing) | 2026-10-24 | 2026-11-12 | 2026-10-24 | 2026-11-12 | 2026-12-31 | 18 | 2027-01-20 | 59
TA Field Instrument Modification |  | 2026-02-20 | 2026-02-20 | 01-May-25 A | 15-May-25 A | 2026-12-01 | 10 | 2026-12-01
A21850 | Dp Flow Transmitters to be re-calibrated ( approx qty- 20 nos.) in existing EU3 plant area | 2026-02-20 | 2026-02-20 | 01-May-25 A | 15-May-25 A | 2026-12-01 | 3 | 2026-12-01
A21860 | Replacement of 13-PV-4515 and stroke calibration, loop Testing (Intrument Tie-In- 4) | 2026-02-20 | 2026-02-20 | 01-May-25 A | 15-May-25 A | 2026-12-01 | 10 | 2026-12-01
A34700 | Flow Element to be re-calibrated ( approx qty- 19 nos.) in existing EU3 plant area | 2026-02-20 | 2026-02-20 | 01-May-25 A | 15-May-25 A | 2026-12-01 | 3 | 2026-12-01
GF Integrated Protection Control System |  | 2026-09-16 | 2026-12-23 | 2026-09-16 | 2026-12-23 | 2026-10-15 | 84 | 2027-01-20 | 24
A3769 | Installation of IPCS | 2026-09-16 | 2026-10-21 | 2026-09-16 | 2026-10-21 | 2026-10-15 | 30 | 2026-11-18 | 24
A24390 | Cable terminations and loop testing - IPCS | 2026-10-21 | 2026-11-25 | 2026-10-21 | 2026-11-25 | 2026-11-19 | 30 | 2026-12-23 | 24
A24600 | IPCS - Pre Comm | 2026-11-25 | 2026-12-23 | 2026-11-25 | 2026-12-23 | 2026-12-24 | 24 | 2027-01-20 | 24
TA Instrumentation Work |  | 2026-02-20 | 2026-02-20 | 01-May-25 A | 15-May-25 A | 2026-11-02 | 25 | 2026-12-01
A18330 | Instrument Air Tubing from existing Spare ADP connections to new valves in Brown Field area- @ 7 nos. | 2026-02-20 | 2026-02-20 | 01-May-25 A | 15-May-25 A | 2026-12-01 | 14 | 2026-12-01
A23560 | Heath Check for ICSS Report | 2026-02-20 | 2026-02-20 | 01-May-25 A | 15-May-25 A | 2026-11-02 | 25 | 2026-11-02
Cabling work |  | 2026-03-26 | 2026-11-18 | 2026-03-26 | 2026-11-18 | 2026-09-17 | 204 | 2027-01-20 | 54
GF Cable Tray and Instrument Junction Box (Perforated Cable tray Heavy duty= 5982 Mtrs, JBs= 73 Nos) |  | 2026-07-29 | 2026-11-18 | 2026-07-29 | 2026-11-18 | 2026-10-01 | 96 | 2027-01-20 | 54
A61680 | GF Cable Tray and Junction Box | 2026-07-29 | 2026-11-18 | 2026-07-29 | 2026-11-18 | 2026-10-01 | 96 | 2027-01-20 | 54
GF Fibre Optic Cable (Armoured, Telecom/IT/MAS) |  | 2026-03-26 | 2026-07-15 | 2026-03-26 | 2026-07-15 | 2026-09-17 | 96 | 2027-01-06 | 150
A61690 | GF Fiber Optic cable | 2026-03-26 | 2026-07-15 | 2026-03-26 | 2026-07-15 | 2026-09-17 | 96 | 2027-01-06 | 150
BF Instrumentation Works |  | 2026-05-23 | 2026-09-14 | 2026-05-23 | 2026-09-14 | 2026-09-28 | 98 | 2027-01-20 | 111
A21790 | Cable tray in EU3 SIS and H2 Extraction Plant SIS | 2026-05-23 | 2026-06-04 | 2026-05-23 | 2026-06-04 | 2026-11-12 | 11 | 2026-11-25 | 149
A18730 | Laying UTP/CAT5 cable from B3-CCB Network cabinet (82-JS- 4844) located Ethernet swtich to B3-CCB located SOE PC | 2026-07-29 | 2026-08-20 | 2026-07-29 | 2026-08-20 | 2026-10-14 | 19 | 2026-11-05 | 67
FO Cable Laying |  | 2026-05-23 | 2026-06-22 | 2026-05-23 | 2026-06-22 | 2026-10-14 | 26 | 2026-12-09 | 147
A17760 | Laying FO cables inside existing trenches/pipe/conduit between EU3 SIS &new H2 Plant SIS | 2026-05-23 | 2026-06-20 | 2026-05-23 | 2026-06-20 | 2026-11-12 | 24 | 2026-12-09 | 149
A21880 | Laying PU ASC PLC (TRICONEX) FO cable between new SIS at H2 Green Field area and B3-CCB for TRICONEX PLC | 2026-06-06 | 2026-06-20 | 2026-06-06 | 2026-06-20 | 2026-10-19 | 12 | 2026-11-01 | 116
A21780 | Laying FO cables inside existing trenches/pipe/conduit between B3 CCB to new H2 Plant SIS | 2026-06-01 | 2026-06-22 | 2026-06-01 | 2026-06-22 | 2026-10-14 | 18 | 2026-11-03 | 116
Hardwired Cable Laying |  | 2026-05-23 | 2026-07-02 | 2026-05-23 | 2026-07-02 | 2026-09-28 | 35 | 2027-01-20 | 174
A18320 | Hardwired multicore/pair cable laying between EU3 SIS to H2 Extraction Plant SIS | 2026-05-23 | 2026-06-20 | 2026-05-23 | 2026-06-20 | 2026-09-28 | 24 | 2026-10-26 | 110
A17770 | Trench & cable laying | 2026-05-23 | 2026-07-02 | 2026-05-23 | 2026-07-02 | 2026-12-12 | 35 | 2027-01-20 | 174
Termination |  | 2026-05-23 | 2026-09-14 | 2026-05-23 | 2026-09-14 | 2026-10-10 | 98 | 2026-11-30 | 67
A17780 | FO Patch cord laying | 2026-05-23 | 2026-06-18 | 2026-05-23 | 2026-06-18 | 2026-10-10 | 24 | 2026-11-05 | 120
A21830 | Termination of Hardwiring multicore/pair cable inside existing/new marshalling cabinets | 2026-06-20 | 2026-07-11 | 2026-06-20 | 2026-07-11 | 2026-10-26 | 18 | 2026-11-15 | 110
A21890 | Termination at Green Field H2 SIS of' PU ASC PLC (TRICONEX) FO cable between new SIS at H2 Green Field area and B3-CCB | 2026-06-27 | 2026-07-26 | 2026-06-27 | 2026-07-26 | 2026-11-02 | 25 | 2026-11-30 | 110
A21810 | Termination & Testing of various FO cables laid between EU3 SIS to new H2 Plant SIS | 2026-08-20 | 2026-09-14 | 2026-08-20 | 2026-09-14 | 2026-11-07 | 21 | 2026-11-30 | 67
A21820 | Termination & Testing of FO cables laid between B3-CCB to new H2 Plant SIS | 2026-08-20 | 2026-09-14 | 2026-08-20 | 2026-09-14 | 2026-11-07 | 21 | 2026-11-30 | 67
Telecommunication System Installation |  | 2026-02-20 | 2026-10-31 | 01-May-25 A | 2026-10-31 | 2026-03-27 | 343 | 2027-01-20 | 58
GF PAGA + Telephone |  | 2026-08-22 | 2026-10-19 | 2026-08-22 | 2026-10-19 | 2026-11-23 | 51 | 2027-01-20 | 80
A3809 | Installation of PAGA+Telephone | 2026-08-22 | 2026-09-14 | 2026-08-22 | 2026-09-14 | 2026-11-23 | 21 | 2026-12-16 | 80
A24440 | Cable terminations and loop testing - PAGA + Telephone | 2026-09-15 | 2026-10-01 | 2026-09-15 | 2026-10-01 | 2026-12-17 | 15 | 2027-01-03 | 80
A24630 | PAGA + Telephone - Pre Comm | 2026-10-03 | 2026-10-19 | 2026-10-03 | 2026-10-19 | 2027-01-04 | 15 | 2027-01-20 | 80
GF CCTV |  | 2026-08-25 | 2026-10-31 | 2026-08-25 | 2026-10-31 | 2026-11-16 | 57 | 2027-01-20 | 70
A3819 | Installation of CCTV | 2026-08-25 | 2026-09-19 | 2026-08-25 | 2026-09-19 | 2026-11-16 | 21 | 2026-12-09 | 70
A24520 | Cable terminations and loop testing - CCTV | 2026-09-19 | 2026-10-13 | 2026-09-19 | 2026-10-13 | 2026-12-10 | 21 | 2027-01-03 | 70
A24730 | CCTV - Pre Comm | 2026-10-13 | 2026-10-31 | 2026-10-13 | 2026-10-31 | 2027-01-04 | 15 | 2027-01-20 | 70
TA Telecom Related |  | 2026-02-20 | 2026-02-20 | 01-May-25 A | 15-May-25 A | 2026-03-27 | 13 | 2026-03-27
A18010 | Installation of 08 Nos of Cards in existing system | 2026-02-20 | 2026-02-20 | 01-May-25 A | 15-May-25 A | 2026-03-27 | 13 | 2026-03-27
A37380 | Installation of SFP in existing distribution switch (Hemal / Rommel). | 2026-02-20 | 2026-02-20 | 01-May-25 A | 15-May-25 A | 2026-03-27 | 13 | 2026-03-27
Testing |  | 2026-06-20 | 2026-08-01 | 2026-06-20 | 2026-08-01 | 2026-12-10 | 36 | 2027-01-20 | 149
A61700 | Fiber Optical Testing | 2026-06-20 | 2026-08-01 | 2026-06-20 | 2026-08-01 | 2026-12-10 | 36 | 2027-01-20 | 149
Others |  | 2026-02-20 | 2026-02-20 | 11-Feb-25 A | 26-Apr-25 A | 2026-03-27 | 233 | 2026-03-27
TA Site Survey For IPCS (ABB) |  | 2026-02-20 | 2026-02-20 | 20-Feb-25 A | 18-Mar-25 A | 2026-03-27 | 10 | 2026-03-27
A34990 | Site Survey for IPCS Modification | 2026-02-20 | 2026-02-20 | 20-Feb-25 A | 25-Feb-25 A | 2026-03-27 | 4 | 2026-03-27
A35150 | Health Check / Site Survey Report | 2026-02-20 | 2026-02-20 | 26-Feb-25 A | 18-Mar-25 A | 2026-03-27 | 4 | 2026-03-27
TA Site Survey For ICSS (Honeywell) |  | 2026-02-20 | 2026-02-20 | 20-Feb-25 A | 18-Mar-25 A | 2026-03-27 | 10 | 2026-03-27
A35000 | Site Survey for ICSS Modification | 2026-02-20 | 2026-02-20 | 20-Feb-25 A | 25-Feb-25 A | 2026-03-27 | 4 | 2026-03-27
A37510 | Health Check / Site Survey Report | 2026-02-20 | 2026-02-20 | 26-Feb-25 A | 18-Mar-25 A | 2026-03-27 | 4 | 2026-03-27
TA Site Survey For LAN System (CISCO) |  | 2026-02-20 | 2026-02-20 | 19-Apr-25 A | 26-Apr-25 A | 2026-03-27 | 10 | 2026-03-27
A37370 | Site Survey for LAN System Modification | 2026-02-20 | 2026-02-20 | 19-Apr-25 A | 22-Apr-25 A | 2026-03-27 | 4 | 2026-03-27
A37520 | Health Check / Site Survey Report | 2026-02-20 | 2026-02-20 | 23-Apr-25 A | 26-Apr-25 A | 2026-03-27 | 4 | 2026-03-27
TA Site Survey For CGC Turbine Software Upgarde |  | 2026-02-20 | 2026-02-20 | 11-Feb-25 A | 21-Feb-25 A | 2026-03-27 | 10 | 2026-03-27
A37390 | Site Survey for CGC Turbine Software Upgrade | 2026-02-20 | 2026-02-20 | 11-Feb-25 A | 14-Feb-25 A | 2026-03-27 | 4 | 2026-03-27
A37530 | Site Survey Report for CGC Turbine Software Upgrade | 2026-02-20 | 2026-02-20 | 17-Feb-25 A | 21-Feb-25 A | 2026-03-27 | 4 | 2026-03-27
TA Site Survey Fire Alarm System (SAFCO) |  | 2026-02-20 | 2026-02-20 | 19-Apr-25 A | 26-Apr-25 A | 2026-03-27 | 10 | 2026-03-27
A35030 | Site Survey for Fire Alaram System Modification | 2026-02-20 | 2026-02-20 | 19-Apr-25 A | 22-Apr-25 A | 2026-03-27 | 4 | 2026-03-27
A37560 | Site Survey Report for Fire Alaram System Modification | 2026-02-20 | 2026-02-20 | 23-Apr-25 A | 26-Apr-25 A | 2026-03-27 | 4 | 2026-03-27
Pre-commissioning |  | 2026-07-30 | 2027-01-20 | 2026-07-30 | 2027-01-20 | 2026-12-01 | 150 | 2027-01-20 | 0
GF Pre Commissioning FG/OG Compressor |  | 2026-12-02 | 2027-01-20 | 2026-12-02 | 2027-01-20 | 2026-12-02 | 43 | 2027-01-20 | 0
C1011 | Lube Oil Flushing | 2026-12-02 | 2026-12-13 | 2026-12-02 | 2026-12-13 | 2026-12-02 | 10 | 2026-12-13 | 0
C1010 | Flushing/Airblowing and inspection of piping | 2026-12-02 | 2026-12-19 | 2026-12-02 | 2026-12-19 | 2026-12-02 | 15 | 2026-12-19 | 0
C1013 | Final compressor/driver alignment | 2026-12-14 | 2027-01-03 | 2026-12-14 | 2027-01-03 | 2026-12-14 | 18 | 2027-01-03 | 0
C1014 | Pre-commissioning punchlist clearing | 2027-01-04 | 2027-01-20 | 2027-01-04 | 2027-01-20 | 2027-01-04 | 15 | 2027-01-20 | 0
GF Pre-Comm |  | 2026-10-06 | 2027-01-07 | 2026-10-06 | 2027-01-07 | 2026-12-10 | 81 | 2027-01-20 | 11
A3560 | Piping Cleaning, Flushing & Blowing (Pre Comm) | 2026-10-06 | 2026-11-16 | 2026-10-06 | 2026-11-16 | 2026-12-10 | 36 | 2027-01-20 | 56
A23900 | CCB/SIS systems overall Pre-commissioning |  | 2026-12-28 |  | 2026-12-28 |  | 0 | 2027-01-20 | 20
A17800 | Overall Plant & CCB/SIS Building Pre-Commissioning |  | 2027-01-07 |  | 2027-01-07 |  | 0 | 2027-01-20 | 11
A23590 | Plant Equipments Pre Commissionning | 2026-11-29 | 2027-01-07 | 2026-11-29 | 2027-01-07 | 2026-12-12 | 35 | 2027-01-20 | 11
BF Pre Commissioning |  | 2026-07-30 | 2026-12-28 | 2026-07-30 | 2026-12-28 | 2026-12-01 | 130 | 2027-01-20 | 20
BFW4100 | Equipment pre commissioning | 2026-07-30 | 2026-08-30 | 2026-07-30 | 2026-08-30 | 2026-12-22 | 26 | 2027-01-20 | 124
BFW4070 | Pre Commissioning works - Instrumentation & Control | 2026-09-14 | 2026-10-18 | 2026-09-14 | 2026-10-18 | 2026-12-01 | 29 | 2027-01-03 | 67
BFW4090 | Piping Cleaning, Flushing & Blowing (Pre Comm) | 2026-11-10 | 2026-12-28 | 2026-11-10 | 2026-12-28 | 2026-12-03 | 42 | 2027-01-20 | 20
Commissioning, RFSU, Start-Up |  | 2026-05-23 | 2027-04-28 | 2026-05-23 | 2027-04-28 | 2027-02-08 | 293 | 2027-07-20 | 71
Commissioning and Start-up |  | 2026-05-23 | 2027-04-15 | 2026-05-23 | 2027-04-15 | 2027-02-08 | 281 | 2027-07-20 | 83
A27180 | Industrial Buildings (MCC / Control Room including HVAC System / Building Fire Alarm System / Clean Agent etc) | 2027-01-21 | 2027-02-03 | 2027-01-21 | 2027-02-03 | 2027-02-08 | 12 | 2027-02-22 | 16
A27310 | Fire Water & Fire Suppression System | 2027-01-24 | 2027-02-03 | 2027-01-24 | 2027-02-03 | 2027-02-10 | 10 | 2027-02-22 | 16
A27160 | Potable & Service Water System | 2027-01-30 | 2027-02-06 | 2027-01-30 | 2027-02-06 | 2027-02-16 | 7 | 2027-02-24 | 16
A27290 | Instrument & Plant Air System | 2027-01-26 | 2027-02-06 | 2027-01-26 | 2027-02-06 | 2027-02-13 | 10 | 2027-02-24 | 16
A27300 | Inert Gas / Nitrogen System | 2027-01-27 | 2027-02-09 | 2027-01-27 | 2027-02-09 | 2027-02-14 | 12 | 2027-02-28 | 16
A27170 | Sanitary Waste Water System | 2027-02-06 | 2027-02-10 | 2027-02-06 | 2027-02-10 | 2027-02-23 | 5 | 2027-03-01 | 16
A27320 | LP Steam System | 2027-02-01 | 2027-02-11 | 2027-02-01 | 2027-02-11 | 2027-02-18 | 10 | 2027-03-02 | 16
A27360 | LP Condensate Collection System | 2027-02-03 | 2027-02-14 | 2027-02-03 | 2027-02-14 | 2027-02-21 | 10 | 2027-03-04 | 16
A27150 | Emergency Diesel Storage & Power Generation System | 2027-02-08 | 2027-02-18 | 2027-02-08 | 2027-02-18 | 2027-02-25 | 10 | 2027-03-09 | 16
A27200 | Power Supply System (Existing 33 KVA) | 2027-02-10 | 2027-02-21 | 2027-02-10 | 2027-02-21 | 2027-02-28 | 10 | 2027-03-11 | 16
A27240 | MCC | 2027-02-13 | 2027-02-25 | 2027-02-13 | 2027-02-25 | 2027-03-02 | 12 | 2027-03-16 | 16
A27250 | UPS System | 2027-02-15 | 2027-02-25 | 2027-02-15 | 2027-02-25 | 2027-03-04 | 10 | 2027-03-16 | 16
A27190 | Plant Lighting System | 2027-02-17 | 2027-02-28 | 2027-02-17 | 2027-02-28 | 2027-03-07 | 10 | 2027-03-18 | 16
A27340 | Slop / Drainage System | 2027-03-01 | 2027-03-06 | 2027-03-01 | 2027-03-06 | 2027-03-18 | 5 | 2027-03-24 | 16
A27270 | Anti-Surge Protection System/ PSA2 PLC Control System / Plant F&G System / Deluge Fire Suppression System / Analyzers | 2027-02-22 | 2027-03-07 | 2027-02-22 | 2027-03-07 | 2027-03-11 | 12 | 2027-03-25 | 16
A27280 | CP System / Heat Tracing System | 2027-02-24 | 2027-03-07 | 2027-02-24 | 2027-03-07 | 2027-03-14 | 10 | 2027-03-25 | 16
A27330 | Oily Water System | 2027-03-03 | 2027-03-08 | 2027-03-03 | 2027-03-08 | 2027-03-21 | 5 | 2027-03-27 | 16
A26480 | Telecom (PAGA / PABX / LAN / CCTV) | 2027-02-27 | 2027-03-09 | 2027-02-27 | 2027-03-09 | 2027-03-16 | 10 | 2027-03-28 | 16
A27260 | DCS / ESD / Compressor Control Systems / Machine Monitoring Systems (MMS) | 2027-02-20 | 2027-03-11 | 2027-02-20 | 2027-03-11 | 2027-03-09 | 18 | 2027-03-30 | 16
A27370 | Cooling Water Distribution System | 2027-03-06 | 2027-03-13 | 2027-03-06 | 2027-03-13 | 2027-03-23 | 7 | 2027-03-31 | 16
A27350 | Warm & Cold Flare Blowdown System | 2027-03-08 | 2027-03-21 | 2027-03-08 | 2027-03-21 | 2027-03-25 | 12 | 2027-04-08 | 16
A27380 | C4 Guard Bed Adsorber Regeneration Gas Cooler & Drip Leg to Existing Fuel Gas System | 2027-03-10 | 2027-03-23 | 2027-03-10 | 2027-03-23 | 2027-03-28 | 12 | 2027-04-11 | 16
A27390 | Feed Gas from Existing Fuel Gas, C1/C2 Separation Tail Gas Expander Booster Interface Battery Limits | 2027-03-13 | 2027-03-25 | 2027-03-13 | 2027-03-25 | 2027-03-30 | 12 | 2027-04-13 | 16
A27400 | PSA2 Feed Gas Compressor | 2027-03-16 | 2027-03-29 | 2027-03-16 | 2027-03-29 | 2027-04-03 | 12 | 2027-04-17 | 16
A27410 | PSA2 H2 Extraction Unit, Closed Sampling & Onwards to Interface Battery Limits | 2027-03-20 | 2027-04-01 | 2027-03-20 | 2027-04-01 | 2027-04-06 | 12 | 2027-04-20 | 16
A27420 | PSA2 Off Gas Compression (including all drums & coolers), Drip Leg & Onwards to Interface Battery Limits | 2027-03-23 | 2027-04-04 | 2027-03-23 | 2027-04-04 | 2027-04-10 | 10 | 2027-04-21 | 16
Commissioning & Handover |  | 2026-05-23 | 2027-02-17 | 2026-05-23 | 2027-02-17 | 2027-02-23 | 233 | 2027-07-20 | 131
A9915 | As BuiltUpdation of UG Composite Layouts in B3/U3 areas, Substation Layouts (B3/ U3) under revamp / modification scope | 2026-05-23 | 2026-09-12 | 2026-05-23 | 2026-09-12 | 2027-03-30 | 96 | 2027-07-20 | 268
C1039 | PSSR | 2027-01-21 | 2027-02-17 | 2027-01-21 | 2027-02-17 | 2027-02-23 | 24 | 2027-03-22 | 28
FG & OG Compressor - Commissioing |  | 2027-01-21 | 2027-03-10 | 2027-01-21 | 2027-03-10 | 2027-02-17 | 42 | 2027-04-06 | 23
C1015 | Compressor UCP Pre-Check / Power | 2027-01-21 | 2027-02-10 | 2027-01-21 | 2027-02-10 | 2027-02-17 | 18 | 2027-03-09 | 23
C1016 | Hot Loop Testing | 2027-01-27 | 2027-02-16 | 2027-01-27 | 2027-02-16 | 2027-02-23 | 18 | 2027-03-15 | 23
C1017 | Energization and Motor Solo Run | 2027-02-01 | 2027-02-21 | 2027-02-01 | 2027-02-21 | 2027-02-28 | 18 | 2027-03-20 | 23
C1020 | Compressor Oil Lubrication System Check | 2027-02-18 | 2027-02-23 | 2027-02-18 | 2027-02-23 | 2027-03-17 | 5 | 2027-03-22 | 23
C1018 | Interlock and Emergency Shutdown Tests - Part of Dry Commissioning (C&E Check) | 2027-02-09 | 2027-03-01 | 2027-02-09 | 2027-03-01 | 2027-03-08 | 18 | 2027-03-28 | 23
C1021 | PSSR | 2027-02-24 | 2027-03-02 | 2027-02-24 | 2027-03-02 | 2027-03-23 | 6 | 2027-03-29 | 23
C1019 | Control system sequence checks - Part of Dry Commissioning | 2027-02-18 | 2027-03-10 | 2027-02-18 | 2027-03-10 | 2027-03-17 | 18 | 2027-04-06 | 23
RFSU & Handover |  | 2027-02-18 | 2027-04-15 | 2027-02-18 | 2027-04-15 | 2027-03-30 | 48 | 2027-07-20 | 83
PC1010 | Ready for Start-Up |  | 2027-04-04 |  | 2027-04-04 |  | 0 | 2027-04-21 | 16
PC1050 | Project Close Out ( Handover of Care, Custody & Control of Plant ) |  | 2027-04-14 |  | 2027-04-14 |  | 0 | 2027-07-20 | 83
PC1030 | Issue "AS BUILT STATUS" Maintenance & Safety Manual | 2027-02-18 | 2027-04-15 | 2027-02-18 | 2027-04-15 | 2027-05-26 | 48 | 2027-07-20 | 83
FG & OG Compressor - RFSU |  | 2027-03-03 | 2027-03-25 | 2027-03-03 | 2027-03-25 | 2027-03-30 | 20 | 2027-04-21 | 23
C1022 | Surge Testing | 2027-03-03 | 2027-03-23 | 2027-03-03 | 2027-03-23 | 2027-03-30 | 18 | 2027-04-19 | 23
C1023 | For motor drives, motor current readings shall be obtained. | 2027-03-03 | 2027-03-23 | 2027-03-03 | 2027-03-23 | 2027-03-30 | 18 | 2027-04-19 | 23
C1024 | Vibration signatures shall be obtained for all bearings | 2027-03-03 | 2027-03-23 | 2027-03-03 | 2027-03-23 | 2027-03-30 | 18 | 2027-04-19 | 23
C1025 | Equipment performance data - Mapping | 2027-03-06 | 2027-03-25 | 2027-03-06 | 2027-03-25 | 2027-04-01 | 18 | 2027-04-21 | 23
Commissioning |  | 2027-01-21 | 2027-03-17 | 2027-01-21 | 2027-03-17 | 2027-04-14 | 48 | 2027-06-08 | 71
A61710 | Commissioning | 2027-01-21 | 2027-03-17 | 2027-01-21 | 2027-03-17 | 2027-04-14 | 48 | 2027-06-08 | 71
Start-up |  | 2027-03-18 | 2027-03-31 | 2027-03-18 | 2027-03-31 | 2027-06-23 | 12 | 2027-07-07 | 84
A61720 | Start-Up | 2027-03-18 | 2027-03-31 | 2027-03-18 | 2027-03-31 | 2027-06-23 | 12 | 2027-07-07 | 84
Initial Operations |  | 2027-04-01 | 2027-04-07 | 2027-04-01 | 2027-04-07 | 2027-07-07 | 6 | 2027-07-14 | 84
A61730 | Intial Operations | 2027-04-01 | 2027-04-07 | 2027-04-01 | 2027-04-07 | 2027-07-07 | 6 | 2027-07-14 | 84
Performance Test Run |  | 2027-04-07 | 2027-04-14 | 2027-04-07 | 2027-04-14 | 2027-07-14 | 6 | 2027-07-20 | 84
A61740 | Performance test Run | 2027-04-07 | 2027-04-14 | 2027-04-07 | 2027-04-14 | 2027-07-14 | 6 | 2027-07-20 | 84
Training |  | 2027-03-18 | 2027-04-28 | 2027-03-18 | 2027-04-28 | 2027-06-09 | 36 | 2027-07-20 | 71
A61750 | Training | 2027-03-18 | 2027-04-28 | 2027-03-18 | 2027-04-28 | 2027-06-09 | 36 | 2027-07-20 | 71
Optional Item’s Prices |  |  |  | 10-Sep-25 A | 10-Sep-25 A |  | 0
Furnace Modification – Optional Scope |  |  |  | 10-Sep-25 A | 10-Sep-25 A |  | 0
A61080 | COMPANY Activation for Optional Scope |  |  |  | 10-Sep-25 A |  | 0
Reimbursable Items (Provisional Sums) |  | 2027-01-21 | 2027-03-09 | 2027-01-21 | 2027-03-09 | 2027-06-03 | 48 | 2027-07-20 | 133
Provisional Sum for Two Year Operating Spares |  | 2027-01-21 | 2027-03-09 | 2027-01-21 | 2027-03-09 | 2027-06-03 | 48 | 2027-07-20 | 133
A61760 | Provisional Sum for Two Year Operating Spares | 2027-01-21 | 2027-03-09 | 2027-01-21 | 2027-03-09 | 2027-06-03 | 60 | 2027-07-20 | 166
Provisional Sum for Additional Assistance to Company IPMT’s |  | 2027-01-21 | 2027-03-09 | 2027-01-21 | 2027-03-09 | 2027-06-03 | 48 | 2027-07-20 | 133
A61770 | Provisional Sum for Additional Assistance to Company IPMT’s | 2027-01-21 | 2027-03-09 | 2027-01-21 | 2027-03-09 | 2027-06-03 | 60 | 2027-07-20 | 166
Provisional Sum for Additional Start Up Assistance to COMPANY |  | 2027-01-21 | 2027-03-09 | 2027-01-21 | 2027-03-09 | 2027-06-03 | 48 | 2027-07-20 | 133
A61780 | Provisional Sum for Additional Start Up Assistance to COMPANY | 2027-01-21 | 2027-03-09 | 2027-01-21 | 2027-03-09 | 2027-06-03 | 60 | 2027-07-20 | 166
Training of COMPANY personnel |  | 2027-01-21 | 2027-03-09 | 2027-01-21 | 2027-03-09 | 2027-06-03 | 48 | 2027-07-20 | 133
A61790 | Training of COMPANY personnel | 2027-01-21 | 2027-03-09 | 2027-01-21 | 2027-03-09 | 2027-06-03 | 60 | 2027-07-20 | 166
Initial Fills and / or One (1) full Spare Charge (refer to Addendum to Scope |  | 2027-01-21 | 2027-03-09 | 2027-01-21 | 2027-03-09 | 2027-06-03 | 48 | 2027-07-20 | 133
A61800 | Initial Fills and / or One (1) full Spare Charge (refer to Addendum to Scope | 2027-01-21 | 2027-03-09 | 2027-01-21 | 2027-03-09 | 2027-06-03 | 60 | 2027-07-20 | 166
Feed-gas Compressor Final design configuration (3 Casing design) |  | 2027-01-21 | 2027-03-09 | 2027-01-21 | 2027-03-09 | 2027-06-03 | 48 | 2027-07-20 | 133
A61810 | Feed-gas Compressor Final design configuration (3 Casing design) | 2027-01-21 | 2027-03-09 | 2027-01-21 | 2027-03-09 | 2027-06-03 | 60 | 2027-07-20 | 166
Accommodation for IPMT (Site) |  | 2027-01-21 | 2027-03-09 | 2027-01-21 | 2027-03-09 | 2027-06-03 | 48 | 2027-07-20 | 133
A61820 | Accommodation for IPMT (Site) | 2027-01-21 | 2027-03-09 | 2027-01-21 | 2027-03-09 | 2027-06-03 | 60 | 2027-07-20 | 166
Unforeseen development during Execution for additional services over and above |  | 2027-01-21 | 2027-03-09 | 2027-01-21 | 2027-03-09 | 2027-06-03 | 48 | 2027-07-20 | 133
A61830 | Unforeseen development during Execution for additional services over and above | 2027-01-21 | 2027-03-09 | 2027-01-21 | 2027-03-09 | 2027-06-03 | 60 | 2027-07-20 | 166